## B end and quotes Pending
Order Received | VzB POC | UHG PO # | LOCATION | PRODUCT | VzB ORDER | TIN | SERVICE NUMBER | PVC ID | GOLD CAR | VzB CKT ID | LEC CKT ID | ASR SENT | TELCO DUE (FOC) | TELCO COMPLETE | REQUESTED DUE DATE | VzB DUE | VzB COMPLETE | AS NUMBER | UHT Engineer | ACTIVATION SCHEDULED | ORDER STATUS COMMENTS
Order Received | VzB POC | UHG PO # | LOCATION | PRODUCT | VzB ORDER | TIN | SERVICE NUMBER | PVC ID | GOLD CAR | VzB CKT ID | LEC CKT ID | ASR SENT | TELCO DUE (FOC) | TELCO COMPLETE | CARRIER | VzB DUE | VzB COMPLETE | AS NUMBER | Goal Date | Disonnect Request that needs to be Entered by UHG | ORDER STATUS COMMENTS
2021-02-22 |  | II549 | 5th floor, south block, SP plot No 16-20 &20 A Tamarai Chennai, India 600032 | 100 meg port 200 meg access CAR: 72meg | 6442540: W1E23544 6442541: W1E23545 | 1-2352990292 | [14 empty] | 4/8 - FOC date 5/20/21 3/22 - site survey to be completed this week: FOC to be shared afterwards 3/9 - pending FOC 2/22 - SOF signed
2021-03-30 |  | CB501-01-IM | We-Work, Avenida Calle 26 # 92 – 32 / Edificio Gold 2 Bogotá DC, Colombia 111071-111071000 | 50 meg access 30 meg port: 15 meg CAR | [16 empty] | 3/30 - pending SOF

## Summary
United
Pending Order Status | # of Orders | Help Section
Provisioning Accepted | 15 | Order Validation: Orders that are currently in the validation phase and have not been submitted to our Provisioning Department.
Customer Action | 5 | Sales: The order is currently being reviewed by the Sales Team
Pending FOC | 15 | Pending NOV: The Network Order Verification process is pending input from our Customer. Orders will not progress until the NOV process is complete.
Pending Loop Accepted | 11 | Pending TEV: Technical Validation in progress
Pending BEAS Install | 1 | Pending Early Site Survey: Site Survey in progress
Pending Completion | 2 | Provisioning Accepted: Provisioning Department accepted the order and has begun processing.
Customer Action: Any order where direct action needs to be taken by our Customer. Orders will not progress until the issue is resolved
Pending Build: The order requires a Verizon Build and it is in progress
Pending FOC: Request sent to the Local Exchange Carrier (LEC), waiting for Firm Order Confirmation (FOC) of circuit delivery.
Pending Loop Delivery: FOC provided by the LEC, waiting on the Loop Delivery
BEAS Install: Circuit delivered, waiting on installation of BEAS Converter Box
Pending CPE : Pending Customer Premise Equipment Delivery on non Managed Orders
Pending Managed: Order is pending work by our Managed Services Delivery Team
Pending Completion: Order is provisioned and is pending completion
Pending Cancel: Cancel request submitted and pending full processing
Over all Order Status | # of Orders
Completed | 892
Pending | 49
Canceled | 217
Total | 1158

## Site Readiness
SITE READINESS: PARTNERING WITH VERIZON
A 'Site Readiness Walkthrough' with a local contact is required to confirm your site is properly prepared for on-time delivery of your service. Be sure that your onsite representative is aware of your pending service request and is knowledgeable about site and access requirements. The 'Activation Delays' section of your contract indicates you are required to do what is necessary to activate your service, which would include a Site Readiness Walkthrough and related remediation. If your site is not ready to accept service, Verizon may cause charges to accrue in accordance with the 'Activation' section of your contract.
Verizon's site readiness website will guide you in preparing your location for the successful installation of service(s) ordered. You can view a short video tutorial on site readiness by visiting:
http://www.verizonenterprise.com/resources/media/large-133966-customerreadiness.xml
Direct access to the site readiness website:
https://www.verizonenterprise.com/Support/customerreadiness/
The billing Activation Date will be no later than five Business Days after delivery and successful testing of the Access and Transport and, if applicable, the availability of Verizon provided equipment.
Note - If your order includes one of Verizon's Managed Services products, you will be contacted as your order progresses with preparation instructions for this service. An out-of-band or modem connection may be required.
-----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------
Site Location Requirements:
The following is a list of items that must be completed prior to scheduling a Site Survey (If required), Circuit Install, or a Construction Build (If required). Failure to have the right infrastructure in place will result in delayed installations and/or increased costs. - Access to the Site. - Access to Electrical Outlet: required to connect network equipment, ensure proper grounding is provided. - Physical Space: Backboard and/or Rack Space must be provided to install equipment. - Site Environment: The environment must be climate controlled and sufficiently lit. - Cable Path and Conduit: if the site location is different than the building's Minimum Point of Entry (MPOE), a cable path or conduit must be provided between the MPOE and the point of Demarcation at the site
If you have any further questions on site readiness, you can view a short video tutorial on site readiness by visiting:
Site Readiness Video
The site readiness website can be accessed directly by following the below link:
Site Readiness Website
Additional dispatches may be required after the initial delivery, but prior to your service being ready for activation.
-----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------
DID YOU KNOW?
You can access our new automated ordering platform through Verizon Enterprise Center to place your next Private IP or Internet Dedicated order online by visiting Verizon Enterprise Center
Are you registered for Verizon Enterprise Center? It's a powerful management tools that allows you to create orders, check order status, be notified when your invoice is ready, and create and status a repair ticket, and much more! To register today, access Verizon Enterprise Center at: Click on the link below and click Sign In/Register.
Verizon Enterprise Center
For training on this powerful tool, go to below link:
Click Here
-----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------

## Pending
Customer Summary Status | Site ID | Location - Customer Location Z Full Address | Access Speed | External Comments - Latest | TIN/ProQuest Service Order ID | Location Name | Product (Order ID) | Order ID | Port Speed | COMS Service ID | Service ID | Circuit ID | Telco Circuit ID | PVC ID | Gold CAR | PIP Configlet | TPV LAN Interface | WAN Interface to the CE (Customer Edge) | Customer Handoff | Telco Name (Purchase Order Number) | Telco ASR Sent | Telco FOC Date | Loop Accepted | Dispatch Scheduled (NID) | Dispatch Completion Date | Actual Demarc | Site Contact A | Site Contact Z | Technical Contact Name | Technical Contact Email | Technical Contact Number | Close to Bill | Hotcut Completed Date | VZ Committed Due Date | Requested Due Date | Service Order Billing Complete | Cancel Date | Managed Status | Expedite Flag | BAN | Jeop Notification | Description | Email ID | Request Date
Pending Loop Accepted | FL432 | 15471 SW 12TH ST BLDG B FORT LAUDERDALE, FL 33326-1997 US | 50 MBPS (33283962) | 04/14/2021: City permit has been delayed to 4/27. Permit authority did not provide a reason for the delay. New ECD 5/25, PTD 6/3. | 204279157 | Sunrise | WAN Analysis Reporting (33283963) Access (33283962) Private IP - PIP (33283961) | 33283963 33283962 33283961 | 20 MBPS (33283961) |  | 1322784683 (WAN Analysis Reporting) 1322784677 (Access) 1322784681 (Private IP (PIP)) | C4024824/ADD (33283961) E4064862/ADD (33283962) | 38.KGGS.026259..CBCL.. (3328396286529801) | 6195750 | 15000 | PVC ID : 6195750 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65220 PE IP Address : 152.164.151.133 CE Address : 152.164.151.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33283962) | 1000Base-SX (850nm, Multi Mode Fiber) (33283962) | Ethernet | COMCAST (3328396286529801) | 10/19/2020 (3328396286529801) | 03/09/2021 (3328396286529801) | [5 empty] | BRIAN STOCKFISCH 1-810-768-9920 bstockfisch@diplomat.is | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 |  |  | 03/18/2021 (33283961) 03/16/2021 (33283962) | 04/21/2021 04/15/2021 |  |  | Scheduled | N (33283963) N (33283962) N (33283961) | U0101953 |  |  | NSPE0014166568
Pending FOC | TX634 | 207 S Fm 548 Forney, TX 75126-4107 US | 50 MBPS (33777579) | 04/14/2021: Per LEC, the earliest date that they can schedule this for dispatch to complete the NID install is on 4/19 at 2pm CST. Follow up sent to enduser to secure access. | 204754629 | TX634 | WAN Analysis Reporting (33777580) Access (33777579) Private IP - PIP (33777578) | 33777580 33777579 33777578 | 10 MBPS (33777578) |  | 94935101 (WAN Analysis Reporting) 94934597 (Access) 94934599 (Private IP (PIP)) | C4025430/ADD (33777578) E4066862/ADD (33777579) |  | 6213011 | 5500 | PVC ID : 6213011 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64626 PE IP Address : 152.181.56.85 CE Address : 152.181.56.86 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (33777579) | 1000Base-SX (850nm, Multi Mode Fiber) (33777579) | Ethernet | NITEL USA (3377757989689301) | 02/26/2021 (3377757989689301) | [6 empty] | SHERRY GREEN 1-612-642-7302 sgreen11@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  | 03/02/2021 (33777578) 02/26/2021 (33777579) | 04/14/2021 04/08/2021 |  |  | Scheduled | N (33777580) N (33777579) N (33777578) | U0101953 | Jeopardy Notification 1 (02/19/2021) |  | NSPE0014318126
Provisioning Accepted | TX555 | 1901 W WILLIAM CANNON DR STE 112 AUSTIN, TX 78745-5322 US | 50 MBPS (33820408) | 04/14/2021: Permits obtained, pending construction completion. FOC date 6/4. | 204795557 | TX555 | Access (33820408) Private IP - PIP WAN Analysis Reporting (33820409) | 33820408 33820409 | 10 MBPS |  | 94764159 (Access) 94764161 94764163 (WAN Analysis Reporting) | E4056114/NONE (33820408) |  |  |  |  | 1000Base-SX-850nm (33820408) | 1000Base-SX (850nm, Multi Mode Fiber) (33820408) | Ethernet | [8 empty] | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  |  | 03/31/2021 01/29/2021 01/29/2021 (28972703.1) |  |  | Scheduled Scheduled Status Set | N (33820408) N N (33820409) | U0101953 |  |  | NSPE0014498103
Customer Action | IN022-02-IJ | 1050 PATROL RD JEFFERSONVILLE, IN 47130 USA | 200 MBPS (IQBL3Q15) 100 MBPS (IQBL3Q2C) | 04/14/2021: Customer action required, pending rescheduling of beas install. Informed customer this secondary circuit was installed by the LEC on 2/1 so we can proceed with scheduling of the beas installation, whether or not end user decides to proceed with the diversity with primary order IQBL3Q18 Customer asked for extension until 4/16 to provide confirmation on how they will proceed. | 10594731 |  | EACS (IQBL3Q15) EVC/PVC Service (N.12521483.6215572) Private IP (IQBL3Q2C) | IQBL3Q15 N.12521483.6215572 IQBL3Q2C | 200 MBPS (IQBL3Q15) 100 MBPS | P2493355 P2493360 |  | EDBLS2320001 (IQBL3Q15) BCBLS2360001 (IQBL3Q2C) | 81.L1XX.931109..CHTR (IQBL3Q15ZRX3MB01) | 6215572 | 50000 | VPN Name : UnitedHealthGroup Router Name : DTRT3E01 VRF Name : Vi95552-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 152.164.24.249 CE Address : 152.164.24.250 QoS - Egress Profile: R12 PVC ID : 6215572 |  |  |  | CHARTER (IQBL3Q15ZRX3MB01) | 01/15/2021 (IQBL3Q15ZRX3MB01) | 03/15/2021 (IQBL3Q15ZRX3MB01) | 02/01/2021 (IQBL3Q15ZRX3MB01) |  |  |  |  | MATT MCQUEARY 8129244105 WILLIS.MCQUEARY@OPTUM.COM | [5 empty] | 03/22/2021 (IQBL3Q15) 03/22/2021 (IQBL3Q2C) | 02/11/2021 (IQBL3Q15) 02/11/2021 (IQBL3Q2C) |  |  |  | N (IQBL3Q15) N (N.12521483.6215572) N (IQBL3Q2C) | 05017789 0C54Z3 |  |  | NSPE0014337949
Customer Action | IN022-02-IJ | 1050 PATROL RD JEFFERSONVILLE, IN 47130 USA | 200 MBPS (IQBL3Q18) 100 MBPS (IQBL3Q19) | 04/14/2021: Customer action required, pending confirmation to proceed with order from end-user. Per customer, they have still not decided if they will move forward with the new design/path. Informed customer, the Jeffersonville orders have been on customer hold since 2/17, 40 business days, pending confirmation on if the end user will proceed with the new diversity changes. Customer asked for extension until 4/16 to provide confirmation on how they will proceed. | 10591998 |  | EACS (IQBL3Q18) EVC/PVC Service (N.12521829.6215670) Private IP (IQBL3Q19) | IQBL3Q18 N.12521829.6215670 IQBL3Q19 | 200 MBPS (IQBL3Q18) 100 MBPS | P2493358 P2493359 |  | EDBLS2330001 (IQBL3Q18) BCBLS2340001 (IQBL3Q19) | 81.L1XX.931164..CHTR (IQBL3Q183RX3MB02) | 6215670 | 50000 | VPN Name : UnitedHealthGroup Router Name : CPZXE04 VRF Name : Vd99231-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 206.115.15.33 CE Address : 206.115.15.34 QoS - Egress Profile: R12 PVC ID : 6215670 |  |  |  | TIME WARNER CABLE (IQBL3Q183RX3MB02) | 01/20/2021 (IQBL3Q183RX3MB02) | 05/21/2021 (IQBL3Q183RX3MB02) | [5 empty] | MATT MCQUEARY 8129244105 WILLIS.MCQUEARY@OPTUM.COM | [5 empty] | 05/28/2021 (IQBL3Q18) 05/28/2021 (IQBL3Q19) | 02/01/2021 (IQBL3Q18) 02/01/2021 (IQBL3Q19) |  |  |  | N (IQBL3Q18) N (N.12521829.6215670) N (IQBL3Q19) | 05017789 0C54Z4 |  |  | NSPE0014331630
Pending Loop Accepted | TX525 | 2413 MEMORIAL PKWY PORTLAND, TX 78374-3209 US | 50 MBPS (34072343) | 04/14/2021: FOC date 4/28. Scope of Work below: Construction Started 4/13/2021 Construction Completed- 4/20/2021 Splicing- 4/20/2021 Hardware Installed- 4/21/2021 Final Config/Testing/Handoff-4/28/2021 | 205010781 | TX525 | Private IP - PIP (34072342) WAN Analysis Reporting (34072344) Access (34072343) | 34072342 34072344 34072343 | 10 MBPS (34072342) |  | 1346351647 (Private IP (PIP)) 1346351649 (WAN Analysis Reporting) 1346351643 (Access) | C4025823/ADD (34072342) E4068020/ADD (34072343) | EPL/133294520/001 (3407234361903701) | 6222534 | 5500 | PVC ID : 6222534 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65243 PE IP Address : 68.137.101.53 CE Address : 68.137.101.54 QoS - Egress Profile: R12 | 1000Base-T (34072343) | 1000Base-T (34072343) | Ethernet | CB10 (3407234361903701) | 03/05/2021 (3407234361903701) | 04/28/2021 (3407234361903701) | [5 empty] | GABE RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | JASON SALAPING | jason_salaping@optum.com | 1-210-862-6784 |  |  | 05/07/2021 (34072342) 05/05/2021 (34072343) | 04/15/2021 04/21/2021 |  |  | Scheduled | N (34072342) N (34072344) N (34072343) | U0101953 |  |  | NSPE0014412385
Pending FOC | VT001 | 46 Main St Winooski, VT 05404-2242 US | 50 MBPS (34085640) | 04/14/2021: Pending FOC date. Signed MOP is already forwarded to LEC. LEC is now working on setting the updated FOC for this order. | 205023623 | UNITED HEALTH GROUP | Private IP - PIP (34085639) WAN Analysis Reporting (34085641) Access (34085640) | 34085639 34085641 34085640 | 10 MBPS (34085639) |  | 94956363 (Private IP (PIP)) 94956366 (WAN Analysis Reporting) 94956361 (Access) | C4025844/ADD (34085639) E4068072/ADD (34085640) |  | 6222839 |  | PVC ID : 6222839 | 1000Base-SX-850nm (34085640) | 1000Base-SX (850nm, Multi Mode Fiber) (34085640) | Ethernet | OXFORD (3408564033842702) | 03/10/2021 (3408564033842702) | [6 empty] | Muralidhar Mulpuri 1-802-734-0383 muralidhar_mulpuri@optum.com | JOSE CARLO RITUAL | jose_ritual@optum.com | 632-790-6489 |  |  | 03/18/2021 (34085639) 03/16/2021 (34085640) | 04/19/2021 04/23/2021 |  |  | Scheduled | N (34085639) N (34085641) N (34085640) | U0101953 |  |  | NSPE0014418952
Pending FOC | TX632 | 1315 St Joseph Pkwy ste 1310 Houston, TX 77002-8236 US | 50 MBPS (34097415) | 04/14/2021: Pending FOC date. | 205035275 | TX632 | Access (34097415) Private IP - PIP (34097414) WAN Analysis Reporting (34097416) | 34097415 34097414 34097416 | 10 MBPS (34097414) |  | 94958108 (Access) 94958110 (Private IP (PIP)) 94958113 (WAN Analysis Reporting) | E4068144/ADD (34097415) C4025873/ADD (34097414) |  | 6223281 | 5500 | PVC ID : 6223281 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64675 PE IP Address : 68.136.68.137 CE Address : 68.136.68.138 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (34097415) | 1000Base-LX (1310nm Single Mode Fiber) (34097415) | Ethernet | ALPHEUS (3409741591041901) | 04/08/2021 (3409741591041901) | [6 empty] | Scott Cannon 1-813-695-3652 scannon@wellmed.net | JEGIN MIKO DIMAYUGA | jegin_dimayuga@optum.com | 63-928-790-6468 |  |  | 04/16/2021 (34097415) 04/20/2021 (34097414) | 05/19/2021 05/25/2021 |  |  | Scheduled | N (34097415) N (34097414) N (34097416) | U0101953 |  |  | NSPE0014423130
Pending FOC | TX620 | 7737 Southwest Fwy ste 640 Houston, TX 77074-1800 US | 50 MBPS (34118340) | 04/14/2021: FOC date 7/7/21. Per LEC: will let you know when both the ROE and the permit have been approved. | 205056989 | TX620 | WAN Analysis Reporting (34118341) Access (34118340) Private IP - PIP (34118339) | 34118341 34118340 34118339 | 10 MBPS (34118339) |  | 94959694 (WAN Analysis Reporting) 94959687 (Access) 94959689 (Private IP (PIP)) | C4025951/ADD (34118339) E4068279/ADD (34118340) |  | 6224611 | 5500 | PVC ID : 6224611 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64627 PE IP Address : 147.225.183.21 CE Address : 147.225.183.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34118340) | 1000Base-SX (850nm, Multi Mode Fiber) (34118340) | Ethernet | CLEC or INDEPENDENT (3411834091099701) | 01/26/2021 (3411834091099701) | [6 empty] | JASON OZER 1-210-951-3251 jozer@wellmed.net | AVINASH CHIB | avinash_chib@optum.com | 1-952-936-1300 |  |  | 03/16/2021 (34118339) 03/12/2021 (34118340) | 06/15/2021 06/09/2021 |  |  | Scheduled | N (34118341) N (34118340) N (34118339) | U0101953 |  |  | NSPE0014431054
Pending FOC | TX636 | 2111 Fort Worth Hwy Weatherford, TX 76086-4834 US | 50 MBPS (34177927) | 04/14/2021: Build complete. FOC date 4/27. | 205122669 | TX636 | Private IP - PIP (34177926) WAN Analysis Reporting (34177928) Access (34177927) | 34177926 34177928 34177927 | 10 MBPS (34177926) |  | 94964409 (Private IP (PIP)) 94964411 (WAN Analysis Reporting) 94964413 (Access) | C4026052/ADD (34177926) E4068580/ADD (34177927) |  | 6227153 | 5500 | PVC ID : 6227153 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64778 PE IP Address : 68.137.144.141 CE Address : 68.137.144.142 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34177927) | 1000Base-SX (850nm, Multi Mode Fiber) (34177927) | Ethernet | NITEL USA (3417792790020901) | 02/02/2021 (3417792790020901) | [6 empty] | KHANH NGUYEN 1-817-918-2920 knguyen11@wellmed.net | BRANDON LITTLE | Brandon_little@optum.com | 1-952-687-3694 |  |  | 05/06/2021 (34177926) 05/04/2021 (34177927) | 03/15/2021 03/19/2021 |  |  | Scheduled | N (34177926) N (34177928) N (34177927) | U0101953 |  |  | NSPE0014455202
Customer Action | UT029 | 2146 N Main St ste 514 Layton, UT 84041-4975 US | 100 MBPS (34235149) | 04/14/2021: Customer approved SCON charges. Pending approval from Verizon Finance department to proceed before submitting the order back to provisioning. | 205169349 | UT029 | Private IP - PIP (34235148) WAN Analysis Reporting (34235150) Access (34235149) | 34235148 34235150 34235149 | 50 MBPS (34235148) |  | 94967066 (Private IP (PIP)) 94967064 (WAN Analysis Reporting) 94967068 (Access) | C1152719/ADD (34235148) E4068850/ADD (34235149) | 69.KXGS.583239..MS (3423514991736101) | 6229427 | 30000 | PVC ID : 6229427 VPN Name : UnitedHealthGroup Router Name : SLKC9E01 VRF Name : V661371:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65163 PE IP Address : 152.177.98.97 CE Address : 152.177.98.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34235149) | 1000Base-SX (850nm, Multi Mode Fiber) (34235149) | Ethernet | CENTURYLINK (3423514991736101) | 02/09/2021 (3423514991736101) | 05/04/2021 (3423514991736101) | [5 empty] | Dave Tornell 1-952-205-7103 david.d.tornell@optum.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 |  |  | 05/13/2021 (34235148) 05/11/2021 (34235149) | 03/19/2021 03/25/2021 |  |  | Scheduled | N (34235148) N (34235150) N (34235149) | U0101953 |  |  | NSPE0014472390
Pending Loop Accepted | FL463 | 1259 S Pinellas Ave Tarpon Springs, FL 34689-3719 US | 50 MBPS (34371281) | 04/14/2021: FOC date 5/7. Pending building completion. Scope of work, FIBER PLACING/FIBER SPLICING LESS THAN 2,500. | 205302103 | FL483 | Private IP - PIP (34371280) WAN Analysis Reporting (34371282) Access (34371281) | 34371280 34371282 34371281 | 10 MBPS (34371280) |  | 94975784 (Private IP (PIP)) 94975788 (WAN Analysis Reporting) 94975786 (Access) | C4026398/ADD (34371280) E4069442/ADD (34371281) | 65/KRGN/569955//FTNC/ (3437128192284302) | 6232510 | 5500 | PVC ID : 6232510 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65093 PE IP Address : 68.137.254.169 CE Address : 68.137.254.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34371281) | 1000Base-SX (850nm, Multi Mode Fiber) (34371281) | Ethernet | FRONTIER (3437128192284302) FRONTIER (3437128192284301) | 03/06/2021 (3437128192284302) 03/03/2021 (3437128192284301) | 05/07/2021 (3437128192284302) | [5 empty] | Todd VanDerSchaegen 1-813-629-2611 tvanderschaegen@wellmed.net | MANISH SARKHEL | manish_sarkhel@optum.com | 632-671-2655 |  |  | 05/18/2021 (34371280) 05/14/2021 (34371281) | 04/05/2021 04/09/2021 |  |  | Approved | N (34371280) N (34371282) N (34371281) | U0101953 |  |  | NSPE0014520988
Pending Loop Accepted | FL464 Trinity FL | 4111 Little Rd New Port Richey, FL 34655-1743 US | 50 MBPS (34409335) | 04/14/2021: FOC date 5/7. Per Frontier - the scope of work is: PLACE & SPLICE FIBER <1,000' with an ECD of 4/27/2021. | 205338997 | 34655 | Private IP - PIP (34409334) WAN Analysis Reporting (34409336) Access (34409335) | 34409334 34409336 34409335 | 10 MBPS (34409334) |  | 94977730 (Private IP (PIP)) 94977728 (WAN Analysis Reporting) 94977726 (Access) | C4026637/ADD (34409334) E4069585/ADD (34409335) | 65/KRGN/565402//FTNC/ (3440933592568701) | 6234934 | 5500 | PVC ID : 6234934 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64928 PE IP Address : 152.162.33.121 CE Address : 152.162.33.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34409335) | 1000Base-SX (850nm, Multi Mode Fiber) (34409335) | Ethernet | FRONTIER (3440933592568701) | 02/26/2021 (3440933592568701) | 05/07/2021 (3440933592568701) | [5 empty] | Todd VanDerSchaegen 1-210-780-6809 tvanderschaegen@wellmed.net | MANISH SARKHEL | manish_sarkhel@optum.com | 632-671-2655 |  |  | 05/18/2021 (34409334) 05/14/2021 (34409335) | 04/08/2021 04/14/2021 |  |  | Scheduled | N (34409334) N (34409336) N (34409335) | U0101953 |  |  | NSPE0014535036
Pending FOC | TX621 | 1315 ST JOSEPH PKWY HOUSTON, TX 77002-8233 US | 50 MBPS (34410674) | 04/14/2021: Install scheduled for 4/15. Order on schedule to complete on or before FOC. Per LEC: the install could take place anywhere from 8am-5pm local time but that the tech typically contacts the LCON when they are on their way to confirm. | 205340601 | Houston | Access (34410674) Private IP - PIP (34410673) WAN Analysis Reporting (34410675) | 34410674 34410673 34410675 | 10 MBPS (34410673) |  | 1357185997 (Access) 1357186001 (Private IP (PIP)) 1357186003 (WAN Analysis Reporting) | E4069640/ADD (34410674) C4026458/ADD (34410673) |  | 6233247 | 5500 | PVC ID : 6233247 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64578 PE IP Address : 68.137.27.217 CE Address : 68.137.27.218 QoS - Egress Profile: R12 | 1000Base-T (34410674) | 1000Base-T (34410674) | Ethernet | INDATEL SERVICES, LLC (3441067491293501) | 04/09/2021 (3441067491293501) | [6 empty] | SCOTT CANNON 1-813-695-3652 scannon@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 |  |  | 04/30/2021 (34410674) 05/04/2021 (34410673) | 05/20/2021 05/26/2021 |  |  | Scheduled | N (34410674) N (34410673) N (34410675) | U0101953 |  |  | NSPE0014535450
Pending FOC | CB502 | Avenida Calle 26, 92-32 Bogotá110911 CO | 500 MBPS (34460349) | 04/14/2021: Customer action required, pending special construction charge approval. | 205340963 | Bogotá | Private IP - PIP (34460348) WAN Analysis Reporting (34460350) Access (34460349) | 34460348 34460350 34460349 | 400 MBPS (34460348) |  | 1350181185 (Private IP (PIP)) 1350181187 (WAN Analysis Reporting) 1350181181 (Access) | C5013983/ADD (34460348) E5033708/ADD (34460349) |  | 6234245 | 250000 | PVC ID : 6234245 VPN Name : UnitedHealthGroup Router Name : BGTAXE01 VRF Name : Vj21552-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65242 PE IP Address : 68.138.51.201 CE Address : 68.138.51.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34460349) | 1000Base-SX (850nm, Multi Mode Fiber) (34460349) | Ethernet | COUF (34460349PTT00001) | 03/10/2021 (34460349PTT00001) | [6 empty] | ALEXANDRA GONZALEZ 571-744-1410 Alexandra.Gonzalez@am.jll.com | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 |  |  |  | 05/25/2021 05/31/2021 |  |  | Scheduled | N (34460348) N (34460350) N (34460349) | U0101953 |  |  | NSPE0014535539
Customer Action | TX584 | 125 E Grubb Dr Mesquite, TX 75149 US | 100 MBPS (34384662) | 04/14/2021: Customer action required, pending site readiness. Follow up sent to the LEC asking if they can proceed with their works prior to the customer providing permanent power. Pending response back. Per customer, the latest update from the builder as of last week is that he is still waiting on the info for permanent power, with some additional delays with the city. Is there a possibility that we can proceed with everything up to that point of perm power requirement in dmarc? At this time I do not have a firm date of when that will be completed. | 205313475 | MESQUITE | Private IP - PIP (34384661) WAN Analysis Reporting (34384663) Access (34384662) | 34384661 34384663 34384662 | 50 MBPS (34384661) |  | 94976952 (Private IP (PIP)) 94976956 (WAN Analysis Reporting) 94976954 (Access) | C1153616/ADD (34384661) E4069498/ADD (34384662) |  | 6232809 | 30000 | PVC ID : 6232809 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64798 PE IP Address : 159.24.134.221 CE Address : 159.24.134.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34384662) | 1000Base-SX (850nm, Multi Mode Fiber) (34384662) | Ethernet | NITEL USA (3438466285777201) | 02/26/2021 (3438466285777201) | [6 empty] | KHANH NGUYEN 1-817-918-2920 knguyen11@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 |  |  |  | 04/06/2021 04/12/2021 |  |  | Scheduled | N (34384661) N (34384663) N (34384662) | U0101953 | Jeopardy Notification 4 (04/11/2021) |  | NSPE0014525488
Provisioning Accepted | 100G IDE ELK RIVER TO COLOGNE | 14100 BUSINESS CENTER DR NW ELK RIVER, MN 55330 USA |  | 04/14/2021: Verizon build CCR 1908210 for a Roadm Card add to install 100Gb capacity in the private UnitedHealth roadm. Ready for traffic date 4/30. To date materials are still back ordered - if received by this week - still on track. After CCR is complete will step the order to BNE for review, proceed with scheduling of any required local dispatches and final testing. 03/18/2021: Per the provisioning team, please allow 8 to 12 weeks augmentation and once done port will be assigned. | 10652116 |  | Internet Dedicated (IQBL36NS) Internet Dedicated (U8003801) | IQBL36NS U8003801 | [19 empty] | TIM GUNDERSON 7637442081 TIM_GUNDERSON@OPTUM.COM | [10 empty] | N (IQBL36NS) N (U8003801) |  |  |  | NSPE0014531944
Provisioning Accepted | 100G IDE CHASKA TO COLOGNE | 1707 W CREEK LN CHASKA, MN 55318 USA |  | 04/14/2021: Verizon build CCR 1908200 for a Roadm Card add to install 100Gb capacity in the private UnitedHealth roadm. Ready for traffic date 4/30. To date materials are still back ordered - if received by this week - still on track. After CCR is complete will step the order to BNE for review, proceed with scheduling of any required local dispatches and final testing. 04/01/2021: Verizon build CCR 1908200 for a Roadm Card add to install 100Gb capacity in the private UnitedHealth roadm. Ready for traffic date 4/30. After CCR is complete will step the order to BNE for review, proceed with scheduling of any required local dispatches and final testing. | 10652114 |  | Internet Dedicated (IQBL36N6) Internet Dedicated (U8003803) | IQBL36N6 U8003803 | [19 empty] | TIM GUNDERSON 7637442081 TIM_GUNDERSON@OPTUM.COM | [10 empty] | N (IQBL36N6) N (U8003803) |  |  |  | NSPE0014531921
Pending Loop Accepted | TX627 | 6430 Hillcroft St Houston, TX 77081-3191 US | 50 MBPS (34501577) | 04/14/2021: FOC date 7/21. Overall build ECD 7/16. 1-5 splices needed, placing up to 2000 feet of fiber. Long term permit approvals need to be obtained.: | 205435367 | TX627 | Private IP - PIP (34501576) WAN Analysis Reporting (34501578) Access (34501577) | 34501576 34501578 34501577 | 10 MBPS (34501576) |  | 94983230 (Private IP (PIP)) 94983233 (WAN Analysis Reporting) 94983235 (Access) | C4026675/ADD (34501576) E4070119/ADD (34501577) | 28/KRGN/751349//SW (3450157793155201) | 6235380 | 5500 | PVC ID : 6235380 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64752 PE IP Address : 68.138.71.45 CE Address : 68.138.71.46 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (34501577) | 1000Base-SX (850nm, Multi Mode Fiber) (34501577) | Ethernet | ATT (3450157793155201) | 03/09/2021 (3450157793155201) | 07/21/2021 (3450157793155201) | [5 empty] | SCOTT B CANNON 1-813-695-3652 scannon1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 |  |  | 07/30/2021 (34501576) 07/28/2021 (34501577) | 04/19/2021 04/23/2021 |  |  | Approved | N (34501576) N (34501578) N (34501577) | U0101953 |  |  | NSPE0014578259
Customer Action | NV190 | 8410 W Warm Springs Rd ste 10 Las Vegas, NV 89113-3624 US | 100 MBPS (34515739) | 04/14/2021: Customer action required, pending site readiness. Pending confirmation from customer if site is now ready. Follow up made. | 205447923 | NV190 | Private IP - PIP (34515738) WAN Analysis Reporting (34515740) Access (34515739) | 34515738 34515740 34515739 | 100 MBPS (34515738) |  | 94983972 (Private IP (PIP)) 94983975 (WAN Analysis Reporting) 94983977 (Access) | C1154113/ADD (34515738) E4070218/ADD (34515739) |  | 6235688 | 70000 | PVC ID : 6235688 VPN Name : UnitedHealthGroup Router Name : LSVG3E01 VRF Name : V460106-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65295 PE IP Address : 152.162.1.145 CE Address : 152.162.1.146 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34515739) | 1000Base-SX (850nm, Multi Mode Fiber) (34515739) | Ethernet | CENTURYLINK (3451573992571701) | 03/10/2021 (3451573992571701) | [6 empty] | DAVID RUCKDASCHEL 1-702-243-8580 david.ruckdaschel@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  |  | 05/10/2021 05/14/2021 |  |  | Scheduled | N (34515738) N (34515740) N (34515739) | U0101953 | Jeopardy Notification 2 (04/07/2021) |  | NSPE0014582149
Pending Loop Accepted | TX622 | 6969 Gulf Fwy Houston, TX 77087-2554 US | 50 MBPS (34522865) | 04/14/2021: FOC date 5/26. Build ECD 5/20. SOW: 1-5 splices needed, placing up to 2000 feet of fiber. Long term permit approvals need to be obtained. | 205455571 | TX622 | Private IP - PIP (34522864) WAN Analysis Reporting (34522866) Access (34522865) | 34522864 34522866 34522865 | 10 MBPS (34522864) |  | 94985379 (Private IP (PIP)) 94985384 (WAN Analysis Reporting) 94985377 (Access) | C4026720/ADD (34522864) E4070272/ADD (34522865) | 28/KRGN/751367//SW (3452286593292001) | 6235853 | 5500 | PVC ID : 6235853 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65293 PE IP Address : 152.181.77.1 CE Address : 152.181.77.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34522865) | 1000Base-SX (850nm, Multi Mode Fiber) (34522865) | Ethernet | ATT (3452286593292001) | 03/18/2021 (3452286593292001) | 05/26/2021 (3452286593292001) | [5 empty] | SCOTT B CANNON 1-813-695-3652 scannon1@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 |  |  | 06/07/2021 (34522864) 06/03/2021 (34522865) | 04/28/2021 05/04/2021 |  |  | Scheduled | N (34522864) N (34522866) N (34522865) | U0101953 | Jeopardy Notification 1 (03/17/2021) |  | NSPE0014584542
Pending Loop Accepted | TX644 | 951 York Dr Desoto, TX 75115-2052 US | 50 MBPS (34538505) | 04/14/2021: FOC date 6/28. | 205469353 | TX644 | Private IP - PIP (34538504) WAN Analysis Reporting (34538506) Access (34538505) | 34538504 34538506 34538505 | 10 MBPS (34538504) |  | 94987115 (Private IP (PIP)) 94987120 (WAN Analysis Reporting) 94987113 (Access) | C4026744/ADD (34538504) E4070335/ADD (34538505) | 46.L1XX.002975..CHTR (3453850593355801) | 6236187 | 5500 | PVC ID : 6236187 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64896 PE IP Address : 68.138.71.245 CE Address : 68.138.71.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34538505) | 1000Base-SX (850nm, Multi Mode Fiber) (34538505) | Ethernet | TIME WARNER CABLE (3453850593355801) | 03/12/2021 (3453850593355801) | 06/28/2021 (3453850593355801) | [5 empty] | SHERRY GREEN 1-612-642-7302 sgreen11@wellmed.net | ED KIMUEL RAMOS | kimuel_ramos@optum.com | 632-588-5397 |  |  | 07/07/2021 (34538504) 07/05/2021 (34538505) | 07/12/2021 07/16/2021 |  |  | Approved | N (34538504) N (34538506) N (34538505) | U0101953 |  |  | NSPE0014587817
Pending Completion | MD144 | 307 International Cir ste 200 Cockeysville, MD 21030-1322 US | 500 MBPS (34778630) | 04/14/2021: Circuit delivered. Tested completed and order closed. Ready for activation. | 205524805 | MD144 | WAN Analysis Reporting (34778631) Access (34778630) Private IP - PIP (34778629) | 34778631 34778630 34778629 | 300 MBPS (34778629) |  | 94989054 (WAN Analysis Reporting) 94989047 (Access) 94989049 (Private IP (PIP)) | C5014463/ADD (34778629) E5034570/ADD (34778630) | 38.KFGS.305490..CM (3477863093610001) | 6239822 | 140000 | PVC ID : 6239822 VPN Name : UnitedHealthGroup Router Name : BA59E01 VRF Name : Vj45076:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64804 PE IP Address : 152.164.211.1 CE Address : 152.164.211.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34778630) | 1000Base-SX (850nm, Multi Mode Fiber) (34778630) | Ethernet | VERIZON (3477863093610001) | 03/29/2021 (3477863093610001) | 04/05/2021 (3477863093610001) | 04/14/2021 (3477863093610001) |  |  |  |  | Bob Poirier 1-763-361-6661 bob_poirier@optum.com | BRANDON LITTLE | Brandon_little@optum.com | 1-952-687-3694 |  |  | 04/23/2021 (34778629) 04/21/2021 (34778630) | 05/17/2021 05/11/2021 |  |  | Scheduled | N (34778631) N (34778630) N (34778629) | U0101953 | Jeopardy Notification 2 (04/13/2021) |  | NSPE0014614084
Pending Loop Accepted | TX630 | 7707 Fannin St ste 250 Houston, TX 77054-1989 US | 50 MBPS (34775809) | 04/14/2021: FOC date 5/5. | 205697297 | TX630 | Private IP - PIP (34775808) WAN Analysis Reporting (34775810) Access (34775809) | 34775808 34775810 34775809 | 10 MBPS (34775808) |  | 94999380 (Private IP (PIP)) 94999382 (WAN Analysis Reporting) 94999378 (Access) | C4027003/ADD (34775808) E4070984/ADD (34775809) | TX/KXFN/589833/LVLC (3477580994670601) | 6239706 |  | PVC ID : 6239706 | 1000Base-SX-850nm (34775809) | 1000Base-SX (850nm, Multi Mode Fiber) (34775809) | Ethernet | LEVEL 3 (3477580994670601) | 03/29/2021 (3477580994670601) | 05/05/2021 (3477580994670601) | [5 empty] | SCOTT CANNON 1-813-695-3652 scannon@wellmed.net | JEGIN MIKO DIMAYUGA | jegin_dimayuga@optum.com | 63-928-790-6468 |  |  | 05/14/2021 (34775808) 05/12/2021 (34775809) | 05/07/2021 05/13/2021 |  |  | Scheduled | N (34775808) N (34775810) N (34775809) | U0101953 |  |  | NSPE0014662193
Pending FOC | TX640 | 420 N Highway 67 ste D1 Cedar Hill, TX 75104-6069 US | 50 MBPS (34787692) | 04/14/2021: Site visit ECD set to 4/16. Pending FOC date. | 205709789 | TX640 | Private IP - PIP (34787691) WAN Analysis Reporting (34787693) Access (34787692) | 34787691 34787693 34787692 | 10 MBPS (34787691) |  | 94999485 (Private IP (PIP)) 94999487 (WAN Analysis Reporting) 94999483 (Access) | C4027019/ADD (34787691) E4071042/ADD (34787692) |  | 6240058 | 5500 | PVC ID : 6240058 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64719 PE IP Address : 68.138.19.237 CE Address : 68.138.19.238 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34787692) | 1000Base-SX (850nm, Multi Mode Fiber) (34787692) | Ethernet | ATT (3478769294793701) | 04/13/2021 (3478769294793701) | [6 empty] | KHANH NGUYEN 1-817-918-2920 knguyen11@wellmed.net | PAUL BARCLAY | paul.barclay@optum.com | 1-617-530-2394 |  |  |  | 05/24/2021 05/28/2021 |  |  | Scheduled | N (34787691) N (34787693) N (34787692) | U0101953 | Jeopardy Notification 2 (04/12/2021) |  | NSPE0014666161
Pending Loop Accepted | TX652 | 2324 Jacaman Rd Laredo, TX 78041-6201 US | 100 MBPS (34813749) | 04/14/2021: FOC date 6/22. Build ECD 06/17. SOW 6-10 splices needed, placing up to 2000 feet of fiber. Long term permit approvals need to be obtained. | 205724175 | TX652 | Private IP - PIP (34813748) WAN Analysis Reporting (34813750) Access (34813749) | 34813748 34813750 34813749 | 50 MBPS (34813748) |  | 95000630 (Private IP (PIP)) 95000636 (WAN Analysis Reporting) 95000633 (Access) | C1155025/ADD (34813748) E4071117/ADD (34813749) | 31/KRGN/655456//SW (3481374994901001) | 6240392 |  | PVC ID : 6240392 | 1000Base-SX-850nm (34813749) | 1000Base-SX (850nm, Multi Mode Fiber) (34813749) | Ethernet | ATT (3481374994901001) | 04/01/2021 (3481374994901001) | 06/22/2021 (3481374994901001) | [5 empty] | Gabriel Rodriguez 1-210-974-6678 gRodriguez1@wellmed.net | PAUL BARCLAY | paul.barclay@optum.com | 1-617-530-2394 |  |  | 07/01/2021 (34813748) 06/29/2021 (34813749) | 05/11/2021 05/17/2021 |  |  | Approved | N (34813748) N (34813750) N (34813749) | U0101953 |  |  | NSPE0014669741
Pending FOC | FL149 | 201 N Tarragona St Pensacola, FL 32502-4843 US | 50 MBPS (34839663) | 04/14/2021: Pending FOC date. Follow up sent to LEC requesting status of FOC. | 205760157 | UNITEDHEALTH GROUP | Private IP - PIP (34839662) WAN Analysis Reporting (34839664) Access (34839663) | 34839662 34839664 34839663 | 10 MBPS (34839662) |  | 95000984 (Private IP (PIP)) 95000980 (WAN Analysis Reporting) 95000982 (Access) | C4027086/ADD (34839662) E4071184/ADD (34839663) |  | 6240712 |  | PVC ID : 6240712 | 1000Base-SX-850nm (34839663) | 1000Base-SX (850nm, Multi Mode Fiber) (34839663) | Ethernet | SOUTHERN LIGHT (3483966327241901) | 04/01/2021 (3483966327241901) | [6 empty] | KELLEY MAJEWSKI 1-850-454-4474 kmajewski@ambienthealth.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 |  |  |  | 08/20/2021 08/26/2021 |  |  | Scheduled | N (34839662) N (34839664) N (34839663) | U0101953 |  |  | NSPE0014676204
Provisioning Accepted | CN522 | 3rd Floor - 555 Industrial Dr Milton, ON L9T 5E1 CA | 100 MBPS (34873386) | 04/14/2021: Target Install Date: May 14th, 2021. Follow up sent to provisioning asking if site survey has been completed and if the Telco has a FIRM install date yet. Pending response back. | 205763895 | Milton | Internet Dedicated Services (34873385) Access (34873386) | 34873385 34873386 | 100 MBPS (34873385) |  | 1359263343 (Internet Dedicated Services) 1359263339 (Access) | C1155199/ADD (34873385) E4071360/ADD (34873386) |  | 6241466 6241671 |  | PVC ID : 6241466,6241671 | 100Base-TX (34873386) | 100Base-TX (34873386) | Ethernet | [8 empty] | LAURIE FAULKNOR 1-416-560-4680 laurie.faulknor@optum.com | LAURIE FAULKNOR | laurie.faulknor@optum.com | 1-416-560-4680 |  |  | 05/26/2021 (34873385) 05/26/2021 (34873386) | 06/22/2021 |  | 04/07/2021 (34873385) |  | N (34873385) N (34873386) | U0101953 |  |  | NSPE0014677105
Provisioning Accepted | C1663 | 6900 S PEORIA ST CENTENNIAL, CO 80112-4137 US | 10 GBPS | 04/14/2021: Customer action required, pending new date/time to schedule to turn up for circuit. | 205764569 | UHG- Trizetto | Private IP - PIP (34843690) Access WAN Analysis Reporting (34843692) | 34843690 34843692 | 1 GBPS (34843690) |  | 1341961883 (Private IP (PIP)) 1341961879 1341961885 (WAN Analysis Reporting) | C0210882/NONE (34843690) |  | 6214643 | 550000 | PVC ID : 6214643 VPN Name : UHG-ECC Router Name : EADXE01 VRF Name : Vi90743-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65436 PE IP Address : 68.136.181.93 CE Address : 68.136.181.94 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) | Ethernet | [8 empty] | Vaishna Priya 91-804-670-4313 Vaishna@optum.com | Vaishna Priya | Vaishna@optum.com | 91-804-670-4313 |  |  | 04/02/2021 (34843690) | 04/21/2021 04/12/2021 (19608601.5) |  |  | Scheduled Scheduled Status Set | N (34843690) N N (34843692) | U0101953 |  |  | NSPE0014677329
Provisioning Accepted | W1B73055- DISCONNECT | 4200 NASH COURT JOHN SMITH DRIVE OXFORDOX4 2RU GBR | PETHE-1-ETHER 20 (6446379) | 04/14/2021: This was escalated to provisioning management for assistance to get confirmation if technical verification is needed and if not when will the disconnect request be sent to local PTT. Pending response back. | 10674085 |  | Private IP (6446379) | 6446379 | 20 MBPS |  |  | W1B73055 (6446379) |  | 5614080 | 3072 | PVC ID : 5614080 VPN Name : UnitedHealthGroup Router Name : WGTN9E01 VRF Name : Vj04345:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65147 PE IP Address : 152.185.78.9 CE Address : 152.185.78.10 QoS - Egress Profile: R12 |  |  |  | VERIZON BUSINESS - INTL LOCS | [6 empty] | TECH ON DUTY 9999 999 999 | LESLIE PATRICK ISAAC +44 01865 787320 LESLIE.ISAAC@OPTUM.COM | [6 empty] | 05/17/2021 (6446379) |  |  |  | N (6446379) | 00179802 |  | W1B73055- DISCONNECT | NSPE0014631313
Pending FOC | TX624 | 12036 Airline Dr Houston, TX 77037-1006 US | 50 MBPS (34852555) | 04/14/2021: Pending FOC date. | 205770811 | TX624 | Private IP - PIP (34852554) WAN Analysis Reporting (34852556) Access (34852555) | 34852554 34852556 34852555 | 10 MBPS (34852554) |  | 95000995 (Private IP (PIP)) 95000991 (WAN Analysis Reporting) 95000993 (Access) | C4027100/ADD (34852554) E4071239/ADD (34852555) |  | 6240956 | 8 | PVC ID : 6240956 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65292 PE IP Address : 152.177.58.225 CE Address : 152.177.58.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34852555) | 1000Base-SX (850nm, Multi Mode Fiber) (34852555) | Ethernet | ATT (3485255595133601) | 04/02/2021 (3485255595133601) | [6 empty] | SCOTT B CANNON 1-813-695-3652 scannon1@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 |  |  |  | 05/13/2021 05/19/2021 |  |  | Scheduled | N (34852554) N (34852556) N (34852555) | U0101953 |  |  | NSPE0014679230
Pending Loop Accepted | FL470 | 11399 16th Ct N ste 110 Saint Petersburg, FL 33716-2322 US | 200 MBPS (34854800) | 04/14/2021: FOC date 5/10. | 205772167 | FL470 | Access (34854800) Private IP - PIP (34854799) WAN Analysis Reporting (34854801) | 34854800 34854799 34854801 | 100 MBPS (34854799) |  | 95001508 (Access) 95001503 (Private IP (PIP)) 95001505 (WAN Analysis Reporting) | E5034734/ADD (34854800) C5014524/ADD (34854799) | FL/KXFN/592301/LVLC (3485480095163802) FL/KXFN/594489/LVLC (3485480095163801) | 6241049 | 70000 | PVC ID : 6241049 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64556 PE IP Address : 152.176.116.241 CE Address : 152.176.116.242 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34854800) | 1000Base-SX (850nm, Multi Mode Fiber) (34854800) | Ethernet | LEVEL 3 (3485480095163802) LEVEL 3 (3485480095163801) | 04/02/2021 (3485480095163802) 04/02/2021 (3485480095163801) | 05/10/2021 (3485480095163802) 05/10/2021 (3485480095163801) | [5 empty] | Alison Paxson 1-410-324-2929 Alison.Paxson@connectyourcare.com | BRANDON LITTLE | emurugan@marchvisioncare.com | 1-952-687-3694 |  |  |  | 05/13/2021 05/19/2021 |  |  | Scheduled | N (34854800) N (34854799) N (34854801) | U0101953 |  |  | NSPE0014679692
Pending FOC | TX653 | 8168 Hwy 77 Sinton, TX 78387-9746 US | 50 MBPS (34865428) | 04/14/2021: Pending FOC date. Per ATT: Customer is ready, next step infrastructure complete ECD 05/24/21. Construction Complexity: Placing up to 2,000ft Fiber, Splicing, Long Term Permits Required and NTE required. Per customer, got an update that the unit is expected to be on-site on 10 MAY, with on-site interior work to start on 17 MAY. | 205782429 | TX653 | Private IP - PIP (34865427) WAN Analysis Reporting (34865429) Access (34865428) | 34865427 34865429 34865428 | 10 MBPS (34865427) |  | 95002372 (Private IP (PIP)) 95002376 (WAN Analysis Reporting) 95002370 (Access) | C4027115/ADD (34865427) E4071304/ADD (34865428) |  |  | 5500 | VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64792 PE IP Address : 152.177.71.113 CE Address : 152.177.71.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34865428) | 1000Base-SX (850nm, Multi Mode Fiber) (34865428) | Ethernet | ATT (3486542895348501) | 04/05/2021 (3486542895348501) | [6 empty] | Rick Williamson 1-210-951-3129 RWilliamson@wellmed.net | PAUL BARCLAY | paul.barclay@optum.com | 1-617-530-2394 |  |  |  | 05/14/2021 05/20/2021 |  |  | Approved | N (34865427) N (34865429) N (34865428) | U0101953 |  |  | NSPE0014682324
Pending FOC | TX352 | 1959 Saratoga Blvd Corpus Christi, TX 78417-3415 US | 50 MBPS (34867136) | 04/14/2021: Order reflected to update dmarc building 29. Pending FOC date. | 205783791 | TX352-02-IM Corpus Christi, TX | Private IP - PIP (34867135) WAN Analysis Reporting (34867137) Access (34867136) | 34867135 34867137 34867136 | 10 MBPS (34867135) |  | 95002382 (Private IP (PIP)) 95002386 (WAN Analysis Reporting) 95002380 (Access) | C4027120/ADD (34867135) E4071313/ADD (34867136) |  | 6241367 | 5500 | PVC ID : 6241367 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65080 PE IP Address : 152.177.251.81 CE Address : 152.177.251.82 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (34867136) | 1000Base-LX (1310nm Single Mode Fiber) (34867136) | Ethernet | TIME WARNER CABLE (3486713624907701) | 04/06/2021 (3486713624907701) | [6 empty] | DeeAnne Luevano 1-361-883-3095 dluevano@wellmed.net | JEALINE TEODORO | jealine.teodoro@optum.com | 632-588-5307 |  |  |  | 08/12/2021 08/18/2021 |  |  | Scheduled | N (34867135) N (34867137) N (34867136) | U0101953 |  |  | NSPE0014682762
Pending FOC | NM047 | 530 N Telshor Blvd ste C Las Cruces, NM 88011-8243 US | 50 MBPS (34876677) | 04/14/2021: Pending FOC date. | 205792907 | NM047 | Private IP - PIP (34876676) WAN Analysis Reporting (34876678) Access (34876677) | 34876676 34876678 34876677 | 10 MBPS (34876676) |  | 95002945 (Private IP (PIP)) 95002941 (WAN Analysis Reporting) 95002943 (Access) | C4027137/ADD (34876676) E4071370/ADD (34876677) |  | 6241554 |  | PVC ID : 6241554 | 1000Base-SX-850nm (34876677) | 1000Base-LX (1310nm Single Mode Fiber) (34876677) | Ethernet | CENTURYLINK (3487667795422601) | 04/06/2021 (3487667795422601) | [6 empty] | Valeria Lozano 1-915-259-1544 vlozano@wellmed.net | JEALINE TEODORO | jealine.teodoro@optum.com | 632-588-5307 |  |  |  | 05/17/2021 05/21/2021 |  |  | Scheduled | N (34876676) N (34876678) N (34876677) | U0101953 |  |  | NSPE0014685516
Pending FOC | AL015 | 660 University Blvd ste A Birmingham, AL 35233-1123 US | 20 MBPS (34877257) | 04/14/2021: Pending FOC date. | 205793969 | AL015-02-IJ Birmingham AL | Private IP - PIP (34877256) WAN Analysis Reporting (34877258) Access (34877257) | 34877256 34877258 34877257 | 10 MBPS (34877256) |  | 95003064 (Private IP (PIP)) 95003066 (WAN Analysis Reporting) 95003069 (Access) | C3037080/ADD (34877256) E3105132/ADD (34877257) |  | 6241576 | 5500 | PVC ID : 6241576 VPN Name : UnitedHealthGroup Router Name : B6S3E01 VRF Name : V546882-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64650 PE IP Address : 68.136.194.125 CE Address : 68.136.194.126 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34877257) | 1000Base-SX (850nm, Multi Mode Fiber) (34877257) | Ethernet | ATT (3487725716589101) | 04/06/2021 (3487725716589101) | [6 empty] | Jane Johnson 1-859-229-0900 jjohnson1@optum.com | Ricardo Kalaw | ricardo_kalaw@optum.com | 63-977-234-2133 |  |  |  | 05/17/2021 05/21/2021 |  |  | Scheduled | N (34877256) N (34877258) N (34877257) | U0101953 |  |  | NSPE0014685734
Pending FOC | FL208 | 8509 Benjamin Rd Tampa, FL 33634-1224 US | 20 MBPS (34885601) | 04/14/2021: Pending FOC date. | 205795563 | FL208-02-IJ | Private IP - PIP (34885600) WAN Analysis Reporting (34885602) Access (34885601) | 34885600 34885602 34885601 | 10 MBPS (34885600) |  | 95003074 (Private IP (PIP)) 95003076 (WAN Analysis Reporting) 95003079 (Access) | C3037161/ADD (34885600) E3105356/ADD (34885601) |  | 6242657 | 8 | PVC ID : 6242657 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64547 PE IP Address : 152.164.64.193 CE Address : 152.164.64.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34885601) | 1000Base-SX (850nm, Multi Mode Fiber) (34885601) | Ethernet | FRONTIER (3488560122320601) | 04/13/2021 (3488560122320601) | [6 empty] | Nancy Davenport 1-813-559-3201 Ndavenport@optum.com | RICARDO KALAW | ricardo_kalaw@optum.com | 63-977-234-2133 |  |  |  | 05/17/2021 05/21/2021 |  |  | Scheduled | N (34885600) N (34885602) N (34885601) | U0101953 |  |  | NSPE0014686221
Pending BEAS Install | FL370 | 21301 Powerline Rd Boca Raton, FL 33433-2388 US | 20 MBPS (34885759) | 04/14/2021: Circuit delivered. Pending scheduling of beas install. | 205800809 | FL370-01-IM | Private IP - PIP (34885758) WAN Analysis Reporting (34885760) Access (34885759) | 34885758 34885760 34885759 | 10 MBPS (34885758) |  | 95003196 (Private IP (PIP)) 95003200 (WAN Analysis Reporting) 95003194 (Access) | C3037096/ADD (34885758) E3105164/ADD (34885759) | 60/KRGN/767175//SB (3488575944405701) | 6241814 | 5500 | PVC ID : 6241814 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64741 PE IP Address : 152.164.17.213 CE Address : 152.164.17.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34885759) | 1000Base-SX (850nm, Multi Mode Fiber) (34885759) | Ethernet | ATT (3488575944405701) | 04/08/2021 (3488575944405701) | 04/13/2021 (3488575944405701) | 04/13/2021 (3488575944405701) |  |  | DEMARCADDR - 21301 Powerline Rd Boca Raton FL DEMARCDET - 2ND FLR SUITE 206 REAR TELCO WALL SLIM BOX 1 LC CONNECTOR HANDOFF MMF |  | Sue Schuldt 1-561-314-0644 sschuldt@optum.com | RICARDO KALAW | ricardo_kalaw@optum.com | 63-977-234-2133 |  |  | 04/22/2021 (34885758) 04/20/2021 (34885759) | 05/18/2021 05/24/2021 |  |  | Scheduled | N (34885758) N (34885760) N (34885759) | U0101953 |  |  | NSPE0014686297
Provisioning Accepted | CB501 | Avenida Calle 26, 92-32 Bogotá110911 CO | 50 MBPS (34972979) | 04/14/2021: TEV (technical verification) was completed with customer. Order submitted to provisioning for review/approval before the order is sent to the local PTT to request the FOC date. | 205818427 | Bogotá | Private IP - PIP (34972978) WAN Analysis Reporting (34972980) Access (34972979) | 34972978 34972980 34972979 | 30 MBPS (34972978) |  | 1365547791 (Private IP (PIP)) 1365547793 (WAN Analysis Reporting) 1365547787 (Access) |  |  | 6243058 |  | PVC ID : 6243058 | 100Base-TX (34972979) | 100Base-TX (34972979) | Ethernet | [8 empty] | Robert Loaiza 1-763-330-3161 robert.loaiza@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  |  | 07/02/2021 07/09/2021 |  |  |  | N (34972978) N (34972980) N (34972979) | U0101953 |  |  | NSPE0014686719
Provisioning Accepted | TX654 | 1039 N Twin City Hwy ste B Nederland, TX 77627-3851 US | 50 MBPS (34889422) | 04/14/2021: Pending FOC date. | 205804497 | TX654 | WAN Analysis Reporting (34889423) Access (34889422) Private IP - PIP (34889421) | 34889423 34889422 34889421 | 10 MBPS (34889421) |  | 95003541 (WAN Analysis Reporting) 95003543 (Access) 95003545 (Private IP (PIP)) | C4027161/ADD (34889421) E4071439/ADD (34889422) |  | 6241893 | 5500 | PVC ID : 6241893 VPN Name : UnitedHealthGroup Router Name : HSTN9E02 VRF Name : Vh45943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65278 PE IP Address : 152.177.134.205 CE Address : 152.177.134.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34889422) | 1000Base-SX (850nm, Multi Mode Fiber) (34889422) | Ethernet | ATT (3488942295520103) | [7 empty] | Paul Polanco 1-346-227-7949 ppolanco@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-907-841-6163 |  |  |  | 05/24/2021 05/18/2021 |  |  | Scheduled | N (34889423) N (34889422) N (34889421) | U0101953 |  |  | NSPE0014688901
Pending Loop Accepted | CT123 | 33 N Plains Industrial Rd Wallingford, CT 06492-5841 US | 20 MBPS (34906246) | 04/14/2021: FOC date 5/10. | 205820357 | ENT CT123 Wallingford | Private IP - PIP (34906245) WAN Analysis Reporting (34906247) Access (34906246) | 34906245 34906247 34906246 | 10 MBPS (34906245) |  | 95004849 (Private IP (PIP)) 95004853 (WAN Analysis Reporting) 95004851 (Access) | C3037142/ADD (34906245) E3105253/ADD (34906246) | FA/KRGN/588799//SN/ (3490624627179801) | 6242183 |  | PVC ID : 6242183 | 1000Base-SX-850nm (34906246) | 1000Base-SX (850nm, Multi Mode Fiber) (34906246) | Ethernet | FRONTIER (3490624627179801) | 04/09/2021 (3490624627179801) | 05/10/2021 (3490624627179801) | [5 empty] | Pauline Cleaver 1-201-303-5547 pcleaver@optum.com | RICARDO KALAW | ricardo_kalaw@optum.com | 63-977-234-2133 |  |  | 05/19/2021 (34906245) 05/17/2021 (34906246) | 05/19/2021 05/25/2021 |  |  | Scheduled | N (34906245) N (34906247) N (34906246) | U0101953 |  |  | NSPE0014692662
Verizon Restricted

## Close to Bill
Customer Summary Status | Site ID | Location - Customer Location Z Full Address | Access Speed | External Comments - Latest | TIN/ProQuest Service Order ID | Location Name | Product (Order ID) | Order ID | Port Speed | COMS Service ID | Service ID | Circuit ID | Telco Circuit ID | PVC ID | Gold CAR | PIP Configlet | TPV LAN Interface | WAN Interface to the CE (Customer Edge) | Customer Handoff | Telco Name (Purchase Order Number) | Telco ASR Sent | Telco FOC Date | Loop Accepted | Dispatch Scheduled (NID) | Dispatch Completion Date | Actual Demarc | Site Contact A | Site Contact Z | Technical Contact Name | Technical Contact Email | Technical Contact Number | Close to Bill | Activation Date | Hotcut Completed Date | VZ Committed Due Date | Requested Due Date | Service Order Billing Complete | Cancel Date | Managed Status | Expedite Flag | BAN | Jeop Notification | Description | Email ID | Request Date
Completed | TX038-05-IJ San Antonio TX | 5859 FARINON DR SAN ANTONIO, TX 78249-3460 US | 100 MBPS (21656820) |  | 191884960 | TX038-05-IJ San Antonio TX | Access (21656820) Private IP - PIP (21656819) | 21656820 21656819 | 100 MBPS (21656819) |  | 82053205 (Access) 82053207 (Private IP (PIP)) | E4007185/ADD (21656820) C1027141/ADD (21656819) | 31/KRGN/651668//SW (2165682018846901) | 5664069 | 10000 | PVC ID : 5664069 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65044 PE IP Address : 152.176.58.21 CE Address : 152.176.58.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21656820) | 1000Base-SX (850nm, Multi Mode Fiber) (21656820) | Ethernet | ATT (2165682018846901) | 10/14/2015 (2165682018846901) | 10/29/2015 (2165682018846901) | 10/29/2015 (2165682018846901) | 11/19/2015 (VFORCE) (21656820) | 11/19/2015 (VFORCE) (21656820) | DEMARCADDR - 5859 FARINON DR SAN ANTONIO TX DEMARCDET - 1ST FLR STE 100 INSIDE ELECTRICAL RM WALL MT HANDOFF TRAY#POS3 |  | Brad Niemeyer 1-210-393-7714 brad_niemeyer@uhg.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 11/20/2015(Access) 11/20/2015(Private IP - PIP) | 12/04/2015 |  | 11/30/2015 (21656820) 12/02/2015 (21656819) | 11/30/2015 | 11/20/2015 |  |  | N (21656820) N (21656819) | U0101953 |  | NSPE0010786007 CW 193610881 | NSPE0009722303
Completed | United Health Group Aurora ILL | 4205 WESTBROOK DR AURORA, IL 60504-4124 US | 100 MBPS (21745039) |  | 192053879 | United Health Group Aurora ILL | Private IP - PIP (21745038) Access (21745039) | 21745038 21745039 | 100 MBPS (21745038) |  | 83690680 (Private IP (PIP)) 83690678 (Access) | C1028709/ADD (21745038) E4007618/ADD (21745039) | /KQGN/122482//LB (2174503914275301) /KQGN/122482//LB (VZBCHGU217450391) | 5675603 | 7000 | PVC ID : 5675603 VPN Name : UnitedHealthGroup Router Name : RVDL3E04 VRF Name : V556999-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65253 PE IP Address : 152.161.15.209 CE Address : 152.161.15.210 QoS - Egress Profile: R12 | 100Base-TX (21745039) | 100Base-TX (21745039) | Ethernet | ATT (2174503914275301) ATT (VZBCHGU217450391) | 11/05/2015 (2174503914275301) 03/16/2016 (VZBCHGU217450391) | 11/23/2015 (2174503914275301) 03/28/2016 (VZBCHGU217450391) | 11/19/2015 (2174503914275301) | 11/24/2015 (VFORCE) (21745039) | 11/24/2015 (VFORCE) (21745039) | DEMARCADDR - 4205 WESTBROOK DR AURORA IL DEMARCDET - 1ST FLR TELCO CLOSET NORTH WALL/UNI |  | John Seppelfrick 1-630-849-2384 johnseppelfrick@wellness-inc.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 11/24/2015(Private IP - PIP) 11/24/2015(Access) | 01/19/2016 |  | 12/04/2015 (21745038) 12/02/2015 (21745039) | 12/18/2015 | 11/24/2015 |  |  | N (21745038) N (21745039) | U0101953 |  | TX493-04-IM | NSPE0009768432
Completed | UMD97-06-IJ Baltimore | 1050 HULL ST BALTIMORE, MD 21230-5342 US | 500 MBPS (21733967) |  | 192024840 | UMD97-06-IJ Baltimore | Private IP - PIP (21733966) Access (21733967) | 21733966 21733967 | 500 MBPS (21733966) |  | 83812188 (Private IP (PIP)) 83812186 (Access) | C5001421/ADD (21733966) E5002325/ADD (21733967) | 38.KFGS.301501..CM (2173396785469601) | 5674788 | 30000 | PVC ID : 5674788 VPN Name : UnitedHealthGroup Router Name : RAY9E03 VRF Name : V534296:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65071 PE IP Address : 152.176.14.209 CE Address : 152.176.14.210 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (21733967) | 1000Base-LX (1310nm Single Mode Fiber) (21733967) | Ethernet | VERIZON (2173396785469601) | 11/04/2015 (2173396785469601) | 11/25/2015 (2173396785469601) | 12/01/2015 (2173396785469601) | 12/03/2015 (VFORCE) (21733967) | 12/07/2015 (VFORCE) (21733967) | DEMARCADDR - 1050 HULL ST, BALTIMORE, MD DEMARCDET - 1ST FLR DATA CENTER. RELAY RACK #R2C14. CANOGA J. TAGGED. |  | Ed McLaughlin 1-410-949-2258 edward.mclaughlin@optum.com | Steve Brown | skbrown1@optum.com | 1-763-694-7333 | 12/07/2015(Private IP - PIP) 12/07/2015(Access) | 12/11/2015 |  | 12/15/2015 (21733966) 12/11/2015 (21733967) | 12/11/2015 | 12/07/2015 |  |  | N (21733966) N (21733967) | U0101953 |  |  | NSPE0009772231
|  | 20 GRENFELL ROAD MAIDENHEAD,BERKSHIRESL6 1EH GBR | DS-3PPP-44.736MB (5668920) | 01/07/2016: 1/7- Move completed. | 8319587 |  |  | 5668920 | 44.736 MBPS |  |  | W0W76572 (5668920) | Y0501509A (5494172) Y0501509A (5494174) |  | 12288 | VPN Name : UnitedHealthGroup Router Name : LNDNES04 VRF Name : V227445:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65150 PE IP Address : 206.115.90.13 CE Address : 206.115.90.14 QoS - Egress Profile: R12 |  |  |  | WILLIAMS TELECOMMUNICATIONS (UK) CABLE & WIRELESS UK (5494172) (UK) CABLE & WIRELESS UK (5494174) | 04/17/2015 (5494174) | 12/24/2015 (5494174) | 12/24/2015 (5494174) | [8 empty] | 01/06/2016 (5668920) |  |  | 01/11/2016 (5668920) | 01/11/2016 (5668920) |  |  |  |  | 00219957
Completed | UNC24-07-IJ Charlotte NC | 6101 CARNEGIE BLVD STE 500 CHARLOTTE, NC 28209-4653 US | 100 MBPS (21216973) | 02/04/2016: 2/4- Beas install scheduled 2/5. | 191354243 | UNC24-07-IJ Charlotte NC | Private IP - PIP (21216972) Access (21216973) | 21216972 21216973 | 100 MBPS (21216972) |  | 72458646 (Private IP (PIP)) 72458624 (Access) | C1022537/ADD (21216972) E4005341/ADD (21216973) | 70.L1XX.001688..TWCC (2121697390555601) | 5614453 | 9000 | PVC ID : 5614453 VPN Name : UnitedHealthGroup Router Name : CHRL3E03 VRF Name : V516000-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64926 PE IP Address : 68.136.162.197 CE Address : 68.136.162.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21216973) | 1000Base-SX (850nm, Multi Mode Fiber) (21216973) | Ethernet | TIME WARNER CABLE (2121697390555601) | 12/02/2015 (2121697390555601) | 12/16/2015 (2121697390555601) | 02/01/2016 (2121697390555601) | 02/08/2016 (VFORCE) (21216973) | 02/09/2016 (VFORCE) (21216973) | DEMARCDET - 5th floor mail room then to IT closet. Rad is in the 2nd rack and trifold is on the wall. |  | Ken Sifford 1-704-442-4145 kensifford@uhc.com | Anupam Datt | anupam_datt@optum.com | 1-987-313-9388 | 02/09/2016(Private IP - PIP) 02/09/2016(Access) | 03/15/2016 |  | 02/18/2016 (21216972) 02/16/2016 (21216973) | 02/16/2016 | 02/09/2016 |  |  | N (21216972) N (21216973) | U0101953 |  |  | NSPE0009399573
Completed | WA708-02-IJ Allere Seattle | 223 TAYLOR AVE N SEATTLE, WA 98109-5021 US | 500 MBPS (21686025) | 01/27/2016: 1/27- Beas install complete 1/20. Circuit tested, ready for activation. | 191958482 | WA708-02-IJ Allere Seattle | Private IP - PIP (21686024) Access (21686025) | 21686024 21686025 | 500 MBPS (21686024) |  | 82765174 (Private IP (PIP)) 82765172 (Access) | C5001379/ADD (21686024) E5002245/ADD (21686025) | 1D/KFFN/002347/TWCS (2168602585167301) | 5667980 | 1500 | PVC ID : 5667980 VPN Name : UnitedHealthGroup Router Name : HICGE02 VRF Name : V556790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64824 PE IP Address : 208.219.142.5 CE Address : 208.219.142.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21686025) | 1000Base-SX (850nm, Multi Mode Fiber) (21686025) | Ethernet | LEVEL 3 (2168602585167301) | 10/22/2015 (2168602585167301) | 11/19/2015 (2168602585167301) | 01/12/2016 (2168602585167301) | 01/20/2016 (VFORCE) (21686025) | 01/20/2016 (VFORCE) (21686025) | DEMARCDET - 3rd floor, colo area, customer colo cage, rack #1, ED005 Adva, access port 5, MMF, LC, 1000Full. Tagged w/CID. |  | Kevin Griffin 1-404-538-3584 Kevin.Griffen@alere.com | Mohan Basnet | mohan_basnet@optum.com | 1-763-744-1971 | 01/20/2016(Private IP - PIP) 01/20/2016(Access) | 01/28/2016 |  | 01/21/2016 (21686024) 01/19/2016 (21686025) | 01/19/2016 | 01/20/2016 |  |  | N (21686024) N (21686025) | U0101953 |  |  | NSPE0009743725
Completed | GA019-02-IJ Atlanta GA | 2100 RIVEREDGE PKWY ATLANTA, GA 30328-4693 US | 150 MBPS (21341300) |  | 191490902 | GA019-02-IJ Atlanta, GA | Private IP - PIP (21341299) Access (21341300) | 21341299 21341300 | 150 MBPS (21341299) |  | 75260670 (Private IP (PIP)) 75260668 (Access) | C4001829/ADD (21341299) E4005837/ADD (21341300) |  | 5627905 | 70000 | PVC ID : 5627905 VPN Name : UnitedHealthGroup Router Name : CPZ3E02 VRF Name : V450868-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64818 PE IP Address : 152.176.226.109 CE Address : 152.176.226.110 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (21341300) | Ethernet | [8 empty] | Agnieszka Seremak 1-404-267-6571 agnieszka_seremak@uhg.com | Humayun Rafi | humayun_rafi@optum.com | 91-990-002-2170 | 12/03/2015(Private IP - PIP) 12/03/2015(Access) | 01/12/2016 |  | 12/09/2015 (21341299) 12/07/2015 (21341300) | 01/05/2016 | 12/03/2015 |  |  | N (21341299) N (21341300) | U0101953 |  |  | NSPE0009470070
Completed | C1345-05-IJ West San Antonio TX | 11330 W INTERSTATE 10 SAN ANTONIO, TX 78249-3347 US | 100 MBPS (21348337) |  | 191535071 | C1345-05-IJ West San Antonio, TX | Private IP - PIP (21348336) Access (21348337) | 21348336 21348337 | 100 MBPS (21348336) |  | 75609603 (Private IP (PIP)) 75609601 (Access) | C1024169/ADD (21348336) E4005866/ADD (21348337) | 21.L1XX.004941..TWCC (2134833710089301) | 5629969 | 1500 | PVC ID : 5629969 VPN Name : UHG-ECC Router Name : RCN9E01 VRF Name : V565764:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65483 PE IP Address : 152.161.45.121 CE Address : 152.161.45.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21348337) | 1000Base-SX (850nm, Multi Mode Fiber) (21348337) | Ethernet | TIME WARNER CABLE (2134833710089301) | 08/05/2015 (2134833710089301) | 11/25/2015 (2134833710089301) | 11/18/2015 (2134833710089301) | 12/01/2015 (VFORCE) (21348337) | 12/01/2015 (VFORCE) (21348337) | DEMARCDET - 1st floor Suite 150 Server room, Rack RU 30 |  | Mark Hettler 1-210-535-8588 Mark.Hettler@alorica.com | TIM GUNDERSON | tim_gunderson@optum.com | 1-763-744-2081 | 12/04/2015(Private IP - PIP) 12/04/2015(Access) | 12/04/2015 |  | 12/08/2015 (21348336) 12/04/2015 (21348337) | 12/04/2015 | 12/04/2015 |  |  | N (21348336) N (21348337) | U0101953 |  |  | NSPE0009487822
Completed | NM020-07-IJ Albuquerque NM | 8220 SAN PEDRO DR NE STE 300 ALBUQUERQUE, NM 87113-2476 US | 50 MBPS (21483971) |  | 191651622 | NM020-07-IJ Albuquerque NM | Private IP - PIP (21483970) Access (21483971) | 21483970 21483971 | 50 MBPS (21483970) |  | 77712035 (Private IP (PIP)) 77712033 (Access) | C4002014/ADD (21483970) E4006406/ADD (21483971) | 59/KXGS/119611//MS (2148397185652201) | 5640161 | 13000 | PVC ID : 5640161 VPN Name : UnitedHealthGroup Router Name : AQHGE02 VRF Name : V551714:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65232 PE IP Address : 152.162.67.113 CE Address : 152.162.67.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21483971) | 1000Base-SX (850nm, Multi Mode Fiber) (21483971) | Ethernet | CENTURYLINK (2148397185652201) | 08/28/2015 (2148397185652201) | 10/19/2015 (2148397185652201) | 11/24/2015 (2148397185652201) | 11/30/2015 (VFORCE) (21483971) | 12/02/2015 (VFORCE) (21483971) | DEMARCADDR - 8220 SAN PEDRO DR NE DEMARCDET - 1ST FL TELCO RM, E-WALL, PORT-4 |  | Andrew J Schesser 1-505-449-4123 andy_schesser@optum.com | Pradeep Yada | pradeep_yadav@optum.com | 1-763-744-1582 | 12/02/2015(Private IP - PIP) 12/02/2015(Access) | 12/07/2015 |  | 12/08/2015 (21483970) 12/04/2015 (21483971) | 12/04/2015 | 12/02/2015 |  |  | N (21483970) N (21483971) | U0101953 |  |  | NSPE0009565517
Completed | UNITED HEALTH GROUP | 1210 NW 95TH ST MIAMI, FL 33147-3318 US | 10 MBPS (21456292) | 12/09/2015: 12/9- ready for activation, customer notified. | 191618986 | UNITED HEALTH GROUP | Private IP - PIP (21456291) Access (21456292) | 21456291 21456292 | 10 MBPS (21456291) |  | 77842757 (Private IP (PIP)) 77842735 (Access) | C0060823/ADD (21456291) E3013139/ADD (21456292) | 60/KRGN/756110//SB (2145629274246101) | 5637380 | 4000 | PVC ID : 5637380 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64811 PE IP Address : 68.139.233.137 CE Address : 68.139.233.138 QoS - Egress Profile: G1 | 1000Base-SX-850nm (21456292) | 1000Base-SX (850nm, Multi Mode Fiber) (21456292) | Ethernet | ATT (2145629274246101) | 11/17/2015 (2145629274246101) | 12/03/2015 (2145629274246101) | 12/04/2015 (2145629274246101) | 12/07/2015 (VFORCE) (21456292) | 12/07/2015 (VFORCE) (21456292) | DEMARCADDR - 1210 NW 95TH ST MIA FL DEMARCDET - 1FL SVR RM RR POS15 CIENA UNIT1 |  | Sandra Chi 1-305-691-1820 SChi@PCPMedicalGroup.Com | ROBERT BENSON | robert_a_benson@optum.com | 1-763-744-2077 | 12/09/2015(Private IP - PIP) 12/09/2015(Access) | 12/28/2015 |  | 12/14/2015 (21456291) 12/10/2015 (21456292) | 12/30/2015 | 12/09/2015 |  |  | N (21456291) N (21456292) | U0101953 |  |  | NSPE0009573236
Completed | FL045-05-IJ Hialeah FL | 5355 W 20TH AVE HIALEAH, FL 33012-2100 US | 10 MBPS (21456820) |  | 191618914 | FL045-05-IJ Hialeah, FL | Private IP - PIP (21456819) Access (21456820) | 21456819 21456820 | 10 MBPS (21456819) |  | 77843124 (Private IP (PIP)) 77843122 (Access) | C0060833/ADD (21456819) E3013146/ADD (21456820) | 60/KRGN/756107//SB (2145682092075501) | 5637424 | 4000 | PVC ID : 5637424 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65167 PE IP Address : 152.183.71.17 CE Address : 152.183.71.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21456820) | 1000Base-SX (850nm, Multi Mode Fiber) (21456820) | Ethernet | ATT (2145682092075501) | 10/27/2015 (2145682092075501) | 11/16/2015 (2145682092075501) | 11/19/2015 (2145682092075501) | 11/23/2015 (VFORCE) (21456820) | 11/23/2015 (VFORCE) (21456820) | DEMARCADDR - 5355 W 20TH AV HLH FL DEMARCDET - 1ST FLR MAIN TELCO RM RR MTD ENGIN |  | Bert Rico 1-305-824-5660 brico2@pcpmedicalgroup.com | ROBERT BENSON | robert_a_benson@optum.com | 1-763-744-2077 | 12/01/2015(Private IP - PIP) 12/01/2015(Access) | 12/04/2015 |  | 12/17/2015 (21456819) 12/15/2015 (21456820) | 11/27/2015 | 12/01/2015 |  |  | N (21456819) N (21456820) | U0101953 |  |  | NSPE0009573236
Completed | UMD43-07-IJ Frederick MD | 800 OAK ST FREDERICK, MD 21703-8443 US | 200 MBPS (21616499) | 12/16/2015: 12/16- ready for activation, customer notified | 191710118 | UMD43-07-IJ Frederick, MD | Private IP - PIP (21616498) Access (21616499) | 21616498 21616499 | 200 MBPS (21616498) |  | 79359082 (Private IP (PIP)) 79359080 (Access) | C5001331/ADD (21616498) E5002148/ADD (21616499) | 40.KFGS.301453..CM (2161649910848801) | 5658778 | 25000 | PVC ID : 5658778 VPN Name : UnitedHealthGroup Router Name : RAY9E03 VRF Name : V534296:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64694 PE IP Address : 152.177.42.229 CE Address : 152.177.42.230 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21616499) | 1000Base-SX (850nm, Multi Mode Fiber) (21616499) | Ethernet | VERIZON (2161649910848801) | 10/02/2015 (2161649910848801) | 10/16/2015 (2161649910848801) | 12/08/2015 (2161649910848801) | 12/17/2015 (VFORCE) (21616499) | 12/16/2015 (VFORCE) (21616499) | DEMARCADDR - 800 OAK ST, FREDERICK, MD DEMARCDET - DATA CENTER RELAY RACK#2 POSITION #9 FROM TOP..TAGGED WITH CKT ID... |  | David Cohagan 1-301-360-8391 david_cohagan@optum.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 12/16/2015(Private IP - PIP) 12/16/2015(Access) | 12/20/2015 |  | 12/23/2015 (21616498) 12/21/2015 (21616499) | 12/21/2015 | 12/16/2015 |  |  | N (21616498) N (21616499) | U0101953 |  |  | NSPE0009629029
|  | 185 ASYLUM ST HARTFORD, CT 06103 USA | 150 MBPS (CQBK7988) 150 MBPS (CQBK799P) | 02/04/2016: 2/4- Hotcut rescheduled for today, 2/4 at 5pm CST. | 8550725 |  | EACS (CQBK7988) Private IP (CQBK799P) | CQBK7988 CQBK799P | 150 MBPS (CQBK7988) 150 MBPS | P1947691 P1947697 |  | EDBKVSLW0001 (CQBK7988) BCBKVSMM0001 (CQBK799P) | earxo rxo 0011 (C0015175.HRT) |  | 22000 | VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65153 PE IP Address : 199.220.114.129 CE Address : 199.220.114.130 QoS - Egress Profile: R12 | [5 empty] | 02/07/2016 (C0015175.HRT) | 02/07/2016 (C0015175.HRT) |  |  |  |  | ANDREW J SCHESSER 8607028284 ANDY_SCHESSER@OPTUM.COM |  |  |  | 02/04/2016 (CQBK7988) 02/04/2016 (CQBK799P) | 02/04/2016 |  | 02/15/2016 (CQBK7988) 02/15/2016 (CQBK799P) | 02/01/2016 (CQBK7988) 02/01/2016 (CQBK799P) |  |  |  | N (CQBK7988) N (CQBK799P) | 05017789 |  |  | NSPE0009686777
Completed | MN051-07-IJ Eden Prairie MN | 13625 TECHNOLOGY DR EDEN PRAIRIE, MN 55344-2252 US | 20 MBPS (21683341) | 01/27/2016: 1/27- Waiting for local contact to schedule beas install with dispatch. | 191951060 | MN051-07-IJ Eden Prairie, MN | Private IP - PIP (21683339) Access (21683341) Private IP - PIP (21683340) | 21683339 21683341 21683340 | 2 MBPS (21683339) 2 MBPS (21683340) |  | 82255225 (Private IP (PIP)) 82255218 (Access) 82255220 (Private IP (PIP)) | C3004642/ADD (21683339) E3015248/ADD (21683341) C3004641/ADD (21683340) | 03/KXGS/128168//NW (2168334123837901) | 5667660 5667659 | 1000 | PVC ID : 5667660 VPN Name : UHG-Lab-VCC,UHG-Lab-UC Router Name : MN39E01 VRF Name : V603210:UHGLabVCC,V569457:UHGLabUC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64954 PE IP Address : v4-68.139.209.1,v6-68.137.246.33 CE Address : v4-68.139.209.2,v6-68.137.246.34 QoS - Egress Profile: R12 PVC ID : 5667659 | 100Base-TX (21683341) | 100Base-TX (21683341) | Ethernet | CENTURYLINK (2168334123837901) | 12/18/2015 (2168334123837901) | 01/05/2016 (2168334123837901) | 01/07/2016 (2168334123837901) | 02/03/2016 (VFORCE) (21683341) | 02/03/2016 (VFORCE) (21683341) | DEMARCDET - LOWER LEVEL ROOM B010 DCF LAB, RACK AE121 CIENA3916 ELE PORT 1 |  | PETER CHISHOLM 1-763-744-1500 peter_chisholm@optum.com | PETER CHISHOLM | peter_chisholm@optum.com | 1-763-744-1500 | 02/04/2016(Private IP - PIP) 02/04/2016(Access) |  |  | 02/16/2016 (21683339) 02/12/2016 (21683341) 02/16/2016 (21683340) | 02/12/2016 | 02/04/2016 |  |  | N (21683339) N (21683341) N (21683340) | U0101953 |  |  | NSPE0009729327
Completed | MN051-07-IJ Eden Prairie MN | 13625 TECHNOLOGY DR EDEN PRAIRIE, MN 55344-2252 US | 20 MBPS (21683367) | 01/27/2016: 1/27- Customer confirmed demarc extension not needed. Waiting for beas install to be scheduled. | 191951041 | MN051-07-IJ Eden Prairie, MN | Private IP - PIP (21683365) Access (21683367) Private IP - PIP (21683366) | 21683365 21683367 21683366 | 2 MBPS (21683365) 2 MBPS (21683366) |  | 82255217 (Private IP (PIP)) 82255155 (Access) 82255224 (Private IP (PIP)) | C3004643/ADD (21683365) E3015250/ADD (21683367) C3004644/ADD (21683366) | 03/KXGS/128636//NW (2168336723837901) | 5667663 5667664 | 1000 | PVC ID : 5667663 VPN Name : UHG-Lab-UC,UHG-Lab-VCC Router Name : MN39E01,MPLS9E01 VRF Name : V569457:UHGLabUC,V573955:UHGLabVCC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64954 PE IP Address : v4-68.138.114.133,v6-152.161.111.125 CE Address : v4-68.138.114.134,v6-152.161.111.126 QoS - Egress Profile: R12 PVC ID : 5667664 VPN Name : UHG-Lab-VCC,UHG-Lab-UC Router Name : MPLS9E01,MN39E01 VRF Name : V573955:UHGLabVCC,V569457:UHGLabUC PE IP Address : v4-152.161.111.125,v6-68.138.114.133 CE Address : v4-152.161.111.126,v6-68.138.114.134 | 100Base-TX (21683367) | 100Base-TX (21683367) | Ethernet | CENTURYLINK (2168336723837901) | 10/22/2015 (2168336723837901) | 01/20/2016 (2168336723837901) | 01/21/2016 (2168336723837901) | 02/03/2016 (VFORCE) (21683367) |  | DEMARCDET - Basement Computer Room Rack Mounted, Ciena 3916 Electrical port #2 |  | PETER CHISHOLM 1-763-744-1500 peter_chisholm@optum.com | PETER CHISHOLM | peter_chisholm@optum.com | 1-763-744-1500 | 02/04/2016(Private IP - PIP) 02/04/2016(Access) |  |  | 02/16/2016 (21683365) 02/12/2016 (21683367) 02/16/2016 (21683366) | 02/12/2016 | 02/04/2016 |  |  | N (21683365) N (21683367) N (21683366) | U0101953 |  |  | NSPE0009729327
Completed | TX777-05-IJ Student Resources Internet T1 | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US | 1.5 MBPS (21745248) |  | 192066444 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (21745247) Access (21745248) | 21745247 21745248 | 1.5 MBPS (21745247) |  | 83540696 (Internet Dedicated Services) 83540694 (Access) | C0068183/ADD (21745247) D1053737/ADD (21745248) |  | 5675569 | 0 | PVC ID : 5675569 VPN Name : Internet Router Name : GW15DFW9 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 26843 PE IP Address : 152.179.253.145 CE Address : 152.179.253.146 DLCI : 500 |  | DS1 (21745248) | TDM | [8 empty] | John Curtiss 1-469-229-6712 jcurtiss@uhcsr.com | John Curtiss | jcurtiss@uhcsr.com | 1-469-229-6712 | 12/01/2015(Internet Dedicated Services) 12/01/2015(Access) | 02/07/2016 |  | 12/03/2015 (21745247) 12/03/2015 (21745248) | 12/01/2015 | 12/01/2015 |  |  | N (21745247) N (21745248) | U0101953 |  |  | NSPE0009764309
|  | UHG 251 ADELAIDE TERRACE PERTHWA 6000 AUS | NX0PPP-1.984MBS (5779065) | 01/15/2016: 1/15- Disconnect complete. | 8557538 |  | Private IP (5779065) | 5779065 | 1.984 MBPS |  |  | W0X83783 (5779065) | N9068359L - TELSTRA EXPRESS 4 (5622126) |  | 512 | VPN Name : UnitedHealthGroup Router Name : PRTHES01 VRF Name : V259925:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65228 PE IP Address : 152.181.45.113 CE Address : 152.181.45.114 QoS - Egress Profile: R12 |  |  |  | WILLIAMS TELECOMMUNICATIONS (AS) TELSTRA COMMUNICATIONS (5622126) | 11/09/2015 (5622126) | 11/09/2015 (5622126) | 11/09/2015 (5622126) |  |  |  | TECH ON DUTY +999 999 9999 | KIM KERSLAKE +61 892254522 | [6 empty] | 01/14/2016 (5779065) | 11/13/2015 (5779065) |  |  |  | N (5779065) | 00179802 |  |  | NSPE0009763768
Completed | KS003-05-IJ Overland park KS | 10895 GRANDVIEW DR STE 200 OVERLAND PARK, KS 66210-1562 US | 250 MBPS (21746239) | 12/16/2015: 12/16- ready for activation, customer notified. | 192053880 | KS003-05-IJ Overland park, KS | Private IP - PIP (21746238) Access (21746239) | 21746238 21746239 | 200 MBPS (21746238) |  | 83690684 (Private IP (PIP)) 83690682 (Access) | C0068131/ADD (21746238) E0000354/ADD (21746239) | 82/KRGN/702801//SW (VZBCHGU217462391) 82/KRGN/702801//SW (2174623911770501) | 5675665 | 13000 | PVC ID : 5675665 VPN Name : UnitedHealthGroup Router Name : IDCXE03 VRF Name : V560358-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65041 PE IP Address : 152.185.253.57 CE Address : 152.185.253.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21746239) | 1000Base-SX (850nm, Multi Mode Fiber) (21746239) | Ethernet | ATT (VZBCHGU217462391) ATT (2174623911770501) | 03/09/2016 (VZBCHGU217462391) 11/05/2015 (2174623911770501) | 03/24/2016 (VZBCHGU217462391) 12/02/2015 (2174623911770501) | 12/03/2015 (2174623911770501) | 12/11/2015 (VFORCE) (21746239) | 12/11/2015 (VFORCE) (21746239) | DEMARCADDR - 10895 GRANDVIEW ST OVERLAND PARK DEMARCDET - 2ND FLOOR SUITE 200 SERVER ROOM WEST WALL PANEL 1, POS 7&8 |  | Teara Foster 1-913-253-0771 teara_foster@uhg.com | Terry Bjorke | terry_bjorke@optum.com | 1-763-694-7409 | 12/11/2015(Private IP - PIP) 12/11/2015(Access) |  |  | 12/23/2015 (21746238) 12/21/2015 (21746239) | 12/18/2015 | 12/11/2015 |  |  | N (21746238) N (21746239) | U0101953 |  |  | NSPE0009768432
Completed | AZ012-05-IJ Phoenix 100mg | 2222 W DUNLAP AVE PHOENIX, AZ 85021-2818 US | 50 MBPS (21813102) | 01/27/2016: 1/27- Beas install completed 1/19. Circuit Ready for activation, customer notified. | 192201431 | AZ012-05-IJ Phoenix 100mg | Private IP - PIP (21813101) Access (21813102) | 21813101 21813102 | 50 MBPS (21813101) |  | 84739624 (Private IP (PIP)) 84739622 (Access) | C4002626/ADD (21813101) E4007939/ADD (21813102) | 23.KFGX.990368..COXC. (2181310271892401) | 5681451 | 9000 | PVC ID : 5681451 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64711 PE IP Address : 68.136.52.165 CE Address : 68.136.52.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21813102) | 1000Base-SX (850nm, Multi Mode Fiber) (21813102) | Ethernet | COX (2181310271892401) | 11/25/2015 (2181310271892401) | 01/05/2016 (2181310271892401) |  | 01/19/2016 (VFORCE) (21813102) | 01/19/2016 (VFORCE) (21813102) | DEMARCDET - 1st floor phone closet north end by next to the cafe. relay rack patch panel port #16 |  | Jina Kim 1-602-293-4474 jina_kim@uhg.com | Matt Primozich | matt_primozich@optum.com | 1-763-553-4750 | 01/19/2016(Private IP - PIP) 01/19/2016(Access) | 02/10/2016 |  | 01/26/2016 (21813101) 01/22/2016 (21813102) | 01/22/2016 | 01/19/2016 |  |  | N (21813101) N (21813102) | U0101953 |  |  | NSPE0009830604
Completed | UNITED HEALTH GROUP | 7067 N MARIPOSA ST FRESNO, CA 93720-2988 US |  | 12/08/2015: 11/12- order submitted to disconnect team 11/18- pending disconnect completion due date 12/30 12/1- pending disconnect completion due date 12/30 | 192129842 | UNITED HEALTH GROUP | Private IP - PIP (21778269) WAN Analysis Reporting (21778271) Access (21778270) | 21778269 21778271 21778270 |  |  | 9628295 (Private IP (PIP)) 9636662 (WAN Analysis Reporting) 9634061 (Access) | C0057672/REMOVE (21778269) D1047324/REMOVE (21778270) |  | 5359056 |  | PVC ID : 5359056 |  |  | TDM | [8 empty] | JOHN SERGOT 1-763-744-1582 john_sergot@optum.com | JOHN SERGOT | john_sergot@optum.com | 1-763-744-1582 | 12/08/2015(Private IP - PIP) 12/08/2015(WAN Analysis Reporting) 12/08/2015(Access) |  |  | 12/30/2015 (21778269) 12/30/2015 (21778270) | 12/01/2015 | 01/25/2016 |  | Activated/Installed | N (21778269) N (21778271) N (21778270) | U0101953 |  |  | NSPE0009815754
Completed | CA048-05-IJ Sacramento CA | 9300 TECH CENTER DR STE 200 SACRAMENTO, CA 95826-2589 US | 100 MBPS (21800749) | 02/04/2016: 2/4- BEAS install is scheduled today 1:00pm with tech jon cannon. | 192168686 | CA048-05-IJ Sacramento, CA | Private IP - PIP (21800748) Access (21800749) | 21800748 21800749 | 100 MBPS (21800748) |  | 85130738 (Private IP (PIP)) 85130716 (Access) | C1029445/ADD (21800748) E4007865/ADD (21800749) | 18/KQGN/520025//PT (VZBCHGU218007491) 18/KQGN/520025//PT (2180074912035301) | 5680027 | 10000 | PVC ID : 5680027 VPN Name : UnitedHealthGroup Router Name : SCM9E01 VRF Name : V535343:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65254 PE IP Address : 152.176.235.249 CE Address : 152.176.235.250 QoS - Egress Profile: R12 | 100Base-TX (21800749) | 100Base-FX (1310nm, Multi Mode Fiber) (21800749) | Ethernet | ATT (VZBCHGU218007491) ATT (2180074912035301) | 03/08/2016 (VZBCHGU218007491) 11/20/2015 (2180074912035301) | 03/29/2016 (VZBCHGU218007491) 12/22/2015 (2180074912035301) | 01/26/2016 (2180074912035301) | 02/04/2016 (VFORCE) (21800749) | 02/04/2016 (VFORCE) (21800749) | DEMARCDET - 1.1 mpoe hand off panel 1 jack 3. Tagged and labeled |  | jill feagans 1-916-288-2567 jill_feagans@optum.com | Matt Primozich | matt_primozich@optum.com | 1-763-553-4750 | 02/04/2016(Private IP - PIP) 02/04/2016(Access) | 02/18/2016 |  | 02/16/2016 (21800748) 02/12/2016 (21800749) | 02/12/2016 | 02/04/2016 |  |  | N (21800748) N (21800749) | U0101953 |  |  | NSPE0009812850
Completed | Qwest Denver Cyber Center CO751-05-IJ | 8534 CONCORD CENTER DR ENGLEWOOD, CO 80112-7005 US | 1 GBPS (21813041) | 01/07/2016: 1/7- Ready for activation, customer notified. | 192201609 | Qwest Denver Cyber Center CO751-05-IJ | Private IP - PIP (21813040) Access (21813041) | 21813040 21813041 | 1 GBPS (21813040) |  | 85669493 (Private IP (PIP)) 85669491 (Access) | C0070131/ADD (21813040) E5002463/ADD (21813041) | 29/KXGS/133664//MS (2181304179527401) | 5681444 | 20000 | PVC ID : 5681444 VPN Name : UnitedHealthGroup Router Name : DNJ9E01 VRF Name : V563406:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64710 PE IP Address : 152.183.240.125 CE Address : 152.183.240.126 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (21813041) | 1000Base-LX (1310nm Single Mode Fiber) (21813041) | Ethernet | CENTURYLINK (2181304179527401) | 11/24/2015 (2181304179527401) | 12/10/2015 (2181304179527401) | 12/21/2015 (2181304179527401) | 12/24/2015 (VFORCE) (21813041) | 12/24/2015 (VFORCE) (21813041) | DEMARCDET - DATA CENTER MEET ME CAGE AREA CTL RACK OPTICAL PORT 3 |  | FRAN LOWERY 1-720-267-3499 fran.lowery@centurylink.com | STEVE BROWN | skbrown1@optum.com | 1-763-694-7333 | 12/28/2015(Private IP - PIP) 12/28/2015(Access) | 02/15/2016 |  | 01/12/2016 (21813040) 01/08/2016 (21813041) | 01/08/2016 | 12/28/2015 |  |  | N (21813040) N (21813041) | U0101953 |  |  | NSPE0009831667
Completed | IA005-02-IJ Davenport IA | 250 E 90TH ST DAVENPORT, IA 52806-7340 US | 500 MBPS (21834169) | 02/16/2017: 02/15 Successfully activated | 192238304 | IA005-02-IJ Davenport, IA | Private IP - PIP (21834168) Access (21834169) | 21834168 21834169 | 500 MBPS (21834168) |  | 88604594 (Private IP (PIP)) 88604592 (Access) | C5001490/ADD (21834168) E5002497/ADD (21834169) | WS/KRGS/673181/ /WXN / (2183416912315401) | 5685166 | 10000 | PVC ID : 5685166 VPN Name : UnitedHealthGroup Router Name : RVDL9E01 VRF Name : V550197:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64709 PE IP Address : 68.138.154.237 CE Address : 68.138.154.238 QoS - Egress Profile: R12 | 1000Base-T (21834169) | 1000Base-SX (850nm, Multi Mode Fiber) (21834169) | Ethernet | WINDSTREAM (2183416912315401) | 08/25/2016 (2183416912315401) | 11/22/2016 (2183416912315401) | 11/08/2016 (2183416912315401) | 12/14/2016 (VFORCE) (21834169) | 01/26/2017 (VFORCE) (21834169) | 1st FL telco closet, tagged with the circuit id |  | STEVE TOBIN 1-563-529-9127 stobin@estesconstruction.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 01/26/2017(Private IP - PIP) 01/26/2017(Access) | 02/15/2017 |  | 02/09/2017 (21834168) 02/07/2017 (21834169) | 02/07/2017 | 01/26/2017 |  |  | N (21834168) N (21834169) | U0101953 |  |  | NSPE0009860701
Completed | UTX34-08-IJ San Antonio | 6200 NORTHWEST PKWY SAN ANTONIO, TX 78249-3348 US | 400 MBPS (21914656) | 02/24/2016: 2/24- Circuit delivered. Waiting for customer to confirm if circuit has to be extended prior to scheduling beas install. | 192287124 | UTX34-08-IJ San Antonio | Private IP - PIP (21914655) Access (21914656) | 21914655 21914656 | 400 MBPS (21914655) |  | 88553909 (Private IP (PIP)) 88553907 (Access) | C5001557/ADD (21914655) E5002626/ADD (21914656) | 21.L1XX.006259..TWCC (2191465683086701) | 5695526 | 25000 | PVC ID : 5695526 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64608 PE IP Address : 68.136.178.165 CE Address : 68.136.178.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21914656) | 1000Base-SX (850nm, Multi Mode Fiber) (21914656) | Ethernet | TIME WARNER CABLE (2191465683086701) | 12/24/2015 (2191465683086701) | 03/28/2016 (2191465683086701) | 02/24/2016 (2191465683086701) | 03/01/2016 (VFORCE) (21914656) | 03/01/2016 (VFORCE) (21914656) | DEMARCDET - FL 1ST RM TELCO |  | Brad Niemeyer 1-210-393-7714 brad_niemeyer@uhg.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 03/01/2016(Private IP - PIP) 03/01/2016(Access) | 04/08/2016 |  | 04/06/2016 (21914655) 04/04/2016 (21914656) | 02/04/2016 | 03/01/2016 |  |  | N (21914655) N (21914656) | U0101953 |  |  | NSPE0009868595
Completed | PA062-05-IJ Horsham PA | 680 BLAIR MILL RD HORSHAM, PA 19044-2223 US | 200 MBPS (21913054) | 02/04/2016: 2/4- LEC still working on completing build. No ECD due to heavy workload and backlogs. | 192299782 | PA062-05-IJ Horsham PA | Private IP - PIP (21913053) Access (21913054) | 21913053 21913054 | 200 MBPS (21913053) |  | 88611451 (Private IP (PIP)) 88611449 (Access) | C5001554/ADD (21913053) E5002622/ADD (21913054) | 11.KFGS.304681..PA (2191305412316801) | 5695288 | 110000 | PVC ID : 5695288 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65203 PE IP Address : 199.220.102.17 CE Address : 199.220.102.18 QoS - Egress Profile: R1 | 1000Base-SX-850nm (21913054) | 1000Base-SX (850nm, Multi Mode Fiber) (21913054) | Ethernet | VERIZON (2191305412316801) | 12/22/2015 (2191305412316801) | 01/26/2016 (2191305412316801) | 02/09/2016 (2191305412316801) |  |  | DEMARCADDR - 680 BLAIR MILL RD, HORSHAM, PA DEMARCDET - 1ST FLR, CSR MDF RM, CSR EQPT RACK, POS 24 ... TAGGED |  | Harry Miller 1-215-902-8251 harry_s_miller@uhc.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 02/09/2016(Private IP - PIP) 02/09/2016(Access) | 02/24/2017 |  | 02/04/2016 (21913053) 02/02/2016 (21913054) | 02/12/2016 | 02/09/2016 |  |  | N (21913053) N (21913054) | U0101953 |  |  | NSPE0009890191
Completed | TN019-02-IJ Franklin TN | 1897 GENERAL GEORGE PATTON DR STE 112 FRANKLIN, TN 37067-6319 US | 100 MBPS (21942780) | 02/04/2016: 2/4- BEAS install is scheduled today 9:00 am with tech STEVEN ASHWORTH | 192335445 | TN019-02-IJ Franklin, TN | Private IP - PIP (21942779) Access (21942780) | 21942779 21942780 | 100 MBPS (21942779) |  | 89524521 (Private IP (PIP)) 89524439 (Access) | C1030690/ADD (21942779) E4008470/ADD (21942780) | T4/KQGN/825304//SC (2194278012468001) | 5698640 | 1500 | PVC ID : 5698640 VPN Name : UnitedHealthGroup Router Name : NSVL3E03 VRF Name : V414602-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64739 PE IP Address : 152.161.244.65 CE Address : 152.161.244.66 QoS - Egress Profile: R12 | 100Base-TX (21942780) | 100Base-FX (1310nm, Multi Mode Fiber) (21942780) | Ethernet | ATT (2194278012468001) | 01/04/2016 (2194278012468001) | 02/02/2016 (2194278012468001) | 02/02/2016 (2194278012468001) | 02/04/2016 (VFORCE) (21942780) | 02/04/2016 (VFORCE) (21942780) | DEMARCDET - port 1 telco closet rack mounted tagged with the circuit id |  | Randy Pennington 1-615-791-5256 randy.pennington@catamaranrx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 02/04/2016(Private IP - PIP) 02/04/2016(Access) | 08/02/2016 |  | 02/11/2016 (21942779) 02/09/2016 (21942780) | 02/16/2016 | 02/04/2016 |  |  | N (21942779) N (21942780) | U0101953 |  |  | NSPE0009894157
Completed | IN023-02-IJ Indianapolis IN | 150 W MARKET ST STE 300 INDIANAPOLIS, IN 46204-2809 US | 100 MBPS (21900699) | 02/11/2016: 2/11- Order on hold, waiting for customer to extend demarc. | 192335520 | IN023-02-IJ Indianapolis, IN | Private IP - PIP (21900698) Access (21900699) | 21900698 21900699 | 100 MBPS (21900698) |  | 89524524 (Private IP (PIP)) 89524522 (Access) | C1030375/ADD (21900698) E4008265/ADD (21900699) | /KQGN/106142//NB (2190069912468001) | 5693382 | 4000 | PVC ID : 5693382 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64784 PE IP Address : 152.176.252.209 CE Address : 152.176.252.210 QoS - Egress Profile: R12 | 100Base-TX (21900699) | 100Base-FX (1310nm, Multi Mode Fiber) (21900699) | Ethernet | ATT (2190069912468001) | 12/18/2015 (2190069912468001) | 01/20/2016 (2190069912468001) | 01/20/2016 (2190069912468001) | 02/17/2016 (VFORCE) (21900699) | 02/17/2016 (VFORCE) (21900699) | DEMARCADDR - 250 SPECCODE: OEMAM1 DEMARCDET - 3RD FLOOR DEMARK, PORT 2. |  | Derrik McGee 1-317-532-9214 derrik.mcgee@optum.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 02/17/2016(Private IP - PIP) 02/17/2016(Access) | 08/09/2016 |  | 03/01/2016 (21900698) 02/26/2016 (21900699) | 02/26/2016 | 02/17/2016 |  |  | N (21900698) N (21900699) | U0101953 |  |  | NSPE0009894157
Completed | IN022-02-IJ Catamaran Jeffersonville | 1050 PATROL RD JEFFERSONVILLE, IN 47130-7750 US | 250 MBPS (21900413) | 02/17/2016: 2/18- Pending scheduling of beas install. | 192366099 | IN022-02-IJ Catamaran Jeffersonville | Private IP - PIP (21900412) Access (21900413) | 21900412 21900413 | 200 MBPS (21900412) |  | 90041076 (Private IP (PIP)) 90041074 (Access) | C0072260/ADD (21900412) E0000396/ADD (21900413) | /KRGN/103412//NB (2190041312560402) | 5693320 | 10000 | PVC ID : 5693320 VPN Name : UnitedHealthGroup Router Name : LOU9E01 VRF Name : V511133:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 68.137.53.249 CE Address : 68.137.53.250 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (21900413) | 1000Base-LX (1310nm Single Mode Fiber) (21900413) | Ethernet | ATT (2190041312560402) | 12/18/2015 (2190041312560402) | 01/19/2016 (2190041312560402) | 02/18/2016 (2190041312560402) | 02/22/2016 (VFORCE) (21900413) | 02/22/2016 (VFORCE) (21900413) | DEMARCDET - IT RM RACK MNT PORTS 6 |  | John Holcomb 1-812-256-8643 John.holcomb@catamaranrx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 02/22/2016(Private IP - PIP) 02/22/2016(Access) | 07/06/2016 |  | 03/02/2016 (21900412) 02/29/2016 (21900413) | 02/29/2016 | 02/23/2016 |  |  | N (21900412) N (21900413) | U0101953 |  |  | NSPE0009910658
Completed | IL043-02-IJ Catamaran Schaumburg | 1600 MCCONNOR PKWY SCHAUMBURG, IL 60173-6801 US | 200 MBPS (21900301) | 02/11/2016: 2/11- Order on hold, waiting for customer to extend demarc. | 192366083 | IL043-02-IJ Catamaran Schaumburg | Private IP - PIP (21900300) Access (21900301) | 21900300 21900301 | 200 MBPS (21900300) |  | 90041080 (Private IP (PIP)) 90041078 (Access) | C5001545/ADD (21900300) E5002600/ADD (21900301) |  | 5693340 | 20000 | PVC ID : 5693340 VPN Name : UnitedHealthGroup Router Name : RVDL3E04 VRF Name : V556999-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64791 PE IP Address : 68.139.202.129 CE Address : 68.139.202.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21900301) | 1000Base-LX (1310nm Single Mode Fiber) (21900301) | Ethernet | COMCAST (2190030112560401) | 12/18/2015 (2190030112560401) | 01/27/2016 (2190030112560401) | 01/28/2016 (2190030112560401) | 02/17/2016 (VFORCE) (21900301) | 02/17/2016 (VFORCE) (21900301) | DEMARCDET - 2nd floor room 210 rack 2 RU28 DEVICE tagged with VZN |  | Tim Fernandez 1-224-231-1154 timothy.fernandez@optum.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 02/17/2016(Private IP - PIP) 02/17/2016(Access) | 09/15/2016 |  | 03/01/2016 (21900300) 02/26/2016 (21900301) | 02/26/2016 | 02/17/2016 |  |  | N (21900300) N (21900301) | U0101953 |  |  | NSPE0009910658
Completed | AZ023-02-IJ Catamaran PHOENIX | 4805 E THISTLE LANDING DR STE 100D PHOENIX, AZ 85044-6479 US | 200 MBPS (21930383) | 09/27/2016: 9/27 Activation completed 9/26 successfully | 192407272 | AZ023-02-IJ Catamaran PHOENIX | Private IP - PIP (21930382) Access (21930383) | 21930382 21930383 | 100 MBPS (21930382) |  | 90456230 (Private IP (PIP)) 90456228 (Access) | C5001566/ADD (21930382) E5002645/ADD (21930383) | 23.KFGX.990375..COXC. (2193038312617001) | 5697438 | 40000 | PVC ID : 5697438 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64803 PE IP Address : 152.183.164.5 CE Address : 152.183.164.6 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (21930383) | 1000Base-LX (1310nm Single Mode Fiber) (21930383) | Ethernet | COX (2193038312617001) | 12/30/2015 (2193038312617001) | 02/04/2016 (2193038312617001) |  | 02/15/2016 (VFORCE) (21930383) | 02/15/2016 (VFORCE) (21930383) | DEMARCDET - 1st floor inside the customer server room, 2nd rack in the cox equipment demarcation panel, port 15, equipment: Alcatel Lucent 7210, tagged with the ckt id |  | Michael Bernard 1-480-606-5229 Michael.bernard@catamaranrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 02/15/2016(Private IP - PIP) 02/15/2016(Access) | 09/26/2016 |  | 02/29/2016 (21930382) 02/25/2016 (21930383) | 02/25/2016 | 02/15/2016 |  |  | N (21930382) N (21930383) | U0101953 |  |  | NSPE0009918906
Completed | NV077-02-IJ Catamaran Las Vegas | 10050 BANBURRY CROSS DR STE 290 LAS VEGAS, NV 89144-7059 US | 200 MBPS (21913573) | 03/17/2016: 3/17- Circuit extended. Beas install scheduled for Friday, 3/18. | 192407271 | NV077-02-IJ Catamaran Las Vegas | Private IP - PIP (21913572) Access (21913573) | 21913572 21913573 | 100 MBPS (21913572) |  | 90456233 (Private IP (PIP)) 90456231 (Access) | C5001556/ADD (21913572) E5002625/ADD (21913573) | 33.KFGX.001024..COXC. (2191357312643301) | 5695382 | 10000 | PVC ID : 5695382 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64767 PE IP Address : 152.161.232.209 CE Address : 152.161.232.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21913573) | 1000Base-LX (1310nm Single Mode Fiber) (21913573) | Ethernet | COX (2191357312643301) | 12/23/2015 (2191357312643301) | 01/29/2016 (2191357312643301) |  | 03/18/2016 (VFORCE) (21913573) | 03/18/2016 (VFORCE) (21913573) | DEMARCDET - 1st floor head end MDF room. Rack mounted ru 34 Aou 7705 port 4 |  | Chuck German 1-678-347-2354 cgerman@scripnet.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/21/2016(Private IP - PIP) 03/21/2016(Access) |  |  | 04/04/2016 (21913572) 03/31/2016 (21913573) | 03/31/2016 | 03/21/2016 |  |  | N (21913572) N (21913573) | U0101953 |  |  | NSPE0009918906
Completed | TX234-02-IJ Catamaran Lubbock | 6310 GENOA AVE STE B LUBBOCK, TX 79424-2708 US | 100 MBPS (21930187) | 04/07/2016: 4/7- Beas install complete. Pending end to end testing and closing of order. | 192407703 | TX234-02-IJ Catamaran Lubbock, | Private IP - PIP (21930186) Access (21930187) | 21930186 21930187 | 10 MBPS (21930186) |  | 90455254 (Private IP (PIP)) 90455252 (Access) | C1030574/ADD (21930186) E4008405/ADD (21930187) | 250-001-0383 (2193018712643401) | 5697414 | 1500 | PVC ID : 5697414 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64731 PE IP Address : 152.181.121.221 CE Address : 152.181.121.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21930187) | 1000Base-SX (850nm, Multi Mode Fiber) (21930187) | Ethernet | SUDDEN LINK (2193018712643401) | 12/31/2015 (2193018712643401) | 03/31/2016 (2193018712643401) | 03/31/2016 (2193018712643401) | 04/06/2016 (VFORCE) (21930187) | 04/06/2016 (VFORCE) (21930187) | DEMARCDET - Main BLDG Telco Room 1st FL |  | Cherie Payton 1-806-535-4044 Cherie.Payton@briovarx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 04/07/2016(Private IP - PIP) 04/07/2016(Access) | 07/27/2016 |  | 04/04/2016 (21930186) 03/31/2016 (21930187) | 05/04/2016 | 04/07/2016 |  |  | N (21930186) N (21930187) | U0101953 |  |  | NSPE0009918925
Completed | TX233-02-IJ Catamaran San Antonio | 4590 LOCKHILL SELMA RD SAN ANTONIO, TX 78249-2073 US | 100 MBPS (21929698) | 03/10/2016: 3/10- BEAS installation is scheduled tomorrow 3/11. | 192407739 | TX233-02-IJ Catamaran San Antonio | Private IP - PIP (21929697) Access (21929698) | 21929697 21929698 | 20 MBPS (21929697) |  | 90455257 (Private IP (PIP)) 90455255 (Access) | C1030569/ADD (21929697) E4008397/ADD (21929698) | 21.L1XX.006302..TWCC (2192969812643401) | 5697385 | 10000 | PVC ID : 5697385 VPN Name : UnitedHealthGroup Router Name : RCN3E02 VRF Name : V454456-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64732 PE IP Address : 152.183.168.169 CE Address : 152.183.168.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21929698) | 1000Base-SX (850nm, Multi Mode Fiber) (21929698) | Ethernet | TIME WARNER CABLE (2192969812643401) | 12/30/2015 (2192969812643401) | 03/30/2016 (2192969812643401) | 03/08/2016 (2192969812643401) | 03/11/2016 (VFORCE) (21929698) | 03/11/2016 (VFORCE) (21929698) | DEMARCDET - 1st flr server room rack mounted |  | Tim White Tim White 1-210-564-2225 Tim.white@catamaranrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/11/2016(Private IP - PIP) 03/11/2016(Access) |  |  | 04/08/2016 (21929697) 04/06/2016 (21929698) | 02/10/2016 | 03/11/2016 |  |  | N (21929697) N (21929698) | U0101953 |  |  | NSPE0009918925
Completed | UOR15-05-IJ New ethernet Lake Oswego OR | 5 CENTERPOINTE DR STE 600 LAKE OSWEGO, OR 97035-8662 US | 100 MBPS (21970134) | 03/03/2016: 3/3- Beas install scheduled for 3/7. | 192433521 | UOR15-05-IJ, New ethernet Lake Oswego OR | Private IP - PIP (21970133) Access (21970134) | 21970133 21970134 | 100 MBPS (21970133) |  | 90815628 (Private IP (PIP)) 90815626 (Access) | C1030937/ADD (21970133) E4008602/ADD (21970134) | EL/KEED/838295/ /ELG (2197013412706801) | 5701821 | 5000 | PVC ID : 5701821 VPN Name : UnitedHealthGroup Router Name : HIC9E03 VRF Name : V575829:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64612 PE IP Address : 152.185.187.21 CE Address : 152.185.187.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21970134) | 1000Base-SX (850nm, Multi Mode Fiber) (21970134) | Ethernet | INTEGRA (2197013412706801) | 01/12/2016 (2197013412706801) | 02/16/2016 (2197013412706801) | 02/26/2016 (2197013412706801) | 03/07/2016 (VFORCE) (21970134) | 03/07/2016 (VFORCE) (21970134) | DEMARCDET - Accedian NID, SFP Port A, Multi-mode Fiber handoff, 1st floor Electrical/Telco room, wall mounted, labelled with circuit ID and customer name |  | Rhonda Fraley 1-503-603-7355 rhonda.fraley@uhc.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 03/07/2016(Private IP - PIP) 03/07/2016(Access) | 03/15/2016 |  | 03/16/2016 (21970133) 03/14/2016 (21970134) | 03/14/2016 | 03/07/2016 |  |  | N (21970133) N (21970134) | U0101953 |  |  | NSPE0009931310
Completed | MA008-02-IJ Boston MA | 1325 BOYLSTON ST BOSTON, MA 02215-3909 US | 100 MBPS (21977697) | 05/12/2016: 5/12- Pending new FOC date. | 192433720 | MA008-02-IJ Boston MA | Private IP - PIP (21977696) Access (21977697) | 21977696 21977697 | 50 MBPS (21977696) |  | 91074935 (Private IP (PIP)) 91074933 (Access) | C1030989/ADD (21977696) E4008632/ADD (21977697) | 95.KFGS.005594..NE (2197769712749601) | 5702049 | 25000 | PVC ID : 5702049 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64705 PE IP Address : 68.139.45.41 CE Address : 68.139.45.42 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21977697) | 1000Base-SX (850nm, Multi Mode Fiber) (21977697) | Ethernet | VERIZON (2197769712749601) | 05/10/2016 (2197769712749601) | 05/17/2016 (2197769712749601) | 05/14/2016 (2197769712749601) |  |  | DEMARCADDR - 1325 BOYLSTON, BOS, MA DEMARCDET - 9TH FLOOR SERVER ROOM WALL MOUNTED AND TAGGED |  | Doug Downie 1-781-420-0830 douglas_downie@uhg.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 05/16/2016(Private IP - PIP) 05/16/2016(Access) | 11/22/2016 |  | 04/26/2016 (21977696) 04/22/2016 (21977697) | 05/20/2016 | 05/16/2016 |  |  | N (21977696) N (21977697) | U0101953 |  |  | NSPE0009942969
Completed | NY008-02-IJ New ethernet | 300 MERIDIAN CENTRE BLVD ROCHESTER, NY 14618-3981 US | 50 MBPS (21951404) | 02/24/2016: 2/24- Customer confirmed circuit extended. Beas install scheduled for 2/25. | 192444980 | NY008-02-IJ, New ethernet | Private IP - PIP (21951403) Access (21951404) | 21951403 21951404 | 10 MBPS (21951403) |  | 91076015 (Private IP (PIP)) 91076013 (Access) | C4002863/ADD (21951403) E4008517/ADD (21951404) | 2O/KFFN/002039/LVLC (2195140412750001) | 5699581 | 1500 | PVC ID : 5699581 VPN Name : UnitedHealthGroup Router Name : SRD3E02 VRF Name : V572396-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65194 PE IP Address : 152.176.182.9 CE Address : 152.176.182.10 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (21951404) | 1000Base-SX (850nm, Multi Mode Fiber) (21951404) | Ethernet | LEVEL 3 (2195140412750001) | 01/06/2016 (2195140412750001) | 02/03/2016 (2195140412750001) | 02/23/2016 (2195140412750001) | 02/25/2016 (VFORCE) (21951404) | 02/25/2016 (VFORCE) (21951404) | DEMARCDET - 3rd floor customer server room rack mounted adva and tagged on access port 5 |  | Elizabeth Sabik 1-585-463-3138 elizabeth_sabik@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 02/25/2016(Private IP - PIP) 02/25/2016(Access) | 03/12/2016 |  | 03/10/2016 (21951403) 03/08/2016 (21951404) | 03/08/2016 | 02/25/2016 |  |  | N (21951403) N (21951404) | U0101953 |  |  | NSPE0009944059
Completed | MD084-02-IJ Elkridge MD | 6675 BUSINESS PKWY STE F ELKRIDGE, MD 21075-6349 US | 50 MBPS (22170263) | 06/09/2016: 6/9- FOC date 6/20 | 192445063 | MD084-02-IJ Elkridge MD | Private IP - PIP (22170262) Access (22170263) | 22170262 22170263 | 10 MBPS (22170262) |  | 91075582 (Private IP (PIP)) 91075580 (Access) | C4003298/ADD (22170262) E4009440/ADD (22170263) | 38.KFGS.301775..CM (2217026312749802) 38.KFGS.301645..CM (2217026312749801) | 5715051 | 1500 | PVC ID : 5715051 VPN Name : UnitedHealthGroup Router Name : BA59E01 VRF Name : Vd65225:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64706 PE IP Address : 68.136.31.233 CE Address : 68.136.31.234 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22170263) | 1000Base-SX (850nm, Multi Mode Fiber) (22170263) | Ethernet | VERIZON (2217026312749802) VERIZON (2217026312749801) | 05/16/2016 (2217026312749802) 02/25/2016 (2217026312749801) | 06/20/2016 (2217026312749802) 03/17/2016 (2217026312749801) | 06/09/2016 (2217026312749802) |  |  | DEMARCADDR - 6675 BUSINESS PKWY, ELKRIDGE, MD DEMARCDET - STE F. 1ST FL MDF RM. RM 117. RACK MOUNT. TGD |  | William Snook 1-410-227-4752 william.snook@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 06/09/2016(Private IP - PIP) 06/09/2016(Access) | 08/10/2016 |  | 06/29/2016 (22170262) 06/27/2016 (22170263) | 06/15/2016 | 06/09/2016 |  |  | N (22170262) N (22170263) | U0101953 |  |  | NSPE0009945496
Completed | UNITED HEALTH GROUP | 5345 W 20TH AVE HIALEAH, FL 33012-2100 US |  | 01/28/2016: 1/28- Disconnect complete. | 192495065 | UNITED HEALTH GROUP | Private IP - PIP (21970832) WAN Analysis Reporting (21970834) Access (21970833) | 21970832 21970834 21970833 |  |  | 9628288 (Private IP (PIP)) 9636299 (WAN Analysis Reporting) 9634041 (Access) | C0057408/REMOVE (21970832) D1047108/REMOVE (21970833) |  | 5347428 |  | PVC ID : 5347428 |  |  | TDM | [8 empty] | JOHN SERGOT 1-763-744-1582 john_sergot@optum.com | JOHN SERGOT | john_sergot@optum.com | 1-763-744-1582 | 01/28/2016(Private IP - PIP) 01/28/2016(WAN Analysis Reporting) 01/28/2016(Access) |  |  | 02/23/2016 (21970832) 02/23/2016 (21970833) | 01/25/2016 | 01/29/2016 |  | Activated/Installed | N (21970832) N (21970834) N (21970833) | U0101953 |  |  | NSPE0009930073
Completed | MA006-02-IJ Avon MA | 145 BODWELL ST STE 2A AVON, MA 02322-1179 US | 100 MBPS (22024600) | 02/04/2016: 2/4- FOC date 2/9. | 192495906 | MA006-02-IJ Avon, MA | Private IP - PIP (22024599) Access (22024600) | 22024599 22024600 | 20 MBPS (22024599) |  | 91498584 (Private IP (PIP)) 91498582 (Access) | C1031334/ADD (22024599) E4008844/ADD (22024600) | 95.KFGS.005646..NE (2202460012827201) | 5704584 | 1500 | PVC ID : 5704584 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64778 PE IP Address : 152.177.246.29 CE Address : 152.177.246.30 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22024600) | 1000Base-SX (850nm, Multi Mode Fiber) (22024600) | Ethernet | VERIZON (2202460012827201) | 01/26/2016 (2202460012827201) | 02/09/2016 (2202460012827201) | 02/10/2016 (2202460012827201) |  |  | DEMARCDET - SERVER RM. WALL MNTD. EXTENDED FROM ELECTRIC RM FDP. TAGGED |  | Kerry Mello 1-508-513-6906 Kerry.Mello@catamaranRx.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 02/10/2016(Private IP - PIP) 02/10/2016(Access) |  |  | 02/18/2016 (22024599) 02/16/2016 (22024600) | 03/07/2016 | 02/10/2016 |  |  | N (22024599) N (22024600) | U0101953 |  |  | NSPE0009959458
Completed | IL046-02-IJ Catmaran Chicago IL | 300 N LA SALLE DR STE 1600 CHICAGO, IL 60654-3413 US | 100 MBPS (21994365) | 03/10/2016: 3/10- Order now progressing and new due date requested. Customer confirmed to move forward with installing SMF. | 192495891 | IL046-02-IJ Catmaran Chicago IL | Private IP - PIP (21994364) Access (21994365) | 21994364 21994365 | 50 MBPS (21994364) |  | 91498590 (Private IP (PIP)) 91498588 (Access) | C1031085/ADD (21994364) E4008702/ADD (21994365) |  | 5702783 | 40000 | PVC ID : 5702783 VPN Name : UnitedHealthGroup Router Name : RVDLGE01 VRF Name : V583540:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64786 PE IP Address : 68.137.221.181 CE Address : 68.137.221.182 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (21994365) | Ethernet |  |  |  |  | 02/03/2016 (VFORCE) (21994364) 02/03/2016 (CCP) (21994364) 02/03/2016 (CCP) (21994365) | 02/02/2016 (VFORCE) (21994364) 02/02/2016 (CCP) (21994364) 02/02/2016 (CCP) (21994365) |  |  | Mark Zichmiller 1-312-261-7816 Mark.zichmiller@optum.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 03/17/2016(Private IP - PIP) 03/17/2016(Access) | 08/19/2016 |  | 03/25/2016 (21994364) 03/23/2016 (21994365) | 04/12/2016 | 03/17/2016 |  |  | N (21994364) N (21994365) | U0101953 |  |  | NSPE0009959458
Completed | KS013-02-IJ Catamaran Lenexa | 11142 RENNER BLVD LENEXA, KS 66219-9621 US | 100 MBPS (21986910) | 03/03/2016: 3/3- Beas install scheduled for 3/7. | 192495905 | KS013-02-IJ Catamaran Lenexa | Private IP - PIP (21986909) Access (21986910) | 21986909 21986910 | 10 MBPS (21986909) |  | 91498587 (Private IP (PIP)) 91498585 (Access) | C1031040/ADD (21986909) E4008666/ADD (21986910) | 74/KQGN/906562//SW (2198691012827202) | 5702420 | 1500 | PVC ID : 5702420 VPN Name : UnitedHealthGroup Router Name : IDCXE03 VRF Name : V560358-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64780 PE IP Address : 152.177.210.41 CE Address : 152.177.210.42 QoS - Egress Profile: R12 | 100Base-TX (21986910) | 100Base-FX (1310nm, Multi Mode Fiber) (21986910) | Ethernet | ATT (2198691012827202) | 01/19/2016 (2198691012827202) | 02/04/2016 (2198691012827202) | 03/02/2016 (2198691012827202) | 03/07/2016 (VFORCE) (21986910) | 03/07/2016 (VFORCE) (21986910) | DEMARCDET - 1ST FLR TELCO CLOSET, ETHERNET DMARC - PANEL 1 PORT 1 |  | Sara Hanson 1-913-307-2640 sara.hanson@briovarx.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 03/07/2016(Private IP - PIP) 03/07/2016(Access) |  |  | 03/15/2016 (21986909) 03/11/2016 (21986910) | 03/11/2016 | 03/07/2016 |  |  | N (21986909) N (21986910) | U0101953 |  |  | NSPE0009959458
Completed | ME008-02-IJ Catamaran South Portland | 53 DARLING AVE SOUTH PORTLAND, ME 04106-2301 US | 100 MBPS (21986757) | 02/04/2016: 2/4- FOC date is 2/16. | 192495875 | ME008-02-IJ Catamaran South Portland | Private IP - PIP (21986756) Access (21986757) | 21986756 21986757 | 10 MBPS (21986756) |  | 91498596 (Private IP (PIP)) 91498594 (Access) | C1031039/ADD (21986756) E4008664/ADD (21986757) | VB02-14 (2198675712827401) | 5702418 | 4000 | PVC ID : 5702418 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64775 PE IP Address : 68.138.250.221 CE Address : 68.138.250.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21986757) | 1000Base-SX (850nm, Multi Mode Fiber) (21986757) | Ethernet | OXFORD (2198675712827401) | 01/14/2016 (2198675712827401) | 02/16/2016 (2198675712827401) |  | 02/11/2016 (VFORCE) (21986757) | 02/11/2016 (VFORCE) (21986757) |  |  | Josh Frautten 1-207-228-1218 Josh.frautten@catamaranrx.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 02/11/2016(Private IP - PIP) 02/11/2016(Access) | 07/08/2016 |  | 02/25/2016 (21986756) 02/23/2016 (21986757) | 02/26/2016 | 02/11/2016 |  |  | N (21986756) N (21986757) | U0101953 |  |  | NSPE0009959458
Completed | GA023-02-IJ Catamaran Cornelia GA | 166 COMMERCE PKWY CORNELIA, GA 30531-5357 US | 100 MBPS (22008333) | 07/28/2016: 7/28- Extension not required. Beas install scheduled for 7/29. | 192496044 | GA023-02-IJ Catamaran Cornelia GA | Private IP - PIP (22008332) Access (22008333) | 22008332 22008333 | 10 MBPS (22008332) |  | 91515042 (Private IP (PIP)) 91514820 (Access) | C1031195/ADD (22008332) E4008769/ADD (22008333) | GA/KRGS/983235/ /WINS/ (2200833312830601) | 5703543 | 1500 | PVC ID : 5703543 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64796 PE IP Address : 68.136.189.149 CE Address : 68.136.189.150 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22008333) | 1000Base-SX (850nm, Multi Mode Fiber) (22008333) | Ethernet | WINDSTREAM (2200833312830601) | 01/20/2016 (2200833312830601) | 06/06/2016 (2200833312830601) |  | 07/29/2016 (VFORCE) (22008333) | 07/29/2016 (VFORCE) (22008333) | DEMARCDET - 1st Floor, Server Room, Rack Mounted, Tagged, Not Extended |  | Kyle Wilbanks 1-877-855-7753 kyle.wilbanks@briovarx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/02/2016(Private IP - PIP) 08/02/2016(Access) | 08/08/2016 |  | 08/09/2016 (22008332) 08/05/2016 (22008333) | 08/05/2016 | 08/02/2016 |  |  | N (22008332) N (22008333) | U0101953 |  |  | NSPE0009962320
Completed | OR006-02-IJ | 3723 FAIRVIEW INDUSTRIAL DR SE STE 270 SALEM, OR 97302-4975 US | 100 MBPS (22008045) | 09/16/2016: 9/16 Activation sucessfully completed | 192496025 | OR006-02-IJ | Private IP - PIP (22008044) Access (22008045) | 22008044 22008045 | 50 MBPS (22008044) |  | 91514816 (Private IP (PIP)) 91514814 (Access) | C1031193/ADD (22008044) E4008767/ADD (22008045) | 05/KXGS/141675//PN (2200804512830501) | 5703524 | 35000 | PVC ID : 5703524 VPN Name : UnitedHealthGroup Router Name : HICGE02 VRF Name : V556790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64753 PE IP Address : 152.162.82.237 CE Address : 152.162.82.238 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22008045) | 1000Base-SX (850nm, Multi Mode Fiber) (22008045) | Ethernet | CENTURYLINK (2200804512830501) | 01/20/2016 (2200804512830501) | 02/09/2016 (2200804512830501) | 03/10/2016 (2200804512830501) | 03/23/2016 (VFORCE) (22008045) |  | DEMARCDET - MAIN FLOOR TELCO / SERVER ROOM CUSTOMER RR 101.02 SHELF #6 OOPTICAL PORT 3 |  | Terry Wilson 1-503-383-3616 Terry.Wilson@Optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/23/2016(Private IP - PIP) 03/23/2016(Access) | 09/16/2016 |  | 04/05/2016 (22008044) 04/01/2016 (22008045) | 04/01/2016 | 03/23/2016 |  |  | N (22008044) N (22008045) | U0101953 |  |  | NSPE0009962320
Completed | GA024-02-IJ | 3025 WINDWARD PLZ STE 200 ALPHARETTA, GA 30005-7451 US | 100 MBPS (21987211) | 02/24/2016: 2/24- Customer confirmed extension not needed. Beas install scheduled for Monday, 2/29. | 192496061 | GA024-02-IJ | Access (21987211) Private IP - PIP (21987210) | 21987211 21987210 | 20 MBPS (21987210) |  | 91515043 (Access) 91515045 (Private IP (PIP)) | E4008670/ADD (21987211) C1031045/ADD (21987210) | 38/KQGN/620568//SB (2198721112830601) | 5702442 | 1500 | PVC ID : 5702442 VPN Name : UnitedHealthGroup Router Name : CPZ3E02 VRF Name : V450868-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64795 PE IP Address : 152.185.169.153 CE Address : 152.185.169.154 QoS - Egress Profile: R12 | 100Base-TX (21987211) | 100Base-FX (1310nm, Multi Mode Fiber) (21987211) | Ethernet | ATT (2198721112830601) | 01/14/2016 (2198721112830601) | 02/15/2016 (2198721112830601) | 02/17/2016 (2198721112830601) | 02/29/2016 (VFORCE) (21987211) | 02/29/2016 (VFORCE) (21987211) | DEMARCADDR - 3025 WINDWARD PLZ ALPH GA DEMARCDET - SERVER RM 3930#1 ELECT HD OFF V/E PNL1 JK6 TAG |  | Mark Hall 1-770-776-2010 Mark.Hall@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 02/29/2016(Access) 02/29/2016(Private IP - PIP) |  |  | 03/11/2016 (21987211) 03/15/2016 (21987210) | 03/11/2016 | 02/29/2016 |  |  | N (21987211) N (21987210) | U0101953 |  |  | NSPE0009962320
Completed | FL139-02-IJ Catamaran | 8301 SOUTHPARK CIR STE 150 ORLANDO, FL 32819-9013 US | 100 MBPS (22004865) | 09/16/2016: 9/16 Activation sched 9/21 10am CST | 192496043 | FL139-02-IJ Catamaran | Private IP - PIP (22004864) Access (22004865) | 22004864 22004865 | 50 MBPS (22004864) |  | 91514819 (Private IP (PIP)) 91514817 (Access) | C1031173/ADD (22004864) E4008748/ADD (22004865) | 58/KQGN/703788//SB (2200486512830601) | 5703352 | 20000 | PVC ID : 5703352 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64798 PE IP Address : 68.137.171.13 CE Address : 68.137.171.14 QoS - Egress Profile: R12 | 100Base-TX (22004865) | 100Base-FX (1310nm, Multi Mode Fiber) (22004865) | Ethernet | ATT (2200486512830601) | 01/19/2016 (2200486512830601) | 02/03/2016 (2200486512830601) | 02/15/2016 (2200486512830601) | 02/18/2016 (VFORCE) (22004865) | 02/17/2016 (VFORCE) (22004865) | DEMARCDET - 1st floor suit 150 relay rack 1 panel 1 position 2 tagged with ID |  | Michael Curzman 1-407-591-3822 Mcurzman@catalystrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 02/19/2016(Private IP - PIP) 02/19/2016(Access) |  |  | 03/04/2016 (22004864) 03/02/2016 (22004865) | 03/02/2016 | 02/19/2016 |  |  | N (22004864) N (22004865) | U0101953 |  |  | NSPE0009962320
Completed | NV058-02-IJ Catamaran Las Vegas | 1650 SPRING GATE LN STE 100 LAS VEGAS, NV 89134-6200 US | 100 MBPS (22008192) | 02/24/2016: 2/24- Order on hold, waiting for customer to confirm if circuit will be extended prior to beas install. | 192496067 | NV058-02-IJ Catamaran Las Vegas | Private IP - PIP (22008191) Access (22008192) | 22008191 22008192 | 50 MBPS (22008191) |  | 91647242 (Private IP (PIP)) 91647040 (Access) | C1031194/ADD (22008191) E4008768/ADD (22008192) | 33.KFGX.001029..COXC. (2200819212847201) | 5703527 | 10000 | PVC ID : 5703527 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64770 PE IP Address : 152.162.64.157 CE Address : 152.162.64.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22008192) | 1000Base-SX (850nm, Multi Mode Fiber) (22008192) | Ethernet | COX (2200819212847201) | 01/22/2016 (2200819212847201) | 02/24/2016 (2200819212847201) |  | 02/29/2016 (VFORCE) (22008192) | 02/29/2016 (VFORCE) (22008192) | DEMARCDET - RM SERVER RACK 1 |  | KELLY BEST 1-702-304-2988 kelly.best@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 02/29/2016(Private IP - PIP) 02/29/2016(Access) | 08/26/2016 |  | 03/15/2016 (22008191) 03/11/2016 (22008192) | 03/11/2016 | 02/29/2016 |  |  | N (22008191) N (22008192) | U0101953 |  |  | NSPE0009967826
Completed | NV078-02-IJ Catamaran Las Vegas | 8350 BRIOVA DR LAS VEGAS, NV 89113-2257 US | 200 MBPS (21994788) | 02/17/2016: 2/17- FOC date 2/19. | 192496065 | NV078-02-IJ Catamaran Las Vegas | Private IP - PIP (21994787) Access (21994788) | 21994787 21994788 | 100 MBPS (21994787) |  | 91659013 (Private IP (PIP)) 91659011 (Access) | C5001597/ADD (21994787) E5002731/ADD (21994788) | 33.KFGX.001030..COXC. (2199478812847604) | 5702801 | 25000 | PVC ID : 5702801 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64766 PE IP Address : 152.187.23.25 CE Address : 152.187.23.26 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (21994788) | 1000Base-LX (1310nm Single Mode Fiber) (21994788) | Ethernet | COX (2199478812847604) | 01/22/2016 (2199478812847604) | 02/19/2016 (2199478812847604) |  | 02/23/2016 (VFORCE) (21994788) | 02/23/2016 (VFORCE) (21994788) | DEMARCDET - 1st floor, server room,on the carriers rack, on demarc panel port no 15 Single mode fibre |  | Kelly Best 1-702-304-2988 Kelly.Best@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 02/23/2016(Private IP - PIP) 02/23/2016(Access) | 07/22/2016 |  | 03/01/2016 (21994787) 02/26/2016 (21994788) | 02/29/2016 | 02/23/2016 |  |  | N (21994787) N (21994788) | U0101953 |  |  | NSPE0009967826
Completed | NV059-02-IJ Catamaran Las Vegas | 1945 LAS VEGAS BLVD S LAS VEGAS, NV 89104-1310 US | 100 MBPS (21994820) | 02/18/2016: 2/18- Circuit delivered. Waiting for customer to confirm if demarc will be extended. | 192496066 | NV059-02-IJ Catamaran Las Vegas | Private IP - PIP (21994819) Access (21994820) | 21994819 21994820 | 50 MBPS (21994819) |  | 91647245 (Private IP (PIP)) 91647243 (Access) | C1031088/ADD (21994819) E4008705/ADD (21994820) | 33.KFGX.001028..COXC. (2199482012847302) | 5702803 | 3000 | PVC ID : 5702803 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64768 PE IP Address : 152.177.173.181 CE Address : 152.177.173.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21994820) | 1000Base-SX (850nm, Multi Mode Fiber) (21994820) | Ethernet | COX (2199482012847302) | 01/22/2016 (2199482012847302) | 02/12/2016 (2199482012847302) |  | 02/24/2016 (VFORCE) (21994820) | 02/24/2016 (VFORCE) (21994820) | DEMARCDET - patch panel CUST.01.00141 on port 15, first floor server room wall mounted on south wall of the server room |  | Kelly Best 1-702-304-2988 Kelly.Best@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 02/24/2016(Private IP - PIP) 02/24/2016(Access) | 09/07/2016 |  | 02/23/2016 (21994819) 02/19/2016 (21994820) | 02/29/2016 | 02/24/2016 |  |  | N (21994819) N (21994820) | U0101953 |  |  | NSPE0009967826
Completed | IL044-02-IJ Catamaran Lisle IL | 2441 WARRENVILLE RD STE 610 LISLE, IL 60532-3642 US | 250 MBPS (22009344) | 10/05/2016: Ivue sched 10/4 at 11am CST- AL THoreson canceled 10/3 From: Thoreson, Alvin [mailto:al_thoreson@optum.com] Sent: Monday, October 03, 2016 3:16 PM To: Espino, Patrick Noel Subject: [E] RE: Install Scheduler Request - Circuit ID: C0073746,C0073746, Please cancel this TTU for now. There is a delay in the equipment arrival. Thanks, Al | 192509768 | IL044-02-IJ Catamaran Lisle, IL | Private IP - PIP (22009343) Access (22009344) | 22009343 22009344 | 100 MBPS (22009343) |  | 92076139 (Private IP (PIP)) 92076137 (Access) | C0073746/ADD (22009343) E0000403/ADD (22009344) | /KRGN/112465//LB (2200934412916701) | 5703602 | 25000 | PVC ID : 5703602 VPN Name : UnitedHealthGroup Router Name : DNG3E03 VRF Name : V437829-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64790 PE IP Address : 152.161.177.213 CE Address : 152.161.177.214 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22009344) | 1000Base-LX (1310nm Single Mode Fiber) (22009344) | Ethernet | ATT (2200934412916701) | 01/21/2016 (2200934412916701) | 02/29/2016 (2200934412916701) | 02/26/2016 (2200934412916701) | 03/03/2016 (VFORCE) (22009344) | 03/03/2016 (VFORCE) (22009344) | DEMARCADDR - 2441 WARRENVILLE RD LISLE IL DEMARCDET - BEM TAGGED AT HANDOFF PORTS 5 AND 6 SHELF 1 OF DEMARC BAY 4 |  | Paul Gausemel 1-630-664-9139 Paul.Gausemel@optum.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 03/03/2016(Private IP - PIP) 03/03/2016(Access) | 10/11/2016 |  | 03/09/2016 (22009343) 03/07/2016 (22009344) | 03/02/2016 | 03/03/2016 |  |  | N (22009343) N (22009344) | U0101953 |  |  | NSPE0009976492
Completed | GA721-02-IJ Catamaran Suwanee GA | 300 SATELLITE BLVD NW SUWANEE, GA 30024-7123 US | 1 GBPS (22005366) | 02/11/2016: 2/11- Pending end to end testing. Reporting a loss of signal, port is not syncing to hardloop left at extended demarc. | 192509769 | GA721-02-IJ Catamaran Suwanee, GA | Private IP - PIP (22005365) Access (22005366) | 22005365 22005366 | 500 MBPS (22005365) |  | 92076185 (Private IP (PIP)) 92076183 (Access) | C0074272/ADD (22005365) E5002752/ADD (22005366) |  | 5703404 | 50000 | PVC ID : 5703404 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65099 PE IP Address : 199.220.169.41 CE Address : 199.220.169.42 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (22005366) | Ethernet | [8 empty] | Brandon Cannon 1-678-347-2352 Brandon.cannon@cypresscare.com | Jonathan Edwards | jonathan.edwards@optum.com | 1-781-419-8604 | 02/16/2016(Private IP - PIP) 02/16/2016(Access) | 07/07/2016 |  | 02/16/2016 (22005365) 02/12/2016 (22005366) | 02/16/2016 | 02/16/2016 |  |  | N (22005365) N (22005366) | U0101953 |  |  | NSPE0009976492
Completed | OH013-02-IJ Avon Lake OH | 33381 WALKER RD AVON LAKE, OH 44012-1463 US | 45 MBPS (22004759) | 02/04/2016: 2/4- Loop has already been delivered, however order is not yet ready for testing as this was still on provisioning for design review. | 192509770 | OH013-02-IJ Avon Lake OH | Private IP - PIP (22004758) Access (22004759) | 22004758 22004759 | 45 MBPS (22004758) |  | 92076188 (Private IP (PIP)) 92076186 (Access) | C4002974/ADD (22004758) D3000869/ADD (22004759) | 50/HFGS/252855//CNTY (2200475912770102) | 5703346 | 5500 | PVC ID : 5703346 VPN Name : UnitedHealthGroup Router Name : NORXE05 VRF Name : V575848-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 64761 PE IP Address : 152.164.123.225 CE Address : 152.164.123.226 QoS - Egress Profile: R12 |  | DS3 (22004759) | TDM | ATT (2200475912770102) | 01/22/2016 (2200475912770102) | 02/01/2016 (2200475912770102) | 02/09/2016 (2200475912770102) |  |  |  |  | JEFF MCCARTHY 1-440-930-9522 jeff.mccarthy@optum.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 02/09/2016(Private IP - PIP) 02/09/2016(Access) |  |  | 02/15/2016 (22004758) 02/11/2016 (22004759) | 02/10/2016 | 02/09/2016 |  |  | N (22004758) N (22004759) | U0101953 |  |  | NSPE0009976492
Completed | AL013-02-IJ Catamaran Montgomery | 4525 EXECUTIVE PARK DR MONTGOMERY, AL 36116-1624 US | 100 MBPS (21997076) | 11/23/2016: 11/12 Activation comopleted customer accepted | 192496023 | AL013-02-IJ Catamaran Montgomery | Private IP - PIP (21997075) Access (21997076) | 21997075 21997076 | 50 MBPS (21997075) |  | 91514813 (Private IP (PIP)) 91514811 (Access) | C1031099/ADD (21997075) E4008713/ADD (21997076) | PENDING (2199707612830501) | 5702926 | 70000 | PVC ID : 5702926 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64806 PE IP Address : 68.136.248.221 CE Address : 68.136.248.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21997076) | 1000Base-SX (850nm, Multi Mode Fiber) (21997076) | Ethernet | CHARTER (2199707612830501) | 01/18/2016 (2199707612830501) | 06/10/2016 (2199707612830501) | 06/02/2016 (2199707612830501) | 06/09/2016 (VFORCE) (21997076) |  | DEMARCADDR - 56 MARIETTA STREET, ATLANTA GA DEMARCDET - MAIN GROUND SWITCH ROO |  | Russell Mackin 1-334-956-7537 Russell.mackin@catamaranrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 06/09/2016(Private IP - PIP) 06/09/2016(Access) | 11/23/2016 |  | 06/21/2016 (21997075) 06/17/2016 (21997076) | 07/13/2016 | 06/09/2016 |  |  | N (21997075) N (21997076) | U0101953 |  |  | NSPE0009962320
Completed | GA039-02-IJ | 2736 MEADOW CHURCH RD STE 300 DULUTH, GA 30097-5236 US | 200 MBPS (22008262) | 03/10/2017: 03/09 Successfully activated | 192496024 | GA039-02-IJ | Private IP - PIP (22008261) Access (22008262) | 22008261 22008262 | 100 MBPS (22008261) |  | 91515048 (Private IP (PIP)) 91515046 (Access) | C5001606/ADD (22008261) E5002755/ADD (22008262) | 4Y/KFFN/002803/LVLC (2200826212830601) | 5703533 | 25000 | PVC ID : 5703533 VPN Name : UnitedHealthGroup Router Name : CHRL3E03 VRF Name : V516000-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64792 PE IP Address : 152.177.51.57 CE Address : 152.177.51.58 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22008262) | 1000Base-LX (1310nm Single Mode Fiber) (22008262) | Ethernet | LEVEL 3 (2200826212830601) | 02/24/2016 (2200826212830601) | 03/04/2016 (2200826212830601) | 03/11/2016 (2200826212830601) | 03/16/2016 (VFORCE) (22008262) | 03/16/2016 (VFORCE) (22008262) | DEMARCDET - 3rd fl, suite 300, customer server room, rear wallmount ADVA DLTH130AED002 access port 5, SM LC connectors, tagged w/circuit ID |  | Brandon Cannon 1-678-347-2352 Brandon.Cannon@cypresscare.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/16/2016(Private IP - PIP) 03/16/2016(Access) | 03/09/2017 |  | 04/06/2016 (22008261) 04/04/2016 (22008262) | 04/04/2016 | 03/16/2016 |  |  | N (22008261) N (22008262) | U0101953 |  |  | NSPE0009962320
Completed | Catamaran OH023-02-IJ Lewis Center OH | 7840 GRAPHICS WAY LEWIS CENTER, OH 43035-8002 US | 100 MBPS (22005342) | 03/24/2016: 3/24- Order on hold, waiting for to complete demarc extension. | 192535179 | Catamaran OH023-02-IJ Lewis Center OH | Private IP - PIP (22005341) Access (22005342) | 22005341 22005342 | 50 MBPS (22005341) |  | 92493945 (Private IP (PIP)) 92493943 (Access) | C1031180/ADD (22005341) E4008757/ADD (22005342) | 5B/KFFN/002459/LVLC (2200534212988401) | 5703400 | 4000 | PVC ID : 5703400 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64758 PE IP Address : 152.161.181.249 CE Address : 152.161.181.250 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22005342) | 1000Base-SX (850nm, Multi Mode Fiber) (22005342) | Ethernet | LEVEL 3 (2200534212988401) | 01/20/2016 (2200534212988401) | 03/18/2016 (2200534212988401) | 03/22/2016 (2200534212988401) | 03/25/2016 (VFORCE) (22005342) | 03/25/2016 (VFORCE) (22005342) | DEMARCDET - 1st flr, customer main data room, wallmount |  | Jack Wolf 1-614-499-0878 jwolf@modernmedical.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 03/29/2016(Private IP - PIP) 03/29/2016(Access) |  |  | 03/29/2016 (22005341) 03/25/2016 (22005342) | 03/01/2016 | 03/29/2016 |  |  | N (22005341) N (22005342) | U0101953 |  |  | NSPE0009991437
Completed | FL070-05-IJ Jacksonville | 7159 CORKLAN DR JACKSONVILLE, FL 32258-4455 US | 250 MBPS (22005166) | 03/31/2016: 3/31- BEAS install is scheduled today 3/31 with field tech RONALD RODGERS. | 192535262 | FL070-05-IJ Jacksonville | Private IP - PIP (22005165) Access (22005166) | 22005165 22005166 | 100 MBPS (22005165) |  | 92297424 (Private IP (PIP)) 92297422 (Access) | C0073686/ADD (22005165) E0000402/ADD (22005166) | 52/KRGN/701882//SB (2200516611103301) | 5703375 | 110000 | PVC ID : 5703375 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65031 PE IP Address : 152.185.180.117 CE Address : 152.185.180.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22005166) | 1000Base-SX (850nm, Multi Mode Fiber) (22005166) | Ethernet | ATT (2200516611103301) | 01/20/2016 (2200516611103301) | 02/22/2016 (2200516611103301) | 02/23/2016 (2200516611103301) | 03/31/2016 (VFORCE) (22005166) | 04/04/2016 (VFORCE) (22005166) | DEMARCADDR - 7159 CORKLAN DR JKVL FL DEMARCDET - 1ST FL EQ RM WL MNT FIBER 6 PK PT 1/2 TAGGED |  | Rick Gross 1-904-226-7465 rick.gross@optum.com | PRADEEP YADA | pradeep_yadav@optum.com | 91-981-005-9326 | 04/04/2016(Private IP - PIP) 04/04/2016(Access) | 04/11/2016 |  | 04/13/2016 (22005165) 04/11/2016 (22005166) | 04/11/2016 | 04/04/2016 |  |  | N (22005165) N (22005166) | U0101953 |  |  | NSPE0009991401
|  | 415 W 49TH ST HIALEAH, FL 33012 USA | 1.536 MBPS (IQBK89C0) | 02/04/2016: 2/4- Per ATT, per the tech notes he tried to contact the engineering, Sandra Taylor and they are working on it right now. CNR is they lost on access last 02/02 and 02/03. Sent email to 2nd level for updates and completion today. Once issue is resolved, we will proceed on loop testing. | 8619125 |  | Private IP (IQBK89C0) EVC/PVC Service (N.10946163.5703418) | IQBK89C0 N.10946163.5703418 | 10.752 MBPS | P2131675 |  | BCBK9FS70001 (IQBK89C0) BCBK9FS70002 (IQBK89C0) BCBK9FS70003 (IQBK89C0) BCBK9FS70004 (IQBK89C0) BCBK9FS70005 (IQBK89C0) BCBK9FS70006 (IQBK89C0) BCBK9FS70007 (IQBK89C0) | 60/HCGS/471016//SB (IQBK89C0QRUVMB01) | 5703418 | 4000 | VPN Name : UnitedHealthGroup Router Name : POB3E02 VRF Name : V368211-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65274 PE IP Address : 152.181.255.165 CE Address : 152.181.255.166 QoS - Egress Profile: R12 PVC ID : 5703418 |  |  |  | ATT (IQBK89C0QRUVMB01) | 01/20/2016 (IQBK89C0QRUVMB01) | 02/03/2016 (IQBK89C0QRUVMB01) | 02/09/2016 (IQBK89C0QRUVMB01) |  |  |  |  | MARITZA PUERTO 0013053643404 MPUERTO@PCPMEDICALGROUP.COM |  |  |  | 02/10/2016 (IQBK89C0) |  |  | 02/10/2016 (IQBK89C0) | 02/12/2016 (IQBK89C0) |  |  |  | N (IQBK89C0) N (N.10946163.5703418) | 05017789 87521937 |  |  | NSPE0009984683
Completed | PA104-02-IJ Catamaran Norristown | 2500 MONROE BLVD STE 100 NORRISTOWN, PA 19403-2421 US | 200 MBPS (22024635) | 02/04/2016: 2/4- FOC date is 2/5. | 192559060 | PA104-02-IJ Catamaran Norristown | Private IP - PIP (22024634) Access (22024635) | 22024634 22024635 | 100 MBPS (22024634) |  | 92872506 (Private IP (PIP)) 92872504 (Access) | C5001624/ADD (22024634) E5002790/ADD (22024635) | 11.KFGS.304741..PA (2202463513052701) | 5704589 | 5500 | PVC ID : 5704589 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64747 PE IP Address : 147.225.254.149 CE Address : 147.225.254.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22024635) | 1000Base-SX (850nm, Multi Mode Fiber) (22024635) | Ethernet | VERIZON (2202463513052701) | 01/25/2016 (2202463513052701) | 02/05/2016 (2202463513052701) | 02/05/2016 (2202463513052701) |  |  | DEMARCDET - 1ST FLR, SRVR RM, RACK-2 LVL 40, LEFT NID, DUAL MOUNT TAGGED, NOT EXT |  | John Kelly 1-610-290-7282 john.kelly@procura-inc.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 02/11/2016(Private IP - PIP) 02/11/2016(Access) |  |  | 02/16/2016 (22024634) 02/12/2016 (22024635) | 03/07/2016 | 02/11/2016 |  |  | N (22024634) N (22024635) | U0101953 |  |  | NSPE0009998570
Completed | Qwest Denver Cyber Center CO751-05-IJ | 8534 CONCORD CENTER DR ENGLEWOOD, CO 80112-7005 US | 1 GBPS | 01/27/2016: 1/27- Vlan tagging request complete. Customer notified. | 192568322 | Qwest Denver Cyber Center CO751-05-IJ | Private IP - PIP (22014027) Access | 22014027 | 1 GBPS (22014027) |  | 85669493 (Private IP (PIP)) 85669491 | C0070131/NONE (22014027) |  | 5681444 | 20000 | PVC ID : 5681444 VPN Name : UnitedHealthGroup Router Name : DNJ9E01 VRF Name : V563406:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64710 PE IP Address : 152.183.240.125 CE Address : 152.183.240.126 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Steve Brown 1-763-694-7333 skbrown1@optum.com | Steve Brown | skbrown1@optum.com | 1-763-694-7333 | 01/22/2016(Private IP |  |  | 01/22/2016 (22014027) | 02/01/2016 | 01/25/2016 |  |  | N (22014027) N | U0101953 |  |  | NSPE0010007358
|  | 250 E 90TH ST DAVENPORT, IA 52806 USA | 1.536 MBPS (IQBK9CH7) | 02/11/2016: 2/11- Circuits delivered. Pending testing and closing of order. | 8624467 |  | Private IP (IQBK9CH7) EVC/PVC Service (N.10950808.5704608) | IQBK9CH7 N.10950808.5704608 | 12.288 MBPS | P2132084 |  | BCBK9F800001 (IQBK9CH7) BCBK9F800002 (IQBK9CH7) BCBK9F800003 (IQBK9CH7) BCBK9F800004 (IQBK9CH7) BCBK9F800005 (IQBK9CH7) BCBK9F800006 (IQBK9CH7) BCBK9F800007 (IQBK9CH7) BCBK9F800008 (IQBK9CH7) | 33/HCGS/06584041//NW (IQBK9CH76YUVMB01) | 5704608 | 10000 | VPN Name : UnitedHealthGroup Router Name : DNGGE07 VRF Name : V575975:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64709 PE IP Address : 68.138.114.177 CE Address : 68.138.114.178 QoS - Egress Profile: R12 PVC ID : 5704608 |  |  |  | CENTURYLINK (IQBK9CH76YUVMB01) | 01/28/2016 (IQBK9CH76YUVMB01) | 02/12/2016 (IQBK9CH76YUVMB01) | 02/10/2016 (IQBK9CH76YUVMB01) |  |  |  |  | STEVE TOBIN 0015635299127 STOBIN@ESTESCONSTRUCTION.COM |  |  |  | 02/15/2016 (IQBK9CH7) |  |  | 02/12/2016 (IQBK9CH7) | 02/17/2016 (IQBK9CH7) |  |  |  | N (IQBK9CH7) N (N.10950808.5704608) | 05017789 P2132084 |  |  | NSPE0010003606
Completed | KY010-05-IJ Louisville. | 9100 SHELBYVILLE RD STE 250 LOUISVILLE, KY 40222-5150 US | 3 MBPS (22060289) | 02/04/2016: 2/4- FOC date 2/12. | 192607763 | KY010-05-IJ Louisville. | Private IP - PIP (22060288) Access (22060289) | 22060288 22060289 | 3 MBPS (22060288) |  | 93981074 (Private IP (PIP)) 93981072 (Access) | C1031578/ADD (22060288) N1026912/ADD (22060289) N1026911/ADD (22060289) | K1/HCGS/424187//SC (2206028913270801) | 5706608 | 1500 | PVC ID : 5706608 VPN Name : UnitedHealthGroup Router Name : WYV9E02 VRF Name : V578727:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65021 PE IP Address : 152.181.52.201 CE Address : 152.181.52.202 QoS - Egress Profile: R12 |  | DS1 (22060289) | TDM | ATT (2206028913270801) | 02/02/2016 (2206028913270801) | 02/12/2016 (2206028913270801) | 02/10/2016 (2206028913270801) |  |  | DEMARCDET - DEMARC LOC: 2 FL PHONE CLOSET HALLWAY CAB 2 SLOT1 |  | Eddie Gibson 1-502-318-1820 todd.gibson@optum.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 02/11/2016(Private IP - PIP) 02/11/2016(Access) |  |  | 02/19/2016 (22060288) 02/17/2016 (22060289) | 02/25/2016 | 02/11/2016 |  |  | N (22060288) N (22060289) | U0101953 |  |  | NSPE0010015808
Completed | MA005-02-IJ Commonwealth of MA Boston | 19 STANIFORD ST BOSTON, MA 02114-2502 US | 100 MBPS (22060928) | 03/24/2016: 3/24- FOC date today, 3/24. | 192607801 | MA005-02-IJ Commonwealth of MA Boston | Private IP - PIP (22060927) Access (22060928) | 22060927 22060928 | 20 MBPS (22060927) |  | 93981077 (Private IP (PIP)) 93981075 (Access) | C1031590/ADD (22060927) E4009012/ADD (22060928) | 95.KFGS.005660..NE (2206092810040501) | 5706668 | 4000 | PVC ID : 5706668 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64816 PE IP Address : 152.185.217.245 CE Address : 152.185.217.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22060928) | 1000Base-SX (850nm, Multi Mode Fiber) (22060928) | Ethernet | VERIZON (2206092810040501) | 03/10/2016 (2206092810040501) | 03/24/2016 (2206092810040501) | 03/24/2016 (2206092810040501) |  |  | DEMARCADDR - 19 STANIFORD, BOS, MA DEMARCDET - 5TH FLOOR CONFERENCE ROOM, IT CLOSET, RACK-MOUNTED, TAGGED. |  | FRANK CALNAN 1-617-447-0372 frank.calnan@optum.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 | 03/24/2016(Private IP - PIP) 03/24/2016(Access) |  |  | 04/04/2016 (22060927) 03/31/2016 (22060928) | 04/20/2016 | 03/24/2016 |  |  | N (22060927) N (22060928) | U0101953 |  |  | NSPE0010015808
Completed | UNITED HEALTH GROUP | 9945 FEDERAL DR COLORADO SPRINGS, CO 80921-3617 US | 50 MBPS (22038128) | 06/02/2016: 6/2- Beas installation rescheduled because of defective beas box | 192607800 | UNITED HEALTH GROUP | Private IP - PIP (22038127) Access (22038128) | 22038127 22038128 | 30 MBPS (22038127) |  | 93981080 (Private IP (PIP)) 93981078 (Access) | C4003032/ADD (22038127) E4008910/ADD (22038128) | 29/KXGS/145757//MS (2203812874246201) | 5705277 | 10000 | PVC ID : 5705277 VPN Name : UnitedHealthGroup Router Name : DNJXE01 VRF Name : V469377-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65263 PE IP Address : 68.137.34.133 CE Address : 68.137.34.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22038128) | 1000Base-SX (850nm, Multi Mode Fiber) (22038128) | Ethernet | CENTURYLINK (2203812874246201) | 04/28/2016 (2203812874246201) | 04/29/2016 (2203812874246201) | 05/04/2016 (2203812874246201) | 06/06/2016 (VFORCE) (22038128) | 06/06/2016 (VFORCE) (22038128) | DEMARCDET - 1ST FL OUTSIDE TELCO RM, WALL MT CIENA 3916, OPT PORT 4 |  | CAROLYN VISALLI 1-303-714-3248 carolyn_visalli@uhg.com | MASROOR KHAN | masroor_khan@optum.com | 1-763-694-7370 | 06/06/2016(Private IP - PIP) 06/06/2016(Access) | 06/09/2016 |  | 06/14/2016 (22038127) 06/10/2016 (22038128) | 06/10/2016 | 06/06/2016 |  |  | N (22038127) N (22038128) | U0101953 |  |  | NSPE0010015808
Completed | IA021-11-IJ Des Moines | 1089 JORDAN CREEK PKWY STE 320 WEST DES MOINES, IA 50266-5830 US | 100 MBPS (22090600) | 04/28/2016: 4/28- Beas installation is scheduled for 4/29. Please secure access for Field tech. | 192630657 | IA021-11-IJ Des Moines | Private IP - PIP (22090599) Access (22090600) | 22090599 22090600 | 20 MBPS (22090599) |  | 99637219 (Private IP (PIP)) 99637217 (Access) | C1031797/ADD (22090599) E4009119/ADD (22090600) | 01/KXGS/145012//NW (2209060013399201) | 5708828 | 5500 | PVC ID : 5708828 VPN Name : UnitedHealthGroup Router Name : PLSHXE01 VRF Name : V588242-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65134 PE IP Address : 208.220.198.209 CE Address : 208.220.198.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22090600) | 1000Base-SX (850nm, Multi Mode Fiber) (22090600) | Ethernet | CENTURYLINK (2209060013399201) | 02/09/2016 (2209060013399201) | 04/06/2016 (2209060013399201) | 04/08/2016 (2209060013399201) | 04/29/2016 (VFORCE) (22090600) | 04/29/2016 (VFORCE) (22090600) | DEMARCDET - 3RD FLR. TELCO RM, WALLMOUNT 3916, OPTICAL PORT #3 |  | Jackie Powell 1-515-727-2023 jackie_a_powell@uhc.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 04/29/2016(Private IP - PIP) 04/29/2016(Access) |  |  | 05/04/2016 (22090599) 05/02/2016 (22090600) | 06/06/2016 | 04/29/2016 |  |  | N (22090599) N (22090600) | U0101953 |  |  | NSPE0010027395
Completed | C1567-02-IJ West - Denver Gas and Electric ECC | 910 15TH ST STE 350 DENVER, CO 80202-3234 US | 1 GBPS (22050482) | 02/18/2016: 2/18- Circuit designed. Order stepped for site survey. | 192631505 | C1567-02-IJ West - Denver Gas and Electric ECC | Private IP - PIP (22050481) Access (22050482) | 22050481 22050482 | 600 MBPS (22050481) |  | 99394493 (Private IP (PIP)) 99394491 (Access) | C0076663/ADD (22050481) E5002835/ADD (22050482) |  | 5705902 | 450000 | PVC ID : 5705902 VPN Name : UHG-ECC Router Name : DNJXE01 VRF Name : V595692-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65482 PE IP Address : 206.115.61.185 CE Address : 206.115.61.186 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (22050482) | Ethernet | [8 empty] | OVIDIO RESENDEZ 1-303-825-2552 ovi-dgeb@qwestoffice.net | SCOTT MOYER | scott_moyer@optum.com | 1-763-744-2154 | 02/22/2016(Private IP - PIP) 02/22/2016(Access) |  |  | 02/26/2016 (22050481) 02/24/2016 (22050482) | 02/26/2016 | 02/22/2016 |  |  | N (22050481) N (22050482) | U0101953 |  |  | NSPE0010027135
|  | 2974 SW 8TH ST MIAMI, FL 33135 USA | 1.536 MBPS (IQBK9GLD) | 02/04/2016: 2/4- FOC date 2/5. | 8638711 |  | Private IP (IQBK9GLD) EVC/PVC Service (N.10958375.5706791) | IQBK9GLD N.10958375.5706791 | 10.752 MBPS | P2132763 |  | BCBK9G2G0001 (IQBK9GLD) BCBK9G2G0002 (IQBK9GLD) BCBK9G2G0003 (IQBK9GLD) BCBK9G2G0004 (IQBK9GLD) BCBK9G2G0005 (IQBK9GLD) BCBK9G2G0006 (IQBK9GLD) BCBK9G2G0007 (IQBK9GLD) | 60/HCGS/471183//SB (IQBK9GLDACVVMB01) | 5706791 | 4000 | VPN Name : UnitedHealthGroup Router Name : POB3E02 VRF Name : V368211-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64813 PE IP Address : 199.220.73.13 CE Address : 199.220.73.14 QoS - Egress Profile: R12 PVC ID : 5706791 |  |  |  | ATT (IQBK9GLDACVVMB01) | 02/03/2016 (IQBK9GLDACVVMB01) | 02/05/2016 (IQBK9GLDACVVMB01) | 02/09/2016 (IQBK9GLDACVVMB01) |  |  |  |  | CRISTY ALFONSO 0013056313000 CALFONSO@PCPMEDICALGROUP.COM |  |  |  | 02/09/2016 (IQBK9GLD) |  |  | 02/09/2016 (IQBK9GLD) | 02/12/2016 (IQBK9GLD) |  |  |  | Y (IQBK9GLD) Y (N.10958375.5706791) | 05017789 87521938 |  |  | NSPE0010023141
Completed | AL012-02-IJ Birmingham AL | 1100 LEE BRANCH LN BIRMINGHAM, AL 35242-7298 US | 100 MBPS (22087905) | 02/24/2016: 2/24- Customer confirmed extension not needed. Waiting for beas install to be scheduled. | 192647847 | AL012-02-IJ Birmingham, AL | Private IP - PIP (22087904) Access (22087905) | 22087904 22087905 | 100 MBPS (22087904) |  | 100161730 (Private IP (PIP)) 100161728 (Access) | C1031772/ADD (22087904) E4009100/ADD (22087905) | A3/KRGN/601456//SC (2208790512617001) | 5708647 | 10000 | PVC ID : 5708647 VPN Name : UnitedHealthGroup Router Name : B6S9E01 VRF Name : Vb34594:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64815 PE IP Address : 152.162.131.37 CE Address : 152.162.131.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22087905) | 1000Base-SX (850nm, Multi Mode Fiber) (22087905) | Ethernet | ATT (2208790512617001) | 02/08/2016 (2208790512617001) | 02/24/2016 (2208790512617001) | 02/24/2016 (2208790512617001) | 03/02/2016 (VFORCE) (22087905) | 03/02/2016 (VFORCE) (22087905) | DEMARCDET - 1st floor customer equipment room, backboard mounted Ciena 3930 port 6 |  | Dan Jarnigan 1-630-577-3827 Dan.jarnigan@catamaranrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/02/2016(Private IP - PIP) 03/02/2016(Access) |  |  | 03/04/2016 (22087904) 03/02/2016 (22087905) | 03/21/2016 | 03/02/2016 |  |  | N (22087904) N (22087905) | U0101953 |  |  | NSPE0010037527
Completed | MS003-02-IJ UHG Columbus | 2102 5TH ST N STE 3 COLUMBUS, MS 39705-2222 US | 100 MBPS (22117542) | 03/03/2016: 3/3- Circuit delivered. Customer confirmed demark. Waiting for beas install to be scheduled. | 192694027 | MS003-02-IJ UHG Columbus | Private IP - PIP (22117541) Access (22117542) | 22117541 22117542 | 10 MBPS (22117541) |  | 100485022 (Private IP (PIP)) 100485020 (Access) | C1032384/ADD (22117541) E4009236/ADD (22117542) | M1/KRGN/822967//SC (2211754212768301) | 5710904 | 1500 | PVC ID : 5710904 VPN Name : UnitedHealthGroup Router Name : CPZGE03 VRF Name : V205712:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64772 PE IP Address : 152.185.155.201 CE Address : 152.185.155.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22117542) | 1000Base-SX (850nm, Multi Mode Fiber) (22117542) | Ethernet | ATT (2211754212768301) | 02/15/2016 (2211754212768301) | 03/02/2016 (2211754212768301) | 03/04/2016 (2211754212768301) | 03/07/2016 (VFORCE) (22117542) | 03/07/2016 (VFORCE) (22117542) | DEMARCADDR - 2102 5TH ST N COLUMBUS MS DEMARCDET - 1ST FLOOR SERVER RM WALL MOUNT PORT 6 |  | Dan Jarnigan 1-630-577-3827 Dan.jarnigan@catamaranrx.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 03/07/2016(Private IP - PIP) 03/07/2016(Access) |  |  | 03/11/2016 (22117541) 03/09/2016 (22117542) | 03/28/2016 | 03/07/2016 |  |  | N (22117541) N (22117542) | U0101953 |  |  | NSPE0010039407
Completed | CA109-02-IJ La Palma CA Ethernet | 18 CENTERPOINTE DR LA PALMA, CA 90623-1069 US | 100 MBPS (22099152) | 03/24/2016: 3/24- FOC date 4/11 | 192694093 | CA109-02-IJ La Palma, CA Ethernet | Private IP - PIP (22099151) Access (22099152) | 22099151 22099152 | 40 MBPS (22099151) |  | 100506800 (Private IP (PIP)) 100506798 (Access) | C1031859/ADD (22099151) E4009164/ADD (22099152) | 71.L1XX.002821..TWCC (2209915291058901) | 5709491 | 50000 | PVC ID : 5709491 VPN Name : UnitedHealthGroup Router Name : BB39E01 VRF Name : V581972:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64821 PE IP Address : 152.185.155.169 CE Address : 152.185.155.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22099152) | 1000Base-SX (850nm, Multi Mode Fiber) (22099152) | Ethernet | TIME WARNER CABLE (2209915291058901) | 02/10/2016 (2209915291058901) | 04/11/2016 (2209915291058901) | 03/25/2016 (2209915291058901) | 03/30/2016 (VFORCE) (22099152) | 03/30/2016 (VFORCE) (22099152) | DEMARCDET - data room rack 2 port 5 labelled |  | Irving Calderon 1-714-680-9200 Irving.Calderon@excelconstruction.biz | MOHAN BASNET | mohan_basnet@optum.com | 1-763-744-1971 | 03/30/2016(Private IP - PIP) 03/30/2016(Access) | 04/07/2016 |  | 04/20/2016 (22099151) 04/18/2016 (22099152) | 03/23/2016 | 03/30/2016 |  |  | N (22099151) N (22099152) | U0101953 |  |  | NSPE0010041246
Completed | FL140-02-IJ Catamaran Miramar | 9994 PREMIER PKWY MIRAMAR, FL 33025-3209 US | 100 MBPS (22090952) | 03/03/2016: 3/3- Beas install scheduled for 3/7. | 192694119 | FL140-02-IJ Catamaran Miramar | Private IP - PIP (22090951) Access (22090952) | 22090951 22090952 | 20 MBPS (22090951) |  | 100506797 (Private IP (PIP)) 100506795 (Access) | C1031798/ADD (22090951) E4009120/ADD (22090952) | 60/KRGN/756752//SB (2209095212847301) | 5708841 | 10000 | PVC ID : 5708841 VPN Name : UnitedHealthGroup Router Name : POB3E03 VRF Name : V581033-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64797 PE IP Address : 152.185.11.13 CE Address : 152.185.11.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22090952) | 1000Base-SX (850nm, Multi Mode Fiber) (22090952) | Ethernet | ATT (2209095212847301) | 02/10/2016 (2209095212847301) | 02/25/2016 (2209095212847301) | 03/02/2016 (2209095212847301) | 03/07/2016 (VFORCE) (22090952) | 03/07/2016 (VFORCE) (22090952) | DEMARCADDR - 9994 PREMIER PKWY MIRAMAR FL DEMARCDET - 1ST FLR SERVER RM RACK MNTD UNI PORT 6 |  | Acton Ryner 1-954-364-6583 Acton.ryner@catamaranrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/07/2016(Private IP - PIP) 03/07/2016(Access) | 06/20/2016 |  | 03/25/2016 (22090951) 03/23/2016 (22090952) | 03/23/2016 | 03/07/2016 |  |  | N (22090951) N (22090952) | U0101953 |  |  | NSPE0010041246
Completed | CA157-02-IJ Catamaran Los Angeles | 1902 MARENGO ST STE 201 LOS ANGELES, CA 90033-1317 US | 100 MBPS (22104882) | 03/17/2016: 3/17- Circuit extended. Beas install scheduled for Monday, 3/21. | 192694482 | CA157-02-IJ Catamaran Los Angeles | Private IP - PIP (22104881) Access (22104882) | 22104881 22104882 | 20 MBPS (22104881) |  | 100484628 (Private IP (PIP)) 100484546 (Access) | C1032300/ADD (22104881) E4009192/ADD (22104882) | 13/KRGN/586630//PT (2210488212641901) | 5709951 | 10000 | PVC ID : 5709951 VPN Name : UnitedHealthGroup Router Name : BB39E01 VRF Name : V581972:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64801 PE IP Address : 152.176.103.69 CE Address : 152.176.103.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22104882) | 1000Base-SX (850nm, Multi Mode Fiber) (22104882) | Ethernet | ATT (2210488212641901) | 02/11/2016 (2210488212641901) | 02/29/2016 (2210488212641901) | 03/01/2016 (2210488212641901) | 03/21/2016 (VFORCE) (22104882) | 03/21/2016 (VFORCE) (22104882) | DEMARCADDR - 1902 MARENGO LA DEMARCDET - ENINUITY MTG 1 POS 5 AND 6 AT 1.1 MPOE |  | Laurie Faulknor 1-416-560-4680 Laurie.Faulknor@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/21/2016(Private IP - PIP) 03/21/2016(Access) | 06/22/2016 |  | 04/08/2016 (22104881) 04/06/2016 (22104882) | 04/06/2016 | 03/21/2016 |  |  | N (22104881) N (22104882) | U0101953 |  |  | NSPE0010041439
Completed | GA029-02-IJ Catamaran Duluth | 1855 SATELLITE BLVD DULUTH, GA 30097-5295 US | 100 MBPS (22117824) | 05/05/2017: 05/05 Successfully activated | 192694500 | GA029-02-IJ Catamaran Duluth, | Private IP - PIP (22117823) Access (22117824) | 22117823 22117824 | 20 MBPS (22117823) |  | 100484631 (Private IP (PIP)) 100484629 (Access) | C1032386/ADD (22117823) E4009239/ADD (22117824) | 4Y/KFFN/002924/LVLC (2211782412641901) | 5710915 | 4000 | PVC ID : 5710915 VPN Name : UnitedHealthGroup Router Name : CHRL3E03 VRF Name : V516000-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64794 PE IP Address : 68.139.135.197 CE Address : 68.139.135.198 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22117824) | 1000Base-SX (850nm, Multi Mode Fiber) (22117824) | Ethernet | LEVEL 3 (2211782412641901) | 03/31/2016 (2211782412641901) | 04/21/2016 (2211782412641901) | 04/21/2016 (2211782412641901) | 05/03/2016 (VFORCE) (22117824) | 05/03/2016 (VFORCE) (22117824) | DEMARCDET - 1st floor suite 600, server room, right wall mounted 8 ft up ADVA ED002. |  | Brandon Cannon 1-678-347-2352 Brandon.cannon@cypresscare.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 | 05/03/2016(Private IP - PIP) 05/03/2016(Access) | 05/05/2017 |  | 05/11/2016 (22117823) 05/09/2016 (22117824) | 06/13/2016 | 05/03/2016 |  |  | N (22117823) N (22117824) | U0101953 |  |  | NSPE0010041439
Completed | PA100-02-IJ Catamaran Philadelphia | 1650 ARCH ST STE 2600 PHILADELPHIA, PA 19103-2040 US | 100 MBPS (22136396) | 03/31/2016: 3/31- FOC date 4/4. | 192694593 | PA100-02-IJ Catamaran Philadelphia | Private IP - PIP (22136395) Access (22136396) | 22136395 22136396 | 20 MBPS (22136395) |  | 99445960 (Private IP (PIP)) 99445958 (Access) | C1032495/ADD (22136395) E4009311/ADD (22136396) | 11.KFGS.304860..PA (2213639613361001) | 5712498 | 4000 | PVC ID : 5712498 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64752 PE IP Address : 68.139.59.165 CE Address : 68.139.59.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22136396) | 1000Base-SX (850nm, Multi Mode Fiber) (22136396) | Ethernet | VERIZON (2213639613361001) | 02/18/2016 (2213639613361001) | 04/04/2016 (2213639613361001) | 03/31/2016 (2213639613361001) |  |  | DEMARCADDR - 1650 ARCH ST, PHILA, PA DEMARCDET - 26TH FLOOR SERVER ROOM RACK MNT POS #4 TAGGED |  | Summer Allen 1-215-553-5151 Summer.allen@optum.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 04/01/2016(Private IP - PIP) 04/01/2016(Access) | 09/20/2016 |  | 04/13/2016 (22136395) 04/11/2016 (22136396) | 04/12/2016 | 04/01/2016 |  |  | N (22136395) N (22136396) | U0101953 |  |  | NSPE0010047048
Completed | PA101-02-IJ Catamaran Warminster PA | 738 LOUIS DR WARMINSTER, PA 18974-2829 US | 200 MBPS (22139760) | 11/07/2016: 11/7 Customer (Ranjit Adhikari) confirmed ckt is up and accepted. Order completed. | 192694619 | PA101-02-IJ Catamaran Warminster PA | Private IP - PIP (22139759) Access (22139760) | 22139759 22139760 | 100 MBPS (22139759) |  | 99445963 (Private IP (PIP)) 99445961 (Access) | C5001711/ADD (22139759) E5002990/ADD (22139760) | 11.KFGS.304865..PA (2213976013361101) | 5712704 | 4000 | PVC ID : 5712704 VPN Name : UnitedHealthGroup Router Name : PTNGE04 VRF Name : V784544:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64749 PE IP Address : 68.136.59.1 CE Address : 68.136.59.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22139760) | 1000Base-SX (850nm, Multi Mode Fiber) (22139760) | Ethernet | VERIZON (2213976013361101) | 02/19/2016 (2213976013361101) | 03/03/2016 (2213976013361101) | 03/09/2016 (2213976013361101) |  |  | DEMARCDET - BLDG MAIN FLR 1ST RM TELCO |  | Enzo Mastromarco 1-267-280-5149 Enzo.mastromarco@hbsrx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 03/09/2016(Private IP - PIP) 03/09/2016(Access) | 11/07/2016 |  | 03/14/2016 (22139759) 03/10/2016 (22139760) | 03/31/2016 | 03/09/2016 |  |  | N (22139759) N (22139760) | U0101953 |  |  | NSPE0010047048
Completed | PA727-02-IJ Catamaran Norristown PA | 1000 ADAMS AVE NORRISTOWN, PA 19403-2402 US | 300 MBPS (22104939) | 02/24/2016: 2/24- FOC date 2/25. | 192694725 | PA727-02-IJ Catamaran Norristown, PA | Private IP - PIP (22104938) Access (22104939) | 22104938 22104939 | 150 MBPS (22104938) |  | 101312155 (Private IP (PIP)) 101312153 (Access) | C5001692/ADD (22104938) E5002926/ADD (22104939) | 11.KFGS.304810..PA (2210493912916701) | 5709954 | 20000 | PVC ID : 5709954 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64839 PE IP Address : 147.225.28.153 CE Address : 147.225.28.154 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22104939) | 1000Base-LX (1310nm Single Mode Fiber) (22104939) | Ethernet | VERIZON (2210493912916701) | 02/11/2016 (2210493912916701) | 02/25/2016 (2210493912916701) | 03/01/2016 (2210493912916701) |  |  | DEMARCDET - 3RD FL CUST RACK 2ND FROM END MIDDLE ISLE TOP OF RACK UNIT 3 TAGGED |  | John Kelly 1-610-290-7282 john.kelly@procura-inc.com | Jonathan Edwards | jonathan.edwards@optum.com | 1-781-419-8604 | 03/01/2016(Private IP - PIP) 03/01/2016(Access) | 06/30/2016 |  | 03/07/2016 (22104938) 03/03/2016 (22104939) | 03/24/2016 | 03/01/2016 |  |  | N (22104938) N (22104939) | U0101953 |  |  | NSPE0010051349
Completed | Centennial CO UCO17-07-IJ | 6465 GREENWOOD PLAZA BLVD STE 300 GREENWOOD VILLAGE, CO 80111-7101 US | 100 MBPS (22101161) | 03/24/2016: 3/24- BEAS install is scheduled 3/28. | 192720505 | Centennial CO UCO17-07-IJ | Private IP - PIP (22101160) Access (22101161) | 22101160 22101161 | 100 MBPS (22101160) |  | 101736718 (Private IP (PIP)) 101736716 (Access) | C1031884/ADD (22101160) E4009178/ADD (22101161) | 60.KGGS.001381..CBCL.. (2210116113766201) | 5709616 | 10000 | PVC ID : 5709616 VPN Name : UnitedHealthGroup Router Name : DNJ9E01 VRF Name : V563406:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64736 PE IP Address : 152.185.77.209 CE Address : 152.185.77.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22101161) | 1000Base-SX (850nm, Multi Mode Fiber) (22101161) | Ethernet | COMCAST (2210116113766201) | 02/11/2016 (2210116113766201) | 03/17/2016 (2210116113766201) | 03/21/2016 (2210116113766201) | 03/28/2016 (VFORCE) (22101161) | 03/28/2016 (VFORCE) (22101161) | DEMARCDET - 1st FLR server room 4th rack 1st pos. labeled with ckt ID. VLAN: 3955 |  | JEANNIE HERTEL 1-303-267-3339 jeannie_m_hertel@uhc.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 03/28/2016(Private IP - PIP) 03/28/2016(Access) |  |  | 03/28/2016 (22101160) 03/24/2016 (22101161) | 03/23/2016 | 03/28/2016 |  |  | N (22101160) N (22101161) | U0101953 |  |  | NSPE0010057405
Completed | PA105-02-IJ Catamaran Pittsburgh | 285 KAPPA DR STE 350 PITTSBURGH, PA 15238-2821 US | 100 MBPS (22136499) | 03/03/2016: 3/3- FOC date 3/10. | 192720840 | PA105-02-IJ Catamaran Pittsburgh | Private IP - PIP (22136498) Access (22136499) | 22136498 22136499 | 100 MBPS (22136498) |  | 101145024 (Private IP (PIP)) 101145022 (Access) | C1032494/ADD (22136498) E4009308/ADD (22136499) | 15.KFGS.304861..PA (2213649913649201) | 5712478 | 1500 | PVC ID : 5712478 VPN Name : UnitedHealthGroup Router Name : PTBXE01 VRF Name : V576619-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64745 PE IP Address : 68.139.238.241 CE Address : 68.139.238.242 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22136499) | 1000Base-SX (850nm, Multi Mode Fiber) (22136499) | Ethernet | VERIZON (2213649913649201) | 02/18/2016 (2213649913649201) | 03/10/2016 (2213649913649201) | 03/04/2016 (2213649913649201) |  |  | DEMARCDET - 3RD FLR, TELCO RM, SUITE 350 RACK MNTD, TAGGED, NOT EXT |  | Robin Lambermont 1-866-308-4547 Robin.Lambermont@catamaranrx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 03/04/2016(Private IP - PIP) 03/04/2016(Access) |  |  | 03/21/2016 (22136498) 03/17/2016 (22136499) | 03/30/2016 | 03/04/2016 |  |  | N (22136498) N (22136499) | U0101953 |  |  | NSPE0010057520
Completed | Catamaran LA007-02-IJ | 1737A SAM HOUSTON JONES PKWY LAKE CHARLES, LA 70611-5454 US | 100 MBPS (22125033) | 03/03/2016: 3/3- Circuit installed and customer confirmed demarc. Waiting for beas install to be scheduled. | 192763967 | Catamaran LA007-02-IJ | Private IP - PIP (22125032) Access (22125033) | 22125032 22125033 | 100 MBPS (22125032) |  | 102686041 (Private IP (PIP)) 102686039 (Access) | C1032435/ADD (22125032) E4009278/ADD (22125033) | L3/KRGN/820551//SC (2212503313936101) | 5711362 | 1500 | PVC ID : 5711362 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : V583494:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64779 PE IP Address : 152.161.25.245 CE Address : 152.161.25.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22125033) | 1000Base-SX (850nm, Multi Mode Fiber) (22125033) | Ethernet | ATT (2212503313936101) | 02/17/2016 (2212503313936101) | 03/02/2016 (2212503313936101) | 03/02/2016 (2212503313936101) | 03/07/2016 (VFORCE) (22125033) | 03/08/2016 (VFORCE) (22125033) | DEMARCADDR - ADRS_UNKNOWN DEMARCDET - 1ST FLOOR/TELCO RM/CUST JACK/POS. 7 & NA |  | Jodi Roy 1-337-217-0033 jodi-roy@briovarx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 03/08/2016(Private IP - PIP) 03/08/2016(Access) | 07/08/2016 |  | 03/11/2016 (22125032) 03/09/2016 (22125033) | 06/21/2016 | 03/08/2016 |  |  | N (22125032) N (22125033) | U0101953 |  |  | NSPE0010075170
|  | 6675 BUSINESS PKWY ELKRIDGE, MD 21075 USA | 1.536 MBPS (IQBK9T26) | 03/10/2016: 3/10- Pending confirmation from LEC that circuit was installed as scheduled. | 8673232 |  | Private IP (IQBK9T26) EVC/PVC Service (N.10983154.5716058) | IQBK9T26 N.10983154.5716058 | 10.752 MBPS | P2135005 |  | BCBK9KY00001 (IQBK9T26) BCBK9KY00002 (IQBK9T26) BCBK9KY00003 (IQBK9T26) BCBK9KY00004 (IQBK9T26) BCBK9KY00005 (IQBK9T26) BCBK9KY00006 (IQBK9T26) BCBK9KY00007 (IQBK9T26) | 38.HCGS.009366..CM (1265923) | 5716058 | 1536 | VPN Name : UnitedHealthGroup Router Name : RAY9E02 VRF Name : V416181:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64706 PE IP Address : 152.183.183.121 CE Address : 152.183.183.122 QoS - Egress Profile: R12 PVC ID : 5716058 |  |  |  | VERIZON (1265923) | 03/01/2016 (1265923) | 03/10/2016 (1265923) | 09/21/2016 (1265923) |  |  |  |  | BILL SNOOK 0014102274752 WILLIAM.SNOOK@OPTUM.COM |  |  |  | 03/14/2016 (IQBK9T26) |  |  | 03/17/2016 (IQBK9T26) | 03/24/2016 (IQBK9T26) |  |  |  | N (IQBK9T26) N (N.10983154.5716058) | 05017789 P2135005 |  |  | NSPE0010104695
Completed |  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBK9ZRN) | 03/24/2016: 3/24- Comments: Activation completed. Circuit is UP and processing traffic and Tim accepts this circuit. Customer Contact: TIM GUNDERSON 7637442081 | 8687205 |  | Private IP Port Only (CQBK9ZRN) | CQBK9ZRN | 7000 MBPS 7000 MBPS (CQBK9ZRN) | P1932297 |  | BOBKTD960001 (CQBK9ZRN) |  | 5212513 5539402 5723530 | 110500 270000 314000 384 360000 1500000 | PVC ID : 5212513,5539402,5723530 VPN Name : UHG-XLHealth,UHG-UC,UHG-IPTF,UnitedHealthGroup-IDN,UHG-ECC,UnitedHealthGroup Router Name : MN3GE01 VRF Name : V594628:UHGXLHealth,V656367:UHGUC,V594624:UHGIPTF,V594626:UnitedHealthGroupIDN,V594627:UHGECC,V594623:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : v4-152.162.46.225,v6-68.137.39.25,v4-152.176.215.13,v6-152.192.111.185,v4-147.225.22.233,v6-152.161.107.161 CE Address : v4-152.162.46.226,v6-68.137.39.26,v4-152.176.215.14,v6-152.192.111.186,v4-147.225.22.234,v6-152.161.107.162 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 03/24/2016 (CQBK9ZRN) | 03/23/2016 |  | 04/06/2016 (CQBK9ZRN) | 04/06/2016 (CQBK9ZRN) |  |  |  | N (CQBK9ZRN) | 05017789 |  |  | NSPE0010110894
|  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBK9ZQY) | 03/17/2016: 3/17- Ready for hotcut, customer notified. | 8687323 |  | Private IP Port Only (CQBK9ZQY) | CQBK9ZQY | 7000 MBPS | P1955436 |  | BOBKWCW20001 (CQBK9ZQY) |  | 5538820 5210728 5210727 | 24576 | PVC ID : 5538820,5210728,5210727 VPN Name : Alere-LLC-WAN Router Name : MZZGE01 VRF Name : Vg35543:AlereLLCWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : 152.176.170.69 CE Address : 152.176.170.70 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 04/05/2016 (CQBK9ZQY) | 04/05/2016 |  | 04/06/2016 (CQBK9ZQY) | 04/06/2016 (CQBK9ZQY) |  |  |  | N (CQBK9ZQY) | 05017789 |  |  | NSPE0010111876
Completed | NM023-09-IJ Albuquerque NM | 8801 HORIZON BLVD NE STE 260 ALBUQUERQUE, NM 87113-1534 US | 200 MBPS (22188409) | 01/20/2017: 01/19 Successfully activated | 192876311 | NM023-09-IJ Albuquerque NM | Private IP - PIP (22188408) Access (22188409) | 22188408 22188409 | 100 MBPS (22188408) |  | 104531635 (Private IP (PIP)) 104531633 (Access) | C5001744/ADD (22188408) E5003065/ADD (22188409) | 59/KXGS/148759//MS (2218840914297901) | 5716556 | 25000 | PVC ID : 5716556 VPN Name : UnitedHealthGroup Router Name : AQHGE02 VRF Name : V551714:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65190 PE IP Address : 68.137.57.41 CE Address : 68.137.57.42 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22188409) | 1000Base-LX (1310nm Single Mode Fiber) (22188409) | Ethernet | CENTURYLINK (2218840914297901) | 03/01/2016 (2218840914297901) | 03/15/2016 (2218840914297901) | 03/21/2016 (2218840914297901) | 05/04/2016 (VFORCE) (22188409) | 05/04/2016 (VFORCE) (22188409) | DEMARCADDR - X DEMARCDET - 1ST FL FRAME RM, RR, SH-1, PORT-2 OPT |  | Tim Cavanaugh 1-505-798-5796 tim.cavanaugh@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 05/04/2016(Private IP - PIP) 05/04/2016(Access) | 01/19/2017 |  | 05/09/2016 (22188408) 05/05/2016 (22188409) | 06/09/2016 | 05/04/2016 |  |  | N (22188408) N (22188409) | U0101953 |  |  | NSPE0010112636
Completed | C1598-02-IJ NRECA Lincoln NE | 8701 FIRETHORN LN LINCOLN, NE 68520-1402 US | 20 MBPS (22220919) | 04/07/2016: 4/7- Loop has been delivered. Waiting for LEC to complete the logical side of the order. | 192920407 | C1598-02-IJ NRECA Lincoln NE | Private IP - PIP (22220918) Access (22220919) | 22220918 22220919 | 10 MBPS (22220918) |  | 94036325 (Private IP (PIP)) 94036322 (Access) | C3006154/ADD (22220918) E3020976/ADD (22220919) | NE/KQGS/323579/ /WINW/ (2222091913163401) | 5719558 | 1500 | PVC ID : 5719558 VPN Name : UHG-ECC Router Name : PLSHXE01 VRF Name : V449266-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65514 PE IP Address : 68.138.244.241 CE Address : 68.138.244.242 QoS - Egress Profile: R12 | 100Base-TX (22220919) | 100Base-FX (1310nm, Multi Mode Fiber) (22220919) | Ethernet | WINDSTREAM (2222091913163401) | 03/08/2016 (2222091913163401) | 04/06/2016 (2222091913163401) |  | 04/12/2016 (VFORCE) (22220919) | 04/12/2016 (VFORCE) (22220919) |  |  | Lyle Peterson 1-402-484-9509 Lyle.Petersen@nreca.coop | Eric Taylor | eric_taylor@optum.com | 1-763-744-2082 | 04/12/2016(Private IP - PIP) 04/12/2016(Access) |  |  | 04/22/2016 (22220918) 04/20/2016 (22220919) | 04/18/2016 | 04/12/2016 |  |  | N (22220918) N (22220919) | U0101953 |  |  | NSPE0010123173
Completed | NC021-02-IJ Raliegh NC | 4242 SIX FORKS RD FL 11 RALEIGH, NC 27609-5716 US | 100 MBPS (22221044) | 05/27/2016: 5/26- BEAS install schedule 5/31. ** TECH JAMES BROWN | 192920784 | NC021-02-IJ Raliegh, NC | Access (22221044) Private IP - PIP (22221043) | 22221044 22221043 | 100 MBPS (22221043) |  | 94036361 (Access) 94036364 (Private IP (PIP)) | E4010011/ADD (22221044) C1033891/ADD (22221043) | 26/KRGN/401000//SB (2222104414418501) | 5719561 | 70000 | PVC ID : 5719561 VPN Name : UnitedHealthGroup Router Name : RLGH9E01 VRF Name : V477622:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64699 PE IP Address : 152.177.30.77 CE Address : 152.177.30.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22221044) | 1000Base-SX (850nm, Multi Mode Fiber) (22221044) | Ethernet | ATT (2222104414418501) | 03/24/2016 (2222104414418501) | 04/11/2016 (2222104414418501) | 04/11/2016 (2222104414418501) | 06/02/2016 (VFORCE) (22221044) | 06/03/2016 (VFORCE) (22221044) | DEMARCADDR - 4242 SIX FORKS RD RAL NC DEMARCDET - 11TH FLR TELCO RM PORT 3/4 OF VIRTUAL |  | Cary Lail 1-919-832-3770 CLail@mcdonaldyork.com | Masroor Khan | masroor_khan@optum.com | 1-763-694-7370 | 06/03/2016(Access) 06/03/2016(Private IP - PIP) | 06/20/2016 |  | 06/10/2016 (22221044) 06/14/2016 (22221043) | 06/10/2016 | 06/03/2016 |  |  | N (22221044) N (22221043) | U0101953 |  |  | NSPE0010125086
Completed | UNITED HEALTH GROUP | 10290 W 70TH ST EDEN PRAIRIE, MN 55344-3440 US | 20 MBPS (22286350) | 05/05/2016: 5/5- BEAS installation scheduled today. | 192965914 | UNITED HEALTH GROUP | Private IP - PIP (22286349) Access (22286350) | 22286349 22286350 | 10 MBPS (22286349) |  | 106765040 (Private IP (PIP)) 106765038 (Access) | C3006317/ADD (22286349) E3021548/ADD (22286350) | 03/KXGS/152222//NW (2228635074246201) | 5724763 | 1500 | PVC ID : 5724763 VPN Name : UHG-ECC Router Name : MN39E01 VRF Name : V594781:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65468 PE IP Address : 208.219.150.221 CE Address : 208.219.150.222 QoS - Egress Profile: R12 | 100Base-TX (22286350) | 100Base-TX (22286350) | Ethernet | CENTURYLINK (2228635074246201) | 03/22/2016 (2228635074246201) | 04/05/2016 (2228635074246201) | 04/08/2016 (2228635074246201) | 05/05/2016 (VFORCE) (22286350) | 05/05/2016 (VFORCE) (22286350) | DEMARCDET - SEE SECURITY FOR ESCORT) CAB DD147, RACK MOUNT CIENA 3916 WITHELECTRICAL SFP IN PORT 3 |  | mark lanie 1-952-992-2653 mark.lanie@medica.com | SCOTT MOYER | scott_moyer@optum.com | 1-763-744-2154 | 05/05/2016(Private IP - PIP) 05/05/2016(Access) |  |  | 05/05/2016 (22286349) 05/03/2016 (22286350) | 05/02/2016 | 05/05/2016 |  |  | N (22286349) N (22286350) | U0101953 |  |  | NSPE0010176335
Completed | Miami FL | 11300 NW 25TH ST DORAL, FL 33172-1802 US | 250 MBPS (22309082) | 07/28/2016: 7/28- Circuit extended. Waiting for beas install to be scheduled. | 192969887 | Miami, FL | Private IP - PIP (22309081) Access (22309082) | 22309081 22309082 | 100 MBPS (22309081) |  | 107614549 (Private IP (PIP)) 107614487 (Access) | C0080403/ADD (22309081) E0000493/ADD (22309082) | 60/KRGN/756986//SB (2230908218163601) | 5726794 | 10000 | PVC ID : 5726794 VPN Name : UnitedHealthGroup Router Name : POB3E03 VRF Name : V581033-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64561 PE IP Address : 68.136.112.9 CE Address : 68.136.112.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22309082) | 1000Base-SX (850nm, Multi Mode Fiber) (22309082) | Ethernet | ATT (2230908218163601) | 04/08/2016 (2230908218163601) | 04/27/2016 (2230908218163601) | 07/27/2016 (2230908218163601) | 08/01/2016 (VFORCE) (22309082) |  | DEMARCDET - 1st floor server room 2 at&t rr 01 100.01 CIENNA unit 1 port 7 tagged with ckt ID MULTI MODE |  | FATIMA VILCHEZ 1-305-632-9826 fatima.vilchez.ext@telefonica.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/01/2016(Private IP - PIP) 08/01/2016(Access) |  |  | 08/04/2016 (22309081) 08/02/2016 (22309082) | 08/02/2016 | 08/01/2016 |  |  | N (22309081) N (22309082) | U0101953 |  |  | NSPE0010180386
Completed | MA023-05-IJ Wakefield MA | 100 QUANNAPOWITT PKWY WAKEFIELD, MA 01880-1319 US | 100 MBPS (22353175) | 06/02/2016: 6/2- Loop delivery missed. This order is impacted by the strike, expect delays on the process | 192978708 | MA023-05-IJ Wakefield MA | Private IP - PIP (22353174) Access (22353175) | 22353174 22353175 | 20 MBPS (22353174) |  | 107895106 (Private IP (PIP)) 107895104 (Access) | C1034200/ADD (22353174) E4010216/ADD (22353175) | 95.KFGS.005882..NE (2235317569192101) | 5729990 | 4000 | PVC ID : 5729990 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65110 PE IP Address : 147.225.153.17 CE Address : 147.225.153.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22353175) | 1000Base-SX (850nm, Multi Mode Fiber) (22353175) | Ethernet | VERIZON (2235317569192101) | 04/05/2016 (2235317569192101) | 04/15/2016 (2235317569192101) | 06/02/2016 (2235317569192101) |  |  | DEMARCADDR - 100 QUANNAPOWITT PKWY, WAK, MA DEMARCDET - NO DEMARC AVAILABLE AT THIS TIME |  | John MacLean 1-781-557-3014 John_A_MacLean@Optum.com | ROBERT BENSON | robert_a_benson@optum.com | 1-763-744-2077 | 06/02/2016(Private IP - PIP) 06/02/2016(Access) | 06/29/2016 |  | 04/26/2016 (22353174) 04/22/2016 (22353175) | 05/16/2016 | 06/02/2016 |  |  | N (22353174) N (22353175) | U0101953 |  |  | NSPE0010186163
Completed | CT719-01-IJ Shelton CT | 1 ENTERPRISE DR SHELTON, CT 06484-4631 US | 150 MBPS (22323586) | 06/09/2016: 6/9- BEAS install complete. circuit testing in progress. waiting for confirmation that the circuit is ready for activation. | 192978927 | CT719-01-IJ Shelton, CT | Private IP - PIP (22323585) Access (22323586) | 22323585 22323586 | 100 MBPS (22323585) |  | 108097783 (Private IP (PIP)) 108097781 (Access) | C4003593/ADD (22323585) E4010104/ADD (22323586) |  | 5727857 | 1500 | PVC ID : 5727857 VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64684 PE IP Address : 152.177.4.225 CE Address : 152.177.4.226 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22323586) | Ethernet |  |  |  |  | 05/26/2016 (CCP) (22323585) 05/26/2016 (CCP) (22323586) | 06/07/2016 (CCP) (22323585) 06/07/2016 (CCP) (22323586) |  |  | Andy Rodriguez 1-860-284-5278 arodriguez@prohealthmd.com | MOHAN BASNET | mohan_basnet@optum.com | 1-763-744-1971 | 06/15/2016(Private IP - PIP) 06/15/2016(Access) | 07/12/2016 |  | 06/28/2016 (22323585) 06/24/2016 (22323586) | 04/26/2016 | 06/15/2016 |  |  | N (22323585) N (22323586) | U0101953 |  |  | NSPE0010186355
Completed | ALH GA026 Atlanta | 3200 WINDY HILL RD SE ATLANTA, GA 30339-5640 US | 100 MBPS (22332844) | 05/05/2016: 5/5- Cable pull was completed yesterday 5/4. Circuit is pending local end testing. | 192978984 | ALH GA026 Atlanta | Private IP - PIP (22332843) Access (22332844) | 22332843 22332844 | 50 MBPS (22332843) |  | 108107787 (Private IP (PIP)) 108107785 (Access) | C1034104/ADD (22332843) E4010148/ADD (22332844) |  | 5728592 | 35000 | PVC ID : 5728592 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64698 PE IP Address : 68.139.74.165 CE Address : 68.139.74.166 QoS - Egress Profile: R12 |  | 1000Base-T (22332844) | Ethernet | [5 empty] | 04/14/2016 (CCP) (22332843) 04/14/2016 (CCP) (22332844) |  |  | Leigh Keller 1-770-767-4978 Leigh.Keller@Optum.com | SONJA MROCZYNSKI | sonja_d_mroczynski@optum.com | 1-763-553-4801 | 05/09/2016(Private IP - PIP) 05/09/2016(Access) |  |  | 04/18/2016 (22332843) 04/14/2016 (22332844) | 05/04/2016 | 05/09/2016 |  |  | N (22332843) N (22332844) | U0101953 |  |  | NSPE0010186496
Completed | WA057-05-IJ Tacoma | 3315 S 23RD ST STE 310 TACOMA, WA 98405-1617 US | 100 MBPS (22323743) | 09/08/2016: 9/8 resched Ivue 9/12 at 9pm CST | 192979045 | WA057-05-IJ Tacoma | Access (22323743) Private IP - PIP (22323742) | 22323743 22323742 | 10 MBPS (22323742) |  | 108331074 (Access) 108331077 (Private IP (PIP)) | E4010107/ADD (22323743) C1034034/ADD (22323742) | 04/KXGS/153687//PN (2232374314913701) | 5727874 | 4000 | PVC ID : 5727874 VPN Name : UnitedHealthGroup Router Name : HICGE02 VRF Name : V556790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65183 PE IP Address : 152.176.148.57 CE Address : 152.176.148.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22323743) | 1000Base-SX (850nm, Multi Mode Fiber) (22323743) | Ethernet | CENTURYLINK (2232374314913701) | 03/30/2016 (2232374314913701) | 08/04/2016 (2232374314913701) | 05/25/2016 (2232374314913701) | 08/11/2016 (VFORCE) (22323743) | 08/11/2016 (VFORCE) (22323743) | DEMARCADDR - NONE DEMARCDET - BASEMENT TELEPHONE ROOM, WALL MOUNTED, OPTICAL PORT 3, MULTIMODE |  | Janine Johnson 1-253-292-4202 janine.johnson@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 08/11/2016(Access) 08/11/2016(Private IP - PIP) | 09/15/2016 |  | 08/19/2016 (22323743) 08/23/2016 (22323742) | 08/19/2016 | 08/11/2016 |  |  | N (22323743) N (22323742) | U0101953 |  |  | NSPE0010186992
Completed | UFL73-07-IJ Jacksonville | 10151 DEERWOOD PARK BLVD STE 420 JACKSONVILLE, FL 32256-0566 US | 100 MBPS (22325472) | 11/10/2016: 11/10 Activation completed on 11/9 | 192986557 | UFL73-07-IJ Jacksonville | Private IP - PIP (22325471) Access (22325472) | 22325471 22325472 | 10 MBPS (22325471) |  | 108733108 (Private IP (PIP)) 108733106 (Access) | C1034041/ADD (22325471) E4010115/ADD (22325472) | BDFK6936 (2232547215014801) | 5727973 | 4000 | PVC ID : 5727973 VPN Name : UnitedHealthGroup Router Name : JAP3E02 VRF Name : V380184-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64742 PE IP Address : 152.183.87.193 CE Address : 152.183.87.194 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22325472) | 1000Base-SX (850nm, Multi Mode Fiber) (22325472) | Ethernet | LEVEL 3 (2232547215014801) | 05/04/2016 (2232547215014801) | 08/04/2016 (2232547215014801) | 07/29/2016 (2232547215014801) | 08/03/2016 (VFORCE) (22325472) | 08/10/2016 (VFORCE) (22325472) | DEMARCDET - 4th Floor,suite-420 ,customer server room, wall mounted port 9, tagged with ckt id. |  | Shalon Brooks 1-904-296-7893 shalon_brooks@uhc.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 08/10/2016(Private IP - PIP) 08/10/2016(Access) | 11/09/2016 |  | 08/15/2016 (22325471) 08/11/2016 (22325472) | 06/15/2016 | 08/10/2016 |  |  | N (22325471) N (22325472) | U0101953 |  |  | NSPE0010196147
Completed |  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBK9691) | 04/07/2016: 4/7- Ready for hotcut. Per Melissa, the cutovers will need to be scheduled once the access piece is ready. She is working on submitting the change orders. | 8703193 |  | Private IP Port Only (CQBK9691) | CQBK9691 | 7000 MBPS | P1957529 |  | BOBKWHD00001 (CQBK9691) |  | 5463422 5212868 | 0 | PVC ID : 5463422,5212868 VPN Name : UnitedHealthGroup-ECCMA Router Name : MZZ9E01 VRF Name : V600584:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : 152.161.80.1 CE Address : 152.161.80.2 QoS - Egress Profile: R12 | [11 empty] | STEVE BROWN 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 04/12/2016 (CQBK9691) |  |  | 04/26/2016 (CQBK9691) | 04/26/2016 (CQBK9691) |  |  |  | N (CQBK9691) | 05017789 |  |  | NSPE0010187687
|  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBK97CC) | 04/14/2016: 4/14- hotcut scheduled 4/19 10:30PM CST | 8703199 |  | Private IP Port Only (CQBK97CC) | CQBK97CC | 7000 MBPS 7000 MBPS (CQBK97CC) | P1932463 |  | BOBKTFPX0001 (CQBK97CC) |  | 5605731 5189840 5189860 5463424 | 360000 270000 314000 2688 1500000 | PVC ID : 5605731,5189840,5189860,5463424 VPN Name : UHG-ECC,UHG-UC,UHG-IPTF,UnitedHealthGroup-ECCMA,UnitedHealthGroup Router Name : MN39E01 VRF Name : V594781:UHGECC,V645094:UHGUC,V601668:UHGIPTF,V601670:UnitedHealthGroupECCMA,V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : v4-152.177.151.97,v6-199.220.202.221,v4-152.187.248.73,v6-68.136.152.241,v4-152.162.11.193 CE Address : v4-152.177.151.98,v6-199.220.202.222,v4-152.187.248.74,v6-68.136.152.242,v4-152.162.11.194 QoS - Egress Profile: R12 | [11 empty] | STEVE BROWN 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 04/19/2016 (CQBK97CC) |  |  | 04/26/2016 (CQBK97CC) | 04/26/2016 (CQBK97CC) |  |  |  | N (CQBK97CC) | 05017789 |  |  | NSPE0010187802
Completed | WV033-02-IJ Dunbar WV | 206 ROXALANA BUSINESS PARK DUNBAR, WV 25064-2727 US | 100 MBPS (22349998) | 05/12/2016: 5/12- circuit installed. Pending BEAS installation. | 192999705 | WV033-02-IJ Dunbar WV | Private IP - PIP (22349997) Access (22349998) | 22349997 22349998 | 10 MBPS (22349997) |  | 109450079 (Private IP (PIP)) 109450077 (Access) | C1034180/ADD (22349997) E4010207/ADD (22349998) | 50/KFGS/608380//FVNC/ (2234999812468001) | 5729750 | 1500 | PVC ID : 5729750 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64729 PE IP Address : 152.177.100.105 CE Address : 152.177.100.106 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22349998) | 1000Base-SX (850nm, Multi Mode Fiber) (22349998) | Ethernet | FRONTIER (2234999812468001) | 04/05/2016 (2234999812468001) | 05/02/2016 (2234999812468001) |  | 05/16/2016 (VFORCE) (22349998) | 05/16/2016 (VFORCE) (22349998) | DEMARCDET - 1st Floor Telco room, wall mount RAD NID, port 5 |  | DON TORMAN 1-304-553-6991 don.torman@briovarx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 05/16/2016(Private IP - PIP) 05/16/2016(Access) |  |  | 05/24/2016 (22349997) 05/20/2016 (22349998) | 06/24/2016 | 05/16/2016 |  |  | N (22349997) N (22349998) | U0101953 |  |  | NSPE0010207094
Completed | FL144-02-IJ Seffner FL Wellmed | 2204 S PARSONS AVE SEFFNER, FL 33584-5212 US | 100 MBPS (22412447) | 09/02/2016: 9/2 Tech already confirmed work already done via email | 193028829 | FL144-02-IJ Seffner, FL Wellmed | Private IP - PIP (22412446) Access (22412447) | 22412446 22412447 | 10 MBPS (22412446) |  | 109025888 (Private IP (PIP)) 109025886 (Access) | C1034726/ADD (22412446) E4010494/ADD (22412447) | 65/KEGS/854091//FTNC/ (2241244715054501) 65/KEGS/854091//FTNC/ (2241244715054503) | 5734241 | 3000 | PVC ID : 5734241 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64675 PE IP Address : 152.187.238.209 CE Address : 152.187.238.210 QoS - Egress Profile: R12 | 100Base-TX (22412447) | 100Base-TX (22412447) | Ethernet | FRONTIER (2241244715054501) FRONTIER (2241244715054503) | 04/19/2016 (2241244715054501) 08/05/2016 (2241244715054503) | 06/21/2016 (2241244715054501) 08/25/2016 (2241244715054503) |  | 09/01/2016 (VFORCE) (22412447) | 09/02/2016 (VFORCE) (22412447) | DEMARCDET - main bldg floor 1 telco room canoga perkins tagged with circuit id |  | Mike Nelson 1-207-877-7874 minelson@wellmed.net | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/02/2016(Private IP - PIP) 09/02/2016(Access) |  |  | 09/08/2016 (22412446) 09/06/2016 (22412447) | 08/05/2016 | 09/02/2016 |  |  | N (22412446) N (22412447) | U0101953 |  |  | NSPE0010233647
Completed | FL145-02-IJ Thonotosassa FL- Wellmed | 10616 MAIN ST THONOTOSASSA, FL 33592-2828 US | 100 MBPS (22406999) | 07/06/2016: 7/7- LEC corrected handoff. Beas install scheduled for 7/7. | 193029105 | FL145-02-IJ Thonotosassa, FL- Wellmed | Private IP - PIP (22406998) Access (22406999) | 22406998 22406999 | 10 MBPS (22406998) |  | 109025932 (Private IP (PIP)) 109025930 (Access) | C1034685/ADD (22406998) E4010463/ADD (22406999) | OR/KQE-/417530/BHNS (2240699915054501) | 5733946 | 3000 | PVC ID : 5733946 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64672 PE IP Address : 152.177.245.17 CE Address : 152.177.245.18 QoS - Egress Profile: R12 | 100Base-FX - MMF (22406999) | 100Base-FX (1310nm, Multi Mode Fiber) (22406999) | Ethernet | BRIGHT HOUSE (2240699915054501) | 04/18/2016 (2240699915054501) | 06/24/2016 (2240699915054501) | 06/24/2016 (2240699915054501) | 07/07/2016 (VFORCE) (22406999) | 07/08/2016 (VFORCE) (22406999) | DEMARCDET - DATA ROOM OF THE BREAK ROOM CISCO ASR 920 PORT 5 TAGGED CUSTOMERS NAME AND CIRCUIT ID OR/KQE-/417530/BHNS |  | Mike Nelson 1-207-877-7874 minelson@wellmed.net | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 07/11/2016(Private IP - PIP) 07/11/2016(Access) | 08/04/2016 |  | 07/15/2016 (22406998) 07/13/2016 (22406999) | 07/11/2016 | 07/11/2016 |  |  | N (22406998) N (22406999) | U0101953 |  |  | NSPE0010233647
Completed | FL062-04-IJ | 2020 FLAMINGO DR BARTOW, FL 33830-4262 US | 100 MBPS (22416602) | 11/03/2016: 11/3 Cust sayus ckt is up - activation from 10/13 unsuccessful cust needed someone at site to check connection. Cktis now BGP up- activation team is completing Ivue request now that ckt is up | 193029206 | FL062-04-IJ | Private IP - PIP (22416601) Access (22416602) | 22416601 22416602 | 20 MBPS (22416601) |  | 110016417 (Private IP (PIP)) 110016415 (Access) | C1035796/ADD (22416601) E4010626/ADD (22416602) | 65/KFGS/935383//FTNC/ (2241660215181501) | 5734520 | 1500 | PVC ID : 5734520 VPN Name : UnitedHealthGroup Router Name : TAMP3E02 VRF Name : V444060-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65019 PE IP Address : 152.183.36.213 CE Address : 152.183.36.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22416602) | 1000Base-SX (850nm, Multi Mode Fiber) (22416602) | Ethernet | FRONTIER (2241660215181501) | 05/12/2016 (2241660215181501) | 07/27/2016 (2241660215181501) |  | 07/20/2016 (VFORCE) (22416602) | 07/20/2016 (VFORCE) (22416602) | DEMARCDET - 1ST FLR, TELCO/DATA RM, WALL MTD |  | Darling St. Jean 1-863-533-4104 dstjean@wellmed.net | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 07/20/2016(Private IP - PIP) 07/20/2016(Access) | 11/03/2016 |  | 08/05/2016 (22416601) 08/03/2016 (22416602) | 05/31/2016 | 07/20/2016 |  |  | N (22416601) N (22416602) | U0101953 |  |  | NSPE0010234756
Completed | CT039-10-IJ UHG hartford | 185 ASYLUM ST HARTFORD, CT 06103-3408 US | 300 MBPS (22412522) | 11/16/2016: 11/15 Activation completed | 193029226 | CT039-10-IJ UHG hartford | Private IP - PIP (22412521) Access (22412522) | 22412521 22412522 | 300 MBPS (22412521) |  | 110016421 (Private IP (PIP)) 110016419 (Access) | C5001922/ADD (22412521) E5003424/ADD (22412522) |  | 5734264 | 90000 | PVC ID : 5734264 VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65153 PE IP Address : 68.138.155.77 CE Address : 68.138.155.78 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (22412522) | Ethernet |  |  |  |  | 06/03/2016 (CCP) (22412521) 06/03/2016 (CCP) (22412522) | 05/21/2016 (CCP) (22412521) 05/21/2016 (CCP) (22412522) | risor hand off in the basement--patched out fiber to there risor pos # 5 |  | Anthony Daley 1-860-702-5612 tony_daley@optum.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 06/16/2016(Private IP - PIP) 06/16/2016(Access) | 11/15/2016 |  | 07/05/2016 (22412521) 06/30/2016 (22412522) | 05/13/2016 | 06/16/2016 |  |  | N (22412521) N (22412522) | U0101953 |  |  | NSPE0010234756
Completed | CA129-02-IJ LA Catamaran | 1155 N MISSION RD LOS ANGELES, CA 90033-1040 US | 100 MBPS (22416710) | 07/14/2016: 7/14- Order on hold, waiting for customer to confirm demark. | 193030883 | CA129-02-IJ LA Catamaran | Access (22416710) Private IP - PIP (22416709) | 22416710 22416709 | 20 MBPS (22416709) |  | 111040785 (Access) 111040787 (Private IP (PIP)) | E4012179/ADD (22416710) C1037269/ADD (22416709) | 13/KRGN/587657//PT (2241671012617101) | 5734535 | 1500 | PVC ID : 5734535 VPN Name : UnitedHealthGroup Router Name : LSA29E01 VRF Name : V461763:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64802 PE IP Address : 152.177.41.237 CE Address : 152.177.41.238 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22416710) | 1000Base-SX (850nm, Multi Mode Fiber) (22416710) | Ethernet | ATT (2241671012617101) | 06/16/2016 (2241671012617101) | 07/08/2016 (2241671012617101) | 07/08/2016 (2241671012617101) | 07/15/2016 (VFORCE) (22416710) |  | DEMARCADDR - 1155 N MISSION RD LA DEMARCDET - H/O POS 5 AND 6 @ 1155-1.1 TGD FIBER MPOE ACC OFFICE MGR |  | David Border 1-905-876-4741 Dave@missionroadpharmacy.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 07/18/2016(Access) 07/18/2016(Private IP - PIP) | 08/11/2016 |  | 07/25/2016 (22416710) 07/27/2016 (22416709) | 07/19/2016 | 07/18/2016 |  |  | N (22416710) N (22416709) | U0101953 |  |  | NSPE0010240300
Completed | UNITED HEALTH GROUP | 9945 FEDERAL DR COLORADO SPRINGS, CO 80921-3617 US | 200 MBPS (22420770) | 07/13/2016: 7/13- Beas install scheduled for 7/13. | 193030921 | UNITED HEALTH GROUP | Private IP - PIP (22420769) Access (22420770) | 22420769 22420770 | 100 MBPS (22420769) |  | 111040783 (Private IP (PIP)) 111040781 (Access) | C5001929/ADD (22420769) E5003441/ADD (22420770) | 29/KXGS/157839//MS (2242077074246201) | 5734702 | 70000 | PVC ID : 5734702 VPN Name : UnitedHealthGroup Router Name : DNJXE01 VRF Name : V469377-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65040 PE IP Address : 68.137.207.113 CE Address : 68.137.207.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22420770) | 1000Base-SX (850nm, Multi Mode Fiber) (22420770) | Ethernet | CENTURYLINK (2242077074246201) | 04/20/2016 (2242077074246201) | 07/14/2016 (2242077074246201) | 06/28/2016 (2242077074246201) | 07/13/2016 (VFORCE) (22420770) | 07/13/2016 (VFORCE) (22420770) | DEMARCDET - TELCO ROOM 1ST FLOORWALL MT OPT OPT PORT 1 |  | Melody Spring 1-719-799-2305 melody_spring@uhc.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 07/14/2016(Private IP - PIP) 07/14/2016(Access) | 09/07/2016 |  | 07/25/2016 (22420769) 07/21/2016 (22420770) | 05/31/2016 | 07/14/2016 |  |  | N (22420769) N (22420770) | U0101953 |  |  | NSPE0010240300
Completed | ULA06-05-IJ Baton Route LA | 8550 UNITED PLAZA BLVD STE 703 BATON ROUGE, LA 70809-0200 US | 50 MBPS (22416884) | 11/16/2016: 11/15 Activation completed | 193030906 | ULA06-05-IJ Baton Route, LA | Private IP - PIP (22416883) Access (22416884) | 22416883 22416884 | 20 MBPS (22416883) |  | 111429597 (Private IP (PIP)) 111429595 (Access) | C4003768/ADD (22416883) E4010517/ADD (22416884) | BDFF0706 (2241688415371601) | 5734540 | 5000 | PVC ID : 5734540 VPN Name : UnitedHealthGroup Router Name : HSJ9E04 VRF Name : V622583:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64712 PE IP Address : 68.139.127.73 CE Address : 68.139.127.74 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22416884) | 1000Base-SX (850nm, Multi Mode Fiber) (22416884) | Ethernet | LEVEL 3 (2241688415371601) | 05/18/2016 (2241688415371601) | 06/21/2016 (2241688415371601) | 08/10/2016 (2241688415371601) | 08/12/2016 (VFORCE) (22416884) | 08/12/2016 (VFORCE) (22416884) | DEMARCDET - The MDF room is on the 7th floor. It is inside our Suite. Suite # 703. |  | Eric Singleton 1-225-237-2038 eric.singleton@optumhealth.com | PRADEEP YADA | pradeep_yadav@optum.com | 91-981-005-9326 | 08/12/2016(Private IP - PIP) 08/12/2016(Access) | 11/15/2016 |  | 08/19/2016 (22416883) 08/17/2016 (22416884) | 08/17/2016 | 08/12/2016 |  |  | N (22416883) N (22416884) | U0101953 |  |  | NSPE0010244915
Completed | UHG Macon GA | 115 ARKWRIGHT LNDG MACON, GA 31210-1364 US | 50 MBPS (22417468) | 10/07/2016: 10/7 Activation sched 10/11 10:30pm CST customer bridge direct USA number 763-957-6301 //Tech can also call webex meeting by dialing Philippines: 63-2-58-84771 // India, Bangalore: 91-80-4920-3693 //India, Gurgaon: 91-12-4382-0499 // India, Hyderabad: 91-40-3083-7963 | 193030922 | UHG Macon GA | Private IP - PIP (22417467) Access (22417468) | 22417467 22417468 | 10 MBPS (22417467) |  | 111429601 (Private IP (PIP)) 111429599 (Access) | C4003771/ADD (22417467) E4010525/ADD (22417468) | 17.KFGX.000085..COXC. (2241746814486401) | 5734572 | 3000 | PVC ID : 5734572 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65297 PE IP Address : 68.137.64.69 CE Address : 68.137.64.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22417468) | 1000Base-SX (850nm, Multi Mode Fiber) (22417468) | Ethernet | COX (2241746814486401) | 04/19/2016 (2241746814486401) | 06/23/2016 (2241746814486401) |  | 06/21/2016 (VFORCE) (22417468) | 06/21/2016 (VFORCE) (22417468) | DEMARCDET - 1st Floor, telco room, closet in the center of the bldg, SFPA on accedian metro nid- MMF |  | Carol Soles 1-478-321-9070 carol_soles@optum.com | PRADEEP YADv | pradeep_yadav@optum.com | 91-981-005-9326 | 06/21/2016(Private IP - PIP) 06/21/2016(Access) | 10/11/2016 |  | 07/05/2016 (22417467) 06/30/2016 (22417468) | 05/31/2016 | 06/21/2016 |  |  | N (22417467) N (22417468) | U0101953 |  |  | NSPE0010244915
Completed | UNITED HEALTHCARE | 3838 N CAUSEWAY BLVD METAIRIE, LA 70002-8194 US | 100 MBPS (22418091) | 08/18/2017: 08/18 Successfully activated | 193030923 | UNITED HEALTHCARE | Private IP - PIP (22418090) Access (22418091) | 22418090 22418091 | 30 MBPS (22418090) |  | 111429605 (Private IP (PIP)) 111429603 (Access) | C1034778/ADD (22418090) E4010529/ADD (22418091) | BDFF0028 (2241809174246001) | 5734604 | 15000 | PVC ID : 5734604 VPN Name : UnitedHealthGroup Router Name : HSJ9E04 VRF Name : V622583:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64582 PE IP Address : 152.181.168.101 CE Address : 152.181.168.102 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22418091) | 1000Base-SX (850nm, Multi Mode Fiber) (22418091) | Ethernet | LEVEL 3 (2241809174246001) | 05/02/2016 (2241809174246001) | 06/14/2016 (2241809174246001) | 06/15/2016 (2241809174246001) | 06/29/2016 (VFORCE) (22418091) | 06/29/2016 (VFORCE) (22418091) | DEMARCDET - eubfdp.026.2600.w01.001.25. that is port 1 and 2 Flr 26. |  | Solange Cook 1-504-849-1603 ayn_cook@uhc.com | PRADEEP YADA | pradeep_yadav@optum.com | 91-981-005-9326 | 06/29/2016(Private IP - PIP) 06/29/2016(Access) | 08/17/2017 |  | 07/15/2016 (22418090) 07/13/2016 (22418091) | 07/13/2016 | 06/29/2016 |  |  | N (22418090) N (22418091) | U0101953 |  |  | NSPE0010244915
Completed | IA707-02-IJ Catamaran Cedar Rapids | 5070 ROCKWELL DR NE CEDAR RAPIDS, IA 52402-2003 US | 10 MBPS (22421122) | 10/24/2016: 10/24 Activation completed 10/21 | 193037908 | IA707-02-IJ Catamaran Cedar Rapids | Private IP - PIP (22421121) Access (22421122) | 22421121 22421122 | 10 MBPS (22421121) |  | 111933348 (Private IP (PIP)) 111933345 (Access) | C0081111/ADD (22421121) E3022937/ADD (22421122) | 01/KXGS/157880//NW (2242112215441601) | 5734749 | 1500 | PVC ID : 5734749 VPN Name : UnitedHealthGroup Router Name : PLSHXE01 VRF Name : V588242-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64677 PE IP Address : 152.181.168.237 CE Address : 152.181.168.238 QoS - Egress Profile: R12 | 100Base-TX (22421122) | 100Base-TX (22421122) | Ethernet | CENTURYLINK (2242112215441601) | 04/20/2016 (2242112215441601) | 05/20/2016 (2242112215441601) | 05/23/2016 (2242112215441601) | 06/09/2016 (VFORCE) (22421122) | 06/09/2016 (VFORCE) (22421122) | DEMARCADDR - X DEMARCDET - 5070 ROCKWELL DR NE 1 CEDAR RAPIDS IA |  | Darwin Carstensen 1-319-377-5497 Darwin.Carstensen@catamaranRx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 06/09/2016(Private IP - PIP) 06/09/2016(Access) | 10/21/2016 |  | 06/17/2016 (22421121) 06/15/2016 (22421122) | 06/13/2016 | 06/09/2016 |  |  | N (22421121) N (22421122) | U0101953 |  |  | NSPE0010249784
Completed | UMA07-07-IJ Waltham MA | 950 WINTER ST STE 2200 WALTHAM, MA 02451-1404 US | 100 MBPS (22421112) | 10/05/2016: 10/5 Activation sched 10/6 1pm CST | 193037938 | UMA07-07-IJ Waltham MA | Private IP - PIP (22421111) Access (22421112) | 22421111 22421112 | 50 MBPS (22421111) |  | 111933342 (Private IP (PIP)) 111933340 (Access) | C1034797/ADD (22421111) E4010560/ADD (22421112) | 15852-ET-BSTPMALL-BSTPMALL (2242111215441601) | 5734744 | 4000 | PVC ID : 5734744 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64930 PE IP Address : 199.220.225.157 CE Address : 199.220.225.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22421112) | 1000Base-SX (850nm, Multi Mode Fiber) (22421112) | Ethernet | LIGHT TOWER (2242111215441601) | 04/20/2016 (2242111215441601) | 09/30/2016 (2242111215441601) | 09/22/2016 (2242111215441601) | 09/29/2016 (VFORCE) (22421112) | 09/29/2016 (VFORCE) (22421112) | DEMARCDET - MDF Room 3rd floor Wall Mount WLHMMAABMC2 Port 5 |  | Karen McMullen 1-781-472-8464 karen.mcmullen@optum.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 09/29/2016(Private IP - PIP) 09/29/2016(Access) |  |  | 10/11/2016 (22421111) 10/07/2016 (22421112) | 10/10/2016 | 09/29/2016 |  |  | N (22421111) N (22421112) | U0101953 | Jeopardy Notification 1 (08/22/2016) |  | NSPE0010249784
Completed | WV040-02-IJ Charleston | 700 WASHINGTON ST E CHARLESTON, WV 25301-1657 US | 50 MBPS (22421130) | 06/16/2016: 6/16- Beas install scheduled for 6/17. | 193039915 | WV040-02-IJ Charleston | Private IP - PIP (22421129) Access (22421130) | 22421129 22421130 | 10 MBPS (22421129) |  | 112098130 (Private IP (PIP)) 112098108 (Access) | C4003786/ADD (22421129) E4010561/ADD (22421130) | 50/KEGS/858465//FVNC/ (2242113015185901) | 5734751 | 1500 | PVC ID : 5734751 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64670 PE IP Address : 152.181.221.193 CE Address : 152.181.221.194 QoS - Egress Profile: R12 | 100Base-TX (22421130) | 100Base-FX (1310nm, Multi Mode Fiber) (22421130) | Ethernet | FRONTIER (2242113015185901) | 04/21/2016 (2242113015185901) | 05/19/2016 (2242113015185901) |  | 06/17/2016 (VFORCE) (22421130) | 06/21/2016 (VFORCE) (22421130) | DEMARCDET - SLNA#SHLF#PRTPORT 4#PHYLUALL mount telco room at the bottom of the NE stairwell#JKR45#EXT#EAGY |  | Martin Riggs 1-304-389-4994 w.martin.riggs@gmail.com | Javier Segui | javier.segui@optum.com | 1-407-541-8143 | 06/21/2016(Private IP - PIP) 06/21/2016(Access) |  |  | 06/29/2016 (22421129) 06/27/2016 (22421130) | 06/27/2016 | 06/21/2016 |  |  | N (22421129) N (22421130) | U0101953 |  |  | NSPE0010254034
Completed | OH029-02-IJ | 400 E BUSINESS WAY STE 100 SHARONVILLE, OH 45241-2399 US | 100 MBPS (22441050) | 10/28/2016: 10/28 Activation completed 10/27 | 193045036 | OH029-02-IJ | Private IP - PIP (22441049) Access (22441050) | 22441049 22441050 | 50 MBPS (22441049) |  | 112419372 (Private IP (PIP)) 112419370 (Access) | C1034963/ADD (22441049) E4010672/ADD (22441050) | /KRGS/550103//CB (2244105015506501) | 5736219 | 15000 | PVC ID : 5736219 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64665 PE IP Address : 152.181.208.53 CE Address : 152.181.208.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22441050) | 1000Base-SX (850nm, Multi Mode Fiber) (22441050) | Ethernet | CINCINNATTI BELL (2244105015506501) | 08/09/2016 (2244105015506501) | 08/31/2016 (2244105015506501) | 09/16/2016 (2244105015506501) | 09/22/2016 (VFORCE) (22441050) | 09/22/2016 (VFORCE) (22441050) | Demarc provided : SECOND FLOOR NETWORK ROOM WALL MOUNTED ALCATEL 7210 PORT 6 TAGGED WITH CIRCUIT ID |  | ART CALAMARI 1-513-608-2222 acregold@hotmail.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 09/22/2016(Private IP - PIP) 09/22/2016(Access) | 10/27/2016 |  | 10/05/2016 (22441049) 10/03/2016 (22441050) | 10/03/2016 | 09/22/2016 |  |  | N (22441049) N (22441050) | U0101953 |  |  | NSPE0010259448
Completed | TN041-07-IJ Franklin TN | 1021 WINDCROSS CT FRANKLIN, TN 37067-2678 US | 500 MBPS (22442339) | 05/27/2016: 5/26- Order is pending BEAS installation. Order placed on hold as LCON is unreachable. | 193045061 | TN041-07-IJ Franklin, TN | Private IP - PIP (22442338) Access (22442339) | 22442338 22442339 | 200 MBPS (22442338) |  | 112419376 (Private IP (PIP)) 112419374 (Access) | C5001955/ADD (22442338) E5003486/ADD (22442339) | T4/KRGN/822564//SC (2244233915506501) | 5736313 | 25000 | PVC ID : 5736313 VPN Name : UnitedHealthGroup Router Name : NSVLXE01 VRF Name : Vj39243-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65173 PE IP Address : 199.220.188.165 CE Address : 199.220.188.166 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22442339) | 1000Base-LX (1310nm Single Mode Fiber) (22442339) | Ethernet | ATT (2244233915506501) | 04/25/2016 (2244233915506501) | 05/16/2016 (2244233915506501) | 05/12/2016 (2244233915506501) | 06/01/2016 (VFORCE) (22442339) |  | DEMARCADDR - 1021 WINDCROSS CT FRANKLIN TN DEMARCDET - 1ST FL TELCO ROOM |  | Michael Ciccarelli 1-615-503-1435 Michael.Ciccarelli@optum.com | HUMAYUN RAFI | humayun_rafi@optum.com | 91-990-002-2170 | 06/01/2016(Private IP - PIP) 06/01/2016(Access) | 09/22/2016 |  | 06/14/2016 (22442338) 06/10/2016 (22442339) | 06/10/2016 | 06/01/2016 |  |  | N (22442338) N (22442339) | U0101953 |  |  | NSPE0010259448
Completed |  | 720 E THUNDERBIRD RD PHOENIX, AZ 85022 USA | 1.536 MBPS (IQBLBJNJ) | 06/30/2016: 6/29- FOC date for remaining circuits, 7/6. | 8718914 |  | Private IP (IQBLBJNJ) EVC/PVC Service (N.11046837.5737020) | IQBLBJNJ N.11046837.5737020 | 12.288 MBPS | P2139257 |  | BCBK9R3F0001 (IQBLBJNJ) BCBK9R3F0002 (IQBLBJNJ) BCBK9R3F0003 (IQBLBJNJ) BCBK9R3F0004 (IQBLBJNJ) BCBK9R3F0005 (IQBLBJNJ) BCBK9R3F0006 (IQBLBJNJ) BCBK9R3F0007 (IQBLBJNJ) BCBK9R3F0008 (IQBLBJNJ) | 14/HCGS/456145//MS (IQBLBJNJ29YVMB01) | 5737020 | 1512 | VPN Name : UnitedHealthGroup Router Name : WIT9E01 VRF Name : V603341:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64667 PE IP Address : 68.136.187.173 CE Address : 68.136.187.174 QoS - Egress Profile: R12 PVC ID : 5737020 |  |  |  | USWEST - WY, CO CENTURYLINK (IQBLBJNJ29YVMB01) | 06/22/2016 (IQBLBJNJ29YVMB01) | 07/06/2016 (IQBLBJNJ29YVMB01) | 06/30/2016 (IQBLBJNJ29YVMB01) |  |  | DEMARC LOC: 1st FLR MAIN ELECTRICAL ROOM SHELF 3 SLOT 8 OF 14 TAGGED NO EXT DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: RJ48C DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes |  | JENNIFER WILLIAMS 0016237070050 JENNIFER.A.WILLIAMS@OPTUM.COM |  |  |  | 06/30/2016 (IQBLBJNJ) |  |  | 07/13/2016 (IQBLBJNJ) | 06/30/2016 (IQBLBJNJ) |  |  |  | N (IQBLBJNJ) N (N.11046837.5737020) | 05017789 P2139257 |  |  | NSPE0010264981
Completed | UFL68-07-IJ Oldsmar FL | 601 BROOKER CREEK BLVD OLDSMAR, FL 34677-2962 US | 200 MBPS (22540658) | 02/07/2017: 01/24 Activation scheduled 02/08 8PM CST | 193088317 | UFL68-07-IJ Oldsmar, FL | Private IP - PIP (22540657) Access (22540658) | 22540657 22540658 | 150 MBPS (22540657) |  | 113955640 (Private IP (PIP)) 113955638 (Access) | C5002019/ADD (22540657) E5003619/ADD (22540658) | 65/KFGS/945553//FTNC/ (2254065820616601) | 5743835 | 30000 | PVC ID : 5743835 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64615 PE IP Address : 152.181.76.153 CE Address : 152.181.76.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22540658) | 1000Base-SX (850nm, Multi Mode Fiber) (22540658) | Ethernet | FRONTIER (2254065820616601) | 09/16/2016 (2254065820616601) | 10/17/2016 (2254065820616601) | 09/21/2016 (2254065820616601) | 10/04/2016 (VFORCE) (22540658) | 10/04/2016 (VFORCE) (22540658) | DEMARCDET - 1st floor, data room, verizon-02 MP-35, tagged with ckt |  | Rick Baruta 1-813-818-5510 rick_baruta@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 10/06/2016(Private IP - PIP) 10/06/2016(Access) | 02/08/2017 |  | 11/01/2016 (22540657) 10/28/2016 (22540658) | 10/28/2016 | 10/06/2016 |  |  | N (22540657) N (22540658) | U0101953 |  |  | NSPE0010294290
Completed | AR001-05-IJ Little Rock | 1401 W CAPITOL AVE STE 375 LITTLE ROCK, AR 72201-2994 US | 50 MBPS (22541026) | 03/07/2017: 03/06 Activation successfully completed | 193088319 | AR001-05-IJ Little Rock | Private IP - PIP (22541025) Access (22541026) | 22541025 22541026 | 10 MBPS (22541025) |  | 113955636 (Private IP (PIP)) 113955634 (Access) | C4004073/ADD (22541025) E4011383/ADD (22541026) | 4U/KFFN/002195/LVLC (2254102615744701) | 5743930 | 4000 | PVC ID : 5743930 VPN Name : UnitedHealthGroup Router Name : PLVXE01 VRF Name : V669152-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64718 PE IP Address : 68.136.229.33 CE Address : 68.136.229.34 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22541026) | 1000Base-SX (850nm, Multi Mode Fiber) (22541026) | Ethernet | LEVEL 3 (2254102615744701) | 05/24/2016 (2254102615744701) | 07/15/2016 (2254102615744701) | 08/03/2016 (2254102615744701) | 08/12/2016 (VFORCE) (22541026) | 08/12/2016 (VFORCE) (22541026) | DEMARCDET - 3rd floor, customer ste 375, server room, rack 3, rmu 45, FDP positions 1/2, SMF, LC connector, tagged w/CID |  | Steve Love 1-501-660-1172 steve_love@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/15/2016(Private IP - PIP) 08/15/2016(Access) | 03/06/2017 |  | 08/23/2016 (22541025) 08/19/2016 (22541026) | 08/19/2016 | 08/15/2016 |  |  | N (22541025) N (22541026) | U0101953 |  |  | NSPE0010294290
Completed | UNITED HEALTH GROUP | 205 E WATERTOWER ST MERIDIAN, ID 83642-6282 US | 50 MBPS (22626857) | 10/28/2016: 10/28 activation completed 10/27 | 193088318 | UNITED HEALTH GROUP | Private IP - PIP (22626856) Access (22626857) | 22626856 22626857 | 20 MBPS (22626856) |  | 113955644 (Private IP (PIP)) 113955642 (Access) | C4004220/ADD (22626856) E4011767/ADD (22626857) | 39/KXGS/165780//MS (2262685774246301) | 5751121 | 5500 | PVC ID : 5751121 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65285 PE IP Address : 152.164.181.89 CE Address : 152.164.181.90 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22626857) | 1000Base-SX (850nm, Multi Mode Fiber) (22626857) | Ethernet | CENTURYLINK (2262685774246301) | 06/27/2016 (2262685774246301) | 08/04/2016 (2262685774246301) | 08/03/2016 (2262685774246301) | 10/05/2016 (VFORCE) (22626857) | 10/05/2016 (VFORCE) (22626857) | DEMARCDET - 1ST FLOOR EQUIPMENT ROOM EAST WALL OPTICAL CIENNA 3916 PORT 4 TAGGED WITH CIRCUIT ID |  | Ione Coleman 1-208-914-2217 ione.coleman@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 10/05/2016(Private IP - PIP) 10/05/2016(Access) | 10/27/2016 |  | 10/10/2016 (22626856) 10/06/2016 (22626857) | 10/03/2016 | 10/05/2016 |  |  | N (22626856) N (22626857) | U0101953 |  |  | NSPE0010294290
Completed | IL059-05-IJ Rockford IL | 973 FEATHERSTONE RD STE 200 ROCKFORD, IL 61107-5911 US | 100 MBPS (22565138) | 11/03/2016: 11/3 Activatioon completed | 193084537 | IL059-05-IJ Rockford IL | Private IP - PIP (22565137) Access (22565138) | 22565137 22565138 | 50 MBPS (22565137) |  | 114623154 (Private IP (PIP)) 114623152 (Access) | C1036165/ADD (22565137) E4011408/ADD (22565138) | /KRGN/113726//LB (2256513815844401) | 5745959 | 10000 | PVC ID : 5745959 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65278 PE IP Address : 147.225.169.5 CE Address : 147.225.169.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22565138) | 1000Base-SX (850nm, Multi Mode Fiber) (22565138) | Ethernet | ATT (2256513815844401) | 05/23/2016 (2256513815844401) | 06/08/2016 (2256513815844401) | 06/08/2016 (2256513815844401) | 07/12/2016 (VFORCE) (22565138) | 07/12/2016 (VFORCE) (22565138) | DEMARCADDR - 973 FEATHERSTONE RD RCFR IL DEMARCDET - 1ST FLR PHONE RM WALL MOUNT HANDOFF PANEL POSITION 3 UNI PORT 6 |  | Brian McGivney 1-815-721-8372 brian.mcgivney@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 07/12/2016(Private IP - PIP) 07/12/2016(Access) | 11/02/2016 |  | 07/26/2016 (22565137) 07/22/2016 (22565138) | 07/22/2016 | 07/12/2016 |  |  | N (22565137) N (22565138) | U0101953 |  |  | NSPE0010294268
Completed | KY001-05-IJ Lexington KY | 333 W VINE ST LEXINGTON, KY 40507-1622 US | 100 MBPS (22553114) | 11/11/2016: 11/11 Activation completed on 11/10 | 193084562 | KY001-05-IJ Lexington, KY | Access (22553114) Private IP - PIP (22553113) | 22553114 22553113 | 50 MBPS (22553113) |  | 114623156 (Access) 114623158 (Private IP (PIP)) | E4011274/ADD (22553114) C1035998/ADD (22553113) | BDFQ1060 (2255311415844401) | 5744754 | 13000 | PVC ID : 5744754 VPN Name : UnitedHealthGroup Router Name : NSVLXE01 VRF Name : Vj39243-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65280 PE IP Address : 68.139.176.25 CE Address : 68.139.176.26 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22553114) | 1000Base-SX (850nm, Multi Mode Fiber) (22553114) | Ethernet | LEVEL 3 (2255311415844401) | 05/18/2016 (2255311415844401) | 07/13/2016 (2255311415844401) | 08/19/2016 (2255311415844401) | 09/02/2016 (VFORCE) (22553114) | 09/02/2016 (VFORCE) (22553114) | DEMARCDET - 5th floor, Server Room, Rack 2, Shelf 4, ADVA TID ED002 Access Port 5, SMF LC tagged with CID |  | Ike Norris 1-859-226-1792 ike_norris@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/02/2016(Access) 09/02/2016(Private IP - PIP) | 11/10/2016 |  | 09/09/2016 (22553114) 09/13/2016 (22553113) | 09/09/2016 | 09/02/2016 |  |  | N (22553114) N (22553113) | U0101953 | Jeopardy Notification 1 (08/24/2016) |  | NSPE0010294268
Completed | M0015-05-IJ Schaumburg IL | 1900 E GOLF RD SCHAUMBURG, IL 60173-5834 US | 100 MBPS (22652872) | 04/04/2017: 04/03 Successfully activated | 193084563 | M0015-05-IJ Schaumburg, IL | Private IP - PIP (22652871) Access (22652872) | 22652871 22652872 | 50 MBPS (22652871) |  | 114623150 (Private IP (PIP)) 114623048 (Access) | C1036945/ADD (22652871) E4011996/ADD (22652872) |  | 5753487 | 10000 | PVC ID : 5753487 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64579 PE IP Address : 152.164.178.165 CE Address : 152.164.178.166 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22652872) | Ethernet | [5 empty] | 06/24/2016 (CCP) (22652871) 06/24/2016 (CCP) (22652872) | 6th floor pop tech ran multimode fiber from the Overture, 1.3.9:0.2 the fiber patch port 1/2, labeled with ckt id. Then went to the 2nd floor and requested access to the server room at MDF Rm 219. Saw the extended demark at cabinet 1. Provided a hardloop at port 1/2. Tyler asked tech to leave the hardloop. Labeled the panel with ckt id. |  | Susan Dickinson 1-847-585-4873 susan.dickinson@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/15/2016(Private IP - PIP) 08/15/2016(Access) | 04/03/2017 |  | 08/17/2016 (22652871) 08/15/2016 (22652872) | 09/02/2016 | 08/15/2016 |  |  | N (22652871) N (22652872) | U0101953 |  |  | NSPE0010294268
|  |  |  | 06/26/2016: 6/26- Hotcut complete, customer accepted circuit. | 8740281 |  | EVC/PVC Service (C.11097895.5309077) | C.11097895.5309077 | [5 empty] | 5309077 |  | PVC ID : 5309077 | [11 empty] | LEIGH KELLER 4044063919 LEIGH.KELLER@OPTUM.COM | [11 empty] | N (C.11097895.5309077) | 0CV3F3 |  |  | NSPE0010287138
Completed | MI041-05-IJ Lansing Michigan | 822 CENTENNIAL WAY LANSING, MI 48917-8254 US | 50 MBPS (22626751) | 02/14/2017: 02/06 Successfully activated. Circuit accepted by john_raymundo@optum.com | 193111541 | MI041-05-IJ Lansing Michigan | Private IP - PIP (22626750) Access (22626751) | 22626750 22626751 | 10 MBPS (22626750) |  | 115121202 (Private IP (PIP)) 115121200 (Access) | C4004288/ADD (22626750) E4011983/ADD (22626751) | /KRGN/209231//MB (2262675176502601) | 5751116 | 25000 | PVC ID : 5751116 VPN Name : UnitedHealthGroup Router Name : BDGGE05 VRF Name : V505882:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65258 PE IP Address : 147.225.30.41 CE Address : 147.225.30.42 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22626751) | 1000Base-SX (850nm, Multi Mode Fiber) (22626751) | Ethernet | ATT (2262675176502601) | 07/08/2016 (2262675176502601) | 07/22/2016 (2262675176502601) | 08/02/2016 (2262675176502601) | 08/05/2016 (VFORCE) (22626751) | 08/05/2016 (VFORCE) (22626751) | DEMARCADDR - 822 CENTENNIAL WAY LANSING MI DEMARCDET - EAST EXT LWER LEVL WALL CABINET HANDOFF PORT 1 |  | ANGELA SORRELLS 1-517-993-0918 angela.sorrells@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/05/2016(Private IP - PIP) 08/05/2016(Access) | 02/06/2017 |  | 08/22/2016 (22626750) 08/18/2016 (22626751) | 08/18/2016 | 08/05/2016 |  |  | N (22626750) N (22626751) | U0101953 |  |  | NSPE0010301088
Completed | KY002-05-IJ Lexington KY | 230 LEXINGTON GREEN CIR STE 400 LEXINGTON, KY 40503-3337 US | 50 MBPS (22626794) | 11/03/2016: 11/3 Activation completed 11/2 | 193111542 | KY002-05-IJ Lexington, KY | Private IP - PIP (22626793) Access (22626794) | 22626793 22626794 | 10 MBPS (22626793) |  | 115152614 (Private IP (PIP)) 115152612 (Access) | C4004282/ADD (22626793) E4011970/ADD (22626794) | 85.L1XX.001062..TWCC (2262679415924201) | 5751119 | 4000 | PVC ID : 5751119 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65050 PE IP Address : 199.220.107.77 CE Address : 199.220.107.78 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22626794) | 1000Base-SX (850nm, Multi Mode Fiber) (22626794) | Ethernet | TIME WARNER CABLE (2262679415924201) | 06/10/2016 (2262679415924201) | 08/15/2016 (2262679415924201) | 08/02/2016 (2262679415924201) | 08/05/2016 (VFORCE) (22626794) | 08/05/2016 (VFORCE) (22626794) | DEMARCDET - BLDG MAIN FLR MAIN FLOOR SUIT MPOE |  | Vicki Peavler 1-859-825-6151 vicki_peavler@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/05/2016(Private IP - PIP) 08/05/2016(Access) | 11/02/2016 |  | 08/24/2016 (22626793) 08/22/2016 (22626794) | 07/15/2016 | 08/05/2016 |  |  | N (22626793) N (22626794) | U0101953 |  |  | NSPE0010301088
Completed | UVA01-05-IJ Richmond | 9020 STONY POINT PKWY RICHMOND, VA 23235-1947 US | 100 MBPS (22599741) | 04/05/2017: 04/04 Successfully activated | 193125134 | UVA01-05-IJ Richmond | Private IP - PIP (22599740) Access (22599741) | 22599740 22599741 | 10 MBPS (22599740) |  | 115870299 (Private IP (PIP)) 115870297 (Access) | C1036352/ADD (22599740) E4011547/ADD (22599741) | 10/ETTA/616481/1 /CFW / (2259974116049301) | 5748573 | 25000 | PVC ID : 5748573 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64623 PE IP Address : 152.161.56.21 CE Address : 152.161.56.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22599741) | 1000Base-SX (850nm, Multi Mode Fiber) (22599741) | Ethernet | LUMOS (2259974116049301) | 12/09/2016 (2259974116049301) | 11/08/2016 (2259974116049301) | 12/16/2016 (2259974116049301) | 12/20/2016 (VFORCE) (22599741) | 12/22/2016 (VFORCE) (22599741) | DEMARCDET - 4TH FLR, RM 405, CONNECTED TO A LIGHT WAVE PORTS 1 AND 2 CIENA 3930 PORT 1 |  | Jaki Davis-Carter 1-804-267-5217 jaki_daviscarter@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 12/22/2016(Private IP - PIP) 12/22/2016(Access) | 04/04/2017 |  | 12/28/2016 (22599740) 12/23/2016 (22599741) | 01/20/2017 | 12/22/2016 |  |  | N (22599740) N (22599741) | U0101953 | Jeopardy Notification 2 (11/11/2016) |  | NSPE0010322068
Completed | TN035-05-IJ Memphis | 3175 LENOX PARK BLVD STE 400 MEMPHIS, TN 38115-4438 US | 50 MBPS (22599836) | 04/20/2017: 04/19 Successfully activated. | 193125147 | TN035-05-IJ Memphis | Private IP - PIP (22599835) Access (22599836) | 22599835 22599836 | 10 MBPS (22599835) |  | 115870303 (Private IP (PIP)) 115870301 (Access) | C4004133/ADD (22599835) E4011549/ADD (22599836) | ETYX/134826//ZYO (2259983616049301) | 5748582 | 4000 | PVC ID : 5748582 VPN Name : UnitedHealthGroup Router Name : CPZ3E02 VRF Name : V450868-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65236 PE IP Address : 152.181.219.129 CE Address : 152.181.219.130 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22599836) | 1000Base-SX (850nm, Multi Mode Fiber) (22599836) | Ethernet | ZAYO (2259983616049301) | 06/17/2016 (2259983616049301) | 10/12/2016 (2259983616049301) | 10/21/2016 (2259983616049301) | 11/04/2016 (VFORCE) (22599836) | 10/26/2016 (VFORCE) (22599836) | DEMARCDET - Fl-4/Rm-Telco RR: Wallmount Shelf/MP: Zayo Ports: 1-2, tagged and Labeled |  | Katherine Veazey 1-901-248-0439 Katherine_Veazey@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 11/09/2016(Private IP - PIP) 11/09/2016(Access) | 04/19/2017 |  | 11/17/2016 (22599835) 11/15/2016 (22599836) | 11/14/2016 | 11/09/2016 |  |  | N (22599835) N (22599836) | U0101953 |  |  | NSPE0010322068
Completed | KS706-02-IJ | 10605 W 84TH TER OVERLAND PARK, KS 66214-1627 US | 1 GBPS (22599881) | 06/26/2016: 6/26- End to end testing scheduled 6/27. | 193125156 | KS706-02-IJ | Private IP - PIP (22599880) Access (22599881) | 22599880 22599881 | 500 MBPS (22599880) |  | 115331584 (Private IP (PIP)) 115331582 (Access) | C0083732/ADD (22599880) E5003716/ADD (22599881) |  | 5748584 | 25000 | PVC ID : 5748584 VPN Name : UnitedHealthGroup Router Name : IDCGE01 VRF Name : V613653:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65115 PE IP Address : 152.187.32.9 CE Address : 152.187.32.10 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22599881) | Ethernet | [5 empty] | 06/17/2016 (CCP) (22599880) 06/17/2016 (CCP) (22599881) |  |  | Scott Williams 1-913-747-3785 swilliams@axelacare.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 06/27/2016(Private IP - PIP) 06/27/2016(Access) | 08/10/2016 |  | 06/28/2016 (22599880) 06/24/2016 (22599881) | 06/24/2016 | 06/27/2016 |  |  | N (22599880) N (22599881) | U0101953 |  |  | NSPE0010322105
Completed | UNITED HEALTH GROUP | 107 WESTPARK BLVD COLUMBIA, SC 29210-3871 US | 50 MBPS (22600131) | 03/21/2017: 03/20 Successfully activated | 193125133 | UNITED HEALTH GROUP | Private IP - PIP (22600130) Access (22600131) | 22600130 22600131 | 10 MBPS (22600130) |  | 115908983 (Private IP (PIP)) 115908981 (Access) | C4004136/ADD (22600130) E4011556/ADD (22600131) | 34/KRGN/400994//SB (2260013174246301) | 5748602 | 4000 | PVC ID : 5748602 VPN Name : UnitedHealthGroup Router Name : RLGH9E01 VRF Name : V477622:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64575 PE IP Address : 68.139.109.141 CE Address : 68.139.109.142 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22600131) | 1000Base-SX (850nm, Multi Mode Fiber) (22600131) | Ethernet | ATT (2260013174246301) | 05/27/2016 (2260013174246301) | 06/16/2016 (2260013174246301) | 08/08/2016 (2260013174246301) | 09/29/2016 (VFORCE) (22600131) | 09/29/2016 (VFORCE) (22600131) | DEMARCDET - Ciena3930 port 6 2nd floor extended to suite 110 healthcare room Fiber 3 and 4 and tagged ckt ID |  | kelly sawyer 1-803-454-1345 kellysawyer@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/29/2016(Private IP - PIP) 09/29/2016(Access) | 03/20/2017 |  | 10/05/2016 (22600130) 10/03/2016 (22600131) | 10/03/2016 | 09/29/2016 |  |  | N (22600130) N (22600131) | U0101953 |  |  | NSPE0010326975
Completed | UNITED HEALTH CARE | 1001 LAKESIDE AVE E CLEVELAND, OH 44114-1158 US | 50 MBPS (22600194) | 04/13/2017: 04/12 As per customer, this needs to be rescheduled. | 193125143 | UNITED HEALTH CARE | Private IP - PIP (22600193) Access (22600194) | 22600193 22600194 | 20 MBPS (22600193) |  | 115908987 (Private IP (PIP)) 115908985 (Access) | C4004137/ADD (22600193) E4011557/ADD (22600194) |  | 5748606 | 10000 | PVC ID : 5748606 VPN Name : UnitedHealthGroup Router Name : CLEV9E01 VRF Name : V648146:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64618 PE IP Address : 68.137.25.153 CE Address : 68.137.25.154 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (22600194) | Ethernet | [5 empty] | 07/13/2016 (CCP) (22600193) 07/13/2016 (CCP) (22600194) |  |  | SUSAN HIGHAM 1-216-420-9472 susan_b_higham@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 07/14/2016(Private IP - PIP) 07/14/2016(Access) |  |  | 08/02/2016 (22600193) 07/29/2016 (22600194) | 07/18/2016 | 07/14/2016 |  |  | N (22600193) N (22600194) | U0101953 |  |  | NSPE0010326975
Completed | TX016-05-IJ | 200 S 10TH ST STE 1610 MCALLEN, TX 78501-7930 US | 4.6 MBPS (22600266) | 06/09/2016: 6/9- Order sent to LEC, awaiting FOC date. | 193125136 | TX016-05-IJ | Private IP - PIP (22600265) Access (22600266) | 22600265 22600266 | 4.6 MBPS (22600265) |  | 116671667 (Private IP (PIP)) 116671665 (Access) | C0083726/ADD (22600265) N1029873/ADD (22600266) N1029872/ADD (22600266) N1029874/ADD (22600266) | 38/HCGS/630728//SW (2260026616159201) | 5748616 | 1500 | PVC ID : 5748616 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65096 PE IP Address : 199.220.177.153 CE Address : 199.220.177.154 QoS - Egress Profile: R12 |  | DS1 (22600266) | TDM | ATT (2260026616159201) | 05/27/2016 (2260026616159201) | 06/07/2016 (2260026616159201) | 06/10/2016 (2260026616159201) |  |  | DEMARCADDR - 200 S 10TH ST MCALLEN TX DEMARCDET - 16TH FLR MECHANIAL RM MM #01 POS #14- |  | Conrado Alvarado 1-956-217-8051 conrado.alvarado@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 06/10/2016(Private IP - PIP) 06/10/2016(Access) |  |  | 06/14/2016 (22600265) 06/10/2016 (22600266) | 06/21/2016 | 06/11/2016 |  |  | N (22600265) N (22600266) | U0101953 |  |  | NSPE0010327034
Completed | UCA97-07-IJ Cypress CA | 5757 PLAZA DR CYPRESS, CA 90630-5000 US | 200 MBPS (22663828) | 02/03/2017: 02/02 Successfully activated | 193173497 | UCA97-07-IJ Cypress CA | Private IP - PIP (22663827) Access (22663828) | 22663827 22663828 | 150 MBPS (22663827) |  | 119784675 (Private IP (PIP)) 119784673 (Access) | C5002115/ADD (22663827) E5003814/ADD (22663828) | 71.L1XX.003244..TWCC (2266382868749601) | 5754253 | 110000 | PVC ID : 5754253 VPN Name : UnitedHealthGroup Router Name : BB39E01 VRF Name : V581972:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64605 PE IP Address : 152.162.0.173 CE Address : 152.162.0.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663828) | 1000Base-SX (850nm, Multi Mode Fiber) (22663828) | Ethernet | TIME WARNER CABLE (2266382868749601) | 06/13/2016 (2266382868749601) | 08/15/2016 (2266382868749601) | 09/23/2016 (2266382868749601) | 12/20/2016 (VFORCE) (22663828) | 12/20/2016 (VFORCE) (22663828) | DEMARCDET - Main MPOE server room wall mounted RAD Port 5 |  | Reid Banek 1-763-744-0856 reid_banek@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-176-374-4098 | 12/20/2016(Private IP - PIP) 12/20/2016(Access) | 02/02/2017 |  | 01/05/2017 (22663827) 01/03/2017 (22663828) | 01/03/2017 | 12/20/2016 |  |  | N (22663827) N (22663828) | U0101953 | Jeopardy Notification 5 (12/02/2016) |  | NSPE0010376352
Completed | UCT15-08-IJ Rocky Hill CT | 400 CAPITAL BLVD ROCKY HILL, CT 06067-3576 US | 200 MBPS (22663805) | 01/27/2017: 01/26 Successfully activated | 193173527 | UCT15-08-IJ Rocky Hill, CT | Private IP - PIP (22663804) Access (22663805) | 22663804 22663805 | 100 MBPS (22663804) |  | 119784680 (Private IP (PIP)) 119784678 (Access) | C5002114/ADD (22663804) E5003813/ADD (22663805) | 18.KFGX.150007..COXC. (2266380571074601) | 5754251 | 30000 | PVC ID : 5754251 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64878 PE IP Address : 68.138.71.81 CE Address : 68.138.71.82 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663805) | 1000Base-SX (850nm, Multi Mode Fiber) (22663805) | Ethernet | COX (2266380571074601) | 06/13/2016 (2266380571074601) | 08/22/2016 (2266380571074601) |  | 08/12/2016 (VFORCE) (22663805) |  | DEMARCDET - main building, 1st floor, IT room, left corner back |  | David Lapoint 1-860-221-0666 dlapoint@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/12/2016(Private IP - PIP) 08/12/2016(Access) | 01/26/2017 |  | 08/31/2016 (22663804) 08/29/2016 (22663805) | 07/25/2016 | 08/12/2016 |  |  | N (22663804) N (22663805) | U0101953 |  |  | NSPE0010376352
Completed | UCA20-05-IJ Chico | 2080 E 20TH ST CHICO, CA 95928-7702 US | 250 MBPS (22663835) | 11/04/2016: 11/4 Activatin completed 11/3 | 193173518 | UCA20-05-IJ Chico | Private IP - PIP (22663834) Access (22663835) | 22663834 22663835 | 100 MBPS (22663834) |  | 119784671 (Private IP (PIP)) 119784669 (Access) | C0084598/ADD (22663834) E0000504/ADD (22663835) | 23/KRGN/503117//PT (2266383516621901) | 5754254 | 70000 | PVC ID : 5754254 VPN Name : UnitedHealthGroup Router Name : SCM3E03 VRF Name : V447827-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64532 PE IP Address : 152.187.167.253 CE Address : 152.187.167.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663835) | 1000Base-SX (850nm, Multi Mode Fiber) (22663835) | Ethernet | ATT (2266383516621901) | 08/05/2016 (2266383516621901) | 08/22/2016 (2266383516621901) | 08/23/2016 (2266383516621901) | 09/07/2016 (VFORCE) (22663835) | 09/07/2016 (VFORCE) (22663835) | DEMARCADDR - 2080 E 20TH CHICO DEMARCDET - 1ST FLR MPOE RM. SO WALL, PORT 1 OPTICAL |  | Steve Riske 1-530-879-7041 steven_g_riske@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/07/2016(Private IP - PIP) 09/07/2016(Access) | 11/03/2016 |  | 08/16/2016 (22663834) 08/12/2016 (22663835) | 09/16/2016 | 09/07/2016 |  |  | N (22663834) N (22663835) | U0101953 | Jeopardy Notification 1 (08/23/2016) |  | NSPE0010376352
Completed | UFL75-08-IJ Miami FL | 7600 NW 19TH ST MIAMI, FL 33126-1219 US | 250 MBPS (22663794) | 10/04/2016: 10/3 Activation completed 10/3/2016 10:45:00 PM CST; cust accepted ckt | 193173498 | UFL75-08-IJ Miami, FL | Private IP - PIP (22663793) Access (22663794) | 22663793 22663794 | 100 MBPS (22663793) |  | 119784684 (Private IP (PIP)) 119784682 (Access) | C0084597/ADD (22663793) E0000503/ADD (22663794) | 60/KRGN/757241//SB (2266379416623001) | 5754250 | 70000 | PVC ID : 5754250 VPN Name : UnitedHealthGroup Router Name : POB3E03 VRF Name : V581033-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64860 PE IP Address : 152.187.166.69 CE Address : 152.187.166.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663794) | 1000Base-SX (850nm, Multi Mode Fiber) (22663794) | Ethernet | ATT (2266379416623001) | 06/13/2016 (2266379416623001) | 06/28/2016 (2266379416623001) | 08/16/2016 (2266379416623001) | 08/24/2016 (VFORCE) (22663794) | 08/24/2016 (VFORCE) (22663794) | DEMARCADDR - 7600 NW 19TH ST MIA FL DEMARCDET - 3RD FLR IT RM AT&T RACK PNL JACKS 3/4 |  | Steve Gaudette 1-305-715-2537 steven_gaudette@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/24/2016(Private IP - PIP) 08/24/2016(Access) | 10/03/2016 |  | 08/31/2016 (22663793) 08/29/2016 (22663794) | 08/29/2016 | 08/24/2016 |  |  | N (22663793) N (22663794) | U0101953 |  |  | NSPE0010376352
Completed | CA145-02-IJ Marina CA | 455 RESERVATION RD STE EFGI MARINA, CA 93933-3328 US | 50 MBPS (22663898) | 11/10/2016: 11/10 tag and locae dispatch has the beas reconnected and layer 3 connectivity tested- Per BNE Beas is Up and csutoemr needs to call GLP on demand to get the BGP Up. BNE?GLP see two way traffic.- Sent email to Diane Reyes Eng for UHG with all info and GLP on demand # to call about the BGP getting UP. | 193173515 | CA145-02-IJ Marina, CA | Private IP - PIP (22663897) Access (22663898) | 22663897 22663898 | 10 MBPS (22663897) |  | 119756122 (Private IP (PIP)) 119756120 (Access) | C4004360/ADD (22663897) E4012244/ADD (22663898) | 50/KRGN/502660//PT (2266389816618001) | 5754264 | 1500 | PVC ID : 5754264 VPN Name : UnitedHealthGroup Router Name : HAY9E01 VRF Name : V640365:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64657 PE IP Address : 152.162.14.181 CE Address : 152.162.14.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663898) | 1000Base-SX (850nm, Multi Mode Fiber) (22663898) | Ethernet | ATT (2266389816618001) | 08/10/2016 (2266389816618001) | 07/13/2016 (2266389816618001) | 08/12/2016 (2266389816618001) | 08/16/2016 (VFORCE) (22663898) | 08/16/2016 (VFORCE) (22663898) | DEMARCDET - 1st floor SERVER ROOM BACKBOARD JACKS 1 & 2 tagged with ckt id |  | Candido Barretto 1-831-384-8080 cbarreto@accessiv.com | Dianne Reyes | drreyes@optum.com | 632-588-3551 | 08/16/2016(Private IP - PIP) 08/16/2016(Access) |  |  | 08/23/2016 (22663897) 08/19/2016 (22663898) | 09/21/2016 | 08/16/2016 |  |  | N (22663897) N (22663898) | U0101953 |  |  | NSPE0010377142
Completed | CA143-02-IJ Rohnert Park CA | 170 PROFESSIONAL CENTER DR STE C ROHNERT PARK, CA 94928-2169 US | 50 MBPS (22663892) | 10/24/2016: 10/24 Activation completed 10/22 | 193173496 | CA143-02-IJ Rohnert Park , CA | Private IP - PIP (22663891) Access (22663892) | 22663891 22663892 | 10 MBPS (22663891) |  | 119756118 (Private IP (PIP)) 119756116 (Access) | C4004307/ADD (22663891) E4012057/ADD (22663892) | 86/KRGN/580646//PT (2266389216618001) | 5754263 | 1500 | PVC ID : 5754263 VPN Name : UnitedHealthGroup Router Name : HAY9E01 VRF Name : V640365:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64658 PE IP Address : 68.139.160.149 CE Address : 68.139.160.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663892) | 1000Base-SX (850nm, Multi Mode Fiber) (22663892) | Ethernet | ATT (2266389216618001) | 06/14/2016 (2266389216618001) | 06/29/2016 (2266389216618001) | 06/29/2016 (2266389216618001) | 10/20/2016 (VFORCE) (22663892) | 10/20/2016 (VFORCE) (22663892) | DEMARCDET - telco room 1.1 hand of anel port 4 and 5 |  | Jan Johnson 1-707-588-8894 jljohnson@accessiv.com | Dianne Reyes | drreyes@optum.com | 632-588-3551 | 10/20/2016(Private IP - PIP) 10/20/2016(Access) | 10/22/2016 |  | 11/03/2016 (22663891) 11/01/2016 (22663892) | 11/01/2016 | 10/20/2016 |  |  | N (22663891) N (22663892) | U0101953 |  |  | NSPE0010377142
Completed | CT003-05-IJ Windsor CT | 100 NORTHFIELD DR WINDSOR, CT 06095-4730 US | 250 MBPS (22663904) | 01/26/2017: 01/26 Successfully activated, accepted by kevin_cantor@optum.com | 193173516 | CT003-05-IJ Windsor, CT | Private IP - PIP (22663903) Access (22663904) | 22663903 22663904 | 100 MBPS (22663903) |  | 119756126 (Private IP (PIP)) 119756124 (Access) | C0084599/ADD (22663903) E0000505/ADD (22663904) | FA/KRGN/617656//SN/ (2266390469191101) | 5754265 | 10000 | PVC ID : 5754265 VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64673 PE IP Address : 152.161.35.165 CE Address : 152.161.35.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663904) | 1000Base-SX (850nm, Multi Mode Fiber) (22663904) | Ethernet | FRONTIER (2266390469191101) | 06/13/2016 (2266390469191101) | 07/15/2016 (2266390469191101) |  | 11/03/2016 (VFORCE) (22663904) | 11/03/2016 (VFORCE) (22663904) | DEMARCDET - 1st floor telco room wall mount on A24 patch panel jack 9 and 10 |  | Eric Kilberg 1-860-502-6658 eric_kilberg@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 11/03/2016(Private IP - PIP) 11/03/2016(Access) | 01/25/2017 |  | 11/10/2016 (22663903) 11/08/2016 (22663904) | 11/08/2016 | 11/03/2016 |  |  | N (22663903) N (22663904) | U0101953 |  |  | NSPE0010377142
Completed | OK003-02-IJ Oklahoma OK | 7512 BROADWAY EXT STE 308 OKLAHOMA CITY, OK 73116-9055 US | 6 MBPS (22663886) | 12/07/2016: 4xT1 Demarc location info N1030409- 1st floor, equipment room, multi mount 2 position 3, N1030410- 1st floor, equipment room, multi mount 3 position 1, N1030411- 1st floor, equipment room, multi mount 3 position 2, N1030412- 1st floor, equipment room, multi mount 3 position 3 | 193173524 | OK003-02-IJ Oklahoma, OK | Private IP - PIP (22663885) Access (22663886) | 22663885 22663886 | 6 MBPS (22663885) |  | 119756114 (Private IP (PIP)) 119756112 (Access) | C1037311/ADD (22663885) N1030409/ADD (22663886) N1030411/ADD (22663886) N1030412/ADD (22663886) N1030410/ADD (22663886) | 97/HCGS/945480//SW (2266388616618001) 13tpw uqw 0017 (I0008143.OKC) 13tpw uqw 0014 (I0008143.OKC) 13tpw uqw 0016 (I0008143.OKC) 13tpw uqw 0015 (I0008143.OKC) | 5754262 | 1500 | PVC ID : 5754262 VPN Name : UnitedHealthGroup Router Name : OKL3E02 VRF Name : V371754-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64663 PE IP Address : 152.162.161.185 CE Address : 152.162.161.186 QoS - Egress Profile: R12 |  | DS1 (22663886) | TDM | ATT (2266388616618001) | 07/12/2016 (2266388616618001) | 07/20/2016 (2266388616618001) 07/06/2016 (I0008143.OKC) | 07/25/2016 (2266388616618001) |  |  | DEMARCADDR - 7512 BROADWAY EXTENSION OKLAHOMA CITY OK DEMARCDET - 1ST FLR EQUIP RM, MM 2, SLOT 3 |  | Cody Turpin 1-405-848-0338 wturpin@axelacare.com | PRADEEP YADAV | pradeep_yadav@optum.com | 91-981-005-9326 | 07/25/2016(Private IP - PIP) 07/25/2016(Access) |  |  | 08/01/2016 (22663885) 07/28/2016 (22663886) | 07/06/2016 | 07/25/2016 | 09/09/2018 (22663886) |  | N (22663885) N (22663886) | U0101953 |  |  | NSPE0010377142
Completed | AL015-02-IJ Birmingham AL | 660 UNIVERSITY BLVD STE A BIRMINGHAM, AL 35233-1123 US | 6 MBPS (22663910) | 08/04/2016: 8/4- Per AT&T, We have escalated this order to the next level of our Dispatch center to get a field tech assigned to go work the T1 installs. As soon as they get a tech assigned we will let you know. | 193173494 | AL015-02-IJ Birmingham AL | Private IP - PIP (22663909) Access (22663910) | 22663909 22663910 | 6 MBPS (22663909) |  | 119579949 (Private IP (PIP)) 119579907 (Access) | C1037276/ADD (22663909) N1030388/ADD (22663910) N1030390/ADD (22663910) N1030389/ADD (22663910) N1030387/ADD (22663910) | A3/HCGS/441875//SC (2266391016589101) | 5754266 | 1500 | PVC ID : 5754266 VPN Name : UnitedHealthGroup Router Name : B6S3E01 VRF Name : V546882-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64650 PE IP Address : 152.187.166.61 CE Address : 152.187.166.62 QoS - Egress Profile: R12 |  | DS1 (22663910) | TDM | ATT (2266391016589101) | 06/21/2016 (2266391016589101) | 07/18/2016 (2266391016589101) | 08/11/2016 (2266391016589101) |  |  | DEMARCDET - 1ST FLR PHONE ROOM MM4 SLOT 1 |  | Ava Tidwell 1-205-324-4566 atidwell@nphc.net | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 08/11/2016(Private IP - PIP) 08/11/2016(Access) |  |  | 07/25/2016 (22663909) 07/21/2016 (22663910) | 07/06/2016 | 08/11/2016 |  |  | N (22663909) N (22663910) | U0101953 |  |  | NSPE0010377179
Completed | OH017-02-IJ Dublin OH | 555 METRO PL N STE 325 DUBLIN, OH 43017-5341 US | 10 MBPS (22663916) | 10/12/2016: 10/12 *****ACTIVATION COMPLETED****** | 193173506 | OH017-02-IJ Dublin, OH | Private IP - PIP (22663915) Access (22663916) | 22663915 22663916 | 10 MBPS (22663915) |  | 119588799 (Private IP (PIP)) 119588797 (Access) | C0084600/ADD (22663915) E3025685/ADD (22663916) | 61.L1XX.002268..TWCC (2266391616589001) | 5754267 | 1500 | PVC ID : 5754267 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64760 PE IP Address : 147.225.140.33 CE Address : 147.225.140.34 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663916) | 1000Base-SX (850nm, Multi Mode Fiber) (22663916) | Ethernet | TIME WARNER CABLE (2266391616589001) | 06/13/2016 (2266391616589001) | 08/15/2016 (2266391616589001) | 08/05/2016 (2266391616589001) | 08/11/2016 (VFORCE) (22663916) | 08/11/2016 (VFORCE) (22663916) | DEMARCDET - Suite 325 rack unit 40 port 5 on RAD 203A |  | Denise Bee 1-866-970-7500 Denise.bee@hospiscript.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 08/11/2016(Private IP - PIP) 08/11/2016(Access) | 10/12/2016 |  | 08/24/2016 (22663915) 08/22/2016 (22663916) | 08/19/2016 | 08/11/2016 |  |  | N (22663915) N (22663916) | U0101953 |  |  | NSPE0010377179
Completed | AL014-02-IJ Huntsville AL | 2650 LEEMAN FERRY RD SW STE C HUNTSVILLE, AL 35801-6532 US | 100 MBPS (22663922) | 02/24/2017: 01/27 Circuit is up. All good on Verizon side. anupam_datt@optum.com circuit is up too. | 193173505 | AL014-02-IJ Huntsville AL | Private IP - PIP (22663921) Access (22663922) | 22663921 22663922 | 50 MBPS (22663921) |  | 119579905 (Private IP (PIP)) 119579903 (Access) | C1037050/ADD (22663921) E4012058/ADD (22663922) | HUAL/CETHS/EVTAWI7R/WOW (2266392216589002) | 5754272 | 3000 | PVC ID : 5754272 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64632 PE IP Address : 152.181.50.121 CE Address : 152.181.50.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663922) | 1000Base-SX (850nm, Multi Mode Fiber) (22663922) | Ethernet | ATT (2266392216589003) WIDE OPEN WEST (2266392216589002) | 06/27/2016 (2266392216589003) 06/16/2016 (2266392216589002) | 08/24/2016 (2266392216589002) | 08/26/2016 (2266392216589002) 07/11/2016 (2266392216589003) | 10/27/2016 (VFORCE) (22663922) | 10/27/2016 (VFORCE) (22663922) | DEMARCDET - customer network rack above customer's switch aou7210 port 1/1/1 |  | Donald Griggs 1-256-534-4663 dgriggs@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 91-987-313-9388 | 10/27/2016(Private IP - PIP) 10/27/2016(Access) | 01/27/2017 |  | 11/07/2016 (22663921) 11/03/2016 (22663922) | 11/03/2016 | 10/27/2016 |  |  | N (22663921) N (22663922) | U0101953 | Jeopardy Notification 4 (09/28/2016) |  | NSPE0010377179
Completed | NC004-05-IJ Morrisville NC | 3131 RDU CENTER DR MORRISVILLE, NC 27560-7687 US | 200 MBPS (22663941) | 03/28/2017: 03/23 Successfully activated | 193173528 | NC004-05-IJ Morrisville NC | Private IP - PIP (22663940) Access (22663941) | 22663940 22663941 | 100 MBPS (22663940) |  | 120303871 (Private IP (PIP)) 120303869 (Access) | C5002119/ADD (22663940) E5003819/ADD (22663941) | 91.L1XX.004417..TWCC (2266394118891201) | 5754268 | 25000 | PVC ID : 5754268 VPN Name : UnitedHealthGroup Router Name : CHRL9E01 VRF Name : V638950:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65288 PE IP Address : 159.24.235.117 CE Address : 159.24.235.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663941) | 1000Base-SX (850nm, Multi Mode Fiber) (22663941) | Ethernet | TIME WARNER CABLE (2266394118891201) | 06/13/2016 (2266394118891201) | 11/16/2016 (2266394118891201) | 10/28/2016 (2266394118891201) | 11/08/2016 (VFORCE) (22663941) |  | DEMARCDET - 1ST FLOOR ELECTRICAL ROOM RAD 203 PORT 5 TAGGED WITH CIRCUIT ID |  | Kurt Doellinger 1-336-540-7719 kurt_doellinger@uhg.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 11/08/2016(Private IP - PIP) 11/08/2016(Access) | 03/23/2017 |  | 11/29/2016 (22663940) 11/23/2016 (22663941) | 11/09/2016 | 11/08/2016 |  |  | N (22663940) N (22663941) | U0101953 |  |  | NSPE0010380840
Completed | UNE50-08-IJ Omaha | 2717 N 118TH ST OMAHA, NE 68164-9688 US | 200 MBPS (22663928) | 02/02/2017: 02/01 Successfully activated | 193173499 | UNE50-08-IJ Omaha | Private IP - PIP (22663927) Access (22663928) | 22663927 22663928 | 100 MBPS (22663927) |  | 120303875 (Private IP (PIP)) 120303873 (Access) | C5002118/ADD (22663927) E5003818/ADD (22663928) | 21.KFGX.000499..COXC. (2266392816711302) | 5754270 | 25000 | PVC ID : 5754270 VPN Name : UnitedHealthGroup Router Name : PLSHXE01 VRF Name : V588242-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64756 PE IP Address : 199.220.168.201 CE Address : 199.220.168.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663928) | 1000Base-SX (850nm, Multi Mode Fiber) (22663928) | Ethernet | COX (2266392816711302) | 06/15/2016 (2266392816711302) | 07/27/2016 (2266392816711302) |  | 10/31/2016 (VFORCE) (22663928) | 10/31/2016 (VFORCE) (22663928) | DEMARCDET - 2nd floor common room north side of the building COX wall rack NID shelf 1 NID 2 SFP B multimode fiber handoff |  | Joe Roscoe 1-402-445-5510 joseph_roscoe@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 10/31/2016(Private IP - PIP) 10/31/2016(Access) | 02/01/2017 |  | 11/14/2016 (22663927) 11/10/2016 (22663928) | 11/10/2016 | 10/31/2016 |  |  | N (22663927) N (22663928) | U0101953 |  |  | NSPE0010380840
Completed | UNH01-08-IJ Hooksett | 14 CENTRAL PARK DR HOOKSETT, NH 03106-2507 US | 300 MBPS (22663934) | 10/28/2016: 10/28 Activation completed 10/27 | 193173544 | UNH01-08-IJ Hooksett | Private IP - PIP (22663933) Access (22663934) | 22663933 22663934 | 150 MBPS (22663933) |  | 120303879 (Private IP (PIP)) 120303877 (Access) | C5002120/ADD (22663933) E5003820/ADD (22663934) | 84/KRGN/042002/00/MJD/ (2266393471074701) | 5754269 | 110000 | PVC ID : 5754269 VPN Name : UnitedHealthGroup Router Name : CHTXE03 VRF Name : V637075-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64746 PE IP Address : 152.162.81.137 CE Address : 152.162.81.138 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663934) | 1000Base-SX (850nm, Multi Mode Fiber) (22663934) | Ethernet | FAIRPOINT (2266393471074701) | 06/13/2016 (2266393471074701) | 07/19/2016 (2266393471074701) |  | 09/16/2016 (VFORCE) (22663934) | 09/16/2016 (VFORCE) (22663934) | DEMARCDET - floor 1, server rm wall mounted tagged not extended |  | Christopher Tremblay 1-603-629-7998 ctrembl@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/19/2016(Private IP - PIP) 09/19/2016(Access) | 10/27/2016 |  | 09/28/2016 (22663933) 09/26/2016 (22663934) | 09/19/2016 | 09/19/2016 |  |  | N (22663933) N (22663934) | U0101953 | Jeopardy Notification 2 (09/18/2016) |  | NSPE0010380840
Completed | UMD92-08-IJ Columbia MD | 6220 OLD DOBBIN LN COLUMBIA, MD 21045-5812 US | 200 MBPS (22764587) | 01/25/2017: 01/24 Successfully activated | 193177728 | UMD92-08-IJ Columbia MD | Private IP - PIP (22764586) Access (22764587) | 22764586 22764587 | 100 MBPS (22764586) |  | 120280675 (Private IP (PIP)) 120280673 (Access) | C5002207/ADD (22764586) E5003988/ADD (22764587) | 38.KFGS.301841..CM (2276458716707201) | 5764293 | 25000 | PVC ID : 5764293 VPN Name : UnitedHealthGroup Router Name : RAY9E03 VRF Name : V534296:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64763 PE IP Address : 152.164.158.65 CE Address : 152.164.158.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22764587) | 1000Base-SX (850nm, Multi Mode Fiber) (22764587) | Ethernet | VERIZON (2276458716707201) | 09/26/2016 (2276458716707201) | 10/06/2016 (2276458716707201) | 09/30/2016 (2276458716707201) |  |  | 4th floor, data room, rack 1, pos 25, NID 1, tagged LEC Demarc-1st floor; suite 100; MDF3 relay rack 1 NID 2 tagged |  | Bernadette Green 1-443-896-0400 bgreen@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/30/2016(Private IP - PIP) 09/30/2016(Access) | 01/24/2017 |  | 10/24/2016 (22764586) 10/20/2016 (22764587) | 10/21/2016 | 09/30/2016 |  |  | N (22764586) N (22764587) | U0101953 | Jeopardy Notification 2 (09/25/2016) |  | NSPE0010385453
Completed | UMO15-08-IJ Maryland Heights | 13655 RIVERPORT DR MARYLAND HEIGHTS, MO 63043-4812 US | 400 MBPS (22663841) | 12/12/2016: 12/12 Status: Activation scheduled 12/14/2016 10PM CST Next action: Activate the circuit Who owns the next action: customer and tech Ticket: NA | 193177727 | UMO15-08-IJ Maryland Heights | Private IP - PIP (22663840) Access (22663841) | 22663840 22663841 | 200 MBPS (22663840) |  | 120280679 (Private IP (PIP)) 120280677 (Access) | C5002116/ADD (22663840) E5003815/ADD (22663841) | 41/KRGN/704969//SW (2266384116707301) | 5754255 | 90000 | PVC ID : 5754255 VPN Name : UnitedHealthGroup Router Name : STLS3E01 VRF Name : V432785-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64678 PE IP Address : 147.225.184.225 CE Address : 147.225.184.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663841) | 1000Base-SX (850nm, Multi Mode Fiber) (22663841) | Ethernet | ATT (2266384116707301) | 08/01/2016 (2266384116707301) | 08/18/2016 (2266384116707301) | 11/15/2016 (2266384116707301) | 11/28/2016 (VFORCE) (22663841) | 11/28/2016 (VFORCE) (22663841) | DEMARCADDR - ADRS_UNKNOWN DEMARCDET - 1ST FLR MAIN TELCO RM, PATCH PANEL 1, RTS 5/6 , TAGGED, NOT |  | Thomas Meyers 1-314-592-7461 thomas_p_meyers@uhc.com | Thomas Meyers | thomas_p_meyers@uhc.com | 1-314-592-7461 | 11/28/2016(Private IP - PIP) 11/28/2016(Access) | 12/14/2016 |  | 12/01/2016 (22663840) 11/29/2016 (22663841) | 11/29/2016 | 11/28/2016 |  |  | N (22663840) N (22663841) | U0101953 | Jeopardy Notification 1 (11/11/2016) |  | NSPE0010385453
Completed | Cypress CA 50M Ethernet PIP | 5701 KATELLA AVE CYPRESS, CA 90630-5006 US | 300 MBPS (22663850) | 08/14/2017: 08/10 Activation complete | 193177702 | Cypress CA 50M Ethernet PIP | Private IP - PIP (22663849) Access (22663850) | 22663849 22663850 | 300 MBPS (22663849) |  | 120280671 (Private IP (PIP)) 120280669 (Access) | C5002117/ADD (22663849) E5003816/ADD (22663850) |  | 5754256 | 90000 | PVC ID : 5754256 VPN Name : UnitedHealthGroup Router Name : LSA29E01 VRF Name : V461763:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65444 PE IP Address : 152.164.224.89 CE Address : 152.164.224.90 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22663850) | Ethernet |  |  |  |  | 08/26/2016 (CCP) (22663849) 08/26/2016 (CCP) (22663850) | 09/15/2016 (CCP) (22663849) 09/15/2016 (CCP) (22663850) | VZ Lec/beas:1st Floor Server Room, VZB Blue Cabinet. ISG port 0.1, left MM fiber |  | Michael Anders 1-714-252-0502 michael_anders@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/16/2016(Private IP - PIP) 09/16/2016(Access) | 08/10/2017 |  | 10/04/2016 (22663849) 09/30/2016 (22663850) | 07/25/2016 | 09/16/2016 |  |  | N (22663849) N (22663850) | U0101953 |  |  | NSPE0010385453
Completed | UIL44-08-IJ Moline IL | 1300 RIVER DR STE 200 MOLINE, IL 61265-1356 US | 200 MBPS (22663856) | 11/22/2017: 11/21 Successfully activation | 193177726 | UIL44-08-IJ Moline, IL | Private IP - PIP (22663855) Access (22663856) | 22663855 22663856 | 100 MBPS (22663855) |  | 120280667 (Private IP (PIP)) 120280665 (Access) | C5002127/ADD (22663855) E5003817/ADD (22663856) | /OBGS/706441//LB (2266385616707301) /ODGS/728752//LB (2266385616707302) c6ueg d2dp0001 (I0000304.DVP) | 5754257 | 30000 | PVC ID : 5754257 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64584 PE IP Address : 68.137.6.233 CE Address : 68.137.6.234 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22663856) | Ethernet | CENTURYLINK (2266385616707301) ATT (2266385616707303) CENTURYLINK (2266385616707302) | 09/27/2016 (2266385616707301) 10/20/2016 (2266385616707303) 10/26/2016 (2266385616707302) | 10/07/2016 (2266385616707301) 11/07/2016 (2266385616707302) 01/23/2017 (I0000304.DVP) | 11/07/2016 (2266385616707303) 11/17/2016 (2266385616707301) 11/17/2016 (2266385616707302) 01/23/2017 (I0000304.DVP) | 12/05/2016 (VFORCE) (22663856) | 07/15/2016 (CCP) (22663855) 01/23/2017 (VFORCE) (22663856) 07/15/2016 (CCP) (22663856) | BEAS Demarc: MPOE west wall on customer provided plywood. BEAS labeled with Verizon circuit ID (E5003817)on port one and LEC I''''d on port 4. Customer port hand off is MMF. customer’s router is needed to be connected to the Port-1 of the BEAS box 1, PORTS 1 |  | Robert Popp 1-309-736-4680 robert.popp@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 01/23/2017(Private IP - PIP) 01/23/2017(Access) | 11/21/2017 |  | 02/07/2017 (22663855) 02/03/2017 (22663856) | 02/03/2017 | 01/23/2017 |  |  | N (22663855) N (22663856) | U0101953 | Jeopardy Notification 3 (01/11/2017) |  | NSPE0010385453
Completed | C1600-02-IJ Dialog Direct Highland Park | 13700 OAKLAND ST HIGHLAND PARK, MI 48203-3173 US | 250 MBPS (22647718) | 06/26/2016: 6/26- Circuit delivered. Order on hold, waiting for customer to confirm if demarc extension required before proceeding with beas install. | 193162560 | C1600-02-IJ Dialog Direct Highland Park | Private IP - PIP (22647717) Access (22647718) | 22647717 22647718 | 100 MBPS (22647717) |  | 118399323 (Private IP (PIP)) 118399321 (Access) | C0084374/ADD (22647717) E0000502/ADD (22647718) | /KRGN/209219//MB (2264771816421901) | 5753013 | 40000 | PVC ID : 5753013 VPN Name : UHG-ECC Router Name : DTRT3E01 VRF Name : V657944-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65496 PE IP Address : 152.161.38.145 CE Address : 152.161.38.146 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22647718) | 1000Base-SX (850nm, Multi Mode Fiber) (22647718) | Ethernet | ATT (2264771816421901) | 06/10/2016 (2264771816421901) | 06/23/2016 (2264771816421901) | 06/23/2016 (2264771816421901) | 06/29/2016 (VFORCE) (22647718) | 06/29/2016 (VFORCE) (22647718) | DEMARCADDR - 13700 OAKLAND HIGHLAND PARK MI DEMARCDET - TURNED UP PORT 5 AND INSTALLED HANDOFF INSTALLED HANDOFF JACKS ON |  | Jesse Fawcett 1-248-598-0486 Jesse.Fawcett@dialog-direct.com | Mark Landis | Mark.Landis@dialog-direct.com | 1-313-957-5075 | 06/29/2016(Private IP - PIP) 06/29/2016(Access) | 07/28/2016 |  | 07/06/2016 (22647717) 07/01/2016 (22647718) | 07/20/2016 | 06/29/2016 |  |  | N (22647717) N (22647718) | U0101953 |  |  | NSPE0010360253
Completed | FL171-02-IJ | 15951 SW 41ST ST STE 500&600 DAVIE, FL 33331-1535 US | 50 MBPS (22663862) | 12/23/2016: 12/22 Successfully activated. | 193183510 | FL171-02-IJ | Private IP - PIP (22663861) Access (22663862) | 22663861 22663862 | 10 MBPS (22663861) |  | 119702146 (Private IP (PIP)) 119702144 (Access) | C4004304/ADD (22663861) E4012054/ADD (22663862) | 60/KRGN/757513//SB (2266386216609602) | 5754258 | 1500 | PVC ID : 5754258 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64644 PE IP Address : 147.225.175.129 CE Address : 147.225.175.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663862) | 1000Base-SX (850nm, Multi Mode Fiber) (22663862) | Ethernet | ATT (2266386216609602) | 08/19/2016 (2266386216609602) | 09/06/2016 (2266386216609602) | 09/06/2016 (2266386216609602) | 12/08/2016 (VFORCE) (22663862) | 12/08/2016 (VFORCE) (22663862) | DEMARCADDR - 15951 SW 41ST ST DAVIE FL DEMARCDET - STE#500 1ST FLR REAR TELCO WALL WALLMOUNT CIENA 3903 PORT#2 |  | Karen Hitchen 1-954-389-1126 khitchen@ambienthealth.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 12/08/2016(Private IP - PIP) 12/08/2016(Access) | 12/22/2016 |  | 12/20/2016 (22663861) 12/16/2016 (22663862) | 12/16/2016 | 12/09/2016 |  |  | N (22663861) N (22663862) | U0101953 |  |  | NSPE0010377075
Completed | AL016-02-IJ Tuscaloosa AL | 500 PAUL W BRYANT DR TUSCALOOSA, AL 35401-2057 US | 6 MBPS (22663865) | 07/06/2016: 7/6- Circuit delivered. Pending demarc verification. | 193183474 | AL016-02-IJ Tuscaloosa, AL | Private IP - PIP (22663864) Access (22663865) | 22663864 22663865 | 6 MBPS (22663864) |  | 119702151 (Private IP (PIP)) 119702149 (Access) | C1037049/ADD (22663864) N1030234/ADD (22663865) N1030233/ADD (22663865) N1030231/ADD (22663865) N1030232/ADD (22663865) | A3/HCGS/441842//SC (2266386516609701) | 5754261 | 3000 | PVC ID : 5754261 VPN Name : UnitedHealthGroup Router Name : CPZ3E03 VRF Name : V628602-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64651 PE IP Address : 152.176.77.41 CE Address : 152.176.77.42 QoS - Egress Profile: R12 |  | DS1 (22663865) | TDM | ATT (2266386516609701) | 06/14/2016 (2266386516609701) | 07/05/2016 (2266386516609701) | 07/07/2016 (2266386516609701) |  |  | DEMARCADDR - 500 PAUL W BRYANT DR TUSCALOOSA AL DEMARCDET - 1ST FLR TELCO CLST QUAD MNT#4 POS 4 TA GGED |  | Karen Hitchen 1-954-389-1126 khitchen@ambienthealth.com | PRADEEP YADAV | pradeep_yadav@optum.com | 91-981-005-9326 | 07/07/2016(Private IP - PIP) 07/07/2016(Access) |  |  | 07/12/2016 (22663864) 07/08/2016 (22663865) | 07/07/2016 | 07/07/2016 |  |  | N (22663864) N (22663865) | U0101953 |  |  | NSPE0010377075
Completed | CA141-02-IJ Cerritos CA | 12604 HIDDENCREEK WAY STE C CERRITOS, CA 90703-2137 US | 60 MBPS (22663868) | 01/03/2017: 01/03 Successfully activated | 193183473 | CA141-02-IJ Cerritos, CA | Private IP - PIP (22663867) Access (22663868) | 22663867 22663868 | 10 MBPS (22663867) |  | 119702137 (Private IP (PIP)) 119702135 (Access) | C4004306/ADD (22663867) E4012056/ADD (22663868) | CHC00340787 (2266386816609501) | 5754260 | 1500 | PVC ID : 5754260 VPN Name : UnitedHealthGroup Router Name : BB39E01 VRF Name : V581972:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64655 PE IP Address : 152.185.27.181 CE Address : 152.185.27.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663868) | 1000Base-SX (850nm, Multi Mode Fiber) (22663868) | Ethernet | CHARTER (2266386816609501) | 06/13/2016 (2266386816609501) | 10/10/2016 (2266386816609501) | 09/08/2016 (2266386816609501) | 09/27/2016 (VFORCE) (22663868) | 09/28/2016 (VFORCE) (22663868) | DEMARCADDR - 624 S GRAND AVE, LOS ANGELES DEMARCDET - MAIN GROUND SERVER ROO |  | Teri Molthen 1-562-263-5602 tmolthen@axelacare.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 09/28/2016(Private IP - PIP) 09/28/2016(Access) | 01/03/2017 |  | 10/19/2016 (22663867) 10/17/2016 (22663868) | 07/25/2016 | 09/28/2016 |  |  | N (22663867) N (22663868) | U0101953 |  |  | NSPE0010377075
Completed | CA149-02-IJ Sacramento CA | 4610 NORTHGATE BLVD STE 130 SACRAMENTO, CA 95834-1154 US | 50 MBPS (22663880) | 09/08/2016: 9/8 Activation resched 9/14 at 9pm cst | 193183509 | CA149-02-IJ Sacramento, CA | Access (22663880) Private IP - PIP (22663879) | 22663880 22663879 | 10 MBPS (22663879) |  | 119702139 (Access) 119702141 (Private IP (PIP)) | E4012055/ADD (22663880) C4004305/ADD (22663879) | 18/KRGN/518271//PT (2266388016609601) | 5754259 | 7000 | PVC ID : 5754259 VPN Name : UnitedHealthGroup Router Name : SCM3E03 VRF Name : V447827-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64656 PE IP Address : 152.161.77.85 CE Address : 152.161.77.86 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663880) | 1000Base-SX (850nm, Multi Mode Fiber) (22663880) | Ethernet | ATT (2266388016609601) | 06/13/2016 (2266388016609601) | 07/07/2016 (2266388016609601) | 07/08/2016 (2266388016609601) | 08/16/2016 (VFORCE) (22663880) | 08/16/2016 (VFORCE) (22663880) | DEMARCADDR - 4610 NORTHGATE BL SAC DEMARCDET - MPOE, WLMNTD, JKPNL 1 MM |  | Ramona Moenter 1-916-648-0124 rmoenter@accessiv.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 08/16/2016(Access) 08/16/2016(Private IP - PIP) | 09/15/2016 |  | 08/26/2016 (22663880) 08/30/2016 (22663879) | 08/26/2016 | 08/16/2016 |  |  | N (22663880) N (22663879) | U0101953 |  |  | NSPE0010377075
Completed |  | 13891 JETPORT LOOP FORT MYERS, FL 33913 USA | 1.536 MBPS (IQBLB58F) | 12/23/2016: 12/23 Order complete; Cust notified as plug and play (call fail plug and play line (866) 829-9719) | 8763863 |  | Private IP (IQBLB58F) | IQBLB58F | 7.68 MBPS | P2143795 |  | BCBK9YXH0001 (IQBLB58F) BCBK9YXH0002 (IQBLB58F) BCBK9YXH0003 (IQBLB58F) BCBK9YXH0004 (IQBLB58F) BCBK9YXH0005 (IQBLB58F) | 25.HCGS.287809..UFLG (IQBLB58F9M1VMB01) 25.HCGS.294047..UFLG (IQBLB58F9M1VMB02) |  | 1536 | VPN Name : UnitedHealthGroup Router Name : AUB9E02 VRF Name : V428808:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64643 PE IP Address : 152.176.87.249 CE Address : 152.176.87.250 QoS - Egress Profile: R12 |  |  |  | CENTURYLINK (IQBLB58F9M1VMB01) CENTURYLINK (IQBLB58F9M1VMB02) | 06/29/2016 (IQBLB58F9M1VMB01) 12/07/2016 (IQBLB58F9M1VMB02) | 07/08/2016 (IQBLB58F9M1VMB01) 12/16/2016 (IQBLB58F9M1VMB02) | 12/21/2016 (IQBLB58F9M1VMB01) 12/21/2016 (IQBLB58F9M1VMB02) |  |  | Verizon circuit ID: P2143795 = BCBK9YXH0001-0005 LEC circuit ID: MCI CKT ID LEC CKT ID: BCBK9YXH0001 - 25.HCGS.294046..UFLG BCBK9YXH0002 - 25.HCGS.294047..UFLG BCBK9YXH0003 - 25.HCGS.294048..UFLG BCBK9YXH0004 - 25.HCGS.294049..UFLG BCBK9YXH0005 - 25.HCGS.294050..UFLG DMARC Location: BCBK9YXH0001 --- DEMARC LOC: 1st floor telco room wall-mounted 1st T1 housing slot 1 of 4 --- BCBK9YXH0002 --- DEMARC LOC: 1st floor telco room wall-mounted 1st T1 housing slot 2 of 4 --- BCBK9YXH0003 --- DEMARC LOC: 1st floor telco room wall-mounted 1st T1 housing slot 3 of 4 --- BCBK9YXH0004 --- DEMARC LOC: 1st floor telco room wall-mounted 1st T1 housing slot 4 of 4 ---- BCBK9YXH0005 ---- DEMARC LOC: 1st floor telco room wall-mounted 2nd T1 housing slot 4 of 4 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes |  | VIRGINIA SEXTON 0012395612388 SEXTON@AMBIENTHEALTH.COM |  |  |  | 12/23/2016 (IQBLB58F) |  |  | 01/06/2017 (IQBLB58F) | 01/06/2017 (IQBLB58F) |  |  |  | N (IQBLB58F) | 05017789 |  |  | NSPE0010369741
|  | 201 N TARRAGONA ST PENSACOLA, FL 32502 USA | 1.536 MBPS (IQBLB6Q0) | 02/10/2017: 2/9 Multicasting enable completed | 8763864 |  | Private IP (IQBLB6Q0) EVC/PVC Service (N.11110056.5760957) | IQBLB6Q0 N.11110056.5760957 | 7.68 MBPS | P2143851 |  | BCBK9YN70001 (IQBLB6Q0) BCBK9YN70002 (IQBLB6Q0) BCBK9YN70003 (IQBLB6Q0) BCBK9YN70004 (IQBLB6Q0) BCBK9YN70005 (IQBLB6Q0) | 48/HCGS/715410//SB (IQBLB6Q0FP1VMB01) | 5760957 | 1536 | VPN Name : UnitedHealthGroup Router Name : JAP3E02 VRF Name : V380184-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64640 PE IP Address : 147.225.40.65 CE Address : 147.225.40.66 QoS - Egress Profile: R12 PVC ID : 5760957 |  |  |  | ATT (IQBLB6Q0FP1VMB01) | 06/27/2016 (IQBLB6Q0FP1VMB01) | 07/11/2016 (IQBLB6Q0FP1VMB01) | 07/12/2016 (IQBLB6Q0FP1VMB01) |  |  |  |  | KELLY MAJEWSKI 0018504301259 KELLY.MAJEWSKI@AMBIENTHEALTH.COM |  |  |  | 07/13/2016 (IQBLB6Q0) | 11/03/2016 |  | 07/18/2016 (IQBLB6Q0) | 07/21/2016 (IQBLB6Q0) |  |  |  | N (IQBLB6Q0) N (N.11110056.5760957) | 05017789 87472027 |  |  | NSPE0010369779
Completed |  | 12503 E EUCLID DR ENGLEWOOD, CO 80111 USA | 1.536 MBPS (IQBLB5WC) | 07/06/2016: 7/7- FOC date 7/7. | 8763867 |  | Private IP (IQBLB5WC) | IQBLB5WC | 7.68 MBPS | P2143702 |  | BCBK9YH30001 (IQBLB5WC) BCBK9YH30002 (IQBLB5WC) BCBK9YH30003 (IQBLB5WC) BCBK9YH30004 (IQBLB5WC) BCBK9YH30005 (IQBLB5WC) | 24/HCGS/759961//MS (IQBLB5WCUL1VMB01) |  | 1536 | VPN Name : UnitedHealthGroup Router Name : DNJ3E02 VRF Name : V309857-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64654 PE IP Address : 152.162.3.181 CE Address : 152.162.3.182 QoS - Egress Profile: R12 |  |  |  | CENTURYLINK (IQBLB5WCUL1VMB01) | 06/22/2016 (IQBLB5WCUL1VMB01) | 07/07/2016 (IQBLB5WCUL1VMB01) | 07/08/2016 (IQBLB5WCUL1VMB01) |  |  |  |  | FRANK ALLEVA 0013037081124 FALLEVA@AXELACARE.COM |  |  |  | 07/11/2016 (IQBLB5WC) |  |  | 07/14/2016 (IQBLB5WC) | 07/15/2016 (IQBLB5WC) |  |  |  | N (IQBLB5WC) | 05017789 |  |  | NSPE0010369972
Completed |  | 3135 NEW GERMANY RD EBENSBURG, PA 15931 USA | 1.536 MBPS (IQBLB58P) | 07/14/2016: 7/14- Had a FOC of 7/7 for the previous PON: IQBLB58PAN1VMB01 and this has been completed but the tester is having some trouble in testing so they need to change the CFA. So an ASR has been sent which has a FOC of 7/18 to change the CFA. | 8763866 |  | Private IP (IQBLB58P) | IQBLB58P | 7.68 MBPS | P2143797 |  | BCBK9YML0001 (IQBLB58P) BCBK9YML0002 (IQBLB58P) BCBK9YML0003 (IQBLB58P) BCBK9YML0004 (IQBLB58P) BCBK9YML0005 (IQBLB58P) | 14.HCGS.765837..PA (IQBLB58PAN1VMB02) 14.HCGS.765837..PA (IQBLB58PAN1VMB03) 14.HCGS.765837..PA (IQBLB58PAN1VMB01) |  | 1536 | VPN Name : UnitedHealthGroup Router Name : PTBGE03 VRF Name : V640376:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64660 PE IP Address : 147.225.24.229 CE Address : 147.225.24.230 QoS - Egress Profile: R12 |  |  |  | VERIZON (IQBLB58PAN1VMB02) VERIZON (IQBLB58PAN1VMB03) VERIZON (IQBLB58PAN1VMB01) | 07/12/2016 (IQBLB58PAN1VMB02) 07/12/2016 (IQBLB58PAN1VMB03) 06/24/2016 (IQBLB58PAN1VMB01) | 07/18/2016 (IQBLB58PAN1VMB02) 07/18/2016 (IQBLB58PAN1VMB03) 07/07/2016 (IQBLB58PAN1VMB01) | 07/18/2016 (IQBLB58PAN1VMB02) 07/18/2016 (IQBLB58PAN1VMB03) 07/07/2016 (IQBLB58PAN1VMB01) |  |  |  |  | LAURIE SLEBODNIK 0018144728900 LSLEBODNIK@SUMMITHOMEINFUSION.COM |  |  |  | 07/19/2016 (IQBLB58P) |  |  | 07/19/2016 (IQBLB58P) | 07/19/2016 (IQBLB58P) |  |  |  | N (IQBLB58P) | 05017789 |  |  | NSPE0010370018
|  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBLB7W8) |  | 8768517 |  | Private IP Port Only (CQBLB7W8) | CQBLB7W8 | 7000 MBPS 7000 MBPS (CQBLB7W8) | P1932463 |  | BOBKTFPX0001 (CQBLB7W8) |  | 5761097 | 360000 270000 314000 2688 1500000 | PVC ID : 5761097 VPN Name : UHG-ECC,UHG-UC,UHG-IPTF,UnitedHealthGroup-ECCMA,UnitedHealthGroup Router Name : MN39E01 VRF Name : V594781:UHGECC,V645094:UHGUC,V601668:UHGIPTF,V601670:UnitedHealthGroupECCMA,V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : v4-152.177.151.97,v6-199.220.202.221,v4-152.187.248.73,v6-68.136.152.241,v4-152.162.11.193 CE Address : v4-152.177.151.98,v6-199.220.202.222,v4-152.187.248.74,v6-68.136.152.242,v4-152.162.11.194 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 06/29/2016 (CQBLB7W8) |  |  | 07/21/2016 (CQBLB7W8) | 07/21/2016 (CQBLB7W8) |  |  |  | N (CQBLB7W8) | 05017789 |  |  | NSPE0010386256
Completed | NY019-02-IJ Colonie NY | 25 POST RD COLONIE, NY 12205-4781 US | 100 MBPS (22697464) | 12/29/2016: 12/29 Customer confirms circuit is up and running. emad@optum.com accepts circuit. | 193200203 | NY019-02-IJ Colonie, NY | Private IP - PIP (22697463) Access (22697464) | 22697463 22697464 | 20 MBPS (22697463) |  | 121237543 (Private IP (PIP)) 121237541 (Access) | C1037404/ADD (22697463) E4012252/ADD (22697464) | 51.L1XX.005901..TWCC (2269746416867301) | 5757593 | 3000 | PVC ID : 5757593 VPN Name : UnitedHealthGroup Router Name : CHTXE03 VRF Name : V637075-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65148 PE IP Address : 152.164.87.149 CE Address : 152.164.87.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22697464) | 1000Base-SX (850nm, Multi Mode Fiber) (22697464) | Ethernet | TIME WARNER CABLE (2269746416867301) | 06/23/2016 (2269746416867301) | 08/23/2016 (2269746416867301) | 08/16/2016 (2269746416867301) | 08/18/2016 (VFORCE) (22697464) | 08/18/2016 (VFORCE) (22697464) | DEMARCDET - main floor suit 5 back data room top rack location RAd port 5 |  | Mary Ellen Roberts 1-800-582-3409 mroberts@aciiv.com | JOHN SERGOT | john.sergot@optum.com | 1-763-744-1582 | 08/18/2016(Private IP - PIP) 08/18/2016(Access) | 12/29/2016 |  | 09/01/2016 (22697463) 08/30/2016 (22697464) | 08/01/2016 | 08/18/2016 |  |  | N (22697463) N (22697464) | U0101953 |  |  | NSPE0010393616
Completed | AZ028-02-IJ Chandler AZ | 460 S BENSON LN STE 11-12 CHANDLER, AZ 85224-5663 US | 100 MBPS (22697508) | 12/29/2016: 12/29 Customer confirms circuit is up and running. drreyes@optum.com accepts circuit. | 193200201 | AZ028-02-IJ Chandler, AZ | Private IP - PIP (22697507) Access (22697508) | 22697507 22697508 | 50 MBPS (22697507) |  | 121230824 (Private IP (PIP)) 121230822 (Access) | C1037405/ADD (22697507) E4012253/ADD (22697508) | 23.KFGX.990470..COXC. (2269750816867301) | 5757597 | 4000 | PVC ID : 5757597 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64634 PE IP Address : 206.115.90.81 CE Address : 206.115.90.82 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22697508) | 1000Base-SX (850nm, Multi Mode Fiber) (22697508) | Ethernet | COX (2269750816867301) | 06/21/2016 (2269750816867301) | 07/19/2016 (2269750816867301) |  | 09/29/2016 (VFORCE) (22697508) |  | DEMARCDET - 1st floor electrical room south east corner cox demark panle port 16 Optical MMf VZB "23.kfgx.990470..coxc." |  | Carlos Pena 1-480-705-6200 cpena@sironainfusion.com | JOHN SERGOT | john.sergot@optum.com | 1-763-744-1582 | 09/29/2016(Private IP - PIP) 09/29/2016(Access) | 12/29/2016 |  | 10/06/2016 (22697507) 10/04/2016 (22697508) | 11/07/2016 | 09/29/2016 |  |  | N (22697507) N (22697508) | U0101953 |  |  | NSPE0010393616
Completed | FL162-02-IJ Tampa FL | 4710 EISENHOWER BLVD STE A12 TAMPA, FL 33634-6347 US | 50 MBPS (22703479) | 11/04/2016: 11/4 Ready to activate | 193200217 | FL162-02-IJ Tampa FL | WAN Analysis Reporting (22703480) Access (22703479) Private IP - PIP (22703478) | 22703480 22703479 22703478 | 10 MBPS (22703478) |  | 121412121 (WAN Analysis Reporting) 121412118 (Access) 121412120 (Private IP (PIP)) | C4004376/ADD (22703478) E4012280/ADD (22703479) | 65/KFGS/106652//FTNC/ (2270347916894302) | 5758330 | 2000 | PVC ID : 5758330 VPN Name : UnitedHealthGroup Router Name : TAMP3E02 VRF Name : V444060-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64637 PE IP Address : 208.219.159.173 CE Address : 208.219.159.174 QoS - Egress Profile: G1 | 1000Base-SX-850nm (22703479) | 1000Base-SX (850nm, Multi Mode Fiber) (22703479) | Ethernet | FRONTIER (2270347916894302) | 08/09/2016 (2270347916894302) | 09/30/2016 (2270347916894302) | 10/27/2016 (2270347916894302) | 11/03/2016 (VFORCE) (22703479) | 11/03/2016 (VFORCE) (22703479) | Demarc: 1ST FLR SERVER ROOM WALLMOUNTED TAGGED |  | Alexander Petrovich 1-813-886-5866 apetrovich@ambienthealth.com | DIANNE REYES | drreyes@optum.com | 1-063-258-8355 | 11/03/2016(WAN Analysis Reporting) 11/03/2016(Access) 11/03/2016(Private IP - PIP) |  |  | 11/09/2016 (22703478) 11/07/2016 (22703479) | 12/13/2016 12/07/2016 | 11/03/2016 |  | Activated/Installed | N (22703480) N (22703479) N (22703478) | U0101953 |  |  | NSPE0010399415
Completed | NC019-02-IJ Kernersville NC | 556 ARBOR HILL RD KERNERSVILLE, NC 27284-3375 US | 50 MBPS (22703617) | 01/19/2017: 01/17 Successfully activated | 193200274 | NC019-02-IJ Kernersville NC | Private IP - PIP (22703616) WAN Analysis Reporting (22703618) Access (22703617) | 22703616 22703618 22703617 | 50 MBPS (22703616) |  | 121302183 (Private IP (PIP)) 121302184 (WAN Analysis Reporting) 121302181 (Access) | C4004377/ADD (22703616) E4012281/ADD (22703617) | 33.L1XX.003433..TWCC (2270361716880201) | 5758337 | 1500 | PVC ID : 5758337 VPN Name : UnitedHealthGroup Router Name : CHRL9E01 VRF Name : V638950:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64621 PE IP Address : 152.164.185.169 CE Address : 152.164.185.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22703617) | 1000Base-SX (850nm, Multi Mode Fiber) (22703617) | Ethernet | TIME WARNER CABLE (2270361716880201) | 06/24/2016 (2270361716880201) | 09/27/2016 (2270361716880201) | 09/27/2016 (2270361716880201) | 09/28/2016 (VFORCE) (22703617) | 09/28/2016 (VFORCE) (22703617) | LEC DEMARC: 1st floor, Suite F, Server room, middle rack EASER DEMARC: BLDG MAIN FLR 1ST RM TELCO |  | Allen Williams 1-336-659-0899 awilliams2@axelacare.com | PRADEEP YADAV | pradeep_yadav@optum.com | 1-981-005-9326 | 09/28/2016(Private IP - PIP) 09/28/2016(WAN Analysis Reporting) 09/28/2016(Access) | 01/17/2017 |  | 10/06/2016 (22703616) 10/04/2016 (22703617) | 10/10/2016 10/14/2016 | 09/28/2016 |  | Activated/Installed | N (22703616) N (22703618) N (22703617) | U0101953 |  |  | NSPE0010399365
Completed | FL147-02-IJ Ocala FL | 202 SW 17TH ST STE C OCALA, FL 34471-8138 US | 50 MBPS (22703635) | 01/23/2017: 01/13 Need to reschedule activation | 193200285 | FL147-02-IJ Ocala FL | Private IP - PIP (22703634) WAN Analysis Reporting (22703636) Access (22703635) | 22703634 22703636 22703635 | 20 MBPS (22703634) |  | 121415824 (Private IP (PIP)) 121415825 (WAN Analysis Reporting) 121415822 (Access) | C4004378/ADD (22703634) E4012282/ADD (22703635) | 40.KFGX.000070..COXC. (2270363516894701) | 5758338 | 1500 | PVC ID : 5758338 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64620 PE IP Address : 152.187.139.25 CE Address : 152.187.139.26 QoS - Egress Profile: G1 | 1000Base-SX-850nm (22703635) | 1000Base-SX (850nm, Multi Mode Fiber) (22703635) | Ethernet | COX (2270363516894701) | 06/22/2016 (2270363516894701) | 07/28/2016 (2270363516894701) |  | 09/06/2016 (VFORCE) (22703635) | 09/02/2016 (VFORCE) (22703635) | DEMARCDET - rack on the wall on the left side of the commost rm. rack position u7 and u9 |  | Janna Bohner 1-352-622-4141 jbohner@ambienthealth.com | PRADEEP YADAV | pradeep_yadav@optum.com | 1-981-005-9326 | 09/02/2016(Private IP - PIP) 09/02/2016(WAN Analysis Reporting) 09/02/2016(Access) |  |  | 09/12/2016 (22703634) 09/08/2016 (22703635) | 09/08/2016 09/14/2016 | 09/02/2016 |  | Activated/Installed | N (22703634) N (22703636) N (22703635) | U0101953 |  |  | NSPE0010399195
Completed | FL148-02-IJ Jacksonville FL | 9655 FLORIDA MINING BLVD W STE 411 JACKSONVILLE, FL 32257-2041 US | 50 MBPS (22703686) | 02/10/2017: 2/9 Ivue request to change the following had been completed A. COS should be R12 B. Multicast: Enabled C. BFD: Enabled | 193200291 | FL148-02-IJ Jacksonville FL | Private IP - PIP (22703685) WAN Analysis Reporting (22703687) Access (22703686) | 22703685 22703687 22703686 | 10 MBPS (22703685) |  | 121417127 (Private IP (PIP)) 121417128 (WAN Analysis Reporting) 121417125 (Access) | C4004380/ADD (22703685) E4012284/ADD (22703686) | 52/KRGN/701984//SB (2270368616894903) | 5758342 | 2000 | PVC ID : 5758342 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64613 PE IP Address : 152.181.236.17 CE Address : 152.181.236.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22703686) | 1000Base-SX (850nm, Multi Mode Fiber) (22703686) | Ethernet | ATT (2270368616894901) ATT (2270368616894903) | 06/24/2016 (2270368616894903) | 07/13/2016 (2270368616894903) | 07/14/2016 (2270368616894903) | 07/19/2016 (VFORCE) (22703686) | 07/19/2016 (VFORCE) (22703686) | DEMARCADDR - 9655 W FLORIDA MINING BLVD JKVL FL DEMARCDET - 1ST FLR EQ RM 3903 #1 PORT 1 |  | Michael Bowen 1-904-652-1990 mbowen@ambienthealth.com | PRADEEP YADAV | pradeep_yadav@optum.com | 1-981-005-9326 | 07/19/2016(Private IP - PIP) 07/19/2016(WAN Analysis Reporting) 07/19/2016(Access) | 11/10/2016 |  | 07/22/2016 (22703685) 07/20/2016 (22703686) | 08/02/2016 08/08/2016 | 07/19/2016 |  | Activated/Installed | N (22703685) N (22703687) N (22703686) | U0101953 |  |  | NSPE0010399272
Completed | GA043-02-IJ Marietta GA | 805 FRANKLIN CT SE STE A MARIETTA, GA 30067-8942 US | 50 MBPS (22698473) | 01/03/2017: 01/03 Successfully activated | 193200322 | GA043-02-IJ Marietta, GA | Private IP - PIP (22698472) Access (22698473) | 22698472 22698473 | 20 MBPS (22698472) |  | 121303760 (Private IP (PIP)) 121303758 (Access) | C4004366/ADD (22698472) E4012265/ADD (22698473) | 38/KRGN/609864//SB (2269847316880201) | 5757722 | 1500 | PVC ID : 5757722 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64602 PE IP Address : 68.137.171.213 CE Address : 68.137.171.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22698473) | 1000Base-SX (850nm, Multi Mode Fiber) (22698473) | Ethernet | ATT (2269847316880201) | 06/21/2016 (2269847316880201) | 07/19/2016 (2269847316880201) | 07/25/2016 (2269847316880201) | 12/29/2016 (VFORCE) (22698473) | 12/29/2016 (VFORCE) (22698473) | DEMARCADDR - 805 FRANKLIN CT SE MRETA GA DEMARCDET - 1ST FLR MOPE WALL MOUNT UNIT 1 H/O ON DSX 1 PORT 2 |  | Sharla Goins 1-770-420-3993 sgoins@ambienthealth.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 12/29/2016(Private IP - PIP) 12/29/2016(Access) | 01/03/2017 |  | 01/06/2017 (22698472) 01/04/2017 (22698473) | 12/29/2016 | 12/29/2016 |  |  | N (22698472) N (22698473) | U0101953 | Jeopardy Notification 3 (12/14/2016) |  | NSPE0010393433
Completed | UNITED HEALTH GROUP | 1250 W 14 MILE RD TROY, MI 48083-1030 US | 100 MBPS (22697622) | 08/17/2016: 8/17- Circuit extended. Waiting for beas install to be scheduled. | 193200324 | UNITED HEALTH GROUP | Private IP - PIP (22697621) Access (22697622) | 22697621 22697622 | 50 MBPS (22697621) |  | 121303728 (Private IP (PIP)) 121303726 (Access) | C1037408/ADD (22697621) E4012255/ADD (22697622) | /KRGN/209305//MB (2269762274246301) | 5757609 | 1500 | PVC ID : 5757609 VPN Name : UHG-ECC Router Name : DTRT3E01 VRF Name : V657944-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65414 PE IP Address : 68.138.154.177 CE Address : 68.138.154.178 QoS - Egress Profile: R12 | 1000Base-T (22697622) | 1000Base-T (22697622) | Ethernet | ATT (2269762274246301) | 06/30/2016 (2269762274246301) | 07/19/2016 (2269762274246301) | 07/19/2016 (2269762274246301) | 08/23/2016 (VFORCE) (22697622) | 08/23/2016 (VFORCE) (22697622) | DEMARCADDR - 1250 W FOURTEEN MILE RD TROY MI DEMARCDET - 1ST FLOOR TELCO ROOM, RR01, PANEL 1 PORT 8 OF 24, TAGGED |  | REBECCA DEAN 1-248-837-7309 rebecca.dean@sourcehov.com | SONJA MROCZYNSKI | sonja_d_mroczynski@optum.com | 1-763-553-4801 | 08/23/2016(Private IP - PIP) 08/23/2016(Access) | 10/13/2016 |  | 08/31/2016 (22697621) 08/29/2016 (22697622) | 08/29/2016 | 08/23/2016 |  |  | N (22697621) N (22697622) | U0101953 |  |  | NSPE0010393433
Completed | GA042-02-IJ Savannah GA | 1000 BUSINESS CENTER DR STE 120 SAVANNAH, GA 31405-7453 US | 50 MBPS (22698436) | 08/25/2016: 8/25- Customer confirmed no extension needed. Waiting for beas install to be scheduled. | 193200323 | GA042-02-IJ Savannah, GA | Private IP - PIP (22698435) Access (22698436) | 22698435 22698436 | 10 MBPS (22698435) |  | 121303756 (Private IP (PIP)) 121303754 (Access) | C4004363/ADD (22698435) E4012260/ADD (22698436) | 40/KRGN/600542//SB (2269843616880201) | 5757714 | 1500 | PVC ID : 5757714 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64604 PE IP Address : 152.187.212.197 CE Address : 152.187.212.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22698436) | 1000Base-SX (850nm, Multi Mode Fiber) (22698436) | Ethernet | ATT (2269843616880201) | 06/30/2016 (2269843616880201) | 08/03/2016 (2269843616880201) | 07/27/2016 (2269843616880201) | 08/30/2016 (VFORCE) (22698436) | 08/30/2016 (VFORCE) (22698436) | DEMARCDET - Demarc: 1st FLR, suit 120, back rm cienna 3903, port 1 |  | Shane Sanders 1-912-355-1053 ssanders1@ambienthealth.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 08/30/2016(Private IP - PIP) 08/30/2016(Access) | 11/23/2016 |  | 09/13/2016 (22698435) 09/09/2016 (22698436) | 09/09/2016 | 08/30/2016 |  |  | N (22698435) N (22698436) | U0101953 |  |  | NSPE0010393433
Completed | FL161-02-IJ Orlando | 12689 CHALLENGER PKWY STE 100 ORLANDO, FL 32826-2750 US | 100 MBPS (22698406) | 11/21/2016: 11/19 Customer acepted the ckt via email (Anupam Datt) | 193200306 | FL161-02-IJ Orlando | Private IP - PIP (22698405) Access (22698406) | 22698405 22698406 | 50 MBPS (22698405) |  | 121303752 (Private IP (PIP)) 121303750 (Access) | C1037418/ADD (22698405) E4012261/ADD (22698406) | 58/KRGN/701599//SB (2269840616880101) | 5757712 | 1500 | PVC ID : 5757712 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64607 PE IP Address : 68.136.158.153 CE Address : 68.136.158.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22698406) | 1000Base-SX (850nm, Multi Mode Fiber) (22698406) | Ethernet | ATT (2269840616880101) | 06/20/2016 (2269840616880101) | 07/07/2016 (2269840616880101) | 07/07/2016 (2269840616880101) | 07/18/2016 (VFORCE) (22698406) | 07/18/2016 (VFORCE) (22698406) | DEMARCADDR - 12689 CHALLENGER PKWY ORL FL DEMARCDET - 1ST FLOOR SERVER ROOM JACK PANEL #1 POSITIONS 3/4 T/R |  | Nelson Perez 1-407-678-2068 nperez@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 07/18/2016(Private IP - PIP) 07/18/2016(Access) | 11/19/2016 |  | 07/18/2016 (22698405) 07/14/2016 (22698406) | 08/01/2016 | 07/18/2016 |  |  | N (22698405) N (22698406) | U0101953 |  |  | NSPE0010393433
Completed | SC007-02-IJ Charleston SC | 4476 LEEDS PL W CHARLESTON, SC 29405-8402 US | 50 MBPS (22698585) | 09/27/2016: 9/27 Ready to activate | 193200329 | SC007-02-IJ Charleston, SC | Access (22698585) Private IP - PIP (22698584) | 22698585 22698584 | 10 MBPS (22698584) |  | 121427825 (Access) 121427827 (Private IP (PIP)) | E4012263/ADD (22698585) C4004365/ADD (22698584) | NCSC/CETHS/EA55Y5XZ/WOW (2269858516896102) | 5757717 | 1500 | PVC ID : 5757717 VPN Name : UnitedHealthGroup Router Name : CPZ3E02 VRF Name : V450868-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64592 PE IP Address : 152.192.8.5 CE Address : 152.192.8.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22698585) | 1000Base-SX (850nm, Multi Mode Fiber) (22698585) | Ethernet | WIDE OPEN WEST (2269858516896102) | 06/24/2016 (2269858516896102) | 07/29/2016 (2269858516896102) | 08/05/2016 (2269858516896102) | 09/26/2016 (VFORCE) (22698585) | 09/26/2016 (VFORCE) (22698585) | DEMARCDET - calex 742 ont(device),floor 1 computer room, |  | Richard Lee 1-843-747-0847 rlee1@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 09/26/2016(Access) 09/26/2016(Private IP - PIP) |  |  | 09/30/2016 (22698585) 10/04/2016 (22698584) | 09/30/2016 | 09/26/2016 |  |  | N (22698585) N (22698584) | U0101953 |  |  | NSPE0010399845
Completed | NY188-02-IJ Syracuse NY | 6508A BASILE ROWE EAST SYRACUSE, NY 13057-2942 US | 50 MBPS (22929566) | 09/15/2016: 9/15- FOC date 9/16. | 193200317 | NY188-02-IJ Syracuse, NY | Private IP - PIP (22929565) Access (22929566) | 22929565 22929566 | 20 MBPS (22929565) |  | 121427875 (Private IP (PIP)) 121427873 (Access) | C4004831/ADD (22929565) E4013643/ADD (22929566) | 36.KFGS.210258..NY (2292956616896101) | 5781747 | 2000 | PVC ID : 5781747 VPN Name : UnitedHealthGroup Router Name : SRDXE01 VRF Name : V699748-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64598 PE IP Address : 68.139.67.65 CE Address : 68.139.67.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22929566) | 1000Base-SX (850nm, Multi Mode Fiber) (22929566) | Ethernet | VERIZON (2292956616896101) | 08/05/2016 (2292956616896101) | 09/16/2016 (2292956616896101) | 09/15/2016 (2292956616896101) |  |  | DEMARCDET - ground floor server room wallmounted tagged |  | Susan Ford 1-888-919-0009 sford@aciiv.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 09/15/2016(Private IP - PIP) 09/15/2016(Access) |  |  | 09/27/2016 (22929565) 09/23/2016 (22929566) | 08/31/2016 | 09/15/2016 |  | Managed | N (22929565) N (22929566) | U0101953 |  |  | NSPE0010399845
Completed | OH730-02-IJ Westerville OH | 35 COLLEGEVIEW RD WESTERVILLE, OH 43081-1463 US | 1 GBPS (22700587) | 11/18/2016: 11/18 Packet lost issue resolved per BNE (Nagendra Ashish) issue with speed and duplex- Customer contact Ronal Wasdo now accept the circuit. | 193200341 | OH730-02-IJ Westerville, OH | Private IP - PIP (22700586) Access (22700587) | 22700586 22700587 | 500 MBPS (22700586) |  | 121427879 (Private IP (PIP)) 121427877 (Access) | C0084993/ADD (22700586) E5003871/ADD (22700587) | 61.L1XX.002285..TWCC (2270058716717301) | 5758116 | 50000 | PVC ID : 5758116 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64622 PE IP Address : 68.139.57.65 CE Address : 68.139.57.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22700587) | 1000Base-SX (850nm, Multi Mode Fiber) (22700587) | Ethernet | TIME WARNER CABLE (2270058716717301) | 06/27/2016 (2270058716717301) | 09/23/2016 (2270058716717301) | 09/22/2016 (2270058716717301) | 10/25/2016 (VFORCE) (22700587) | 10/25/2016 (VFORCE) (22700587) | DEMARCDET - 1st floor telco room. Juniper EX4200, its Optical Port 0003 |  | Scott Jackson 1-614-212-8198 scott.jackson@helioscomp.com | Ronald F. Wasdo | ronald_wasdo@optum.com | 1-763-383-2802 | 10/25/2016(Private IP - PIP) 10/25/2016(Access) | 11/18/2016 |  | 11/04/2016 (22700586) 11/02/2016 (22700587) | 11/02/2016 | 10/25/2016 |  |  | N (22700586) N (22700587) | U0101953 | Jeopardy Notification 1 (09/22/2016) |  | NSPE0010399845
Completed | NE006-02-IJ La Vista NE | 8720 S 114TH ST LA VISTA, NE 68128-5585 US | 50 MBPS (22698728) | 01/09/2017: 01/09 Successfully activated | 193200318 | NE006-02-IJ La Vista, NE | Private IP - PIP (22698727) Access (22698728) | 22698727 22698728 | 10 MBPS (22698727) |  | 121446619 (Private IP (PIP)) 121446617 (Access) | C4004368/ADD (22698727) E4012267/ADD (22698728) | 21.KFGX.000501..COXC. (2269872816896101) | 5757733 | 1500 | PVC ID : 5757733 VPN Name : UnitedHealthGroup Router Name : PLSHXE01 VRF Name : V588242-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64600 PE IP Address : 68.136.231.197 CE Address : 68.136.231.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22698728) | 1000Base-SX (850nm, Multi Mode Fiber) (22698728) | Ethernet | COX (2269872816896101) | 06/21/2016 (2269872816896101) | 08/01/2016 (2269872816896101) |  | 07/22/2016 (VFORCE) (22698728) | 07/22/2016 (VFORCE) (22698728) | DEMARCDET - single floor building Located in back NW corner, Comes off ALU port 2 goes to Accedian #2 SFPA , customer plugs into Accedian #2 SFPB MMF tagged with circuit id (NEED AN 8TH FOOT LADDER TO REACH T |  | Bill Cary 1-402-331-5086 wcary@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 07/22/2016(Private IP - PIP) 07/22/2016(Access) | 01/09/2017 |  | 08/10/2016 (22698727) 08/08/2016 (22698728) | 08/01/2016 | 07/22/2016 |  |  | N (22698727) N (22698728) | U0101953 |  |  | NSPE0010399845
|  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBLB78Z) |  | 8765772 |  | Private IP Port Only (CQBLB78Z) | CQBLB78Z | 7000 MBPS | P1957529 |  | BOBKWHD00001 (CQBLB78Z) |  |  | 0 | VPN Name : UnitedHealthGroup-ECCMA Router Name : MZZ9E01 VRF Name : V600584:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : 152.161.80.1 CE Address : 152.161.80.2 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 06/28/2016 (CQBLB78Z) |  |  | 07/22/2016 (CQBLB78Z) | 07/22/2016 (CQBLB78Z) |  |  |  | N (CQBLB78Z) | 05017789 |  |  | NSPE0010386203
Completed | UHG Eau Claire WI 150M PIP | 2725 MALL DR EAU CLAIRE, WI 54701-6864 US | 400 MBPS (22663947) | 02/08/2017: 02/07 Successfully activated Circuit accepted by john_raymundo@optum.com | 193173545 | UHG Eau Claire WI 150M PIP | Private IP - PIP (22663946) Access (22663947) | 22663946 22663947 | 300 MBPS (22663946) |  | 120303827 (Private IP (PIP)) 120303825 (Access) | C5002121/ADD (22663946) E5003821/ADD (22663947) | 42/KRGN/100185//WT (2266394714102501) | 5754271 | 180000 | PVC ID : 5754271 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64534 PE IP Address : 152.176.171.13 CE Address : 152.176.171.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22663947) | 1000Base-SX (850nm, Multi Mode Fiber) (22663947) | Ethernet | ATT (2266394714102501) | 06/13/2016 (2266394714102501) | 06/28/2016 (2266394714102501) | 06/28/2016 (2266394714102501) | 07/05/2016 (VFORCE) (22663947) | 07/05/2016 (VFORCE) (22663947) | DEMARCADDR - 2725 MALL DR EAU CLAIRE WI DEMARCDET - 1ST FLOOR IT ROOM, WALL MOUNT PORT 6 |  | Ryan Abrahamson 1-715-858-2332 ryan_t_abrahamson@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 07/05/2016(Private IP - PIP) 07/05/2016(Access) | 02/07/2017 |  | 07/08/2016 (22663946) 07/06/2016 (22663947) | 07/25/2016 | 07/05/2016 |  |  | N (22663946) N (22663947) | U0101953 |  |  | NSPE0010380840
Completed | KS016-02-IJ Lenexa | 15529 COLLEGE BLVD LENEXA, KS 66219-1351 US | 400 MBPS (22692142) | 09/22/2016: 9/22- BEAS install scheduled 9/26 | 193200129 | KS016-02-IJ Lenexa | Private IP - PIP (22692141) Access (22692142) | 22692141 22692142 | 150 MBPS (22692141) |  | 120529770 (Private IP (PIP)) 120529748 (Access) | C5002151/ADD (22692141) E5003854/ADD (22692142) | 74/KRGN/904858//SW (2269214216751202) | 5756873 | 30000 | PVC ID : 5756873 VPN Name : UnitedHealthGroup Router Name : IDCXE03 VRF Name : V560358-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64635 PE IP Address : 152.162.55.157 CE Address : 152.162.55.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22692142) | 1000Base-SX (850nm, Multi Mode Fiber) (22692142) | Ethernet | ATT (2269214216751202) | 06/20/2016 (2269214216751202) | 08/30/2016 (2269214216751202) | 08/31/2016 (2269214216751202) | 09/27/2016 (VFORCE) (22692142) | 09/27/2016 (VFORCE) (22692142) | DEMARCADDR - 15529 COLLEGE BLVD LENEXA KS DEMARCDET - 1ST FLR PH/SRVR RM, RR 3, DEMARC PANEL |  | SCOTT WILLIAMS 1-913-747-3785 swilliams@axelacare.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/27/2016(Private IP - PIP) 09/27/2016(Access) |  |  | 10/12/2016 (22692141) 10/10/2016 (22692142) | 10/10/2016 | 09/27/2016 |  |  | N (22692141) N (22692142) | U0101953 | Jeopardy Notification 1 (09/07/2016) |  | NSPE0010388051
Completed | MD083-02-IJ Columbia | 9204 BERGER RD STE A COLUMBIA, MD 21046-1729 US | 50 MBPS (22937408) | 09/07/2016: 9/7- FOC date 2016-09-13 | 193200113 | MD083-02-IJ Columbia | Private IP - PIP (22937407) Access (22937408) | 22937407 22937408 | 20 MBPS (22937407) |  | 120529742 (Private IP (PIP)) 120529740 (Access) | C4004841/ADD (22937407) E4013695/ADD (22937408) | 38.KFGS.301905..CM (2293740816751201) | 5782601 | 7000 | PVC ID : 5782601 VPN Name : UnitedHealthGroup Router Name : RAY9E03 VRF Name : V534296:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64659 PE IP Address : 152.183.150.193 CE Address : 152.183.150.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22937408) | 1000Base-SX (850nm, Multi Mode Fiber) (22937408) | Ethernet | VERIZON (2293740816751201) | 08/08/2016 (2293740816751201) | 09/13/2016 (2293740816751201) | 09/12/2016 (2293740816751201) |  |  | DEMARCADDR - 9204 BERGER RD, COLUMBIA, MD DEMARCDET - DEMARK SUITE A 1 ST FLOOR SERVER TAGGED |  | Shaun Johnson 1-410-203-1701 sjohnson@equinoxhealthcare.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/12/2016(Private IP - PIP) 09/12/2016(Access) |  |  | 09/22/2016 (22937407) 09/20/2016 (22937408) | 09/30/2016 | 09/12/2016 |  |  | N (22937407) N (22937408) | U0101953 |  |  | NSPE0010388051
Completed | C1425-07-IJ Teletech/Global Grossing Phoenix | 801 S 16TH ST PHOENIX, AZ 85034-4133 US | 1 GBPS (22700787) | 10/17/2016: 10/17 Activation completed 10/16 after dispatch ticket to VZ POP - error physical connectin There is still as LOS of signal receive alarm, in both the Tellabs and the Optera, at the A93 site. LOS is most likely due to a physical connectivity problem. . | 193200347 | C1425-07-IJ Teletech/Global Grossing Phoenix | Access (22700787) Private IP - PIP (22700786) | 22700787 22700786 | 800 MBPS (22700786) |  | 121437620 (Access) 121437622 (Private IP (PIP)) | E5003870/ADD (22700787) C0085010/ADD (22700786) |  | 5758115 | 350000 | PVC ID : 5758115 VPN Name : UHG-ECC Router Name : WIT9E01 VRF Name : V773343:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65430 PE IP Address : 152.177.159.9 CE Address : 152.177.159.10 QoS - Egress Profile: C13 | 1000Base-SX-850nm (22700787) | 1000Base-SX (850nm, Multi Mode Fiber) (22700787) | Ethernet | [6 empty] | Type 1 - actual handoff SMF- (ordered as MMF) had escalated dispatch to A93 vz pop to fix physical connection issue. 3 activation attempts- activatipn completed 10/16/16 |  | CARLOS NUNEZ 1-303-397-9097 carlosnunez@teletech.com | TRAVIS DENT | travis_dent@optum.com | 1-763-744-2265 | 08/08/2016(Access) 08/08/2016(Private IP - PIP) | 10/16/2016 |  | 08/03/2016 (22700787) 08/05/2016 (22700786) | 08/02/2016 | 08/08/2016 |  |  | N (22700787) N (22700786) | U0101953 |  |  | NSPE0010400009
Completed | AZ029-02-IJ Chandler AZ | 985 W CHANDLER HEIGHTS RD CHANDLER, AZ 85248-5725 US | 3 MBPS (22718573) | 07/25/2016: 7/24- FOC date 8/1. | 193200363 | AZ029-02-IJ Chandler, AZ | Private IP - PIP (22718572) Access (22718573) | 22718572 22718573 | 3 MBPS (22718572) |  | 121437626 (Private IP (PIP)) 121437624 (Access) | C1037499/ADD (22718572) N1030513/ADD (22718573) N1030514/ADD (22718573) | 14/HCGS/456481//MS (2271857316897501) | 5759736 | 1500 | PVC ID : 5759736 VPN Name : UnitedHealthGroup Router Name : WIT9E01 VRF Name : V603341:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64610 PE IP Address : 68.137.205.21 CE Address : 68.137.205.22 QoS - Egress Profile: R12 |  | DS1 (22718573) | TDM | CENTURYLINK (2271857316897501) | 07/19/2016 (2271857316897501) | 08/01/2016 (2271857316897501) | 07/26/2016 (2271857316897501) |  |  |  |  | Ben Brock 1-623-707-0811 Ben.Brock@optum.com | DIANNE REYES | drreyes@optum.com | 632-588-3551 | 07/26/2016(Private IP - PIP) 07/26/2016(Access) |  |  | 08/08/2016 (22718572) 08/04/2016 (22718573) | 08/05/2016 | 07/26/2016 |  |  | N (22718572) N (22718573) | U0101953 |  |  | NSPE0010400009
Completed | OR007-02-IJ Bend OR | 2065 NE WILLIAMSON CT STE B BEND, OR 97701-3867 US | 50 MBPS (22700939) | 01/06/2017: 01/05 Successfully activated | 193200348 | OR007-02-IJ Bend, OR | Private IP - PIP (22700938) Access (22700939) | 22700938 22700939 | 10 MBPS (22700938) |  | 121437632 (Private IP (PIP)) 121437630 (Access) | C4004373/ADD (22700938) E4012274/ADD (22700939) | 05/KXGS/168754//PN (2270093916897501) | 5758119 | 1500 | PVC ID : 5758119 VPN Name : UnitedHealthGroup Router Name : HIC9E03 VRF Name : V575829:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64597 PE IP Address : 147.225.180.169 CE Address : 147.225.180.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22700939) | 1000Base-SX (850nm, Multi Mode Fiber) (22700939) | Ethernet | CENTURYLINK (2270093916897501) | 09/27/2016 (2270093916897501) | 10/12/2016 (2270093916897501) | 10/11/2016 (2270093916897501) | 10/21/2016 (VFORCE) (22700939) | 10/21/2016 (VFORCE) (22700939) | DEMARCDET - BREAK ROOM IMPOP CLOSET GROUND FLOOR WALL MT OPT PORT 3 MM |  | Michael Sullivan 1-541-382-0287 msullivan@homecareiv.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 10/21/2016(Private IP - PIP) 10/21/2016(Access) | 01/05/2017 |  | 10/27/2016 (22700938) 10/25/2016 (22700939) | 12/01/2016 | 10/21/2016 |  |  | N (22700938) N (22700939) | U0101953 |  |  | NSPE0010400009
Completed | AZ032-02-IJ GOODYEAR AZ | 1981 N PEBBLE CREEK PKWY GOODYEAR, AZ 85395-2543 US | 3 MBPS (22701006) | 06/26/2016: 6/26- Waiting for LEC to provide FOC date. | 193200380 | AZ032-02-IJ GOODYEAR, AZ | Private IP - PIP (22701005) Access (22701006) | 22701005 22701006 | 3 MBPS (22701005) |  | 121683762 (Private IP (PIP)) 121683760 (Access) | C1037426/ADD (22701005) N1030457/ADD (22701006) N1030458/ADD (22701006) | 14/HCGS/456454//MS (2270100616333101) | 5758131 | 1500 | PVC ID : 5758131 VPN Name : UnitedHealthGroup Router Name : WITGE03 VRF Name : V637094:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64902 PE IP Address : 152.177.205.125 CE Address : 152.177.205.126 QoS - Egress Profile: R12 |  | DS1 (22701006) | TDM | CENTURYLINK (2270100616333101) | 06/21/2016 (2270100616333101) | 07/05/2016 (2270100616333101) | 06/28/2016 (2270100616333101) |  |  | DEMARCADDR - 1981 N PEBBLE CREEK PKWY GOODYEAR AZ DEMARCDET - 1ST FLR MAIN IT RISER RM IN SE CORNER OF BLDG. SHELF#1 SLOT 4/4 |  | Jeff Jensen 1-763-744-1651 jeff_jensen@optum.com | JAVIER SEGUI | javier.segui@optum.com | 1-140-754-1814 | 06/28/2016(Private IP - PIP) 06/28/2016(Access) | 08/19/2016 |  | 07/12/2016 (22701005) 07/08/2016 (22701006) | 07/14/2016 | 06/28/2016 |  |  | N (22701005) N (22701006) | U0101953 |  |  | NSPE0010406080
Completed | UT006-02-IJ West Valley UT | 4225 W LAKE PARK BLVD STE 300 WEST VALLEY, UT 84120-8215 US | 500 MBPS (22692112) | 10/28/2016: 10/28 Activation completed | 193200748 | UT006-02-IJ West Valley UT | Private IP - PIP (22692111) Access (22692112) | 22692111 22692112 | 400 MBPS (22692111) |  | 122062333 (Private IP (PIP)) 122062331 (Access) | C5002150/ADD (22692111) E5003853/ADD (22692112) | SL/L1XX/201125/ /TQW /ELK (2269211216719301) | 5756871 | 20000 | PVC ID : 5756871 VPN Name : UnitedHealthGroup Router Name : SLKC9E01 VRF Name : V661371:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64625 PE IP Address : 152.176.210.1 CE Address : 152.176.210.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22692112) | 1000Base-SX (850nm, Multi Mode Fiber) (22692112) | Ethernet | XO (2269211216719301) | 06/20/2016 (2269211216719301) | 08/22/2016 (2269211216719301) | 09/27/2016 (2269211216719301) | 10/13/2016 (VFORCE) (22692112) | 10/13/2016 (VFORCE) (22692112) | DEMARCDET - 1ST FLOOR TELCO ROOM RACK NUMBER 1 FIBER DISTUBUTION PANEL 1 JACK 5 & 6 MMF HANDOFF |  | Tyler Howell 1-801-417-6546 tyler.howell@helioscomp.com | Ronald Wasdo | ronald_wasdo@optum.com | 1-763-383-2802 | 10/13/2016(Private IP - PIP) 10/13/2016(Access) | 10/28/2016 |  | 10/25/2016 (22692111) 10/21/2016 (22692112) | 10/21/2016 | 10/13/2016 |  |  | N (22692111) N (22692112) | U0101953 | Jeopardy Notification 2 (10/03/2016) |  | NSPE0010406817
|  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBLB8R0) | 06/29/2016: 6/29- Request to add 400MEG VLAN OPTUMUC TO EXISTING 4GIG PIPO circuit has been submitted to provisioning. | 8765773 |  | Private IP Port Only (CQBLB8R0) | CQBLB8R0 | 7000 MBPS 7000 MBPS (CQBLB8R0) | P1932297 |  | BOBKTD960001 (CQBLB8R0) |  | 5762263 | 110500 270000 314000 384 360000 1500000 | PVC ID : 5762263 VPN Name : UHG-XLHealth,UHG-UC,UHG-IPTF,UnitedHealthGroup-IDN,UHG-ECC,UnitedHealthGroup Router Name : MN3GE01 VRF Name : V594628:UHGXLHealth,V656367:UHGUC,V594624:UHGIPTF,V594626:UnitedHealthGroupIDN,V594627:UHGECC,V594623:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : v4-152.162.46.225,v6-68.137.39.25,v4-152.176.215.13,v6-152.192.111.185,v4-147.225.22.233,v6-152.161.107.161 CE Address : v4-152.162.46.226,v6-68.137.39.26,v4-152.176.215.14,v6-152.192.111.186,v4-147.225.22.234,v6-152.161.107.162 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 06/30/2016 (CQBLB8R0) |  |  | 07/25/2016 (CQBLB8R0) | 07/25/2016 (CQBLB8R0) |  |  |  | N (CQBLB8R0) | 05017789 |  |  | NSPE0010386303
Completed |  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBLB8S8) |  | 8765771 |  | Private IP Port Only (CQBLB8S8) | CQBLB8S8 | 7000 MBPS | P1955436 |  | BOBKWCW20001 (CQBLB8S8) |  |  | 24576 | VPN Name : Alere-LLC-WAN Router Name : MZZGE01 VRF Name : Vg35543:AlereLLCWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : 152.176.170.69 CE Address : 152.176.170.70 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 06/30/2016 (CQBLB8S8) |  |  | 07/25/2016 (CQBLB8S8) | 07/25/2016 (CQBLB8S8) |  |  |  | N (CQBLB8S8) | 05017789 |  |  | NSPE0010386278
Completed | OH018-02-IJ | 250 PROGRESSIVE WAY BLDG 3 WESTERVILLE, OH 43082-9615 US | 1 GBPS (22738849) | 09/22/2017: 09/21 Successfully activated | 193222077 | OH018-02-IJ | Private IP - PIP (22738848) Access (22738849) | 22738848 22738849 | 500 MBPS (22738848) |  | 122762084 (Private IP (PIP)) 122762082 (Access) | C0085275/ADD (22738848) E5003934/ADD (22738849) | 94/KRGN/201379//OB (2273884917116801) | 5761750 | 10000 | PVC ID : 5761750 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64631 PE IP Address : 152.181.239.1 CE Address : 152.181.239.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22738849) | 1000Base-SX (850nm, Multi Mode Fiber) (22738849) | Ethernet | ATT (2273884917116801) | 08/03/2016 (2273884917116801) | 08/18/2016 (2273884917116801) | 08/04/2016 (2273884917116801) | 08/08/2016 (VFORCE) (22738849) |  | DEMARCDET - DEMARC: 1ST FLR MAIN TELCO RM,BACK BOARD MOUNTED PORT 5 cienna 3930 TAGGED WITH CIRCUIT ID |  | SCOTT JACKSON 1-614-212-8198 scott.jackson@helioscomp.com | DEVEN PATTERSON | deven_patterson@optum.com | 1-210-877-7969 | 08/18/2016(Private IP - PIP) 08/18/2016(Access) | 09/21/2017 |  | 08/29/2016 (22738848) 08/25/2016 (22738849) | 09/12/2016 | 08/18/2016 |  |  | N (22738848) N (22738849) | U0101953 |  |  | NSPE0010421749
Completed | C1558-05-IJ Doral FL ECC | 1525 NW 98TH CT DORAL, FL 33172-2759 US | 200 MBPS (22738742) | 09/29/2016: 9/29 Activation completed 9/28 | 193222553 | C1558-05-IJ Doral FL ECC | Private IP - PIP (22738741) Access (22738742) | 22738741 22738742 | 100 MBPS (22738741) |  | 122651486 (Private IP (PIP)) 122651484 (Access) | C5002176/ADD (22738741) E5003933/ADD (22738742) |  | 5761745 | 110000 | PVC ID : 5761745 VPN Name : UHG-ECC Router Name : 1MJ3E01 VRF Name : V648854-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65526 PE IP Address : 68.136.64.121 CE Address : 68.136.64.122 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22738742) | Ethernet | [5 empty] | 07/13/2016 (CCP) (22738741) 07/13/2016 (CCP) (22738742) | 1000Base-SX (850nm, Multi Mode Fiber 1st floor mc lineup,not extended. Hard Loop placed at demark for testing as requested. --bjf5 demark:- RR 318.10.2:1.2 |  | CHUCK MATULIK 1-954-903-5950 cmatulik@conveyhs.com | William Goss | william_Goss@optum.com | 1-763-744-1528 | 08/01/2016(Private IP - PIP) 08/01/2016(Access) | 09/28/2016 |  | 07/25/2016 (22738741) 07/21/2016 (22738742) | 07/26/2016 | 08/01/2016 |  |  | N (22738741) N (22738742) | U0101953 |  |  | NSPE0010420919
Completed | C1333-05-IJ West Omaha ECC | 9910 MAPLE ST OMAHA, NE 68134-5551 US | 1 GBPS (22738918) | 09/29/2016: 9/29 Activation completed 9/29 | 193222100 | C1333-05-IJ West Omaha ECC | Private IP - PIP (22738917) Access (22738918) | 22738917 22738918 | 500 MBPS (22738917) |  | 122762088 (Private IP (PIP)) 122762086 (Access) | C0085272/ADD (22738917) E5003935/ADD (22738918) | 21.KFGX.000509..COXC. (2273891871061301) | 5761752 | 250000 | PVC ID : 5761752 VPN Name : UHG-ECC Router Name : PLSHXE01 VRF Name : V449266-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65478 PE IP Address : 159.24.239.1 CE Address : 159.24.239.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22738918) | 1000Base-SX (850nm, Multi Mode Fiber) (22738918) | Ethernet | COX (2273891871061301) | 06/29/2016 (2273891871061301) | 08/09/2016 (2273891871061301) |  | 09/23/2016 (VFORCE) (22738918) | 09/23/2016 (VFORCE) (22738918) | DEMARCDET - BLDG MAIN FLR 1ST RM TELCO |  | DANIEL HOLCOMB 1-402-651-2392 daniel.holcomb@alorica.com | Will Goss | william_Goss@optum.com | 1-763-744-1528 | 09/23/2016(Private IP - PIP) 09/23/2016(Access) | 09/29/2016 |  | 09/26/2016 (22738917) 09/22/2016 (22738918) | 10/26/2016 | 09/23/2016 |  |  | N (22738917) N (22738918) | U0101953 |  |  | NSPE0010421749
Completed | UHG | 624 S GRAND AVE LOS ANGELES, CA 90017-3335 US | 1 GBPS (22751948) | 09/28/2016: 9/28 Ive requested for 9/30 3pm cst | 193221989 | UHG | Private IP - PIP (22751947) Access (22751948) | 22751947 22751948 | 600 MBPS (22751947) |  | 123006387 (Private IP (PIP)) 123006385 (Access) | C0085376/ADD (22751947) E5003951/ADD (22751948) |  | 5762974 | 180000 | PVC ID : 5762974 VPN Name : UHG-ECC Router Name : RTO3E04 VRF Name : V650644-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65488 PE IP Address : 199.220.198.221 CE Address : 199.220.198.222 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22751948) | Ethernet |  |  |  |  | 09/09/2016 (CCP) (22751947) 09/09/2016 (CCP) (22751948) | 10/04/2016 (CCP) (22751947) 10/04/2016 (CCP) (22751948) |  |  | TRIEU VU 1-714-766-0633 trieu.vu@teleperformance.com | Trix Lizardo | trix.lizardo@teleperformance.com | 1-213-873-5110 | 07/31/2016(Private IP - PIP) 07/31/2016(Access) |  |  | 08/04/2016 (22751947) 08/02/2016 (22751948) | 07/28/2016 | 07/31/2016 |  |  | N (22751947) N (22751948) | U0101953 |  |  | NSPE0010421497
Completed | C1530-08-IJ | 11830 WEBB CHAPEL RD STE 200 DALLAS, TX 75234-2784 US | 1 GBPS (22751861) | 10/06/2016: 10/6 Ivue requested 10/11 3pm CST | 193221958 | C1530-08-IJ | Private IP - PIP (22751860) Access (22751861) | 22751860 22751861 | 600 MBPS (22751860) |  | 123006383 (Private IP (PIP)) 123006381 (Access) | C0085443/ADD (22751860) E5003950/ADD (22751861) |  | 5762970 | 180000 | PVC ID : 5762970 VPN Name : UHG-ECC Router Name : IAEXE01 VRF Name : V652655-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65489 PE IP Address : 152.181.75.193 CE Address : 152.181.75.194 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (22751861) | Ethernet | [5 empty] | 07/14/2016 (CCP) (22751860) 07/14/2016 (CCP) (22751861) | 1st floor data center, cage B-19-01-B SM 31/32 |  | Chuck Close 1-972-830-1891 CloseC@aegiscomgroup.com | Sanjay Sharma | JohnsonT@aegiscomgroup.com | 1-972-830-1834 | 09/19/2016(Private IP - PIP) 09/19/2016(Access) | 10/12/2016 |  | 09/28/2016 (22751860) 09/26/2016 (22751861) | 10/04/2016 | 09/19/2016 |  |  | N (22751860) N (22751861) | U0101953 | Jeopardy Notification 3 (09/06/2016) |  | NSPE0010421497
Completed | UUT05-07-IJ Salt Lake City | 2525 S LAKE PARK BLVD SALT LAKE CITY, UT 84120-8230 US | 300 MBPS (22739189) | 10/06/2016: 10/6 Activation failed 10/6 7pm cst- BnE submit ETMS ticket 2016100700326 to check fiber at site. | 193221770 | UUT05-07-IJ Salt Lake City | Private IP - PIP (22739188) Access (22739189) | 22739188 22739189 | 150 MBPS (22739188) |  | 123034778 (Private IP (PIP)) 123034776 (Access) | C5002178/ADD (22739188) E5003937/ADD (22739189) | 69/KXGS/170374//MS (2273918917154401) | 5761764 | 25000 | PVC ID : 5761764 VPN Name : UnitedHealthGroup Router Name : SLKC9E01 VRF Name : V661371:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64762 PE IP Address : 152.164.105.189 CE Address : 152.164.105.190 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22739189) | 1000Base-LX (1310nm Single Mode Fiber) (22739189) | Ethernet | CENTURYLINK (2273918917154401) | 07/15/2016 (2273918917154401) | 09/22/2016 (2273918917154401) | 08/30/2016 (2273918917154401) | 08/31/2016 (VFORCE) (22739189) | 08/31/2016 (VFORCE) (22739189) | DEMARCDET - MAIN TELCO 1ST FLOOR CENTURLINK RELAY RACK SHELF 3 PORT 1 OPTICAL SMF(SINGLE MODE FIBER) |  | Gregory Collins 1-801-982-3004 greg_collins@uhg.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 08/31/2016(Private IP - PIP) 08/31/2016(Access) | 10/11/2016 |  | 10/03/2016 (22739188) 09/29/2016 (22739189) | 08/24/2016 | 08/31/2016 |  |  | N (22739188) N (22739189) | U0101953 |  |  | NSPE0010421735
Completed | CA174-02-IJ Menlo Park | 2440 SAND HILL RD MENLO PARK, CA 94025-6900 US | 400 MBPS (22739273) | 08/25/2016: 8/25- Customer confirmed circuit extended. Waiting for beas install to be scheduled. | 193221748 | CA174-02-IJ Menlo Park | Private IP - PIP (22739272) Access (22739273) | 22739272 22739273 | 150 MBPS (22739272) |  | 123034782 (Private IP (PIP)) 123034780 (Access) | C5002179/ADD (22739272) E5003938/ADD (22739273) | 86/KRGN/580925//PT (2273927317154601) | 5761772 | 1500 | PVC ID : 5761772 VPN Name : UnitedHealthGroup Router Name : HAY9E02 VRF Name : Vb46944:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64669 PE IP Address : 206.115.4.253 CE Address : 206.115.4.254 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22739273) | 1000Base-LX (1310nm Single Mode Fiber) (22739273) | Ethernet | ATT (2273927317154601) | 06/30/2016 (2273927317154601) | 07/15/2016 (2273927317154601) | 07/14/2016 (2273927317154601) | 08/30/2016 (VFORCE) (22739273) | 08/30/2016 (VFORCE) (22739273) | DEMARCADDR - 2440 SAND HILL RD MNLO PK DEMARCDET - 1.1 MPOE, WALL MNT'D ELECT. PORT#1 TO JACKPANEL#1-POS#3 |  | Sean Kochems 1-530-879-7043 sean.kochems@am.jll.com | SONJA MROCZYNSKI | sonja_d_mroczynski@optum.com | 1-763-553-4801 | 08/30/2016(Private IP - PIP) 08/30/2016(Access) | 09/14/2016 |  | 09/13/2016 (22739272) 09/09/2016 (22739273) | 09/09/2016 | 08/30/2016 |  |  | N (22739272) N (22739273) | U0101953 |  |  | NSPE0010421735
Completed | C1518-08-IJ Columbus OH | 4335 EQUITY DR COLUMBUS, OH 43228-3842 US | 500 MBPS (22731332) | 08/04/2016: 8/4- Circuit installed. Waiting for John to confirm demark. | 193221990 | C1518-08-IJ Columbus, OH | Private IP - PIP (22731331) Access (22731332) | 22731331 22731332 | 300 MBPS (22731331) |  | 123006379 (Private IP (PIP)) 123006377 (Access) | C5002170/ADD (22731331) E5003918/ADD (22731332) | 5B/KFFN/002715/LVLC (2273133211490901) | 5761053 | 90000 | PVC ID : 5761053 VPN Name : UHG-ECC Router Name : CMKXE01 VRF Name : V676351-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65516 PE IP Address : 152.185.144.81 CE Address : 152.185.144.82 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22731332) | 1000Base-SX (850nm, Multi Mode Fiber) (22731332) | Ethernet | LEVEL 3 (2273133211490901) | 07/19/2016 (2273133211490901) | 07/29/2016 (2273133211490901) | 08/03/2016 (2273133211490901) | 08/10/2016 (VFORCE) (22731332) | 08/10/2016 (VFORCE) (22731332) | DEMARCDET - Demarc: 1st flr data rm, level 3 cabinet 2 ciscoo 3600 labeled with clmeohctw2001 port 014, LC fiber connector tagged with circuit id. |  | Jesse Garrett 1-801-257-5833 jesse.garrett@teleperformance.com | William Goss | william_Goss@optum.com | 1-763-744-1528 | 08/10/2016(Private IP - PIP) 08/10/2016(Access) | 10/12/2016 |  | 08/11/2016 (22731331) 08/09/2016 (22731332) | 08/29/2016 | 08/10/2016 |  |  | N (22731331) N (22731332) | U0101953 |  |  | NSPE0010421497
Completed | C1093-05-IJ ATT Secaucus Data Center | 15 ENTERPRISE AVE N SECAUCUS, NJ 07094-2505 US | 500 MBPS (22753759) | 10/07/2016: 10/7 Resched activation 10/12/2016 8:00:00 AM CST | 193234163 | C1093-05-IJ ATT Secaucus Data Center | Private IP - PIP (22753755) Access (22753759) | 22753755 22753759 | 300 MBPS (22753755) |  | 123815986 (Private IP (PIP)) 123815984 (Access) | C5002183/ADD (22753755) E5003955/ADD (22753759) |  | 5763134 | 140000 | PVC ID : 5763134 VPN Name : UHG-ECC Router Name : WOR9E02 VRF Name : V771145:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65440 PE IP Address : 152.162.60.61 CE Address : 152.162.60.62 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22753759) | Ethernet |  |  |  |  | 08/26/2016 (CCP) (22753755) 08/26/2016 (CCP) (22753759) | 09/03/2016 (CCP) (22753755) 09/03/2016 (CCP) (22753759) | 1st floor data center, vzb cabinet 1079.70.5:1.1 (Ran fiber to media converter) |  | BILL LEE 1-732-733-9037 wl2317@att.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 | 09/29/2016(Private IP - PIP) 09/29/2016(Access) | 10/12/2016 |  | 10/06/2016 (22753755) 10/04/2016 (22753759) | 10/24/2016 | 09/29/2016 |  |  | N (22753755) N (22753759) | U0101953 | Jeopardy Notification 3 (09/14/2016) |  | NSPE0010434992
Completed | C1246-05-IJ El Segundo | 200 N NASH ST EL SEGUNDO, CA 90245-4529 US | 500 MBPS (22754578) | 10/07/2016: 10/7 resched 10/11/2016 4:00:00 PM CST | 193234508 | C1246-05-IJ El Segundo | Private IP - PIP (22754577) Access (22754578) | 22754577 22754578 | 300 MBPS (22754577) |  | 123859838 (Private IP (PIP)) 123859836 (Access) | C5002184/ADD (22754577) E5003957/ADD (22754578) |  | 5763230 | 140000 | PVC ID : 5763230 VPN Name : UHG-ECC Router Name : BB39E01 VRF Name : V670563:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65458 PE IP Address : 152.162.190.101 CE Address : 152.162.190.102 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22754578) | Ethernet | [5 empty] | 07/27/2016 (CCP) (22754577) 07/27/2016 (CCP) (22754578) |  |  | paul ladue 1-888-638-6771 paul.ladue@centurylink.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 | 07/29/2016(Private IP - PIP) 07/29/2016(Access) | 10/13/2016 |  | 08/12/2016 (22754577) 08/10/2016 (22754578) | 07/28/2016 | 07/29/2016 |  |  | N (22754577) N (22754578) | U0101953 |  |  | NSPE0010440151
Completed | UNITED HEALTH GROUP | 1250 W 14 MILE RD TROY, MI 48083-1030 US | 100 MBPS (22753751) | 10/28/2016: 10/28 Resched activation for 10/26 to bring up BGP, was not turned up on 10/13 customer wasn't fully ready. Complete activation done on 10/26 | 193234164 | UNITED HEALTH GROUP | Private IP - PIP (22753750) Access (22753751) | 22753750 22753751 | 50 MBPS (22753750) |  | 123815982 (Private IP (PIP)) 123815980 (Access) | C1037774/ADD (22753750) E4012508/ADD (22753751) | /KRGN/209317//MB (2275375174246301) | 5763132 | 1500 | PVC ID : 5763132 VPN Name : UHG-ECC-TCW Router Name : DTRT3E01 VRF Name : V663964-UHGECCTCW Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65204 PE IP Address : 152.183.93.209 CE Address : 152.183.93.210 QoS - Egress Profile: R12 | 1000Base-T (22753751) | 1000Base-T (22753751) | Ethernet | ATT (2275375174246301) | 07/06/2016 (2275375174246301) | 07/20/2016 (2275375174246301) | 07/19/2016 (2275375174246301) | 08/23/2016 (VFORCE) (22753751) | 08/23/2016 (VFORCE) (22753751) | DEMARCADDR - 1250 W FOURTEEN MILE RD TROY MI DEMARCDET - 1ST FLOOR TELCO ROOM, RR 01, PANEL 1, PORT 9 OF 24. TAGGED AND |  | REBECCA DEAN 1-248-837-7309 rebecca.dean@sourcehov.com | SONJA MROCZYNSKI | sonja_d_mroczynski@optum.com | 1-763-553-4801 | 08/23/2016(Private IP - PIP) 08/23/2016(Access) | 10/26/2016 |  | 08/31/2016 (22753750) 08/29/2016 (22753751) | 08/29/2016 | 08/23/2016 |  |  | N (22753750) N (22753751) | U0101953 |  |  | NSPE0010434992
Completed | WV040-02-IJ Charleston | 700 WASHINGTON ST E CHARLESTON, WV 25301-1657 US | 100 MBPS (22764799) | 08/11/2016: 8/11- Beas install scheduled for 8/12. | 193240499 | WV040-02-IJ Charleston | Private IP - PIP (22764798) Access (22764799) | 22764798 22764799 | 50 MBPS (22764798) |  | 124385337 (Private IP (PIP)) 124385335 (Access) | C1037834/ADD (22764798) E4012567/ADD (22764799) | 50/KFGS/032992//FVNC/ (2276479915185901) | 5764302 | 25000 | PVC ID : 5764302 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64670 PE IP Address : 152.183.11.53 CE Address : 152.183.11.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22764799) | 1000Base-SX (850nm, Multi Mode Fiber) (22764799) | Ethernet | FRONTIER (2276479915185901) | 07/18/2016 (2276479915185901) | 08/16/2016 (2276479915185901) |  | 08/11/2016 (VFORCE) (22764799) | 08/16/2016 (VFORCE) (22764799) | DEMARCDET - 1st Floor Telco Room Closet in the north wall stairwall and wall mounted tagged with ckt ID |  | Martin Riggs 1-304-389-4994 w.martin.riggs@gmail.com | Javier Segui | javier.segui@optum.com | 1-407-541-8143 | 08/16/2016(Private IP - PIP) 08/16/2016(Access) | 08/22/2016 |  | 08/25/2016 (22764798) 08/23/2016 (22764799) | 08/19/2016 | 08/16/2016 |  |  | N (22764798) N (22764799) | U0101953 |  |  | NSPE0010446960
Completed | TN019-02-IJ Franklin TN | 1897 GENERAL GEORGE PATTON DR STE 112 FRANKLIN, TN 37067-6319 US | 100 MBPS (22761360) | 07/25/2016: 7/25- Pending beas install. Informed John, We tried to have the dispatch schedule on Monday however, our tech called LCON: RANDY PENNINGTO / 615-791-5256 number just ring and ALCON: DON OSBORN / 214-647-4442 this is not a working number. Could you please validate LCON and contact information or have someone call dispatch as soon as possible to schedule? 877-628-6672 reference 22761360 | 193238750 | TN019-02-IJ Franklin, TN | Access (22761360) Private IP - PIP | 22761360 | 10 MBPS |  | 89524439 (Access) 89524521 | E4012570/ADD (22761360) E4008470/REMOVE (22761360) |  |  |  |  | 100Base-TX (22761360) | 100Base-TX (22761360) | Ethernet |  |  |  |  | 07/27/2016 (VFORCE) (22761360) |  |  |  | RANDY PENNINGTON 1-615-791-5256 randy.pennington@catamaranrx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 07/28/2016(Access) |  |  | 08/01/2016 (22761360) | 09/02/2016 08/12/2016 | 07/28/2016 |  |  | N (22761360) N | U0101953 |  |  | NSPE0010444759
Completed | C1600-02-IJ Dialog Direct Highland Park | 13700 OAKLAND ST HIGHLAND PARK, MI 48203-3173 US | 250 MBPS | 07/11/2016: 7/11- VPN updated, circuit ready for activation. | 193244608 | C1600-02-IJ Dialog Direct Highland Park | Private IP - PIP (22771840) Access | 22771840 | 200 MBPS (22771840) |  | 118399323 (Private IP (PIP)) 118399321 | C0084374/NONE (22771840) |  | 5753013 | 40000 | PVC ID : 5753013 VPN Name : UHG-ECC Router Name : DTRT3E01 VRF Name : V657944-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65496 PE IP Address : 152.161.38.145 CE Address : 152.161.38.146 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | John Sergot 1-763-744-1582 john_sergot@optum.com | John Sergot | john_sergot@optum.com | 1-763-744-1582 | 07/08/2016(Private IP |  |  | 07/06/2016 (22771840) | 07/15/2016 | 07/08/2016 |  |  | N (22771840) N | U0101953 |  |  | NSPE0010451815
Completed | PA007-01-IJ Newton Square | 15 CAMPUS BLVD NEWTOWN SQUARE, PA 19073-3200 US | 1 GBPS | 08/17/2016: 8/17- Hotcut scheduled for 8/18 at 230am CST. | 193252284 | PA007-01-IJ Newton Square | Private IP - PIP (22782927) Access | 22782927 | 1 GBPS (22782927) |  | 66170213 (Private IP (PIP)) 66170211 | C0050641/NONE (22782927) |  | 5590934 | 30000 | PVC ID : 5590934 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64887 PE IP Address : 152.185.81.157 CE Address : 152.185.81.158 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Andrew Lexa 1-610-550-7935 alexa@ehrdocs.com | Sonja Mroczynski | sonja_d_mroczynski@optum.com | 1-763-553-4801 | 08/18/2016(Private IP |  |  | 07/08/2016 (22782927) | 07/19/2016 | 08/18/2016 |  |  | N (22782927) N | U0101953 |  |  | NSPE0010455446
Completed | MA713-02-IJ Waltham MA | 265 WINTER ST WALTHAM, MA 02451-8717 US | 500 MBPS (22804235) | 08/04/2016: 8/4- Ready for activation. | 193261415 | MA713-02-IJ Waltham, MA | Private IP - PIP (22804234) Access (22804235) | 22804234 22804235 | 50 MBPS (22804234) |  | 124982608 (Private IP (PIP)) 124982606 (Access) | C5002232/ADD (22804234) E5004055/ADD (22804235) |  | 5768182 | 10000 | PVC ID : 5768182 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64565 PE IP Address : 152.187.183.181 CE Address : 152.187.183.182 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22804235) | Ethernet | [5 empty] | 08/12/2016 (CCP) (22804234) 08/12/2016 (CCP) (22804235) | Room com/ Floor(FL) 1 MMF |  | Doug Fleming 1-781-292-3505 dfleming@dovetailhealth.com | Manoj Reddy | manoj_reddy@optum.com | 1-763-744-1925 | 08/04/2016(Private IP - PIP) 08/04/2016(Access) | 11/14/2016 |  | 08/19/2016 (22804234) 08/17/2016 (22804235) | 07/29/2016 | 08/04/2016 |  |  | N (22804234) N (22804235) | U0101953 |  |  | NSPE0010461599
|  | 1 MAIN ST CAMBRIDGE, MA 02142 USA | 100 MBPS (CQBLCMV9) 20 MBPS (CQBLCMWB) | 03/24/2017: Background: Inside fiber Move request Status:Per customer move completed 3/24 (MDF 1014 to MDF 1015 Next action: Prov Bcom order Who owns the next action: Prov/BnE | 8785028 |  | EACS (CQBLCMV9) Private IP (CQBLCMWB) | CQBLCMV9 CQBLCMWB | 100 MBPS (CQBLCMV9) 20 MBPS (CQBLCMWB) | P2038039 P2038118 |  | EDBK2WK60001 (CQBLCMV9) BCBK2WP90001 (CQBLCMWB) | [13 empty] | move fiber order- demarc moved from LAB MDF ROOM 1014 TO THE UHG MDF ROOM 1015 |  | DOUG DOWNIE 5084931751 DOUGLAS_DOWNIE@UHG.COM |  |  |  | 03/24/2017 (CQBLCMV9) 03/24/2017 (CQBLCMWB) | 03/24/2017 |  | 10/28/2016 (CQBLCMV9) 10/28/2016 (CQBLCMWB) | 10/28/2016 (CQBLCMV9) 10/28/2016 (CQBLCMWB) |  |  |  | N (CQBLCMV9) N (CQBLCMWB) | 05017789 |  |  | NSPE0010457490
Completed | AZ001-02-IJ Phoenix AZ | 8041 N BLACK CANYON HWY PHOENIX, AZ 85021-4876 US | 50 MBPS (22834882) | 01/06/2017: Cust accepted ckt/Activation completed | 193280223 | AZ001-02-IJ Phoenix, AZ | Private IP - PIP (22834881) Access (22834882) | 22834881 22834882 | 20 MBPS (22834881) |  | 125834077 (Private IP (PIP)) 125834075 (Access) | C4004705/ADD (22834881) E4013077/ADD (22834882) | 19/KXGS/173753//MS (2283488217612101) | 5771826 | 30000 | PVC ID : 5771826 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64569 PE IP Address : 152.187.41.173 CE Address : 152.187.41.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22834882) | 1000Base-SX (850nm, Multi Mode Fiber) (22834882) | Ethernet | CENTURYLINK (2283488217612101) | 11/15/2016 (2283488217612101) | 12/14/2016 (2283488217612101) | 12/16/2016 (2283488217612101) | 12/28/2016 (VFORCE) (22834882) | 12/28/2016 (VFORCE) (22834882) | DEMARCADDR - X DEMARCDET - UPLINK IS IN OPTICAL PORT 6, DROP IS IN OPTICAL PORT 3. DEMARK IS LOCATED IN THE 1ST FLOOR MAIN MPOP,REAR OF BUILDING,WALL MOUNTED |  | JENNIFER A WILLIAMS 1-623-707-0050 jennifer.a.williams@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 12/28/2016(Private IP - PIP) 12/28/2016(Access) | 01/05/2017 |  | 01/09/2017 (22834881) 01/05/2017 (22834882) | 01/05/2017 | 12/28/2016 |  |  | N (22834881) N (22834882) | U0101953 | Jeopardy Notification 1 (12/20/2016) |  | NSPE0010476782
Completed | CA176-02-IJ March Vision Care | 6701 CENTER DR W LOS ANGELES, CA 90045-1535 US | 500 MBPS (22834879) | 01/03/2017: 01/03 Successfully activated | 193280206 | CA176-02-IJ March Vision Care | Private IP - PIP (22834878) Access (22834879) | 22834878 22834879 | 150 MBPS (22834878) |  | 125834073 (Private IP (PIP)) 125834071 (Access) | C5002255/ADD (22834878) E5004097/ADD (22834879) |  | 5771831 | 1500 | PVC ID : 5771831 VPN Name : UnitedHealthGroup Router Name : LO03E01 VRF Name : V690366-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65104 PE IP Address : 68.137.179.65 CE Address : 68.137.179.66 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22834879) | Ethernet |  |  |  |  | 09/09/2016 (CCP) (22834878) 09/09/2016 (CCP) (22834879) | 10/04/2016 (CCP) (22834878) 10/04/2016 (CCP) (22834879) | site at L25, building security provided access to the mpoe, removed the hard loop, installed a 6m lc/lc multimode fiber jumper from the overture to the customer fiber panel went to suite 790 and customer provided access to the server room, placed a hard loop |  | Shawn Shahzad 1-310-216-2306 sshahzad@marchvisioncare.com | RANJI ADHIKAI | ranjit_adhikari@optum.com | 1-763-744-1957 | 09/27/2016(Private IP - PIP) 09/27/2016(Access) | 01/03/2017 |  | 10/11/2016 (22834878) 10/07/2016 (22834879) | 09/27/2016 | 09/27/2016 |  |  | N (22834878) N (22834879) | U0101953 |  |  | NSPE0010476782
Completed | TN025-02-IJ Memphis TN | 6410 POPLAR AVE STE 800 MEMPHIS, TN 38119-4839 US | 200 MBPS (22834885) | 03/01/2017: 03/01 Successfully activated. al_thoreson@optum.com accepted the circuit. | 193280208 | TN025-02-IJ Memphis, TN | Private IP - PIP (22834884) Access (22834885) | 22834884 22834885 | 100 MBPS (22834884) |  | 125834085 (Private IP (PIP)) 125834083 (Access) | C5002256/ADD (22834884) E5004099/ADD (22834885) | 3M/KFFN/002582/LVLC (2283488517612501) | 5771827 | 2500 | PVC ID : 5771827 VPN Name : UnitedHealthGroup Router Name : PLVXE01 VRF Name : V669152-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64559 PE IP Address : 68.139.172.5 CE Address : 68.139.172.6 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22834885) | 1000Base-SX (850nm, Multi Mode Fiber) (22834885) | Ethernet | LEVEL 3 (2283488517612501) | 11/14/2016 (2283488517612501) | 12/16/2016 (2283488517612501) | 12/13/2016 (2283488517612501) | 12/29/2016 (VFORCE) (22834885) | 12/29/2016 (VFORCE) (22834885) | DEMARCDET - 8th Floor suite 800 customer data room. south west wall corner panel position 1 SFP.Cisco3600 port gig0/14. |  | Cody Jones 1-901-653-2585 cody.jones@helioscomp.com | DEVEN PATTERSON | deven_patterson@optum.com | 1-210-877-7969 | 12/29/2016(Private IP - PIP) 12/29/2016(Access) | 03/01/2017 |  | 01/04/2017 (22834884) 01/02/2017 (22834885) | 12/28/2016 | 12/29/2016 |  |  | N (22834884) N (22834885) | U0101953 | Jeopardy Notification 1 (11/04/2016) |  | NSPE0010476782
Completed | FL182-02-IJ Tampa FL | 175 KELSEY LN TAMPA, FL 33619-4336 US | 500 MBPS (22834876) | 03/17/2017: 03/16 Successfully activated | 193280207 | FL182-02-IJ Tampa, FL | Access (22834876) Private IP - PIP (22834875) | 22834876 22834875 | 300 MBPS (22834875) |  | 125834079 (Access) 125834081 (Private IP (PIP)) | E5004098/ADD (22834876) C5002257/ADD (22834875) | TPA5-700333-01 (2283487617610001) | 5771832 | 10000 | PVC ID : 5771832 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64560 PE IP Address : 159.24.133.5 CE Address : 159.24.133.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22834876) | 1000Base-SX (850nm, Multi Mode Fiber) (22834876) | Ethernet | BRIGHT HOUSE (2283487617610001) | 07/20/2016 (2283487617610001) | 09/23/2016 (2283487617610001) | 12/22/2016 (2283487617610001) | 12/30/2016 (VFORCE) (22834876) | 12/30/2016 (VFORCE) (22834876) | the fiber term shelf is mounted on the wall next to an XO/BHN ME3400 2CS. The ASR920 is in the customer rack about 30 feet from the term shelf |  | Richard Dick Fiore 1-813-503-3702 richard.fiore@optum.com | DEVEN PATTERSON | deven_patterson@optum.com | 1-210-877-7969 | 01/02/2017(Access) 01/02/2017(Private IP - PIP) | 03/16/2017 |  | 01/09/2017 (22834876) 01/11/2017 (22834875) | 01/05/2017 | 01/02/2017 |  |  | N (22834876) N (22834875) | U0101953 | Jeopardy Notification 1 (12/09/2016) |  | NSPE0010476782
Completed | UT007-02-IJ | 680 W PRICE RIVER DR PRICE, UT 84501-2839 US | 50 MBPS (22834873) | 06/02/2017: 06/02 Customer did not join the activation call. Customer need to secure BEAS connectivity. | 193280224 | UT007-02-IJ | Private IP - PIP (22834872) Access (22834873) | 22834872 22834873 | 20 MBPS (22834872) |  | 125862171 (Private IP (PIP)) 125862169 (Access) | C4004708/ADD (22834872) E4013079/ADD (22834873) | 64/OBGS/139299//MS (2283487317618202) c5vqo wpy 0002 (I0011636.SLC) | 5771829 | 2500 | PVC ID : 5771829 VPN Name : UnitedHealthGroup Router Name : SLKCGE01 VRF Name : V693743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64558 PE IP Address : 68.136.82.149 CE Address : 68.136.82.150 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22834873) | Ethernet | CLEC or INDEPENDENT (2283487317618201) CENTURYLINK (2283487317618202) | 08/04/2016 (2283487317618202) | 09/01/2016 (2283487317618202) 09/23/2016 (I0011636.SLC) | 09/20/2016 (2283487317618202) 09/23/2016 (I0011636.SLC) | 09/21/2016 (VFORCE) (22834873) |  | DEMARCADDR - NO ANT DEMARCDET - 1ST FLR TELCO CLOSET 4 PORT PATCH PNL SC CONN |  | STEVE TATRO 1-901-653-2565 steve.tatro@helioscomp.com | DEVEN PATTERSON | deven_patterson@optum.com | 1-210-877-7969 | 09/23/2016(Private IP - PIP) 09/23/2016(Access) |  |  | 09/13/2016 (22834872) 09/09/2016 (22834873) | 08/30/2016 | 09/23/2016 |  |  | N (22834872) N (22834873) | U0101953 |  |  | NSPE0010476782
|  | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10GL-MPL-WL-MP (5904713) |  | 8833487 |  | US Private Line (5904713) | 5904713 | 10GL-MPL-WL-MP (5904713) |  |  | W0Y51076 (5904713) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | STEVE BROWN 763 694 7333 | STEVE BROWN 763 694 7333 |  |  |  | 07/21/2016 (5904713) |  |  | 07/29/2016 (5904713) | 08/10/2016 (5904713) |  |  |  | N (5904713) | 00198894 |  |  | NSPE0010466839
|  | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10GL-MPL-WL-MP (5904683) |  | 8833417 |  | US Private Line (5904683) | 5904683 | 10GL-MPL-WL-MP (5904683) |  |  | W0Y51078 (5904683) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | STEVE BROWN 763 694 7333 | STEVE BROWN 763 694 7333 |  |  |  | 07/21/2016 (5904683) |  |  | 07/29/2016 (5904683) | 08/10/2016 (5904683) |  |  |  | N (5904683) | 00198894 |  |  | NSPE0010466913
|  | 1707 W CREEK LN CHASKA, MN 55318 USA | 10GL-MPL-WL-SEP (5904685) |  | 8833395 |  | US Private Line (5904685) | 5904685 | 10GL-MPL-WL-SEP (5904685) |  |  | W0Z66371 (5904685) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | STEVE BROWN 763 694 7333 | STEVE BROWN 763 694 7333 |  |  |  | 07/21/2016 (5904685) |  |  | 07/29/2016 (5904685) | 08/10/2016 (5904685) |  |  |  | N (5904685) | 00198894 |  |  | NSPE0010467184
|  | 14100 BUSINESS CTR DR NW ELK RIVER, MN 55330 USA | 10GL-MPL-WL-SEP (5905105) |  | 8833297 |  | US Private Line (5905105) | 5905105 | 10GL-MPL-WL-SEP (5905105) |  |  | W1B05870 (5905105) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | STEVE BROWN 763 694 7333 | KRIS SEEHOFF 763 744 1584 |  |  |  | 07/21/2016 (5905105) |  |  | 07/29/2016 (5905105) | 08/11/2016 (5905105) |  |  |  | N (5905105) | 00198894 |  |  | NSPE0010467306
Completed |  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBLCZT0) | 08/18/2016: 8/18- Ready for hotcut, customer notified. | 8835774 |  | EVC/PVC Service (C.11150385.5210727) Private IP Port Only (CQBLCZT0) | C.11150385.5210727 CQBLCZT0 | 7000 MBPS | P1955436 |  | BOBKWCW20001 (CQBLCZT0) |  | 5210727 | 24576 | PVC ID : 5210727 VPN Name : Alere-LLC-WAN Router Name : MZZGE01 VRF Name : Vg35543:AlereLLCWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : 152.176.170.69 CE Address : 152.176.170.70 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 7637442081 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/15/2016 (CQBLCZT0) |  |  | 09/08/2016 (CQBLCZT0) | 09/08/2016 (CQBLCZT0) |  |  |  | N (C.11150385.5210727) N (CQBLCZT0) | P1955436 05017789 |  |  | NSPE0010467344
|  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBLCQ7Y) |  | 8835771 |  | Private IP Port Only (CQBLCQ7Y) | CQBLCQ7Y | 7000 MBPS 7000 MBPS (CQBLCQ7Y) | P1932297 |  | BOBKTD960001 (CQBLCQ7Y) |  | 5212513 | 110500 270000 314000 384 360000 1500000 | PVC ID : 5212513 VPN Name : UHG-XLHealth,UHG-UC,UHG-IPTF,UnitedHealthGroup-IDN,UHG-ECC,UnitedHealthGroup Router Name : MN3GE01 VRF Name : V594628:UHGXLHealth,V656367:UHGUC,V594624:UHGIPTF,V594626:UnitedHealthGroupIDN,V594627:UHGECC,V594623:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : v4-152.162.46.225,v6-68.137.39.25,v4-152.176.215.13,v6-152.192.111.185,v4-147.225.22.233,v6-152.161.107.161 CE Address : v4-152.162.46.226,v6-68.137.39.26,v4-152.176.215.14,v6-152.192.111.186,v4-147.225.22.234,v6-152.161.107.162 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 07/26/2016 (CQBLCQ7Y) |  |  | 07/26/2016 (CQBLCQ7Y) | 08/18/2016 (CQBLCQ7Y) |  |  |  | N (CQBLCQ7Y) | 05017789 |  |  | NSPE0010467278
|  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBLCQ2C) |  | 8835765 |  | Private IP Port Only (CQBLCQ2C) | CQBLCQ2C | 7000 MBPS 7000 MBPS (CQBLCQ2C) | P1932463 |  | BOBKTFPX0001 (CQBLCQ2C) |  | 5189860 | 360000 270000 314000 2688 1500000 | PVC ID : 5189860 VPN Name : UHG-ECC,UHG-UC,UHG-IPTF,UnitedHealthGroup-ECCMA,UnitedHealthGroup Router Name : MN39E01 VRF Name : V594781:UHGECC,V645094:UHGUC,V601668:UHGIPTF,V601670:UnitedHealthGroupECCMA,V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : v4-152.177.151.97,v6-199.220.202.221,v4-152.187.248.73,v6-68.136.152.241,v4-152.162.11.193 CE Address : v4-152.177.151.98,v6-199.220.202.222,v4-152.187.248.74,v6-68.136.152.242,v4-152.162.11.194 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 07/26/2016 (CQBLCQ2C) |  |  | 08/17/2016 (CQBLCQ2C) | 08/17/2016 (CQBLCQ2C) |  |  |  | N (CQBLCQ2C) | 05017789 |  |  | NSPE0010467228
|  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBLCRCG) | 08/12/2016: 8/11- Pending hotcut, customer notified. | 8825384 |  | EVC/PVC Service (C.11139977.5212868) Private IP Port Only (CQBLCRCG) | C.11139977.5212868 CQBLCRCG | 7000 MBPS | P1957529 |  | BOBKWHD00001 (CQBLCRCG) |  | 5212868 | 0 | PVC ID : 5212868 VPN Name : UnitedHealthGroup-ECCMA Router Name : MZZ9E01 VRF Name : V600584:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : 152.161.80.1 CE Address : 152.161.80.2 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 7637442081 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 07/26/2016 (CQBLCRCG) |  |  | 07/26/2016 (CQBLCRCG) | 08/18/2016 (CQBLCRCG) |  |  |  | N (C.11139977.5212868) N (CQBLCRCG) | P1957529 05017789 |  |  | NSPE0010467160
Completed | C1380-05-IJ Convergys Cincinatti Data Center | 229 W 7TH ST FL 6 CINCINNATI, OH 45202-2308 US | 500 MBPS (22925370) | 12/16/2016: 12/16 Successfully activated. scott_moyer@optum.com accepted the circuit. | 193312490 | C1380-05-IJ Convergys Cincinatti Data Center | Private IP - PIP (22925369) Access (22925370) | 22925369 22925370 | 400 MBPS (22925369) |  | 127750779 (Private IP (PIP)) 127750777 (Access) | C5002317/ADD (22925369) E5004255/ADD (22925370) | 51.L1XX.006221..TWCC (2292537015181401) | 5781423 | 250000 | PVC ID : 5781423 VPN Name : UHG-ECC Router Name : CMKXE01 VRF Name : V676351-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65497 PE IP Address : 152.187.178.85 CE Address : 152.187.178.86 QoS - Egress Profile: C13 | 1000Base-SX-850nm (22925370) | 1000Base-SX (850nm, Multi Mode Fiber) (22925370) | Ethernet | TIME WARNER CABLE (2292537015181401) | 08/05/2016 (2292537015181401) | 10/14/2016 (2292537015181401) | 10/19/2016 (2292537015181401) | 10/24/2016 (VFORCE) (22925370) | 10/24/2016 (VFORCE) (22925370) | DEMARCDET - BLDG 1 FLR 6 RM TELCO |  | PAT HENRY 1-513-723-7692 patrick.henry@convergys.com | Will Goss | william_Goss@optum.com | 1-763-744-1528 | 10/24/2016(Private IP - PIP) 10/24/2016(Access) | 12/15/2016 |  | 11/07/2016 (22925369) 11/03/2016 (22925370) | 11/03/2016 | 10/24/2016 |  |  | N (22925369) N (22925370) | U0101953 |  |  | NSPE0010508476
|  | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330-4654 USA | 100GLMPL-WL-MU (5911876) | 10/13/2016: 10/13 - Ready for activation. Customer to provide their preferred activation date and time. | 8848680 |  | Metro Private Line (5911876) | 5911876 | 100GLMPL-WL-MU (5911876) |  |  | W1C49747 (5911876) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | TOM KRENN 763 744 3141 TOM_KRENN@OPTUM.COM | TOM KRENN 763 744 3141 TOM_KRENN@OPTUM.COM |  |  |  | 10/13/2016 (5911876) |  |  | 09/23/2016 (5911876) | 11/01/2016 (5911876) |  |  |  | N (5911876) | 00265649 |  |  | NSPE0010403550
|  | 14100 BUSINESS CENTER DR NW ELK RIVER, MN 55330-4654 USA | 100GLMPL-WL-MU (5912618) | 10/24/2016: 10/24 Ready to activate | 8848690 |  | Metro Private Line (5912618) | 5912618 | 100GLMPL-WL-MU (5912618) |  |  | W1C49881 (5912618) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | TOM KRENN 763 744 3141 | TOM KRENN 763 744 3141 |  |  |  | 10/23/2016 (5912618) |  |  | 11/02/2016 (5912618) | 10/27/2016 (5912618) |  |  |  | Y (5912618) | 00265674 |  |  | NSPE0010403550
|  | 1707 W CREEK LN CHASKA, MN 55318 USA | 100GLMPL-WL-MU (5912651) | 12/15/2016: 10/25 - Ready for activation. | 8848697 |  | Metro Private Line (5912651) | 5912651 | 100GLMPL-WL-MU (5912651) |  |  | W1C49885 (5912651) | [7 empty] | NORTHWESTERN BELL (MN & ND) | [6 empty] | TOM KRENN 763 744 3141 | TOM KRENN 763 744 3141 |  |  |  | 10/23/2016 (5912651) |  |  | 11/02/2016 (5912651) | 10/27/2016 (5912651) |  |  |  | Y (5912651) | 00265675 |  |  | NSPE0010403550
|  | 4225 W LAKE PARK BLVD WEST VALLEY, UT 84120 USA 35 COLLEGEVIEW RD WESTERVILLE, OH 43081 | 1000 MBPS (IQBLCVP4) 1000 MBPS (IQBLCVP5) | 06/05/2017: 06/02 Successfully activated | 8848082 |  | EACS (IQBLCVP4) EVC/PVC Service (N.11148871.5780351) EACS (IQBLCVP5) | IQBLCVP4 N.11148871.5780351 IQBLCVP5 | 1000 MBPS (IQBLCVP4) 1000 MBPS (IQBLCVP5) | P2147020 P2147021 |  | EDBK93B90001 (IQBLCVP4) EDBK93CB0001 (IQBLCVP5) | 67.KGGS.001121..CBCL.. (IQBLCVP4IE3VMB01) 5B/KFFN/002783/LVLC (IQBLCVP5JE3VMB01) | 5780351 |  | PVC ID : 5780351 |  |  |  | COMCAST (IQBLCVP4IE3VMB01) LEVEL 3 (IQBLCVP5JE3VMB01) | 08/03/2016 (IQBLCVP4IE3VMB01) 08/05/2016 (IQBLCVP5JE3VMB01) | 09/08/2016 (IQBLCVP4IE3VMB01) 09/06/2016 (IQBLCVP5JE3VMB01) | 09/08/2016 (IQBLCVP4IE3VMB01) 09/01/2016 (IQBLCVP5JE3VMB01) |  |  | IQBLCVP54 West UT LEC demarc:COMCAST TELEPHONE CLOSET ON THE 1ST FLOOR RACK 2 (THEIR EQUIPMENT IS MIDWAY DOWN FROM THE TOP OF THE RACK ON PORT 1) Beas Demarc: BEAS box in data room 3rd floor half way down rack 3 LEC DEMARC: 1st Floor, Data Center Cabinet Row MM, CAB 8 per cust demarc ext Z-Loc Floor:1st Floor Room: Data Center Row: Cage 1 Cabinet: 5 Device: Fiber patch panel, U46 Port: 21/22 |  | SCOTT JACKSON 8016532565 6142128198 SCOTT.JACKSON@HELIOSCOMP.COM |  |  |  | 10/03/2016 (IQBLCVP4) 10/26/2016 (IQBLCVP5) | 06/02/2017 |  | 10/31/2016 (IQBLCVP4) 11/01/2016 (IQBLCVP5) | 10/31/2016 (IQBLCVP4) 10/26/2016 (IQBLCVP5) |  |  |  | N (IQBLCVP4) N (N.11148871.5780351) N (IQBLCVP5) | 05017789 0C282J |  |  | NSPE0010505655
Completed | NJ050-05-IJ | 170 WOOD AVE S ISELIN, NJ 08830-2741 US | 100 MBPS (23178509) | 04/07/2017: 04/07 Successfully activated | 193330549 | NJ050-05-IJ | Private IP - PIP (23178508) Access (23178509) | 23178508 23178509 | 50 MBPS (23178508) |  | 128590882 (Private IP (PIP)) 128590880 (Access) | C1043729/ADD (23178508) E4014747/ADD (23178509) | .KFGS.307641..NJ (2317850915957601) | 5806153 | 10000 | PVC ID : 5806153 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64585 PE IP Address : 152.187.200.45 CE Address : 152.187.200.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23178509) | 1000Base-SX (850nm, Multi Mode Fiber) (23178509) | Ethernet | VERIZON (2317850915957601) | 10/20/2016 (2317850915957601) | 11/07/2016 (2317850915957601) | 11/04/2016 (2317850915957601) |  |  | DEMARCADDR - 170 WOOD AV S, WDBG TWP, NJ DEMARCDET - FLR 3 SERVER ROOM RACK MOUNT 3 CONOGA 1 TAGGED |  | Christine Bannon 1-732-623-1172 christine_bannon@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 11/04/2016(Private IP - PIP) 11/04/2016(Access) | 04/06/2017 |  | 11/16/2016 (23178508) 11/14/2016 (23178509) | 11/17/2016 | 11/04/2016 |  |  | N (23178508) N (23178509) | U0101953 |  |  | NSPE0010512676
Completed | VA726-02-IJ | 22451 SHAW RD STERLING, VA 20166-4319 US | 1 GBPS (22939497) | 11/10/2016: 11/10 activation completed 11/9 | 193335269 | VA726-02-IJ | Private IP - PIP (22939496) WAN Analysis Reporting (22939498) Access (22939497) | 22939496 22939498 22939497 | 500 MBPS (22939496) |  | 72089712 (Private IP (PIP)) 72089713 (WAN Analysis Reporting) 72089710 (Access) | C0056130/NONE (22939496) E5001563/NONE (22939497) |  | 5612760 5789652 | 0 | PVC ID : 5612760,5789652 VPN Name : UnitedHealthGroup-ECCMA Router Name : RAY9E04 VRF Name : V526873:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64827 PE IP Address : 206.115.102.177 CE Address : 206.115.102.178 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (22939497) | Ethernet | [8 empty] | JOHN SERGOT 1-763-744-1582 john.sergot@uhc.com | JOHN SERGOT | john.sergot@uhc.com | 1-763-744-1582 | 11/11/2016(Private IP - PIP) 11/11/2016(Access) | 11/09/2016 |  | 11/07/2016 (22939496) 11/07/2016 (22939497) | 12/21/2016 12/21/2016 (8171377.1) | 11/16/2016 |  | Cancelled Activated/Installed | N (22939496) N (22939498) N (22939497) | U0101953 | Jeopardy Notification 1 (11/04/2016) |  | NSPE0010522508
Completed | UWI29-11-IJ Green Bay | 3100 AMS BLVD GREEN BAY, WI 54313-9700 US | 1 GBPS (22953491) | 11/29/2016: 11/29 - Activation complete. | 193338070 | UWI29-11-IJ Green Bay | Private IP - PIP (22953490) Access (22953491) | 22953490 22953491 | 400 MBPS (22953490) |  | 128953327 (Private IP (PIP)) 128953325 (Access) | C0091061/ADD (22953490) E5004293/ADD (22953491) | 92.L1XX.001033..TWCC (2295349166854901) | 5784013 | 350000 | PVC ID : 5784013 VPN Name : UnitedHealthGroup Router Name : MWAGE04 VRF Name : V415040:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64990 PE IP Address : 147.225.6.233 CE Address : 147.225.6.234 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22953491) | 1000Base-SX (850nm, Multi Mode Fiber) (22953491) | Ethernet | TIME WARNER CABLE (2295349166854901) | 08/10/2016 (2295349166854901) | 10/26/2016 (2295349166854901) | 10/25/2016 (2295349166854901) | 11/02/2016 (VFORCE) (22953491) | 11/03/2016 (VFORCE) (22953491) | DEMARCDET - 1ST FLOOR SUITE THE WELL/UNITED ONE. UH1 MDF RACK MOUNTED |  | Scott Berg 1-920-661-2315 sberg@unitedhealthone.com | RANJI ADHIKAI | ranjit_adhikari@optum.com | 1-763-744-1957 | 11/03/2016(Private IP - PIP) 11/03/2016(Access) | 11/29/2016 |  | 11/16/2016 (22953490) 11/14/2016 (22953491) | 11/14/2016 | 11/03/2016 |  |  | N (22953490) N (22953491) | U0101953 |  |  | NSPE0010529786
Completed | UIN08-10-IJ Indianapolis | 7440 WOODLAND DR INDIANAPOLIS, IN 46278-1720 US | 1 GBPS (22953406) | 02/03/2017: 02/03 Successfully activated | 193338053 | UIN08-10-IJ Indianapolis | Private IP - PIP (22953405) Access (22953406) | 22953405 22953406 | 400 MBPS (22953405) |  | 128953323 (Private IP (PIP)) 128953321 (Access) | C0091053/ADD (22953405) E5004291/ADD (22953406) | 3J/KFFN/002868/LVLC (2295340617290601) | 5783973 | 250000 | PVC ID : 5783973 VPN Name : UnitedHealthGroup Router Name : PLVXE01 VRF Name : V669152-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64734 PE IP Address : 152.185.68.181 CE Address : 152.185.68.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22953406) | 1000Base-SX (850nm, Multi Mode Fiber) (22953406) | Ethernet | LEVEL 3 (2295340617290601) | 09/01/2016 (2295340617290601) | 09/20/2016 (2295340617290601) | 09/15/2016 (2295340617290601) | 09/19/2016 (VFORCE) (22953406) | 09/19/2016 (VFORCE) (22953406) | DEMARCDET - 1st floor main phone room relay rack RR 001.01.01, RMU 32, cisco 3600 port gigabit 0/11 tagged and labeled |  | Mike Dillon 1-317-715-7768 MDillon@unitedhealthone.com | RANJI ADHIKAI | ranjit_adhikari@optum.com | 1-763-744-1957 | 09/19/2016(Private IP - PIP) 09/19/2016(Access) | 02/03/2017 |  | 09/29/2016 (22953405) 09/27/2016 (22953406) | 09/21/2016 | 09/19/2016 |  |  | N (22953405) N (22953406) | U0101953 |  |  | NSPE0010529786
Completed | UHG XL Health | 6514 MEADOWRIDGE RD ELKRIDGE, MD 21075-6115 US | 300 MBPS (23007012) | 08/31/2016: 8/31- FOC date 9/2. | 193338041 | UHG XL Health | Private IP - PIP (23007011) Access (23007012) | 23007011 23007012 | 200 MBPS (23007011) |  | 128953335 (Private IP (PIP)) 128953333 (Access) | C5002350/ADD (23007011) E5004352/ADD (23007012) | 38.KFGS.301977..CM (2300701210323001) | 5788077 | 30000 | PVC ID : 5788077 VPN Name : UnitedHealthGroup Router Name : BA59E01 VRF Name : V673546:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65065 PE IP Address : 68.138.141.225 CE Address : 68.138.141.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23007012) | 1000Base-SX (850nm, Multi Mode Fiber) (23007012) | Ethernet | VERIZON (2300701210323001) | 08/18/2016 (2300701210323001) | 09/02/2016 (2300701210323001) | 09/01/2016 (2300701210323001) |  |  | DEMARCADDR - 6514 MEADOWRIDGE RD, ELKRIDGE, MD DEMARCDET - 1ST FLR MAIN TELCO RM REAR OF BLDG...IN CUST EQPT CAB |  | ROB WINSTON 1-763-283-3152 robert.winston@optum.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 | 09/01/2016(Private IP - PIP) 09/01/2016(Access) |  |  | 09/14/2016 (23007011) 09/12/2016 (23007012) | 09/20/2016 | 09/01/2016 |  |  | N (23007011) N (23007012) | U0101953 |  |  | NSPE0010529786
Completed | UNITED HEALTH GROUP | 3049 UALENA ST HONOLULU, HI 96819-1942 US | 3 MBPS | 09/27/2016: 9/27 activation completed on 9/24/16 | 193340178 | UNITED HEALTH GROUP | Private IP - PIP (22950098) Access WAN Analysis Reporting (22950100) | 22950098 22950100 | 3 MBPS (22950098) |  | 9627365 (Private IP (PIP)) 9634013 9636155 (WAN Analysis Reporting) | C1023193/NONE (22950098) |  | 5300321 | 2000 | PVC ID : 5300321 VPN Name : UnitedHealthGroup Router Name : HNL3E01 VRF Name : V347791-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65363 PE IP Address : 199.220.248.225 CE Address : 199.220.248.226 QoS - Egress Profile: R12 |  | DS1 | TDM | [6 empty] | ckt1: 8th flr mechanical room backboard shelf 2 positions 1 rj48c tagged and notextended ckt2: 8th flr mechanical room backboard shelf 2 positions 2 rj48c tagged and notextended ckt1: HNL XB WBDXC SHELF 22:HRNUMBER 3:VC3 3:DS1 19 ckt2: HNL XB WBDXC SHELF 22:HRNUMBER |  | Masroor Khan 1-952-201-1673 maskhan@optum.com | Masroor Khan | maskhan@optum.com | 1-952-201-1673 | 09/26/2016(Private IP | 09/24/2016 |  | 09/30/2016 (22950098) | 09/30/2016 09/30/2016 (8491579.1) | 09/26/2016 |  | Activated/Installed | N (22950098) N N (22950100) | U0101953 |  |  | NSPE0010533180
Completed | NY187-02-IJ Farmingdale NY | 931 CONKLIN ST STE C&D FARMINGDALE, NY 11735-2429 US | 100 MBPS (22982802) | 10/3/16 Ready to activate; customer notified | 193342196 | NY187-02-IJ Farmingdale, NY | Private IP - PIP (22982801) Access (22982802) | 22982801 22982802 | 50 MBPS (22982801) |  | 130306738 (Private IP (PIP)) 130306736 (Access) | C1040928/ADD (22982801) E4013870/ADD (22982802) | 32.KFGS.210346..NY (2298280216867301) | 5786186 | 7000 | PVC ID : 5786186 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64664 PE IP Address : 199.220.251.21 CE Address : 199.220.251.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22982802) | 1000Base-SX (850nm, Multi Mode Fiber) (22982802) | Ethernet | VERIZON (2298280216867301) | 08/15/2016 (2298280216867301) | 09/30/2016 (2298280216867301) | 10/01/2016 (2298280216867301) |  |  | DEMARCADDR - 931 CONKLIN, FARMINGDALE, NY DEMARCDET - 931 CONKLIN, 1ST FL, SERVER RM, WALL MTD, TAGGED W/ID + MTC NO. |  | Sunil Orie 1-800-346-6348 sorie@aciiv.com | JOHN SERGOT | john.sergot@optum.com | 1-763-744-1582 | 10/03/2016(Private IP - PIP) 10/03/2016(Access) |  |  | 10/11/2016 (22982801) 10/07/2016 (22982802) | 10/20/2016 | 10/03/2016 |  |  | N (22982801) N (22982802) | U0101953 |  |  | NSPE0010534539
|  | UNIT 4 ALIA HOUSE DEAKINACT 2600 AUS | NX0PPP-1.984MBS (5916965) | 09/07/2016: 9/7- disconnection completed | 8872632 |  | Private IP (5916965) | 5916965 | 1.984 MBPS |  |  | W0Y10678 (5916965) | N6003253L (5780056) | 2038789 | 512 | PVC ID : 2038789 VPN Name : UnitedHealthGroup Router Name : CAN29E01 VRF Name : V528667:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65148 PE IP Address : 152.183.242.253 CE Address : 152.183.242.254 QoS - Egress Profile: R12 |  |  |  | VERIZON BUSINESS - INTL LOCS (AS) TELSTRA COMMUNICATIONS (5780056) | 08/25/2016 (5780056) | 08/31/2016 (5780056) | 08/31/2016 (5780056) |  |  |  |  | BILL PREECE +61-(040)031-7033 | [6 empty] | 09/07/2016 (5916965) | 08/31/2016 (5916965) |  |  |  | N (5916965) | 00179802 |  |  | NSPE0010270041
Completed |  |  |  | 08/31/2016: 8/31- Hotcut scheduled for 8/31 at 11pm CST. | 8877328 |  | Private IP (C.11164146.5423041) | C.11164146.5423041 | 4.608 MBPS |  |  |  |  | 5423041 | 768 | PVC ID : 5423041 VPN Name : UnitedHealthGroup Router Name : ANCG3E01 VRF Name : V726744-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65446 PE IP Address : 68.136.254.57 CE Address : 68.136.254.58 QoS - Egress Profile: R12 | [23 empty] | N (C.11164146.5423041) | W1A72836 |  |  | NSPE0010536311
Completed | AZ012-05-IJ Phoenix 100mg | 2222 W DUNLAP AVE PHOENIX, AZ 85021-2818 US | 100 MBPS | 09/30/2016: 9/30 Activation complete successfullt-MOVE VPN complete 9/30 4:30am CST- change order can be closed now | 193363546 | AZ012-05-IJ Phoenix 100mg | Private IP - PIP (23008507) Access | 23008507 | 100 MBPS (23008507) |  | 63630031 (Private IP (PIP)) 63630029 | C1018210/NONE (23008507) |  | 5574047 | 70000 | PVC ID : 5574047 VPN Name : UnitedHealthGroup Router Name : WIT3E04 VRF Name : V446114-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65426 PE IP Address : 199.220.4.133 CE Address : 199.220.4.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | JOHN SERGOT 1-763-744-1582 john.sergot@uhc.com | JOHN SERGOT | john.sergot@uhc.com | 1-763-744-1582 | 09/30/2016(Private IP |  |  | 08/18/2016 (23008507) | 08/29/2016 | 09/30/2016 | 09/30/2016 (23008507) |  | N (23008507) N | U0101953 |  |  | NSPE0010555590
|  | 4601 CORPORATE DR NW CONCORD, NC 280279659 USA | 0 KBPS (IQBLC909) | 11/22/2016: 11/22 Supped order to allow order to close new DD 11/30 POC called Voice activation team today since he now has cabling. working on completing Voice hotcut today. | 8883472 |  | Dedicated Long Distance (IQBLC909) | IQBLC909 | 0 KBPS (IQBLC909) | N6251499 |  | IBBJ7LBP0025 (IQBLC909) IBBJ7LBP0026 (IQBLC909) IBBJ7LBP0027 (IQBLC909) IBBJ7LBP0028 (IQBLC909) IBBJ7LBP0029 (IQBLC909) IBBJ7LBP0030 (IQBLC909) IBBJ7LBP0031 (IQBLC909) IBBJ7LBP0032 (IQBLC909) IBBJ7LBP0033 (IQBLC909) IBBJ7LBP0034 (IQBLC909) IBBJ7LBP0035 (IQBLC909) IBBJ7LBP0036 (IQBLC909) IBBJ7LBP0037 (IQBLC909) IBBJ7LBP0038 (IQBLC909) IBBJ7LBP0039 (IQBLC909) IBBJ7LBP0040 (IQBLC909) IBBJ7LBP0041 (IQBLC909) IBBJ7LBP0042 (IQBLC909) IBBJ7LBP0043 (IQBLC909) IBBJ7LBP0044 (IQBLC909) IBBJ7LBP0045 (IQBLC909) IBBJ7LBP0046 (IQBLC909) IBBJ7LBP0047 (IQBLC909) IBBJ7LBP0048 (IQBLC909) IBBJ7LBP0049 (IQBLC909) IBBJ7LBP0050 (IQBLC909) IBBJ7LBP0051 (IQBLC909) IBBJ7LBP0052 (IQBLC909) IBBJ7LBP0053 (IQBLC909) IBBJ7LBP0054 (IQBLC909) IBBJ7LBP0055 (IQBLC909) IBBJ7LBP0056 (IQBLC909) IBBJ7LBP0057 (IQBLC909) IBBJ7LBP0058 (IQBLC909) IBBJ7LBP0059 (IQBLC909) IBBJ7LBP0060 (IQBLC909) IBBJ7LBP0061 (IQBLC909) IBBJ7LBP0062 (IQBLC909) IBBJ7LBP0063 (IQBLC909) IBBJ7LBP0064 (IQBLC909) IBBJ7LBP0065 (IQBLC909) IBBJ7LBP0066 (IQBLC909) IBBJ7LBP0067 (IQBLC909) IBBJ7LBP0068 (IQBLC909) IBBJ7LBP0069 (IQBLC909) IBBJ7LBP0070 (IQBLC909) IBBJ7LBP0071 (IQBLC909) IBBJ7LBP0072 (IQBLC909) IBBJ7LBP0073 (IQBLC909) IBBJ7LBP0074 (IQBLC909) IBBJ7LBP0075 (IQBLC909) IBBJ7LBP0076 (IQBLC909) IBBJ7LBP0077 (IQBLC909) IBBJ7LBP0078 (IQBLC909) IBBJ7LBP0079 (IQBLC909) IBBJ7LBP0080 (IQBLC909) IBBJ7LBP0081 (IQBLC909) IBBJ7LBP0082 (IQBLC909) IBBJ7LBP0083 (IQBLC909) IBBJ7LBP0084 (IQBLC909) IBBJ7LBP0085 (IQBLC909) IBBJ7LBP0086 (IQBLC909) IBBJ7LBP0087 (IQBLC909) IBBJ7LBP0088 (IQBLC909) IBBJ7LBP0089 (IQBLC909) IBBJ7LBP0090 (IQBLC909) IBBJ7LBP0091 (IQBLC909) IBBJ7LBP0092 (IQBLC909) IBBJ7LBP0093 (IQBLC909) IBBJ7LBP0094 (IQBLC909) IBBJ7LBP0095 (IQBLC909) IBBJ7LBP0096 (IQBLC909) IBBJ7LBP0097 (IQBLC909) IBBJ7LBP0098 (IQBLC909) IBBJ7LBP0099 (IQBLC909) IBBJ7LBP0100 (IQBLC909) IBBJ7LBP0101 (IQBLC909) IBBJ7LBP0102 (IQBLC909) IBBJ7LBP0103 (IQBLC909) IBBJ7LBP0104 (IQBLC909) IBBJ7LBP0105 (IQBLC909) IBBJ7LBP0106 (IQBLC909) IBBJ7LBP0107 (IQBLC909) IBBJ7LBP0108 (IQBLC909) IBBJ7LBP0109 (IQBLC909) IBBJ7LBP0110 (IQBLC909) IBBJ7LBP0111 (IQBLC909) IBBJ7LBP0112 (IQBLC909) IBBJ7LBP0113 (IQBLC909) IBBJ7LBP0114 (IQBLC909) IBBJ7LBP0115 (IQBLC909) IBBJ7LBP0116 (IQBLC909) IBBJ7LBP0117 (IQBLC909) IBBJ7LBP0118 (IQBLC909) IBBJ7LBP0119 (IQBLC909) IBBJ7LBP0169 (IQBLC909) IBBJ7LBP0170 (IQBLC909) IBBJ7LBP0171 (IQBLC909) IBBJ7LBP0172 (IQBLC909) IBBJ7LBP0173 (IQBLC909) | NC/HCGS/499413/ /WINS/ (IZA10RFAW25JMB01) NC/HCGS/499414/ /WINS/ (IZA10RFBW25JMB01) NC/HCGS/610154/ /WINS/ (IZA10RTTW25JMB01) NC/HCGS/498506/ /WINS/ (IZA10RF9W25JMB01) NC/HCGS/499416/ /WINS/ (IZA10RFCW25JMB01) | [6 empty] | CLEC or INDEPENDENT (IZA10RFAW25JMB01) CLEC or INDEPENDENT (IZA10RFBW25JMB01) CLEC or INDEPENDENT (IZA10RTTW25JMB01) CLEC or INDEPENDENT (IZA10RF9W25JMB01) CLEC or INDEPENDENT (IZA10RFCW25JMB01) | 08/25/2016 (IZA10RFAW25JMB01) 08/25/2016 (IZA10RFBW25JMB01) 09/01/2016 (IZA10RTTW25JMB01) 08/25/2016 (IZA10RF9W25JMB01) 08/25/2016 (IZA10RFCW25JMB01) | 09/16/2016 (IZA10RFAW25JMB01) 09/16/2016 (IZA10RFBW25JMB01) 09/20/2016 (IZA10RTTW25JMB01) 09/16/2016 (IZA10RF9W25JMB01) 09/16/2016 (IZA10RFCW25JMB01) | 09/19/2016 (IZA10RFAW25JMB01) 09/16/2016 (IZA10RFBW25JMB01) 09/16/2016 (IZA10RTTW25JMB01) 09/15/2016 (IZA10RF9W25JMB01) 09/16/2016 (IZA10RFCW25JMB01) |  |  | IZA10RFC - 1st Floor Main Telco Room MM |  | ALEX URQUILOA 0017042622400 |  |  |  | 11/30/2016 (IQBLC909) | 11/22/2016 |  | 11/23/2016 (IQBLC909) | 11/30/2016 (IQBLC909) |  |  |  | N (IQBLC909) | 05542765 |  |  | NSPE0010563480
Completed | C1585-02-IJ Johnson Roundtree Premium San Diego | 6160 LUSK BLVD STE 203 SAN DIEGO, CA 92121-2740 US | 50 MBPS (23031585) | 09/27/2016: 9/26 activation completed successfully | 193377884 | C1585-02-IJ Johnson Roundtree Premium San Diego | Private IP - PIP (23031584) Access (23031585) | 23031584 23031585 | 30 MBPS (23031584) |  | 132485870 (Private IP (PIP)) 132485868 (Access) | C4004961/ADD (23031584) E4014054/ADD (23031585) | 19/KRGN/530400//PT (2303158511903201) | 5790376 | 4000 | PVC ID : 5790376 VPN Name : UHG-ECC Router Name : S7X9E01 VRF Name : V717255:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65525 PE IP Address : 152.181.239.253 CE Address : 152.181.239.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23031585) | 1000Base-SX (850nm, Multi Mode Fiber) (23031585) | Ethernet | ATT (2303158511903201) | 08/23/2016 (2303158511903201) | 09/07/2016 (2303158511903201) | 09/08/2016 (2303158511903201) | 09/21/2016 (VFORCE) (23031585) | 09/21/2016 (VFORCE) (23031585) | DEMARCADDR - 6160 LUSK BL SD DEMARCDET - 1ST FLR MOPE,PATCH PANEL #2, POS 1 AND TAGGED WITH CKT ID.; |  | HAU NGUYEN 1-619-719-0014 hnguyen@jrpremium.com | William Goss | william_Goss@optum.com | 1-763-744-1528 | 09/21/2016(Private IP - PIP) 09/21/2016(Access) | 09/26/2016 |  | 09/28/2016 (23031584) 09/26/2016 (23031585) | 10/28/2016 | 09/21/2016 |  |  | N (23031584) N (23031585) | U0101953 |  |  | NSPE0010561696
Completed | C1577-03-IJ EXL Services Inc. (AT&T Hosting) NY | 811 10TH AVE NEW YORK, NY 10019-5042 US | 100 MBPS (23053719) | 03/02/2017: 03/01 Successfully activated. | 193388238 | C1577-03-IJ EXL Services Inc. (AT&T Hosting) NY | Private IP - PIP (23053718) Access (23053719) | 23053718 23053719 | 100 MBPS (23053718) |  | 133428450 (Private IP (PIP)) 133428448 (Access) | C1042282/ADD (23053718) E4014154/ADD (23053719) | VLXX/368003/LVLC (2305371917330601) | 5792271 | 20000 | PVC ID : 5792271 VPN Name : UHG-ECC Router Name : SRDXE01 VRF Name : V754645-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65512 PE IP Address : 68.136.76.121 CE Address : 68.136.76.122 QoS - Egress Profile: C13 | 1000Base-SX-850nm (23053719) | 1000Base-SX (850nm, Multi Mode Fiber) (23053719) | Ethernet | LEVEL 3 (2305371917330601) | 10/10/2016 (2305371917330601) | 10/24/2016 (2305371917330601) | 10/17/2016 (2305371917330601) | 12/19/2016 (VFORCE) (23053719) | 12/19/2016 (VFORCE) (23053719) | DEMARCDET - 16th floor MDF room rack 16.04.06 RMU 36 panel port 25 and 26 MMF tagged with IDs |  | DON EMPSON 1-510-557-8575 don.empson@exlservice.com | Ketul Patel | ketul.patel@exlservice.com | 1-646-712-1497 | 12/19/2016(Private IP - PIP) 12/19/2016(Access) | 03/01/2017 |  | 01/02/2017 (23053718) 12/29/2016 (23053719) | 12/29/2016 | 12/19/2016 |  |  | N (23053718) N (23053719) | U0101953 | Jeopardy Notification 2 (11/04/2016) |  | NSPE0010572005
Completed | AL019-02-IJ Hoover AL | 22 INVERNESS CENTER PKWY BIRMINGHAM, AL 35242-4814 US | 50 MBPS (23096185) | 01/11/2017: 01/10 Successfully activated | 193402375 | AL019-02-IJ Hoover, AL | Access (23096185) Private IP - PIP (23096184) | 23096185 23096184 | 10 MBPS (23096184) |  | 134282513 (Access) 134282515 (Private IP (PIP)) | E4014364/ADD (23096185) C4005057/ADD (23096184) | 5Y/KFFN/002578/LVLC (2309618518692501) | 5796719 | 1500 | PVC ID : 5796719 VPN Name : UnitedHealthGroup Router Name : JAP3E01 VRF Name : V484472-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64551 PE IP Address : 159.24.186.245 CE Address : 159.24.186.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23096185) | 1000Base-SX (850nm, Multi Mode Fiber) (23096185) | Ethernet | LEVEL 3 (2309618518692501) | 10/24/2016 (2309618518692501) | 12/06/2016 (2309618518692501) | 12/06/2016 (2309618518692501) | 12/27/2016 (VFORCE) (23096185) | 12/23/2016 (VFORCE) (23096185) | 3rd foor MDF room |  | Cathy Butler 1-205-437-8636 cathy_butler@uhg.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 12/27/2016(Access) 12/27/2016(Private IP - PIP) | 01/10/2017 |  | 01/04/2017 (23096185) 01/06/2017 (23096184) | 01/04/2017 | 12/27/2016 |  |  | N (23096185) N (23096184) | U0101953 | Jeopardy Notification 1 (11/22/2016) |  | NSPE0010588320
Completed | TX232-02-IJ Frisco Texas | 3000 INTERNET BLVD STE 550 FRISCO, TX 75034-1992 US | 50 MBPS (23101976) | 12/05/2016: 12/05 Status: Activation scheduled 12/8/2016 15:00 CST. Next action: Awaiting activation date Who owns the next action: Customer an dBNE Ticket: NA | 193404258 | TX232-02-IJ Frisco Texas | Private IP - PIP (23101975) WAN Analysis Reporting (23101977) Access (23101976) | 23101975 23101977 23101976 | 50 MBPS (23101975) |  | 134506245 (Private IP (PIP)) 134506246 (WAN Analysis Reporting) 134506243 (Access) | C4005059/ADD (23101975) E4014397/ADD (23101976) | 1T/KFFN/004577/LVLC (2310197618733601) | 5797494 | 1500 | PVC ID : 5797494 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64738 PE IP Address : 152.161.229.93 CE Address : 152.161.229.94 QoS - Egress Profile: R12 | 1000Base-T (23101976) | 1000Base-T (23101976) | Ethernet | LEVEL 3 (2310197618733601) | 09/08/2016 (2310197618733601) | 10/13/2016 (2310197618733601) | 11/04/2016 (2310197618733601) | 11/21/2016 (VFORCE) (23101976) | 11/22/2016 (VFORCE) (23101976) | Deamrc 5th fl, suite 550, customer server room, wallmount 1 port biscuit jack, RJ45, tagged w/circuit ID |  | Jolynn Ashby 1-877-591-0636 jolynn.ashby@optum.com | DEVEN PATTERSON | deven_patterson@optum.com | 1-210-877-7969 | 11/22/2016(Private IP - PIP) 11/22/2016(WAN Analysis Reporting) 11/22/2016(Access) | 12/08/2016 |  | 11/30/2016 (23101975) 11/28/2016 (23101976) | 11/22/2016 11/30/2016 | 11/22/2016 |  | Activated/Installed | N (23101975) N (23101977) N (23101976) | U0161525 | Jeopardy Notification 1 (11/11/2016) |  | NSPE0010588845
|  | 8325 SOUTHPARK CIR ORLANDO, FL 32819 USA | 1.536 MBPS (IQBLDDQ0) | 09/22/2016: 9/22- Circuit testing in progress. | 8891077 |  | Private IP (IQBLDDQ0) EVC/PVC Service (N.11179855.5795244) | IQBLDDQ0 N.11179855.5795244 | 1.536 MBPS (IQBLDDQ0) | P2149372 |  | BCBK954N0001 (IQBLDDQ0) BCBK954N0002 (IQBLDDQ0) BCBK954N0003 (IQBLDDQ0) BCBK954N0004 (IQBLDDQ0) BCBK954N0005 (IQBLDDQ0) BCBK954N0006 (IQBLDDQ0) BCBK954N0007 (IQBLDDQ0) | 58/HCGS/792564//SB (1278783) | 5795244 |  | PVC ID : 5795244 |  |  |  | ATT (1278783) | 09/07/2016 (1278783) | 09/21/2016 (1278783) | 09/23/2016 (1278783) |  |  | DEMARC VERIFIED AS: 58/HCGS/792563//SB - 1FL/MAIN TELCO ROOM,CAB3 SL1, RJ48C, TAGGED & NOT EXTENDED 58/HCGS/792564//SB - 1FL/MAIN TELCO ROOM,CAB3 SL2, RJ48C, TAGGED & NOT EXTENDED. 58/HCGS/792565//SB - 1FL/MAIN TELCO ROOM/CAB3 SL3 RJ48C, TAGGED & NOT EXTENDED. 58/HCGS/792566//SB - 1FL/MAIN TELCO ROOM/CAB3 SL4, RJ48C, TAGGED & NOT EXTENDED. 58/HCGS/792567//SB - 1FL/MAIN TELCO ROOM/CAB3 SL5, RJ48C, TAGGED & NOT EXTENDED 58/HCGS/792568//SB - 1FL/MAIN TELCO ROOM/CAB3 SL6, RJ48C, TAGGED & NOT EXTENDED. 58/HCGS/792569//SB - 1FL/MAIN TELCO ROOM/CAB3 SL7, RJ48C, TAGGED & NOT EXTENDED. |  | ANTHONY ATKINSON 0014072412108 TONY.ATKINSON@PHOENIX.EDU |  |  |  | 09/23/2016 (IQBLDDQ0) |  |  | 09/28/2016 (IQBLDDQ0) | 09/27/2016 (IQBLDDQ0) |  |  |  | N (IQBLDDQ0) N (N.11179855.5795244) | 05017789 P2149372 |  |  | NSPE0010576880
|  | 1707 W CREEK LN CHASKA, MN 55318 USA | 10GL-MPL-WL-PU (5926674) | 10/13/2016: 10/13 - Ready activation. | 8897980 |  | Metro Private Line (5926674) | 5926674 | 10GL-MPL-WL-PU (5926674) |  |  | W1C53359 (5926674) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | TOM KRENN 763 744 3141 | TOM KRENN 763 744 3141 |  |  |  | 10/13/2016 (5926674) |  |  | 10/26/2016 (5926674) | 12/05/2016 (5926674) |  |  |  | N (5926674) | 00265649
Completed | C3 Connect Miami FL | 2115 NW 22ND ST MIAMI, FL 33142-7335 US | 200 MBPS (23070663) | 02/02/2017: 02/01 Successfully activated | 193397123 | C3 Connect Miami FL | Private IP - PIP (23070662) Access (23070663) | 23070662 23070663 | 200 MBPS (23070662) |  | 133415543 (Private IP (PIP)) 133415541 (Access) | C5002387/ADD (23070662) E5004448/ADD (23070663) |  | 5794191 | 35000 | PVC ID : 5794191 VPN Name : UHG-ECC Router Name : POBGE02 VRF Name : V210878:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65417 PE IP Address : 152.187.120.121 CE Address : 152.187.120.122 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (23070663) | Ethernet | [5 empty] | 09/09/2016 (CCP) (23070662) 09/09/2016 (CCP) (23070663) | demarc: CoreSite, cage C100, Verizon rack, RR 113.0b.4E , Overture 1400 port 0.3, MM, LC connectors |  | WINSTON HONORE 1-954-305-1508 winston.honore@c3connect.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 | 09/26/2016(Private IP - PIP) 09/26/2016(Access) | 02/01/2017 |  | 09/27/2016 (23070662) 09/22/2016 (23070663) | 09/27/2016 | 09/26/2016 |  |  | N (23070662) N (23070663) | U0101953 |  |  | NSPE0010574461
|  | 5908 HAMPTON OAKS PKWY TAMPA, FL 33610 USA | 0 KBPS (IQBLDK7B) | 10/14/2016: 10/14 Activatin completed 10/13/16 | 8905063 |  | Dedicated Long Distance (IQBLDK7B) | IQBLDK7B | 0 KBPS (IQBLDK7B) | N6500055 |  | IBBK1VPY0145 (IQBLDK7B) IBBK1VPY0146 (IQBLDK7B) IBBK1VPY0147 (IQBLDK7B) IBBK1VPY0148 (IQBLDK7B) IBBK1VPY0149 (IQBLDK7B) IBBK1VPY0150 (IQBLDK7B) IBBK1VPY0151 (IQBLDK7B) IBBK1VPY0152 (IQBLDK7B) IBBK1VPY0153 (IQBLDK7B) IBBK1VPY0154 (IQBLDK7B) IBBK1VPY0155 (IQBLDK7B) IBBK1VPY0156 (IQBLDK7B) IBBK1VPY0157 (IQBLDK7B) IBBK1VPY0158 (IQBLDK7B) IBBK1VPY0159 (IQBLDK7B) IBBK1VPY0160 (IQBLDK7B) IBBK1VPY0161 (IQBLDK7B) IBBK1VPY0162 (IQBLDK7B) IBBK1VPY0163 (IQBLDK7B) IBBK1VPY0164 (IQBLDK7B) IBBK1VPY0165 (IQBLDK7B) IBBK1VPY0166 (IQBLDK7B) IBBK1VPY0167 (IQBLDK7B) IBBK1VPY0168 (IQBLDK7B) IBBK1VPY0169 (IQBLDK7B) IBBK1VPY0170 (IQBLDK7B) IBBK1VPY0171 (IQBLDK7B) IBBK1VPY0172 (IQBLDK7B) IBBK1VPY0173 (IQBLDK7B) IBBK1VPY0174 (IQBLDK7B) IBBK1VPY0175 (IQBLDK7B) IBBK1VPY0176 (IQBLDK7B) IBBK1VPY0177 (IQBLDK7B) IBBK1VPY0178 (IQBLDK7B) IBBK1VPY0179 (IQBLDK7B) IBBK1VPY0180 (IQBLDK7B) IBBK1VPY0181 (IQBLDK7B) IBBK1VPY0182 (IQBLDK7B) IBBK1VPY0183 (IQBLDK7B) IBBK1VPY0184 (IQBLDK7B) IBBK1VPY0185 (IQBLDK7B) IBBK1VPY0186 (IQBLDK7B) IBBK1VPY0187 (IQBLDK7B) IBBK1VPY0188 (IQBLDK7B) IBBK1VPY0189 (IQBLDK7B) IBBK1VPY0190 (IQBLDK7B) IBBK1VPY0191 (IQBLDK7B) IBBK1VPY0192 (IQBLDK7B) | [15 empty] | TREVOR LEWELLEN 0018136309705 |  |  |  | 09/28/2016 (IQBLDK7B) | 10/13/2016 |  | 10/07/2016 (IQBLDK7B) | 10/07/2016 (IQBLDK7B) |  |  |  | N (IQBLDK7B) | 05657026 |  |  | NSPE0010570391
|  | 110 STARGRASS SPRING BRANCH, TX 78070 USA | 1.536 MBPS (IQBLDJM1) | 10/14/2016: 10/13 Order completed; ready to activate | 8906227 |  | Private IP (IQBLDJM1) EVC/PVC Service (N.11190711.5800333) | IQBLDJM1 N.11190711.5800333 | 10.752 MBPS | P2150400 |  | BCBK97B40001 (IQBLDJM1) BCBK97B40002 (IQBLDJM1) BCBK97B40003 (IQBLDJM1) BCBK97B40004 (IQBLDJM1) BCBK97B40005 (IQBLDJM1) BCBK97B40006 (IQBLDJM1) BCBK97B40007 (IQBLDJM1) | 31/HCGS/710959//SW (IQBLDJM1QB5VMB01) | 5800333 | 1512 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65095 PE IP Address : 152.162.196.229 CE Address : 152.162.196.230 QoS - Egress Profile: R12 PVC ID : 5800333 |  |  |  | ATT (IQBLDJM1QB5VMB01) | 09/26/2016 (IQBLDJM1QB5VMB01) | 10/05/2016 (IQBLDJM1QB5VMB01) | 10/05/2016 (IQBLDJM1QB5VMB01) |  |  | DEMARC LOC: 1FLR COMM RM NID2 PORT 4 |  | RICK WILLIAMSON 0018302142920 2109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 10/06/2016 (IQBLDJM1) |  |  | 10/03/2016 (IQBLDJM1) | 10/07/2016 (IQBLDJM1) |  |  |  | N (IQBLDJM1) N (N.11190711.5800333) | 05017789 87522246 |  |  | NSPE0010602198
Completed | NM007-02-IJ Albuquerque | 2420 COMANCHE RD NE STE A5 ALBUQUERQUE, NM 87107-4754 US | 50 MBPS (23137964) | 02/13/2017: 02/13 Successfully activated. | 193433222 | NM007-02-IJ Albuquerque | Access (23137964) Private IP - PIP (23137963) | 23137964 23137963 | 20 MBPS (23137963) |  | 136255448 (Access) 136255450 (Private IP (PIP)) | E4014589/ADD (23137964) C4005152/ADD (23137963) | 59.KXGS.184911..MS (2313796416751201) | 5801699 | 1500 | PVC ID : 5801699 VPN Name : UnitedHealthGroup Router Name : AQHGE02 VRF Name : V551714:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64653 PE IP Address : 152.161.12.25 CE Address : 152.161.12.26 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23137964) | 1000Base-SX (850nm, Multi Mode Fiber) (23137964) | Ethernet | CENTURYLINK (2313796416751201) | 11/08/2016 (2313796416751201) 01/31/2017 (2313796416751201) | 11/22/2016 (2313796416751201) | 01/30/2017 (2313796416751201) | 01/31/2017 (VFORCE) (23137964) | 01/31/2017 (VFORCE) (23137964) | DEMARC: 1ST FL SERVER RM, WALL MTD CN3916M OPT PORT 4 MMF |  | Linda Manning 1-505-830-1800 lmanning@sironainfusion.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 01/31/2017(Access) 01/31/2017(Private IP - PIP) | 02/13/2017 |  | 02/06/2017 (23137964) 02/08/2017 (23137963) | 12/22/2016 | 01/31/2017 |  |  | N (23137964) N (23137963) | U0101953 | Jeopardy Notification 1 (11/04/2016) |  | NSPE0010619792
Completed |  | 3539 BLUECUTT RD COLUMBUS, MS 39705 USA | 1.536 MBPS (IQBLDHL1) | 11/23/2016: 11/23 Activation completd on 11/22 ckt accepted | 8895325 |  | Private IP (IQBLDHL1) | IQBLDHL1 | 10.752 MBPS | P2150143 |  | BCBK962H0001 (IQBLDHL1) BCBK962H0002 (IQBLDHL1) BCBK962H0003 (IQBLDHL1) BCBK962H0004 (IQBLDHL1) BCBK962H0005 (IQBLDHL1) BCBK962H0006 (IQBLDHL1) BCBK962H0007 (IQBLDHL1) | M1/HCGS/452449//SC (IQBLDHL1S54VMB01) |  | 2000 | VPN Name : UnitedHealthGroup Router Name : CPZGE08 VRF Name : V367200:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64552 PE IP Address : 152.185.157.173 CE Address : 152.185.157.174 QoS - Egress Profile: R12 |  |  |  | ATT (IQBLDHL1S54VMB01) | 09/12/2016 (IQBLDHL1S54VMB01) | 10/14/2016 (IQBLDHL1S54VMB01) | 10/14/2016 (IQBLDHL1S54VMB01) |  |  | VZ Ckt ID - LEC Ckt ID - Demarc : BCBK962H0001 - M1/HCGS/452448 /SC - 1ST FLR TERM RM,MULTI MT,POS |  | MELISSA ANDERSON 0016624192886 MELISSA.ANDERSON@BRIOVARX.COM |  |  |  | 10/19/2016 (IQBLDHL1) | 11/22/2016 |  | 10/19/2016 (IQBLDHL1) | 11/02/2016 (IQBLDHL1) |  |  |  | N (IQBLDHL1) | 05017789 |  |  | NSPE0010577047
Completed | FL196-02-IJ Orlando | 5979 VINELAND RD STE 208 ORLANDO, FL 32819-7855 US | 10 MBPS (23156009) | 01/06/2017: Activation completed/ cust accepted ckt | 193449790 | FL196-02-IJ Orlando | Private IP - PIP (23156008) Access (23156009) | 23156008 23156009 | 10 MBPS (23156008) |  | 137444180 (Private IP (PIP)) 137444178 (Access) | C0100812/ADD (23156008) E3028868/ADD (23156009) | 58/KRGN/701688//SB (2315600919225501) | 5803621 | 1500 | PVC ID : 5803621 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64544 PE IP Address : 68.136.166.49 CE Address : 68.136.166.50 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23156009) | 1000Base-SX (850nm, Multi Mode Fiber) (23156009) | Ethernet | ATT (2315600919225501) | 12/05/2016 (2315600919225501) | 01/10/2017 (2315600919225501) | 12/08/2016 (2315600919225501) | 12/13/2016 (VFORCE) (23156009) | 12/13/2016 (VFORCE) (23156009) | 2ND FLR TELCO RM IN SUITE #208OFS POS DEMARC LOC Continued: #8NTE #2 ,PORT 2, |  | Mike Nelson 1-207-877-7874 minelson@wellmed.net | Kyle Harsma | kyle_harsma@optum.com | 1-763-553-4195 | 12/13/2016(Private IP - PIP) 12/13/2016(Access) | 01/05/2017 |  | 01/05/2017 (23156008) 01/03/2017 (23156009) | 12/27/2016 | 12/13/2016 |  |  | N (23156008) N (23156009) | U0101953 | Jeopardy Notification 2 (10/01/2016) |  | NSPE0010633076
|  | 14100 BUSINESS CENTER DR NW ELK RIVER, MN 55330 | 9953.28 MBPS (CQBJ64SR) 9953.28 MBPS (IQBJY3VF) 9953.28 MBPS (OQBL1YLM) | 10/07/2016: 10/7 Background:upgrade IDE 10GigE Burstable Select 2G Next action: DD 11/11 tie down assignment comp- pending order completion Who owns the next action: Proj Eng Ticket:na Next update due by:10/13/2016 | 8921355 |  | Internet Dedicated (U309696) | U309696 | 9953.28 MBPS (CQBJ64SR) 9953.28 MBPS (IQBJY3VF) 9953.28 MBPS (OQBL1YLM) |  |  | PLBKM2V70001 (CQBJ64SR) PLBKM2V70001 (IQBJY3VF) PLBKM2V70001 (OQBL1YLM) | JY-73C-LLM8-0001 (OQBL1YLMXMSQMB01) | [6 empty] | WCOM/MFS MCI (OQBL1YLMXMSQMB01) | 04/16/2020 (OQBL1YLMXMSQMB01) | 04/29/2020 (OQBL1YLMXMSQMB01) | 04/27/2020 (OQBL1YLMXMSQMB01) | [11 empty] | 05/23/2012 (CQBJ64SR) 11/10/2011 (IQBJY3VF) 04/16/2020 (OQBL1YLM) 11/11/2016 (U309696) | 11/11/2016 (U309696) |  |  |  | N (U309696) |  |  | MN053-59-CJ Change commit IDE 10GigE Burstable Select 2G
Completed | NY361-02-IJ Catamaran Rx | 3030 47TH AVE LONG ISLAND CITY, NY 11101-3433 US | 100 MBPS (23199129) | 10/27/2016: 10/27 Activation completed | 193469571 | NY361-02-IJ Catamaran Rx | Private IP - PIP (23199128) Access (23199129) | 23199128 23199129 | 100 MBPS (23199128) |  | 138818603 (Private IP (PIP)) 138818561 (Access) | C1043906/ADD (23199128) E4014842/ADD (23199129) | 32.KFGS.210747..NY (2319912914414101) | 5807592 | 4000 | PVC ID : 5807592 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64700 PE IP Address : 152.192.24.229 CE Address : 152.192.24.230 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23199129) | 1000Base-SX (850nm, Multi Mode Fiber) (23199129) | Ethernet | VERIZON (2319912914414101) | 09/29/2016 (2319912914414101) | 10/20/2016 (2319912914414101) | 10/20/2016 (2319912914414101) |  |  | DEMARCDET - BLDG MAIN FLR 1ST RM TRLCO |  | BILL DOWNEY 1-718-361-4955 bdowney@salveospecialty.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 10/20/2016(Private IP - PIP) 10/20/2016(Access) | 10/27/2016 |  | 12/09/2016 (23199128) 12/07/2016 (23199129) | 12/19/2016 | 10/20/2016 |  |  | N (23199128) N (23199129) | U0101953 |  | Long Island | NSPE0010651554
Completed | C1425-07-IJ Teletech/Global Grossing Phoenix | 801 S 16TH ST PHOENIX, AZ 85034-4133 US | 1 GBPS |  | 193530315 | C1425-07-IJ Teletech/Global Grossing Phoenix | Private IP - PIP (23295005) Access | 23295005 | 800 MBPS (23295005) |  | 121437622 (Private IP (PIP)) 121437620 | C0085010/NONE (23295005) |  | 5758115 | 350000 | PVC ID : 5758115 VPN Name : UHG-ECC Router Name : WIT9E01 VRF Name : V773343:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65430 PE IP Address : 152.177.159.9 CE Address : 152.177.159.10 QoS - Egress Profile: C13 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | TRAVIS DENT 1-763-744-2265 travis_dent@optum.com | TRAVIS DENT | travis_dent@optum.com | 1-763-744-2265 | 10/19/2016(Private IP | 10/18/2016 |  | 10/18/2016 (23295005) | 10/27/2016 | 10/19/2016 |  |  | N (23295005) N | U0101953 |  | Change order circuit C0085010 C1425-07-IJ change VPN to UHG-ECC | NSPE0010708714
|  | 14100 BUSINESS CENTER DR NW ELK RIVER, MN 55330 USA | 10G-LANP-10GBSUU (5946374) | 05/03/2017: 05/02 Need to rescheduling. Customer will need to check cabling on their end first. | 8922883 |  | US Private Line (5946374) | 5946374 | 10G-LANP-10GBSUU (5946374) |  |  | W1C58354 (5946374) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | Minneapolis: LEC circuit: jx511llm80001 Demarc Location: -LLM8/06 location extended to Ao161 FB6 (A) left panel position 1,2 Handoff: SMF Chicago: LEC circuit: jcbb5sbb5s0021 Demarc Location: 5th FL cage 400 rack 0110 PP: 1012914 position 25 & 26 Handoff: SMF | TOM KRENN 763 744 1500 TOM.KRENN@OPTUM.COM | JOHN SERGOT 763 744 1582 JOHN.SERGOT@OPTUM.COM |  |  |  | 12/14/2016 (5946374) |  |  | 01/06/2017 (5946374) | 01/16/2017 (5946374) |  |  |  | N (5946374) | 00198894 |  | 10G USPL type1 Elk River MN to Chicago IL
|  | 4500 WILLIAMS DR GEORGETOWN, TX 78633 USA | 1.536 MBPS (IQBLD4R2) | 03/30/2017: 03/30 Background: Georgetown, TX; New 10.752 7xT1 PIP MLPPP; Frontier; No NID; No MNS Status: Loop delivered 03/27. Pending line testing Next action: Circuit ready for activation Who owns the next action: TASC Ticket: NA | 8938926 |  | Private IP (IQBLD4R2) EVC/PVC Service (N.11224274.5813261) | IQBLD4R2 N.11224274.5813261 | 10.752 MBPS | P2153754 |  | BCBLBCBV0001 (IQBLD4R2) BCBLBCBV0002 (IQBLD4R2) BCBLBCBV0003 (IQBLD4R2) BCBLBCBV0004 (IQBLD4R2) BCBLBCBV0005 (IQBLD4R2) BCBLBCBV0006 (IQBLD4R2) BCBLBCBV0007 (IQBLD4R2) | 13/HCGS/219274//FTNC/ (IQBLD4R2M36VMB01) | 5813261 | 1512 | VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64542 PE IP Address : 152.187.199.185 CE Address : 152.187.199.186 QoS - Egress Profile: R12 PVC ID : 5813261 |  |  |  | FRONTIER (IQBLD4R2M36VMB01) | 10/26/2016 (IQBLD4R2M36VMB01) | 01/05/2017 (IQBLD4R2M36VMB01) | 03/27/2017 (IQBLD4R2M36VMB01) |  |  | Verizon circuit ID: P2153754 (BCBLBCBV0001-0007 ) LEC circuit ID: 13/HCGS/219274//FTNC/ DMARC Location: TELCO TERM CABINET BCBLBCBV0001 -shelf 1 slot 1 BCBLBCBV0002 -shelf 1 slot 2 BCBLBCBV0003 -shelf 1 slot 3 BCBLBCBV0004 -shelf 1 slot 4 BCBLBCBV0005 -shelf 2 slot 1 BCBLBCBV0006 -shelf 2 slot 2 BCBLBCBV0007 -shelf 2 slot 3 |  | MICHAEL HOLIMAN 0015127969583 MHOLIMAN@TRIMBUILT.COM |  |  |  | 03/30/2017 (IQBLD4R2) |  |  | 01/06/2017 (IQBLD4R2) | 02/06/2017 (IQBLD4R2) |  |  |  | Y (IQBLD4R2) Y (N.11224274.5813261) | 05017789 87521939 |  | OR 193533640 - 7xT1 10.752K TX255-05-IJ Georgetown TX | NSPE0010711845
|  | 1707 W CREEK LN CHASKA, MN 55318 USA | 10G-LANP-10GBSUU (5944694) | 05/08/2017: 05/07 Successfully activated | 8922799 |  | US Private Line (5944694) | 5944694 | 10G-LANP-10GBSUU (5944694) |  |  | W1C58337 (5944694) | [7 empty] | SOUTHWESTERN BELL-NORTH TEXAS | [6 empty] | TOM KRENN 763 744 1500 TOM.KRENN@OPTUM.COM | JOHN SERGOT 763 744 1582 JOHN.SERGOT@OPTUM.COM |  |  |  | 01/12/2017 (5944694) | 05/07/2017 |  | 01/13/2017 (5944694) | 01/12/2017 (5944694) |  |  |  | N (5944694) | 00198894 |  | 10G USPL type1 Chaska MN to Dallas TX
|  | 1900 N MAIN AVE SAN ANTONIO, TX 78212 USA | 1.536 MBPS (IQBLD6VS) | 11/17/2016: 11/17 - Customer site ready. Pending loop delivery date. | 8945570 |  | Private IP (IQBLD6VS) EVC/PVC Service (N.11230179.5815254) | IQBLD6VS N.11230179.5815254 | 10.752 MBPS | P2154157 |  | BCBLBCTS0001 (IQBLD6VS) BCBLBCTS0002 (IQBLD6VS) BCBLBCTS0003 (IQBLD6VS) BCBLBCTS0004 (IQBLD6VS) BCBLBCTS0005 (IQBLD6VS) BCBLBCTS0006 (IQBLD6VS) BCBLBCTS0007 (IQBLD6VS) | 31/HCGS/711123//SW (1282957) | 5815254 | 3000 | VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64538 PE IP Address : 68.136.26.229 CE Address : 68.136.26.230 QoS - Egress Profile: R12 PVC ID : 5815254 |  |  |  | ATT (1282957) | 11/16/2016 (1282957) | 11/23/2016 (1282957) | 11/17/2016 (1282957) |  |  |  |  | ANDREW ROSALES 0012103302945 AROSALES@WELLMED.NET |  |  |  | 11/18/2016 (IQBLD6VS) |  |  | 11/16/2016 (IQBLD6VS) | 12/16/2016 (IQBLD6VS) |  |  |  | N (IQBLD6VS) N (N.11230179.5815254) | 05017789 87521941 |  | TX116-05-IJ New 7xT1 O-1612077 CW Order (ID : 193555019) NSPE0010733961 | NSPE0010733961
|  | 2701 W SAINT ISABEL ST TAMPA, FL 33607 USA | 1.536 MBPS (IQBLD6R3) | 01/27/2017: 1/27 Order completed- ready for plug and play- cust notified | 8945301 |  | Private IP (IQBLD6R3) EVC/PVC Service (N.11229994.5815211) | IQBLD6R3 N.11229994.5815211 | 10.752 MBPS | P2154139 |  | BCBLBCS50001 (IQBLD6R3) BCBLBCS50002 (IQBLD6R3) BCBLBCS50003 (IQBLD6R3) BCBLBCS50004 (IQBLD6R3) BCBLBCS50005 (IQBLD6R3) BCBLBCS50006 (IQBLD6R3) BCBLBCS50007 (IQBLD6R3) | 65/HCGS/229893//FTNC/ (IQBLD6R3SB7VMB01) 65/HCGS/229895//FTNC/ (IQBLD6R3SB7VMB02) | 5815211 | 1512 | VPN Name : UnitedHealthGroup Router Name : AUBGE03 VRF Name : V542236:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64555 PE IP Address : 152.192.76.149 CE Address : 152.192.76.150 QoS - Egress Profile: R12 PVC ID : 5815211 |  |  |  | FRONTIER (IQBLD6R3SB7VMB01) FRONTIER (IQBLD6R3SB7VMB02) | 11/23/2016 (IQBLD6R3SB7VMB01) 11/23/2016 (IQBLD6R3SB7VMB02) | 01/23/2017 (IQBLD6R3SB7VMB01) 01/23/2017 (IQBLD6R3SB7VMB02) | 01/19/2017 (IQBLD6R3SB7VMB01) 01/26/2017 (IQBLD6R3SB7VMB02) |  |  | Verizon circuit ID: P2154139= (BCBLBCS50001-0007) LEC circuit ID: Listed below VZ CKT ID LEC CKT/ Demarc BCBLBCS50001 65/HCGS/229893/ / Demarc: 2nd Floor IT Room: Slot 1, Shelf 1, Port 1, Jack RJ48C BCBLBCS50002 65/HCGS/229894/ / Demarc: 2nd Floor IT Room: Slot 6, Shelf 1, Port 6, Jack RJ48C BCBLBCS50003 65/HCGS/229895/ / Demarc : 2nd Floor IT Room: Slot 3, Shelf 1, Port 3, Jack RJ48C BCBLBCS50004 65/HCGS/229896/ / Demarc: 2nd Floor IT Room: Slot 8, Shelf 1, Port 8, Jack RJ48C BCBLBCS50005 65/HCGS/229897/ / Demarc: 2nd Floor IT Room: Slot 4, Shelf 1, Port 4, Jack RJ48C BCBLBCS50006 65/HCGS/229898/ / Demarc: 2nd Floor IT Room: Slot 7, Shelf 1, Port 7, Jack RJ48C BCBLBCS50007 65/HCGS/229899/ / Demarc: 2nd Floor IT Room: Slot 5, Shelf 1, Port 5, Jack RJ48C |  | MIKE NELSON 0017278730822 2109513126 MINELSON@WELLMED.NET |  |  |  | 01/26/2017 (IQBLD6R3) |  |  | 01/30/2017 (IQBLD6R3) | 11/21/2016 (IQBLD6R3) |  |  |  | N (IQBLD6R3) N (N.11229994.5815211) | 05017789 87521940 |  | FL194-05-IJ New 7xT1 O-1612077 CW Order (ID : 193557475) NSPE0010734027 | NSPE0010734027
Completed | AL018-05-IJ | 1416 W I65 SERVICE RD S MOBILE, AL 36693-5100 US | 10 MBPS (23369488) | 02/09/2017: 02/09 Activation scheduled 02/10 12PM CST | 193568775 | AL018-05-IJ | Private IP - PIP (23369487) Access (23369488) | 23369487 23369488 | 5 MBPS (23369487) |  | 143624894 (Private IP (PIP)) 143624892 (Access) | C0105864/ADD (23369487) E3030164/ADD (23369488) | A2/KRGN/466383//SC (2336948816589101) | 5816268 | 1500 | PVC ID : 5816268 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64649 PE IP Address : 152.187.238.113 CE Address : 152.187.238.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23369488) | 1000Base-SX (850nm, Multi Mode Fiber) (23369488) | Ethernet | ATT (2336948816589101) | 11/07/2016 (2336948816589101) | 02/08/2017 (2336948816589101) | 02/07/2017 (2336948816589101) | 02/10/2017 (VFORCE) (23369488) | 02/08/2017 (VFORCE) (23369488) | DEMARCADDR - 1416 WEST I-65 SERVICE RD S MOBILE AL DEMARCDET - 2ND FLR TELCO RM 3903 WALL MOUNT PORT |  | Amanda Bardwell 1-251-476-1866 abardwell@nphc.net | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 02/08/2017(Private IP - PIP) 02/08/2017(Access) |  |  | 02/17/2017 (23369487) 02/15/2017 (23369488) | 12/15/2016 | 02/08/2017 |  |  | N (23369487) N (23369488) | U0101953 |  | AL018-05-IJ New ethernet NSPE0010742299 OR 193566987 Gig UNI 1000BaseSX MMF LC 10mg access 5mg port | NSPE0010742299
Completed | PA119-02-IJ Pittsburgh | 2 ALLEGHENY CTR PITTSBURGH, PA 15212-5402 US | 200 MBPS (23660106) | 02/17/2017: 02/17 Need to be rescheduled as per al_thoreson@optum.com | 193576802 | PA119-02-IJ Pittsburgh | Access (23660106) Private IP - PIP (23660105) | 23660106 23660105 | 100 MBPS (23660105) |  | 144186987 (Access) 144186989 (Private IP (PIP)) | E5005541/ADD (23660106) C5002782/ADD (23660105) | 15.KFGS.306347..PA (2366010620296101) | 5830085 | 25000 | PVC ID : 5830085 VPN Name : UnitedHealthGroup Router Name : NORXE05 VRF Name : V575848-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64537 PE IP Address : 152.176.85.61 CE Address : 152.176.85.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23660106) | 1000Base-SX (850nm, Multi Mode Fiber) (23660106) | Ethernet | VERIZON (2366010620296101) | 12/29/2016 (2366010620296101) | 01/23/2017 (2366010620296101) | 01/18/2017 (2366010620296101) |  |  | DEMARCDET - 6TH FLR, SRVR RM, RIGHT WALL |  | Ben Fortun 1-412-501-0696 ben_fortun@uhg.com | Al Thoreson | al_thoreson@optum.com | 1-763-553-4196 | 01/18/2017(Access) 01/18/2017(Private IP - PIP) |  |  | 01/30/2017 (23660106) 02/01/2017 (23660105) | 02/13/2017 | 01/18/2017 |  |  | N (23660106) N (23660105) | U0101953 | Jeopardy Notification 1 (01/16/2017) |  | NSPE0010752619
Completed | C1328-05-IJ Teletech Englewood CO | 9197 S PEORIA ST ENGLEWOOD, CO 80112-5833 US | 1 GBPS (23419339) | 01/16/2017: 01/13 Successfully activated | 193591934 | C1328-05-IJ Teletech Englewood, CO | Private IP - PIP (23419338) Access (23419339) | 23419338 23419339 | 800 MBPS (23419338) |  | 145009664 (Private IP (PIP)) 145009602 (Access) | C0106575/ADD (23419338) E5005143/ADD (23419339) | 1V/KFFN/003330/LVLC (2341933917098202) | 5818888 | 550000 | PVC ID : 5818888 VPN Name : UHG-ECC Router Name : PHN19E01 VRF Name : V794184:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65431 PE IP Address : 152.192.93.201 CE Address : 152.192.93.202 QoS - Egress Profile: C13 | 1000Base-SX-850nm (23419339) | 1000Base-SX (850nm, Multi Mode Fiber) (23419339) | Ethernet | LEVEL 3 (2341933917098202) | 11/14/2016 (2341933917098202) | 11/30/2016 (2341933917098202) | 11/17/2016 (2341933917098202) | 12/01/2016 (VFORCE) (23419339) | 12/01/2016 (VFORCE) (23419339) | first floor data center rack 2A12 in RU 14 HANDOFF TYPE: 1000Base-SX (850nm, Multi Mode Fiber) |  | KEVIN WALL 1-303-397-8408 kevinwall@teletech.com | William Goss | william_Goss@optum.com | 1-763-744-1528 | 12/01/2016(Private IP - PIP) 12/01/2016(Access) | 01/13/2017 |  | 11/30/2016 (23419338) 11/28/2016 (23419339) | 12/23/2016 | 12/01/2016 |  |  | N (23419338) N (23419339) | U0101953 |  |  | NSPE0010766285
Completed | TX023-05-IJ Richardson TX | 1311 W PRESIDENT GEORGE BUSH HWY RICHARDSON, TX 75080-1153 US | 100 MBPS (23423328) | 03/22/2017: 03/21 Successfully activated | 193593782 | TX023-05-IJ Richardson, TX | Private IP - PIP (23423327) Access (23423328) | 23423327 23423328 | 100 MBPS (23423327) |  | 145216330 (Private IP (PIP)) 145216328 (Access) | C1046156/ADD (23423327) E4015844/ADD (23423328) | 14/KRGN/879720//SW (2342332822568901) | 5819053 | 110000 | PVC ID : 5819053 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64517 PE IP Address : 199.220.252.217 CE Address : 199.220.252.218 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23423328) | 1000Base-SX (850nm, Multi Mode Fiber) (23423328) | Ethernet | ATT (2342332822568901) | 11/14/2016 (2342332822568901) | 11/30/2016 (2342332822568901) | 12/01/2016 (2342332822568901) | 12/05/2016 (VFORCE) (23423328) | 12/05/2016 (VFORCE) (23423328) | LEC: 1ST FLOOR TELCO CLOSET WALL MOUNT SHELF 1 PORT 6. |  | RAYMOND EGANA 1-214-438-8244 raymond_egana@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 12/05/2016(Private IP - PIP) 12/05/2016(Access) | 03/21/2017 |  | 12/09/2016 (23423327) 12/07/2016 (23423328) | 12/27/2016 | 12/05/2016 |  |  | N (23423327) N (23423328) | U0101953 |  |  | NSPE0010768419
Completed | MA008-02-IJ Boston MA | 1325 BOYLSTON ST BOSTON, MA 02215-3909 US | 100 MBPS | 01/16/2017: 11/22 Upgraded to 100M. | 193608343 | MA008-02-IJ Boston MA | Private IP - PIP (23452834) Access | 23452834 | 100 MBPS (23452834) |  | 91074935 (Private IP (PIP)) 91074933 | C1030989/NONE (23452834) |  | 5702049 | 25000 | PVC ID : 5702049 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64705 PE IP Address : 68.139.45.41 CE Address : 68.139.45.42 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Doug Downie 1-781-420-0830 douglas_downie@uhg.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 11/23/2016(Private IP | 11/22/2016 |  | 11/17/2016 (23452834) | 11/29/2016 | 11/23/2016 |  |  | N (23452834) N | U0101953 |  | OR 193607293 - upgrade | NSPE0010782700
Completed | MD101-05-IJ Columbia MD | 10175 LITTLE PATUXENT PKWY COLUMBIA, MD 21044-2602 US | 200 MBPS (23639591) | 04/27/2017: 04/27 Activaiton needs to be rescheduled. BEAS is not pinging. Created ticket for dispatch MDRE-615-850 to check it. | 193610174 | MD101-05-IJ Columbia MD | Private IP - PIP (23639590) Access (23639591) | 23639590 23639591 | 100 MBPS (23639590) |  | 146054703 (Private IP (PIP)) 146054541 (Access) | C5002776/ADD (23639590) E5005528/ADD (23639591) | 38.KFGS.302290..CM (2363959120653801) | 5828858 | 15000 | PVC ID : 5828858 VPN Name : UnitedHealthGroup Router Name : RAY9E03 VRF Name : V534296:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64530 PE IP Address : 152.164.58.81 CE Address : 152.164.58.82 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23639591) | 1000Base-SX (850nm, Multi Mode Fiber) (23639591) | Ethernet | VERIZON (2363959120653801) | 02/21/2017 (2363959120653801) | 04/03/2017 (2363959120653801) | 03/21/2017 (2363959120653801) |  |  | DEMARCADDR - 10175 LITTLE PATUXENT PKWY, COLUMBIA, MD DEMARCDET - 3RD ROOM 305 CLOSET WALL MOUNTED NID #2 |  | Brian Shumate 1-410-740-9500 bshumate@costelloconstruction.com | MASROOR KHAN | masroor_khan@optum.com | 1-763-694-7370 | 03/21/2017(Private IP - PIP) 03/21/2017(Access) |  |  | 04/12/2017 (23639590) 04/10/2017 (23639591) | 04/04/2017 | 03/21/2017 |  |  | N (23639590) N (23639591) | U0101953 | Jeopardy Notification 2 (02/13/2017) |  | NSPE0010784824
Completed | PA097-02-IJ Havertown PA | 4 RAYMOND DR STE H HAVERTOWN, PA 19083-3188 US | 50 MBPS (23767820) | 04/20/2017: 04/20 Activation successful | 193627569 | PA097-02-IJ Havertown, PA | Access (23767820) Private IP - PIP (23767819) | 23767820 23767819 | 10 MBPS (23767819) |  | 141324891 (Access) 141324893 (Private IP (PIP)) | E4017371/ADD (23767820) C4006269/ADD (23767819) | 11.KEGS.318844..PA (2376782016913501) | 5837472 | 1500 | PVC ID : 5837472 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64595 PE IP Address : 152.187.251.233 CE Address : 152.187.251.234 QoS - Egress Profile: R12 | 100Base-FX - MMF (23767820) | 100Base-FX (1310nm, Multi Mode Fiber) (23767820) | Ethernet | VERIZON (2376782016913501) | 01/20/2017 (2376782016913501) | 04/06/2017 (2376782016913501) | 03/22/2017 (2376782016913501) |  |  | DEMARCADDR - 4 RAYMOND DR, HAVERFORD, PA DEMARCDET - DEMARK GROUND FLOOR SERVER ROOM WALL MOUNTED UNIT #1 TAGGED NOT EXTENDED |  | Jenny Cleary 1-484-450-0140 jcleary@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 | 03/22/2017(Access) 03/22/2017(Private IP - PIP) | 04/20/2017 |  | 04/13/2017 (23767820) 04/17/2017 (23767819) | 04/26/2017 | 03/22/2017 |  |  | N (23767820) N (23767819) | U0101953 |  | Order Request 193619298 NSPE0010792911 PI Sup of SO 193527450 | NSPE0010792911
Completed | UHG XL Health | 3100 SW 145TH AVE MIRAMAR, FL 33027-6610 US | 100 MBPS (23518960) | 06/28/2017: 06/28 Successfully activated | 193637658 | UHG XL Health | Private IP - PIP (23518959) Access (23518960) | 23518959 23518960 | 100 MBPS (23518959) |  | 148014328 (Private IP (PIP)) 148014326 (Access) | C1047307/ADD (23518959) E4016211/ADD (23518960) | 60/KRGN/757873//SB (2351896016272601) | 5823217 | 70000 | PVC ID : 5823217 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65215 PE IP Address : 68.138.172.29 CE Address : 68.138.172.30 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23518960) | 1000Base-SX (850nm, Multi Mode Fiber) (23518960) | Ethernet | ATT (2351896016272601) | 11/30/2016 (2351896016272601) | 12/14/2016 (2351896016272601) | 12/15/2016 (2351896016272601) | 01/04/2017 (VFORCE) (23518960) | 01/05/2017 (VFORCE) (23518960) | DEMARCADDR - 3100 SW 145TH AV MIRAMAR FL DEMARCDET - 4TH FLOOR METER ROOM WALL MOUNTED |  | Jan Seoane 1-954-378-0680 jan_seoane@uhg.com | Katherine Acain | katherine_acain@optum.com | 632-588-5327 | 01/05/2017(Private IP - PIP) 01/05/2017(Access) | 06/27/2017 |  | 12/23/2016 (23518959) 12/21/2016 (23518960) | 01/12/2017 | 01/05/2017 |  |  | N (23518959) N (23518960) | U0101953 |  | FL054-05-IJ New Ethernet NSPE0010807815 OR 193635036 | NSPE0010807815
Completed | RI001-02-IJ Johnston RI | 1301 ATWOOD AVE JOHNSTON, RI 02919-4900 US | 200 MBPS (23639612) | 02/10/2017: 2/9 Activation completed | 193664769 | RI001-02-IJ Johnston, RI | Private IP - PIP (23639611) Access (23639612) | 23639611 23639612 | 100 MBPS (23639611) |  | 148922197 (Private IP (PIP)) 148922195 (Access) | C5002770/ADD (23639611) E5005520/ADD (23639612) | 85.KFGS.006717..NE (2363961219490601) | 5828856 | 40000 | PVC ID : 5828856 VPN Name : UnitedHealthGroup Router Name : HLB9E01 VRF Name : V385919:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64545 PE IP Address : 147.225.125.77 CE Address : 147.225.125.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23639612) | 1000Base-SX (850nm, Multi Mode Fiber) (23639612) | Ethernet | VERIZON (2363961219490601) | 12/22/2016 (2363961219490601) | 02/07/2017 (2363961219490601) | 02/03/2017 (2363961219490601) |  |  | DEMARCADDR - 1301 ATWOOD AV, JSTN, RI DEMARCDET - 3RD FLOOR SERVER ROOM RACK MOUNTED POS 2 OF 2 TAGGED ID'S |  | DAVID LAWLEY 1-603-629-7751 david_lawley@uhg.com | MATT PRIMOZICH | matt_primozich@optum.com | 1-763-553-4750 | 02/03/2017(Private IP - PIP) 02/03/2017(Access) | 02/09/2017 |  | 02/16/2017 (23639611) 02/14/2017 (23639612) | 02/15/2017 | 02/03/2017 |  |  | N (23639611) N (23639612) | U0101953 |  |  | NSPE0010833683
Completed | GA024-05-IJ Apharetta | 3025 WINDWARD PLZ ALPHARETTA, GA 30005-8728 US | 50 MBPS (23661181) | 02/08/2017: 02/08 Successfully activated. Matthew_Adams@optum.com accepted the circuit. | 193706381 | GA024-05-IJ Apharetta | Private IP - PIP (23661180) Access (23661181) | 23661180 23661181 | 20 MBPS (23661180) |  | 151017200 (Private IP (PIP)) 151017198 (Access) | C4006141/ADD (23661180) E4016901/ADD (23661181) | 38/KRGN/610708//SB (2366118121455701) | 5830176 | 5500 | PVC ID : 5830176 VPN Name : UnitedHealthGroup Router Name : CPZ3E02 VRF Name : V450868-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64725 PE IP Address : 152.181.92.173 CE Address : 152.181.92.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23661181) | 1000Base-SX (850nm, Multi Mode Fiber) (23661181) | Ethernet | ATT (2366118121455701) | 12/29/2016 (2366118121455701) | 01/18/2017 (2366118121455701) | 01/18/2017 (2366118121455701) | 01/25/2017 (VFORCE) (23661181) | 01/25/2017 (VFORCE) (23661181) | DEMARCADDR - 3025 WINDWARD PLZ ALPH GA DEMARCDET - 2ND FLSTE200 PH RM 3930#1 OPT HDOFFJK5 |  | Angieska Vaqar 1-404-772-7211 agnieszka_vaqar@uhg.com | HUMAYUN RAFI | humayun_rafi@optum.com | 91-990-002-2170 | 01/25/2017(Private IP - PIP) 01/25/2017(Access) | 02/08/2017 |  | 02/03/2017 (23661180) 02/01/2017 (23661181) | 02/01/2017 | 01/25/2017 |  |  | N (23661180) N (23661181) | U0101953 | Jeopardy Notification 1 (01/23/2017) | O-1860447 Quote ID: 193705021 Order Request 193706353 GA024-05-IJ | NSPE0010873861
Completed | UNV51-02-IJ Las Vegas | 650 N NELLIS BLVD LAS VEGAS, NV 89110-5382 US | 100 MBPS (23661279) | 04/27/2017: 04/26 Successfully activated | 193706499 | UNV51-02-IJ Las Vegas | Private IP - PIP (23661278) Access (23661279) | 23661278 23661279 | 50 MBPS (23661278) |  | 151012734 (Private IP (PIP)) 151012732 (Access) | C1048611/ADD (23661278) E4016904/ADD (23661279) | 33.KFGX.001260..COXC. (2366127921455601) | 5830180 | 3000 | PVC ID : 5830180 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65210 PE IP Address : 68.138.104.181 CE Address : 68.138.104.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23661279) | 1000Base-SX (850nm, Multi Mode Fiber) (23661279) | Ethernet | COX (2366127921455601) | 12/29/2016 (2366127921455601) | 04/24/2017 (2366127921455601) |  | 03/29/2017 (VFORCE) (23661279) | 03/29/2017 (VFORCE) (23661279) | DEMARCDET - 1st floor data room customer provided rack patch panel 01, CUST .01.27 ,port 16 of patch paneL |  | TAUOA FALO 1-702-242-7654 tauoa.falo@optum.com | Joseph Zaepfel | Joseph_Zaepfel@optum.com | 1-763-744-2027 | 03/29/2017(Private IP - PIP) 03/29/2017(Access) | 04/26/2017 |  | 04/04/2017 (23661278) 03/31/2017 (23661279) | 02/09/2017 | 03/29/2017 |  |  | N (23661278) N (23661279) | U0101953 |  | O-1580611 Quote ID: 193704960 Order Request 193706349 UNV51-02-IJ | NSPE0010873893
|  | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10G-LANP-10GBSUU (5970102) | 12/20/2016: 12/20 Pending Ready For Traffic for CCR(Capacity creation request) is 1327445. Next action: Cust sched activation Who owns the next action:Cust Ticket: | 9003754 |  | US Private Line (5970102) | 5970102 | 10G-LANP-10GBSUU (5970102) |  |  | W1C58354 (5970102) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | Minneapolis: LEC circuit: jx511llm80001 Demarc Location: -LLM8/06 location extended to Ao161 FB6 (A) left panel position 1,2 Handoff: SMF Chicago: LEC circuit: jcbb5sbb5s0021 Demarc Location: 5th FL cage 400 rack 0110 PP: 1012914 position 25 & 26 Handoff: SMF | TOM KRENN 763 744 1500 TOM.KRENN@OPTUM.COM | JOHN SERGOT 763 744 1582 JOHN.SERGOT@OPTUM.COM |  |  |  | 01/19/2017 (5970102) |  |  | 02/10/2017 (5970102) | 03/14/2017 (5970102) |  |  |  | N (5970102) | 00198894
Completed | 100M Ethernet PIP Tampa FL | 5908 HAMPTON OAKS PKWY TAMPA, FL 33610-9505 US | 1 GBPS | 02/09/2017: 02/09 Successfully activated. Najiulla Kalleru +9900504264 accepted the circuit. | 193708366 | 100M Ethernet PIP Tampa FL | Private IP - PIP (23666681) Access | 23666681 | 500 MBPS (23666681) |  | 59254582 (Private IP (PIP)) 59254581 | C0028306/NONE (23666681) |  | 5552638 5552639 | 450000 | PVC ID : 5552638,5552639 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65033 PE IP Address : 147.225.208.33 CE Address : 147.225.208.34 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | John Marrone 1-407-926-2411 john.marrone@connextions.com | Tauoa Falo | tauoa.falo@optum.com | 1-702-242-7654 | 02/09/2017(Private IP | 02/09/2017 |  | 12/30/2016 (23666681) | 01/11/2017 | 02/09/2017 |  |  | N (23666681) N | U0101953 |  | Quote ID: 193707088 Order Request 193708063 UFL88-11-CJ | NSPE0010875533
Completed | TX720-02-IJ | 1950 N STEMMONS FWY STE 1070 DALLAS, TX 75207-3134 US | 500 MBPS (23666897) | 04/11/2017: 04/10 Successfully activated | 193708529 | TX720-02-IJ | Private IP - PIP (23666896) WAN Analysis Reporting (23666898) Access (23666897) | 23666896 23666898 23666897 | 150 MBPS (23666896) |  | 151199285 (Private IP (PIP)) 151199286 (WAN Analysis Reporting) 151199283 (Access) | C5002789/ADD (23666896) E5005555/ADD (23666897) |  | 5830521 | 180000 | PVC ID : 5830521 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64795 PE IP Address : 68.137.1.21 CE Address : 68.137.1.22 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (23666897) | Ethernet | [5 empty] | 02/18/2017 (CCP) (23666896) 02/18/2017 (CCP) (23666897) | Viawest j3 suite 1070--MEET-ME-ROOM--105.3.12 --PORT 1 |  | Arvin Manalo 1-817-514-5999 arvin.manalo@usmd.com | RANJI ADHIKAI | ranjit_adhikari@optum.com | 1-763-744-1957 | 02/21/2017(Private IP - PIP) 02/21/2017(WAN Analysis Reporting) 02/21/2017(Access) | 04/10/2017 |  | 02/21/2017 (23666896) 02/17/2017 (23666897) | 02/21/2017 02/27/2017 | 02/21/2017 |  | Activated/Installed | N (23666896) N (23666898) N (23666897) | U0101953 |  | SFDC Opportunity ID O-1750737 Quote ID: 193707835 Order Request 193708175 TX720-02-IJ | NSPE0010875601
Completed | CA768-02-IJ UHG - Monarch | 2301 W 120TH ST HAWTHORNE, CA 90250-3319 US | 1 GBPS (23666835) | 03/10/2017: 3/10 Ready to activate; customer notified | 193708498 | CA768-02-IJ UHG - Monarch | Access (23666835) Private IP - PIP (23666834) | 23666835 23666834 | 300 MBPS (23666834) |  | 151204082 (Access) 151204124 (Private IP (PIP)) | E5005553/ADD (23666835) C0111524/ADD (23666834) | 13/KRGN/589394//PT (2366683581893201) | 5830516 | 500000 | PVC ID : 5830516 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65011 PE IP Address : 152.183.25.173 CE Address : 152.183.25.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23666835) | 1000Base-SX (850nm, Multi Mode Fiber) (23666835) | Ethernet | ATT (2366683581893201) | 01/12/2017 (2366683581893201) | 01/23/2017 (2366683581893201) | 01/26/2017 (2366683581893201) | 03/09/2017 (VFORCE) (23666835) | 03/09/2017 (VFORCE) (23666835) | DEMARCADDR - 2301 W 120TH HAW DEMARCDET - RR101.04 SHELF-8,PORT 5&6 |  | AMIR SEMNANIAN 1-949-573-3530 asemnanian@mhealth.com | HUMAYUN RAFI | humayun_rafi@optum.com | 91-990-002-2170 | 03/09/2017(Access) 03/09/2017(Private IP - PIP) |  |  | 03/22/2017 (23666835) 03/24/2017 (23666834) | 03/22/2017 | 03/09/2017 |  |  | N (23666835) N (23666834) | U0101953 | Jeopardy Notification 1 (03/07/2017) | O-1863703 Order Request 193708296 has been generated for the Quote 193708093 CA768-11-IJ | NSPE0010875668
Completed | TX272-02-IJ Irving | 8400 ESTERS BLVD STE 185 IRVING, TX 75063-2864 US | 50 MBPS (23716329) | 05/10/2017: 05/09 Successfully activated | 193730453 | TX272-02-IJ Irving | Private IP - PIP (23716328) Access (23716329) | 23716328 23716329 | 10 MBPS (23716328) |  | 151821669 (Private IP (PIP)) 151821667 (Access) | C4006219/ADD (23716328) E4017130/ADD (23716329) | 1T/KFFN/005311/LVLC (2371632921583601) | 5833632 | 1500 | PVC ID : 5833632 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64834 PE IP Address : 152.183.108.25 CE Address : 152.183.108.26 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23716329) | 1000Base-SX (850nm, Multi Mode Fiber) (23716329) | Ethernet | LEVEL 3 (2371632921583601) | 01/12/2017 (2371632921583601) | 02/09/2017 (2371632921583601) | 02/07/2017 (2371632921583601) | 04/04/2017 (VFORCE) (23716329) | 04/04/2017 (VFORCE) (23716329) | DEMARCDET - 1st fl, common telco room, row 1, rack 1, RMU 15 cisco 3600 IRNGTX29W2001 port g0/10, MM LC connectors, tagged w/circuit ID. |  | Larry Freni 1-913-747-3700 lfreni@axelacare.com | Raul Barloso | raul_barloso@optum.com | 632-790-6271 | 04/04/2017(Private IP - PIP) 04/04/2017(Access) | 05/09/2017 |  | 04/18/2017 (23716328) 04/14/2017 (23716329) | 04/14/2017 | 04/04/2017 |  |  | N (23716328) N (23716329) | U0101953 | Jeopardy Notification 2 (02/14/2017) | Order Request # 193724571 - TX272-02-IJ Irving | NSPE0010891048
Completed | UIN09-08-IJ Vincennes IN | 2011 WILLOW ST VINCENNES, IN 47591-5463 US | 100 MBPS (23716332) | 09/15/2017: 09/14 Successfully activated | 193730412 | UIN09-08-IJ Vincennes IN | Private IP - PIP (23716331) Access (23716332) | 23716331 23716332 | 50 MBPS (23716331) |  | 151821673 (Private IP (PIP)) 151821671 (Access) | C1048994/ADD (23716331) E4017131/ADD (23716332) | /KRGN/104065//NB (2371633221583601) | 5833631 | 2500 | PVC ID : 5833631 VPN Name : UnitedHealthGroup Router Name : PLVXE01 VRF Name : V669152-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64730 PE IP Address : 68.136.55.5 CE Address : 68.136.55.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23716332) | 1000Base-SX (850nm, Multi Mode Fiber) (23716332) | Ethernet | ATT (2371633221583601) | 01/11/2017 (2371633221583601) | 02/08/2017 (2371633221583601) | 02/07/2017 (2371633221583601) | 02/20/2017 (VFORCE) (23716332) | 02/20/2017 (VFORCE) (23716332) | DEMARCADDR - 2011 WILLOW ST VINCENNES IN DEMARCDET - 1ST FLR, SERVER RM, WALL MOUNT UNDER TERMINAL PORT 2 OF FURUKAWA |  | Jeffrey S Cole 1-317-405-2965 jeffrey_cole@uhg.com | Javier Segui | Javier_segui@optum.com | 1-407-541-8143 | 02/20/2017(Private IP - PIP) 02/20/2017(Access) | 09/14/2017 |  | 03/07/2017 (23716331) 03/03/2017 (23716332) | 03/03/2017 | 02/20/2017 |  |  | N (23716331) N (23716332) | U0101953 |  | Order Request # 193724571 - UIN09-08-IJ Vincennes IN | NSPE0010891048
Completed |  | 9801 W HIGGINS RD ROSEMONT, IL 60018 USA ROSEMONT, IL 60018 | 10 MBPS (CQBLF1HT) 20 MBPS (CQBLF1HR) 20 MBPS (CQBLF2BV) | 03/31/2017: 02/22 Changes deployed | 9026665 |  | Private IP (CQBLF1HT) EACS (CQBLF1HR) EACS (C.11294459.5537385) EACS (CQBLF2BV) | CQBLF1HT CQBLF1HR C.11294459.5537385 CQBLF2BV | 10 MBPS 20 MBPS (CQBLF1HR) 20 MBPS (CQBLF2BV) | P2093906 P2093869 |  | BCBK61KL0001 (CQBLF1HT) EDBK61HL0001 (CQBLF1HR) EDBK61HL0001 (CQBLF2BV) |  | 5537385 | 5000 | VPN Name : UnitedHealthGroup Router Name : RVDL3E04 VRF Name : V556999-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64697 PE IP Address : 147.225.111.209 CE Address : 147.225.111.210 QoS - Egress Profile: R12 PVC ID : 5537385 | [11 empty] | JOHN SERGOT 8479282351 7637441582 JOHN_SERGOT@OPTUM.COM |  |  |  | 01/30/2017 (CQBLF1HT) 01/18/2017 (CQBLF1HR) 01/30/2017 (CQBLF2BV) | 02/22/2017 |  | 02/14/2017 (CQBLF1HT) 02/10/2017 (CQBLF1HR) 02/14/2017 (CQBLF2BV) | 02/14/2017 (CQBLF1HT) 02/10/2017 (CQBLF1HR) 02/10/2017 (11294459) 02/14/2017 (CQBLF2BV) |  |  |  | N (CQBLF1HT) N (CQBLF1HR) N (C.11294459.5537385) N (CQBLF2BV) | 05686886 0C08H7 |  | NSPE0010898435 CW 193732267 | NSPE0010898435
Completed |  | 6451 N FEDERAL HWY FT LAUDERDALE, FL 33308 USA | 50 MBPS (CQBLF0V0) 20 MBPS (CQBLF0Z5) | 03/02/2017: 03/01 Successfully activated | 9026663 |  | EACS (CQBLF0V0) Private IP (CQBLF0Z5) | CQBLF0V0 CQBLF0Z5 | 50 MBPS (CQBLF0V0) 20 MBPS | P2093743 P2093856 |  | EDBK60880001 (CQBLF0V0) BCBK61G70001 (CQBLF0Z5) |  |  | 10000 | VPN Name : UnitedHealthGroup Router Name : JAP3E01 VRF Name : V484472-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64695 PE IP Address : 68.139.117.81 CE Address : 68.139.117.82 QoS - Egress Profile: R12 | [11 empty] | JOHN SERGOT 9547721646 JOHN_SERGOT@OPTUM.COM |  |  |  | 01/19/2017 (CQBLF0V0) 03/01/2017 (CQBLF0Z5) | 03/01/2017 |  | 02/13/2017 (CQBLF0V0) 02/13/2017 (CQBLF0Z5) | 02/13/2017 (CQBLF0V0) 02/13/2017 (CQBLF0Z5) |  |  |  | N (CQBLF0V0) N (CQBLF0Z5) | 05686886 |  | NSPE0010898426 CW 193732578 | NSPE0010898426
Completed |  | 877 FRANKLIN RD SE MARIETTA, GA 30067 USA | 10 MBPS (CQBLF1LS) 10 MBPS (CQBLF1LV) | 04/27/2017: 04/26 Changes successfully deployed | 9026797 |  | EVC/PVC Service (C.11294693.5544407) Private IP (CQBLF1LV) EACS (CQBLF1LS) | C.11294693.5544407 CQBLF1LV CQBLF1LS | 10 MBPS (CQBLF1LS) 10 MBPS | P2096042 P2096077 |  | EDBK65YD0001 (CQBLF1LS) BCBK650X0001 (CQBLF1LV) |  | 5544407 | 5000 | PVC ID : 5544407 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64691 PE IP Address : 152.181.163.189 CE Address : 152.181.163.190 QoS - Egress Profile: R12 | [11 empty] | JOHN SERGOT 7637441582 7707677900 JOHN_SERGOT@OPTUM.COM |  |  |  | 01/20/2017 (CQBLF1LS) 01/20/2017 (CQBLF1LV) | 04/26/2017 |  | 02/13/2017 (CQBLF1LS) 02/13/2017 (CQBLF1LV) | 02/13/2017 (11294693) 02/13/2017 (CQBLF1LV) 02/13/2017 (CQBLF1LS) |  |  |  | N (C.11294693.5544407) N (CQBLF1LV) N (CQBLF1LS) | 0C1B75 05686886 |  | NSPE0010900456 CW 193735371 | NSPE0010900456
Completed |  | 9400 N CENTRAL EXPY DALLAS, TX 75231 USA | 20 MBPS (CQBLF01B) 10 MBPS (CQBLF01D) | 04/06/2017: 04/05 Changes successfully deployed VPN: UnitedHealthGroup ; ASN: 64688 ; bgp mdf password: UHGVERbgpbqZyofa ; BFD: Enable ; MULTICAST: Yes - Receive Auto RP ; COS: R12- Video ; ETH SHAPING : 85% ; | 9026814 |  | EACS (CQBLF01B) Private IP (CQBLF01D) | CQBLF01B CQBLF01D | 20 MBPS (CQBLF01B) 10 MBPS | P2095594 P2095624 |  | EDBK644F0001 (CQBLF01B) BCBK64540001 (CQBLF01D) |  |  | 5000 | VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64688 PE IP Address : 68.137.206.1 CE Address : 68.137.206.2 QoS - Egress Profile: R12 | [11 empty] | JOHN SERGOT 4693718890 JOHN_SERGOT@OPTUM.COM |  |  |  | 01/18/2017 (CQBLF01B) 01/18/2017 (CQBLF01D) | 04/05/2017 |  | 02/22/2017 (CQBLF01B) 02/22/2017 (CQBLF01D) | 02/22/2017 (CQBLF01B) 02/22/2017 (CQBLF01D) |  |  |  | N (CQBLF01B) N (CQBLF01D) | 05686886 |  | NSPE0010901286 CW 193736276 | NSPE0010901286
Completed | WI017-01-IJ LaCrosse WI | 328 FRONT ST S LA CROSSE, WI 54601-4023 US | 1 GBPS | 01/20/2017: 01/19 Hotcut successful | 193744546 | WI017-01-IJ LaCrosse WI | Private IP - PIP (23743428) Access | 23743428 | 300 MBPS (23743428) |  | 61514709 (Private IP (PIP)) 61514708 | C0029818/NONE (23743428) |  | 5565372 | 550000 | PVC ID : 5565372 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65168 PE IP Address : 152.183.189.157 CE Address : 152.183.189.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Tom Pesik 1-608-793-2910 tpesik@logisticshealth.com | Mark Dasovic | mark_dasovic@optum.com | 1-952-512-8650 | 01/26/2017(Private IP | 01/19/2017 |  | 01/17/2017 (23743428) | 01/25/2017 | 01/26/2017 |  |  | N (23743428) N | U0101953 |  | LA CROSSE WI US - OR 193739901 | NSPE0010904486
Completed | GA010-02-IJ Marietta GA | 1850 PARKWAY PL SE STE 1025 MARIETTA, GA 30067-4439 US | 1 GBPS | 01/20/2017: 01/19 Hotcut successful | 193744530 | GA010-02-IJ Marietta GA | Private IP - PIP (23743431) Access | 23743431 | 400 MBPS (23743431) |  | 71939287 (Private IP (PIP)) 71939285 | C0055697/NONE (23743431) |  | 5613296 | 250000 | PVC ID : 5613296 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64829 PE IP Address : 152.177.238.133 CE Address : 152.177.238.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Kevin Griffin 1-404-538-3584 Kevin.Griffen@alere.com | Mohan Basnet | mohan_basnet@optum.com | 1-763-744-1971 | 01/26/2017(Private IP | 01/19/2017 |  | 01/17/2017 (23743431) | 01/25/2017 | 01/26/2017 |  |  | N (23743431) N | U0101953 |  | MARIETTA GA US - OR 193739901 | NSPE0010904486
Completed | GA019-02-IJ Atlanta GA | 2100 RIVEREDGE PKWY ATLANTA, GA 30328-4693 US | 150 MBPS | 01/20/2017: 01/19 Hotcut successful | 193744528 | GA019-02-IJ Atlanta, GA | Private IP - PIP (23743423) Access | 23743423 | 100 MBPS (23743423) |  | 75260670 (Private IP (PIP)) 75260668 | C4001829/NONE (23743423) |  | 5627905 | 70000 | PVC ID : 5627905 VPN Name : UnitedHealthGroup Router Name : CPZ3E02 VRF Name : V450868-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64818 PE IP Address : 152.176.226.109 CE Address : 152.176.226.110 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Agnieszka Seremak 1-404-267-6571 agnieszka_seremak@uhg.com | Humayun Rafi | humayun_rafi@optum.com | 91-990-002-2170 | 01/26/2017(Private IP | 01/19/2017 |  | 01/26/2017 (23743423) | 01/25/2017 | 01/26/2017 |  |  | N (23743423) N | U0101953 |  | ATLANTA GA US - OR 193739901 | NSPE0010904486
Completed | IL043-02-IJ Catamaran Schaumburg | 1600 MCCONNOR PKWY SCHAUMBURG, IL 60173-6801 US | 200 MBPS | 01/20/2017: 01/19 Hotcut successful | 193744529 | IL043-02-IJ Catamaran Schaumburg | Private IP - PIP (23743434) Access | 23743434 | 150 MBPS (23743434) |  | 90041080 (Private IP (PIP)) 90041078 | C5001545/NONE (23743434) |  | 5693340 | 20000 | PVC ID : 5693340 VPN Name : UnitedHealthGroup Router Name : RVDL3E04 VRF Name : V556999-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64791 PE IP Address : 68.139.202.129 CE Address : 68.139.202.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Tim Fernandez 1-224-231-1154 timothy.fernandez@optum.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 01/26/2017(Private IP | 01/19/2017 |  | 01/17/2017 (23743434) | 01/25/2017 | 01/26/2017 |  |  | N (23743434) N | U0101953 |  | SCHAUMBURG IL US - OR 193739901 | NSPE0010904486
Completed | NY385-02-IJ Lake Success NY | 1 DAKOTA DR NEW HYDE PARK, NY 11042-1119 US | 100 MBPS | 01/20/2017: 01/19 Hotcut successful | 193744545 | NY385-02-IJ Lake Success NY | Private IP - PIP (23743422) Access | 23743422 | 10 MBPS (23743422) |  | 71742750 (Private IP (PIP)) 71742748 | C1022692/NONE (23743422) |  | 5616138 | 3000 | PVC ID : 5616138 VPN Name : UnitedHealthGroup Router Name : NV89E01 VRF Name : V105387:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64866 PE IP Address : 152.177.98.209 CE Address : 152.177.98.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Lawrence Douglas 1-516-622-6000 ldouglas@ProHEALTHcare.com | Deven Patterson | Deven_Patterson@optum.com | 1-210-877-7969 | 01/26/2017(Private IP | 01/19/2017 |  | 01/17/2017 (23743422) | 01/25/2017 | 01/26/2017 |  |  | N (23743422) N | U0101953 |  | NEW HYDE PARK NY US - OR 193739901 | NSPE0010904486
Completed | C1610-02-IJ Jefferson City | 3225 W TRUMAN BLVD JEFFERSON CITY, MO 65109-5709 US | 100 MBPS (23747281) | 02/28/2017: 02/28 Successfully activated. | 193746504 | C1610-02-IJ Jefferson City | Private IP - PIP (23747280) Access (23747281) | 23747280 23747281 | 30 MBPS (23747280) |  | 152880091 (Private IP (PIP)) 152880089 (Access) | C1049241/ADD (23747280) E4017272/ADD (23747281) | 48.KXGS.207881..UDMO (2374728121802301) | 5835539 | 25000 | PVC ID : 5835539 VPN Name : UHG-ECC Router Name : IDCXE03 VRF Name : V864747-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65530 PE IP Address : 68.139.3.73 CE Address : 68.139.3.74 QoS - Egress Profile: C13 | 1000Base-T (23747281) | 1000Base-T (23747281) | Ethernet | CENTURYLINK (2374728121802301) | 01/17/2017 (2374728121802301) | 02/24/2017 (2374728121802301) | 02/06/2017 (2374728121802301) | 02/08/2017 (VFORCE) (23747281) | 02/13/2017 (VFORCE) (23747281) | DEMARCDET - 1ST FLOOR, TELCO ROOM. RACK 1 OF 2, POSITION 2. |  | MICK BRIDGINS 1-636-812-4000 mick@roseint.com | JAVIER SEGUI | javier.segui@optum.com | 1-407-541-8143 | 02/13/2017(Private IP - PIP) 02/13/2017(Access) | 02/28/2017 |  | 03/07/2017 (23747280) 03/03/2017 (23747281) | 02/27/2017 | 02/13/2017 |  |  | N (23747280) N (23747281) | U0101953 |  | OR 193746148 - C1610-02-IJ | NSPE0010909413
Completed | TN019-02-IJ Franklin TN | 1897 GENERAL GEORGE PATTON DR STE 112 FRANKLIN, TN 37067-6319 US | 50 MBPS (23763892) | 03/15/2017: 03/15 Successfully activated | 193755124 | TN019-02-IJ Franklin, TN | Private IP - PIP (23763891) Access (23763892) | 23763891 23763892 | 50 MBPS (23763891) |  | 153388713 (Private IP (PIP)) 153388711 (Access) | C4006265/ADD (23763891) E4017356/ADD (23763892) | T4/KRGN/823002//SC (2376389212468001) | 5836835 | 1500 | PVC ID : 5836835 VPN Name : UnitedHealthGroup Router Name : NSVLXE01 VRF Name : V558718-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64739 PE IP Address : 152.185.6.185 CE Address : 152.185.6.186 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23763892) | 1000Base-SX (850nm, Multi Mode Fiber) (23763892) | Ethernet | ATT (2376389212468001) | 01/20/2017 (2376389212468001) | 02/06/2017 (2376389212468001) | 01/31/2017 (2376389212468001) | 02/01/2017 (VFORCE) (23763892) | 02/01/2017 (VFORCE) (23763892) | DMARC: SUITE 112 TELCO EQPT RM, RACK MOUNTED PORT 6 |  | RANDY PENNINGTON 1-615-791-5256 randy.pennington@catamaranrx.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 02/01/2017(Private IP - PIP) 02/01/2017(Access) | 03/14/2017 |  | 02/15/2017 (23763891) 02/13/2017 (23763892) | 03/01/2017 | 02/01/2017 |  |  | N (23763891) N (23763892) | U0101953 |  | OR 193754714 / NSPE0010916753 | NSPE0010916753
Completed | AZ046-02-IJ Green Valley | 695 S PECAN TREE LN GREEN VALLEY, AZ 85614-5114 US | 10 MBPS (23796365) | 07/28/2017: 07/27 Successfully activated | 193774822 | AZ046-02-IJ Green Valley | Private IP - PIP (23796364) Access (23796365) | 23796364 23796365 | 10 MBPS (23796364) |  | 154314430 (Private IP (PIP)) 154314428 (Access) | C0113052/ADD (23796364) E3033540/ADD (23796365) | 19.KXGS.210836..MS (2379636521224201) | 5839155 | 1500 | PVC ID : 5839155 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64799 PE IP Address : 68.136.204.121 CE Address : 68.136.204.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23796365) | 1000Base-SX (850nm, Multi Mode Fiber) (23796365) | Ethernet | CENTURYLINK (2379636521224201) | 04/19/2017 (2379636521224201) | 05/02/2017 (2379636521224201) | 04/28/2017 (2379636521224201) | 05/02/2017 (VFORCE) (23796365) | 05/02/2017 (VFORCE) (23796365) | DEMARCDET - 1st floor utility room wall mount optical port 2 |  | Edelmira Edi Cecena 1-520-625-8116 Edelmira.cecena@optum.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 | 05/02/2017(Private IP - PIP) 05/02/2017(Access) | 07/27/2017 |  | 04/27/2017 (23796364) 04/25/2017 (23796365) | 05/15/2017 | 05/02/2017 |  |  | N (23796364) N (23796365) | U0101953 |  | OR 193773804 - AZ046-02-IJ | NSPE0010934056
Completed | TX023-05-IJ Richardson TX | 1311 W PRESIDENT GEORGE BUSH HWY RICHARDSON, TX 75080-1153 US | 250 MBPS (23807864) | 03/23/2017: 3/23 Order Complete Cust notified | 193782692 | TX023-05-IJ Richardson, TX | Private IP - PIP (23807863) Access (23807864) | 23807863 23807864 | 150 MBPS (23807863) |  | 145216330 (Private IP (PIP)) 145216328 (Access) | C1046156/NONE (23807863) E4015844/NONE (23807864) | 14/KRGN/879720//SW (2380786422568903) | 5819053 | 110000 | PVC ID : 5819053 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64517 PE IP Address : 199.220.252.217 CE Address : 199.220.252.218 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23807864) | 1000Base-SX (850nm, Multi Mode Fiber) (23807864) | Ethernet | ATT (2380786422568903) | 02/21/2017 (2380786422568903) | 03/01/2017 (2380786422568903) |  |  |  | 1ST FLOOR TELCO CLOSET WALL MOUNT SHELF 1 PORT 6 |  | Susan Wagner 1-763-744-0632 susan_i_wagner@optum.com | Susan Wagner | susan_i_wagner@optum.com | 1-763-744-0632 | 03/22/2017(Private IP - PIP) 03/22/2017(Access) | 03/21/2017 |  | 03/08/2017 (23807863) 03/08/2017 (23807864) | 03/10/2017 | 03/22/2017 |  |  | N (23807863) N (23807864) | U0101953 |  | OR 193782468 - NSPE0010941559 | NSPE0010941559
Completed | Quality Metric-Fortinet-CPE | 6900 MUIRKIRK MEADOWS DR BELTSVILLE, MD 20705-6309 US |  | 02/16/2017: 02/16 Background: Beltsville, MD; Maintenance Renewal License; Status: Pending completion Next action: CPE group Who owns the next action: CPE Kristen Gates Ticket: NA | 193787264 | Quality Metric-Fortinet-CPE | CPE (23815174) | 23815174 |  |  | 152018392 (CPE) | [16 empty] | Kevin Plouffe 1-401-642-9228 kplouffe@qualitymetric.com | Kevin Plouffe | kplouffe@qualitymetric.com | 1-401-642-9228 | 02/22/2017(CPE) |  |  | 01/01/2018 (23815174) | 02/13/2017 | 02/22/2017 |  |  | N (23815174) | U0180027 |  | OR 193762633 | NSPE0010924467
Completed | OH044-02-IJ Columbus OH | 2182 DIVIDEND DR COLUMBUS, OH 43228-3806 US | 50 MBPS (23815249) | 06/07/2017: 06/07 Successfully activated | 193787341 | OH044-02-IJ Columbus, OH | Private IP - PIP (23815248) Access (23815249) | 23815248 23815249 | 10 MBPS (23815248) |  | 155120894 (Private IP (PIP)) 155120892 (Access) | C4006352/ADD (23815248) E4017696/ADD (23815249) | 94/KRGN/201564//OB (2381524922175501) | 5840388 | 7000 | PVC ID : 5840388 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64519 PE IP Address : 152.161.130.57 CE Address : 152.161.130.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23815249) | 1000Base-SX (850nm, Multi Mode Fiber) (23815249) | Ethernet | ATT (2381524922175501) | 01/31/2017 (2381524922175501) | 05/15/2017 (2381524922175501) | 05/15/2017 (2381524922175501) | 05/25/2017 (VFORCE) (23815249) | 05/25/2017 (VFORCE) (23815249) | DEMARCADDR - 2182 DIVIDEND DR COLUMBUS OH DEMARCDET - OUTSIDE WEST SIDE OF BLDG, FIBER TERM BOARD, FIBER |  | Terri Foley 1-614-799-2100 tfoley@rjboll.com | Charlie Vang | charlie_vang@optum.com | 1-763-744-1644 | 05/25/2017(Private IP - PIP) 05/25/2017(Access) | 06/07/2017 |  | 06/13/2017 (23815248) 06/09/2017 (23815249) | 06/09/2017 | 05/25/2017 |  |  | N (23815248) N (23815249) | U0101953 | Jeopardy Notification 1 (05/24/2017) | OR 193786882 | NSPE0010945173
|  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBLF7CK) | 02/10/2017: 2/10 Hotcut ready to acti vate; cust notified | 9042513 |  | EVC/PVC Service (N.11308485.5841491) Private IP Port Only (CQBLF7CK) | N.11308485.5841491 CQBLF7CK | 7000 MBPS | P1957529 |  | BOBKWHD00001 (CQBLF7CK) |  | 5841773 5841491 | 0 | PVC ID : 5841773,5841491 VPN Name : UnitedHealthGroup-ECCMA Router Name : MZZ9E01 VRF Name : V600584:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : 152.161.80.1 CE Address : 152.161.80.2 QoS - Egress Profile: R12 PVC ID : 5841773 | [11 empty] | ED MCLAUGHLIN ED ED 4438533646 0017637442081 EDWARD.MCLAUGHLIN@OPTUM.COM |  |  |  | 02/09/2017 (CQBLF7CK) | 09/16/2019 |  | 02/28/2017 (CQBLF7CK) | 02/28/2017 (CQBLF7CK) |  |  |  | N (N.11308485.5841491) N (CQBLF7CK) | P1957529 05017789 |  | CW 193786299 | NSPE0010946163
Completed | MS010-05-IJ | 795 WOODLANDS PKWY STE 301 RIDGELAND, MS 39157-5236 US | 100 MBPS (23848063) | 08/18/2017: 08/18 Ready for activation. Customer notified. | 193805164 | MS010-05-IJ | Private IP - PIP (23848061) Access (23848063) | 23848061 23848063 | 50 MBPS (23848061) |  | 94139099 (Private IP (PIP)) 94139095 (Access) | C1050578/ADD (23848061) E4017895/ADD (23848063) | 4I/KFFN/002008/LVLC (2384806322357001) | 5843035 | 25000 | PVC ID : 5843035 VPN Name : UnitedHealthGroup Router Name : NSVLXE01 VRF Name : Vj39243-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64713 PE IP Address : 152.187.253.37 CE Address : 152.187.253.38 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (23848063) | 1000Base-SX (850nm, Multi Mode Fiber) (23848063) | Ethernet | LEVEL 3 (2384806322357001) | 04/19/2017 (2384806322357001) | 08/18/2017 (2384806322357001) | 08/14/2017 (2384806322357001) | 08/16/2017 (VFORCE) (23848063) | 08/16/2017 (VFORCE) (23848063) | DEMARCDET - 2nd fl, comm room behind elevators, wall mount FDP ports 1 & 2, SM SC connectors, tagged w/circuit ID |  | Kobie Wells 1-601-718-6578 kobie_wells@uhc.com | Jerimiah Loscano | jermimiah_loscano@optum.com | 1-410-265-6033 | 08/16/2017(Private IP - PIP) 08/16/2017(Access) |  |  | 08/29/2017 (23848061) 08/25/2017 (23848063) | 09/25/2017 | 08/16/2017 |  |  | N (23848061) N (23848063) | U0101953 | Jeopardy Notification 1 (04/18/2017) | NSPE0010960246; OR 193803410 | NSPE0010960246
Completed | AZ124-05-IJ | 6245 E BROADWAY BLVD STE 600 TUCSON, AZ 85711-4037 US | 50 MBPS (23848066) | 10/26/2017: 10/25 Successfully activated | 193805180 | AZ124-05-IJ | Access (23848066) Private IP - PIP (23848065) | 23848066 23848065 | 20 MBPS (23848065) |  | 155925198 (Access) 155925200 (Private IP (PIP)) | E4017899/ADD (23848066) C4006430/ADD (23848065) | 1C/KFFN/002545/LVLC (2384806622359701) | 5842696 | 7000 | PVC ID : 5842696 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65106 PE IP Address : 152.177.20.149 CE Address : 152.177.20.150 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (23848066) | 1000Base-SX (850nm, Multi Mode Fiber) (23848066) | Ethernet | LEVEL 3 (2384806622359701) | 02/10/2017 (2384806622359701) | 03/17/2017 (2384806622359701) | 03/16/2017 (2384806622359701) | 03/30/2017 (VFORCE) (23848066) | 03/30/2017 (VFORCE) (23848066) | DEMARCDET - 2nd floor common telco room |  | Vince Lyons 1-623-777-3703 vincent_lyons@uhg.com | John Richard Raymundo | john_raymundo@optum.com | 632-588-5392 | 03/30/2017(Access) 03/30/2017(Private IP - PIP) | 10/25/2017 |  | 04/12/2017 (23848066) 04/14/2017 (23848065) | 04/12/2017 | 03/30/2017 |  |  | N (23848066) N (23848065) | U0101953 | Jeopardy Notification 2 (03/26/2017) | NSPE0010960246; OR 193803410 | NSPE0010960246
Completed | WA022-05-IJ | 1111 3RD AVE STE 1100 SEATTLE, WA 98101-3207 US | 50 MBPS (23848060) | 01/25/2018: 01/24 Need to reschedule activation as per customer | 193805131 | WA022-05-IJ | Access (23848060) Private IP - PIP (23848059) | 23848060 23848059 | 20 MBPS (23848059) |  | 94139050 (Access) 94139054 (Private IP (PIP)) | E4017880/ADD (23848060) C4006425/ADD (23848059) | 1D/KFFN/003546/LVLC (2384806022354801) | 5842646 | 7000 | PVC ID : 5842646 VPN Name : UnitedHealthGroup Router Name : K1B3E02 VRF Name : V461088-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65202 PE IP Address : 152.187.144.141 CE Address : 152.187.144.142 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (23848060) | 1000Base-SX (850nm, Multi Mode Fiber) (23848060) | Ethernet | LEVEL 3 (2384806022354801) | 02/09/2017 (2384806022354801) | 03/02/2017 (2384806022354801) | 02/28/2017 (2384806022354801) | 03/16/2017 (VFORCE) (23848060) |  | DEMARCADDR - . DEMARCDET - . |  | Mark N Franks 1-530-879-8072 mark_franks@uhg.com | Jerimiah Loscano | jermimiah_loscano@optum.com | 632-588-5331 | 03/16/2017(Access) 03/16/2017(Private IP - PIP) |  |  | 03/09/2017 (23848060) 03/13/2017 (23848059) | 03/22/2017 | 03/16/2017 |  |  | N (23848060) N (23848059) | U0101953 |  | NSPE0010960246; OR 193803410 | NSPE0010960246
Completed | MD021-05-CJ Towson | 8501 LA SALLE RD STE 200 TOWSON, MD 21286-5923 US | 100 MBPS (24108319) | 10/10/2017: 10/10 Activation scheduled 10/12/2017 10:30PM CST. | 193806428 | MD021-05-CJ Towson | Private IP - PIP (24108318) Access (24108319) | 24108318 24108319 | 50 MBPS (24108318) |  | 156062197 (Private IP (PIP)) 156062195 (Access) | C1051573/ADD (24108318) E4018646/ADD (24108319) | 38.KEGS.308996..CM (2410831922380001) | 5852255 | 25000 | PVC ID : 5852255 VPN Name : UnitedHealthGroup Router Name : HRJXE01 VRF Name : V607200-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65067 PE IP Address : 199.220.203.13 CE Address : 199.220.203.14 QoS - Egress Profile: R12 | 100Base-TX (24108319) | 100Base-TX (24108319) | Ethernet | VERIZON (2410831922380001) | 03/08/2017 (2410831922380001) | 04/03/2017 (2410831922380001) | 03/30/2017 (2410831922380001) |  |  | DEMARCADDR - . . . DEMARCDET - . . . . . . |  | Colleen Bartley 1-410-308-7949 colleen.bartley@uhcglobal.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 03/30/2017(Private IP - PIP) 03/30/2017(Access) |  |  | 04/12/2017 (24108318) 04/10/2017 (24108319) | 04/04/2017 | 03/30/2017 |  |  | N (24108318) N (24108319) | U0101953 |  | NSPE0010962533; OR 193805846 | NSPE0010962533
Completed | IL004-05-IJ Chicago IL | 200 E RANDOLPH ST CHICAGO, IL 60601-6436 US | 100 MBPS | 02/21/2017: 02/20 Upgrade successful. | 193824514 | IL004-05-IJ Chicago, IL | Private IP - PIP (23900540) Access | 23900540 | 50 MBPS (23900540) |  | 79359078 (Private IP (PIP)) 79359056 | C1026298/NONE (23900540) |  | 5650541 | 10000 | PVC ID : 5650541 VPN Name : UnitedHealthGroup Router Name : RVDL9E01 VRF Name : V550197:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65073 PE IP Address : 152.162.18.177 CE Address : 152.162.18.178 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Pete Wisniewski 1-312-348-7039 Peter.wisiniewski@optum.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 02/22/2017(Private IP | 02/20/2017 |  | 02/14/2017 (23900540) | 02/22/2017 | 02/22/2017 |  |  | N (23900540) N | U0101953 |  | NSPE0010963697 - Order RequesT 193807203 ; Davenport Ia; Downgrade to 150M PIP-Eth; NID; No MNS | NSPE0010963697
Completed | CT006-02-IJ Shelton CT | 4 RESEARCH DR SHELTON, CT 06484-6280 US | 400 MBPS | 03/13/2017: 03/10 Changes deployed successfully | 193824512 | CT006-02-IJ Shelton, CT | Private IP - PIP (23900963) Access | 23900963 | 150 MBPS (23900963) |  | 46729431 (Private IP (PIP)) 46729430 | C1008297/NONE (23900963) |  | 5509949 | 30000 | PVC ID : 5509949 VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65244 PE IP Address : 152.164.72.97 CE Address : 152.164.72.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Erica Swanson 1-203-459-7277 erica_swanson@uhg.com | Donald Osborn | Donald_r_osborn@optum.com | 1-214-647-4442 | 03/13/2017(Private IP | 03/10/2017 |  | 02/28/2017 (23900963) | 02/23/2017 | 03/13/2017 |  |  | N (23900963) N | U0101953 |  | NSPE0010963697 - Order RequesT 193807203; Chicago IL; Upgrade the port to 50M; 50M/100M Speed; NID; No MNS | NSPE0010963697
Completed | IA005-02-IJ Davenport IA | 250 E 90TH ST DAVENPORT, IA 52806-7340 US | 500 MBPS | 02/16/2017: 02/15 Successfully activated | 193824515 | IA005-02-IJ Davenport, IA | Access Private IP - PIP (23900537) | 23900537 | 150 MBPS (23900537) |  | 88604592 88604594 (Private IP (PIP)) | C5001490/NONE (23900537) |  | 5685166 | 10000 | PVC ID : 5685166 VPN Name : UnitedHealthGroup Router Name : RVDL9E01 VRF Name : V550197:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64709 PE IP Address : 68.138.154.237 CE Address : 68.138.154.238 QoS - Egress Profile: R12 | 1000Base-T | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | STEVE TOBIN 1-563-529-9127 stobin@estesconstruction.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 02/16/2017(Private IP | 02/15/2017 |  | 02/14/2017 (23900537) | 02/22/2017 | 02/16/2017 |  |  | N N (23900537) | U0101953 |  | NSPE0010963697 - Order RequesT 193807203; SHELTON CT; Upgrade the port to 150M; 150M/400M Speed; NID; No MNS | NSPE0010963697
Completed | GA024-05-IJ Apharetta | 3025 WINDWARD PLZ ALPHARETTA, GA 30005-8728 US |  | 02/16/2017: 02/16 Background: Record Change Only; Changing record from Optical to Electrical Status: To be closed Next action: to be closed Who owns the next action: Prov Ticket: NA | 193814216 | GA024-05-IJ Apharetta | Private IP - PIP (23888198) | 23888198 | 20 MBPS (23888198) |  |  | C4006141/NONE (23888198) |  | 5830176 | 5500 | PVC ID : 5830176 VPN Name : UnitedHealthGroup Router Name : CPZ3E02 VRF Name : V450868-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64725 PE IP Address : 152.181.92.173 CE Address : 152.181.92.174 QoS - Egress Profile: R12 | [11 empty] | Angieska Vaqar 1-404-772-7211 agnieszka_vaqar@uhg.com | HUMAYUN RAFI | humayun_rafi@optum.com | 91-990-002-2170 | 09/20/2017(Private IP | 03/09/2017 |  | 02/13/2017 (23888198) | 02/22/2017 | 09/20/2017 |  |  | N (23888198) | U0101953 |  | ***THIS IS A RECORD CHANGE ONLY. NO ACCESS/LOOP TO BE DELIVERED*** CHANGING RECORD FROM OPTICAL TO COPPER(1000BASE-T; RJ45) ONLY*** | NSPE0010969545
Completed | FL208-02-IJ | 8509 BENJAMIN RD TAMPA, FL 33634-1224 US | 4.6 MBPS (23888328) | 04/26/2017: 4/24 Ready to plug and play- cust notified | 193822585 | FL208-02-IJ | Access (23888328) Private IP - PIP (23888327) | 23888328 23888327 | 4.6 MBPS (23888327) |  | 156978505 (Access) 156978507 (Private IP (PIP)) | N1035418/ADD (23888328) N1035416/ADD (23888328) N1035417/ADD (23888328) C0114789/ADD (23888327) | 65/HCGS/640311//FTNC/ (2388832822320601) 65/HCGS/640312//FTNC/ (2388832822320601) | 5844330 | 2000 | PVC ID : 5844330 VPN Name : UnitedHealthGroup Router Name : AUB9E02 VRF Name : V428808:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64547 PE IP Address : 68.137.139.245 CE Address : 68.137.139.246 QoS - Egress Profile: R12 |  | DS1 (23888328) | TDM | FRONTIER (2388832822320601) | 04/11/2017 (2388832822320601) | 04/21/2017 (2388832822320601) | 04/21/2017 (2388832822320601) |  |  | DEMARCADDR - 8509 BENJAMEN RD, STE A DEMARCDET - POS@3 OF 8, SHELF#1, LOCATED IN 1ST FLOOR SERVER ROOM, W/OPE NER |  | Wendell Radcliff 1-828-768-4975 wendell@radcliffconstructionllc.com | Vincent Andal | vincent_andal@optum.com | 632-462-2485 | 04/21/2017(Access) 04/21/2017(Private IP - PIP) |  |  | 04/26/2017 (23888328) 04/28/2017 (23888327) | 05/02/2017 | 04/21/2017 |  |  | N (23888328) N (23888327) | U0101953 | Jeopardy Notification 3 (04/04/2017) | Order Request 193819046 | NSPE0010973610
|  | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10G-LANP-10GBSUU (5992751) | 05/08/2017: 05/07 Activation need to be reschedule due LOS alarm. Need to dispatch a tech to investigate and clear the LOS alarm. 05/05 Activation scheduled 05/07/2017 2PM CST | 9058338 |  | US Private Line (5992751) | 5992751 | 10G-LANP-10GBSUU (5992751) |  |  | W1C58354 (5992751) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | TOM KRENN 763 744 1500 TOM.KRENN@OPTUM.COM | JOHN SERGOT 763 744 1582 JOHN.SERGOT@OPTUM.COM |  |  |  | 02/16/2017 (5992751) |  |  | 03/01/2017 (5992751) | 03/14/2017 (5992751) |  |  |  | N (5992751) | 00198894 |  | Elk River MN & Chicago IL; Change Demarc; US PL; Metropolitan; No NID; No MNS
Completed | CA087-05-IJ Riverside | 1770 IOWA AVE STE 260 RIVERSIDE, CA 92507-7479 US | 3 MBPS (23933667) | 03/03/2017: 3/3 Ready for plug and play (2xT1); cust notified | 193831335 | CA087-05-IJ Riverside | Private IP - PIP (23933666) Access (23933667) | 23933666 23933667 | 3 MBPS (23933666) |  | 157555002 (Private IP (PIP)) 157555000 (Access) | C1050846/ADD (23933666) N1035477/ADD (23933667) N1035478/ADD (23933667) | 13/HCGS/874751//PT (2393366722640201) | 5845062 | 2000 | PVC ID : 5845062 VPN Name : UnitedHealthGroup Router Name : RTOGE04 VRF Name : V471548:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64945 PE IP Address : 152.177.53.81 CE Address : 152.177.53.82 QoS - Egress Profile: R12 |  | DS1 (23933667) | TDM | ATT (2393366722640201) | 02/16/2017 (2393366722640201) | 03/02/2017 (2393366722640201) | 03/02/2017 (2393366722640201) |  |  | DEMARCADDR - 1770 IOWA AV RIV DEMARCDET - 2.1 SH-3 SLOT-2 RJ48C POS-2 |  | Marcela Tovar 1-951-335-3398 marcela.tovar@uhc.com | jeremiah lascano | jeremiah_lascano@optum.com | 632-588-5331 | 03/02/2017(Private IP - PIP) 03/02/2017(Access) |  |  | 03/09/2017 (23933666) 03/07/2017 (23933667) | 03/09/2017 | 03/02/2017 |  |  | N (23933666) N (23933667) | U0101953 |  | Order Request 193830771 | NSPE0010983820
Completed | UOK03-07-IJ Tulsa | 7666 E 61ST ST STE 500 TULSA, OK 74133-1154 US | 10 MBPS (23933676) | 07/28/2017: 07/28 Successfully activated | 193831334 | UOK03-07-IJ Tulsa | Access (23933676) Private IP - PIP (23933675) | 23933676 23933675 | 5 MBPS (23933675) |  | 157555044 (Access) 157555046 (Private IP (PIP)) | E3034419/ADD (23933676) C0114900/ADD (23933675) | 2R/KFFN/002293/LVLC (2393367622640101) | 5845066 | 5000 | PVC ID : 5845066 VPN Name : UnitedHealthGroup Router Name : IDCXE03 VRF Name : V560358-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64994 PE IP Address : 68.136.220.137 CE Address : 68.136.220.138 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (23933676) | 1000Base-SX (850nm, Multi Mode Fiber) (23933676) | Ethernet | LEVEL 3 (2393367622640101) | 03/24/2017 (2393367622640101) | 05/26/2017 (2393367622640101) | 05/24/2017 (2393367622640101) | 05/26/2017 (VFORCE) (23933676) | 05/26/2017 (VFORCE) (23933676) | DEMARCDET - Floor 4 telco closet wallmounted ASR port G0/0/0 SMF tagged with CKT ID |  | Tracy Reese 1-918-459-1235 tracy_m_reese@uhc.com | Jason Salaping | jason_salaping@optum.com | 632-462-2446 | 05/26/2017(Access) 05/26/2017(Private IP - PIP) | 07/28/2017 |  | 06/15/2017 (23933676) 06/19/2017 (23933675) | 06/15/2017 | 05/26/2017 |  |  | N (23933676) N (23933675) | U0101953 | Jeopardy Notification 2 (03/19/2017) | Order Request 193830771 | NSPE0010983820
Completed | UHG El Paso T1 PIP | 4050 RIO BRAVO ST STE 103 EL PASO, TX 79902-1036 US | 3 MBPS (23951592) | 03/30/2017: 3/30 Order completed; cust notified | 193831322 | UHG El Paso T1 PIP | Private IP - PIP (23951591) Access (23951592) | 23951591 23951592 | 3 MBPS (23951591) |  | 157555054 (Private IP (PIP)) 157555051 (Access) | C1050858/ADD (23951591) N1035484/ADD (23951592) N1035483/ADD (23951592) | 30/HCGS/630895//SW (2395159215430301) | 5845322 | 1700 | PVC ID : 5845322 VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64722 PE IP Address : 152.192.130.177 CE Address : 152.192.130.178 QoS - Egress Profile: R12 |  | DS1 (23951592) | TDM | ATT (2395159215430301) | 03/16/2017 (2395159215430301) | 03/28/2017 (2395159215430301) | 03/28/2017 (2395159215430301) |  |  | DEMARCADDR - 4050 RIO BRAVO ST EL PASO TX DEMARCDET - 1ST FLR MAIN TELCO RM BACKBOAR D CABINET- 4, SLOT-2 |  | Jean Negrete 1-915-585-4673 jnegrete@uhc.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 03/29/2017(Private IP - PIP) 03/29/2017(Access) |  |  | 04/04/2017 (23951591) 03/31/2017 (23951592) | 04/06/2017 | 03/29/2017 |  |  | N (23951591) N (23951592) | U0101953 | Jeopardy Notification 2 (03/07/2017) | Order Request 193830771 | NSPE0010983820
Completed | TN040-07-IJ Knoxville | 2035 LAKESIDE CENTRE WAY KNOXVILLE, TN 37922-6593 US | 50 MBPS (23933670) | 06/29/2017: 06/28 Successfully activated | 193831312 | TN040-07-IJ Knoxville | Private IP - PIP (23933669) Access (23933670) | 23933669 23933670 | 20 MBPS (23933669) |  | 157561941 (Private IP (PIP)) 157561939 (Access) | C4006513/ADD (23933669) E4018122/ADD (23933670) | T2/KRGN/821847//SC (2393367022641601) | 5845063 | 7000 | PVC ID : 5845063 VPN Name : UnitedHealthGroup Router Name : NSVL3E03 VRF Name : V414602-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65234 PE IP Address : 152.177.65.177 CE Address : 152.177.65.178 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23933670) | 1000Base-SX (850nm, Multi Mode Fiber) (23933670) | Ethernet | ATT (2393367022641601) | 02/15/2017 (2393367022641601) | 03/08/2017 (2393367022641601) | 03/22/2017 (2393367022641601) | 03/23/2017 (VFORCE) (23933670) | 03/23/2017 (VFORCE) (23933670) | DEMARCADDR - 2035 LAKESIDE CENTRE WAY KNOXVILLE TN DEMARCDET - 2ND FLOOR MAIN TELCO ROOMUNIT 1 TAGGED BOTH ID'S |  | Jennifer Shell 1-865-293-0412 jennifer_m_shell@uhc.com | Seenivasan B | seenivasan.b@optum.com | 91-804-670-4287 | 03/23/2017(Private IP - PIP) 03/23/2017(Access) | 06/28/2017 |  | 03/17/2017 (23933669) 03/15/2017 (23933670) | 03/28/2017 | 03/23/2017 |  |  | N (23933669) N (23933670) | U0101953 | Jeopardy Notification 2 (02/28/2017) | Order Request 193830771 | NSPE0010983820
Completed | UHG | 4051 OGLETOWN RD NEWARK, DE 19713-3101 US | 100 MBPS (24004212) | 06/07/2017: 06/06 "Circuit turn up has been completed today without an issue." as per customer joseph_sanorjo@optum.com | 193831336 | UHG | Private IP - PIP (24004211) Access (24004212) | 24004211 24004212 | 50 MBPS (24004211) |  | 157617873 (Private IP (PIP)) 157617871 (Access) | C1051044/ADD (24004211) E4018258/ADD (24004212) | 11.KFGS.300852..DS (2400421274246201) | 5846580 | 4000 | PVC ID : 5846580 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65094 PE IP Address : 152.187.175.221 CE Address : 152.187.175.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24004212) | 1000Base-SX (850nm, Multi Mode Fiber) (24004212) | Ethernet | VERIZON (2400421274246201) | 02/21/2017 (2400421274246201) | 03/10/2017 (2400421274246201) | 03/02/2017 (2400421274246201) |  |  | DEMARCADDR - 4051 OGLETOWN RD, NEWARK, DE DEMARCDET - DEMARC: 1ST FLR TELCO REMARC ROOM, EXT ON 200FT FIBER TO SUITE 200 MDF ROOM 211 SERVER ROOM, RACK MN |  | Marcia Patten 1-302-781-6775 marcia_patten@uhc.com | Joseph Mark Sanorjo | joseph_sanorjo@optum.com | 632-790-6484 | 03/02/2017(Private IP - PIP) 03/02/2017(Access) | 06/06/2017 |  | 03/21/2017 (24004211) 03/17/2017 (24004212) | 03/20/2017 | 03/02/2017 |  |  | N (24004211) N (24004212) | U0101953 |  | Order Request 193830771 | NSPE0010983820
Completed | NJ013-05-IJ Hamilton NJ | 1 QUAKERBRIDGE PLZ HAMILTON, NJ 08619-1248 US | 10 MBPS (24000421) | 05/23/2017: 05/22 Successfully activated | 193831311 | NJ013-05-IJ Hamilton, NJ | Private IP - PIP (24000420) Access (24000421) | 24000420 24000421 | 5 MBPS (24000420) |  | 157626544 (Private IP (PIP)) 157626502 (Access) | C0115053/ADD (24000420) E3034559/ADD (24000421) | .KFGS.308543..NJ (2400042111255101) | 5846386 | 1500 | PVC ID : 5846386 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65240 PE IP Address : 152.162.83.125 CE Address : 152.162.83.126 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24000421) | 1000Base-SX (850nm, Multi Mode Fiber) (24000421) | Ethernet | VERIZON (2400042111255101) | 02/21/2017 (2400042111255101) | 03/10/2017 (2400042111255101) | 03/07/2017 (2400042111255101) |  |  | DEMARCADDR - 1 QUAKERBRIDGE PLZ, HMLTN TWP, NJ DEMARCDET - GROUND FLR PHONE ROOM RACK MOUNTED NID, TAGGED |  | JEFF JOHNSON 1-609-528-9932 jeff.a.johnson@optum.com | Jason Salaping | jason_salaping@optum.com | 632-462-2446 | 03/07/2017(Private IP - PIP) 03/07/2017(Access) | 05/22/2017 |  | 03/21/2017 (24000420) 03/17/2017 (24000421) | 03/17/2017 | 03/07/2017 |  |  | N (24000420) N (24000421) | U0101953 |  | Order Request 193830771 | NSPE0010983820
Completed | FL148-02-IJ Jacksonville FL | 9655 FLORIDA MINING BLVD W STE 411 JACKSONVILLE, FL 32257-2041 US | 50 MBPS | 02/23/2017: 02/23 Background: Change Order; upgrade port to 20M and gold CAR to 2000k on circuit C5001554; BNE & GLP Status: Hotcut scheduled 02/24/2017 11PM CST Next action: tech to deploy changes Who owns the next action: BNE&GLP Ticket: NA | 193837329 | FL148-02-IJ Jacksonville FL | Private IP - PIP (23988904) Access WAN Analysis Reporting (23988906) | 23988904 23988906 | 20 MBPS (23988904) |  | 121417127 (Private IP (PIP)) 121417125 121417128 (WAN Analysis Reporting) | C4004380/NONE (23988904) |  | 5758342 | 2000 | PVC ID : 5758342 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64613 PE IP Address : 152.181.236.17 CE Address : 152.181.236.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Michael Bowen 1-904-652-1990 mbowen@ambienthealth.com | PRADEEP YADAV | pradeep_yadav@optum.com | 1-981-005-9326 | 02/24/2017(Private IP | 02/23/2017 |  | 03/01/2017 (23988904) | 03/01/2017 03/01/2017 (13558189.1) | 02/24/2017 |  | Activated/Installed | N (23988904) N N (23988906) | U0101953 |  | NSPE0010987736 - Order Request 193835965 | NSPE0010987736
Completed | PA062-05-IJ Horsham PA | 680 BLAIR MILL RD HORSHAM, PA 19044-2223 US | 200 MBPS | 02/27/2017: 02/24 Upgrade complete. | 193837388 | PA062-05-IJ Horsham PA | Access Private IP - PIP (23989623) | 23989623 | 150 MBPS (23989623) |  | 88611449 88611451 (Private IP (PIP)) | C5001554/NONE (23989623) |  | 5695288 | 110000 | PVC ID : 5695288 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65203 PE IP Address : 199.220.102.17 CE Address : 199.220.102.18 QoS - Egress Profile: R1 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Harry Miller 1-215-902-8251 harry_s_miller@uhc.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 02/27/2017(Private IP | 02/24/2017 |  | 02/17/2017 (23989623) | 02/28/2017 | 02/27/2017 |  |  | N N (23989623) | U0101953 |  | NSPE0010987765 - Order Request # 193836010 | NSPE0010987765
Completed | AZ047-02-IJ Tucson | 1669 W INA RD TUCSON, AZ 85704-1982 US | 10 MBPS (24008587) | 07/18/2017: 07/18 Activation scheduled 07/21/2017 11PM CST | 193848413 | AZ047-02-IJ Tucson | Private IP - PIP (24008586) Access (24008587) | 24008586 24008587 | 10 MBPS (24008586) |  | 158157817 (Private IP (PIP)) 158157815 (Access) | C0115172/ADD (24008586) E3034643/ADD (24008587) | 56/KGFN/112955/TWCS (2400858721224201) | 5846794 | 7000 | PVC ID : 5846794 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64525 PE IP Address : 65.250.18.201 CE Address : 65.250.18.202 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (24008587) | 1000Base-SX (850nm, Multi Mode Fiber) (24008587) | Ethernet | LEVEL 3 (2400858721224201) | 02/23/2017 (2400858721224201) | 05/24/2017 (2400858721224201) | 05/24/2017 (2400858721224201) | 05/31/2017 (VFORCE) (24008587) | 05/31/2017 (VFORCE) (24008587) | DEMARCDET - 1st Floor Telco Room, wallmount ZG001 Gi 0/0/1 SMF LC, tagged with ID. |  | Angel Gillett 1-520-795-6183 angel.gillett@optum.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 | 05/31/2017(Private IP - PIP) 05/31/2017(Access) | 07/21/2017 |  | 06/05/2017 (24008586) 06/01/2017 (24008587) | 04/03/2017 | 05/31/2017 |  |  | N (24008586) N (24008587) | U0101953 |  | Order Request 193846391 - TWT | NSPE0010994927
Completed | AZ045-02-IJ Tucson | 1460 W VALENCIA RD TUCSON, AZ 85746-6001 US | 10 MBPS (24008427) | 07/28/2017: 07/25 Successfully activated | 193848414 | AZ045-02-IJ Tucson, | Access (24008427) Private IP - PIP (24008426) | 24008427 24008426 | 10 MBPS (24008426) |  | 158157968 (Access) 158157970 (Private IP (PIP)) | E3034639/ADD (24008427) C0115168/ADD (24008426) | 1C/KFFN/002553/LVLC (2400842721224001) | 5846787 | 1500 | PVC ID : 5846787 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64522 PE IP Address : 152.192.129.89 CE Address : 152.192.129.90 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (24008427) | 1000Base-SX (850nm, Multi Mode Fiber) (24008427) | Ethernet | LEVEL 3 (2400842721224001) | 02/22/2017 (2400842721224001) | 05/18/2017 (2400842721224001) | 05/17/2017 (2400842721224001) | 05/19/2017 (VFORCE) (24008427) | 05/19/2017 (VFORCE) (24008427) | DEMARCDET - 1st floor main(east) telco room wall mt 3600 port g0/9 SMF tagged w/CID |  | Anisa Lopez 1-520-573-0966 anisa.lopez@optum.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 | 05/19/2017(Access) 05/19/2017(Private IP - PIP) | 07/25/2017 |  | 05/25/2017 (24008427) 05/30/2017 (24008426) | 04/03/2017 | 05/20/2017 |  |  | N (24008427) N (24008426) | U0101953 |  | Order Request 193846391 - TWT | NSPE0010994927
Completed | UCO14 | 6455 S YOSEMITE ST GREENWOOD VILLAGE, CO 80111-5139 US | 50 MBPS (24014628) | 06/22/2017: 06/21 Successfully activated | 193852358 | UCO14 | Access (24014628) Private IP - PIP (24014627) WAN Analysis Reporting (24014629) | 24014628 24014627 24014629 | 20 MBPS (24014627) |  | 158368357 (Access) 158368359 (Private IP (PIP)) 158368360 (WAN Analysis Reporting) | E4018302/ADD (24014628) C4006574/ADD (24014627) | 29.KXGS.222846..MS (2401462874246002) | 5847257 | 4000 | PVC ID : 5847257 VPN Name : UnitedHealthGroup Router Name : DNJXE01 VRF Name : V469377-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64624 PE IP Address : 199.220.230.41 CE Address : 199.220.230.42 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24014628) | 1000Base-SX (850nm, Multi Mode Fiber) (24014628) | Ethernet | CENTURYLINK (2401462874246002) | 03/23/2017 (2401462874246002) | 05/17/2017 (2401462874246002) | 05/02/2017 (2401462874246002) | 05/19/2017 (VFORCE) (24014628) | 05/19/2017 (VFORCE) (24014628) | DEMARCADDR - X DEMARCDET - 8TH FL ELECTRICAL/PHONE RM. AS PER WORD DOC, WALL MOUNTED CIENA MINI. CUSTOMER HANDOFF PORT#3 MULTIMODE OPTICAL SFP. AS PER NCI CODE. TYPE: OPTICAL |  | Rocky Gahring 1-303-714-2052 rodney_gahring@optum.com | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 05/19/2017(Access) 05/19/2017(Private IP - PIP) 05/19/2017(WAN Analysis Reporting) | 06/21/2017 |  | 05/25/2017 (24014628) 05/30/2017 (24014627) | 05/25/2017 06/01/2017 | 05/19/2017 |  | Activated/Installed | N (24014628) N (24014627) N (24014629) | U0101953 | Jeopardy Notification 2 (05/09/2017) | NSPE0010998316 Order Request # 193850428 | NSPE0010998316
Completed | MI028-07-IJ | 950 TRADE CENTRE WAY STE 320 PORTAGE, MI 49002-0493 US | 50 MBPS (24020208) | 06/16/2017: 06/15 Successfully activated | 193854425 | MI028-07-IJ | WAN Analysis Reporting (24020209) Access (24020208) Private IP - PIP (24020207) | 24020209 24020208 24020207 | 50 MBPS (24020207) |  | 158830965 (WAN Analysis Reporting) 158830782 (Access) 158830964 (Private IP (PIP)) | C4006581/ADD (24020207) E4018324/ADD (24020208) | /KRGN/210475//MB (2402020822854601) | 5847634 | 4000 | PVC ID : 5847634 VPN Name : UnitedHealthGroup Router Name : DTRT9E01 VRF Name : V922267:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64515 PE IP Address : 68.138.114.245 CE Address : 68.138.114.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24020208) | 1000Base-SX (850nm, Multi Mode Fiber) (24020208) | Ethernet | ATT (2402020822854601) | 02/23/2017 (2402020822854601) | 03/10/2017 (2402020822854601) | 03/10/2017 (2402020822854601) | 03/14/2017 (VFORCE) (24020208) | 03/14/2017 (VFORCE) (24020208) | DEMARCADDR - 950 TRADE CENTRE WAY PORTAGE MI DEMARCDET - 1ST FLOOT NET WORK ROOM PANEL 1 11 AND 12 |  | Liza Amos 1-269-459-3954 liza_a_amos@uhc.com | RAUL BARLOSO | raul_barloso@optum.com | 632-790-6271 | 03/14/2017(WAN Analysis Reporting) 03/14/2017(Access) 03/14/2017(Private IP - PIP) | 06/15/2017 |  | 03/23/2017 (24020207) 03/21/2017 (24020208) | 04/28/2017 04/24/2017 | 03/14/2017 |  | Activated/Installed | N (24020209) N (24020208) N (24020207) | U0101953 | Jeopardy Notification 3 (03/11/2017) | NSPE0011000293 Order Request # 193853444 | NSPE0011000293
Completed | UNITED HEALTHCARE | 2 GATEWAY CTR NEWARK, NJ 07102-5005 US | 50 MBPS (24147537) | 04/19/2017: 4/18 Ready to activate cust notified | 193861751 | UNITED HEALTHCARE | Access (24147537) WAN Analysis Reporting (24147538) Private IP - PIP (24147536) | 24147537 24147538 24147536 | 20 MBPS (24147536) |  | 158671040 (Access) 158671143 (WAN Analysis Reporting) 158671042 (Private IP (PIP)) | E4018772/ADD (24147537) C4006791/ADD (24147536) | .KFGS.308633..NJ (2414753774246001) | 5853792 | 4000 | PVC ID : 5853792 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64516 PE IP Address : 68.139.43.53 CE Address : 68.139.43.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24147537) | 1000Base-SX (850nm, Multi Mode Fiber) (24147537) | Ethernet | VERIZON (2414753774246001) | 03/15/2017 (2414753774246001) | 04/19/2017 (2414753774246001) | 04/18/2017 (2414753774246001) |  |  | DEMARCADDR - 2 GATEWAY PLZ, NWK, NJ DEMARCDET - BASEMENT MDF RR# 1, POS# 4, RACK MOUNTED NID. |  | YAHAIRA VENTRE 1-973-849-1583 yahaira_hernandez@uhc.com | RAUL BARLOSO | raul_barloso@optum.com | 632-790-6271 | 04/18/2017(Access) 04/18/2017(WAN Analysis Reporting) 04/18/2017(Private IP - PIP) |  |  | 04/26/2017 (24147537) 04/28/2017 (24147536) | 04/27/2017 05/03/2017 | 04/18/2017 |  | Activated/Installed | N (24147537) N (24147538) N (24147536) | U0101953 | Jeopardy Notification 2 (04/09/2017) | NSPE0011004005 Order Request # 193857340 | NSPE0011004005
Completed | WA004-05-IJ Seattle WA 2xT1 | 1633 WESTLAKE AVE N SEATTLE, WA 98109-6227 US | 10 MBPS (24035145) | 07/21/2017: 07/21 Successfully activated | 193861777 | WA004-05-IJ Seattle WA 2xT1 | WAN Analysis Reporting (24035146) Access (24035145) Private IP - PIP (24035144) | 24035146 24035145 24035144 | 5 MBPS (24035144) |  | 158671147 (WAN Analysis Reporting) 158671144 (Access) 158671146 (Private IP (PIP)) | C0115354/ADD (24035144) E3035118/ADD (24035145) | 04.KXGS.216846..PN (2403514568736101) | 5848429 | 2000 | PVC ID : 5848429 VPN Name : UnitedHealthGroup Router Name : K1B3E02 VRF Name : V461088-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65046 PE IP Address : 68.139.255.129 CE Address : 68.139.255.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24035145) | 1000Base-SX (850nm, Multi Mode Fiber) (24035145) | Ethernet | CENTURYLINK (2403514568736101) | 02/27/2017 (2403514568736101) | 05/08/2017 (2403514568736101) | 04/17/2017 (2403514568736101) | 04/28/2017 (VFORCE) (24035145) | 04/28/2017 (VFORCE) (24035145) | DEMARCDET - PARKING LEVEL P3 IN TELCO ROOM RACK MT TAGGED OPTICAL PORT 4 |  | Chad Foster 1-206-786-0678 chad.foster@unionbay.com | RAUL BARLOSO | raul_barloso@optum.com | 632-790-6271 | 04/28/2017(WAN Analysis Reporting) 04/28/2017(Access) 04/28/2017(Private IP - PIP) | 07/20/2017 |  | 05/17/2017 (24035144) 05/15/2017 (24035145) | 05/11/2017 05/05/2017 | 04/28/2017 |  | Activated/Installed | N (24035146) N (24035145) N (24035144) | U0101953 | Jeopardy Notification 2 (04/25/2017) | NSPE0011004005 Order Request # 193857340 | NSPE0011004005
Completed | UNITED HEALTH CARE | 8880 CAL CENTER DR SACRAMENTO, CA 95826-3222 US | 50 MBPS (24061476) | 10/06/2017: 10/05 Successfully activated. Pending acceptance from customer. | 193873310 | UNITED HEALTH CARE | Private IP - PIP (24061474) WAN Analysis Reporting (24061478) Access (24061476) | 24061474 24061478 24061476 | 50 MBPS (24061474) |  | 159353705 (Private IP (PIP)) 159353706 (WAN Analysis Reporting) 159353703 (Access) | C4006635/ADD (24061474) E4018443/ADD (24061476) | 18/KRGN/518806//PT (2406147674246201) | 5849979 | 7000 | PVC ID : 5849979 VPN Name : UnitedHealthGroup Router Name : SCM3E03 VRF Name : V447827-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65185 PE IP Address : 147.225.43.221 CE Address : 147.225.43.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24061476) | 1000Base-SX (850nm, Multi Mode Fiber) (24061476) | Ethernet | ATT (2406147674246201) | 03/01/2017 (2406147674246201) | 03/16/2017 (2406147674246201) | 03/16/2017 (2406147674246201) | 03/17/2017 (VFORCE) (24061476) | 03/17/2017 (VFORCE) (24061476) | DEMARCADDR - 8880 CAL CENTER DR SAC DEMARCDET - PORT 5 TO ENGINUITY PANEL, PORT 5 OF BELOW SWITCH 0BW. FLOOR 2 |  | Emily Livaich 1-916-403-0677 Emily.Livaich@uhc.com | HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 | 03/17/2017(Private IP - PIP) 03/17/2017(WAN Analysis Reporting) 03/17/2017(Access) |  |  | 03/27/2017 (24061474) 03/23/2017 (24061476) | 04/10/2017 04/14/2017 | 03/18/2017 |  | Activated/Installed | N (24061474) N (24061478) N (24061476) | U0101953 |  | NSPE0011015417 Order Request # 193872041 | NSPE0011015417
Completed | UWI30 | 10701 W RESEARCH DR WAUWATOSA, WI 53226-3452 US | 150 MBPS (24061466) | 05/22/2017: 05/22 Successfully activated circuit. | 193873309 | UWI30 | WAN Analysis Reporting (24061467) Access (24061466) Private IP - PIP (24061465) | 24061467 24061466 24061465 | 150 MBPS (24061465) |  | 159353714 (WAN Analysis Reporting) 159353711 (Access) 159353713 (Private IP (PIP)) | C4006634/ADD (24061465) E4018442/ADD (24061466) | 44/KRGN/101542//WT (2406146622908901) | 5849977 | 30000 | PVC ID : 5849977 VPN Name : UnitedHealthGroup Router Name : MWAGE04 VRF Name : V415040:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64567 PE IP Address : 152.192.152.193 CE Address : 152.192.152.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24061466) | 1000Base-SX (850nm, Multi Mode Fiber) (24061466) | Ethernet | ATT (2406146622908901) | 03/01/2017 (2406146622908901) | 04/04/2017 (2406146622908901) | 04/07/2017 (2406146622908901) | 04/11/2017 (VFORCE) (24061466) | 04/11/2017 (VFORCE) (24061466) | DEMARCADDR - 10701 W RESEARCH DR WAUWATOSA WI DEMARCDET - LOWER LEVEL, DATA ROOM, RR 00000.02, HANDOFF PANEL #2, PORT #2 |  | William Nichols 1-414-443-4464 bnichols@uhg.com | HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 | 04/11/2017(WAN Analysis Reporting) 04/11/2017(Access) 04/11/2017(Private IP - PIP) | 05/18/2017 |  | 04/20/2017 (24061465) 04/18/2017 (24061466) | 04/24/2017 04/18/2017 | 04/11/2017 |  | Activated/Installed | N (24061467) N (24061466) N (24061465) | U0101953 | Jeopardy Notification 2 (03/08/2017) | NSPE0011015417 Order Request # 193872041 | NSPE0011015417
Completed | NY025-02-IJ Brooklyn NY | 30 FLATBUSH AVE BROOKLYN, NY 11217-1121 US | 3 MBPS (24067147) | 04/11/2017: 4/11 Ready for plug and Play/ Cust notified | 193874836 | NY025-02-IJ Brooklyn NY | Access (24067147) Private IP - PIP (24067146) WAN Analysis Reporting (24067148) | 24067147 24067146 24067148 | 3 MBPS (24067146) |  | 159481408 (Access) 159481410 (Private IP (PIP)) 159481411 (WAN Analysis Reporting) | N1035633/ADD (24067147) N1035632/ADD (24067147) C1051293/ADD (24067146) | 32.HCGS.884415..NY (2406714720617601) | 5850200 | 1500 | PVC ID : 5850200 VPN Name : UnitedHealthGroup Router Name : HLB9E02 VRF Name : V932063:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65268 PE IP Address : 206.115.9.137 CE Address : 206.115.9.138 QoS - Egress Profile: R12 |  | DS1 (24067147) | TDM | VERIZON (2406714720617601) | 03/09/2017 (2406714720617601) | 03/31/2017 (2406714720617601) | 04/05/2017 (2406714720617601) |  |  | Verizon order: Access: 24067147 Port: 24067146 Tcoms: NYCI0339847 Verizon circuit ID Access: Port: C1051293 Tcoms: 13xwu tl2 0091 / 13xwu tl2 0092 LEC circuit ID: 32.HCGS.884412..NY / 32.HCGS.884415..NY DMARC Location: N1035632 /32.HCGS.884412..NY- RJ48c basement sub telco room slot 1 of 2 N1035633 / 32.HCGS.884415..NY- RJ48c basement sub telco room slot 2 of 2 |  | Wali Omarkheil 1-516-306-5957 wali_u_omarkheil@uhc.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 04/05/2017(Access) 04/05/2017(Private IP - PIP) 04/05/2017(WAN Analysis Reporting) |  |  | 04/05/2017 (24067147) 04/07/2017 (24067146) | 04/10/2017 04/14/2017 | 04/05/2017 |  | Activated/Installed | N (24067147) N (24067146) N (24067148) | U0101953 |  | NSPE0011015566 Order Request # 193872291 | NSPE0011015566
Completed | MN051-07-IJ Eden Prairie MN | 13625 TECHNOLOGY DR EDEN PRAIRIE, MN 55344-2252 US | 10 MBPS (24069350) | 06/02/2017: 06/02 Successfully activated | 193876223 | MN051-07-IJ Eden Prairie, MN | Internet Dedicated Services (24069349) Access (24069350) | 24069349 24069350 | 10 MBPS (24069349) |  | 159488253 (Internet Dedicated Services) 159488251 (Access) | C0115549/ADD (24069349) E3036208/ADD (24069350) | 03.KXGS.217266..NW (2406935023837901) | 5850307 | 0 | PVC ID : 5850307 VPN Name : Internet Router Name : GW7CHI2 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : v4-152.179.169.105,v6-2600:805:13F::4D CE Address : v4-152.179.169.106,v6-2600:805:13F::4E | 100Base-TX (24069350) | 100Base-TX (24069350) | Ethernet | CENTURYLINK (2406935023837901) | 03/10/2017 (2406935023837901) | 03/24/2017 (2406935023837901) | 03/15/2017 (2406935023837901) | 03/24/2017 (VFORCE) (24069350) | 03/24/2017 (VFORCE) (24069350) | DEMARCADDR - X DEMARCDET - SEE CUSTOMER FOR ACCESS AND ESCORT TYPE: OPTICAL |  | Derek Dukhorn 1-952-917-8067 derek_dukhorn@optum.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 03/24/2017(Internet Dedicated Services) 03/24/2017(Access) | 06/02/2017 |  | 04/04/2017 (24069349) 03/31/2017 (24069350) | 04/20/2017 | 03/24/2017 |  |  | N (24069349) N (24069350) | U0101953 |  | NSPE0011018531 Order Request # 193876026 | NSPE0011018531
Completed | UNITED HEALTH GROUP | 979 DEL MAR DR THE VILLAGES, FL 32159-7734 US | 10 MBPS (24072065) | 08/07/2017: 08/03 Successfully activated | 193877640 | UNITED HEALTH GROUP | Private IP - PIP (24072064) WAN Analysis Reporting (24072066) Access (24072065) | 24072064 24072066 24072065 | 10 MBPS (24072064) |  | 159298579 (Private IP (PIP)) 159298580 (WAN Analysis Reporting) 159298577 (Access) | C0115585/ADD (24072064) E3036224/ADD (24072065) | 25.KXGS.217728..UFLG (2407206574246001) | 5850401 | 4000 | PVC ID : 5850401 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65273 PE IP Address : 152.192.154.201 CE Address : 152.192.154.202 QoS - Egress Profile: R12 | 100Base-TX (24072065) | 100Base-TX (24072065) | Ethernet | CENTURYLINK (2407206574246001) | 06/02/2017 (2407206574246001) | 06/09/2017 (2407206574246001) | 06/08/2017 (2407206574246001) | 06/12/2017 (VFORCE) (24072065) | 06/12/2017 (VFORCE) (24072065) | Serial Number Format(AP): 25/KXGS/217728 /UFLG DEMARC LOC: 1st floor, telco room, mounted on the wall, RAD204, port 3, T/L with circuit ID Jack Type: 100Base-TX Loop Location: DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes |  | Dennis Prindle 1-352-674-7160 dennis_prindle@uhc.com | RAUL BARLOSO | raul_barloso@optum.com | 632-790-6271 | 06/12/2017(Private IP - PIP) 06/12/2017(WAN Analysis Reporting) 06/12/2017(Access) | 08/03/2017 |  | 06/20/2017 (24072064) 06/16/2017 (24072065) | 06/14/2017 06/20/2017 | 06/12/2017 |  | Activated/Installed | N (24072064) N (24072066) N (24072065) | U0101953 | Jeopardy Notification 1 (05/11/2017) | NSPE0011018911 Order Request # 193876441 | NSPE0011018911
Completed | Southfield MI | 26957 NORTHWESTERN HWY STE 400480 SOUTHFIELD, MI 48033-4700 US | 200 MBPS (24077003) | 06/01/2017: 05/31 Successfully activated. | 193879062 | Southfield, MI | Private IP - PIP (24077002) WAN Analysis Reporting (24077004) Access (24077003) | 24077002 24077004 24077003 | 100 MBPS (24077002) |  | 159646256 (Private IP (PIP)) 159646257 (WAN Analysis Reporting) 159646254 (Access) | C5002950/ADD (24077002) E5006103/ADD (24077003) |  | 5850630 | 25000 | PVC ID : 5850630 VPN Name : UnitedHealthGroup Router Name : DTRT9E01 VRF Name : V922267:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65175 PE IP Address : 152.183.186.149 CE Address : 152.183.186.150 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (24077003) | Ethernet |  |  |  |  | 03/15/2017 (CCP) (24077002) 03/15/2017 (CCP) (24077003) | 03/17/2017 (CCP) (24077002) 03/17/2017 (CCP) (24077003) | 4th FL MDF |  | Bill Stranahan 1-248-331-4415 bstranahan@optum.com | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 03/29/2017(Private IP - PIP) 03/29/2017(WAN Analysis Reporting) 03/29/2017(Access) | 05/31/2017 |  | 04/11/2017 (24077002) 04/07/2017 (24077003) | 03/29/2017 04/04/2017 | 03/29/2017 |  | Activated/Installed | N (24077002) N (24077004) N (24077003) | U0101953 |  | NSPE0011019982 Order Request # 193878038 | NSPE0011019982
Completed |  | 1902 VALLEY PINE CIR INTERNATIONAL FALLS, MN 56649 USA | 1.536 MBPS (IQBLGMVZ) | 09/13/2017: 09/12 Successfully activated | 9082798 |  | Private IP (IQBLGMVZ) EVC/PVC Service (N.11340178.5852084) | IQBLGMVZ N.11340178.5852084 | 10.752 MBPS | P2162248 |  | BCBLBN8S0001 (IQBLGMVZ) BCBLBN8S0002 (IQBLGMVZ) BCBLBN8S0003 (IQBLGMVZ) BCBLBN8S0004 (IQBLGMVZ) BCBLBN8S0005 (IQBLGMVZ) BCBLBN8S0006 (IQBLGMVZ) BCBLBN8S0007 (IQBLGMVZ) | 23/HCGS/642478//CZUC/ (IQBLGMVZPJBWMB01) | 5852084 | 9008 | VPN Name : UnitedHealthGroup Router Name : MZZ9E01 VRF Name : V600583:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64596 PE IP Address : 152.161.72.161 CE Address : 152.161.72.162 QoS - Egress Profile: R12 PVC ID : 5852084 |  |  |  | NORTHLAND TEL CO CENTURYLINK (IQBLGMVZPJBWMB01) | 03/08/2017 (IQBLGMVZPJBWMB01) | 03/23/2017 (IQBLGMVZPJBWMB01) | 03/20/2017 (IQBLGMVZPJBWMB01) |  |  | 1ST FL COM ROOM NORTH wall 23/HCGS/642477//CZUC/ Slot 1 of 4, 4 Mount 23/HCGS/642478//CZUC/ Slot 2 of 4, 4 Mount 23/HCGS/642479//CZUC/ Slot 3 of 4, 4 Mount 23/HCGS/642480//CZUC/ Slot 4 of 4, 4 Mount 23/HCGS/ 642481//CZUC/ Slot 1 of 1, Single Mount 23/HCGS/642482//CZUC/ Slot 1 of 1, Single Mount 23/HCGS/642483//CZUC/ Slot 1 of 1, Single Mount |  | TIMOTHY STENCEL 0012182855912 TIM_STENCEL@UHC.COM |  |  |  | 03/28/2017 (IQBLGMVZ) | 09/12/2017 |  | 03/30/2017 (IQBLGMVZ) | 03/31/2017 (IQBLGMVZ) |  |  |  | N (IQBLGMVZ) N (N.11340178.5852084) | 05650532 P2162248 |  |  | NSPE0011029737
Completed |  | 1902 VALLEY PINE CIR INTERNATIONAL FALLS, MN 56649 USA | 1.536 MBPS (IQBLGMTH) 1.536 MBPS (OQBLGM7H) | 09/13/2017: 09/12 Hotcut complete | 9083396 |  | EVC/PVC Service (C.11341111.1974406) Private IP (OQBLGM7H) Private IP (IQBLGMTH) | C.11341111.1974406 OQBLGM7H IQBLGMTH | 10.752 MBPS 1.536 MBPS (OQBLGM7H) | P2162236 P1913413 |  | BCBLBN8C0001 (IQBLGMTH) BCBLBN8C0002 (IQBLGMTH) BCBLBN8C0003 (IQBLGMTH) BCBLBN8C0004 (IQBLGMTH) BCBLBN8C0005 (IQBLGMTH) BCBLBN8C0006 (IQBLGMTH) BCBLBN8C0007 (IQBLGMTH) BCBKR0ST0001 (OQBLGM7H) BCBKR0ST0002 (OQBLGM7H) BCBKR0ST0003 (OQBLGM7H) BCBKR0ST0004 (OQBLGM7H) BCBKR0ST0005 (OQBLGM7H) BCBKR0ST0006 (OQBLGM7H) | 23/HCGS/642833//CZUC (IQBLGMTHDLBWMB03) 23.HCGS.070150..CZUC (IQBLGMTHDLBWMB02) 23.HCGS.483990..CZUC (IQBLGMTHDLBWMB01) | 1974406 | 9008 | PVC ID : 1974406 VPN Name : UnitedHealthGroup Router Name : MZZ3E01 VRF Name : V338870-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64596 PE IP Address : 147.225.237.237 CE Address : 147.225.237.238 QoS - Egress Profile: R12 |  |  |  | CENTURYLINK (IQBLGMTHDLBWMB03) CENTURYLINK (IQBLGMTHDLBWMB02) CENTURYLINK (IQBLGMTHDLBWMB01) CITIZENS TELECOM | 03/13/2017 (IQBLGMTHDLBWMB03) 03/13/2017 (IQBLGMTHDLBWMB02) 03/13/2017 (IQBLGMTHDLBWMB01) | 03/27/2017 (IQBLGMTHDLBWMB03) 03/27/2017 (IQBLGMTHDLBWMB02) 03/27/2017 (IQBLGMTHDLBWMB01) | 03/24/2017 (IQBLGMTHDLBWMB03) 03/24/2017 (IQBLGMTHDLBWMB02) 03/24/2017 (IQBLGMTHDLBWMB01) |  |  |  |  | TIMOTHY STENCEL 2182855912 0012182855912 TIM_STENCEL@UHC.COM |  |  |  | 09/19/2017 (IQBLGMTH) 09/19/2017 (OQBLGM7H) | 09/12/2017 |  | 09/19/2017 (IQBLGMTH) 09/26/2017 (OQBLGM7H) | 09/26/2017 (IQBLGMTH) 09/26/2017 (OQBLGM7H) |  |  |  | N (C.11341111.1974406) N (OQBLGM7H) N (IQBLGMTH) | P2162236 05017789 05650532 |  |  | NSPE0011029795
Completed | Dublin OH | 5900 PARKWOOD PL DUBLIN, OH 43016-1216 US | 200 MBPS (24108794) | 08/14/2017: 08/14 Customer confirmed circuit already up. | 193894703 | Dublin, OH | Private IP - PIP (24108793) WAN Analysis Reporting (24108795) Access (24108794) | 24108793 24108795 24108794 | 100 MBPS (24108793) |  | 160189250 (Private IP (PIP)) 160189251 (WAN Analysis Reporting) 160189248 (Access) | C5002985/ADD (24108793) E5006175/ADD (24108794) | 5B/KFFN/003599/LVLC (2410879423100501) | 5852270 | 45000 | PVC ID : 5852270 VPN Name : UnitedHealthGroup Router Name : CMK3E01 VRF Name : V449952-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64932 PE IP Address : 152.164.163.241 CE Address : 152.164.163.242 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (24108794) | 1000Base-SX (850nm, Multi Mode Fiber) (24108794) | Ethernet | LEVEL 3 (2410879423100501) | 07/18/2017 (2410879423100501) | 08/10/2017 (2410879423100501) | 08/08/2017 (2410879423100501) | 08/09/2017 (VFORCE) (24108794) | 08/09/2017 (VFORCE) (24108794) | DEMARCDET - 2nd floor MDF room wall mounted cisco asr920 circuit |  | Danielle Maiorana 1-952-202-0064 Danielle.Maiorana@am.jll.com | AL THORESON | al_thoreson@optum.com | 1-763-553-4196 | 08/09/2017(Private IP - PIP) 08/09/2017(WAN Analysis Reporting) 08/09/2017(Access) | 08/14/2017 |  | 10/31/2017 (24108793) 10/27/2017 (24108794) | 08/28/2017 09/01/2017 | 08/09/2017 |  | Activated/Installed | N (24108793) N (24108795) N (24108794) | U0101953 | Jeopardy Notification 2 (07/15/2017) | NSPE0011034281 OR 193893890 | NSPE0011034281
Completed | UNITED HEALTHCARE | 250 FULTON AVE HEMPSTEAD, NY 11550-3917 US | 10 MBPS (24269049) | 10/13/2017: 10/12 Successfully activated | 193911108 | UNITED HEALTHCARE | Private IP - PIP (24269048) WAN Analysis Reporting (24269050) Access (24269049) | 24269048 24269050 24269049 | 5 MBPS (24269048) |  | 161085750 (Private IP (PIP)) 161085753 (WAN Analysis Reporting) 161085748 (Access) | C0119625/ADD (24269048) E3037966/ADD (24269049) | 32.KFGS.213632..NY (2426904974246002) | 5861692 | 1500 | PVC ID : 5861692 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65145 PE IP Address : 152.185.88.149 CE Address : 152.185.88.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24269049) | 1000Base-SX (850nm, Multi Mode Fiber) (24269049) | Ethernet | VERIZON (2426904974246002) | 09/06/2017 (2426904974246002) | 09/22/2017 (2426904974246002) | 09/19/2017 (2426904974246002) |  |  | DEMARCADDR - 250 FULTON AV, HEMPSTEAD, NY DEMARCDET - 1ST FLR MDF ROOM/1ST CANOGA- WLLMTD. |  | Angelo Zuffante 1-516-247-6351 angelo_zuffante@uhc.com | RAUL BARLOSO | raul_barloso@optum.com | 632-790-6271 | 09/19/2017(Private IP - PIP) 09/19/2017(WAN Analysis Reporting) 09/19/2017(Access) | 10/12/2017 |  | 10/03/2017 (24269048) 09/29/2017 (24269049) | 10/03/2017 10/09/2017 | 09/19/2017 |  | Activated/Installed | N (24269048) N (24269050) N (24269049) | U0101953 | Jeopardy Notification 3 (08/22/2017) | Order Request: 193910867 | NSPE0011048821
Completed |  | 1707 W CREEK LN CHASKA, MN 55318 USA | 10G-LANP-10GBSUU (6010924) | 09/21/2017: 09/21 Successfully activated. Confirmed by brandon_little@optum.com / 952-687-3694 | 9092914 |  | US Private Line (6010924) | 6010924 | 10G-LANP-10GBSUU (6010924) |  |  | W1C75278 (6010924) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | CHICAGO DEMARK IS 2.02 SH 6 PORT SET 15 LOOPED AND TAGGED WITH THE CIRCUIT I D JX-511-M6L7-0001 | BRIAN LADD 331 223 7121 | STEVE BROWN 763 694 7333 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 05/12/2017 (6010924) | 09/21/2017 |  | 05/30/2017 (6010924) | 06/23/2017 (6010924) |  |  |  | N (6010924) | 00198894 |  | NSPE0011053934 USPL | NSPE0011053934
Completed | CA768-02-IJ UHG - Monarch | 2301 W 120TH ST HAWTHORNE, CA 90250-3319 US | 1 GBPS (24162565) | 06/26/2017: 06/26 Successfully activated | 193922721 | CA768-02-IJ UHG - Monarch | Private IP - PIP (24162564) WAN Analysis Reporting (24162566) Access (24162565) | 24162564 24162566 24162565 | 1 GBPS (24162564) |  | 161669852 (Private IP (PIP)) 161669853 (WAN Analysis Reporting) 161669850 (Access) | C0118613/ADD (24162564) E5006244/ADD (24162565) | 13/KRGN/590008//PT (2416256581893201) | 5854661 | 700000 | PVC ID : 5854661 VPN Name : UHG-Monarch Router Name : RTO9E01 VRF Name : V961148:UHGMonarch Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65501 PE IP Address : 68.139.16.217 CE Address : 68.139.16.218 QoS - Egress Profile: R1 | 1000Base-SX-850nm (24162565) | 1000Base-SX (850nm, Multi Mode Fiber) (24162565) | Ethernet | ATT (2416256581893201) | 03/20/2017 (2416256581893201) | 04/10/2017 (2416256581893201) | 04/10/2017 (2416256581893201) | 04/27/2017 (VFORCE) (24162565) | 04/27/2017 (VFORCE) (24162565) | DEMARCADDR - 2301 W 120TH HAW DEMARCDET - RACK 4 VIRTUAL EDGE PANEL 8 POSITION 9-10 |  | Pooyan Haghighi 1-510-717-2602 phaghighi@mhealth.com | Santosh Tendolkar | stendolkar@mhealth.com | 1-562-382-7377 | 04/27/2017(Private IP - PIP) 04/27/2017(WAN Analysis Reporting) 04/27/2017(Access) | 06/23/2017 |  | 05/08/2017 (24162564) 05/04/2017 (24162565) | 05/04/2017 05/10/2017 | 04/27/2017 |  | Activated/Installed | N (24162564) N (24162566) N (24162565) | U0101953 | Jeopardy Notification 3 (04/25/2017) | NSPE0011057973 Order Request # 193921334 Please note: New VPN: UHG- Monarch Goldcar: 700mg (600mg not available) | NSPE0011057973
Completed | CA105-05-IM | 2 ADA IRVINE, CA 92618-5323 US | 100 MBPS (24168295) | 06/27/2017: 06/27 Successfully activated | 193924593 | CA105-05-IM | Private IP - PIP (24168294) WAN Analysis Reporting (24168296) Access (24168295) | 24168294 24168296 24168295 | 100 MBPS (24168294) |  | 161754463 (Private IP (PIP)) 161754544 (WAN Analysis Reporting) 161754461 (Access) | C1052216/ADD (24168294) E4018846/ADD (24168295) | 1L/KEFN/003180/LVLC (2416829523351501) | 5854856 | 70000 | PVC ID : 5854856 VPN Name : UHG-Monarch Router Name : LSA29E02 VRF Name : V976456:UHGMonarch Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65503 PE IP Address : 199.220.123.229 CE Address : 199.220.123.230 QoS - Egress Profile: R1 | 100Base-TX (24168295) | 100Base-TX (24168295) | Ethernet | LEVEL 3 (2416829523351501) | 03/20/2017 (2416829523351501) | 04/28/2017 (2416829523351501) | 04/20/2017 (2416829523351501) | 04/24/2017 (VFORCE) (24168295) | 04/24/2017 (VFORCE) (24168295) | DEMARCDET - 1st floor, suite 100, server room 126, rack #4, rmu 39, Adva 4P001, port 3, RJ45 labeled with "port 3 customer access" |  | SANTOSH TENDOLKAR 1-562-382-7377 stendolkar@mhealth.com | POOYAN HAGHIGHI | phaghighi@mhealth.com | 1-510-717-2602 | 04/24/2017(Private IP - PIP) 04/24/2017(WAN Analysis Reporting) 04/24/2017(Access) | 06/27/2017 |  | 05/09/2017 (24168294) 05/05/2017 (24168295) | 04/27/2017 05/03/2017 | 04/25/2017 |  | Activated/Installed | N (24168294) N (24168296) N (24168295) | U0101953 |  | NSPE0011060612 Order Request # 193924338 - 70M GCAR | NSPE0011060612
Completed | CA016 -06-IM | 17900 VON KARMAN AVE IRVINE, CA 92614-6246 US | 150 MBPS (24175072) | 07/25/2017: 07/24 Successfully activated | 193931682 | CA016 -06-IM | Private IP - PIP (24175071) WAN Analysis Reporting (24175073) Access (24175072) | 24175071 24175073 24175072 | 100 MBPS (24175071) |  | 161976664 (Private IP (PIP)) 161976665 (WAN Analysis Reporting) 161976662 (Access) | C4006835/ADD (24175071) E4018876/ADD (24175072) | 12.KFGX.000482..COXC. (2417507223425201) | 5855293 | 25000 | PVC ID : 5855293 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65085 PE IP Address : 68.136.71.125 CE Address : 68.136.71.126 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24175072) | 1000Base-SX (850nm, Multi Mode Fiber) (24175072) | Ethernet | COX (2417507223425201) | 03/20/2017 (2417507223425201) | 05/23/2017 (2417507223425201) |  | 05/23/2017 (VFORCE) (24175072) | 05/23/2017 (VFORCE) (24175072) | DEMARCDET - bldg main 2nd floor cst server room rack cust center rak RU 17 Accedian IRVNCAJK1BW-IR03CPED70 port SFP-B 850 NM set to auto. tagged 12.VLXX.002435..COXC. |  | zack Coleman 1-949-252-5552 zack_coleman@optum.com | Herbert villostas | herbert_villostas@optum.com | 632-790-6516 | 05/23/2017(Private IP - PIP) 05/23/2017(WAN Analysis Reporting) 05/23/2017(Access) | 07/24/2017 |  | 08/28/2017 (24175071) 08/24/2017 (24175072) | 04/28/2017 05/04/2017 | 05/23/2017 |  | Activated/Installed | N (24175071) N (24175073) N (24175072) | U0101953 |  | NSPE0011064112 Order Request # 193930858 | NSPE0011064112
Completed | San Antonio TX | 4350 LOCKHILL SELMA RD STE 300 SAN ANTONIO, TX 78249-2166 US | 200 MBPS (24177897) | 11/02/2017: 11/02 Unattended Activation scheduled 11/07/2017 10:30PM CST | 193933609 | San Antonio TX | Private IP - PIP (24177896) WAN Analysis Reporting (24177898) Access (24177897) | 24177896 24177898 24177897 | 100 MBPS (24177896) |  | 162258521 (Private IP (PIP)) 162258522 (WAN Analysis Reporting) 162258519 (Access) | C5003019/ADD (24177896) E5006258/ADD (24177897) | 21.L1XX.009247..TWCC (2417789723470201) | 5855418 | 25000 | PVC ID : 5855418 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65055 PE IP Address : 68.139.255.137 CE Address : 68.139.255.138 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24177897) | 1000Base-SX (850nm, Multi Mode Fiber) (24177897) | Ethernet | TIME WARNER CABLE (2417789723470201) | 05/02/2017 (2417789723470201) | 06/15/2017 (2417789723470201) | 06/07/2017 (2417789723470201) | 06/08/2017 (VFORCE) (24177897) | 06/08/2017 (VFORCE) (24177897) | DEMARCDET - 3rd flr, suite 300 MDF RM |  | David Gamez 1-210-563-7553 david.gamez@optum.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 06/08/2017(Private IP - PIP) 06/08/2017(WAN Analysis Reporting) 06/08/2017(Access) |  |  | 09/18/2099 (24177896) 09/16/2099 (24177897) | 07/13/2017 07/19/2017 | 06/08/2017 |  | Activated/Installed | N (24177896) N (24177898) N (24177897) | U0101953 | Jeopardy Notification 2 (05/29/2017) | NSPE0011064958 Order Request # 193931890 | NSPE0011064958
Completed | CA013-02-IJ UHG - Monarch Irvine | 7 TECHNOLOGY DR IRVINE, CA 92618-2302 US | 1 GBPS (24210092) | 06/20/2017: 06/19 Successfully activated | 193951678 | CA013-02-IJ UHG - Monarch Irvine | Private IP - PIP (24210091) WAN Analysis Reporting (24210093) Access (24210092) | 24210091 24210093 24210092 | 1 GBPS (24210091) |  | 163242182 (Private IP (PIP)) 163242183 (WAN Analysis Reporting) 163242180 (Access) | C0119013/ADD (24210091) E5006315/ADD (24210092) | 12.KFGX.000483..COXC. (2421009281411201) | 5857203 | 700000 | PVC ID : 5857203 VPN Name : UHG-Monarch Router Name : LSA29E02 VRF Name : V976456:UHGMonarch Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65502 PE IP Address : 199.220.172.137 CE Address : 199.220.172.138 QoS - Egress Profile: R1 | 1000Base-SX-850nm (24210092) | 1000Base-SX (850nm, Multi Mode Fiber) (24210092) | Ethernet | COX (2421009281411201) | 03/24/2017 (2421009281411201) | 04/24/2017 (2421009281411201) |  | 04/24/2017 (VFORCE) (24210092) | 04/24/2017 (VFORCE) (24210092) | DEMARCDET - 1st floor, mpoe, cox wall mounted data rack, accedian port sfp-B |  | Santosh Tendolkar 1-949-573-3530 stendolkar@mhealth.com | Pooyan Haghighi | phaghighi@mhealth.com | 1-510-717-2602 | 04/24/2017(Private IP - PIP) 04/24/2017(WAN Analysis Reporting) 04/24/2017(Access) | 06/19/2017 |  | 05/03/2017 (24210091) 05/01/2017 (24210092) | 05/04/2017 05/10/2017 | 04/25/2017 |  | Activated/Installed | N (24210091) N (24210093) N (24210092) | U0101953 |  | NSPE0011079797 Order Request 193951523 Reissued. Preferred Carrier Cox | NSPE0011079797
|  | 6150 TRENTON LN N PLYMOUTH, MN 55442-3240 | 9953.28 MBPS (CQBLHJJF) 9953.28 MBPS (IQBLCZ21) 9953.28 MBPS (OQBL137B) | 05/18/2017: 05/18 Background: Change USPL order to add ring/line side protection to the 10 Gig LAN PHY Status: Capacity Creation Request 1340355 estimated due date 05/31. Cards already received per Matt on the call Next action: LEC Build Who owns the next action: VzT Ticket: NA | 9111101 |  | Internet Dedicated (U334131) | U334131 | 9953.28 MBPS (CQBLHJJF) 9953.28 MBPS (IQBLCZ21) 9953.28 MBPS (OQBL137B) |  |  | PLBK94BB0001 (CQBLHJJF) PLBK94BB0001 (IQBLCZ21) PLBK94BB0001 (OQBL137B) | [15 empty] | TOM KRENN 7637443141 TOM_KRENN@OPTUM.COM | [6 empty] | 06/01/2017 (CQBLHJJF) 09/08/2016 (IQBLCZ21) 05/11/2020 (OQBL137B) 05/31/2017 (U334131) | 05/31/2017 (U334131) |  |  |  | N (U334131) |  |  | NSPE0011087072 add ring/line side protection | NSPE0011087072
Completed | AZ056-02-IM | 20040 N 19TH AVE PHOENIX, AZ 85027-4255 US | 10 MBPS (24229418) | 08/09/2017: 08/08 Successfully activated | 193963045 | AZ056-02-IM | Private IP - PIP (24229417) WAN Analysis Reporting (24229419) Access (24229418) | 24229417 24229419 24229418 | 10 MBPS (24229417) |  | 163750078 (Private IP (PIP)) 163750079 (WAN Analysis Reporting) 163750076 (Access) | C0119198/ADD (24229417) E3037640/ADD (24229418) | 23.KEGN.000092..COXC. (2422941823717601) | 5858505 | 1500 | PVC ID : 5858505 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65184 PE IP Address : 152.181.157.69 CE Address : 152.181.157.70 QoS - Egress Profile: R12 | 1000Base-T (24229418) | 1000Base-SX (850nm, Multi Mode Fiber) (24229418) | Ethernet | COX (2422941823717601) | 03/29/2017 (2422941823717601) | 05/10/2017 (2422941823717601) |  | 05/04/2017 (VFORCE) (24229418) | 05/04/2017 (VFORCE) (24229418) | DEMARCDET - 1ST FLR, SERVER RM, WALL MTD, NEXT TO THE RACK, PORT B |  | JENNIFER A WILLIAMS 1-623-707-0050 jennifer.a.williams@optum.com | Leslie Isaac | Leslie.Isaac@optum.com | 44-186-578-7320 | 05/04/2017(Private IP - PIP) 05/04/2017(WAN Analysis Reporting) 05/04/2017(Access) | 08/08/2017 |  | 05/05/2017 (24229417) 05/03/2017 (24229418) | 05/09/2017 05/15/2017 | 05/04/2017 |  | Activated/Installed | N (24229417) N (24229419) N (24229418) | U0101953 |  | Order Request 193962395 | NSPE0011089916
Completed | CA056-05-IM Signal Hill CA | 1100 E WILLOW ST SIGNAL HILL, CA 90755-3433 US | 100 MBPS (24246886) | 07/18/2017: 07/15 Successfully activated | 193975143 | CA056-05-IM Signal Hill, CA | Private IP - PIP (24246885) WAN Analysis Reporting (24246887) Access (24246886) | 24246885 24246887 24246886 | 100 MBPS (24246885) |  | 164189596 (Private IP (PIP)) 164189597 (WAN Analysis Reporting) 164189594 (Access) | C1052805/ADD (24246885) E4019301/ADD (24246886) | CHC00426879 (2424688623351201) | 5859675 | 70000 | PVC ID : 5859675 VPN Name : UHG-Monarch Router Name : LSA29E02 VRF Name : V976456:UHGMonarch Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65504 PE IP Address : 152.162.43.233 CE Address : 152.162.43.234 QoS - Egress Profile: R12 | 100Base-TX (24246886) | 100Base-TX (24246886) | Ethernet | CHARTER (2424688623351201) | 03/31/2017 (2424688623351201) | 06/27/2017 (2424688623351201) | 06/30/2017 (2424688623351201) | 07/06/2017 (VFORCE) (24246886) | 07/06/2017 (VFORCE) (24246886) | DEMARCADDR - 624 S GRAND AVE, LOS ANGELES CA 90017 DEMARCDET - BLDG MAIN, 1ST FLR, ROOM MPOE, RACK MOUNTED/UPPER PART OF RACK, CISCO ASR920, |  | SANTOSH TENDOLKAR 1-562-382-7377 stendolkar@mhealth.com | POOYAN HAGHIGHI | phaghighi@mhealth.com | 1-510-717-2602 | 07/06/2017(Private IP - PIP) 07/06/2017(WAN Analysis Reporting) 07/06/2017(Access) | 07/18/2017 |  | 07/12/2017 (24246885) 07/10/2017 (24246886) | 07/07/2017 07/13/2017 | 07/06/2017 |  | Activated/Installed | N (24246885) N (24246887) N (24246886) | U0101953 | Jeopardy Notification 1 (05/30/2017) | NSPE0011097025 Order Request # 193973090 | NSPE0011097025
Completed | WA057-05-IJ Tacoma WA | 3315 S 23RD ST STE 310 TACOMA, WA 98405-1617 US | 100 MBPS | 04/06/2017: 04/06 Changes deployed successfully | 193976820 | WA057-05-IJ Tacoma | Private IP - PIP (24247584) Access | 24247584 | 20 MBPS (24247584) |  | 108331077 (Private IP (PIP)) 108331074 | C1034034/NONE (24247584) |  | 5727874 | 4000 | PVC ID : 5727874 VPN Name : UnitedHealthGroup Router Name : HICGE02 VRF Name : V556790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65183 PE IP Address : 152.176.148.57 CE Address : 152.176.148.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Janine Johnson 1-253-292-4202 janine.johnson@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 05/01/2017(Private IP | 04/06/2017 |  | 04/03/2017 (24247584) | 04/11/2017 | 05/01/2017 |  |  | N (24247584) N | U0101953 |  | Upgrade 10M to 20M | NSPE0011098629
Completed | TX342-02-IM | 1701 S STAPLES ST CORPUS CHRISTI, TX 78404-3022 US | 4.6 MBPS (24265761) | 05/11/2017: 05/11 Background: TX342-02-IM Corpus Christi, TX; New 4.5Mbps - 3XT1 MLPPP; ATT; No NID; No MS; Status: Loop not yet fully delivered due to defective cable pair. Escalation ticket has been stepped up to 1st Level Escalation Executive requesting for an immediate resolution. Next action: LEC to complete handover Who owns the next action: ATT Ticket: B201705034028 | 193987528 | TX342-02-IM | Private IP - PIP (24265760) WAN Analysis Reporting (24265762) Access (24265761) | 24265760 24265762 24265761 | 4.6 MBPS (24265760) |  | 164613410 (Private IP (PIP)) 164613411 (WAN Analysis Reporting) 164613408 (Access) | C0119588/ADD (24265760) N1036322/ADD (24265761) N1036324/ADD (24265761) N1036323/ADD (24265761) | 34/HCGS/629533//SW (2426576123871201) 34/HCGS/629534//SW (2426576123871201) | 5861447 | 1500 | PVC ID : 5861447 VPN Name : UnitedHealthGroup Router Name : SAJGE03 VRF Name : V989647:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65116 PE IP Address : 152.181.204.197 CE Address : 152.181.204.198 QoS - Egress Profile: R12 |  | DS1 (24265761) | TDM | ATT (2426576123871201) | 04/24/2017 (2426576123871201) | 05/02/2017 (2426576123871201) | 05/12/2017 (2426576123871201) |  |  | DEMARCADDR - 1701 S STAPLES ST CORPUS CHRISTI TX DEMARCDET - 1ST FLR I 1701 S STAPLES, BACK RM BY PWR MTR,MM POS#6 |  | Rick Williamson 1-210-951-3129 RWilliamson@wellmed.net | Rick Williamson | RWilliamson@wellmed.net | 1-210-951-3129 | 05/12/2017(Private IP - PIP) 05/12/2017(WAN Analysis Reporting) 05/12/2017(Access) |  |  | 05/09/2017 (24265760) 05/05/2017 (24265761) | 05/16/2017 05/22/2017 | 05/12/2017 |  | Scheduled Status Set | N (24265760) N (24265762) N (24265761) | U0101953 |  | NSPE0011108085 - Order Request # 193987332 | NSPE0011108085
Completed | TX349-02-IM | 6513 SMITHFIELD RD STE C NORTH RICHLAND HILLS, TX 76182-4683 US | 1.5 MBPS (24276655) | 07/25/2017: 07/25 Successfully activated | 193994105 | TX349-02-IM | Private IP - PIP (24276654) WAN Analysis Reporting (24276656) Access (24276655) | 24276654 24276656 24276655 | 1.5 MBPS (24276654) |  | 164852082 (Private IP (PIP)) 164852083 (WAN Analysis Reporting) 164852080 (Access) | C0119717/ADD (24276654) D1085144/ADD (24276655) | 14/HCGS/160367//SW (2427665523920501) | 5862272 | 1300 | PVC ID : 5862272 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : V991844-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65193 PE IP Address : 152.176.207.161 CE Address : 152.176.207.162 QoS - Egress Profile: R12 |  | DS1 (24276655) | TDM | ATT (2427665523920501) | 04/20/2017 (2427665523920501) | 04/28/2017 (2427665523920501) | 04/28/2017 (2427665523920501) |  |  |  |  | Patricia Milford 1-214-548-0011 patricia.milford@homecaredimensions.com | JEFF RODRIGUEZ | jeff.rodriguez@optum.com | 1-617-530-2397 | 04/28/2017(Private IP - PIP) 04/28/2017(WAN Analysis Reporting) 04/28/2017(Access) | 07/25/2017 |  | 05/05/2017 (24276654) 05/03/2017 (24276655) | 05/12/2017 05/18/2017 | 04/28/2017 |  | Activated/Installed | N (24276654) N (24276656) N (24276655) | U0101953 | Jeopardy Notification 1 (04/19/2017) | NSPE0011111646 Order Reqeust # 193991861 | NSPE0011111646
Completed | TX348-02-IM | 6344 DAVIS BLVD NORTH RICHLAND HILLS, TX 76180-4762 US | 1.5 MBPS (24276475) | 07/03/2017: 07/03 Background: TX348-02-IM North Richland Hills, TX; New 1.5Mbps 1XT1 MLPPP; ATT; No NID; No MS; Status: Ready for activation. Next action: Customer to activate Who owns the next action: Customer Ticket: NA | 193994049 | TX348-02-IM | Private IP - PIP (24276474) WAN Analysis Reporting (24276476) Access (24276475) | 24276474 24276476 24276475 | 1.5 MBPS (24276474) |  | 164880611 (Private IP (PIP)) 164880612 (WAN Analysis Reporting) 164880609 (Access) | C0119712/ADD (24276474) D1085142/ADD (24276475) | 14/HCGS/160362//SW (2427647523924601) | 5862264 | 768 | PVC ID : 5862264 VPN Name : UnitedHealthGroup Router Name : IAE3E03 VRF Name : V414342-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65163 PE IP Address : 152.162.37.165 CE Address : 152.162.37.166 QoS - Egress Profile: R12 |  | DS1 (24276475) | TDM | ATT (2427647523924601) | 06/09/2017 (2427647523924601) | 06/16/2017 (2427647523924601) | 06/16/2017 (2427647523924601) |  |  | REAR OF BLDB DUAL MOUNT CAB-1,SL CAB-1,SLOT-2 extended to Telco Back board tagged RJ48-C |  | CATHY BUTLER 1-205-948-1845 cathy_butler@uhg.com | JEFF RODRIGUEZ | jeff.rodriguez@optum.com | 1-781-557-2317 | 06/16/2017(Private IP - PIP) 06/16/2017(WAN Analysis Reporting) 06/16/2017(Access) |  |  | 06/23/2017 (24276474) 06/21/2017 (24276475) | 06/30/2017 07/07/2017 | 06/19/2017 |  | Activated/Installed | N (24276474) N (24276476) N (24276475) | U0101953 | Jeopardy Notification 1 (04/19/2017) | Order Request 193993058 | NSPE0011112654
Completed | TX346-02-IM | 7198 MERCHANT AVE EL PASO, TX 79915-1235 US | 4.6 MBPS (24276478) | 06/15/2017: 6/15 Ready for plug and play- cust notified | 193994050 | TX346-02-IM | Private IP - PIP (24276477) WAN Analysis Reporting (24276479) Access (24276478) | 24276477 24276479 24276478 | 4.6 MBPS (24276477) |  | 164889743 (Private IP (PIP)) 164889764 (WAN Analysis Reporting) 164889741 (Access) | C0119714/ADD (24276477) N1036364/ADD (24276478) N1036366/ADD (24276478) N1036365/ADD (24276478) | 30/HCGS/630926//SW (2427647823926801) 30/HCGS/630927//SW (2427647823926801) | 5862266 | 1500 | PVC ID : 5862266 VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64832 PE IP Address : 152.176.77.69 CE Address : 152.176.77.70 QoS - Egress Profile: R12 |  | DS1 (24276478) | TDM | ATT (2427647823926801) | 06/05/2017 (2427647823926801) | 06/12/2017 (2427647823926801) | 06/13/2017 (2427647823926801) |  |  | DEMARCADDR - 7198 MERCHANT AVE EL PASO TX DEMARCDET - INSIDE SUITE 1C, TELCO CLOSET CAB 2, S CAB 2, SLOT 1 |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | RICK WILLIAMSON | rwilliamson@wellmed.net | 1-210-951-3129 | 06/14/2017(Private IP - PIP) 06/14/2017(WAN Analysis Reporting) 06/14/2017(Access) |  |  | 06/20/2017 (24276477) 06/16/2017 (24276478) | 07/05/2017 07/11/2017 | 06/14/2017 |  | Activated/Installed | N (24276477) N (24276479) N (24276478) | U0101953 | Jeopardy Notification 1 (06/13/2017) | Order Request 193993058 | NSPE0011112654
Completed | TX347-02-IM | 1317 E JASMINE AVE MCALLEN, TX 78501-5708 US | 4.6 MBPS (24276472) | 04/20/2017: Ready for plug and play 3xT1 Cust notified | 193994048 | TX347-02-IM | Access (24276472) Private IP - PIP (24276471) WAN Analysis Reporting (24276473) | 24276472 24276471 24276473 | 4.6 MBPS (24276471) |  | 164880613 (Access) 164880615 (Private IP (PIP)) 164880616 (WAN Analysis Reporting) | N1036367/ADD (24276472) N1036368/ADD (24276472) N1036369/ADD (24276472) C0119715/ADD (24276471) | 38/HCGS/631034//SW (2427647223924601) 38/HCGS/631035//SW (2427647223924601) | 5862265 | 1500 | PVC ID : 5862265 VPN Name : UnitedHealthGroup Router Name : AX33E01 VRF Name : V993346-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65219 PE IP Address : 68.136.198.193 CE Address : 68.136.198.194 QoS - Egress Profile: R12 |  | DS1 (24276472) | TDM | ATT (2427647223924601) | 04/07/2017 (2427647223924601) | 04/17/2017 (2427647223924601) | 04/17/2017 (2427647223924601) |  |  | DEMARCADDR - 1317 E JASMINE AVE MCALLEN TX DEMARCDET - UTSIDE SNI, D. MT., POS 2JT=RJ48 C |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | RICK WILLIAMSON | rwilliamson@wellmed.net | 1-210-951-3129 | 04/19/2017(Access) 04/19/2017(Private IP - PIP) 04/19/2017(WAN Analysis Reporting) |  |  | 04/20/2017 (24276472) 04/24/2017 (24276471) | 04/28/2017 05/04/2017 | 04/19/2017 |  | Activated/Installed | N (24276472) N (24276471) N (24276473) | U0101953 |  | Order Request 193993058 | NSPE0011112654
Completed | TX263-05-IM | 8107 SPRINGDALE RD STE 110 AUSTIN, TX 78724-2437 US | 4.6 MBPS (24281871) | 04/21/2017: 4/21 cust notified ready for plug and play | 193997251 | TX263-05-IM | Private IP - PIP (24281870) WAN Analysis Reporting (24281872) Access (24281871) | 24281870 24281872 24281871 | 4.6 MBPS (24281870) |  | 164982170 (Private IP (PIP)) 164982171 (WAN Analysis Reporting) 164982168 (Access) | C0119778/ADD (24281870) N1036395/ADD (24281871) N1036394/ADD (24281871) N1036393/ADD (24281871) | 32/HCGS/697049//SW (2428187123944801) 32/HCGS/697050//SW (2428187123944801) | 5862530 | 1500 | PVC ID : 5862530 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65218 PE IP Address : 152.176.43.201 CE Address : 152.176.43.202 QoS - Egress Profile: R12 |  | DS1 (24281871) | TDM | ATT (2428187123944801) | 04/10/2017 (2428187123944801) | 04/19/2017 (2428187123944801) | 04/19/2017 (2428187123944801) |  |  | DEMARCADDR - 8107 SPRINGDALE RD AUSTIN TX DEMARCDET - 1ST FL, SUITE 110, NETWORK WALL, CA WALL, CAB 1 SLOT 1 |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | SEENIVASAN B | seenivasan.b@optum.com | 91-804-670-4287 | 04/20/2017(Private IP - PIP) 04/20/2017(WAN Analysis Reporting) 04/20/2017(Access) |  |  | 04/26/2017 (24281870) 04/24/2017 (24281871) | 05/01/2017 05/05/2017 | 04/20/2017 |  | Activated/Installed | N (24281870) N (24281872) N (24281871) | U0101953 |  | NSPE0011115435 Order Request # 193996806 | NSPE0011115435
Completed | FL213-02-IM | 8380 BAYMEADOWS RD JACKSONVILLE, FL 32256-4446 US | 1.5 MBPS (24287449) | 04/21/2017: 4/21 Cust notified/ ready for plug and play | 193999926 | FL213-02-IM | Private IP - PIP (24287448) WAN Analysis Reporting (24287450) Access (24287449) | 24287448 24287450 24287449 | 1.5 MBPS (24287448) |  | 165059070 (Private IP (PIP)) 165059073 (WAN Analysis Reporting) 165059068 (Access) | C0119879/ADD (24287448) D1085170/ADD (24287449) | 52/HCGS/777752//SB (2428744923959001) | 5863015 | 900 | PVC ID : 5863015 VPN Name : UnitedHealthGroup Router Name : JAP3E03 VRF Name : V523238-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65196 PE IP Address : 147.225.133.209 CE Address : 147.225.133.210 QoS - Egress Profile: R12 |  | DS1 (24287449) | TDM | ATT (2428744923959001) | 04/10/2017 (2428744923959001) | 04/20/2017 (2428744923959001) | 04/20/2017 (2428744923959001) |  |  | DEMARCADDR - 8380 BAYMEADOWS RD JKVL FL DEMARCDET - 1S T FL TELCO WALL QM SLOT2 RJ48C NO RJ48C NON EXT |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | Faiq Syed | faiq_syed@optum.com | 1-847-619-5605 | 04/20/2017(Private IP - PIP) 04/20/2017(WAN Analysis Reporting) 04/20/2017(Access) |  |  | 04/27/2017 (24287448) 04/25/2017 (24287449) | 05/02/2017 05/08/2017 | 04/20/2017 |  | Activated/Installed | N (24287448) N (24287450) N (24287449) | U0101953 |  | NSPE0011115891 Order Request # 193997370 | NSPE0011115891
Completed | TX341-02-IM | 1313 E ALTON GLOOR BLVD BROWNSVILLE, TX 78526-3909 US | 1.5 MBPS (24287455) | 04/19/2017: 4/18 Ready for plug and play- cuto notified | 193999967 | TX341-02-IM | Private IP - PIP (24287454) WAN Analysis Reporting (24287456) Access (24287455) | 24287454 24287456 24287455 | 1.5 MBPS (24287454) |  | 165059066 (Private IP (PIP)) 165059067 (WAN Analysis Reporting) 165059064 (Access) | C0119878/ADD (24287454) D1085169/ADD (24287455) | 38/HCGS/631038//SW (2428745523959001) | 5863016 | 1300 | PVC ID : 5863016 VPN Name : UnitedHealthGroup Router Name : SAJ3E02 VRF Name : V439040-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65242 PE IP Address : 68.137.109.25 CE Address : 68.137.109.26 QoS - Egress Profile: R12 |  | DS1 (24287455) | TDM | ATT (2428745523959001) | 04/10/2017 (2428745523959001) | 04/18/2017 (2428745523959001) | 04/18/2017 (2428745523959001) |  |  | DEMARCADDR - 1313 E ALTON GLOOR BLVD BROWNSVILLE TX DEMARCDET - ONI 1, POS 1, LOCATED AT REAR OF BUILD OF BUILDING |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | SEENIVASAN B | seenivasan.b@optum.com | 91-804-670-4287 | 04/18/2017(Private IP - PIP) 04/18/2017(WAN Analysis Reporting) 04/18/2017(Access) |  |  | 04/25/2017 (24287454) 04/21/2017 (24287455) | 05/02/2017 05/08/2017 | 04/18/2017 |  | Activated/Installed | N (24287454) N (24287456) N (24287455) | U0101953 |  | NSPE0011115891 Order Request # 193997370 | NSPE0011115891
Completed | TX343-02-IM | 1711 S STAPLES ST CORPUS CHRISTI, TX 78404-3022 US | 1.5 MBPS (24287452) | 05/11/2017: 5/11 Ready to plug and play- cust notified | 193999934 | TX343-02-IM | Private IP - PIP (24287451) WAN Analysis Reporting (24287453) Access (24287452) | 24287451 24287453 24287452 | 1.5 MBPS (24287451) |  | 165059002 (Private IP (PIP)) 165059003 (WAN Analysis Reporting) 165059000 (Access) | C0119881/ADD (24287451) D1085171/ADD (24287452) | 34/HCGS/629541//SW (2428745223958901) | 5863013 | 1300 | PVC ID : 5863013 VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65243 PE IP Address : 68.138.25.77 CE Address : 68.138.25.78 QoS - Egress Profile: R12 |  | DS1 (24287452) | TDM | ATT (2428745223958901) | 04/10/2017 (2428745223958901) | 04/19/2017 (2428745223958901) | 05/11/2017 (2428745223958901) |  |  | DEMARCADDR - 1711 S STAPLES ST CORPUS CHRISTI TX DEMARCDET - 1ST FLR I 1711 S STAPLES, WAREHOUSE AREA,DUALL MT POS#1 |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | JEBIN GEORGE | jebin.george@optum.com | 1-804-670-4595 | 05/11/2017(Private IP - PIP) 05/11/2017(WAN Analysis Reporting) 05/11/2017(Access) |  |  | 04/26/2017 (24287451) 04/24/2017 (24287452) | 05/02/2017 05/08/2017 | 05/11/2017 |  | Activated/Installed | N (24287451) N (24287453) N (24287452) | U0101953 | Jeopardy Notification 1 (04/20/2017) | NSPE0011115891 Order Request # 193997370 | NSPE0011115891
Completed | FL212-02-IM | 809 S ORLANDO AVE WINTER PARK, FL 32789-7101 US | 1.5 MBPS (24288826) | 04/20/2017: 4/20 ready fro plug and play / customer notified | 194000285 | FL212-02-IM | Private IP - PIP (24288825) WAN Analysis Reporting (24288827) Access (24288826) | 24288825 24288827 24288826 | 1.5 MBPS (24288825) |  | 165193806 (Private IP (PIP)) 165193807 (WAN Analysis Reporting) 165193804 (Access) | C0119893/ADD (24288825) D1085172/ADD (24288826) | 25/HCGS/301375//UFLG (2428882623986901) | 5863153 | 1300 | PVC ID : 5863153 VPN Name : UnitedHealthGroup Router Name : AUB9E01 VRF Name : V428374:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65271 PE IP Address : 206.115.85.185 CE Address : 206.115.85.186 QoS - Egress Profile: R12 |  | DS1 (24288826) | TDM | CENTURYLINK (2428882623986901) | 04/10/2017 (2428882623986901) | 04/20/2017 (2428882623986901) | 04/19/2017 (2428882623986901) |  |  | DEMARCADDR - 809 S ORLANDO AVE WINTER PARK FL DEMARCDET - 1ST FLOOR, IT ROOM, POSITION 1 OF 2 |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | LAEEQ SAJJAD | laeeq_sajjad@optum.com | 1-312-617-5537 | 04/19/2017(Private IP - PIP) 04/19/2017(WAN Analysis Reporting) 04/19/2017(Access) |  |  | 04/27/2017 (24288825) 04/25/2017 (24288826) | 05/02/2017 05/08/2017 | 04/19/2017 |  | Activated/Installed | N (24288825) N (24288827) N (24288826) | U0101953 |  | NSPE0011119301 Order Request # 193999718 | NSPE0011119301
Completed |  | 20021 120TH AVE NE BOTHELL, WA 98011 USA | 1.536 MBPS (IQBLG504) | 07/07/2017: 07/07 Cancelling activation scheduled. Circuit extension is still being worked by customer. | 9126999 |  | Private IP (IQBLG504) | IQBLG504 | 12.288 MBPS | P2165056 |  | BCBLBTRP0001 (IQBLG504) BCBLBTRP0002 (IQBLG504) BCBLBTRP0003 (IQBLG504) BCBLBTRP0004 (IQBLG504) BCBLBTRP0005 (IQBLG504) BCBLBTRP0006 (IQBLG504) BCBLBTRP0007 (IQBLG504) BCBLBTRP0008 (IQBLG504) | 86/HCGS/484089//FTNC/ (IQBLG50482CWMB01) |  | 1536 | VPN Name : UnitedHealthGroup Router Name : SEJGE02 VRF Name : V264785:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65282 PE IP Address : v4-152.161.29.245,v6-2600:810:600:0:0:0:0:e319 CE Address : v4-152.161.29.246,v6-2600:810:600:0:0:0:0:e31a QoS - Egress Profile: R12 |  |  |  | FRONTIER (IQBLG50482CWMB01) | 04/20/2017 (IQBLG50482CWMB01) | 05/02/2017 (IQBLG50482CWMB01) | 04/28/2017 (IQBLG50482CWMB01) |  |  | LEC Circuit ID: 86/HCGS/484089//FTNC/ Circuit ID: P2165056 BCBLBTRP0001 DEMARC LOC: SLOT: 01=0A SHELF: 02=0A PORT: 01=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0002 DEMARC LOC: SLOT: 02=0A SHELF: 02=0A PORT: 02=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0003 DEMARC LOC: SLOT: 03=0A SHELF: 02=0A PORT: 02=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0004 DEMARC LOC: SLOT: 04=0A SHELF: 02=0A PORT: 04=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0005 DEMARC LOC: SLOT: 05=0A SHELF: 02=0A PORT: 05=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0006 DEMARC LOC: SLOT: 06=0A SHELF: 02=0A PORT: 06=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0007 DEMARC LOC: SLOT: 05=0A SHELF: 02=0A PORT: 05=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0008 DEMARC LOC: SLOT: 08=0A SHELF: 02=0A PORT: 08=0A PHYS LOC: MPOE 1ST FLOOR |  | DAVE LOWRY 0014256861202 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 05/03/2017 (IQBLG504) |  |  | 05/09/2017 (IQBLG504) | 05/11/2017 (IQBLG504) |  |  |  | N (IQBLG504) | 05650532 |  | NSPE0011136498 | NSPE0011136498
Completed | FL147-05-IM | 2800 E SILVER SPRINGS BLVD STE 201 OCALA, FL 34470-7057 US | 50 MBPS (24347393) | 06/29/2017: 06/29 Background: Background: FL147-05-IM Ocala, FL; New 10M/50M PIP-Eth; Cox; NID; No MS Status: BEAS delivered Next action: Pending line testing Who owns the next action: ACD Ticket: NA | 194026499 | FL147-05-IM | Private IP - PIP (24347392) WAN Analysis Reporting (24347394) Access (24347393) | 24347392 24347394 24347393 | 10 MBPS (24347392) |  | 166234004 (Private IP (PIP)) 166234005 (WAN Analysis Reporting) 166234002 (Access) | C4007189/ADD (24347392) E4019742/ADD (24347393) | 40.KFGX.000079..COXC. (2434739324173001) | 5865789 | 4000 | PVC ID : 5865789 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65291 PE IP Address : 152.183.205.153 CE Address : 152.183.205.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24347393) | 1000Base-SX (850nm, Multi Mode Fiber) (24347393) | Ethernet | COX (2434739324173001) | 04/19/2017 (2434739324173001) | 06/30/2017 (2434739324173001) |  | 06/29/2017 (VFORCE) (24347393) |  | DEMARCDET - NA |  | Robert Barr 1-952-202-0159 robert_barr@uhg.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 06/30/2017(Private IP - PIP) 06/30/2017(WAN Analysis Reporting) 06/30/2017(Access) |  |  | 06/30/2017 (24347392) 06/28/2017 (24347393) | 09/28/2017 10/04/2017 | 06/30/2017 |  | Activated/Installed | N (24347392) N (24347394) N (24347393) | U0101953 | Jeopardy Notification 2 (06/20/2017) | NSPE0011142865 Order Request # 194025538 | NSPE0011142865
Completed | AZ057-02-IM | 1107 E BELL RD STE 3 PHOENIX, AZ 85022-2692 US | 50 MBPS (24386990) | 09/19/2017: 09/18 Successfully activated | 194049139 | AZ057-02-IM | Private IP - PIP (24386989) WAN Analysis Reporting (24386991) Access (24386990) | 24386989 24386991 24386990 | 10 MBPS (24386989) |  | 167620178 (Private IP (PIP)) 167620179 (WAN Analysis Reporting) 167620176 (Access) | C4007260/ADD (24386989) E4019939/ADD (24386990) | 23.KFGX.990642..COXC. (2438699024400401) | 5867950 | 30000 | PVC ID : 5867950 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65113 PE IP Address : 152.183.132.205 CE Address : 152.183.132.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24386990) | 1000Base-T (24386990) | Ethernet | COX (2438699024400401) | 04/27/2017 (2438699024400401) | 09/15/2017 (2438699024400401) |  | 09/13/2017 (VFORCE) (24386990) | 09/13/2017 (VFORCE) (24386990) | DEMARCDET - 1st flr suite #3, port 3 on BELL AGGA367 7210, tagged and labelled |  | Thomas Zmyslo 1-952-905-7602 thomas_zmyslo@uhg.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 09/13/2017(Private IP - PIP) 09/13/2017(WAN Analysis Reporting) 09/13/2017(Access) | 09/18/2017 |  | 09/26/2017 (24386989) 09/22/2017 (24386990) | 12/19/2017 12/26/2017 | 09/13/2017 |  | Activated/Installed | N (24386989) N (24386991) N (24386990) | U0101953 | Jeopardy Notification 1 (09/07/2017) | NSPE0011161282 Order Request # 194048664 | NSPE0011161282
Completed | C1616-01-IM | 304 E CARSON AVE LAS VEGAS, NV 89101-5903 US | 1.5 MBPS (24424332) | 05/11/2017: 05/11 Background: C1616-01-IM Las Vegas, NV; NV; New 1.5M PIP TDM; Carrier Div: CL; No NID; No MS; Status: Loop delivery date 05/16/2017 Next action: LEC to deliver Who owns the next action: CL Ticket: NA | 194069133 | C1616-01-IM | Private IP - PIP (24424331) WAN Analysis Reporting (24424333) Access (24424332) | 24424331 24424333 24424332 | 1.5 MBPS (24424331) |  | 168432055 (Private IP (PIP)) 168432056 (WAN Analysis Reporting) 168432053 (Access) | C0121691/ADD (24424331) D1086055/ADD (24424332) | 53/HCGS/303228//CTRL (2442433224424401) 13fnwssprt0219 (I0002986.LSV) | 5869991 | 1000 | PVC ID : 5869991 VPN Name : UHG-ECC Router Name : LSVG3E01 VRF Name : V101395-UHGECC Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65518 PE IP Address : 152.187.174.73 CE Address : 152.187.174.74 QoS - Egress Profile: C13 |  | DS1 (24424332) | TDM | CENTURYLINK (2442433224424401) | 05/05/2017 (2442433224424401) | 05/16/2017 (2442433224424401) 05/25/2017 (I0002986.LSV) | 05/17/2017 (2442433224424401) 05/17/2017 (I0002986.LSV) |  |  |  |  | Jason Stauss 1-206-274-7952 jstauss@revenueadvantage.com | Travis Dent | travis.dent@optum.com | 1-763-744-2265 | 05/17/2017(Private IP - PIP) 05/17/2017(WAN Analysis Reporting) 05/17/2017(Access) |  |  | 05/23/2017 (24424331) 05/19/2017 (24424332) | 05/25/2017 06/01/2017 | 05/17/2017 |  | Activated/Installed | N (24424331) N (24424333) N (24424332) | U0101953 |  | NSPE0011178488 Order Request # 194068962 | NSPE0011178488
Completed | HI015-02-IM | 1132 BISHOP ST STE 400 HONOLULU, HI 96813-2867 US | 50 MBPS (24395345) | 09/18/2017: 09/15 Successfully activated | 194053944 | HI015-02-IM | WAN Analysis Reporting (24395346) Access (24395345) Private IP - PIP (24395344) | 24395346 24395345 24395344 | 30 MBPS (24395344) |  | 167781070 (WAN Analysis Reporting) 167781067 (Access) 167781069 (Private IP (PIP)) | C4007269/ADD (24395344) E4019976/ADD (24395345) | 1G/KFFN/003448/LVLC (2439534518068501) | 5868328 | 5000 | PVC ID : 5868328 VPN Name : UnitedHealthGroup Router Name : HNL9E01 VRF Name : Va62144:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65290 PE IP Address : 68.136.201.117 CE Address : 68.136.201.118 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (24395345) | 1000Base-SX (850nm, Multi Mode Fiber) (24395345) | Ethernet | LEVEL 3 (2439534518068501) | 05/02/2017 (2439534518068501) | 05/26/2017 (2439534518068501) | 05/25/2017 (2439534518068501) | 06/02/2017 (VFORCE) (24395345) | 06/02/2017 (VFORCE) (24395345) | DEMARCDET - . . . . |  | Leah Young 1-808-599-5009 leah_young@optum.com | David Jzen Dimayuga | david_dimayuga@optum.com | 632-790-6503 | 06/02/2017(WAN Analysis Reporting) 06/02/2017(Access) 06/02/2017(Private IP - PIP) | 09/15/2017 |  | 06/13/2017 (24395344) 06/09/2017 (24395345) | 06/15/2017 06/09/2017 | 06/02/2017 |  | Activated/Installed | N (24395346) N (24395345) N (24395344) | U0101953 | Jeopardy Notification 2 (05/31/2017) | NSPE0011164824 Order Request # 194053628 | NSPE0011164824
Completed | NY165-01-IJ Lake Success NY | 7 VERMONT DR NEW HYDE PARK, NY 11042-1128 US | 500 MBPS | 05/11/2017: 05/10 Successfully upgraded | 194077119 | NY165-01-IJ Lake Success NY | Private IP - PIP (24440358) Access | 24440358 | 500 MBPS (24440358) |  | 66063653 (Private IP (PIP)) 66063651 | C5000928/NONE (24440358) |  | 5588896 | 25000 | PVC ID : 5588896 VPN Name : UnitedHealthGroup Router Name : NV89E02 VRF Name : V101790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65108 PE IP Address : 147.225.60.217 CE Address : 147.225.60.218 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Patrick Dunn 1-516-622-2957 pdunn@prohealthcare.com | Mohan Basnet | mohan_basnet@optum.com | 1-763-744-1971 | 05/11/2017(Private IP | 05/10/2017 |  | 05/08/2017 (24440358) | 05/16/2017 | 05/11/2017 |  |  | N (24440358) N | U0101953 |  | NSPE0011185791 Order Request # 194076448 | NSPE0011185791
Completed | M0206-05-IJ East Syracuse | 5015 CAMPUSWOOD DR EAST SYRACUSE, NY 13057-4232 US | 50 MBPS (24495741) | 09/14/2017: 09/13 Successfully activated | 194077154 | M0206-05-IJ East Syracuse | Private IP - PIP (24495740) WAN Analysis Reporting (24495742) Access (24495741) | 24495740 24495742 24495741 | 20 MBPS (24495740) |  | 168795347 (Private IP (PIP)) 168795348 (WAN Analysis Reporting) 168795345 (Access) | C4007428/ADD (24495740) E4020393/ADD (24495741) | 36.KFGS.212431..NY (2449574116054701) | 5873774 | 4000 | PVC ID : 5873774 VPN Name : UnitedHealthGroup Router Name : SRD3E02 VRF Name : V572396-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64548 PE IP Address : 206.115.122.229 CE Address : 206.115.122.230 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24495741) | 1000Base-SX (850nm, Multi Mode Fiber) (24495741) | Ethernet | VERIZON (2449574116054701) | 05/16/2017 (2449574116054701) | 06/19/2017 (2449574116054701) | 06/01/2017 (2449574116054701) |  |  | DEMARCDET - DEMARK |  | Bradley Johns 1-315-433-5841 bjohns@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 06/01/2017(Private IP - PIP) 06/01/2017(WAN Analysis Reporting) 06/01/2017(Access) | 09/13/2017 |  | 06/28/2017 (24495740) 06/26/2017 (24495741) | 07/07/2017 07/13/2017 | 06/01/2017 |  | Activated/Installed | N (24495740) N (24495742) N (24495741) | U0101953 |  | NSPE0011184655 Order Request # 194075335 | NSPE0011184655
| SECAUCUS NJ | 800 SECAUCUS RD SECAUCUS, NJ 07094 USA | 2000 MBPS (IQBLHG35) | 10/09/2017: 10/06 Successfully activated | 9152921 |  | Private IP Port Only (IQBLHG35) EVC/PVC Service (N.11401378.5873608) | IQBLHG35 N.11401378.5873608 | 2000 MBPS | P2166788 |  | BOBLBWTG0001 (IQBLHG35) |  | 5874317 5873608 5875329 | 122500 | PVC ID : 5874317,5873608,5875329 VPN Name : UnitedHealthGroup Router Name : 9O2XE02 VRF Name : V103192-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65239 PE IP Address : 152.164.43.229 CE Address : 152.164.43.230 QoS - Egress Profile: R12 PVC ID : 5875329,5873608,5874317 | [9 empty] | ROUTER 9O2XE02 XE-0/3/0 WITHIN VERIZON CAGE 51115 IN THE EQUINIX AREA IS W!RED TO DEMARC RR PP:0000:1071102 PORT:13/14 01.01.G (ROUTER 9O2XE02 XE-0/3/0 WITHIN VERIZON CAGE 51115 IN THE EQUINIX AREA IS W!RED TO DEMARC RR PP:0000:175651 PORT:1/2 |  | PAT DUNN 0012016082870 5166082870 PDUNN@PROHEALTHCARE.COM |  |  |  | 06/29/2017 (IQBLHG35) | 10/06/2017 |  | 07/13/2017 (IQBLHG35) | 07/13/2017 (IQBLHG35) |  |  |  | N (IQBLHG35) N (N.11401378.5873608) | 05650532 P2166788 |  | NSPE0011192693 CW 194078804 | NSPE0011192693
Completed | FL216-01-IM PORT SAINT LUCIE FL | 585 NW LAKE WHITNEY PL PORT SAINT LUCIE, FL 34986 US | 50 MBPS (24483984) | 07/25/2017: Ready for Activation. Customer notified. | 194094651 | FL216-01-IM | Private IP - PIP (24483983) WAN Analysis Reporting (24483985) Access (24483984) | 24483983 24483985 24483984 | 10 MBPS (24483983) |  | 169751464 (Private IP (PIP)) 169751465 (WAN Analysis Reporting) 169751402 (Access) | C4007412/ADD (24483983) E4020359/ADD (24483984) | 60/KRGN/758576//SB (2448398424737601) | 5873244 | 2000 | PVC ID : 5873244 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65101 PE IP Address : 68.137.167.53 CE Address : 68.137.167.54 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (24483984) | 1000Base-SX (850nm, Multi Mode Fiber) (24483984) | Ethernet | ATT (2448398424737601) | 05/12/2017 (2448398424737601) | 07/07/2017 (2448398424737601) | 07/07/2017 (2448398424737601) | 07/11/2017 (VFORCE) (24483984) | 07/11/2017 (VFORCE) (24483984) | DEMARCADDR - 585 NW LAKE WHITNEY PL PSL FL DEMARCDET - 1ST FL EQ RM UNIT 1 PORT 2 OPITAL HANDOFF SC TAGGED |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | MOHAMMED HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 | 07/11/2017(Private IP - PIP) 07/11/2017(WAN Analysis Reporting) 07/11/2017(Access) |  |  | 07/25/2017 (24483983) 07/21/2017 (24483984) | 08/01/2017 08/07/2017 | 07/11/2017 |  | Activated/Installed | N (24483983) N (24483985) N (24483984) | U0101953 | Jeopardy Notification 4 (06/19/2017) | NSPE0011202077 Order Request 194094541 | NSPE0011202077
Completed | C1617-01-IM Tukwila WA | 3311 S 120TH PL TUKWILA, WA 98168-5125 US | 20 MBPS (24534422) | 12/11/2017: 12/11 Successfully activated | 194111951 | C1617-01-IM Tukwila, WA | Private IP - PIP (24534421) WAN Analysis Reporting (24534423) Access (24534422) | 24534421 24534423 24534422 | 10 MBPS (24534421) |  | 169879722 (Private IP (PIP)) 169879723 (WAN Analysis Reporting) 169879720 (Access) | C3013154/ADD (24534421) E3039655/ADD (24534422) | 04.KXGS.235853..PN (2453442224754601) | 5875389 | 5500 | PVC ID : 5875389 VPN Name : UHG-ECC Router Name : HIC9E03 VRF Name : V103212:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65519 PE IP Address : 152.162.163.173 CE Address : 152.162.163.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24534422) | 1000Base-T (24534422) | Ethernet | CENTURYLINK (2453442224754601) | 07/17/2017 (2453442224754601) | 07/26/2017 (2453442224754601) | 07/18/2017 (2453442224754601) | 07/20/2017 (VFORCE) (24534422) | 07/20/2017 (VFORCE) (24534422) | DEMARCDET - ZCOLO SUITE 120 RR 102.01 SHELF 4 CIENA MM OPTICAL PORT 2 LC CONN |  | Matt Overvold 1-206-794-5453 matt.overvold@zayo.com | TRAVIS DENT | travis.dent@optum.com | 1-763-744-2265 | 07/20/2017(Private IP - PIP) 07/20/2017(WAN Analysis Reporting) 07/20/2017(Access) | 12/10/2017 |  | 08/04/2017 (24534421) 08/02/2017 (24534422) | 08/25/2017 08/31/2017 | 07/20/2017 |  | Activated/Installed | N (24534421) N (24534423) N (24534422) | U0101953 | Jeopardy Notification 2 (06/14/2017) | NSPE0011214176 Order Request # 194107814 C1617-01-IM Tukwila WA | NSPE0011214176
Completed | C1579-02-IJ Las Vegas NV; Shutterfly SuperNAP8 | 5225 W CAPOVILLA AVE LAS VEGAS, NV 89118-5005 US | 100 MBPS | 07/31/2017: 07/28 Successfully upgraded | 194112001 | Shutterfly SuperNAP8 Las Vegas C1579-02-IJ | Private IP - PIP (24534788) Access | 24534788 | 100 MBPS (24534788) |  | 68753703 (Private IP (PIP)) 68753701 | C1021225/NONE (24534788) |  | 5603266 | 1500 | PVC ID : 5603266 VPN Name : UHG-ECC Router Name : DOH9E01 VRF Name : V545813:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65534 PE IP Address : 152.162.53.197 CE Address : 152.162.53.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Paul Juarez 1-925-200-8280 Pjuarez@shutterfly.com | Eric Taylor | eric_taylor@optum.com | 1-763-744-2082 | 07/31/2017(Private IP | 07/28/2017 |  | 05/19/2017 (24534788) | 05/30/2017 | 07/31/2017 |  |  | N (24534788) N | U0101953 | Jeopardy Notification 1 (07/19/2017) | NSPE0011215754 Order Request # 194108959 C1579-04-CM Las Vegas NV | NSPE0011215754
Completed | TX352-02-IM Corpus Christi TX | 1959 SARATOGA BLVD CORPUS CHRISTI, TX 78417-3415 US | 4.6 MBPS (24552797) | 06/06/2017: 6/6 Order complete; cust notified | 194121060 | TX352-02-IM Corpus Christi, TX | Private IP - PIP (24552796) WAN Analysis Reporting (24552798) Access (24552797) | 24552796 24552798 24552797 | 4.6 MBPS (24552796) |  | 170640061 (Private IP (PIP)) 170640062 (WAN Analysis Reporting) 170640059 (Access) | C0122310/ADD (24552796) N1036984/ADD (24552797) N1036982/ADD (24552797) N1036983/ADD (24552797) | 34/HCGS/629574//SW (2455279724907701) 34/HCGS/629575//SW (2455279724907701) | 5876122 | 2500 | PVC ID : 5876122 VPN Name : UnitedHealthGroup Router Name : SAJGE03 VRF Name : V989647:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65080 PE IP Address : 152.161.14.97 CE Address : 152.161.14.98 QoS - Egress Profile: R12 |  | DS1 (24552797) | TDM | ATT (2455279724907701) | 05/23/2017 (2455279724907701) | 06/01/2017 (2455279724907701) | 06/02/2017 (2455279724907701) |  |  | DEMARCADDR - 1959 SARATOGA BLVD CORPUS CHRISTI TX DEMARCDET - ONI AT REAR OF BLDG 29, CAB#2, P CAB#2, POS#1 |  | dean Moen 1-763-553-4889 dean_moen@optum.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 06/02/2017(Private IP - PIP) 06/02/2017(WAN Analysis Reporting) 06/02/2017(Access) |  |  | 06/08/2017 (24552796) 06/06/2017 (24552797) | 06/14/2017 06/20/2017 | 06/02/2017 |  | Activated/Installed | N (24552796) N (24552798) N (24552797) | U0101953 |  | NSPE0011218032 Order Request # 194111198 | NSPE0011218032
Completed | C1618-02-IM LAKE MARY FL | 287 INTERNATIONAL PKWY LAKE MARY, FL 32746-5007 US | 500 MBPS (24552827) | 07/25/2017: Ready fro activation. Customer notified. | 194121109 | C1618-02-IM | WAN Analysis Reporting (24552828) Access (24552827) Private IP - PIP (24552826) | 24552828 24552827 24552826 | 400 MBPS (24552826) |  | 170968712 (WAN Analysis Reporting) 170968709 (Access) 170968711 (Private IP (PIP)) | C5003218/ADD (24552826) E5006869/ADD (24552827) | 6H/KFFN/002082/LVLC (2455282724976401) | 5876123 | 250000 | PVC ID : 5876123 VPN Name : UHG-ECC Router Name : JAP3E01 VRF Name : V103497-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65490 PE IP Address : 147.225.209.137 CE Address : 147.225.209.138 QoS - Egress Profile: C13 | 1000Base-T (24552827) | 1000Base-SX (850nm, Multi Mode Fiber) (24552827) | Ethernet | LEVEL 3 (2455282724976401) | 06/13/2017 (2455282724976401) | 07/11/2017 (2455282724976401) | 07/07/2017 (2455282724976401) | 07/11/2017 (VFORCE) (24552827) | 07/11/2017 (VFORCE) (24552827) | DEMARCDET - 1st floor, 0650 PBX server room, Level (3) Cab, cisco3600 cilli code HTRWFLAKW2002 Gig port (0/15), RJ-45 , Tagge |  | Sam Ortiz 1-407-771-5368 sam.ortiz@convergys.com | BRANDON BENSON | brandon_benson@optum.com | 1-763-553-4929 | 07/11/2017(WAN Analysis Reporting) 07/11/2017(Access) 07/11/2017(Private IP - PIP) |  |  | 07/14/2017 (24552826) 07/12/2017 (24552827) | 07/10/2017 07/03/2017 | 07/11/2017 |  | Activated/Installed | N (24552828) N (24552827) N (24552826) | U0101953 |  | NSPE0011221462 Order Request # 194116304 | NSPE0011221462
Completed | CT719-01-IJ Shelton CT | 1 ENTERPRISE DR SHELTON, CT 06484-4631 US |  | 06/08/2017: 06/08 Background: Disco E4010104 Due Date 06/08/2017 Status: Soft disconnect 06/08/2017 Next action: To be hard disconnected then close order Who owns the next action: CDG Ticket: NA | 194129821 | CT719-01-IJ Shelton, CT | Private IP - PIP (24572978) Access (24572979) | 24572978 24572979 | 100 MBPS |  | 108097783 (Private IP (PIP)) 108097781 (Access) | C4003593/REMOVE (24572978) E4010104/REMOVE (24572979) |  | 5727857 | 1500 | PVC ID : 5727857 VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64684 PE IP Address : 152.177.4.225 CE Address : 152.177.4.226 QoS - Egress Profile: R12 |  |  | Ethernet | [8 empty] | MELISSA CHAPMAN 1-763-744-2114 melissa_r_chapman@optum.com | MELISSA CHAPMAN | melissa_r_chapman@optum.com | 1-763-744-2114 | 06/14/2017(Private IP - PIP) 06/14/2017(Access) |  |  | 07/07/2017 (24572978) 07/07/2017 (24572979) | 06/08/2017 | 06/14/2017 |  |  | N (24572978) N (24572979) | U0101953 |  |  | NSPE0011226893
Completed | C1613-02-IJ Sandy UT | 510 W PARKLAND DR SANDY, UT 84070-6419 US | 100 MBPS (24604932) | 09/29/2017: 09/29 Successfully activated | 194141220 | C1613-02-IJ Sandy UT | Private IP - PIP (24604931) WAN Analysis Reporting (24604933) Access (24604932) | 24604931 24604933 24604932 | 30 MBPS (24604931) |  | 172119555 (Private IP (PIP)) 172119556 (WAN Analysis Reporting) 172119553 (Access) | C1054895/ADD (24604931) E4020652/ADD (24604932) | SL/L2XX/248908/ /TQW /ELK (2460493224874001) | 5879999 | 25000 | PVC ID : 5879999 VPN Name : UHG-ECC Router Name : SLKC9E01 VRF Name : V104001:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65443 PE IP Address : 152.183.230.229 CE Address : 152.183.230.230 QoS - Egress Profile: C13 | 100Base-TX (24604932) | 1000Base-SX (850nm, Multi Mode Fiber) (24604932) | Ethernet | XO (2460493224874001) | 06/13/2017 (2460493224874001) | 08/01/2017 (2460493224874001) | 06/28/2017 (2460493224874001) | 06/29/2017 (VFORCE) (24604932) | 06/29/2017 (VFORCE) (24604932) | DEMARCDET - XO cabinet 2... Cienna 311v port 2 |  | Steve Niederhauser 1-801-352-3162 Steve.Niederhauser@conduent.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 06/29/2017(Private IP - PIP) 06/29/2017(WAN Analysis Reporting) 06/29/2017(Access) | 09/29/2017 |  | 08/08/2017 (24604931) 08/04/2017 (24604932) | 07/13/2017 07/19/2017 | 06/29/2017 |  | Activated/Installed | N (24604931) N (24604933) N (24604932) | U0101953 |  |  | NSPE0011238059
Completed | DE003-07-IJ; Newark DE | 4051 OGLETOWN RD NEWARK, DE 19713-3101 US | 50 MBPS (24612370) | 07/28/2017: 07/28 Background: DE003-07-IJ; Newark, DE; Downgrade Access speed from 100M to 50M only Status: Successfully downgraded to 50M access. Customer requested to keep the Port Speed to 10M. Account Manger to submit a PI sup to change the Port Speed from 50M to 10M. Next action: AM to submit a PI Sup. Who owns the next action: AM/OM/OC Ticket: NA | 194144550 | UHG | Private IP - PIP (24612369) Access (24612370) | 24612369 24612370 | 50 MBPS (24612369) |  | 157617873 (Private IP (PIP)) 157617871 (Access) | C1051044/NONE (24612369) E4018258/NONE (24612370) |  | 5846580 | 4000 | PVC ID : 5846580 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65094 PE IP Address : 152.187.175.221 CE Address : 152.187.175.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24612370) | 1000Base-SX (850nm, Multi Mode Fiber) (24612370) | Ethernet | [8 empty] | Marcia Patten 1-302-781-6775 marcia_patten@uhc.com | Joseph Mark Sanorjo | joseph_sanorjo@optum.com | 632-790-6484 | 08/08/2017(Private IP - PIP) 08/08/2017(Access) | 07/24/2017 |  | 06/13/2017 (24612369) 06/13/2017 (24612370) | 06/26/2017 | 08/08/2017 |  |  | N (24612369) N (24612370) | U0101953 | Jeopardy Notification 1 (07/19/2017) | NSPE0011228923 Order Request # 194126944 | NSPE0011228923
Completed | Allen TX | 900 VENTURE DR ALLEN, TX 75013-1197 US | 250 MBPS (24619395) | 09/19/2017: 09/18 Successfully activated | 194149532 | Allen TX | WAN Analysis Reporting (24619396) Access (24619395) Private IP - PIP (24619394) | 24619396 24619395 24619394 | 100 MBPS (24619394) |  | 172134140 (WAN Analysis Reporting) 172134135 (Access) 172134137 (Private IP (PIP)) | C0122692/ADD (24619394) E0001225/ADD (24619395) | 14/KRGN/880662//SW (2461939525180401) | 5880941 | 110000 | PVC ID : 5880941 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65529 PE IP Address : 152.162.5.13 CE Address : 152.162.5.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24619395) | 1000Base-SX (850nm, Multi Mode Fiber) (24619395) | Ethernet | ATT (2461939525180401) | 05/31/2017 (2461939525180401) | 06/15/2017 (2461939525180401) | 06/15/2017 (2461939525180401) | 08/10/2017 (VFORCE) (24619395) | 08/10/2017 (VFORCE) (24619395) | DEMARCADDR - 900 VENTURE DR ALLEN TX DEMARCDET - 1ST FLOOR, INSIDE SBC CO-LOCATION RR 3.02, E-PNL 1,PRTS |  | PATRICK STOEHR 1-954-903-5786 pstoehr@conveyhs.com | Edward Sawyerr | edward.sawyerr@optum.com | 1-763-595-3403 | 08/10/2017(WAN Analysis Reporting) 08/10/2017(Access) 08/10/2017(Private IP - PIP) | 09/18/2017 |  | 08/18/2017 (24619394) 08/16/2017 (24619395) | 08/22/2017 08/16/2017 | 08/10/2017 |  | Activated/Installed | N (24619396) N (24619395) N (24619394) | U0101953 | Jeopardy Notification 4 (07/23/2017) | NSPE0011242408 Order Request # 194145184 - C13 QOS | NSPE0011242408
Completed | C1614-02-IJ Lexington KY | 101 YORKSHIRE BLVD LEXINGTON, KY 40509-1883 US | 100 MBPS (24631854) | 07/31/2017: 07/31 Ready fro Activation. Customer notified. | 194157494 | C1614-02-IJ Lexington, KY | Private IP - PIP (24631853) WAN Analysis Reporting (24631855) Access (24631854) | 24631853 24631855 24631854 | 30 MBPS (24631853) |  | 172365404 (Private IP (PIP)) 172365409 (WAN Analysis Reporting) 172365402 (Access) | C1055100/ADD (24631853) E4020802/ADD (24631854) | KY/KRGS/027898//WINN/ (2463185424874001) | 5881831 | 25000 | PVC ID : 5881831 VPN Name : UHG-ECC Router Name : LOU9E01 VRF Name : Vb58968:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65442 PE IP Address : 68.139.25.229 CE Address : 68.139.25.230 QoS - Egress Profile: C13 | 1000Base-T (24631854) | 1000Base-SX (850nm, Multi Mode Fiber) (24631854) | Ethernet | WINDSTREAM (2463185424874001) | 06/02/2017 (2463185424874001) | 06/30/2017 (2463185424874001) |  | 07/31/2017 (VFORCE) (24631854) |  | DEMARCDET - first floor server room Rack untagged ZT fiber handoff port 2 |  | Randy Abshear 1-859-389-3743 Randy.Abshear@conduent.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 07/28/2017(Private IP - PIP) 07/28/2017(WAN Analysis Reporting) 07/28/2017(Access) |  |  | 08/17/2017 (24631853) 08/15/2017 (24631854) | 07/14/2017 07/20/2017 | 07/28/2017 |  | Activated/Installed | N (24631853) N (24631855) N (24631854) | U0101953 |  | NSPE0011246191 Order Request # 194150332 | NSPE0011246191
Completed | TX354-03-IM Terrell TX | 809 W NASH ST TERRELL, TX 75160 USA | 1.536 MBPS (IQBLHPFR) | 06/15/2017: 06/15 Background: TX354-03-IM Terrell, TX; New 10.542 7xT1 PIP MLPPP; Metro Fiber Sys; No NID; No MS Status: Loop delivered. Pending line testing Next action: ready for plug&play Who owns the next action: Customer Ticket: NA | 9174972 |  | Private IP (IQBLHPFR) | IQBLHPFR | 1.536 MBPS (IQBLHPFR) | P2167928 |  | BCBLBX570001 (IQBLHPFR) BCBLBX570002 (IQBLHPFR) BCBLBX570003 (IQBLHPFR) BCBLBX570004 (IQBLHPFR) BCBLBX570005 (IQBLHPFR) BCBLBX570006 (IQBLHPFR) BCBLBX570007 (IQBLHPFR) | 14/HCGS/160763//SW (1296513) 14/HCGS/160764//SW (1296513) 14/HCGS/160765//SW (1296513) 14/HCGS/160766//SW (1296513) 14/HCGS/160767//SW (1296513) 14/HCGS/160768//SW (1296513) | [6 empty] | ATT (1296513) | 06/06/2017 (1296513) | 06/15/2017 (1296513) | 06/15/2017 (1296513) |  |  | Access: IQBLHPFR Tcoms: I0105390.DAL Verizon Combined Circuit ID: P2167928 VZ Ckt ID |  | JASON OZER 0012109513251 JOZER@WELLMED.NET |  |  |  | 06/20/2017 (IQBLHPFR) |  |  | 06/20/2017 (IQBLHPFR) | 06/28/2017 (IQBLHPFR) |  |  |  | N (IQBLHPFR) | 05650532 |  | NSPE0011249660 CW 194154523 | NSPE0011249660
Completed | CO039-02-IM Grand Junction CO | 2775 CROSSROADS BLVD GRAND JUNCTION, CO 81506-8712 US | 500 MBPS (24635561) | 07/18/2017: 07/18 Successfully activated | 194159927 | CO039-02-IM Grand Junction, CO | Private IP - PIP (24635560) WAN Analysis Reporting (24635562) Access (24635561) | 24635560 24635562 24635561 | 300 MBPS (24635560) |  | 173359243 (Private IP (PIP)) 173359264 (WAN Analysis Reporting) 173359241 (Access) | C5003265/ADD (24635560) E5006981/ADD (24635561) | 29.KXGS.239031..MS (2463556124727601) | 5882001 | 250000 | PVC ID : 5882001 VPN Name : UnitedHealthGroup Router Name : DNVR9E01 VRF Name : V483292:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65060 PE IP Address : 152.176.198.197 CE Address : 152.176.198.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24635561) | 1000Base-SX (850nm, Multi Mode Fiber) (24635561) | Ethernet | CENTURYLINK (2463556124727601) | 06/02/2017 (2463556124727601) | 06/16/2017 (2463556124727601) | 06/14/2017 (2463556124727601) | 06/16/2017 (VFORCE) (24635561) | 06/16/2017 (VFORCE) (24635561) | DEMARCDET - MN PBX ROOM 3750 WALL MTG'D OPT PORT 2 |  | Ed Frederick 1-970-254-5798 ed.frederick@rmhp.org | SCOTT MOYER | scott_moyer@optum.com | 1-763-744-2154 | 06/16/2017(Private IP - PIP) 06/16/2017(WAN Analysis Reporting) 06/16/2017(Access) |  |  | 06/27/2017 (24635560) 06/23/2017 (24635561) | 07/14/2017 07/20/2017 | 06/16/2017 |  | Activated/Installed | N (24635560) N (24635562) N (24635561) | U0101953 |  | NSPE0011250358 Order Request # 194155653 | NSPE0011250358
Completed | WEST LAKE HILLS TX | 1250 S CAPITAL OF TEXAS HWY WEST LAKE HILLS, TX 78746 USA | 1.536 MBPS (OQBLHV8M) 1.536 MBPS (IQBLHV3F) | 11/22/2017: 11/21 Successfully activated | 9186364 |  | Private IP (OQBLHV8M) Private IP (IQBLHV3F) EVC/PVC Service (C.11431880.3374298) | OQBLHV8M IQBLHV3F C.11431880.3374298 | 3.072 MBPS 6.144 MBPS | P1885545 P2168687 |  | BCBKNYRH0001 (OQBLHV8M) BCBKNYRH0002 (OQBLHV8M) BCBLBY4J0001 (IQBLHV3F) BCBLBY4J0002 (IQBLHV3F) BCBLBY4J0003 (IQBLHV3F) BCBLBY4J0004 (IQBLHV3F) | 32/HCGS/697169//SW (IQBLHV3FNXEWMB01) 32/HCGS/686597//SW (IQBLHV3FNXEWMB02) | 3374298 | 2752 2475 | VPN Name : UnitedHealthGroup Router Name : IAE3E02 VRF Name : V311110-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65102 PE IP Address : 68.136.67.41 CE Address : 68.136.67.42 QoS - Egress Profile: R12 PVC ID : 3374298 |  |  |  | SW BELL - SAN ANTONIO ATT (IQBLHV3FNXEWMB01) ATT (IQBLHV3FNXEWMB02) | 06/16/2017 (IQBLHV3FNXEWMB01) 06/16/2017 (IQBLHV3FNXEWMB02) | 06/23/2017 (IQBLHV3FNXEWMB01) 06/23/2017 (IQBLHV3FNXEWMB02) | 06/23/2017 (IQBLHV3FNXEWMB01) 06/23/2017 (IQBLHV3FNXEWMB02) |  |  | NEW PORT: BCBLBY4J0003: T6M.3B.0.8.6.1 BCBLBY4J0004: T6M.3B.0.8.7.1 NMT COMMANDS: N/A CKT PREPPED IN PLC: YES HYP MUX MSGS: BCBLBY4J0003: RVRP630 BCBLBY4J0004: RVRP634 HYP TICKETS: N/A LIFT AND LAY REQUEST MADE: N/A CKT PROVISIONED IN VDDS: PROVISIONED VDDS INFO: Site IAE DXC AA1309WBD Switch Name IAE3E02 |  | KIM HOWELL KRISTI AMANN 0015123472670 0015123281211 5123472625 KRISTINE_AMANN@UHC.COM |  |  |  | 11/22/2017 (OQBLHV8M) 11/22/2017 (IQBLHV3F) | 11/21/2017 |  | 11/29/2017 (OQBLHV8M) 11/29/2017 (IQBLHV3F) | 11/29/2017 (OQBLHV8M) 11/29/2017 (IQBLHV3F) |  |  |  | N (OQBLHV8M) N (IQBLHV3F) N (C.11431880.3374298) | 05017789 05650532 P2168687 |  | NSPE0011262050 CW 194163279 | NSPE0011262050
Completed | FL218-01-IM Doral FL | 7765 NW 48TH ST DORAL, FL 33166-5404 US | 4.6 MBPS (24679420) | 07/27/2017: 07/27 - Background: FL218-01-IM Doral FL; New 4.608, 3xT1 MLPPP; South Bell; No NID; No MNS; Status: Testing complete. Ready for activation/Plug and play. Next action: Activation. Who owns the next action: Customer Ticket: NA | 194180809 | FL218-01-IM Doral FL | Private IP - PIP (24679419) WAN Analysis Reporting (24679421) Access (24679420) | 24679419 24679421 24679420 | 4.6 MBPS (24679419) |  | 174309320 (Private IP (PIP)) 174309321 (WAN Analysis Reporting) 174309318 (Access) | C0123255/ADD (24679419) N1037172/ADD (24679420) N1037174/ADD (24679420) N1037173/ADD (24679420) | 60/HCGS/476203//SB (2467942025585501) 60/HCGS/476204//SB (2467942025585501) | 5884274 | 2500 | PVC ID : 5884274 VPN Name : UnitedHealthGroup Router Name : POB3E02 VRF Name : V368211-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64696 PE IP Address : 152.177.113.141 CE Address : 152.177.113.142 QoS - Egress Profile: R12 |  | DS1 (24679420) | TDM | ATT (2467942025585501) | 06/15/2017 (2467942025585501) | 06/28/2017 (2467942025585501) | 07/24/2017 (2467942025585501) |  |  | DEMARCDET - 60/HCGS/476202//SB- DEMARC: 3 rd west telco cabinet 1 slot 2 rj48c tag not extended |  | ROBERT BARR 1-706-268-3427 robert_barr@uhg.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 07/24/2017(Private IP - PIP) 07/24/2017(WAN Analysis Reporting) 07/24/2017(Access) |  |  | 08/11/2017 (24679419) 08/09/2017 (24679420) | 08/09/2017 08/15/2017 | 07/24/2017 |  | Activated/Installed | N (24679419) N (24679421) N (24679420) | U0101953 | Jeopardy Notification 3 (07/14/2017) | NSPE0011268488 Order Request # 194177814 | NSPE0011268488
Completed | C1559-05-IJ Catamaran Elk Grove Village IL | 2425 BUSSE RD ELK GROVE VILLAGE, IL 60007-5737 US | 1 GBPS | 07/25/2017: 07/10 Successfully upgraded. | 194206202 | C1559-05-IJ Catamaran Elk Grove Village, IL | Private IP - PIP (24740391) Access | 24740391 | 1 GBPS (24740391) |  | 79950007 (Private IP (PIP)) 79950005 | C0064222/NONE (24740391) |  | 5650006 | 140000 | PVC ID : 5650006 VPN Name : UnitedHealthGroup Router Name : RVDL9E01 VRF Name : V550197:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64721 PE IP Address : 147.225.8.37 CE Address : 147.225.8.38 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Brian Ladd 1-331-223-7121 brian.ladd@optum.com | STEVE BROWN | skbrown1@optum.com | 1-763-694-7333 | 07/20/2017(Private IP | 07/10/2017 |  | 06/15/2017 (24740391) | 06/26/2017 | 07/20/2017 |  |  | N (24740391) N | U0101953 |  | NSPE0011288009 Order Request # 194203392 | NSPE0011288009
Completed | COLOGNE MN | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 6000 MBPS (CQBLHX5G) | 08/07/2017: 07/27 Successfully upgraded | 9195658 |  | Private IP Port Only (CQBLHX5G) | CQBLHX5G | 7000 MBPS | P1957529 |  | BOBKWHD00001 (CQBLHX5G) |  | 5212870 5417303 5212868 5463422 5841773 5763658 | 0 | PVC ID : 5212870,5417303,5212868,5463422,5841773,5763658 VPN Name : UnitedHealthGroup-ECCMA Router Name : MZZ9E01 VRF Name : V600584:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : 152.161.80.1 CE Address : 152.161.80.2 QoS - Egress Profile: R12 | [11 empty] | ED ED 0017637442081 EDWARD.MCLAUGHLIN@OPTUM.COM |  |  |  | 07/27/2017 (CQBLHX5G) | 07/27/2017 |  | 08/03/2017 (CQBLHX5G) | 08/03/2017 (CQBLHX5G) |  |  |  | N (CQBLHX5G) | 05017789 |  | NSPE0011307849
| MINNEAPOLIS MN | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 6000 MBPS (CQBLHX5J) | 08/28/2017: 08/25 Successfully upgraded | 9195698 |  | Private IP Port Only (CQBLHX5J) | CQBLHX5J | 7000 MBPS 7000 MBPS (CQBLHX5J) | P1932463 |  | BOBKTFPX0001 (CQBLHX5J) |  | 5605731 5463424 5189840 5761097 5189860 | 360000 270000 314000 2688 1500000 | PVC ID : 5605731,5463424,5189840,5761097,5189860 VPN Name : UHG-ECC,UHG-UC,UHG-IPTF,UnitedHealthGroup-ECCMA,UnitedHealthGroup Router Name : MN39E01 VRF Name : V594781:UHGECC,V645094:UHGUC,V601668:UHGIPTF,V601670:UnitedHealthGroupECCMA,V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : v4-152.177.151.97,v6-199.220.202.221,v4-152.187.248.73,v6-68.136.152.241,v4-152.162.11.193 CE Address : v4-152.177.151.98,v6-199.220.202.222,v4-152.187.248.74,v6-68.136.152.242,v4-152.162.11.194 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/28/2017 (CQBLHX5J) | 08/25/2017 |  | 07/19/2017 (CQBLHX5J) | 07/19/2017 (CQBLHX5J) |  |  |  | N (CQBLHX5J) | 05017789 |  | NSPE0011307849 | NSPE0011307849
| MINNEAPOLIS MN | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 6000 MBPS (CQBLHX71) | 08/09/2017: 08/08 Successfully upgraded | 9195909 |  | Private IP Port Only (CQBLHX71) | CQBLHX71 | 7000 MBPS 7000 MBPS (CQBLHX71) | P1932297 |  | BOBKTD960001 (CQBLHX71) |  | 5212513 5762263 5452983 5209867 5723530 5539402 | 110500 270000 314000 384 360000 1500000 | PVC ID : 5212513,5762263,5452983,5209867,5723530,5539402 VPN Name : UHG-XLHealth,UHG-UC,UHG-IPTF,UnitedHealthGroup-IDN,UHG-ECC,UnitedHealthGroup Router Name : MN3GE01 VRF Name : V594628:UHGXLHealth,V656367:UHGUC,V594624:UHGIPTF,V594626:UnitedHealthGroupIDN,V594627:UHGECC,V594623:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : v4-152.162.46.225,v6-68.137.39.25,v4-152.176.215.13,v6-152.192.111.185,v4-147.225.22.233,v6-152.161.107.161 CE Address : v4-152.162.46.226,v6-68.137.39.26,v4-152.176.215.14,v6-152.192.111.186,v4-147.225.22.234,v6-152.161.107.162 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017636947333 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/08/2017 (CQBLHX71) |  |  | 07/19/2017 (CQBLHX71) | 07/19/2017 (CQBLHX71) |  |  |  | N (CQBLHX71) | 05017789 |  | NSPE0011307849 | NSPE0011307849
| COLOGNE MN | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 6000 MBPS (CQBLHYBC) | 08/30/2017: 08/29 Successfully upgraded | 9195917 |  | Private IP Port Only (CQBLHYBC) | CQBLHYBC | 7000 MBPS | P1955436 |  | BOBKWCW20001 (CQBLHYBC) |  | 5762254 5210727 5538820 5210728 | 24576 | PVC ID : 5762254,5210727,5538820,5210728 VPN Name : Alere-LLC-WAN Router Name : MZZGE01 VRF Name : Vg35543:AlereLLCWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : 152.176.170.69 CE Address : 152.176.170.70 QoS - Egress Profile: R12 | [11 empty] | MELISSA CHAPMAN 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/29/2017 (CQBLHYBC) | 08/29/2017 |  | 07/19/2017 (CQBLHYBC) | 07/19/2017 (CQBLHYBC) |  |  |  | N (CQBLHYBC) | 05017789 |  | NSPE0011307849 | NSPE0011307849
| BOTHELL WA | 20021 120TH AVE NE BOTHELL, WA 98011 USA | 1.536 MBPS (CQBLH0WJ) | 08/09/2017: 08/08 Successfully activated | 9209105 |  | Private IP (CQBLH0WJ) | CQBLH0WJ | 12.288 MBPS | P2165056 |  | BCBLBTRP0001 (CQBLH0WJ) BCBLBTRP0002 (CQBLH0WJ) BCBLBTRP0003 (CQBLH0WJ) BCBLBTRP0004 (CQBLH0WJ) BCBLBTRP0005 (CQBLH0WJ) BCBLBTRP0006 (CQBLH0WJ) BCBLBTRP0007 (CQBLH0WJ) BCBLBTRP0008 (CQBLH0WJ) |  |  | 1536 | VPN Name : UnitedHealthGroup Router Name : SEJGE02 VRF Name : V264785:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65282 PE IP Address : v4-152.161.29.245,v6-2600:810:600:0:0:0:0:e319 CE Address : v4-152.161.29.246,v6-2600:810:600:0:0:0:0:e31a QoS - Egress Profile: R12 | [9 empty] | LEC Circuit ID: 86/HCGS/484089//FTNC/ Circuit ID: P2165056 BCBLBTRP0001 DEMARC LOC: SLOT: 01=0A SHELF: 02=0A PORT: 01=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0002 DEMARC LOC: SLOT: 02=0A SHELF: 02=0A PORT: 02=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0003 DEMARC LOC: SLOT: 03=0A SHELF: 02=0A PORT: 02=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0004 DEMARC LOC: SLOT: 04=0A SHELF: 02=0A PORT: 04=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0005 DEMARC LOC: SLOT: 05=0A SHELF: 02=0A PORT: 05=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0006 DEMARC LOC: SLOT: 06=0A SHELF: 02=0A PORT: 06=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0007 DEMARC LOC: SLOT: 05=0A SHELF: 02=0A PORT: 05=0A PHYS LOC: MPOE 1ST FLOOR BCBLBTRP0008 DEMARC LOC: SLOT: 08=0A SHELF: 02=0A PORT: 08=0A PHYS LOC: MPOE 1ST FLOOR |  | DAVE LOWRY 0014256861202 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 08/08/2017 (CQBLH0WJ) |  |  | 08/07/2017 (CQBLH0WJ) | 08/10/2017 (CQBLH0WJ) |  |  |  | N (CQBLH0WJ) | 05650532 |  |  | NSPE0011136498
Completed | Sitel Operating Corporation | 5601 N 103RD ST OMAHA, NE 68134-1006 US | 100 MBPS (24904537) | 08/30/2017: 08/30 Ready for Activation. Customer notified. | 194281235 | Sitel Operating Corporation | Private IP - PIP (24904536) WAN Analysis Reporting (24904538) Access (24904537) | 24904536 24904538 24904537 | 50 MBPS (24904536) |  | 178392413 (Private IP (PIP)) 178392414 (WAN Analysis Reporting) 178392411 (Access) | C1056902/ADD (24904536) E4021626/ADD (24904537) | 21.KFGX.000615..COXC. (2490453726284201) | 5893415 | 25000 | PVC ID : 5893415 VPN Name : UHG-ECC Router Name : PLSHXE01 VRF Name : V449266-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65504 PE IP Address : 152.162.176.173 CE Address : 152.162.176.174 QoS - Egress Profile: C13 | 1000Base-T (24904537) | 1000Base-T (24904537) | Ethernet | COX (2490453726284201) | 08/21/2017 (2490453726284201) | 08/31/2017 (2490453726284201) |  | 08/29/2017 (VFORCE) (24904537) | 08/29/2017 (VFORCE) (24904537) | DEMARCDET - 1st flr data rm rack no. 8 Accedian Nid shelf 1 slot 2 port 3 |  | Tim Gombold 1-402-963-6035 tim.gombold@sitel.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/29/2017(Private IP - PIP) 08/29/2017(WAN Analysis Reporting) 08/29/2017(Access) |  |  | 09/12/2017 (24904536) 09/08/2017 (24904537) | 10/02/2017 10/06/2017 | 08/29/2017 |  | Activated/Installed | N (24904536) N (24904538) N (24904537) | U0101953 | Jeopardy Notification 3 (08/18/2017) | NSPE0011340359 Order Request # 194280541 | NSPE0011340359
Completed | C1530-08-IJ DALLAS TX | 11830 WEBB CHAPEL RD STE 200 DALLAS, TX 75234-2784 US | 100 MBPS (24905485) | 09/29/2017: 09/29 Successfully activated | 194282052 | C1530-08-IJ | Private IP - PIP (24905484) WAN Analysis Reporting (24905486) Access (24905485) | 24905484 24905486 24905485 | 50 MBPS (24905484) |  | 178400076 (Private IP (PIP)) 178400077 (WAN Analysis Reporting) 178400074 (Access) | C1056905/ADD (24905484) E4021629/ADD (24905485) |  | 5893544 | 25000 | PVC ID : 5893544 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65509 PE IP Address : 152.164.45.245 CE Address : 152.164.45.246 QoS - Egress Profile: C13 |  | 1000Base-LX (1310nm Single Mode Fiber) (24905485) | Ethernet |  |  |  |  | 07/31/2017 (CCP) (24905484) 07/31/2017 (CCP) (24905485) | 08/02/2017 (CCP) (24905484) 08/02/2017 (CCP) (24905485) | Verizon cage at C-08-21 SM ports 43 and 44 |  | Tim Gombold 1-402-963-6035 tim.gombold@sitel.com | Matthew Adams | matthew_adams@optum.com | 1-763-553-4616 | 08/09/2017(Private IP - PIP) 08/09/2017(WAN Analysis Reporting) 08/09/2017(Access) | 09/29/2017 |  | 08/18/2017 (24905484) 08/16/2017 (24905485) | 08/16/2017 08/22/2017 | 08/09/2017 |  | Activated/Installed | N (24905484) N (24905486) N (24905485) | U0101953 | Jeopardy Notification 2 (08/02/2017) | NSPE0011340648 Order Request # 194280967 (QOS to C13 via ivue) | NSPE0011340648
Completed | MA008-02-IJ Boston MA | 1325 BOYLSTON ST BOSTON, MA 02215-3909 US | 200 MBPS (24942379) | 01/16/2018: 01/12 Successfully activated | 194289539 | MA008-02-IJ Boston MA | Private IP - PIP (24942378) WAN Analysis Reporting (24942380) Access (24942379) | 24942378 24942380 24942379 | 150 MBPS (24942378) |  | 178638278 (Private IP (PIP)) 178638279 (WAN Analysis Reporting) 178638276 (Access) | C5003389/ADD (24942378) E5007381/ADD (24942379) | 95.KFGS.007479..NE (2494237912749601) | 5897279 | 70000 | PVC ID : 5897279 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64705 PE IP Address : 152.177.161.53 CE Address : 152.177.161.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24942379) | 1000Base-SX (850nm, Multi Mode Fiber) (24942379) | Ethernet | VERIZON (2494237912749601) | 08/02/2017 (2494237912749601) | 08/04/2017 (2494237912749601) | 08/03/2017 (2494237912749601) |  |  | DEMARCADDR - 1325 BOYLSTON, BOS, MA DEMARCDET - 9TH FLR SERVER ROOM WALL MOUNTED NOT EXTENDED TAGGGED |  | DOUG DOWNIE 1-781-420-0830 douglas_downie@uhg.com | LAEEQ SAJJAD | laeeq_sajjad@optum.com | 1-312-617-5537 | 08/03/2017(Private IP - PIP) 08/03/2017(WAN Analysis Reporting) 08/03/2017(Access) | 01/12/2018 |  | 08/10/2017 (24942378) 08/08/2017 (24942379) | 08/15/2017 08/21/2017 | 08/03/2017 |  | Activated/Installed | N (24942378) N (24942380) N (24942379) | U0101953 |  | NSPE0011375369 Order Request # 194286984 | NSPE0011375369
Completed | UKS08-09-10 Overland Park KS | 6860 W 115TH ST OVERLAND PARK, KS 66211-2457 US | 250 MBPS (24978742) | 09/29/2017: 09/28 Successfully activated | 194331430 | UNITED HEALTH GROUP | Private IP - PIP (24978741) WAN Analysis Reporting (24978743) Access (24978742) | 24978741 24978743 24978742 | 150 MBPS (24978741) |  | 180321432 (Private IP (PIP)) 180321433 (WAN Analysis Reporting) 180321430 (Access) | C0126299/ADD (24978741) E0001946/ADD (24978742) | 74/KRGN/905056//SW (2497874225704802) | 5899251 | 15000 | PVC ID : 5899251 VPN Name : UnitedHealthGroup Router Name : IDCXE03 VRF Name : V560358-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64905 PE IP Address : 152.176.67.225 CE Address : 152.176.67.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24978742) | 1000Base-SX (850nm, Multi Mode Fiber) (24978742) | Ethernet | ATT (2497874225704802) | 07/24/2017 (2497874225704802) | 08/08/2017 (2497874225704802) | 08/08/2017 (2497874225704802) | 08/11/2017 (VFORCE) (24978742) | 08/11/2017 (VFORCE) (24978742) | DEMARCADDR - 8686 W COLLEGE BLVD KANSAS CITY KS DEMARCDET - MDF RM,BCU RACK 2,RU 34,PNL1, POS 7/8 |  | John Sanburg 1-913-253-0859 john.sanburg@optum.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 08/11/2017(Private IP - PIP) 08/11/2017(WAN Analysis Reporting) 08/11/2017(Access) | 09/28/2017 |  | 08/17/2017 (24978741) 08/15/2017 (24978742) | 08/31/2017 09/07/2017 | 08/11/2017 |  | Activated/Installed | N (24978741) N (24978743) N (24978742) | U0101953 |  | NSPE0011404743 Order Request # 194330847 | NSPE0011404743
Completed | UNJ08-05-IJ Basking Ridge | 131 MORRISTOWN RD BASKING RIDGE, NJ 07920-1654 US | 500 MBPS (25159925) | 07/03/2018: 07/02 Successfully activated | 194369648 | UNJ08-05-IJ Basking Ridge | Private IP - PIP (25159924) WAN Analysis Reporting (25159926) Access (25159925) | 25159924 25159926 25159925 | 400 MBPS (25159924) |  | 182400450 (Private IP (PIP)) 182400451 (WAN Analysis Reporting) 182400448 (Access) | C5003520/ADD (25159924) E5007730/ADD (25159925) | .KFGS.309404..NJ (2515992599390401) | 5909134 | 50000 | PVC ID : 5909134 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64541 PE IP Address : 152.176.157.25 CE Address : 152.176.157.26 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25159925) | 1000Base-SX (850nm, Multi Mode Fiber) (25159925) | Ethernet | VERIZON (2515992599390401) | 08/16/2017 (2515992599390401) | 08/28/2017 (2515992599390401) | 08/25/2017 (2515992599390401) |  |  | DEMARCADDR - 131 MORRISTOWN RD, BERND TWP, NJ DEMARCDET - FLOOR 1 MAIN TELCO ROOM RACK MOUNT POS #1 TAGGED |  | Ed Naugin 1-908-696-2665 ed_naugin@optum.com | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 08/25/2017(Private IP - PIP) 08/25/2017(WAN Analysis Reporting) 08/25/2017(Access) | 07/02/2018 |  | 09/07/2017 (25159924) 09/05/2017 (25159925) | 09/13/2017 09/19/2017 | 08/25/2017 |  | Activated/Installed | N (25159924) N (25159926) N (25159925) | U0101953 |  | NSPE0011431883 Order Request # 194367674 | NSPE0011431883
Completed | UCA9Z-02-IM UHG-MSLA Cypress CA | 5995 PLAZA DR CYPRESS, CA 90630-5028 US | 500 MBPS (25040550) | 10/20/2017: 10/20 Background: UCA9Z-02-IM UHG-MSLA Cypress, CA; New 150M/500M PIP-E; VzB; Colo; NID; No MS; Status: Ready for activation. Customer notified. Circuit ID: E5007574 Demarc: rack 1.01 fiber panel ports 1 & 2 on 4th floor computor room | 194369851 | UCA9Z-02-IM UHG-MSLA Cypress, CA | Access (25040550) Private IP - PIP (25040549) WAN Analysis Reporting (25040551) | 25040550 25040549 25040551 | 150 MBPS (25040549) |  | 182550286 (Access) 182550288 (Private IP (PIP)) 182550289 (WAN Analysis Reporting) | E5007574/ADD (25040550) C5003461/ADD (25040549) |  | 5903974 | 1000 | PVC ID : 5903974 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65287 PE IP Address : 206.115.23.17 CE Address : 206.115.23.18 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (25040550) | Ethernet |  |  |  |  | 10/23/2017 (CCP) (25040550) 10/23/2017 (CCP) (25040549) | 10/14/2017 (CCP) (25040550) 10/14/2017 (CCP) (25040549) |  |  | Adela Kaba 1-714-820-1286 a.kaba@mslaca.com | RANJIT ADHIKARI | ranijt_adhikari@optum.com | 1-763-744-1957 | 10/19/2017(Access) 10/19/2017(Private IP - PIP) 10/19/2017(WAN Analysis Reporting) |  |  | 11/22/2017 (25040550) 11/28/2017 (25040549) | 09/13/2017 09/19/2017 | 10/19/2017 |  | Activated/Installed | N (25040550) N (25040549) N (25040551) | U0101953 |  | NSPE0011433238 Order Request # 194369498 | NSPE0011433238
Completed | NY432-02-IM Syracuse NY | 2425 JAMES ST SYRACUSE, NY 13206-2821 US | 200 MBPS (25276002) | 10/26/2017: 10/26 Background: NY432-02-IM Syracuse NY; New 100M/200M PIP-E; VzT; No NID; No MNS Status: ready for Activation. LEC Circuit ID: 36.KFGS.213637..NY Demarc: 2425 JAMES ST SYRACUSE NY 13206-2821; GROUND FLOOR DATA CENTER REAR WALL MOUNTED MOUNTING#1/1 PORT 1/1 TAGGED WITH CIRCUIT ID 36.KFGS.213637..NY | 194391633 | NY432-02-IM | Private IP - PIP (25276001) WAN Analysis Reporting (25276003) Access (25276002) | 25276001 25276003 25276002 | 100 MBPS (25276001) |  | 183243400 (Private IP (PIP)) 183243404 (WAN Analysis Reporting) 183243398 (Access) | C5003603/ADD (25276001) E5007976/ADD (25276002) | 36.KFGS.213637..NY (2527600227127301) | 5914791 | 50000 | PVC ID : 5914791 VPN Name : UnitedHealthGroup Router Name : SRDXE01 VRF Name : V699748-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64637 PE IP Address : 199.220.164.65 CE Address : 199.220.164.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25276002) | 1000Base-SX (850nm, Multi Mode Fiber) (25276002) | Ethernet | VERIZON (2527600227127301) | 09/06/2017 (2527600227127301) | 10/25/2017 (2527600227127301) | 10/25/2017 (2527600227127301) |  |  | DEMARCADDR - 2425 JAMES ST SYRACUSE NY 13206-2821 DEMARCDET - GROUND FLOOR DATA CENTER REAR WALL MOUNTED MOUNTING#1/1 PORT 1/1 TAGGED WITH CIRCUIT ID 36.KFGS.213637..NY |  | Ed Christopher 1-315-432-9171 echristo@pomco.com | SONJA MROCZYNSKI | sonja_d_mroczynski@optum.com | 1-612-632-6919 | 10/25/2017(Private IP - PIP) 10/25/2017(WAN Analysis Reporting) 10/25/2017(Access) |  |  | 11/03/2017 (25276001) 11/01/2017 (25276002) | 11/15/2017 11/21/2017 | 10/25/2017 |  | Completed | N (25276001) N (25276003) N (25276002) | U0101953 |  | NSPE0011446803 Order Request # 194391491 | NSPE0011446803
Completed | CT123-02-IM WALLINGFORD CT | 33 N PLAINS INDUSTRIAL RD STE B WALLINGFORD, CT 06492-5841 US | 3 MBPS (25099089) | 08/29/2017: 08/29 Ready for Activation. Customer notified. | 194395795 | CT123-02-IM | Access (25099089) Private IP - PIP (25099088) WAN Analysis Reporting (25099090) | 25099089 25099088 25099090 | 3 MBPS (25099088) |  | 183252193 (Access) 183252195 (Private IP (PIP)) 183252196 (WAN Analysis Reporting) | N1037917/ADD (25099089) N1037916/ADD (25099089) C1057918/ADD (25099088) | FA/HCGS/634083//SN/ (2509908927129701) 133dn 67u 0069 (I0002082.BRP) 133dn 67u 0068 (I0002082.BRP) | 5906536 | 1500 | PVC ID : 5906536 VPN Name : UnitedHealthGroup Router Name : HLBGE02 VRF Name : Va29344:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65237 PE IP Address : 147.225.101.81 CE Address : 147.225.101.82 QoS - Egress Profile: R12 |  | DS1 (25099089) | TDM | FRONTIER (2509908927129701) | 08/10/2017 (2509908927129701) | 08/21/2017 (2509908927129701) 08/31/2017 (I0002082.BRP) | 08/28/2017 (2509908927129701) |  |  | DEMARCADDR - 33 N PLAINS INDUSTRIAL RD BLDG MAIN, FL FIRST, STE B DEMARCDET - 7PCK, SLOT6 |  | Tracy Rowland 1-817-677-2517 tracy_rowland@uhg.com | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 08/28/2017(Access) 08/28/2017(Private IP - PIP) 08/28/2017(WAN Analysis Reporting) |  |  | 08/24/2017 (25099089) 08/28/2017 (25099088) | 08/31/2017 09/07/2017 | 08/28/2017 |  | Activated/Installed | N (25099089) N (25099088) N (25099090) | U0101953 |  | NSPE0011447910 Order Request # 194393343 | NSPE0011447910
Completed | IL090-02-IM DOWNERS GROVE IL | 2655 WARRENVILLE RD DOWNERS GROVE, IL 60515-5555 US | 250 MBPS (25099540) | 11/28/2017: 11/28 Activation successful | 194396099 | IL090-02-IM | Private IP - PIP (25099539) WAN Analysis Reporting (25099541) Access (25099540) | 25099539 25099541 25099540 | 100 MBPS (25099539) |  | 183362926 (Private IP (PIP)) 183362927 (WAN Analysis Reporting) 183362924 (Access) | C0127060/ADD (25099539) E0002724/ADD (25099540) | /KRGN/117268//LB (2509954027149001) | 5906579 | 18000 | PVC ID : 5906579 VPN Name : UnitedHealthGroup Router Name : RVDL9E01 VRF Name : V550197:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64948 PE IP Address : 68.138.15.165 CE Address : 68.138.15.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25099540) | 1000Base-SX (850nm, Multi Mode Fiber) (25099540) | Ethernet | ATT (2509954027149001) | 08/09/2017 (2509954027149001) | 08/24/2017 (2509954027149001) | 08/22/2017 (2509954027149001) | 08/23/2017 (VFORCE) (25099540) | 08/23/2017 (VFORCE) (25099540) | DEMARCDET - 1ST FLOOR TELCO ROOM BAY 4 CIENNA 3930 PORT 5 TAGGED WITH CIRCUIT ID |  | Jan Bicicchi 1-630-725-2310 jan_bicicchi@uhg.com | LESLIE ISAAC | leslie.isaac@optum.com | 44-186-578-7320 | 08/23/2017(Private IP - PIP) 08/23/2017(WAN Analysis Reporting) 08/23/2017(Access) | 11/28/2017 |  | 09/05/2017 (25099539) 08/31/2017 (25099540) | 09/20/2017 09/26/2017 | 08/23/2017 |  | Activated/Installed | N (25099539) N (25099541) N (25099540) | U0101953 |  | NSPE0011449290 Order Request # 194395602 | NSPE0011449290
Completed | UVA04-09-IM Roanoke VA | 3645 THIRLANE RD NW ROANOKE, VA 24019-3000 US | 200 MBPS (25223190) | 02/02/2018: 02/01 Successfully activated | 194397376 | UVA04-09-IM Roanoke, VA | WAN Analysis Reporting (25223191) Access (25223190) Private IP - PIP (25223189) | 25223191 25223190 25223189 | 100 MBPS (25223189) |  | 183440224 (WAN Analysis Reporting) 183440181 (Access) 183440183 (Private IP (PIP)) | C5003561/ADD (25223189) E5007846/ADD (25223190) | 44.KFGS.303803..CV (2522319027161601) | 5912089 | 40000 | PVC ID : 5912089 VPN Name : UnitedHealthGroup Router Name : RIJ3E06 VRF Name : Va31643-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64759 PE IP Address : 147.225.249.113 CE Address : 147.225.249.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25223190) | 1000Base-SX (850nm, Multi Mode Fiber) (25223190) | Ethernet | VERIZON (2522319027161601) | 08/28/2017 (2522319027161601) | 09/08/2017 (2522319027161601) | 09/13/2017 (2522319027161601) |  |  | DEMARCADDR - 3645 THIRLANE RD NW, ROANOKE, VA DEMARCDET - GND,,RM 122,TEL RM,,SFP,LP Y,CAB N,,RCK,1,POS,44, |  | Gary Brown 1-540-777-9924 gbrow15@corpimsvcs.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 09/13/2017(WAN Analysis Reporting) 09/13/2017(Access) 09/13/2017(Private IP - PIP) | 02/02/2018 |  | 10/04/2017 (25223189) 10/02/2017 (25223190) | 10/06/2017 10/02/2017 | 09/13/2017 |  | Activated/Installed | N (25223191) N (25223190) N (25223189) | U0101953 |  | NSPE0011450280 Order Request # 194397100 | NSPE0011450280
Completed | TX356-04-IJ MESQUITE TX | 200 W KEARNEY ST MESQUITE, TX 75149 USA | 1.536 MBPS (IQBLJG24) | 09/01/2017: 09/01 Background: TX356-04-IJ MESQUITE, TX; NEW 10.752M 7XT1 PIP MLPPP; NO NID; NO MS; Status: Ready for Activation Next action: Customer to plug and play Who owns the next action: Customer Ticket: NA | 9259431 |  | Private IP (IQBLJG24) | IQBLJG24 | 10.752 MBPS | P2173723 |  | BCBLB5810001 (IQBLJG24) BCBLB5810002 (IQBLJG24) BCBLB5810003 (IQBLJG24) BCBLB5810004 (IQBLJG24) BCBLB5810005 (IQBLJG24) BCBLB5810006 (IQBLJG24) BCBLB5810007 (IQBLJG24) | 14/HCGS/161208//SW (IQBLJG242FHWMB01) |  | 5000 | VPN Name : UnitedHealthGroup Router Name : IAEGE01 VRF Name : V112379:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64617 PE IP Address : 68.139.182.81 CE Address : 68.139.182.82 QoS - Egress Profile: R12 |  |  |  | ATT (IQBLJG242FHWMB01) | 08/17/2017 (IQBLJG242FHWMB01) | 08/28/2017 (IQBLJG242FHWMB01) | 08/29/2017 (IQBLJG242FHWMB01) |  |  |  |  | JASON OZER 0012103919106 JCRANE@WELLMED.NET |  |  |  | 08/29/2017 (IQBLJG24) |  |  | 09/05/2017 (IQBLJG24) | 09/11/2017 (IQBLJG24) |  |  |  | N (IQBLJG24) | 05650532 |  | NSPE0011455384 CW 194396908; | NSPE0011455384
Completed | LA010-02-IJ BATON ROUGE LA | 11211 INDUSTRIPLEX BLVD BATON ROUGE, LA 70809-4177 US | 50 MBPS (25162391) | 11/20/2017: 11/20 Customer confirms circuit is up | 194418918 | LA010-02-IJ | Private IP - PIP (25162390) WAN Analysis Reporting (25162392) Access (25162391) | 25162390 25162392 25162391 | 10 MBPS (25162390) |  | 183728407 (Private IP (PIP)) 183728408 (WAN Analysis Reporting) 183728405 (Access) | C4008329/ADD (25162390) E4022562/ADD (25162391) | 24.KFGX.000151..COXC. (2516239127213401) | 5909211 | 7000 | PVC ID : 5909211 VPN Name : UnitedHealthGroup Router Name : NWO2GE01 VRF Name : V486980:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65229 PE IP Address : 152.183.86.37 CE Address : 152.183.86.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25162391) | 1000Base-SX (850nm, Multi Mode Fiber) (25162391) | Ethernet | COX (2516239127213401) | 10/06/2017 (2516239127213401) | 11/09/2017 (2516239127213401) |  | 10/23/2017 (VFORCE) (25162391) | 10/23/2017 (VFORCE) (25162391) | DEMARCDET - . . . . . . |  | Jason Engel 1-303-594-1125 jason_engel@uhg.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 10/23/2017(Private IP - PIP) 10/23/2017(WAN Analysis Reporting) 10/23/2017(Access) | 11/16/2017 |  | 11/20/2017 (25162390) 11/16/2017 (25162391) | 10/25/2017 10/31/2017 | 10/23/2017 |  | Completed | N (25162390) N (25162392) N (25162391) | U0101953 | Jeopardy Notification 2 (09/19/2017) | NSPE0011515174 Order Request # 194418347 | NSPE0011515174
Completed | CA013-02-IJ UHG-Monarch Irvine CA | 7 TECHNOLOGY DR IRVINE, CA 92618-2302 US | 500 MBPS (25173143) | 10/09/2017: 10/06 Successfully activated | 194423573 | CA013-02-IJ UHG - Monarch Irvine | WAN Analysis Reporting (25173144) Access (25173143) Private IP - PIP (25173142) | 25173144 25173143 25173142 | 300 MBPS (25173142) |  | 184240716 (WAN Analysis Reporting) 184240713 (Access) 184240715 (Private IP (PIP)) | C5003527/ADD (25173142) E5007751/ADD (25173143) | 12.KFGX.000522..COXC. (2517314381411201) | 5909651 | 250000 | PVC ID : 5909651 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65010 PE IP Address : 152.187.185.57 CE Address : 152.187.185.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25173143) | 1000Base-SX (850nm, Multi Mode Fiber) (25173143) | Ethernet | COX (2517314381411201) | 08/17/2017 (2517314381411201) | 09/12/2017 (2517314381411201) |  | 09/13/2017 (VFORCE) (25173143) | 09/13/2017 (VFORCE) (25173143) | DEMARCDET - 1st floor MDF on the panel port 5 and 6 accendian nid port 3 untagged VLAN labelled with CKT ID |  | AMIR SEMNANIAN 1-949-923-3392 asemnanian@mhealth.com | RANJIT ADHIKARI | ranijt_adhikari@optum.com | 1-763-744-1957 | 09/13/2017(WAN Analysis Reporting) 09/13/2017(Access) 09/13/2017(Private IP - PIP) | 10/06/2017 |  | 09/21/2017 (25173142) 09/19/2017 (25173143) | 10/04/2017 09/28/2017 | 09/13/2017 |  | Activated/Installed | N (25173144) N (25173143) N (25173142) | U0101953 |  | NSPE0011519243 Order Request # 194423119 | NSPE0011519243
Completed | TX261-02-IM Corpus Christi TX | 13725 NORTHWEST BLVD STE A CORPUS CHRISTI, TX 78410-5124 US | 50 MBPS (25179995) | 04/06/2018: 04/06 Circuit is up and running. Confirmed by customer. | 194427434 | TX261-02-IM | Private IP - PIP (25179994) WAN Analysis Reporting (25179996) Access (25179995) | 25179994 25179996 25179995 | 10 MBPS (25179994) |  | 184156121 (Private IP (PIP)) 184156122 (WAN Analysis Reporting) 184156119 (Access) | C4008363/ADD (25179994) E4022648/ADD (25179995) | 36.L1XX.000831..TWCC (2517999527289701) | 5909946 | 5500 | PVC ID : 5909946 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65228 PE IP Address : 152.187.194.57 CE Address : 152.187.194.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25179995) | 1000Base-SX (850nm, Multi Mode Fiber) (25179995) | Ethernet | TIME WARNER CABLE (2517999527289701) | 02/13/2018 (2517999527289701) | 03/16/2018 (2517999527289701) | 03/12/2018 (2517999527289701) | 03/13/2018 (VFORCE) (25179995) | 03/13/2018 (VFORCE) (25179995) | DEMARCDET - . . . . . . |  | LUIS CASAS 1-956-455-5057 luisecasas@yahoo.com | Jason Salapiong | jason_salaping@gmail.com | 1-210-862-6784 | 03/13/2018(Private IP - PIP) 03/13/2018(WAN Analysis Reporting) 03/13/2018(Access) | 04/02/2018 |  | 03/27/2018 (25179994) 03/23/2018 (25179995) | 03/26/2018 03/30/2018 | 03/13/2018 |  | Completed | N (25179994) N (25179996) N (25179995) | U0101953 | Jeopardy Notification 1 (01/26/2018) | NSPE0011522013 Order Request # 194426903 | NSPE0011522013
Completed | TX064-06-IM HARLINGEN TX | 2222 S 77 SUNSHINESTRIP HARLINGEN, TX 78550-8334 US | 250 MBPS (25185469) | 10/06/2017: 10/05 Activated. Customer confirmed link is stable and no issues. | 194433774 | TX064-06-IM | Private IP - PIP (25185468) WAN Analysis Reporting (25185470) Access (25185469) | 25185468 25185470 25185469 | 100 MBPS (25185468) |  | 184389531 (Private IP (PIP)) 184389532 (WAN Analysis Reporting) 184389529 (Access) | C0128045/ADD (25185468) E0003154/ADD (25185469) | 38/KRGN/613550//SW (2518546912464401) | 5910318 | 25000 | PVC ID : 5910318 VPN Name : UnitedHealthGroup Router Name : HSJ9E04 VRF Name : V622583:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65195 PE IP Address : 147.225.6.169 CE Address : 147.225.6.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25185469) | 1000Base-SX (850nm, Multi Mode Fiber) (25185469) | Ethernet | ATT (2518546912464401) | 08/21/2017 (2518546912464401) | 09/08/2017 (2518546912464401) | 09/08/2017 (2518546912464401) | 09/12/2017 (VFORCE) (25185469) | 09/12/2017 (VFORCE) (25185469) | DEMARCADDR - 2222 S 77 SUNSHINE STRIP HARLINGEN TX DEMARCDET - 1ST FLOOR MDF ROOM, CIENA 3930 RACK MOUNTED UNIT, PORT 5 TAGGED |  | Zulfiker Ali 1-956-734-9236 zulfiker_ali@uhc.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 09/12/2017(Private IP - PIP) 09/12/2017(WAN Analysis Reporting) 09/12/2017(Access) | 10/04/2017 |  | 10/09/2017 (25185468) 10/05/2017 (25185469) | 10/02/2017 10/06/2017 | 09/12/2017 |  | Activated/Installed | N (25185468) N (25185470) N (25185469) | U0101953 |  | NSPE0011522519 Order Request # 194427471 | NSPE0011522519
Completed | VA060-05-IJ Reston VA | 12018 SUNRISE VALLEY DR STE 400 RESTON, VA 20191-3434 US | 50 MBPS (25276927) | 10/02/2017: 10/02 Background: VA060-05-IJ Reston, VA; New 20M/50M PIP-E; VzT; No NID; No MS; Status: Ready for Plug&Play. Customer notified. Demarc: 1st flr, main Telco, wall mounted canoga, tagged. | 194442470 | VA060-05-IJ | Private IP - PIP (25276926) WAN Analysis Reporting (25276928) Access (25276927) | 25276926 25276928 25276927 | 20 MBPS (25276926) |  | 184841312 (Private IP (PIP)) 184841313 (WAN Analysis Reporting) 184841310 (Access) | C4008554/ADD (25276926) E4023158/ADD (25276927) | 36.KFGS.307571..CD (2527692722383201) | 5914821 | 10000 | PVC ID : 5914821 VPN Name : UnitedHealthGroup Router Name : RIJ9E02 VRF Name : Va44559:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65176 PE IP Address : 152.164.34.121 CE Address : 152.164.34.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25276927) | 1000Base-SX (850nm, Multi Mode Fiber) (25276927) | Ethernet | VERIZON (2527692722383201) | 09/06/2017 (2527692722383201) | 10/02/2017 (2527692722383201) | 10/02/2017 (2527692722383201) |  |  | DEMARCADDR - 12018 SUNRISE VALLEY DR, RESTON, VA DEMARCDET - 1ST FLR, MAIN TELCO, WALL MOUNTED CANOGA, TAGGED. |  | Michael O'Neal 1-443-766-3031 michael.oneal@am.jll.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 10/02/2017(Private IP - PIP) 10/02/2017(WAN Analysis Reporting) 10/02/2017(Access) |  |  | 10/11/2017 (25276926) 10/09/2017 (25276927) | 10/19/2017 10/25/2017 | 10/02/2017 |  | Activated/Installed | N (25276926) N (25276928) N (25276927) | U0101953 |  | NSPE0011531258 Order Request # 194442092 | NSPE0011531258
Completed | CO038-02-IM GREENWOOD VILLAGE CO | 8051 E MAPLEWOOD AVE STE 300 GREENWOOD VILLAGE, CO 80111-4742 US | 20 MBPS (25209646) | 10/13/2017: 10/13 Circuit is up and running as per customer. | 194447926 | CO038-02-IM | Private IP - PIP (25209645) WAN Analysis Reporting (25209647) Access (25209646) | 25209645 25209647 25209646 | 10 MBPS (25209645) |  | 183524195 (Private IP (PIP)) 183524196 (WAN Analysis Reporting) 183524193 (Access) | C3014460/ADD (25209645) E3043393/ADD (25209646) | 60.KGGS.003721..CBCL.. (2520964624333301) | 5911431 | 10000 | PVC ID : 5911431 VPN Name : UnitedHealthGroup Router Name : DNVR3E01 VRF Name : V410055-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64773 PE IP Address : 208.219.128.181 CE Address : 208.219.128.182 QoS - Egress Profile: R12 | 100Base-TX (25209646) | 100Base-TX (25209646) | Ethernet | COMCAST (2520964624333301) | 08/25/2017 (2520964624333301) | 10/09/2017 (2520964624333301) | 10/06/2017 (2520964624333301) | 10/09/2017 (VFORCE) (25209646) | 10/09/2017 (VFORCE) (25209646) | DEMARCDET - 3RD FLOOR IDF RACK MOUNTED IN CUSTOMER RACK LABELED WITH THE CKT ID |  | MIKE LANDAUER 1-303-749-1169 mlandauer@cnichs.com | MOHAMMED HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 | 10/09/2017(Private IP - PIP) 10/09/2017(WAN Analysis Reporting) 10/09/2017(Access) | 10/13/2017 |  | 11/08/2017 (25209645) 11/06/2017 (25209646) | 10/06/2017 10/12/2017 | 10/09/2017 |  | Activated/Installed | N (25209645) N (25209647) N (25209646) | U0101953 |  | NSPE0011534937 Order Request 194447128; Comcast Please note used 100Base UNI per Melissa | NSPE0011534937
Completed | UTX43-08-IM Plano TX | 2301 W PLANO PKWY STE 300 PLANO, TX 75075-8436 US | 20 MBPS (25244445) | 10/12/2017: 10/11 Background: UTX43-08-IM Plano, TX; New 10M/ 20M PIP-IDE; Carrier Div: TWC; NID; No MS; Status: Ready for Plug and Play. Customer notified. Next action: Customer to plug and play; or they may call 8628299719 for assistance activating the circuit Who owns the next action: Customer Ticket: NA Demarc: 2nd floor customer data center relay rack number 4 middle of rack labeled | 194469600 | UnitedHealthcare StudentResources | Internet Dedicated Services (25244444) Access (25244445) | 25244444 25244445 | 10 MBPS (25244444) |  | 185094547 (Internet Dedicated Services) 185094583 (Access) | C3014579/ADD (25244444) E3043627/ADD (25244445) | 97.L1XX.003703..TWCC (2524444525383301) | 5913182 | 0 | PVC ID : 5913182 VPN Name : Internet Router Name : GW16DFW9 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 26843 PE IP Address : 157.130.132.53 CE Address : 157.130.132.54 | 100Base-TX (25244445) | 100Base-FX (1310nm, Multi Mode Fiber) (25244445) | Ethernet | TIME WARNER CABLE (2524444525383301) | 08/30/2017 (2524444525383301) | 10/31/2017 (2524444525383301) | 10/06/2017 (2524444525383301) | 10/11/2017 (VFORCE) (25244445) | 10/11/2017 (VFORCE) (25244445) | DEMARCDET - MAIN FLOOR 2ND SUITE 300 PORT 3 ON RAD 203 |  | TODD CALYER 1-214-564-6061 tcalyer@uhcsr.com | Melissa Chapman | melissa.chapman@optum.com | 1-763-744-2114 | 10/11/2017(Internet Dedicated Services) 10/11/2017(Access) | 10/17/2017 |  | 11/09/2017 (25244444) 11/07/2017 (25244445) | 11/20/2017 | 10/11/2017 |  |  | N (25244444) N (25244445) | U0101953 | Jeopardy Notification 1 (10/10/2017) | NSPE0011547427 Order Request # 194467253 | NSPE0011547427
Completed | UMD11-07-IJ Rockville MD | 800 KING FARM BLVD ROCKVILLE, MD 20850-5979 US | 100 MBPS (25497091) | 12/22/2017: 12/22 Successfully activated | 194483110 | UMD11-07 | Private IP - PIP (25497090) WAN Analysis Reporting (25497092) Access (25497091) | 25497090 25497092 25497091 | 50 MBPS (25497090) |  | 190639954 (Private IP (PIP)) 190639955 (WAN Analysis Reporting) 190639952 (Access) | C1061052/ADD (25497090) E4024035/ADD (25497091) | 36.KEGS.321938..CD (2549709122908901) | 5923922 | 10000 | PVC ID : 5923922 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64855 PE IP Address : 152.181.190.57 CE Address : 152.181.190.58 QoS - Egress Profile: R12 | 100Base-TX (25497091) | 100Base-TX (25497091) | Ethernet | VERIZON (2549709122908901) | 10/05/2017 (2549709122908901) | 11/03/2017 (2549709122908901) | 11/02/2017 (2549709122908901) |  |  | DEMARCADDR - 800 KING FARM BLVD, ROCKVILLE, MD DEMARCDET - 6TH FLOOR SUITE 600, ROOM 712 SERVER ROOM, RACK #2 NID#2 |  | Todd Trybus 1-240-632-8127 totrybus@uhc.com | MOHAMMED HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 | 11/02/2017(Private IP - PIP) 11/02/2017(WAN Analysis Reporting) 11/02/2017(Access) | 12/21/2017 |  | 11/16/2017 (25497090) 11/14/2017 (25497091) | 11/14/2017 11/20/2017 | 11/02/2017 |  | Completed | N (25497090) N (25497092) N (25497091) | U0101953 | Jeopardy Notification 2 (11/02/2017) | NSPE0011559440 Order Request # 194482727 | NSPE0011559440
Completed | PR516-02-IM Puerto Rico Guaynabo | 100 CARR 165 GUAYNABO, PR 00968-8047 PR | 50 MBPS (25320806) | 04/17/2018: 04/17 Successfully activated | 194487405 | PR516-02-IM Puerto Rico, Guaynabo | Private IP - PIP (25320805) WAN Analysis Reporting (25320807) Access (25320806) | 25320805 25320807 25320806 | 10 MBPS (25320805) |  | 190071477 (Private IP (PIP)) 190071478 (WAN Analysis Reporting) 190071475 (Access) | C4008767/ADD (25320805) E4023740/ADD (25320806) | SF 154 0066 (25320806PTT00002) SF 154 0066 (25320806PTT00003) | 5916931 | 25000 | PVC ID : 5916931 VPN Name : UnitedHealthGroup Router Name : SNJN9E01 VRF Name : Vc13521:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65216 PE IP Address : 152.176.132.153 CE Address : 152.176.132.154 QoS - Egress Profile: R12 | 100Base-TX (25320806) | 100Base-TX (25320806) | Ethernet | RQCA (25320806PTT00001) RQCL (25320806PTT00002) RQCA (25320806PTT00003) | 01/18/2018 (25320806PTT00002) 01/18/2018 (25320806PTT00003) | 03/26/2018 (25320806PTT00003) | 03/28/2018 (25320806PTT00003) | 03/30/2018 (VFORCE) (25320806) |  | Telco Circuit ID: SF 154 0066 Telco Demarcation: 8th floor, data room 802, Tmarc 280; port 2/1. |  | LUIS SANCHEZ-SIERRA 1-787-400-2322 lsanchez@ssspr.com | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 03/28/2018(Private IP - PIP) 03/28/2018(WAN Analysis Reporting) 03/28/2018(Access) | 04/16/2018 |  | 04/05/2018 (25320805) 04/02/2018 (25320806) | 05/09/2018 05/15/2018 | 03/28/2018 |  | Completed | N (25320805) N (25320807) N (25320806) | U0101953 | Jeopardy Notification 2 (02/15/2018) | NSPE0011562343 Order Request # 194486961 | NSPE0011562343
Completed | FL220-01-IM Orlando FL | 6545 CORPORATE CENTRE BLVD STE 240 ORLANDO, FL 32822-3253 US | 50 MBPS (25287885) | 07/25/2018: 07/24 Customer no show. Need to reschedule activation | 194494034 | 6545 Corporate Center Blvd. - Suite 240 | Private IP - PIP (25287884) WAN Analysis Reporting (25287886) Access (25287885) | 25287884 25287886 25287885 | 10 MBPS (25287884) |  | 191056562 (Private IP (PIP)) 191056563 (WAN Analysis Reporting) 191056560 (Access) | C4008567/ADD (25287884) E4023199/ADD (25287885) | 5S/KEFN/003553/LVLC (2528788529807701) | 5915337 | 5500 | PVC ID : 5915337 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64950 PE IP Address : 152.164.247.5 CE Address : 152.164.247.6 QoS - Egress Profile: R12 | 100Base-TX (25287885) | 100Base-TX (25287885) | Ethernet | LEVEL 3 (2528788529807701) | 09/29/2017 (2528788529807701) | 10/18/2017 (2528788529807701) | 10/17/2017 (2528788529807701) | 10/18/2017 (VFORCE) (25287885) | 10/18/2017 (VFORCE) (25287885) | DEMARCDET - 2nd fl, server room, csutomer rack 007, RMU 10 cisco 3600 ORLD129GW2001 port g0/17, RJ45, tagged w/circuit ID. |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 10/18/2017(Private IP - PIP) 10/18/2017(WAN Analysis Reporting) 10/18/2017(Access) |  |  | 10/27/2017 (25287884) 10/25/2017 (25287885) | 11/13/2017 11/17/2017 | 10/18/2017 |  | Activated/Installed | N (25287884) N (25287886) N (25287885) | U0101953 |  | NSPE0011566611 Order Request # 194493447 | NSPE0011566611
Completed | NJ113 -02-IM Camden NJ | 800 COOPER ST CAMDEN, NJ 08102-1155 US | 3 MBPS (25331057) | 10/16/2017: 10/15 Background: NJ113 -02-IM Camden, NJ; New 2xT1 MLPPP; VzT; No NID; No MS; Status: Ready for Plug and Play. Customer may call 862-829-9719 for assistance in activating the circuit. Customer notified. Circuit ID: .HCGS.859020..NJ Demarc: BSNT,UTIL,RM TELCO,TEL RM,,RJ48C,LP Y,CAB N,,SHELF,2,POS,1 | 194513966 | 800 Cooper St | Private IP - PIP (25331056) WAN Analysis Reporting (25331058) Access (25331057) | 25331056 25331058 25331057 | 3 MBPS (25331056) |  | 191540685 (Private IP (PIP)) 191540686 (WAN Analysis Reporting) 191540683 (Access) | C1060120/ADD (25331056) N1038456/ADD (25331057) N1038455/ADD (25331057) | .HCGS.859020..NJ (2533105729897101) | 5917539 | 1500 | PVC ID : 5917539 VPN Name : UnitedHealthGroup Router Name : PTN3E02 VRF Name : V280778-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64944 PE IP Address : 147.225.225.29 CE Address : 147.225.225.30 QoS - Egress Profile: R12 |  | DS1 (25331057) | TDM | VERIZON (2533105729897101) | 10/03/2017 (2533105729897101) | 10/13/2017 (2533105729897101) | 10/15/2017 (2533105729897101) |  |  | DEMARCADDR - 800 COOPER ST,CAM, NJ,BLDG MAIN; FLR 1; RM MDF DEMARCDET - BSNT,TELCO,RM UTIL,UTIL RM,,RJ48C,LP Y,CAB N,,SHELF,2,POS,2, |  | Robin Donaghy 1-973-348-1235 robin_donaghy@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 10/15/2017(Private IP - PIP) 10/15/2017(WAN Analysis Reporting) 10/15/2017(Access) |  |  | 10/20/2017 (25331056) 10/18/2017 (25331057) | 10/24/2017 10/30/2017 | 10/15/2017 |  | Activated/Installed | N (25331056) N (25331058) N (25331057) | U0101953 | Jeopardy Notification 1 (10/02/2017) | NSPE0011580837 Order Request # 194512824 | NSPE0011580837
Completed | MO050-14-IM Maryland Heights MO | 13655 RIVERPORT DR MARYLAND HEIGHTS, MO 63043-4812 US | 250 MBPS (25372931) | 02/16/2018: 02/16 Successfully activated | 194534158 | UMO15-08-IJ Maryland Heights | Private IP - PIP (25372930) WAN Analysis Reporting (25372932) Access (25372931) | 25372930 25372932 25372931 | 100 MBPS (25372930) |  | 192689047 (Private IP (PIP)) 192689048 (WAN Analysis Reporting) 192689045 (Access) | C0130008/ADD (25372930) E0004434/ADD (25372931) | 41/KRGN/705732//SW (2537293116707301) | 5919565 | 70000 | PVC ID : 5919565 VPN Name : UnitedHealthGroup Router Name : SC99E01 VRF Name : Vf03180:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64678 PE IP Address : 152.161.154.205 CE Address : 152.161.154.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25372931) | 1000Base-SX (850nm, Multi Mode Fiber) (25372931) | Ethernet | ATT (2537293116707301) | 09/20/2017 (2537293116707301) | 10/05/2017 (2537293116707301) | 10/05/2017 (2537293116707301) | 10/20/2017 (VFORCE) (25372931) | 10/20/2017 (VFORCE) (25372931) | DEMARCADDR - ADRS_UNKNOWN DEMARCDET - 1ST FLR TELCO RM, PATCH PANEL 1 PORTS 2, SC MM HANDOFF |  | Robert Skebo 1-314-592-7082 robert_skebo@uhg.com | Vaishna Priya | vaishna@optum.com | 91-988-619-5805 | 10/06/2017(Private IP - PIP) 10/06/2017(WAN Analysis Reporting) 10/06/2017(Access) | 02/15/2018 |  | 10/16/2017 (25372930) 10/12/2017 (25372931) | 10/31/2017 11/06/2017 | 10/06/2017 |  | Activated/Installed | N (25372930) N (25372932) N (25372931) | U0101953 | Jeopardy Notification 1 (09/21/2017) | NSPE0011593798 Order Request # 194531392 | NSPE0011593798
Completed | C1624-01-IM Chandler AZ | 2335 S ELLIS ST CHANDLER, AZ 85286-6701 US | 500 MBPS (25384150) | 03/02/2018: 03/02 Successfully activated | 194540418 | Chandler | Private IP - PIP (25384149) WAN Analysis Reporting (25384151) Access (25384150) | 25384149 25384151 25384150 | 300 MBPS (25384149) |  | 192878962 (Private IP (PIP)) 192878983 (WAN Analysis Reporting) 192878960 (Access) | C5003681/ADD (25384149) E5008154/ADD (25384150) | ELINE/950467/ZYO (2538415030126301) | 5920197 | 90000 | PVC ID : 5920197 VPN Name : UHG-ECC Router Name : PHN13E01 VRF Name : Vc02419-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65513 PE IP Address : 68.136.113.85 CE Address : 68.136.113.86 QoS - Egress Profile: C13 | 1000Base-SX-850nm (25384150) | 1000Base-SX (850nm, Multi Mode Fiber) (25384150) | Ethernet | INTEGRA (2538415030126301) | 02/14/2018 (2538415030126301) | 02/21/2018 (2538415030126301) | 02/22/2018 (2538415030126301) | 02/22/2018 (VFORCE) (25384150) | 02/22/2018 (VFORCE) (25384150) | DEMARCADDR - . DEMARCDET - CYRUS ONE data center cage. MAX 04.FDU3 Cab CA10 |  | Buddy Jerome 1-303-495-7104 george.jerome@cognizant.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 02/22/2018(Private IP - PIP) 02/22/2018(WAN Analysis Reporting) 02/22/2018(Access) | 03/02/2018 |  | 03/02/2018 (25384149) 02/28/2018 (25384150) | 03/27/2018 04/02/2018 | 02/22/2018 |  | Completed | N (25384149) N (25384151) N (25384150) | U0101953 | Jeopardy Notification 1 (01/08/2018) | QOS: C13; NSPE0011598327 Order Request # 194540048 | NSPE0011598327
Completed |  | 2220 CAMPBELL CRK RICHARDSON, TX 75082-4420 US | 100 MBPS (25477543) | 10/16/2017: 10/13 Gold CAR upgrade to 70M successfully. | 194577873 | Connextions 2220 Campbell Creek, Richardson, TX 75082 | Private IP - PIP (25477542) Access (25477543) | 25477542 25477543 | 100 MBPS (25477542) |  | 36584656 (Private IP (PIP)) 36584655 (Access) | C1004787/NONE (25477542) E4000903/NONE (25477543) |  | 5477394 | 70000 | PVC ID : 5477394 VPN Name : UnitedHealthGroup Router Name : RCN3E02 VRF Name : V454456-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64918 PE IP Address : 199.220.240.93 CE Address : 199.220.240.94 QoS - Egress Profile: R12 | 100Base-TX (25477543) | 100Base-TX (25477543) | Ethernet | [8 empty] | Sonja Mroczynski 1-763-553-4801 sonja_d_mroczynski@optum.com | Sonja Mroczynski | sonja_d_mroczynski@optum.com | 1-763-553-4801 | 10/13/2017(Private IP - PIP) 10/13/2017(Access) | 10/13/2017 |  | 11/13/2017 (25477542) 11/13/2017 (25477543) | 11/13/2017 | 10/13/2017 |  |  | N (25477542) N (25477543) | U0106710 |  | NSPE0011623490 Order Request # 194577788 | NSPE0011623490
Completed | UTX12 | 2000 WEST LOOP S HOUSTON, TX 77027-3513 US | 200 MBPS (25490983) | 11/09/2017: 11/09 Successfully activated | 194582097 | UTX12 | Private IP - PIP (25490982) WAN Analysis Reporting (25490984) Access (25490983) | 25490982 25490984 25490983 | 100 MBPS (25490982) |  | 194629897 (Private IP (PIP)) 194629898 (WAN Analysis Reporting) 194629895 (Access) | C5003774/ADD (25490982) E5008339/ADD (25490983) |  | 5923810 | 70000 | PVC ID : 5923810 VPN Name : UnitedHealthGroup Router Name : HSJGE02 VRF Name : V207050:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64633 PE IP Address : 152.176.128.105 CE Address : 152.176.128.106 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (25490983) | Ethernet |  |  |  |  | 10/24/2017 (CCP) (25490982) 10/24/2017 (CCP) (25490983) | 11/04/2017 (CCP) (25490982) 11/04/2017 (CCP) (25490983) |  |  | Bret Smith 1-713-599-5707 bret_a_smith@optum.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 11/03/2017(Private IP - PIP) 11/03/2017(WAN Analysis Reporting) 11/03/2017(Access) | 11/09/2017 |  | 11/14/2017 (25490982) 11/10/2017 (25490983) | 10/31/2017 11/06/2017 | 11/03/2017 |  | Completed | N (25490982) N (25490984) N (25490983) | U0101953 |  | NSPE0011626410 Order Request # 194582091 | NSPE0011626410
Completed | TX347-05-CM MCALLEN TX | 1317 E JASMINE AVE MCALLEN, TX 78501 USA | 1.536 MBPS (IQBLJ3XF) | 10/19/2017: 10/19 Ready for Plug and Play. Customer may call 8668299719 for assistance in activating the circuit | 9316247 |  | Private IP (IQBLJ3XF) EVC/PVC Service (N.11533590.5924298) | IQBLJ3XF N.11533590.5924298 | 1.536 MBPS (IQBLJ3XF) | P2178765 |  | BCBLCC2H0001 (IQBLJ3XF) BCBLCC2H0002 (IQBLJ3XF) BCBLCC2H0003 (IQBLJ3XF) BCBLCC2H0004 (IQBLJ3XF) BCBLCC2H0005 (IQBLJ3XF) BCBLCC2H0006 (IQBLJ3XF) BCBLCC2H0007 (IQBLJ3XF) | 38/HCGS/631144//SW (IQBLJ3XFWSJWMB01) | 5924298 |  | PVC ID : 5924298 |  |  |  | ATT (IQBLJ3XFWSJWMB01) | 10/06/2017 (IQBLJ3XFWSJWMB01) | 10/18/2017 (IQBLJ3XFWSJWMB01) | 10/18/2017 (IQBLJ3XFWSJWMB01) |  |  | BCBLCC2H0001 - All Weather Mount 1 Position 1 next to power meter RJ48C Tagged and not extended BCBLCC2H0002 - All Weather Mount 1 Position 2 next to power meter RJ48C Tagged and not extended BCBLCC2H0003 - All Weather Mount 1 Position 3 next to power meter RJ48C Tagged and not extended BCBLCC2H0004 - All Weather Mount 1 Position 4 next to power meter RJ48C Tagged and not extended BCBLCC2H0005 - All Weather Mount 1 Position 5 next to power meter RJ48C Tagged and not extended BCBLCC2H0006 - All Weather Mount 1 Position 6 next to power meter RJ48C Tagged and not extended BCBLCC2H0007 - All Weather Mount 1 Position 7 next to power meter RJ48C Tagged and not extended |  | RICK WILLIAMSON 0012109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 10/19/2017 (IQBLJ3XF) |  |  | 10/25/2017 (IQBLJ3XF) | 10/31/2017 (IQBLJ3XF) |  |  |  | N (IQBLJ3XF) N (N.11533590.5924298) | 05650532 87559536 |  | NSPE0011627542 CW 194583640 | NSPE0011627542
Completed | TX346-05-CM El Paso TX | 7198 MERCHANT AVE EL PASO, TX 79915 USA | 1.536 MBPS (IQBLJ3WM) | 11/30/2017: 12/01 Background: TX346-05-CM El Paso, TX; New 10.5M 7XT1 MLPPP; SB; No NID; No MNS Status: Ready for Plug and Play Next action: If customer needs assistance in activating the circuit, they may call our 24/7 activation hotline 866-829-9719. Who owns the next action: Customer Ticket: NA Telco Circuit ID - Demarcation: Circuit BCBLCC100001 Leg 0 Seg 0 SAJ AA WBDXC OC12 297:OC3 04:DS3 01:DS1 21 (SAJ1AA T3AS) Split E Circuit BCBLCC100002 Leg 0 Seg 0 SAJ AA WBDXC OC12 297:OC3 02:DS3 02:DS1 23 (SAJ1AA T3AS) Split E Circuit BCBLCC100003 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 01:DS3 01:DS1 12 (SAJ1AA T3AS) Split E Circuit BCBLCC100004 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 04:DS3 03:DS1 06 (SAJ1AA T3AS) Split E Circuit BCBLCC100005 Leg 0 Seg 0 SAJ AA WBDXC OC12 297:OC3 02:DS3 02:DS1 27 (SAJ1AA T3AS) Split E Circuit BCBLCC100006 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 01:DS3 01:DS1 21 (SAJ1AA T3AS) Split E Circuit BCBLCC100007 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 04:DS3 03:DS1 07 (SAJ1AA T3AS) Split E | 9316268 |  | Private IP (IQBLJ3WM) EVC/PVC Service (N.11532377.5923940) | IQBLJ3WM N.11532377.5923940 | 10.752 MBPS | P2178749 |  | BCBLCC100001 (IQBLJ3WM) BCBLCC100002 (IQBLJ3WM) BCBLCC100003 (IQBLJ3WM) BCBLCC100004 (IQBLJ3WM) BCBLCC100005 (IQBLJ3WM) BCBLCC100006 (IQBLJ3WM) BCBLCC100007 (IQBLJ3WM) | 30/HCGS/631060//SW (IQBLJ3WMCSJWMB01) | 5923940 | 1536 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64832 PE IP Address : 68.138.92.89 CE Address : 68.138.92.90 QoS - Egress Profile: R12 PVC ID : 5923940 |  |  |  | ATT (IQBLJ3WMCSJWMB01) | 11/20/2017 (IQBLJ3WMCSJWMB01) | 11/30/2017 (IQBLJ3WMCSJWMB01) | 11/29/2017 (IQBLJ3WMCSJWMB01) |  |  | Circuit BCBLCC100001 Leg 0 Seg 0 SAJ AA WBDXC OC12 297:OC3 04:DS3 01:DS1 21 (SAJ1AA T3AS) Split E Circuit BCBLCC100002 Leg 0 Seg 0 SAJ AA WBDXC OC12 297:OC3 02:DS3 02:DS1 23 (SAJ1AA T3AS) Split E Circuit BCBLCC100003 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 01:DS3 01:DS1 12 (SAJ1AA T3AS) Split E Circuit BCBLCC100004 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 04:DS3 03:DS1 06 (SAJ1AA T3AS) Split E Circuit BCBLCC100005 Leg 0 Seg 0 SAJ AA WBDXC OC12 297:OC3 02:DS3 02:DS1 27 (SAJ1AA T3AS) Split E Circuit BCBLCC100006 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 01:DS3 01:DS1 21 (SAJ1AA T3AS) Split E Circuit BCBLCC100007 Leg 0 Seg 0 SAJ AA WBDXC OC12 299:OC3 04:DS3 03:DS1 07 (SAJ1AA T3AS) Split E |  | RICK WILLIAMSON 0012109513129 RWILLIAMSON@WELLMED.NET | LAEEQ SAJJAD | LAEEQ_SAJJAD@OPTUM.COM | 3126175537 | 11/30/2017 (IQBLJ3WM) |  |  | 11/20/2017 (IQBLJ3WM) | 12/01/2017 (IQBLJ3WM) |  |  |  | N (IQBLJ3WM) N (N.11532377.5923940) | 05650532 87600961 |  | NSPE0011627709 CW 194583941 TIN 9316268 Note: We are moving from Legacy platform to VRD because VRD cannot accommodate 7xT1. So we are installing an entirely NEW order. No need to reuse loop. Please install entirely new loops. Disconnection Request for the existing Legacy Circuit will be submitted by the account team. Existing Circuit ID C0119714 access N1036364 N1036365 and N1036366 (sales to submit a disconnection request once new install is complete) | NSPE0011627709
Completed | TX263-08-CM AUSTIN TX | 8107 SPRINGDALE RD AUSTIN, TX 78724 USA | 1.536 MBPS (IQBLJ33Z) | 03/29/2021: Order Completed on Nov 2, 2017 | 9316274 |  | Private IP (IQBLJ33Z) EVC/PVC Service (N.11533012.5924152) | IQBLJ33Z N.11533012.5924152 | 10.752 MBPS | P2178815 |  | BCBLCC4B0001 (IQBLJ33Z) BCBLCC4B0002 (IQBLJ33Z) BCBLCC4B0003 (IQBLJ33Z) BCBLCC4B0004 (IQBLJ33Z) BCBLCC4B0005 (IQBLJ33Z) BCBLCC4B0006 (IQBLJ33Z) BCBLCC4B0007 (IQBLJ33Z) | 32/HCGS/697362//SW (IQBLJ33ZNTJWMB01) | 5924152 | 1536 | VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65218 PE IP Address : 68.139.198.225 CE Address : 68.139.198.226 QoS - Egress Profile: R12 PVC ID : 5924152 |  |  |  | ATT (IQBLJ33ZNTJWMB01) | 10/10/2017 (IQBLJ33ZNTJWMB01) | 10/20/2017 (IQBLJ33ZNTJWMB01) | 11/01/2017 (IQBLJ33ZNTJWMB01) |  |  | 32/HCGS/697361//SW: 1st Floor Suite 110 Telco Wall Cabinet 4 Slot 1 RJ48C Tagged and not extended 32/HCGS/697362//SW: 1st Floor Suite 110 Telco Wall Cabinet 4 Slot 2 RJ48C Tagged and not extended 32/HCGS/697363//SW: 1st Floor Suite 110 Telco Wall Cabinet 4 Slot 3 RJ48C Tagged and not extended 32/HCGS/697364//SW: 1st Floor Suite 110 Telco Wall Cabinet 4 Slot 4 RJ48C Tagged and not extended 32/HCGS/697365//SW: 1st Floor Suite 110 Telco Wall Cabinet 5 Slot 1 RJ48C Tagged and not extended 32/HCGS/697366//SW: 1st Floor Suite 110 Telco Wall Cabinet 5 Slot 2 RJ48C Tagged and not extended 32/HCGS/697367//SW: 1st Floor Suite 110 Telco Wall Cabinet 5 Slot 3 RJ48C Tagged and not extended |  | RICK WILLAMSON 0012109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 11/02/2017 (IQBLJ33Z) |  |  | 10/27/2017 (IQBLJ33Z) | 10/30/2017 (IQBLJ33Z) |  |  |  | N (IQBLJ33Z) N (N.11533012.5924152) | 05650532 87559537 |  | NSPE0011627753 CW 194584249 TIN 9316274 Note: We are moving from Legacy platform to VRD because VRD cannot accommodate 7xT1. So we are installing an entirely NEW order. No need to reuse loop. Please install entirely new loops. Disconnection Request for the existing Legacy Circuit will be submitted by the account team. Existing Circuit ID C0119778 access N1036393-nN1036395; | NSPE0011627753
Completed | TX371-05-IM SAN BENITO TX | 850 W US HIGHWAY 77 SAN BENITO, TX 78586 USA | 1.536 MBPS (IQBLJ36S) | 11/20/2017: 11/20 Background: TX371-05-IM SAN BENITO, TX; NEW 7XT1 10.752M PIP MLPPP; SB; NO NID; NO MNS; Status: Ready for PLug and Play. Next action: Customer to activate Who owns the next action: Customer Ticket: NA | 9316813 |  | Private IP (IQBLJ36S) EVC/PVC Service (N.11533293.5924199) | IQBLJ36S N.11533293.5924199 | 10.752 MBPS | P2178837 |  | BCBLCC460001 (IQBLJ36S) BCBLCC460002 (IQBLJ36S) BCBLCC460003 (IQBLJ36S) BCBLCC460004 (IQBLJ36S) BCBLCC460005 (IQBLJ36S) BCBLCC460006 (IQBLJ36S) BCBLCC460007 (IQBLJ36S) | 38/HCGS/631152//SW (IQBLJ36S8TJWMB01) | 5924199 | 1536 | VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65279 PE IP Address : 68.136.210.17 CE Address : 68.136.210.18 QoS - Egress Profile: R12 PVC ID : 5924199 |  |  |  | ATT (IQBLJ36S8TJWMB01) | 11/14/2017 (IQBLJ36S8TJWMB01) | 11/22/2017 (IQBLJ36S8TJWMB01) | 11/17/2017 (IQBLJ36S8TJWMB01) |  |  | 001--38/HCGS/631151/SW - 1ST FLOOR SERVER ROOM MM1 SLOT8 RJ48C NOT EXT. 002- 38/HCGS/631152/SW - 1ST FLOOR SERVER ROOM MM1 SLOT9 RJ48C NOT EXT. 003- 38/HCGS/631153/SW - 1ST FLOOR SERVER ROOM MM1 SLOT10 RJ48C NOT EXT. 004- 38/HCGS/631154/SW - 1ST FLOOR SERVER ROOM MM1 SLOT11 RJ48C NOT EXT. 005- 38/HCGS/631155/SW - 1ST FLOOR SERVER ROOM MM1 SLOT12 RJ48C NOT EXT. 006- 38/HCGS/631156/SW - 1ST FLOOR SERVER ROOM MM1 SLOT13 RJ48C NOT EXT. 007- 38/HCGS/631157/SW - 1ST FLOOR SERVER ROOM MM1 SLOT14 RJ48C NOT EXT |  | LUIS CASAS JASON OZER 0019564555057 2109513251 JOZER@WELLMED.NET |  |  |  | 11/20/2017 (IQBLJ36S) |  |  | 11/14/2017 (IQBLJ36S) | 12/07/2017 (IQBLJ36S) |  |  |  | N (IQBLJ36S) N (N.11533293.5924199) | 05650532 87559538 |  | NSPE0011629845 CW 194587324 | NSPE0011629845
Completed | TX341-05-IM BROWNSVILLE TX | 1313 E ALTON GLOOR BLVD BROWNSVILLE, TX 78526 USA | 1.536 MBPS (IQBLJ5R6) | 01/20/2021: Order Completed on Oct 26, 2017 | 9318907 |  | Private IP (IQBLJ5R6) EVC/PVC Service (N.11538069.5925592) | IQBLJ5R6 N.11538069.5925592 | 10.752 MBPS | P2179264 |  | BCBLCDML0001 (IQBLJ5R6) BCBLCDML0002 (IQBLJ5R6) BCBLCDML0003 (IQBLJ5R6) BCBLCDML0004 (IQBLJ5R6) BCBLCDML0005 (IQBLJ5R6) BCBLCDML0006 (IQBLJ5R6) BCBLCDML0007 (IQBLJ5R6) | 38/HCGS/631176//SW (IQBLJ5R6N2JWMB01) | 5925592 | 1536 | VPN Name : UnitedHealthGroup Router Name : SAJ3E02 VRF Name : V439040-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65242 PE IP Address : 152.176.123.93 CE Address : 152.176.123.94 QoS - Egress Profile: R12 PVC ID : 5925592 |  |  |  | ATT (IQBLJ5R6N2JWMB01) | 10/13/2017 (IQBLJ5R6N2JWMB01) | 10/24/2017 (IQBLJ5R6N2JWMB01) | 10/25/2017 (IQBLJ5R6N2JWMB01) |  |  | LEC Circuit ID: 38/HCGS/630245 /SW 38/HCGS/630173 /SW 38/HCGS/629463 /SW 38/HCGS/629464 /SW 38/HCGS/619269 /SW 38/HCGS/619268 /SW 38/HCGS/619144 /SW Demarc: ONI 2, POS 8, LOCATED AT REAR OF BUILDING ONI 3, POS 3, LOCATED AT REAR OF BUILDING ONI 3, POS 6, LOCATED AT REAR OF BUILDING ONI 3, POS 2, LOCATED AT REAR OF BUILDING ONI 3, POS 5, LOCATED AT REAR OF BUILDING ONI 3, POS 4, LOCATED AT REAR OF BUILDING ONI 3, POS 7, LOCATED AT REAR OF BUILDING |  | RICK WILLIAMSON 0012109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 10/26/2017 (IQBLJ5R6) |  |  | 10/31/2017 (IQBLJ5R6) | 11/06/2017 (IQBLJ5R6) |  |  |  | N (IQBLJ5R6) N (N.11538069.5925592) | 05650532 87559539 |  | NSPE0011638809 CW 194603936 | NSPE0011638809
Completed | TX349-02-IM NORTH RICHLAND HILLS TX | 6513 SMITHFIELD RD NORTH RICHLAND HILLS, TX 76182 USA | 1.536 MBPS (IQBLJ5SB) | 12/20/2017: 12/20 Background: TX349-02-IM NORTH RICHLAND HILLS, TX; NEW 10.5M-7XT1 MLPPP; SWB; NO NID; NO MS; Status: Ready for plug and play. Customer may call 866-829-9719 if they need assistance in activating this service Next action: NA Who owns next action: NA Ticket: NA | 9318906 |  | Private IP (IQBLJ5SB) EVC/PVC Service (N.11538097.5925602) | IQBLJ5SB N.11538097.5925602 | 10.752 MBPS | P2179266 |  | BCBLCDMN0001 (IQBLJ5SB) BCBLCDMN0002 (IQBLJ5SB) BCBLCDMN0003 (IQBLJ5SB) BCBLCDMN0004 (IQBLJ5SB) BCBLCDMN0005 (IQBLJ5SB) BCBLCDMN0006 (IQBLJ5SB) BCBLCDMN0007 (IQBLJ5SB) | 14/HCGS/161971//SW (1306315) 14/HCGS/161972//SW (1306315) 14/HCGS/161973//SW (1306315) 14/HCGS/161974//SW (1306315) 14/HCGS/161975//SW (1306315) 14/HCGS/161976//SW (1306315) | 5925602 | 1536 | VPN Name : UnitedHealthGroup Router Name : IAE3E03 VRF Name : V414342-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65193 PE IP Address : 159.24.135.245 CE Address : 159.24.135.246 QoS - Egress Profile: R12 PVC ID : 5925602 |  |  |  | ATT (1306315) | 11/22/2017 (1306315) | 12/04/2017 (1306315) | 01/18/2018 (1306315) |  |  | 14/HCGS/161970 /SW - DEMARC LOC: 1STFLR WAREHOUSE TELPH BB CAB |  | RICK WILLIAMSON 0012109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 12/20/2017 (IQBLJ5SB) |  |  | 12/05/2017 (IQBLJ5SB) | 12/13/2017 (IQBLJ5SB) |  |  |  | N (IQBLJ5SB) N (N.11538097.5925602) | 05650532 87584498 |  | NSPE0011638831 CW 194603876 | NSPE0011638831
Completed | TX343-05-IM CORPUS CHRIS TX | 1711 S STAPLES ST CORPUS CHRISTI, TX 78404 USA | 1.536 MBPS (IQBLJ5SH) | 11/10/2017: 11/10 Background: TX343-05-IM CORPUS CHRIS, TX; NEW 10.5M-7XT1 MLPPP; ATT; NO NID; NO MS; Status: Ready for Plug and Play. Customer may call 866-829-9719 if they need assistance in activating this service. Telco Ckt ID:34/HCGS/629679/SW Telco Ckt ID:34/HCGS/629679/SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT#7,RJ48C ---------------------------------------------------- Telco Ckt ID:34/HCGS/629676 /SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT#4,RJ48C ----------------------------------------------------- Telco Ckt ID:34/HCGS/629675 /SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT#3,RJ48C ----------------------------------------------------- Telco Ckt ID:34/HCGS/629674 /SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT#2,RJ48C ----------------------------------------------------- Telco Ckt ID:34/HCGS/629673 /SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT#1,RJ48C ----------------------------------------------------- Telco Ckt ID:34/HCGS/629678 /SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT#6,RJ48C ----------------------------------------------------- Telco Ckt ID:34/HCGS/629677 /SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT#5,RJ48C | 9318912 |  | EVC/PVC Service (N.11538120.5925607) Private IP (IQBLJ5SH) | N.11538120.5925607 IQBLJ5SH | 10.752 MBPS | P2179269 |  | BCBLCDMR0001 (IQBLJ5SH) BCBLCDMR0002 (IQBLJ5SH) BCBLCDMR0003 (IQBLJ5SH) BCBLCDMR0004 (IQBLJ5SH) BCBLCDMR0005 (IQBLJ5SH) BCBLCDMR0006 (IQBLJ5SH) BCBLCDMR0007 (IQBLJ5SH) | 34/HCGS/629674//SW (IQBLJ5SHS2JWMB01) | 5925607 | 1536 | PVC ID : 5925607 VPN Name : UnitedHealthGroup Router Name : SAJ3E02 VRF Name : V439040-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65243 PE IP Address : 199.220.144.209 CE Address : 199.220.144.210 QoS - Egress Profile: R12 |  |  |  | ATT (IQBLJ5SHS2JWMB01) | 10/12/2017 (IQBLJ5SHS2JWMB01) | 10/24/2017 (IQBLJ5SHS2JWMB01) | 11/10/2017 (IQBLJ5SHS2JWMB01) |  |  | Telco Ckt ID:34/HCGS/629679/SW DEMARC LOC: 1ST FLR,BACK TELCO WALL,14- DEMARC LOC Continued: SLOT MULTIMOUNT,SLOT |  | RICK WILLAMSON 2109513129 0012109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 11/10/2017 (IQBLJ5SH) |  |  | 11/08/2017 (IQBLJ5SH) | 12/15/2017 (IQBLJ5SH) |  |  |  | N (N.11538120.5925607) N (IQBLJ5SH) | P2179269 05650532 |  | NSPE0011638865 CW 194604158 | NSPE0011638865
Completed | FL212-05-IM WINTER PARK FL | 809 S ORLANDO AVE WINTER PARK, FL 32789 USA | 1.536 MBPS (IQBLJ5SY) | 11/22/2017: 11/17 Background: FL212-05-IM WINTER PARK, FL; NEW 10.5M-7XT1 MLPPP; Metropolitan Fiber Sys; NO NID; NO MS; Status: Ready for Plug and Play Next action: Customer to activate Who owns the next action: Customer Ticket: NA Telco Circuit ID - Demarcation: BCBLCDMT0001 DEMARC LOC: 1st floor data room position 1 of 7 Jack Type: RJ48x BCBLCDMT0002 DEMARC LOC: 1st floor data room position 2 of 7 Jack Type: RJ48x BCBLCDMT0003 DEMARC LOC: 1st floor data room position 3 of 7 Jack Type: RJ48x BCBLCDMT0004 DEMARC LOC: 1st floor data room position 4 of 7 Jack Type: RJ48x BCBLCDMT0005 DEMARC LOC: 1st floor data room position 5 of 7 Jack Type: RJ48x BCBLCDMT0006 DEMARC LOC: 1st floor data room position 6 of 7 Jack Type: RJ48x BCBLCDMT0007 DEMARC LOC: 1st floor data room position 7 of 7 Jack Type: RJ48x | 9318913 |  | Private IP (IQBLJ5SY) EVC/PVC Service (N.11538147.5925613) | IQBLJ5SY N.11538147.5925613 | 10.752 MBPS | P2179272 |  | BCBLCDMT0001 (IQBLJ5SY) BCBLCDMT0002 (IQBLJ5SY) BCBLCDMT0003 (IQBLJ5SY) BCBLCDMT0004 (IQBLJ5SY) BCBLCDMT0005 (IQBLJ5SY) BCBLCDMT0006 (IQBLJ5SY) BCBLCDMT0007 (IQBLJ5SY) | 25.HCGS.313519..UFLG (1304192) 25.HCGS.313520..UFLG (1304192) 25.HCGS.313521..UFLG (1304192) 25.HCGS.313522..UFLG (1304192) 25.HCGS.313523..UFLG (1304192) 25.HCGS.313524..UFLG (1304192) | 5925613 | 5392 | VPN Name : UnitedHealthGroup Router Name : AUBGE03 VRF Name : V542236:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65271 PE IP Address : 68.136.31.125 CE Address : 68.136.31.126 QoS - Egress Profile: R12 PVC ID : 5925613 |  |  |  | CENTURYLINK (1304192) | 11/06/2017 (1304192) | 11/15/2017 (1304192) | 09/12/2018 (1304192) |  |  | BCBLCDMT0001 DEMARC LOC: 1st floor data room position 1 of 7 Jack Type: RJ48x BCBLCDMT0002 DEMARC LOC: 1st floor data room position 2 of 7 Jack Type: RJ48x BCBLCDMT0003 DEMARC LOC: 1st floor data room position 3 of 7 Jack Type: RJ48x BCBLCDMT0004 DEMARC LOC: 1st floor data room position 4 of 7 Jack Type: RJ48x BCBLCDMT0005 DEMARC LOC: 1st floor data room position 5 of 7 Jack Type: RJ48x BCBLCDMT0006 DEMARC LOC: 1st floor data room position 6 of 7 Jack Type: RJ48x BCBLCDMT0007 DEMARC LOC: 1st floor data room position 7 of 7 Jack Type: RJ48x |  | RICK WILLIAMSON 0013053643404 2109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 11/17/2017 (IQBLJ5SY) |  |  | 11/15/2017 (IQBLJ5SY) | 11/30/2017 (IQBLJ5SY) |  |  |  | N (IQBLJ5SY) N (N.11538147.5925613) | 05650532 87615957 |  | NSPE0011638905 CW 194604197 | NSPE0011638905
Provisioning Accepted | TX348-05-IM NORTH RICHLAND HILLS TX | 6344 DAVIS BLVD NORTH RICHLAND HILLS, TX 76180 USA | 1.536 MBPS (IQBLJ5S1) | 02/19/2018: 02/19 Background: TX348-05-IM NORTH RICHLAND HILLS, TX; NEW 10.5M-7XT1 MLPPP; SWB; NO NID; NO MS; Status: Ready for plug and play (activation ) Next action: If customer needs assistance in activating this circuit, they may call 866-829-9719 Who owns next action: BNE Ticket: NA | 9319872 |  | Private IP (IQBLJ5S1) | IQBLJ5S1 | 10.752 MBPS | P2179275 |  | BCBLCDMX0001 (IQBLJ5S1) BCBLCDMX0002 (IQBLJ5S1) BCBLCDMX0003 (IQBLJ5S1) BCBLCDMX0004 (IQBLJ5S1) BCBLCDMX0005 (IQBLJ5S1) BCBLCDMX0006 (IQBLJ5S1) BCBLCDMX0007 (IQBLJ5S1) | 14/HCGS/161685//SW (IQBLJ5S1X2JWMB01) |  | 1536 | VPN Name : UnitedHealthGroup Router Name : IAE3E02 VRF Name : V311110-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65163 PE IP Address : 68.137.229.53 CE Address : 68.137.229.54 QoS - Egress Profile: R12 |  |  |  | ATT (IQBLJ5S1X2JWMB01) | 01/30/2018 (IQBLJ5S1X2JWMB01) | 02/07/2018 (IQBLJ5S1X2JWMB01) | 02/13/2018 (IQBLJ5S1X2JWMB01) |  |  | BCBLCDMX00010001 14/HCGS/161684//SW DEMARC LOC: IT/PHONE RM CAB1 SLOT 1 DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:No IW Authorized Jack Type: RJ48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes BCBLCDMX00020002 14/HCGS/161685//SW DEMARC LOC: IT/PHONE ROOM CAB 1 SLOT 2 DEMARC LOC Continued: Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes BCBLCDMX00030003 14/HCGS/161686//SW DEMARC LOC: IT/PHONE ROOM CAB 1 SLOT 3. DEMARC LOC Continued: Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes BCBLCDMX00040004 14/HCGS/161687//SW DEMARC LOC: IT/PHONE ROOM CAB 1 SLOT 4. DEMARC LOC Continued: Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes BCBLCDMX00050005 14/HCGS/161688//SW DEMARC LOC: IT/PHONE ROOM CAB 1 SLOT 5. DEMARC LOC Continued: Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes BCBLCDMX00060006 14/HCGS/161689//SW DEMARC LOC: IT/PHONE RM CAB 1 SLOT 6. DEMARC LOC Continued: Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes BCBLCDMX00070007 14/HCGS/161690//SW DEMARC LOC: IT/PHONE RM CAB 1 SLOT 7. DEMARC LOC Continued: Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes |  | RICK WILLIAMNSON 0012109513129 RWILLIAMSON@WELLMED.NET |  |  |  | 02/19/2018 (IQBLJ5S1) |  |  | 02/19/2018 (IQBLJ5S1) | 02/21/2018 (IQBLJ5S1) |  |  |  | N (IQBLJ5S1) | 05017789 |  | NSPE0011642025 CW 194608159 | NSPE0011642025
Completed | WI011-07-IM Wausau WI | 11 SCOTT ST WAUSAU, WI 54403-4875 US | 600 MBPS (25558615) | 07/18/2018: 07/18 Successfully activated | 194609316 | UHG WI011 | Private IP - PIP (25558614) WAN Analysis Reporting (25558616) Access (25558615) | 25558614 25558616 25558615 | 200 MBPS (25558614) |  | 195132634 (Private IP (PIP)) 195132635 (WAN Analysis Reporting) 195132632 (Access) | C5003802/ADD (25558614) E5008461/ADD (25558615) | 39/KRGN/714291//FTNC/ (2555861524272401) | 5925664 | 70000 | PVC ID : 5925664 VPN Name : UnitedHealthGroup Router Name : DNG3E03 VRF Name : Vc41653-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65284 PE IP Address : 152.176.145.153 CE Address : 152.176.145.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25558615) | 1000Base-SX (850nm, Multi Mode Fiber) (25558615) | Ethernet | FRONTIER (2555861524272401) | 10/12/2017 (2555861524272401) | 01/30/2018 (2555861524272401) | 03/20/2018 (2555861524272401) | 03/26/2018 (VFORCE) (25558615) | 03/26/2018 (VFORCE) (25558615) | DEMARCADDR - 11 SCOTT ST WAUSAU WI DEMARCDET - SLN/A#SHLFN/A#PRTN/A#PHYN/A#JKN/A#EXTN#TAGY, SLN/A#SHLFN/A#P RTN/A#PHYN/A#JKN/A#EXTN#TAGY |  | BRAD LEININGER 1-715-841-7888 bradley_j_leininger@optum.com | Tony Epperson Epperson | tony.epperson@optum.com | 1-312-315-5612 | 03/26/2018(Private IP - PIP) 03/26/2018(WAN Analysis Reporting) 03/26/2018(Access) | 07/17/2018 |  | 04/02/2018 (25558614) 03/29/2018 (25558615) | 05/02/2018 05/08/2018 | 03/26/2018 |  | Completed | N (25558614) N (25558616) N (25558615) | U0101953 | Jeopardy Notification 2 (02/07/2018) | NSPE0011642592 Order Request # 194609110 | NSPE0011642592
Completed | C1626-02-IM Alpharetta GA | 12655 EDISON DR ALPHARETTA, GA 30005 US | 500 MBPS (25568196) | 02/01/2018: 02/01 Successfully activated | 194613345 | C1626-02-IM | Access (25568196) Private IP - PIP (25568195) WAN Analysis Reporting (25568197) | 25568196 25568195 25568197 | 300 MBPS (25568195) |  | 195156976 (Access) 195638078 (Private IP (PIP)) 195638079 (WAN Analysis Reporting) | E5008475/ADD (25568196) C5003808/ADD (25568195) | ETYX/155637//ZYO (2556819630592501) | 5926226 | 250000 | PVC ID : 5926226 VPN Name : UHG-ECC Router Name : CPZXE03 VRF Name : Vb74787-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65413 PE IP Address : 152.181.17.1 CE Address : 152.181.17.2 QoS - Egress Profile: C13 | 1000Base-LX-1310nm (25568196) | 1000Base-LX (1310nm Single Mode Fiber) (25568196) | Ethernet | ZAYO (2556819630592501) | 01/22/2018 (2556819630592501) | 01/19/2018 (2556819630592501) | 01/23/2018 (2556819630592501) | 01/26/2018 (VFORCE) (25568196) | 01/26/2018 (VFORCE) (25568196) | DEMARCDET - ALPSGASG RR ZAYO, MP074 P:49/50 |  | Marco Onorato 1-267-250-5508 Marco.onorato@peak10.com | BRANDON BENSON | brandon_benson@optum.com | 1-763-553-4929 | 01/26/2018(Access) 01/26/2018(Private IP - PIP) 01/26/2018(WAN Analysis Reporting) | 02/01/2018 |  | 01/26/2018 (25568196) 01/30/2018 (25568195) | 02/28/2018 03/06/2018 | 01/26/2018 |  | Completed | N (25568196) N (25568195) N (25568197) | U0101953 | Jeopardy Notification 2 (12/06/2017) | NSPE0011645152 Order Request # 194613073 | NSPE0011645152
Completed | FL213-05-IM JACKSONVILLE FL | 8380 BAYMEADOWS RD JACKSONVILLE, FL 32256 USA | 1.536 MBPS (IQBLJ6P1) | 11/07/2017: 11/07 Background: FL213-05-IM JACKSONVILLE, FL; NEW 10.5MBPS-7XT1 MLPPP; ATT; NO N ID; NO MNS Status: Ready for Plug and Play. Customer may call 866-829-9719, if they need assistance in activating the circuit. Customer informed Telco Circuit IDs- Demarcation: 52/HCGS/778209/SB- 1ST FL ST 12 DATA RM QM5-2 RJ48c not Extend tagged 52/HCGS/778208/SB- 1ST FL ST 12 DATA RM QM5-1 RJ48c not Extend tagged 52/HCGS/778206/SB- 1ST FL ST 12 DATA RM QM4-3 RJ48c not Extend tagged 52/HCGS/778204/SB- 1ST FL ST 12 DATA RM QM4-1 RJ48c not Extend tagged 52/HCGS/778207/SB- 1ST FL ST 12 DATA RM QM4-4 RJ48c not Extend tagged 52/HCGS/778205/SB- 1ST FL ST 12 DATA RM QM4-2 RJ48c not Extend tagged 52/HCGS/778210/SB- 1ST FL ST 12 DATA RM QM5-3 RJ48c not Extend tagged | 9321043 |  | Private IP (IQBLJ6P1) EVC/PVC Service (N.11541063.5927010) | IQBLJ6P1 N.11541063.5927010 | 10.752 MBPS | P2179447 |  | BCBLCDT40001 (IQBLJ6P1) BCBLCDT40002 (IQBLJ6P1) BCBLCDT40003 (IQBLJ6P1) BCBLCDT40004 (IQBLJ6P1) BCBLCDT40005 (IQBLJ6P1) BCBLCDT40006 (IQBLJ6P1) BCBLCDT40007 (IQBLJ6P1) | 52/HCGS/778205//SB (IQBLJ6P1V5JWMB01) | 5927010 | 5392 | VPN Name : UnitedHealthGroup Router Name : JAP3E03 VRF Name : V523238-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65196 PE IP Address : 68.139.7.229 CE Address : 68.139.7.230 QoS - Egress Profile: R12 PVC ID : 5927010 |  |  |  | ATT (IQBLJ6P1V5JWMB01) | 10/23/2017 (IQBLJ6P1V5JWMB01) | 11/02/2017 (IQBLJ6P1V5JWMB01) | 11/06/2017 (IQBLJ6P1V5JWMB01) |  |  | 52/HCGS/778209/SB- 1ST FL ST 12 DATA RM QM5-2 RJ48c not Extend tagged 52/HCGS/778208/SB- 1ST FL ST 12 DATA RM QM5-1 RJ48c not Extend tagged 52/HCGS/778206/SB- 1ST FL ST 12 DATA RM QM4-3 RJ48c not Extend tagged 52/HCGS/778204/SB- 1ST FL ST 12 DATA RM QM4-1 RJ48c not Extend tagged 52/HCGS/778207/SB- 1ST FL ST 12 DATA RM QM4-4 RJ48c not Extend tagged 52/HCGS/778205/SB- 1ST FL ST 12 DATA RM QM4-2 RJ48c not Extend tagged 52/HCGS/778210/SB- 1ST FL ST 12 DATA RM QM5-3 RJ48c not Extend tagged |  | RICK WILLIAMSON 0013053643404 2109513129 RWILLIAMSON@WELLMED.NET | KEVIN CANTOR | KEVIN_CANTOR@OPTUM.COM | 6325885331 | 11/06/2017 (IQBLJ6P1) |  |  | 11/09/2017 (IQBLJ6P1) | 11/07/2017 (IQBLJ6P1) |  |  |  | N (IQBLJ6P1) N (N.11541063.5927010) | 05650532 87600962 |  | NSPE0011647314 CW 194616061 | NSPE0011647314
Completed | WI012-11-IM Wausau WI | 115 W WAUSAU AVE WAUSAU, WI 54401-2875 US | 1 GBPS (25610739) | 07/25/2018: 07/25 Successfully activated | 194633491 | WI012-05-IJ Wausau, WI | Private IP - PIP (25610738) WAN Analysis Reporting (25610740) Access (25610739) | 25610738 25610740 25610739 | 400 MBPS (25610738) |  | 195463871 (Private IP (PIP)) 195463993 (WAN Analysis Reporting) 195463869 (Access) | C0131646/ADD (25610738) E5008563/ADD (25610739) | CHC00465690 (2561073925122401) | 5927894 | 140000 | PVC ID : 5927894 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64521 PE IP Address : 152.162.106.17 CE Address : 152.162.106.18 QoS - Egress Profile: C13 | 1000Base-SX-850nm (25610739) | 1000Base-SX (850nm, Multi Mode Fiber) (25610739) | Ethernet | CHARTER (2561073925122401) | 10/18/2017 (2561073925122401) | 02/05/2018 (2561073925122401) | 02/15/2018 (2561073925122401) | 02/19/2018 (VFORCE) (25610739) | 02/19/2018 (VFORCE) (25610739) | DEMARCADDR - . DEMARCDET - main building 1st floor MDF room wall mounted customer plugs to 002 cisco ASR 920 handoff |  | BRAD LEININGER 1-715-841-7888 bradley_j_leininger@optum.com | Tony Epperson | tony.epperson@optum.com | 1-312-315-5612 | 02/19/2018(Private IP - PIP) 02/19/2018(WAN Analysis Reporting) 02/19/2018(Access) | 07/24/2018 |  | 02/26/2018 (25610738) 02/22/2018 (25610739) | 03/28/2018 04/03/2018 | 02/19/2018 |  | Completed | N (25610738) N (25610740) N (25610739) | U0101953 |  | NSPE0011674947 Order Request # 194632869 | NSPE0011674947
Completed | NC021-07-IM Raleigh NC | 4242 SIX FORKS RD RALEIGH, NC 27609-6084 US | 100 MBPS (25620104) | 11/28/2017: 11/28 Background: NC021-07-IM Raleigh, NC; New 50M/100M PIP-IDS; TWT; NID; No MNS; ENID; Status: Customer to complete extension first before scheduling activation with Verizon. Next action: Customer to complete demark extension then provide activation date and time allowing 3business days advance notice Who owns the next action: Customer Ticket: NA LEC Circuit ID: 4S/KEFN/003817/LVLC LEC Demarc: 1st floor telco room; Centurylink relay rack; RMU 14; RLGONCIRZG001; GI 0/7; RJ-45; tagged w/CID. BEAS Box: E4024450 BEAS Demarc: Ckt found on 1st floor. Ckt not extended to cust network room on 11th floor. Cust aware of need to extend to 11fl, and will need to get facilities involved to get work done. | 194639987 | 4242 SIx Forks Road | Internet Dedicated Services (25620103) Access (25620104) | 25620103 25620104 | 100 MBPS (25620103) |  | 196343036 (Internet Dedicated Services) 196343034 (Access) | C1062188/ADD (25620103) E4024450/ADD (25620104) | 4S/KEFN/003817/LVLC (2562010430809701) | 5928254 | 0 | PVC ID : 5928254 VPN Name : Internet Router Name : GW1RDU1 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.134.33 CE Address : 204.148.134.34 | 100Base-TX (25620104) | 100Base-TX (25620104) | Ethernet | LEVEL 3 (2562010430809701) | 10/31/2017 (2562010430809701) | 11/20/2017 (2562010430809701) | 11/22/2017 (2562010430809701) | 11/28/2017 (VFORCE) (25620104) | 11/28/2017 (VFORCE) (25620104) | DEMARCADDR - . DEMARCDET - 1st floor telco room; Centurylink relay rack; RMU 14; RLGONCIRZG001; GI 0/7; RJ-45; tagged w/CID. |  | CARY LAIL 1-919-832-3770 clail@mcdonaldyork.com | DOUG LEHNEN | doug_lehnen@optum.com | 1-763-694-7443 | 11/28/2017(Internet Dedicated Services) 11/28/2017(Access) |  |  | 12/01/2017 (25620103) 11/29/2017 (25620104) | 12/01/2017 | 11/28/2017 |  |  | N (25620103) N (25620104) | U0101953 |  | NSPE0011678278 Order Request # 194639467 | NSPE0011678278
Completed | C1627-02-IM Richardson TX | 1001 E CAMPBELL RD RICHARDSON, TX 75081-1821 US | 100 MBPS (25633603) | 02/02/2018: 02/02 Activation needs to be rescheduled due to handoff issue. This was ordered as 100Base-FX MMF. Customer is expecting Gig handoff. | 194647920 | UHG- Vox | Access (25633603) Private IP - PIP (25633602) WAN Analysis Reporting (25633604) | 25633603 25633602 25633604 | 50 MBPS (25633602) |  | 196478956 (Access) 196478958 (Private IP (PIP)) 196478959 (WAN Analysis Reporting) | E4024509/ADD (25633603) C1062303/ADD (25633602) |  | 5928707 | 10000 | PVC ID : 5928707 VPN Name : UHG-ECC Router Name : RCN3E02 VRF Name : V471741-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65405 PE IP Address : 152.164.114.1 CE Address : 152.164.114.2 QoS - Egress Profile: C13 |  | 100Base-FX (1310nm, Multi Mode Fiber) (25633603) | Ethernet |  |  |  |  | 11/16/2017 (CCP) (25633603) 11/16/2017 (CCP) (25633602) | 11/15/2017 (CCP) (25633603) 11/15/2017 (CCP) (25633602) | Circuit ID: E4024509 BEAS Demarc: 3.06.09:31/32 MM LC loop left in place for testing. Labeled with circuit ID and order number. |  | Ryan Gelobter 1-469-904-6321 DfwLcon1@VoxScienceCorporation.com | BRANDON BENSON | brandon_benson@optum.com | 1-763-553-4929 | 11/17/2017(Access) 11/17/2017(Private IP - PIP) 11/17/2017(WAN Analysis Reporting) |  |  | 11/30/2017 (25633603) 12/04/2017 (25633602) | 11/20/2017 11/28/2017 | 11/17/2017 |  | Completed | N (25633603) N (25633602) N (25633604) | U0101953 |  | NSPE0011681286 Order Request # 194646016 • The original order was 50M Access and 10M Port / correct order is 100M Access and 50M Port. • Requesting COS c13 – please make sure the order is updated to reflect this custom request. | NSPE0011681286
Completed | TX367-02-IM Dallas TX | 1320 INWOOD RD DALLAS, TX 75247-6806 US | 50 MBPS (25650668) | 01/09/2018: 01/09 Background: TX367-02-IM Dallas, TX; New 10M/50M PIP-Eth; AT&T; NID; No MNS; Status: Ready for Activation Next action: Customer to provide activation date and time allowing 3 business days advance notice Who owns the next action: Customer (BNE) Ticket: NA Telco Circuit ID: 14/KRGN/881460//SW Telco Demarcation: 1ST FLR-SERVER RM-TELCO BB-WALL MOUNT PORT# 5 TGGD/LBLD - CIENA 3930 BEAS Circuit ID: E4024589 BEAS Demarc: 1ST FLOOR SERVER ROOM, WALL MOUNTED OVERTURE ISG1400 MM SFP PORT 1, MOUNTED TO TELCO BACK BOARD ON BACK WALL. DEMARC TAGGED WITH CIRCUIT ID AND ORDER NUMBER | 194659199 | UHG- Wellmed | Private IP - PIP (25650667) WAN Analysis Reporting (25650669) Access (25650668) | 25650667 25650669 25650668 | 10 MBPS (25650667) |  | 197015336 (Private IP (PIP)) 197015337 (WAN Analysis Reporting) 197015334 (Access) | C4009074/ADD (25650667) E4024589/ADD (25650668) | 14/KRGN/881460//SW (2565066830928901) | 5929359 | 5000 | PVC ID : 5929359 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64909 PE IP Address : 152.183.106.17 CE Address : 152.183.106.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25650668) | 1000Base-SX (850nm, Multi Mode Fiber) (25650668) | Ethernet | ATT (2565066830928901) | 12/20/2017 (2565066830928901) | 01/05/2018 (2565066830928901) | 01/05/2018 (2565066830928901) | 01/08/2018 (VFORCE) (25650668) | 01/08/2018 (VFORCE) (25650668) | DEMARCADDR - 1320 INWOOD RD DALLAS TX DEMARCDET - 1ST FLR-SERVER RM-TELCO BB-WALL MOUNT PORT# 5 TGGD/LBLD |  | Patricia Milford 1-214-548-0011 pmilford@homecaredimensions.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 01/08/2018(Private IP - PIP) 01/08/2018(WAN Analysis Reporting) 01/08/2018(Access) |  |  | 01/16/2018 (25650667) 01/12/2018 (25650668) | 01/31/2018 02/06/2018 | 01/08/2018 |  | Completed | N (25650667) N (25650669) N (25650668) | U0101953 | Jeopardy Notification 1 (12/18/2017) | NSPE0011688208 Order Request # 194659019 | NSPE0011688208
Completed | C1625-02-IM Centennial CO | 6900 S PEORIA ST CENTENNIAL, CO 80112-4137 US | 500 MBPS (25666561) | 03/02/2018: 03/02 Successfully activated | 194665818 | UHG- Trizetto | Access (25666561) Private IP - PIP (25666560) WAN Analysis Reporting (25666562) | 25666561 25666560 25666562 | 200 MBPS (25666560) |  | 197285736 (Access) 197285738 (Private IP (PIP)) 197285739 (WAN Analysis Reporting) | E5008701/ADD (25666561) C5003879/ADD (25666560) | DV/L1XX/268273/ /TQW /ELK (2566656130963501) | 5930332 | 90000 | PVC ID : 5930332 VPN Name : UHG-ECC Router Name : DNJXE01 VRF Name : V595692-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65535 PE IP Address : 199.220.23.101 CE Address : 199.220.23.102 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (25666561) | 1000Base-SX (850nm, Multi Mode Fiber) (25666561) | Ethernet | XO (2566656130963501) | 10/30/2017 (2566656130963501) | 11/30/2017 (2566656130963501) | 11/21/2017 (2566656130963501) | 12/08/2017 (VFORCE) (25666561) | 12/08/2017 (VFORCE) (25666561) | DEMARCDET - MDF 2 rack A3 shelf 10 port 5 and 6 CIENA 4200, Single Mode Fiber SFP |  | BUDDY JEROME 1-303-495-7104 george.jerome@cognizant.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 12/08/2017(Access) 12/08/2017(Private IP - PIP) 12/08/2017(WAN Analysis Reporting) | 03/02/2018 |  | 12/14/2017 (25666561) 12/18/2017 (25666560) | 12/14/2017 12/20/2017 | 12/08/2017 |  | Completed | N (25666561) N (25666560) N (25666562) | U0101953 | Jeopardy Notification 1 (12/01/2017) | NSPE0011692200 Order Request # 194664859 (C13) | NSPE0011692200
Completed | TX342-07-IM Corpus Christi TX | 1701 S STAPLES ST CORPUS CHRISTI, TX 78404-3022 US | 50 MBPS (25671371) | 12/06/2017: 12/06 Background: TX342-07-IM Corpus Christi, TX; New 10M/50M PIP-Eth; AT&T; NID; No MNS; Status: Ready for activation Next action: Customer to provide activation date and time Who owns the next action: Customer/BNE Ticket: NA Telco Circuit ID: 34/KRGN/613732//SW Telco Demarc: inside building, back warehouse area,wall mount 3930, port 5. Tagged and Labelled BEAS: E4024671 BEAS Demarc: 1st Room: Back warehouse area, SMF, a box mounted inside wall mount cabinet pos 7 | 194668470 | TX342-02-IM | Private IP - PIP (25671370) WAN Analysis Reporting (25671372) Access (25671371) | 25671370 25671372 25671371 | 10 MBPS (25671370) |  | 197293269 (Private IP (PIP)) 197293270 (WAN Analysis Reporting) 197293267 (Access) | C4009114/ADD (25671370) E4024671/ADD (25671371) | 34/KRGN/613732//SW (2567137123871201) | 5930601 | 5000 | PVC ID : 5930601 VPN Name : UnitedHealthGroup Router Name : HSJ9E04 VRF Name : V622583:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65116 PE IP Address : 152.183.219.185 CE Address : 152.183.219.186 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25671371) | 1000Base-SX (850nm, Multi Mode Fiber) (25671371) | Ethernet | ATT (2567137123871201) | 10/26/2017 (2567137123871201) | 11/30/2017 (2567137123871201) | 11/30/2017 (2567137123871201) | 12/04/2017 (VFORCE) (25671371) | 12/04/2017 (VFORCE) (25671371) | DEMARCADDR - 1701 S STAPLES ST CORPUS CHRISTI TX DEMARCDET - inside building, back warehouse area,wall mount 3930, port 5. TAGGED AND LABELED |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 12/04/2017(Private IP - PIP) 12/04/2017(WAN Analysis Reporting) 12/04/2017(Access) |  |  | 01/05/2018 (25671370) 01/03/2018 (25671371) | 12/08/2017 12/14/2017 | 12/04/2017 |  | Completed | N (25671370) N (25671372) N (25671371) | U0101953 | Jeopardy Notification 1 (11/01/2017) | NSPE0011694021 Order Request 194667179 (C13) | NSPE0011694021
Completed | TX361-02-IJ Houston TX | 8888 INTERCHANGE DR HOUSTON, TX 77054-2512 US | 50 MBPS (25716825) | 03/07/2018: 03/05 03/05 Circuit successfully activated. Unattended. | 194688266 | TX361-02-IJ Houston, TX | Private IP - PIP (25716824) WAN Analysis Reporting (25716826) Access (25716825) | 25716824 25716826 25716825 | 10 MBPS (25716824) |  | 198061659 (Private IP (PIP)) 198061660 (WAN Analysis Reporting) 198061657 (Access) | C4009228/ADD (25716824) E4024888/ADD (25716825) | 28/KRGN/746142//SW (2571682527176001) | 5932382 | 10000 | PVC ID : 5932382 VPN Name : UnitedHealthGroup Router Name : HSTN3E03 VRF Name : Vb20898-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65231 PE IP Address : 152.185.44.1 CE Address : 152.185.44.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25716825) | 1000Base-SX (850nm, Multi Mode Fiber) (25716825) | Ethernet | ATT (2571682527176001) | 11/14/2017 (2571682527176001) | 12/15/2017 (2571682527176001) | 12/08/2017 (2571682527176001) | 12/08/2017 (VFORCE) (25716825) | 12/08/2017 (VFORCE) (25716825) | DEMARCDET - 1st flr, warehouse wall mounted cienna 3903 optical port #2 on the hand off port 3&4 |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | JEREMIAH LASCANO | jeremiah_lascano@optum.com | 632-588-5331 | 12/08/2017(Private IP - PIP) 12/08/2017(WAN Analysis Reporting) 12/08/2017(Access) | 03/08/2018 |  | 01/23/2018 (25716824) 01/19/2018 (25716825) | 12/22/2017 12/29/2017 | 12/08/2017 |  | Scheduled | N (25716824) N (25716826) N (25716825) | U0101953 | Jeopardy Notification 1 (11/09/2017) | NSPE0011710041 Order Request # 194688187 | NSPE0011710041
Completed | UHG- FL219 STUART FL | 2155 SE FEDERAL HWY STUART, FL 34994-4514 US | 50 MBPS (25720651) | 05/08/2018 Successfully activated | 194690281 | UHG- FL219 | Private IP - PIP (25720650) WAN Analysis Reporting (25720652) Access (25720651) | 25720650 25720652 25720651 | 10 MBPS (25720650) |  | 198088279 (Private IP (PIP)) 198088280 (WAN Analysis Reporting) 198088277 (Access) | C4009238/ADD (25720650) E4024903/ADD (25720651) |  | 5932530 | 5500 | PVC ID : 5932530 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64886 PE IP Address : 152.185.74.65 CE Address : 152.185.74.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25720651) | 1000Base-SX (850nm, Multi Mode Fiber) (25720651) | Ethernet |  |  |  |  | 11/16/2017 (VFORCE) (25720651) | 11/16/2017 (VFORCE) (25720651) | DEMARCADDR - 2155 SE FEDERAL HWY STU FL DEMARCDET - 1ST FL METER RM, WALL MOUNT PORT 6 LABELED W/CKT ID |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 11/16/2017(Private IP - PIP) 11/16/2017(WAN Analysis Reporting) 11/16/2017(Access) | 05/07/2018 |  | 11/30/2017 (25720650) 11/28/2017 (25720651) | 12/15/2017 12/21/2017 | 11/16/2017 |  | Completed | N (25720650) N (25720652) N (25720651) | U0101953 |  | NSPE0011710499 Order Request # 194688844 | NSPE0011710499
Completed | IL090-02-IM DOWNERS GROVE IL | 2655 WARRENVILLE RD DOWNERS GROVE, IL 60515-5555 US | 250 MBPS (25724918) | 11/28/2017: 11/28 Activation successful | 194692262 | IL090-02-IM | Access (25724918) Private IP - PIP WAN Analysis Reporting (25724919) | 25724918 25724919 | 100 MBPS |  | 183362924 (Access) 183362926 183362927 (WAN Analysis Reporting) | E0002724/NONE (25724918) | /KRGN/117268//LB (2572491827149001) |  |  |  | 1000Base-LX-1310nm (25724918) | 1000Base-LX (1310nm Single Mode Fiber) (25724918) | Ethernet | ATT (2572491827149001) | 11/06/2017 (2572491827149001) | 11/15/2017 (2572491827149001) | 11/15/2017 (2572491827149001) | 11/27/2017 (VFORCE) (25724918) | 11/27/2017 (VFORCE) (25724918) |  |  | Jan Bicicchi 1-630-725-2310 jan_bicicchi@uhg.com | LESLIE ISAAC | leslie.isaac@optum.com | 44-186-578-7320 | 11/28/2017(Access) | 11/28/2017 |  | 12/08/2017 (25724918) | 12/08/2017 12/08/2017 (18528991.1) | 11/28/2017 |  | Completed Activated/Installed | N (25724918) N N (25724919) | U0101953 |  | Order Request 194692181 | NSPE0011712988
Completed |  | 5500 N SERVICE RD BURLINGTON, CA L7L6W6 CAN | MLPPPT1B-3.072MBS (6105982) DS-1-BEARER (6105983) | 12/20/2017: Order close. Disconnected 11/30/2017 | 9340111 |  | Private IP (6105982) Private IP (6105983) | 6105982 6105983 | 3.072 MBPS |  |  | W0Y34798 (6105982) W0Y35276 (6105983) W0Y35277 (6105983) | 05DHAT245446BLCA (5989809) | 2059443 | 2688 | PVC ID : 2059443 VPN Name : UnitedHealthGroup Router Name : TOROGE01 VRF Name : V286478:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65130 PE IP Address : 152.162.102.225 CE Address : 152.162.102.226 QoS - Egress Profile: R12 |  |  |  | WILLIAMS TELECOMMUNICATIONS UNKNOWN (5989809) | 11/10/2017 (5989809) |  | 12/11/2017 (5989809) |  |  |  | TECH ON DUTY 999 999 9999 | JOHN SERGOT 763 744 1582 | [6 empty] | 11/29/2017 (6105982) 11/29/2017 (6105983) | 12/11/2017 (6105982) 12/11/2017 (6105983) |  |  |  | N (6105982) N (6105983) | 00179802 |  | NSPE0011701061 | NSPE0011701061
Completed | CA250-02-IM Irvine CA | 4 TECHNOLOGY DR IRVINE, CA 92618-5314 US | 1 GBPS (25809503) | 04/16/2018: 04/16 Successfully activated | 194737852 | UnitedHealth Group- Monarch | Private IP - PIP (25809502) WAN Analysis Reporting (25809504) Access (25809503) | 25809502 25809504 25809503 | 1 GBPS (25809502) |  | 199562278 (Private IP (PIP)) 199562279 (WAN Analysis Reporting) 199562276 (Access) | C0133289/ADD (25809502) E5008985/ADD (25809503) |  | 5936704 | 70000 | PVC ID : 5936704 VPN Name : UHG-Monarch Router Name : LSA29E02 VRF Name : V976456:UHGMonarch Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65506 PE IP Address : 152.181.60.185 CE Address : 152.181.60.186 QoS - Egress Profile: G1 | 1000Base-SX-850nm (25809503) | 1000Base-SX (850nm, Multi Mode Fiber) (25809503) | Ethernet |  |  |  |  | 01/03/2018 (VFORCE) (25809503) | 02/05/2018 (VFORCE) (25809503) | DEMARCADDR - . DEMARCDET - Main telco Room in the MPOE Tagged - Accedian NID Port 3. |  | POOYAN HAGHIGHI 1-510-717-2602 phaghighi@mhealth.com | SANTOSH TENDOLKAR | stendolkar@mhealth.com | 1-562-382-7377 | 02/05/2018(Private IP - PIP) 02/05/2018(WAN Analysis Reporting) 02/05/2018(Access) | 04/16/2018 |  | 02/08/2018 (25809502) 02/06/2018 (25809503) | 03/12/2018 03/16/2018 | 02/05/2018 |  | Completed | N (25809502) N (25809504) N (25809503) | U0101953 | Jeopardy Notification 3 (01/17/2018) | Order Request 194737758 | NSPE0011743732
Completed | FL038-10-IM Miami FL | 2974 SW 8TH ST MIAMI, FL 33135-2827 US | 50 MBPS (25809607) | 04/18/2018: 04/17 Successfully activated | 194737933 | UNITED HEALTH GROUP | Private IP - PIP (25809606) WAN Analysis Reporting (25809608) Access (25809607) | 25809606 25809608 25809607 | 10 MBPS (25809606) |  | 199968542 (Private IP (PIP)) 199968543 (WAN Analysis Reporting) 199968540 (Access) | C4009462/ADD (25809606) E4025367/ADD (25809607) |  | 5936709 | 4500 | PVC ID : 5936709 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65255 PE IP Address : 152.176.21.21 CE Address : 152.176.21.22 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (25809607) | 1000Base-SX (850nm, Multi Mode Fiber) (25809607) | Ethernet | ATT (2580960789386601) | 11/20/2017 (2580960789386601) |  | 01/24/2018 (2580960789386601) | 01/25/2018 (VFORCE) (25809607) | 01/26/2018 (VFORCE) (25809607) | DEMARCDET - 1ST FLOOR TELCO ROOM SC PORT # 1 AND 2 SHOULD BE PORT #5 OF CIENNA 3930 |  | CRISTY ALFONSO 1-305-631-3000 calfonso@pcpmedicalgroup.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 01/26/2018(Private IP - PIP) 01/26/2018(WAN Analysis Reporting) 01/26/2018(Access) |  |  | 02/02/2018 (25809606) 01/31/2018 (25809607) | 01/02/2018 01/08/2018 | 01/26/2018 |  | Completed | N (25809606) N (25809608) N (25809607) | U0101953 |  | Order Request # 194737838 | NSPE0011743759
Completed | VA072-02-IM Richmond VA | 411 E FRANKLIN ST FL 2 RICHMOND, VA 23219-2221 US | 20 MBPS (26127412) | 04/13/2018: 04/13 Successfully activated | 194748928 | Richmond VA | Access (26127412) Private IP - PIP (26127411) WAN Analysis Reporting (26127413) | 26127412 26127411 26127413 | 10 MBPS (26127411) |  | 200803528 (Access) 200803530 (Private IP (PIP)) 200803531 (WAN Analysis Reporting) | E3048539/ADD (26127412) C3016673/ADD (26127411) | 48.KFGS.304218..CV (2612741231581801) | 5950393 | 5500 | PVC ID : 5950393 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64922 PE IP Address : 152.162.253.153 CE Address : 152.162.253.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26127412) | 1000Base-SX (850nm, Multi Mode Fiber) (26127412) | Ethernet | VERIZON (2612741231581801) | 01/17/2018 (2612741231581801) | 02/28/2018 (2612741231581801) | 02/27/2018 (2612741231581801) |  |  | DEMARCADDR - 411 E FRANKLIN ST, RICHMOND, VA DEMARCDET - 2ND FLOOR SUITE COMPUTER ROOM RACK MOUNTED NID TAGGED |  | Cindy King 1-804-643-5500 cking@douglasdev.com | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 02/27/2018(Access) 02/27/2018(Private IP - PIP) 02/27/2018(WAN Analysis Reporting) | 04/13/2018 |  | 03/09/2018 (26127412) 03/13/2018 (26127411) | 03/21/2018 03/27/2018 | 02/27/2018 |  | Completed | N (26127412) N (26127411) N (26127413) | U0101953 |  | NSPE0011752039 Order Request # 194748599 | NSPE0011752039
Completed | TX401-01-IM PHARR TX | 1104 W SAM HOUSTON BLVD PHARR, TX 78577 USA | 1.536 MBPS (IQBLKM9D) | 02/16/2018: 02/15 Background: TX401-01-IM PHARR, TX; NEW 3XT1 MLPPP; SWB; NO NID; NO MNS Status: Ready for activation Next action: Customer to plug and play. If they need assistance in activating this, they may call 866-829-9719 Who owns the next action: Customer (DTAC/GLP) Telco Circuit ID and Telco Demarcation: 38/HCGS/631241//SW : 1st floor telco room, Back board quad mount 1, slot 1, rj48c, tagged not extended. 38/HCGS/631205//SW: 1st floor, telco room, quad mount 1, slot 2, rj48c, tagged not extended. 38/HCGS/631206//SW: 1st floor, telco room, quad mount 1, slot3, rj48c, tagged not extended. | 9355223 |  | Private IP (IQBLKM9D) EVC/PVC Service (N.11577410.5939071) | IQBLKM9D N.11577410.5939071 | 4.608 MBPS | P2182453 |  | BCBLCJJ50001 (IQBLKM9D) BCBLCJJ50002 (IQBLKM9D) BCBLCJJ50003 (IQBLKM9D) | 38/HCGS/631241//SW (IQBLKM9D1MLWMB05) 38/HCGS/631205//SW (IQBLKM9D1MLWMB02) 38/HCGS/631204//SW (IQBLKM9D1MLWMB03) | 5939071 | 3000 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64914 PE IP Address : 68.138.143.153 CE Address : 68.138.143.154 QoS - Egress Profile: R12 PVC ID : 5939071 |  |  |  | ATT (IQBLKM9D1MLWMB05) ATT (IQBLKM9D1MLWMB02) ATT (IQBLKM9D1MLWMB03) | 02/06/2018 (IQBLKM9D1MLWMB05) 12/27/2017 (IQBLKM9D1MLWMB02) 01/25/2018 (IQBLKM9D1MLWMB03) | 02/12/2018 (IQBLKM9D1MLWMB05) 01/03/2018 (IQBLKM9D1MLWMB02) 02/01/2018 (IQBLKM9D1MLWMB03) | 02/14/2018 (IQBLKM9D1MLWMB05) 02/14/2018 (IQBLKM9D1MLWMB02) 02/14/2018 (IQBLKM9D1MLWMB03) |  |  |  |  | JASON OZER 0012109513251 2102501454 JOZER@WELLMED.NET |  |  |  | 02/15/2018 (IQBLKM9D) |  |  | 02/14/2018 (IQBLKM9D) | 02/28/2018 (IQBLKM9D) |  |  |  | N (IQBLKM9D) N (N.11577410.5939071) | 05017789 87584500 |  | NSPE0011758082 CW 194761272 | NSPE0011758082
Completed | C1628-01-IM Santa Clara, CA | 2805 LAFAYETTE ST SANTA CLARA, CA 95050-2639 US | 500 MBPS (25918695) | 01/30/2018: 01/29 Successfully activated | 194795452 | UHG | Private IP - PIP (25918694) WAN Analysis Reporting (25918696) Access (25918695) | 25918694 25918696 25918695 | 200 MBPS (25918694) |  | 202520113 (Private IP (PIP)) 202520114 (WAN Analysis Reporting) 202520111 (Access) | C5004065/ADD (25918694) E5009200/ADD (25918695) |  | 5941772 | 40000 | PVC ID : 5941772 VPN Name : UnitedHealthGroup Router Name : HAY9E02 VRF Name : Vb46944:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65206 PE IP Address : 68.138.90.141 CE Address : 68.138.90.142 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (25918695) | Ethernet | [5 empty] | 12/30/2017 (CCP) (25918694) 12/30/2017 (CCP) (25918695) |  |  | MARK POWLEY 1-909-605-8000 mpowley@nammcal.com | RANJI ADHIKAI | ranjit_adhikari@optum.com | 1-763-744-1957 | 01/11/2018(Private IP - PIP) 01/11/2018(WAN Analysis Reporting) 01/11/2018(Access) | 01/29/2018 |  | 01/22/2018 (25918694) 01/18/2018 (25918695) | 01/04/2018 01/10/2018 | 01/11/2018 |  | Completed | N (25918694) N (25918696) N (25918695) | U0101953 |  | NSPE0011778549 Order Request # 194792711 | NSPE0011778549
Completed | FL047-06-IM Miami, FL | 9100 S DADELAND BLVD STE 1250 MIAMI, FL 33156-7838 US | 200 MBPS (25918918) | 03/26/2018: 03/23 Successfully activated | 194795526 | Miami | Private IP - PIP (25918917) WAN Analysis Reporting (25918919) Access (25918918) | 25918917 25918919 25918918 | 80 MBPS (25918917) |  | 202785699 (Private IP (PIP)) 202785700 (WAN Analysis Reporting) 202785697 (Access) | C5004066/ADD (25918917) E5009201/ADD (25918918) |  | 5941781 | 40000 | PVC ID : 5941781 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64528 PE IP Address : 199.220.95.245 CE Address : 199.220.95.246 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (25918918) | Ethernet |  |  |  |  | 01/05/2018 (CCP) (25918917) 01/05/2018 (CCP) (25918918) | 01/09/2018 (CCP) (25918917) 01/09/2018 (CCP) (25918918) | Demarcation: The circuit`s handoff is at: Customer Data Room. IBM Cabinet.Media Converter port: MM where a hard loop was left. |  | EDDY HERNANDEZ 1-786-437-5305 eddy_hernandez@optum.com | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 01/11/2018(Private IP - PIP) 01/11/2018(WAN Analysis Reporting) 01/11/2018(Access) | 03/23/2018 |  | 01/19/2018 (25918917) 01/17/2018 (25918918) | 01/04/2018 01/10/2018 | 01/11/2018 |  | Completed | N (25918917) N (25918919) N (25918918) | U0101953 |  | NSPE0011780645 Order Request # 194795115 | NSPE0011780645
Completed | UTX43-08-IM Plano, TX | 2301 W PLANO PKWY STE 300 PLANO, TX 75075-8436 US | 20 MBPS | 12/15/2017: 12/14 Upgrade complete | 194798424 | UnitedHealthcare StudentResources | Internet Dedicated Services (25924515) Access | 25924515 | 20 MBPS (25924515) |  | 185094547 (Internet Dedicated Services) 185094583 | C3014579/NONE (25924515) |  | 5913182 | 0 | PVC ID : 5913182 VPN Name : Internet Router Name : GW16DFW9 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 26843 PE IP Address : 157.130.132.53 CE Address : 157.130.132.54 | 100Base-TX | 100Base-TX | Ethernet | [8 empty] | TODD CALYER 1-214-564-6061 tcalyer@uhcsr.com | Melissa Chapman | melissa.chapman@optum.com | 1-763-744-2114 | 12/14/2017(Internet Dedicated Services) | 12/14/2017 |  | 12/08/2017 (25924515) | 12/19/2017 | 12/14/2017 |  |  | N (25924515) N | U0101953 |  | NSPE0011782517 Order Request # 194797811 | NSPE0011782517
Completed | C1584-05-IM Carrollton, TX | 1649 W FRANKFORD RD CARROLLTON, TX 75007-4605 US | 1 GBPS (25933955) | 03/14/2018: 03/14 Successfully activated | 194805327 | UHG | Private IP - PIP (25933954) WAN Analysis Reporting (25933956) Access (25933955) | 25933954 25933956 25933955 | 500 MBPS (25933954) |  | 202950124 (Private IP (PIP)) 202950125 (WAN Analysis Reporting) 202950122 (Access) | C0134645/ADD (25933954) E5009240/ADD (25933955) |  | 5942555 | 450000 | PVC ID : 5942555 VPN Name : UHG-ECC Router Name : IAE9E01 VRF Name : V481056:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65404 PE IP Address : 206.115.83.185 CE Address : 206.115.83.186 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (25933955) | Ethernet |  |  |  |  | 12/29/2017 (CCP) (25933954) 12/29/2017 (CCP) (25933955) | 01/20/2018 (CCP) (25933954) 01/20/2018 (CCP) (25933955) | Telco Circuit ID: ea-ggyh-nrc-0011 Telco Demarcation: Fiber panel 1c.9.32 ports 13/14 |  | Edward Williams 1-469-877-5846 Edward.Williams@egscorp.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 01/22/2018(Private IP - PIP) 01/22/2018(WAN Analysis Reporting) 01/22/2018(Access) | 03/14/2018 |  | 01/12/2018 (25933954) 01/10/2018 (25933955) | 01/11/2018 01/17/2018 | 01/22/2018 |  | Completed | N (25933954) N (25933956) N (25933955) | U0101953 |  | NSPE0011783869 Order Request # 194799524 (C13) | NSPE0011783869
Completed | UMD14-08-IM Baltimore, MD | 2111 VAN DEMAN ST BALTIMORE, MD 21224-6609 US | 50 MBPS (25976658) | 04/06/2018: 04/05 Pending confirmation from customer if they are good with the circuit. | 194805945 | UMD14-05-IJ Baltimore, MD | WAN Analysis Reporting (25976659) Access (25976658) Private IP - PIP (25976657) | 25976659 25976658 25976657 | 20 MBPS (25976657) |  | 203382247 (WAN Analysis Reporting) 203381904 (Access) 203382246 (Private IP (PIP)) | C4009850/ADD (25976657) E4026119/ADD (25976658) | 38.KFGS.303053..CM (2597665815924201) | 5944379 | 9000 | PVC ID : 5944379 VPN Name : UnitedHealthGroup Router Name : RAY9E03 VRF Name : V534296:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64935 PE IP Address : 68.137.185.241 CE Address : 68.137.185.242 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25976658) | 1000Base-SX (850nm, Multi Mode Fiber) (25976658) | Ethernet | VERIZON (2597665815924201) | 12/18/2017 (2597665815924201) | 01/18/2018 (2597665815924201) | 02/22/2018 (2597665815924201) |  |  | DEMARCADDR - 2111 VAN DEMAN ST, BALTIMORE, MD DEMARCDET - MAIN DATA ROOM 1ST FLOOR WALL MOUNTED POSITION A...TAGGED |  | MICHAEL O'NEAL 1-301-977-7884 michael.oneal@am.jll.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 02/22/2018(WAN Analysis Reporting) 02/22/2018(Access) 02/22/2018(Private IP - PIP) |  |  | 03/02/2018 (25976657) 02/28/2018 (25976658) | 03/02/2018 02/26/2018 | 02/22/2018 |  | Completed | N (25976659) N (25976658) N (25976657) | U0101953 |  | NSPE0011787113 Order Request # 194805738 | NSPE0011787113
Completed | C1583-05-IM Sterling, VA | 21111 RIDGETOP CIR STERLING, VA 20166-6592 US | 1 GBPS (25935284) | 03/14/2018: 03/14 Successfully activated | 194805815 | C1583-01-IJ Sterling VA | Private IP - PIP (25935283) WAN Analysis Reporting (25935285) Access (25935284) | 25935283 25935285 25935284 | 500 MBPS (25935283) |  | 203021225 (Private IP (PIP)) 203021306 (WAN Analysis Reporting) 203021223 (Access) | C0134642/ADD (25935283) E5009241/ADD (25935284) |  | 5942582 | 250000 | PVC ID : 5942582 VPN Name : UHG-ECC Router Name : WA39E01 VRF Name : Vb35049:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65403 PE IP Address : 152.177.170.121 CE Address : 152.177.170.122 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (25935284) | Ethernet | [5 empty] | 01/25/2018 (CCP) (25935283) 01/25/2018 (CCP) (25935284) |  |  | ALEX KANTSIOS 1-571-214-0662 alex.kantsios@egscorp.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 02/08/2018(Private IP - PIP) 02/08/2018(WAN Analysis Reporting) 02/08/2018(Access) | 03/14/2018 |  | 02/15/2018 (25935283) 02/13/2018 (25935284) | 02/05/2018 02/09/2018 | 02/08/2018 |  | Completed | N (25935283) N (25935285) N (25935284) | U0101953 | Jeopardy Notification 1 (01/09/2018) | NSPE0011785665 Order Request # 194803877 (C13) | NSPE0011785665
Completed | VA012-02-IM McLean, VA | 8270 GREENSBORO DR MC LEAN, VA 22102-3800 US | 50 MBPS (26317818) | 03/05/2018: 03/05 Background: VA012-02-IM McLean, VA; New 20M/50M PIP-Eth; VzT; No NID; No MNS; Status: Ready for activation Next action: Customer to provide activation date and time allowing 3 business days advance notice Who owns the next action: Customer (BNE) Ticket: NA Telco Circuit ID: 36.KFGS.308248..CD Telco Demarcation: UPR,5,RM CLOSET,REAR WALL,,RJ48C,LP N,CAB N,,OTHER,REAR,OTHER,WALL | 194847055 | VA012-02-IM | Private IP - PIP (26317817) WAN Analysis Reporting (26317819) Access (26317818) | 26317817 26317819 26317818 | 20 MBPS (26317817) |  | 205414502 (Private IP (PIP)) 205414503 (WAN Analysis Reporting) 205414500 (Access) | C4010627/ADD (26317817) E4027844/ADD (26317818) | 36.KFGS.308248..CD (2631781832404501) | 5958660 | 15000 | PVC ID : 5958660 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64870 PE IP Address : 147.225.201.69 CE Address : 147.225.201.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26317818) | 1000Base-SX (850nm, Multi Mode Fiber) (26317818) | Ethernet | VERIZON (2631781832404501) | 02/20/2018 (2631781832404501) | 03/05/2018 (2631781832404501) | 03/02/2018 (2631781832404501) |  |  | DEMARCADDR - 8270 GREENSBORO DR, MCLEAN, VA DEMARCDET - UPR,5,RM CLOSET,REAR WALL,,RJ48C,LP N,CAB N,,OTHER,REAR,OTHER,WALL, |  | Sinclair Tamakloe 1-301-977-7884 stamakloe@qssinc.com | ED STILES | ed.stiles@optum.com | 1-770-767-8212 | 03/02/2018(Private IP - PIP) 03/02/2018(WAN Analysis Reporting) 03/02/2018(Access) |  |  | 03/14/2018 (26317817) 03/12/2018 (26317818) | 03/16/2018 03/22/2018 | 03/02/2018 |  | Completed | N (26317817) N (26317819) N (26317818) | U0101953 |  | NSPE0011815447 Order Request # 194846673 | NSPE0011815447
Completed | NV018-08-IM Las Vegas, NV | 2720 N TENAYA WAY LAS VEGAS, NV 89128-0424 US | 300 MBPS (26027198) | 07/09/2018: 07/05 Activated. Pending customer acceptance | 194850804 | NV018-05-IJ Las Vegas 100mg | Private IP - PIP (26027197) WAN Analysis Reporting (26027199) Access (26027198) | 26027197 26027199 26027198 | 200 MBPS (26027197) |  | 205704874 (Private IP (PIP)) 205704875 (WAN Analysis Reporting) 205704872 (Access) | C5004132/ADD (26027197) E5009392/ADD (26027198) | 33.KFGX.001608..COXC. (2602719872440701) | 5946539 | 110000 | PVC ID : 5946539 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64591 PE IP Address : 68.139.137.17 CE Address : 68.139.137.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26027198) | 1000Base-SX (850nm, Multi Mode Fiber) (26027198) | Ethernet | COX (2602719872440701) | 12/28/2017 (2602719872440701) | 01/31/2018 (2602719872440701) |  | 02/05/2018 (VFORCE) (26027198) | 02/06/2018 (VFORCE) (26027198) | DEMARCDET - 6th floor data room customer rack north locatation |  | TAUOA FALO 1-702-242-7654 tauoa.falo@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 02/06/2018(Private IP - PIP) 02/06/2018(WAN Analysis Reporting) 02/06/2018(Access) |  |  | 02/09/2018 (26027197) 02/07/2018 (26027198) | 02/07/2018 02/13/2018 | 02/06/2018 |  | Completed | N (26027197) N (26027199) N (26027198) | U0101953 |  | NSPE0011818342 Order Request # 194850688 | NSPE0011818342
Completed | NV039-08-IM North Las Vegas, NV | 2239 CRESTLINE LOOP NORTH LAS VEGAS, NV 89030-4101 US | 300 MBPS (26028696) | 07/12/2018: 07/11 Customer accepted the circuit. | 194851409 | NV039-02-IJ North Las Vegas | WAN Analysis Reporting (26028697) Access (26028696) Private IP - PIP (26028695) | 26028697 26028696 26028695 | 200 MBPS (26028695) |  | 205706398 (WAN Analysis Reporting) 205706395 (Access) 205706397 (Private IP (PIP)) | C5004134/ADD (26028695) E5009395/ADD (26028696) | 33.KFGX.001609..COXC. (2602869610230701) | 5946579 | 110000 | PVC ID : 5946579 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64826 PE IP Address : 147.225.169.109 CE Address : 147.225.169.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26028696) | 1000Base-SX (850nm, Multi Mode Fiber) (26028696) | Ethernet | COX (2602869610230701) | 01/24/2018 (2602869610230701) | 04/20/2018 (2602869610230701) |  | 04/17/2018 (VFORCE) (26028696) | 04/19/2018 (VFORCE) (26028696) | DEMARCDET - 1st flr server room port 114 |  | TAUOA FALO 1-702-303-7293 tauoa.falo@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 04/19/2018(WAN Analysis Reporting) 04/19/2018(Access) 04/19/2018(Private IP - PIP) | 07/10/2018 |  | 05/15/2018 (26028695) 05/11/2018 (26028696) | 05/14/2018 05/08/2018 | 04/19/2018 |  | Completed | N (26028697) N (26028696) N (26028695) | U0101953 | Jeopardy Notification 1 (01/22/2018) | NSPE0011818853 Order Request # 194851387 | NSPE0011818853
Completed | TX343-07-IM Corpus Christi, TX | 1711 S STAPLES ST CORPUS CHRISTI, TX 78404-3022 US | 50 MBPS (26042084) | 02/21/2018: 02/20 Successfully activated | 194856843 | TX343-02-IM | Private IP - PIP (26042083) WAN Analysis Reporting (26042085) Access (26042084) | 26042083 26042085 26042084 | 10 MBPS (26042083) |  | 205935272 (Private IP (PIP)) 205935273 (WAN Analysis Reporting) 205935270 (Access) | C4010027/ADD (26042083) E4026452/ADD (26042084) |  | 5947148 | 5000 | PVC ID : 5947148 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65243 PE IP Address : 68.139.127.17 CE Address : 68.139.127.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26042084) | 1000Base-SX (850nm, Multi Mode Fiber) (26042084) | Ethernet |  |  |  |  | 01/26/2018 (VFORCE) (26042084) | 01/26/2018 (VFORCE) (26042084) | DEMARCADDR - 1711 S STAPLES ST CORPUS CHRISTI TX DEMARCDET - INSIDE BLDG. RACK MOUNTED CIENA 3930 LIM-JIM HANDOFF PORTS 3/4. |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 01/26/2018(Private IP - PIP) 01/26/2018(WAN Analysis Reporting) 01/26/2018(Access) | 02/20/2018 |  | 03/27/2018 (26042083) 03/23/2018 (26042084) | 02/12/2018 02/16/2018 | 01/26/2018 |  | Completed | N (26042083) N (26042085) N (26042084) | U0101953 |  | NSPE0011822815 Order Request # 194855406 | NSPE0011822815
Completed | AL016-05-IM Tuscaloosa, AL; New 20M/100M PIP-Ethernet | 500 PAUL W BRYANT DR TUSCALOOSA, AL 35401-2057 US | 100 MBPS (26097219) | 04/11/2018: 04/10 Successfully activated | 194883572 | AL016-02-IJ Tuscaloosa, AL | Private IP - PIP (26097218) WAN Analysis Reporting (26097220) Access (26097219) | 26097218 26097220 26097219 | 20 MBPS (26097218) |  | 207158497 (Private IP (PIP)) 207158498 (WAN Analysis Reporting) 207158494 (Access) | C1066139/ADD (26097218) E4026695/ADD (26097219) | A3/KRGN/602420//SC (2609721916609701) | 5949181 | 10000 | PVC ID : 5949181 VPN Name : UnitedHealthGroup Router Name : B6S9E01 VRF Name : Vb34594:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64651 PE IP Address : 152.181.249.33 CE Address : 152.181.249.34 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26097219) | 1000Base-SX (850nm, Multi Mode Fiber) (26097219) | Ethernet | ATT (2609721916609701) | 01/11/2018 (2609721916609701) | 03/12/2018 (2609721916609701) | 03/09/2018 (2609721916609701) | 03/14/2018 (VFORCE) (26097219) | 03/13/2018 (VFORCE) (26097219) | DEMARCADDR - 500 PAUL W BRYANT DR TUSCALOOSA AL DEMARCDET - 1ST FLR TELCO ROOMWALL MOUNTED,TAGGED |  | AVA TIDWELL 1-205-324-4566 atidwell@nphc.net | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 03/13/2018(Private IP - PIP) 03/13/2018(WAN Analysis Reporting) 03/13/2018(Access) | 04/10/2018 |  | 03/21/2018 (26097218) 03/19/2018 (26097219) | 03/06/2018 03/12/2018 | 03/13/2018 |  | Completed | N (26097218) N (26097220) N (26097219) | U0101953 |  | NSPE0011843408 Order Request # 194883314 | NSPE0011843408
Completed | AZ034-02-IM Tucson, AZ | 6365 E TANQUE VERDE RD STE 120 TUCSON, AZ 85715-3848 US | 50 MBPS (26108612) | 08/29/2018: 08/28 Successfully activated | 194888282 | AZ034-02-IM | Access (26108612) Private IP - PIP (26108611) WAN Analysis Reporting (26108613) | 26108612 26108611 26108613 | 10 MBPS (26108611) |  | 207124964 (Access) 207124966 (Private IP (PIP)) 207124967 (WAN Analysis Reporting) | E4026731/ADD (26108612) C4010122/ADD (26108611) | 1C/KEFN/002784/LVLC (2610861232693301) | 5949510 | 30000 | PVC ID : 5949510 VPN Name : UnitedHealthGroup Router Name : WIT9E02 VRF Name : Vc49959:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65172 PE IP Address : 152.176.82.177 CE Address : 152.176.82.178 QoS - Egress Profile: R12 | 100Base-TX (26108612) | 100Base-TX (26108612) | Ethernet | LEVEL 3 (2610861232693301) | 01/18/2018 (2610861232693301) | 02/15/2018 (2610861232693301) | 02/13/2018 (2610861232693301) | 02/13/2018 (VFORCE) (26108612) | 02/13/2018 (VFORCE) (26108612) | DEMARCDET - 1st floow main telco wall mt omnitron slot 2 of 2 rj45 tagged |  | Deena Lynn 1-520-901-1415 Deena_Lynn@optum.com | Deven Patterson | deven.patterson@optum.com | 1-210-877-7969 | 02/13/2018(Access) 02/13/2018(Private IP - PIP) 02/13/2018(WAN Analysis Reporting) | 08/28/2018 |  | 02/22/2018 (26108612) 02/26/2018 (26108611) | 02/23/2018 03/01/2018 | 02/13/2018 |  | Completed | N (26108612) N (26108611) N (26108613) | U0101953 |  | NSPE0011844618 Order Request # 194885381 | NSPE0011844618
Completed | UFL42-07-IM St Petersburg, FL | 805 EXECUTIVE CENTER DR W ST PETERSBURG, FL 33702-2407 US | 50 MBPS (26136260) | 01/02/2019: 01/02 Activation scheduled 01/04/2019 10AM CST | 194902901 | STUDENT RESOURCES/UHC | Private IP - PIP (26136259) WAN Analysis Reporting (26136261) Access (26136260) | 26136259 26136261 26136260 | 50 MBPS (26136259) |  | 208216115 (Private IP (PIP)) 208216116 (WAN Analysis Reporting) 208216113 (Access) | C4010259/ADD (26136259) E4026949/ADD (26136260) | 1I/KEFN/004454/LVLC (2613626074246201) | 5950732 | 13000 | PVC ID : 5950732 VPN Name : UnitedHealthGroup Router Name : JAP3E01 VRF Name : V484472-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64751 PE IP Address : 152.183.120.153 CE Address : 152.183.120.154 QoS - Egress Profile: R12 | 100Base-TX (26136260) | 100Base-FX (1310nm, Single Mode Fiber) (26136260) | Ethernet | LEVEL 3 (2613626074246201) | 01/30/2018 (2613626074246201) | 06/11/2018 (2613626074246201) | 05/24/2018 (2613626074246201) | 05/29/2018 (VFORCE) (26136260) | 05/29/2018 (VFORCE) (26136260) | DEMARCDET - 2nd flr suite 220 server room coiled cable on rear wall RJ45 labelled with circuit ID |  | Douglas Alford 1-727-563-3445 dalford@uhcsr.com | Charlie Evangelio | charlie_evangelio@optum.com | 632-588-3409 | 05/29/2018(Private IP - PIP) 05/29/2018(WAN Analysis Reporting) 05/29/2018(Access) | 07/05/2018 |  | 06/20/2018 (26136259) 06/18/2018 (26136260) | 06/07/2018 06/13/2018 | 05/29/2018 |  | Completed | N (26136259) N (26136261) N (26136260) | U0101953 |  | NSPE0011856591 Order Request # 194901048 | NSPE0011856591
Completed | C1631-01-IM Salt Lake City, UT | 683 S 4150 W SALT LAKE CITY, UT 84104-4409 US | 1 GBPS (26143615) | 03/16/2018: 03/16 Background: C1631-01-IM Salt Lake City, UT; New 600M/1G PIP-Eth; XO Comm; NID; No MNS; Status: Ready for activation Next action: Customer to provide activation date and time allowing 3 business days advance notice Who owns the next action: Customer (BNE) Ticket: NA Telco Circuit ID: SL/L1XX/278010/ /TQW /ELK Telco Demarcation: Customer server room. XO rack RR:01.01.00.06 SH 09 JKS 15 & 16 Equipment Type: Cienna 6500 BEAS ID: USAUT32947718COV400001 / E5009670 BEAS Demarcation: customer rack Q2 -E1 Slot 38 | 194906385 | C1631-01-IM | Private IP - PIP (26143614) WAN Analysis Reporting (26143616) Access (26143615) | 26143614 26143616 26143615 | 600 MBPS (26143614) |  | 208399637 (Private IP (PIP)) 208399638 (WAN Analysis Reporting) 208399635 (Access) | C0136280/ADD (26143614) E5009670/ADD (26143615) | SL/L1XX/278010/ /TQW /ELK (2614361532947701) | 5951000 | 550000 | PVC ID : 5951000 VPN Name : UHG-ECC Router Name : SLY9E01 VRF Name : V466953:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65455 PE IP Address : 152.183.150.141 CE Address : 152.183.150.142 QoS - Egress Profile: C13 | 1000Base-LX-1310nm (26143615) | 1000Base-SX (850nm, Multi Mode Fiber) (26143615) | Ethernet | XO (2614361532947701) | 01/19/2018 (2614361532947701) | 02/21/2018 (2614361532947701) | 03/14/2018 (2614361532947701) | 03/16/2018 (VFORCE) (26143615) | 03/16/2018 (VFORCE) (26143615) | DEMARCDET - Customer server room. XO rack RR:01.01.00.06 SH 09 JKS 15 & 16 |  | DAN KEPPLER 1-801-257-6363 dan.keppler@teleperformance.com | Erwin Edoria | erwin_edoria@optum.com | 632-588-3204 | 03/16/2018(Private IP - PIP) 03/16/2018(WAN Analysis Reporting) 03/16/2018(Access) |  |  | 03/21/2018 (26143614) 03/19/2018 (26143615) | 04/20/2018 04/26/2018 | 03/16/2018 |  | Completed | N (26143614) N (26143616) N (26143615) | U0101953 | Jeopardy Notification 1 (03/09/2018) | NSPE0011857863 Order Request # 194902923 | NSPE0011857863
Completed | TX777-11-IM Dallas, TX | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US |  | 02/18/2019 Successfully activated | 194906445 | TX777-05-IJ Student Resources Internet T1 | Access (26143691) Private IP - PIP (26143690) | 26143691 26143690 | 200 MBPS (26143690) |  | 208192495 (Access) 208192497 (Private IP (PIP)) | E5009672/ADD (26143691) C1066785/ADD (26143690) |  | 5951006 | 50000 | PVC ID : 5951006 VPN Name : UHG-OFE Router Name : 9O4XE02 VRF Name : Vb74843-UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65519 PE IP Address : 152.162.251.173 CE Address : 152.162.251.174 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (26143691) | Ethernet | [8 empty] | TOM KRENN 1-763-744-3141 tom_krenn@optum.com | TOM KRENN | tom_krenn@optum.com | 1-763-744-3141 | 02/22/2018(Access) 02/22/2018(Private IP - PIP) | 02/18/2019 |  | 03/02/2018 (26143691) 03/02/2018 (26143690) | 02/22/2018 | 02/23/2018 |  |  | N (26143691) N (26143690) | U0101953 |  | NSPE0011857372 Order Request # 194902050 C1 | NSPE0011857372
Completed | VA729-02-IM Ashburn, VA | 44480 HASTINGS DR ASHBURN, VA 20147-6043 US | 1 GBPS (26217531) | 04/23/2018: 04/20 Successfully activated | 194927993 | VA729-02-IM | Private IP - PIP (26217530) WAN Analysis Reporting (26217532) Access (26217531) | 26217530 26217532 26217531 | 500 MBPS (26217530) |  | 210045072 (Private IP (PIP)) 210045073 (WAN Analysis Reporting) 210045070 (Access) | C0136891/ADD (26217530) E5009873/ADD (26217531) | 46.KFGS.304270..CV (2621753179531601) | 5954071 | 250000 | PVC ID : 5954071 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64918 PE IP Address : 152.183.81.165 CE Address : 152.183.81.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26217531) | 1000Base-SX (850nm, Multi Mode Fiber) (26217531) | Ethernet | VERIZON (2621753179531601) | 02/01/2018 (2621753179531601) | 02/14/2018 (2621753179531601) | 02/13/2018 (2621753179531601) |  |  | DEMARCADDR - 44480 HASTINGS DR, ASHBURN, VA DEMARCDET - 1ST FLR, DATA CENTER, ROOM FAC, WALL MOUNTED, UNIT 7, TAGGED |  | EDWARD JONES 1-719-425-4044 edward.jones@optum.com | EDWARD JONES | edward.jones@optum.com | 1-719-425-4044 | 02/13/2018(Private IP - PIP) 02/13/2018(WAN Analysis Reporting) 02/13/2018(Access) | 04/20/2018 |  | 02/23/2018 (26217530) 02/21/2018 (26217531) | 02/28/2018 03/06/2018 | 02/13/2018 |  | Completed | N (26217530) N (26217532) N (26217531) | U0101953 |  | NSPE0011873543 Order Request # 194927234 | NSPE0011873543
Completed | CO054-01-IM Greenwood Village, CO | 6251 GREENWOOD PLAZA BLVD STE 300 GREENWOOD VILLAGE, CO 80111-4808 US | 50 MBPS (26215230) | 05/04/2018: 05/04 Need to rescheduled activation. Customer requested 100Base-FX MMF but customer is currently using 1000Base-SX. Customer to verify handoff. | 194946577 | Optum-RMHP | Private IP - PIP (26215229) WAN Analysis Reporting (26215231) Access (26215230) | 26215229 26215231 26215230 | 10 MBPS (26215229) |  | 210655149 (Private IP (PIP)) 210655150 (WAN Analysis Reporting) 210655147 (Access) | C4010399/ADD (26215229) E4027282/ADD (26215230) | 1V/KEFN/004755/LVLC (2621523033321301) | 5953983 | 25000 | PVC ID : 5953983 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64917 PE IP Address : 152.181.255.181 CE Address : 152.181.255.182 QoS - Egress Profile: R12 | 100Base-FX (26215230) | 100Base-FX (1310nm, Multi Mode Fiber) (26215230) | Ethernet | LEVEL 3 (2621523033321301) | 02/01/2018 (2621523033321301) | 03/19/2018 (2621523033321301) | 03/19/2018 (2621523033321301) | 03/20/2018 (VFORCE) (26215230) | 03/20/2018 (VFORCE) (26215230) | DEMARCDET - 3rd Floor, Suite 300, server room, rack 2, RMU 25,M CISCO ASR 920 FDP port 1 tagged with ckt. |  | Sam Orr 1-720-493-2056 sam.orr@rmhp.org | ED STILES | ed.stiles@optum.com | 1-770-767-8212 | 03/23/2018(Private IP - PIP) 03/23/2018(WAN Analysis Reporting) 03/23/2018(Access) |  |  | 03/01/2018 (26215229) 02/27/2018 (26215230) | 03/13/2018 03/19/2018 | 03/23/2018 |  | Completed | N (26215229) N (26215231) N (26215230) | U0101953 |  | NSPE0011881669 Order Request # 194939678 | NSPE0011881669
Completed | VA730-02-IM Ashburn, VA | 44664 GUILFORD DR ASHBURN, VA 20147-6042 US | 1 GBPS (26215666) | 06/05/2018: 06/05 Successfully activated | 194946910 | VA730-02-IM | Private IP - PIP (26215665) WAN Analysis Reporting (26215667) Access (26215666) | 26215665 26215667 26215666 | 500 MBPS (26215665) |  | 211117887 (Private IP (PIP)) 211117888 (WAN Analysis Reporting) 211117885 (Access) | C0136915/ADD (26215665) E5009851/ADD (26215666) |  | 5953993 | 350000 | PVC ID : 5953993 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64933 PE IP Address : 152.183.191.249 CE Address : 152.183.191.250 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (26215666) | Ethernet | [5 empty] | 02/21/2018 (CCP) (26215665) 02/21/2018 (CCP) (26215666) |  |  | David Roush 1-202-266-6811 support@ragingwire.com | Sonha Mroczysnki | sonja_d_mroczynski@optum.com | 1-763-744-3000 | 02/27/2018(Private IP - PIP) 02/27/2018(WAN Analysis Reporting) 02/27/2018(Access) | 06/04/2018 |  | 02/28/2018 (26215665) 02/26/2018 (26215666) | 02/27/2018 03/05/2018 | 02/27/2018 |  | Completed | N (26215665) N (26215667) N (26215666) | U0101953 |  | NSPE0011883103 Order Request # 194941774 | NSPE0011883103
Completed | C1630-02-IM Charleston, WV | 1900 KANAWHA BLVD E CHARLESTON, WV 25305-0009 US | 1 GBPS (26215940) | 06/06/2018: 06/05 Successfully activated | 194947033 | OPTUM STATE GOVT | Private IP - PIP (26215939) WAN Analysis Reporting (26215941) Access (26215940) | 26215939 26215941 26215940 | 100 MBPS (26215939) |  | 211293682 (Private IP (PIP)) 211293683 (WAN Analysis Reporting) 211293680 (Access) | C0136855/ADD (26215939) E5009852/ADD (26215940) | 50/KRGN/800454//FVNC/ (2621594031958901) | 5954005 | 50000 | PVC ID : 5954005 VPN Name : UHG-OFE Router Name : RIJ9E03 VRF Name : Vc19168:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65535 PE IP Address : 152.164.78.125 CE Address : 152.164.78.126 QoS - Egress Profile: G1 | 1000Base-SX-850nm (26215940) | 1000Base-LX (1310nm Single Mode Fiber) (26215940) | Ethernet | FRONTIER (2621594031958901) | 02/01/2018 (2621594031958901) | 03/02/2018 (2621594031958901) | 02/21/2018 (2621594031958901) | 04/04/2018 (VFORCE) (26215940) | 04/04/2018 (VFORCE) (26215940) | DEMARCADDR - 1900 E KANAWHA BLVD CHARLESTON WV DEMARCDET - NID IS AT DEMARCATION IN TELCO ROOM |  | Michael Ebert 1-304-558-7365 michael.ebert@wv.gov | TOM KRENN | tom_krenn@optum.com | 1-763-744-3141 | 04/04/2018(Private IP - PIP) 04/04/2018(WAN Analysis Reporting) 04/04/2018(Access) | 06/05/2018 |  | 04/11/2018 (26215939) 04/09/2018 (26215940) | 04/10/2018 04/16/2018 | 04/04/2018 |  | Completed | N (26215939) N (26215941) N (26215940) | U0101953 | Jeopardy Notification 4 (03/24/2018) | NSPE0011884659 Order Request # 194944550 | NSPE0011884659
Completed | TX413-01-IM Edinburg, TX | 1501 S CLOSNER BLVD EDINBURG, TX 78539-5669 US | 50 MBPS (26240521) | 03/22/2018: Background: TX413-01-IM Edinburg, TX; New 10M/50M PIP-Eth; AT&T; NID; No MNS; Status: FOC 4/2 Next action: Circuit delivery Who owns the next action: AT&T | 194961448 | Wellmed | Private IP - PIP (26240520) WAN Analysis Reporting (26240522) Access (26240521) | 26240520 26240522 26240521 | 10 MBPS (26240520) |  | 211881143 (Private IP (PIP)) 211881164 (WAN Analysis Reporting) 211881141 (Access) | C4010466/ADD (26240520) E4027428/ADD (26240521) | 38/KRGN/613614//SW (2624052133549801) | 5955308 | 5000 | PVC ID : 5955308 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65093 PE IP Address : 68.139.42.189 CE Address : 68.139.42.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26240521) | 1000Base-SX (850nm, Multi Mode Fiber) (26240521) | Ethernet | ATT (2624052133549801) | 03/16/2018 (2624052133549801) | 04/02/2018 (2624052133549801) | 03/27/2018 (2624052133549801) | 03/28/2018 (VFORCE) (26240521) | 03/28/2018 (VFORCE) (26240521) | DEMARCADDR - 1501 S CLOSNER BLVD EDINBURG TX DEMARCDET - 1ST FLOOR,SERVER ROOM, W/M SLIM BOX, PORT 1 TAGGED |  | Jason Ozer 1-210-951-3251 jozer@wellmed.net | Sushil Gautam | sushil_gautam@uhc.com | 1-612-855-7475 | 03/28/2018(Private IP - PIP) 03/28/2018(WAN Analysis Reporting) 03/28/2018(Access) |  |  | 04/11/2018 (26240520) 04/09/2018 (26240521) | 04/26/2018 05/02/2018 | 03/28/2018 |  | Completed | N (26240520) N (26240522) N (26240521) | U0101953 | Jeopardy Notification 2 (03/15/2018) | NSPE0011895076 Order Request # 194960727 | NSPE0011895076
Completed | Chaska MN to Dallas TX; | 1707 W CREEK LN CHASKA, MN 55318 USA | 10G-LANP-10GBSUU (6134686) | 06/07/2018: Ready to activate; LOA provided to UHG for both location A and Z | 9449173 |  | US Private Line (6134686) | 6134686 | 10G-LANP-10GBSUU (6134686) |  |  | W1D11401 (6134686) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 05/29/2018 (6134686) |  |  | 05/30/2018 (6134686) | 05/25/2018 (6134686) |  |  |  | N (6134686) | 00268272 |  | New 10G USPL;
Completed | OH730-02-IM Westerville, OH | 35 COLLEGEVIEW RD WESTERVILLE, OH 43081-1463 US | 1 GBPS (26247314) | 10/22/2018: 10/22 Activation scheduled 10/25/2018 23:00 EST | 194966005 | OH730-02-IJ Westerville, OH | Access (26247314) | 26247314 |  |  | 212083541 (Access) | E5009996/ADD (26247314) | CS/L1XX/279601/ /TQW /ELK (2624731416717301) |  |  |  | 1000Base-SX-850nm (26247314) | 1000Base-SX (850nm, Multi Mode Fiber) (26247314) | Ethernet | XO (2624731416717301) | 02/06/2018 (2624731416717301) | 05/04/2018 (2624731416717301) | 05/04/2018 (2624731416717301) | 06/11/2018 (VFORCE) (26247314) | 06/11/2018 (VFORCE) (26247314) | DEMARCDET - :row 6 self 1 slot 1 port 7 |  | Kevin Stykemain 1-614-212-8302 Kevin.Stykemain@optum.com | ED STILES | ed.stiles@optum.com | 1-770-767-8212 | 06/12/2018(Access) | 10/25/2018 |  | 06/12/2018 (26247314) | 07/16/2018 | 06/12/2018 |  |  | N (26247314) | U0101953 | Jeopardy Notification 2 (06/05/2018) | NSPE0011897639 Order Request # 194964210 | NSPE0011897639
Completed | GA721-02-IM Suwanee, GA | 300 SATELLITE BLVD NW SUWANEE, GA 30024-7123 US | 1 GBPS (26247312) | 10/22/2018: 10/22 Activation scheduled 10/25/2018 23:00 EST | 194966012 | GA721-02-IJ Catamaran Suwanee, GA | Access (26247312) | 26247312 |  |  | 212083543 (Access) | E5009998/ADD (26247312) | [5 empty] | 1000Base-SX (850nm, Multi Mode Fiber) (26247312) | Ethernet | [5 empty] | 02/21/2018 (CCP) (26247312) |  |  | Brandon Cannon 1-678-835-5000 brandon.cannon@optum.com | ED STILES | ed.stiles@optum.com | 1-763-361-7959 | 06/12/2018(Access) |  |  | 03/07/2018 (26247312) | 03/05/2018 | 06/12/2018 |  |  | N (26247312) | U0101953 |  | 194966005 | NSPE0011897639
Completed | P2P 1G Eth MPL Chaska MN to Cologne MN | 1707 W CREEK LN CHASKA, MN 55318 USA | 1GEMPL-WL-PP (6135743) | 03/23/2018: Background: P2P 1G Eth MPL Chaska MN to Cologne MN; New 1Gig Ethernet Protected MPL Status Mux & C L complete FOC 3/27 | 9452415 |  | Metro Private Line (6135743) | 6135743 | 1GEMPL-WL-PP (6135743) |  |  | W1D11510 (6135743) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 03/28/2018 (6135743) | 03/29/2018 |  | 04/02/2018 (6135743) | 05/04/2018 (6135743) |  |  |  | N (6135743) | 00198894
Completed | P2P 1G Eth MPL Plymouth MN to Minnerapolis MN | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 1GEMPL-WL-PP (6135748) | 03/30/2018: Background: P2P MPL PLYMOUTH MN TO MINNERAPOLIS MN; NEW 1GIG ETHERNET PROTECTED MPL; VzB Status: Pending end to end testing | 9452471 |  | Metro Private Line (6135748) | 6135748 | 1GEMPL-WL-PP (6135748) |  |  | W1D11511 (6135748) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | new circuit gd-jcfg-511-0001 to lower right fdb jack 5 (in same bay 7.0q1) which takes circuit to demark in bay 7m fdb FB1 jack a5 | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | WILLIAM GOSS 763 744 1528 WILLIAM_GOSS@OPTUM.COM |  |  |  | 03/30/2018 (6135748) |  |  | 04/06/2018 (6135748) | 05/04/2018 (6135748) |  |  |  | N (6135748) | 00268272
Completed | DC006-02-IM Washington, DC | 2445 M ST NW WASHINGTON, DC 20037-1435 US | 200 MBPS (26473671) | 07/24/2018: 07/23 Successfully activated | 195001139 | Optum Insight | Private IP - PIP (26473670) WAN Analysis Reporting (26473672) Access (26473671) | 26473670 26473672 26473671 | 150 MBPS (26473670) |  | 213998423 (Private IP (PIP)) 213998424 (WAN Analysis Reporting) 213998421 (Access) | C5004557/ADD (26473670) E5010592/ADD (26473671) | 36.KFGS.308364..CD (2647367133958001) | 5967479 | 90000 | PVC ID : 5967479 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65105 PE IP Address : 68.139.122.21 CE Address : 68.139.122.22 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (26473671) | 1000Base-LX (1310nm Single Mode Fiber) (26473671) | Ethernet | VERIZON (2647367133958001) | 03/19/2018 (2647367133958001) | 04/06/2018 (2647367133958001) | 04/05/2018 (2647367133958001) |  |  | DEMARCDET - c1 level main telco room, rack mount in first rack, tagged |  | Ethan Harris 1-202-568-7164 HarrisE@advisory.com | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 04/05/2018(Private IP - PIP) 04/05/2018(WAN Analysis Reporting) 04/05/2018(Access) | 07/23/2018 |  | 04/17/2018 (26473670) 04/13/2018 (26473671) | 04/12/2018 04/18/2018 | 04/05/2018 |  | Completed | N (26473670) N (26473672) N (26473671) | U0101953 |  | NSPE0011920391 Order Request # 194999698 | NSPE0011920391
Completed | PA134-02-IJ Plymouth, PA | 620 W GERMANTOWN PIKE PLYMOUTH MEETING, PA 19462-1068 US | 50 MBPS (26436922) | 06/11/2018: 06/08 Successfully activated | 195025631 | PA134-02-IJ | WAN Analysis Reporting (26436923) Access (26436922) Private IP - PIP (26436921) | 26436923 26436922 26436921 | 10 MBPS (26436921) |  | 215057123 (WAN Analysis Reporting) 215057120 (Access) 215057122 (Private IP (PIP)) | C4010972/ADD (26436921) E4028680/ADD (26436922) | 11.KFGS.308752..PA (2643692234131001) | 5966057 | 10000 | PVC ID : 5966057 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65171 PE IP Address : 68.139.49.245 CE Address : 68.139.49.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26436922) | 1000Base-SX (850nm, Multi Mode Fiber) (26436922) | Ethernet | VERIZON (2643692234131001) | 03/12/2018 (2643692234131001) | 03/22/2018 (2643692234131001) | 03/27/2018 (2643692234131001) | 04/03/2018 (VFORCE) (26436922) | 04/03/2018 (VFORCE) (26436922) | DEMARCADDR - 620 W GERMANTOWN PKE, PLYMOUTH, PA DEMARCDET - DEMARC - 2ND FL DATA RM, WALL MOUNTED NID #1, TAGGED BOTH ID'S, NOT EXT. |  | Carmen Phillips 1-484-690-0742 PhillipC@advisory.com | Larry Walsh | larry_l_walsh@optum.com | 1-317-715-7773 | 04/03/2018(WAN Analysis Reporting) 04/03/2018(Access) 04/03/2018(Private IP - PIP) | 06/13/2018 |  | 04/05/2018 (26436921) 04/03/2018 (26436922) | 04/10/2018 04/04/2018 | 04/03/2018 |  | Completed | N (26436923) N (26436922) N (26436921) | U0101953 | Jeopardy Notification 1 (03/21/2018) | NSPE0011933243 Order Request # 195025481 | NSPE0011933243
Completed | Change VPN to UHG-ECC | 6900 S PEORIA ST CENTENNIAL, CO 80112-4137 US | 500 MBPS | 02/26/2018: 02/26 Background: VPN change to UHG-ECC Status: Change deployed Next action: NA Who owns the next action: NA Ticket: NA | 195032225 | UHG- Trizetto | Private IP - PIP (26352910) Access WAN Analysis Reporting (26352912) | 26352910 26352912 | 200 MBPS (26352910) |  | 197285738 (Private IP (PIP)) 197285736 197285739 (WAN Analysis Reporting) | C5003879/NONE (26352910) |  | 5930332 | 90000 | PVC ID : 5930332 VPN Name : UHG-ECC Router Name : DNJXE01 VRF Name : V595692-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65535 PE IP Address : 199.220.23.101 CE Address : 199.220.23.102 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | BUDDY JEROME 1-303-495-7104 george.jerome@cognizant.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 02/27/2018(Private IP | 02/27/2018 |  | 02/23/2018 (26352910) | 03/06/2018 03/06/2018 (19608601.1) | 02/27/2018 |  | Completed Activated/Installed | N (26352910) N N (26352912) | U0101953 |  | Order Request # 195032231 | NSPE0011937348
Completed | TN048-02-IJ Nashville, TN | 3102 WEST END AVE STE 800 NASHVILLE, TN 37203-1382 US | 50 MBPS (26362186) | 06/28/2018: 06/27 Successfully activated | 195038932 | Advisory Board | Private IP - PIP (26362185) WAN Analysis Reporting (26362187) Access (26362186) | 26362185 26362187 26362186 | 20 MBPS (26362185) |  | 215654558 (Private IP (PIP)) 215654559 (WAN Analysis Reporting) 215654556 (Access) | C4010713/ADD (26362185) E4028064/ADD (26362186) | 31.KGGS.003084..CBCL.. (2636218634156502) | 5961501 | 13000 | PVC ID : 5961501 VPN Name : UnitedHealthGroup Router Name : NSVLXE01 VRF Name : V558718-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65142 PE IP Address : 152.162.192.53 CE Address : 152.162.192.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26362186) | 1000Base-SX (850nm, Multi Mode Fiber) (26362186) | Ethernet | COMCAST (2636218634156502) | 02/27/2018 (2636218634156502) | 04/04/2018 (2636218634156502) |  | 04/04/2018 (VFORCE) (26362186) | 04/04/2018 (VFORCE) (26362186) | Telco Circuit ID: 31.KGGS.003084..CBCL.. Telco Demarcation: 8th FL In server Room Left most Rack; Right between fiber tray labelled with COMCAST Cienna 3916 - Port 1 UnTagged at the customer premise BEAS ID: USATN34156565COV400001 / E4028064 BEAS Demarcation: Overture mounted in cust 8th floor server room next to LRC dmarc |  | Nick Cunningham 1-615-760-7676 cunningn@advisory.com | Keithley Huggins | keithleyhuggins@optum.com | 1-678-600-5136 | 04/04/2018(Private IP - PIP) 04/04/2018(WAN Analysis Reporting) 04/04/2018(Access) | 06/27/2018 |  | 04/17/2018 (26362185) 04/13/2018 (26362186) | 04/06/2018 04/12/2018 | 04/04/2018 |  | Completed | N (26362185) N (26362187) N (26362186) | U0101953 |  | NSPE0011941521 Order Request # 195037224 | NSPE0011941521
Completed | TX406-02-IM Austin, TX | 12357 RIATA TRACE PKWY AUSTIN, TX 78727-7171 US | 100 MBPS (26396334) | 07/12/2018: 07/12 Successfully activated | 195058759 | Advisory Board | WAN Analysis Reporting (26396335) Access (26396334) Private IP - PIP (26396333) | 26396335 26396334 26396333 | 80 MBPS (26396333) |  | 216246009 (WAN Analysis Reporting) 216246006 (Access) 216246008 (Private IP (PIP)) | C1068505/ADD (26396333) E4028380/ADD (26396334) | TX/KXFN/009043/LVLC (2639633434305701) | 5963728 | 50000 | PVC ID : 5963728 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65154 PE IP Address : 152.185.201.45 CE Address : 152.185.201.46 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (26396334) | 1000Base-SX (850nm, Multi Mode Fiber) (26396334) | Ethernet | LEVEL 3 (2639633434305701) | 03/19/2018 (2639633434305701) | 06/28/2018 (2639633434305701) | 07/05/2018 (2639633434305701) | 07/06/2018 (VFORCE) (26396334) |  | DEMARCDET - X |  | Mark Garcia 1-512-681-2335 mark.garcia@advisory.com | Larry Walsh | larry_l_walsh@optum.com | 1-317-715-7773 | 07/07/2018(WAN Analysis Reporting) 07/07/2018(Access) 07/07/2018(Private IP - PIP) | 07/12/2018 |  | 07/16/2018 (26396333) 07/12/2018 (26396334) | 08/21/2018 08/15/2018 | 07/06/2018 |  | Completed | N (26396335) N (26396334) N (26396333) | U0101953 |  | NSPE0011952594 Order Request # 195052868 | NSPE0011952594
Completed | NJ139-02-IM Pine Brook, NJ | 19 CHAPIN RD PINE BROOK, NJ 07058-9385 US | 50 MBPS (26932099) | 07/23/2018: Background: NJ139-02-IM Pine Brook; New 10M/50M PIP-Eth; VzT; No NID; No MNS; Status Site ready FOC 7/24 | 195064464 | NJ139-02-IM | Private IP - PIP (26932098) WAN Analysis Reporting (26932100) Access (26932099) | 26932098 26932100 26932099 | 50 MBPS (26932098) |  | 216862110 (Private IP (PIP)) 216862111 (WAN Analysis Reporting) 216862108 (Access) | C4012748/ADD (26932098) E4032388/ADD (26932099) | .KFGS.310768..NJ (2693209934402901) | 5984366 | 5000 | PVC ID : 5984366 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64850 PE IP Address : 68.138.74.9 CE Address : 68.138.74.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26932099) | 1000Base-SX (850nm, Multi Mode Fiber) (26932099) | Ethernet | VERIZON (2693209934402901) | 07/19/2018 (2693209934402901) | 07/24/2018 (2693209934402901) | 07/25/2018 (2693209934402901) |  |  | DEMARCADDR - 19 CHAPIN RD, MTVIL, NJ DEMARCDET - GROUND LEVEL MAIN TELCO ROOM WALL MOUNTED TAGGED (PER IT VENDOR JERRY, THEY WL RUN EXTENSION) |  | Steven Ambrosino 1-516-220-4505 sambrosino@ambrosinocorp.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 07/26/2018(Private IP - PIP) 07/26/2018(WAN Analysis Reporting) 07/26/2018(Access) |  |  | 08/02/2018 (26932098) 07/31/2018 (26932099) | 08/15/2018 08/21/2018 | 07/26/2018 |  | Completed | N (26932098) N (26932100) N (26932099) | U0101953 | Jeopardy Notification 1 (07/06/2018) | NSPE0011959419 Order Request # 195062722 | NSPE0011959419
Completed | Chaska-73c Cologne, MN | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 1000 MBPS (IQBLLJGY) | 09/04/2018: 09/04 Successfully activated | 9474447 |  | Private IP Port Only (IQBLLJGY) | IQBLLJGY | 200 MBPS | P2189060 |  | BOBLCS7M0001 (IQBLLJGY) |  |  | 50000 | VPN Name : UHG-OFE Router Name : MZZ9E01 VRF Name : Vc13143:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65517 PE IP Address : 147.225.90.197 CE Address : 147.225.90.198 QoS - Egress Profile: R12 | [11 empty] | JAMES CRAWFORD 0017635952550 JAMES.CRAWFORD@VERIZON.COM |  |  |  | 03/29/2018 (IQBLLJGY) |  |  | 04/19/2018 (IQBLLJGY) | 04/19/2018 (IQBLLJGY) |  |  |  | N (IQBLLJGY) | 05650532 |  | NSPE0011956784 CW 195058952 | NSPE0011956784
Completed | ElkRiver511 Minneapolis, MN | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 1000 MBPS (IQBLLJHM) | 04/09/2018: Order ready to activate LOA sent to customer | 9474448 |  | Private IP Port Only (IQBLLJHM) | IQBLLJHM | 200 MBPS | P2189072 |  | BOBLCS7X0001 (IQBLLJHM) |  | 5964449 | 50000 | PVC ID : 5964449 VPN Name : UHG-OFE Router Name : MN39E01 VRF Name : Vc13322:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64995 PE IP Address : 152.177.19.85 CE Address : 152.177.19.86 QoS - Egress Profile: R12 | [9 empty] | new circuit gd-jcfg-511-0001 to lower right fdb jack 5 (in same bay 7.0q1) which takes circuit to demark in bay 7m fdb FB1 jack a5 |  | JAMES CRAWFORD 0017635952550 JAMES.CRAWFORD@VERIZON.COM |  |  |  | 03/30/2018 (IQBLLJHM) |  |  | 04/20/2018 (IQBLLJHM) | 04/20/2018 (IQBLLJHM) |  |  |  | N (IQBLLJHM) | 05650532 |  | NSPE0011956804 CW 195058962 | NSPE0011956804
Completed | AK010-05-CJ Anchorage, AK | 310 K ST ANCHORAGE, AK 99501-2043 USA 6831 ARCTIC BLVD ANCHORAGE, AK 99518 | MLPPPT1B-4.608MBS (6147063) 1.544 MBPS (OQBLLJ9Y) DS-1-BEARER (6147067) DS-1-BEARER (6147064) | 05/03/2018: Disco completed 4/9/18 | 9477205 |  | Private IP (6147063) Private IP (OQBLLJ9Y) Private IP (6147067) Private IP (6147064) | 6147063 OQBLLJ9Y 6147067 6147064 | 4.608 MBPS 1.544 MBPS (OQBLLJ9Y) | P2045994 |  | W1A72836 (6147063) MGBK3DWH0001 (OQBLLJ9Y) MGBK3DWH0002 (OQBLLJ9Y) MGBK3DWH0003 (OQBLLJ9Y) W1A72824 (6147067) W1B03451 (6147067) W1A72823 (6147064) |  | 5423041 | 768768 | PVC ID : 5423041 VPN Name : UnitedHealthGroup Router Name : ANCG3E01 VRF Name : V726744-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65446 PE IP Address : 68.136.254.57 CE Address : 68.136.254.58 QoS - Egress Profile: R12 |  |  |  | WILLIAMS TELECOMMUNICATIONS | [6 empty] | TECH ON DUTY 907 999 9999 999 999 9999 | FRANK WILLIAMS TOM RYAN 907 365 9522 0019075656689 FRANK_WILLIAMS@UHC.COM |  |  |  | 04/09/2018 (OQBLLJ9Y) | 04/09/2018 | 04/09/2018 | 04/09/2018 (6147063) 04/09/2018 (OQBLLJ9Y) 04/09/2018 (6147067) 04/09/2018 (6147064) | 03/31/2018 (6147063) 04/09/2018 (OQBLLJ9Y) 03/31/2018 (6147067) 03/31/2018 (6147064) |  |  |  | N (6147063) N (OQBLLJ9Y) N (6147067) N (6147064) | 00260967 05028501 00219957 00259048 |  | NSPE0011951223 | NSPE0011951223
Completed | FL273-02-IM Lutz, FL | 15953 N FLORIDA AVE LUTZ, FL 33549-8102 US | 50 MBPS (26419004) | 05/15/2018: Background: FL273-02-IM Lutz, FL; New 10M/50M PIP-Eth; Frontier; NID; No MNS; Status: FOC 5/17; Major Build (Fiber splicing Rad NID install/ EWO: FL-2979393 ETA 5/14) Next action: Circuit delivery Who owns the next action: Frontier | 195072586 | FL273-02-IM Lutz, FL | WAN Analysis Reporting (26419005) Access (26419004) Private IP - PIP (26419003) | 26419005 26419004 26419003 | 50 MBPS (26419003) |  | 217105300 (WAN Analysis Reporting) 217105297 (Access) 217105299 (Private IP (PIP)) | C4010912/ADD (26419003) E4028580/ADD (26419004) | 65/KFGS/825012//FTNC/ (2641900434433501) | 5964980 | 5000 | PVC ID : 5964980 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65082 PE IP Address : 68.139.198.121 CE Address : 68.139.198.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26419004) | 1000Base-SX (850nm, Multi Mode Fiber) (26419004) | Ethernet | FRONTIER (2641900434433501) | 03/09/2018 (2641900434433501) | 05/17/2018 (2641900434433501) | 05/16/2018 (2641900434433501) | 05/17/2018 (VFORCE) (26419004) | 05/17/2018 (VFORCE) (26419004) | DEMARCADDR - 15953 FLORIDA AVE LUTZ FL DEMARCDET - DEMARCINFO SL00#SHLF00#PRT00#PHY1ST FLOOR IT CLOSET MOU NTED ON WEST WALL AND TAGGED#JKRJ45#EXTN#TAGY CIRCUIT TEST |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | MELISSA CHAPMAN | melissa_r_chapman@optum.com | 1-763-744-2114 | 05/17/2018(WAN Analysis Reporting) 05/17/2018(Access) 05/17/2018(Private IP - PIP) |  |  | 05/29/2018 (26419003) 05/24/2018 (26419004) | 04/23/2018 04/17/2018 | 05/17/2018 |  | Completed | N (26419005) N (26419004) N (26419003) | U0101953 |  | NSPE0011963735 Order Request # 195069050 | NSPE0011963735
Completed | VA729-03-CM Ashburn, VA | 44480 HASTINGS DR ASHBURN, VA 20147-6043 US | 1 GBPS (26423389) | 04/23/2018: 04/20 Successfully activated | 195075535 | VA729-02-IM | Access (26423389) Private IP - PIP WAN Analysis Reporting (26423390) | 26423389 26423390 | 500 MBPS |  | 210045070 (Access) 210045072 210045073 (WAN Analysis Reporting) | E5009873/NONE (26423389) | 46.KFGS.304357..CV (2642338979531601) 46.KFGS.304270..CV (2642338979531602) |  |  |  | 1000Base-LX-1310nm (26423389) | 1000Base-LX (1310nm Single Mode Fiber) (26423389) | Ethernet | VERIZON (2642338979531601) VERIZON (2642338979531602) | 03/08/2018 (2642338979531601) 03/08/2018 (2642338979531602) | 03/23/2018 (2642338979531601) 03/23/2018 (2642338979531602) | 03/22/2018 (2642338979531601) 03/22/2018 (2642338979531602) |  |  | DEMARCADDR - 44480 HASTINGS DR, ASHBURN, VA DEMARCDET - 1ST FLR DATA CENTER RM 183 WALL MOUNT UNIT 7 TAGGED 2 IDS |  | EDWARD JONES 1-719-425-4044 edward.jones@optum.com | EDWARD JONES | edward.jones@optum.com | 1-719-425-4044 | 03/25/2018(Access) | 03/25/2018 |  | 03/30/2018 (26423389) | 04/04/2018 04/04/2018 (20686589.2) | 03/25/2018 |  | Completed Activated/Installed | N (26423389) N N (26423390) | U0101953 |  | NSPE0011967885 Order Request # 195075380 | NSPE0011967885
Completed | MD742-02-IM Beltsville, MD | 6900 MUIRKIRK MEADOWS DR BELTSVILLE, MD 20705-6309 US | 300 MBPS (26434263) | 05/25/2018: 05/25 Activation scheduled 05/30/2018 4PM CST | 195082662 | Quality Metric-Fortinet-CPE | Private IP - PIP (26434262) WAN Analysis Reporting (26434264) Access (26434263) | 26434262 26434264 26434263 | 200 MBPS (26434262) |  | 217645750 (Private IP (PIP)) 217645751 (WAN Analysis Reporting) 217645748 (Access) | C5004531/ADD (26434262) E5010481/ADD (26434263) |  | 5965775 | 110000 | PVC ID : 5965775 VPN Name : UnitedHealthGroup Router Name : 9QG9E01 VRF Name : Vc12269:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65107 PE IP Address : 152.164.45.157 CE Address : 152.164.45.158 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (26434263) | Ethernet |  |  |  |  | 04/23/2018 (CCP) (26434262) 04/23/2018 (CCP) (26434263) | 04/25/2018 (CCP) (26434262) 04/25/2018 (CCP) (26434263) |  |  | DEVIN WINTERFELDT 1-240-264-4227 devin.winterfeldt@verizon.com | RANJI ADHIKARI | ranjit_adhikari@optum.com | 1-763-744-1957 | 04/24/2018(Private IP - PIP) 04/24/2018(WAN Analysis Reporting) 04/24/2018(Access) |  |  | 04/23/2018 (26434262) 04/19/2018 (26434263) | 04/19/2018 04/25/2018 | 04/24/2018 |  | Completed | N (26434262) N (26434264) N (26434263) | U0101953 |  | NSPE0011971585 Order Request # 195081011 | NSPE0011971585
Completed | UAK01-02-IM Anchorage, AK | 310 K ST FL 7 ANCHORAGE, AK 99501-2043 US | 10 MBPS (26464746) | 07/19/2018: 07/19 Service ready for use. Confirmed for plug and play. | 195100154 | UAK01-02-IM | Private IP - PIP (26464745) WAN Analysis Reporting (26464747) Access (26464746) | 26464745 26464747 26464746 | 10 MBPS (26464745) |  | 218483519 (Private IP (PIP)) 218483520 (WAN Analysis Reporting) 218483517 (Access) | C0140182/ADD (26464745) E3051051/ADD (26464746) | E3051051 (2646474634645601) | 5967225 | 5000 | PVC ID : 5967225 VPN Name : UnitedHealthGroup Router Name : ANCG9E01 VRF Name : Vc11615:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65446 PE IP Address : 152.161.216.253 CE Address : 152.161.216.254 QoS - Egress Profile: R12 | 100Base-TX (26464746) | 100Base-TX (26464746) | Ethernet | CLEC or INDEPENDENT (2646474634645601) | 03/28/2018 (2646474634645601) | 04/04/2018 (2646474634645601) | 03/29/2018 (2646474634645601) |  |  | DEMARCADDR - 310, K STREET, ANCHORAGE DEMARCDET - Bldg - Main, Floor: 7, Room ?????? MPOE |  | Kelly Fischer 1-907-717-3992 kf.allstar@gmail.com | Toni Johnson | toni_johnson@optum.com | 1-763-553-4807 | 04/12/2018(Private IP - PIP) 04/12/2018(WAN Analysis Reporting) 04/12/2018(Access) |  |  | 05/08/2018 (26464745) 04/11/2018 (26464746) | 05/08/2018 05/14/2018 | 04/12/2018 |  | Completed | N (26464745) N (26464747) N (26464746) | U0101953 |  | NSPE0011984275 Order Request # 195098731 | NSPE0011984275
Completed | MN066-02-IM Roseville, MN | 2685 PATTON RD ROSEVILLE, MN 55113-1137 US | 50 MBPS (26497333) | 03/29/2018: Background: MN066-02-IM Roseville, MN; New 10M/50M PIP-Eth; Qwest; NID; No MNS; Status: Circuit delivered 3/28 and Beas install scheduled for 3/30 Next action: Beas installation Who owns the next action: VZ Ticket: NA | 195118970 | MN066-02-IM | Private IP - PIP (26497332) WAN Analysis Reporting (26497334) Access (26497333) | 26497332 26497334 26497333 | 10 MBPS (26497332) |  | 219765083 (Private IP (PIP)) 219765084 (WAN Analysis Reporting) 219765081 (Access) | C4011164/ADD (26497332) E4029038/ADD (26497333) | 03.KXGS.307370..NW (2649733334845201) | 5968584 | 5500 | PVC ID : 5968584 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65236 PE IP Address : 152.181.165.209 CE Address : 152.181.165.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26497333) | 1000Base-SX (850nm, Multi Mode Fiber) (26497333) | Ethernet | CENTURYLINK (2649733334845201) | 03/21/2018 (2649733334845201) | 04/02/2018 (2649733334845201) | 03/28/2018 (2649733334845201) | 03/29/2018 (VFORCE) (26497333) | 03/30/2018 (VFORCE) (26497333) | DEMARCADDR - X DEMARCDET - REAR LOADING DOCK. LOCKBOX CODE: 0 7. WALL MOUNT 3916. MM OPTICAL PORT 3. TAGGED. TYPE: OPTICAL |  | Jason Magid 1-203-494-5904 Jason_Magid@uhg.com | SUSHIL GAUTAM | sushil_gautam@uhc.com | 1-612-855-7475 | 03/30/2018(Private IP - PIP) 03/30/2018(WAN Analysis Reporting) 03/30/2018(Access) |  |  | 04/11/2018 (26497332) 04/09/2018 (26497333) | 05/01/2018 05/07/2018 | 03/30/2018 |  | Completed | N (26497332) N (26497334) N (26497333) | U0101953 |  | NSPE0011996265 Order Request # 195117514 | NSPE0011996265
Completed | C1631-01-IM Salt Lake City, UT | 683 S 4150 W SALT LAKE CITY, UT 84104-4409 US | 1 GBPS (26514298) | 04/17/2018: 04/16 Successfully activated | 195127158 | C1631-01-IM | Access (26514298) Private IP - PIP WAN Analysis Reporting (26514299) | 26514298 26514299 | 600 MBPS |  | 208399635 (Access) 208399637 208399638 (WAN Analysis Reporting) | E5009670/NONE (26514298) |  |  |  |  | 1000Base-LX-1310nm (26514298) | 1000Base-LX (1310nm Single Mode Fiber) (26514298) | Ethernet |  |  |  |  | 03/29/2018 (VFORCE) (26514298) | 03/29/2018 (VFORCE) (26514298) |  |  | DAN KEPPLER 1-801-257-6363 dan.keppler@teleperformance.com | Erwin Edoria | erwin_edoria@optum.com | 632-588-3204 | 04/17/2018(Access) | 04/16/2018 |  | 03/27/2018 (26514298) | 05/03/2018 05/03/2018 (20785787.1) | 04/17/2018 |  | Completed Activated/Installed | N (26514298) N N (26514299) | U0101953 |  | Order Request # 195127120 | NSPE0012002996
Completed | UIL55-02-IM St. Lawrenceville, IL | 1001 JEFFERSON ST LAWRENCEVILLE, IL 62439-2435 US | 100 MBPS (26531373) | 08/06/2018: Background: UIL55-02-IM LAWRENCEVILLE, IL; New 50M/100M PIP-Eth; Frontier; NID; No MNS; Status: SFP card installed pending Frontier testing and handoff then schedule Beas | 195137792 | UIL24-17-IJ | Private IP - PIP (26531372) WAN Analysis Reporting (26531374) Access (26531373) | 26531372 26531374 26531373 | 50 MBPS (26531372) |  | 220549304 (Private IP (PIP)) 220549305 (WAN Analysis Reporting) 220549282 (Access) | C1069384/ADD (26531372) E4029194/ADD (26531373) | 30/KRGN/837665//FTNC/ (2653137330487301) | 5969986 | 20000 | PVC ID : 5969986 VPN Name : UnitedHealthGroup Router Name : PLVXE01 VRF Name : V669152-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64764 PE IP Address : 147.225.163.197 CE Address : 147.225.163.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26531373) | 1000Base-SX (850nm, Multi Mode Fiber) (26531373) | Ethernet | FRONTIER (2653137330487301) | 03/27/2018 (2653137330487301) | 07/27/2018 (2653137330487301) | 08/07/2018 (2653137330487301) | 08/09/2018 (VFORCE) (26531373) | 08/09/2018 (VFORCE) (26531373) | customer MDF room, 1st FL., and mounted in relay rack 6, position 26 |  | SANDRA CARY 1-618-943-8000 sandra_cary@unitedhealthone.com | SONHA MROCZYSNKI | sonja_d_mroczynski@optum.com | 1-612-632-6919 | 08/09/2018(Private IP - PIP) 08/09/2018(WAN Analysis Reporting) 08/09/2018(Access) |  |  | 08/08/2018 (26531372) 08/06/2018 (26531373) | 07/31/2018 08/06/2018 | 08/09/2018 |  | Completed | N (26531372) N (26531374) N (26531373) | U0101953 |  | NSPE0012006650 Order Request # 195132395 | NSPE0012006650
Completed | C1625 Centennial, CO; | 6900 S PEORIA ST CENTENNIAL, CO 80112-4137 US | 500 MBPS (26532216) | 04/12/2018: 04/09 Successfully activated | 195138387 | UHG- Trizetto | Access (26532216) Private IP - PIP WAN Analysis Reporting (26532217) | 26532216 26532217 | 200 MBPS |  | 197285736 (Access) 197285738 197285739 (WAN Analysis Reporting) | E5008701/NONE (26532216) |  |  |  |  | 1000Base-LX-1310nm (26532216) | 1000Base-LX (1310nm Single Mode Fiber) (26532216) | Ethernet |  |  |  |  | 03/30/2018 (VFORCE) (26532216) | 03/30/2018 (VFORCE) (26532216) |  |  | BUDDY JEROME 1-303-495-7104 george.jerome@cognizant.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 04/17/2018(Access) | 04/09/2018 |  | 03/29/2018 (26532216) | 05/07/2018 05/07/2018 (19608601.2) | 04/17/2018 |  | Completed Activated/Installed | N (26532216) N N (26532217) | U0101953 |  | Order Request # 195138277 | NSPE0012011138
Completed | CA269-04-IM Irwindale, CA | 4900 RIVERGRADE RD IRWINDALE, CA 91706 USA | 1.536 MBPS (IQBLLRGM) | 04/27/2018: Order complete ready for plug and play | 9505958 |  | Private IP (IQBLLRGM) EVC/PVC Service (N.11672871.5970893) | IQBLLRGM N.11672871.5970893 | 10.752 MBPS | P2190795 |  | BCBLCV6W0001 (IQBLLRGM) BCBLCV6W0002 (IQBLLRGM) BCBLCV6W0003 (IQBLLRGM) BCBLCV6W0004 (IQBLLRGM) BCBLCV6W0005 (IQBLLRGM) BCBLCV6W0006 (IQBLLRGM) BCBLCV6W0007 (IQBLLRGM) | 45/HCGS/840554//FTNC/ (1312632) | 5970893 | 5000 | VPN Name : UnitedHealthGroup Router Name : LO0GE02 VRF Name : V291787:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65092 PE IP Address : 152.164.216.165 CE Address : 152.164.216.166 QoS - Egress Profile: R12 PVC ID : 5970893 |  |  |  | FRONTIER (1312632) | 03/30/2018 (1312632) | 04/19/2018 (1312632) | 04/27/2018 (1312632) |  |  |  |  | PAUL KELSEY 0019499299934 PAUL.KELSEY@AM.JLL.COM |  |  |  | 04/26/2018 (IQBLLRGM) |  |  | 04/26/2018 (IQBLLRGM) | 04/26/2018 (IQBLLRGM) |  |  |  | N (IQBLLRGM) N (N.11672871.5970893) | 05650532 P2190795 |  | NSPE0012017393 CW 195147251 | NSPE0012017393
Completed | CA269-04-IM Irwindale, CA | 4900 RIVERGRADE RD STE E100 IRWINDALE, CA 91706-1401 US | 50 MBPS (26605379) | 08/07/2018: 08/07 Customer cabling not complete. need to reschedule activation | 195187917 | Optum RX | Private IP - PIP (26605378) WAN Analysis Reporting (26605380) Access (26605379) | 26605378 26605380 26605379 | 10 MBPS (26605378) |  | 222974307 (Private IP (PIP)) 222974308 (WAN Analysis Reporting) 222974305 (Access) | C4011458/ADD (26605378) E4029797/ADD (26605379) | 45/KFGS/847386//FTNC/ (2660537934290401) | 5973390 | 30000 | PVC ID : 5973390 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65092 PE IP Address : 206.115.117.165 CE Address : 206.115.117.166 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (26605379) | 1000Base-LX (1310nm Single Mode Fiber) (26605379) | Ethernet | FRONTIER (2660537934290401) | 04/10/2018 (2660537934290401) | 06/05/2018 (2660537934290401) | 06/20/2018 (2660537934290401) | 06/22/2018 (VFORCE) (26605379) |  | DEMARCADDR - 4900 RIVERGRADE RD BALDWIN PARK CA DEMARCDET - NID IS AT DEMARCATION IN TELCO ROOM |  | PAUL KELSEY 1-949-929-9934 paul.kelsey@am.jll.com | JASON SALAPING | jason_salaping@gmail.com | 1-210-862-6784 | 06/22/2018(Private IP - PIP) 06/22/2018(WAN Analysis Reporting) 06/22/2018(Access) |  |  | 07/02/2018 (26605378) 06/28/2018 (26605379) | 08/01/2018 08/07/2018 | 06/22/2018 |  | Completed | N (26605378) N (26605380) N (26605379) | U0101953 |  | NSPE0012037936 Order Request # 195181507 | NSPE0012037936
Completed | C1632-02-IM McKinney, TX | 2091 COMMERCE DR MCKINNEY, TX 75069-8262 US | 1 GBPS (26605878) | 06/05/2018: 06/05 Activation scheduled 06/19/2018 10PM CT | 195188443 | UnitedHealth Group M&R | Private IP - PIP (26605877) WAN Analysis Reporting (26605879) Access (26605878) | 26605877 26605879 26605878 | 600 MBPS (26605877) |  | 223260401 (Private IP (PIP)) 223260402 (WAN Analysis Reporting) 223260399 (Access) | C0141185/ADD (26605877) E5010966/ADD (26605878) | 14/KRGN/882816//SW (2660587835387801) | 5973396 | 350000 | PVC ID : 5973396 VPN Name : UHG-ECC Router Name : RCN3E02 VRF Name : V471741-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65463 PE IP Address : 68.139.76.177 CE Address : 68.139.76.178 QoS - Egress Profile: C13 | 1000Base-LX-1310nm (26605878) | 1000Base-LX (1310nm Single Mode Fiber) (26605878) | Ethernet | ATT (2660587835387801) | 04/10/2018 (2660587835387801) | 05/16/2018 (2660587835387801) | 05/17/2018 (2660587835387801) | 05/21/2018 (VFORCE) (26605878) | 05/21/2018 (VFORCE) (26605878) | DEMARCADDR - 2091 COMMERCE DR MCKINNEY TX DEMARCDET - 1ST FLR DEMARC ROOM 1 RELAY RACK B3 E PANEL 1 PORT 2 TAGGED NO |  | DAN KEPPLER 1-801-257-6363 dan.keppler@teleperformance.com | ERWIN EDORIA | erwin_edoria@optum.com | 632-588-3204 | 05/21/2018(Private IP - PIP) 05/21/2018(WAN Analysis Reporting) 05/21/2018(Access) | 06/19/2018 |  | 06/08/2018 (26605877) 06/06/2018 (26605878) | 05/21/2018 05/25/2018 | 05/21/2018 |  | Completed | N (26605877) N (26605879) N (26605878) | U0101953 |  | NSPE0012037656 Order Request # 195180675 - C13 | NSPE0012037656
Completed | URI10-05-IM Warwick, RI | 475 KILVERT ST WARWICK, RI 02886-1379 US | 50 MBPS (26638597) | 05/02/2018: E2E complete pending Bcom | 195192083 | URI10-02-IJ UNITEDHEALTH | Private IP - PIP (26638596) WAN Analysis Reporting (26638598) Access (26638597) | 26638596 26638598 26638597 | 20 MBPS (26638596) |  | 221663265 (Private IP (PIP)) 221663266 (WAN Analysis Reporting) 221662863 (Access) | C4011614/ADD (26638596) E4030048/ADD (26638597) | 85.KFGS.008410..NE (2663859725704801) | 5974667 | 18000 | PVC ID : 5974667 VPN Name : UnitedHealthGroup Router Name : CHT3E05 VRF Name : V406341-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65069 PE IP Address : 199.220.111.237 CE Address : 199.220.111.238 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26638597) | 1000Base-SX (850nm, Multi Mode Fiber) (26638597) | Ethernet | VERIZON (2663859725704801) | 04/13/2018 (2663859725704801) | 05/03/2018 (2663859725704801) | 05/02/2018 (2663859725704801) |  |  | DEMARCADDR - 475 KILVERT, WRWK, RI DEMARCDET - 3RD FLR DATA RM..RACK MOUNTED..TAGGED |  | Claudette Levesque 1-401-732-7220 claudette_i_levesque@uhc.com | SUSHIL Kumar | sushil_gautam@uhc.com | 1-612-855-7475 | 05/03/2018(Private IP - PIP) 05/03/2018(WAN Analysis Reporting) 05/03/2018(Access) |  |  | 05/14/2018 (26638596) 05/10/2018 (26638597) | 05/22/2018 05/28/2018 | 05/02/2018 |  | Completed | N (26638596) N (26638598) N (26638597) | U0101953 |  | NSPE0012041001 Order Request # 195190617 | NSPE0012041001
Completed | IL043-08-IM Schaumburg, IL | 1600 MCCONNOR PKWY SCHAUMBURG, IL 60173-6801 US | 300 MBPS (26675160) | 06/06/2018: 06/05 Background: IL043-08-IM Schaumburg, IL; New 300M/300M PIP-Eth; Comcast; NID; No MNS; ENID Status: Ready for Activation once customer completes their internal cabling. Customer informed. Next action: Customer to provide activation date and time allowing 3 business days advance notice Who owns the next action: Customer (BNE ) Ticket: NA Telco Circuit ID: 22.KGGS.021420..CBCL.. Telco Demarcation: 2nd flr IDF rm next to the gym row 2 cabinet 2 ru 24 tagged w/ Comcast. 1000Base-LX-1310nm SMF LC BEAS/Verizon Circuit ID: E5011186 / USAIL12560455COV400002 BEAS/Verizon Demarcation: Overture 1400 Aisle: 2, Bay: 2, Shelf: RU 17, Port: 1, Floor: 2, Room: MDF / Computer Room, LC | 195257595 | IL043-02-IJ Catamaran Schaumburg | Private IP - PIP (26675159) WAN Analysis Reporting (26675161) Access (26675160) | 26675159 26675161 26675160 | 300 MBPS (26675159) |  | 94518247 (Private IP (PIP)) 94518253 (WAN Analysis Reporting) 94518251 (Access) | C5004792/ADD (26675159) E5011186/ADD (26675160) | 22.KGGS.021420..CBCL.. (2667516012560401) | 5976196 | 140000 | PVC ID : 5976196 VPN Name : UnitedHealthGroup Router Name : RVDL9E01 VRF Name : V550197:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64791 PE IP Address : 152.187.35.117 CE Address : 152.187.35.118 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (26675160) | 1000Base-LX (1310nm Single Mode Fiber) (26675160) | Ethernet | COMCAST (2667516012560401) | 05/09/2018 (2667516012560401) | 06/01/2018 (2667516012560401) | 06/04/2018 (2667516012560401) | 06/05/2018 (VFORCE) (26675160) | 06/05/2018 (VFORCE) (26675160) | DEMARCDET - 2nd flr IDF rm next to the gym row 2 cabinet 2 ru 24 tagged w/comcast |  | Matthew Schabowski 1-708-426-4153 matthew_schabowski1@uhg.com | Clifford Remigio | clifford_remigio@optum.com | 1-763-744-2114 | 06/05/2018(Private IP - PIP) 06/05/2018(WAN Analysis Reporting) 06/05/2018(Access) |  |  | 06/12/2018 (26675159) 06/08/2018 (26675160) | 06/14/2018 06/20/2018 | 06/05/2018 |  | Completed | N (26675159) N (26675161) N (26675160) | U0101953 | Jeopardy Notification 1 (05/04/2018) | NSPE0012062851 Order Request # 195254215 | NSPE0012062851
Completed | FL220 | 6545 CORPORATE CENTRE BLVD STE 240 ORLANDO, FL 32822-3253 US | 50 MBPS (26597091) | 07/17/2018: Tedlc o corrected error, ticket closed, beas pingable | 195178001 | 6545 Corporate Center Blvd. - Suite 240 | Access (26597091) Private IP - PIP WAN Analysis Reporting (26597092) | 26597091 26597092 | 10 MBPS |  | 191056560 (Access) 191056562 191056563 (WAN Analysis Reporting) | E4023199/NONE (26597091) | 5S/KEFN/003978/LVLC (2659709129807701) |  |  |  | 100Base-TX (26597091) | 100Base-TX (26597091) | Ethernet | LEVEL 3 (2659709129807701) | 04/12/2018 (2659709129807701) | 05/22/2018 (2659709129807701) | 04/23/2018 (2659709129807701) |  |  | 2nd Floor, Suite 240, Server Room, RJ-45 Biscuit Jack, West Wall Labeled |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 04/24/2018(Access) | 04/24/2018 |  | 04/09/2018 (26597091) | 05/18/2018 05/18/2018 (18906989.1) | 04/24/2018 |  | Completed Activated/Installed | N (26597091) N N (26597092) | U0101953 |  | NSPE0012031781 Order Request # 195169894 | NSPE0012031781
Completed | C1599-10-IM Dallas, TX | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US | 10 MBPS (26627358) | 06/04/2018: Order complete ready for cust plug and play | 195213205 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (26627357) Access (26627358) | 26627357 26627358 | 10 MBPS (26627357) |  | 224811959 (Internet Dedicated Services) 224811955 (Access) | C0141369/ADD (26627357) E3052051/ADD (26627358) |  | 5974328 | 0 | PVC ID : 5974328 VPN Name : Internet Router Name : GW9DFW7 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 26843 PE IP Address : 157.130.148.105 CE Address : 157.130.148.106 |  | 1000Base-LX (1310nm Single Mode Fiber) (26627358) | Ethernet |  |  |  |  | 04/25/2018 (CCP) (26627357) 04/25/2018 (CCP) (26627358) | 04/24/2018 (CCP) (26627357) 04/24/2018 (CCP) (26627358) | Facility Location: 1950 N STEMMONS FWY, DALLAS, TX Verizon’s Local Order Number: DAL I107801 Verizon’s Local Circuit ID: ea-ste-ste-0347 Verizon’s Order Number: 26627358 Customer/Agent PON Number: NA Quantity/Type: 10m LEC/ICSC: ___N/A____________________ Facility Assignment: 1st Floor, Suite 1039A, IBX DA3, Cage 10325, Rack/Cabinet 0508, Patch Panel 0508:144126 ports 35/36. SingleMode Handoff. |  | TODD CALYER 1-214-564-6061 tcalyer@uhcsr.com | NCC UHG | uhttier2@uhc.com | 1-763-744-3000 | 05/25/2018(Internet Dedicated Services) 05/25/2018(Access) |  |  | 06/05/2018 (26627357) 06/01/2018 (26627358) | 06/20/2018 | 05/25/2018 |  |  | N (26627357) N (26627358) | U0101953 | Jeopardy Notification 2 (05/24/2018) | NSPE0012047707 Order Request # 195212573 | NSPE0012047707
Completed | MN060-02-IM; Brooklyn Center, MN | 6200 SHINGLE CREEK PKWY BROOKLYN CENTER, MN 55430-2128 US | 200 MBPS (26763174) | 09/12/2018: 09/11 Successfully activated | 195351927 | UNITED HEALTH GROUP | Private IP - PIP (26763173) WAN Analysis Reporting (26763175) Access (26763174) | 26763173 26763175 26763174 | 100 MBPS (26763173) |  | 94522611 (Private IP (PIP)) 94522615 (WAN Analysis Reporting) 94522613 (Access) | C5004977/ADD (26763173) E5011485/ADD (26763174) | 70.KGGS.003883..CBCL.. (2676317474246201) | 5979453 | 70000 | PVC ID : 5979453 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65042 PE IP Address : 152.181.77.101 CE Address : 152.181.77.102 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26763174) | 1000Base-SX (850nm, Multi Mode Fiber) (26763174) | Ethernet | COMCAST (2676317474246201) | 05/03/2018 (2676317474246201) | 06/20/2018 (2676317474246201) | 06/18/2018 (2676317474246201) | 06/19/2018 (VFORCE) (26763174) |  | DEMARCADDR - . DEMARCDET - . |  | Albert Lao 1-612-298-8306 AlbertLao@Savvysherpa.com | BRANDON LITTLE | brandon_little@optum.com | 1-195-268-7369 | 06/19/2018(Private IP - PIP) 06/19/2018(WAN Analysis Reporting) 06/19/2018(Access) | 09/11/2018 |  | 07/18/2018 (26763173) 07/16/2018 (26763174) | 06/11/2018 06/15/2018 | 06/19/2018 |  | Completed | N (26763173) N (26763175) N (26763174) | U0101953 |  | NSPE0012088990 Order Request # 195344797 | NSPE0012088990
Completed | UT011-02-IM Sandy, UT | 280 W 10200 S SANDY, UT 84070-4379 US | 1 GBPS (26817205) | 01/22/2019: 1/18 Successfully activated | 195397563 | Sandy 1 gig | WAN Analysis Reporting (26817206) Access (26817205) Private IP - PIP (26817204) | 26817206 26817205 26817204 | 300 MBPS (26817204) |  | 94524287 (WAN Analysis Reporting) 94524280 (Access) 94524283 (Private IP (PIP)) | C0144195/ADD (26817204) E5011570/ADD (26817205) | 69.KXGS.319925..MS (2681720536657601) | 5981066 | 150000 | PVC ID : 5981066 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64862 PE IP Address : 147.225.192.117 CE Address : 147.225.192.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26817205) | 1000Base-SX (850nm, Multi Mode Fiber) (26817205) | Ethernet | CENTURYLINK (2681720536657601) | 06/14/2018 (2681720536657601) | 06/25/2018 (2681720536657601) | 06/18/2018 (2681720536657601) | 06/25/2018 (VFORCE) (26817205) |  | DEMARCADDR - X DEMARCDET - 1ST FLR MAIN IT RACK MOUNT CIENA 5142 TYPE: OPTICAL |  | Garret Nichols 1-801-654-7264 gnichols@natmedtrans.com | RANJI ADHIKARI | ranjit_adhikari@optum.com | 1-176-374-4195 | 06/25/2018(WAN Analysis Reporting) 06/25/2018(Access) 06/25/2018(Private IP - PIP) | 01/18/2019 |  | 07/05/2018 (26817204) 07/02/2018 (26817205) | 06/29/2018 06/25/2018 | 06/25/2018 |  | Completed | N (26817206) N (26817205) N (26817204) | U0101953 |  | NSPE0012103578 Order Request # 195385115 | NSPE0012103578
Completed | NY464-02-IM Ronkonkoma, NY | 992 S 2ND ST RONKONKOMA, NY 11779-7204 US | 1 GBPS (26873038) | 03/25/2019 Successfully activated | 195399761 | Ronkonoma NY Quote | Private IP - PIP (26873037) WAN Analysis Reporting (26873039) Access (26873038) | 26873037 26873039 26873038 | 300 MBPS (26873037) |  | 94524273 (Private IP (PIP)) 94524277 (WAN Analysis Reporting) 94524270 (Access) | C0144568/ADD (26873037) E5011747/ADD (26873038) | 32.KFGS.215958..NY (2687303836659701) | 5982294 | 150000 | PVC ID : 5982294 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64848 PE IP Address : 199.220.19.233 CE Address : 199.220.19.234 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26873038) | 1000Base-SX (850nm, Multi Mode Fiber) (26873038) | Ethernet | VERIZON (2687303836659701) | 05/23/2018 (2687303836659701) | 07/10/2018 (2687303836659701) | 07/09/2018 (2687303836659701) |  |  | DEMARCADDR - 992 S 2, RONKONKOMA, NY DEMARCDET - FIRST FLOOR IT ROOM WALL MOUNTED TAGGED |  | Daniel Mukamal 1-516-661-8231 dmukamal@natmedtrans.com | RANJI ADHIKARI | ranjit_adhikari@optum.com | 1-176-374-4195 | 07/09/2018(Private IP - PIP) 07/09/2018(WAN Analysis Reporting) 07/09/2018(Access) | 03/25/2019 |  | 07/19/2018 (26873037) 07/17/2018 (26873038) | 07/30/2018 08/03/2018 | 07/09/2018 |  | Completed | N (26873037) N (26873039) N (26873038) | U0101953 |  | NSPE0012104091 Order Request # 195386681 | NSPE0012104091
Completed | Upgrade Speed to 1G and GCAR to 50K | 328 FRONT ST S LA CROSSE, WI 54601-4023 US | 1 GBPS | 05/12/2018: Background: Upgrade Port speed to 1G and GCAR to 550M only. Status: Hotcut scheduled 05/14/2018 7PM CST Next action: Hotcut activity / Order Closure Who owns the next action: Customer/BNE/GLP | 195426779 | WI017-01-IJ LaCrosse WI | Private IP - PIP (26837192) Access | 26837192 | 1 GBPS (26837192) |  | 61514709 (Private IP (PIP)) 61514708 | C0029818/NONE (26837192) |  | 5565372 | 550000 | PVC ID : 5565372 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65168 PE IP Address : 152.183.189.157 CE Address : 152.183.189.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Tom Pesik 1-608-793-2910 tpesik@logisticshealth.com | Mark Dasovic | mark_dasovic@optum.com | 1-952-512-8650 | 05/17/2018(Private IP | 05/14/2018 |  | 05/10/2018 (26837192) | 05/21/2018 | 05/17/2018 |  |  | N (26837192) N | U0101953 |  | NSPE0012115131 Order Request # 195426413 | NSPE0012115131
Completed | Hooksett, NH | 14 CENTRAL PARK DR HOOKSETT, NH 03106-2507 US | 300 MBPS (26887063) | 06/28/2018: Background: Hooksett, NH; New 150M/300M PIP-Eth; Fairpoint; NID; No MNS; Status: FOC changed from 7/3 to 6/28 | 195489259 | UNH01-08-IJ Hooksett | Private IP - PIP (26887062) WAN Analysis Reporting (26887064) Access (26887063) | 26887062 26887064 26887063 | 150 MBPS (26887062) |  | 94529918 (Private IP (PIP)) 94529922 (WAN Analysis Reporting) 94529915 (Access) | C5005127/ADD (26887062) E5011787/ADD (26887063) | 84/KRGN/766216/00/MJD/ (2688706371074701) | 5982756 | 70000 | PVC ID : 5982756 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64746 PE IP Address : 152.162.80.173 CE Address : 152.162.80.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26887063) | 1000Base-SX (850nm, Multi Mode Fiber) (26887063) | Ethernet | FAIRPOINT (2688706371074701) | 05/31/2018 (2688706371074701) | 07/03/2018 (2688706371074701) |  | 07/02/2018 (VFORCE) (26887063) |  | DEMARCADDR - 14 CENTRAL PARK DRIVE HOOKSETT, NH 03106 DEMARCDET - FL1 NETWORK RM WALL-MTD METRONID GT SFP-2 TAGGED. NOT EXT |  | DAVID LAWLEY 1-160-362-9775 david_lawley@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 1-804-670-4280 | 07/02/2018(Private IP - PIP) 07/02/2018(WAN Analysis Reporting) 07/02/2018(Access) |  |  | 07/13/2018 (26887062) 07/11/2018 (26887063) | 06/27/2018 07/03/2018 | 07/02/2018 |  | Completed | N (26887062) N (26887064) N (26887063) | U0101953 |  | NSPE0012130215 Order Request # 195486299 | NSPE0012130215
Completed | TX428-02-IM San Antonio, TX | 5627 UNIVERSITY HTS STE 108 SAN ANTONIO, TX 78249-3549 US | 50 MBPS (26892640) | 07/18/2018: Order complete ready for plug andplay | 195500451 | TX428-02-IM | Private IP - PIP (26892639) WAN Analysis Reporting (26892641) Access (26892640) | 26892639 26892641 26892640 | 50 MBPS (26892639) |  | 237629829 (Private IP (PIP)) 237629831 (WAN Analysis Reporting) 237629825 (Access) | C4012389/ADD (26892639) E4032015/ADD (26892640) | 31/KRGN/653064//SW (2689264037799501) | 5982907 | 5500 | PVC ID : 5982907 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64831 PE IP Address : 152.177.217.249 CE Address : 152.177.217.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26892640) | 1000Base-SX (850nm, Multi Mode Fiber) (26892640) | Ethernet | ATT (2689264037799501) | 07/06/2018 (2689264037799501) | 07/13/2018 (2689264037799501) | 07/13/2018 (2689264037799501) | 07/17/2018 (VFORCE) (26892640) | 07/17/2018 (VFORCE) (26892640) | DEMARCADDR - 5627 UNIVERSITY HTS SAN ANTONIO TX DEMARCDET - TELCO ROOM |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 07/17/2018(Private IP - PIP) 07/17/2018(WAN Analysis Reporting) 07/17/2018(Access) |  |  | 07/05/2018 (26892639) 07/02/2018 (26892640) | 08/03/2018 08/09/2018 | 07/17/2018 |  | Completed | N (26892639) N (26892641) N (26892640) | U0101953 |  | NSPE0012130926 Order Request # 195489207 | NSPE0012130926
Completed | UMO15-13-IM Maryland Heights, MO | 13655 RIVERPORT DR MARYLAND HEIGHTS, MO 63043-4812 US | 100 MBPS (26938684) | 08/31/2018: 08/31 Successfully activated | 195583657 | UMO15-08-IJ Maryland Heights | Internet Dedicated Services (26938683) Access (26938684) | 26938683 26938684 | 100 MBPS (26938683) |  | 240759255 (Internet Dedicated Services) 240759251 (Access) | C1073555/ADD (26938683) E4032458/ADD (26938684) | 41/KQGN/712324//SW (2693868416707301) | 5984621 | 0 | PVC ID : 5984621 VPN Name : Internet Router Name : GW9STL3 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 157.130.171.25 CE Address : 157.130.171.26 | 100Base-TX (26938684) | 100Base-TX (26938684) | Ethernet | ATT (2693868416707301) | 05/29/2018 (2693868416707301) | 06/05/2018 (2693868416707301) | 06/06/2018 (2693868416707301) | 06/07/2018 (VFORCE) (26938684) | 06/07/2018 (VFORCE) (26938684) | DEMARCADDR - 13655 RIVERPORT DR MARYLAND HEIGHTS MO DEMARCDET - 1ST FLR, MN ELEC RM, WALL MNT'D 3930, PNL 1, POS 8, TAGGED |  | ROBERT SKEBO 1-314-592-7082 robert_skebo@uhg.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 | 06/08/2018(Internet Dedicated Services) 06/08/2018(Access) | 08/31/2018 |  | 06/14/2018 (26938683) 06/12/2018 (26938684) | 07/05/2018 | 06/08/2018 |  |  | N (26938683) N (26938684) | U0101953 |  | NSPE0012146545 Order Request # 195574693 | NSPE0012146545
Completed | UnitedHealth Group M&R McKinney, TX | 2091 COMMERCE DR MCKINNEY, TX 75069-8262 US | 1 GBPS (26939035) | 08/17/2018: 08/17 Customer confirmed circuit is up and running | 195584111 | UnitedHealth Group M&R | Private IP - PIP (26939034) WAN Analysis Reporting (26939036) Access (26939035) | 26939034 26939036 26939035 | 600 MBPS (26939034) |  | 94533502 (Private IP (PIP)) 94533506 (WAN Analysis Reporting) 94533508 (Access) | C0145288/ADD (26939034) E5011969/ADD (26939035) | 46.L1XX.001310..TWCC (2693903535387802) 46.L1XX.001310..TWCC (2693903535387803) | 5984470 | 550000 | PVC ID : 5984470 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65463 PE IP Address : 152.164.217.77 CE Address : 152.164.217.78 QoS - Egress Profile: C13 | 1000Base-LX-1310nm (26939035) | 1000Base-LX (1310nm Single Mode Fiber) (26939035) | Ethernet | TIME WARNER CABLE (2693903535387802) TIME WARNER CABLE (2693903535387803) | 05/29/2018 (2693903535387802) 07/18/2018 (2693903535387803) | 07/30/2018 (2693903535387802) 07/30/2018 (2693903535387803) | 07/05/2018 (2693903535387802) | 08/02/2018 (VFORCE) (26939035) | 08/07/2018 (VFORCE) (26939035) | DEMARCDET - bld main flr 1st rm MPOE |  | Dan Keppler 1-801-257-6363 Dan.keppler@teleperformance.com | ERWIN EDORIA | erwin_edoria@optum.com | 1-763-744-2114 | 08/07/2018(Private IP - PIP) 08/07/2018(WAN Analysis Reporting) 08/07/2018(Access) | 08/17/2018 |  | 08/08/2018 (26939034) 08/06/2018 (26939035) | 08/27/2018 08/31/2018 | 08/07/2018 |  | Completed | N (26939034) N (26939036) N (26939035) | U0101953 | Jeopardy Notification 1 (07/05/2018) | NSPE0012147217 Order Request # 195578209 | NSPE0012147217
Completed | DC007-02-IM Washington, DC | 655 NEW YORK AVE NW WASHINGTON, DC 20001-3626 US | 200 MBPS (27185542) | 02/26/2019 Background: DC007-02-IM Optum Insight; Washington, DC; New 100M/100M PIP-E; (VzT); Single NID; No MNS; Status: Ready for activation Telco Circuit ID: 36.KFGS.308819..CD Telco Demarcation: Basement Shelf, 9, POS,1, Garage MTR Rack Mount | 195626279 | DC007-02-IM Optum Insight. | Private IP - PIP (27185541) WAN Analysis Reporting (27185543) Access (27185542) | 27185541 27185543 27185542 | 100 MBPS (27185541) |  | 94535770 (Private IP (PIP)) 94535775 (WAN Analysis Reporting) 94535768 (Access) | C5005496/ADD (27185541) E5012579/ADD (27185542) | 36.KFGS.308819..CD (2718554238707301) | 5990683 | 70000 | PVC ID : 5990683 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64813 PE IP Address : 68.138.84.109 CE Address : 68.138.84.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27185542) | 1000Base-SX (850nm, Multi Mode Fiber) (27185542) | Ethernet | VERIZON (2718554238707301) | 08/20/2018 (2718554238707301) | 09/06/2018 (2718554238707301) | 02/26/2019 (2718554238707301) |  |  | DEMARCADDR - 655 NEW YORK AV NW, WASHINGTON, DC DEMARCDET - GARAGE LEVEL MTR RACK MOUNTED TAGGED |  | Katie Maloney 1-617-852-7976 katharine_maloney@uhg.com | Sushil Kumar | sushil_gautam@uhc.com | 1-763-744-2114 | 02/26/2019(Private IP - PIP) 02/26/2019(WAN Analysis Reporting) 02/26/2019(Access) |  |  | 02/28/2019 (27185541) 02/26/2019 (27185542) | 03/14/2019 03/20/2019 | 02/26/2019 |  | Completed | N (27185541) N (27185543) N (27185542) | U0101953 |  | NSPE0012159001 Order Request # 195626313 | NSPE0012159001
Completed | Plymouth MN to Cologne MN; New 10G Prot MPL; | 6150 TRENTON LN N 6150 TRENTON LN N, MN 55442 USA | 10GL-MPL-WL-SPP (6180243) | 07/24/2018: Order complete | 9573398 |  | Metro Private Line (6180243) | 6180243 | 10GL-MPL-WL-SPP (6180243) |  |  | W1D29882 (6180243) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | COLOGNE DEMARCATION: ACTL: CLGNMNAA Facility Location: 7383 COUNTY ROAD 140 COLOGNE MN US Verizon¿s Order Number: 6180243Verizon¿s Circuit ID: W1D29882Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039254 / jx-jcfg-73c-0001DEMARC INFO:Aisle: 10Bay: 10.26Shelf: 2Slot: 6Port: 6/12Floor: 1Room: Equipment. PLYMOUTH DEMARCATION: ACTL: PLMOMNEM Facility Location: 6150 TRENTON LN N PLYMOUTH MN US Verizon¿s Order Number: 6180243Verizon¿s Circuit ID: W1D29882Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039254 / jx-jcfg-73c-0001DEMARC INFO:Aisle: N/ABay: 7.0qShelf: 99Slot: 1Port: 3Floor: 1Room: Data room. ............RELATED PORT: BOBLC5X60001 | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 07/24/2018 (6180243) | 07/24/2018 |  | 08/06/2018 (6180243) | 09/03/2018 (6180243) |  |  |  | N (6180243) | 00198894
Completed | MN013-60-IM Plymouth MN to Cologne MN; New 4G PIP-O | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (IQBLMRYF) | 03/17/2019 Successfully activated | 9585940 |  | Private IP Port Only (IQBLMRYF) | IQBLMRYF N.11782717.5997745 | 4000 MBPS | P2198253 |  | BOBLC5X60001 (IQBLMRYF) |  | 5996017 5997745 5997743 5996019 | 768 | PVC ID : 5996017,5997745,5997743,5996019 VPN Name : UHG-SDWAN Router Name : MZZ9E01 VRF Name : Vd76606:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.161.122.109 CE Address : 152.161.122.110 QoS - Egress Profile: R12 PVC ID : 5997745 | [9 empty] | RELATED ACCESS: W1D29882 |  | TIM GUNDERSON 0015072950001 7637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/07/2018 (IQBLMRYF) | 03/17/2019 |  | 08/29/2018 (IQBLMRYF) | 08/29/2018 (IQBLMRYF) |  |  |  | N (IQBLMRYF) N (N.11782717.5997745) | 05017789 P2198253 |  | NSPE0012167898 | NSPE0012167898
Completed | Plymouth MN to Minneapolis MN; New 10G Prot MPL; | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 10GL-MPL-WL-SPP (6181143) | 07/18/2018: Background: Plymouth, MN (JCFG) to Minneapolis;(511) New 10 GIG MPL Port Status: CCR 1381664 ROADM Cards RFT 7/24 equipment install schedule 7/19 | 9573407 |  | Metro Private Line (6181143) | 6181143 | 10GL-MPL-WL-SPP (6181143) |  |  | W1D29691 (6181143) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | MINNEAPOLIS DEMARC: ACTL: MPLSMNCD Facility Location: 511 11TH AVE S MINNEAPOLIS MN US Verizon¿s Order Number: 6181143Verizon¿s Circuit ID: W1D29691Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039251 / jx-jcfg-511-0001DEMARC INFO:Aisle: 113Bay: 3Shelf: 9aSlot: NaPort: 2Floor: 3Room: 320. PLYMOUTH DEMARC: ACTL: PLMOMNEM Facility Location: 6150 TRENTON LN N PLYMOUTH MN US Verizon¿s Order Number: 6181143Verizon¿s Circuit ID: W1D29691Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039251 / jx-jcfg-511-0001Aisle: NaBay: NaShelf: NaSlot: NaPort: NaFloor: NaRoom: NA. RELATED PORT: BOBLC5XS0001 | MELISSA CHAPMAN 763 744 2114 | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 07/19/2018 (6181143) | 07/19/2018 |  | 08/07/2018 (6181143) | 08/28/2018 (6181143) |  |  |  | N (6181143) | 00198894
Cancelled | MN013-61-IM Plymouth MN to Minneapolis MN; New PIP-O | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 4000 MBPS (IQBLMRW3) | 07/21/2018: Background: Minneapolis MN013-61-IM; NEW PIP-O; Related Access W1D29691 Status: OPSA. Pending access to be complete. Configs to be deployed. | 9574830 |  | Private IP Port Only (IQBLMRW3) | IQBLMRW3 | 4000 MBPS | P2198241 |  | BOBLC5XS0001 (IQBLMRW3) |  | 5994799 | 72000 | PVC ID : 5994799 VPN Name : UHG-SDWAN Router Name : MN39E01 VRF Name : Vd76602:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.164.75.1 CE Address : 152.164.75.2 QoS - Egress Profile: R12 | [9 empty] | MINNEAPOLIS DEMARC: ACTL: MPLSMNCD Facility Location: 511 11TH AVE S MINNEAPOLIS MN US Verizon¿s Order Number: 6181143Verizon¿s Circuit ID: W1D29691Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039251 / jx-jcfg-511-0001DEMARC INFO:Aisle: 113Bay: 3Shelf: 9aSlot: NaPort: 2Floor: 3Room: 320. PLYMOUTH DEMARC: ACTL: PLMOMNEM Facility Location: 6150 TRENTON LN N PLYMOUTH MN US Verizon¿s Order Number: 6181143Verizon¿s Circuit ID: W1D29691Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039251 / jx-jcfg-511-0001Aisle: NaBay: NaShelf: NaSlot: NaPort: NaFloor: NaRoom: NARELATED ACCESS: W1D29691 |  | MELISSA CHAPMAN 0015072950001 TIM_GUNDERSON@OPTUM.COM |  |  |  | 07/24/2018 (IQBLMRW3) |  |  | 08/13/2018 (IQBLMRW3) | 08/13/2018 (IQBLMRW3) |  |  |  | N (IQBLMRW3) | 05017789 |  | NSPE0012167898 | NSPE0012167898
Completed | Chaska, MN to Elk River, MN MPL | 1707 W CREEK LN CHASKA, MN 55318 USA | 100N-MPL-WL-PU (6181924) | 08/10/2018: Ckt id 2sm6l7llm80001 | 9577689 |  | Metro Private Line (6181924) | 6181924 | 100N-MPL-WL-PU (6181924) |  |  | W1D29718 (6181924) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | CHASKA DEMARK: ACTL: CHSKMNCC Facility Location: 1707 W CREEK LN CHASKA MN US Verizon¿s Order Number: 6181924Verizon¿s Circuit ID: W1D29718Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039255 / 2sm6l7llm80001 DEMARC INFO:Cage: NoCabinet/Rack: 7100Patch panel: Lower leftJack Number: 7Floor: 1stRoom: Same. ELK RIVER DEMARC: ACTL: EKRVMNDX Facility Location: 14100 BUSINESS CENTER DR ELK RIVER MN US Verizon¿s Order Number: 6181924Verizon¿s Circuit ID: W1D29718Customer/Agent PON Number: N/AQuantity/Type: 1 LEC/ICSC: N/ADemarc: MIN-I0039255 /2sm6l7llm80001 DEMARC INFO:Cage: NaCabinet/Rack: NaPatch panel: NaJack Number: NaFloor: 1Room: Na | TOM KRENN 763 744 3141 TOM_KRENN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 07/27/2018 (6181924) | 07/26/2018 |  | 08/08/2018 (6181924) | 08/30/2018 (6181924) |  |  |  | N (6181924) | 00198894 |  | NSPE0012167898 | NSPE0012167898
Completed | CA377-03-IM Pomona, CA | 3191 W TEMPLE AVE POMONA, CA 91768-3287 US | 200 MBPS (27025466) | 07/19/2018: Order complete | 195677621 | CA377-03-IM Epic Hearing. | Private IP - PIP (27025465) WAN Analysis Reporting (27025467) Access (27025466) | 27025465 27025467 27025466 | 100 MBPS (27025465) |  | 94537298 (Private IP (PIP)) 94537603 (WAN Analysis Reporting) 94537296 (Access) | C5005295/ADD (27025465) E5012168/ADD (27025466) | 90.L1XX.002128..TWCC (2702546638975701) | 5986741 | 70000 | PVC ID : 5986741 VPN Name : UnitedHealthGroup Router Name : RTO9E01 VRF Name : Vg10944:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64807 PE IP Address : 152.183.193.193 CE Address : 152.183.193.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27025466) | 1000Base-SX (850nm, Multi Mode Fiber) (27025466) | Ethernet | TIME WARNER CABLE (2702546638975701) | 06/08/2018 (2702546638975701) | 07/13/2018 (2702546638975701) | 07/13/2018 (2702546638975701) | 07/18/2018 (VFORCE) (27025466) | 07/18/2018 (VFORCE) (27025466) | DEMARCDET - RAD 114, Port 4, Rack mounted on customer network closet. |  | Sean Casey 1-909-719-8425 Sean.Casey@epichearing.com | LARRY WALSH | larry_l_walsh@optum.com | 1-131-771-5777 | 07/19/2018(Private IP - PIP) 07/19/2018(WAN Analysis Reporting) 07/19/2018(Access) | 11/14/2018 |  | 07/24/2018 (27025465) 07/20/2018 (27025466) | 09/19/2018 09/25/2018 | 07/18/2018 |  | Completed | N (27025465) N (27025467) N (27025466) | U0101953 |  | NSPE0012169144 Order Request # 195671275 | NSPE0012169144
Completed | UT021-01-IM West Valley, UT | 4071 S 4000 W WEST VALLEY, UT 84120-4143 US | 50 MBPS (27030259) | 10/04/2018: Background: UT021-01-IM West Valley, UT; New 10M/50M PIP-Eth; Qwest; NID; No MNS; Status: Ready for customer activation. Telco Circuit ID: 69.KXGS.326638..MS Telco Demarcation: First Floor, Main Comm Room, Wall mount Ciena 3916 BEAS / Verizon Circuit ID: USAUT38020063COV400002 / E4033129 BEAS/ Verizon Circuit Demarc: 1st floor server room. For the BEAS install, it is a single rack at the top. It is labeled and pingable. | 195709419 | UT021-01-IM Pico | Private IP - PIP (27030258) WAN Analysis Reporting (27030260) Access (27030259) | 27030258 27030260 27030259 | 10 MBPS (27030258) |  | 94539125 (Private IP (PIP)) 94539131 (WAN Analysis Reporting) 94539128 (Access) | C4013057/ADD (27030258) E4033129/ADD (27030259) | 69.KXGS.326638..MS (2703025938020001) | 5986927 | 5500 | PVC ID : 5986927 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64847 PE IP Address : 152.181.162.153 CE Address : 152.181.162.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27030259) | 1000Base-SX (850nm, Multi Mode Fiber) (27030259) | Ethernet | CENTURYLINK (2703025938020001) | 07/16/2018 (2703025938020001) | 10/15/2018 (2703025938020001) | 09/27/2018 (2703025938020001) | 10/01/2018 (VFORCE) (27030259) | 10/01/2018 (VFORCE) (27030259) | DEMARCDET - FIRST FLR MAIN COMM RM WALL MOUNT CIENA 3916M Type: OPTICAL Port: 3. |  | Darrick Porter 1-801-870-4617 darrick@bigtreeconst.com | DAVID CASANOVA | david_casanova@optum.com | 1-176-374-4158 | 10/01/2018(Private IP - PIP) 10/01/2018(WAN Analysis Reporting) 10/01/2018(Access) |  |  | 09/26/2018 (27030258) 09/24/2018 (27030259) | 10/11/2018 10/17/2018 | 10/01/2018 |  | Completed | N (27030258) N (27030260) N (27030259) | U0101953 |  | NSPE0012173811 Order Request # 195709257 | NSPE0012173811
Completed | TX422-02-IM Dallas, TX | 3107 W CAMP WISDOM RD DALLAS, TX 75237-2643 US | 50 MBPS (27040484) | 02/01/2019: Background: TX422-02-IM Dallas, TX; New 10M/50M PIP-Eth; (TWC); NID; No MNS; 897 Status: Ready for activation Next action: Line testing Who owns the next action: T&I Telco Circuit ID: 21.L1XX.012084..TWCC Telco Demarcation: Data room, RAD is mounted on the Rack RU 19; RAD 203 port 5 The MODEM is untagged, MMF Verizon BEAS Circuit ID: E4033285 Verizon BEAS Demarcation: first floor server room, Beas box is mounted on the Relay Rack 1.1.1 shelf 1 next to spectrum equipment label with VERIZON circuit id | 195720877 | TX422-02-IM Wellmed. | Private IP - PIP (27040483) WAN Analysis Reporting (27040485) Access (27040484) | 27040483 27040485 27040484 | 10 MBPS (27040483) |  | 94539113 (Private IP (PIP)) 94539119 (WAN Analysis Reporting) 94539116 (Access) | C4013157/ADD (27040483) E4033285/ADD (27040484) | 21.L1XX.012084..TWCC (2704048439023301) | 5987046 | 5500 | PVC ID : 5987046 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64811 PE IP Address : 147.225.5.153 CE Address : 147.225.5.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27040484) | 1000Base-SX (850nm, Multi Mode Fiber) (27040484) | Ethernet | TIME WARNER CABLE (2704048439023301) | 12/20/2018 (2704048439023301) | 01/24/2019 (2704048439023301) | 01/23/2019 (2704048439023301) | 01/24/2019 (VFORCE) (27040484) | 01/24/2019 (VFORCE) (27040484) | DEMARCDET - data room RAD is mounted on the rack RU 19 |  | LIZDELI GUERRIDO 1-917-981-9347 lguerrido@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 1-763-744-2114 | 01/24/2019(Private IP - PIP) 01/24/2019(WAN Analysis Reporting) 01/24/2019(Access) |  |  | 01/30/2019 (27040483) 01/28/2019 (27040484) | 04/03/2019 04/09/2019 | 01/24/2019 |  | Completed | N (27040483) N (27040485) N (27040484) | U0101953 | Jeopardy Notification 2 (07/12/2018) | NSPE0012174785 Order Request # 195713837 | NSPE0012174785
Completed | UCA92-10-CM | 3110 W LAKE CENTER DR SANTA ANA, CA 92704 USA | 100 MBPS (CQBLMKB1) 100 MBPS (CQBLMKB2) | 05/01/2020: Order Completed on May 1, 2020 | 9599436 |  | Private IP (CQBLMKB1) EACS (CQBLMKB2) | CQBLMKB1 CQBLMKB2 | 100 MBPS 100 MBPS (CQBLMKB2) | P1969628 P1969305 |  | BCBKXH1G0001 (CQBLMKB1) EDBKXHGX0001 (CQBLMKB2) |  |  | 21504 | VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64822 PE IP Address : 152.162.17.93 CE Address : 152.162.17.94 QoS - Egress Profile: R12 | [11 empty] | RICHARD MARCUS 7144450404 RICHARD.MARCUS@OPTUM.COM |  |  |  | 07/09/2018 (CQBLMKB1) 06/22/2018 (CQBLMKB2) |  |  | 07/18/2018 (CQBLMKB1) 07/18/2018 (CQBLMKB2) | 07/18/2018 (CQBLMKB1) 07/18/2018 (CQBLMKB2) |  |  |  | N (CQBLMKB1) N (CQBLMKB2) | 05017789 |  | Santa Ana, CA | NSPE0012200247
Completed | M0331-10-IM West Lake Hills, TX | 1250 S CAPITAL OF TEXAS HWY WEST LAKE HILLS, TX 78746-6446 US | 50 MBPS (27165601) | 10/22/2018: 10/20 Successfully activated. | 195987625 | M0331-10-IM | Private IP - PIP (27165600) WAN Analysis Reporting (27165602) Access (27165601) | 27165600 27165602 27165601 | 20 MBPS (27165600) |  | 94542913 (Private IP (PIP)) 94542918 (WAN Analysis Reporting) 94542915 (Access) | C4013260/ADD (27165600) E4033643/ADD (27165601) | TX/KXFN/024713/LVLC (2716560125447501) | 5990217 | 13000 | PVC ID : 5990217 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65102 PE IP Address : 152.161.73.25 CE Address : 152.161.73.26 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (27165601) | 1000Base-SX (850nm, Multi Mode Fiber) (27165601) | Ethernet | LEVEL 3 (2716560125447501) | 07/16/2018 (2716560125447501) | 08/20/2018 (2716560125447501) | 08/20/2018 (2716560125447501) | 09/12/2018 (VFORCE) (27165601) | 09/12/2018 (VFORCE) (27165601) | Telco Circuit ID: TX/KXFN/024713/LVLC Telco Demarcation: Bldg 2 first floor telecom/ATT cell site room, CenturyLink rack RMU35 CISCO ASR 920 port 0 AUSTTXDBZG001 0/0/0 SM-LC sfp handoff BEAS ID: USATX25447590COV400001 / E4033643 BEAS Demarcation: Overture 1400 and LEC hand off is in telco room of building 2 on the first floor. It is on the wall behind the Centrylink bay. |  | Ryan Sibbet 1-512-347-2716 ryan_sibbet@uhc.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 1-763-744-2114 | 09/12/2018(Private IP - PIP) 09/12/2018(WAN Analysis Reporting) 09/12/2018(Access) | 10/20/2018 |  | 09/20/2018 (27165600) 09/18/2018 (27165601) | 09/24/2018 09/28/2018 | 09/12/2018 |  | Completed | N (27165600) N (27165602) N (27165601) | U0101953 | Jeopardy Notification 3 (09/06/2018) | NSPE0012206074 Order Request # 195978197 | NSPE0012206074
Completed | PR517-02-IM San Juan, Puerto Rico | 9615 AVE LOS ROMEROS SAN JUAN, PR 00926-7036 PR | 200 MBPS (27391057) | 10/18/2018: 10/18 - Background: PR517-02-IM San Juan, Puerto Rico; New /200M PIP-Eth; No NID; No MNS; Status: Recvd loop delivery confirmation from PTT. Circuit testing completed. PTT confirmed LC type connector, 2 fiber cable. Ready for Plug and Play.Customer to call ondemand 866-829-9719 Demarc: FLOOR NUMBER 1ST FLOOR COMUNICATION ROOM | 195997831 | PR517-02-IM | Private IP - PIP (27391056) Access (27391057) | 27391056 27391057 | 80 MBPS (27391056) |  | 252325385 (Private IP (PIP)) 252325383 (Access) | C5005749/ADD (27391056) E5013251/ADD (27391057) | 154-1827 (27391057PTT00001) | 5997385 | 90000 | PVC ID : 5997385 VPN Name : UnitedHealthGroup Router Name : SNJN9E01 VRF Name : Vc13521:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64805 PE IP Address : 199.220.128.9 CE Address : 199.220.128.10 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (27391057) | 1000Base-LX (1310nm Single Mode Fiber) (27391057) | Ethernet | RQCA (27391057PTT00001) | 08/31/2018 (27391057PTT00001) |  | 10/18/2018 (27391057PTT00001) |  |  |  |  | BRENDA DAVILA 1-787-806-5748 brenda.davila@am.jll.com | sahil Tuteja | sahil_tuteja@optum.com | 91-828-567-0647 | 10/18/2018(Private IP - PIP) 10/18/2018(Access) |  |  | 11/19/2018 (27391056) 11/14/2018 (27391057) | 11/06/2018 | 10/18/2018 |  |  | N (27391056) N (27391057) | U0101953 |  | NSPE0012210835 Order Request # 195994623 | NSPE0012210835
Completed | VA074-02-IM Falls Church, VA | 3160 FAIRVIEW PARK DR FALLS CHURCH, VA 22042-4516 US | 50 MBPS (27279545) | 01/05/2019 Successfully activated | 195897089 | VA074-02-IM | Private IP - PIP (27279544) WAN Analysis Reporting (27279546) Access (27279545) | 27279544 27279546 27279545 | 10 MBPS (27279544) |  | 94539900 (Private IP (PIP)) 94539906 (WAN Analysis Reporting) 94539903 (Access) | C4013444/ADD (27279544) E4034283/ADD (27279545) | 36.KFGS.308906..CD (2727954539395801) | 5993918 | 10000 | PVC ID : 5993918 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64800 PE IP Address : 199.220.117.61 CE Address : 199.220.117.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27279545) | 1000Base-SX (850nm, Multi Mode Fiber) (27279545) | Ethernet | VERIZON (2727954539395801) | 08/14/2018 (2727954539395801) | 09/04/2018 (2727954539395801) | 09/05/2018 (2727954539395801) |  |  | Main lobby level, main telco room, wall mounted canoga #1 |  | Jessica Celi 1-571-342-7505 jessica_celi@uhg.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 1-763-744-2114 | 09/05/2018(Private IP - PIP) 09/05/2018(WAN Analysis Reporting) 09/05/2018(Access) | 01/05/2019 |  | 09/11/2018 (27279544) 09/07/2018 (27279545) | 09/07/2018 09/13/2018 | 09/05/2018 |  | Completed | N (27279544) N (27279546) N (27279545) | U0161525 | Jeopardy Notification 2 (08/13/2018) | NSPE0012179799 Order Request #195846677 | NSPE0012179799
Completed | Remove WAN and ETM Reporting | 505 N BRAND BLVD GLENDALE, CA 91203-1906 US | 50 MBPS (27242503) | 03/21/2019 Successfully activated | 196069249 | UNITED HEALTH-GLENDALE | Private IP - PIP (27242502) WAN Analysis Reporting (27242504) Access (27242503) | 27242502 27242504 27242503 | 10 MBPS (27242502) |  | 94545314 (Private IP (PIP)) 94545316 (WAN Analysis Reporting) 94545312 (Access) | C4013381/ADD (27242502) E4034006/ADD (27242503) |  | 5992638 | 5500 | PVC ID : 5992638 VPN Name : UnitedHealthGroup Router Name : LSA29E01 VRF Name : V461763:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64744 PE IP Address : 147.225.239.145 CE Address : 147.225.239.146 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (27242503) | Ethernet |  |  |  |  | 07/26/2018 (CCP) (27242502) 07/26/2018 (CCP) (27242503) | 07/27/2018 (CCP) (27242502) 07/27/2018 (CCP) (27242503) | Building nbb GLDLCAFP Location: 01 GLDLCAFPW04 Designator: Room Basement Floor(FL) Bas ISG400 1.1.4:0.2 Aisle.Bay.Shelf:Slot.P |  | Christopher Floyd 1-909-605-8052 christopher_floyd@uhg.com | KEVIN CANTOR | kevin_cantor@optum.com | 1-763-744-2114 | 07/27/2018(Private IP - PIP) 07/27/2018(WAN Analysis Reporting) 07/27/2018(Access) | 03/21/2019 |  | 08/08/2018 (27242502) 08/06/2018 (27242503) | 08/08/2018 08/14/2018 | 07/27/2018 |  | Completed | N (27242502) N (27242504) N (27242503) | U0101953 |  | NSPE0012238304 Order Request 196086275 | NSPE0012238304
Completed | TX410-02-IM Kyle, TX | 830 KOHLERS XING KYLE, TX 78640 US | 50 MBPS (27317177) | 03/28/2019 Background: TX410-02-IM Kyle, TX; New 10M/50M PIP-Eth; (Frontier); Dual NID; No MNS; ENID Status: Ready for activation. Telco Circuit ID: 13/OBGS/683204//FTNC/ Telco Demarcation: 1st floor comm room fiber patch panel port 1 & 2 tagged and labelled with circuit id there's a hard loop plugged in Verizon BEAS Circuit ID: 13/OBGS/683204//FTNC / E4034455 Verizon BEAS Demarcation: IT room on Rack 1 RU 37. | 196165895 | TX410-02-IM | Private IP - PIP (27317176) WAN Analysis Reporting (27317178) Access (27317177) | 27317176 27317178 27317177 | 10 MBPS (27317176) |  | 94549526 (Private IP (PIP)) 94549533 (WAN Analysis Reporting) 94549529 (Access) | C4013517/ADD (27317176) E4034455/ADD (27317177) | 13/OBGS/683204//FTNC (2731717741636501) c5wkv wkk 0001 (I0011778.AUS) | 5994919 | 5500 | PVC ID : 5994919 VPN Name : UnitedHealthGroup Router Name : AX39E01 VRF Name : Vd31961:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64794 PE IP Address : 152.185.162.13 CE Address : 152.185.162.14 QoS - Egress Profile: R12 |  | 100Base-FX (1310nm, Multi Mode Fiber) (27317177) | Ethernet | ATT (2731717741636501) | 03/07/2019 (2731717741636501) | 03/27/2019 (2731717741636501) 03/27/2019 (I0011778.AUS) | 03/25/2019 (2731717741636501) | 03/28/2019 (VFORCE) (27317177) | 03/28/2019 (VFORCE) (27317177) | DEMARCDET - 1st floor comm room fiber patch panel port 1 AND 2 tagged and labelled with circuit id there's a hard loop plugged in |  | Jenna King 1-512-504-7206 JKing@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 1-763-744-1111 | 03/28/2019(Private IP - PIP) 03/28/2019(WAN Analysis Reporting) 03/28/2019(Access) |  |  | 04/11/2019 (27317176) 04/09/2019 (27317177) | 04/17/2019 04/23/2019 | 03/28/2019 |  | Completed | N (27317176) N (27317178) N (27317177) | U0101953 | Jeopardy Notification 1 (01/29/2019) | NSPE0012261348 Order Request # 196165523 | NSPE0012261348
Completed | C1638 CTC CLX P2P; Chaska to Minneapolis; New 10G Protected 10G MPL | 1707 W CREEK LN CHASKA, MN 55318 USA | 10GL-MPL-WL-SPP (6197243) | 08/30/2018: Order complete LOA''s sent to customer | 9635111 |  | Metro Private Line (6197243) | 6197243 | 10GL-MPL-WL-SPP (6197243) |  |  | W1D34686 (6197243) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [5 empty] | Ckt id W1D34686/ Tcoms ckt id jxm6l7511 0001 Chask EQI-511-20 Minn ERC-M6L7 | PAULI GUILD 612 924 3956 | THOMAS KRENN 763 744 3141 TOM_KRENN@OPTUM.COM |  |  |  | 08/24/2018 (6197243) | 10/02/2018 |  | 10/15/2018 (6197243) | 10/15/2018 (6197243) |  |  |  | N (6197243) | 00198894 |  | NSPE0012167898 | NSPE0012167898
Completed | C1638 CTC CLX P2P; Elk River to Minneapolis; New 10G Protected MPL | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10GL-MPL-WL-SPP (6197283) | 08/30/2018: Order complete LOAs sent to customer | 9635192 |  | Metro Private Line (6197283) | 6197283 | 10GL-MPL-WL-SPP (6197283) |  |  | W1D34687 (6197283) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | PAULI GUILD 612 924 3956 PAUL_GUILD@OPTUM.COM | THOMAS KRENN 763 744 3141 TOM_KRENN@OPTUM.COM |  |  |  | 08/23/2018 (6197283) | 10/02/2018 |  | 10/15/2018 (6197283) | 10/15/2018 (6197283) |  |  |  | N (6197283) | 00198894 |  | NSPE0012167898 | NSPE0012167898
Completed | TOSA Terrell, TX |  | 10.8 MBPS (27357055) |  | 196216669 |  | Private IP - PIP (27357054) WAN Analysis Reporting (27357056) Access (27357055) | 27357054 27357056 27357055 | 10.8 MBPS (27357054) |  | 87492411 (Private IP (PIP)) 87499252 (WAN Analysis Reporting) 87496119 (Access) | C0129269/NONE (27357054) N3009497/NONE (27357055) N3009495/NONE (27357055) N3009491/NONE (27357055) N3009494/NONE (27357055) N3009492/NONE (27357055) N3009496/NONE (27357055) N3009493/NONE (27357055) |  | 5882011 | 2688 | PVC ID : 5882011 VPN Name : UnitedHealthGroup Router Name : IAEGE02 VRF Name : V104807:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64594 PE IP Address : 152.177.102.101 CE Address : 152.177.102.102 QoS - Egress Profile: R12 |  | DS1 (27357055) | TDM | [8 empty] | BECKY BROWN 1-763-744-1715 becky_j_brown@optum.com | BECKY BROWN | becky_j_brown@optum.com | 1-763-744-1715 | 07/31/2018(Private IP - PIP) 07/31/2018(WAN Analysis Reporting) 07/31/2018(Access) | 07/31/2018 |  | 07/31/2018 (27357054) 07/31/2018 (27357055) | 08/07/2018 08/01/2018 | 07/31/2018 |  |  | N (27357054) N (27357056) N (27357055) | U0101953 |  | NSPE0012275562 Order Request # 196210987 | NSPE0012275562
Completed | TOSA Bothell, WA |  | 12.3 MBPS (27357045) | 08/02/2018: Background: TOSA Service ID 87496117 Status: Pending changes to be deployed | 196216599 |  | Access (27357045) Private IP - PIP (27357044) WAN Analysis Reporting (27357046) | 27357045 27357044 27357046 | 12.3 MBPS (27357044) |  | 87496117 (Access) 87492410 (Private IP (PIP)) 87499283 (WAN Analysis Reporting) | N3009473/NONE (27357045) N3009472/NONE (27357045) N3009475/NONE (27357045) N3009474/NONE (27357045) N3009477/NONE (27357045) N3009470/NONE (27357045) N3009476/NONE (27357045) N3009471/NONE (27357045) C0129268/NONE (27357044) |  | 5865216 |  | PVC ID : 5865216 |  | DS1 (27357045) | TDM | [8 empty] | DAVE LOWRY 1-425-686-1202 DAVE.LOWRY@UHC.COM | BECKY BROWN | becky_j_brown@optum.com | 1-763-744-1715 | 08/10/2018(Access) 08/10/2018(Private IP - PIP) 08/10/2018(WAN Analysis Reporting) | 08/10/2018 |  | 07/31/2018 (27357045) 07/31/2018 (27357044) | 08/01/2018 08/07/2018 | 08/10/2018 |  |  | N (27357045) N (27357044) N (27357046) | U0101953 |  | NSPE0012275562 Order Request # 196210987 | NSPE0012275562
Completed | VA074-02-IM Falls Church, VA | 3160 FAIRVIEW PARK DR FALLS CHURCH, VA 22042-4516 US | 500 MBPS (27420464) | 01/22/2019: 01/18 - Successfully activated | 196202951 | VA074-02-IM | Access (27420464) Private IP - PIP (27420463) WAN Analysis Reporting (27420465) | 27420464 27420463 27420465 | 300 MBPS (27420463) |  | 94553234 (Access) 94553236 (Private IP (PIP)) 94553241 (WAN Analysis Reporting) | E5013385/ADD (27420464) C5005813/ADD (27420463) | 36.KFGS.309020..CD (2742046439395801) | 5998325 5998324 | 90000 | PVC ID : 5998325,5998324 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64800 PE IP Address : 152.164.143.65 CE Address : 152.164.143.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27420464) | 1000Base-SX (850nm, Multi Mode Fiber) (27420464) | Ethernet | VERIZON (2742046439395801) | 08/08/2018 (2742046439395801) | 09/04/2018 (2742046439395801) | 09/05/2018 (2742046439395801) |  |  | Lobby level, main telco, near employee lounge, wall mounted |  | BRAD HARRISON 1-170-326-9555 brad.harrison@lewin.com | RANJIT ADHIKARI | ranijt_adhikari@optum.com | 1-176-374-4195 | 09/05/2018(Access) 09/05/2018(Private IP - PIP) 09/05/2018(WAN Analysis Reporting) | 01/18/2019 |  | 08/31/2018 (27420464) 09/05/2018 (27420463) | 09/13/2018 09/19/2018 | 09/05/2018 |  | Completed | N (27420464) N (27420463) N (27420465) | U0101953 |  | NSPE0012273083 Order Request # 196202905 | NSPE0012273083
Completed | IL043-02-IJ Schaumburg, IL | 1600 MCCONNOR PKWY SCHAUMBURG, IL 60173-6801 US | 500 MBPS (27359679) | 01/25/2019 Successfully activated | 196223299 | IL043-02-IJ Catamaran Schaumburg | Private IP - PIP (27359678) WAN Analysis Reporting (27359680) Access (27359679) | 27359678 27359680 27359679 | 300 MBPS (27359678) |  | 94552643 (Private IP (PIP)) 94552647 (WAN Analysis Reporting) 94552645 (Access) | C5005713/ADD (27359678) E5013159/ADD (27359679) | 22.KGGS.023499..CBCL.. (2735967912560401) | 5996304 | 140000 | PVC ID : 5996304 VPN Name : UnitedHealthGroup Router Name : DNG9E03 VRF Name : Vc53414:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64791 PE IP Address : 152.177.168.221 CE Address : 152.177.168.222 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (27359679) | 1000Base-LX (1310nm Single Mode Fiber) (27359679) | Ethernet | COMCAST (2735967912560401) | 07/27/2018 (2735967912560401) | 09/14/2018 (2735967912560401) | 09/13/2018 (2735967912560401) | 09/18/2018 (VFORCE) (27359679) | 09/18/2018 (VFORCE) (27359679) |  |  | Matthew Schabowski 1-708-426-4153 matthew_schabowski1@uhg.com | CLIFFORD REMIGIO | clifford_remigio@optum.com | 1-763-744-2114 | 09/18/2018(Private IP - PIP) 09/18/2018(WAN Analysis Reporting) 09/18/2018(Access) | 01/28/2019 |  | 09/25/2018 (27359678) 09/21/2018 (27359679) | 09/24/2018 09/28/2018 | 09/18/2018 |  | Completed | N (27359678) N (27359680) N (27359679) | U0101953 |  | NSPE0012270812 Order Request # 196196523 | NSPE0012270812
Completed | TX078-02-IM Corpus Christi, TX | 3434 SARATOGA BLVD BLDG 1 CORPUS CHRISTI, TX 78415-5822 US | 50 MBPS (27359693) | 10/04/2018: Background: TX078-02-IM Corpus Christi, TX; New 20M/50M PIP-Eth; TWC; NID; No MNS; Status: Loop delivered on 9/27 and testing completed. Ready for customer activation. Telco Circuit ID: 36.L1XX.001088..TWCC Telco Demarc: 1st flr comm rm / IT rm rack mounted Equipment: adva 114 port 4 Verizon Circuit/BEAS ID: USATX42062233COV400001 / E4034707 Verizon Circuit/BEAS Demarc: same LAN rack | 196223647 | TX078-02-IM | Private IP - PIP (27359692) WAN Analysis Reporting (27359694) Access (27359693) | 27359692 27359694 27359693 | 20 MBPS (27359692) |  | 94554000 (Private IP (PIP)) 94554002 (WAN Analysis Reporting) 94554004 (Access) | C4013579/ADD (27359692) E4034707/ADD (27359693) | 36.L1XX.001088..TWCC (2735969342062201) | 5996307 | 10000 | PVC ID : 5996307 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64793 PE IP Address : 152.177.194.217 CE Address : 152.177.194.218 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (27359693) | 1000Base-SX (850nm, Multi Mode Fiber) (27359693) | Ethernet | TIME WARNER CABLE (2735969342062201) | 07/27/2018 (2735969342062201) | 12/03/2018 (2735969342062201) | 09/26/2018 (2735969342062201) | 09/27/2018 (VFORCE) (27359693) | 09/27/2018 (VFORCE) (27359693) | DEMARCDET - 1st flr comm rm / IT rm rack mounted |  | LUIS CASAS 1-195-645-5505 luisecasas@yahoo.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 1-763-744-2114 | 09/27/2018(Private IP - PIP) 09/27/2018(WAN Analysis Reporting) 09/27/2018(Access) |  |  | 12/12/2018 (27359692) 12/10/2018 (27359693) | 09/06/2018 09/12/2018 | 09/27/2018 |  | Completed | N (27359692) N (27359694) N (27359693) | U0101953 |  | NSPE0012277047 Order Request # 196215323 | NSPE0012277047
Completed | TN050 Franklin, TN | 1893 GENERAL GEORGE PATTON DR FRANKLIN, TN 37067-2655 US | 3 MBPS (27381325) | 08/02/2018: Background: TN050-02-IM Franklin, TN; New 3M/3M MLPPP; BellSouth; No NID; No MNS Status: FOC 8/13 | 196245555 | TN050-02-IM | Private IP - PIP (27381324) WAN Analysis Reporting (27381326) Access (27381325) | 27381324 27381326 27381325 | 3 MBPS (27381324) |  | 264801673 (Private IP (PIP)) 264801755 (WAN Analysis Reporting) 264801669 (Access) | C1076603/ADD (27381324) N1043996/ADD (27381325) N1043997/ADD (27381325) | T4/HCGS/866907//SC (2738132542136001) | 5997010 | 1700 | PVC ID : 5997010 VPN Name : UnitedHealthGroup Router Name : MEJ3E01 VRF Name : Vc45293-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64790 PE IP Address : 147.225.28.97 CE Address : 147.225.28.98 QoS - Egress Profile: R12 |  | DS1 (27381325) | TDM | ATT (2738132542136001) | 07/31/2018 (2738132542136001) | 08/13/2018 (2738132542136001) | 08/13/2018 (2738132542136001) |  |  | Telco Circuit ID: T4/HCGS/866907//SC Telco Demarcation: Main Bldg, MDF Room N1043997 -MM CAB SLOT 2 N1043996 -MM CAB SLOT 1 RJ48C Tagged and Not Extended |  | RYANE CAMERON 1-404-308-5876 ryane.cameron@am.jll.com | Sahil Tuteja | sahil_tuteja@optum.com | 1-828-567-0647 | 08/14/2018(Private IP - PIP) 08/14/2018(WAN Analysis Reporting) 08/14/2018(Access) |  |  | 08/20/2018 (27381324) 08/16/2018 (27381325) | 08/22/2018 08/28/2018 | 08/14/2018 |  | Completed | N (27381324) N (27381326) N (27381325) | U0101953 |  | NSPE0012282981 Order Request # 196231303 | NSPE0012282981
Completed | UT019-01-IM Sandy, UT | 1403 E SEGO LILY DR SANDY, UT 84092-4350 US | 20 MBPS (27381460) | 09/07/2018: Order complete | 196245893 | Pico UT019-01-IM | Private IP - PIP (27381459) WAN Analysis Reporting (27381461) Access (27381460) | 27381459 27381461 27381460 | 10 MBPS (27381459) |  | 264869211 (Private IP (PIP)) 264869213 (WAN Analysis Reporting) 264869207 (Access) | C3019532/ADD (27381459) E3056436/ADD (27381460) | 69.KXGS.338723..MS (2738146038000401) | 5997015 | 5500 | PVC ID : 5997015 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64833 PE IP Address : 68.136.105.169 CE Address : 68.136.105.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27381460) | 1000Base-SX (850nm, Multi Mode Fiber) (27381460) | Ethernet | CENTURYLINK (2738146038000401) | 08/17/2018 (2738146038000401) | 09/10/2018 (2738146038000401) | 09/05/2018 (2738146038000401) | 09/06/2018 (VFORCE) (27381460) | 09/06/2018 (VFORCE) (27381460) | DEMARCDET - MAIN TELECO ROOM IN BASEMENT NORTH WEST CORNER OF BUILDING, BACK SIDE OF ELEVATOR, COME DOWN STAIRS TURN LEFT, LEFT AGAIN, LEFT INTO ELECTRIC ROOM Type: OPTICAL Port: 3 |  | Darrick Porter 1-801-870-4617 darrick@bigtreeconst.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 09/06/2018(Private IP - PIP) 09/06/2018(WAN Analysis Reporting) 09/06/2018(Access) |  |  | 10/26/2018 (27381459) 10/24/2018 (27381460) | 09/27/2018 10/03/2018 | 09/06/2018 |  | Completed | N (27381459) N (27381461) N (27381460) | U0101953 |  | NSPE0012284042 Order Request # 196234475 | NSPE0012284042
Completed | MN013-61-IM Configuration correction | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 4000 MBPS (CQBLMX14) |  | 9646354 |  | Private IP Port Only (CQBLMX14) | CQBLMX14 | 4000 MBPS | P2198241 |  | BOBLC5XS0001 (CQBLMX14) |  | 5994799 5998251 | 72000 | PVC ID : 5994799,5998251 VPN Name : UHG-SDWAN Router Name : MN39E01 VRF Name : Vd76602:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.164.75.1 CE Address : 152.164.75.2 QoS - Egress Profile: R12 | [9 empty] | RELATED ACCEESW1D29691 |  | MELISSA CHAPMAN 0015072950001 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/07/2018 (CQBLMX14) | 08/07/2018 |  | 08/30/2018 (CQBLMX14) | 08/30/2018 (CQBLMX14) |  |  |  | N (CQBLMX14) | 05017789 |  |  | NSPE0012167898
Completed | C1641-02-IM Ashburn, VA | 21635 RED RUM DR ASHBURN, VA 20147-7501 US | 1 GBPS (27457242) | 08/21/2018: Order complete ready for self activation | 196297407 | C1641-02-IM | Access (27457242) Private IP - PIP (27457241) WAN Analysis Reporting (27457243) | 27457242 27457241 27457243 | 800 MBPS (27457241) |  | 94557019 (Access) 94557014 (Private IP (PIP)) 94557016 (WAN Analysis Reporting) | E5013506/ADD (27457242) C0150585/ADD (27457241) | 46.KFGS.304854..CV (2745724242462301) | 5999749 | 500000 | PVC ID : 5999749 VPN Name : UHG-ECC Router Name : WA39E02 VRF Name : Vc47595:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65477 PE IP Address : 152.177.6.113 CE Address : 152.177.6.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27457242) | 1000Base-SX (850nm, Multi Mode Fiber) (27457242) | Ethernet | VERIZON (2745724242462301) | 08/20/2018 (2745724242462301) | 08/20/2018 (2745724242462301) | 08/20/2018 (2745724242462301) |  |  |  |  | Tanu Bah 1-571-474-8531 tanu.bah@ttec.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 08/20/2018(Access) 08/20/2018(Private IP - PIP) 08/20/2018(WAN Analysis Reporting) |  |  | 08/27/2018 (27457242) 08/29/2018 (27457241) | 09/12/2018 09/18/2018 | 08/20/2018 |  | Completed | N (27457242) N (27457241) N (27457243) | U0101953 | Jeopardy Notification 1 (08/15/2018) | NSPE0012297528 Order Request # 196286251 | NSPE0012297528
Completed | TX042-01-IM Corpus Christi, TX | 5262 S STAPLES ST STE 300 CORPUS CHRISTI, TX 78411-4137 US | 10 MBPS (27420270) | 01/14/2019: 01/11 Successfully activated | 196298789 | TX042-01-IM | Private IP - PIP (27420269) WAN Analysis Reporting (27420271) Access (27420270) | 27420269 27420271 27420270 | 10 MBPS (27420269) |  | 94555897 (Private IP (PIP)) 94556901 (WAN Analysis Reporting) 94555899 (Access) | C0149543/ADD (27420269) E3056709/ADD (27420270) | 34/KRGN/613864//SW (2742027042449701) | 5998317 | 5500 | PVC ID : 5998317 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64783 PE IP Address : 68.138.232.253 CE Address : 68.138.232.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27420270) | 1000Base-SX (850nm, Multi Mode Fiber) (27420270) | Ethernet | ATT (2742027042449701) | 11/30/2018 (2742027042449701) | 12/20/2018 (2742027042449701) | 12/21/2018 (2742027042449701) | 12/27/2018 (VFORCE) (27420270) | 12/27/2018 (VFORCE) (27420270) | DEMARCDET - INSIDE THE BLDG 1ST FL TELEPHONE RM MPOE WALLMOUNTED HANDOFF PANEL POS 1 AND 2 |  | Felipe Meza 1-210-388-2220 Felipe_meza@uhc.com | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 1-763-744-2114 | 12/27/2018(Private IP - PIP) 12/27/2018(WAN Analysis Reporting) 12/27/2018(Access) | 01/11/2019 |  | 12/11/2018 (27420269) 12/07/2018 (27420270) | 01/10/2019 01/16/2019 | 12/27/2018 |  | Completed | N (27420269) N (27420271) N (27420270) | U0101953 | Jeopardy Notification 1 (12/26/2018) | NSPE0012299214 Order Request # 196290795 | NSPE0012299214
Completed | AZ024-02-IM Tucson, AZ | 4811 E GRANT RD STE 119 TUCSON, AZ 85712-2763 US | 50 MBPS (27421314) | 02/21/2019: 2/21Background: AZ024-02-IM Tucson, AZ; New 10M/50M PIP-Eth; (Qwest/CTL); NID; No MNS Status: Ready for activation Next action: Ready for activation | 196300177 | AZ024-02-IM | Access (27421314) Private IP - PIP (27421313) WAN Analysis Reporting (27421315) | 27421314 27421313 27421315 | 10 MBPS (27421313) |  | 94557285 (Access) 94557280 (Private IP (PIP)) 94557282 (WAN Analysis Reporting) | E4035034/ADD (27421314) C4013691/ADD (27421313) | 19/KXGS/340459//MS (2742131442584101) | 5998338 | 10000 | PVC ID : 5998338 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64777 PE IP Address : 68.138.169.173 CE Address : 68.138.169.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27421314) | 1000Base-SX (850nm, Multi Mode Fiber) (27421314) | Ethernet | CENTURYLINK (2742131442584101) | 12/18/2018 (2742131442584101) | 02/28/2019 (2742131442584101) | 02/11/2019 (2742131442584101) | 02/13/2019 (VFORCE) (27421314) | 02/13/2019 (VFORCE) (27421314) | DEMARCDET - XXX |  | Zak Becker 1-612-817-2386 Zachery.becker@uhc.com | DAVID CASANOVA | david_casanova@optum.com | 1-176-374-4158 | 02/13/2019(Access) 02/13/2019(Private IP - PIP) 02/13/2019(WAN Analysis Reporting) | 03/11/2019 |  | 01/17/2019 (27421314) 01/22/2019 (27421313) | 01/28/2019 02/01/2019 | 02/13/2019 |  | Completed | N (27421314) N (27421313) N (27421315) | U0101953 |  | NSPE0012302402 Order Request # 196300121 | NSPE0012302402
Completed | Change Billing (MRV) info | 1707 W CREEK LN CHASKA, MN 55318 USA | 100GLMPL-WL-PU (6203551) 100N-MPL-WL-PU (6203552) | 08/24/2018: Background: Chaska to Elk River record change W1D29718 Change METRO PL 100GB-OTU4 UNPROT WAVE P2P to a METRO PL 100GB-ETHER LAN PHY UNPROT P2P. Status Pending order progress Chaska dispatch 8/23 Elk dispatch 8/24 | 9652321 |  | Metro Private Line (6203551) Metro Private Line (6203552) | 6203551 6203552 | 100GLMPL-WL-PU (6203551) 100N-MPL-WL-PU (6203552) |  |  | W1D37987 (6203551) W1D29718 (6203552) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | MELISSA CHAPMAN TOM KRENN 763 744 2114 763 744 3141 TOM_KRENN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 08/27/2018 (6203551) | 09/11/2018 | 08/27/2018 | 11/02/2018 (6203551) 11/02/2018 (6203552) | 11/02/2018 (6203551) 08/30/2018 (6203552) |  |  |  | N (6203551) N (6203552) | 00198894
Completed | KS015 Overland Park, KS | 6860 W 115TH ST OVERLAND PARK, KS 66211-2457 US | 1 GBPS (27426060) | 08/09/2019 - Successfully activated | 196305975 | UNITED HEALTH GROUP | Private IP - PIP (27426059) WAN Analysis Reporting (27426061) Access (27426060) | 27426059 27426061 27426060 | 500 MBPS (27426059) |  | 94557402 (Private IP (PIP)) 94557407 (WAN Analysis Reporting) 94557404 (Access) | C0149571/ADD (27426059) E5013400/ADD (27426060) | 91.L1XX.009643..TWCC (2742606025704801) | 5998511 | 250000 | PVC ID : 5998511 VPN Name : UnitedHealthGroup Router Name : IDCXE03 VRF Name : V560358-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64905 PE IP Address : 152.161.161.209 CE Address : 152.161.161.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27426060) | 1000Base-SX (850nm, Multi Mode Fiber) (27426060) | Ethernet | TIME WARNER CABLE (2742606025704801) | 03/28/2019 (2742606025704801) | 04/30/2019 (2742606025704801) | 04/12/2019 (2742606025704801) | 04/15/2019 (VFORCE) (27426060) | 04/15/2019 (VFORCE) (27426060) | DEMARCDET - RAD INSTALLED IN BASEMENT SERVER ROOM |  | Stuart Griswold 1-913-253-0660 stuart_griswold@uhg.com | Rajesh John Catalonia | rajesh_catalonia@optum.com | 1-763-744-2114 | 04/15/2019(Private IP - PIP) 04/15/2019(WAN Analysis Reporting) 04/15/2019(Access) | 08/09/2019 |  | 05/09/2019 (27426059) 05/07/2019 (27426060) | 07/10/2019 07/16/2019 | 04/15/2019 |  | Scheduled Completed | N (27426059) N (27426061) N (27426060) | U0101953 | Jeopardy Notification 1 (01/25/2019) | NSPE0012303684 Order Request # 196304127 | NSPE0012303684
Completed | UT016-02-IM Draper, UT | 13961 S MINUTEMAN DR STE 330 DRAPER, UT 84020-8086 US | 50 MBPS (27479893) | 08/29/2018: Order complete. Ready to self-activate | 196381929 | UT016-02-IM | Private IP - PIP (27479892) WAN Analysis Reporting (27479894) Access (27479893) | 27479892 27479894 27479893 | 20 MBPS (27479892) |  | 270021429 (Private IP (PIP)) 270021431 (WAN Analysis Reporting) 270021421 (Access) | C4013833/ADD (27479892) E4035393/ADD (27479893) | 69.KXGS.342533..MS (2747989342206001) | 6000334 | 13000 | PVC ID : 6000334 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65058 PE IP Address : 152.162.61.25 CE Address : 152.162.61.26 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27479893) | 1000Base-SX (850nm, Multi Mode Fiber) (27479893) | Ethernet | CENTURYLINK (2747989342206001) | 08/16/2018 (2747989342206001) | 08/27/2018 (2747989342206001) | 08/27/2018 (2747989342206001) | 08/28/2018 (VFORCE) (27479893) |  | DEMARCDET - MAIN TELECO ROOM DOWM HALLWAY EAST OF ELEVATORS PAST MAIL |  | Geronimo Arbutante 1-612-274-3897 garbutante@savvysherpa.com | TONY EPPERSON EPPERSON | tony.epperson@optum.com | 1-131-231-5561 | 08/28/2018(Private IP - PIP) 08/28/2018(WAN Analysis Reporting) 08/28/2018(Access) |  |  | 09/06/2018 (27479892) 09/04/2018 (27479893) | 09/26/2018 10/02/2018 | 08/28/2018 |  | Completed | N (27479892) N (27479894) N (27479893) | U0101953 |  | NSPE0012320943 Order Request # 196373265 | NSPE0012320943
Completed | TX427-02-IM McAllen, TX | 3300 N MCCOLL RD MCALLEN, TX 78501-5776 US | 50 MBPS (27499428) | 12/17/2018 Background: TX427-02-IM McAllen, TX; New 20M/50M PIP-Eth; TWC; NID; No MNS; Status: Ready for activation Next action: Customer to activate Who owns the next action: Customer Ticket: NA Telco Circuit ID: 95.L1XX.008748..TWCC Telco Demarcation: First Floor, Network Room, Wall Mounted Equipment, RAD 203, Port 5 Verizon BEAS Circuit ID: USATX43294029COV400001 / E4035587 Verizon BEAS Demarcation: First Floor, Network Room, Wall Mounted Equipment, Unit 38 on the rack, labeled | 196538379 | TX427-02-IM | Private IP - PIP (27499427) WAN Analysis Reporting (27499429) Access (27499428) | 27499427 27499429 27499428 | 20 MBPS (27499427) |  | 94559424 (Private IP (PIP)) 94559427 (WAN Analysis Reporting) 94559422 (Access) | C4013901/ADD (27499427) E4035587/ADD (27499428) | 95.L1XX.008748..TWCC (2749942843294001) | 6001262 | 13000 | PVC ID : 6001262 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64771 PE IP Address : 68.138.110.49 CE Address : 68.138.110.50 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27499428) | 1000Base-SX (850nm, Multi Mode Fiber) (27499428) | Ethernet | TIME WARNER CABLE (2749942843294001) | 08/20/2018 (2749942843294001) | 12/21/2018 (2749942843294001) | 12/14/2018 (2749942843294001) | 12/17/2018 (VFORCE) (27499428) |  | DEMARCDET - FIRST FLOOR, NETWORK ROOM, WALL MOUNTED |  | Jason Ozer 1-210-250-1454 jozer@wellmed.net | Rizwan Anugula | rizwan.anugula@optum.com | 91-804-670-4280 | 12/17/2018(Private IP - PIP) 12/17/2018(WAN Analysis Reporting) 12/17/2018(Access) |  |  | 01/03/2019 (27499427) 12/31/2018 (27499428) | 12/03/2018 12/07/2018 | 12/17/2018 |  | Completed | N (27499427) N (27499429) N (27499428) | U0101953 |  | NSPE0012329921 | NSPE0012329921
Completed | TX442 Dallas, TX | 1251 E RED BIRD LN DALLAS, TX 75241-2008 US | 50 MBPS (27508236) | 12/06/2018: 12/05 Background: TX442 Dallas, TX; New 10M/50M PIP-Eth; (TWC); NID; No MNS; ENID; Status: Ready for activation. Customer informed Next action: Customer to activate service Who owns the next action: Customer Ticket: NA Telco Circuit ID: 21.L1XX.022420..TWCC Telco Demarcation: IT closet behind the main desk mounted in the wing rack w/the jumper going to th NID Equipmen:RAD 203 port 5 Verizon BEAS Circuit ID: USATX43621187COV400001 / E4035623 Verizon BEAS Demarcation: 1st floor, server closet, backboard wall mounted cabinet, next to LEC, MM SFP port 0/1. Tagged with ckt id and order number. | 196576759 | TX442 | Private IP - PIP (27508235) WAN Analysis Reporting (27508237) Access (27508236) | 27508235 27508237 27508236 | 10 MBPS (27508235) |  | 272788157 (Private IP (PIP)) 272788159 (WAN Analysis Reporting) 272787953 (Access) | C4013914/ADD (27508235) E4035623/ADD (27508236) | 21.L1XX.022420..TWCC (2750823643621101) | 6001477 | 5500 | PVC ID : 6001477 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65094 PE IP Address : 68.136.210.85 CE Address : 68.136.210.86 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27508236) | 1000Base-SX (850nm, Multi Mode Fiber) (27508236) | Ethernet | TIME WARNER CABLE (2750823643621101) | 08/21/2018 (2750823643621101) | 12/19/2018 (2750823643621101) | 12/03/2018 (2750823643621101) | 12/05/2018 (VFORCE) (27508236) | 12/05/2018 (VFORCE) (27508236) | DEMARCDET - IT closet behind the main desk mounted in the wing rack w/the jumper going to th NID |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 12/05/2018(Private IP - PIP) 12/05/2018(WAN Analysis Reporting) 12/05/2018(Access) |  |  | 12/31/2018 (27508235) 12/27/2018 (27508236) | 12/03/2018 12/07/2018 | 12/09/2018 |  | Completed | N (27508235) N (27508237) N (27508236) | U0101953 |  | NSPE0012333018 | NSPE0012333018
Completed | NY004-07-IM New York, NY | 168 CENTRE ST NEW YORK, NY 10013-3477 US | 50 MBPS (27592623) | 05/21/2019 Successfully activated | 196601589 | UNITED HEALTH GROUP | Private IP - PIP (27592622) WAN Analysis Reporting (27592624) Access (27592623) | 27592622 27592624 27592623 | 20 MBPS (27592622) |  | 273292165 (Private IP (PIP)) 273292167 (WAN Analysis Reporting) 273292161 (Access) | C4014132/ADD (27592622) E4036176/ADD (27592623) | 32.KFGS.217156..NY (2759262374246201) | 6004558 | 9000 | PVC ID : 6004558 VPN Name : UnitedHealthGroup Router Name : NV89E01 VRF Name : V105387:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64761 PE IP Address : 152.161.83.89 CE Address : 152.161.83.90 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27592623) | 1000Base-SX (850nm, Multi Mode Fiber) (27592623) | Ethernet | VERIZON (2759262374246201) | 09/06/2018 (2759262374246201) | 09/26/2018 (2759262374246201) | 09/24/2018 (2759262374246201) |  |  | DEMARCDET - NA |  | Angela Tse 1-212-271-0761 antse@uhc.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 09/25/2018(Private IP - PIP) 09/25/2018(WAN Analysis Reporting) 09/25/2018(Access) | 05/21/2019 |  | 09/21/2018 (27592622) 09/19/2018 (27592623) | 10/02/2018 10/08/2018 | 09/24/2018 |  | Completed | N (27592622) N (27592624) N (27592623) | U0101953 |  | NSPE0012335473 | NSPE0012335473
Completed | Ashburn Access | 21721 FILIGREE CT ASHBURN, VA 20147-6207 US | 1 GBPS (27539424) | 12/28/2018: 12/28 Activation scheduled 01/16/2019 2:30PM - 5:30PM CST | 196619747 | Ashburn | Access (27539424) | 27539424 |  |  | 265961345 (Access) | E5013713/ADD (27539424) | 46.KFGS.304894..CV (2753942483067501) |  |  |  | 1000Base-LX-1310nm (27539424) | 1000Base-LX (1310nm Single Mode Fiber) (27539424) | Ethernet | VERIZON (2753942483067501) | 08/31/2018 (2753942483067501) | 09/06/2018 (2753942483067501) | 09/07/2018 (2753942483067501) |  |  | VZB DMARC: 1ST FL DATA CTR CAGE 62300 R/R 0102 UNIT #6 EXT TO PNL PP:-1-3:150720 JK #6 |  | Ryan Kristoffersen 1-408-451-1931 rkristoffersen@equinix.com | Ryan Kristoffersen | rkristoffersen@equinix.com | 1-408-451-1931 | 09/06/2018(Access) |  |  | 09/13/2018 (27539424) | 09/21/2018 | 09/06/2018 |  |  | N (27539424) | U0101953 |  | NSPE0012327576 | NSPE0012327576
Completed | Falls Church-Ashburn Connection | 21721 FILIGREE CT ASHBURN, VA 20147-6207 US |  | 11/28/2018: 11/28 Eline Falls Church-Ashburn Connection Status: Associated access Service Order: 196619743. Access update: Delivered and ready for customer activation | 196620339 |  | Ethernet Switched E-Line (28149085) | 28149085 |  |  | 265972423 (Ethernet Switched E-Line) | C0157088/ADD (28149085) | [14 empty] | Susan Wagner 1-763-744-0632 susan_l_wagner@optum.com | Kris Seehoff 1-763-744-1584 brad.harrison@lewin.com |  |  |  | 11/30/2018(Ethernet Switched E |  |  | 12/03/2018 (28149085) | 12/07/2018 | 11/30/2018 |  |  | N (28149085) | U0101953 |  | NSPE0012327576 | NSPE0012327576
Completed | Falls Church Access | 3160 FAIRVIEW PARK DR FALLS CHURCH, VA 22042-4516 US | 1 GBPS (27754922) | 01/23/2019: 01/23 - Activation needs to be rescheduled due to customer cabling issue | 196619743 | VA074-02-IM | Access (27754922) | 27754922 |  |  | 265961349 (Access) | E5014363/ADD (27754922) | 36.KFGS.309235..CD (2775492239395801) |  |  |  | 1000Base-LX-1310nm (27754922) | 1000Base-LX (1310nm Single Mode Fiber) (27754922) | Ethernet | VERIZON (2775492239395801) | 09/28/2018 (2775492239395801) | 10/12/2018 (2775492239395801) | 10/12/2018 (2775492239395801) |  |  | DEMARCDET - LOBBY LEVEL MTR WALL MOUNT NID #3. TAGGED |  | BRAD HARRISON 1-703-269-5999 brad.harrison@lewin.com | BRAD HARRISON | brad.harrison@lewin.com | 1-703-269-5999 | 10/18/2018(Access) |  |  | 10/19/2018 (27754922) | 10/25/2018 | 10/18/2018 |  |  | N (27754922) | U0101953 |  | NSPE0012327576 | NSPE0012327576
Completed | Falls Church-Atlanta Connection | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 10/04/2018: Eline Falls Church-Ashburn Connection Status: Associated access Service Order: 196619743. Access update: FOC 10/12/18. | 196620337 |  | Ethernet Switched E-Line (27866704) | 27866704 |  |  | 265973675 (Ethernet Switched E-Line) | C0153728/ADD (27866704) | [14 empty] | Susan Wagner 1-763-744-0632 susan_l_wagner@optum.com | Kris Seehoff 1-763-744-1584 kevin.arts@broad-path.com |  |  |  | 10/18/2018(Ethernet Switched E |  |  | 10/16/2018 (27866704) | 10/23/2018 | 10/18/2018 |  |  | N (27866704) | U0101953 |  | NSPE0012327576 | NSPE0012327576
Completed | Atlanta Access | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US | 1 GBPS (27528391) | 01/24/2019: 01/22 Successfully activated | 196619745 | Equinix hub Atlanta Peachtree GA777-04-IJ | Access (27528391) | 27528391 |  |  | 265961353 (Access) | E5013682/ADD (27528391) | [5 empty] | 1000Base-LX (1310nm Single Mode Fiber) (27528391) | Ethernet | [6 empty] | 2nd floor Equinix meet-me room--Cage 21720 PP205:1110141 pair 13,14 |  | Ryan Kristoffersen 1-408-451-1931 rkristoffersen@equinix.com | Ryan Kristoffersen | rkristoffersen@equinix.com | 1-408-451-1931 | 09/06/2018(Access) | 01/22/2019 |  | 09/04/2018 (27528391) | 09/20/2018 | 09/06/2018 |  |  | N (27528391) | U0101953 |  | NSPE0012327576 | NSPE0012327576
Completed | Ashburn-Atlanta Connection | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 09/07/2018: Ashburn-Atlanta closed | 196619925 |  | Ethernet Switched E-Line (27570645) | 27570645 |  |  | 265972747 (Ethernet Switched E-Line) | C1078316/ADD (27570645) | [14 empty] | BRAD HARRISON 1-703-269-5551 brad.harrison@lewin.com | Kris Seehoff 1-763-744-1584 kevin.arts@broad-path.com |  |  |  | 09/06/2018(Ethernet Switched E |  |  | 09/14/2018 (27570645) | 09/27/2018 | 09/06/2018 |  |  | N (27570645) | U0101953 |  | NSPE0012327576 | NSPE0012327576
Completed | TX437-02-IJ Houston, TX | 9380 W SAM HOUSTON PKWY S HOUSTON, TX 77099-5222 US | 50 MBPS (27533159) | 05/23/2019: 05/22 Successfully activated | 196697387 | TX437-02-IJ | WAN Analysis Reporting (27533160) Access (27533159) Private IP - PIP (27533158) | 27533160 27533159 27533158 | 10 MBPS (27533158) |  | 271756647 (WAN Analysis Reporting) 271756641 (Access) 271756645 (Private IP (PIP)) | C4013993/ADD (27533158) E4035745/ADD (27533159) | 54.KGGS.013270..CBCL.. (2753315943461701) | 6002284 | 5000 | PVC ID : 6002284 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64769 PE IP Address : 199.220.218.9 CE Address : 199.220.218.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27533159) | 1000Base-SX (850nm, Multi Mode Fiber) (27533159) | Ethernet | COMCAST (2753315943461701) | 08/27/2018 (2753315943461701) | 01/15/2019 (2753315943461701) | 04/15/2019 (2753315943461701) | 04/16/2019 (VFORCE) (27533159) | 04/16/2019 (VFORCE) (27533159) | DEMARCDET - main flr IT rm labeled verizon comcast rack 2 mounted RU 28 port 1 |  | Paul Keating 1-713-855-5487 Paul.Keating@forneyconstruction.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 04/16/2019(WAN Analysis Reporting) 04/16/2019(Access) 04/16/2019(Private IP - PIP) | 05/22/2019 |  | 01/25/2019 (27533158) 01/23/2019 (27533159) | 10/10/2018 10/04/2018 | 04/16/2019 |  | Completed | N (27533160) N (27533159) N (27533158) | U0101953 |  | NSPE0012335924 Order Request # 196605961 | NSPE0012335924
Completed | KY010-08-IM Louisville, KY | 9100 SHELBYVILLE RD STE 200 LOUISVILLE, KY 40222-5160 US | 50 MBPS (27533633) | 02/20/2019: 02/19 Successfully activated. | 196541017 | KY010-08-IM | Private IP - PIP (27533632) WAN Analysis Reporting (27533634) Access (27533633) | 27533632 27533634 27533633 | 10 MBPS (27533632) |  | 94560787 (Private IP (PIP)) 94560793 (WAN Analysis Reporting) 94560789 (Access) | C4014005/ADD (27533632) E4035749/ADD (27533633) | KY/KXFN/046659/LVLC (2753363343621101) | 6002300 | 5500 | PVC ID : 6002300 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65021 PE IP Address : 152.181.22.125 CE Address : 152.181.22.126 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (27533633) | 1000Base-SX (850nm, Multi Mode Fiber) (27533633) | Ethernet | LEVEL 3 (2753363343621101) | 08/30/2018 (2753363343621101) | 10/11/2018 (2753363343621101) | 10/15/2018 (2753363343621101) | 10/16/2018 (VFORCE) (27533633) | 10/16/2018 (VFORCE) (27533633) | Telco Circuit ID: KY/KXFN/046659/LVLC Telco Demarcation: 2nd Floor, Suite 270, Server Room, RR #1 RMU 43, Rack mount CISCO 3600 port 11 ext FDP fibers 1/2, SMF, LC tagged Verizon BEAS Circuit ID: NID:USAKY43621189COV400001 / E4035749 Verizon BEAS Demarcation: Suite 270, Data Room. Rack mounted, Slot 41. AM SEP connects to LEC |  | Eddie Gibson 1-502-318-1820 todd.gibson@optum.com | Jason Salaping | jason_salaping@optum.com | 632-462-2446 | 10/16/2018(Private IP - PIP) 10/16/2018(WAN Analysis Reporting) 10/16/2018(Access) | 02/19/2019 |  | 10/22/2018 (27533632) 10/18/2018 (27533633) | 10/09/2018 10/15/2018 | 10/16/2018 |  | Completed | N (27533632) N (27533634) N (27533633) | U0101953 |  | NSPE0012330442 Order Request # 196539783 | NSPE0012330442
Completed | VA731-01-IM Ashburn, VA | 21721 FILIGREE CT ASHBURN, VA 20147-6207 US | 1 GBPS (27554215) | 12/13/2018 Successfully activated | 196642351 | Ashburn | Private IP - PIP (27554214) WAN Analysis Reporting (27554216) Access (27554215) | 27554214 27554216 27554215 | 400 MBPS (27554214) |  | 94563664 (Private IP (PIP)) 94563662 (WAN Analysis Reporting) 94563668 (Access) | C0151346/ADD (27554214) E5013765/ADD (27554215) | 46.KFGS.304912..CV (2755421583067501) | 6003048 6003047 | 45000 | PVC ID : 6003048,6003047 VPN Name : UnitedHealthGroup-ECCMA Router Name : RIJ9E03 VRF Name : Vc75267:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64767 PE IP Address : 206.115.119.9 CE Address : 206.115.119.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27554215) | 1000Base-SX (850nm, Multi Mode Fiber) (27554215) | Ethernet | VERIZON (2755421583067501) | 08/31/2018 (2755421583067501) | 10/05/2018 (2755421583067501) | 11/15/2018 (2755421583067501) |  |  | DEMARCDET - dc6, cage 62300, rr0105, unit 10L, ext to rr0103, patch panel cp:0103:1049049, jk 27, tagged |  | BRAD HARRISON 1-703-269-5551 brad.harrison@lewin.com | RANJIT ADHIKARI | ranijt_adhikari@optum.com | 1-763-744-1957 | 11/15/2018(Private IP - PIP) 11/15/2018(WAN Analysis Reporting) 11/15/2018(Access) | 12/13/2018 |  | 10/16/2018 (27554214) 10/12/2018 (27554215) | 09/25/2018 10/01/2018 | 11/15/2018 |  | Completed | N (27554214) N (27554216) N (27554215) | U0101953 |  | NSPE0012339015 Order Request # 196642337 | NSPE0012339015
Completed | FL349-02-IM Clearwater, FL | 1685 GULF TO BAY BLVD CLEARWATER, FL 33755-6422 US | 50 MBPS (27538322) | 03/04/2019 Successfully activated | 196702987 | FL349-02-IM | Access (27538322) Private IP - PIP (27538321) WAN Analysis Reporting (27538323) | 27538322 27538321 27538323 | 10 MBPS (27538321) |  | 94564036 (Access) 94564033 (Private IP (PIP)) 94564031 (WAN Analysis Reporting) | E4035769/ADD (27538322) C4014037/ADD (27538321) | 72.L1XX.800086..TWCC (2753832243866501) | 6002444 | 5000 | PVC ID : 6002444 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64757 PE IP Address : 152.183.208.9 CE Address : 152.183.208.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27538322) | 1000Base-SX (850nm, Multi Mode Fiber) (27538322) | Ethernet | BRIGHT HOUSE (2753832243866501) | 12/28/2018 (2753832243866501) | 02/15/2019 (2753832243866501) | 02/11/2019 (2753832243866501) | 02/13/2019 (VFORCE) (27538322) | 02/13/2019 (VFORCE) (27538322) | DEMARCDET - wall mounted in electrical rm |  | TODD VANDERSCHAEGEN 1-813-629-2611 tvanderschaegen@wellmed.net | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 02/13/2019(Access) 02/13/2019(Private IP - PIP) 02/13/2019(WAN Analysis Reporting) | 03/04/2019 |  | 01/11/2019 (27538322) 01/15/2019 (27538321) | 04/10/2019 04/16/2019 | 02/13/2019 |  | Completed | N (27538322) N (27538321) N (27538323) | U0101953 |  | NSPE0012339396 Order Request # 196648457 | NSPE0012339396
Completed | TX430-02-IM Windcrest, TX | 5340 WALZEM RD STE 5340 WINDCREST, TX 78218-2123 US | 100 MBPS (27538376) | 12/19/2018: 12/19 Background: TX430-02-IM Windcrest, TX; New 10M/100M PIP-Eth; (AT&T); NID; No MNS; Status: Loop delivered. Pending BEAS installation schedule Next action: Line testing | 196703025 | TX430-02-IM | Private IP - PIP (27538375) WAN Analysis Reporting (27538377) Access (27538376) | 27538375 27538377 27538376 | 10 MBPS (27538375) |  | 94563943 (Private IP (PIP)) 94563947 (WAN Analysis Reporting) 94563945 (Access) | C1078022/ADD (27538375) E4035771/ADD (27538376) | 31/KRGN/653235//SW (2753837643868501) | 6002599 | 5500 | PVC ID : 6002599 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65077 PE IP Address : 68.137.212.165 CE Address : 68.137.212.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27538376) | 1000Base-SX (850nm, Multi Mode Fiber) (27538376) | Ethernet | ATT (2753837643868501) | 11/27/2018 (2753837643868501) | 12/10/2018 (2753837643868501) | 12/18/2018 (2753837643868501) | 12/20/2018 (VFORCE) (27538376) |  | DEMARCADDR - . DEMARCDET - 1ST FLR IT ROOM 3903 PORT 2 TAGGED MMF |  | Gabriel Rodriguez 1-210-974-6678 GRodriguez1@wellmed.net | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 12/20/2018(Private IP - PIP) 12/20/2018(WAN Analysis Reporting) 12/20/2018(Access) |  |  | 12/19/2018 (27538375) 12/17/2018 (27538376) | 01/07/2019 01/11/2019 | 12/20/2018 |  | Completed | N (27538375) N (27538377) N (27538376) | U0101953 | Jeopardy Notification 1 (11/26/2018) | NSPE0012339541 Order Request # 196651609 | NSPE0012339541
Completed | TX415-02-IM San Antonio, TX | 448 CASTROVILLE RD SAN ANTONIO, TX 78207-5147 US | 50 MBPS (27539476) | 01/14/2019: 01/11 Successfully activated | 196688351 | TX415-02-IM | Private IP - PIP (27539475) WAN Analysis Reporting (27539477) Access (27539476) | 27539475 27539477 27539476 | 10 MBPS (27539475) |  | 94565103 (Private IP (PIP)) 94565107 (WAN Analysis Reporting) 94565109 (Access) | C4013992/ADD (27539475) E4035773/ADD (27539476) | 21.L1XX.022488..TWCC (2753947643953001) | 6002462 | 5500 | PVC ID : 6002462 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64754 PE IP Address : 147.225.29.13 CE Address : 147.225.29.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27539476) | 1000Base-SX (850nm, Multi Mode Fiber) (27539476) | Ethernet | TIME WARNER CABLE (2753947643953001) | 08/28/2018 (2753947643953001) | 12/19/2018 (2753947643953001) | 12/04/2018 (2753947643953001) | 12/07/2018 (VFORCE) (27539476) | 12/07/2018 (VFORCE) (27539476) | DEMARCADDR - . DEMARCDET - . |  | Saundra Watson 1-972-762-1139 swatson@wellmed.net | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 12/07/2018(Private IP - PIP) 12/07/2018(WAN Analysis Reporting) 12/07/2018(Access) | 01/11/2019 |  | 12/31/2018 (27539475) 12/27/2018 (27539476) | 01/16/2019 01/22/2019 | 12/09/2018 |  | Completed | N (27539475) N (27539477) N (27539476) | U0101953 |  | NSPE0012341938 Order Request # 196686573 | NSPE0012341938
Completed | AZ007 Tucson, AZ | 9040 S RITA RD TUCSON, AZ 85747-9194 US | 300 MBPS (27540838) | 07/17/2019: Activation scheduled 07/17/2019 2330 CT | 196706061 | ENT AZ007 TUCSON | Private IP - PIP (27540837) WAN Analysis Reporting (27540839) Access (27540838) | 27540837 27540839 27540838 | 200 MBPS (27540837) |  | 94565045 (Private IP (PIP)) 94565043 (WAN Analysis Reporting) 94565049 (Access) | C5005938/ADD (27540837) E5013720/ADD (27540838) | 47.KFGX.990142..COXC. (2754083825672501) | 6002496 | 140000 | PVC ID : 6002496 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64882 PE IP Address : 68.137.136.109 CE Address : 68.137.136.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27540838) | 1000Base-SX (850nm, Multi Mode Fiber) (27540838) | Ethernet | COX (2754083825672501) COX (2754083825672502) | 08/27/2018 (2754083825672501) 09/17/2018 (2754083825672502) | 09/28/2018 (2754083825672501) 09/28/2018 (2754083825672502) | 09/26/2018 (2754083825672502) | 09/28/2018 (VFORCE) (27540838) | 09/28/2018 (VFORCE) (27540838) | DEMARCADDR - . DEMARCDET - 19 in floor rack , left rack inside room |  | Anthony Cook 1-520-250-7430 Anthony.Cook@optum.com | JASON SALAPING | jason_salaping@optum.com | 1-210-862-6784 | 09/28/2018(Private IP - PIP) 09/28/2018(WAN Analysis Reporting) 09/28/2018(Access) | 07/17/2019 |  | 10/09/2018 (27540837) 10/05/2018 (27540838) | 10/02/2018 10/08/2018 | 09/28/2018 |  | Completed | N (27540837) N (27540839) N (27540838) | U0101953 |  | NSPE0012345100 Order Request # 196703097 | NSPE0012345100
Completed | ME008-02-IJ Catamaran South Portland, ME | 53 DARLING AVE SOUTH PORTLAND, ME 04106-2301 US | 100 MBPS | 08/31/2018: Background: ME008-02-IJ Catamaran South Portland, ME; UHG upgrade order to 200M Port ONLY Status: Ready for hotcut. customer informed. | 196706131 | ME008-02-IJ Catamaran South Portland | Private IP - PIP (27540985) Access | 27540985 | 20 MBPS (27540985) |  | 91498596 (Private IP (PIP)) 91498594 | C1031039/NONE (27540985) |  | 5702418 | 4000 | PVC ID : 5702418 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64775 PE IP Address : 68.138.250.221 CE Address : 68.138.250.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Josh Frautten 1-207-228-1218 Josh.frautten@catamaranrx.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 | 09/13/2018(Private IP | 09/12/2018 |  | 08/27/2018 (27540985) | 09/05/2018 | 09/13/2018 |  |  | N (27540985) N | U0101953 |  | NSPE0012346067 Order Request # 196705743 | NSPE0012346067
Completed | Islandia, NY | 2950 EXPRESS DR S ISLANDIA, NY 11749-1400 US | 100 MBPS (27748339) | 02/08/2019 Successfully activated | 196362051 | UNITED HEALTH GROUP | Private IP - PIP (27748338) Access (27748339) WAN Analysis Reporting (27748340) | 27748338 27748339 27748340 | 50 MBPS (27748338) |  | 94559071 (Private IP (PIP)) 94559075 (Access) 94559078 (WAN Analysis Reporting) | C1079488/ADD (27748338) E4037150/ADD (27748339) | 32.KFGS.217384..NY (2774833933843001) | 6009394 | 30000 | PVC ID : 6009394 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64553 PE IP Address : 68.139.92.193 CE Address : 68.139.92.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27748339) | 1000Base-SX (850nm, Multi Mode Fiber) (27748339) | Ethernet | VERIZON (2774833933843001) | 09/28/2018 (2774833933843001) | 10/15/2018 (2774833933843001) | 10/12/2018 (2774833933843001) |  |  | DEMARCDET - 2nd flr suite 240 server room wall mounted tagged |  | Stephani Horyczun 1-631-348-5728 stephani_j_horyczun@uhc.com | Jason Salaping | jason_salaping@optum.com | 632-462-2446 | 10/12/2018(Private IP - PIP) 10/12/2018(Access) 10/12/2018(WAN Analysis Reporting) | 02/08/2019 |  | 11/06/2018 (27748338) 11/02/2018 (27748339) | 11/16/2018 11/22/2018 | 10/12/2018 |  | Completed | N (27748338) N (27748339) N (27748340) | U0101953 |  | NSPE0012318784 Order Request # 196361555 | NSPE0012318784
Completed | FL370-01-IM Boca Raton, FL | 21301 POWERLINE RD BOCA RATON, FL 33433-2388 US | 3 MBPS (27573453) | 10/05/2018: Background: FL370-01-IM Boca Raton, FL; New 3M/3M MLPPP; Bell South; NID; No MNS Status: FOC 10/10/2018. Please confirm access is granted. | 196831319 | FL370-01-IM | Private IP - PIP (27573452) WAN Analysis Reporting (27573454) Access (27573453) | 27573452 27573454 27573453 | 3 MBPS (27573452) |  | 94566767 (Private IP (PIP)) 94566765 (WAN Analysis Reporting) 94566769 (Access) | C1078293/ADD (27573452) N1044335/ADD (27573453) N1044334/ADD (27573453) | 60/HCGS/478960//SB (2757345344405701) | 6003715 | 1500 | PVC ID : 6003715 VPN Name : UnitedHealthGroup Router Name : POBGE03 VRF Name : V370197:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64741 PE IP Address : 68.136.111.73 CE Address : 68.136.111.74 QoS - Egress Profile: R12 |  | DS1 (27573453) | TDM | ATT (2757345344405701) | 09/26/2018 (2757345344405701) | 10/10/2018 (2757345344405701) | 10/10/2018 (2757345344405701) |  |  | DEMARCDET - 2ND FLOOR SUITE 206, MM2 SLOT1 RJ |  | RYAN CAMERON 1-404-308-5876 ryane.cameron@am.jll.com | SUSHIL KUMAR | sushil_gautam@uhc.com | 91-896-855-7475 | 10/11/2018(Private IP - PIP) 10/11/2018(WAN Analysis Reporting) 10/11/2018(Access) |  |  | 10/03/2018 (27573452) 10/01/2018 (27573453) | 10/18/2018 10/24/2018 | 10/11/2018 |  | Completed | N (27573452) N (27573454) N (27573453) | U0101953 |  | NSPE0012359045 Order Request # 196831235 | NSPE0012359045
Completed | AZ029-02-IJ Chandler, AZ | 985 W CHANDLER HEIGHTS RD CHANDLER, AZ 85248-5725 US | 50 MBPS (27585113) | 07/30/2019 Successfully activated | 196842199 | AZ029-02-IJ Chandler, AZ | Private IP - PIP (27585112) WAN Analysis Reporting (27585114) Access (27585113) | 27585112 27585114 27585113 | 10 MBPS (27585112) |  | 94565871 (Private IP (PIP)) 94565869 (WAN Analysis Reporting) 94565874 (Access) | C4014084/ADD (27585112) E4036105/ADD (27585113) |  | 6004253 | 5500 | PVC ID : 6004253 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64610 PE IP Address : 68.139.128.225 CE Address : 68.139.128.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27585113) | 1000Base-SX (850nm, Multi Mode Fiber) (27585113) | Ethernet | COX (2758511316897501) COX (2758511316897502) | 09/11/2018 (2758511316897501) 02/22/2019 (2758511316897502) | 06/26/2019 (2758511316897502) | 06/27/2019 (2758511316897502) | 07/01/2019 (VFORCE) (27585113) |  | DEMARCADDR - . DEMARCDET - . |  | Christina Brown 1-657-222-7249 Christina_brown3@uhg.com | JASON SALAPING | jason_salaping@gmail.com | 632-462-2446 | 06/28/2019(Private IP - PIP) 06/28/2019(WAN Analysis Reporting) 06/28/2019(Access) | 07/30/2019 |  | 06/05/2019 (27585112) 06/03/2019 (27585113) | 07/09/2019 07/15/2019 | 06/28/2019 |  | Completed | N (27585112) N (27585114) N (27585113) | U0101953 | Jeopardy Notification 3 (03/28/2019) | NSPE0012359818 Order Request # 196833577 | NSPE0012359818
Completed | M0289-05-IJ Duncan, SC | 170 PARKWAY W DUNCAN, SC 29334-8882 US | 250 MBPS (27592911) | 03/06/2019: 3/6Background: M0289-05-IJ Duncan SC; New 100M/250M PIP-Eth; (Charter); Dual NID; No MNS Status: Loop delivered 3/4. BEAS installation 03/07/2019; Next action: BEAS install | 196856085 | M0289-05-IJ Duncan SC | Access (27592911) Private IP - PIP (27592910) WAN Analysis Reporting (27592912) | 27592911 27592910 27592912 | 100 MBPS (27592910) |  | 94567637 (Access) 94567635 (Private IP (PIP)) 94567633 (WAN Analysis Reporting) | E0017432/ADD (27592911) C0151768/ADD (27592910) | 86.L1XX.800724..TWCC (2759291122568402) | 6004568 | 110000 | PVC ID : 6004568 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65259 PE IP Address : 152.162.176.173 CE Address : 152.162.176.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27592911) | 1000Base-SX (850nm, Multi Mode Fiber) (27592911) | Ethernet | CHARTER (2759291122568402) | 10/10/2018 (2759291122568402) | 03/06/2019 (2759291122568402) | 03/04/2019 (2759291122568402) | 03/07/2019 (VFORCE) (27592911) | 03/07/2019 (VFORCE) (27592911) | DEMARCADDR - . DEMARCDET - . |  | Blake McCullough 1-864-486-6768 blake_mccullough@optum.com | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 03/07/2019(Access) 03/07/2019(Private IP - PIP) 03/07/2019(WAN Analysis Reporting) |  |  | 02/22/2019 (27592911) 02/26/2019 (27592910) | 11/19/2018 11/23/2018 | 03/07/2019 |  | Scheduled | N (27592911) N (27592910) N (27592912) | U0187327 |  | NSPE0012364049 Order Request # 196845957 | NSPE0012364049
Completed | NY078-09-IM Flushing, NY | 13602 ROOSEVELT AVE FLUSHING, NY 11354-5510 US | 50 MBPS (28105208) | 02/21/2019: 2/21Background: NY078-07-IM Flushing, NY; New 10M/50M PIP-Eth; (VzT); Single NID; No MNS; SCON; NRD 03/19/2019 Status: Loop Delivered 2/21- Ready for activation Next action: Ready for activation | 196900867 | UNITEDHEALTH GROUP | Private IP - PIP (28105202) WAN Analysis Reporting (28105209) Access (28105208) | 28105202 28105209 28105208 | 10 MBPS (28105202) |  | 94567783 (Private IP (PIP)) 94567788 (WAN Analysis Reporting) 94567781 (Access) | C4015025/ADD (28105202) E4039000/ADD (28105208) | 32.KEGS.062638..NY (2810520874246101) | 6020314 | 5500 | PVC ID : 6020314 VPN Name : UnitedHealthGroup Router Name : NV89E02 VRF Name : V101790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65131 PE IP Address : 152.176.38.13 CE Address : 152.176.38.14 QoS - Egress Profile: R12 | 100Base-FX - MMF (28105208) | 100Base-FX (1310nm, Multi Mode Fiber) (28105208) | Ethernet | VERIZON (2810520874246101) | 11/21/2018 (2810520874246101) | 02/28/2019 (2810520874246101) | 02/21/2019 (2810520874246101) |  |  | DEMARCADDR - 136 02 ROOSEVELT AV FLUSHING NY DEMARCDET - DMC MAIN FLR DATA RM WALL MOUNTED TAGGED |  | Wencong (Melody) Yu 1-718-559-0485 wyu@uhc.com | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 02/21/2019(Private IP - PIP) 02/21/2019(WAN Analysis Reporting) 02/21/2019(Access) |  |  | 03/11/2019 (28105202) 03/07/2019 (28105208) | 03/19/2019 03/25/2019 | 02/21/2019 |  | Completed | N (28105202) N (28105209) N (28105208) | U0101953 |  | NSPE0012371307 Order Request # 196900679 | NSPE0012371307
Completed | Change W1D34687 | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10GL-MPL-WL-SPP (6214188) | 10/05/2018: Background: CHANGE LOCA L ACCESS 10G Elk River to Minneapolis Status: Circuit is ready for activation. Demarc details below. CIRCUIT WAS EXTENDED TO THE 2ND FLOOR, SUITE 261, COLOGIX SITE, ON VERIZON FDP JACKS 35 AND 36. | 9688693 |  | US Private Line (6214188) | 6214188 | 10GL-MPL-WL-SPP (6214188) |  |  | W1D34687 (6214188) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | PAULI GUILD 612 924 3956 PAUL_GUILD@OPTUM.COM | THOMAS KRENN 763 744 3141 TOM_KRENN@OPTUM.COM |  |  |  | 09/20/2018 (6214188) | 09/20/2018 |  | 09/28/2018 (6214188) | 12/07/2018 (6214188) |  |  |  | N (6214188) | 00198894
Completed | Change W1D34686 | 1707 W CREEK LN CHASKA, MN 55318 USA | 10GL-MPL-WL-SPP (6214206) | 09/20/2018: Order complete | 9689000 |  | US Private Line (6214206) | 6214206 | 10GL-MPL-WL-SPP (6214206) |  |  | W1D34686 (6214206) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | PAULI GUILD 612 924 3956 | THOMAS KRENN 763 744 3141 |  |  |  | 09/19/2018 (6214206) | 09/19/2018 |  | 09/28/2018 (6214206) | 12/07/2018 (6214206) |  |  |  | N (6214206) | 00198894
Completed | MA008-02-IJ Boston, MA | 1325 BOYLSTON ST BOSTON, MA 02215-3909 US | 400 MBPS (27789583) | 12/15/2018 Successfully activated | 197114863 | MA008-02-IJ Boston MA | Private IP - PIP (27789582) WAN Analysis Reporting (27789584) Access (27789583) | 27789582 27789584 27789583 | 300 MBPS (27789582) |  | 94569903 (Private IP (PIP)) 94569910 (WAN Analysis Reporting) 94569905 (Access) | C5006173/ADD (27789582) E5014443/ADD (27789583) | 95.KFGS.009153..NE (2778958312749601) | 6010309 | 180000 | PVC ID : 6010309 VPN Name : UnitedHealthGroup Router Name : CHTXE03 VRF Name : V637075-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64705 PE IP Address : 152.177.71.221 CE Address : 152.177.71.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27789583) | 1000Base-SX (850nm, Multi Mode Fiber) (27789583) | Ethernet | VERIZON (2778958312749601) | 10/03/2018 (2778958312749601) | 10/15/2018 (2778958312749601) | 10/09/2018 (2778958312749601) |  |  | DEMARCDET - 9th flr data center wall mounted tagged |  | DOUG DOWNIE 1-781-420-0830 douglas_downie@uhg.com | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 10/09/2018(Private IP - PIP) 10/09/2018(WAN Analysis Reporting) 10/09/2018(Access) | 12/15/2018 |  | 10/18/2018 (27789582) 10/16/2018 (27789583) | 10/30/2018 11/05/2018 | 10/09/2018 |  | Completed | N (27789582) N (27789584) N (27789583) | U0101953 |  | NSPE0012389394 Order Request # 197081823 | NSPE0012389394
Completed | CA009 Glendale, CA | 505 N BRAND BLVD GLENDALE, CA 91203-1906 US | 50 MBPS (27668219) | 10/05/2018: Background: Inside move CA009 Glendale, CA Status: Inside move to the 8th FL completed. | 197118639 | UNITED HEALTH-GLENDALE | Access (27668219) Private IP - PIP WAN Analysis Reporting (27668220) | 27668219 27668220 | 10 MBPS |  | 94545312 (Access) 94545314 94545316 (WAN Analysis Reporting) | E4034006/NONE (27668219) | [5 empty] | 1000Base-LX (1310nm Single Mode Fiber) (27668219) | Ethernet | [8 empty] | Christopher Floyd 1-909-605-8052 christopher_floyd@uhg.com | KEVIN CANTOR | kevin_cantor@optum.com | 1-763-744-2114 | 09/25/2018(Access) | 09/25/2018 |  | 09/26/2018 (27668219) | 10/15/2018 10/15/2018 (22973901.2) | 09/25/2018 |  | Completed Activated/Installed | N (27668219) N N (27668220) | U0101953 |  | NSPE0012393347 Order Request # 197118539 | NSPE0012393347
Completed | C1626-02-IM Alpharetta, GA | 12655 EDISON DR ALPHARETTA, GA 30005 US | 1 GBPS (27686321) | 03/08/2019 - Successfully activated | 197171301 | C1626-02-IM | Access (27686321) Private IP - PIP (27686320) WAN Analysis Reporting (27686322) | 27686321 27686320 27686322 | 1 GBPS (27686320) |  | 94569987 (Access) 94569985 (Private IP (PIP)) 94569992 (WAN Analysis Reporting) | E5014176/ADD (27686321) C0152534/ADD (27686320) | ETYX/179738//ZYO (2768632130592501) | 6007719 | 70000 | PVC ID : 6007719 VPN Name : UHG-ECC Router Name : CPZXE03 VRF Name : Vb74787-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65413 PE IP Address : 152.162.89.205 CE Address : 152.162.89.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27686321) | 1000Base-SX (850nm, Multi Mode Fiber) (27686321) | Ethernet | ZAYO (2768632130592501) | 09/24/2018 (2768632130592501) | 10/26/2018 (2768632130592501) | 11/26/2018 (2768632130592501) | 11/28/2018 (VFORCE) (27686321) | 11/28/2018 (VFORCE) (27686321) | DEMARCDET - 1st flr main colo area customer cage RR J66 MP 100 tagged with Zayo sticker and TID: ALPSGASGDU4 Cienna 3903 port 1 |  | MICHAEL LUBIN 1-404-495-7238 mlubin@nexidia.com | Paul Barclay | paul.barclay@optum.com | 1-617-530-2394 | 11/28/2018(Access) 11/28/2018(Private IP - PIP) 11/28/2018(WAN Analysis Reporting) | 03/08/2019 |  | 11/27/2018 (27686321) 11/29/2018 (27686320) | 12/26/2018 01/01/2019 | 11/28/2018 |  | Completed | N (27686321) N (27686320) N (27686322) | U0101953 | Jeopardy Notification 1 (10/25/2018) | NSPE0012395203 Order Request # 197136519 | NSPE0012395203
Completed | FL353-02-IM Tampa, FL | 508 S HABANA AVE STE 280 TAMPA, FL 33609-4198 US | 50 MBPS (27702139) | 08/01/2019: 07/31 Successfully activated | 197192929 | FL353-02-IM | Private IP - PIP (27702138) WAN Analysis Reporting (27702140) Access (27702139) | 27702138 27702140 27702139 | 10 MBPS (27702138) |  | 94572227 (Private IP (PIP)) 94572225 (WAN Analysis Reporting) 94572230 (Access) | C4014347/ADD (27702138) E4036972/ADD (27702139) | 81.L1XX.800739..TWCC (2770213945713801) | 6008227 | 5500 | PVC ID : 6008227 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64687 PE IP Address : 147.225.19.97 CE Address : 147.225.19.98 QoS - Egress Profile: R12 | 100Base-TX (27702139) | 100Base-TX (27702139) | Ethernet | BRIGHT HOUSE (2770213945713801) | 09/21/2018 (2770213945713801) | 01/21/2019 (2770213945713801) | 01/22/2019 (2770213945713801) | 01/23/2019 (VFORCE) (27702139) | 01/23/2019 (VFORCE) (27702139) | DEMARCDET - 2ND FLOOR IT ROOM TAGGED NOT EXTENDED |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 01/23/2019(Private IP - PIP) 01/23/2019(WAN Analysis Reporting) 01/23/2019(Access) | 07/31/2019 |  | 01/23/2019 (27702138) 01/18/2019 (27702139) | 11/01/2018 11/07/2018 | 01/23/2019 |  | Completed | N (27702138) N (27702140) N (27702139) | U0101953 |  | NSPE0012402209 Order Request # 197192851 | NSPE0012402209
Completed | FL350-02-IM Oviedo, FL | 5700 DOT COM CT OVIEDO, FL 32765-3400 US | 100 MBPS (27715335) | 06/07/2019: 6/7Background: Oviedo, FL; New 100M/50M PIPE (Bright House); NID; No MNS; Status: Ready for activation | 197205435 | Location97061401072 | Access (27715335) Private IP - PIP (27715334) WAN Analysis Reporting (27715336) | 27715335 27715334 27715336 | 50 MBPS (27715334) |  | 94570826 (Access) 94570823 (Private IP (PIP)) 94570821 (WAN Analysis Reporting) | E4037009/ADD (27715335) C1079322/ADD (27715334) | 40.L1XX.800369..TWCC (2771533545537101) | 6008561 | 30000 | PVC ID : 6008561 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64738 PE IP Address : 147.225.78.109 CE Address : 147.225.78.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27715335) | 1000Base-SX (850nm, Multi Mode Fiber) (27715335) | Ethernet | BRIGHT HOUSE (2771533545537101) | 11/14/2018 (2771533545537101) | 04/21/2019 (2771533545537101) | 06/04/2019 (2771533545537101) | 06/06/2019 (VFORCE) (27715335) | 06/06/2019 (VFORCE) (27715335) | DEMARCDET - room MPE floor 1 in the main building |  | RYAN CAMERON 1-404-308-5876 ryane.cameron@am.jll.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 06/06/2019(Access) 06/06/2019(Private IP - PIP) 06/06/2019(WAN Analysis Reporting) |  |  | 06/11/2019 (27715335) 06/13/2019 (27715334) | 09/16/2019 09/20/2019 | 06/06/2019 |  | Completed | N (27715335) N (27715334) N (27715336) | U0101953 | Jeopardy Notification 3 (06/01/2019) | NSPE0012399181 Order Request # 197184073 | NSPE0012399181
Completed | Remove ETM Select Reporting only | 505 N BRAND BLVD GLENDALE, CA 91203-1906 US | 7.7 MBPS (27752343) |  | 197240749 | UNITED HEALTH-GLENDALE | Private IP - PIP (27752342) WAN Analysis Reporting (27752344) Access (27752343) | 27752342 27752344 27752343 | 7.7 MBPS (27752342) |  | 87492503 (Private IP (PIP)) 87499336 (WAN Analysis Reporting) 87495772 (Access) | C0129539/NONE (27752342) N3009900/NONE (27752343) N3009902/NONE (27752343) N3009903/NONE (27752343) N3009901/NONE (27752343) N3009899/NONE (27752343) |  | 1977560 |  | PVC ID : 1977560 |  | DS1 (27752343) | TDM | [8 empty] | Christopher Floyd 1-909-605-8052 christopher_floyd@uhg.com | KEVIN CANTOR | kevin_cantor@optum.com | 1-763-744-2114 | 09/28/2018(Private IP - PIP) 09/28/2018(WAN Analysis Reporting) 09/28/2018(Access) | 10/01/2018 |  | 10/02/2018 (27752342) 10/02/2018 (27752343) | 10/22/2018 10/26/2018 | 09/28/2018 |  | Completed | N (27752342) N (27752344) N (27752343) | U0157845 |  | NSPE0012408455 Order Request # 197212699 | NSPE0012408455
Completed | FL363-02-IM Sun City Center, FL | 1901 HAVERFORD AVE STE 101 SUN CITY CENTER, FL 33573-5200 US | 50 MBPS (27752406) | 05/10/2019: 05/09 Successfully activated | 197240937 | FL363-02-IM | Private IP - PIP (27752405) WAN Analysis Reporting (27752407) Access (27752406) | 27752405 27752407 27752406 | 10 MBPS (27752405) |  | 94572770 (Private IP (PIP)) 94572768 (WAN Analysis Reporting) 94572766 (Access) | C4014422/ADD (27752405) E4037162/ADD (27752406) | 81.L1XX.800783..TWCC (2775240645829701) | 6009493 | 5500 | PVC ID : 6009493 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64614 PE IP Address : 68.137.12.25 CE Address : 68.137.12.26 QoS - Egress Profile: R12 | 100Base-TX (27752406) | 100Base-TX (27752406) | Ethernet | BRIGHT HOUSE (2775240645829701) | 09/28/2018 (2775240645829701) | 01/21/2019 (2775240645829701) | 02/21/2019 (2775240645829701) | 02/25/2019 (VFORCE) (27752406) | 02/25/2019 (VFORCE) (27752406) | DEMARCADDR - . DEMARCDET - in customers closet on the wall rad 203 port 3 |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 02/25/2019(Private IP - PIP) 02/25/2019(WAN Analysis Reporting) 02/25/2019(Access) | 05/09/2019 |  | 02/19/2019 (27752405) 01/29/2019 (27752406) | 05/23/2019 05/29/2019 | 02/25/2019 |  | Completed | N (27752405) N (27752407) N (27752406) | U0101953 |  | NSPE0012408985 Order Request # 197214439 | NSPE0012408985
Completed | FL367-02-IM St Petersburg, FL | 6350 CENTRAL AVE ST PETERSBURG, FL 33707-1430 US | 50 MBPS (27752624) | 03/11/2019 Successfully activated | 197241465 | FL367-02-IM | Private IP - PIP (27752623) WAN Analysis Reporting (27752625) Access (27752624) | 27752623 27752625 27752624 | 10 MBPS (27752623) |  | 94573699 (Private IP (PIP)) 94574001 (WAN Analysis Reporting) 94573697 (Access) | C4014423/ADD (27752623) E4037167/ADD (27752624) | 65/KEGS/991860//FTNC/ (2775262445917901) | 6009506 | 5500 | PVC ID : 6009506 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64603 PE IP Address : 152.181.16.189 CE Address : 152.181.16.190 QoS - Egress Profile: R12 | 100Base-TX (27752624) | 100Base-TX (27752624) | Ethernet | FRONTIER (2775262445917901) | 09/28/2018 (2775262445917901) | 01/14/2019 (2775262445917901) | 12/04/2018 (2775262445917901) | 12/07/2018 (VFORCE) (27752624) | 12/07/2018 (VFORCE) (27752624) | DEMARCADDR - 6350 CENTRAL AVE SAINT PETERSBURG FL DEMARCDET - SL01#SHLF01#PRT01#PHYTELCO CLOSET/ WALL MOUNTED RAD-NID. #JK |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 12/07/2018(Private IP - PIP) 12/07/2018(WAN Analysis Reporting) 12/07/2018(Access) | 03/11/2019 |  | 01/24/2019 (27752623) 01/22/2019 (27752624) | 11/08/2018 11/14/2018 | 12/09/2018 |  | Completed | N (27752623) N (27752625) N (27752624) | U0101953 |  | NSPE0012414261 Order Request # 197232273 | NSPE0012414261
Completed | FL366-02-IM Land O Lakes, FL | 20615 AMBERFIELD DR STE 102 LAND O LAKES, FL 34638-4387 US | 50 MBPS (27754397) | 12/19/2018: 12/19 Background: FL366-02-IM Land O Lakes, FL; New 10M/50M PIP-Eth; (Bright House); NID; No MNS; Status: BEAS installation 12/20/2018. Access confirmed Next action: Line testing | 197242969 | FL366-02-IM | Private IP - PIP (27754396) WAN Analysis Reporting (27754398) Access (27754397) | 27754396 27754398 27754397 | 10 MBPS (27754396) |  | 94573361 (Private IP (PIP)) 94573364 (WAN Analysis Reporting) 94573358 (Access) | C4014436/ADD (27754396) E4037183/ADD (27754397) | 81.L1XX.800795..TWCC (2775439745942001) | 6009584 | 5500 | PVC ID : 6009584 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64593 PE IP Address : 152.181.203.17 CE Address : 152.181.203.18 QoS - Egress Profile: R12 | 100Base-TX (27754397) | 100Base-TX (27754397) | Ethernet | BRIGHT HOUSE (2775439745942001) | 11/29/2018 (2775439745942001) | 01/11/2019 (2775439745942001) | 12/18/2018 (2775439745942001) | 12/20/2018 (VFORCE) (27754397) | 12/20/2018 (VFORCE) (27754397) | DEMARCDET - wall mounted in the customer's room labled as storage room |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 12/20/2018(Private IP - PIP) 12/20/2018(WAN Analysis Reporting) 12/20/2018(Access) |  |  | 12/18/2018 (27754396) 12/14/2018 (27754397) | 01/08/2019 01/14/2019 | 12/20/2018 |  | Completed | N (27754396) N (27754398) N (27754397) | U0101953 | Jeopardy Notification 2 (11/27/2018) | NSPE0012417344 Order Request # 197241261 | NSPE0012417344
Completed | FL354-02-IM Tampa, FL | 13301 N DALE MABRY HWY STE A TAMPA, FL 33618-2400 US | 50 MBPS (27753527) | 07/08/2019 Successfully activated | 197201499 | FL354-02-IM | Private IP - PIP (27753526) WAN Analysis Reporting (27753528) Access (27753527) | 27753526 27753528 27753527 | 10 MBPS (27753526) |  | 94572425 (Private IP (PIP)) 94572432 (WAN Analysis Reporting) 94572427 (Access) | C4014425/ADD (27753526) E4037171/ADD (27753527) | 81.L1XX.800817..TWCC (2775352745714001) | 6009551 | 5500 | PVC ID : 6009551 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64679 PE IP Address : 152.181.67.17 CE Address : 152.181.67.18 QoS - Egress Profile: R12 | 100Base-TX (27753527) | 100Base-TX (27753527) | Ethernet | BRIGHT HOUSE (2775352745714001) | 09/28/2018 (2775352745714001) | 03/08/2019 (2775352745714001) | 03/14/2019 (2775352745714001) | 03/19/2019 (VFORCE) (27753527) | 03/19/2019 (VFORCE) (27753527) | Telco Circuit ID: 81.L1XX.800817..TWCC Telco Demarcation: 1st floor Storage Closet Wall mount near De-Marc rad 203 port 3 Verizon BEAS Circuit ID: USAFL45714025COV400001 / E4037171 Verizon BEAS Demarcation: 1st floor , suite A, phone closet, back wall |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 03/19/2019(Private IP - PIP) 03/19/2019(WAN Analysis Reporting) 03/19/2019(Access) | 07/05/2019 |  | 01/29/2019 (27753526) 01/25/2019 (27753527) | 01/10/2019 01/16/2019 | 03/19/2019 |  | Completed | N (27753526) N (27753528) N (27753527) | U0101953 |  | NSPE0012404601 Order Request # 197201413 | NSPE0012404601
Completed | FL359-02-IM Tampa, FL | 10933 COUNTRYWAY BLVD TAMPA, FL 33626-2630 US | 50 MBPS (27753769) | 08/26/2019 - Activation scheduled 08/29/2019 7:30PM CT | 197203965 | FL359-02-IM | WAN Analysis Reporting (27753770) Access (27753769) Private IP - PIP (27753768) | 27753770 27753769 27753768 | 10 MBPS (27753768) |  | 94572283 (WAN Analysis Reporting) 94572288 (Access) 94572285 (Private IP (PIP)) | C4014428/ADD (27753768) E4037175/ADD (27753769) | 81.L1XX.800796..TWCC (2775376945786101) | 6009561 | 5500 | PVC ID : 6009561 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64648 PE IP Address : 68.139.194.129 CE Address : 68.139.194.130 QoS - Egress Profile: R12 | 100Base-TX (27753769) | 100Base-TX (27753769) | Ethernet | BRIGHT HOUSE (2775376945786101) | 02/04/2019 (2775376945786101) | 02/06/2019 (2775376945786101) | 02/07/2019 (2775376945786101) | 02/14/2019 (VFORCE) (27753769) | 02/14/2019 (VFORCE) (27753769) | DEMARCDET - customers telecom closet RAD ETX203 port 3 |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 02/14/2019(WAN Analysis Reporting) 02/14/2019(Access) 02/14/2019(Private IP - PIP) |  |  | 02/21/2019 (27753768) 02/19/2019 (27753769) | 05/31/2019 05/27/2019 | 02/14/2019 |  | Completed | N (27753770) N (27753769) N (27753768) | U0101953 | Jeopardy Notification 1 (02/11/2019) | NSPE0012405451 Order Request # 197203867 | NSPE0012629818
Completed | FL357-02-IM Tampa, FL | 6502 GUNN HWY TAMPA, FL 33625-4022 US | 50 MBPS (27753825) | 08/07/2019 Successfully activated | 197203963 | FL357-02-IM | Private IP - PIP (27753824) Access (27753825) WAN Analysis Reporting (27753826) | 27753824 27753825 27753826 | 10 MBPS (27753824) |  | 94572469 (Private IP (PIP)) 94572471 (Access) 94572476 (WAN Analysis Reporting) | C4014429/ADD (27753824) E4037176/ADD (27753825) | 81.L1XX.800780..TWCC (2775382545785501) | 6009564 | 5500 | PVC ID : 6009564 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64661 PE IP Address : 152.181.89.197 CE Address : 152.181.89.198 QoS - Egress Profile: R12 | 100Base-TX (27753825) | 100Base-TX (27753825) | Ethernet | BRIGHT HOUSE (2775382545785501) | 09/28/2018 (2775382545785501) | 01/18/2019 (2775382545785501) | 01/03/2019 (2775382545785501) | 01/08/2019 (VFORCE) (27753825) | 01/08/2019 (VFORCE) (27753825) | DEMARCDET - MPOE |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 01/08/2019(Private IP - PIP) 01/08/2019(Access) 01/08/2019(WAN Analysis Reporting) | 08/07/2019 |  | 01/30/2019 (27753824) 01/28/2019 (27753825) | 01/10/2019 01/16/2019 | 01/08/2019 |  | Completed | N (27753824) N (27753825) N (27753826) | U0101953 |  | NSPE0012405451 Order Request # 197203867 | NSPE0012405451
Completed | FL358-02-IM Tampa, FL | 11924 SHELDON RD TAMPA, FL 33626-3643 US | 50 MBPS (27753954) | 02/08/2019: Background: FL358-02-IM Tampa, FL; New 10M/50M PIP-Eth; (Bright House); Dual NID; No MNS; ENID Status: Ready for activation once customer internal cabling is complete. Telco Circuit ID: 81.L1XX.800836..TWCC Telco Demarcation: MDF Room, 1st Floor, Main Building Verizon BEAS Circuit ID: USAFL45785873COV400001 / E4037177 Verizon BEAS Demarcation: 1st floor server room mounted in customer rack tagged with the circuit id | 197203919 | FL358-02-IM | Access (27753954) WAN Analysis Reporting (27753955) Private IP - PIP (27753953) | 27753954 27753955 27753953 | 10 MBPS (27753953) |  | 94572277 (Access) 94572272 (WAN Analysis Reporting) 94572274 (Private IP (PIP)) | E4037177/ADD (27753954) C4014431/ADD (27753953) | 81.L1XX.800836..TWCC (2775395445785801) | 6009566 | 5500 | PVC ID : 6009566 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64652 PE IP Address : 152.181.93.101 CE Address : 152.181.93.102 QoS - Egress Profile: R12 | 100Base-TX (27753954) | 100Base-TX (27753954) | Ethernet | BRIGHT HOUSE (2775395445785801) | 09/28/2018 (2775395445785801) | 01/25/2019 (2775395445785801) | 02/04/2019 (2775395445785801) | 02/07/2019 (VFORCE) (27753954) |  | DEMARCDET - MDF FLR 1 BLDG MAIN |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 02/07/2019(Access) 02/07/2019(WAN Analysis Reporting) 02/07/2019(Private IP - PIP) |  |  | 02/13/2019 (27753954) 02/15/2019 (27753953) | 05/21/2019 05/27/2019 | 02/07/2019 |  | Completed | N (27753954) N (27753955) N (27753953) | U0101953 |  | NSPE0012405451 Order Request # 197203867 | NSPE0012405451
Completed | FL362-02-IM Brandon, FL | 500 VONDERBURG DR BRANDON, FL 33511-5964 US | 50 MBPS (27754039) | 06/11/2019: 06/11 Successfully activated | 197212807 | FL362-02-IM | Access (27754039) Private IP - PIP (27754038) WAN Analysis Reporting (27754040) | 27754039 27754038 27754040 | 10 MBPS (27754038) |  | 94572851 (Access) 94572848 (Private IP (PIP)) 94572855 (WAN Analysis Reporting) | E4037179/ADD (27754039) C4014432/ADD (27754038) | 81.L1XX.800784..TWCC (2775403945823201) | 6009572 | 5500 | PVC ID : 6009572 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64627 PE IP Address : 152.181.92.149 CE Address : 152.181.92.150 QoS - Egress Profile: R12 | 100Base-TX (27754039) | 100Base-TX (27754039) | Ethernet | BRIGHT HOUSE (2775403945823201) | 10/01/2018 (2775403945823201) | 01/14/2019 (2775403945823201) | 02/18/2019 (2775403945823201) | 02/19/2019 (VFORCE) (27754039) | 02/19/2019 (VFORCE) (27754039) | DEMARCADDR - . DEMARCDET - . |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 02/19/2019(Access) 02/19/2019(Private IP - PIP) 02/19/2019(WAN Analysis Reporting) | 06/11/2019 |  | 01/22/2019 (27754039) 01/24/2019 (27754038) | 11/05/2018 11/09/2018 | 02/19/2019 |  | Completed | N (27754039) N (27754038) N (27754040) | U0101953 |  | NSPE0012408410 Order Request # 197212661 | NSPE0012629644
Completed | FL361-02-IM Apollo Beach, FL | 415 APOLLO BEACH BLVD APOLLO BEACH, FL 33572-2281 US | 50 MBPS (27754080) | 04/04/2019: 4/4Background: FL361-02-IM Apollo Beach, FL; New 10M/50M PIP-Eth; (Bright House); Dual NID; No MNS; special off net build 75 Status: Loop delivered 04/04 Pending Beas Next action: BEAS install | 197212809 | FL361-02-IM | Access (27754080) Private IP - PIP (27754079) WAN Analysis Reporting (27754081) | 27754080 27754079 27754081 | 10 MBPS (27754079) |  | 94572926 (Access) 94572924 (Private IP (PIP)) 94572929 (WAN Analysis Reporting) | E4037180/ADD (27754080) C4014435/ADD (27754079) | 81.L1XX.800797..TWCC (2775408045822201) | 6009587 | 5500 | PVC ID : 6009587 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64644 PE IP Address : 152.181.104.29 CE Address : 152.181.104.30 QoS - Egress Profile: R12 | 100Base-TX (27754080) | 100Base-TX (27754080) | Ethernet | BRIGHT HOUSE (2775408045822201) | 10/19/2018 (2775408045822201) | 04/23/2019 (2775408045822201) | 04/04/2019 (2775408045822201) | 04/08/2019 (VFORCE) (27754080) | 04/08/2019 (VFORCE) (27754080) |  |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 04/08/2019(Access) 04/08/2019(Private IP - PIP) 04/08/2019(WAN Analysis Reporting) | 04/09/2019 |  | 01/25/2019 (27754080) 01/29/2019 (27754079) | 01/10/2019 01/16/2019 | 04/08/2019 |  | Completed | N (27754080) N (27754079) N (27754081) | U0101953 |  | NSPE0012408410 Order Request # 197212661 | NSPE0012408410
Completed | FL360-02-IM Tampa, FL | 2706 W SAINT ISABEL ST TAMPA, FL 33607-6382 US | 50 MBPS (27754143) | 04/03/2019: 4/3Background: FL360-02-IM Tampa, FL; New 10M/50M PIP-Eth; (Bright House); Dual NID; No MNS; offnet build Status: Loop delivered 04/02. BEAS installation 04/03/2019- Order complete; Ready for activation Next action: Ready for activation | 197212773 | FL360-02-IM | Access (27754143) Private IP - PIP (27754142) WAN Analysis Reporting (27754144) | 27754143 27754142 27754144 | 10 MBPS (27754142) |  | 94572754 (Access) 94572758 (Private IP (PIP)) 94572756 (WAN Analysis Reporting) | E4037181/ADD (27754143) C4014433/ADD (27754142) | 81.L1XX.800816..TWCC (2775414345820401) | 6009575 | 5500 | PVC ID : 6009575 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64646 PE IP Address : 152.181.96.145 CE Address : 152.181.96.146 QoS - Egress Profile: R12 | 100Base-TX (27754143) | 100Base-TX (27754143) | Ethernet | BRIGHT HOUSE (2775414345820401) | 09/28/2018 (2775414345820401) | 03/21/2019 (2775414345820401) | 04/02/2019 (2775414345820401) | 04/03/2019 (VFORCE) (27754143) | 04/03/2019 (VFORCE) (27754143) |  |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 04/03/2019(Access) 04/03/2019(Private IP - PIP) 04/03/2019(WAN Analysis Reporting) |  |  | 01/04/2019 (27754143) 01/08/2019 (27754142) | 01/10/2019 01/16/2019 | 04/03/2019 |  | Completed | N (27754143) N (27754142) N (27754144) | U0101953 |  | NSPE0012408410 Order Request # 197212661 | NSPE0012408410
Completed | St Petersburg, FL | 2191 9TH AVE N ST PETERSBURG, FL 33713-7146 US | 50 MBPS (27754180) | 03/28/2019 Successfully activated. | 197234567 | UNITED HEALTH GROUP | WAN Analysis Reporting (27754181) Access (27754180) Private IP - PIP (27754179) | 27754181 27754180 27754179 | 10 MBPS (27754179) |  | 94573465 (WAN Analysis Reporting) 94573461 (Access) 94573458 (Private IP (PIP)) | C4014434/ADD (27754179) E4037182/ADD (27754180) | 72.L1XX.800879..TWCC (2775418029896501) | 6009577 | 5500 | PVC ID : 6009577 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64601 PE IP Address : 152.176.89.245 CE Address : 152.176.89.246 QoS - Egress Profile: R12 | 100Base-TX (27754180) | 100Base-TX (27754180) | Ethernet | BRIGHT HOUSE (2775418029896501) | 09/28/2018 (2775418029896501) | 12/28/2018 (2775418029896501) | 12/12/2018 (2775418029896501) | 12/17/2018 (VFORCE) (27754180) | 12/17/2018 (VFORCE) (27754180) | DEMARCADDR - 1 DEMARCDET - customers IT closet on the wall |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 12/17/2018(WAN Analysis Reporting) 12/17/2018(Access) 12/17/2018(Private IP - PIP) | 03/28/2019 |  | 01/09/2019 (27754179) 01/07/2019 (27754180) | 11/13/2018 11/07/2018 | 12/17/2018 |  | Completed | N (27754181) N (27754180) N (27754179) | U0101953 |  | NSPE0012415033 Order Request # 197234471 | NSPE0012415033
Completed | FL355-02-IM Tampa, FL | 4278 W LINEBAUGH AVE STE B TAMPA, FL 33624-5241 US | 50 MBPS (27753658) | 07/11/2019 Successfully activated | 197201523 | FL355-02-IM | Private IP - PIP (27753657) WAN Analysis Reporting (27753659) Access (27753658) | 27753657 27753659 27753658 | 10 MBPS (27753657) |  | 94570061 (Private IP (PIP)) 94570066 (WAN Analysis Reporting) 94570059 (Access) | C4014427/ADD (27753657) E4037174/ADD (27753658) | 40.L1XX.800384..TWCC (2775365845714301) | 6009555 | 5500 | PVC ID : 6009555 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64676 PE IP Address : 152.181.70.165 CE Address : 152.181.70.166 QoS - Egress Profile: R12 | 100Base-TX (27753658) | 100Base-TX (27753658) | Ethernet | BRIGHT HOUSE (2775365845714301) | 09/28/2018 (2775365845714301) | 02/21/2019 (2775365845714301) | 02/07/2019 (2775365845714301) | 02/11/2019 (VFORCE) (27753658) |  | DEMARCDET - MDF 1 MAIN |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 02/11/2019(Private IP - PIP) 02/11/2019(WAN Analysis Reporting) 02/11/2019(Access) | 07/11/2019 |  | 03/04/2019 (27753657) 02/28/2019 (27753658) | 05/23/2019 05/29/2019 | 02/11/2019 |  | Completed | N (27753657) N (27753659) N (27753658) | U0101953 | Jeopardy Notification 4 (11/24/2018) | NSPE0012404601 Order Request # 197201413 | NSPE0012404601
Completed | FL356-02-IM Lutz, FL | 18956 N DALE MABRY HWY STE 102 LUTZ, FL 33548-4915 US | 50 MBPS (27753620) | 06/18/2019 Successfully activated | 197201525 | FL356-02-IM | Private IP - PIP (27753619) WAN Analysis Reporting (27753621) Access (27753620) | 27753619 27753621 27753620 | 10 MBPS (27753619) |  | 94572436 (Private IP (PIP)) 94572443 (WAN Analysis Reporting) 94572438 (Access) | C4014426/ADD (27753619) E4037172/ADD (27753620) | 81.L1XX.800785..TWCC (2775362045714501) | 6009553 | 5500 | PVC ID : 6009553 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64666 PE IP Address : 152.181.71.5 CE Address : 152.181.71.6 QoS - Egress Profile: R12 | 100Base-TX (27753620) | 100Base-TX (27753620) | Ethernet | BRIGHT HOUSE (2775362045714501) | 09/28/2018 (2775362045714501) | 01/17/2019 (2775362045714501) | 03/13/2019 (2775362045714501) | 03/14/2019 (VFORCE) (27753620) |  | DEMARCADDR - . DEMARCDET - . |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 03/14/2019(Private IP - PIP) 03/14/2019(WAN Analysis Reporting) 03/14/2019(Access) | 06/18/2019 |  | 01/29/2019 (27753619) 01/25/2019 (27753620) | 01/10/2019 01/16/2019 | 03/14/2019 |  | Scheduled | N (27753619) N (27753621) N (27753620) | U0101953 | Jeopardy Notification 3 (11/22/2018) | NSPE0012404601 Order Request # 197201413 | NSPE0012404601
Completed | TX079-05-IM Rancho Cordova UHG 50M Ethernet PIP | 3215 PROSPECT PARK DR RANCHO CORDOVA, CA 95670-6017 US | 400 MBPS (27803361) | 02/08/2019 Successfully activated | 197280573 | Rancho Cordova UHG 50M Ethernet PIP | WAN Analysis Reporting (27803362) Access (27803361) Private IP - PIP (27803360) | 27803362 27803361 27803360 | 200 MBPS (27803360) |  | 94574224 (WAN Analysis Reporting) 94574220 (Access) 94574217 (Private IP (PIP)) | C5006191/ADD (27803360) E5014478/ADD (27803361) | 18/KRGN/520043//PT (2780336117060001) | 6010673 | 110000 | PVC ID : 6010673 VPN Name : UnitedHealthGroup Router Name : SCM9E02 VRF Name : Vc55458:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64787 PE IP Address : 68.137.136.13 CE Address : 68.137.136.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27803361) | 1000Base-SX (850nm, Multi Mode Fiber) (27803361) | Ethernet | ATT (2780336117060001) | 10/04/2018 (2780336117060001) | 10/23/2018 (2780336117060001) | 10/23/2018 (2780336117060001) | 10/24/2018 (VFORCE) (27803361) | 10/24/2018 (VFORCE) (27803361) | DEMARCDET - MPOE 1.1 PNL 2 POS 3,4 |  | Vanessa Francis 1-818-274-2803 Vanessa.Francis@optum360.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 1-763-744-2114 | 10/25/2018(WAN Analysis Reporting) 10/25/2018(Access) 10/25/2018(Private IP - PIP) | 12/14/2018 |  | 11/05/2018 (27803360) 11/01/2018 (27803361) | 11/20/2018 11/14/2018 | 10/24/2018 |  | Completed | N (27803362) N (27803361) N (27803360) | U0101953 |  | NSPE0012422086 Order Request # 197254737 | NSPE0012422086
Completed | TX436-02-IM Austin, TX | 2200 PARK BEND DR STE 300 AUSTIN, TX 78758-5386 US | 50 MBPS (27823454) | 11/15/2018: 11/15 Background: TX436-02-IM Austin, TX; New 10M/50M PIP-Eth; (TWC); NID; No MNS; ENID; Status: Ready for Activation, loop delivered and Beas installed. | 197300135 | TX436-02-IM | Private IP - PIP (27823453) WAN Analysis Reporting (27823455) Access (27823454) | 27823453 27823455 27823454 | 10 MBPS (27823453) |  | 94574248 (Private IP (PIP)) 94574255 (WAN Analysis Reporting) 94574251 (Access) | C4014517/ADD (27823453) E4037494/ADD (27823454) | TX/KXFN/070077/LVLC (2782345446076201) | 6011221 | 5500 | PVC ID : 6011221 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64579 PE IP Address : 147.225.102.217 CE Address : 147.225.102.218 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (27823454) | 1000Base-LX (1310nm Single Mode Fiber) (27823454) | Ethernet | LEVEL 3 (2782345446076201) | 10/18/2018 (2782345446076201) | 11/08/2018 (2782345446076201) | 11/09/2018 (2782345446076201) | 11/13/2018 (VFORCE) (27823454) |  | DEMARCDET - BLDG 1, 4th floor, Telephone Room, Wallmounted , AUSA48SBW2001, Cisco 3600 port 0/14, tagged with circuit ID TX/KXFN/070077/LVLC |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 91-124-309-5736 | 11/14/2018(Private IP - PIP) 11/14/2018(WAN Analysis Reporting) 11/14/2018(Access) |  |  | 11/16/2018 (27823453) 11/14/2018 (27823454) | 11/19/2018 11/23/2018 | 11/14/2018 |  | Completed | N (27823453) N (27823455) N (27823454) | U0101953 |  | NSPE0012424471 Order Request # 197262427 | NSPE0012424471
Completed | GA777-Change | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 12/14/2018 Successfully deployed UnitedHealthGroup VPN with peak speed 900M; Add 100M ECCMA VPN to the existing circuit, ASN : 65138 and Add pvc level queing | 197300565 | Equinix hub Atlanta Peachtree GA777-04-IJ | Private IP - PIP (27824020) Access | 27824020 | 1 GBPS (27824020) |  | 64817622 (Private IP (PIP)) 64817620 | C1019330/NONE (27824020) |  | 5580133 6011246 | 2000 18000 | PVC ID : 5580133,6011246 VPN Name : UHG-ECC,UnitedHealthGroup Router Name : 95JXE01 VRF Name : Vc78843-UHGECC,Vc78844-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65138 PE IP Address : v4-68.137.77.57,v6-68.137.219.169 CE Address : v4-68.137.77.58,v6-68.137.219.170 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Ryan Kristoffersen 1-408-451-1931 rkristoffersen@equinix.com | Ryan Kristoffersen | rkristoffersen@equinix.com | 1-408-451-1931 | 12/15/2018(Private IP | 12/14/2018 |  | 11/19/2018 (27824020) | 11/28/2018 | 12/15/2018 |  |  | N (27824020) N | U0101953 |  | NSPE0012432928 Order Request # 197290195 | NSPE0012432928
Completed | TX401-04-IM Pharr, TX | 1104 W SAM HOUSTON BLVD PHARR, TX 78577-5104 US | 50 MBPS (27824313) | 02/01/2019: Background: TX401-04-IM Pharr, TX; New 10M/50M PIP-Eth; (TWC); Dual NID; No MNS; offnet build Status: Ready for activation Next action: Customer to activate service Who owns the next action: Customer Telco Circuit ID: 95.L1XX.008857..TWCC Telco Demarcation: IT Room, installed the customer rack rackmounted rad 203 port 5 Verizon BEAS Circuit ID: USATX39424785COV400001 / E4037505 Verizon BEAS Demarcation: installed in same rack where RAD unit is installed. Installed on unit 22 in LAN rack | 197300669 | UNITED HEALTH GROUP | Private IP - PIP (27824312) WAN Analysis Reporting (27824314) Access (27824313) | 27824312 27824314 27824313 | 10 MBPS (27824312) |  | 94575002 (Private IP (PIP)) 94575008 (WAN Analysis Reporting) 94575004 (Access) | C4014519/ADD (27824312) E4037505/ADD (27824313) | 95.L1XX.008857..TWCC (2782431339424701) | 6011273 | 5500 | PVC ID : 6011273 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64914 PE IP Address : 208.220.203.33 CE Address : 208.220.203.34 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27824313) | 1000Base-SX (850nm, Multi Mode Fiber) (27824313) | Ethernet | TIME WARNER CABLE (2782431339424701) | 11/19/2018 (2782431339424701) | 02/18/2019 (2782431339424701) | 01/29/2019 (2782431339424701) | 01/31/2019 (VFORCE) (27824313) | 01/31/2019 (VFORCE) (27824313) | DEMARCADDR - 1104 W SAM HOUSTON BLVD PHARR TX 78577 5104 DEMARCDET - IT room installed the customer rack rackmounted rad 203 port 5 |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 01/31/2019(Private IP - PIP) 01/31/2019(WAN Analysis Reporting) 01/31/2019(Access) |  |  | 02/27/2019 (27824312) 02/25/2019 (27824313) | 03/01/2019 03/07/2019 | 01/31/2019 |  | Completed | N (27824312) N (27824314) N (27824313) | U0101953 | Jeopardy Notification 4 (11/16/2018) | NSPE0012433013 Order Request # 197290359 | NSPE0012433013
Completed | VA074-06-CM Falls Church, VA | 3160 FAIRVIEW PARK DR FALLS CHURCH, VA 22042-4516 US | 50 MBPS | 10/26/2018: 10/26 - Background: VA074-02-IM Falls Church, VA; Change port speed from 10M to 20M Status: Hot-cut completed on 10/21. Layer 3 updated with port speed of 20 mbps. | 197324253 | VA074-02-IM | Access WAN Analysis Reporting (27856088) Private IP - PIP (27856086) | 27856086 27856088 | 20 MBPS (27856086) |  | 94539903 94539906 (WAN Analysis Reporting) 94539900 (Private IP (PIP)) | C4013444/NONE (27856086) |  | 5993918 | 10000 | PVC ID : 5993918 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64800 PE IP Address : 199.220.117.61 CE Address : 199.220.117.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | BRAD HARRISON 1-703-269-5999 brad.harrison@lewin.com | BRAD HARRISON | brad.harrison@lewin.com | 1-703-269-5999 | 10/21/2018(Private IP |  |  | 10/11/2018 (27856086) | 10/22/2018 (23192299.3) 10/22/2018 | 10/21/2018 |  | Activated/Installed Completed | N N (27856088) N (27856086) | U0101953 |  | NSPE0012405471 Order Request # 197203889 | NSPE0012405471
Completed | PA134-02-IJ Plymouth Meeting, PA | 620 W GERMANTOWN PIKE PLYMOUTH MEETING, PA 19462-1068 US | 50 MBPS | 01/06/2019 Successfully Changed port speed from 10M to 20M | 197332423 | PA134-02-IJ | Private IP - PIP (27864804) Access WAN Analysis Reporting (27864806) | 27864804 27864806 | 20 MBPS (27864804) |  | 215057122 (Private IP (PIP)) 215057120 215057123 (WAN Analysis Reporting) | C4010972/NONE (27864804) |  | 5966057 | 10000 | PVC ID : 5966057 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65171 PE IP Address : 68.139.49.245 CE Address : 68.139.49.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | susan wagner 1-763-744-0632 susan_l_wagner@optum.com | susan wagner | susan_l_wagner@optum.com | 1-763-744-0632 | 01/07/2019(Private IP | 01/06/2019 |  | 10/12/2018 (27864804) | 10/23/2018 10/23/2018 (21686589.1) | 01/07/2019 |  | Completed Activated/Installed | N (27864804) N N (27864806) | U0101953 |  | NSPE0012437045 Order Request # 197304027 | NSPE0012437045
Completed | TX456 Austin, TX | 901 S MO PAC EXPY AUSTIN, TX 78746-5776 US | 50 MBPS (27874924) | 03/14/2019: 03/13 Successfully activated | 197337665 | quote | WAN Analysis Reporting (27874925) Access (27874924) Private IP - PIP (27874923) | 27874925 27874924 27874923 | 10 MBPS (27874923) |  | 94577447 (WAN Analysis Reporting) 94577443 (Access) 94577445 (Private IP (PIP)) | C4014607/ADD (27874923) E4037726/ADD (27874924) | TX/KXFN/076853/LVLC (2787492445458001) | 6012660 | 5500 | PVC ID : 6012660 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65232 PE IP Address : 199.220.98.109 CE Address : 199.220.98.110 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (27874924) | 1000Base-SX (850nm, Multi Mode Fiber) (27874924) | Ethernet | LEVEL 3 (2787492445458001) | 10/29/2018 (2787492445458001) | 11/26/2018 (2787492445458001) | 11/30/2018 (2787492445458001) | 12/18/2018 (VFORCE) (27874924) | 02/22/2019 (VFORCE) (27874924) | DEMARCDET - 3rd floor telco room wall mount w2001 port 9 tagged withj CKLT ID TX/KXFN/076853/LVLC |  | Emilia Rich 1-737-218-9167 emilia_rich@uhg.com | JASON SALAPING | jason_salaping@gmail.com | 632-462-2446 | 02/22/2019(WAN Analysis Reporting) 02/22/2019(Access) 02/22/2019(Private IP - PIP) | 03/13/2019 |  | 02/26/2019 (27874923) 02/22/2019 (27874924) | 03/21/2019 03/15/2019 | 02/22/2019 |  | Completed | N (27874925) N (27874924) N (27874923) | U0101953 | Jeopardy Notification 2 (01/29/2019) | NSPE0012444955 Order Request # 197327897 | NSPE0012444955
Completed | TX448-02-IM Kaufman, TX | 874 ED HALL DR STE 106 KAUFMAN, TX 75142-1800 US | 50 MBPS (27876511) | 02/06/2019: 2/6Background: TX448-02-IM Kaufman, TX; New 10M/50M PIP-Eth; (Century Link); Dual NID; No MNS; Status: FOC 02/12/2019. Customer informed and acknowledge. Escalated to 1st level Next action: BEAS installation | 197337623 | TX448-02-IM | Private IP - PIP (27876510) WAN Analysis Reporting (27876512) Access (27876511) | 27876510 27876512 27876511 | 10 MBPS (27876510) |  | 94579042 (Private IP (PIP)) 94579040 (WAN Analysis Reporting) 94579045 (Access) | C4014608/ADD (27876510) E4037735/ADD (27876511) | 86.KXGS.372425..UDTX (2787651146505102) | 6012725 | 5500 | PVC ID : 6012725 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64562 PE IP Address : 206.114.64.201 CE Address : 206.114.64.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27876511) | 1000Base-SX (850nm, Multi Mode Fiber) (27876511) | Ethernet | CENTURYLINK (2787651146505102) | 12/17/2018 (2787651146505102) | 02/12/2019 (2787651146505102) | 02/11/2019 (2787651146505102) | 02/13/2019 (VFORCE) (27876511) |  | DEMARCDET - FIRST FLOOR COMMUNICATIONS ROOM WALL MOUNTED RACK POSITION 3 RAD2 RAD 203A PORT 03 OPTICAL TL |  | LIZDELI GUERRIDO 1-917-981-9347 lguerrido@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 1-763-744-2114 | 02/13/2019(Private IP - PIP) 02/13/2019(WAN Analysis Reporting) 02/13/2019(Access) |  |  | 03/06/2019 (27876510) 03/04/2019 (27876511) | 01/25/2019 01/31/2019 | 02/13/2019 |  | Completed | N (27876510) N (27876512) N (27876511) | U0101953 | Jeopardy Notification 2 (12/13/2018) | NSPE0012447761 Order Request # 197336617 | NSPE0012447761
Completed | PA062-05-IJ Horsham PA | 680 BLAIR MILL RD HORSHAM, PA 19044-2223 US | 200 MBPS | 11/01/2018: 11/01 - Background: PA062-05-IJ Horsham, PA; Upgrade 200M Port and 110M Gold CAR Status: Port Speed Upgrade from 150Mbps to 200Mbps completed on 10/27. | 197378553 | PA062-05-IJ Horsham PA | Private IP - PIP (27909979) Access | 27909979 | 200 MBPS (27909979) |  | 88611451 (Private IP (PIP)) 88611449 | C5001554/NONE (27909979) |  | 5695288 | 110000 | PVC ID : 5695288 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65203 PE IP Address : 199.220.102.17 CE Address : 199.220.102.18 QoS - Egress Profile: R1 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Susan Wagner 1-763-744-0632 susan_l_wagner@optum.com | RAJESH JOHN CATALONIA | rajesh_catalonia@optum.com | 1-763-790-6177 | 12/10/2018(Private IP | 10/29/2018 |  | 10/19/2018 (27909979) | 10/30/2018 | 12/10/2018 |  |  | N (27909979) N | U0101953 |  | NSPE0012405876 Order Request # 197205127 | NSPE0012405876
Completed | TX777-05-IJ Student Resources Internet T1 | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US | 10 GBPS (27940004) | 11/29/2018: 11/29 Background: TX777-05-IJ Student Resources Internet T1; Dallas, TX; New 2G/10G PIP-Eth; No NID; No MNS Status: Order complete Next action: Order closure Who owns the next action: SD | 197420221 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (27940003) Access (27940004) | 27940003 27940004 | 2 GBPS (27940003) |  | 289292535 (Internet Dedicated Services) 289292531 (Access) | C0155297/ADD (27940003) E7000741/ADD (27940004) |  | 6014524 | 0 | PVC ID : 6014524 VPN Name : Internet Router Name : GW7DFW13 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.14.49 CE Address : 204.148.14.50 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (27940004) | Ethernet | [8 empty] | MATTHEW ADAMS 1-763-553-4616 matthew_adams@optum.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 11/29/2018(Internet Dedicated Services) 11/29/2018(Access) |  |  | 12/03/2018 (27940003) 11/29/2018 (27940004) | 11/20/2018 | 11/29/2018 |  | Managed | N (27940003) N (27940004) | U0101953 |  | NSPE0012470487 Order Request # 197415177 | NSPE0012470487
Completed | FL351-02-IM Tampa, FL | 15320 AMBERLY DR STE B TAMPA, FL 33647-1647 US | 300 MBPS (28009167) | 02/25/2019 - Activation scheduled 02/28/2019 7:30 PM CST | 197495169 | FL351-02-IM | Private IP - PIP (28009166) WAN Analysis Reporting (28009168) Access (28009167) | 28009166 28009168 28009167 | 150 MBPS (28009166) |  | 94584938 (Private IP (PIP)) 94584945 (WAN Analysis Reporting) 94584942 (Access) | C5006395/ADD (28009166) E5015044/ADD (28009167) | 81.L1XX.807047..TWCC (2800916747552101) | 6016717 | 90000 | PVC ID : 6016717 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64688 PE IP Address : 199.220.43.49 CE Address : 199.220.43.50 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28009167) | 1000Base-SX (850nm, Multi Mode Fiber) (28009167) | Ethernet | BRIGHT HOUSE (2800916747552101) | 11/05/2018 (2800916747552101) | 02/18/2019 (2800916747552101) | 01/16/2019 (2800916747552101) | 01/22/2019 (VFORCE) (28009167) | 01/22/2019 (VFORCE) (28009167) | DEMARCDET - MDF flr 1 main bldg wall mounted tagged with equipment port and ckt ID on the box |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | ED STILES | ed.stiles@optum.com | 1-770-767-8212 | 01/22/2019(Private IP - PIP) 01/22/2019(WAN Analysis Reporting) 01/22/2019(Access) |  |  | 02/27/2019 (28009166) 02/25/2019 (28009167) | 12/14/2018 12/20/2018 | 01/22/2019 |  | Completed | N (28009166) N (28009168) N (28009167) | U0101953 | Jeopardy Notification 1 (12/04/2018) | NSPE0012493135 Order Request # 197494943 | NSPE0012493135
Completed | TX444-05-IM Cedar Park, TX | 11901 W PARMER LN CEDAR PARK, TX 78613 USA | 1.536 MBPS (IQBLN0J0) | 12/18/2018: Background: TX444-05-IM Cedar Park, TX; New 7xT1 MLPPP; No NID; No MNS; Status: Ready for activation (Plug & Play) Next action: Customer to activate Who owns the next action: Customer Ticket: NA DEMARC INFO: BCBLDJNN0001 DEMARC LOC: LOC 1ST FL STE 300 TEL RM CAB # 1 POS DEMARC LOC Continued: # 1 POS # 1 TAGGED Extended Wire (Yes or No): NO EW Reason/Location:CLSD BLDG MPOE ONLY GROUND OK Jack Type: RJ48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 11 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0002 DEMARC LOC: 1FL/STE 300 TELCO RM/CAB1 POS2 DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:No IW Authorized Jack Type: 48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 13 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0003 DEMARC LOC: 1FL/STE 300 TELCO RM/CAB1 POS3 DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:No IW Authorized Jack Type: 48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 16 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0004 DEMARC LOC: LOC 1ST FL STE 300 TEL RM CAB # 1 POS DEMARC LOC Continued: # 1 POS # 4, TAGGED Extended Wire (Yes or No): NO EW Reason/Location:CLSD BLDG MPOE ONLY GROUND OK Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 22 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0005 DEMARC LOC: 1FL/STE 300 TELCO RM/CAB2 POS1 DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:No IW Authorized Jack Type: 48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 24 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0006 DEMARC LOC: 1FL/STE 300 TELCO RM/CAB2 POS2 DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:No IW Authorized Jack Type: 48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 26 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0007 DEMARC LOC: LOC 1ST FL STE 300 TEL RM CAB # 2 POS DEMARC LOC Continued: # 2 POS # 3, TAGGED Extended Wire (Yes or No): NO EW Reason/Location:CLSD BLDG MPOE ONLY GROUND OK Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 27 AUSTTXFIHB1 AUSTTXJOK11 12/18/2018: Background: TX444-05-IM Cedar Park, TX; New 7xT1 MLPPP; No NID; No MNS; Status: Ready for activation (Plug & Play) Next action: Customer to activate Who owns the next action: Customer Ticket: NA DEMARC INFO: BCBLDJNN0001 DEMARC LOC: LOC 1ST FL STE 300 TEL RM CAB # 1 POS DEMARC LOC Continued: # 1 POS # 1 TAGGED Extended Wire (Yes or No): NO EW Reason/Location:CLSD BLDG MPOE ONLY GROUND OK Jack Type: RJ48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 11 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0002 DEMARC LOC: 1FL/STE 300 TELCO RM/CAB1 POS2 DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:No IW Authorized Jack Type: 48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 13 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0003 DEMARC LOC: 1FL/STE 300 TELCO RM/CAB1 POS3 DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:No IW Authorized Jack Type: 48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes CFA or Tie-down At ACTL: 106 T3Z 16 AUSTTXFIHB1 AUSTTXJOK11 =========== BCBLDJNN0004 DEMARC LOC: LOC 1ST FL STE 300 TEL RM CAB # 1 POS DEMARC LOC Continued: # 1 POS # 4, TAGGED Extended Wire (Yes or No): NO EW Reason/Location:CLSD BLDG MPOE ONLY GROUN Pls check order record | 9735606 |  | Private IP (IQBLN0J0) EVC/PVC Service (N.11869899.6018348) | IQBLN0J0 N.11869899.6018348 | 10.752 MBPS | P2207804 |  | BCBLDJNN0001 (IQBLN0J0) BCBLDJNN0002 (IQBLN0J0) BCBLDJNN0003 (IQBLN0J0) BCBLDJNN0004 (IQBLN0J0) BCBLDJNN0005 (IQBLN0J0) BCBLDJNN0006 (IQBLN0J0) BCBLDJNN0007 (IQBLN0J0) | 32/HCGS/697766//SW (IQBLN0J0H3YWMB01) | 6018348 | 7200 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64583 PE IP Address : 68.137.109.13 CE Address : 68.137.109.14 QoS - Egress Profile: R12 PVC ID : 6018348 |  |  |  | ATT (IQBLN0J0H3YWMB01) | 12/04/2018 (IQBLN0J0H3YWMB01) | 12/11/2018 (IQBLN0J0H3YWMB01) | 12/11/2018 (IQBLN0J0H3YWMB01) |  |  | DEMARC INFO: BCBLDJNN0001 DEMARC LOC: LOC 1ST FL STE 300 TEL RM CAB |  | JASON OZER 0012109513251 JOZER@WELLMED.NET |  |  |  | 12/17/2018 (IQBLN0J0) |  |  | 01/07/2019 (IQBLN0J0) | 01/07/2019 (IQBLN0J0) |  |  |  | N (IQBLN0J0) N (N.11869899.6018348) | 05017789 P2207804 |  | NSPE0012499530 CW 197486659 | NSPE0012499530
Completed | TX079-05-IM El Paso, TX | 9999 KENWORTHY ST STE A EL PASO, TX 79924-4413 US | 50 MBPS (27697730) | 11/21/2018: 11/20 Background: TX079-05-IM El Paso, TX; New 20M/50M PIP-Eth; (TWT); NID; No MNS; Status: Ready for activation Next action: Customer to activate Who owns the next action: Customer Ticket: NA Telco Circuit ID: TX/KXFN/056424/LVLC Telco Demarcation: 1st floor, Suite B (3000), Storage Room, Relay Rack, RMU Position 37, ADVA Port 3, RJ45, tagged with circuit id Verizon BEAS Circuit ID: USATX45629831COV400001 / E4036994 Verizon BEAS Demarcation: 1st Floor, Suite B/3000 storage room. relay rack RMU position 34. | 197185299 | TX079-05-IM | Access (27697730) WAN Analysis Reporting (27697731) Private IP - PIP (27697729) | 27697730 27697731 27697729 | 20 MBPS (27697729) |  | 94570166 (Access) 94570160 (WAN Analysis Reporting) 94570162 (Private IP (PIP)) | E4036994/ADD (27697730) C4014355/ADD (27697729) | TX/KXFN/056424/LVLC (2769773045629801) | 6008429 | 13000 | PVC ID : 6008429 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64572 PE IP Address : 147.225.164.201 CE Address : 147.225.164.202 QoS - Egress Profile: R12 | 100Base-TX (27697730) | 100Base-TX (27697730) | Ethernet | LEVEL 3 (2769773045629801) | 09/25/2018 (2769773045629801) | 10/30/2018 (2769773045629801) | 11/09/2018 (2769773045629801) | 11/20/2018 (VFORCE) (27697730) | 11/13/2018 (VFORCE) (27697730) | DEMARCDET - 1st floor, Suite B (3000), Storage Room, Relay Rack, RMU Position 37, ADVA Port 3, RJ45, tagged with CID |  | GABRIEL RODRIGUEZ 1-210-833-8929 grodriguez1@wellmed.net | Sahil Tuteja | sahil_tuteja@optum.com | 91-828-567-0647 | 11/20/2018(Access) 11/20/2018(WAN Analysis Reporting) 11/20/2018(Private IP - PIP) |  |  | 11/27/2018 (27697730) 11/29/2018 (27697729) | 12/18/2018 12/24/2018 | 11/20/2018 |  | Completed | N (27697730) N (27697731) N (27697729) | U0101953 | Jeopardy Notification 1 (11/14/2018) | NSPE0012399573 Order Request # 197185187 | NSPE0012399573
Completed | TX449-02-IM Sunnyvale, TX | 2858 N BELT LINE RD STE 600 SUNNYVALE, TX 75182-9303 US | 50 MBPS (28076479) | 03/26/2019 Background: TX449-02-IM Sunnyvale, TX; New 10M/50M PIP-Eth; (TWC); Dual NID; No MNS; Status: Ready for activation Telco Circuit ID: 97.L1XX.005367..TWCC Telco Demarcation: installed in customer telco room on the south wall on the spectrum rack rad 203 port 5 Verizon BEAS Circuit ID: USATX46919879COV400001 / E4038879 Verizon BEAS Demarcation: suite 600 telephone/server room. south wall. wall mounted rack. installed Overture just beneath the Spectrum RAD. tagged with local ckt id and Verizon. | 197574843 | TX449-02-IM | WAN Analysis Reporting (28076480) Access (28076479) Private IP - PIP (28076478) | 28076480 28076479 28076478 | 10 MBPS (28076478) |  | 94581842 (WAN Analysis Reporting) 94581838 (Access) 94581835 (Private IP (PIP)) | C4014993/ADD (28076478) E4038879/ADD (28076479) | 97.L1XX.005367..TWCC (2807647946919801) | 6019337 | 5500 | PVC ID : 6019337 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64556 PE IP Address : 152.176.230.125 CE Address : 152.176.230.126 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28076479) | 1000Base-SX (850nm, Multi Mode Fiber) (28076479) | Ethernet | TIME WARNER CABLE (2807647946919801) | 11/16/2018 (2807647946919801) | 04/05/2019 (2807647946919801) | 03/22/2019 (2807647946919801) | 03/26/2019 (VFORCE) (28076479) | 03/26/2019 (VFORCE) (28076479) | DEMARCADDR - 2858 N BELT LINE RD SUNNYVALE TX 75182 DEMARCDET - installed in customer telco room on the south wall on the spectrum rack rad 203 port 5 |  | Saundra Watson 1-210-955-6641 swatson@wellmed.net | KEITHLEY HUGGINS | KeithleyHuggins@optum.com | 1-770-767-8282 | 03/26/2019(WAN Analysis Reporting) 03/26/2019(Access) 03/26/2019(Private IP - PIP) |  |  | 04/16/2019 (28076478) 04/12/2019 (28076479) | 01/01/2019 12/26/2018 | 03/26/2019 |  | Completed | N (28076480) N (28076479) N (28076478) | U0101953 | Jeopardy Notification 1 (01/02/2019) | NSPE0012516635 Order Request # 197567879 | NSPE0012516635
Completed | TX454-02-IM Rockport, TX | 1202 FM 3036 ROCKPORT, TX 78382-7798 US | 10 MBPS (28078122) | 02/08/2019: Background: TX454-02-IM Rockport, TX; New 10M/10M PIP-Eth; (AT&T); Dual NID; No MNS; Status: Ready for activation Next action: Customer to activate Who owns the next action: Customer Telco Circuit ID: 34/KRGN/613936//SW Telco Demarcation: 1st floor server room wall mounted port 1 Ciena 3930 Verizon BEAS Circuit ID: USATX47210391COV400001 / E3061298 Verizon BEAS Demarcation: Mounted on the backboard in the dmarc room, behind the Xray room | 197583991 | TX454-02-IM | Access (28078122) WAN Analysis Reporting (28078123) Private IP - PIP (28078121) | 28078122 28078123 28078121 | 10 MBPS (28078121) |  | 94582842 (Access) 94582839 (WAN Analysis Reporting) 94582837 (Private IP (PIP)) | E3061298/ADD (28078122) C0156597/ADD (28078121) | 34/KRGN/613936//SW (2807812247210301) | 6019350 | 5500 | PVC ID : 6019350 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64554 PE IP Address : 152.164.188.245 CE Address : 152.164.188.246 QoS - Egress Profile: R12 | 1000Base-T (28078122) | 1000Base-SX (850nm, Multi Mode Fiber) (28078122) | Ethernet | ATT (2807812247210301) | 11/15/2018 (2807812247210301) | 02/04/2019 (2807812247210301) | 02/04/2019 (2807812247210301) | 02/06/2019 (VFORCE) (28078122) | 02/07/2019 (VFORCE) (28078122) | DEMARCDET - 1st floor server room wall mounted port 1 Ciena 3930 |  | Gabe Rodriguez 1-210-974-6678 grodriguez1@wellmed.net | HERBERT VILLOSTAS | herbert_villostas@optum.com | 1-763-744-2114 | 02/07/2019(Access) 02/07/2019(WAN Analysis Reporting) 02/07/2019(Private IP - PIP) |  |  | 02/11/2019 (28078122) 02/13/2019 (28078121) | 02/06/2019 02/12/2019 | 02/07/2019 |  | Completed | N (28078122) N (28078123) N (28078121) | U0101953 | Jeopardy Notification 3 (12/26/2018) | NSPE0012518589 Order Request # 197573465 | NSPE0012518589
Completed | Irving, TX | 909 HIDDEN RDG STE 300 IRVING, TX 75038-3801 US | 500 MBPS (28098033) | 05/23/2019: Activation rescheduled 05/28/2019 2230 CST | 197604407 | Location4205607503 | Private IP - PIP (28098032) WAN Analysis Reporting (28098034) Access (28098033) | 28098032 28098034 28098033 | 200 MBPS (28098032) |  | 94589781 (Private IP (PIP)) 94589787 (WAN Analysis Reporting) 94589784 (Access) | C5006457/ADD (28098032) E5015227/ADD (28098033) | TX/KXFN/087429/LVLC (2809803379644501) | 6019899 | 140000 | PVC ID : 6019899 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64546 PE IP Address : 199.220.53.157 CE Address : 199.220.53.158 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (28098033) | 1000Base-SX (850nm, Multi Mode Fiber) (28098033) | Ethernet | LEVEL 3 (2809803379644501) | 11/27/2018 (2809803379644501) | 12/18/2018 (2809803379644501) | 12/14/2018 (2809803379644501) | 12/20/2018 (VFORCE) (28098033) | 12/20/2018 (VFORCE) (28098033) | DEMARCDET - 1st floor, main telephone rm, wall mounted biscuit jack, SMF LC handoff, tagged with ckt id TX/KXFN/087429/LVLC |  | Lynn Nipper 1-972-791-1224 lynn.nipper@medsynergies.com | JASON SALAPING | jason_salaping@gmail.com | 632-462-2446 | 12/20/2018(Private IP - PIP) 12/20/2018(WAN Analysis Reporting) 12/20/2018(Access) |  |  | 12/28/2018 (28098032) 12/26/2018 (28098033) | 01/07/2019 01/11/2019 | 12/20/2018 |  | Completed | N (28098032) N (28098034) N (28098033) | U0101953 |  | NSPE0012527587 Order Request # 197604241 | NSPE0012527587
Completed | TX452-02-IM Fort Worth, TX | 8030 CAMP BOWIE WEST BLVD FORT WORTH, TX 76116-6313 US | 10 MBPS (28101446) | 04/24/2019: 4/24Background: TX452-02-IM Fort Worth, TX; New 10M/10M PIP-Eth; (AT&T); Dual NID; No MNS; Status: Loop delivered;Pending testing on LEC end. Next Action: Beas Install | 197601655 | TX452-02-IM | WAN Analysis Reporting (28101447) Private IP - PIP (28101445) Access (28101446) | 28101447 28101445 28101446 | 10 MBPS (28101445) |  | 94590033 (WAN Analysis Reporting) 94590031 (Private IP (PIP)) 94590035 (Access) | E3061471/ADD (28101446) C0156768/ADD (28101445) | 14/KRGN/885307//SW (2810144648126602) | 6020155 | 5500 | PVC ID : 6020155 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64540 PE IP Address : 199.220.49.181 CE Address : 199.220.49.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28101446) | 1000Base-SX (850nm, Multi Mode Fiber) (28101446) | Ethernet | ATT (2810144648126602) | 04/17/2019 (2810144648126602) | 04/23/2019 (2810144648126602) | 04/25/2019 (2810144648126602) | 04/30/2019 (VFORCE) (28101446) | 04/30/2019 (VFORCE) (28101446) | DEMARCDET - 1st flr it rm backboard on cienna 3903 port 2 taged with crt id |  | Jason Ozer 1-210-951-3251 jozer@wellmed.net | HERBERT VILLOSTAS | herbert_villostas@optum.com | 632-790-6516 | 04/30/2019(WAN Analysis Reporting) 04/30/2019(Private IP - PIP) 04/30/2019(Access) |  |  | 04/30/2019 (28101446) 05/02/2019 (28101445) | 05/23/2019 05/17/2019 | 04/30/2019 |  | Completed | N (28101447) N (28101445) N (28101446) | U0101953 | Jeopardy Notification 1 (04/02/2019) | NSPE0012526805 Order Request # 197601439 | NSPE0012526805
Completed | CA377-03-IM Epic Hearing Pomona, CA | 3191 W TEMPLE AVE POMONA, CA 91768-3287 US | 200 MBPS (28105098) | 12/26/2018: Order complete | 197616985 | CA377-03-IM Epic Hearing. | Private IP - PIP WAN Analysis Reporting (28105099) Access (28105098) | 28105098 28105099 | 100 MBPS |  | 94537298 94537603 (WAN Analysis Reporting) 94537296 (Access) | E5012168/NONE (28105098) |  |  |  |  | 1000Base-SX-850nm (28105098) | 1000Base-SX (850nm, Multi Mode Fiber) (28105098) | Ethernet | [8 empty] | Kris Seehoff 1-763-744-1584 | LARRY WALSH | larry_l_walsh@optum.com | 1-131-771-5777 | 12/24/2018(Access) | 12/14/2018 |  | 12/18/2018 (28105098) | 01/17/2019 (22906287.1) 01/17/2019 | 12/24/2018 |  | Activated/Installed Completed | N N (28105099) N (28105098) | U0101953 |  | NSPE0012530705 Order Request # 197616601 | NSPE0012530705
Completed | FL371-02-IM Ruskin, FL | 819 CYPRESS VILLAGE BLVD RUSKIN, FL 33573-6834 US | 50 MBPS (28167351) | 06/04/2019 Successfully activated | 197682125 | FL371 | Private IP - PIP (28167350) WAN Analysis Reporting (28167352) Access (28167351) | 28167350 28167352 28167351 | 10 MBPS (28167350) |  | 94591576 (Private IP (PIP)) 94591582 (WAN Analysis Reporting) 94591579 (Access) | C4015144/ADD (28167350) E4039300/ADD (28167351) | 65/KFGS/036586//FTNC/ (2816735148590401) | 6021999 | 5000 | PVC ID : 6021999 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64935 PE IP Address : 68.136.11.253 CE Address : 68.136.11.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28167351) | 1000Base-SX (850nm, Multi Mode Fiber) (28167351) | Ethernet | FRONTIER (2816735148590401) | 01/15/2019 (2816735148590401) | 02/20/2019 (2816735148590401) | 02/04/2019 (2816735148590401) | 02/06/2019 (VFORCE) (28167351) | 02/06/2019 (VFORCE) (28167351) | DEMARCADDR - 819 CYPRESS VILLAGE BLVD RUSKIN FL DEMARCDET - 1st floor IT closet wall mounted rad nid user port 5 |  | TODD VANDERSCHAEGEN 1-210-780-6809 tvanderschaegen@wellmed.net | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 02/06/2019(Private IP - PIP) 02/06/2019(WAN Analysis Reporting) 02/06/2019(Access) | 06/04/2019 |  | 03/01/2019 (28167350) 02/27/2019 (28167351) | 02/26/2019 03/04/2019 | 02/06/2019 |  | Completed | N (28167350) N (28167352) N (28167351) | U0101953 | Jeopardy Notification 1 (01/15/2019) | NSPE0012547133 Order Request # 197671323 | NSPE0012547133
Completed | FL368 Riverview, FL | 13142 ELK MOUNTAIN DR STE 106 RIVERVIEW, FL 33579-7182 US | 50 MBPS (28179111) | 03/29/2019 Background: FL368 Riverview, FL; New 10M/50M PIP-Eth; (Bright House); Dual NID; No MNS; 100BD offnet build Status: Ready for activation Telco Circuit ID: 81.L1XX.807706..TWCC Telco Demarcation: Wall mounted on Telco Closet Verizon BEAS Circuit ID: USAFL48756297COV400001 Verizon BEAS Demarcation: 1st floor, data closet, placed on book shelf, tag, no loops | 197695293 | FL368 | Private IP - PIP (28179110) WAN Analysis Reporting (28179112) Access (28179111) | 28179110 28179112 28179111 | 10 MBPS (28179110) |  | 94593431 (Private IP (PIP)) 94593429 (WAN Analysis Reporting) 94593433 (Access) | C4015180/ADD (28179110) E4039382/ADD (28179111) | 81.L1XX.807706..TWCC (2817911148756201) | 6022548 | 5500 | PVC ID : 6022548 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64543 PE IP Address : 199.220.143.101 CE Address : 199.220.143.102 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28179111) | 1000Base-SX (850nm, Multi Mode Fiber) (28179111) | Ethernet | BRIGHT HOUSE (2817911148756201) | 12/04/2018 (2817911148756201) | 03/22/2019 (2817911148756201) | 03/22/2019 (2817911148756201) | 03/29/2019 (VFORCE) (28179111) | 03/29/2019 (VFORCE) (28179111) | DEMARCDET - WALL MOUNTED ON TELCO CLOSET |  | TODD VANDERSCHAEGEN 1-813-629-2611 tvanderschaegen@wellmed.net | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 1-763-744-2114 | 03/29/2019(Private IP - PIP) 03/29/2019(WAN Analysis Reporting) 03/29/2019(Access) |  |  | 04/02/2019 (28179110) 03/29/2019 (28179111) | 05/23/2019 05/29/2019 | 03/29/2019 |  | Completed | N (28179110) N (28179112) N (28179111) | U0101953 | Jeopardy Notification 3 (01/02/2019) | NSPE0012553017 Order Request # 197690689 | NSPE0012553017
Completed | UMNEA-04-IM Saint Paul, MN | 513 EATON ST SAINT PAUL, MN 55107-2474 US | 1.5 MBPS (28197684) | 12/19/2018: 12/19Background: UMNEA-04-IM Saint Paul, MN; New 1.5 MLPPP; (Qwest); No NID; No MNS Status:FOC 12/20/2018. Access confirmed. Next action: Line testing | 197718251 | UMNEA MN003 | WAN Analysis Reporting (28197685) Private IP - PIP (28197683) Access (28197684) | 28197685 28197683 28197684 | 1.5 MBPS (28197683) |  | 94594634 (WAN Analysis Reporting) 94594638 (Private IP (PIP)) 94594636 (Access) | D1097834/ADD (28197684) C0157932/ADD (28197683) | 03/HCGS/333389//NW (2819768448874201) | 6023568 | 768 | PVC ID : 6023568 VPN Name : UnitedHealthGroup Router Name : MWAGE02 VRF Name : Vc71705:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 64564 PE IP Address : 68.137.130.169 CE Address : 68.137.130.170 QoS - Egress Profile: R12 |  | DS1 (28197684) | TDM | CENTURYLINK (2819768448874201) | 12/06/2018 (2819768448874201) | 12/20/2018 (2819768448874201) | 12/20/2018 (2819768448874201) |  |  | DEMARCDET - FIRST FLOOR MAIN TELCO/MDF ROOM SINGLE SLOT SHELF # 1 |  | JEFFREY PHILLIPS 1-724-597-6226 jeffrey.phillips@medexpress.com | EDWARD JONES | edward.jones@optum.com | 1-719-425-4044 | 12/21/2018(WAN Analysis Reporting) 12/21/2018(Private IP - PIP) 12/21/2018(Access) |  |  | 12/28/2018 (28197684) 01/02/2019 (28197683) | 01/03/2019 12/28/2018 | 12/21/2018 |  | Completed | N (28197685) N (28197683) N (28197684) | U0101953 |  | NSPE0012561584 Order Request # 197718091 | NSPE0012561584
Completed |  | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US | 10 GBPS | 01/03/2019: 1/3Background: Dallas, TX; Change from Tiered and Burstable; Status: Changes Complete | 197749583 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (28221696) Access | 28221696 | 10 GBPS (28221696) |  | 289292535 (Internet Dedicated Services) 289292531 | C0155297/NONE (28221696) |  | 6014524 | 0 | PVC ID : 6014524 VPN Name : Internet Router Name : GW7DFW13 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.14.49 CE Address : 204.148.14.50 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) | Ethernet | [8 empty] | MATTHEW ADAMS 1-763-553-4616 matthew_adams@optum.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 01/03/2019(Internet Dedicated Services) | 12/19/2018 |  | 12/19/2018 (28221696) | 12/20/2018 | 01/07/2019 |  |  | N (28221696) N | U0101953 |  | Change to burstable NSPE0012569891 Order Request # 197746611 | NSPE0012569891
Completed | Minneapolis, MN | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 200 MBPS (CQBLN8YW) | 12/14/2018: Background: Minneapolis, Minnesota; Downgrade PIP Port Only from 1G to 200M; Status: Complete Next action: NA Who owns the next action: NA Ticket: NA | 9759191 |  | Private IP Port Only (CQBLN8YW) | CQBLN8YW | 200 MBPS | P2189072 |  | BOBLCS7X0001 (CQBLN8YW) |  | 5969712 | 50000 | PVC ID : 5969712 VPN Name : UHG-OFE Router Name : MN39E01 VRF Name : Vc13322:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64995 PE IP Address : 152.177.19.85 CE Address : 152.177.19.86 QoS - Egress Profile: R12 | [11 empty] | JAMES CRAWFORD 0017635952550 JAMES.CRAWFORD@VERIZON.COM |  |  |  | 12/12/2018 (CQBLN8YW) | 12/12/2018 |  | 01/04/2019 (CQBLN8YW) | 01/04/2019 (CQBLN8YW) |  |  |  | N (CQBLN8YW) | 05017789 |  | NSPE0012563752 | NSPE0012563752
Completed | Cologne, MN | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 200 MBPS (CQBLN8X1) | 12/17/2018: 12/14 Successfully downgraded port speed to 200M | 9759201 |  | Private IP Port Only (CQBLN8X1) | CQBLN8X1 | 200 MBPS | P2189060 |  | BOBLCS7M0001 (CQBLN8X1) |  | 5969596 | 50000 | PVC ID : 5969596 VPN Name : UHG-OFE Router Name : MZZ9E01 VRF Name : Vc13143:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65517 PE IP Address : 147.225.90.197 CE Address : 147.225.90.198 QoS - Egress Profile: R12 | [11 empty] | JAMES CRAWFORD 0017635952550 JAMES.CRAWFORD@VERIZON.COM |  |  |  | 12/14/2018 (CQBLN8X1) | 12/14/2018 |  | 01/04/2019 (CQBLN8X1) | 01/04/2019 (CQBLN8X1) |  |  |  | N (CQBLN8X1) | 05017789 |  | NSPE0012563752 | NSPE0012563752
Completed | FL367-02-IM Davenport, FL | 2380 NORTH BLVD W DAVENPORT, FL 33837-8924 US | 50 MBPS (28248194) | 02/13/2019: Background: FL367-02-IM Davenport, FL; New 10M/50M PIP-Eth; (Frontier); NID; No MNS; ENID Status: Ready for activation once customer cabling is complete Next action: Customer to activate Who owns the next action: Customer Ticket: NA Telco Circuit ID: 65/KEGS/043417//FTNC/ Telco Demarcation: 1st Floor, SL3 Shelf 1, Port 3, PHYSH 1 POS 3 wallmounted, tagged. Verizon BEAS Circuit ID: USAFL46449867COV400001 / E4039786 Verizon BEAS Demarcation: pending | 197784467 | FL367-02-IM new address | Private IP - PIP (28248193) WAN Analysis Reporting (28248195) Access (28248194) | 28248193 28248195 28248194 | 10 MBPS (28248193) |  | 94599247 (Private IP (PIP)) 94599249 (WAN Analysis Reporting) 94599251 (Access) | C4015329/ADD (28248193) E4039786/ADD (28248194) | 65/KEGS/043417//FTNC/ (2824819446449801) | 6027012 | 5500 | PVC ID : 6027012 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64740 PE IP Address : 68.139.76.229 CE Address : 68.139.76.230 QoS - Egress Profile: R12 | 100Base-TX (28248194) | 100Base-TX (28248194) | Ethernet | FRONTIER (2824819446449801) | 01/07/2019 (2824819446449801) | 02/26/2019 (2824819446449801) | 02/11/2019 (2824819446449801) | 02/12/2019 (VFORCE) (28248194) | 02/12/2019 (VFORCE) (28248194) | DEMARCDET - FLOOR 1 SL3 SHELF 1 PORT 3 PHYSH 1 POS 3 WALLMOUNTED TAGGED |  | TODD VANDERSCHAEGEN 1-813-629-2611 anderschaegen@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 02/12/2019(Private IP - PIP) 02/12/2019(WAN Analysis Reporting) 02/12/2019(Access) |  |  | 03/07/2019 (28248193) 03/05/2019 (28248194) | 02/04/2019 02/08/2019 | 02/12/2019 |  | Completed | N (28248193) N (28248195) N (28248194) | U0101953 | Jeopardy Notification 1 (01/04/2019) | NSPE0012580775 Order Request # 197784361 | NSPE0012580775
Completed | C1641-04-IM Ashburn, VA | 21635 RED RUM DR ASHBURN, VA 20147-7501 US | 1 GBPS (28293598) | 02/01/2019: Background: Ashburn, VA; Change handoff from MMF to SMF; Single NID Status: Handoff successfully changed. | 197842555 | C1641-02-IM | WAN Analysis Reporting (28293599) Private IP - PIP Access (28293598) | 28293599 28293598 | 800 MBPS |  | 94557016 (WAN Analysis Reporting) 94557014 94557019 (Access) | E5013506/NONE (28293598) | 46.KFGS.304854..CV (2829359842462302) |  |  |  | 1000Base-LX-1310nm (28293598) | 1000Base-LX (1310nm Single Mode Fiber) (28293598) | Ethernet | VERIZON (2829359842462304) VERIZON (2829359842462302) | 01/29/2019 (2829359842462304) 01/09/2019 (2829359842462302) | 01/30/2019 (2829359842462304) 01/28/2019 (2829359842462302) | 01/31/2019 (2829359842462304) |  |  | DEMARCDET - 1st Floor Data Closet Room DC1 RR 2 Unit 15 Tagged |  | Tanu Bah 1-571-474-8531 tanu.bah@ttec.com | DAVID CASANOVA | david_casanova@optum.com | 1-763-744-1589 | 01/31/2019(Access) | 01/31/2019 |  | 02/04/2019 (28293598) | 01/24/2019 (23529899.1) 01/24/2019 | 01/31/2019 |  | Completed Activated/Installed | N (28293599) N N (28293598) | U0101953 |  | Order Request # 197842683 Change handoff from MMF to SMF only. | NSPE0012599955
Completed | AZ086 Tempe, AZ | 1805 N SCOTTSDALE RD TEMPE, AZ 85281-1556 US | 50 MBPS (28293806) | 05/20/2019: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equimpent | 197838909 | AZ086 | Private IP - PIP (28293805) WAN Analysis Reporting (28293807) Access (28293806) | 28293805 28293807 28293806 | 10 MBPS (28293805) |  | 94601683 (Private IP (PIP)) 94601679 (WAN Analysis Reporting) 94601681 (Access) | C4015439/ADD (28293805) E4040076/ADD (28293806) | 19.KXGS.374499..MS (2829380649755601) | 6028842 | 5500 | PVC ID : 6028842 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64802 PE IP Address : 159.24.177.249 CE Address : 159.24.177.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28293806) | 1000Base-SX (850nm, Multi Mode Fiber) (28293806) | Ethernet | CENTURYLINK (2829380649755601) | 05/15/2019 (2829380649755601) | 05/20/2019 (2829380649755601) | 05/20/2019 (2829380649755601) | 05/23/2019 (VFORCE) (28293806) | 05/23/2019 (VFORCE) (28293806) | DEMARCDET - X |  | Scott Fyffe 1-818-967-7640 Scott.Fyffe@am.jll.com | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 05/23/2019(Private IP - PIP) 05/23/2019(WAN Analysis Reporting) 05/23/2019(Access) |  |  | 05/30/2019 (28293805) 05/28/2019 (28293806) | 06/25/2019 07/01/2019 | 05/23/2019 |  | Completed | N (28293805) N (28293807) N (28293806) | U0101953 | Jeopardy Notification 1 (05/14/2019) | NSPE0012598686 Order Request # 197838857 | NSPE0012598686
Completed | VA732 Ashburn, VA | 44245 GIGABIT PLZ ASHBURN, VA 20147 US | 1 GBPS (28314406) | 01/10/2019: Your order is on track: Request sent to the Local Exchange Carrier (LEC) CHESAPEAKE AND POTOMAC BELL (MD WV) on Jan 4, 2019, waiting for Firm Order Confirmation (FOC) of circuit delivery. | 197844969 | VA732 | WAN Analysis Reporting (28314407) Access (28314406) Private IP - PIP (28314405) | 28314407 28314406 28314405 | 300 MBPS (28314405) |  | 94602533 (WAN Analysis Reporting) 94602537 (Access) 94602535 (Private IP (PIP)) | C0159304/ADD (28314405) E5015844/ADD (28314406) | 46.KFGS.305275..CV (2831440649779701) | 6029471 | 180000 | PVC ID : 6029471 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64566 PE IP Address : 152.181.73.193 CE Address : 152.181.73.194 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (28314406) | 1000Base-LX (1310nm Single Mode Fiber) (28314406) | Ethernet | VERIZON (2831440649779701) | 01/04/2019 (2831440649779701) | 01/14/2019 (2831440649779701) | 01/11/2019 (2831440649779701) |  |  | DEMARCADDR - 44245 GIGABIT PLZ, ASHBURN, VA DEMARCDET - DATA CENTER 1ST FLOOR ROOM MMR RR A.2 UNIT 4 EXT TO PANEL 1 |  | Craig Mcphadeun 1-703-773-6305 c.mcphaden@ntta.com | EDWARD JONES | edward.jones@optum.com | 1-719-425-4044 | 01/11/2019(WAN Analysis Reporting) 01/11/2019(Access) 01/11/2019(Private IP - PIP) |  |  | 01/24/2019 (28314405) 01/22/2019 (28314406) | 02/13/2019 02/07/2019 | 01/11/2019 |  | Completed | N (28314407) N (28314406) N (28314405) | U0101953 |  | NSPE0012600734 Order Request # 197844845 | NSPE0012600734
Completed | TX446 Wellmed Lakeway, TX | 1921 LOHMANS CROSSING RD STE 150 LAKEWAY, TX 78734-5280 US | 50 MBPS (28307854) | 02/28/2019: 2/28Background: TX446 Wellmed Lakeway, TX; New 10M/50M PIP-Ethernet; (TWC) Dual NID; No MNS; ENID Status: Ready for activation once customer completes their internal cabling Next action: Customer | 197852653 | TX446 Wellmed | Private IP - PIP (28307853) WAN Analysis Reporting (28307855) Access (28307854) | 28307853 28307855 28307854 | 10 MBPS (28307853) |  | 94602582 (Private IP (PIP)) 94602580 (WAN Analysis Reporting) 94602584 (Access) | C4015462/ADD (28307853) E4040120/ADD (28307854) | 51.L1XX.802503..TWCC (2830785448115401) | 6029206 | 5500 | PVC ID : 6029206 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64689 PE IP Address : 152.162.13.165 CE Address : 152.162.13.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28307854) | 1000Base-SX (850nm, Multi Mode Fiber) (28307854) | Ethernet | TIME WARNER CABLE (2830785448115401) | 02/18/2019 (2830785448115401) | 03/04/2019 (2830785448115401) | 02/25/2019 (2830785448115401) | 02/27/2019 (VFORCE) (28307854) | 02/27/2019 (VFORCE) (28307854) | DEMARCADDR - . DEMARCDET - CPE is installed in the 1st floor electrical room in the rack with MTU rad 203 port 5 |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 02/27/2019(Private IP - PIP) 02/27/2019(WAN Analysis Reporting) 02/27/2019(Access) |  |  | 03/13/2019 (28307853) 03/11/2019 (28307854) | 03/13/2019 03/19/2019 | 02/27/2019 |  | Completed | N (28307853) N (28307855) N (28307854) | U0101953 | Jeopardy Notification 1 (02/18/2019) | NSPE0012604297 Order Request # 197852597 | NSPE0012604297
Completed | TX423-01-IM Floresville, TX | 100 WILSON DR FLORESVILLE, TX 78114 US | 50 MBPS (28309088) | 04/24/2019: 4/24Background: TX423-01-IM Floresville, TX; New 10M/50M PIP-Ethernet; (TWC) Dual NID; No MNS; Status: Foc 5/17-Permits received; Construction complete; Install date is for 4/25 Next action: Loop Delivery//BEAS installation | 197855283 | TX423-01-IM | WAN Analysis Reporting (28309089) Access (28309088) Private IP - PIP (28309087) | 28309089 28309088 28309087 | 10 MBPS (28309087) |  | 308412903 (WAN Analysis Reporting) 308412885 (Access) 308412891 (Private IP (PIP)) | C4015470/ADD (28309087) E4040132/ADD (28309088) | 83.L1XX.004888..TWCC (2830908845680601) | 6029243 | 5500 | PVC ID : 6029243 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64724 PE IP Address : 152.162.51.85 CE Address : 152.162.51.86 QoS - Egress Profile: R12 | 100Base-TX (28309088) | 100Base-FX (1310nm, Multi Mode Fiber) (28309088) | Ethernet | TIME WARNER CABLE (2830908845680601) | 01/30/2019 (2830908845680601) | 05/17/2019 (2830908845680601) | 04/26/2019 (2830908845680601) | 04/30/2019 (VFORCE) (28309088) | 04/30/2019 (VFORCE) (28309088) | DEMARCDET - 1st FL IT Rm wall mounted |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 04/30/2019(WAN Analysis Reporting) 04/30/2019(Access) 04/30/2019(Private IP - PIP) |  |  | 05/29/2019 (28309087) 05/24/2019 (28309088) | 06/21/2019 06/17/2019 | 04/30/2019 |  | Completed | N (28309089) N (28309088) N (28309087) | U0101953 | Jeopardy Notification 1 (01/23/2019) | NSPE0012605143 Order Request # 197854927 | NSPE0012605143
Completed | VA074 Falls Church, VA | 3160 FAIRVIEW PARK DR FALLS CHURCH, VA 22042-4516 US | 50 MBPS |  | 197869313 | VA074-02-IM | WAN Analysis Reporting (28320460) Private IP - PIP (28320458) Access | 28320460 28320458 | 20 MBPS (28320458) |  | 94539906 (WAN Analysis Reporting) 94539900 (Private IP (PIP)) 94539903 | C4013444/NONE (28320458) |  | 5993918 | 10000 | PVC ID : 5993918 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64800 PE IP Address : 199.220.117.61 CE Address : 199.220.117.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Susan Wagner 1-763-744-0632 susan_l_wagner@optum.com | Susan Wagner | susan_l_wagner@optum.com | 1-763-744-0632 | 01/07/2019(Private IP | 01/04/2019 |  | 01/04/2019 (28320458) | 01/15/2019 (23192299.4) 01/15/2019 | 01/07/2019 |  | Completed Activated/Installed | N (28320460) N (28320458) N | U0161525 |  | NSPE0012609409 Order Request # 197868859 | NSPE0012609409
Completed | TX450 Dallas, TX | 2301 S HAMPTON RD STE 900 DALLAS, TX 75224-1677 US | 50 MBPS (28336668) | 06/27/2019 Successfully activated | 197889199 | TX450 | Private IP - PIP (28336667) WAN Analysis Reporting (28336669) Access (28336668) | 28336667 28336669 28336668 | 10 MBPS (28336667) |  | 94603802 (Private IP (PIP)) 94603198 (WAN Analysis Reporting) 94603800 (Access) | C4015524/ADD (28336667) E4040278/ADD (28336668) | 21.L1XX.124372..TWCC (2833666850073701) | 6030222 | 5500 | PVC ID : 6030222 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64512 PE IP Address : 152.181.74.237 CE Address : 152.181.74.238 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28336668) | 1000Base-SX (850nm, Multi Mode Fiber) (28336668) | Ethernet | TIME WARNER CABLE (2833666850073701) | 01/08/2019 (2833666850073701) | 02/15/2019 (2833666850073701) | 02/01/2019 (2833666850073701) | 02/06/2019 (VFORCE) (28336668) | 02/06/2019 (VFORCE) (28336668) | DEMARCDET - RAD r80 EXT203 customer port 5 office no 900 ser rack near rack no 12 wit lateral running MPOFTP next back exit |  | Kristina Nyiri 1-210-850-6272 knyiri@wellmed.net | Laeeq Sajjad | Laeeq_sajjad@optum.com | 1-312-617-5537 | 02/06/2019(Private IP - PIP) 02/06/2019(WAN Analysis Reporting) 02/06/2019(Access) | 06/27/2019 |  | 02/06/2019 (28336667) 02/04/2019 (28336668) | 02/18/2019 02/22/2019 | 02/06/2019 |  | Completed | N (28336667) N (28336669) N (28336668) | U0101953 |  | NSPE0012616484 Order Request # 197889173 | NSPE0012616484
Completed | IL043 Schaumburg, IL | 1600 MCCONNOR PKWY SCHAUMBURG, IL 60173-6801 US | 500 MBPS | 01/28/2019: Background: Change QOS to R12, GCAR to 140M, Tagged to untagged Status: Changes deployed. | 197890699 | IL043-02-IJ Catamaran Schaumburg | Private IP - PIP (28336734) Access WAN Analysis Reporting (28336736) | 28336734 28336736 | 300 MBPS (28336734) |  | 94552643 (Private IP (PIP)) 94552645 94552647 (WAN Analysis Reporting) | C5005713/NONE (28336734) |  | 5996304 | 140000 | PVC ID : 5996304 VPN Name : UnitedHealthGroup Router Name : DNG9E03 VRF Name : Vc53414:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64791 PE IP Address : 152.177.168.221 CE Address : 152.177.168.222 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Melissa Chapman Melissa Chapman 1-176-374-4211 melissa_r_chapman@optum.com | CLIFFORD REMIGIO | clifford_remigio@optum.com | 1-763-744-2114 | 01/26/2019(Private IP | 01/25/2019 |  | 01/10/2019 (28336734) | 01/21/2019 01/21/2019 (10854977.5) | 01/26/2019 |  | Completed Activated/Installed | N (28336734) N N (28336736) | U0101953 |  | NSPE0012616053 Order Request # 197887853 | NSPE0012616053
Completed | UVA01-07-CM Richmond, VA | 9020 STONY POINT PKWY RICHMOND, VA 23235-1947 US | 100 MBPS | 01/10/2019: 1/10Background: UVA01-07-CM Richmond, VA; Configuration changes Status: Hotcut 01/12/2019 10:30PM CST Next action: Order closure | 197899241 | UVA01-05-IJ Richmond | Private IP - PIP (28343565) Access | 28343565 | 10 MBPS (28343565) |  | 115870299 (Private IP (PIP)) 115870297 | C1036352/NONE (28343565) |  | 5748573 | 25000 | PVC ID : 5748573 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64623 PE IP Address : 152.161.56.21 CE Address : 152.161.56.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Jaki Davis-Carter 1-804-267-5217 jaki_daviscarter@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 01/14/2019(Private IP | 01/11/2019 |  | 01/09/2019 (28343565) | 01/18/2019 | 01/14/2019 |  |  | N (28343565) N | U0101953 |  | NSPE0012616977 Order Request # 197891331 | NSPE0012616977
Completed | Optum Insight, Washington,DC | 2445 M ST NW WASHINGTON, DC 20037-1435 US | 500 MBPS (28498326) | 02/06/2019: Your order is on track: Verizon has received a Firm Order Confirmation (FOC) Date for your telco access delivery for Feb 8, 2019 CHESAPEAKE AND POTOMAC BELL (MD WV) - pending loop acceptance | 197900837 | Optum Insight | Private IP - PIP (28498325) WAN Analysis Reporting (28498327) Access (28498326) | 28498325 28498327 28498326 | 300 MBPS (28498325) |  | 94604402 (Private IP (PIP)) 94604408 (WAN Analysis Reporting) 94604404 (Access) | C5006804/ADD (28498325) E5016356/ADD (28498326) | 36.KFGS.309749..CD (2849832633958001) | 6035970 6035971 | 250000 | PVC ID : 6035970,6035971 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65105 PE IP Address : 152.164.112.13 CE Address : 152.164.112.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28498326) | 1000Base-SX (850nm, Multi Mode Fiber) (28498326) | Ethernet | VERIZON (2849832633958001) | 02/01/2019 (2849832633958001) | 02/08/2019 (2849832633958001) | 02/08/2019 (2849832633958001) |  |  | DEMARCADDR - 2445 M ST NW, WASHINGTON, DC DEMARCDET - C1 LEVEL MTR RR 1 SH 14 |  | Ethen Harris 1-202-568-7164 HarrisE@advisory.com | CLIFFORD REMIGIO | clifford_remigio@optum.com | 1-612-790-6518 | 02/08/2019(Private IP - PIP) 02/08/2019(WAN Analysis Reporting) 02/08/2019(Access) |  |  | 02/19/2019 (28498325) 02/15/2019 (28498326) | 02/28/2019 03/06/2019 | 02/08/2019 | 02/01/2019 (28498325) | Completed | N (28498325) N (28498327) N (28498326) | U0101953 |  | NSPE0012619108 Order Request # 197899061 | NSPE0012619108
Completed | Elk River, MN; New Wireless PIP Gateway | 14100 BUSINESS CENTER DR NW ELK RIVER, MN 55330-4654 US |  | 01/16/2019: Order complete | 197917453 | UNITED HEALTHCARE SERVICES | Private IP Gateways (28360597) | 28360597 | 10 MBPS |  | 307144355 (Private IP Gateways) | MB000681/ADD (28360597) MP000681/ADD (28360597) |  | 6031023 6031022 | 5000 | PVC ID : 6031023,6031022 Router Name : DNGXE01,MWAGE03 VRF Name : Vc98166-UHGCellular,Vc98513:UHGCellular Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 6167 PE IP Address : v4-152.187.108.165,v6-68.137.232.89 CE Address : v4-152.187.108.166,v6-68.137.232.90 QoS - Egress Profile: R12 | [11 empty] | DANIEL BARTLETT 1-763-744-1815 daniel_l_bartlett@optum.com | DANIEL BARTLETT | daniel_l_bartlett@optum.com | 1-763-744-1815 | 01/16/2019(Private IP Gateways) |  |  | 01/17/2019 (28360597) | 01/24/2019 | 01/16/2019 |  |  | N (28360597) | U0101953 |  | NSPE0012624550 Order Request # 197916745 | NSPE0012624550
Completed | NJ777-13-IM Equinix Data Center Secaucus Rd, NJ | 755 SECAUCUS RD SECAUCUS, NJ 07094-2511 US | 10 GBPS (28367884) | 03/05/2019: Background: NJ777-13-IM Equinix Data Center Secaucus Rd, NJ; New 2G/10G Internet Burstable; (VzB); Single NID; No MNS Status: Ready for Activation Next action: Customer to provide activation date and time allowing 3 business days advance notice. | 197925953 | NJ777-03-IJ Equinix Internet | Internet Dedicated Services (28367883) Access (28367884) | 28367883 28367884 | 10 GBPS (28367883) |  | 303422229 (Internet Dedicated Services) 303422225 (Access) | C0160169/ADD (28367883) E7000874/ADD (28367884) |  | 6031246 | 0 | PVC ID : 6031246 VPN Name : Internet Router Name : GW12EWR6 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 10879 PE IP Address : 152.193.15.213 CE Address : 152.193.15.214 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (28367884) | Ethernet | [5 empty] | 02/15/2019 (CCP) (28367883) 02/15/2019 (CCP) (28367884) |  |  | ALAN KROTH 1-952-833-7895 alan@optum.com | EMAD BHATT | emad@optum.com | 91-804-670-4757 | 03/05/2019(Internet Dedicated Services) 03/05/2019(Access) |  |  | 03/22/2019 (28367883) 03/20/2019 (28367884) | 03/01/2019 | 03/05/2019 |  |  | N (28367883) N (28367884) | U0101953 | Jeopardy Notification 1 (01/16/2019) | NSPE0012626521Order Request # 197923723 | NSPE0012626521
Completed | ID011-02-IM Boise, ID | 322 E FRONT ST BOISE, ID 83702-7374 US | 50 MBPS (28402529) | 06/17/2019 Successfully activated | 197962821 | ID011-02-IM | Private IP - PIP (28402528) WAN Analysis Reporting (28402530) Access (28402529) | 28402528 28402530 28402529 | 20 MBPS (28402528) |  | 94607135 (Private IP (PIP)) 94607141 (WAN Analysis Reporting) 94607137 (Access) | C4015641/ADD (28402528) E4040606/ADD (28402529) | ETYX/238720//ZYO (2840252950565301) | 6032135 | 13000 | PVC ID : 6032135 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65106 PE IP Address : 68.136.12.221 CE Address : 68.136.12.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28402529) | 1000Base-SX (850nm, Multi Mode Fiber) (28402529) | Ethernet | INTEGRA (2840252950565301) | 05/01/2019 (2840252950565301) | 06/06/2019 (2840252950565301) | 06/06/2019 (2840252950565301) | 06/10/2019 (VFORCE) (28402529) | 06/10/2019 (VFORCE) (28402529) | DEMARCDET - 4TH FLR RM 467 DISTRIBUTION FRAME SOUTH RR 2 MP 151 |  | Aaron Delabr 1-815-258-3716 aaron_delabre@uhg.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 06/10/2019(Private IP - PIP) 06/10/2019(WAN Analysis Reporting) 06/10/2019(Access) | 06/17/2019 |  | 06/17/2019 (28402528) 06/13/2019 (28402529) | 07/12/2019 07/18/2019 | 06/10/2019 |  | Completed | N (28402528) N (28402530) N (28402529) | U0101953 | Jeopardy Notification 1 (05/29/2019) | NSPE0012636232 Order Request # 197961937 | NSPE0012636232
Completed | GA722 MedExpres Atlanta, GA | 1033 JEFFERSON ST NW ATLANTA, GA 30318-8024 US | 100 MBPS (28403635) | 02/22/2019: Background: GA722 MedExpres Atlanta, GA; New 100M/100M PIP-Eth; (VzB); Dual NID; No MNS; Status: Ready for activation Telco Circuit ID: ea-h17t-h17t-0127 / E4040614 Demarcation: Floor(FL) 1, Room MMR 3E1 at ISG400 Aisle 100. Bay 7. Shelf 7E. Slot/port: 0.1 Slot.P | 197963689 | MedExpres Atlanta GA722 | WAN Analysis Reporting (28403636) Access (28403635) Private IP - PIP (28403634) | 28403636 28403635 28403634 | 100 MBPS (28403634) |  | 94606579 (WAN Analysis Reporting) 94606575 (Access) 94606573 (Private IP (PIP)) | C1084499/ADD (28403634) E4040614/ADD (28403635) |  | 6032181 | 90000 | PVC ID : 6032181 VPN Name : UHG-MedExpress Router Name : CPZXE03 VRF Name : Vd07318-UHGMedExpress Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 1 PE IP Address : 152.187.14.189 CE Address : 152.187.14.190 QoS - Egress Profile: R12 |  | 100Base-FX (1310nm, Single Mode Fiber) (28403635) | Ethernet |  |  |  |  | 02/11/2019 (CCP) (28403634) 02/11/2019 (CCP) (28403635) | 02/15/2019 (CCP) (28403634) 02/15/2019 (CCP) (28403635) |  |  | Doug Spencer 1-440-817-0322 douglas.spencer@gdt.com | Doug Spencer | douglas.spencer@gdt.com | 1-440-817-0322 | 02/21/2019(WAN Analysis Reporting) 02/21/2019(Access) 02/21/2019(Private IP - PIP) |  |  | 03/11/2019 (28403634) 03/07/2019 (28403635) | 03/05/2019 02/27/2019 | 02/21/2019 |  | Completed | N (28403636) N (28403635) N (28403634) | U0101953 |  | NSPE0012636523 Order Request # 197962965 | NSPE0012636523
Completed | GA777-16-IM Atlanta, GA | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 04/30/2019: Activation scheduled 05/02/2019 2300 CST | 197971793 | Equinix hub Atlanta Peachtree GA777-04-IJ | Internet Dedicated Services (28411242) Access (28411243) | 28411242 28411243 | 10 GBPS (28411242) |  | 309416063 (Internet Dedicated Services) 309416059 (Access) | C1084961/ADD (28411242) E7000878/ADD (28411243) | jx8hk 0xd 0004 (I0091070.ATL) jx8hk 25u 0001 (I0090961.ATL) | 6032508 | 0 | PVC ID : 6032508 VPN Name : Internet Router Name : GW4ATL4 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 10879 PE IP Address : 152.179.152.21 CE Address : 152.179.152.22 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (28411243) | Ethernet | [8 empty] | ALAN KROTH 1-952-833-7895 alan@optum.com | EMAD BHATT | emad@optum.com | 91-804-670-4757 | 02/28/2019(Internet Dedicated Services) 02/28/2019(Access) | 05/02/2019 |  | 03/07/2019 (28411242) 03/07/2019 (28411243) | 03/19/2019 | 02/28/2019 |  |  | N (28411242) N (28411243) | U0101953 |  | NSPE0012636730 Order Request # 197963647 | NSPE0012636730
Completed | AL013-05-CM Montgomery, AL | 4525 EXECUTIVE PARK DR MONTGOMERY, AL 36116-1624 US | 100 MBPS | 03/07/2019 Successfully upgraded. | 198006447 | AL013-02-IJ Catamaran Montgomery | Private IP - PIP (28440229) Access | 28440229 | 100 MBPS (28440229) |  | 91514813 (Private IP (PIP)) 91514811 | C1031099/NONE (28440229) |  | 5702926 | 70000 | PVC ID : 5702926 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64806 PE IP Address : 68.136.248.221 CE Address : 68.136.248.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Susan Wagner 1-763-744-0632 susan_l_wagner@optum.com | Susan Wagner | susan_l_wagner@optum.com | 1-763-744-0632 | 03/08/2019(Private IP | 03/07/2019 |  | 01/24/2019 (28440229) | 02/04/2019 | 03/08/2019 |  |  | N (28440229) N | U0101953 |  | NSPE0012649155 Order Request # 198006339 | NSPE0012649155
Completed | NY165-01-IJ Lake Success, NY | 7 VERMONT DR NEW HYDE PARK, NY 11042-1128 US | 1 GBPS (28469303) | 04/23/2019: 04/22 Activated | 198008665 | NY165-01-IJ Lake Success NY | Private IP - PIP (28469302) WAN Analysis Reporting (28469304) Access (28469303) | 28469302 28469304 28469303 | 1 GBPS (28469302) |  | 94610566 (Private IP (PIP)) 94610569 (WAN Analysis Reporting) 94610564 (Access) | C0160725/ADD (28469302) E5016276/ADD (28469303) | 32.KFGS.218370..NY (2846930374361001) | 6034804 | 700000 | PVC ID : 6034804 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65108 PE IP Address : 208.220.221.213 CE Address : 208.220.221.214 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (28469303) | 1000Base-LX (1310nm Single Mode Fiber) (28469303) | Ethernet | VERIZON (2846930374361001) | 01/30/2019 (2846930374361001) | 03/05/2019 (2846930374361001) | 02/14/2019 (2846930374361001) |  |  | DEMARCADDR - 7 DELAWARE DR NEW HYDE PARK NY DEMARCDET - NA |  | Kyle Little 1-516-608-6882 klittle@prohealthcare.com | RANJI ADHIKARI | ranjit_adhikari@optum.com | 1-763-744-1957 | 02/14/2019(Private IP - PIP) 02/14/2019(WAN Analysis Reporting) 02/14/2019(Access) | 04/22/2019 |  | 03/14/2019 (28469302) 03/12/2019 (28469303) | 03/22/2019 03/28/2019 | 02/14/2019 |  | Completed | N (28469302) N (28469304) N (28469303) | U0101953 |  | NSPE0012649778 Order Request # 198008653 | NSPE0012649778
Completed | DC007-04-IM Optum Insight; Washington, DC | 655 NEW YORK AVE NW WASHINGTON, DC 20001-3626 US | 100 MBPS (28506429) | 03/15/2019: 3/15Background: DC007-04-IM Optum Insight; Washington, DC; New 100M/100M IDS; (VzT) Single NID; No MNS; Status: Loop Delivered 3/14 - Ready for activation Next action: Ready for activation Who owns the next action: OM | 198043195 | DC007-02-IM Optum Insight. | Internet Dedicated Services (28506428) Access (28506429) | 28506428 28506429 | 100 MBPS (28506428) |  | 310623471 (Internet Dedicated Services) 310623467 (Access) | C1085101/ADD (28506428) E4041269/ADD (28506429) | 36.KEGS.325944..CD (2850642938707301) | 6036315 | 0 | PVC ID : 6036315 VPN Name : Internet Router Name : GW5DCA5 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.109.93 CE Address : 204.148.109.94 | 100Base-TX (28506429) | 100Base-TX (28506429) | Ethernet | VERIZON (2850642938707301) | 02/05/2019 (2850642938707301) | 03/19/2019 (2850642938707301) | 03/14/2019 (2850642938707301) |  |  | DEMARCDET - p1 garage level, mtr rack mounted , Verizon rack |  | KATIE MALONEY 1-617-852-7976 katharine_maloney@uhg.com | SAHIL TUTEJA | sahil_tuteja@optum.com | 91-828-567-0647 | 03/14/2019(Internet Dedicated Services) 03/14/2019(Access) |  |  | 03/28/2019 (28506428) 03/26/2019 (28506429) | 03/27/2019 | 03/14/2019 |  |  | N (28506428) N (28506429) | U0101953 |  | NSPE0012658965 Order Request # 198039207 | NSPE0012658965
Completed | CA269-04-IM Irwindale, CA | 4900 RIVERGRADE RD STE E100 IRWINDALE, CA 91706-1401 US | 50 MBPS | 02/25/2019 - Hotcut successful. | 198053967 | Optum RX | Private IP - PIP (28488238) Access WAN Analysis Reporting (28488240) | 28488238 28488240 | 50 MBPS (28488238) |  | 222974307 (Private IP (PIP)) 222974305 222974308 (WAN Analysis Reporting) | C4011458/NONE (28488238) |  | 5973390 | 30000 | PVC ID : 5973390 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65092 PE IP Address : 206.115.117.165 CE Address : 206.115.117.166 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | PAUL KELSEY 1-949-929-9934 paul.kelsey@am.jll.com | JASON SALAPING | jason_salaping@gmail.com | 1-210-862-6784 | 02/26/2019(Private IP | 02/25/2019 |  | 01/31/2019 (28488238) | 02/11/2019 02/11/2019 (21532987.2) | 02/26/2019 |  | Completed Activated/Installed | N (28488238) N N (28488240) | U0101953 |  | NSPE0012661653 Order Request # 198048411 | NSPE0012661653
Completed | FL070-05-IJ Jacksonville, FL | 7159 CORKLAN DR JACKSONVILLE, FL 32258-4455 US | 250 MBPS | 02/18/2019: 02/15 Successfully upgraded to 200M Port Speed and 110m GCAR. | 198058079 | FL070-05-IJ Jacksonville | Private IP - PIP (28490719) Access | 28490719 | 200 MBPS (28490719) |  | 92297424 (Private IP (PIP)) 92297422 | C0073686/NONE (28490719) |  | 5703375 | 110000 | PVC ID : 5703375 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65031 PE IP Address : 152.185.180.117 CE Address : 152.185.180.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | SUSAN WAGNER 1-763-744-0632 susan_l_wagner@optum.com | SUSAN WAGNER | susan_l_wagner@optum.com | 1-763-744-0632 | 02/15/2019(Private IP |  |  | 01/31/2019 (28490719) | 02/11/2019 | 02/15/2019 |  |  | N (28490719) N | U0101953 |  | NSPE0012664601 Order Request # 198057721 | NSPE0012664601
Completed | TX436-02-IM Austin, TX | 2200 PARK BEND DR STE 300 AUSTIN, TX 78758-5386 US | 50 MBPS (28540504) | 08/01/2019: Approved for ENID | 198123815 | TX436-02-IM | Private IP - PIP (28540503) WAN Analysis Reporting (28540505) Access (28540504) | 28540503 28540505 28540504 | 10 MBPS (28540503) |  | 94613250 (Private IP (PIP)) 94613253 (WAN Analysis Reporting) 94613255 (Access) | C4015961/ADD (28540503) E4041449/ADD (28540504) | TX/KXFN/125864/LVLC (2854050446076201) | 6037214 | 5500 | PVC ID : 6037214 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64579 PE IP Address : 68.139.21.229 CE Address : 68.139.21.230 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (28540504) | 1000Base-LX (1310nm Single Mode Fiber) (28540504) | Ethernet | LEVEL 3 (2854050446076201) | 02/20/2019 (2854050446076201) | 08/22/2019 (2854050446076201) | 07/31/2019 (2854050446076201) | 08/01/2019 (VFORCE) (28540504) | 08/01/2019 (VFORCE) (28540504) | DEMARCDET - X |  | JASON Ozer 1-210-951-3251 jozer@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 08/01/2019(Private IP - PIP) 08/01/2019(WAN Analysis Reporting) 08/01/2019(Access) |  |  | 09/03/2019 (28540503) 08/29/2019 (28540504) | 08/21/2019 08/27/2019 | 08/01/2019 |  | Completed | N (28540503) N (28540505) N (28540504) | U0101953 |  | NSPE0012679622 Order Request # 198123795 | NSPE0012679622
Completed | Equinix Internet Bustable Los Angeles, CA | 600 W 7TH ST FL 6 LOS ANGELES, CA 90017-3859 US |  | 08/08/2019 - Activation needs to be rescheduled due to VLAN tagging issue on customer end. | 198135041 | Equinix Internet Los Angeles | Internet Dedicated Services (28553132) Access (28553133) | 28553132 28553133 | 10 GBPS (28553132) |  | 319582979 (Internet Dedicated Services) 319582975 (Access) | C0162782/ADD (28553132) E7000931/ADD (28553133) | fs7um 7um 0012 (I0151456.LSA) | 6040333 | 0 | PVC ID : 6040333 VPN Name : Internet Router Name : GW8LAX15 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 10879 PE IP Address : 157.130.245.21 CE Address : 157.130.245.22 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (28553133) | Ethernet | [8 empty] | EMAD BHATT 91-804-670-4757 emad@optum.com | EMAD BHATT | emad@optum.com | 91-804-670-4757 | 03/11/2019(Internet Dedicated Services) 03/11/2019(Access) |  |  | 03/08/2019 (28553132) 03/08/2019 (28553133) | 03/07/2019 | 03/11/2019 | 02/27/2019 (28553133) |  | N (28553132) N (28553133) | U0101953 |  | NSPE0012681711 Order Request # 198130967 | NSPE0012681711
Completed | PIPO Change | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 4000 MBPS (CQBLPPW2) |  | 9815520 |  | Private IP Port Only (CQBLPPW2) EVC/PVC Service (N.11938490.6037433) | CQBLPPW2 N.11938490.6037433 | 4000 MBPS | P2198241 |  | BOBLC5XS0001 (CQBLPPW2) |  | 6037433 | 72000 | VPN Name : UHG-SDWAN Router Name : MN39E01 VRF Name : Vd76602:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.164.75.1 CE Address : 152.164.75.2 QoS - Egress Profile: R12 PVC ID : 6037433 | [11 empty] | MELISSA CHAPMAN TIM GUNDERSON 0015072950001 7637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 02/28/2019 (CQBLPPW2) |  |  | 03/06/2019 (CQBLPPW2) | 03/06/2019 (CQBLPPW2) |  |  |  | N (CQBLPPW2) N (N.11938490.6037433) | 05017789 P2198241 |  |  | NSPE0012683057
Completed | TX47 Hurst, TX | 466 MID CITIES BLVD HURST, TX 76054-2430 US | 50 MBPS (28610598) | 10/31/2019: 10/31Background: TX47 Hurst, TX; New 10M/50M PIP-Eth; (Charter); 100BD offnet build Status:Beas installed 10/31 > handoff corrected 10/30 > pending access Next action: Order complettion Who owns the next action: prov/ bne | 198147381 | TX474 | Private IP - PIP (28610597) WAN Analysis Reporting (28610599) Access (28610598) | 28610597 28610599 28610598 | 10 MBPS (28610597) |  | 94614970 (Private IP (PIP)) 94614975 (WAN Analysis Reporting) 94614968 (Access) | C4016122/ADD (28610597) E4041809/ADD (28610598) | 81.L1XX.881778..TWCC (2861059851927301) | 6039839 | 5500 | PVC ID : 6039839 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65174 PE IP Address : 152.192.45.253 CE Address : 152.192.45.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28610598) | 1000Base-SX (850nm, Multi Mode Fiber) (28610598) | Ethernet | CHARTER (2861059851927301) | 02/20/2019 (2861059851927301) | 07/01/2019 (2861059851927301) | 10/14/2019 (2861059851927301) | 11/01/2019 (VFORCE) (28610598) | 10/31/2019 (VFORCE) (28610598) | DEMARCDET - wall mounted inside data rm in back of doctors personal office |  | KEVIN MCCORMICK 1-952-833-6179 kevin.mccormick@optum.com | CLIFFORD REMIGIO | clifford_remigio@gmail.com | 1-763-744-2114 | 10/31/2019(Private IP - PIP) 10/31/2019(WAN Analysis Reporting) 10/31/2019(Access) |  |  | 10/16/2019 (28610597) 10/14/2019 (28610598) | 11/01/2019 11/07/2019 | 10/31/2019 |  | Completed | N (28610597) N (28610599) N (28610598) | U0101953 | Jeopardy Notification 3 (10/29/2019) | NSPE0012688596 OR 198147337 | NSPE0012688596
Completed | TX720 Dallas, TX; Change | 1950 N STEMMONS FWY STE 1070 DALLAS, TX 75207-3134 US | 500 MBPS | 02/20/2019: 2/20Background: TX720-02-IJ Dallas, TX; Change AS # 64795 and GCAR to 180mg; Status:Activation complete Next action: order complete | 198165395 | TX720-02-IJ | Private IP - PIP (28584364) Access WAN Analysis Reporting (28584366) | 28584364 28584366 | 300 MBPS (28584364) |  | 151199285 (Private IP (PIP)) 151199283 151199286 (WAN Analysis Reporting) | C5002789/NONE (28584364) |  | 5830521 | 180000 | PVC ID : 5830521 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64795 PE IP Address : 68.137.1.21 CE Address : 68.137.1.22 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Arvin Manalo 1-817-514-5999 arvin.manalo@usmd.com | RANJI ADHIKAI | ranjit_adhikari@optum.com | 1-763-744-1957 | 02/19/2019(Private IP | 02/18/2019 |  | 02/15/2019 (28584364) | 02/22/2019 02/22/2019 (15982195.1) | 02/19/2019 |  | Completed Activated/Installed | N (28584364) N N (28584366) | U0101953 |  | NSPE0012691980 Order Request # 198158241 | NSPE0012691980
Completed | NV124-05-IM Las Vegas, NV | 4090 W CRAIG RD NORTH LAS VEGAS, NV 89032 USA | 1.536 MBPS (IQBLPTBN) | 03/01/2019: Background: NV124-05-IM Las Vegas, NV; New 7xT1; (Centruy Link); Single NID; No MNS Status: Ready for plug and play DEMARC INFO: BCBLDP6Y0001 Customer Contact Phone: 7028775081 DEMARC LOC: 1st flr main telco rm, slot 5/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: A 101 T3Z 13 X4 ========== BCBLDP6Y0002 DEMARC LOC: 1st flr main telco rm, slot 6/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 23 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0003 DEMARC LOC: 1st flr main telco rm, slot 7/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 24 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0004 DEMARC LOC: 1st flr main telco rm, slot 8/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 25 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0005 DEMARC LOC: 1st flr main telco rm, slot 9/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 26 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0006 DEMARC LOC: 1st flr main telco rm, slot 10/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 27 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y00027 DEMARC LOC: 1st flr main telco rm, slot 11/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 28 LSVGNVXBW53 LSVGNVXHHM9 03/01/2019: Background: NV124-05-IM Las Vegas, NV; New 7xT1; (Centruy Link); Single NID; No MNS Status: Ready for plug and play DEMARC INFO: BCBLDP6Y0001 Customer Contact Phone: 7028775081 DEMARC LOC: 1st flr main telco rm, slot 5/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: A 101 T3Z 13 X4 ========== BCBLDP6Y0002 DEMARC LOC: 1st flr main telco rm, slot 6/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 23 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0003 DEMARC LOC: 1st flr main telco rm, slot 7/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 24 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0004 DEMARC LOC: 1st flr main telco rm, slot 8/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 25 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0005 DEMARC LOC: 1st flr main telco rm, slot 9/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 26 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0006 DEMARC LOC: 1st flr main telco rm, slot 10/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 2 Pls check order record | 9819259 |  | Private IP (IQBLPTBN) EVC/PVC Service (N.11944056.6039374) | IQBLPTBN N.11944056.6039374 | 10.752 MBPS | P2212512 |  | BCBLDP6Y0001 (IQBLPTBN) BCBLDP6Y0002 (IQBLPTBN) BCBLDP6Y0003 (IQBLPTBN) BCBLDP6Y0004 (IQBLPTBN) BCBLDP6Y0005 (IQBLPTBN) BCBLDP6Y0006 (IQBLPTBN) BCBLDP6Y0007 (IQBLPTBN) | 53.HCGS.335430..CTRL (IQBLPTBNHH1WMB01) | 6039374 | 7200 | VPN Name : UnitedHealthGroup Router Name : RTOGE04 VRF Name : V471548:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64760 PE IP Address : 68.136.80.157 CE Address : 68.136.80.158 QoS - Egress Profile: R12 PVC ID : 6039374 |  |  |  | CENTURYLINK (IQBLPTBNHH1WMB01) | 02/18/2019 (IQBLPTBNHH1WMB01) | 02/26/2019 (IQBLPTBNHH1WMB01) | 02/27/2019 (IQBLPTBNHH1WMB01) |  |  | DEMARC INFO: BCBLDP6Y0001 Customer Contact Phone: 7028775081 DEMARC LOC: 1st flr main telco rm, slot 5/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: A 101 T3Z 13 X4 ========== BCBLDP6Y0002 DEMARC LOC: 1st flr main telco rm, slot 6/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 23 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0003 DEMARC LOC: 1st flr main telco rm, slot 7/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 24 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0004 DEMARC LOC: 1st flr main telco rm, slot 8/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 25 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0005 DEMARC LOC: 1st flr main telco rm, slot 9/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 26 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y0006 DEMARC LOC: 1st flr main telco rm, slot 10/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 27 LSVGNVXBW53 LSVGNVXHHM9 ========== BCBLDP6Y00027 DEMARC LOC: 1st flr main telco rm, slot 11/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: rj48c DMARC Labeled MCI (Yes or No): yes DMARC Labeled LEC (Yes or No): yes CFA or Tie-down at ACTL: C 101 T3Z 28 LSVGNVXBW53 LSVGNVXHHM9 |  | RON RUBIN 0017028775081 RON.RUBIN@OPTUM.COM |  |  |  | 02/28/2019 (IQBLPTBN) |  |  | 03/05/2019 (IQBLPTBN) | 03/12/2019 (IQBLPTBN) |  |  |  | N (IQBLPTBN) N (N.11944056.6039374) | 05017789 P2212512 |  | NSPE0012694942 CW 198164533 | NSPE0012694942
Completed | UPA04 Medexpress Pittsburg, PA | 2500 ALLEGHENY CENTER MALL STE 138 PITTSBURGH, PA 15212-5303 US | 100 MBPS (28639219) | 04/11/2019: 4/11Background: UPA04 Medexpress Pittsburg, PA; New 100M/100M PIP-Eth; (VzT); Single NID; No MNS; Status: Pending EWO, Escalated to 1st level. EscalationLevel: 1st level Next action: Line testing | 198186011 | UPA04 | Access (28639219) Private IP - PIP (28639218) WAN Analysis Reporting (28639220) | 28639219 28639218 28639220 | 100 MBPS (28639218) |  | 320686359 (Access) 320686363 (Private IP (PIP)) 320686365 (WAN Analysis Reporting) | E4041953/ADD (28639219) C1086793/ADD (28639218) | 15.KFGS.310621..PA (2863921951276801) | 6040617 | 50000 | PVC ID : 6040617 VPN Name : UHG-MedExpress Router Name : PTBXE01 VRF Name : Vd37337-UHGMedExpress Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65242 PE IP Address : 152.187.246.201 CE Address : 152.187.246.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28639219) | 1000Base-SX (850nm, Multi Mode Fiber) (28639219) | Ethernet | VERIZON (2863921951276801) | 02/22/2019 (2863921951276801) | 03/25/2019 (2863921951276801) | 04/15/2019 (2863921951276801) |  |  | DEMARCDET - 1st floor colo rr 01.07.007 pos 5 tagged not ext |  | Thomas Mayernick 1-412-929-5035 Thomas.Mayernik@citynet.net | DOUG SPENCER | douglas.spencer@gdt.com | 1-440-817-0322 | 04/15/2019(Access) 04/15/2019(Private IP - PIP) 04/15/2019(WAN Analysis Reporting) |  |  | 04/01/2019 (28639219) 04/03/2019 (28639218) | 04/02/2019 04/08/2019 | 04/15/2019 |  | Completed | N (28639219) N (28639218) N (28639220) | U0101953 |  | NSPE0012697850 Order Request # 198177589 | NSPE0012697850
Completed |  | 1685 GULF TO BAY BLVD CLEARWATER, FL 33755-6422 US | 50 MBPS |  | 198195689 | FL349-02-IM | Private IP - PIP (28611608) Access WAN Analysis Reporting (28611610) | 28611608 28611610 | 10 MBPS (28611608) |  | 94564033 (Private IP (PIP)) 94564036 94564031 (WAN Analysis Reporting) | C4014037/NONE (28611608) |  | 6002444 | 5000 | PVC ID : 6002444 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64757 PE IP Address : 152.183.208.9 CE Address : 152.183.208.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | TODD VANDERSCHAEGEN 1-813-629-2611 tvanderschaegen@wellmed.net | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 02/20/2019(Private IP | 02/20/2019 |  | 02/18/2019 (28611608) | 02/27/2019 02/27/2019 (23671501.1) | 02/20/2019 |  | Completed Activated/Installed | N (28611608) N N (28611610) | U0101953 |  | Remove VLAN | NSPE0012702346
Completed | KY003 Louisville, KY | 401 S 4TH ST LOUISVILLE, KY 40202-3426 US | 50 MBPS (28622992) | 03/26/2019 03/26/2019 Background: KY003 Louisville, KY; New 20M/50M PIP-Eth; (TWT/Level3); Dual NID; No MNS; ENID Status: Ready for activation once customer internal cabling is complete. Telco Circuit ID: KY/KXFN/129826/LVLC Telco Demarcation: Floor 20 Electrical room wall mounted tagged with circuit ID, CISCO 3600 port # 16 Verizon BEAS Circuit ID: USAKY52382813COV400001 / E4041873 Verizon BEAS Demarcation: 17th floor customer data room. Beasbox is mounted to north wall. Tagged with ckt I'd. Handoff is multi mode fiber LC connector. | 198204647 | KY003 | Private IP - PIP (28622991) WAN Analysis Reporting (28622993) Access (28622992) | 28622991 28622993 28622992 | 20 MBPS (28622991) |  | 94616473 (Private IP (PIP)) 94616476 (WAN Analysis Reporting) 94616478 (Access) | C4016137/ADD (28622991) E4041873/ADD (28622992) | KY/KXFN/129826/LVLC (2862299252382801) | 6040142 | 13000 | PVC ID : 6040142 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65224 PE IP Address : 152.177.244.237 CE Address : 152.177.244.238 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28622992) | 1000Base-SX (850nm, Multi Mode Fiber) (28622992) | Ethernet | LEVEL 3 (2862299252382801) | 02/27/2019 (2862299252382801) | 03/21/2019 (2862299252382801) | 03/22/2019 (2862299252382801) | 03/26/2019 (VFORCE) (28622992) |  | DEMARCDET - X |  | Holly Bracco 1-502-410-0187 holly.bracco@optum360.com | CLIFFORD REMIGIO | clifford_remigio@optum.com | 1-763-744-2114 | 03/26/2019(Private IP - PIP) 03/26/2019(WAN Analysis Reporting) 03/26/2019(Access) |  |  | 04/01/2019 (28622991) 03/28/2019 (28622992) | 04/04/2019 04/10/2019 | 03/26/2019 |  | Completed | N (28622991) N (28622993) N (28622992) | U0101953 |  | NSPE0012705245 Order Request # 198204601 | NSPE0012705245
Completed | TX500-02-IM Garland, TX | 126 N INTERNATIONAL RD STE B GARLAND, TX 75042-6515 US | 50 MBPS (28646658) | 05/14/2019: 5/14Background: TX500-02-IM Garland, TX; New 10M/50M PIP-Eth; (Frontier); Dual NID; No MNS Status: Loop delivered 5/14. Pending BEAS installation; Access confirmed, 8am - 5pm Next action: Line testing | 198231263 | TX500 | WAN Analysis Reporting (28646659) Access (28646658) Private IP - PIP (28646657) | 28646659 28646658 28646657 | 10 MBPS (28646657) |  | 324444965 (WAN Analysis Reporting) 324444959 (Access) 324444963 (Private IP (PIP)) | C4016168/ADD (28646657) E4041979/ADD (28646658) | 13/KFGS/077026//FTNC/ (2864665852539801) | 6040752 | 5500 | PVC ID : 6040752 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64939 PE IP Address : 206.114.92.105 CE Address : 206.114.92.106 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28646658) | 1000Base-SX (850nm, Multi Mode Fiber) (28646658) | Ethernet | FRONTIER (2864665852539801) | 05/03/2019 (2864665852539801) | 06/03/2019 (2864665852539801) | 05/10/2019 (2864665852539801) | 05/16/2019 (VFORCE) (28646658) | 05/16/2019 (VFORCE) (28646658) | DEMARCDET - 1ST FLOOR TELCO |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 05/16/2019(WAN Analysis Reporting) 05/16/2019(Access) 05/16/2019(Private IP - PIP) |  |  | 05/31/2019 (28646657) 05/29/2019 (28646658) | 06/05/2019 05/30/2019 | 05/16/2019 |  | Completed | N (28646659) N (28646658) N (28646657) | U0101953 | Jeopardy Notification 1 (04/30/2019) | NSPE0012711213 Order Request # 198225327 | NSPE0012711213
Completed | AZ034-05-CM Tuczon, AZ | 6365 E TANQUE VERDE RD STE 120 TUCSON, AZ 85715-3848 US | 50 MBPS | 03/13/2019: 3/13Background: Tucson, AZ; Change port speed to 10M, GCAR to 30M, QOS to R12; Circuit active Status: Hotcut 03/13/2019 10PM CST Action Taken: Scheduled in IVUE | 198230877 | AZ034-02-IM | Private IP - PIP (28646456) Access WAN Analysis Reporting (28646458) | 28646456 28646458 | 50 MBPS (28646456) |  | 207124966 (Private IP (PIP)) 207124964 207124967 (WAN Analysis Reporting) | C4010122/NONE (28646456) |  | 5949510 | 30000 | PVC ID : 5949510 VPN Name : UnitedHealthGroup Router Name : WIT9E02 VRF Name : Vc49959:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65172 PE IP Address : 152.176.82.177 CE Address : 152.176.82.178 QoS - Egress Profile: R12 | 100Base-TX | 100Base-TX | Ethernet | [8 empty] | Deena Lynn 1-520-901-1415 Deena_Lynn@optum.com | Deven Patterson | deven.patterson@optum.com | 1-210-877-7969 | 03/13/2019(Private IP | 03/13/2019 |  | 03/13/2019 (28646456) | 03/22/2019 03/05/2019 (20686587.2) | 03/13/2019 |  | Scheduled Scheduled Status Set | N (28646456) N N (28646458) | U0101953 |  | NSPE0012711290 Order Request # 198225581 | NSPE0012711290
Completed | TX454 Rockport, TX change | 1202 FM 3036 ROCKPORT, TX 78382-7798 US | 10 MBPS | 03/06/2019: 3/6 Status: Ready for Hotcut. | 198243163 | TX454-02-IM | Private IP - PIP (28656757) Access WAN Analysis Reporting (28656759) | 28656757 28656759 | 10 MBPS (28656757) |  | 94582837 (Private IP (PIP)) 94582842 94582839 (WAN Analysis Reporting) | C0156597/NONE (28656757) |  | 6019350 | 5500 | PVC ID : 6019350 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64554 PE IP Address : 152.164.188.245 CE Address : 152.164.188.246 QoS - Egress Profile: R12 | 1000Base-T | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Gabe Rodriguez 1-210-974-6678 grodriguez1@wellmed.net | HERBERT VILLOSTAS | herbert_villostas@optum.com | 1-763-744-2114 | 03/08/2019(Private IP |  |  | 02/25/2019 (28656757) | 03/06/2019 03/06/2019 (24652307.1) | 03/08/2019 |  | Scheduled Scheduled Status Set | N (28656757) N N (28656759) | U0101953 |  | NSPE0012717237 OR 198240711 | NSPE0012717237
Completed | AZ066 Phoenix, AZ; Cox | 5830 N 19TH AVE PHOENIX, AZ 85015-2494 US | 50 MBPS (28695999) | 09/26/2019: 9/26Background:50 MBPS 20 MBPS /PIP-E/ PHOENIX, AZ, /COX COMMUNICATIONS - COX Status: Loop Delivered 9/24 ;Beas install 9/26 Next action: BEAS Installation Who owns the next action: VZB | 198285053 | AZ066 | Private IP - PIP (28695998) WAN Analysis Reporting (28696000) Access (28695999) | 28695998 28696000 28695999 | 20 MBPS (28695998) |  | 325985853 (Private IP (PIP)) 325985855 (WAN Analysis Reporting) 325985849 (Access) | C4016260/ADD (28695998) E4042239/ADD (28695999) |  | 6042057 | 18000 | PVC ID : 6042057 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64828 PE IP Address : 68.137.126.209 CE Address : 68.137.126.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28695999) | 1000Base-SX (850nm, Multi Mode Fiber) (28695999) | Ethernet | COX (2869599950848702) | 03/01/2019 (2869599950848702) | 09/27/2019 (2869599950848702) | 09/25/2019 (2869599950848702) | 10/01/2019 (VFORCE) (28695999) |  | DEMARCADDR - 5830 N 19TH AVE DEMARCDET - CUSTOMER IT ROOM. COX DEMARK PANEL PORT 02 / BASEMENT OF BUILDING A SERVER ROOM ON CUSTOMER WALLBOARD ON THE RIGHT SIDE |  | JENNIE COMER 1-602-336-1966 jennie.comer@optum.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 09/27/2019(Private IP - PIP) 09/27/2019(WAN Analysis Reporting) 09/27/2019(Access) |  |  | 06/25/2019 (28695998) 06/21/2019 (28695999) | 06/06/2019 06/12/2019 | 09/27/2019 |  | Completed | N (28695998) N (28696000) N (28695999) | U0101953 |  | NSPE0012725574 Order Request # 198266867 | NSPE0012725574
Completed | UFL42-08-CM ST PETERSBURG, FL | 805 EXECUTIVE CENTER DR W ST PETERSBURG, FL 33702-2407 US | 50 MBPS | 03/21/2019 Successfully downgraded to 20M | 198318163 | STUDENT RESOURCES/UHC | Private IP - PIP (28731622) Access WAN Analysis Reporting (28731624) | 28731622 28731624 | 20 MBPS (28731622) |  | 208216115 (Private IP (PIP)) 208216113 208216116 (WAN Analysis Reporting) | C4010259/NONE (28731622) |  | 5950732 | 13000 | PVC ID : 5950732 VPN Name : UnitedHealthGroup Router Name : JAP3E01 VRF Name : V484472-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64751 PE IP Address : 152.183.120.153 CE Address : 152.183.120.154 QoS - Egress Profile: R12 | 100Base-TX | 100Base-FX (1310nm, Single Mode Fiber) | Ethernet | [8 empty] | MELISSA CHAPMAN 1-763-744-2114 melissa_r_chapman@optum.com | MELISSA CHAPMAN | melissa_r_chapman@optum.com | 1-763-744-2114 | 03/22/2019(Private IP | 03/21/2019 |  | 03/06/2019 (28731622) | 03/15/2019 03/15/2019 (8491731.3) | 03/22/2019 |  | Completed Activated/Installed | N (28731622) N N (28731624) | U0101953 |  | NSPE0012740136 Order Request # 198315007 | NSPE0012740136
Completed | LUTZ, FL | 15953 N FLORIDA AVE LUTZ, FL 33549-8102 US | 50 MBPS | 03/21/2019 Successfully downgraded to 20M | 198318207 | FL273-02-IM Lutz, FL | Private IP - PIP (28731700) Access WAN Analysis Reporting (28731702) | 28731700 28731702 | 10 MBPS (28731700) |  | 217105299 (Private IP (PIP)) 217105297 217105300 (WAN Analysis Reporting) | C4010912/NONE (28731700) |  | 5964980 | 5000 | PVC ID : 5964980 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65082 PE IP Address : 68.139.198.121 CE Address : 68.139.198.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Susan Wagner 1-763-744-0632 susan_l_wagner@optum.com | Susan Wagner | susan_l_wagner@optum.com | 1-763-744-0632 | 03/22/2019(Private IP | 03/21/2019 |  | 03/07/2019 (28731700) | 03/15/2019 03/15/2019 (21641791.2) | 03/22/2019 |  | Completed Activated/Installed | N (28731700) N N (28731702) | U0101953 |  | NSPE0012740211 Order Request # 198315225 | NSPE0012740211
Completed | NC021-07-CM Raleigh, NC | 4242 SIX FORKS RD RALEIGH, NC 27609-6084 US | 100 MBPS | 03/07/2019: Background: Pricing plan burstable select to tiered Status: Complete Next action: NA Who owns the next action: NA Ticket: NA | 198318531 | 4242 SIx Forks Road | Internet Dedicated Services (28732013) Access | 28732013 | 100 MBPS (28732013) |  | 196343036 (Internet Dedicated Services) 196343034 | C1062188/NONE (28732013) |  | 5928254 | 0 | PVC ID : 5928254 VPN Name : Internet Router Name : GW1RDU1 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.134.33 CE Address : 204.148.134.34 | 100Base-TX | 100Base-TX | Ethernet | [8 empty] | CARY LAIL 1-919-832-3770 clail@mcdonaldyork.com | DOUG LEHNEN | doug_lehnen@optum.com | 1-763-694-7443 | 03/06/2019(Internet Dedicated Services) |  |  | 03/06/2019 (28732013) | 03/15/2019 | 03/06/2019 |  |  | N (28732013) N | U0101953 |  | NSPE0012740154 Order Request # 198315103 | NSPE0012740154
Completed | M0111 Kingston, NY | 505 BOICES LN KINGSTON, NY 12401-1083 US | 200 MBPS | 03/22/2019 Successfully upgraded | 198328541 | M0111 Kingston, NY | Access Private IP - PIP (28740415) | 28740415 | 200 MBPS (28740415) |  | 77712029 77712031 (Private IP (PIP)) | C5001271/NONE (28740415) |  | 5643172 | 140000 | PVC ID : 5643172 VPN Name : UnitedHealthGroup Router Name : NV89E02 VRF Name : V101790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64662 PE IP Address : 152.181.192.249 CE Address : 152.181.192.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Alice De Beaumont 1-845-382-7522 alice_m_de_beaumont@uhc.com | PRADEEP YADAV | pradeep_yadav@optum.com | 91-981-005-9326 | 03/23/2019(Private IP | 03/22/2019 |  | 03/08/2019 (28740415) | 03/18/2019 | 03/23/2019 |  |  | N N (28740415) | U0101953 |  | NSPE0012742923 Order Request # 198323629 | NSPE0012742923
Completed | TX501 Pharr, TX | 1701 S CAGE BLVD STE 16-21 PHARR, TX 78577-9575 US | 50 MBPS (28788665) | 08/07/2019 Successfully activated | 198378817 | TX501 | Private IP - PIP (28788664) WAN Analysis Reporting (28788666) Access (28788665) | 28788664 28788666 28788665 | 10 MBPS (28788664) |  | 94623704 (Private IP (PIP)) 94623706 (WAN Analysis Reporting) 94623708 (Access) | C4016555/ADD (28788664) E4042903/ADD (28788665) | 95.L1XX.801120..TWCC (2878866553357001) | 6045311 | 5500 | PVC ID : 6045311 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64923 PE IP Address : 152.192.46.13 CE Address : 152.192.46.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28788665) | 1000Base-SX (850nm, Multi Mode Fiber) (28788665) | Ethernet | TIME WARNER CABLE (2878866553357001) | 03/14/2019 (2878866553357001) | 07/19/2019 (2878866553357001) | 07/26/2019 (2878866553357001) | 07/26/2019 (VFORCE) (28788665) | 07/26/2019 (VFORCE) (28788665) | DEMARCADDR - . DEMARCDET - 1ST FLOOR MDF WALL MOUNTED RACK / RAD ETX203AX/2SFP/2UTP2SFP, PHRRTXEP1ZW / ETH PORT 5 / VLAN: 57 |  | Gabriel Rodriguez 1-210-833-8929 grodriguez1@wellmed.net | David Dimayuga | david_dimayuga@optum.com | 632-790-6503 | 07/26/2019(Private IP - PIP) 07/26/2019(WAN Analysis Reporting) 07/26/2019(Access) |  |  | 06/25/2019 (28788664) 06/21/2019 (28788665) | 09/04/2019 09/10/2019 | 07/26/2019 |  | Completed | N (28788664) N (28788666) N (28788665) | U0101953 | Jeopardy Notification 3 (04/05/2019) | NSPE0012757062 Order Request # 198369653 | NSPE0012757062
Completed | PA138 PHILADELPHIA, PA | 1818 MARKET ST PHILADELPHIA, PA 19103-3638 US | 50 MBPS (28830937) | 06/26/2019 Successfully activated | 198419475 | PA138 | Private IP - PIP (28830936) WAN Analysis Reporting (28830938) Access (28830937) | 28830936 28830938 28830937 | 50 MBPS (28830936) |  | 331652871 (Private IP (PIP)) 331652883 (WAN Analysis Reporting) 331652865 (Access) | C4016623/ADD (28830936) E4043171/ADD (28830937) |  | 6046861 | 30000 | PVC ID : 6046861 VPN Name : UnitedHealthGroup Router Name : PBYXE04 VRF Name : Vd28902-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64529 PE IP Address : 152.176.72.245 CE Address : 152.176.72.246 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (28830937) | Ethernet | [6 empty] | Verizon BEAS Circuit ID: eay18 y18 0016 / E4043171 Verizon BEAS Demarcation: Fiber Cross connects to to 19th fl |  | Kim Zirkle 1-952-202-0058 Kim_Zirkle@uhg.com | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 05/31/2019(Private IP - PIP) 05/31/2019(WAN Analysis Reporting) 05/31/2019(Access) | 06/26/2019 |  | 06/11/2019 (28830936) 06/07/2019 (28830937) | 06/27/2019 07/03/2019 | 05/31/2019 |  | Completed | N (28830936) N (28830938) N (28830937) | U0101953 | Jeopardy Notification 3 (05/07/2019) | NSPE0012770185 Order Request # 198413315 | NSPE0012770185
Completed | AZ057 Phoenix, AZ | 1107 E BELL RD STE 3 PHOENIX, AZ 85022-2692 US | 50 MBPS | 04/02/2019: 04/02 Upgrade to 50M port and 30M Gold CAR successful | 198430451 | AZ057-02-IM | Private IP - PIP (28836149) Access WAN Analysis Reporting (28836151) | 28836149 28836151 | 50 MBPS (28836149) |  | 167620178 (Private IP (PIP)) 167620176 167620179 (WAN Analysis Reporting) | C4007260/NONE (28836149) |  | 5867950 | 30000 | PVC ID : 5867950 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65113 PE IP Address : 152.183.132.205 CE Address : 152.183.132.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-T | Ethernet | [8 empty] | Thomas Zmyslo 1-952-905-7602 thomas_zmyslo@uhg.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 04/02/2019(Private IP | 04/01/2019 |  | 03/25/2019 (28836149) | 04/02/2019 04/02/2019 (17161387.1) | 04/02/2019 |  | Completed Activated/Installed | N (28836149) N N (28836151) | U0101953 |  | NSPE0012774904 Order Request # 198428799 | NSPE0012774904
Completed | AZ001Phoenix, AZ | 8041 N BLACK CANYON HWY PHOENIX, AZ 85021-4876 US | 50 MBPS | 05/01/2019: 5/1Applied hold: waiting on hotcut to complete | 198430453 | AZ001-02-IJ Phoenix, AZ | Access Private IP - PIP (28836168) | 28836168 | 50 MBPS (28836168) |  | 125834075 125834077 (Private IP (PIP)) | C4004705/NONE (28836168) |  | 5771826 | 30000 | PVC ID : 5771826 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64569 PE IP Address : 152.187.41.173 CE Address : 152.187.41.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | JENNIFER A WILLIAMS 1-623-707-0050 jennifer.a.williams@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 05/07/2019(Private IP | 05/02/2019 |  | 03/22/2019 (28836168) | 04/02/2019 | 05/07/2019 |  |  | N N (28836168) | U0101953 |  | NSPE0012774904 Order Request # 198428799 | NSPE0012774904
Completed | UTX52-02-IM Plano, TX | 6653 PINECREST DR PLANO, TX 75024-2924 US | 1 GBPS (28863015) | 05/15/2019: 5/16 Background: UTX52-02-IM Plano, TX; New 1G/1G IDS; (XO); Dual NID; No MNS; Status: FOC 04/25/2019- Cross connect complete, escalating with XO PM. advised that there are alarms on the circuit that needs to be cleared after which a dispatch will be in place for install. Next Action: Loop delivery | 198457033 | UTX52-02-IM | Internet Dedicated Services (28863014) Access (28863015) | 28863014 28863015 | 1 GBPS (28863014) |  | 332997223 (Internet Dedicated Services) 332997219 (Access) | C0164721/ADD (28863014) E5017258/ADD (28863015) | DA/L1XX/318021/ /TQW /ELK (2886301550898101) | 6048137 | 0 | PVC ID : 6048137 VPN Name : Internet Router Name : GW1DFW27 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 26843 PE IP Address : 204.148.6.181 CE Address : 204.148.6.182 | 1000Base-LX-1310nm (28863015) | 1000Base-LX (1310nm Single Mode Fiber) (28863015) | Ethernet | XO (2886301550898101) | 03/28/2019 (2886301550898101) | 05/20/2019 (2886301550898101) | 05/17/2019 (2886301550898101) | 05/20/2019 (VFORCE) (28863015) |  | DEMARCDET - 6653 pine crest dr building main floor 1 room MDF shef 19 jack 19 and 20 |  | JOHN CURTISS 1-469-229-6712 jcurtiss@uhcsr.com | JOHN CURTISS | jcurtiss@uhcsr.com | 1-469-229-6712 | 05/21/2019(Internet Dedicated Services) 05/21/2019(Access) |  |  | 05/24/2019 (28863014) 05/22/2019 (28863015) | 05/24/2019 | 05/21/2019 |  |  | N (28863014) N (28863015) | U0101953 |  | Order Request 198454619 | NSPE0012782738
Completed | Well Lake Hills, TX; Disconnect E4033643 / C4013260 | 1250 S CAPITAL OF TEXAS HWY WEST LAKE HILLS, TX 78746-6446 US |  | 04/24/2019: 4/24Background: Well Lake Hills, TX; Disconnect E4033643 / C4013260; TWT Status: Disconnected 04/05. Pending equipment retrieval ETD after 4/25 Next action: Order closure Who owns the next action: SD | 198458401 | M0331-10-IM | Private IP - PIP (28870132) WAN Analysis Reporting (28870134) Access (28870133) | 28870132 28870134 28870133 | 20 MBPS |  | 94542913 (Private IP (PIP)) 94542918 (WAN Analysis Reporting) 94542915 (Access) | C4013260/REMOVE (28870132) E4033643/REMOVE (28870133) | TX/KXFN/024713/LVLC (2887013325447501) | 5990217 | 13000 | PVC ID : 5990217 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65102 PE IP Address : 152.161.73.25 CE Address : 152.161.73.26 QoS - Egress Profile: R12 |  |  | Ethernet | LEVEL 3 (2887013325447501) | 03/27/2019 (2887013325447501) | 04/29/2019 (2887013325447501) | 04/05/2019 (2887013325447501) | 07/09/2019 (VFORCE) (28870133) |  |  |  | Melissa Chapman Melissa Chapman 1-176-374-4211 melissa_r_chapman@optum.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 1-763-744-2114 | 04/29/2019(Private IP - PIP) 04/29/2019(WAN Analysis Reporting) 04/29/2019(Access) |  |  | 04/29/2019 (28870132) 04/29/2019 (28870133) | 04/25/2019 | 04/30/2019 |  | Completed | N (28870132) N (28870134) N (28870133) | U0101953 |  | NSPE0012782093 Order Request # 198452235 | NSPE0012782093
Completed | AZ056-04-IJ Phoenix, AZ | 20040 N 19TH AVE STE A PHOENIX, AZ 85027-4256 US | 50 MBPS (28865341) | 04/25/2019: Background: AZ056 Phoenix,, AZ; New 20/50M PIP-Eth; (Centurylink); Dual NID; No MNS; ENID Status: Ready for activation Telco Circuit ID: 19/KXGS/405830//MS Telco Demarcation: 1st flr telco room wall mounted Ceina 3916 optical port 4 Verizon BEAS Circuit ID: USAAZ53852163COV400001 / E4043601 Verizon BEAS Demarcation: installed the Overture on the 1st floor of the customer's network equipment room. It's mounted in the data rack, RU#32 | 198458491 | AZ056-02-IM | Private IP - PIP (28865340) WAN Analysis Reporting (28865342) Access (28865341) | 28865340 28865342 28865341 | 20 MBPS (28865340) |  | 332273869 (Private IP (PIP)) 332273871 (WAN Analysis Reporting) 332273865 (Access) | C4016814/ADD (28865340) E4043601/ADD (28865341) | 19/KXGS/405830//MS (2886534153852101) | 6049364 | 15000 | PVC ID : 6049364 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65184 PE IP Address : 152.192.39.117 CE Address : 152.192.39.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28865341) | 1000Base-SX (850nm, Multi Mode Fiber) (28865341) | Ethernet | CENTURYLINK (2886534153852101) | 04/05/2019 (2886534153852101) | 04/24/2019 (2886534153852101) | 04/23/2019 (2886534153852101) | 04/24/2019 (VFORCE) (28865341) | 04/24/2019 (VFORCE) (28865341) | DEMARCDET - 1ST FLOOR TELCO ROOM WALL MOUNTED Type: OPTICAL Port: 4 |  | Marjorie Matthews 1-602-361-6901 marjorie.matthews@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 04/24/2019(Private IP - PIP) 04/24/2019(WAN Analysis Reporting) 04/24/2019(Access) |  |  | 05/03/2019 (28865340) 05/01/2019 (28865341) | 05/06/2019 05/10/2019 | 04/24/2019 |  | Completed | N (28865340) N (28865342) N (28865341) | U0101953 |  | NSPE0012782781 Order Request # 198454743 | NSPE0012782781
Completed | MA084-02-IJ Boston, MA | 75 STATE ST FL 29 BOSTON, MA 02109-1827 US | 50 MBPS (28872905) | 06/18/2019: Background: MA084 Boston, MA / 50 Mbps / 20 Mbps / Access, Private IP (PIP) / Dual NID / No MNS Status: Ready for activation Telco Circuit ID: ea-75s-75s-0024 Demarcation: Slot: 2-Port: 1-Floor: 29-Room: DATA-Jack Type: SC MM | 198466941 | Boston_ MA084-02-IJ | Private IP - PIP (28872904) WAN Analysis Reporting (28872906) Access (28872905) | 28872904 28872906 28872905 | 20 MBPS (28872904) |  | 332274075 (Private IP (PIP)) 332274077 (WAN Analysis Reporting) 332274071 (Access) | C4016734/ADD (28872904) E4043419/ADD (28872905) |  | 6048429 | 15000 | PVC ID : 6048429 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64697 PE IP Address : 152.176.104.85 CE Address : 152.176.104.86 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (28872905) | Ethernet | [8 empty] | Janice Buss 1-781-247-4962 JBuss@coretelligent.com | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 06/18/2019(Private IP - PIP) 06/18/2019(WAN Analysis Reporting) 06/18/2019(Access) |  |  | 06/19/2019 (28872904) 06/17/2019 (28872905) | 07/04/2019 07/10/2019 | 06/18/2019 |  | Completed | N (28872904) N (28872906) N (28872905) | U0101953 | Jeopardy Notification 2 (05/31/2019) | NSPE0012784162 Order Request # 198459425 | NSPE0012784162
Completed | TX481-02-IM Carollton, TX | 4323 N JOSEY LN CARROLLTON, TX 75010 USA | 1.536 MBPS (IQBLP5DR) | 04/24/2019: 4/24Background: TX481-02-IM Carollton, TX; New 7xT1 MLPPP; (ATT); Single NID; No MNS; Status: Ready for plug and play Next action: Customer to activate Who owns the next action: Customer | 9859796 |  | Private IP (IQBLP5DR) EVC/PVC Service (N.11982308.6049406) | IQBLP5DR N.11982308.6049406 | 10.752 MBPS | P2214739 |  | BCBLDTXB0001 (IQBLP5DR) BCBLDTXB0002 (IQBLP5DR) BCBLDTXB0003 (IQBLP5DR) BCBLDTXB0004 (IQBLP5DR) BCBLDTXB0005 (IQBLP5DR) BCBLDTXB0006 (IQBLP5DR) BCBLDTXB0007 (IQBLP5DR) | 13/HCGS/697073//FTNC/ (IQBLP5DRBT2WMB01) | 6049406 | 7200 | VPN Name : UnitedHealthGroup Router Name : RCNGE09 VRF Name : V344449:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64695 PE IP Address : 152.187.97.85 CE Address : 152.187.97.86 QoS - Egress Profile: R12 PVC ID : 6049406 |  |  |  | ATT (IQBLP5DRBT2WMB01) | 04/04/2019 (IQBLP5DRBT2WMB01) | 04/16/2019 (IQBLP5DRBT2WMB01) | 04/18/2019 (IQBLP5DRBT2WMB01) |  |  | DEMARC INFO: 13/HCGS/697084/ /FTNC/ - 1ST FLR TELCO RM, SH 6 SL 3, RJ48C, TAGGED NOT EXT 13/HCGS/697073/ /FTNC/ - 1ST FLR TELCO RM, SH 4 SL 1, RJ48C, TAGGED NOT EXT 13/HCGS/697076/ /FTNC/ - 1ST FLR TELCO RM, SH 4 SL 3, RJ48C, TAGGED NOT EXT 13/HCGS/697078/ /FTNC/ - 1ST FLR TELCO RM, SH 6 SL 1, RJ48C, TAGGED NOT EXT 13/HCGS/697079/ /FTNC/ - 1ST FLR TELCO RM, SH 4 SL 4, RJ48C, TAGGED NOT EXT 13/HCGS/697083/ /FTNC/ - 1ST FLR TELCO RM, SH 6 SL 2, RJ48C, TAGGED NOT EXT |  | LIZ GUERRIDO 0012107623635 LGUERRIDO@WELLMED.NET |  |  |  | 04/23/2019 (IQBLP5DR) |  |  | 04/23/2019 (IQBLP5DR) | 04/25/2019 (IQBLP5DR) |  |  |  | N (IQBLP5DR) N (N.11982308.6049406) | 05017789 P2214739 |  | NSPE0012788951 CW 198474293 | NSPE0012788951
Completed | TX482 Cedar Park, TX | 1779 E WHITESTONE BLVD BLDG 2 CEDAR PARK, TX 78613-6934 US | 50 MBPS (28900191) | 10/30/2019: 10/30Background: TX482 Cedar Park, TX; New 10M/50M PIP-Eth; (ATT); Dual NID; Status: Loop delivered 10/30-Pending Beas Next Action: Pending Beas Who owns the next action: VZB tech | 198495505 | TX482 | Private IP - PIP (28900190) WAN Analysis Reporting (28900192) Access (28900191) | 28900190 28900192 28900191 | 10 MBPS (28900190) |  | 94627040 (Private IP (PIP)) 94627042 (WAN Analysis Reporting) 94627038 (Access) | C4016810/ADD (28900190) E4043590/ADD (28900191) | 32/KRGN/653483//SW (2890019154225501) | 6049314 | 5500 | PVC ID : 6049314 VPN Name : UnitedHealthGroup Router Name : AX39E01 VRF Name : Vd31961:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65183 PE IP Address : 152.192.37.89 CE Address : 152.192.37.90 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28900191) | 1000Base-SX (850nm, Multi Mode Fiber) (28900191) | Ethernet | ATT (2890019154225501) | 10/25/2019 (2890019154225501) | 10/30/2019 (2890019154225501) | 10/30/2019 (2890019154225501) | 10/31/2019 (VFORCE) (28900191) | 10/31/2019 (VFORCE) (28900191) | DEMARCADDR - . DEMARCDET - MAIN FLOOR MPOE BLDG 2 |  | JASON Ozer 1-210-951-3251 jozer@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 10/31/2019(Private IP - PIP) 10/31/2019(WAN Analysis Reporting) 10/31/2019(Access) |  |  | 11/08/2019 (28900190) 11/06/2019 (28900191) | 12/04/2019 12/10/2019 | 10/31/2019 |  | Completed | N (28900190) N (28900192) N (28900191) | U0101953 | Jeopardy Notification 1 (10/21/2019) | NSPE0012795564 Order Request # 198495395 | NSPE0012795564
Completed | AZ046-02-IJ Green Valley, AZ | 695 S PECAN TREE LN GREEN VALLEY, AZ 85614-5114 US | 50 MBPS (28880865) | 05/22/2019 Successfully activated | 198475353 | AZ046-02-IJ Green Valley | Private IP - PIP (28880864) WAN Analysis Reporting (28880866) Access (28880865) | 28880864 28880866 28880865 | 20 MBPS (28880864) |  | 94626414 (Private IP (PIP)) 94626420 (WAN Analysis Reporting) 94626416 (Access) | C4016752/ADD (28880864) E4043465/ADD (28880865) | 19.KXGS.400292..MS (2888086521224201) | 6048646 | 13000 | PVC ID : 6048646 VPN Name : UnitedHealthGroup Router Name : WIT9E01 VRF Name : V603341:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64799 PE IP Address : 152.183.197.229 CE Address : 152.183.197.230 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28880865) | 1000Base-SX (850nm, Multi Mode Fiber) (28880865) | Ethernet | CENTURYLINK (2888086521224201) | 03/28/2019 (2888086521224201) | 04/08/2019 (2888086521224201) | 04/03/2019 (2888086521224201) | 04/09/2019 (VFORCE) (28880865) | 04/09/2019 (VFORCE) (28880865) | DEMARCADDR - X DEMARCDET - 1ST FLOOR IT EAST WALL MOUNTED 3916 TYPE: OPTICAL |  | EDELMIRA EDI CECENA 1-520-625-8116 edelmira.cecena@optum.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 04/09/2019(Private IP - PIP) 04/09/2019(WAN Analysis Reporting) 04/09/2019(Access) | 05/22/2019 |  | 04/17/2019 (28880864) 04/15/2019 (28880865) | 05/08/2019 05/14/2019 | 04/09/2019 |  | Completed | N (28880864) N (28880866) N (28880865) | U0101953 |  | NSPE0012789156 Order Request # 198475297 | NSPE0012789156
Completed | AZ047-02-IJ Tucson, AZ | 1669 W INA RD TUCSON, AZ 85704-1982 US | 50 MBPS (28880862) | 04/23/2019: 04/22 Successfully activated | 198475403 | AZ047-02-IJ Tucson | Private IP - PIP (28880861) WAN Analysis Reporting (28880863) Access (28880862) | 28880861 28880863 28880862 | 20 MBPS (28880861) |  | 94626604 (Private IP (PIP)) 94626606 (WAN Analysis Reporting) 94626602 (Access) | C4016753/ADD (28880861) E4043464/ADD (28880862) | 19.KXGS.399745..MS (2888086221224201) | 6048645 | 13000 | PVC ID : 6048645 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64525 PE IP Address : 152.176.74.45 CE Address : 152.176.74.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28880862) | 1000Base-SX (850nm, Multi Mode Fiber) (28880862) | Ethernet | CENTURYLINK (2888086221224201) | 03/28/2019 (2888086221224201) | 04/09/2019 (2888086221224201) | 04/03/2019 (2888086221224201) | 04/09/2019 (VFORCE) (28880862) | 04/09/2019 (VFORCE) (28880862) | DEMARCADDR - X DEMARCDET - 1ST FLOOR IT WALL MOUNT SOUTH WALL ABOVE FDP TYPE OPTICAL |  | ANGEL GILLETT 1-520-795-6183 angel.gillett@optum.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 04/09/2019(Private IP - PIP) 04/09/2019(WAN Analysis Reporting) 04/09/2019(Access) | 04/22/2019 |  | 04/18/2019 (28880861) 04/16/2019 (28880862) | 05/08/2019 05/14/2019 | 04/09/2019 |  | Completed | N (28880861) N (28880863) N (28880862) | U0101953 |  | NSPE0012789156 Order Request # 198475297 | NSPE0012789156
Completed | AZ045-02-IJ Tucson, AZ | 1460 W VALENCIA RD TUCSON, AZ 85746-6001 US | 50 MBPS (28882430) | 05/29/2019 Successfully activated | 198475351 | AZ045-02-IJ Tucson, | Private IP - PIP (28882429) WAN Analysis Reporting (28882431) Access (28882430) | 28882429 28882431 28882430 | 50 MBPS (28882429) |  | 94626403 (Private IP (PIP)) 94626409 (WAN Analysis Reporting) 94626405 (Access) | C4016760/ADD (28882429) E4043475/ADD (28882430) | 19.KXGS.399748..MS (2888243021224001) | 6048678 | 30000 | PVC ID : 6048678 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64522 PE IP Address : 199.220.34.17 CE Address : 199.220.34.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28882430) | 1000Base-SX (850nm, Multi Mode Fiber) (28882430) | Ethernet | CENTURYLINK (2888243021224001) | 03/28/2019 (2888243021224001) | 04/09/2019 (2888243021224001) | 04/01/2019 (2888243021224001) | 04/08/2019 (VFORCE) (28882430) | 04/08/2019 (VFORCE) (28882430) | DEMARCADDR - X DEMARCDET - 1ST FLOOR IT EAST WALL TYPE: OPTICAL |  | ANISA LOPEZ 1-520-573-0966 anisa.lopez@optum.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 04/08/2019(Private IP - PIP) 04/08/2019(WAN Analysis Reporting) 04/08/2019(Access) | 05/29/2019 |  | 04/18/2019 (28882429) 04/16/2019 (28882430) | 04/30/2019 05/06/2019 | 04/08/2019 |  | Completed | N (28882429) N (28882431) N (28882430) | U0101953 | Jeopardy Notification 1 (04/03/2019) | NSPE0012789156 Order Request # 198475297 | NSPE0012789156
Completed | NC054 Asheville, NC | 1200 RIDGEFIELD BLVD STE 145 ASHEVILLE, NC 28806-4568 US | 3 MBPS (28933034) | 04/24/2019: 4/24Background: 3 Mbps / 3 Mbps / Access, Private IP (PIP) / ASHEVILLE, NC, US / ATT Status:Foc 4/16- testing complete BGW team have one more task to complete for order closure. Next Action: Loop Delivery Who owns the next action: LEC | 198524745 | NC054 | Private IP - PIP (28933033) WAN Analysis Reporting (28933035) Access (28933034) | 28933033 28933035 28933034 | 3 MBPS (28933033) |  | 94627745 (Private IP (PIP)) 94627747 (WAN Analysis Reporting) 94627743 (Access) | C1089166/ADD (28933033) N1046035/ADD (28933034) N1046034/ADD (28933034) | 20/HCGS/413604//SB (2893303454434601) | 6050269 | 1500 | PVC ID : 6050269 VPN Name : UnitedHealthGroup Router Name : GNJGE08 VRF Name : V397551:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65018 PE IP Address : 152.164.14.97 CE Address : 152.164.14.98 QoS - Egress Profile: R12 |  | DS1 (28933034) | TDM | ATT (2893303454434601) | 04/04/2019 (2893303454434601) | 04/16/2019 (2893303454434601) | 04/23/2019 (2893303454434601) |  |  | DEMARCDET - 1ST FLR MPOE CUST REQ MM 1 SLOT 2 |  | Lisa McNamara 1-952-202-0242 lisa_mcnamara@uhg.com | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 04/24/2019(Private IP - PIP) 04/24/2019(WAN Analysis Reporting) 04/24/2019(Access) |  |  | 04/29/2019 (28933033) 04/25/2019 (28933034) | 04/26/2019 05/02/2019 | 04/24/2019 |  | Completed | N (28933033) N (28933035) N (28933034) | U0101953 |  | NSPE0012804358 Order Request # 198524605 | NSPE0012804358
Completed | TX483 Dallas, TX | 1717 N GARRETT AVE DALLAS, TX 75206-7514 US | 50 MBPS (28934875) | 07/23/2019: Background: TX483 / 50 Mbps / 10 Mbps / Access, Private IP (PIP) / DALLAS, TX, US / ATT / Dual NID / ENID Status: Ready for activation once customer internal cabling is complete Telco Circuit ID: 14/KRGN/885542//SW Telco Demarcation: 1F MPOE WL MNTD PORT 1 TGGD Verizon BEAS Circuit ID: 400 /USATX54477649COV400001 / E4043771 Verizon BEAS Demarcation: 1st floor, server closet, backboard wall, optional port 0/1. MMF, LC. Tagged with ckt id and order number | 198527515 | TX483 | Private IP - PIP (28934874) WAN Analysis Reporting (28934876) Access (28934875) | 28934874 28934876 28934875 | 10 MBPS (28934874) |  | 94627674 (Private IP (PIP)) 94627672 (WAN Analysis Reporting) 94627670 (Access) | C4016863/ADD (28934874) E4043771/ADD (28934875) | 14/KRGN/885542//SW (2893487554477601) | 6050307 | 5500 | PVC ID : 6050307 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64548 PE IP Address : 147.225.172.245 CE Address : 147.225.172.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28934875) | 1000Base-SX (850nm, Multi Mode Fiber) (28934875) | Ethernet | ATT (2893487554477601) | 07/15/2019 (2893487554477601) | 07/18/2019 (2893487554477601) | 07/18/2019 (2893487554477601) | 07/22/2019 (VFORCE) (28934875) |  | DEMARCDET - 1F MPOE WL MNTD PORT 1 TGGD |  | LIZDELI GUERRIDO 1-210-762-3635 lguerrido@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 07/22/2019(Private IP - PIP) 07/22/2019(WAN Analysis Reporting) 07/22/2019(Access) |  |  | 07/29/2019 (28934874) 07/25/2019 (28934875) | 08/22/2019 08/28/2019 | 07/22/2019 |  | Completed | N (28934874) N (28934876) N (28934875) | U0101953 | Jeopardy Notification 1 (07/22/2019) | NSPE0012804851 Order Request # 198526379 | NSPE0012804851
Completed | Cologne, MA | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBLP741) |  | 9879274 |  | Private IP Port Only (CQBLP741) | CQBLP741 | 4000 MBPS | P2198253 |  | BOBLC5X60001 (CQBLP741) |  | 5997743 5997745 | 768 | PVC ID : 5997743,5997745 VPN Name : UHG-SDWAN Router Name : MZZ9E01 VRF Name : Vd76606:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.161.122.109 CE Address : 152.161.122.110 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0015072950001 TIM_GUNDERSON@OPTUM.COM |  |  |  | 04/10/2019 (CQBLP741) | 04/10/2019 |  | 05/03/2019 (CQBLP741) | 05/03/2019 (CQBLP741) |  |  |  | N (CQBLP741) | 05017789
Completed | 511 Cologix Minneapolis, MN | 511 11TH AVE S MINNEAPOLIS, MN 55415-1537 US |  | 05/22/2019: 5/22Background: 500 Mbps / Access, Private IP (PIP) / MINNEAPOLIS, MN, US Status: Mux messaging and BGW are complete; Following up for further updates. Who owns the next action: Prov Team | 198575547 | 511 | Private IP - PIP (28987355) WAN Analysis Reporting (28987357) Access (28987356) | 28987355 28987357 28987356 | 500 MBPS (28987355) |  | 337301409 (Private IP (PIP)) 337301411 (WAN Analysis Reporting) 337301365 (Access) | C0167608/ADD (28987355) E5017587/ADD (28987356) | fs511 511 0014 (I0039955.MIN) | 6051867 | 250000 | PVC ID : 6051867 VPN Name : UHG-OFE Router Name : MN39E01 VRF Name : Vc13322:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65483 PE IP Address : 68.138.244.229 CE Address : 68.138.244.230 QoS - Egress Profile: G1 |  | 1000Base-LX (1310nm Single Mode Fiber) (28987356) | Ethernet |  |  | 05/22/2019 (I0039955.MIN) | [5 empty] | Scott Mccrady 1-612-800-6534 scott.mccrady@cologix.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 | 05/24/2019(Private IP - PIP) 05/24/2019(WAN Analysis Reporting) 05/24/2019(Access) |  |  | 06/04/2019 (28987355) 06/04/2019 (28987356) | 05/08/2019 05/14/2019 | 05/24/2019 |  | Completed | N (28987355) N (28987357) N (28987356) | U0101953 |  | NSPE0012817156 Order Request # 198566563 | NSPE0012817156
Completed | TX451 Lancaster, TX | 2424 W PLEASANT RUN RD LANCASTER, TX 75146-4005 US | 50 MBPS (28989368) | 08/06/2019: Background: TX451 Lncaster, TX; New 10M/50M PIP-Eth; (AT&T); Dual NID; No MNS; Status: Ready for activation Telco Circuit ID: 14/KRGN/885603//SW Telco Demarcation: OUTSIDE REAR H FRAME Equipment & Port: CIENA 3931 / PORT 1 Verizon BEAS Circuit ID: USATX54726825COV400001 / E4044075 Verizon BEAS Demarcation: 1st floor, IT / data room. Tagged with ckt id and order number. | 198572887 | TX451 | WAN Analysis Reporting (28989369) Access (28989368) Private IP - PIP (28989367) | 28989369 28989368 28989367 | 10 MBPS (28989367) |  | 94629505 (WAN Analysis Reporting) 94629511 (Access) 94629507 (Private IP (PIP)) | C4016959/ADD (28989367) E4044075/ADD (28989368) | 14/KRGN/885603//SW (2898936854726801) | 6051911 | 5500 | PVC ID : 6051911 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64739 PE IP Address : 152.187.189.21 CE Address : 152.187.189.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28989368) | 1000Base-SX (850nm, Multi Mode Fiber) (28989368) | Ethernet | ATT (2898936854726801) | 04/11/2019 (2898936854726801) | 06/19/2019 (2898936854726801) | 07/18/2019 (2898936854726801) | 08/05/2019 (VFORCE) (28989368) | 08/05/2019 (VFORCE) (28989368) | DEMARCDET - OUTSIDE REAR H FRAME |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 08/05/2019(WAN Analysis Reporting) 08/05/2019(Access) 08/05/2019(Private IP - PIP) |  |  | 08/13/2019 (28989367) 08/09/2019 (28989368) | 09/18/2019 09/12/2019 | 08/05/2019 |  | Completed | N (28989369) N (28989368) N (28989367) | U0101953 | Jeopardy Notification 1 (06/20/2019) | NSPE0012818830 Order Request # 198572855 | NSPE0012818830
Completed | Disconnect W0W76572 Berkshire, United Kingdom | 20 GRENFELL ROAD MAIDENHEAD,BERKSHIRESL6 1EH GBR | DS-3PPP-44.736MB (6278654) | 07/19/2019: Background: W0W76572 Berkshire, UK; Disconnect Status: Disconnected date 06/13/2019 - hardware retrieval retriggered, awaiting schedule Next action: order closure Who owns the next action: SD | 9882121 |  | Private IP (6278654) | 6278654 | 44.736 MBPS |  |  | W0W76572 (6278654) | Y0501509A (6181885) | 1906399 | 12288 | PVC ID : 1906399 VPN Name : UnitedHealthGroup Router Name : LNDNES04 VRF Name : V227445:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65150 PE IP Address : 206.115.90.13 CE Address : 206.115.90.14 QoS - Egress Profile: R12 |  |  |  | WILLIAMS TELECOMMUNICATIONS (UK) CABLE & WIRELESS UK (6181885) | 05/06/2019 (6181885) | 05/21/2019 (6181885) | 06/13/2019 (6181885) |  |  |  | TECH ON DUTY +9999999999 | TOBY KNIGHT 0208 283 2573 TOBY.KNIGHT@EU.JLL.COM, 07788 188884 | [6 empty] | 06/06/2019 (6278654) | 06/06/2019 (6278654) |  |  |  | N (6278654) | 00219957 |  | NSPE0012809256 | NSPE0012809256
Completed | TX512 Donna, TX | 605 N MAIN ST STE C DONNA, TX 78537-2726 US | 50 MBPS (29016705) | 07/24/2019: Background: TX512 Donna, TX; New 10M/50M PIP-Eth; (TWC); Dual NID; No MNS; 100days offnet build Status: Ready for activation Telco Circuit ID: 95.L1XX.801192..TWCC Telco Demarcation: 1st floor IT room mounted on the rack on the wall RAD 203 PORT 5 Verizon BEAS Circuit ID: USATX55004841COV400001 / E4044233 Verizon BEAS Demarcation: LAN Room, 1st floor, Port 5. On same Telco board where Telco Circuit ID is. | 198604633 | TX512 | Private IP - PIP (29016704) WAN Analysis Reporting (29016706) Access (29016705) | 29016704 29016706 29016705 | 10 MBPS (29016704) |  | 94630319 (Private IP (PIP)) 94630323 (WAN Analysis Reporting) 94630316 (Access) | C4017051/ADD (29016704) E4044233/ADD (29016705) | 95.L1XX.801192..TWCC (2901670555004801) | 6053015 | 5500 | PVC ID : 6053015 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65201 PE IP Address : 152.162.94.197 CE Address : 152.162.94.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29016705) | 1000Base-SX (850nm, Multi Mode Fiber) (29016705) | Ethernet | TIME WARNER CABLE (2901670555004801) | 04/17/2019 (2901670555004801) | 08/05/2019 (2901670555004801) | 07/22/2019 (2901670555004801) | 07/24/2019 (VFORCE) (29016705) | 07/24/2019 (VFORCE) (29016705) | DEMARCADDR - . DEMARCDET - 1st floor IT room mounted on the rack on the wall RAD 203 PORT 5 |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 07/24/2019(Private IP - PIP) 07/24/2019(WAN Analysis Reporting) 07/24/2019(Access) |  |  | 08/14/2019 (29016704) 08/12/2019 (29016705) | 09/02/2019 09/06/2019 | 07/24/2019 |  | Completed | N (29016704) N (29016706) N (29016705) | U0101953 | Jeopardy Notification 1 (04/17/2019) | NSPE0012830101 Order Request # 198604619 | NSPE0012830101
Completed | TX510 Corpus Christi, TX | 4101 S STAPLES ST CORPUS CHRISTI, TX 78411-5501 US | 50 MBPS (29007174) | 07/25/2019: 7/25Background: TX510 Corpus Christi, TX; New 10M/50M PIP-Eth; (TWC); Dual NID; No MNS Status: Loop delivered7/23; BEAS installation 07/29/2019 Next Action: BEAS installation | 198593933 | TX510 | Private IP - PIP (29007173) WAN Analysis Reporting (29007175) Access (29007174) | 29007173 29007175 29007174 | 10 MBPS (29007173) |  | 94630305 (Private IP (PIP)) 94630309 (WAN Analysis Reporting) 94630302 (Access) | C4017011/ADD (29007173) E4044181/ADD (29007174) |  | 6052732 | 5500 | PVC ID : 6052732 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65058 PE IP Address : 68.139.84.241 CE Address : 68.139.84.242 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29007174) | 1000Base-SX (850nm, Multi Mode Fiber) (29007174) | Ethernet |  |  |  |  | 07/29/2019 (VFORCE) (29007174) | 07/29/2019 (VFORCE) (29007174) |  |  | GABRIEL RODRIGUEZ 1-210-833-8929 grodriguez1@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 07/29/2019(Private IP - PIP) 07/29/2019(WAN Analysis Reporting) 07/29/2019(Access) |  |  | 08/20/2019 (29007173) 08/16/2019 (29007174) | 09/16/2019 09/20/2019 | 07/29/2019 |  | Completed | N (29007173) N (29007175) N (29007174) | U0101953 |  | NSPE0012826818 OR 198593933 | NSPE0012826818
Completed | FL413 Tampa, FL | 3000 BAYPORT DR STE 1170 TAMPA, FL 33607-8402 US | 50 MBPS (29074977) | 05/28/2019: Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / TAMPA, FL, US / LEVEL 3 Status: Ready for activation Telco Circuit ID: FL/KXFN/154325/LVLC Telco Demarcation: 9TH FLOOR ELECTRICAL ROOM COMMON SPACE WALL MOUNTED RMU3 CISCO 3600 PORT 13 RJ45 TAGGED WITH CIRCUIT ID EQUIPMENT & PORT: CISCO 3600 PORT 13 Verizon BEAS Circuit ID: USAFL55485809COV400001 / E4044558 Verizon BEAS Demarcation: Port: 1; Floor: 9; Room: Telco rm; | 198665981 | FL413 | Private IP - PIP (29074976) WAN Analysis Reporting (29074978) Access (29074977) | 29074976 29074978 29074977 | 10 MBPS (29074976) |  | 94632733 (Private IP (PIP)) 94632738 (WAN Analysis Reporting) 94632735 (Access) | C4017186/ADD (29074976) E4044558/ADD (29074977) | FL/KXFN/154325/LVLC (2907497755485801) | 6054850 | 5500 | PVC ID : 6054850 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64708 PE IP Address : 152.164.35.153 CE Address : 152.164.35.154 QoS - Egress Profile: R12 | 100Base-TX (29074977) | 100Base-TX (29074977) | Ethernet | LEVEL 3 (2907497755485801) | 05/15/2019 (2907497755485801) | 06/07/2019 (2907497755485801) | 05/23/2019 (2907497755485801) | 05/28/2019 (VFORCE) (29074977) | 05/28/2019 (VFORCE) (29074977) | DEMARCDET - X |  | Yesenia Acosta 1-813-286-7909 Yesenia.acosta@cushwake.com | SAHIL TUTEJA | sahil_tuteja@optum.com | 91-828-567-0647 | 05/28/2019(Private IP - PIP) 05/28/2019(WAN Analysis Reporting) 05/28/2019(Access) |  |  | 06/18/2019 (29074976) 06/14/2019 (29074977) | 06/25/2019 07/01/2019 | 05/28/2019 |  | Completed | N (29074976) N (29074978) N (29074977) | U0101953 | Jeopardy Notification 1 (05/14/2019) | NSPE0012848848 Order Request # 198663891 | NSPE0012848848
Completed | Dallas, TX | 6181 BONNIE VIEW RD DALLAS, TX 75241 US | 50 MBPS (29084264) | 09/04/2019: 9/4Background: TX511 Dallas, TX; 50M/50M PIP-Eth; (ATT); Dual NID; No MNS Status: Loop delivered; BEAS installed, pending power to line test the circuits. > CRD 08/28 did not push through. New CRD 09/03 COB Next Action: Line testing Who owns the next action: ACD | 198674077 | TX511 | Private IP - PIP (29084263) WAN Analysis Reporting (29084265) Access (29084264) | 29084263 29084265 29084264 | 50 MBPS (29084263) |  | 94633389 (Private IP (PIP)) 94633387 (WAN Analysis Reporting) 94633391 (Access) | C4017197/ADD (29084263) E4044598/ADD (29084264) | 14/KRGN/885753//SW (2908426455544901) | 6055075 | 5500 | PVC ID : 6055075 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65252 PE IP Address : 152.183.138.129 CE Address : 152.183.138.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29084264) | 1000Base-SX (850nm, Multi Mode Fiber) (29084264) | Ethernet | ATT (2908426455544901) | 07/19/2019 (2908426455544901) | 08/05/2019 (2908426455544901) | 08/05/2019 (2908426455544901) | 09/05/2019 (VFORCE) (29084264) | 09/05/2019 (VFORCE) (29084264) | DEMARCDET - 1ST FLR SOUTH WALL CIENA 3931 PORT 2 |  | LIZDELI GUERRIDO 1-210-762-3635 lguerrido@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 09/05/2019(Private IP - PIP) 09/05/2019(WAN Analysis Reporting) 09/05/2019(Access) |  |  | 09/12/2019 (29084263) 09/10/2019 (29084264) | 10/14/2019 10/18/2019 | 09/05/2019 |  | Completed | N (29084263) N (29084265) N (29084264) | U0101953 | Jeopardy Notification 1 (08/20/2019) | NSPE0012851597 Order Request # 198672101 | NSPE0012851597
Completed | San Juan, Puerto Rico | 9615 AVE LOS ROMEROS SAN JUAN, PR 00926-7036 PR | 200 MBPS | 05/22/2019 Hotcut successful | 198682583 | PR517-02-IM | Private IP - PIP (29090191) Access | 29090191 | 200 MBPS (29090191) |  | 252325385 (Private IP (PIP)) 252325383 | C5005749/NONE (29090191) |  | 5997385 | 90000 | PVC ID : 5997385 VPN Name : UnitedHealthGroup Router Name : SNJN9E01 VRF Name : Vc13521:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64805 PE IP Address : 199.220.128.9 CE Address : 199.220.128.10 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | BRENDA DAVILA 1-787-806-5748 brenda.davila@am.jll.com | sahil Tuteja | sahil_tuteja@optum.com | 91-828-567-0647 | 05/21/2019(Private IP | 05/20/2019 |  | 05/14/2019 (29090191) | 05/08/2019 | 05/21/2019 |  |  | N (29090191) N | U0101953 |  | NSPE0012855066 Order Request # 198682125 | NSPE0012855066
Completed | NC056 Fayetteville, NC | 1565 PURDUE DR STE 201A FAYETTEVILLE, NC 28303-5537 US | 1.5 MBPS (29090231) | 05/17/2019: 5/16Background: 1.5 Mbps / 1.5 Mbps / Access, Private IP (PIP) / FAYETTEVILLE, NC, US / CENTURYLINK Status: FOC 5/8- Loop delivered ready for activation Next Action: Loop Delivery Who owns the next action: LEC | 198682059 | NC056 | Private IP - PIP (29090230) WAN Analysis Reporting (29090232) Access (29090231) | 29090230 29090232 29090231 | 1.5 MBPS (29090230) |  | 94632840 (Private IP (PIP)) 94632842 (WAN Analysis Reporting) 94632837 (Access) | C0167459/ADD (29090230) D1099902/ADD (29090231) | 58/HCGS/338225//CRLN (2909023155633001) | 6055314 | 1000 | PVC ID : 6055314 VPN Name : UnitedHealthGroup Router Name : GNJ3E04 VRF Name : Vd44011-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65036 PE IP Address : 68.139.177.73 CE Address : 68.139.177.74 QoS - Egress Profile: R12 |  | DS1 (29090231) | TDM | CENTURYLINK (2909023155633001) | 04/30/2019 (2909023155633001) | 05/08/2019 (2909023155633001) | 05/14/2019 (2909023155633001) |  |  | DEMARCDET - 1st flr eletrical room wall mounted housing 1 slot 1 of 2 |  | LISA MCNAMARA 1-952-202-0242 lisa_mcnamara@uhg.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 05/14/2019(Private IP - PIP) 05/14/2019(WAN Analysis Reporting) 05/14/2019(Access) |  |  | 05/15/2019 (29090230) 05/13/2019 (29090231) | 05/21/2019 05/27/2019 | 05/14/2019 |  | Completed | N (29090230) N (29090232) N (29090231) | U0101953 |  | NSPE0012855028 Order Request # 198681945 | NSPE0012855028
Completed | FL411 Kissimmee, FL | 306 E OAK ST KISSIMMEE, FL 34744-4537 US | 50 MBPS (29091695) | 07/01/2019: Background: 50 Mbps / 50 Mbps / Access, Private IP (PIP) / KISSIMMEE, FL, US / CENTURYLINK / Dual NID Status: Ready for activation Telco Circuit ID: 25.KXGS.409476..UFLG Telco Demarcation: 1st floor, telco room, wall mounted, not extended, t/l, RAD203 Port 2 EQUIPMENT & PORT: RAD 203 port 2 Verizon BEAS Circuit ID: USAFL55639579COV400001 / E4044631 Verizon BEAS Demarcation: Port: 1; Floor: 1; MM LC interface, port 1. | 198682689 | FL411 | Private IP - PIP (29091694) WAN Analysis Reporting (29091696) Access (29091695) | 29091694 29091696 29091695 | 50 MBPS (29091694) |  | 94633844 (Private IP (PIP)) 94633849 (WAN Analysis Reporting) 94633846 (Access) | C4017216/ADD (29091694) E4044631/ADD (29091695) | 25.KXGS.409476..UFLG (2909169555639501) | 6055344 | 5500 | PVC ID : 6055344 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64870 PE IP Address : 68.136.247.93 CE Address : 68.136.247.94 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29091695) | 1000Base-SX (850nm, Multi Mode Fiber) (29091695) | Ethernet | CENTURYLINK (2909169555639501) | 05/23/2019 (2909169555639501) | 06/26/2019 (2909169555639501) | 06/27/2019 (2909169555639501) | 07/01/2019 (VFORCE) (29091695) | 07/01/2019 (VFORCE) (29091695) | DEMARCDET - X |  | Edy Ramos 1-407-989-9869 enieves@wellmed.net | Manish Sarkhel | manish_sarkhel@optum.com | 632-671-2655 | 07/01/2019(Private IP - PIP) 07/01/2019(WAN Analysis Reporting) 07/01/2019(Access) |  |  | 07/08/2019 (29091694) 07/03/2019 (29091695) | 06/07/2019 06/13/2019 | 07/01/2019 |  | Completed | N (29091694) N (29091696) N (29091695) | U0101953 | Jeopardy Notification 1 (06/17/2019) | NSPE0012855265 Order Request # 198682707 | NSPE0012855265
Completed | Downey, CA | 11525 BROOKSHIRE AVE STE 400 DOWNEY, CA 90241-4982 US | 50 MBPS (29112321) | 08/27/2019 - Successfully activated | 198706971 | Location4504981045 | Private IP - PIP (29112320) WAN Analysis Reporting (29112322) Access (29112321) | 29112320 29112322 29112321 | 20 MBPS (29112320) |  | 94635004 (Private IP (PIP)) 94635009 (WAN Analysis Reporting) 94635002 (Access) | C4017264/ADD (29112320) E4044747/ADD (29112321) | 45/KFGS/121421//FTNC/ (2911232185207501) | 6055829 | 13000 | PVC ID : 6055829 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64836 PE IP Address : 152.185.196.97 CE Address : 152.185.196.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29112321) | 1000Base-SX (850nm, Multi Mode Fiber) (29112321) | Ethernet | FRONTIER (2911232185207501) | 05/03/2019 (2911232185207501) | 06/03/2019 (2911232185207501) | 05/23/2019 (2911232185207501) | 05/28/2019 (VFORCE) (29112321) | 05/28/2019 (VFORCE) (29112321) |  |  | SEAN IGARTA 1-714-443-4534 sean.igarta@applecare.com | RANJI ADHIKARI | ranjit_adhikari@optum.com | 1-763-744-1957 | 05/24/2019(Private IP - PIP) 05/24/2019(WAN Analysis Reporting) 05/24/2019(Access) | 08/27/2019 |  | 06/12/2019 (29112320) 06/10/2019 (29112321) | 06/12/2019 06/18/2019 | 05/24/2019 |  | Completed | N (29112320) N (29112322) N (29112321) | U0101953 |  | NSPE0012863382 Order Request # 198706661 | NSPE0012863382
Completed | Miami, FL | 50 NE 9TH ST FL 4 MIAMI, FL 33132-1709 US | 300 MBPS (29084603) | 08/02/2019: 08/01 Successfully activated | 198673115 | Location2775909610 | Private IP - PIP (29084602) WAN Analysis Reporting (29084604) Access (29084603) | 29084602 29084604 29084603 | 300 MBPS (29084602) |  | 94633600 (Private IP (PIP)) 94633398 (WAN Analysis Reporting) 94633602 (Access) | C5007244/ADD (29084602) E5017879/ADD (29084603) |  | 6055378 | 50000 | PVC ID : 6055378 VPN Name : UnitedHealthGroup Router Name : 1MJ3E02 VRF Name : Vd46047-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65146 PE IP Address : 206.115.4.37 CE Address : 206.115.4.38 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (29084603) | Ethernet |  |  |  |  | 05/28/2019 (CCP) (29084602) 05/28/2019 (CCP) (29084603) | 05/21/2019 (CCP) (29084602) 05/21/2019 (CCP) (29084603) |  |  | Nandini Ramond 1-385-259-0198 nandini.ramond@optum.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 05/21/2019(Private IP - PIP) 05/21/2019(WAN Analysis Reporting) 05/21/2019(Access) | 08/01/2019 |  | 05/21/2019 (29084602) 05/17/2019 (29084603) | 05/07/2019 05/13/2019 | 05/21/2019 |  | Completed | N (29084602) N (29084604) N (29084603) | U0101953 |  | NSPE0012851917 Order Request # 198673033 | NSPE0012851917
Completed | FL369 LAKE MARY, FL | 100 TECHNOLOGY PARK STE 155 LAKE MARY, FL 32746-6205 US | 200 MBPS (29254418) | 08/09/2019: Background: 200 Mbps / 100 Mbps / Access, Private IP (PIP) / LAKE MARY, FL, US / BRIGHT HOUSE / DUAL NID / ENID Status: Loop delivered; BEAS installed > Ready for activation once customer completes their internal cabling Telco Circuit ID: 40.L1XX.823686..TWCC Telco Demarcation: MDF in the suite 155 . LEC SETTINGS : . LEC NID : Adva 114 pro port 3 Verizon BEAS Circuit ID: USAFL56880801COV400001 / E5018428 Verizon BEAS Demarcation: Bay 2, Shelf 2, Slot 28, Port 4, Floor 1, Server Room | 198845775 | FL369 | Private IP - PIP (29254417) WAN Analysis Reporting (29254419) Access (29254418) | 29254417 29254419 29254418 | 100 MBPS (29254417) |  | 94639560 (Private IP (PIP)) 94639567 (WAN Analysis Reporting) 94639563 (Access) | C5007486/ADD (29254417) E5018428/ADD (29254418) | 40.L1XX.823686..TWCC (2925441856880801) | 6059533 | 30000 | PVC ID : 6059533 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65130 PE IP Address : 152.162.245.69 CE Address : 152.162.245.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29254418) | 1000Base-SX (850nm, Multi Mode Fiber) (29254418) | Ethernet | BRIGHT HOUSE (2925441856880801) | 05/21/2019 (2925441856880801) | 09/12/2019 (2925441856880801) | 08/08/2019 (2925441856880801) | 08/09/2019 (VFORCE) (29254418) | 08/09/2019 (VFORCE) (29254418) | DEMARCDET - MDF in the suite 155 |  | Rudina Lachman 1-321-315-2177 Rudina.Lachman@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 08/09/2019(Private IP - PIP) 08/09/2019(WAN Analysis Reporting) 08/09/2019(Access) |  |  | 09/23/2019 (29254417) 09/19/2019 (29254418) | 12/03/2019 12/09/2019 | 08/09/2019 |  | Completed | N (29254417) N (29254419) N (29254418) | U0101953 | Jeopardy Notification 4 (07/17/2019) | NSPE0012901100 Order Request # 198845683 | NSPE0012901100
Completed | MO021 SAINT LOUIS, MO, US | 450 N NEW BALLAS RD SAINT LOUIS, MO 63141-6859 US | 100 MBPS (29254503) | 07/25/2019: 7/25Background: MO021 SAINT LOUIS, MO / 100 Mbps / 50 Mbps / Access, Private IP (PIP) / CHARTER Status: Loop delivered 7/24; Beas7/25, access secured Next Action: Line testing Who owns the next action: SD | 198850091 | MO021 | Private IP - PIP (29254502) WAN Analysis Reporting (29254504) Access (29254503) | 29254502 29254504 29254503 | 50 MBPS (29254502) |  | 94639295 (Private IP (PIP)) 94639293 (WAN Analysis Reporting) 94639291 (Access) | C1091344/ADD (29254502) E4046100/ADD (29254503) | 31.L1XX.803283..TWCC (2925450356995801) | 6059538 | 30000 | PVC ID : 6059538 VPN Name : UnitedHealthGroup Router Name : STLS3E01 VRF Name : V432785-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65139 PE IP Address : 147.225.123.221 CE Address : 147.225.123.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29254503) | 1000Base-SX (850nm, Multi Mode Fiber) (29254503) | Ethernet | CHARTER (2925450356995801) | 05/28/2019 (2925450356995801) | 08/12/2019 (2925450356995801) | 07/24/2019 (2925450356995801) | 07/25/2019 (VFORCE) (29254503) |  | DEMARCDET - wall mounted in server closet Adva 114 pro port 3 |  | John Raniero 1-314-227-2560 John.Raniero@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 07/25/2019(Private IP - PIP) 07/25/2019(WAN Analysis Reporting) 07/25/2019(Access) |  |  | 08/21/2019 (29254502) 08/19/2019 (29254503) | 08/28/2019 09/03/2019 | 07/25/2019 |  | Completed | N (29254502) N (29254504) N (29254503) | U0101953 | Jeopardy Notification 3 (06/17/2019) | NSPE0012902560 Order Request # 198850061 | NSPE0012902560
Completed | AZ074 Phoenix, AZ | 23620 N 20TH DR STE 12 PHOENIX, AZ 85085-0621 US | 400 MBPS (29254718) | 07/11/2019: 7/11Background: AZ074Phoenix, AZ; 400 Mbps / 200 Mbps / Access, Private IP (PIP) / COX / Dual NID / ENID Status: Ready for activation once customer internal cabling is complete Next action: Order closure | 198851753 | AZ074 | Access (29254718) Private IP - PIP (29254717) WAN Analysis Reporting (29254719) | 29254718 29254717 29254719 | 200 MBPS (29254717) |  | 94639111 (Access) 94639107 (Private IP (PIP)) 94639109 (WAN Analysis Reporting) | E5018431/ADD (29254718) C5007491/ADD (29254717) |  | 6059552 | 200000 | PVC ID : 6059552 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64901 PE IP Address : 152.164.124.249 CE Address : 152.164.124.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29254718) | 1000Base-SX (850nm, Multi Mode Fiber) (29254718) | Ethernet | COX (2925471856825201) | 05/31/2019 (2925471856825201) | 06/26/2019 (2925471856825201) | 06/18/2019 (2925471856825201) | 07/10/2019 (VFORCE) (29254718) | 07/10/2019 (VFORCE) (29254718) | DEMARCDET - 1st flr inside apothocary data rm, RR NORTH WEST CORNEL WALL |  | Cliff Waldrep 1-480-881-8560 Clifton.Waldrep@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 07/11/2019(Access) 07/11/2019(Private IP - PIP) 07/11/2019(WAN Analysis Reporting) |  |  | 07/11/2019 (29254718) 07/15/2019 (29254717) | 08/13/2019 08/19/2019 | 07/11/2019 |  | Completed | N (29254718) N (29254717) N (29254719) | U0101953 | Jeopardy Notification 1 (07/01/2019) | NSPE0012901270 Order Request # 198846217 | NSPE0012901270
Completed | CO103 Denver, CO | 1245 E COLFAX AVE STE 102 DENVER, CO 80218-2216 US | 100 MBPS (29254893) | 06/17/2019: Background: 100 Mbps / 50 Mbps / Access, Private IP (PIP) / DENVER, CO, US / CENTURYLINK Status: Ready for activation Telco Circuit ID: 29.KXGS.416948..MS Telco Demarcation: MPOP BASEMENT WALL MOUNT CIENA 3916 PORT 4, MULTI MODE HANDOFF Type OPTICAL Port 4 Verizon BEAS Circuit ID: USACO56680641COV400001 / E4046124 Verizon BEAS Demarcation: Aisle: 1 Bay: 1 Shelf: 1 Slot: 1 Port: 1 Floor: 1 Room: 1 | 198851879 | CO103 | Private IP - PIP (29254892) WAN Analysis Reporting (29254894) Access (29254893) | 29254892 29254894 29254893 | 50 MBPS (29254892) |  | 350331485 (Private IP (PIP)) 350331487 (WAN Analysis Reporting) 350331481 (Access) | C1091357/ADD (29254892) E4046124/ADD (29254893) | 29.KXGS.416948..MS (2925489356680601) | 6059561 | 30000 | PVC ID : 6059561 VPN Name : UnitedHealthGroup Router Name : DNVR9E01 VRF Name : V483292:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65233 PE IP Address : 152.176.230.133 CE Address : 152.176.230.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29254893) | 1000Base-SX (850nm, Multi Mode Fiber) (29254893) | Ethernet | CENTURYLINK (2925489356680601) | 05/21/2019 (2925489356680601) | 06/03/2019 (2925489356680601) | 06/03/2019 (2925489356680601) | 06/20/2019 (VFORCE) (29254893) |  | DEMARCDET - MPOP BASEMENT WALL MOUNT CIENA 3916 PORT 4 MULTI MODE HANDOFF Type OPTICAL Port 4 |  | Solomon Victor 91-990-179-8210 solomon_victor@optum.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 06/14/2019(Private IP - PIP) 06/14/2019(WAN Analysis Reporting) 06/14/2019(Access) |  |  | 06/13/2019 (29254892) 06/11/2019 (29254893) | 07/15/2019 07/19/2019 | 06/14/2019 |  | Completed | N (29254892) N (29254894) N (29254893) | U0101953 | Jeopardy Notification 1 (06/03/2019) | NSPE0012902284 Order Request # 198849333 | NSPE0012902284
Completed | CA382 SACRAMENTO, CA | 2288 AUBURN BLVD STE 102 SACRAMENTO, CA 95821-1619 US | 200 MBPS (29254981) | 07/01/2019: Background: CA382 Sacramento, CA; New 200M/100M PIP-Eth; (Consolidated Comm); Dual NID; No MNS; ENID Status: Ready for activation once customer internal cabling is complete Telco Circuit ID: 18/KRGN/053585//RIV/ Telco Demarcation: epoe first flr, ckt mrv port 5 multimode SFP labbelled wit ckkt id Verizon BEAS Circuit ID: USACA56678887COV400001 Verizon BEAS Demarcation: Aisle: 1; Bay: 1; Shelf: 5; Slot: 0.4; Port: 0.4; Floor: 1; Room: 102; Left beas in mpoe for testing as instructed | 198851935 | CA382 | Access (29254981) Private IP - PIP (29254980) WAN Analysis Reporting (29254982) | 29254981 29254980 29254982 | 100 MBPS (29254980) |  | 350326499 (Access) 350326503 (Private IP (PIP)) 350326505 (WAN Analysis Reporting) | E5018433/ADD (29254981) C5007490/ADD (29254980) | 18/KRGN/053585//RIV/ (2925498156678801) | 6059556 | 30000 | PVC ID : 6059556 VPN Name : UnitedHealthGroup Router Name : SCM3E03 VRF Name : V447827-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64516 PE IP Address : 152.176.196.245 CE Address : 152.176.196.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29254981) | 1000Base-SX (850nm, Multi Mode Fiber) (29254981) | Ethernet | ROSEVILLE TEL ROSEVILLECA (2925498156678801) | 05/21/2019 (2925498156678801) | 06/27/2019 (2925498156678801) | 06/28/2019 (2925498156678801) | 06/28/2019 (VFORCE) (29254981) |  | DEMARCDET - epoe first flr ckt mrv port 5 multimode SFP labbelled wit ckkt id |  | David Gonzalez 1-916-342-9599 David.Gonzalez@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 06/28/2019(Access) 06/28/2019(Private IP - PIP) 06/28/2019(WAN Analysis Reporting) |  |  | 07/05/2019 (29254981) 07/09/2019 (29254980) | 07/01/2019 07/05/2019 | 06/28/2019 |  | Completed | N (29254981) N (29254980) N (29254982) | U0101953 |  | NSPE0012902169 Order Request # 198848969 | NSPE0012902169
Completed | AZ078 Phoenix, AZ | 24416 N 19TH AVE PHOENIX, AZ 85085-1887 US | 400 MBPS (29255005) | 06/05/2019: Background: 400 Mbps / 200 Mbps / Access, Private IP (PIP) / PHOENIX, AZ, US / CENTURYLINK Status: Ready for activation Telco Circuit ID: 19.KXGS.416940..MS Telco Demarcation: 1ST FLOOR SERVER ROOM RACK MOUNT EQUIPMENT & PORT: Cisco 3750 port 2 Verizon BEAS Circuit ID: USAAZ56772207COV400001 / E5018432 Verizon BEAS Demarcation: Aisle: 1 Bay: 1 Shelf: Middle of the relay rack Slot: X Port: 1 Floor: 1st Room: Server room Jack Type: Lc Interface Type: Optical labeled 29255005 | 198852021 | AZ078 | Private IP - PIP (29255004) WAN Analysis Reporting (29255006) Access (29255005) | 29255004 29255006 29255005 | 200 MBPS (29255004) |  | 94638527 (Private IP (PIP)) 94638532 (WAN Analysis Reporting) 94638530 (Access) | C5007489/ADD (29255004) E5018432/ADD (29255005) | 19.KXGS.416940..MS (2925500556772201) | 6059557 | 110000 | PVC ID : 6059557 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64533 PE IP Address : 152.176.183.105 CE Address : 152.176.183.106 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29255005) | 1000Base-SX (850nm, Multi Mode Fiber) (29255005) | Ethernet | CENTURYLINK (2925500556772201) | 05/21/2019 (2925500556772201) | 06/03/2019 (2925500556772201) | 06/03/2019 (2925500556772201) | 06/05/2019 (VFORCE) (29255005) | 06/05/2019 (VFORCE) (29255005) | DEMARCDET - X |  | Cliff Waldrep 1-480-881-8560 Clifton.Waldrep@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 06/05/2019(Private IP - PIP) 06/05/2019(WAN Analysis Reporting) 06/05/2019(Access) |  |  | 06/12/2019 (29255004) 06/10/2019 (29255005) | 07/11/2019 07/17/2019 | 06/05/2019 |  | Completed | N (29255004) N (29255006) N (29255005) | U0101953 | Jeopardy Notification 1 (05/30/2019) | NSPE0012902671 Order Request # 198850363 | NSPE0012902671
Completed | NV110 LAS VEGAS, NV | 701 SHADOW LN LAS VEGAS, NV 89106-4131 US | 100 MBPS (29255340) | 06/20/2019 Background: 100 Mbps / 50 Mbps / Access, Private IP (PIP) / LAS VEGAS, NV, US / COX Status: Ready for activation Telco Circuit ID: 33.KFGX.001935..COXC Telco Demarcation: FAR LEFT OF WALL BOARD BEHIND SERVER RACK EQUIPMENT & PORT: NOKIA 7210 SAS MXP PORT # 4 Verizon BEAS Circuit ID: USANV57002021COV400001 / E4046126 Verizon BEAS Demarcation: 1st floor customer data closet, RU 16. Box is pingable, verified by BNE | 198850907 | NV110 | Access (29255340) Private IP - PIP (29255339) WAN Analysis Reporting (29255341) | 29255340 29255339 29255341 | 50 MBPS (29255339) |  | 94639469 (Access) 94639467 (Private IP (PIP)) 94639471 (WAN Analysis Reporting) | E4046126/ADD (29255340) C1091358/ADD (29255339) |  | 6059569 | 30000 | PVC ID : 6059569 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64668 PE IP Address : 199.220.138.53 CE Address : 199.220.138.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29255340) | 1000Base-SX (850nm, Multi Mode Fiber) (29255340) | Ethernet | COX (2925534057002002) | 05/22/2019 (2925534057002002) | 06/19/2019 (2925534057002002) | 06/19/2019 (2925534057002002) | 06/21/2019 (VFORCE) (29255340) | 06/21/2019 (VFORCE) (29255340) | DEMARCDET - 1ST FLOOR SERVER RM |  | Leana Ramirez 1-702-755-2401 Leana.Ramierz@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 06/21/2019(Access) 06/21/2019(Private IP - PIP) 06/21/2019(WAN Analysis Reporting) |  |  | 06/20/2019 (29255340) 06/24/2019 (29255339) | 07/11/2019 07/17/2019 | 06/21/2019 |  | Completed | N (29255340) N (29255339) N (29255341) | U0101953 | Jeopardy Notification 2 (05/28/2019) | NSPE0012902824 Order Request # 198850763 | NSPE0012902824
Completed | OH067 Columbus, OH | 4830 KNIGHTSBRIDGE BLVD COLUMBUS, OH 43214-2300 US | 50 MBPS (29263590) | 06/20/2019 - Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / COLUMBUS, OH, US / TIME WARNER CABLE Status: Ready for activation Telco Circuit ID: 61.L1XX.993509..TWCC Telco Demarcation: floor suite C network room rack #1 rad 203 port 5 Verizon BEAS Circuit ID: USAOH57003191COV400001 / E4046182 Verizon BEAS Demarcation: Installed overture in suite c network room customer rack | 198855261 | OH067 | Private IP - PIP (29263589) WAN Analysis Reporting (29263591) Access (29263590) | 29263589 29263591 29263590 | 20 MBPS (29263589) |  | 94639603 (Private IP (PIP)) 94639610 (WAN Analysis Reporting) 94639606 (Access) | C4018119/ADD (29263589) E4046182/ADD (29263590) | 61.L1XX.993509..TWCC (2926359057003101) | 6059762 | 18000 | PVC ID : 6059762 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64647 PE IP Address : 68.137.29.185 CE Address : 68.137.29.186 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29263590) | 1000Base-SX (850nm, Multi Mode Fiber) (29263590) | Ethernet | TIME WARNER CABLE (2926359057003101) | 05/22/2019 (2926359057003101) | 07/08/2019 (2926359057003101) | 06/19/2019 (2926359057003101) | 06/20/2019 (VFORCE) (29263590) | 06/20/2019 (VFORCE) (29263590) | DEMARCADDR - . DEMARCDET - 1st floor suite C network room rack #1 rad 203 port 5 |  | David Brandebura 1-877-360-2801 David.Brandebura@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 06/20/2019(Private IP - PIP) 06/20/2019(WAN Analysis Reporting) 06/20/2019(Access) |  |  | 07/17/2019 (29263589) 07/15/2019 (29263590) | 07/02/2019 07/08/2019 | 06/20/2019 |  | Completed | N (29263589) N (29263591) N (29263590) | U0101953 | Jeopardy Notification 2 (05/28/2019) | NSPE0012904073 Order Request # 198855197 | NSPE0012904073
Completed | AZ076 PHOENIX, AZ | 1101 N CENTRAL AVE PHOENIX, AZ 85004-1808 US | 200 MBPS (29273375) | 07/01/2019: Background: 200 Mbps / 100 Mbps / Access, Private IP (PIP) / PHOENIX, AZ, US / COX / ENID Status: Ready for activation once customer internal cabling is complete Telco Circuit ID: 23.KFGX.991602..COXC. Telco Demarcation: customer suite wall mounted in electrical rm on the ground flr demarc panel port 16 Verizon BEAS Circuit ID: USAAZ56761109COV400001 / E5018475 Verizon BEAS Demarcation: pending customer internal cabling, left at 1st floor | 198880105 | AZ076 | WAN Analysis Reporting (29273376) Access (29273375) Private IP - PIP (29273374) | 29273376 29273375 29273374 | 100 MBPS (29273374) |  | 94638600 (WAN Analysis Reporting) 94638605 (Access) 94638602 (Private IP (PIP)) | C5007507/ADD (29273374) E5018475/ADD (29273375) |  | 6059994 | 70000 | PVC ID : 6059994 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64749 PE IP Address : 206.115.67.13 CE Address : 206.115.67.14 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29273375) | 1000Base-SX (850nm, Multi Mode Fiber) (29273375) | Ethernet | COX (2927337556761101) | 05/28/2019 (2927337556761101) | 06/27/2019 (2927337556761101) | 06/25/2019 (2927337556761101) | 07/02/2019 (VFORCE) (29273375) | 07/02/2019 (VFORCE) (29273375) | DEMARCDET - customer suite wall mounted in electrical rm on the ground flr demarc panel port 16 |  | Dan Lindell 1-602-526-8547 Dan.Lindell@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 06/28/2019(WAN Analysis Reporting) 06/28/2019(Access) 06/28/2019(Private IP - PIP) |  |  | 07/03/2019 (29273374) 07/01/2019 (29273375) | 07/18/2019 07/12/2019 | 06/28/2019 |  | Completed | N (29273376) N (29273375) N (29273374) | U0101953 | Jeopardy Notification 1 (05/28/2019) | NSPE0012908593 Order Request # 198877195 | NSPE0012908593
Provisioning Accepted | BOBLC5X60001 | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 4000 MBPS (CQBLRV75) | 05/30/2019: 5/30 Status- PIP-O change orders, pending OE(Order Entry) | 9912920 |  | Private IP Port Only (CQBLRV75) | CQBLRV75 | 4000 MBPS | P2198253 |  | BOBLC5X60001 (CQBLRV75) |  | 5997743 | 768 | PVC ID : 5997743 VPN Name : UHG-SDWAN Router Name : MZZ9E01 VRF Name : Vd76606:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.161.122.109 CE Address : 152.161.122.110 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0015072950001 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/31/2019 (CQBLRV75) | 06/03/2019 |  | 05/31/2019 (CQBLRV75) | 06/24/2019 (CQBLRV75) |  |  |  | N (CQBLRV75) | 05017789 |  | NSPE0012914082 | NSPE0012914082
Completed | BOBLC5XS0001 | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 4000 MBPS (CQBLRV6X) | 05/30/2019: 5/30 Status: Pending OE | 9912965 |  | Private IP Port Only (CQBLRV6X) | CQBLRV6X | 4000 MBPS | P2198241 |  | BOBLC5XS0001 (CQBLRV6X) |  | 5998251 | 72000 | PVC ID : 5998251 VPN Name : UHG-SDWAN Router Name : MN39E01 VRF Name : Vd76602:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.164.75.1 CE Address : 152.164.75.2 QoS - Egress Profile: R12 | [11 empty] | MELISSA CHAPMAN 0015072950001 TIM_GUNDERSON@OPTUM.COM |  |  |  | 06/03/2019 (CQBLRV6X) | 06/03/2019 |  | 06/24/2019 (CQBLRV6X) | 06/24/2019 (CQBLRV6X) |  |  |  | N (CQBLRV6X) | 05017789 |  | NSPE0012914082 | NSPE0012914082
Completed | AZ077 Scottsdale, AZ | 9777 N 91ST ST STE 102 SCOTTSDALE, AZ 85258-5087 US | 100 MBPS (29294289) | 06/17/2019: Background: AZ077 SCOTTSDALE, AZ / 100 Mbps / 50 Mbps / Access, Private IP (PIP) / CENTURYLINK / ENID Status: Ready for activation once customer internal cabling is complete Telco Circuit ID: 19.KXGS.418332..MS Telco Demarcation: 1ST FLOOR SERVER ROOM STE 102. CUSTOMER RR/ SH 21 3916 PORT 3 Verizon BEAS Circuit ID: /USAAZ56585767COV400001 Verizon BEAS Demarcation: 1st floor of the customer's network equipment room. Its mounted in their data rack, RU 14. | 198912563 | AZ077 | Private IP - PIP (29294288) WAN Analysis Reporting (29294290) Access (29294289) | 29294288 29294290 29294289 | 50 MBPS (29294288) |  | 94637016 (Private IP (PIP)) 94637018 (WAN Analysis Reporting) 94637020 (Access) | C1091595/ADD (29294288) E4046368/ADD (29294289) | 19.KXGS.418332..MS (2929428956585701) | 6060575 | 30000 | PVC ID : 6060575 VPN Name : Chicos-Corp Router Name : PHN19E01 VRF Name : Vd42855:ChicosCorp Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64667 PE IP Address : 199.220.200.173 CE Address : 199.220.200.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29294289) | 1000Base-SX (850nm, Multi Mode Fiber) (29294289) | Ethernet | CENTURYLINK (2929428956585701) | 05/28/2019 (2929428956585701) | 06/13/2019 (2929428956585701) | 06/12/2019 (2929428956585701) | 06/14/2019 (VFORCE) (29294289) | 06/14/2019 (VFORCE) (29294289) | DEMARCDET - 1ST FLOOR SERVER ROOM STE 102. CUSTOMER RR/ SH 21 3916 PORT 3 |  | Harshal Shah 1-480-451-3771 Harshal.Shah@avella.com | Solomon Victor | solomon_victor@optum.com | 91-990-179-8210 | 06/14/2019(Private IP - PIP) 06/14/2019(WAN Analysis Reporting) 06/14/2019(Access) |  |  | 06/24/2019 (29294288) 06/20/2019 (29294289) | 07/08/2019 07/12/2019 | 06/14/2019 |  | Completed | N (29294288) N (29294290) N (29294289) | U0101953 |  | NSPE0012914343 Order Request # 198910893 | NSPE0012914343
Completed | MI073 Southfield, MI | 3000 TOWN CTR SOUTHFIELD, MI 48075-1102 US | 100 MBPS (29294523) | 08/22/2019: Background: MI073 Southfield, MI; New 100M/100M PIP-Eth; (XO); Dual NID; No MNS / ENID Status: Ready for activation once customer power and server room are build and ready Telco Circuit ID: CL/L2YX/323331/ /TQW Telco Demarcation: 14th floor telephone closet wall mounted Verizon BEAS Circuit ID: USAMI56582115COV400001 / E4046444 Verizon BEAS Demarcation: Circuit is wall mounted in the 14th floor telephone closet | 198912791 | MI073 | Access (29294523) Private IP - PIP (29294522) WAN Analysis Reporting (29294524) | 29294523 29294522 29294524 | 100 MBPS (29294522) |  | 94641985 (Access) 94641983 (Private IP (PIP)) 94641988 (WAN Analysis Reporting) | E4046444/ADD (29294523) C1091682/ADD (29294522) | CL/L2YX/323331/ /TQW /ELK (2929452356582101) | 6060960 | 50000 | PVC ID : 6060960 VPN Name : UnitedHealthGroup Router Name : NORXE05 VRF Name : V575848-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65263 PE IP Address : 152.177.188.41 CE Address : 152.177.188.42 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (29294523) | 1000Base-LX (1310nm Single Mode Fiber) (29294523) | Ethernet | XO (2929452356582101) | 06/13/2019 (2929452356582101) | 07/31/2019 (2929452356582101) | 07/30/2019 (2929452356582101) | 08/21/2019 (VFORCE) (29294523) |  | DEMARCDET - 14TH FLR TELCO RM WALL MOUNTED PORT 1 AND 2 |  | Glenn Joseph 1-248-765-4832 gjoseph@ismofmi.com | Sudhanshu Dutt Tiwari | sudhanshu_tiwari@optum.com | 91-804-670-4384 | 08/21/2019(Access) 08/21/2019(Private IP - PIP) 08/21/2019(WAN Analysis Reporting) |  |  | 08/27/2019 (29294523) 08/29/2019 (29294522) | 09/30/2019 10/04/2019 | 08/21/2019 |  | Scheduled | N (29294523) N (29294522) N (29294524) | U0101953 | Jeopardy Notification 2 (08/08/2019) | NSPE0012914899 Order Request # 198912269 | NSPE0012914899
Completed | Sungard Recovery Services; Philadelphia, PA | 401 N BROAD ST PHILADELPHIA, PA 19108-1001 US | 50 MBPS (29299543) | 06/13/2019: 6/13Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / PHILADELPHIA, PA, US Status:Order complete- Ready for use Next Action: Ready for use Who owns the next action: CCR PM | 198918489 | SUNGARD RECOVERY SERVICES | Private IP - PIP (29299542) WAN Analysis Reporting (29299544) Access (29299543) | 29299542 29299544 29299543 | 20 MBPS (29299542) |  | 351666093 (Private IP (PIP)) 351666103 (WAN Analysis Reporting) 351665647 (Access) | C4018234/ADD (29299542) E4046410/ADD (29299543) |  | 6060705 | 13000 | PVC ID : 6060705 VPN Name : UnitedHealthGroup Router Name : PTNGE01 VRF Name : V201207:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64732 PE IP Address : 68.139.143.193 CE Address : 68.139.143.194 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (29299543) | Ethernet | [8 empty] | David Zach 1-215-351-1068 david.zach@sungardas.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 06/13/2019(Private IP - PIP) 06/13/2019(WAN Analysis Reporting) 06/13/2019(Access) |  |  | 06/21/2019 (29299542) 06/19/2019 (29299543) | 06/25/2019 07/01/2019 | 06/13/2019 |  | Completed | N (29299542) N (29299544) N (29299543) | U0101953 |  | NSPE0012915184 Order Request # 198913595 | NSPE0012915184
Completed | IL134 Moline, IL | 101 17TH ST MOLINE, IL 61265 US | 50 MBPS (29312465) | 08/27/2019 Successfully activated | 198959091 | IL134 | Private IP - PIP (29312464) WAN Analysis Reporting (29312466) Access (29312465) | 29312464 29312466 29312465 | 10 MBPS (29312464) |  | 94642375 (Private IP (PIP)) 94642371 (WAN Analysis Reporting) 94642373 (Access) | C4018295/ADD (29312464) E4046456/ADD (29312465) | /OBGS/706477//LB (2931246557593801) c5ueg d2dp0013 (I0000353.DVP) c5a89 a89 0039 (I0184786.CFO) | 6061033 | 10000 | PVC ID : 6061033 VPN Name : UnitedHealthGroup Router Name : DNG9E03 VRF Name : Vc53414:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64619 PE IP Address : 152.162.79.41 CE Address : 152.162.79.42 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (29312465) | Ethernet | CENTURYLINK (2931246557593801) | 06/05/2019 (2931246557593801) | 06/19/2019 (2931246557593801) 07/09/2019 (I0000353.DVP) 07/09/2019 (I0184786.CFO) | 07/09/2019 (2931246557593801) | 07/10/2019 (VFORCE) (29312465) | 07/10/2019 (VFORCE) (29312465) | DEMARCDET - 2ND FLR, TELCO OR DATA RM, PATCH PANEL 1,PORTS 21 AND 22 HARD LOOP LEFT TAGGED NOT EXTENDED |  | MATT SCHABOWSKI 1-952-202-0145 matthew_schabowski1@uhg.com | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 07/10/2019(Private IP - PIP) 07/10/2019(WAN Analysis Reporting) 07/10/2019(Access) | 08/27/2019 |  | 07/11/2019 (29312464) 07/09/2019 (29312465) | 07/10/2019 07/16/2019 | 07/10/2019 |  | Completed | N (29312464) N (29312466) N (29312465) | U0101953 |  | NSPE0012920583 Order Request # 198958933 | NSPE0012920583
Completed | Fort Pierce, FL | 2940 S US HIGHWAY 1 FORT PIERCE, FL 34982-8141 US | 50 MBPS (29313200) | 08/28/2019: 8/28Background: FL394 Fort Pierce, FL; New 50M/10M PIP-Etth; (Comcast); Dual NID; No MNS; ENID Status: Ready for activation Telco Circuit ID: 38.KGGS.018772..CBCL.. Telco Demarcation: 1ST FLR SERVER CLOSET WALL MOUNTED TAGGED WITH THE CLLI CODE EQUIPMENT & PORT:CIENA 3903 PORT 2 Verizon BEAS Circuit ID: USAFL57495731COV400001 / E4046458 Verizon BEAS Demarcation: 1st floor, server room, data rack position U42 | 198960833 | FL394 | Private IP - PIP (29313199) WAN Analysis Reporting (29313201) Access (29313200) | 29313199 29313201 29313200 | 10 MBPS (29313199) |  | 355833495 (Private IP (PIP)) 355833497 (WAN Analysis Reporting) 355833491 (Access) | C4018255/ADD (29313199) E4046458/ADD (29313200) | 38.KGGS.018772..CBCL.. (2931320057495701) | 6061054 | 5500 | PVC ID : 6061054 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64758 PE IP Address : 68.139.217.241 CE Address : 68.139.217.242 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29313200) | 1000Base-SX (850nm, Multi Mode Fiber) (29313200) | Ethernet | COMCAST (2931320057495701) | 08/26/2019 (2931320057495701) | 08/29/2019 (2931320057495701) | 08/27/2019 (2931320057495701) | 08/28/2019 (VFORCE) (29313200) |  | DEMARCDET - 1ST FLR SERVER CLOSET WALL MOUNTED TAGGED WITH THE CLLI CODE |  | Rebecca Rikarts 1-813-349-6292 rrikarts@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 08/28/2019(Private IP - PIP) 08/28/2019(WAN Analysis Reporting) 08/28/2019(Access) |  |  | 09/10/2019 (29313199) 09/06/2019 (29313200) | 10/04/2019 10/10/2019 | 08/28/2019 |  | Completed | N (29313199) N (29313201) N (29313200) | U0101953 | Jeopardy Notification 2 (08/23/2019) | NSPE0012920869 Order Request # 198959949 | NSPE0012920869
Completed | FL371 Ruskin, FL | 819 CYPRESS VILLAGE BLVD RUSKIN, FL 33573-6834 US | 50 MBPS | 06/04/2019: 06/03 Successfully removed VLAN tagging. | 198981571 | FL371 | Private IP - PIP (29319827) Access WAN Analysis Reporting (29319829) | 29319827 29319829 | 10 MBPS (29319827) |  | 94591576 (Private IP (PIP)) 94591579 94591582 (WAN Analysis Reporting) | C4015144/NONE (29319827) |  | 6021999 | 5000 | PVC ID : 6021999 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64935 PE IP Address : 68.136.11.253 CE Address : 68.136.11.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | TODD VANDERSCHAEGEN 1-210-780-6809 tvanderschaegen@wellmed.net | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 06/03/2019(Private IP | 06/03/2019 |  | 05/31/2019 (29319827) | 06/11/2019 06/11/2019 (24822703.1) | 06/03/2019 |  | Activated/Installed Completed | N (29319827) N N (29319829) | U0101953 |  | Order Request # 198981321 | NSPE0012923051
Completed | FL372 Brandon, FL | 1072 E BRANDON BLVD BRANDON, FL 33511-5509 US | 50 MBPS (29323570) | 08/23/2019: Background: FL372 Brandon, FL; New 20M/50M PIP-Eth; (Brighthouse); Dual NID; No MNS; Status: Ready for activation Telco Circuit ID: 81.L1XX.908258..TWCC Telco Demarcation: 1st floor server room, rack mounted Verizon BEAS Circuit ID: USAFL57595427COV400001 / E4046626 Verizon BEAS Demarcation: left wall of packaging area (suite 1070) next to suite 1072, left wall just inside door, behind cabinet, left side of wallboard near bottom. | 199003877 | FL372 | Private IP - PIP (29323569) Access (29323570) WAN Analysis Reporting (29323571) | 29323569 29323570 29323571 | 20 MBPS (29323569) |  | 1161573037 (Private IP (PIP)) 1161573033 (Access) 1161573039 (WAN Analysis Reporting) | C4018338/ADD (29323569) E4046626/ADD (29323570) | 81.L1XX.908258..TWCC (2932357057595401) | 6061811 | 18000 | PVC ID : 6061811 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65083 PE IP Address : 68.139.58.5 CE Address : 68.139.58.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29323570) | 1000Base-SX (850nm, Multi Mode Fiber) (29323570) | Ethernet | BRIGHT HOUSE (2932357057595401) | 07/11/2019 (2932357057595401) | 08/20/2019 (2932357057595401) | 08/21/2019 (2932357057595401) | 08/22/2019 (VFORCE) (29323570) | 08/22/2019 (VFORCE) (29323570) | DEMARCDET - 1st floor server room, rack mounted |  | Zach Scholl 1-813-689-6303 Zach.Scholl@avella.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-990-179-8210 | 08/23/2019(Private IP - PIP) 08/23/2019(Access) 08/23/2019(WAN Analysis Reporting) |  |  | 08/29/2019 (29323569) 08/27/2019 (29323570) | 08/21/2019 08/27/2019 | 08/23/2019 |  | Scheduled | N (29323569) N (29323570) N (29323571) | U0101953 | Jeopardy Notification 3 (07/03/2019) | NSPE0012923389 Order Request # 198988579 | NSPE0012923389
Completed | PR517 San Juan, PR | 9615 AVE LOS ROMEROS SAN JUAN, PR 00926-7036 PR | 200 MBPS | 06/04/2019: 06/4 Gold CAR successfully upgraded to 90M | 199029997 | PR517-02-IM | Access Private IP - PIP (29334347) | 29334347 | 200 MBPS (29334347) |  | 252325383 252325385 (Private IP (PIP)) | C5005749/NONE (29334347) |  | 5997385 | 90000 | PVC ID : 5997385 VPN Name : UnitedHealthGroup Router Name : SNJN9E01 VRF Name : Vc13521:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64805 PE IP Address : 199.220.128.9 CE Address : 199.220.128.10 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | BRENDA DAVILA 1-787-806-5748 brenda.davila@am.jll.com | sahil Tuteja | sahil_tuteja@optum.com | 91-828-567-0647 | 06/04/2019(Private IP | 06/04/2019 |  | 06/04/2019 (29334347) | 06/12/2019 | 06/04/2019 |  |  | N N (29334347) | U0101953 |  | NSPE0012926557 Order Request # 199020107 | NSPE0012926557
Completed | WA112 Woodinville, WA | 8131A W BOSTIAN RD WOODINVILLE, WA 98072-9788 US | 50 MBPS (29398356) | 08/15/2019: 8/15Background: WA112 WOODINVILLE, WA, US / NEW 50 Mbps / 50 Mbps / Access, Private IP (PIP-ETH) / FRONTIER / DUAL NID / NO MNS Status: Loop delivered; Pending BEAS installation Next Action: Line testing Who owns the next action: ACD/BNE | 199285257 | WA112-02-IM | WAN Analysis Reporting (29398357) Access (29398356) Private IP - PIP (29398355) | 29398357 29398356 29398355 | 50 MBPS (29398355) |  | 94645499 (WAN Analysis Reporting) 94645492 (Access) 94645495 (Private IP (PIP)) | C4018413/ADD (29398355) E4046816/ADD (29398356) | 86/KRGN/703903//FTNC/ (2939835658335401) | 6063002 | 17000 | PVC ID : 6063002 VPN Name : UnitedHealthGroup Router Name : K1B9E01 VRF Name : Vd53143:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64674 PE IP Address : 152.176.162.213 CE Address : 152.176.162.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29398356) | 1000Base-SX (850nm, Multi Mode Fiber) (29398356) | Ethernet | FRONTIER (2939835658335401) | 06/12/2019 (2939835658335401) | 09/16/2019 (2939835658335401) | 08/12/2019 (2939835658335401) | 08/20/2019 (VFORCE) (29398356) | 08/20/2019 (VFORCE) (29398356) | DEMARCADDR - 8131A W BOSTIAN RD WOODINVILLE WA DEMARCDET - NID is at demarcation in Telco Room |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 08/20/2019(WAN Analysis Reporting) 08/20/2019(Access) 08/20/2019(Private IP - PIP) |  |  | 09/25/2019 (29398355) 09/23/2019 (29398356) | 07/26/2019 07/22/2019 | 08/20/2019 |  | Completed | N (29398357) N (29398356) N (29398355) | U0101953 | Jeopardy Notification 3 (07/17/2019) | NSPE0012946482 Order Request # 199284801 | NSPE0012946482
Completed | CIRT0002354 JEFFERSON, GA | 874 THOMAS PKWY JEFFERSON, GA 30549 US | 5 MBPS (29426951) | 08/28/2019: 8/28Background: CIRT0002354 JEFFERSON, GA; NEW 5M/5M IDS; /29; (WIN); DUAL NID; NO MNS; Status: Loop Delivered 8/27; Beas install 8/28 >Next action: Pending Beas Install Who owns the next action: Prov/LEC | 199295615 | CAH - Jefferson GA | Internet Dedicated Services (29426950) Access (29426951) | 29426950 29426951 | 5 MBPS (29426950) |  | 1166563333 (Internet Dedicated Services) 1166563329 (Access) | C1092735/ADD (29426950) E1027732/ADD (29426951) | GA/VLXP/406790/ /WINS/ (2942695184766401) | 6063631 | 0 | PVC ID : 6063631 VPN Name : Internet Router Name : GW4ATL4 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 65.207.159.137 CE Address : 65.207.159.138 | 100Base-TX (29426951) | 100Base-TX (29426951) | Ethernet | WINDSTREAM (2942695184766401) | 06/14/2019 (2942695184766401) | 08/30/2019 (2942695184766401) | 08/27/2019 (2942695184766401) | 08/28/2019 (VFORCE) (29426951) | 08/28/2019 (VFORCE) (29426951) |  |  | BARRY HEARD 1-470-314-1561 barry.heard@cardinalhealth.com | ED SANTANA | g44718@att.com | 1-888-334-7644 | 08/28/2019(Internet Dedicated Services) 08/28/2019(Access) |  |  | 09/11/2019 (29426950) 09/09/2019 (29426951) | 07/25/2019 | 08/28/2019 |  |  | N (29426950) N (29426951) | U0102647 |  |  | NSPE0012948841
Completed | ENT CA015 SAN DIEGO, CA | 3131 CAMINO DEL RIO N SAN DIEGO, CA 92108-5701 US | 100 MBPS (29438362) | 09/12/2019: 9/12Background: 100 Mbps / 50 Mbps / Private IP (PIP) / SAN DIEGO, CA, US / COX Status: Order complete > Next Action: Ready for activation Who owns the next action: customer | 199321285 | ENT CA015 SAN DIEGO | Private IP - PIP (29438361) WAN Analysis Reporting (29438363) Access (29438362) | 29438361 29438363 29438362 | 50 MBPS (29438361) |  | 94648025 (Private IP (PIP)) 94648028 (WAN Analysis Reporting) 94648023 (Access) | C1092779/ADD (29438361) E4047026/ADD (29438362) |  | 6063865 | 30000 | PVC ID : 6063865 VPN Name : UnitedHealthGroup Router Name : SDG3E03 VRF Name : Vd61843-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65087 PE IP Address : 147.225.154.5 CE Address : 147.225.154.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29438362) | 1000Base-SX (850nm, Multi Mode Fiber) (29438362) | Ethernet | COX (2943836221405601) | 08/07/2019 (2943836221405601) | 08/28/2019 (2943836221405601) | 08/28/2019 (2943836221405601) | 09/06/2019 (VFORCE) (29438362) | 09/06/2019 (VFORCE) (29438362) | DEMARCDET - 1st flr |  | Kyle Johnson 1-619-615-8021 dean_moen@optum.com | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 09/12/2019(Private IP - PIP) 09/12/2019(WAN Analysis Reporting) 09/12/2019(Access) |  |  | 09/23/2019 (29438361) 09/19/2019 (29438362) | 10/23/2019 10/29/2019 | 09/12/2019 |  | Completed | N (29438361) N (29438363) N (29438362) | U0101953 | Jeopardy Notification 1 (09/09/2019) | NSPE0012957077 Order Request # 199321297 | NSPE0012957077
Completed | UMD51 ROCKVILLE, MD | 800 KING FARM BLVD STE 300 ROCKVILLE, MD 20850-6697 US | 100 MBPS (30164281) | 10/30/2019: 10/30Background: UMD51 ROCKVILLE, MD; NEW 50M/100M PIP-ETH; (VZT); SINGLE NID; NO MNS; Status:FOC 11/8- pending loop delivery Next action: order completion Who owns the next action: VZT | 199333423 | UMD51 | Private IP - PIP (30164280) WAN Analysis Reporting (30164282) Access (30164281) | 30164280 30164282 30164281 | 50 MBPS (30164280) |  | 94647661 (Private IP (PIP)) 94647667 (WAN Analysis Reporting) 94647665 (Access) | C1096883/ADD (30164280) E4050662/ADD (30164281) | 36.KFGS.311003..CD (3016428158857101) | 6085571 |  | PVC ID : 6085571 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65102 PE IP Address : 152.181.128.57 CE Address : 152.181.128.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30164281) | 1000Base-SX (850nm, Multi Mode Fiber) (30164281) | Ethernet | VERIZON (3016428158857101) | 10/01/2019 (3016428158857101) | 11/08/2019 (3016428158857101) | 10/31/2019 (3016428158857101) |  |  | DEMARCDET - 3rd Floor suite 310 server room wall mounted |  | KELLEY MISH 1-219-805-4002 kelley_mish@uhg.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 10/31/2019(Private IP - PIP) 10/31/2019(WAN Analysis Reporting) 10/31/2019(Access) |  |  | 11/19/2019 (30164280) 11/15/2019 (30164281) | 11/19/2019 11/25/2019 | 10/31/2019 |  | Completed | N (30164280) N (30164282) N (30164281) | U0101953 |  | NSPE0012960732 Order Request # 199333249 | NSPE0012960732
Completed | CA102 CARLSBAD, CA | 2858 LOKER AVE E CARLSBAD, CA 92010-6666 US | 50 MBPS (29483837) | 07/11/2019: Background: 50 Mbps / 50 Mbps / Access, Private IP (PIP) / CARLSBAD, CA, US / AT&T / Dual NID / No MNS / ENID Status: Ready for activation once customer internal cabling is complete Telco Circuit ID: 19/KRGN/533006//PT Telco Demarcation: 1st Floor Server Room Panel 1 Jack 5 and 6 Ciena 3930 Port 5 Tagged Verizon BEAS Circuit ID: USACA23097225COV400001 / E4047274 Verizon BEAS Demarcation: Configured and installed the beas box in the customers server room rack 5 at the top and labeled. Beas is pingable. | 199363433 | Carlsbad | Private IP - PIP (29483836) Access (29483837) WAN Analysis Reporting (29483838) | 29483836 29483837 29483838 | 50 MBPS (29483836) |  | 1168906781 (Private IP (PIP)) 1168906777 (Access) 1168906783 (WAN Analysis Reporting) | C4018660/ADD (29483836) E4047274/ADD (29483837) |  | 6064959 | 40000 | PVC ID : 6064959 VPN Name : UnitedHealthGroup Router Name : SDG3E03 VRF Name : Vd61843-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64895 PE IP Address : 206.115.8.69 CE Address : 206.115.8.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29483837) | 1000Base-SX (850nm, Multi Mode Fiber) (29483837) | Ethernet |  |  |  |  | 07/10/2019 (VFORCE) (29483837) | 07/10/2019 (VFORCE) (29483837) | DEMARCADDR - . DEMARCDET - BLDG MAIN,RM MDF, MPOE FLOOR |  | Charles Mayfield 1-510-754-6986 charles.mayfield@optum.com | BRIAN LADD | brian.ladd@optum.com | 1-331-223-7121 | 07/10/2019(Private IP - PIP) 07/10/2019(Access) 07/10/2019(WAN Analysis Reporting) |  |  | 07/25/2019 (29483836) 07/23/2019 (29483837) | 08/01/2019 08/07/2019 | 07/10/2019 |  | Completed | N (29483836) N (29483837) N (29483838) | U0101953 |  | NSPE0012965572 Order Request # 199349665 | NSPE0012965572
Completed | UTN18 BRENTWOOD, TN | 8 CADILLAC DR BRENTWOOD, TN 37027-5087 US | 100 MBPS (29488985) | 07/11/2019: 7/11Background: 100 Mbps / 50 Mbps / Access, Private IP (PIP) / BRENTWOOD, TN, US / DUAL NID / ATT Status: Loop delivered7/11; Pending BEAS installation. > Access secured Next Action: Line testing | 199363713 | UTN18-05-IJ Brentwood TN | Access (29488985) Private IP - PIP (29488984) WAN Analysis Reporting (29488986) | 29488985 29488984 29488986 | 50 MBPS (29488984) |  | 1168861147 (Access) 1168861151 (Private IP (PIP)) 1168861153 (WAN Analysis Reporting) | E4047287/ADD (29488985) C1092992/ADD (29488984) |  | 6067309 | 25000 | PVC ID : 6067309 VPN Name : UnitedHealthGroup Router Name : NSVLXE01 VRF Name : V558718-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64804 PE IP Address : 152.164.194.149 CE Address : 152.164.194.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29488985) | 1000Base-SX (850nm, Multi Mode Fiber) (29488985) | Ethernet |  |  |  |  | 07/15/2019 (VFORCE) (29488985) | 07/15/2019 (VFORCE) (29488985) | DEMARCDET - 3RD FLR MAIN TELCO MPOE CIENA 3930 WALL MOUNT PORT 5 TAGGED OPTICAL |  | Marvetta Scott 1-615-493-8940 marvetta.scott@uhc.com | BRIAN LADD | brian.ladd@optum.com | 1-331-223-7121 | 07/15/2019(Access) 07/15/2019(Private IP - PIP) 07/15/2019(WAN Analysis Reporting) |  |  | 07/11/2019 (29488985) 07/15/2019 (29488984) | 08/02/2019 08/08/2019 | 07/15/2019 |  | Completed | N (29488985) N (29488984) N (29488986) | U0101953 | Jeopardy Notification 2 (07/10/2019) | NSPE0012966334 Order Request # 199352151 | NSPE0012966334
Completed | SC022 COLUMBIA, SC | 1901 MAIN ST STE 1400 COLUMBIA, SC 29201-2464 US | 50 MBPS (29533524) | 10/24/2019: 10/24Background:50MB 10MB PIP-E COLUMBIA, SC LEVEL 3 Status: Loop delivered 10/21; Beas install 10/24 Next action: Pending BEAS Who owns the next action:VZB Tech | 199413925 | SC022 | Access (29533524) Private IP - PIP (29533523) WAN Analysis Reporting (29533525) | 29533524 29533523 29533525 | 10 MBPS (29533523) |  | 94650303 (Access) 94650305 (Private IP (PIP)) 94650310 (WAN Analysis Reporting) | E4047539/ADD (29533524) C4018771/ADD (29533523) | SC/KXFN/184239/LVLC (2953352459462901) | 6068508 | 5500 | PVC ID : 6068508 VPN Name : UnitedHealthGroup Router Name : CHRL9E01 VRF Name : V638950:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64916 PE IP Address : 68.137.142.81 CE Address : 68.137.142.82 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29533524) | 1000Base-SX (850nm, Multi Mode Fiber) (29533524) | Ethernet | LEVEL 3 (2953352459462901) | 10/14/2019 (2953352459462901) | 11/07/2019 (2953352459462901) | 10/21/2019 (2953352459462901) | 10/24/2019 (VFORCE) (29533524) | 10/24/2019 (VFORCE) (29533524) | DEMARCDET - 5th floor electrical / telco closet MPOEwall mounted port 0 fiber handoff LC connector tagged with cid |  | KIM ZIRKLE 1-952-202-0058 kim_zirkle@uhg.com | Manish Sarkhel | manish_sarkhel@optum.com | 91-120-671-2655 | 10/24/2019(Access) 10/24/2019(Private IP - PIP) 10/24/2019(WAN Analysis Reporting) |  |  | 11/14/2019 (29533524) 11/18/2019 (29533523) | 11/22/2019 11/28/2019 | 10/24/2019 |  | Completed | N (29533524) N (29533523) N (29533525) | U0101953 |  | NSPE0012987000 Order Request # 199413877 | NSPE0012987000
Completed | TX521 Arlington, TX | 4230 W GREEN OAKS BLVD ARLINGTON, TX 76016-4517 US | 50 MBPS (29543406) | 09/25/2019: 9/25Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / ARLINGTON, TX, US / TIME WARNER CABLE / Status:Foc 10/11- Loop accepted 9/20; Beas Install 9/25 Next Action: Beas Install Who owns the next action: LEC | 199424815 | TX521 | Private IP - PIP (29543405) WAN Analysis Reporting (29543407) Access (29543406) | 29543405 29543407 29543406 | 10 MBPS (29543405) |  | 94650178 (Private IP (PIP)) 94650176 (WAN Analysis Reporting) 94650181 (Access) | C4018800/ADD (29543405) E4047609/ADD (29543406) | 81.L1XX.908574..TWCC (2954340659512301) | 6068777 | 7000 | PVC ID : 6068777 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64943 PE IP Address : 152.164.64.177 CE Address : 152.164.64.178 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29543406) | 1000Base-SX (850nm, Multi Mode Fiber) (29543406) | Ethernet | TIME WARNER CABLE (2954340659512301) | 07/02/2019 (2954340659512301) | 10/11/2019 (2954340659512301) | 09/20/2019 (2954340659512301) | 09/25/2019 (VFORCE) (29543406) | 09/25/2019 (VFORCE) (29543406) | DEMARCDET - Fiber panel is in ste B MPOE |  | LIZDELI GUERRIDO 1-210-762-3635 lguerrido@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 09/25/2019(Private IP - PIP) 09/25/2019(WAN Analysis Reporting) 09/25/2019(Access) |  |  | 10/22/2019 (29543405) 10/18/2019 (29543406) | 12/13/2019 12/19/2019 | 09/25/2019 |  | Completed | N (29543405) N (29543407) N (29543406) | U0101953 | Jeopardy Notification 1 (09/12/2019) | NSPE0012989911 Order Request # 199423371 | NSPE0012989911
Completed | TX524 Burleson, TX | 434 SW WILSHIRE BLVD BURLESON, TX 76028-5330 US | 50 MBPS (29544593) | 09/19/2019: 9/19Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / BURLESON, TX, US / ATT Status: Pending BEAS Installation Schedule > Loop has been delivered Next Action: BEAS Installation Who owns the next action: BNE | 199425941 | TX524 | Access (29544593) Private IP - PIP (29544592) WAN Analysis Reporting (29544594) | 29544593 29544592 29544594 | 10 MBPS (29544592) |  | 1172908229 (Access) 1172908233 (Private IP (PIP)) 1172908235 (WAN Analysis Reporting) | E4047619/ADD (29544593) C4018802/ADD (29544592) | 14/KRGN/886265//SW (2954459359530701) | 6068821 6068841 | 7000 | PVC ID : 6068821,6068841 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65253 PE IP Address : 152.164.93.153 CE Address : 152.164.93.154 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29544593) | 1000Base-SX (850nm, Multi Mode Fiber) (29544593) | Ethernet | ATT (2954459359530701) | 07/09/2019 (2954459359530701) | 09/18/2019 (2954459359530701) | 09/19/2019 (2954459359530701) | 09/23/2019 (VFORCE) (29544593) |  | DEMARCADDR - . DEMARCDET - BLDG MAIN, 1ST FLOOR MDF ROOM |  | Marco Wong 1-214-493-4068 mwong@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 09/23/2019(Access) 09/23/2019(Private IP - PIP) 09/23/2019(WAN Analysis Reporting) |  |  | 10/01/2019 (29544593) 10/03/2019 (29544592) | 08/16/2019 08/22/2019 | 09/23/2019 |  | Completed | N (29544593) N (29544592) N (29544594) | U0101953 | Jeopardy Notification 1 (07/08/2019) | NSPE0012990450 Order Request # 199424845 | NSPE0012990450
Completed | TX201 CORPUS CHRISTI, TX | 2922 MORGAN AVE CORPUS CHRISTI, TX 78405-2141 US | 50 MBPS (29551348) | 07/17/2019: 7/17Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / CORPUS CHRISTI, TX, US / ATT Status: loop accepted 7/17 Next Action: Pending Loop Acceptance, Pending Beas Who owns the next action: FT dispatch | 199433647 | TX201 | Private IP - PIP (29551347) Access (29551348) WAN Analysis Reporting (29551349) | 29551347 29551348 29551349 | 20 MBPS (29551347) |  | 94649916 (Private IP (PIP)) 94649920 (Access) 94649918 (WAN Analysis Reporting) | C4018821/ADD (29551347) E4047673/ADD (29551348) | 34/KRGN/614051//SW (2955134859347001) | 6069001 | 13000 | PVC ID : 6069001 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64730 PE IP Address : 68.136.228.5 CE Address : 68.136.228.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29551348) | 1000Base-SX (850nm, Multi Mode Fiber) (29551348) | Ethernet | ATT (2955134859347001) | 07/02/2019 (2955134859347001) | 07/15/2019 (2955134859347001) | 07/17/2019 (2955134859347001) | 07/23/2019 (VFORCE) (29551348) |  | DEMARCDET - 1 LAN RM PORT #2 SC TYPE OPTICAL COUPLER ON BIU |  | Keith McMullen 1-210-617-4260 kmcmullen@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 07/23/2019(Private IP - PIP) 07/23/2019(Access) 07/23/2019(WAN Analysis Reporting) |  |  | 07/29/2019 (29551347) 07/25/2019 (29551348) | 08/28/2019 09/03/2019 | 07/23/2019 |  | Completed | N (29551347) N (29551348) N (29551349) | U0101953 |  | NSPE0012993426 Order Request # 199433587 | NSPE0012993426
Completed | TX431 SAN ANTONIO, TX | 430 W SUNSET RD STE 200 SAN ANTONIO, TX 78209-1736 US | 50 MBPS (29552337) | 02/11/2020: Order Completed on Feb 11, 2020 | 199433933 | TX431 | WAN Analysis Reporting (29552338) Access (29552337) Private IP - PIP (29552336) | 29552338 29552337 29552336 | 50 MBPS (29552336) |  | 94650349 (WAN Analysis Reporting) 94650342 (Access) 94650344 (Private IP (PIP)) | C4018826/ADD (29552336) E4047678/ADD (29552337) | 31/KRGN/654474//SW (2955233759585702) | 6069014 | 5500 | PVC ID : 6069014 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65088 PE IP Address : 68.139.193.165 CE Address : 68.139.193.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29552337) | 1000Base-SX (850nm, Multi Mode Fiber) (29552337) | Ethernet | ATT (2955233759585702) | 12/16/2019 (2955233759585702) | 02/04/2020 (2955233759585702) | 02/10/2020 (2955233759585702) | 02/12/2020 (VFORCE) (29552337) | 02/11/2020 (VFORCE) (29552337) | DEMARCDET - 2ND FL TLCO RM CIENA 3930 PORT 5 HANDING OFF TRAY PORT 1 and 2 |  | GABRIEL RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 02/11/2020(WAN Analysis Reporting) 02/11/2020(Access) 02/11/2020(Private IP - PIP) |  |  | 02/13/2020 (29552336) 02/11/2020 (29552337) | 02/18/2020 02/12/2020 | 02/11/2020 |  | Completed | N (29552338) N (29552337) N (29552336) | U0101953 | Jeopardy Notification 1 (10/25/2019) | NSPE0012993517 Order Request # 199433863 | NSPE0012993517
Completed | SANTA ANA, CA | 3110 W LAKE CENTER DR SANTA ANA, CA 92704-6917 US | 100 MBPS (29560231) | 07/21/2019: Background: 100 Mbps / 100 Mbps / Access, Private IP (PIP) / SANTA ANA, CA, US / ATT Status: Loop Delivered 7/19 - Pending Beas install 7/22 Next Action: Pending BEAS Install - Who owns the next action: Dispatch Team | 199442103 | Santa Ana | Access (29560231) WAN Analysis Reporting (29560232) Private IP - PIP (29560230) | 29560231 29560232 29560230 | 100 MBPS (29560230) |  | 1173131057 (Access) 1173131063 (WAN Analysis Reporting) 1173131061 (Private IP (PIP)) | E4047728/ADD (29560231) C1093547/ADD (29560230) | 13/KRGN/598967//PT (2956023154857801) | 6069265 | 25000 | PVC ID : 6069265 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64822 PE IP Address : 152.176.33.37 CE Address : 152.176.33.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29560231) | 1000Base-SX (850nm, Multi Mode Fiber) (29560231) | Ethernet | ATT (2956023154857801) | 07/16/2019 (2956023154857801) | 07/19/2019 (2956023154857801) | 07/19/2019 (2956023154857801) | 07/22/2019 (VFORCE) (29560231) | 07/22/2019 (VFORCE) (29560231) | DEMARCDET - 2ND FLR NETWORK RM RACKMOUNTED |  | BRIAN LADD 1-331-223-7121 brian.ladd@optum.com | BRIAN LADD | brian.ladd@optum.com | 1-331-223-7121 | 07/22/2019(Access) 07/22/2019(WAN Analysis Reporting) 07/22/2019(Private IP - PIP) |  |  | 07/22/2019 (29560231) 07/24/2019 (29560230) | 08/23/2019 08/29/2019 | 07/22/2019 |  | Completed | N (29560231) N (29560232) N (29560230) | U0101953 | Jeopardy Notification 1 (07/10/2019) | NSPE0012994616 Order Request # 199438061 | NSPE0012994616
Completed | TX028 IRVING, TX | 5150 REGENT BLVD IRVING, TX 75063-2492 US | 100 MBPS (29559406) | 10/08/2019: 10/8Background:TX028 IRVING, TX, US; New 100M/100M PIP-Eth; (Level 3); Dual NID; No MNS; Groom Status: Foc 10/25 Next action: Build Completion Who owns the next action: LEC & Provisioning. | 199442179 | TX028-03-IJ | Private IP - PIP (29559405) WAN Analysis Reporting (29559407) Access (29559406) | 29559405 29559407 29559406 | 100 MBPS (29559405) |  | 1173212483 (Private IP (PIP)) 1173212485 (WAN Analysis Reporting) 1173212479 (Access) | C1093541/ADD (29559405) E4047719/ADD (29559406) | TX/KXFN/206618/LVLC (2955940625141702) | 6069235 | 30000 | PVC ID : 6069235 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64920 PE IP Address : 152.161.101.221 CE Address : 152.161.101.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29559406) | 1000Base-SX (850nm, Multi Mode Fiber) (29559406) | Ethernet | LEVEL 3 (2955940625141702) | 08/23/2019 (2955940625141702) | 10/25/2019 (2955940625141702) | 10/11/2019 (2955940625141702) | 10/14/2019 (VFORCE) (29559406) |  | DEMARCDET - 1st flr data room/mdf rm level 3 rack 01.01 rack mounted unit 25 mmf tagged with ckt id |  | Evetier Hernandez 1-214-498-2362 evetier_hernandez@uhc.com | SUSAN WAGNER | susan_l_wagner@optum.com | 1-763-744-0632 | 10/14/2019(Private IP - PIP) 10/14/2019(WAN Analysis Reporting) 10/14/2019(Access) |  |  | 11/05/2019 (29559405) 11/01/2019 (29559406) | 11/20/2019 11/26/2019 | 10/14/2019 |  | Completed | N (29559405) N (29559407) N (29559406) | U0101953 | Jeopardy Notification 4 (08/17/2019) | NSPE0012995013 Order Request # 199439201 | NSPE0012995013
Completed | TX518 HOUSTON, TX | 4700 W SAM HOUSTON PKWY N STE 220 HOUSTON, TX 77041-8224 US | 50 MBPS (29560163) | 09/24/2019: 9/24Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / HOUSTON, TX, US / LEVEL 3 / Dual NID / No MNS Status: Foc 9/30-Loop delivered 9/23- Beas Install 9/25 Next Action: Pending Beas Who owns the next action: Dispatch Team | 199442443 | TX518 | Access (29560163) WAN Analysis Reporting (29560164) Private IP - PIP (29560162) | 29560163 29560164 29560162 | 20 MBPS (29560162) |  | 94650094 (Access) 94650096 (WAN Analysis Reporting) 94650090 (Private IP (PIP)) | E4047821/ADD (29560163) C4018866/ADD (29560162) | TX/KXFN/187159/LVLC (2956016359645201) | 6069262 | 13000 | PVC ID : 6069262 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65071 PE IP Address : 152.164.40.193 CE Address : 152.164.40.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29560163) | 1000Base-SX (850nm, Multi Mode Fiber) (29560163) | Ethernet | LEVEL 3 (2956016359645201) | 09/09/2019 (2956016359645201) | 09/30/2019 (2956016359645201) | 09/23/2019 (2956016359645201) | 09/25/2019 (VFORCE) (29560163) | 09/25/2019 (VFORCE) (29560163) | DEMARCDET - 2nd floor ST 220 customer server room customer rack RMU 35 port 3 customer interface LC MM tagged with cid |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | Jason LePage | jason_lepage@optum.com | 1-763-744-3108 | 09/25/2019(Access) 09/25/2019(WAN Analysis Reporting) 09/25/2019(Private IP - PIP) |  |  | 09/16/2019 (29560163) 09/18/2019 (29560162) | 10/18/2019 10/24/2019 | 09/25/2019 |  | Completed | N (29560163) N (29560164) N (29560162) | U0101953 | Jeopardy Notification 2 (07/29/2019) | NSPE0012996345 Order Request # 199442463 | NSPE0012996345
Completed | TN050 FRANKLIN, TN | 1893 GENERAL GEORGE PATTON DR FRANKLIN, TN 37067-2655 US | 50 MBPS (29560266) | 11/12/2019: 11/12Background:50 Mbps / 20 Mbps / Access, Private IP (PIP) / FRANKLIN, TN, US / LEVEL 3 Status:BEAS Schedule 11/12 >loop delivered 11/11 Next action: BEAS Install- Order closure Who owns the next action:BNE/ VzT | 199442165 | TN050-02-IM | WAN Analysis Reporting (29560267) Access (29560266) Private IP - PIP (29560265) | 29560267 29560266 29560265 | 20 MBPS (29560265) |  | 94650086 (WAN Analysis Reporting) 94650084 (Access) 94650080 (Private IP (PIP)) | C4018840/ADD (29560265) E4047729/ADD (29560266) | TN/KXFN/185686/LVLC (2956026642136001) | 6069266 | 13000 | PVC ID : 6069266 VPN Name : UnitedHealthGroup Router Name : NSVLXE01 VRF Name : Vj39243-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64790 PE IP Address : 199.220.138.77 CE Address : 199.220.138.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29560266) | 1000Base-SX (850nm, Multi Mode Fiber) (29560266) | Ethernet | LEVEL 3 (2956026642136001) | 10/21/2019 (2956026642136001) | 12/23/2019 (2956026642136001) | 11/11/2019 (2956026642136001) | 11/12/2019 (VFORCE) (29560266) |  | DEMARCDET - X |  | Ben May May 1-615-440-1198 Benjamin.may@briovarx.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 11/12/2019(WAN Analysis Reporting) 11/12/2019(Access) 11/12/2019(Private IP - PIP) |  |  | 01/02/2020 (29560265) 12/31/2019 (29560266) | 12/05/2019 11/29/2019 | 11/12/2019 |  | Completed | N (29560267) N (29560266) N (29560265) | U0101953 |  | NSPE0012996218 Order Request # 199442139 | NSPE0012996218
Completed | CA236 SAN BERNARDINO, CA | 560 E HOSPITALITY LN SAN BERNARDINO, CA 92408-3546 US | 200 MBPS (29576626) | 07/14/2020: Order Completed on Aug 27, 2019 | 199457869 | CA236 | Access (29576626) Private IP - PIP (29576625) WAN Analysis Reporting (29576627) | 29576626 29576625 29576627 | 100 MBPS (29576625) |  | 94650545 (Access) 94650542 (Private IP (PIP)) 94650540 (WAN Analysis Reporting) | E5019313/ADD (29576626) C5007781/ADD (29576625) | CA/KXFN/188793/LVLC (2957662657975002) | 6069770 | 70000 | PVC ID : 6069770 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65085 PE IP Address : 152.183.214.69 CE Address : 152.183.214.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29576626) | 1000Base-SX (850nm, Multi Mode Fiber) (29576626) | Ethernet | LEVEL 3 (2957662657975002) | 08/20/2019 (2957662657975002) | 08/27/2019 (2957662657975002) | 08/23/2019 (2957662657975002) | 08/27/2019 (VFORCE) (29576626) | 08/27/2019 (VFORCE) (29576626) | DEMARCDET - X |  | Po Chan 1-626-476-5337 pchan@marchvisioncare.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 08/27/2019(Access) 08/27/2019(Private IP - PIP) 08/27/2019(WAN Analysis Reporting) |  |  | 09/04/2019 (29576626) 09/06/2019 (29576625) | 09/30/2019 10/04/2019 | 08/27/2019 |  | Completed Activated | N (29576626) N (29576625) N (29576627) | U0101953 | Jeopardy Notification 1 (08/14/2019) | NSPE0013000914 Order Request # 199457825 | NSPE0013000914
Completed | CA178 WOODLAND HILLS, CA | 21300 VICTORY BLVD WOODLAND HILLS, CA 91367-2525 US | 200 MBPS (29576657) | 08/19/2019 Background: 200 Mbps / 100 Mbps / Access, Private IP (PIP) / WOODLAND HILLS, CA, US / TIME WARNER CABLE / ENID Status: Ready for activation once customer internal cabling is done Telco Circuit ID: 81.L1XX.908610..TWCC Telco Demarcation: Third floor, server room, rack mounted EQUIPMENT & PORT: RAD 203 PORT 5 Verizon BEAS Circuit ID: USACA57973999COV400001 / E5019314 Verizon BEAS Demarcation: :8th floor, Suite 850, Rack mounted, overture isg400 tag and labelled | 199459045 | CA178 | Access (29576657) WAN Analysis Reporting (29576658) Private IP - PIP (29576656) | 29576657 29576658 29576656 | 100 MBPS (29576656) |  | 94650903 (Access) 94650910 (WAN Analysis Reporting) 94650905 (Private IP (PIP)) | E5019314/ADD (29576657) C5007782/ADD (29576656) | 81.L1XX.908610..TWCC (2957665757973901) | 6069773 | 70000 | PVC ID : 6069773 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64636 PE IP Address : 152.164.229.73 CE Address : 152.164.229.74 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29576657) | 1000Base-SX (850nm, Multi Mode Fiber) (29576657) | Ethernet | TIME WARNER CABLE (2957665757973901) | 07/08/2019 (2957665757973901) | 08/23/2019 (2957665757973901) | 08/15/2019 (2957665757973901) | 08/19/2019 (VFORCE) (29576657) |  | DEMARCDET - third floor, server room, rack mounted |  | Charles Price 1-310-216-2300 cprice@marchvision.com | Larry Walsh | larry_l_walsh@optum.com | 1-317-715-7773 | 08/19/2019(Access) 08/19/2019(WAN Analysis Reporting) 08/19/2019(Private IP - PIP) |  |  | 08/30/2019 (29576657) 09/04/2019 (29576656) | 08/16/2019 08/22/2019 | 08/19/2019 |  | Completed | N (29576657) N (29576658) N (29576656) | U0101953 |  | NSPE0013001393 Order Request # 199459059 | NSPE0013001393
Completed | CA177 LOS ANGELES, CA | 6601 CENTER DR W LOS ANGELES, CA 90045-1582 US | 1 GBPS (29576670) | 08/30/2019: 8/29Background: CA177 LOS ANGELES, CA, US / 1 Gbps / 500 Mbps / Access, Private IP (PIP) / (XO) / DUAL NID / NO MNS Status: Ready for activation once customer internal cabling is complete | 199459637 | CA177 | Private IP - PIP (29576669) WAN Analysis Reporting (29576671) Access (29576670) | 29576669 29576671 29576670 | 500 MBPS (29576669) |  | 94650573 (Private IP (PIP)) 94650571 (WAN Analysis Reporting) 94650576 (Access) | C0171606/ADD (29576669) E5019315/ADD (29576670) | LA/L1XX/324518/ /TQW /ELK (2957667057973201) | 6069774 | 350000 | PVC ID : 6069774 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65019 PE IP Address : 152.164.189.105 CE Address : 152.164.189.106 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (29576670) | 1000Base-SX (850nm, Multi Mode Fiber) (29576670) | Ethernet | XO (2957667057973201) | 08/12/2019 (2957667057973201) | 09/09/2019 (2957667057973201) | 08/26/2019 (2957667057973201) | 03/10/2020 (VFORCE) (29576670) | 03/10/2020 (VFORCE) (29576670) | DEMARCDET - BASEMENT INSIDE MPOE LEVEL P2 PORT 3 |  | Elango Murugan 1-310-216-2300 emurugan@marchvisioncare.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 08/27/2019(Private IP - PIP) 08/27/2019(WAN Analysis Reporting) 08/27/2019(Access) |  |  | 08/20/2019 (29576669) 08/16/2019 (29576670) | 09/18/2019 09/24/2019 | 08/27/2019 |  | Completed | N (29576669) N (29576671) N (29576670) | U0101953 |  | NSPE0013001617 Order Request # 199459553 | NSPE0013001617
Completed | TX520 DALLAS, TX | 2225 VATICAN LN DALLAS, TX 75224-4719 US | 50 MBPS (29582323) | 09/18/2019: 9/18Background:50 Mbps / 10 Mbps / Access, Private IP (PIP) / DALLAS, TX, US / TIME WARNER CABLE Status: Early Delivery- Loop delivered 9/18; Beas Install 9/19 Next action: Pending Beas Who owns the next action: Dispatch Team | 199465659 | TX520 | Private IP - PIP (29582322) WAN Analysis Reporting (29582324) Access (29582323) | 29582322 29582324 29582323 | 10 MBPS (29582322) |  | 94650831 (Private IP (PIP)) 94650833 (WAN Analysis Reporting) 94650835 (Access) | C4018893/ADD (29582322) E4047879/ADD (29582323) | 21.L1XX.814597..TWCC (2958232359830701) | 6069975 | 5500 | PVC ID : 6069975 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64544 PE IP Address : 68.139.79.145 CE Address : 68.139.79.146 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29582323) | 1000Base-SX (850nm, Multi Mode Fiber) (29582323) | Ethernet | TIME WARNER CABLE (2958232359830701) | 07/16/2019 (2958232359830701) | 10/21/2019 (2958232359830701) | 09/18/2019 (2958232359830701) | 09/19/2019 (VFORCE) (29582323) |  | DEMARCDET - 1ST FLOOR ELECTRICAL ROOM LEFT WALL MOUNTED |  | Tammy Zegarelli 1-817-312-5050 drz@drzcares.com | Philip Joseph Damasco II | philip_damasco@optum.com | 632-790-6235 | 09/19/2019(Private IP - PIP) 09/19/2019(WAN Analysis Reporting) 09/19/2019(Access) |  |  | 10/30/2019 (29582322) 10/28/2019 (29582323) | 11/25/2019 11/29/2019 | 09/19/2019 |  | Managed Completed | N (29582322) N (29582324) N (29582323) | U0101953 | Jeopardy Notification 1 (07/16/2019) | NSPE0013003653 Order Request # 199465593 | NSPE0013003653
Completed | FL110 TAMPA, FL | 500 N WEST SHORE BLVD STE 500 TAMPA, FL 33609-5003 US | 50 MBPS (29582502) | 08/28/2019: 8/28Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / TAMPA, FL, US / LEVEL 3 Status: Foc 9/12; PTD 9/10 Next Action:Loop delivery Who owns the next action: LEC | 199468339 | FL110-02-IJ Tampa FL Westshore BLVD 50M PIP | WAN Analysis Reporting (29582503) Access (29582502) Private IP - PIP (29582501) | 29582503 29582502 29582501 | 20 MBPS (29582501) |  | 1174533855 (WAN Analysis Reporting) 1174533849 (Access) 1174533853 (Private IP (PIP)) | C4018892/ADD (29582501) E4047877/ADD (29582502) | FL/KXFN/189706/LVLC (2958250272962101) | 6069978 | 10000 | PVC ID : 6069978 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65286 PE IP Address : 152.162.5.113 CE Address : 152.162.5.114 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (29582502) | 1000Base-LX (1310nm Single Mode Fiber) (29582502) | Ethernet | LEVEL 3 (2958250272962101) | 07/31/2019 (2958250272962101) | 09/12/2019 (2958250272962101) | 08/29/2019 (2958250272962101) | 08/30/2019 (VFORCE) (29582502) | 08/30/2019 (VFORCE) (29582502) | DEMARCADDR - X DEMARCDET - X |  | Lori Swink 1-813-349-6246 LSwink@wellmed.net | Ed McLaughlin | edward.mclaughlin@optum.com | 1-443-853-3646 | 08/30/2019(WAN Analysis Reporting) 08/30/2019(Access) 08/30/2019(Private IP - PIP) |  |  | 09/23/2019 (29582501) 09/19/2019 (29582502) | 09/16/2019 09/10/2019 | 08/30/2019 |  | Completed | N (29582503) N (29582502) N (29582501) | U0101953 | Jeopardy Notification 1 (08/06/2019) | NSPE0013003992 Order Request # 199466617 | NSPE0013003992
Completed | TX528 CARROLLTON, TX | 1948 E HEBRON PKWY STE 110 CARROLLTON, TX 75007-1515 US | 50 MBPS (29604402) | 09/04/2019: Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / CARROLLTON, TX, US / FRONTIER / ENID Status: Ready for activation Telco Circuit ID: 13/KRGN/168681//FTNC/ Telco Demarcation: main bldg flr 1 rm mdf rad 203 port 6 Verizon BEAS Circuit ID: USATX59922569COV400001 Verizon BEAS Demarcation: 1st floor, on telco backboard of Suite 110 tagged, port 1 | 199488409 | TX528 | Private IP - PIP (29604401) WAN Analysis Reporting (29604403) Access (29604402) | 29604401 29604403 29604402 | 10 MBPS (29604401) |  | 94651707 (Private IP (PIP)) 94651712 (WAN Analysis Reporting) 94651705 (Access) | C4018929/ADD (29604401) E4047978/ADD (29604402) | 13/KRGN/168681//FTNC/ (2960440259922501) | 6070674 | 5500 | PVC ID : 6070674 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64620 PE IP Address : 152.164.1.49 CE Address : 152.164.1.50 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29604402) | 1000Base-SX (850nm, Multi Mode Fiber) (29604402) | Ethernet | FRONTIER (2960440259922501) | 07/11/2019 (2960440259922501) | 09/11/2019 (2960440259922501) | 08/30/2019 (2960440259922501) | 09/03/2019 (VFORCE) (29604402) | 09/03/2019 (VFORCE) (29604402) | DEMARCDET - main bldg flr 1 rm mdf rad 203 port 6 |  | Thomas Sympson 1-214-493-4036 tsympson@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 09/03/2019(Private IP - PIP) 09/03/2019(WAN Analysis Reporting) 09/03/2019(Access) |  |  | 09/20/2019 (29604401) 09/18/2019 (29604402) | 10/09/2019 10/15/2019 | 09/03/2019 |  | Completed | N (29604401) N (29604403) N (29604402) | U0101953 | Jeopardy Notification 3 (08/13/2019) | NSPE0013010026 Order Request # 199485755 | NSPE0013010026
Completed | TX435 AUSTIN, TX | 3016 GUADALUPE ST AUSTIN, TX 78705-2862 US | 100 MBPS (29608926) | 09/12/2019: 9/12Background: 100 Mbps / 50 Mbps / Access, Private IP (PIP) / AUSTIN, TX, US / ATT Status: Customer extension is complete- trying to schedule possible dispatch for tomorrow 9/13 Next Action: Sup order; then BEAS Install Who owns the next action: Dispatch Team | 199488581 | TX435 | Access (29608926) Private IP - PIP (29608925) WAN Analysis Reporting (29608927) | 29608926 29608925 29608927 | 50 MBPS (29608925) |  | 1172996017 (Access) 1172996025 (Private IP (PIP)) 1172996037 (WAN Analysis Reporting) | E4048014/ADD (29608926) C1093834/ADD (29608925) | 32/KRGN/653744//SW (2960892657009101) | 6070793 | 30000 | PVC ID : 6070793 VPN Name : UnitedHealthGroup Router Name : AX39E01 VRF Name : Vd31961:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64577 PE IP Address : 68.139.106.249 CE Address : 68.139.106.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29608926) | 1000Base-SX (850nm, Multi Mode Fiber) (29608926) | Ethernet | ATT (2960892657009101) | 07/12/2019 (2960892657009101) | 07/19/2019 (2960892657009101) | 07/19/2019 (2960892657009101) | 09/16/2019 (VFORCE) (29608926) | 09/16/2019 (VFORCE) (29608926) | DEMARCDET - BASEMENT TELCO BACKBOARD PATCH PANEL POST 4 |  | Celeste Duarte 1-877-470-4608 Celeste.Duarte@avella.com | Solomon Victor | solomon_victor@optum.com | 91-804-670-4304 | 09/16/2019(Access) 09/16/2019(Private IP - PIP) 09/16/2019(WAN Analysis Reporting) |  |  | 09/20/2019 (29608926) 09/24/2019 (29608925) | 10/24/2019 10/30/2019 | 09/16/2019 |  | Completed | N (29608926) N (29608925) N (29608927) | U0101953 | Jeopardy Notification 3 (08/20/2019) | NSPE0013010561 Order Request # 199487631 | NSPE0013010561
Completed | C1515 LITTLE ROCK, AR MLPPP | 4001 N RODNEY PARHAM RD LITTLE ROCK, AR 72212-2459 US | 1.5 MBPS (29621701) | 09/10/2019: 9/10Background: 1.5 Mbps / 1.5 Mbps / Access, Private IP (PIP) / LITTLE ROCK, AR, US Status: Loop Installed- End to End testing 9/10 Next Action: Pending order completion Who owns the next action: LEC | 199494005 | C1515 | WAN Analysis Reporting (29621702) Access (29621701) Private IP - PIP (29621700) | 29621702 29621701 29621700 | 1.5 MBPS (29621700) |  | 94651559 (WAN Analysis Reporting) 94651563 (Access) 94651561 (Private IP (PIP)) | C0171958/ADD (29621700) D1100469/ADD (29621701) |  | 6071102 | 128 | PVC ID : 6071102 VPN Name : UHG-ECC Router Name : MEJ3E01 VRF Name : Vd97983-UHGECC Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65517 PE IP Address : 206.115.81.25 CE Address : 206.115.81.26 QoS - Egress Profile: R12 |  | DS1 (29621701) | TDM | [8 empty] | Jiangtao He 1-416-887-2203 Jiangtao.He@fisglobal.com | John Bremseth | john_bremseth@optum.com | 1-763-553-4895 | 09/10/2019(WAN Analysis Reporting) 09/10/2019(Access) 09/10/2019(Private IP - PIP) |  |  | 08/15/2019 (29621700) 08/13/2019 (29621701) | 08/09/2019 08/05/2019 | 09/10/2019 |  | Completed | N (29621702) N (29621701) N (29621700) | U0101953 |  | NSPE0013012649 Order Request # 199494021 | NSPE0013012649
Completed | TX493 EL PASO, TX | 615 N ZARAGOZA RD EL PASO, TX 79907-4773 US | 50 MBPS (29623240) | 09/26/2019: 9/26Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / EL PASO, TX, US / TIME WARNER CABLE Status: Loop installed : Beas Install 9/27 Next Action:Pending Beas Who owns the next action :Dispatch | 199502741 | TX493 | Private IP - PIP (29623239) WAN Analysis Reporting (29623241) Access (29623240) | 29623239 29623241 29623240 | 10 MBPS (29623239) |  | 94651450 (Private IP (PIP)) 94651455 (WAN Analysis Reporting) 94651448 (Access) | C4018961/ADD (29623239) E4048076/ADD (29623240) | 91.L1XX.802532..TWCC (2962324060145901) | 6071142 | 5500 | PVC ID : 6071142 VPN Name : UnitedHealthGroup Router Name : AQHGE02 VRF Name : V551714:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65030 PE IP Address : 152.183.3.113 CE Address : 152.183.3.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29623240) | 1000Base-SX (850nm, Multi Mode Fiber) (29623240) | Ethernet | TIME WARNER CABLE (2962324060145901) | 07/17/2019 (2962324060145901) | 10/18/2019 (2962324060145901) | 09/26/2019 (2962324060145901) | 09/27/2019 (VFORCE) (29623240) | 09/27/2019 (VFORCE) (29623240) | DEMARCDET - back area comm room rad 203 port 5 |  | Jason Ozer 1-210-250-1454 jozer@wellmed.net | Manish Sarkhel | manish_sarkhel@optum.com | 91-120-671-2655 | 09/27/2019(Private IP - PIP) 09/27/2019(WAN Analysis Reporting) 09/27/2019(Access) |  |  | 10/29/2019 (29623239) 10/25/2019 (29623240) | 11/29/2019 12/05/2019 | 09/27/2019 |  | Completed | N (29623239) N (29623241) N (29623240) | U0101953 |  | NSPE0013017189 Order Request # 199502647 | NSPE0013017189
Completed | UTX01 SAN ANTONIO, TX | 6430 BANDERA RD STE 74 SAN ANTONIO, TX 78238-1513 US | 50 MBPS (29623445) | 12/20/2019: Order Completed on Dec 20, 2019 | 199503491 | UTX01 | Private IP - PIP (29623444) WAN Analysis Reporting (29623446) Access (29623445) | 29623444 29623446 29623445 | 10 MBPS (29623444) |  | 94651582 (Private IP (PIP)) 94651580 (WAN Analysis Reporting) 94651584 (Access) | C4018970/ADD (29623444) E4048100/ADD (29623445) | 21.L1XX.814670..TWCC (2962344560151201) | 6071137 | 5500 | PVC ID : 6071137 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64910 PE IP Address : 152.162.106.69 CE Address : 152.162.106.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29623445) | 1000Base-SX (850nm, Multi Mode Fiber) (29623445) | Ethernet | TIME WARNER CABLE (2962344560151201) | 12/16/2019 (2962344560151201) | 12/26/2019 (2962344560151201) | 12/18/2019 (2962344560151201) | 12/20/2019 (VFORCE) (29623445) | 12/20/2019 (VFORCE) (29623445) | DEMARCDET - 1st F suit 78 electrical R Rack location sepctrum 4RU |  | Gabriel Rodriguez 1-210-833-8929 GRodriguez1@wellmed.net | Manish Sarkhel | manish_sarkhel@optum.com | 91-120-671-2655 | 12/20/2019(Private IP - PIP) 12/20/2019(WAN Analysis Reporting) 12/20/2019(Access) |  |  | 12/16/2019 (29623444) 12/12/2019 (29623445) | 04/22/2020 04/28/2020 | 12/20/2019 |  | Completed | N (29623444) N (29623446) N (29623445) | U0101953 | Jeopardy Notification 1 (11/07/2019) | NSPE0013017505 Order Request # 199503387 | NSPE0013017505
Completed | ENT FL055 DORAL, FL | 1425 NW 82ND AVE DORAL, FL 33126-1507 US | 100 MBPS (29623475) | 08/20/2019: 08/19 Successfully activated | 199507685 | ENT FL055 DORAL | WAN Analysis Reporting (29623476) Access (29623475) Private IP - PIP (29623474) | 29623476 29623475 29623474 | 10 MBPS (29623474) |  | 94651569 (WAN Analysis Reporting) 94651573 (Access) 94651571 (Private IP (PIP)) | C1093893/ADD (29623474) E4048079/ADD (29623475) | 60/KQGN/789031//SB (2962347525682801) | 6071140 | 5500 | PVC ID : 6071140 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64863 PE IP Address : 152.164.130.137 CE Address : 152.164.130.138 QoS - Egress Profile: R12 | 100Base-TX (29623475) | 100Base-TX (29623475) | Ethernet | ATT (2962347525682801) | 07/16/2019 (2962347525682801) | 07/19/2019 (2962347525682801) | 07/17/2019 (2962347525682801) | 07/22/2019 (VFORCE) (29623475) |  | DEMARCADDR - . DEMARCDET - BLDG MAIN, 1ST FLOOR MPOE ROOM |  | Eddie Justo 1-954-881-4379 eduardo_justo@uhcsouthflorida.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 07/22/2019(WAN Analysis Reporting) 07/22/2019(Access) 07/22/2019(Private IP - PIP) | 08/19/2019 |  | 07/30/2019 (29623474) 07/26/2019 (29623475) | 08/29/2019 08/23/2019 | 07/22/2019 |  | Completed | N (29623476) N (29623475) N (29623474) | U0101953 |  | NSPE0013012899 Order Request # 199494951 | NSPE0013012899
Completed | TX526 DALLAS, TX | 1350 N BUCKNER BLVD STE 101 DALLAS, TX 75218-3558 US | 50 MBPS (29613784) | 01/03/2020: Order Completed on Jan 3, 2020 | 199498169 | TX526 | Private IP - PIP (29613783) WAN Analysis Reporting (29613785) Access (29613784) | 29613783 29613785 29613784 | 10 MBPS (29613783) |  | 94651763 (Private IP (PIP)) 94651768 (WAN Analysis Reporting) 94651761 (Access) | C4018945/ADD (29613783) E4048025/ADD (29613784) | 21.L1XX.814662..TWCC (2961378460061701) | 6070892 | 7000 | PVC ID : 6070892 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65105 PE IP Address : 68.138.142.197 CE Address : 68.138.142.198 QoS - Egress Profile: R12 | 100Base-TX (29613784) | 100Base-TX (29613784) | Ethernet | TIME WARNER CABLE (2961378460061701) | 10/24/2019 (2961378460061701) | 11/22/2019 (2961378460061701) | 12/31/2019 (2961378460061701) | 01/03/2020 (VFORCE) (29613784) |  | DEMARCDET - Telecom Room next to the staircase on Suite 101 |  | Thomas Sympson 1-214-493-4036 tsympson@wellmed.net | HERBERT VILLOSTAS | herbert_villostas@optum.com | 632-790-6516 | 01/03/2020(Private IP - PIP) 01/03/2020(WAN Analysis Reporting) 01/03/2020(Access) |  |  | 05/22/2020 (29613783) 05/20/2020 (29613784) | 05/20/2020 05/26/2020 | 01/03/2020 |  | Completed | N (29613783) N (29613785) N (29613784) | U0101953 | Jeopardy Notification 1 (12/20/2019) | NSPE0013013347 Order Request # 199496301 | NSPE0013013347
Completed | Sungard Recovery Services Philadelphia, PA | 401 N BROAD ST PHILADELPHIA, PA 19108-1001 US | 50 MBPS (29629318) | 08/01/2019 Handoff change complete | 199514159 | SUNGARD RECOVERY SERVICES | Access (29629318) Private IP - PIP WAN Analysis Reporting (29629319) | 29629318 29629319 | 20 MBPS |  | 351665647 (Access) 351666093 351666103 (WAN Analysis Reporting) | E4046410/NONE (29629318) | [5 empty] | 1000Base-LX (1310nm Single Mode Fiber) (29629318) | Ethernet | [8 empty] | David Zach 1-215-351-1068 david.zach@sungardas.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 08/01/2019(Access) | 08/01/2019 |  | 08/01/2019 (29629318) | 08/12/2019 08/12/2019 (26709905.1) | 08/02/2019 |  | Approved Scheduled Status Set | N (29629318) N N (29629319) | U0101953 |  | OR 199513909 | NSPE0013021055
Completed | SC023 CHARLESTON, SC | 5895 CORE AVE STE 417 CHARLESTON, SC 29406-6088 US | 50 MBPS (29630356) | 08/22/2019: Background: 50 Mbps / 50 Mbps / Access, Private IP (PIP) / CHARLESTON, SC, US / PALMETTO NET Status: Ready for activation Telco Circuit ID: ETHR.2011953..SPC Telco Demarcation: 1st flr electrical rm wall mounted ciena 3930 port 3 Verizon BEAS Circuit ID: USASC60251191COV400001 / E4048118 Verizon BEAS Demarcation: mounted to the back wall inside the electrical room and is pinging. Customer United HealthCare will require fiber extension from the electrical room to the suite #417 before activation of the Beas Box. | 199515879 | SC023 | Private IP - PIP (29630355) WAN Analysis Reporting (29630357) Access (29630356) | 29630355 29630357 29630356 | 50 MBPS (29630355) |  | 94651496 (Private IP (PIP)) 94653301 (WAN Analysis Reporting) 94651494 (Access) | C4018981/ADD (29630355) E4048118/ADD (29630356) | ETHR.2011953..SPC (2963035660251101) | 6071316 | 5500 | PVC ID : 6071316 VPN Name : UnitedHealthGroup Router Name : RLGH9E01 VRF Name : V477622:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64851 PE IP Address : 152.162.54.85 CE Address : 152.162.54.86 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29630356) | 1000Base-SX (850nm, Multi Mode Fiber) (29630356) | Ethernet | PALMETTO NET (2963035660251101) | 07/17/2019 (2963035660251101) | 08/21/2019 (2963035660251101) | 08/19/2019 (2963035660251101) | 08/20/2019 (VFORCE) (29630356) | 08/20/2019 (VFORCE) (29630356) | DEMARCDET - 1st flr electrical rm wall mounted ciena 3930 port 3 |  | BRIAN LADD 1-331-223-7121 brian.ladd@optum.com | BRIAN LADD | brian.ladd@optum.com | 1-331-223-7121 | 08/20/2019(Private IP - PIP) 08/20/2019(WAN Analysis Reporting) 08/20/2019(Access) |  |  | 08/30/2019 (29630355) 08/28/2019 (29630356) | 08/26/2019 08/30/2019 | 08/20/2019 |  | Completed | N (29630355) N (29630357) N (29630356) | U0101953 | Jeopardy Notification 2 (07/24/2019) | NSPE0013021306 Order Request # 199515003 | NSPE0013021306
Completed | TX506 EL PASO, TX, US | 11820 MIRIAM DR EL PASO, TX 79936-7537 US | 50 MBPS (29630241) | 08/26/2019: Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / EL PASO, TX, US / ATT / ENID Status: Ready for activation once customer internal cabling is complete Telco Circuit ID: 30/KRGN/615315//SW Telco Demarcation: 1ST FLOOR FIRE ROOM, TELCO BACKBOARD PANEL 1 PORT 1 TAGGED Verizon BEAS Circuit ID: USATX60189471COV400001 / E4048123 Verizon BEAS Demarcation: 1st floor telco room backboard aisle 1, Wall mounted. Slot 1, Port 4. | 199514121 | TX506 | Private IP - PIP (29630240) WAN Analysis Reporting (29630242) Access (29630241) | 29630240 29630242 29630241 | 20 MBPS (29630240) |  | 94651476 (Private IP (PIP)) 94651481 (WAN Analysis Reporting) 94651474 (Access) | C4018982/ADD (29630240) E4048123/ADD (29630241) | 30/KRGN/615315//SW (2963024160189401) | 6071314 | 13000 | PVC ID : 6071314 VPN Name : UnitedHealthGroup Router Name : AQHGE02 VRF Name : V551714:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64889 PE IP Address : 152.181.45.73 CE Address : 152.181.45.74 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29630241) | 1000Base-SX (850nm, Multi Mode Fiber) (29630241) | Ethernet | ATT (2963024160189401) | 08/12/2019 (2963024160189401) | 08/23/2019 (2963024160189401) | 08/23/2019 (2963024160189401) | 08/26/2019 (VFORCE) (29630241) | 08/26/2019 (VFORCE) (29630241) | DEMARCADDR - . DEMARCDET - MDF ROOM 1ST FLOOR MAIN BLDG |  | Jason Ozer 1-210-951-3251 jozer@wellmed.net | JASON LEPAGE | jason_lepage@optum.com | 1-763-744-3108 | 08/26/2019(Private IP - PIP) 08/26/2019(WAN Analysis Reporting) 08/26/2019(Access) |  |  | 09/04/2019 (29630240) 08/30/2019 (29630241) | 09/20/2019 09/26/2019 | 08/26/2019 |  | Completed | N (29630240) N (29630242) N (29630241) | U0101953 | Jeopardy Notification 3 (08/07/2019) | NSPE0013021056 Order Request # 199514075 | NSPE0013021056
Completed | FL418 FORT MYERS, FL | 4220 EXECUTIVE CIR STE 60 FORT MYERS, FL 33916-8005 US | 50 MBPS (29632472) | 11/12/2019: 11/12Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / FORT MYERS, FL, US / CENTURYLINK Status: FOC 11/6- Beas install 11/12 Jesse is the main point of contact Jesse Moreno 8328576095 Next action: Pending Beas- order closure | 199516181 | FL418 | Private IP - PIP (29632471) WAN Analysis Reporting (29632473) Access (29632472) | 29632471 29632473 29632472 | 10 MBPS (29632471) |  | 94652775 (Private IP (PIP)) 94652773 (WAN Analysis Reporting) 94652777 (Access) | C4018994/ADD (29632471) E4048162/ADD (29632472) | 25.KXGS.432947..UFLG (2963247260260501) | 6071400 | 5500 | PVC ID : 6071400 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64639 PE IP Address : 147.225.206.133 CE Address : 147.225.206.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29632472) | 1000Base-SX (850nm, Multi Mode Fiber) (29632472) | Ethernet | CENTURYLINK (2963247260260501) | 10/28/2019 (2963247260260501) | 11/06/2019 (2963247260260501) | 11/07/2019 (2963247260260501) | 11/12/2019 (VFORCE) (29632472) |  | DEMARCDET - first floor telco backboard in FACP room wall mount RAD 203AM PORT 3 |  | Jesse Moreno 1-832-857-6095 Melissa_R_Chapman@Optum.com | JASON LEPAGE | jason_lepage@optum.com | 1-763-744-3108 | 11/12/2019(Private IP - PIP) 11/12/2019(WAN Analysis Reporting) 11/12/2019(Access) |  |  | 11/15/2019 (29632471) 11/13/2019 (29632472) | 12/05/2019 12/11/2019 | 11/12/2019 |  | Completed | N (29632471) N (29632473) N (29632472) | U0101953 | Jeopardy Notification 1 (10/22/2019) | NSPE0013021724 Order Request # 199516217 | NSPE0013021724
Completed | NY463 FLUSHING, NY | 3050 WHITESTONE EXPY FLUSHING, NY 11354-1964 US | 100 MBPS (29681144) | 07/24/2019: 7/24Background: 100 Mbps / 50 Mbps / Access, Private IP (PIP) / FLUSHING, NY, US / VERIZON Status: Foc 7/31 Next Action: Pending Loop Acceptance, Who owns the next action: LEC | 199536241 | NY463 | Private IP - PIP (29681143) WAN Analysis Reporting (29681145) Access (29681144) | 29681143 29681145 29681144 | 50 MBPS (29681143) |  | 94652979 (Private IP (PIP)) 94652984 (WAN Analysis Reporting) 94652977 (Access) | C1094212/ADD (29681143) E4048333/ADD (29681144) | 32.KEGS.068355..NY (2968114460534501) | 6072791 | 15000 | PVC ID : 6072791 VPN Name : UnitedHealthGroup Router Name : NV89E01 VRF Name : V105387:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64824 PE IP Address : 152.162.101.97 CE Address : 152.162.101.98 QoS - Egress Profile: R12 | 100Base-TX (29681144) | 100Base-TX (29681144) | Ethernet | VERIZON (2968114460534501) | 07/23/2019 (2968114460534501) | 07/31/2019 (2968114460534501) | 07/27/2019 (2968114460534501) |  |  | DEMARCDET - 2ND FLOOR ROOM NO 203 WALLMOUNTED AND TAGGED |  | Simon Swist 1-631-466-6357 sswist@natmedtrans.com | ED STILES | ed.stiles@optum.com | 1-770-767-8212 | 07/27/2019(Private IP - PIP) 07/27/2019(WAN Analysis Reporting) 07/27/2019(Access) |  |  | 08/09/2019 (29681143) 08/07/2019 (29681144) | 08/19/2019 08/23/2019 | 07/27/2019 |  | Completed | N (29681143) N (29681145) N (29681144) | U0101953 |  | NSPE0013027907 Order Request # 199536139 | NSPE0013027907
Completed | VA094 RESTON, VA, US | 12355 SUNRISE VALLEY DR RESTON, VA 20191-3467 US | 200 MBPS (29672721) | 08/21/2019: 8/21Background: 200 Mbps / 100 Mbps / Access, Private IP (PIP) / RESTON, VA, US / VZB Status: Site survey 08/15/2019 complete; no extension needed; pending CCR completion > CCR 1830169 add oc12 cards oc48 complete > CCR 1830171 BEAS; equipment install 08/21 Next Action: BEAS installation Who owns the next action: CCR PM | 199551523 | VA094 | Private IP - PIP (29672720) WAN Analysis Reporting (29672722) Access (29672721) | 29672720 29672722 29672721 | 100 MBPS (29672720) |  | 94654047 (Private IP (PIP)) 94654045 (WAN Analysis Reporting) 94654049 (Access) | C5007910/ADD (29672720) E5019606/ADD (29672721) |  | 6072567 | 50000 | PVC ID : 6072567 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64702 PE IP Address : 199.220.235.229 CE Address : 199.220.235.230 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (29672721) | Ethernet |  |  |  |  | 08/19/2019 (CCP) (29672720) 08/19/2019 (CCP) (29672721) | 08/22/2019 (CCP) (29672720) 08/22/2019 (CCP) (29672721) |  |  | JC Lamare 1-240-615-1624 jc.lamare@hcentive.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 08/28/2019(Private IP - PIP) 08/28/2019(WAN Analysis Reporting) 08/28/2019(Access) |  |  | 09/03/2019 (29672720) 08/29/2019 (29672721) | 08/29/2019 09/04/2019 | 08/28/2019 |  | Managed Completed | N (29672720) N (29672722) N (29672721) | U0101953 | Jeopardy Notification 1 (08/01/2019) | NSPE0013032708 Order Request # 199551447 | NSPE0013032708
Completed | TX482-04-IM Cedar Park, TX | 1779 E WHITESTONE BLVD CEDAR PARK, TX 78613 USA | 1.536 MBPS (IQBLSFMX) | 10/28/2019: Background:TX482-04-IM Cedar Park, TX; New 7xT1; No NID; No MNS; ATT Status: loop delivered 10/25 pending testing | 9972669 |  | Private IP (IQBLSFMX) | IQBLSFMX | 10.752 MBPS | P2262476 |  | BCBLGL3J0001 (IQBLSFMX) BCBLGL3J0002 (IQBLSFMX) BCBLGL3J0003 (IQBLSFMX) BCBLGL3J0004 (IQBLSFMX) BCBLGL3J0005 (IQBLSFMX) BCBLGL3J0006 (IQBLSFMX) BCBLGL3J0007 (IQBLSFMX) | 32/HCGS/698001//SW (IQBLSFMX7PKYMB01) |  | 7200 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65183 PE IP Address : 152.181.165.41 CE Address : 152.181.165.42 QoS - Egress Profile: R12 |  |  |  | ATT (IQBLSFMX7PKYMB01) | 10/17/2019 (IQBLSFMX7PKYMB01) | 10/25/2019 (IQBLSFMX7PKYMB01) | 10/29/2019 (IQBLSFMX7PKYMB01) |  |  |  |  | JASON OZER 0012109513251 JOZER@WELLMED.NET |  |  |  | 10/30/2019 (IQBLSFMX) | 10/31/2019 |  | 11/11/2019 (IQBLSFMX) | 11/11/2019 (IQBLSFMX) |  |  |  | N (IQBLSFMX) | 05017789 |  | NSPE0013038499 CW 199554299 | NSPE0013038499
Completed | Head end | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10GL-MPL-WL-PP (6308909) | 10/23/2019: Background: MN053-74-IM Elk River to Cologne, MN; New Protected 10G MPL; MCI Status: Pending PIPO order CCR 1834673 ROADM completed Next action: PIPO order submission and completion of augmentation Who owns the next action: VZB | 9974861 |  | Metro Private Line (6308909) | 6308909 | 10GL-MPL-WL-PP (6308909) |  |  | W1D73338 (6308909) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 10/23/2019 (6308909) |  |  | 09/30/2019 (6308909) | 10/23/2019 (6308909) |  |  |  | N (6308909) | 00198894 |  | NSPE0013049539 ; Elk River Protected 10 Gig MPL A end: 14100 Business Center Drive, Room SR1, Elk River, MN 55330 Tcoms: LLM8/06 Z end: 7383 County Road 140, Cologne, MN Tcoms: 73C,00 | NSPE0013049539
Completed | Head end | 14100 BUSINESS CENTER DR ELK RIVER, MN 55330 USA | 10GL-MPL-WL-PP (6308832) | 10/02/2020: Order Completed on Oct 16, 2019 | 9974925 |  | Metro Private Line (6308832) | 6308832 | 10GL-MPL-WL-PP (6308832) |  |  | W1D73252 (6308832) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 10/16/2019 (6308832) |  |  | 10/23/2019 (6308832) | 10/23/2019 (6308832) |  |  |  | N (6308832) | 00198894 |  | NSPE0013049539 ; Protected 10 Gig MPL A end: 14100 Business Center Drive, Room SR1, Elk River, MN 55330 Tcoms: LLM8/07 Z end: 511 11th Ave S, Suite 320, Minneapolis, MN, 55413 Tcoms: 511,20 | NSPE0013049539
Completed | Head end | 1707 W CREEK LN CHASKA, MN 55318 USA | 10GL-MPL-WL-PP (6308778) | 11/06/2019: 11/6Background: Chaska to Minneapolis, MN; New Protected 10G MPL; MCI Status: Delivered. Pending PIPO Next action: Order closure | 9974939 |  | Metro Private Line (6308778) | 6308778 | 10GL-MPL-WL-PP (6308778) |  |  | W1D73334 (6308778) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 11/11/2019 (6308778) |  |  | 11/20/2019 (6308778) | 10/23/2019 (6308778) |  |  |  | N (6308778) | 00198894 |  | NSPE0013049539 ; Protected 10 Gig MPL A end: 1707 West Creek Lane, Chaska, MN 55318 Tcoms: M6L7,01 Z end: 511 11th Ave S, Suite 320, Minneapolis, MN, 55413 Tcoms: 511,20 | NSPE0013049539
Completed | Head end | 1707 W CREEK LN CHASKA, MN 55318 USA | 10GL-MPL-WL-PP (6308820) | 10/02/2020: Order Completed on Nov 13, 2019 | 9974944 |  | Metro Private Line (6308820) | 6308820 | 10GL-MPL-WL-PP (6308820) |  |  | W1D73317 (6308820) | [7 empty] | METROPOLITAN FIBER SYSTEMS MFS | [6 empty] | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM | MELISSA CHAPMAN 763 744 2114 MELISSA_R_CHAPMAN@OPTUM.COM |  |  |  | 11/13/2019 (6308820) |  |  | 11/29/2019 (6308820) | 10/23/2019 (6308820) |  |  |  | N (6308820) | 00198894 |  | NSPE0013049539 ; Protected 10 Gig MPL A end: 1707 West Creek Lane, Chaska, MN 55318 Tcoms: M6L7,02 Z end: 7383 County Road 140, Cologne, MN Tcoms: 73C,00 | NSPE0013049539
Completed |  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 5000 MBPS (CQBLV54S) 10000 MBPS (IQBLVML3) | 11/11/2019: Background: PIPO 10GB chaska to Minneapolis W1D73334 (6308778) Status BGW design complete issued cross connect dispatch Next action: pending cross connect Who owns the next action: prov | 9977341 |  | Private IP Port Only (CQBLV54S) EVC/PVC Service (N.12161481.6091887) Private IP Port Only (IQBLVML3) | CQBLV54S N.12161481.6091887 IQBLVML3 | 4000 MBPS | P2309944 |  | BOBLJKFG0001 (CQBLV54S) BOBLJKFG0001 (IQBLVML3) |  | 6091888 6091887 | 2500000 | VPN Name : UnitedHealthGroup Router Name : MN3XE01 VRF Name : Vd96545-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65398 PE IP Address : 68.138.99.217 CE Address : 68.138.99.218 QoS - Egress Profile: R12 PVC ID : 6091887 PVC ID : 6091888,6091887 | [11 empty] | UHT NCC TIM GUNDERSON 0017637443141 7637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 11/27/2019 (CQBLV54S) 11/11/2019 (IQBLVML3) |  |  | 12/24/2019 (CQBLV54S) 12/04/2019 (IQBLVML3) | 12/24/2019 (CQBLV54S) 12/04/2019 (IQBLVML3) |  |  |  | N (CQBLV54S) N (N.12161481.6091887) N (IQBLVML3) | 05017789 P2309944 |  | NSPE0013056409 CW 199616779 | NSPE0013296374
Completed | TX777-11-IM Correction of Ports | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US | 10 GBPS (29749541) | 08/14/2019: 8/14Background: 10 Gbps / Access, Internet Dedicated Services / DALLAS, TX, US Status:Ports have been assigned; Order stepped to TI Engineering Next Action: Who owns the next action: Prov Team | 199631953 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (29749540) Access (29749541) | 29749540 29749541 | 2 GBPS (29749540) |  | 1182228043 (Internet Dedicated Services) 1182228039 (Access) | C0173321/ADD (29749540) E7001235/ADD (29749541) |  | 6074903 | 0 | PVC ID : 6074903 VPN Name : Internet Router Name : GW7DFW13 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 10879 PE IP Address : 204.148.197.61 CE Address : 204.148.197.62 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (29749541) | Ethernet | [8 empty] | MATTHEW ADAMS 1-763-553-4616 matthew_adams@optum.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 08/19/2019(Internet Dedicated Services) 08/19/2019(Access) |  |  | 08/27/2019 (29749540) 08/23/2019 (29749541) | 08/29/2019 | 08/19/2019 |  |  | N (29749540) N (29749541) | U0101953 |  | NSPE0013058840 Order Request # 199627373 | NSPE0013058840
Completed | FL413 Tampa, FL; Change handoff | 3000 BAYPORT DR STE 1170 TAMPA, FL 33607-8402 US | 50 MBPS (29749572) | 09/19/2019: 9/19Background:50 Mbps / 10 Mbps / Access, Private IP (PIP) / TAMPA, FL, US / LEVEL 3 Status:Loop Delivered; Beas scheduled for 9/20 Next action:BEAS installation Who owns the next action: Dispatch team | 199632273 | FL413 | WAN Analysis Reporting (29749573) Access (29749572) Private IP - PIP (29749571) | 29749573 29749572 29749571 | 10 MBPS (29749571) |  | 1182404585 (WAN Analysis Reporting) 1182403887 (Access) 1182404573 (Private IP (PIP)) | C4019206/ADD (29749571) E4048706/ADD (29749572) | FL/KXFN/197335/LVLC (2974957255485801) | 6074908 | 30000 | PVC ID : 6074908 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64708 PE IP Address : 152.183.161.205 CE Address : 152.183.161.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29749572) | 1000Base-SX (850nm, Multi Mode Fiber) (29749572) | Ethernet | LEVEL 3 (2974957255485801) | 08/02/2019 (2974957255485801) | 09/19/2019 (2974957255485801) | 09/18/2019 (2974957255485801) | 09/20/2019 (VFORCE) (29749572) |  | DEMARCDET - X |  | Ferdinand Vega 1-954-378-0680 ferdinand_vega@uhg.com | SAHIL TUTEJA | sahil_tuteja@optum.com | 91-828-567-0647 | 09/20/2019(WAN Analysis Reporting) 09/20/2019(Access) 09/20/2019(Private IP - PIP) |  |  | 09/30/2019 (29749571) 09/26/2019 (29749572) | 11/01/2019 10/28/2019 | 09/20/2019 |  | Completed | N (29749573) N (29749572) N (29749571) | U0101953 | Jeopardy Notification 2 (09/17/2019) | NSPE0013060425 Order Request # 199632027 | NSPE0013060425
Completed | AZ731 PHOENIX, AZ, US | 615 N 48TH ST PHOENIX, AZ 85008-6608 US | 1 GBPS (29754292) | 10/18/2019: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 199640123 | Phoenix _ AZ731-02-IJ | Private IP - PIP (29754291) WAN Analysis Reporting (29754293) Access (29754292) | 29754291 29754293 29754292 | 500 MBPS (29754291) |  | 1182814037 (Private IP (PIP)) 1182814039 (WAN Analysis Reporting) 1182814033 (Access) | C0173286/ADD (29754291) E5019903/ADD (29754292) | 19.KXGS.437859..MS (2975429253851601) | 6075040 | 550000 | PVC ID : 6075040 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64915 PE IP Address : 152.183.120.233 CE Address : 152.183.120.234 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (29754292) | 1000Base-LX (1310nm Single Mode Fiber) (29754292) | Ethernet | CENTURYLINK (2975429253851601) | 08/02/2019 (2975429253851601) | 08/14/2019 (2975429253851601) | 08/12/2019 (2975429253851601) | 10/29/2019 (VFORCE) (29754292) | 10/29/2019 (VFORCE) (29754292) | DEMARCDET - X |  | CLIFF WALDREP 1-480-881-8560 clifton.waldrep@avella.com | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 10/29/2019(Private IP - PIP) 10/29/2019(WAN Analysis Reporting) 10/29/2019(Access) |  |  | 11/01/2019 (29754291) 10/30/2019 (29754292) | 12/03/2019 12/09/2019 | 10/29/2019 |  | Completed | N (29754291) N (29754293) N (29754292) | U0101953 | Jeopardy Notification 1 (10/21/2019) | NSPE0013063235 Order Request # 199640005 | NSPE0013063235
Completed | TX527 MCALLEN, TX | 4903 N Mccoll Rd Mcallen, Tx 78504-2310 US | 50 MBPS (29778873) | 11/04/2019: 11/4Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / Mcallen, Tx, US / ATT / Dual NID Status: Loop delivered 11/30-BEAS Schedule 11/05 Next Action: BEAS installation Who owns the next action: VZB | 199664363 | TX527 | Private IP - PIP (29778872) WAN Analysis Reporting (29778874) Access (29778873) | 29778872 29778874 29778873 | 10 MBPS (29778872) |  | 94658688 (Private IP (PIP)) 94658695 (WAN Analysis Reporting) 94658691 (Access) | C4019271/ADD (29778872) E4048887/ADD (29778873) | 38/KRGN/613918//SW (2977887361551101) | 6075763 | 5500 | PVC ID : 6075763 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64638 PE IP Address : 68.138.108.93 CE Address : 68.138.108.94 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29778873) | 1000Base-SX (850nm, Multi Mode Fiber) (29778873) | Ethernet | ATT (2977887361551101) | 10/25/2019 (2977887361551101) | 10/30/2019 (2977887361551101) | 10/31/2019 (2977887361551101) | 11/05/2019 (VFORCE) (29778873) |  | DEMARCADDR - . DEMARCDET - MAIN BLDG 1ST FLOOR MPOE ROOM |  | Gabriel Rodriguez 1-210-833-8929 GRodriguez1@wellmed.net | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 11/05/2019(Private IP - PIP) 11/05/2019(WAN Analysis Reporting) 11/05/2019(Access) |  |  | 11/08/2019 (29778872) 11/06/2019 (29778873) | 12/04/2019 12/10/2019 | 11/08/2019 |  | Completed | N (29778872) N (29778874) N (29778873) | U0101953 | Jeopardy Notification 1 (10/23/2019) | NSPE0013071627 Order Request # 199663557 | NSPE0013071627
Completed | TX514 Kingsville, TX | 1601 S Hwy 77 Byp ste E Kingsville, Tx 78363-6679 US | 50 MBPS (29798703) | 11/06/2019: 11/6Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / Kingsville, TX, US Status: Loop Delivered 11/4 BEAS Schedule 11/06 Next Action: BEAS Install | 199681089 | TX514 | Access (29798703) Private IP - PIP (29798702) WAN Analysis Reporting (29798704) | 29798703 29798702 29798704 | 10 MBPS (29798702) |  | 94659495 (Access) 94659493 (Private IP (PIP)) 94659499 (WAN Analysis Reporting) | E4048989/ADD (29798703) C4019302/ADD (29798702) | 34/KRGN/614078//SW (2979870361660901) | 6076336 | 5500 | PVC ID : 6076336 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64838 PE IP Address : 152.164.183.225 CE Address : 152.164.183.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29798703) | 1000Base-SX (850nm, Multi Mode Fiber) (29798703) | Ethernet | ATT (2979870361660901) | 08/28/2019 (2979870361660901) | 11/05/2019 (2979870361660901) | 11/04/2019 (2979870361660901) | 11/06/2019 (VFORCE) (29798703) |  | DEMARCDET - 1ST FLR ELEC RM 12 PORT PANEL POST 1 |  | Gabe rodriguez 1-210-974-6678 GRodriguez1@wellmed.net | JASON SALAPING | jason_salaping@gmail.com | 632-462-2446 | 11/06/2019(Access) 11/06/2019(Private IP - PIP) 11/06/2019(WAN Analysis Reporting) |  |  | 11/27/2019 (29798703) 12/03/2019 (29798702) | 10/08/2019 10/14/2019 | 11/08/2019 |  | Completed | N (29798703) N (29798702) N (29798704) | U0101953 | Jeopardy Notification 2 (08/21/2019) | NSPE0013077769 Order Request # 199681005 | NSPE0013077769
Completed | FL211 Tampa, FL | 10210 Windhorst Rd Tampa, Fl 33619-7828 US | 100 MBPS (29813443) | 09/18/2019: 9/18Background: 100 Mbps / 50 Mbps / Access, Private IP (PIP) / Tampa, Fl, US / BRIGHT HOUSE / DUAL NID Status: Loop delivered-NNI issue resolved; Beas dispatch 9/19 Next Action: Beas installation Who owns the next action: Dispatch team | 199690069 | FL211 | Private IP - PIP (29813442) WAN Analysis Reporting (29813444) Access (29813443) | 29813442 29813444 29813443 | 50 MBPS (29813442) |  | 94659812 (Private IP (PIP)) 94659818 (WAN Analysis Reporting) 94659814 (Access) | C1095235/ADD (29813442) E4049080/ADD (29813443) | 81.L1XX.908930..TWCC (2981344361714901) | 6076775 | 30000 | PVC ID : 6076775 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64763 PE IP Address : 199.220.160.177 CE Address : 199.220.160.178 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29813443) | 1000Base-SX (850nm, Multi Mode Fiber) (29813443) | Ethernet | BRIGHT HOUSE (2981344361714901) | 08/13/2019 (2981344361714901) | 10/10/2019 (2981344361714901) | 09/13/2019 (2981344361714901) | 09/19/2019 (VFORCE) (29813443) | 09/19/2019 (VFORCE) (29813443) | DEMARCDET - Customers MDF room Cisco ASR920 activated on port 009 |  | Khym A Wood 1-540-777-6888 khym_wood@uhg.com | Roderick Mushatt | roderick.mushatt@optum.com | 1-331-725-0303 | 09/19/2019(Private IP - PIP) 09/19/2019(WAN Analysis Reporting) 09/19/2019(Access) |  |  | 10/21/2019 (29813442) 10/17/2019 (29813443) | 09/20/2019 09/26/2019 | 09/23/2019 |  | Completed | N (29813442) N (29813444) N (29813443) | U0101953 |  | NSPE0013083177 Order Request # 199689965 | NSPE0013083177
Completed | TX525 Portland, TX | 2413 Memorial Pkwy Portland, Tx 78374-3209 US | 50 MBPS (29828700) | 10/02/2019: 10/2Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / Portland, Tx, US / TWC / DUAL NID Status: Loop delivered 9/30; Beas install 10/2 Next Action: BEAS Scheduled and Dispatch Who owns the next action: BNE | 199704073 | TX525 | Private IP - PIP (29828699) WAN Analysis Reporting (29828701) Access (29828700) | 29828699 29828701 29828700 | 10 MBPS (29828699) |  | 94661215 (Private IP (PIP)) 94661220 (WAN Analysis Reporting) 94661217 (Access) | C4019375/ADD (29828699) E4049144/ADD (29828700) | 36.L1XX.004780..TWCC (2982870061903701) | 6077111 | 30000 | PVC ID : 6077111 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64841 PE IP Address : 152.161.85.253 CE Address : 152.161.85.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29828700) | 1000Base-SX (850nm, Multi Mode Fiber) (29828700) | Ethernet | TIME WARNER CABLE (2982870061903701) | 08/15/2019 (2982870061903701) | 11/22/2019 (2982870061903701) | 09/30/2019 (2982870061903701) | 10/02/2019 (VFORCE) (29828700) | 10/02/2019 (VFORCE) (29828700) | DEMARCDET - IT closet in the hallway of the 1st flr in a customer owned rack |  | Gabriel Rodriguez 1-210-974-6678 GRodriguez1@wellmed.net | HERBERT VILLOSTAS | herbert_villostas@optum.com | 632-790-6516 | 10/02/2019(Private IP - PIP) 10/02/2019(WAN Analysis Reporting) 10/02/2019(Access) |  |  | 12/05/2019 (29828699) 12/03/2019 (29828700) | 12/31/2019 01/06/2020 | 10/08/2019 |  | Completed | N (29828699) N (29828701) N (29828700) | U0101953 | Jeopardy Notification 1 (08/23/2019) | NSPE0013088146 Order Request # 199704067 | NSPE0013088146
Completed | TX473 LEANDER, TX | 601 CRYSTAL FALLS PKWY STE 100 LEANDER, TX 78641-3613 US | 50 MBPS (29884991) | 02/28/2020: 2/27Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / LEANDER, TX, US / ATT Status:Order complete- Ready for activation Next Action: Who owns the next action:customer | 199761469 | TX473 | Private IP - PIP (29884990) WAN Analysis Reporting (29884992) Access (29884991) | 29884990 29884992 29884991 | 10 MBPS (29884990) |  | 1188198645 (Private IP (PIP)) 1188198647 (WAN Analysis Reporting) 1188198641 (Access) | C4019482/ADD (29884990) E4049502/ADD (29884991) | 32/KRGN/653843//SW (2988499162300801) | 6078795 | 5500 | PVC ID : 6078795 VPN Name : UnitedHealthGroup Router Name : AX39E01 VRF Name : Vd31961:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65222 PE IP Address : 152.181.218.209 CE Address : 152.181.218.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29884991) | 1000Base-SX (850nm, Multi Mode Fiber) (29884991) | Ethernet | ATT (2988499162300801) | 01/30/2020 (2988499162300801) | 02/19/2020 (2988499162300801) | 02/20/2020 (2988499162300801) | 02/21/2020 (VFORCE) (29884991) |  | DEMARCDET - REAR WALL AT THE BACK OF BUILDING TAGGED WITH A CKT ID NOT EXT |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 02/21/2020(Private IP - PIP) 02/21/2020(WAN Analysis Reporting) 02/21/2020(Access) |  |  | 03/19/2020 (29884990) 03/17/2020 (29884991) | 03/11/2020 03/17/2020 | 02/21/2020 |  | Completed | N (29884990) N (29884992) N (29884991) | U0101953 | Jeopardy Notification 2 (01/29/2020) | NSPE0013106235 Order Request # 199752599 | NSPE0013106235
Completed | NM045 LAS CRUCES, NM | 271 PASEO DE DIA STE 1A LAS CRUCES, NM 88011 US | 50 MBPS (29885050) | 10/15/2019: 10/15Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / LAS CRUCES, NM, US / CENTURYLINK / DUAL NID Status: Order ready for activation Next Action: customer activation Who owns the next action: | 199761499 | NM045 | Private IP - PIP (29885049) WAN Analysis Reporting (29885051) Access (29885050) | 29885049 29885051 29885050 | 20 MBPS (29885049) |  | 1188514437 (Private IP (PIP)) 1188514439 (WAN Analysis Reporting) 1188514433 (Access) | C4019483/ADD (29885049) E4049503/ADD (29885050) | 59.KXGS.448483..MS (2988505062396101) | 6078796 | 13000 | PVC ID : 6078796 VPN Name : UnitedHealthGroup Router Name : AQHGE02 VRF Name : V551714:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65039 PE IP Address : 152.181.218.113 CE Address : 152.181.218.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29885050) | 1000Base-SX (850nm, Multi Mode Fiber) (29885050) | Ethernet | CENTURYLINK (2988505062396101) | 08/23/2019 (2988505062396101) | 10/16/2019 (2988505062396101) | 10/10/2019 (2988505062396101) | 10/15/2019 (VFORCE) (29885050) | 10/15/2019 (VFORCE) (29885050) | DEMARCDET - 1ST FLOOR IT ROOM EAST WALL SHELF01 POSITION03 |  | Jason Ozer 1-210-951-3251 jozer@wellmed.net | JASON LEPAGE | jason_lepage@optum.com | 1-763-744-3108 | 10/15/2019(Private IP - PIP) 10/15/2019(WAN Analysis Reporting) 10/15/2019(Access) |  |  | 10/25/2019 (29885049) 10/23/2019 (29885050) | 11/14/2019 11/20/2019 | 10/15/2019 |  | Completed | N (29885049) N (29885051) N (29885050) | U0101953 | Jeopardy Notification 1 (09/16/2019) | NSPE0013108248 Order Request # 199757419 | NSPE0013108248
Completed | Headend w0z48442 / BOBKTD960001 | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 7000 MBPS (CQBLSSGQ) |  | 10001094 |  | Private IP Port Only (CQBLSSGQ) | CQBLSSGQ | 7000 MBPS 7000 MBPS (CQBLSSGQ) | P1932297 |  | BOBKTD960001 (CQBLSSGQ) |  | 5539402 | 110500 270000 314000 384 360000 1500000 | PVC ID : 5539402 VPN Name : UHG-XLHealth,UHG-UC,UHG-IPTF,UnitedHealthGroup-IDN,UHG-ECC,UnitedHealthGroup Router Name : MN3GE01 VRF Name : V594628:UHGXLHealth,V656367:UHGUC,V594624:UHGIPTF,V594626:UnitedHealthGroupIDN,V594627:UHGECC,V594623:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : v4-152.162.46.225,v6-68.137.39.25,v4-152.176.215.13,v6-152.192.111.185,v4-147.225.22.233,v6-152.161.107.161 CE Address : v4-152.162.46.226,v6-68.137.39.26,v4-152.176.215.14,v6-152.192.111.186,v4-147.225.22.234,v6-152.161.107.162 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/28/2019 (CQBLSSGQ) | 09/18/2019 |  | 09/20/2019 (CQBLSSGQ) | 09/20/2019 (CQBLSSGQ) |  |  |  | N (CQBLSSGQ) | 05017789 |  | NSPE0013111440 CW 199759117 | NSPE0013111440
Completed | Headend W1B05846 / BOBKWHD00001 | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 7000 MBPS (CQBLSSGS) | 08/28/2019: 8/28Background: UPGRADE PORT TO 7G AND UHGECC VPN TO 1.4G PIR Status: System issue encountered. Error in port assignment. Ticket created for resolution. Next action: ICOM order, then Ready for hotcut | 10000640 |  | Private IP Port Only (CQBLSSGS) | CQBLSSGS | 7000 MBPS | P1957529 |  | BOBKWHD00001 (CQBLSSGS) |  | 5463422 | 0 | PVC ID : 5463422 VPN Name : UnitedHealthGroup-ECCMA Router Name : MZZ9E01 VRF Name : V600584:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : 152.161.80.1 CE Address : 152.161.80.2 QoS - Egress Profile: R12 | [11 empty] | ED ED 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/30/2019 (CQBLSSGS) |  |  | 09/20/2019 (CQBLSSGS) | 09/20/2019 (CQBLSSGS) |  |  |  | N (CQBLSSGS) | 05017789 |  | NSPE0013105539 CW 199748145 | NSPE0013105539
Completed | Headend W1B05870 / BOBKTFPX0001 | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 7000 MBPS (CQBLSPHS) |  | 10000642 |  | Private IP Port Only (CQBLSPHS) | CQBLSPHS | 7000 MBPS 7000 MBPS (CQBLSPHS) | P1932463 |  | BOBKTFPX0001 (CQBLSPHS) |  | 5463424 | 360000 270000 314000 2688 1500000 | PVC ID : 5463424 VPN Name : UHG-ECC,UHG-UC,UHG-IPTF,UnitedHealthGroup-ECCMA,UnitedHealthGroup Router Name : MN39E01 VRF Name : V594781:UHGECC,V645094:UHGUC,V601668:UHGIPTF,V601670:UnitedHealthGroupECCMA,V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : v4-152.177.151.97,v6-199.220.202.221,v4-152.187.248.73,v6-68.136.152.241,v4-152.162.11.193 CE Address : v4-152.177.151.98,v6-199.220.202.222,v4-152.187.248.74,v6-68.136.152.242,v4-152.162.11.194 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/28/2019 (CQBLSPHS) | 09/17/2019 |  | 09/23/2019 (CQBLSPHS) | 09/23/2019 (CQBLSPHS) |  |  |  | N (CQBLSPHS) | 05017789 |  | NSPE0013105545 CW 199748149 | NSPE0013105545
Completed | Headend W0Z66371 / BOBKWCW20001 | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 7000 MBPS (CQBLSSG0) |  | 10000641 |  | EVC/PVC Service (C.12106380.5538820) Private IP Port Only (CQBLSSG0) | C.12106380.5538820 CQBLSSG0 | 7000 MBPS | P1955436 |  | BOBKWCW20001 (CQBLSSG0) |  | 5538820 | 24576 | PVC ID : 5538820 VPN Name : Alere-LLC-WAN Router Name : MZZGE01 VRF Name : Vg35543:AlereLLCWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : 152.176.170.69 CE Address : 152.176.170.70 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 7637442081 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/28/2019 (CQBLSSG0) |  |  | 09/20/2019 (CQBLSSG0) | 09/20/2019 (CQBLSSG0) |  |  |  | N (C.12106380.5538820) N (CQBLSSG0) | P1955436 05017789 |  | NSPE0013105555 CW 199748141 | NSPE0013105555
Completed | Headend W1D29882 / BOBLC5X60001 | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 5000 MBPS (CQBLSSLX) |  | 10001084 |  | Private IP Port Only (CQBLSSLX) | CQBLSSLX | 4000 MBPS | P2198253 |  | BOBLC5X60001 (CQBLSSLX) |  | 6079548 | 768 | PVC ID : 6079548 VPN Name : UHG-SDWAN Router Name : MZZ9E01 VRF Name : Vd76606:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.161.122.109 CE Address : 152.161.122.110 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0015072950001 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/28/2019 (CQBLSSLX) |  |  | 09/23/2019 (CQBLSSLX) | 09/23/2019 (CQBLSSLX) |  |  |  | N (CQBLSSLX) | 05017789 |  | NSPE0013111425 CW 199758571 | NSPE0013111425
Completed | Headend BOBLC5XS0001 | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 5000 MBPS (CQBLSSK1) |  | 10000619 |  | Private IP Port Only (CQBLSSK1) | CQBLSSK1 | 4000 MBPS | P2198241 |  | BOBLC5XS0001 (CQBLSSK1) |  | 6079543 | 72000 | PVC ID : 6079543 VPN Name : UHG-SDWAN Router Name : MN39E01 VRF Name : Vd76602:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.164.75.1 CE Address : 152.164.75.2 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/28/2019 (CQBLSSK1) |  |  | 09/20/2019 (CQBLSSK1) | 09/20/2019 (CQBLSSK1) |  |  |  | N (CQBLSSK1) | 05017789 |  | NSPE0013102650 CW 199731993 | NSPE0013102650
Completed | C1646 Henderson, NV | 1111 Mary Crest Rd ste H Henderson, NV 89074-8747 US | 100 MBPS (29926738) | 10/15/2019: 10/15Background:100 Mbps / 50 Mbps / Access, Private IP (PIP) / Henderson, NV, US / COX / DUAL NID Status: Loop delivered 10/15- Pending Beas Next action: Pending Beas Who owns the next action: Tech Dispatch | 199799041 | C1646 | Private IP - PIP (29926737) WAN Analysis Reporting (29926739) Access (29926738) | 29926737 29926739 29926738 | 50 MBPS (29926737) |  | 94668509 (Private IP (PIP)) 94668516 (WAN Analysis Reporting) 94668513 (Access) | C1095801/ADD (29926737) E4049684/ADD (29926738) |  | 6079855 | 25000 | PVC ID : 6079855 VPN Name : UHG-ECC Router Name : LSVG9E03 VRF Name : Vd84509:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65475 PE IP Address : 152.176.233.41 CE Address : 152.176.233.42 QoS - Egress Profile: C13 | 1000Base-SX-850nm (29926738) | 1000Base-SX (850nm, Multi Mode Fiber) (29926738) | Ethernet | COX (2992673862659701) | 10/11/2019 (2992673862659701) | 10/15/2019 (2992673862659701) | 10/15/2019 (2992673862659701) | 10/16/2019 (VFORCE) (29926738) | 10/16/2019 (VFORCE) (29926738) | DEMARCDET - 1st flr main electrical rm |  | Hossein Naderi 1-702-929-6289 hnaderi@rdicorp.com | PAUL BARCLAY | paul.barclay@optum.com | 1-617-530-2394 | 10/16/2019(Private IP - PIP) 10/16/2019(WAN Analysis Reporting) 10/16/2019(Access) |  |  | 10/24/2019 (29926737) 10/22/2019 (29926738) | 01/16/2020 01/22/2020 | 10/16/2019 |  | Completed | N (29926737) N (29926739) N (29926738) | U0101953 |  | NSPE0013123248 Order Request # 199799011 | NSPE0013123248
Completed | C1647 Blue Ash, OH | 4500 Lake Forest Dr Blue Ash, OH 45242-3728 US | 100 MBPS (29926790) | 09/24/2019: 9/24Background: 100 Mbps / 50 Mbps / Access, Private IP (PIP) / Blue Ash, OH, US / CINCINNATTI BELL Status: FOC 09/24-Loop delivered 9/23-Beas Install 9/25 Next Action: BEAS installation Who owns the next action: LEC | 199802349 | C1647 | Private IP - PIP (29926789) WAN Analysis Reporting (29926791) Access (29926790) | 29926789 29926791 29926790 | 50 MBPS (29926789) |  | 94668264 (Private IP (PIP)) 94668266 (WAN Analysis Reporting) 94668268 (Access) | C1095800/ADD (29926789) E4049685/ADD (29926790) | /KFGS/563818//CB (2992679062662501) | 6079857 | 25000 | PVC ID : 6079857 VPN Name : UHG-ECC Router Name : WYV9E01 VRF Name : Ve56543:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65473 PE IP Address : 199.220.21.221 CE Address : 199.220.21.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29926790) | 1000Base-SX (850nm, Multi Mode Fiber) (29926790) | Ethernet | CINCINNATTI BELL (2992679062662501) | 08/29/2019 (2992679062662501) | 09/24/2019 (2992679062662501) | 09/24/2019 (2992679062662501) | 09/25/2019 (VFORCE) (29926790) | 09/25/2019 (VFORCE) (29926790) |  |  | Gery Leistner 1-513-600-3522 gleistner@rdicorp.com | PAUL BARCLAY | paul.barclay@optum.com | 1-617-530-2394 | 09/25/2019(Private IP - PIP) 09/25/2019(WAN Analysis Reporting) 09/25/2019(Access) |  |  | 10/03/2019 (29926789) 10/01/2019 (29926790) | 10/08/2019 10/14/2019 | 09/25/2019 |  | Completed | N (29926789) N (29926791) N (29926790) | U0101953 |  | NSPE0013123553 Order Request # 199799745 | NSPE0013123553
Completed | Islandia, NY UPGRADE 50M TO 100M | 2950 EXPRESS DR S ISLANDIA, NY 11749-1400 US | 100 MBPS | 09/08/2019 Successfully activated | 199831159 | UNITED HEALTH GROUP | Private IP - PIP (29959778) Access WAN Analysis Reporting (29959780) | 29959778 29959780 | 100 MBPS (29959778) |  | 94559071 (Private IP (PIP)) 94559075 94559078 (WAN Analysis Reporting) | C1079488/NONE (29959778) |  | 6009394 | 30000 | PVC ID : 6009394 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64553 PE IP Address : 68.139.92.193 CE Address : 68.139.92.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Melissa Chapman Melissa Chapman 1-176-374-4211 melissa_r_chapman@optum.com | Jason Salaping | jason_salaping@optum.com | 632-462-2446 | 09/09/2019(Private IP | 09/08/2019 |  | 09/04/2019 (29959778) | 09/12/2019 09/12/2019 (24061917.2) | 09/09/2019 |  | Approved MSD Approved | N (29959778) N N (29959780) | U0101953 |  | NSPE0013133890 Order Request # 199828459 | NSPE0013133890
Completed | AZ149 Phoenix, AZ | 16620 N 40th St ste C1 Phoenix, AZ 85032-3358 US | 100 MBPS (30019211) | 11/06/2019: 11/6Background:100 MBPS 50 MBPS PIP-E Phoenix, AZ, Status: BEAS Schedule 11/6 Next action: Beas scheduled Who owns the next action: BNE/ customer | 199887223 | AZ149 | Private IP - PIP (30019210) WAN Analysis Reporting (30019212) Access (30019211) | 30019210 30019212 30019211 | 50 MBPS (30019210) |  | 94676389 (Private IP (PIP)) 94676395 (WAN Analysis Reporting) 94676391 (Access) | C1096276/ADD (30019210) E4050093/ADD (30019211) |  | 6082301 | 30000 | PVC ID : 6082301 VPN Name : UnitedHealthGroup Router Name : PHN1XE02 VRF Name : Vd82055-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64646 PE IP Address : 68.137.13.161 CE Address : 68.137.13.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30019211) | 1000Base-SX (850nm, Multi Mode Fiber) (30019211) | Ethernet | COX (3001921163321502) | 09/18/2019 (3001921163321502) | 10/22/2019 (3001921163321502) | 10/23/2019 (3001921163321502) | 11/07/2019 (VFORCE) (30019211) |  | DEMARCADDR - 16620 N 40th St Phoenix AZ DEMARCDET - PHONE ROOM 1ST FLOOR WALL MOUNTEDON THE WEST WALL AND TAGGED |  | Heather Welch 1-602-583-0815 heatherw@4cmedicalgroup.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 11/06/2019(Private IP - PIP) 11/06/2019(WAN Analysis Reporting) 11/06/2019(Access) |  |  | 11/15/2019 (30019210) 11/13/2019 (30019211) | 12/17/2019 12/23/2019 | 11/06/2019 |  | Completed | N (30019210) N (30019212) N (30019211) | U0101953 | Jeopardy Notification 1 (10/24/2019) | NSPE0013155594 | NSPE0013155594
Completed | AZ147 Fountain Hills, AZ | 16838 E Palisades Blvd Fountain Hills, AZ 85268-3786 US | 100 MBPS (30019628) | 01/15/2020: Order Completed on Jan 15, 2020 | 199901015 | AZ147 | Private IP - PIP (30019627) WAN Analysis Reporting (30019629) Access (30019628) | 30019627 30019629 30019628 | 50 MBPS (30019627) |  | 94676430 (Private IP (PIP)) 94676434 (WAN Analysis Reporting) 94676432 (Access) | C1096282/ADD (30019627) E4050099/ADD (30019628) | 19.KXGS.451552..MS (3001962862713001) | 6082314 | 30000 | PVC ID : 6082314 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64750 PE IP Address : 68.138.119.137 CE Address : 68.138.119.138 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30019628) | 1000Base-SX (850nm, Multi Mode Fiber) (30019628) | Ethernet | CENTURYLINK (3001962862713001) | 12/11/2019 (3001962862713001) | 01/17/2020 (3001962862713001) | 01/14/2020 (3001962862713001) | 01/15/2020 (VFORCE) (30019628) | 01/15/2020 (VFORCE) (30019628) | DEMARCDET - 1st flr main It in wall way bEETWEEN 4c smil employee entrance wall mounted on south wall, northside of building c |  | Linda Vaccaro 1-732-371-6347 Lindav@4cmedicalgroup.com | VASUDEV K | vasudev.k@optum.com | 6-386-175-8263 | 01/15/2020(Private IP - PIP) 01/15/2020(WAN Analysis Reporting) 01/15/2020(Access) |  |  | 01/29/2020 (30019627) 01/27/2020 (30019628) | 02/18/2020 02/24/2020 | 01/15/2020 |  | Completed | N (30019627) N (30019629) N (30019628) | U0101953 | Jeopardy Notification 1 (11/11/2019) | NSPE0013155047 Order Request # 199885671 | NSPE0013155047
Completed | AZ148-02-IM | 17218 N 72nd Dr ste 101 Glendale, AZ 85308-8580 US | 100 MBPS (30027666) | 10/04/2019: 10/4Background:100mbps 50mbps PIP-E Glendale, AZ COX DUAL NID Status: loop delivered and Beas Install 10/7 Next action: Pending Beas install Who owns the next action: VZT | 199908675 | AZ148-02-IM | Private IP - PIP (30027665) WAN Analysis Reporting (30027667) Access (30027666) | 30027665 30027667 30027666 | 50 MBPS (30027665) |  | 94677070 (Private IP (PIP)) 94677075 (WAN Analysis Reporting) 94677072 (Access) | C1096317/ADD (30027665) E4050130/ADD (30027666) |  | 6082474 | 30000 | PVC ID : 6082474 VPN Name : UnitedHealthGroup Router Name : PHN1XE02 VRF Name : Vd82055-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64914 PE IP Address : 68.138.177.157 CE Address : 68.138.177.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30027666) | 1000Base-SX (850nm, Multi Mode Fiber) (30027666) | Ethernet | COX (3002766663502801) | 09/13/2019 (3002766663502801) | 10/04/2019 (3002766663502801) | 10/04/2019 (3002766663502801) | 10/09/2019 (VFORCE) (30027666) | 10/09/2019 (VFORCE) (30027666) | DEMARCDET - 1st flr in the MDF wall mounted rack customer is 16 on patch panel at the top of the rack |  | Isaiah Beltran 1-623-521-1407 isaiahb@4cmedicalgroup.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 10/07/2019(Private IP - PIP) 10/07/2019(WAN Analysis Reporting) 10/07/2019(Access) |  |  | 10/15/2019 (30027665) 10/11/2019 (30027666) | 10/24/2019 10/30/2019 | 10/07/2019 |  | Completed | N (30027665) N (30027667) N (30027666) | U0101953 |  |  | NSPE0013162632
Completed | NM047-01-IM TX493-04-IM | 530 N TELSHOR BLVD LAS CRUCES, NM 88011 USA | 1.536 MBPS (IQBLT8M1) | 11/20/2019: 11/7Background: PIP-TDM (7xT1) LAS CRUCES MN Status: Order completed. Ready for activation. Next action: Order activation Who owns the next action: Customer | 10021883 |  | Private IP (IQBLT8M1) EVC/PVC Service (N.12124014.6083592) | IQBLT8M1 N.12124014.6083592 | 10.752 MBPS | P2307944 |  | BCBLJGY50001 (IQBLT8M1) BCBLJGY50002 (IQBLT8M1) BCBLJGY50003 (IQBLT8M1) BCBLJGY50004 (IQBLT8M1) BCBLJGY50005 (IQBLT8M1) BCBLJGY50006 (IQBLT8M1) BCBLJGY50007 (IQBLT8M1) | 59/HCGS/344149//MS (IQBLT8M1X3MZMB01) | 6083592 | 8000 | VPN Name : UnitedHealthGroup Router Name : WITGE03 VRF Name : V637094:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65433 PE IP Address : 152.162.194.117 CE Address : 152.162.194.118 QoS - Egress Profile: R12 PVC ID : 6083592 |  |  |  | CENTURYLINK (IQBLT8M1X3MZMB01) | 09/27/2019 (IQBLT8M1X3MZMB01) | 10/10/2019 (IQBLT8M1X3MZMB01) | 10/29/2019 (IQBLT8M1X3MZMB01) |  |  |  |  | JASON OZER 0015755264941 2109513251 JOZER@WELLMED.NET |  |  |  | 11/07/2019 (IQBLT8M1) |  |  | 11/07/2019 (IQBLT8M1) | 10/15/2019 (IQBLT8M1) |  |  |  | N (IQBLT8M1) N (N.12124014.6083592) | 05017789 P2307944 |  | NSPE0013152308 | NSPE0013152308
Completed | PR518 | 997 CALLE SAN ROBERTO SAN JUAN, PR 00926-2759 PR | 500 MBPS (30141407) | 11/13/2019: 11/13Background: 500 Mbps / 300 Mbps / Access, Private IP (PIP) / SAN JUAN, PR, PR Status:Foc 11/19- Loop delivered 11/13 Next Action: Ready for activation Who owns the next action: | 199971057 | PR518 | WAN Analysis Reporting (30141408) Access (30141407) Private IP - PIP (30141406) | 30141408 30141407 30141406 | 300 MBPS (30141406) |  | 1196155683 (WAN Analysis Reporting) 1196155625 (Access) 1196155629 (Private IP (PIP)) | C5008462/ADD (30141406) E5021254/ADD (30141407) | 154-3697 (30141407PTT00001) | 6084883 | 90000 | PVC ID : 6084883 VPN Name : UnitedHealthGroup Router Name : SNJN9E01 VRF Name : Vc13521:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65256 PE IP Address : 68.136.122.77 CE Address : 68.136.122.78 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (30141407) | 1000Base-LX (1310nm Single Mode Fiber) (30141407) | Ethernet | RQCA (30141407PTT00001) | 10/15/2019 (30141407PTT00001) | 11/19/2019 (30141407PTT00001) | 11/13/2019 (30141407PTT00001) |  |  |  |  | Enrique Vila-Biaggi, 1-787-274-0996 ejvila@iedifiko.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 11/13/2019(WAN Analysis Reporting) 11/13/2019(Access) 11/13/2019(Private IP - PIP) |  |  | 12/06/2019 (30141406) 12/03/2019 (30141407) | 12/18/2019 12/12/2019 | 11/13/2019 |  | Completed | N (30141408) N (30141407) N (30141406) | U0101953 | Jeopardy Notification 1 (10/30/2019) | NSPE0013183506 | NSPE0013183506
Completed | C1631-01-IM | 683 S 4150 W SALT LAKE CITY, UT 84104-4409 US | 1 GBPS | 09/24/2019: Your order is on track: Provisioning Department accepted the order on Sep 24, 2019 and has begun processing. | 199970647 | C1631-01-IM | Private IP - PIP (30107130) Access WAN Analysis Reporting (30107132) | 30107130 30107132 | 1 GBPS (30107130) |  | 208399637 (Private IP (PIP)) 208399635 208399638 (WAN Analysis Reporting) | C0136280/NONE (30107130) |  | 5951000 | 550000 | PVC ID : 5951000 VPN Name : UHG-ECC Router Name : SLY9E01 VRF Name : V466953:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65455 PE IP Address : 152.183.150.141 CE Address : 152.183.150.142 QoS - Egress Profile: C13 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | DAN KEPPLER 1-801-257-6363 dan.keppler@teleperformance.com | Erwin Edoria | erwin_edoria@optum.com | 632-588-3204 | 10/20/2019(Private IP |  |  | 09/24/2019 (30107130) | 10/03/2019 10/03/2019 (20785787.2) | 10/21/2019 |  | Completed Activated/Installed | N (30107130) N N (30107132) | U0101953 |  | NSPE0013179592 | NSPE0013179592
Completed | UnitedHealth Group M&R | 2091 COMMERCE DR MCKINNEY, TX 75069-8262 US | 1 GBPS | 09/24/2019: Your order is on track: Provisioning Department accepted the order on Sep 24, 2019 and has begun processing. | 199970403 | UnitedHealth Group M&R | Private IP - PIP (30106966) Access WAN Analysis Reporting (30106968) | 30106966 30106968 | 1 GBPS (30106966) |  | 94533502 (Private IP (PIP)) 94533508 94533506 (WAN Analysis Reporting) | C0145288/NONE (30106966) |  | 5984470 | 550000 | PVC ID : 5984470 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65463 PE IP Address : 152.164.217.77 CE Address : 152.164.217.78 QoS - Egress Profile: C13 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Melissa Chapman Melissa Chapman 1-176-374-4211 melissa_r_chapman@optum.com | ERWIN EDORIA | erwin_edoria@optum.com | 1-763-744-2114 | 10/20/2019(Private IP |  |  | 09/30/2019 (30106966) | 10/03/2019 10/03/2019 (22155391.3) | 10/21/2019 |  | Completed Activated/Installed | N (30106966) N N (30106968) | U0101953 |  | NSPE0013179646 | NSPE0013179646
Completed | UNITED HEALTH GROUP | 12018 Sunrise Valley Dr Reston, VA 20191-3432 US | 50 MBPS (30136980) | 10/03/2019: 10/3Background: 50 MBPS 20 MBPS PIP-E Reston, VA VZT Status: Loop delivered pending completion notice Next action: Order closure Who owns the next action: VZT | 199942923 | UNITED HEALTH GROUP | Private IP - PIP (30136979) WAN Analysis Reporting (30136981) Access (30136980) | 30136979 30136981 30136980 | 20 MBPS (30136979) |  | 94678203 (Private IP (PIP)) 94678209 (WAN Analysis Reporting) 94678205 (Access) | C4019880/ADD (30136979) E4050548/ADD (30136980) | 36.KFGS.310985..CD (3013698033843001) | 6084786 | 13000 | PVC ID : 6084786 VPN Name : UnitedHealthGroup Router Name : WA39E02 VRF Name : Va87645:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65176 PE IP Address : 152.177.104.181 CE Address : 152.177.104.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30136980) | 1000Base-SX (850nm, Multi Mode Fiber) (30136980) | Ethernet | VERIZON (3013698033843001) | 09/27/2019 (3013698033843001) | 10/03/2019 (3013698033843001) | 10/03/2019 (3013698033843001) |  |  | DEMARCDET - 1ST FLR MTR WALL MOUNTED, UNIT # 4. TAGGED. |  | Alexander Ray 1-919-830-9567 alexander_ray@uhg.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 10/03/2019(Private IP - PIP) 10/03/2019(WAN Analysis Reporting) 10/03/2019(Access) |  |  | 10/14/2019 (30136979) 10/10/2019 (30136980) | 10/16/2019 10/22/2019 | 10/03/2019 |  | Completed | N (30136979) N (30136981) N (30136980) | U0101953 |  | NSPE0013174490 | NSPE0013174490
Completed | TX516 | 509 S Expressway 83 Harlingen, TX 78550-5903 US | 50 MBPS (30093754) | 01/31/2020: 1/31Background: 50MBPS 10 MBPS PIP-E Harlingen, TX TWC DUAL NID Status:Ready for activation Install to complete 1/24 Next action: Who owns the next action: Customer | 199933249 | TX516 | Private IP - PIP (30093753) WAN Analysis Reporting (30093755) Access (30093754) | 30093753 30093755 30093754 | 10 MBPS (30093753) |  | 94677582 (Private IP (PIP)) 94677588 (WAN Analysis Reporting) 94677584 (Access) | C4019796/ADD (30093753) E4050342/ADD (30093754) | 95.L1XX.801610..TWCC (3009375463716101) | 6083768 | 5500 | PVC ID : 6083768 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64660 PE IP Address : 152.176.234.169 CE Address : 152.176.234.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30093754) | 1000Base-SX (850nm, Multi Mode Fiber) (30093754) | Ethernet | TIME WARNER CABLE (3009375463716101) | 10/10/2019 (3009375463716101) | 01/23/2020 (3009375463716101) | 01/24/2020 (3009375463716101) | 01/28/2020 (VFORCE) (30093754) | 01/27/2020 (VFORCE) (30093754) | DEMARCDET - 1st Floor, IT closet, Spectrum wall mount rack |  | ROBERT ESPRAVA 1-915-525-3982 grodriguez1@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 01/27/2020(Private IP - PIP) 01/27/2020(WAN Analysis Reporting) 01/27/2020(Access) |  |  | 02/03/2020 (30093753) 01/30/2020 (30093754) | 01/22/2020 01/28/2020 | 01/27/2020 |  | Completed | N (30093753) N (30093755) N (30093754) | U0101953 | Jeopardy Notification 1 (12/09/2019) | NSPE0013170793 NSPE0013170793 | NSPE0013170793
Completed | Bulverdo | 524 SINGING OAKS BULVERDE, TX 78070-6509 US | 50 MBPS (30127647) | 10/31/2019: 10/31Status: Called and talked to LCON Rick to secure access, access secured. Rick advised to call him on his cell @210-376-9633 if any issues Orlando is the GC on site. | 199985687 | Bulverdo | Access (30127647) Private IP - PIP (30127646) WAN Analysis Reporting (30127648) | 30127647 30127646 30127648 | 10 MBPS (30127646) |  | 1198772587 (Access) 1198772591 (Private IP (PIP)) 1198773633 (WAN Analysis Reporting) | E4050493/ADD (30127647) C4019860/ADD (30127646) | TX/EVPL/000843/IDTL/VBZ (3012764762896101) | 6084492 | 5500 | PVC ID : 6084492 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64682 PE IP Address : 159.24.185.165 CE Address : 159.24.185.166 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (30127647) | 1000Base-SX (850nm, Multi Mode Fiber) (30127647) | Ethernet | INDATEL SERVICES, LLC (3012764762896101) | 09/25/2019 (3012764762896101) | 11/14/2019 (3012764762896101) | 10/29/2019 (3012764762896101) | 11/01/2019 (VFORCE) (30127647) | 11/01/2019 (VFORCE) (30127647) | DEMARCDET - Main Floor Comm Room |  | Rick Williamson 1-210-951-3129 rwilliamson@wellmed.net | Avinash Chib | avinash_chib@optum.com | 1-763-744-1400 | 11/01/2019(Access) 11/01/2019(Private IP - PIP) 11/01/2019(WAN Analysis Reporting) |  |  | 11/21/2019 (30127647) 11/25/2019 (30127646) | 11/05/2019 11/11/2019 | 11/01/2019 |  | Completed | N (30127647) N (30127646) N (30127648) | U0101953 |  | NSPE0013190374 | NSPE0013190374
Completed | FL406 | 1060 Maitland Center Commons Blvd Maitland, FL 32751-7255 US | 50 MBPS (30284064) | 12/11/2019: 12/11Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / Maitland, FL, US / CLEC or INDEPENDENT Status:Loop delivered 12/10- Pending Beas scheduled 12/13 Asr sent 10/18- Next Action: Pending Beas | 200144055 | FL406 | Private IP - PIP (30284063) WAN Analysis Reporting (30284065) Access (30284064) | 30284063 30284065 30284064 | 20 MBPS (30284063) |  | 94692811 (Private IP (PIP)) 94692809 (WAN Analysis Reporting) 94692807 (Access) | C4020140/ADD (30284063) E4051244/ADD (30284064) | E4051244 (3028406465543301) | 6088632 | 13000 | PVC ID : 6088632 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65420 PE IP Address : 68.137.163.109 CE Address : 68.137.163.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30284064) | 1000Base-SX (850nm, Multi Mode Fiber) (30284064) | Ethernet | CLEC or INDEPENDENT (3028406465543301) | 10/18/2019 (3028406465543301) | 12/02/2019 (3028406465543301) | 12/10/2019 (3028406465543301) | 12/13/2019 (VFORCE) (30284064) | 12/13/2019 (VFORCE) (30284064) | DEMARCDET - 3rd floor STE 350 mounted on the wall in server room |  | Patrick Barry 1-407-765-0534 pbarry@excelsiorbenefits.com | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 12/13/2019(Private IP - PIP) 12/13/2019(WAN Analysis Reporting) 12/13/2019(Access) |  |  | 12/11/2019 (30284063) 12/09/2019 (30284064) | 11/28/2019 12/04/2019 | 12/13/2019 |  | Completed | N (30284063) N (30284065) N (30284064) | U0101953 |  | NSPE0013247001 | NSPE0013247001
Completed | MN108 | 23505 Smithtown Rd Excelsior, MN 55331-4541 US | 500 MBPS (30289595) | 11/07/2019: 11/7Background: 500 Mbps / 100 Mbps / Access, Private IP (PIP) / Excelsior, MN, US / CENTURYLINK Status: Loop installed 11/6- Beas Instaled Next Action: ready for activation Who owns the next action: | 200144863 | MN108 | WAN Analysis Reporting (30289596) Access (30289595) Private IP - PIP (30289594) | 30289596 30289595 30289594 | 100 MBPS (30289594) |  | 94692468 (WAN Analysis Reporting) 94692470 (Access) 94692472 (Private IP (PIP)) | C5008485/ADD (30289594) E5021339/ADD (30289595) | 03.KXGS.464910..NW (3028959565567001) | 6088803 | 70000 | PVC ID : 6088803 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65421 PE IP Address : 68.138.109.65 CE Address : 68.138.109.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30289595) | 1000Base-SX (850nm, Multi Mode Fiber) (30289595) | Ethernet | CENTURYLINK (3028959565567001) | 10/29/2019 (3028959565567001) | 11/07/2019 (3028959565567001) | 11/06/2019 (3028959565567001) | 11/07/2019 (VFORCE) (30289595) |  | DEMARCDET - Main MPOE Mechanical room Rear of Building Cienna 3916 mini in Relay rack port 2 |  | Tom Nicol 1-952-474-2237 tnicol@excelsiorbenefits.com | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 11/07/2019(WAN Analysis Reporting) 11/07/2019(Access) 11/07/2019(Private IP - PIP) |  |  | 11/18/2019 (30289594) 11/14/2019 (30289595) | 12/04/2019 11/28/2019 | 11/07/2019 |  | Completed | N (30289596) N (30289595) N (30289594) | U0101953 |  | NSPE0013247326 | NSPE0013247326
Completed | OK021 | 4500 S Garnett Rd Tulsa, OK 74146-5229 US | 50 MBPS (30289634) | 11/08/2019: 11/7Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / Tulsa, OK, US / COX Status:Loop delivered 10/30- Beas installed 11/4 Next Action: Order closure Who owns the next action: LEC | 200145267 | OK021 | Private IP - PIP (30289633) WAN Analysis Reporting (30289635) Access (30289634) | 30289633 30289635 30289634 | 10 MBPS (30289633) |  | 94692499 (Private IP (PIP)) 94692495 (WAN Analysis Reporting) 94692497 (Access) | C4020165/ADD (30289633) E4051285/ADD (30289634) |  | 6088804 | 5500 | PVC ID : 6088804 VPN Name : UnitedHealthGroup Router Name : BRA3E01 VRF Name : Vd91658-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65423 PE IP Address : 152.177.131.33 CE Address : 152.177.131.34 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30289634) | 1000Base-SX (850nm, Multi Mode Fiber) (30289634) | Ethernet | COX (3028963465573301) | 10/21/2019 (3028963465573301) | 11/18/2019 (3028963465573301) | 10/30/2019 (3028963465573301) | 11/04/2019 (VFORCE) (30289634) |  | DEMARCDET - 4th floor common telco, Accedian Nid Port 3 |  | John Ritchie 1-918-770-7420 jritchie@excelsiorbenefits.com | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 11/04/2019(Private IP - PIP) 11/04/2019(WAN Analysis Reporting) 11/04/2019(Access) |  |  | 11/27/2019 (30289633) 11/25/2019 (30289634) | 11/28/2019 12/04/2019 | 11/04/2019 |  | Completed | N (30289633) N (30289635) N (30289634) | U0101953 | Jeopardy Notification 1 (10/31/2019) | NSPE0013247505 | NSPE0013247505
Completed | TX491 | 9151 Boulevard 26 North Richland Hills, TX 76180-5600 US | 1 GBPS (30297528) | 12/27/2019: Order Completed on Dec 27, 2019 | 200158057 | TX491 | Private IP - PIP (30297527) WAN Analysis Reporting (30297529) Access (30297528) | 30297527 30297529 30297528 | 500 MBPS (30297527) |  | 94694121 (Private IP (PIP)) 94694126 (WAN Analysis Reporting) 94694124 (Access) | C0178159/ADD (30297527) E5021408/ADD (30297528) | TX/KXFN/236955/LVLC (3029752865666901) | 6089298 | 350000 | PVC ID : 6089298 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65424 PE IP Address : 68.136.222.41 CE Address : 68.136.222.42 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30297528) | 1000Base-SX (850nm, Multi Mode Fiber) (30297528) | Ethernet | LEVEL 3 (3029752865666901) | 10/25/2019 (3029752865666901) | 11/07/2019 (3029752865666901) | 11/08/2019 (3029752865666901) | 12/27/2019 (VFORCE) (30297528) | 12/27/2019 (VFORCE) (30297528) | DEMARCDET - basement Telco room, TW Telecom rack, Cisco Switch NRHL480HZG001, port 1, MM/SFP/LC, tagged with circuit ID TX/KXFN/236955/LVLC |  | Mike Britain 1-817-255-6478 Mike.Britain@hmkts.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 12/27/2019(Private IP - PIP) 12/27/2019(WAN Analysis Reporting) 12/27/2019(Access) |  |  | 01/02/2020 (30297527) 12/31/2019 (30297528) | 01/31/2020 02/06/2020 | 12/27/2019 |  | Completed | N (30297527) N (30297529) N (30297528) | U0101953 | Jeopardy Notification 1 (11/26/2019) | NSPE0013251912 | NSPE0013251912
Completed | KY027 | 9420 Bunsen Pkwy Louisville, KY 40220-3700 US | 300 MBPS (30315805) | 01/23/2020: Order Completed on Jan 23, 2020 | 200177335 | KY027 | Private IP - PIP (30315803) WAN Analysis Reporting (30315806) Access (30315805) | 30315803 30315806 30315805 | 200 MBPS (30315803) |  | 94695488 (Private IP (PIP)) 94695494 (WAN Analysis Reporting) 94695492 (Access) | C5008506/ADD (30315803) E5021415/ADD (30315805) | KY/KXFN/235892/LVLC (3031580565860301) | 6089440 | 90000 | PVC ID : 6089440 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64561 PE IP Address : 147.225.184.77 CE Address : 147.225.184.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30315805) | 1000Base-SX (850nm, Multi Mode Fiber) (30315805) | Ethernet | LEVEL 3 (3031580565860301) | 11/07/2019 (3031580565860301) | 12/02/2019 (3031580565860301) | 11/25/2019 (3031580565860301) | 11/27/2019 (VFORCE) (30315805) |  | DEMARCDET - 2nd flr telco rm wall mounted LSVL21I64P001 Port 3 MMF labeled with circuit ID |  | Paul Habenstein 1-502-214-6148 Phabenstein@equian.com | Amit Shrivastava | amit_shrivastava21@optum.com | 91-804-670-4478 | 01/23/2020(Private IP - PIP) 01/23/2020(WAN Analysis Reporting) 01/23/2020(Access) |  |  | 01/30/2020 (30315803) 01/28/2020 (30315805) | 03/02/2020 03/06/2020 | 01/23/2020 |  | Completed | N (30315803) N (30315806) N (30315805) | U0101953 | Jeopardy Notification 4 (12/27/2019) | NSPE0013259304 | NSPE0013259304
Completed | OK023 | 2448 E 81st St Tulsa, OK 74137-4250 US | 100 MBPS (30306558) | 11/01/2019: Your order is on track: The order requires a Verizon Build initiated on 2019-10-30T00:00:00 and it is in progress. The Ready for Traffic Date (RFT) is 2019-11-25T00:00:00 | 200167199 | OK023 | Private IP - PIP (30306557) WAN Analysis Reporting (30306559) Access (30306558) | 30306557 30306559 30306558 | 50 MBPS (30306557) |  | 94695293 (Private IP (PIP)) 94695296 (WAN Analysis Reporting) 94695298 (Access) | C1097788/ADD (30306557) E4051356/ADD (30306558) |  | 6089154 | 30000 | PVC ID : 6089154 VPN Name : UnitedHealthGroup Router Name : BRA3E01 VRF Name : Vd91658-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65428 PE IP Address : 68.139.195.181 CE Address : 68.139.195.182 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (30306558) | Ethernet |  |  |  |  | 11/20/2019 (CCP) (30306557) 11/20/2019 (CCP) (30306558) | 11/09/2019 (CCP) (30306557) 11/09/2019 (CCP) (30306558) |  |  | Shari Baldwin 1-800-642-2409 Sbaldwin@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-706-669-2028 | 11/11/2019(Private IP - PIP) 11/11/2019(WAN Analysis Reporting) 11/11/2019(Access) |  |  | 12/06/2019 (30306557) 12/04/2019 (30306558) | 11/21/2019 11/27/2019 | 11/11/2019 |  | Completed | N (30306557) N (30306559) N (30306558) | U0101953 |  | NSPE0013255660 | NSPE0013255660
Completed | AZ150 | 9590 E Ironwood Square Dr Scottsdale, AZ 85258-4581 US | 100 MBPS (30001571) | 02/03/2020: 2/3Background: 100 MB 100MB PIP-E DUAL NID Scottsdale, AZ, COX Status: Loop delivered 2/3- Pending Beas Next action: BEAS install Who owns the next action: VZT tech | 199878661 | AZ150 | Private IP - PIP (30001570) Access (30001571) WAN Analysis Reporting (30001572) | 30001570 30001571 30001572 | 100 MBPS (30001570) |  | 94675068 (Private IP (PIP)) 94675070 (Access) 94675074 (WAN Analysis Reporting) | C1096191/ADD (30001570) E4050011/ADD (30001571) |  | 6081914 | 70000 | PVC ID : 6081914 VPN Name : UnitedHealthGroup Router Name : PHN1XE02 VRF Name : Vd82055-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65179 PE IP Address : 152.164.155.213 CE Address : 152.164.155.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30001571) | 1000Base-SX (850nm, Multi Mode Fiber) (30001571) | Ethernet | COX (3000157162710601) | 09/11/2019 (3000157162710601) | 02/13/2020 (3000157162710601) | 02/03/2020 (3000157162710601) | 02/04/2020 (VFORCE) (30001571) | 02/04/2020 (VFORCE) (30001571) | DEMARCDET - 1st flr suite 125 wall mounted middle wall in MDF |  | Bri Ulmer 1-480-397-9609 briu@4cmedicalgroup.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 02/04/2020(Private IP - PIP) 02/04/2020(Access) 02/04/2020(WAN Analysis Reporting) |  |  | 01/29/2020 (30001570) 01/27/2020 (30001571) | 01/15/2020 01/21/2020 | 02/04/2020 |  | Completed | N (30001570) N (30001571) N (30001572) | U0101953 | Jeopardy Notification 1 (10/03/2019) | NSPE0013151576 | NSPE0013151576
Completed | MI074 | 26555 Evergreen Rd Southfield, MI 48076-4206 US | 300 MBPS (30346278) | 12/17/2019: Order Completed on Dec 16, 2019 | 200195649 | MI074 | WAN Analysis Reporting (30346279) Access (30346278) Private IP - PIP (30346277) | 30346279 30346278 30346277 | 200 MBPS (30346277) |  | 94695994 (WAN Analysis Reporting) 94695998 (Access) 94695996 (Private IP (PIP)) | C5008535/ADD (30346277) E5021499/ADD (30346278) | CL/L1YX/327382/ /TQW /ELK (3034627866032001) | 6090169 | 110000 | PVC ID : 6090169 VPN Name : UnitedHealthGroup Router Name : NORXE05 VRF Name : V575848-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65429 PE IP Address : 159.24.185.141 CE Address : 159.24.185.142 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30346278) | 1000Base-SX (850nm, Multi Mode Fiber) (30346278) | Ethernet | XO (3034627866032001) | 10/30/2019 (3034627866032001) | 12/27/2019 (3034627866032001) | 12/11/2019 (3034627866032001) | 12/13/2019 (VFORCE) (30346278) |  | DEMARCDET - Local basement , Main Phone Room , Wall Mounted |  | Norm Cross 1-248-750-5626 Ncross@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 12/16/2019(WAN Analysis Reporting) 12/16/2019(Access) 12/16/2019(Private IP - PIP) |  |  | 01/07/2020 (30346277) 01/03/2020 (30346278) | 12/27/2019 12/23/2019 | 12/16/2019 |  | Completed | N (30346279) N (30346278) N (30346277) | U0101953 | Jeopardy Notification 1 (11/12/2019) | NSPE0013265222 | NSPE0013265222
Completed | AL042 | 7480 Halcyon Pointe Dr Montgomery, AL 36117-8102 US | 300 MBPS (30346247) | 12/05/2019: 12/5Background: 300 Mbps / 200 Mbps / Access, Private IP (PIP) / Montgomery, AL, US / WIDE OPEN WEST Status: Loop delivered; Beas install 12/6 Next Action: BEAS Installation Who owns the next action: Dispatch Team | 200197777 | AL042 | WAN Analysis Reporting (30346248) Private IP - PIP (30346246) Access (30346247) | 30346248 30346246 30346247 | 200 MBPS (30346246) |  | 94696572 (WAN Analysis Reporting) 94696566 (Private IP (PIP)) 94696570 (Access) | E5021498/ADD (30346247) C5008534/ADD (30346246) | MOAL/CETHS/EPBYE9A7/WOW (3034624766043801) | 6090168 | 110000 | PVC ID : 6090168 VPN Name : UnitedHealthGroup Router Name : CPZXE04 VRF Name : Vd99231-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64561 PE IP Address : 68.137.146.245 CE Address : 68.137.146.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30346247) | 1000Base-SX (850nm, Multi Mode Fiber) (30346247) | Ethernet | WIDE OPEN WEST (3034624766043801) | 10/28/2019 (3034624766043801) | 12/05/2019 (3034624766043801) | 11/26/2019 (3034624766043801) | 12/06/2019 (VFORCE) (30346247) | 12/06/2019 (VFORCE) (30346247) | DEMARCDET - 1st floor telco closet look to the left fiber sfp handoff ALU 7210 PORT 4 |  | Babette Batten 1-334-777-1368 Bbatten@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 12/06/2019(WAN Analysis Reporting) 12/06/2019(Private IP - PIP) 12/06/2019(Access) |  |  | 12/12/2019 (30346247) 12/16/2019 (30346246) | 12/12/2019 12/06/2019 | 12/06/2019 |  | Completed | N (30346248) N (30346246) N (30346247) | U0101953 | Jeopardy Notification 1 (11/26/2019) | NSPE0013266030 | NSPE0013266030
Completed | CO144 | 600 12th St Golden, CO 80401-1179 US | 300 MBPS (30324792) | 11/06/2019: 11/6Background: 300 Mbps / 200 Mbps / Access, Private IP (PIP) / Golden, CO, US / CENTURYLINK Status: loop delivered 11/6- Beas install 11/6 ASR sent 10/28 Next Action: Beas Install Who owns the next action: VZB | 200184065 | CO144 | Private IP - PIP (30324791) WAN Analysis Reporting (30324793) Access (30324792) | 30324791 30324793 30324792 | 200 MBPS (30324791) |  | 94696134 (Private IP (PIP)) 94696140 (WAN Analysis Reporting) 94696138 (Access) | C5008519/ADD (30324791) E5021451/ADD (30324792) | 29.KXGS.465716..MS (3032479265935701) | 6089661 | 110000 | PVC ID : 6089661 VPN Name : UnitedHealthGroup Router Name : DNVR9E01 VRF Name : V483292:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65426 PE IP Address : 152.177.78.113 CE Address : 152.177.78.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30324792) | 1000Base-SX (850nm, Multi Mode Fiber) (30324792) | Ethernet | CENTURYLINK (3032479265935701) | 10/28/2019 (3032479265935701) | 11/06/2019 (3032479265935701) | 11/06/2019 (3032479265935701) | 11/06/2019 (VFORCE) (30324792) |  | DEMARCDET - MPOP 1ST FLOOR, WALL-MOUNT CIENA 3916 (GLDNCOKS02W), PORT 2 (MULTI-MODE HANDOFF). Type: OPTICAL Port: 2 |  | Nick Dahlin 1-720-279-1191 Ndahlin@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 11/06/2019(Private IP - PIP) 11/06/2019(WAN Analysis Reporting) 11/06/2019(Access) |  |  | 11/15/2019 (30324791) 11/13/2019 (30324792) | 12/04/2019 12/10/2019 | 11/06/2019 |  | Completed | N (30324791) N (30324793) N (30324792) | U0101953 |  | NSPE0013261723 | NSPE0013261723
Completed | KY025 | 9390 Bunsen Pkwy Louisville, KY 40220-3789 US | 1 GBPS (30372561) | 11/20/2019: 11/20Background: 1 Gbps / 500 Mbps / Access, Private IP (PIP) / Louisville, KY, US / LEVEL 3 Status: Foc 12/10 Asr sent 10/30 Next Action: Pending loop install Who owns the next action: LEC | 200230591 | KY025 | WAN Analysis Reporting (30372562) Access (30372561) Private IP - PIP (30372560) | 30372562 30372561 30372560 | 500 MBPS (30372560) |  | 94700153 (WAN Analysis Reporting) 94700155 (Access) 94700157 (Private IP (PIP)) | C0178536/ADD (30372560) E5021553/ADD (30372561) | KY/KXFN/239489/LVLC (3037256166327001) | 6090624 | 350000 | PVC ID : 6090624 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65418 PE IP Address : 68.136.118.117 CE Address : 68.136.118.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30372561) | 1000Base-SX (850nm, Multi Mode Fiber) (30372561) | Ethernet | LEVEL 3 (3037256166327001) | 10/30/2019 (3037256166327001) | 12/10/2019 (3037256166327001) | 11/26/2019 (3037256166327001) | 11/27/2019 (VFORCE) (30372561) | 11/27/2019 (VFORCE) (30372561) | DEMARCDET - 1st FLR DATA CENTER RACK MTD ROW C RACK 5 RMU 23 PORT G 0 BY 9 |  | Paul Habenstein 1-502-214-6148 Phabenstein@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 11/27/2019(WAN Analysis Reporting) 11/27/2019(Access) 11/27/2019(Private IP - PIP) |  |  | 12/19/2019 (30372560) 12/17/2019 (30372561) | 12/16/2019 12/10/2019 | 11/27/2019 |  | Completed | N (30372562) N (30372561) N (30372560) | U0101953 |  | NSPE0013277798 | NSPE0013277798
Completed | TX536 | 1108 Dallas Dr Denton, TX 76205-5123 US | 50 MBPS (30379440) | 03/19/2020: Order Completed on Mar 19, 2020 | 200237325 | TX536 | WAN Analysis Reporting (30379441) Private IP - PIP (30379439) Access (30379440) | 30379441 30379439 30379440 | 10 MBPS (30379439) |  | 94697450 (WAN Analysis Reporting) 94697444 (Private IP (PIP)) 94697446 (Access) | E4051600/ADD (30379440) C4020264/ADD (30379439) | 94.L1XX.026051..TWCC (3037944066146601) | 6090784 | 5500 | PVC ID : 6090784 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65110 PE IP Address : 68.139.200.77 CE Address : 68.139.200.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30379440) | 1000Base-SX (850nm, Multi Mode Fiber) (30379440) | Ethernet | CHARTER (3037944066146601) | 02/04/2020 (3037944066146601) | 04/10/2020 (3037944066146601) | 03/16/2020 (3037944066146601) | 03/19/2020 (VFORCE) (30379440) | 03/19/2020 (VFORCE) (30379440) | DEMARCDET - MAIN BLDG, 1ST FLOOR, TELECOM ROOM. |  | Khanh Nguyen 1-817-368-6081 knguyen11@wellmed.net | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 03/19/2020(WAN Analysis Reporting) 03/19/2020(Private IP - PIP) 03/19/2020(Access) |  |  | 04/17/2020 (30379440) 04/21/2020 (30379439) | 06/26/2020 06/22/2020 | 03/19/2020 |  | Completed | N (30379441) N (30379439) N (30379440) | U0101953 | Jeopardy Notification 4 (12/27/2019) | NSPE0013280196 | NSPE0013280196
Completed | TX534 | 2200 W Spring Creek Pkwy Plano, TX 75023-4184 US | 50 MBPS (30410396) | 01/02/2020: Order Completed on Jan 2, 2020 | 200267105 | TX534 | Access (30410396) WAN Analysis Reporting (30410397) Private IP - PIP (30410395) | 30410396 30410397 30410395 | 10 MBPS (30410395) |  | 94706112 (Access) 94706110 (WAN Analysis Reporting) 94706114 (Private IP (PIP)) | E4051734/ADD (30410396) C4020309/ADD (30410395) | 13/KRGN/251386//FTNC/ (3041039666597501) | 6091480 | 5500 | PVC ID : 6091480 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65414 PE IP Address : 68.136.234.25 CE Address : 68.136.234.26 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30410396) | 1000Base-SX (850nm, Multi Mode Fiber) (30410396) | Ethernet | FRONTIER (3041039666597501) | 11/05/2019 (3041039666597501) | 12/27/2019 (3041039666597501) | 01/02/2020 (3041039666597501) | 01/03/2020 (VFORCE) (30410396) | 01/02/2020 (VFORCE) (30410396) |  |  | MARCO WONG 1-214-493-4068 mwong@wellmed.net | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 01/02/2020(Access) 01/02/2020(WAN Analysis Reporting) 01/02/2020(Private IP - PIP) |  |  | 01/03/2020 (30410396) 01/07/2020 (30410395) | 12/16/2019 12/20/2019 | 01/02/2020 |  | Completed | N (30410396) N (30410397) N (30410395) | U0101953 |  |  | NSPE0013291255
Completed | DC007 | 655 New York Ave Nw Washington, DC 20001-4593 US | 500 MBPS (30610123) | 01/09/2020: Order Completed on Jan 9, 2020 | 200270243 | DC007 | Private IP - PIP (30610122) Access (30610123) WAN Analysis Reporting (30610126) | 30610122 30610123 30610126 | 400 MBPS (30610122) |  | 94706028 (Private IP (PIP)) 94706030 (Access) 94706026 (WAN Analysis Reporting) | C5008757/ADD (30610122) E5022215/ADD (30610123) | 36.KFGS.311291..CD (3061012354359301) | 6095766 | 250000 | PVC ID : 6095766 VPN Name : UnitedHealthGroup Router Name : WA3XE01 VRF Name : Ve09021-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64813 PE IP Address : 152.177.227.53 CE Address : 152.177.227.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30610123) | 1000Base-SX (850nm, Multi Mode Fiber) (30610123) | Ethernet | VERIZON (3061012354359301) | 12/05/2019 (3061012354359301) | 01/14/2020 (3061012354359301) | 01/09/2020 (3061012354359301) |  |  | DEMARCDET - P1 LEVEL MTR VZ RR 1 SHELF 14 |  | KATIE MALONEY 1-617-852-7976 katharine_maloney@uhg.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-879-0648 | 01/09/2020(Private IP - PIP) 01/09/2020(Access) 01/09/2020(WAN Analysis Reporting) |  |  | 01/23/2020 (30610122) 01/21/2020 (30610123) | 12/31/2019 01/06/2020 | 01/09/2020 |  | Completed | N (30610122) N (30610123) N (30610126) | U0101953 |  |  | NSPE0013292156
Completed | AR035 | 27 Corporate Hill Dr Little Rock, AR 72205-4537 US | 250 MBPS (30414507) | 11/14/2019: 11/14Background: 250 Mbps / 100 Mbps / Access, Private IP (PIP) / Little Rock, AR, US / ATT Status: Loop delivered;Beas install 11/15 Next Action: Pending BEAS Install - Who owns the next action: Dispatch Team | 200271391 | AR035 | Access (30414507) Private IP - PIP (30414506) WAN Analysis Reporting (30414508) | 30414507 30414506 30414508 | 100 MBPS (30414506) |  | 94706244 (Access) 94706246 (Private IP (PIP)) 94706248 (WAN Analysis Reporting) | E0020070/ADD (30414507) C0178774/ADD (30414506) | 63/KRGN/602437//SW (3041450764968101) | 6091552 | 70000 | PVC ID : 6091552 VPN Name : UnitedHealthGroup Router Name : MEJ9E01 VRF Name : Vd95206:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65015 PE IP Address : 199.220.91.73 CE Address : 199.220.91.74 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30414507) | 1000Base-SX (850nm, Multi Mode Fiber) (30414507) | Ethernet | ATT (3041450764968101) | 11/05/2019 (3041450764968101) | 11/11/2019 (3041450764968101) | 11/11/2019 (3041450764968101) | 11/15/2019 (VFORCE) (30414507) | 11/15/2019 (VFORCE) (30414507) | DEMARCDET - 1st floor server room port 6 of cienna3930 tagged with CKT ID Not extended |  | Howard Backus 1-501-218-7888 Howard.Backus@Healthscopebenefits.com | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 11/15/2019(Access) 11/15/2019(Private IP - PIP) 11/15/2019(WAN Analysis Reporting) |  |  | 11/18/2019 (30414507) 11/20/2019 (30414506) | 12/16/2019 12/20/2019 | 11/15/2019 |  | Completed | N (30414507) N (30414506) N (30414508) | U0101953 |  |  | NSPE0013292653
Completed | CO147 | 169 Inverness Dr W Englewood, CO 80112-5003 US | 200 MBPS (30306492) | 04/15/2020: Order Completed on Apr 15, 2020 | 200165915 | CO147 | Private IP - PIP (30306491) WAN Analysis Reporting (30306493) Access (30306492) | 30306491 30306493 30306492 | 100 MBPS (30306491) |  | 94695128 (Private IP (PIP)) 94695133 (WAN Analysis Reporting) 94695131 (Access) | C5008501/ADD (30306491) E5021389/ADD (30306492) | 60.KGGS.014083..CBCL.. (3030649265741801) | 6089226 | 70000 | PVC ID : 6089226 VPN Name : UnitedHealthGroup Router Name : DNJXE01 VRF Name : V469377-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65419 PE IP Address : 199.220.118.73 CE Address : 199.220.118.74 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30306492) | 1000Base-SX (850nm, Multi Mode Fiber) (30306492) | Ethernet | COMCAST (3030649265741801) | 03/06/2020 (3030649265741801) | 04/01/2020 (3030649265741801) | 04/14/2020 (3030649265741801) | 04/15/2020 (VFORCE) (30306492) | 04/15/2020 (VFORCE) (30306492) | DEMARCADDR - . DEMARCDET - 4th FL Data Room Rack Mounted in back of the room Rack Unit RU 32 Tagged and Labeled |  | Paul Bierbower 1-415-310-3208 Paul_bierbower@uhg.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 04/15/2020(Private IP - PIP) 04/15/2020(WAN Analysis Reporting) 04/15/2020(Access) |  |  | 04/10/2020 (30306491) 04/08/2020 (30306492) | 04/16/2020 04/22/2020 | 04/15/2020 |  | Completed | N (30306491) N (30306493) N (30306492) | U0101953 | Jeopardy Notification 4 (02/22/2020) | NSPE0013255105 | NSPE0013255105
Completed | FL401 | 4901 Nw 17th Way Ft Lauderdale, FL 33309-3780 US | 50 MBPS (30302360) | 01/16/2020: 1/16Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / Ft Lauderdale, FL, US / XO Status:Beas Installed- Order completed Next Action:Ready for activation Who owns the next action: customer | 200163751 | FL401 | Private IP - PIP (30302359) WAN Analysis Reporting (30302361) Access (30302360) | 30302359 30302361 30302360 | 20 MBPS (30302359) |  | 94694774 (Private IP (PIP)) 94694772 (WAN Analysis Reporting) 94694776 (Access) | C4020176/ADD (30302359) E4051348/ADD (30302360) | MI/L2XX/327264/ /TQW /ELK (3030236065720001) | 6089232 | 13000 | PVC ID : 6089232 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65422 PE IP Address : 152.161.197.21 CE Address : 152.161.197.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30302360) | 1000Base-SX (850nm, Multi Mode Fiber) (30302360) | Ethernet | XO (3030236065720001) | 12/24/2019 (3030236065720001) | 01/30/2020 (3030236065720001) | 01/16/2020 (3030236065720001) | 01/16/2020 (VFORCE) (30302360) | 01/16/2020 (VFORCE) (30302360) | DEMARCDET - Customer suite 301 Phone areas / wall mounted label with PSR number port no. 2 of the MRV |  | George Tarke 1-954-375-8111 gtarke@excelsiorbenefits.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 01/16/2020(Private IP - PIP) 01/16/2020(WAN Analysis Reporting) 01/16/2020(Access) |  |  | 02/10/2020 (30302359) 02/06/2020 (30302360) | 01/01/2020 01/07/2020 | 01/16/2020 |  | Completed | N (30302359) N (30302361) N (30302360) | U0101953 | Jeopardy Notification 1 (11/19/2019) | NSPE0013254066 | NSPE0013254066
Provisioning Accepted |  | 7383 COUNTY RD COLOGNE, MN 55322 USA | 4000 MBPS (IQBLVC51) | 12/21/2020: Your order is on track: Provisioning Department accepted the order on Oct 3, 2019 and has begun processing. | 10029872 |  | Private IP Port Only (IQBLVC51) | IQBLVC51 | 4000 MBPS | P2308618 |  | BOBLJHT40001 (IQBLVC51) |  | 6086263 6086261 | 2500000 | PVC ID : 6086263,6086261 VPN Name : UnitedHealthGroup Router Name : MPLS9E01 VRF Name : Vd96554:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65398 PE IP Address : 68.136.41.205 CE Address : 68.136.41.206 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443141 TIM_GUNDERSON@OPTUM.COM |  |  |  | 11/13/2019 (IQBLVC51) |  |  | 11/13/2019 (IQBLVC51) | 10/29/2019 (IQBLVC51) |  |  |  | N (IQBLVC51) | 05017789 |  | NSPE0013181481 | NSPE0013181481
Completed |  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 5000 MBPS (IQBLVCWJ) | 10/10/2019: Background: NEW PIPO 10g related access 6308832 W1D73252 Status: Pending end to end testing Next action: order completion Who owns the next action: BNE | 10029868 |  | Private IP Port Only (IQBLVCWJ) | IQBLVCWJ | 4000 MBPS | P2308555 |  | BOBLJHRP0001 (IQBLVCWJ) |  | 6086112 6086111 6086391 | 2250000 | PVC ID : 6086112,6086111,6086391 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65400 PE IP Address : 152.164.113.173 CE Address : 152.164.113.174 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443141 TIM_GUNDERSON@OPTUM.COM |  |  |  | 10/16/2019 (IQBLVCWJ) |  |  | 10/29/2019 (IQBLVCWJ) | 10/29/2019 (IQBLVCWJ) |  |  |  | N (IQBLVCWJ) | 05017789 |  | NSPE0013181472 | NSPE0013181472
Pending Completion |  | 7383 COUNTY RD COLOGNE, MN 55322 USA | 5000 MBPS (IQBLVC52) | 10/24/2019: 10/23Background: NEW PIPO 10GB related access 6308909 W1D73338 Status:Order complete Next action: Who owns the next action: | 10029871 |  | Private IP Port Only (IQBLVC52) | IQBLVC52 | 4000 MBPS | P2308619 |  | BOBLJHT50001 (IQBLVC52) |  | 6086262 | 2500000 | PVC ID : 6086262 VPN Name : UnitedHealthGroup Router Name : MZZ9E01 VRF Name : V600583:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65400 PE IP Address : 208.219.130.213 CE Address : 208.219.130.214 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443141 TIM_GUNDERSON@OPTUM.COM |  |  |  | 10/23/2019 (IQBLVC52) |  |  | 10/29/2019 (IQBLVC52) | 10/29/2019 (IQBLVC52) |  |  |  | N (IQBLVC52) | 05017789 |  | NSPE0013181517 | NSPE0013181517
Completed | TN071 | 2875 Elm Hill Pike Nashville, TN 37214-3717 US | 50 MBPS (30446385) | 01/31/2020: 1/31Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / Nashville, TN, US / COMCAST Status: Ready for activation Loop delivered 1/27; beas 1/29 Next Action: Order closed Who owns the next action: customer | 200299285 | TN071 | Private IP - PIP (30446384) WAN Analysis Reporting (30446386) Access (30446385) | 30446384 30446386 30446385 | 20 MBPS (30446384) |  | 94708279 (Private IP (PIP)) 94708284 (WAN Analysis Reporting) 94708282 (Access) | C4020358/ADD (30446384) E4051938/ADD (30446385) | 31.KGGS.009810..CBCL.. (3044638564974401) | 6092133 | 13000 | PVC ID : 6092133 VPN Name : UnitedHealthGroup Router Name : NSVL3E03 VRF Name : V414602-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65441 PE IP Address : 152.176.230.233 CE Address : 152.176.230.234 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30446385) | 1000Base-SX (850nm, Multi Mode Fiber) (30446385) | Ethernet | COMCAST (3044638564974401) | 11/12/2019 (3044638564974401) | 02/12/2020 (3044638564974401) | 01/27/2020 (3044638564974401) | 01/29/2020 (VFORCE) (30446385) | 01/29/2020 (VFORCE) (30446385) | DEMARCADDR - 1 DEMARCDET - 1st Floor Rack Mounted number 2 RU16 labeled comcast / CLLI and circuit ID. 3916 Port 3 |  | Ed Grooms 1-615-695-8540 Ed.Grooms@healthscopebenefits.com | Sushil Kumar | sushil_gautam@uhc.com | 91-763-744-2114 | 01/29/2020(Private IP - PIP) 01/29/2020(WAN Analysis Reporting) 01/29/2020(Access) |  |  | 02/21/2020 (30446384) 02/19/2020 (30446385) | 12/19/2019 12/25/2019 | 01/29/2020 |  | Completed | N (30446384) N (30446386) N (30446385) | U0101953 |  | NSPE0013302212 | NSPE0013302212
Completed | TN507 | 221 N Kansas St El Paso, TX 79901-1443 US | 50 MBPS (30446903) | 01/09/2020: Order Completed on Jan 9, 2020 | 200300537 | TX507 | Private IP - PIP (30446902) WAN Analysis Reporting (30446904) Access (30446903) | 30446902 30446904 30446903 | 20 MBPS (30446902) |  | 94709611 (Private IP (PIP)) 94709607 (WAN Analysis Reporting) 94709609 (Access) | C4020359/ADD (30446902) E4051939/ADD (30446903) | TX/KXFN/243438/LVLC (3044690364974501) | 6092143 | 13000 | PVC ID : 6092143 VPN Name : UnitedHealthGroup Router Name : PHN1XE02 VRF Name : Vd82055-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65434 PE IP Address : 68.139.136.97 CE Address : 68.139.136.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30446903) | 1000Base-SX (850nm, Multi Mode Fiber) (30446903) | Ethernet | LEVEL 3 (3044690364974501) | 01/02/2020 (3044690364974501) | 01/23/2020 (3044690364974501) | 01/06/2020 (3044690364974501) | 01/09/2020 (VFORCE) (30446903) |  | DEMARCDET - 4th floor server room, wall mount LC fiber connection, tagged with circuit id |  | Vince Diaz 1-915-231-4250 Vince.Diaz@healthscopebeneifits.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-990-179-8210 | 01/09/2020(Private IP - PIP) 01/09/2020(WAN Analysis Reporting) 01/09/2020(Access) |  |  | 02/03/2020 (30446902) 01/30/2020 (30446903) | 02/12/2020 02/18/2020 | 01/09/2020 |  | Completed | N (30446902) N (30446904) N (30446903) | U0101953 | Jeopardy Notification 3 (12/31/2019) | NSPE0013302648 | NSPE0013302648
Completed | TX538 | 912 Wright St ste A Arlington, TX 76012-4759 US | 50 MBPS (30454512) | 02/28/2020: Order Completed on Feb 28, 2020 | 200308881 | TX538 | Private IP - PIP (30454511) WAN Analysis Reporting (30454513) Access (30454512) | 30454511 30454513 30454512 | 10 MBPS (30454511) |  | 94709997 (Private IP (PIP)) 94710403 (WAN Analysis Reporting) 94709999 (Access) | C4020372/ADD (30454511) E4051985/ADD (30454512) | 68.L1XX.000247..CHTR (3045451266956901) | 6092345 | 5500 | PVC ID : 6092345 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65413 PE IP Address : 199.220.43.145 CE Address : 199.220.43.146 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30454512) | 1000Base-SX (850nm, Multi Mode Fiber) (30454512) | Ethernet | TIME WARNER CABLE (3045451266956901) | 11/11/2019 (3045451266956901) | 03/23/2020 (3045451266956901) | 02/27/2020 (3045451266956901) | 02/28/2020 (VFORCE) (30454512) |  | DEMARCDET - telco rm vertical rack mounted tagged |  | Sherry Green 1-612-642-7302 sgreen11@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 02/28/2020(Private IP - PIP) 02/28/2020(WAN Analysis Reporting) 02/28/2020(Access) |  |  | 04/01/2020 (30454511) 03/30/2020 (30454512) | 03/27/2020 04/02/2020 | 02/28/2020 |  | Managed Completed | N (30454511) N (30454513) N (30454512) | U0101953 |  |  | NSPE0013305257
Completed | MO042 | 2350 S 7th St Saint Louis, MO 63104-4206 US | 50 MBPS (30436580) | 03/12/2020: Circuit and beas install complete. Pending end to end testing. | 200291199 | MO042 | Access (30436580) Private IP - PIP (30436579) WAN Analysis Reporting (30436581) | 30436580 30436579 30436581 | 10 MBPS (30436579) |  | 94707621 (Access) 94707623 (Private IP (PIP)) 94707625 (WAN Analysis Reporting) | E4051887/ADD (30436580) C4020341/ADD (30436579) | 31.L1XX.988910..CHTR (3043658064969401) | 6091966 | 5500 | PVC ID : 6091966 VPN Name : UnitedHealthGroup Router Name : STLS3E01 VRF Name : V432785-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65449 PE IP Address : 65.249.110.193 CE Address : 65.249.110.194 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30436580) | 1000Base-SX (850nm, Multi Mode Fiber) (30436580) | Ethernet | CHARTER (3043658064969401) | 11/07/2019 (3043658064969401) | 04/06/2020 (3043658064969401) | 03/10/2020 (3043658064969401) | 03/12/2020 (VFORCE) (30436580) | 03/12/2020 (VFORCE) (30436580) | DEMARCDET - 1st FL, back storage room, wall mounted, RAD 203, port 5 |  | Carol Birk 1-314-768-7303 Carol.Birk@healthscopebenefits.com | SUSHIL KUMAR | sushil_gautam@uhc.com | 91-896-855-7475 | 03/12/2020(Access) 03/12/2020(Private IP - PIP) 03/12/2020(WAN Analysis Reporting) |  |  | 04/13/2020 (30436580) 04/15/2020 (30436579) | 03/25/2020 03/31/2020 | 03/12/2020 |  | Completed | N (30436580) N (30436579) N (30436581) | U0101953 | Jeopardy Notification 1 (11/13/2019) | NSPE0013299531 | NSPE0013299531
Completed | FL040 | 701 NW 57TH AVE STE 150 MIAMI, FL 33126-2072 US | 50 MBPS (30487261) | 11/20/2019: 11/20Background: NA Status: FOC11/22-Loop delivered 11/20 Asr sent 11/18 Foc received 11/19 Next Action: Pending beas install Who owns the next action: OCC Team | 200343015 | FL040-05-IJ Miami, FL | Private IP - PIP (30487260) WAN Analysis Reporting (30487262) Access (30487261) | 30487260 30487262 30487261 | 20 MBPS (30487260) |  | 1216255821 (Private IP (PIP)) 1216255823 (WAN Analysis Reporting) 1216255817 (Access) | C4020418/ADD (30487260) E4052143/ADD (30487261) | 60/KRGN/764222//SB (3048726110550701) | 6093040 | 13000 | PVC ID : 6093040 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64812 PE IP Address : 68.139.73.5 CE Address : 68.139.73.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30487261) | 1000Base-SX (850nm, Multi Mode Fiber) (30487261) | Ethernet | ATT (3048726110550701) | 11/18/2019 (3048726110550701) | 11/22/2019 (3048726110550701) | 11/20/2019 (3048726110550701) | 11/22/2019 (VFORCE) (30487261) |  | DEMARCADDR - . DEMARCDET - MAIN BLDG MAIN FLOOR SUIT MDF |  | Elsa Cuello 1-305-260-2680 ecuello@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 11/22/2019(Private IP - PIP) 11/22/2019(WAN Analysis Reporting) 11/22/2019(Access) |  |  | 12/05/2019 (30487260) 12/03/2019 (30487261) | 12/26/2019 01/01/2020 | 11/22/2019 |  | Completed | N (30487260) N (30487262) N (30487261) | U0101953 |  | NSPE0013314576 | NSPE0013314576
Completed | disco for AUS | UHG LEVEL 25, 303 COLLINS STREET MELBOURNEVIC 3000 AUS | MLPPPE1B-10.240MB (6332136) E-1-BEARER (6332137) | 01/16/2020: 1/16Background: DIsconnect Status: pending disco date from PTT Another follow up email sent Next action: order closure | 10043508 |  | Private IP (6332136) Private IP (6332137) | 6332136 6332137 | 10.24 MBPS |  |  | W0X83226 (6332136) W0X83221 (6332137) W0X83222 (6332137) W0X83223 (6332137) W0X83224 (6332137) W0X83225 (6332137) |  | 2017032 | 6144 | PVC ID : 2017032 VPN Name : UnitedHealthGroup Router Name : MLBRGE01 VRF Name : V264942:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65264 PE IP Address : 152.183.100.145 CE Address : 152.183.100.146 QoS - Egress Profile: R12 |  |  |  | WILLIAMS TELECOMMUNICATIONS | [6 empty] | TECH ON DUTY +9999999999 | TERRY LU +61-(39)658-0019 | [6 empty] | 01/16/2020 (6332136) 01/16/2020 (6332137) | 12/12/2019 (6332136) 12/12/2019 (6332137) |  |  |  | N (6332136) N (6332137) | 00179802 |  |  | NSPE0013239632
Completed | AL013 | 4525 Executive Park Dr Montgomery, AL 36116-1624 US | 400 MBPS (30500800) | 12/20/2019: Order Completed on Dec 20, 2019 | 200358493 | AL013-02-IJ Catamaran Montgomery | Private IP - PIP (30500799) WAN Analysis Reporting (30500801) Access (30500800) | 30500799 30500801 30500800 | 200 MBPS (30500799) |  | 94715025 (Private IP (PIP)) 94715030 (WAN Analysis Reporting) 94715027 (Access) | C5008671/ADD (30500799) E5021923/ADD (30500800) | A1/KRGN/401773//SC (3050080012830501) | 6093378 | 140000 | PVC ID : 6093378 VPN Name : UnitedHealthGroup Router Name : CPZXE04 VRF Name : Vd99231-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64806 PE IP Address : 199.220.65.97 CE Address : 199.220.65.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30500800) | 1000Base-SX (850nm, Multi Mode Fiber) (30500800) | Ethernet | ATT (3050080012830501) | 12/03/2019 (3050080012830501) | 12/13/2019 (3050080012830501) | 12/17/2019 (3050080012830501) | 12/20/2019 (VFORCE) (30500800) | 12/20/2019 (VFORCE) (30500800) | DEMARCDET - 1ST FLR SERVER RM RELAY RACK MOUNT JACK 1 LABBELED WITH CRKT ID |  | Chris Wright 1-334-523-3447 chrisdwright@optum.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 | 12/20/2019(Private IP - PIP) 12/20/2019(WAN Analysis Reporting) 12/20/2019(Access) |  |  | 12/27/2019 (30500799) 12/24/2019 (30500800) | 01/27/2020 01/31/2020 | 12/20/2019 |  | Completed | N (30500799) N (30500801) N (30500800) | U0101953 | Jeopardy Notification 1 (12/11/2019) | NSPE0013322145 | NSPE0013322145
Completed | TX541 | 7201 Bishop Rd ste E-200 Plano, TX 75024-3641 US | 100 MBPS (30503333) | 12/31/2019: Order Completed on Dec 30, 2019 | 200360949 | TX541 | Private IP - PIP (30503332) WAN Analysis Reporting (30503334) Access (30503333) | 30503332 30503334 30503333 | 50 MBPS (30503332) |  | 94715304 (Private IP (PIP)) 94715309 (WAN Analysis Reporting) 94715302 (Access) | C1098677/ADD (30503332) E4052215/ADD (30503333) | 13/KRGN/261618//FTNC/ (3050333367559901) | 6093417 | 30000 | PVC ID : 6093417 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65171 PE IP Address : 68.138.145.249 CE Address : 68.138.145.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30503333) | 1000Base-SX (850nm, Multi Mode Fiber) (30503333) | Ethernet | FRONTIER (3050333367559901) | 11/19/2019 (3050333367559901) | 12/27/2019 (3050333367559901) | 12/27/2019 (3050333367559901) | 12/30/2019 (VFORCE) (30503333) | 12/30/2019 (VFORCE) (30503333) |  |  | Alan Stryker 1-903-701-3388 a.stryker@vivifyhealth.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 12/30/2019(Private IP - PIP) 12/30/2019(WAN Analysis Reporting) 12/30/2019(Access) |  |  | 01/07/2020 (30503332) 01/03/2020 (30503333) | 12/27/2019 01/02/2020 | 12/30/2019 |  | Completed | N (30503332) N (30503334) N (30503333) | U0101953 | Jeopardy Notification 1 (12/11/2019) | NSPE0013323116 | NSPE0013323116
Completed | NY500 | 600 Airborne Pkwy Buffalo, NY 14225-1434 US | 200 MBPS (31073265) | 04/15/2020: Order Completed on Apr 15, 2020 | 200447105 | NY500 | Private IP - PIP (31073264) WAN Analysis Reporting (31073266) Access (31073265) | 31073264 31073266 31073265 | 100 MBPS (31073264) |  | 94719707 (Private IP (PIP)) 94719705 (WAN Analysis Reporting) 94719703 (Access) | C5009212/ADD (31073264) E5023648/ADD (31073265) | 40.KFGS.222047..NY (3107326568101501) | 6107507 | 70000 | PVC ID : 6107507 VPN Name : UnitedHealthGroup Router Name : SRDXE01 VRF Name : V699748-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64775 PE IP Address : 68.138.123.9 CE Address : 68.138.123.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31073265) | 1000Base-SX (850nm, Multi Mode Fiber) (31073265) | Ethernet | VERIZON (3107326568101501) | 02/28/2020 (3107326568101501) | 04/15/2020 (3107326568101501) | 04/15/2020 (3107326568101501) |  |  | DEMARCDET - flr 1 electrical rm..wall mounted nid #..tagged |  | ROB DARATAR JR 1-716-602-6037 rdaratajr@uniland.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 | 04/15/2020(Private IP - PIP) 04/15/2020(WAN Analysis Reporting) 04/15/2020(Access) |  |  | 06/01/2020 (31073264) 05/28/2020 (31073265) | 05/28/2020 06/03/2020 | 04/15/2020 |  | Completed | N (31073264) N (31073266) N (31073265) | U0101953 | Jeopardy Notification 1 (02/27/2020) |  | NSPE0013343953
Completed | IN710 | 650 W Henry St Indianapolis, IN 46225 US | 500 MBPS (30565919) | 02/27/2020: Order Completed on Feb 27, 2020 | 200451701 | IN710 | Private IP - PIP (30565918) WAN Analysis Reporting (30565920) Access (30565919) | 30565918 30565920 30565919 | 100 MBPS (30565918) |  | 94719903 (Private IP (PIP)) 94719906 (WAN Analysis Reporting) 94719909 (Access) | C5008714/ADD (30565918) E5022087/ADD (30565919) | 174895-ENET-CCF (3056591968159401) | 6094787 | 90000 | PVC ID : 6094787 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64584 PE IP Address : 68.139.33.69 CE Address : 68.139.33.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30565919) | 1000Base-SX (850nm, Multi Mode Fiber) (30565919) | Ethernet | LIGHT TOWER (3056591968159401) | 11/26/2019 (3056591968159401) | 01/13/2020 (3056591968159401) | 01/13/2020 (3056591968159401) | 03/02/2020 (VFORCE) (30565919) | 02/27/2020 (VFORCE) (30565919) | DEMARCDET - 1st Flr/ FT panel room |  | Stephen Klein 1-317-806-2035 Sklein@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 02/27/2020(Private IP - PIP) 02/27/2020(WAN Analysis Reporting) 02/27/2020(Access) |  |  | 03/05/2020 (30565918) 03/03/2020 (30565919) | 04/06/2020 04/10/2020 | 02/27/2020 |  | Completed | N (30565918) N (30565920) N (30565919) | U0101953 | Jeopardy Notification 2 (02/05/2020) |  | NSPE0013344641
Completed | IN123 | 8901 Otis Ave Indianapolis, IN 46216-1037 US | 50 MBPS (30435399) | 12/19/2019: Order Completed on Dec 19, 2019 | 200290719 | IN123 | Access (30435399) Private IP - PIP (30435398) WAN Analysis Reporting (30435400) | 30435399 30435398 30435400 | 10 MBPS (30435398) |  | 94707561 (Access) 94707558 (Private IP (PIP)) 94707563 (WAN Analysis Reporting) | E4051883/ADD (30435399) C4020338/ADD (30435398) | IN/KXFN/246415/LVLC (3043539964969101) | 6091940 | 5500 | PVC ID : 6091940 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65016 PE IP Address : 68.137.126.213 CE Address : 68.137.126.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30435399) | 1000Base-SX (850nm, Multi Mode Fiber) (30435399) | Ethernet | LEVEL 3 (3043539964969101) | 11/26/2019 (3043539964969101) | 12/16/2019 (3043539964969101) | 12/17/2019 (3043539964969101) | 12/19/2019 (VFORCE) (30435399) |  | DEMARCDET - X |  | Jason Brooks 1-317-610-8224 Jason.Brooks@healthscopebenefits.com | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 12/19/2019(Access) 12/19/2019(Private IP - PIP) 12/19/2019(WAN Analysis Reporting) |  |  | 12/23/2019 (30435399) 12/26/2019 (30435398) | 12/25/2019 12/31/2019 | 12/19/2019 |  | Completed | N (30435399) N (30435398) N (30435400) | U0101953 | Jeopardy Notification 1 (11/11/2019) | NSPE0013299443 | NSPE0013299443
Completed | OH148 | 5150 E Dublin Granville Rd Columbus, OH 43081-8701 US | 100 MBPS (30435077) | 01/15/2020: Order Completed on Jan 15, 2020 | 200290823 | OH148 | Private IP - PIP (30435076) WAN Analysis Reporting (30435078) Access (30435077) | 30435076 30435078 30435077 | 50 MBPS (30435076) |  | 94707600 (Private IP (PIP)) 94707602 (WAN Analysis Reporting) 94707398 (Access) | C1098442/ADD (30435076) E4051968/ADD (30435077) | 61.L1XX.995184..CHTR (3043507764974101) | 6092258 | 30000 | PVC ID : 6092258 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65443 PE IP Address : 152.164.94.61 CE Address : 152.164.94.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30435077) | 1000Base-SX (850nm, Multi Mode Fiber) (30435077) | Ethernet | TIME WARNER CABLE (3043507764974101) | 11/11/2019 (3043507764974101) | 02/13/2020 (3043507764974101) | 01/13/2020 (3043507764974101) | 01/15/2020 (VFORCE) (30435077) | 01/15/2020 (VFORCE) (30435077) | DEMARCDET - 3rd flr communications rm mounted on the backwall |  | Robert Campana 1-614-797-5159 Robert.Campana@healthscopebenefits.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-990-179-8210 | 01/15/2020(Private IP - PIP) 01/15/2020(WAN Analysis Reporting) 01/15/2020(Access) |  |  | 02/24/2020 (30435076) 02/20/2020 (30435077) | 12/26/2019 01/01/2020 | 01/15/2020 |  | Completed | N (30435076) N (30435078) N (30435077) | U0101953 | Jeopardy Notification 1 (11/14/2019) | NSPE0013299443 | NSPE0013299443
Completed | 7XT1 LEANDER, TX | 601 CRYSTAL FALLS PKWY LEANDER, TX 78641 USA | 1.536 MBPS (IQBLV623) | 06/03/2020: Order Completed on Jan 16, 2020 | 10071027 |  | Private IP (IQBLV623) EVC/PVC Service (N.12179931.6095811) | IQBLV623 N.12179931.6095811 | 10.752 MBPS | P2323781 |  | BCBLJ41H0001 (IQBLV623) BCBLJ41H0002 (IQBLV623) BCBLJ41H0003 (IQBLV623) BCBLJ41H0004 (IQBLV623) BCBLJ41H0005 (IQBLV623) BCBLJ41H0006 (IQBLV623) BCBLJ41H0007 (IQBLV623) | 32/HCGS/698101//SW (IQBLV623RK0ZMB01) | 6095811 | 0 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65222 PE IP Address : 152.176.179.117 CE Address : 152.176.179.118 QoS - Egress Profile: R12 PVC ID : 6095811 |  |  |  | ATT (IQBLV623RK0ZMB01) | 01/07/2020 (IQBLV623RK0ZMB01) | 01/14/2020 (IQBLV623RK0ZMB01) | 01/15/2020 (IQBLV623RK0ZMB01) |  |  |  |  | RICK WILLIAMSON 0012103769633 RWILLIAMSON@WELLMED.NET |  |  |  | 01/16/2020 (IQBLV623) |  |  | 01/28/2020 (IQBLV623) | 01/28/2020 (IQBLV623) |  |  |  | N (IQBLV623) N (N.12179931.6095811) | 05017789 P2323781 |  | NSPE0013359455 | NSPE0013359455
Completed | change order | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 7000 MBPS (CQBLV7PQ) | 02/28/2020: 2/27Background: upgrade UnitedHealthGroup-ECCMA from 20m to 50m. Peak speed VLAN 31 PVC Id 5417303 Circuit id BOBKWHD00001 Status: Uograde complete Next action: Who owns the next action: | 10073008 |  | EVC/PVC Service (C.12182735.5417303) Private IP Port Only (CQBLV7PQ) | C.12182735.5417303 CQBLV7PQ | 7000 MBPS | P1957529 |  | BOBKWHD00001 (CQBLV7PQ) |  | 5417303 | 0 | PVC ID : 5417303 VPN Name : UnitedHealthGroup-ECCMA Router Name : MZZ9E01 VRF Name : V600584:UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65165 PE IP Address : 152.161.80.1 CE Address : 152.161.80.2 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON ED ED 7637442081 0017637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 02/27/2020 (CQBLV7PQ) |  |  | 01/03/2020 (CQBLV7PQ) | 01/03/2020 (CQBLV7PQ) |  |  |  | N (C.12182735.5417303) N (CQBLV7PQ) | P1957529 05017789 |  | NSPE0013367339 | NSPE0013367339
Completed | MARIETTA, GA |  | 1 GBPS (30556106) | 11/25/2019: Your order is on track: Provisioning Department accepted the order on Nov 25, 2019 and has begun processing. | 200435831 |  | Private IP - PIP (30556105) Access (30556106) | 30556105 30556106 | 1 GBPS (30556105) |  | 57546623 (Private IP (PIP)) 57546622 (Access) | C0022079/NONE (30556105) E5000692/NONE (30556106) |  | 5544488 | 450000 | PVC ID : 5544488 VPN Name : Alere-LLC-WAN,Alere-INC Router Name : ATL29E01 VRF Name : V470996:AlereLLCWAN,V494241:AlereINC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65110 PE IP Address : v4-199.220.202.29,v6-206.114.89.49 CE Address : v4-199.220.202.30,v6-206.114.89.50 QoS - Egress Profile: R1 | 1000Base-SX-850nm (30556106) | 1000Base-SX (850nm, Multi Mode Fiber) (30556106) | Ethernet | [8 empty] | Patrick Hermanto Patrick Hermanto 1-914-909-1837 patrick.hermanto@alere.com | Tony epperson | tony.epperson@alere.com | 1-312-315-5612 | 11/25/2019(Private IP - PIP) 11/25/2019(Access) |  |  | 11/27/2019 (30556105) 11/27/2019 (30556106) | 01/01/2020 | 11/25/2019 |  |  | N (30556105) N (30556106) | U0101953 |  | TOSA | NSPE0013326255
Completed | PH503 | 8th-9th Flr Calyx Centre Cebu I. T. Park Apas Cebu6000 PH | 500 MBPS | 12/19/2019: Order Completed on Dec 19, 2019 | 200769629 | Cebu City | Private IP - PIP (30677589) Access | 30677589 | 500 MBPS (30677589) |  | 142371612 (Private IP (PIP)) 142371610 | C5002793/NONE (30677589) |  | 5829481 | 140000 | PVC ID : 5829481 VPN Name : UnitedHealthGroup Router Name : MAN2GE01 VRF Name : V297577:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64937 PE IP Address : 206.115.34.53 CE Address : 206.115.34.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Armand Arbois 63-908-844-2768 armand_arbois@optum.com | henry Laurequez | henry_laurequez@optum.com | 63-920-905-9198 | 12/19/2019(Private IP |  |  | 12/16/2019 (30677589) | 12/23/2019 | 12/19/2019 |  |  | N (30677589) N | SG00213008 |  | changed CEBU | NSPE0013389625
Completed | TX548 | 3310 LIVE OAK ST DALLAS, TX 75204-6153 US | 50 MBPS (30704134) | 03/25/2020: Order Completed on Mar 25, 2020 | 200916481 | TX548-01 | Private IP - PIP (30704133) WAN Analysis Reporting (30704135) Access (30704134) | 30704133 30704135 30704134 | 10 MBPS (30704133) |  | 1227565753 (Private IP (PIP)) 1227565755 (WAN Analysis Reporting) 1227565749 (Access) | C4020787/ADD (30704133) E4053285/ADD (30704134) | 21.L1XX.815896..CHTR (3070413469247801) | 6098216 | 5500 | PVC ID : 6098216 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65407 PE IP Address : 152.161.216.73 CE Address : 152.161.216.74 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30704134) | 1000Base-SX (850nm, Multi Mode Fiber) (30704134) | Ethernet | TIME WARNER CABLE (3070413469247801) | 12/19/2019 (3070413469247801) | 03/19/2020 (3070413469247801) | 03/20/2020 (3070413469247801) | 03/26/2020 (VFORCE) (30704134) | 03/25/2020 (VFORCE) (30704134) | DEMARCDET - 3RD FLOOR, SUITE 300, IDF ROOM, CUSTOMER RACK |  | KHANH NGUYEN 1-817-368-6081 knguyen11@wellmed.net | Vasduev K | vasduev.k@optum.com | 91-886-175-8263 | 03/25/2020(Private IP - PIP) 03/25/2020(WAN Analysis Reporting) 03/25/2020(Access) |  |  | 03/30/2020 (30704133) 03/26/2020 (30704134) | 05/04/2020 05/08/2020 | 03/25/2020 |  | Completed | N (30704133) N (30704135) N (30704134) | U0101953 | Jeopardy Notification 1 (12/20/2019) |  | NSPE0013397731
Completed | UCA56 | 3515 Harbor Blvd Costa Mesa, CA 92626-1437 US | 500 MBPS (30716019) | 06/05/2020: Order Completed on Jun 5, 2020 | 200971993 | UNITED HEALTH GROUP | Private IP - PIP (30716018) WAN Analysis Reporting (30716020) Access (30716019) | 30716018 30716020 30716019 | 200 MBPS (30716018) |  | 94732160 (Private IP (PIP)) 94732163 (WAN Analysis Reporting) 94732165 (Access) | C5008858/ADD (30716018) E5022502/ADD (30716019) | 71.L1XX.826755..CHTR (3071601933842701) | 6098215 | 140000 | PVC ID : 6098215 VPN Name : UnitedHealthGroup Router Name : LSA29E01 VRF Name : V461763:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64906 PE IP Address : 152.164.113.165 CE Address : 152.164.113.166 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (30716019) | 1000Base-LX (1310nm Single Mode Fiber) (30716019) | Ethernet | TIME WARNER CABLE (3071601933842701) | 05/21/2020 (3071601933842701) | 06/21/2020 (3071601933842701) | 06/04/2020 (3071601933842701) | 06/05/2020 (VFORCE) (30716019) | 06/05/2020 (VFORCE) (30716019) | DEMARCDET - 1st floor rack mounted in the customer MDF room RAD 203 port 5 labeled with ckt id |  | John Pailliotet 1-562-706-8537 john.pailliotet@optum.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 | 06/05/2020(Private IP - PIP) 06/05/2020(WAN Analysis Reporting) 06/05/2020(Access) |  |  | 06/30/2020 (30716018) 06/26/2020 (30716019) | 10/12/2020 10/16/2020 | 06/05/2020 |  | Completed | N (30716018) N (30716020) N (30716019) | U0101953 | Jeopardy Notification 1 (12/23/2019) |  | NSPE0013403306
Completed | UNY33 | 1311 Mamaroneck Ave White Plains, NY 10605-5221 US | 50 MBPS (30752759) | 12/31/2019: Order Completed on Dec 31, 2019 | 200975627 | UNITEDHEALTH GROUP | Private IP - PIP (30752758) WAN Analysis Reporting (30752760) Access (30752759) | 30752758 30752760 30752759 | 10 MBPS (30752758) |  | 94732270 (Private IP (PIP)) 94732276 (WAN Analysis Reporting) 94732274 (Access) | C4020906/ADD (30752758) E4053500/ADD (30752759) | 32.KFGS.221608..NY (3075275989855601) | 6099258 | 5500 | PVC ID : 6099258 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64796 PE IP Address : 199.220.195.45 CE Address : 199.220.195.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30752759) | 1000Base-SX (850nm, Multi Mode Fiber) (30752759) | Ethernet | VERIZON (3075275989855601) | 12/26/2019 (3075275989855601) | 01/02/2020 (3075275989855601) | 12/31/2019 (3075275989855601) |  |  | DEMARCADDR - 1311 Mamaroneck Ave White Plains NY DEMARCDET - 1st floor Server room, wall mounted. Nid 3 tagged. |  | DANIELLE MAIORANA 1-347-909-1344 danielle_maiorana@uhg.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 12/31/2019(Private IP - PIP) 12/31/2019(WAN Analysis Reporting) 12/31/2019(Access) |  |  | 01/13/2020 (30752758) 01/09/2020 (30752759) | 01/28/2020 02/03/2020 | 12/31/2019 |  | Completed | N (30752758) N (30752760) N (30752759) | U0101953 |  |  | NSPE0013403806
Completed | NC061 | 4015 SHOPTON RD CHARLOTTE, NC 28217-3011 US | 100 MBPS (30716615) | 03/26/2020: Order Completed on Mar 26, 2020 | 200977831 | NC061 | Access (30716615) Private IP - PIP (30716614) WAN Analysis Reporting (30716616) | 30716615 30716614 30716616 | 50 MBPS (30716614) |  | 1228439103 (Access) 1228439107 (Private IP (PIP)) 1228439109 (WAN Analysis Reporting) | E4053288/ADD (30716615) C1099814/ADD (30716614) | 70.L1XX.989018..CHTR (3071661569329701) | 6098224 | 25000 | PVC ID : 6098224 VPN Name : UnitedHealthGroup Router Name : CHRL9E01 VRF Name : V638950:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65411 PE IP Address : 152.164.210.117 CE Address : 152.164.210.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30716615) | 1000Base-SX (850nm, Multi Mode Fiber) (30716615) | Ethernet | TIME WARNER CABLE (3071661569329701) | 12/18/2019 (3071661569329701) | 03/27/2020 (3071661569329701) | 03/23/2020 (3071661569329701) | 03/25/2020 (VFORCE) (30716615) |  | DEMARCDET - IT Closet 2nd room to the left in the hallway RAD 203 port 3 |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | JASON SALAPING | jason_salaping@optum.com | 1-210-862-6784 | 03/26/2020(Access) 03/26/2020(Private IP - PIP) 03/26/2020(WAN Analysis Reporting) |  |  | 04/03/2020 (30716615) 04/07/2020 (30716614) | 04/30/2020 05/06/2020 | 03/26/2020 |  | Completed | N (30716615) N (30716614) N (30716616) | U0101953 | Jeopardy Notification 1 (01/06/2020) |  | NSPE0013403941
Completed | MA-093 | 500 Unicorn Park Dr Woburn, MA 01801-3377 US | 300 MBPS (30573049) | 06/18/2020: Beas install scheduled for 6/19. | 200471951 | MA093 | Private IP - PIP (30573048) WAN Analysis Reporting (30573050) Access (30573049) | 30573048 30573050 30573049 | 200 MBPS (30573048) |  | 1222170795 (Private IP (PIP)) 1222170797 (WAN Analysis Reporting) 1222170791 (Access) | C5008721/ADD (30573048) E5022111/ADD (30573049) | 175329-ENET-CCF (3057304965836301) | 6094933 | 15000 | PVC ID : 6094933 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65446 PE IP Address : 152.181.67.173 CE Address : 152.181.67.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30573049) | 1000Base-SX (850nm, Multi Mode Fiber) (30573049) | Ethernet | LIGHT TOWER (3057304965836301) | 03/12/2020 (3057304965836301) | 06/08/2020 (3057304965836301) | 06/08/2020 (3057304965836301) | 07/03/2020 (VFORCE) (30573049) |  | DEMARCDET - 2nd floor, server room rack mounted |  | Brian Meehan 1-781-305-2385 Bmeehan@equia.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 06/19/2020(Private IP - PIP) 06/19/2020(WAN Analysis Reporting) 06/19/2020(Access) |  |  | 06/26/2020 (30573048) 06/24/2020 (30573049) | 07/29/2020 08/04/2020 | 06/19/2020 |  | Completed | N (30573048) N (30573050) N (30573049) | U0101953 | Jeopardy Notification 3 (02/27/2020) |  | NSPE0013346454
Completed | changed order for TX521 | 4230 W GREEN OAKS BLVD ARLINGTON, TX 76016-4517 US | 50 MBPS | 01/09/2020: 1/9Background: changed order Status: Change order complete Next action: completed Who owns the next action: customer | 201030003 | TX521 | Private IP - PIP (30733500) Access WAN Analysis Reporting (30733502) | 30733500 30733502 | 10 MBPS (30733500) |  | 94650178 (Private IP (PIP)) 94650181 94650176 (WAN Analysis Reporting) | C4018800/NONE (30733500) |  | 6068777 | 7000 | PVC ID : 6068777 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64943 PE IP Address : 152.164.64.177 CE Address : 152.164.64.178 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | LIZDELI GUERRIDO 1-210-762-3635 lguerrido@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 01/09/2020(Private IP |  |  | 12/20/2019 (30733500) | 12/31/2019 01/01/2020 (26969125.1) | 01/09/2020 |  | Completed Activated/Installed | N (30733500) N N (30733502) | U0101953 |  |  | NSPE0013417974
Completed | C1648 | 3180 Irving Blvd Dallas, TX 75247-6235 US | 50 MBPS (30776724) | 01/17/2020: Order Completed on Jan 17, 2020 | 201284783 | C1649 | Private IP - PIP (30776723) WAN Analysis Reporting (30776725) Access (30776724) | 30776723 30776725 30776724 | 50 MBPS (30776723) |  | 94737352 (Private IP (PIP)) 94737357 (WAN Analysis Reporting) 94737350 (Access) | C4020947/ADD (30776723) E4053612/ADD (30776724) |  | 6099786 | 9000 | PVC ID : 6099786 VPN Name : UHG-ECC Router Name : IAE9E01 VRF Name : V481056:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65412 PE IP Address : 68.138.69.173 CE Address : 68.138.69.174 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (30776724) | Ethernet | [8 empty] | Keri Christensen 1-385-743-9634 keri.christensen@niceincontact.com | JOHN BREMSETH | john_bremseth@optum.com | 1-763-553-4895 | 01/17/2020(Private IP - PIP) 01/17/2020(WAN Analysis Reporting) 01/17/2020(Access) |  |  | 01/14/2020 (30776723) 01/10/2020 (30776724) | 02/10/2020 02/14/2020 | 01/17/2020 | 01/08/2020 (30776724) | Completed | N (30776723) N (30776725) N (30776724) | U0101953 |  |  | NSPE0013425313
Completed | C1649 | 900 N Alameda St Los Angeles, CA 90012-2904 US | 50 MBPS (30776836) | 03/06/2020: Order Completed on Mar 6, 2020 | 201284589 | C1648 | Access (30776836) Private IP - PIP (30776835) WAN Analysis Reporting (30776837) | 30776836 30776835 30776837 | 50 MBPS (30776835) |  | 94737708 (Access) 94737706 (Private IP (PIP)) 94737713 (WAN Analysis Reporting) | E4053611/ADD (30776836) C4020946/ADD (30776835) |  | 6099782 | 13000 | PVC ID : 6099782 VPN Name : UHG-ECC Router Name : LSA29E01 VRF Name : Ve47055:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65420 PE IP Address : 68.139.92.201 CE Address : 68.139.92.202 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (30776836) | Ethernet | [8 empty] | Keri Christensen 1-385-743-9634 keri.christensen@niceincontact.com | JOHN BREMSETH | john_bremseth@optum.com | 1-763-553-4895 | 03/06/2020(Access) 03/06/2020(Private IP - PIP) 03/06/2020(WAN Analysis Reporting) |  |  | 03/05/2020 (30776836) 03/09/2020 (30776835) | 03/04/2020 03/10/2020 | 03/06/2020 |  | Completed | N (30776836) N (30776835) N (30776837) | U0101953 | Jeopardy Notification 1 (02/05/2020) |  | NSPE0013425295
Completed | TX552 | 4510 Medical Center Dr ste 311 Mckinney, TX 75069-1604 US | 50 MBPS (30800737) | 01/30/2020: 1/30Background:5010PIP-E Mckinney, TX TWT Status: Loop delivered 1/30 -Beas install 1/31 Next action: Beas Install Who owns the next action:VZT tech | 201444589 | TX552 | Private IP - PIP (30800736) WAN Analysis Reporting (30800738) Access (30800737) | 30800736 30800738 30800737 | 10 MBPS (30800736) |  | 94739264 (Private IP (PIP)) 94739262 (WAN Analysis Reporting) 94739266 (Access) | C4021013/ADD (30800736) E4053760/ADD (30800737) | 97.L1XX.815109..CHTR (3080073770298601) | 6100480 | 5500 | PVC ID : 6100480 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65406 PE IP Address : 68.139.85.129 CE Address : 68.139.85.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30800737) | 1000Base-SX (850nm, Multi Mode Fiber) (30800737) | Ethernet | TIME WARNER CABLE (3080073770298601) | 01/28/2020 (3080073770298601) | 02/21/2020 (3080073770298601) | 01/30/2020 (3080073770298601) | 01/31/2020 (VFORCE) (30800737) |  | DEMARCDET - Main Floor CPE MOUNTED IN STE# 311 SERVER CLOSET AT THE OTHER END OF LATERAL, ON WALL ETH PORT 5 MMF |  | Michael Webb 1-214-207-9993 mwebb3@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 01/31/2020(Private IP - PIP) 01/31/2020(WAN Analysis Reporting) 01/31/2020(Access) |  |  | 03/03/2020 (30800736) 02/28/2020 (30800737) | 03/10/2020 03/16/2020 | 01/31/2020 |  | Completed | N (30800736) N (30800738) N (30800737) | U0101953 | Jeopardy Notification 1 (01/28/2020) |  | NSPE0013434406
Completed | KY003 | 401 S 4th St Louisville, KY 40202-3426 US | 1 GBPS (30808493) | 02/06/2020: 2/6Background:1GB 500MB PIP-E Louisville, KY TWT Status: Loop delivered 2/5- Pending Beas install Next action: beas installed Who owns the next action: customer/ bne | 201474593 | KY003 | Private IP - PIP (30808492) WAN Analysis Reporting (30808494) Access (30808493) | 30808492 30808494 30808493 | 500 MBPS (30808492) |  | 94740334 (Private IP (PIP)) 94740336 (WAN Analysis Reporting) 94740332 (Access) | C0181616/ADD (30808492) E5022775/ADD (30808493) | KY/KXFN/268161/LVLC (3080849352382801) | 6100699 | 350000 | PVC ID : 6100699 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65432 PE IP Address : 152.162.117.53 CE Address : 152.162.117.54 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (30808493) | 1000Base-LX (1310nm Single Mode Fiber) (30808493) | Ethernet | LEVEL 3 (3080849352382801) | 01/20/2020 (3080849352382801) | 02/10/2020 (3080849352382801) | 02/05/2020 (3080849352382801) | 02/07/2020 (VFORCE) (30808493) |  | DEMARCDET - X |  | Jeremy Smith 1-502-272-2909 JSmith3@west.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 02/07/2020(Private IP - PIP) 02/07/2020(WAN Analysis Reporting) 02/07/2020(Access) |  |  | 03/09/2020 (30808492) 03/05/2020 (30808493) | 02/17/2020 02/21/2020 | 02/07/2020 |  | Completed | N (30808492) N (30808494) N (30808493) | U0101953 |  |  | NSPE0013436668
Completed | IN022 | 1050 Patrol Rd Jeffersonville, IN 47130-7750 US | 200 MBPS (30853317) | 04/03/2020: Order Completed on Apr 3, 2020 | 201657165 | IN022-02-IJ Catamaran Jeffersonville | WAN Analysis Reporting (30853318) Access (30853317) Private IP - PIP (30853316) | 30853318 30853317 30853316 | 100 MBPS (30853316) |  | 94741648 (WAN Analysis Reporting) 94741644 (Access) 94741646 (Private IP (PIP)) | C5009032/ADD (30853316) E5022901/ADD (30853317) | 81.L1XX.910328..CHTR (3085331712560401) | 6101895 | 50000 | PVC ID : 6101895 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 68.139.205.241 CE Address : 68.139.205.242 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (30853317) | 1000Base-LX (1310nm Single Mode Fiber) (30853317) | Ethernet | TIME WARNER CABLE (3085331712560401) | 03/06/2020 (3085331712560401) | 05/05/2020 (3085331712560401) | 04/01/2020 (3085331712560401) | 04/03/2020 (VFORCE) (30853317) | 04/03/2020 (VFORCE) (30853317) | DEMARCDET - Room 159 warehouse area, wall mounted |  | Melissa Chapman 1-763-744-2114 melissa_r_chapman@optum.com | Melissa Chapman | melissa_r_chapman@optum.com | 1-763-744-2114 | 04/03/2020(WAN Analysis Reporting) 04/03/2020(Access) 04/03/2020(Private IP - PIP) |  |  | 05/14/2020 (30853316) 05/12/2020 (30853317) | 07/29/2020 07/23/2020 | 04/03/2020 |  | Completed | N (30853318) N (30853317) N (30853316) | U0101953 | Jeopardy Notification 3 (02/22/2020) |  | NSPE0013453126
Completed | GA074 | 425 Franklin Gtwy Se Marietta, GA 30067-7748 US | 50 MBPS (30901777) | 04/24/2020: Order Completed on Apr 24, 2020 | 201830241 | GA074 | Private IP - PIP (30901776) WAN Analysis Reporting (30901778) Access (30901777) | 30901776 30901778 30901777 | 20 MBPS (30901776) |  | 94744727 (Private IP (PIP)) 94744734 (WAN Analysis Reporting) 94744730 (Access) | C4021305/ADD (30901776) E4054465/ADD (30901777) | 30.KFGS.042027..CBCL.. (3090177771155801) | 6103118 6103119 | 14000 | PVC ID : 6103118,6103119 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64770 PE IP Address : 152.181.193.37 CE Address : 152.181.193.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30901777) | 1000Base-SX (850nm, Multi Mode Fiber) (30901777) | Ethernet | COMCAST (3090177771155801) | 03/27/2020 (3090177771155801) | 04/28/2020 (3090177771155801) | 04/21/2020 (3090177771155801) | 04/24/2020 (VFORCE) (30901777) | 04/24/2020 (VFORCE) (30901777) | DEMARCADDR - 1 DEMARCDET - 1st floor room 109 rackmounted in rack #2 RU 45 and comcast labeled |  | Charles Philips 1-678-641-3510 cphillips@asacarlton.com | EDWARD SAWYERR | edward.sawyerr@optum.com | 1-763-595-3403 | 04/24/2020(Private IP - PIP) 04/24/2020(WAN Analysis Reporting) 04/24/2020(Access) |  |  | 05/07/2020 (30901776) 05/05/2020 (30901777) | 05/07/2020 05/13/2020 | 04/24/2020 |  | Completed | N (30901776) N (30901778) N (30901777) | U0101953 | Jeopardy Notification 1 (03/03/2020) |  | NSPE0013472042
Completed |  | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US |  | 01/10/2020: Order Completed on Jan 10, 2020 | 200402433 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (30534701) Access (30534702) | 30534701 30534702 | 2000 MBPS |  | 289292535 (Internet Dedicated Services) 289292531 (Access) | C0155297/REMOVE (30534701) E7000741/REMOVE (30534702) |  | 6014524 | 0 | PVC ID : 6014524 VPN Name : Internet Router Name : GW7DFW13 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.14.49 CE Address : 204.148.14.50 |  |  | Ethernet | [8 empty] | MATTHEW ADAMS 1-763-553-4616 matthew_adams@optum.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 01/10/2020(Internet Dedicated Services) 01/10/2020(Access) |  |  | 12/26/2019 (30534701) 12/26/2019 (30534702) | 12/23/2019 | 01/10/2020 |  |  | N (30534701) N (30534702) | U0101953 |  |  | NSPE0013334803
Completed | TX777-05-IJ Student Resources Internet T1 | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US | 10 GBPS (30955048) | 03/19/2020: Changes are complete. Pending order closure. | 201966527 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (30955047) Access (30955048) | 30955047 30955048 | 10 GBPS (30955047) |  | 1182228043 (Internet Dedicated Services) 1182228039 (Access) | C0173321/NONE (30955047) E7001235/NONE (30955048) |  | 6074903 | 0 | PVC ID : 6074903 VPN Name : Internet Router Name : GW7DFW13 VRF Name : XXX Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 10879 PE IP Address : 204.148.197.61 CE Address : 204.148.197.62 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (30955048) | Ethernet | [8 empty] | MATTHEW ADAMS 1-763-553-4616 matthew_adams@optum.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 | 03/20/2020(Internet Dedicated Services) 03/20/2020(Access) |  |  | 02/28/2020 (30955047) 02/25/2020 (30955048) | 03/19/2020 | 03/24/2020 |  |  | N (30955047) N (30955048) | U0101953 |  |  | NSPE0013487232
Completed | TX553 | 219 S O CONNOR RD IRVING, TX 75060-2950 US | 50 MBPS (31017309) | 04/28/2020: Order Completed on Apr 28, 2020 | 202014431 | TX553 | Private IP - PIP (31017308) WAN Analysis Reporting (31017310) Access (31017309) | 31017308 31017310 31017309 | 10 MBPS (31017308) |  | 1240541107 (Private IP (PIP)) 1240541109 (WAN Analysis Reporting) 1240541103 (Access) | C4021527/ADD (31017308) E4055032/ADD (31017309) | 13/KRGN/304733//FTNC/ (3101730971803901) | 6105621 | 5500 | PVC ID : 6105621 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65265 PE IP Address : 152.162.117.25 CE Address : 152.162.117.26 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31017309) | 1000Base-SX (850nm, Multi Mode Fiber) (31017309) | Ethernet | FRONTIER (3101730971803901) | 03/25/2020 (3101730971803901) | 04/22/2020 (3101730971803901) | 04/23/2020 (3101730971803901) | 04/28/2020 (VFORCE) (31017309) | 04/28/2020 (VFORCE) (31017309) |  |  | KHANH NGUYEN 1-817-918-2920 knguyen11@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 04/28/2020(Private IP - PIP) 04/28/2020(WAN Analysis Reporting) 04/28/2020(Access) |  |  | 05/01/2020 (31017308) 04/29/2020 (31017309) | 05/04/2020 05/08/2020 | 04/28/2020 |  | Completed | N (31017308) N (31017310) N (31017309) | U0101953 | Jeopardy Notification 1 (03/11/2020) |  | NSPE0013503021
Completed | Carlsbad | 2858 Loker Ave E Carlsbad, CA 92010-6666 US | 200 MBPS (31057375) | 03/30/2020: Order Completed on Mar 30, 2020 | 202044679 | Carlsbad | Private IP - PIP (31057374) WAN Analysis Reporting (31057376) Access (31057375) | 31057374 31057376 31057375 | 100 MBPS (31057374) |  | 94754272 (Private IP (PIP)) 94754268 (WAN Analysis Reporting) 94754270 (Access) | C5009210/ADD (31057374) E5023606/ADD (31057375) | AS/KRGN/001833/PT (3105737523097201) | 6107079 | 70000 | PVC ID : 6107079 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64895 PE IP Address : 68.136.240.125 CE Address : 68.136.240.126 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31057375) | 1000Base-SX (850nm, Multi Mode Fiber) (31057375) | Ethernet | NITEL USA (3105737523097201) | 02/10/2020 (3105737523097201) | 03/31/2020 (3105737523097201) | 03/26/2020 (3105737523097201) | 03/30/2020 (VFORCE) (31057375) | 03/30/2020 (VFORCE) (31057375) | DEMARCDET - FIRST FLOOR SERVER ROOM WALL MOUNTED |  | GUSTAVO JASSO 1-760-804-2211 jasso.gx@optum.com | Joseph Mark Sanorjo | joseph_sanorjo@optum.com | 632-790-6484 | 03/30/2020(Private IP - PIP) 03/30/2020(WAN Analysis Reporting) 03/30/2020(Access) |  |  | 04/09/2020 (31057374) 04/07/2020 (31057375) | 03/18/2020 03/24/2020 | 03/30/2020 |  | Completed | N (31057374) N (31057376) N (31057375) | U0101953 |  |  | NSPE0013513176
Completed | TX561 | 9209 Elam Rd ste 102 Dallas, TX 75217-7369 US | 50 MBPS (31111078) | 06/23/2020: Order Completed on Jun 23, 2020 | 202095489 | TX561 | Private IP - PIP (31111077) WAN Analysis Reporting (31111079) Access (31111078) | 31111077 31111079 31111078 | 10 MBPS (31111077) |  | 94756639 (Private IP (PIP)) 94756644 (WAN Analysis Reporting) 94756641 (Access) | C4021676/ADD (31111077) E4055513/ADD (31111078) | 97.L1XX.815251..CHTR (3111107872472101) | 6108390 | 5500 | PVC ID : 6108390 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65404 PE IP Address : 68.138.212.109 CE Address : 68.138.212.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31111078) | 1000Base-SX (850nm, Multi Mode Fiber) (31111078) | Ethernet | TIME WARNER CABLE (3111107872472101) | 02/26/2020 (3111107872472101) | 06/30/2020 (3111107872472101) | 06/19/2020 (3111107872472101) | 06/23/2020 (VFORCE) (31111078) | 06/23/2020 (VFORCE) (31111078) | DEMARCDET - 1st Floor STE 012 RAD ETX-205-AX - port 5 |  | MARCO WONG 1-214-493-4068 mwong@wellmed.net | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 06/23/2020(Private IP - PIP) 06/23/2020(WAN Analysis Reporting) 06/23/2020(Access) |  |  | 07/10/2020 (31111077) 07/08/2020 (31111078) | 10/07/2020 10/13/2020 | 06/23/2020 |  | Completed | N (31111077) N (31111079) N (31111078) | U0101953 |  |  | NSPE0013529832
Completed | TX550 | 1200 Binz St ste 1200 Houston, TX 77004-6926 US | 50 MBPS (31111287) | 05/07/2020: Beas install scheduled for 5/8. | 202095471 | TX550 | Private IP - PIP (31111286) WAN Analysis Reporting (31111288) Access (31111287) | 31111286 31111288 31111287 | 20 MBPS (31111286) |  | 94756563 (Private IP (PIP)) 94756570 (WAN Analysis Reporting) 94756566 (Access) | C4021677/ADD (31111286) E4055514/ADD (31111287) | 05.EVC-.003366..ALPH (3111128772406701) | 6108391 | 13000 | PVC ID : 6108391 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65225 PE IP Address : 159.24.145.29 CE Address : 159.24.145.30 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (31111287) | 1000Base-SX (850nm, Multi Mode Fiber) (31111287) | Ethernet | ALPHEUS (3111128772406701) | 02/13/2020 (3111128772406701) | 03/26/2020 (3111128772406701) | 04/03/2020 (3111128772406701) | 05/08/2020 (VFORCE) (31111287) | 05/08/2020 (VFORCE) (31111287) | DEMARCDET - Back of cabinet on playwood floor 1 |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | MANISH SARKHEL | manish_sarkhel@optum.com | 91-120-671-2655 | 05/08/2020(Private IP - PIP) 05/08/2020(WAN Analysis Reporting) 05/08/2020(Access) |  |  | 05/13/2020 (31111286) 05/11/2020 (31111287) | 06/15/2020 06/19/2020 | 05/08/2020 |  | Completed | N (31111286) N (31111288) N (31111287) | U0101953 |  |  | NSPE0013527064
Completed | UVA30 | 9020 Stony Point Pkwy fl 3rd Richmond, VA 23235-1947 US | 50 MBPS (31418222) | 05/20/2020: Order Completed on May 20, 2020 | 202095663 | UVA30 | WAN Analysis Reporting (31418223) Access (31418222) Private IP - PIP (31418221) | 31418223 31418222 31418221 | 20 MBPS (31418221) |  | 94757033 (WAN Analysis Reporting) 94757029 (Access) 94757026 (Private IP (PIP)) | C4022291/ADD (31418221) E4057191/ADD (31418222) | 48.KFGS.306905..CV (3141822272491101) | 6115269 | 15000 | PVC ID : 6115269 VPN Name : UnitedHealthGroup Router Name : RIJ9E03 VRF Name : V601732:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65402 PE IP Address : 152.187.217.225 CE Address : 152.187.217.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31418222) | 1000Base-SX (850nm, Multi Mode Fiber) (31418222) | Ethernet | VERIZON (3141822272491101) | 05/05/2020 (3141822272491101) | 05/21/2020 (3141822272491101) | 05/20/2020 (3141822272491101) |  |  | DEMARCDET - 3RD FL SVR ROOM, RACK 3, SHELF 4, POS 1 |  | KATIE MALONEY 1-617-852-7976 katharine_maloney@uhg.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 05/20/2020(WAN Analysis Reporting) 05/20/2020(Access) 05/20/2020(Private IP - PIP) |  |  | 06/02/2020 (31418221) 05/29/2020 (31418222) | 06/08/2020 06/02/2020 | 05/20/2020 |  | Completed | N (31418223) N (31418222) N (31418221) | U0101953 |  |  | NSPE0013530685
Completed | FL435 | 734 Elkcam Blvd Deltona, FL 32725-2626 US | 50 MBPS (31147242) | 04/06/2020: Order Completed on Apr 6, 2020 | 202116833 | FL435 | Private IP - PIP (31147241) WAN Analysis Reporting (31147243) Access (31147242) | 31147241 31147243 31147242 | 10 MBPS (31147241) |  | 94758356 (Private IP (PIP)) 94758362 (WAN Analysis Reporting) 94758359 (Access) | C4021747/ADD (31147241) E4055702/ADD (31147242) | 25.KXGS.494714..UFLG (3114724272610501) | 6109135 | 7000 | PVC ID : 6109135 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65403 PE IP Address : 68.139.7.45 CE Address : 68.139.7.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31147242) | 1000Base-SX (850nm, Multi Mode Fiber) (31147242) | Ethernet | CENTURYLINK (3114724272610501) | 02/18/2020 (3114724272610501) | 04/07/2020 (3114724272610501) | 04/03/2020 (3114724272610501) | 04/06/2020 (VFORCE) (31147242) | 04/06/2020 (VFORCE) (31147242) | DEMARCADDR - x DEMARCDET - x |  | Scott B Cannon 1-813-465-5418 scannon1@wellmed.net | MANISH SARKHEL | manish_sarkhel@optum.com | 632-671-2655 | 04/06/2020(Private IP - PIP) 04/06/2020(WAN Analysis Reporting) 04/06/2020(Access) |  |  | 04/24/2020 (31147241) 04/22/2020 (31147242) | 03/30/2020 04/03/2020 | 04/06/2020 |  | Completed | N (31147241) N (31147243) N (31147242) | U0101953 |  |  | NSPE0013536456
Completed |  | 1 Harmon Plz Secaucus, NJ 07094-2803 US | 50 MBPS (31281699) | 03/21/2020: Order Completed on Mar 21, 2020 | 202144839 | NJ735 NJ191 | Private IP - PIP (31281698) WAN Analysis Reporting (31281700) Access (31281699) | 31281698 31281700 31281699 | 50 MBPS (31281698) |  | 94759471 (Private IP (PIP)) 94759477 (WAN Analysis Reporting) 94759474 (Access) | C4021978/ADD (31281698) E4056434/ADD (31281699) | .KFGS.313821..NJ (3128169970965701) | 6111964 | 30000 | PVC ID : 6111964 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65397 PE IP Address : 152.187.0.201 CE Address : 152.187.0.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31281699) | 1000Base-SX (850nm, Multi Mode Fiber) (31281699) | Ethernet | VERIZON (3128169970965701) | 03/05/2020 (3128169970965701) | 03/23/2020 (3128169970965701) | 03/20/2020 (3128169970965701) |  |  | DEMARCDET - 3RD FLOOR CUST SERVER ROOM WALL MOUNTED NID TAGGED WITH BOTH ID'S |  | Elena Webb 1-407-304-6567 elena.webb@optum.com | SUDHANSHU DUTT TIWARI | sudhanshu_tiwari@optum.com | 91-804-670-4384 | 03/21/2020(Private IP - PIP) 03/21/2020(WAN Analysis Reporting) 03/21/2020(Access) |  |  | 04/01/2020 (31281698) 03/30/2020 (31281699) | 04/01/2020 04/07/2020 | 03/21/2020 |  | Completed | N (31281698) N (31281700) N (31281699) | U0101953 |  |  | NSPE0013545259
Completed | NJ735 NJ191 | 511 11TH AVE S MINNEAPOLIS, MN 55415-1537 US |  | 02/20/2020: Order Completed on Feb 20, 2020 | 202114151 | 511 | Private IP - PIP (31144013) Access WAN Analysis Reporting (31144015) | 31144013 31144015 | 500 MBPS (31144013) |  | 337301409 (Private IP (PIP)) 337301365 337301411 (WAN Analysis Reporting) | C0167608/NONE (31144013) |  | 6051867 | 250000 | PVC ID : 6051867 VPN Name : UHG-OFE Router Name : MN39E01 VRF Name : Vc13322:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65483 PE IP Address : 68.138.244.229 CE Address : 68.138.244.230 QoS - Egress Profile: G1 |  | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Scott McCrady 1-612-800-6534 scott.mccrady@cologix.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 | 02/20/2020(Private IP |  |  | 02/18/2020 (31144013) | 02/27/2020 02/28/2020 (26386541.3) | 02/20/2020 |  | Completed Activated/Installed | N (31144013) N N (31144015) | U0101953 |  |  | NSPE0013535726
Completed | TX555 | 1901 W William Cannon Dr ste 112 Austin, TX 78745-5322 US | 50 MBPS (31217200) | 04/22/2020: Order Completed on Apr 22, 2020 | 202189251 | TX555 | WAN Analysis Reporting (31217201) Access (31217200) Private IP - PIP (31217199) | 31217201 31217200 31217199 | 10 MBPS (31217199) |  | 94764163 (WAN Analysis Reporting) 94764159 (Access) 94764161 (Private IP (PIP)) | C4021882/ADD (31217199) E4056114/ADD (31217200) | 51.L1XX.815290..TWCC (3121720073082201) | 6110637 | 7000 | PVC ID : 6110637 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64934 PE IP Address : 152.181.127.225 CE Address : 152.181.127.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31217200) | 1000Base-SX (850nm, Multi Mode Fiber) (31217200) | Ethernet | TIME WARNER CABLE (3121720073082201) | 04/15/2020 (3121720073082201) | 04/27/2020 (3121720073082201) | 04/21/2020 (3121720073082201) | 04/22/2020 (VFORCE) (31217200) |  | DEMARCDET - 1ST FLOOR, SUITE 123, BACK BATHROOM, WALL MOUNTED. |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 04/22/2020(WAN Analysis Reporting) 04/22/2020(Access) 04/22/2020(Private IP - PIP) |  |  | 05/06/2020 (31217199) 05/04/2020 (31217200) | 09/04/2020 08/31/2020 | 04/22/2020 |  | Completed | N (31217201) N (31217200) N (31217199) | U0101953 |  |  | NSPE0013559602
Completed | TX475 | 165 Hargraves Dr ste 100 Austin, TX 78737-4795 US | 50 MBPS (31218386) | 11/03/2020: Order Completed on Nov 2, 2020 | 202191377 | TX475 | Private IP - PIP (31218385) WAN Analysis Reporting (31218387) Access (31218386) | 31218385 31218387 31218386 | 10 MBPS (31218385) |  | 94764409 (Private IP (PIP)) 94764414 (WAN Analysis Reporting) 94764411 (Access) | C4021883/ADD (31218385) E4056120/ADD (31218386) | 51.L1XX.816134..CHTR (3121838673097201) | 6110671 | 7000 | PVC ID : 6110671 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64904 PE IP Address : 152.164.53.177 CE Address : 152.164.53.178 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31218386) | 1000Base-SX (850nm, Multi Mode Fiber) (31218386) | Ethernet | TIME WARNER CABLE (3121838673097201) | 10/21/2020 (3121838673097201) | 11/05/2020 (3121838673097201) | 10/29/2020 (3121838673097201) | 11/02/2020 (VFORCE) (31218386) |  | DEMARCDET - 1st Floor, Suite 100, IDF Room rack mounted |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 | 11/02/2020(Private IP - PIP) 11/02/2020(WAN Analysis Reporting) 11/02/2020(Access) |  |  | 11/16/2020 (31218385) 11/12/2020 (31218386) | 03/12/2021 03/18/2021 | 11/02/2020 |  | Completed | N (31218385) N (31218387) N (31218386) | U0101953 |  |  | NSPE0013560362
Completed |  | 100 CARR 165 GUAYNABO, PR 00968-8047 PR |  | 03/26/2020: Disconnect FOC = 27 March. | 202262209 | PR516-02-IM Puerto Rico, Guaynabo | Private IP - PIP (31287469) WAN Analysis Reporting (31287471) Access (31287470) | 31287469 31287471 31287470 | 50 MBPS |  | 190071477 (Private IP (PIP)) 190071478 (WAN Analysis Reporting) 190071475 (Access) | C4008767/REMOVE (31287469) E4023740/REMOVE (31287470) | SF 154-0066 (31287470PTT00001) | 5916931 | 25000 | PVC ID : 5916931 VPN Name : UnitedHealthGroup Router Name : SNJN9E01 VRF Name : Vc13521:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65216 PE IP Address : 152.176.132.153 CE Address : 152.176.132.154 QoS - Egress Profile: R12 |  |  | Ethernet | CLEC or INDEPENDENT (31287470PTT00001) | 03/06/2020 (31287470PTT00001) | 03/27/2020 (31287470PTT00001) | 03/27/2020 (31287470PTT00001) |  |  |  |  | Melissa Chapman Melissa Chapman 1-176-374-4211 melissa_r_chapman@optum.com | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 | 03/31/2020(Private IP - PIP) 03/31/2020(WAN Analysis Reporting) 03/31/2020(Access) |  |  | 03/31/2020 (31287469) 03/31/2020 (31287470) | 03/27/2020 | 03/31/2020 |  | Completed | N (31287469) N (31287471) N (31287470) | U0101953 | Jeopardy Notification 1 (03/06/2020) |  | NSPE0013571494
Completed | UTX12 | 2000 West Loop S Houston, TX 77027-3513 US | 100 MBPS (31372936) | 04/01/2020: Order Completed on Apr 1, 2020 | 202343881 | UTX12 | WAN Analysis Reporting (31372937) Access (31372936) Private IP - PIP (31372935) | 31372937 31372936 31372935 | 50 MBPS (31372935) |  | 94774649 (WAN Analysis Reporting) 94774647 (Access) 94774645 (Private IP (PIP)) | C1104466/ADD (31372935) E4056946/ADD (31372936) |  | 6114074 | 0 | PVC ID : 6114074 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65396 PE IP Address : 208.219.138.97 CE Address : 208.219.138.98 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31372936) | Ethernet | [8 empty] | Kidist Atnafu 1-832-500-6638 kidist_atnafu@uhg.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 04/01/2020(WAN Analysis Reporting) 04/01/2020(Access) 04/01/2020(Private IP - PIP) |  |  | 04/09/2020 (31372935) 04/07/2020 (31372936) | 04/30/2020 04/24/2020 | 04/01/2020 |  | Completed | N (31372937) N (31372936) N (31372935) | U0101953 |  |  | NSPE0013607796
Completed | IN156-01-IM | 5975 CASTLE CREEK PARKWAY NORTH DR INDIANAPOLIS, IN 46250-4340 US | 500 MBPS (31390403) | 04/09/2020: FOC date 4/16. | 202363761 | IN156 | Private IP - PIP (31390402) WAN Analysis Reporting (31390404) Access (31390403) | 31390402 31390404 31390403 | 300 MBPS (31390402) |  | 1254058285 (Private IP (PIP)) 1254058287 (WAN Analysis Reporting) 1254058281 (Access) | C5009626/ADD (31390402) E5024696/ADD (31390403) | IN/KXFN/305525/LVLC (3139040374180401) | 6114494 | 180000 | PVC ID : 6114494 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65042 PE IP Address : 152.177.214.1 CE Address : 152.177.214.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31390403) | 1000Base-SX (850nm, Multi Mode Fiber) (31390403) | Ethernet | LEVEL 3 (3139040374180401) | 03/26/2020 (3139040374180401) | 04/16/2020 (3139040374180401) | 04/14/2020 (3139040374180401) | 04/16/2020 (VFORCE) (31390403) |  | DEMARCADDR - X DEMARCDET - X |  | STEPHEN KLEIN 1-317-806-2035 sklein@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 04/16/2020(Private IP - PIP) 04/16/2020(WAN Analysis Reporting) 04/16/2020(Access) |  |  | 04/27/2020 (31390402) 04/23/2020 (31390403) | 05/06/2020 05/12/2020 | 04/16/2020 |  | Completed | N (31390402) N (31390404) N (31390403) | U0101953 |  |  | NSPE0013611364
Completed | TX554-01-IM | 209 E 2nd St Elgin, TX 78621-2225 US | 50 MBPS (31390618) | 03/31/2020: Order Completed on Mar 31, 2020 | 202364235 | TX554 | Private IP - PIP (31390617) WAN Analysis Reporting (31390619) Access (31390618) | 31390617 31390619 31390618 | 10 MBPS (31390617) |  | 94775847 (Private IP (PIP)) 94775849 (WAN Analysis Reporting) 94775845 (Access) | C4022232/ADD (31390617) E4057048/ADD (31390618) | 32/KRGN/654239//SW (3139061874180401) | 6114500 | 5500 | PVC ID : 6114500 VPN Name : UnitedHealthGroup Router Name : AX39E01 VRF Name : Vd31961:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64761 PE IP Address : 152.187.175.189 CE Address : 152.187.175.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31390618) | 1000Base-SX (850nm, Multi Mode Fiber) (31390618) | Ethernet | ATT (3139061874180401) | 03/19/2020 (3139061874180401) | 03/30/2020 (3139061874180401) | 03/30/2020 (3139061874180401) | 03/31/2020 (VFORCE) (31390618) |  | DEMARCDET - 1st Flr Telco room Ciena 3903 port 2 MM LC Handoff tagged not extended |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 03/31/2020(Private IP - PIP) 03/31/2020(WAN Analysis Reporting) 03/31/2020(Access) |  |  | 04/08/2020 (31390617) 04/06/2020 (31390618) | 04/29/2020 05/05/2020 | 03/31/2020 |  | Completed | N (31390617) N (31390619) N (31390618) | U0101953 |  |  | NSPE0013611763
Completed | TX777-16-IM | 1950 N STEMMONS FWY STE 3050 DALLAS, TX 75207-3173 US |  | 03/26/2020: Order showing tagged when should be untagged. IT ticket opened for this issue and being escalated. Issue has to be resolved for we can request dispatch for testing. | 202365431 | Equinix Dallas 1 gig internet | Private IP - PIP (31392017) WAN Analysis Reporting (31392019) Access (31392018) | 31392017 31392019 31392018 | 5 GBPS (31392017) |  | 1254422925 (Private IP (PIP)) 1254422927 (WAN Analysis Reporting) 1254422921 (Access) | C0186430/ADD (31392017) E7001610/ADD (31392018) | jxste nrc 0032 (I0112643.DAL) | 6114524 | 1200000 | PVC ID : 6114524 VPN Name : UnitedHealthGroup Router Name : 9O4XE02 VRF Name : Vj15594-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65246 PE IP Address : 152.187.236.13 CE Address : 152.187.236.14 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (31392018) | Ethernet | [8 empty] | CARLY GLIEDEN 1-952-912-7849 carly.glieden@optum.com | EMAD BHATT | emad@optum.com | 1-952-833-7538 | 03/31/2020(Private IP - PIP) 03/31/2020(WAN Analysis Reporting) 03/31/2020(Access) |  |  | 04/02/2020 (31392017) 04/02/2020 (31392018) | 04/15/2020 04/21/2020 | 03/31/2020 | 03/25/2020 (31392018) | Completed | N (31392017) N (31392019) N (31392018) | U0101953 |  |  | NSPE0013616495
Completed | GA777-15-IM | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 03/26/2020: Testing scheduled for 3/27. | 202365569 | Equinix hub Atlanta Peachtree GA777-04-IJ | Private IP - PIP (31392098) WAN Analysis Reporting (31392100) Access (31392099) | 31392098 31392100 31392099 | 5 GBPS (31392098) |  | 1254482819 (Private IP (PIP)) 1254483061 (WAN Analysis Reporting) 1254482815 (Access) | C0186433/ADD (31392098) E7001612/ADD (31392099) | jx8hk 25u 0004 (I0092719.ATL) | 6114536 | 2500000 | PVC ID : 6114536 VPN Name : UnitedHealthGroup Router Name : 95JXE01 VRF Name : Vc78844-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65138 PE IP Address : 152.187.234.185 CE Address : 152.187.234.186 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (31392099) | Ethernet | [8 empty] | EMAD BHATT 91-952-833-7538 emad@optum.com | EMAD BHATT | emad@optum.com | 91-804-670-4757 | 03/27/2020(Private IP - PIP) 03/27/2020(WAN Analysis Reporting) 03/27/2020(Access) |  |  | 03/30/2020 (31392098) 03/30/2020 (31392099) | 04/15/2020 04/21/2020 | 03/27/2020 | 03/25/2020 (31392099) | Completed | N (31392098) N (31392100) N (31392099) | U0101953 |  |  | NSPE0013616559
Completed | CA777-08-IM | 600 W 7TH ST FL 6 LOS ANGELES, CA 90017-3859 US |  | 03/31/2020: Order Completed on Mar 31, 2020 | 202365205 | Equinix Internet Los Angeles | Private IP - PIP (31391923) WAN Analysis Reporting (31391925) Access (31391924) | 31391923 31391925 31391924 | 5 GBPS (31391923) |  | 1254291223 (Private IP (PIP)) 1254291225 (WAN Analysis Reporting) 1254291139 (Access) | C0186431/ADD (31391923) E7001611/ADD (31391924) | jx7um 8sh 0018 (I0154051.LSA) | 6114533 | 2500 | PVC ID : 6114533 VPN Name : UnitedHealthGroup Router Name : LL6XE01 VRF Name : V510590-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65155 PE IP Address : 208.219.143.193 CE Address : 208.219.143.194 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (31391924) | Ethernet | [8 empty] | EMAD BHATT 1-952-833-7538 emad@optum.com | EMAD BHATT | emad@optum.com | 1-952-833-7538 | 03/31/2020(Private IP - PIP) 03/31/2020(WAN Analysis Reporting) 03/31/2020(Access) |  |  | 04/03/2020 (31391923) 04/03/2020 (31391924) | 04/15/2020 04/21/2020 | 03/31/2020 | 03/25/2020 (31391924) | Completed | N (31391923) N (31391925) N (31391924) | U0101953 |  |  | NSPE0013616370
Completed | TX566-01-IM | 4682 Mcdermott Rd ste 100 Plano, TX 75024-7772 US | 50 MBPS (31399267) | 05/01/2020: Order Completed on May 1, 2020 | 202368397 | TX566 | Private IP - PIP (31399266) WAN Analysis Reporting (31399268) Access (31399267) | 31399266 31399268 31399267 | 10 MBPS (31399266) |  | 94777157 (Private IP (PIP)) 94777161 (WAN Analysis Reporting) 94777155 (Access) | C4022250/ADD (31399266) E4057095/ADD (31399267) | 97.L1XX.815307..CHTR (3139926774299001) | 6114755 | 9000 | PVC ID : 6114755 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65395 PE IP Address : 152.176.176.81 CE Address : 152.176.176.82 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31399267) | 1000Base-SX (850nm, Multi Mode Fiber) (31399267) | Ethernet | TIME WARNER CABLE (3139926774299001) | 03/20/2020 (3139926774299001) | 05/05/2020 (3139926774299001) | 04/30/2020 (3139926774299001) | 05/01/2020 (VFORCE) (31399267) | 05/01/2020 (VFORCE) (31399267) | DEMARCDET - MAIN BLDG, MAIN FLOOR, MDF ROOM |  | MARCO WONG 1-214-493-4068 mwong@wellmed.net | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 05/01/2020(Private IP - PIP) 05/01/2020(WAN Analysis Reporting) 05/01/2020(Access) |  |  | 05/14/2020 (31399266) 05/12/2020 (31399267) | 04/30/2020 05/06/2020 | 05/01/2020 |  | Completed | N (31399266) N (31399268) N (31399267) | U0101953 |  |  | NSPE0013619660
Completed |  | 20414 N 27th Ave Phoenix, AZ 85027-3250 US | 100 MBPS (31417567) | 05/07/2020: Beas install complete. Pending testing and closing of order. | 202392473 | UNITED HEALTHCARE SERVICES INC | Private IP - PIP (31417566) WAN Analysis Reporting (31417568) Access (31417567) | 31417566 31417568 31417567 | 50 MBPS (31417566) |  | 94778393 (Private IP (PIP)) 94778395 (WAN Analysis Reporting) 94778397 (Access) | C1104635/ADD (31417566) E4057184/ADD (31417567) | 23.KFGX.991832..COXC. (3141756725704801) | 6115240 | 30000 | PVC ID : 6115240 VPN Name : UnitedHealthGroup Router Name : PHN1XE02 VRF Name : Vd82055-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65269 PE IP Address : 152.164.152.169 CE Address : 152.164.152.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31417567) | 1000Base-SX (850nm, Multi Mode Fiber) (31417567) | Ethernet | COX (3141756725704801) | 03/27/2020 (3141756725704801) | 04/21/2020 (3141756725704801) | 04/15/2020 (3141756725704801) | 05/07/2020 (VFORCE) (31417567) |  | DEMARCDET - 1st floor telephone room of Nokia 7210 port 6 its extended to port 15 of the demarc patch panel |  | DANNY STEWART 1-623-707-0837 danny_h_stewart@optum.com | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 05/07/2020(Private IP - PIP) 05/07/2020(WAN Analysis Reporting) 05/07/2020(Access) |  |  | 05/18/2020 (31417566) 05/14/2020 (31417567) | 06/18/2020 06/24/2020 | 05/07/2020 |  | Completed | N (31417566) N (31417568) N (31417567) | U0101953 |  |  | NSPE0013626874
Completed | UNY24-06-IM | 1 Penn Plz New York, NY 10119-0002 US | 100 MBPS (31429446) | 06/09/2020: Order Completed on Jun 9, 2020 | 202406077 | UNITED HEALTHCARE | Private IP - PIP (31429445) WAN Analysis Reporting (31429447) Access (31429446) | 31429445 31429447 31429446 | 50 MBPS (31429445) |  | 94778915 (Private IP (PIP)) 94778917 (WAN Analysis Reporting) 94778919 (Access) | C1104661/ADD (31429445) E4057222/ADD (31429446) |  | 6115477 | 30000 | PVC ID : 6115477 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64782 PE IP Address : 208.219.135.229 CE Address : 208.219.135.230 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (31429446) | Ethernet | [8 empty] | Alejandro Pierre 1-212-216-6608 alejandro_pierre@optum.com | Melissa Chapman | melissa_r_chapman@optum.com | 1-763-744-2114 | 06/09/2020(Private IP - PIP) 06/09/2020(WAN Analysis Reporting) 06/09/2020(Access) |  |  | 04/14/2020 (31429445) 04/10/2020 (31429446) | 05/04/2020 05/08/2020 | 06/09/2020 |  | Completed | N (31429445) N (31429447) N (31429446) | U0101953 |  |  | NSPE0013628387
Completed | MA095 | 100 HANCOCK ST QUINCY, MA 02171-1745 US | 50 MBPS (31507182) | 05/07/2020: FOC date 5/11. | 202433081 | MA095 | Private IP - PIP (31507179) WAN Analysis Reporting (31507183) Access (31507182) | 31507179 31507183 31507182 | 20 MBPS (31507179) |  | 1257327077 (Private IP (PIP)) 1257327079 (WAN Analysis Reporting) 1257327073 (Access) | C4022411/ADD (31507179) E4057648/ADD (31507182) | 95.KFGS.011460..NE (3150718274714801) | 6117412 | 13000 | PVC ID : 6117412 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65394 PE IP Address : 159.24.149.97 CE Address : 159.24.149.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31507182) | 1000Base-SX (850nm, Multi Mode Fiber) (31507182) | Ethernet | VERIZON (3150718274714801) | 04/03/2020 (3150718274714801) | 05/11/2020 (3150718274714801) | 05/14/2020 (3150718274714801) |  |  | DEMARCDET - 2nd flr lan room/rack mtd. |  | FRANK CALNAN 1-617-447-0372 frank.calnan@optum.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 05/14/2020(Private IP - PIP) 05/14/2020(WAN Analysis Reporting) 05/14/2020(Access) |  |  | 05/22/2020 (31507179) 05/20/2020 (31507182) | 05/20/2020 05/26/2020 | 05/14/2020 |  | Completed | N (31507179) N (31507183) N (31507182) | U0101953 |  |  | NSPE0013638821
Completed | C1328-05-IJ | 9197 S PEORIA ST ENGLEWOOD, CO 80112-5833 US | 1 GBPS | 04/07/2020: Order Completed on Apr 7, 2020 | 202442619 | C1328-05-IJ Teletech Englewood, CO | Private IP - PIP (31458749) Access | 31458749 | 1 GBPS (31458749) |  | 145009664 (Private IP (PIP)) 145009602 | C0106575/NONE (31458749) |  | 5818888 | 550000 | PVC ID : 5818888 VPN Name : UHG-ECC Router Name : PHN19E01 VRF Name : V794184:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65431 PE IP Address : 152.192.93.201 CE Address : 152.192.93.202 QoS - Egress Profile: C13 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | KEVIN WALL 1-303-397-8408 kevinwall@teletech.com | William Goss | william_Goss@optum.com | 1-763-744-1528 | 04/07/2020(Private IP |  |  | 03/27/2020 (31458749) | 04/07/2020 | 04/07/2020 |  |  | N (31458749) N | U0101953 |  |  | NSPE0013641980
Completed | TX057 | 12668 Silicon Dr San Antonio, TX 78249-3411 US | 100 MBPS (31486797) | 05/26/2020: Order Completed on May 26, 2020 | 202466185 | ENT TX057 SAN ANTONIO | Private IP - PIP (31486796) WAN Analysis Reporting (31486798) Access (31486797) | 31486796 31486798 31486797 | 50 MBPS (31486796) |  | 1258263791 (Private IP (PIP)) 1258263803 (WAN Analysis Reporting) 1258263785 (Access) | C1104967/ADD (31486796) E4057554/ADD (31486797) | 21.L1XX.990219..CHTR (3148679722100501) | 6116988 | 30000 | PVC ID : 6116988 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64520 PE IP Address : 152.164.197.213 CE Address : 152.164.197.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31486797) | 1000Base-SX (850nm, Multi Mode Fiber) (31486797) | Ethernet | TIME WARNER CABLE (3148679722100501) | 04/28/2020 (3148679722100501) | 06/15/2020 (3148679722100501) | 05/22/2020 (3148679722100501) | 05/26/2020 (VFORCE) (31486797) | 05/26/2020 (VFORCE) (31486797) | DEMARCDET - 1st flr suite 112 CPE is in the server rm in the rack its in the 4th rack unit wall mounted |  | David Gamez 1-210-365-0715 david.gamez@optum.com | Sushil Gautam | sushil_gautam@uhc.com | 91-124-309-5736 | 05/26/2020(Private IP - PIP) 05/26/2020(WAN Analysis Reporting) 05/26/2020(Access) |  |  | 06/24/2020 (31486796) 06/22/2020 (31486797) | 09/15/2020 09/21/2020 | 05/26/2020 |  | Completed | N (31486796) N (31486798) N (31486797) | U0101953 |  |  | NSPE0013648296
Completed | C1653 | 119 W Tyler St ste 248 Longview, TX 75601-6358 US | 50 MBPS (31496192) | 04/28/2020: Order Completed on Apr 28, 2020 | 202474893 | C1653 | Private IP - PIP (31496191) WAN Analysis Reporting (31496193) Access (31496192) | 31496191 31496193 31496192 | 10 MBPS (31496191) |  | 94779833 (Private IP (PIP)) 94779838 (WAN Analysis Reporting) 94779831 (Access) | C4022393/ADD (31496191) E4057594/ADD (31496192) |  | 6117195 |  | PVC ID : 6117195 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65446 PE IP Address : 159.24.158.209 CE Address : 159.24.158.210 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31496192) | Ethernet |  |  |  |  | 04/14/2020 (CCP) (31496191) 04/14/2020 (CCP) (31496192) | 04/14/2020 (CCP) (31496191) 04/14/2020 (CCP) (31496192) |  |  | Mike Truemner 1-903-323-4513 mtruemner@networkip.net | EDWARD JONES | edward.jones@optum.com | 1-952-219-4357 | 04/28/2020(Private IP - PIP) 04/28/2020(WAN Analysis Reporting) 04/28/2020(Access) |  |  | 05/11/2020 (31496191) 05/07/2020 (31496192) | 05/07/2020 05/13/2020 | 04/28/2020 |  | Completed | N (31496191) N (31496193) N (31496192) | U0101953 |  |  | NSPE0013649419
Completed | CO162 | 6547 S Racine Cir ste 300 Englewood, CO 80111-6448 US | 50 MBPS (31530909) | 07/09/2020: Order Completed on Jul 9, 2020 | 202502329 | CO162 | Private IP - PIP (31530908) WAN Analysis Reporting (31530910) Access (31530909) | 31530908 31530910 31530909 | 10 MBPS (31530908) |  | 94782186 (Private IP (PIP)) 94782188 (WAN Analysis Reporting) 94782190 (Access) | C4022447/ADD (31530908) E4057796/ADD (31530909) | 60.KGGS.017324..CBCL.. (3153090975081201) | 6117940 | 5500 | PVC ID : 6117940 VPN Name : UnitedHealthGroup Router Name : DNJXE01 VRF Name : V469377-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64655 PE IP Address : 152.176.45.77 CE Address : 152.176.45.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31530909) | 1000Base-SX (850nm, Multi Mode Fiber) (31530909) | Ethernet | COMCAST (3153090975081201) | 04/07/2020 (3153090975081201) | 07/02/2020 (3153090975081201) | 06/19/2020 (3153090975081201) | 07/09/2020 (VFORCE) (31530909) |  | DEMARCDET - 1st flr main IT closet wall mounted on SE wall halfway up the wall labeled with comcast clli and uni |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-990-179-8210 | 07/09/2020(Private IP - PIP) 07/09/2020(WAN Analysis Reporting) 07/09/2020(Access) |  |  | 07/16/2020 (31530908) 07/14/2020 (31530909) | 08/14/2020 08/20/2020 | 07/09/2020 |  | Completed | N (31530908) N (31530910) N (31530909) | U0101953 |  |  | NSPE0013662297
Completed | UHG Phoenix Az | 4425 E Cotton Center Blvd Phoenix, AZ 85040-8854 US | 500 MBPS (31542575) | 04/19/2020: Order Completed on Apr 19, 2020 | 202514555 | UHG Phoenix Az - 4425 East Cotton | Private IP - PIP (31542574) WAN Analysis Reporting (31542576) Access (31542575) | 31542574 31542576 31542575 | 200 MBPS (31542574) |  | 94783568 (Private IP (PIP)) 94783571 (WAN Analysis Reporting) 94783566 (Access) | C5009789/ADD (31542574) E5025166/ADD (31542575) | 19.KXGS.508711..MS (3154257514035001) | 6118219 | 140000 | PVC ID : 6118219 VPN Name : UnitedHealthGroup Router Name : WIT9E01 VRF Name : V603341:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65132 PE IP Address : 152.177.12.29 CE Address : 152.177.12.30 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31542575) | 1000Base-SX (850nm, Multi Mode Fiber) (31542575) | Ethernet | CENTURYLINK (3154257514035001) | 04/08/2020 (3154257514035001) | 04/20/2020 (3154257514035001) | 04/15/2020 (3154257514035001) | 04/17/2020 (VFORCE) (31542575) | 04/17/2020 (VFORCE) (31542575) | DEMARCADDR - X DEMARCDET - X |  | EDDIE NORWOOD 1-602-462-7394 eddie_norwood@optum.com | JASON SALAPING | jason_salaping@gmail.com | 632-462-2446 | 04/17/2020(Private IP - PIP) 04/17/2020(WAN Analysis Reporting) 04/17/2020(Access) |  |  | 04/29/2020 (31542574) 04/27/2020 (31542575) | 05/18/2020 05/22/2020 | 04/19/2020 |  | Completed | N (31542574) N (31542576) N (31542575) | U0101953 |  |  | NSPE0013666069
Completed | AEGIS | 11830 Webb Chapel Rd Dallas, TX 75234-2790 US | 100 MBPS (31574135) | 05/07/2020: Cross connect to Data Center complete - RR 101 C-08-21 ports 43-44. Pending testing and closing of order. | 202562055 | AEGIS | Access (31574135) Private IP - PIP (31574134) WAN Analysis Reporting (31574136) | 31574135 31574134 31574136 | 50 MBPS (31574134) |  | 94784690 (Access) 94784684 (Private IP (PIP)) 94784686 (WAN Analysis Reporting) | E4057948/ADD (31574135) C1105306/ADD (31574134) |  | 6118616 | 60000 | PVC ID : 6118616 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65509 PE IP Address : 152.181.213.193 CE Address : 152.181.213.194 QoS - Egress Profile: R12 |  | 100Base-FX (1310nm, Single Mode Fiber) (31574135) | Ethernet | [8 empty] | Clark Willms 1-305-606-9214 clark.willms@sitel.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 05/11/2020(Access) 05/11/2020(Private IP - PIP) 05/11/2020(WAN Analysis Reporting) |  |  | 05/11/2020 (31574135) 05/13/2020 (31574134) | 06/01/2020 06/05/2020 | 05/11/2020 |  | Completed | N (31574135) N (31574134) N (31574136) | U0101953 |  |  | NSPE0013681051
Completed | OH018-02-IJ | 250 Progressive Way bldg 3 Westerville, OH 43082-9615 US | 1 GBPS (31601389) | 02/11/2021: Beas dispatch is scheduled for 2/12 between 1-5pm. | 202590991 | OH018-02-IJ | Private IP - PIP (31601388) WAN Analysis Reporting (31601390) Access (31601389) | 31601388 31601390 31601389 | 500 MBPS (31601388) |  | 94784997 (Private IP (PIP)) 94785400 (WAN Analysis Reporting) 94784994 (Access) | C0187620/ADD (31601388) E5025252/ADD (31601389) | 61.L1XX.996627..CHTR (3160138917116801) | 6118991 | 350000 | PVC ID : 6118991 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64631 PE IP Address : 68.136.250.57 CE Address : 68.136.250.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31601389) | 1000Base-SX (850nm, Multi Mode Fiber) (31601389) | Ethernet | TIME WARNER CABLE (3160138917116801) | 01/12/2021 (3160138917116801) | 02/10/2021 (3160138917116801) | 02/10/2021 (3160138917116801) | 02/12/2021 (VFORCE) (31601389) | 02/12/2021 (VFORCE) (31601389) | DEMARCDET - 1st flr server rack 7th rack |  | Ernest Sink 1-614-212-8902 ernest.sink@optum.com | Aidyl bert simbulan | aidyl_simbulan@optum.com | 632-462-2465 | 02/12/2021(Private IP - PIP) 02/12/2021(WAN Analysis Reporting) 02/12/2021(Access) |  |  | 02/19/2021 (31601388) 02/17/2021 (31601389) | 06/02/2021 06/08/2021 | 02/12/2021 |  | Scheduled | N (31601388) N (31601390) N (31601389) | U0101953 | Jeopardy Notification 1 (01/11/2021) |  | NSPE0013697813
Completed | IN023-02-IJ | 150 W Market St ste 300 Indianapolis, IN 46204-2809 US | 100 MBPS (31603563) | 09/24/2020: Order Completed on Sep 24, 2020 | 202593123 | IN023-02-IJ Indianapolis, IN | Private IP - PIP (31603562) WAN Analysis Reporting (31603564) Access (31603563) | 31603562 31603564 31603563 | 10 MBPS (31603562) |  | 94785243 (Private IP (PIP)) 94785239 (WAN Analysis Reporting) 94785241 (Access) | C1105429/ADD (31603562) E4058039/ADD (31603563) | 31.L1XX.990884..CHTR (3160356312468001) | 6119031 | 5500 | PVC ID : 6119031 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64784 PE IP Address : 152.183.231.61 CE Address : 152.183.231.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31603563) | 1000Base-SX (850nm, Multi Mode Fiber) (31603563) | Ethernet | TIME WARNER CABLE (3160356312468001) | 06/02/2020 (3160356312468001) | 09/25/2020 (3160356312468001) | 09/21/2020 (3160356312468001) | 09/24/2020 (VFORCE) (31603563) | 09/24/2020 (VFORCE) (31603563) | DEMARCDET - Customer Server Room In Suite Wall Mount 3rd floor MTU is in the basement Security will provide access 3rd floor is fed from basement via a NID in the 4th floor electrical room |  | Jerry Wolf 1-317-610-5221 jerry.wolf@optum.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 09/24/2020(Private IP - PIP) 09/24/2020(WAN Analysis Reporting) 09/24/2020(Access) |  |  | 10/06/2020 (31603562) 10/02/2020 (31603563) | 12/15/2020 12/21/2020 | 09/24/2020 |  | Completed | N (31603562) N (31603564) N (31603563) | U0101953 |  |  | NSPE0013698822
Completed | KS016-02-IJ Lenexa | 15529 College Blvd Lenexa, KS 66219-1351 US | 400 MBPS (31609770) | 07/13/2020: Order Completed on Jul 13, 2020 | 202598029 | KS016-02-IJ Lenexa | Access (31609770) Private IP - PIP (31609769) WAN Analysis Reporting (31609771) | 31609770 31609769 31609771 | 150 MBPS (31609769) |  | 94784872 (Access) 94784870 (Private IP (PIP)) 94784876 (WAN Analysis Reporting) | E5025284/ADD (31609770) C5009831/ADD (31609769) | 74/KRGN/063828//EVT/ (3160977016751202) | 6119156 | 90000 | PVC ID : 6119156 VPN Name : UnitedHealthGroup Router Name : SC99E01 VRF Name : Vf03180:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64635 PE IP Address : 152.161.181.205 CE Address : 152.161.181.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31609770) | 1000Base-SX (850nm, Multi Mode Fiber) (31609770) | Ethernet | MCI (3160977016751202) | 05/28/2020 (3160977016751202) | 07/07/2020 (3160977016751202) | 07/10/2020 (3160977016751202) | 07/13/2020 (VFORCE) (31609770) | 07/13/2020 (VFORCE) (31609770) | DEMARCDET - BLDG MAIN FLR MAIN RM MPOE |  | Evan Brooks 1-913-242-5729 evan.brooks@optum.com | Ed Kimuel Ramos | kimuel_ramos@optum.com | 632-588-5397 | 07/13/2020(Access) 07/13/2020(Private IP - PIP) 07/13/2020(WAN Analysis Reporting) |  |  | 07/14/2020 (31609770) 07/16/2020 (31609769) | 07/09/2020 07/15/2020 | 07/13/2020 |  | Scheduled | N (31609770) N (31609769) N (31609771) | U0101953 |  |  | NSPE0013700574
Completed | IL090 | 2655 Warrenville Rd ste 500 Downers Grove, IL 60515-5646 US | 1 GBPS (31609862) | 06/15/2020: Order Completed on Jun 15, 2020 | 202598539 | IL090 | Private IP - PIP (31609861) WAN Analysis Reporting (31609863) Access (31609862) | 31609861 31609863 31609862 | 100 MBPS (31609861) |  | 94784860 (Private IP (PIP)) 94784866 (WAN Analysis Reporting) 94784862 (Access) | C0187727/ADD (31609861) E5025286/ADD (31609862) | 183495-ENET-CCF (3160986273737301) | 6119150 | 70000 | PVC ID : 6119150 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64948 PE IP Address : 152.164.240.69 CE Address : 152.164.240.70 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (31609862) | 1000Base-LX (1310nm Single Mode Fiber) (31609862) | Ethernet | LIGHT TOWER (3160986273737301) | 04/15/2020 (3160986273737301) | 06/02/2020 (3160986273737301) | 06/11/2020 (3160986273737301) | 06/15/2020 (VFORCE) (31609862) | 06/15/2020 (VFORCE) (31609862) | DEMARCDET - 5th floor MDF. Rack mounted RU38. Tagged with order number and circuit ID. Handoff LC SMF. |  | Ben Lawhead 1-630-324-9746 Ben.Lawhead@optum.com | ROBERT BENSON | robert_a_benson@optum.com | 1-763-744-2077 | 06/15/2020(Private IP - PIP) 06/15/2020(WAN Analysis Reporting) 06/15/2020(Access) |  |  | 06/11/2020 (31609861) 06/09/2020 (31609862) | 05/26/2020 06/01/2020 | 06/15/2020 |  | Completed | N (31609861) N (31609863) N (31609862) | U0101953 |  |  | NSPE0013699145
Completed | FL070 | 7159 Corklan Dr Jacksonville, FL 32258-4548 US | 200 MBPS (31609976) | 08/27/2020: Order Completed on Aug 19, 2020 | 202597259 | FL070 | Private IP - PIP (31609975) WAN Analysis Reporting (31609977) Access (31609976) | 31609975 31609977 31609976 | 200 MBPS (31609975) |  | 94783979 (Private IP (PIP)) 94783982 (WAN Analysis Reporting) 94783977 (Access) | C5009830/ADD (31609975) E5025285/ADD (31609976) | FL/KXFN/315130/LVLC (3160997673736501) | 6119144 | 110000 | PVC ID : 6119144 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65031 PE IP Address : 152.181.90.61 CE Address : 152.181.90.62 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (31609976) | 1000Base-LX (1310nm Single Mode Fiber) (31609976) | Ethernet | LEVEL 3 (3160997673736501) | 07/09/2020 (3160997673736501) | 08/14/2020 (3160997673736501) | 08/17/2020 (3160997673736501) | 08/19/2020 (VFORCE) (31609976) | 08/19/2020 (VFORCE) (31609976) | DEMARCADDR - X DEMARCDET - X |  | Richard Gross 1-904-423-4223 rick.gross@optum.com | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 08/19/2020(Private IP - PIP) 08/19/2020(WAN Analysis Reporting) 08/19/2020(Access) |  |  | 08/27/2020 (31609975) 08/25/2020 (31609976) | 08/19/2020 08/25/2020 | 08/19/2020 |  | Completed | N (31609975) N (31609977) N (31609976) | U0101953 |  |  | NSPE0013699146
Completed | FL439 | 5575 S Semoran Blvd Orlando, FL 32822-1747 US | 50 MBPS (31614839) | 07/06/2020: Order Completed on Jul 6, 2020 | 202601485 | FL439 | Private IP - PIP (31614838) WAN Analysis Reporting (31614840) Access (31614839) | 31614838 31614840 31614839 | 10 MBPS (31614838) |  | 94785480 (Private IP (PIP)) 94785483 (WAN Analysis Reporting) 94785477 (Access) | C4022537/ADD (31614838) E4058096/ADD (31614839) | 31/KGFN/109479/TWCS (3161483975586601) | 6119219 | 5500 | PVC ID : 6119219 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65146 PE IP Address : 152.177.39.221 CE Address : 152.177.39.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31614839) | 1000Base-SX (850nm, Multi Mode Fiber) (31614839) | Ethernet | LEVEL 3 (3161483975586601) | 06/02/2020 (3161483975586601) | 07/16/2020 (3161483975586601) | 07/01/2020 (3161483975586601) | 07/06/2020 (VFORCE) (31614839) |  | DEMARCDET - Raiser room in the back of building north east corner , cisco 920 port 4 MMF SFP tagged with circut id |  | Christian T Campbell 1-813-462-3162 campbell1@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 | 07/06/2020(Private IP - PIP) 07/06/2020(WAN Analysis Reporting) 07/06/2020(Access) |  |  | 07/27/2020 (31614838) 07/23/2020 (31614839) | 07/07/2020 07/13/2020 | 07/06/2020 |  | Completed | N (31614838) N (31614840) N (31614839) | U0101953 |  |  | NSPE0013815995
Completed | FL083-01-IM | 260 Wekiva Springs Rd Longwood, FL 32779-5947 US | 50 MBPS (31621602) | 06/12/2020: Order Completed on Jun 12, 2020 | 202603777 | UNITED HEALTH GROUP | Private IP - PIP (31621601) WAN Analysis Reporting (31621603) Access (31621602) | 31621601 31621603 31621602 | 10 MBPS (31621601) |  | 94785631 (Private IP (PIP)) 94785633 (WAN Analysis Reporting) 94785637 (Access) | C4022544/ADD (31621601) E4058120/ADD (31621602) | 25.KXGS.510658..UFLG (3162160229896601) | 6119429 | 5500 | PVC ID : 6119429 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65182 PE IP Address : 152.183.246.9 CE Address : 152.183.246.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31621602) | 1000Base-SX (850nm, Multi Mode Fiber) (31621602) | Ethernet | CENTURYLINK (3162160229896601) | 04/16/2020 (3162160229896601) | 06/11/2020 (3162160229896601) | 06/05/2020 (3162160229896601) | 06/11/2020 (VFORCE) (31621602) |  | DEMARCADDR - X DEMARCDET - X |  | Kayla Martin 1-407-865-5909 kamartin@wellmed.net | Jealine Teodoro | jealine.teodoro@optum.com | 632-588-5307 | 06/12/2020(Private IP - PIP) 06/12/2020(WAN Analysis Reporting) 06/12/2020(Access) |  |  | 06/22/2020 (31621601) 06/18/2020 (31621602) | 05/26/2020 06/01/2020 | 06/12/2020 |  | Completed | N (31621601) N (31621603) N (31621602) | U0101953 |  |  | NSPE0013702263
Completed | FL01504IM | 1627 Us Highway 1 Sebastian, FL 32958-3899 US | 50 MBPS (31623551) | 11/05/2020: Order Completed on Nov 5, 2020 | 202611177 | UNITED HEALTH GROUP | WAN Analysis Reporting (31623552) Access (31623551) Private IP - PIP (31623550) | 31623552 31623551 31623550 | 10 MBPS (31623550) |  | 94785695 (WAN Analysis Reporting) 94785699 (Access) 94785693 (Private IP (PIP)) | C4022546/ADD (31623550) E4058124/ADD (31623551) | 38.KFGS.030806..CBCL.. (3162355129896601) | 6119452 | 5500 | PVC ID : 6119452 VPN Name : UnitedHealthGroup Router Name : 94J9E02 VRF Name : Vh50351:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65028 PE IP Address : 68.136.222.101 CE Address : 68.136.222.102 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31623551) | 1000Base-SX (850nm, Multi Mode Fiber) (31623551) | Ethernet | COMCAST (3162355129896601) | 04/16/2020 (3162355129896601) | 09/11/2020 (3162355129896601) | 11/04/2020 (3162355129896601) | 11/05/2020 (VFORCE) (31623551) | 11/05/2020 (VFORCE) (31623551) | DEMARCDET - 1st floor server closet rack mounted in the lower middle of the rack labeled comcast tagged with CLLI |  | Fernando Mata 1-772-581-9551 fmata@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 11/05/2020(WAN Analysis Reporting) 11/05/2020(Access) 11/05/2020(Private IP - PIP) |  |  | 09/22/2020 (31623550) 09/18/2020 (31623551) | 09/16/2020 09/10/2020 | 11/05/2020 |  | Completed | N (31623552) N (31623551) N (31623550) | U0101953 |  |  | NSPE0013705155
Completed | FL212 | 809 S Orlando Ave Winter Park, FL 32789-7101 US | 50 MBPS (31624788) | 05/18/2020: Order Completed on May 18, 2020 | 202611441 | FL212-02-IM | Private IP - PIP (31624787) WAN Analysis Reporting (31624789) Access (31624788) | 31624787 31624789 31624788 | 10 MBPS (31624787) |  | 94785713 (Private IP (PIP)) 94785716 (WAN Analysis Reporting) 94785710 (Access) | C4022550/ADD (31624787) E4058129/ADD (31624788) | 25.KXGS.510730..UFLG (3162478823986901) | 6119469 | 5500 | PVC ID : 6119469 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65271 PE IP Address : 152.176.12.169 CE Address : 152.176.12.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31624788) | 1000Base-SX (850nm, Multi Mode Fiber) (31624788) | Ethernet | CENTURYLINK (3162478823986901) | 04/16/2020 (3162478823986901) | 04/28/2020 (3162478823986901) | 04/23/2020 (3162478823986901) | 05/18/2020 (VFORCE) (31624788) |  | DEMARCDET - wall mounted in main telco rear of building |  | Brittany Malkey 1-618-367-1771 harish_kandpal@optum.com | Sean Olivete | marion_olivete@optum.com | 1-763-744-2114 | 05/18/2020(Private IP - PIP) 05/18/2020(WAN Analysis Reporting) 05/18/2020(Access) |  |  | 05/15/2020 (31624787) 05/13/2020 (31624788) | 06/17/2020 06/23/2020 | 05/18/2020 |  | Completed | N (31624787) N (31624789) N (31624788) | U0101953 |  |  | NSPE0013705279
Completed | FL016-05-IM | 513 Nw Lake Whitney Pl Port St Lucie, FL 34986-1618 US | 50 MBPS (31631314) | 08/13/2020: Beas installed scheduled for 8/17 between 1-5. | 202612981 | UNITED HEALTH GROUP | Access (31631314) Private IP - PIP (31631313) WAN Analysis Reporting (31631315) | 31631314 31631313 31631315 | 10 MBPS (31631313) |  | 94785826 (Access) 94785820 (Private IP (PIP)) 94785822 (WAN Analysis Reporting) | E4058157/ADD (31631314) C4022556/ADD (31631313) | 38.KGGS.024452..CBCL.. (3163131433842701) | 6119564 | 5500 | PVC ID : 6119564 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65091 PE IP Address : 152.177.80.237 CE Address : 152.177.80.238 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31631314) | 1000Base-SX (850nm, Multi Mode Fiber) (31631314) | Ethernet | COMCAST (3163131433842701) | 04/17/2020 (3163131433842701) | 07/16/2020 (3163131433842701) | 07/22/2020 (3163131433842701) | 08/17/2020 (VFORCE) (31631314) | 08/14/2020 (VFORCE) (31631314) | DEMARCADDR - 1 DEMARCDET - 1st FL IT Room Wall mounted in Middle of the Backboard Tagged and LabeleD |  | Joselyn Barrientos 1-772-240-7017 jbarrientos@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 08/14/2020(Access) 08/14/2020(Private IP - PIP) 08/14/2020(WAN Analysis Reporting) |  |  | 08/19/2020 (31631314) 08/21/2020 (31631313) | 09/23/2020 09/29/2020 | 08/14/2020 |  | Completed Approved | N (31631314) N (31631313) N (31631315) | U0101953 |  |  | NSPE0013705711
Completed | FL213-02-IM | 8380 Baymeadows Rd Jacksonville, FL 32256-4446 US | 50 MBPS (31633364) | 08/06/2020: Beas installed however our equipment still not seeing traffic coming from LEC's NID. Not able to ping across through their network. LEC is checking circuit. | 202618903 | FL213-02-IM | Private IP - PIP (31633363) WAN Analysis Reporting (31633365) Access (31633364) | 31633363 31633365 31633364 | 10 MBPS (31633363) |  | 94785849 (Private IP (PIP)) 94785851 (WAN Analysis Reporting) 94785855 (Access) | C4022563/ADD (31633363) E4058165/ADD (31633364) | 36.KGGS.010770..CBCL.. (3163336423959001) | 6119602 | 5500 | PVC ID : 6119602 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65196 PE IP Address : 152.177.157.21 CE Address : 152.177.157.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31633364) | 1000Base-SX (850nm, Multi Mode Fiber) (31633364) | Ethernet | COMCAST (3163336423959001) | 05/06/2020 (3163336423959001) | 08/12/2020 (3163336423959001) | 07/23/2020 (3163336423959001) | 08/12/2020 (VFORCE) (31633364) | 08/12/2020 (VFORCE) (31633364) | DEMARCADDR - 1 DEMARCDET - 1ST FLR COMM ROOM, WALL MOUNTED, LABELED W CLLI NOC NAME AND ADDRESS |  | Julie Frady 1-904-831-3543 jfrady@homecardimensions.com | Sean Olivete | marion_olivete@optum.com | 1-763-744-2114 | 08/12/2020(Private IP - PIP) 08/12/2020(WAN Analysis Reporting) 08/12/2020(Access) |  |  | 08/21/2020 (31633363) 08/19/2020 (31633364) | 09/10/2020 09/16/2020 | 08/12/2020 |  | Completed | N (31633363) N (31633365) N (31633364) | U0101953 |  |  | NSPE0013708018
Completed | FL024-05-IM | 4740 Exploration Ave Lakeland, FL 33812-3319 US | 50 MBPS (31645666) | 05/20/2020: Order Completed on May 19, 2020 | 202621959 | UNITED HEALTH GROUP | Private IP - PIP (31645665) WAN Analysis Reporting (31645667) Access (31645666) | 31645665 31645667 31645666 | 10 MBPS (31645665) |  | 94785388 (Private IP (PIP)) 94785391 (WAN Analysis Reporting) 94785386 (Access) | C4022582/ADD (31645665) E4058208/ADD (31645666) | 65/KRGN/362635//FTNC/ (3164566629896501) | 6119842 | 5500 | PVC ID : 6119842 VPN Name : UnitedHealthGroup Router Name : TAM29E02 VRF Name : Vc70465:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64897 PE IP Address : 152.176.254.205 CE Address : 152.176.254.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31645666) | 1000Base-SX (850nm, Multi Mode Fiber) (31645666) | Ethernet | FRONTIER (3164566629896501) | 05/07/2020 (3164566629896501) | 06/11/2020 (3164566629896501) | 05/13/2020 (3164566629896501) | 05/19/2020 (VFORCE) (31645666) | 05/19/2020 (VFORCE) (31645666) | DEMARCDET - 1st floor telcom rm wall, SL01#SHLF01 |  | Rachel hoffman 91-863-666-9020 rhoffman@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 05/19/2020(Private IP - PIP) 05/19/2020(WAN Analysis Reporting) 05/19/2020(Access) |  |  | 06/22/2020 (31645665) 06/18/2020 (31645666) | 06/18/2020 06/24/2020 | 05/19/2020 |  | Completed | N (31645665) N (31645667) N (31645666) | U0101953 |  |  | NSPE0013709008
Completed | TX213-04-IM | 2821 LACKLAND RD FORT WORTH, TX 76116-4120 US | 50 MBPS (31647096) | 11/11/2020: Order Completed on Nov 11, 2020 | 202638721 | UNITED HEALTH GROUP | Access (31647096) Private IP - PIP (31647095) WAN Analysis Reporting (31647097) | 31647096 31647095 31647097 | 10 MBPS (31647095) |  | 1264078669 (Access) 1264078673 (Private IP (PIP)) 1264078675 (WAN Analysis Reporting) | E4058212/ADD (31647096) C4022584/ADD (31647095) | 81.L1XX.911198..CHTR (3164709629896601) | 6119878 | 5500 | PVC ID : 6119878 VPN Name : UnitedHealthGroup Router Name : RCN3E02 VRF Name : Vh26648-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65250 PE IP Address : 152.164.122.249 CE Address : 152.164.122.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31647096) | 1000Base-SX (850nm, Multi Mode Fiber) (31647096) | Ethernet | CHARTER (3164709629896601) | 09/30/2020 (3164709629896601) | 11/13/2020 (3164709629896601) | 11/06/2020 (3164709629896601) | 11/11/2020 (VFORCE) (31647096) | 11/11/2020 (VFORCE) (31647096) | DEMARCDET - 1st FLR SUIT 101 SERVER ROOM WALL MTD |  | Carol Phillips 1-469-904-3563 cphillips2@wellmed.net | SEAN OLIVETE | marion_olivete@optum.com | 1-469-776-6207 | 11/11/2020(Access) 11/11/2020(Private IP - PIP) 11/11/2020(WAN Analysis Reporting) |  |  | 11/20/2020 (31647096) 11/24/2020 (31647095) | 11/12/2020 11/18/2020 | 11/11/2020 |  | Completed | N (31647096) N (31647095) N (31647097) | U0101953 |  |  | NSPE0013714081
Completed | FL03908IM | 415 W 49th St Hialeah, FL 33012-3637 US | 50 MBPS (31647254) | 09/29/2020: Order Completed on Sep 28, 2020 | 202638943 | UNITED HEALTH GROUP | Private IP - PIP (31647253) WAN Analysis Reporting (31647255) Access (31647254) | 31647253 31647255 31647254 | 10 MBPS (31647253) |  | 94786261 (Private IP (PIP)) 94786266 (WAN Analysis Reporting) 94786259 (Access) | C4022587/ADD (31647253) E4058217/ADD (31647254) | 38.KGGS.024814..CBCL.. (3164725492075801) | 6119886 | 5500 | PVC ID : 6119886 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65274 PE IP Address : 147.225.221.109 CE Address : 147.225.221.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31647254) | 1000Base-SX (850nm, Multi Mode Fiber) (31647254) | Ethernet | COMCAST (3164725492075801) | 07/30/2020 (3164725492075801) | 11/10/2020 (3164725492075801) | 09/23/2020 (3164725492075801) | 09/25/2020 (VFORCE) (31647254) | 09/25/2020 (VFORCE) (31647254) | DEMARCADDR - 1 DEMARCDET - 1st flr mdf rack mounted labeled with comcast/verizon with circuit id |  | Harish Kandpal 91-124-309-5613 harish_kandpal@optum.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 09/28/2020(Private IP - PIP) 09/28/2020(WAN Analysis Reporting) 09/28/2020(Access) |  |  | 11/19/2020 (31647253) 11/17/2020 (31647254) | 09/10/2020 09/16/2020 | 09/28/2020 |  | Completed | N (31647253) N (31647255) N (31647254) | U0101953 |  |  | NSPE0013714134
Completed | TX16404IM | 1143 E Sinton St Sinton, TX 78387-2928 US | 50 MBPS (31653886) | 08/13/2020: Beas install scheduled for 8/17. | 202640221 | UNITED HEALTH GROUP | Private IP - PIP (31653885) WAN Analysis Reporting (31653887) Access (31653886) | 31653885 31653887 31653886 | 10 MBPS (31653885) |  | 94787069 (Private IP (PIP)) 94787071 (WAN Analysis Reporting) 94787067 (Access) | C4022594/ADD (31653885) E4058236/ADD (31653886) | 34/KRGN/614194//SW (3165388629896601) | 6119994 | 5500 | PVC ID : 6119994 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65275 PE IP Address : 152.177.173.29 CE Address : 152.177.173.30 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31653886) | 1000Base-SX (850nm, Multi Mode Fiber) (31653886) | Ethernet | ATT (3165388629896601) | 05/06/2020 (3165388629896601) | 06/11/2020 (3165388629896601) | 06/12/2020 (3165388629896601) | 08/17/2020 (VFORCE) (31653886) |  | DEMARCADDR - . DEMARCDET - . |  | Harish C Kandpal 91-124-309-5613 harish_kandpal@optum.com | Sean Olivete | marion_olivete@optum.com | 1-763-744-2114 | 08/17/2020(Private IP - PIP) 08/17/2020(WAN Analysis Reporting) 08/17/2020(Access) |  |  | 08/24/2020 (31653885) 08/20/2020 (31653886) | 09/24/2020 09/30/2020 | 08/17/2020 |  | Completed | N (31653885) N (31653887) N (31653886) | U0101953 |  |  | NSPE0013714426
Completed | FL158-04-IM | 10151 DEERWOOD PARK BLVD BLDG 300 JACKSONVILLE, FL 32256-0566 US | 50 MBPS (31654885) | 08/27/2020: Order Completed on Aug 24, 2020 | 202645551 | UNITED HEALTH GROUP | Access (31654885) Private IP - PIP (31654884) WAN Analysis Reporting (31654886) | 31654885 31654884 31654886 | 10 MBPS (31654884) |  | 1264220517 (Access) 1264220521 (Private IP (PIP)) 1264220523 (WAN Analysis Reporting) | E4058244/ADD (31654885) C4022599/ADD (31654884) | FL/KXFN/319013/LVLC (3165488575860501) | 6120018 | 5500 | PVC ID : 6120018 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65180 PE IP Address : 152.177.200.69 CE Address : 152.177.200.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31654885) | 1000Base-SX (850nm, Multi Mode Fiber) (31654885) | Ethernet | LEVEL 3 (3165488575860501) | 07/31/2020 (3165488575860501) | 08/17/2020 (3165488575860501) | 08/13/2020 (3165488575860501) | 08/24/2020 (VFORCE) (31654885) | 08/24/2020 (VFORCE) (31654885) | DEMARCDET - customer suite wallmount backside of their rack and tagged circuit id |  | Judie Cattell 1-904-646-6550 Jcattell@wellmed.net | AIDYL BERT SIMBULAN | aidyl_simbulan@optum.com | 632-462-2465 | 08/24/2020(Access) 08/24/2020(Private IP - PIP) 08/24/2020(WAN Analysis Reporting) |  |  | 09/11/2020 (31654885) 09/15/2020 (31654884) | 09/11/2020 09/17/2020 | 08/24/2020 |  | Completed | N (31654885) N (31654884) N (31654886) | U0101953 |  |  | NSPE0013715910
Completed | TX11605IM | 1900 N Main Ave San Antonio, TX 78212-3942 US | 50 MBPS (31657539) | 11/05/2020: Order Completed on Nov 5, 2020 | 202647887 | UNITED HEALTH GROUP | Access (31657539) Private IP - PIP (31657538) WAN Analysis Reporting (31657540) | 31657539 31657538 31657540 | 10 MBPS (31657538) |  | 94785040 (Access) 94785042 (Private IP (PIP)) 94785044 (WAN Analysis Reporting) | E4058251/ADD (31657539) C4022602/ADD (31657538) | 21.L1XX.990398..CHTR (3165753933842501) | 6120050 | 5500 | PVC ID : 6120050 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64538 PE IP Address : 68.136.188.205 CE Address : 68.136.188.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31657539) | 1000Base-SX (850nm, Multi Mode Fiber) (31657539) | Ethernet | TIME WARNER CABLE (3165753933842501) | 10/06/2020 (3165753933842501) | 11/20/2020 (3165753933842501) | 11/02/2020 (3165753933842501) | 11/05/2020 (VFORCE) (31657539) | 11/05/2020 (VFORCE) (31657539) | DEMARCADDR - 1 DEMARCDET - 1ST FLOOR IT ROOM WALL MOUNTED |  | REINA TREVINO 1-210-508-5819 RTrevino@wellmed.net | Sean Olivete | marion_olivete@optum.com | 1-763-744-2114 | 11/05/2020(Access) 11/05/2020(Private IP - PIP) 11/05/2020(WAN Analysis Reporting) |  |  | 12/01/2020 (31657539) 12/03/2020 (31657538) | 11/16/2020 11/20/2020 | 11/05/2020 |  | Completed | N (31657539) N (31657538) N (31657540) | U0101953 |  |  | NSPE0013716815
Completed | TX09204IM | 1030 Bensdale Rd Pleasanton, TX 78064-2037 US | 50 MBPS (31657505) | 08/06/2020: Beas install scheduled for 8/7. | 202647849 | UNITED HEALTH GROUP | WAN Analysis Reporting (31657506) Access (31657505) Private IP - PIP (31657504) | 31657506 31657505 31657504 | 10 MBPS (31657504) |  | 94785381 (WAN Analysis Reporting) 94785376 (Access) 94785378 (Private IP (PIP)) | C4022603/ADD (31657504) E4058252/ADD (31657505) | 31/KRGN/654748//SW (3165750529896601) | 6120053 | 5500 | PVC ID : 6120053 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65277 PE IP Address : 152.183.110.245 CE Address : 152.183.110.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31657505) | 1000Base-SX (850nm, Multi Mode Fiber) (31657505) | Ethernet | ATT (3165750529896601) | 05/22/2020 (3165750529896601) | 05/28/2020 (3165750529896601) | 05/28/2020 (3165750529896601) | 08/07/2020 (VFORCE) (31657505) | 08/07/2020 (VFORCE) (31657505) | DEMARCDET - 1ST FLR IT RM WALLMOUNT |  | Megan Evans 1-210-878-6328 mevans1@wellmed.net | Sean Olivete | marion_olivete@optum.com | 1-763-744-2114 | 08/07/2020(WAN Analysis Reporting) 08/07/2020(Access) 08/07/2020(Private IP - PIP) |  |  | 08/10/2020 (31657504) 08/06/2020 (31657505) | 09/16/2020 09/10/2020 | 08/07/2020 |  | Completed | N (31657506) N (31657505) N (31657504) | U0101953 |  |  | NSPE0013716815
Completed | TX428 | 5627 University Hts bldg B San Antonio, TX 78249-3582 US | 100 MBPS (31659343) | 04/30/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 202650077 | TX428 | Private IP - PIP (31659342) WAN Analysis Reporting (31659344) Access (31659343) | 31659342 31659344 31659343 | 50 MBPS (31659342) |  | 1264648197 (Private IP (PIP)) 1264648209 (WAN Analysis Reporting) 1264648191 (Access) | C1105736/ADD (31659342) E4058258/ADD (31659343) | 21.L1XX.990394..CHTR (3165934373735101) | 6120085 | 5500 | PVC ID : 6120085 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64831 PE IP Address : 152.176.197.45 CE Address : 152.176.197.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31659343) | 1000Base-SX (850nm, Multi Mode Fiber) (31659343) | Ethernet | TIME WARNER CABLE (3165934373735101) | 04/29/2020 (3165934373735101) | 04/15/2020 (3165934373735101) | 04/30/2020 (3165934373735101) | 05/04/2020 (VFORCE) (31659343) |  | DEMARCDET - bldg 1 on 1st flr server rm rack mounted rack 2 RU 37-39 |  | JASON STEIN 1-210-865-6391 Jason.Stein@optum.com | JASON SALAPING | jason_salaping@gmail.com | 632-462-2446 | 05/04/2020(Private IP - PIP) 05/04/2020(WAN Analysis Reporting) 05/04/2020(Access) |  |  | 09/18/2020 (31659342) 09/16/2020 (31659343) | 09/16/2020 09/22/2020 | 05/04/2020 |  | Completed | N (31659342) N (31659344) N (31659343) | U0101953 |  |  | NSPE0013717406
Completed | CA777 | 600 W 7TH ST FL 6 LOS ANGELES, CA 90017-3859 US |  | 04/28/2020: Order Completed on Apr 27, 2020 | 202650341 | Equinix Internet Los Angeles | Private IP - PIP (31659440) Access WAN Analysis Reporting (31659442) | 31659440 31659442 | 5 GBPS (31659440) |  | 1254291223 (Private IP (PIP)) 1254291139 1254291225 (WAN Analysis Reporting) | C0186431/NONE (31659440) |  | 6114533 | 2500 | PVC ID : 6114533 VPN Name : UnitedHealthGroup Router Name : LL6XE01 VRF Name : V510590-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65155 PE IP Address : 208.219.143.193 CE Address : 208.219.143.194 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) | Ethernet | [8 empty] | Melissa Chapman 1-763-744-2114 melissa_r_chapman@optum.com | Melissa Chapman | melissa_r_chapman@optum.com | 1-763-744-2114 | 04/27/2020(Private IP |  |  | 04/24/2020 (31659440) | 04/30/2020 04/30/2020 (6275375.5) | 04/27/2020 |  | Completed Activated/Installed | N (31659440) N N (31659442) | U0101953 |  |  | NSPE0013717519
Completed | FL086-04-IM | 507 W ALEXANDER ST PLANT CITY, FL 33563-7136 US | 50 MBPS (31666197) | 08/07/2020: Install scheduled on 8/7 -12PM-2PM. | 202657297 | UNITED HEALTH GROUP | Private IP - PIP (31666196) WAN Analysis Reporting (31666198) Access (31666197) | 31666196 31666198 31666197 | 10 MBPS (31666196) |  | 1264869879 (Private IP (PIP)) 1264869881 (WAN Analysis Reporting) 1264869875 (Access) | C4022616/ADD (31666196) E4058293/ADD (31666197) | 81.L1XX.911210..CHTR (3166619710550601) | 6120192 | 5500 | PVC ID : 6120192 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64814 PE IP Address : 147.225.220.161 CE Address : 147.225.220.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31666197) | 1000Base-SX (850nm, Multi Mode Fiber) (31666197) | Ethernet | BRIGHT HOUSE (3166619710550601) | 07/30/2020 (3166619710550601) | 08/14/2020 (3166619710550601) | 08/07/2020 (3166619710550601) | 08/12/2020 (VFORCE) (31666197) | 08/12/2020 (VFORCE) (31666197) | DEMARCADDR - 1 DEMARCDET - 2ND FLOOR MDF ROOM WALL MOUNTED |  | Josh Lopez 1-813-846-4623 joshlopez@wellmed.net | JEALINE TEODORO | jealine.teodoro@optum.com | 632-588-5307 | 08/12/2020(Private IP - PIP) 08/12/2020(WAN Analysis Reporting) 08/12/2020(Access) |  |  | 12/24/2020 (31666196) 12/22/2020 (31666197) | 12/22/2020 12/29/2020 | 08/12/2020 |  | Completed | N (31666196) N (31666198) N (31666197) | U0101953 |  |  | NSPE0013719101
Completed |  | 8301 SOUTHPARK CIR STE 150 ORLANDO, FL 32819-9013 US | 100 MBPS (31735989) | 06/23/2020: Order Completed on Jun 23, 2020 | 202731415 | FL139-02-IJ Catamaran | Private IP - PIP (31735988) WAN Analysis Reporting (31735990) Access (31735989) | 31735988 31735990 31735989 | 50 MBPS (31735988) |  | 1262586393 (Private IP (PIP)) 1262586395 (WAN Analysis Reporting) 1262586389 (Access) | C1105999/ADD (31735988) E4058502/ADD (31735989) | 184611-ENET-CCF (3173598912830601) | 6121382 | 30000 | PVC ID : 6121382 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64798 PE IP Address : 152.183.110.97 CE Address : 152.183.110.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31735989) | 1000Base-SX (850nm, Multi Mode Fiber) (31735989) | Ethernet | CLEC or INDEPENDENT (3173598912830601) | 04/30/2020 (3173598912830601) | 06/26/2020 (3173598912830601) | 06/22/2020 (3173598912830601) | 06/25/2020 (VFORCE) (31735989) | 06/23/2020 (VFORCE) (31735989) | DEMARCDET - FLR MAIN SUIT 150 |  | James Brown 1-321-663-1091 jamesbrown@optum.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 06/23/2020(Private IP - PIP) 06/23/2020(WAN Analysis Reporting) 06/23/2020(Access) |  |  | 09/15/2020 (31735988) 09/11/2020 (31735989) | 09/10/2020 09/16/2020 | 06/23/2020 |  | Completed | N (31735988) N (31735990) N (31735989) | U0101953 |  |  | NSPE0013739185
Completed |  | 4100 S Saginaw St Flint, MI 48507-2683 US | 500 MBPS (31736064) | 08/27/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 202727923 | MI078 | Access (31736064) Private IP - PIP (31736063) WAN Analysis Reporting (31736065) | 31736064 31736063 31736065 | 200 MBPS (31736063) |  | 94795667 (Access) 94795665 (Private IP (PIP)) 94795671 (WAN Analysis Reporting) | E5025597/ADD (31736064) C5009970/ADD (31736063) | 21.VLXP.022849.ON.CBCL.. (3173606476450101) | 6121385 | 110000 | PVC ID : 6121385 VPN Name : UnitedHealthGroup Router Name : DTRT9E01 VRF Name : Vh75443:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65045 PE IP Address : 206.115.67.97 CE Address : 206.115.67.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31736064) | 1000Base-SX (850nm, Multi Mode Fiber) (31736064) | Ethernet | COMCAST (3173606476450101) | 07/23/2020 (3173606476450101) | 08/25/2020 (3173606476450101) | 08/24/2020 (3173606476450101) | 08/27/2020 (VFORCE) (31736064) | 08/27/2020 (VFORCE) (31736064) | DEMARCDET - customer IT room 2nd floor ISP/Carrier rack FTS |  | Brad Coyer 1-989-948-7487 bcoyer@diplomat.is | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 08/27/2020(Access) 08/27/2020(Private IP - PIP) 08/27/2020(WAN Analysis Reporting) |  |  | 09/01/2020 (31736064) 09/03/2020 (31736063) | 09/02/2020 09/09/2020 | 08/27/2020 |  | Completed | N (31736064) N (31736063) N (31736065) | U0101953 |  |  | NSPE0013738272
Completed | TX551 | 1387 George Dieter Dr bldg B El Paso, TX 79936-7410 US | 50 MBPS (31749125) | 08/27/2020: Your order is on track: Verizon has received a Firm Order Confirmation (FOC) Date for your telco access delivery for Oct 29, 2020 from TIME WARNER CABLE and is now pending loop acceptance. | 202745825 | TX551 | Private IP - PIP (31749124) WAN Analysis Reporting (31749126) Access (31749125) | 31749124 31749126 31749125 | 10 MBPS (31749124) |  | 94796213 (Private IP (PIP)) 94796211 (WAN Analysis Reporting) 94796209 (Access) | C4022692/ADD (31749124) E4058563/ADD (31749125) | 91.L1XX.804533..CHTR (3174912576621401) | 6121578 | 5500 | PVC ID : 6121578 VPN Name : UnitedHealthGroup Router Name : AQHXE01 VRF Name : Vh57762-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65376 PE IP Address : 152.177.141.189 CE Address : 152.177.141.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31749125) | 1000Base-SX (850nm, Multi Mode Fiber) (31749125) | Ethernet | TIME WARNER CABLE (3174912576621401) | 08/06/2020 (3174912576621401) | 10/29/2020 (3174912576621401) | 08/21/2020 (3174912576621401) | 08/25/2020 (VFORCE) (31749125) | 08/25/2020 (VFORCE) (31749125) | DEMARCDET - MAIN BLDG MAIN FLOOR MDF ROOM |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | JASON SALAPING | jason_salaping@gmail.com | 1-210-862-6784 | 08/25/2020(Private IP - PIP) 08/25/2020(WAN Analysis Reporting) 08/25/2020(Access) |  |  | 11/09/2020 (31749124) 11/05/2020 (31749125) | 09/17/2020 09/23/2020 | 08/25/2020 |  | Completed | N (31749124) N (31749126) N (31749125) | U0101953 |  |  | NSPE0013743078
Completed | CHASKA ADD VRF | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 7000 MBPS (CQBL180N) |  | 10285866 |  | Private IP Port Only (CQBL180N) | CQBL180N | 7000 MBPS | P1955436 |  | BOBKWCW20001 (CQBL180N) |  | 6121750 | 24576 | PVC ID : 6121750 VPN Name : Alere-LLC-WAN Router Name : MZZGE01 VRF Name : Vg35543:AlereLLCWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65074 PE IP Address : 152.176.170.69 CE Address : 152.176.170.70 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/01/2020 (CQBL180N) |  |  | 05/27/2020 (CQBL180N) | 05/27/2020 (CQBL180N) |  |  |  | N (CQBL180N) | 05017789 |  |  | NSPE0013739140
Completed | Omaha - C1622-04-IM. | 5601 N 103RD ST OMAHA, NE 68134-1006 US | 100 MBPS (31759090) | 07/28/2020: Order Completed on Jul 28, 2020 | 202756431 | Sitel Operating Corporation | Access (31759090) WAN Analysis Reporting (31759091) Private IP - PIP (31759089) | 31759090 31759091 31759089 | 50 MBPS (31759089) |  | 94784587 (Access) 94784585 (WAN Analysis Reporting) 94784590 (Private IP (PIP)) | E4058606/ADD (31759090) C1133345/ADD (31759089) |  | 6121771 | 45000 | PVC ID : 6121771 VPN Name : UHG-ECC Router Name : PLSHXE01 VRF Name : V449266-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65504 PE IP Address : 147.225.193.89 CE Address : 147.225.193.90 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31759090) | Ethernet |  |  |  |  | 07/22/2020 (CCP) (31759090) 07/22/2020 (CCP) (31759089) | 07/21/2020 (CCP) (31759090) 07/21/2020 (CCP) (31759089) |  |  | Clark Willms 1-305-606-9214 clark.willms@sitel.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 07/28/2020(Access) 07/28/2020(WAN Analysis Reporting) 07/28/2020(Private IP - PIP) |  |  | 08/03/2020 (31759090) 08/05/2020 (31759089) | 08/31/2020 09/04/2020 | 07/28/2020 |  | Completed | N (31759090) N (31759091) N (31759089) | U0101953 |  |  | NSPE0013744989
Completed | CT039-10-IJ UHG hartford | 185 ASYLUM ST FL 1 HARTFORD, CT 06103-3408 US | 500 MBPS (31760079) | 06/29/2020: Order Completed on Jun 29, 2020 | 202757823 | CT039-10-IJ UHG hartford | Private IP - PIP (31760078) WAN Analysis Reporting (31760080) Access (31760079) | 31760078 31760080 31760079 | 400 MBPS (31760078) |  | 1268728329 (Private IP (PIP)) 1268728331 (WAN Analysis Reporting) 1268728325 (Access) | C5009991/ADD (31760078) E5025638/ADD (31760079) |  | 6121787 | 250000 | PVC ID : 6121787 VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65153 PE IP Address : 152.181.2.45 CE Address : 152.181.2.46 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31760079) | Ethernet |  |  |  |  | 06/11/2020 (CCP) (31760078) 06/11/2020 (CCP) (31760079) | 06/09/2020 (CCP) (31760078) 06/09/2020 (CCP) (31760079) |  |  | KEITH MANGENE 1-860-702-8284 keith_mangene@optum.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 | 06/29/2020(Private IP - PIP) 06/29/2020(WAN Analysis Reporting) 06/29/2020(Access) |  |  | 06/18/2020 (31760078) 06/16/2020 (31760079) | 06/18/2020 06/24/2020 | 06/29/2020 |  | Completed | N (31760078) N (31760080) N (31760079) | U0101953 |  |  | NSPE0013746252
Completed | TX570 | 105 S Main St Cedar Hill, TX 75104-2619 US | 50 MBPS (31771909) | 07/25/2020: Order Completed on Jul 24, 2020 | 202769431 | TX570 | Private IP - PIP (31771908) Access (31771909) WAN Analysis Reporting (31771910) | 31771908 31771909 31771910 | 10 MBPS (31771908) |  | 94796525 (Private IP (PIP)) 94796527 (Access) 94796532 (WAN Analysis Reporting) | C4022738/ADD (31771908) E4058661/ADD (31771909) | 46.L1XX.002765..CHTR (3177190976726001) | 6122023 | 5500 | PVC ID : 6122023 VPN Name : UnitedHealthGroup Router Name : RCN3E02 VRF Name : Vh26648-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65375 PE IP Address : 152.176.210.89 CE Address : 152.176.210.90 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31771909) | 1000Base-SX (850nm, Multi Mode Fiber) (31771909) | Ethernet | TIME WARNER CABLE (3177190976726001) | 05/07/2020 (3177190976726001) | 08/03/2020 (3177190976726001) | 07/23/2020 (3177190976726001) | 07/24/2020 (VFORCE) (31771909) | 07/24/2020 (VFORCE) (31771909) | DEMARCDET - 1st FL Closet next to Entry way Wall mounted and Tagged |  | Emmanuel Udoji 1-214-707-6875 eudoji@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 | 07/24/2020(Private IP - PIP) 07/24/2020(Access) 07/24/2020(WAN Analysis Reporting) |  |  | 08/12/2020 (31771908) 08/10/2020 (31771909) | 10/14/2020 10/20/2020 | 07/24/2020 |  | Completed | N (31771908) N (31771909) N (31771910) | U0101953 |  |  | NSPE0013762833
Completed | WI053 | 125 S 84th St Milwaukee, WI 53214-1469 US | 200 MBPS (31771972) | 08/28/2020: Follow up sent to IT. Order complete, need it to be on close to bill tab. | 202769765 | WI053 | Private IP - PIP (31771971) Access (31771972) WAN Analysis Reporting (31771973) | 31771971 31771972 31771973 | 100 MBPS (31771971) |  | 94796697 (Private IP (PIP)) 94796695 (Access) 94796699 (WAN Analysis Reporting) | C5010004/ADD (31771971) E5025656/ADD (31771972) | WI/KXFN/323749/LVLC (3177197276457301) | 6122026 | 70000 | PVC ID : 6122026 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64944 PE IP Address : 152.183.198.101 CE Address : 152.183.198.102 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31771972) | 1000Base-SX (850nm, Multi Mode Fiber) (31771972) | Ethernet | LEVEL 3 (3177197276457301) | 07/23/2020 (3177197276457301) | 08/20/2020 (3177197276457301) | 08/10/2020 (3177197276457301) | 08/18/2020 (VFORCE) (31771972) |  | DEMARCDET - NA |  | Cassandra Friedi 1-877-543-4739 Cassandra.Friedi@greywp.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 08/18/2020(Private IP - PIP) 08/18/2020(Access) 08/18/2020(WAN Analysis Reporting) |  |  | 08/31/2020 (31771971) 08/27/2020 (31771972) | 09/02/2020 09/09/2020 | 09/01/2020 |  | Completed | N (31771971) N (31771972) N (31771973) | U0101953 |  |  | NSPE0013762988
Completed | FL077-04-IM | 2191 9TH AVE N STE 110 ST PETERSBURG, FL 33713-7147 US | 50 MBPS (31794674) | 08/13/2020: Confirmed access with lcon for beas install. Pending date and time for install. | 202793393 | UNITED HEALTH GROUP | Access (31794674) WAN Analysis Reporting (31794675) Private IP - PIP (31794673) | 31794674 31794675 31794673 | 10 MBPS (31794673) |  | 1264083539 (Access) 1264083705 (WAN Analysis Reporting) 1264083703 (Private IP (PIP)) | E4058737/ADD (31794674) C4022763/ADD (31794673) | 72.L1XX.932682..CHTR (3179467475864001) | 6122452 | 5500 | PVC ID : 6122452 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65187 PE IP Address : 152.183.226.49 CE Address : 152.183.226.50 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31794674) | 1000Base-SX (850nm, Multi Mode Fiber) (31794674) | Ethernet | BRIGHT HOUSE (3179467475864001) | 07/31/2020 (3179467475864001) | 08/13/2020 (3179467475864001) | 08/06/2020 (3179467475864001) | 08/18/2020 (VFORCE) (31794674) | 08/17/2020 (VFORCE) (31794674) | DEMARCADDR - 1 DEMARCDET - 1st floor room 110 rack location in server closet |  | Alan Jackson 1-727-820-7778 ajackson1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 08/17/2020(Access) 08/17/2020(WAN Analysis Reporting) 08/17/2020(Private IP - PIP) |  |  | 08/20/2020 (31794674) 08/24/2020 (31794673) | 09/24/2020 09/30/2020 | 08/17/2020 |  | Completed | N (31794674) N (31794675) N (31794673) | U0101953 |  |  | NSPE0013715508
Completed | NV750-02-IJ | 7135 S Decatur Blvd Las Vegas, NV 89118-4376 US | 1 GBPS (31798301) | 06/09/2020: Order Completed on Jun 8, 2020 | 202796845 | NV750-02-IJ Lad Vegas NV | Private IP - PIP (31798300) WAN Analysis Reporting (31798302) Access (31798301) | 31798300 31798302 31798301 | 300 MBPS (31798300) |  | 94797714 (Private IP (PIP)) 94797719 (WAN Analysis Reporting) 94797717 (Access) | C0188643/ADD (31798300) E5025704/ADD (31798301) |  | 6122519 | 180000 | PVC ID : 6122519 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65267 PE IP Address : 152.177.17.149 CE Address : 152.177.17.150 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (31798301) | Ethernet | [8 empty] | David Ruckdaschel 1-702-243-8580 David.Ruckdaschel@optum.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 1-763-744-2114 | 06/08/2020(Private IP - PIP) 06/08/2020(WAN Analysis Reporting) 06/08/2020(Access) |  |  | 05/27/2020 (31798300) 05/22/2020 (31798301) | 06/17/2020 06/23/2020 | 06/08/2020 |  | Completed | N (31798300) N (31798302) N (31798301) | U0101953 |  |  | NSPE0013770303
Completed | TX346-02-IM | 7198 Merchant Ave El Paso, TX 79915-1235 US | 50 MBPS (31811917) | 09/14/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 202806549 | TX346-02-IM | WAN Analysis Reporting (31811918) Access (31811917) Private IP - PIP (31811916) | 31811918 31811917 31811916 | 10 MBPS (31811916) |  | 94796496 (WAN Analysis Reporting) 94796493 (Access) 94796491 (Private IP (PIP)) | C4022827/ADD (31811916) E4058829/ADD (31811917) | 91.L1XX.804583..CHTR (3181191723926801) | 6122722 | 5500 | PVC ID : 6122722 VPN Name : UnitedHealthGroup Router Name : AQHXE01 VRF Name : Vh57762-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64832 PE IP Address : 152.162.182.161 CE Address : 152.162.182.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31811917) | 1000Base-SX (850nm, Multi Mode Fiber) (31811917) | Ethernet | TIME WARNER CABLE (3181191723926801) | 07/30/2020 (3181191723926801) | 10/23/2020 (3181191723926801) | 09/01/2020 (3181191723926801) | 09/03/2020 (VFORCE) (31811917) | 09/03/2020 (VFORCE) (31811917) | DEMARCDET - flr 1comm rm rack in the warehouse rack mounted |  | Caroline Reyes 1-915-873-9226 CReyes@homecaredimensions.com | ED KIMUEL RAMOS | kimuel_ramos@optum.com | 632-588-5397 | 09/03/2020(WAN Analysis Reporting) 09/03/2020(Access) 09/03/2020(Private IP - PIP) |  |  | 11/03/2020 (31811916) 10/30/2020 (31811917) | 09/16/2020 09/10/2020 | 09/03/2020 |  | Completed | N (31811918) N (31811917) N (31811916) | U0101953 |  |  | NSPE0013773530
Completed | TX371 | 850 W US HIGHWAY 77 SAN BENITO, TX 78586-4319 US | 50 MBPS (31812598) | 08/13/2020: Beas dispatch was rescheduled to 8/17 ETA 2pm to 4pm. | 202807449 | UHG- TX371 Wellmed | Access (31812598) WAN Analysis Reporting (31812599) Private IP - PIP (31812597) | 31812598 31812599 31812597 | 10 MBPS (31812597) |  | 1264969363 (Access) 1264969369 (WAN Analysis Reporting) 1264969367 (Private IP (PIP)) | E4058838/ADD (31812598) C4022829/ADD (31812597) | 38/KRGN/614052//SW (3181259830292601) | 6122736 | 5500 | PVC ID : 6122736 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65279 PE IP Address : 152.177.34.233 CE Address : 152.177.34.234 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31812598) | 1000Base-SX (850nm, Multi Mode Fiber) (31812598) | Ethernet | ATT (3181259830292601) | 05/08/2020 (3181259830292601) | 05/26/2020 (3181259830292601) | 05/26/2020 (3181259830292601) | 08/20/2020 (VFORCE) (31812598) | 08/17/2020 (VFORCE) (31812598) | DEMARCDET - 1ST FLR IT RM WALLMOUNT |  | LUIS CASAS 1-956-455-5057 luisecasas@yahoo.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 08/17/2020(Access) 08/17/2020(WAN Analysis Reporting) 08/17/2020(Private IP - PIP) |  |  | 08/06/2020 (31812598) 08/10/2020 (31812597) | 09/10/2020 09/16/2020 | 08/17/2020 |  | Completed | N (31812598) N (31812599) N (31812597) | U0101953 |  |  | NSPE0013773860
Completed | TX347-02-IM | 1317 E Jasmine Ave Mcallen, TX 78501-5708 US | 50 MBPS (31825106) | 07/30/2020: Pending scheduling of beas install. | 202818569 | TX347-02-IM | Private IP - PIP (31825105) Access (31825106) WAN Analysis Reporting (31825107) | 31825105 31825106 31825107 | 10 MBPS (31825105) |  | 94799660 (Private IP (PIP)) 94799663 (Access) 94799667 (WAN Analysis Reporting) | C4022845/ADD (31825105) E4058867/ADD (31825106) | 95.L1XX.802256..CHTR (3182510623924601) | 6122892 | 5500 | PVC ID : 6122892 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65219 PE IP Address : 152.177.121.149 CE Address : 152.177.121.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31825106) | 1000Base-SX (850nm, Multi Mode Fiber) (31825106) | Ethernet | TIME WARNER CABLE (3182510623924601) | 05/08/2020 (3182510623924601) | 08/20/2020 (3182510623924601) | 06/19/2020 (3182510623924601) | 08/05/2020 (VFORCE) (31825106) | 08/05/2020 (VFORCE) (31825106) | DEMARCDET - 1st flr IT closet spectrum wall mount rack |  | Cassandra Pinon 1-956-240-0469 cpinon@homecaredimensions.com | ED KIMUEL RAMOS | kimuel_ramos@optum.com | 632-588-5397 | 08/05/2020(Private IP - PIP) 08/05/2020(Access) 08/05/2020(WAN Analysis Reporting) |  |  | 08/31/2020 (31825105) 08/27/2020 (31825106) | 12/21/2020 12/28/2020 | 08/05/2020 |  | Completed | N (31825105) N (31825106) N (31825107) | U0101953 |  |  | NSPE0013777610
Completed | TX354 | 809 W NASH ST STE 100 TERRELL, TX 75160-2512 US | 50 MBPS (31825181) | 08/27/2020: Order Completed on Aug 20, 2020 | 202818739 | UHG ENT PROD | Private IP - PIP (31825180) WAN Analysis Reporting (31825182) Access (31825181) | 31825180 31825182 31825181 | 20 MBPS (31825180) |  | 1264972759 (Private IP (PIP)) 1264972761 (WAN Analysis Reporting) 1264972755 (Access) | C4022847/ADD (31825180) E4058870/ADD (31825181) | AS/KRGN/004142/SW (3182518125354001) | 6122903 | 13000 | PVC ID : 6122903 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64594 PE IP Address : 152.185.9.65 CE Address : 152.185.9.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31825181) | 1000Base-SX (850nm, Multi Mode Fiber) (31825181) | Ethernet | NITEL USA (3182518125354001) | 08/03/2020 (3182518125354001) 05/11/2020 (3182518125354001) | 08/12/2020 (3182518125354001) 06/19/2020 (3182518125354001) | 08/17/2020 (3182518125354001) | 08/20/2020 (VFORCE) (31825181) | 08/20/2020 (VFORCE) (31825181) | DEMARCDET - 2ND FLR...TELCO RM. WALL MOUNT. PORT 1 LEC CID: AS/KRGN/004142/SW |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 08/20/2020(Private IP - PIP) 08/20/2020(WAN Analysis Reporting) 08/20/2020(Access) |  |  | 08/21/2020 (31825180) 08/19/2020 (31825181) | 09/14/2020 09/18/2020 | 08/20/2020 |  | Completed | N (31825180) N (31825182) N (31825181) | U0101953 |  |  | NSPE0013775725
Completed | TX263-05-IM | 8107 SPRINGDALE RD STE 110 AUSTIN, TX 78724-2437 US | 50 MBPS (31831124) | 12/10/2020: Order Completed on Dec 9, 2020 | 202825427 | TX263-05-IM | Private IP - PIP (31831123) Access (31831124) WAN Analysis Reporting (31831125) | 31831123 31831124 31831125 | 10 MBPS (31831123) |  | 1264975097 (Private IP (PIP)) 1264975093 (Access) 1264975099 (WAN Analysis Reporting) | C4022856/ADD (31831123) E4058899/ADD (31831124) | TX/KXFN/329603/LVLC (3183112423944801) | 6123106 | 5500 | PVC ID : 6123106 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65218 PE IP Address : 152.164.170.253 CE Address : 152.164.170.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31831124) | 1000Base-SX (850nm, Multi Mode Fiber) (31831124) | Ethernet | LEVEL 3 (3183112423944801) | 10/19/2020 (3183112423944801) | 12/10/2020 (3183112423944801) | 12/08/2020 (3183112423944801) | 12/09/2020 (VFORCE) (31831124) | 12/09/2020 (VFORCE) (31831124) | DEMARCDET - suite 150 1st floor break room black wall mounted cabinet |  | Gertrude Grady 1-512-659-7649 ggrady@homecaredimensions.com | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 12/09/2020(Private IP - PIP) 12/09/2020(Access) 12/09/2020(WAN Analysis Reporting) |  |  | 12/21/2020 (31831123) 12/17/2020 (31831124) | 12/01/2020 12/07/2020 | 12/09/2020 |  | Completed | N (31831123) N (31831124) N (31831125) | U0101953 |  |  | NSPE0013777835
Completed | TX521 | 4230 W GREEN OAKS BLVD ARLINGTON, TX 76016-4517 US | 50 MBPS (31841665) | 08/13/2020: Hotcut scheduled for tonight, 8/13/2020 at 05:30 PM CST. | 202829197 | TX521 | Access (31841665) WAN Analysis Reporting (31841666) Private IP - PIP | 31841665 31841666 | 10 MBPS |  | 94650181 (Access) 94650176 (WAN Analysis Reporting) 94650178 | E4047609/NONE (31841665) |  |  |  |  | 1000Base-SX-850nm (31841665) | 1000Base-SX (850nm, Multi Mode Fiber) (31841665) | Ethernet |  |  |  |  | 08/13/2020 (VFORCE) (31841665) | 08/13/2020 (VFORCE) (31841665) |  |  | MARCO WONG 1-210-762-3623 mwong@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 08/18/2020(Access) |  |  | 08/14/2020 (31841665) | 08/12/2020 08/12/2020 (26969125.2) | 08/18/2020 |  | Activated/Installed Completed | N (31841665) N (31841666) N | U0101953 |  |  | NSPE0013782486
Completed | TX572 | 11255 Garland Rd ste 19 Dallas, TX 75218-2526 US | 50 MBPS (31869896) | 10/23/2020: Order Completed on Oct 23, 2020 | 202862873 | TX572 | Private IP - PIP (31869895) WAN Analysis Reporting (31869897) Access (31869896) | 31869895 31869897 31869896 | 10 MBPS (31869895) |  | 94800656 (Private IP (PIP)) 94800658 (WAN Analysis Reporting) 94800660 (Access) | C4022919/ADD (31869895) E4059044/ADD (31869896) | 21.L1XX.990576..CHTR (3186989677519501) | 6123960 | 5500 | PVC ID : 6123960 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65373 PE IP Address : 152.183.180.177 CE Address : 152.183.180.178 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31869896) | 1000Base-SX (850nm, Multi Mode Fiber) (31869896) | Ethernet | TIME WARNER CABLE (3186989677519501) | 10/08/2020 (3186989677519501) | 10/16/2020 (3186989677519501) | 10/21/2020 (3186989677519501) | 10/23/2020 (VFORCE) (31869896) | 10/23/2020 (VFORCE) (31869896) | DEMARCDET - 1st flr telco rm wall mounted |  | Sherry Green 1-612-642-7302 sgreen11@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 10/23/2020(Private IP - PIP) 10/23/2020(WAN Analysis Reporting) 10/23/2020(Access) |  |  | 10/30/2020 (31869895) 10/28/2020 (31869896) | 03/01/2021 03/05/2021 | 10/23/2020 |  | Completed | N (31869895) N (31869897) N (31869896) | U0101953 |  |  | NSPE0013792929
Completed | TX414-04-IJ | 304 E SAN PATRICIO AVE MATHIS, TX 78368-2350 US | 50 MBPS (31871339) | 09/29/2020: Order Completed on Sep 28, 2020 | 202864213 | TX414 | Private IP - PIP (31871338) WAN Analysis Reporting (31871340) Access (31871339) | 31871338 31871340 31871339 | 10 MBPS (31871338) |  | 1264844399 (Private IP (PIP)) 1264844401 (WAN Analysis Reporting) 1264844395 (Access) | C4022922/ADD (31871338) E4059051/ADD (31871339) | 36.L1XX.004959..CHTR (3187133975968001) | 6124011 | 5500 | PVC ID : 6124011 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65090 PE IP Address : 68.136.130.225 CE Address : 68.136.130.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31871339) | 1000Base-SX (850nm, Multi Mode Fiber) (31871339) | Ethernet | TIME WARNER CABLE (3187133975968001) | 08/03/2020 (3187133975968001) | 10/16/2020 (3187133975968001) | 09/24/2020 (3187133975968001) | 09/28/2020 (VFORCE) (31871339) |  | DEMARCDET - 1ST FL IT R WALL MOUNTED ON THE BACK WALL. |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 09/28/2020(Private IP - PIP) 09/28/2020(WAN Analysis Reporting) 09/28/2020(Access) |  |  | 10/27/2020 (31871338) 10/23/2020 (31871339) | 12/21/2020 12/28/2020 | 09/28/2020 |  | Completed | N (31871338) N (31871340) N (31871339) | U0101953 |  |  | NSPE0013793224
Completed | C1657 | 910 15th St Denver, CO 80202-2912 US | 200 MBPS (31870014) | 06/18/2020: Order Completed on Jun 18, 2020 | 202863115 | C1657 | Private IP - PIP (31870013) WAN Analysis Reporting (31870015) Access (31870014) | 31870013 31870015 31870014 | 150 MBPS (31870013) |  | 94797919 (Private IP (PIP)) 94797917 (WAN Analysis Reporting) 94797915 (Access) | C5010150/ADD (31870013) E5025906/ADD (31870014) |  | 6123979 | 90000 | PVC ID : 6123979 VPN Name : UHG-ECC Router Name : DNVR9E01 VRF Name : Vh72748:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65439 PE IP Address : 152.181.130.77 CE Address : 152.181.130.78 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31870014) | Ethernet | [8 empty] | Kevin Arts 1-303-478-8532 Kevin.Arts@broad-path.com | Vaishna Priya | Vaishna@optum.com | 91-804-670-4313 | 06/18/2020(Private IP - PIP) 06/18/2020(WAN Analysis Reporting) 06/18/2020(Access) |  |  | 06/17/2020 (31870013) 06/15/2020 (31870014) | 06/25/2020 07/01/2020 | 06/18/2020 |  | Completed | N (31870013) N (31870015) N (31870014) | U0101953 |  |  | NSPE0013792976
Completed | C1656 | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US | 200 MBPS (31873768) | 06/01/2020: Order Completed on Jun 1, 2020 | 202862209 | Equinix hub Atlanta Peachtree GA777-04-IJ | Private IP - PIP (31873767) WAN Analysis Reporting (31873769) Access (31873768) | 31873767 31873769 31873768 | 150 MBPS (31873767) |  | 1272860623 (Private IP (PIP)) 1272860635 (WAN Analysis Reporting) 1272860617 (Access) | C5010154/ADD (31873767) E5025921/ADD (31873768) |  | 6124051 | 90000 | PVC ID : 6124051 VPN Name : UHG-ECC Router Name : CPZXE04 VRF Name : Vg63543-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65435 PE IP Address : 152.176.94.73 CE Address : 152.176.94.74 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31873768) | Ethernet |  |  |  |  | 06/09/2020 (CCP) (31873767) 06/09/2020 (CCP) (31873768) | 05/23/2020 (CCP) (31873767) 05/23/2020 (CCP) (31873768) |  |  | KEVIN ARTS 1-303-478-8532 kevin.arts@broad-path.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 | 06/01/2020(Private IP - PIP) 06/01/2020(WAN Analysis Reporting) 06/01/2020(Access) |  |  | 06/23/2020 (31873767) 06/19/2020 (31873768) | 06/11/2020 06/17/2020 | 06/01/2020 |  | Completed | N (31873767) N (31873769) N (31873768) | U0101953 |  |  | NSPE0013791326
Completed | NY187 | 931 CONKLIN ST STE C&D FARMINGDALE, NY 11735-2429 US | 100 MBPS (31891967) | 09/14/2020: Order Completed on Sep 3, 2020 | 202876743 | NY187-02-IJ Farmingdale, NY | Access (31891967) Private IP - PIP (31891966) WAN Analysis Reporting (31891968) | 31891967 31891966 31891968 | 50 MBPS (31891966) |  | 1267389605 (Access) 1267389609 (Private IP (PIP)) 1267389611 (WAN Analysis Reporting) | E4059090/ADD (31891967) C1131525/ADD (31891966) | 186068-ENET-CCF (3189196716867301) | 6124495 | 30000 | PVC ID : 6124495 VPN Name : UnitedHealthGroup Router Name : NV89E02 VRF Name : V101790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64664 PE IP Address : 206.115.36.241 CE Address : 206.115.36.242 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31891967) | 1000Base-SX (850nm, Multi Mode Fiber) (31891967) | Ethernet | LIGHT TOWER (3189196716867301) | 05/15/2020 (3189196716867301) | 09/18/2020 (3189196716867301) | 08/26/2020 (3189196716867301) | 09/03/2020 (VFORCE) (31891967) |  | DEMARCDET - 1st floor server room wall mounted |  | SUNIL ORIE 1-800-346-6348 sorie@aciiv.com | Jegin Miko Dimayuga | jegin_dimayuga@optum.com | 1-631-391-9670 | 09/03/2020(Access) 09/03/2020(Private IP - PIP) 09/03/2020(WAN Analysis Reporting) |  |  | 09/25/2020 (31891967) 09/29/2020 (31891966) | 11/03/2020 11/09/2020 | 09/03/2020 |  | Completed | N (31891967) N (31891966) N (31891968) | U0101953 |  |  | NSPE0013794954
Completed | FL194 | 2701 W Saint Isabel St Tampa, FL 33607-6324 US | 50 MBPS (31906567) | 08/13/2020: Beas install scheduled 8/17 between 1-5 PM. | 202889555 | FL194-02-IJ Tampa, FL | Access (31906567) WAN Analysis Reporting (31906568) Private IP - PIP (31906566) | 31906567 31906568 31906566 | 10 MBPS (31906566) |  | 94803232 (Access) 94803237 (WAN Analysis Reporting) 94803234 (Private IP (PIP)) | E4059138/ADD (31906567) C4022956/ADD (31906566) | 81.L1XX.911501..CHTR (3190656718145501) | 6124991 | 5500 | PVC ID : 6124991 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64555 PE IP Address : 152.176.119.229 CE Address : 152.176.119.230 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (31906567) | 1000Base-SX (850nm, Multi Mode Fiber) (31906567) | Ethernet | BRIGHT HOUSE (3190656718145501) | 05/20/2020 (3190656718145501) | 07/24/2020 (3190656718145501) | 06/22/2020 (3190656718145501) | 08/17/2020 (VFORCE) (31906567) | 08/17/2020 (VFORCE) (31906567) | DEMARCDET - TELECOM ROOM WALL MOUNTED ADVA 114 PORT 3 |  | Ruby Patel 1-813-876-9961 rupatel@wellmed.net | Ed Kimue Ramos | kimuel_ramos@optum.com | 632-588-5397 | 08/17/2020(Access) 08/17/2020(WAN Analysis Reporting) 08/17/2020(Private IP - PIP) |  |  | 08/06/2020 (31906567) 08/10/2020 (31906566) | 12/21/2020 12/28/2020 | 08/17/2020 |  | Completed | N (31906567) N (31906568) N (31906566) | U0101953 |  |  | NSPE0013800032
Completed | TX259-05-IM | 113 STARGRASS SPRING BRANCH, TX 78070-5164 US | 50 MBPS (31902906) | 07/30/2020: Pending scheduling of beas install. | 202888899 | TX259-05-IM | Access (31902906) WAN Analysis Reporting (31902907) Private IP - PIP (31902905) | 31902906 31902907 31902905 | 10 MBPS (31902905) |  | 1270615385 (Access) 1270615391 (WAN Analysis Reporting) 1270615389 (Private IP (PIP)) | E4059115/ADD (31902906) C4022949/ADD (31902905) | TX/EVPL/001088/IDTL/VBZ (3190290677036601) | 6124932 | 5500 | PVC ID : 6124932 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65095 PE IP Address : 152.176.125.209 CE Address : 152.176.125.210 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (31902906) | 1000Base-SX (850nm, Multi Mode Fiber) (31902906) | Ethernet | INDATEL SERVICES, LLC (3190290677036601) | 05/18/2020 (3190290677036601) | 06/24/2020 (3190290677036601) | 07/15/2020 (3190290677036601) | 08/06/2020 (VFORCE) (31902906) | 08/06/2020 (VFORCE) (31902906) | DEMARCDET - Communication Room back wall |  | Maria Melchor 1-830-935-5050 mmelchor@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 08/06/2020(Access) 08/06/2020(WAN Analysis Reporting) 08/06/2020(Private IP - PIP) |  |  | 08/07/2020 (31902906) 08/11/2020 (31902905) | 09/10/2020 09/16/2020 | 08/06/2020 |  | Completed | N (31902906) N (31902907) N (31902905) | U0101953 |  |  | NSPE0013799635
Completed | TX255-08-IM | 4500 WILLIAMS DR STE 285 GEORGETOWN, TX 78633-1339 US | 50 MBPS (31914222) | 08/28/2020: Order Completed on Aug 28, 2020 | 202900583 | UNITED HEALTH GROUP | Private IP - PIP (31914221) Access (31914222) WAN Analysis Reporting (31914223) | 31914221 31914222 31914223 | 10 MBPS (31914221) |  | 1275592149 (Private IP (PIP)) 1275592145 (Access) 1275592151 (WAN Analysis Reporting) | C4022968/ADD (31914221) E4059167/ADD (31914222) | 36/LUXS/000012/UNI/CLVI/ (3191422219889502) | 6125124 | 5500 | PVC ID : 6125124 VPN Name : UnitedHealthGroup Router Name : HSTN9E02 VRF Name : Vh45943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64542 PE IP Address : 147.225.17.241 CE Address : 147.225.17.242 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31914222) | 1000Base-SX (850nm, Multi Mode Fiber) (31914222) | Ethernet | SUDDEN LINK (3191422219889502) | 07/31/2020 (3191422219889502) | 09/25/2020 (3191422219889502) | 08/26/2020 (3191422219889502) | 08/28/2020 (VFORCE) (31914222) | 08/28/2020 (VFORCE) (31914222) | DEMARCDET - flr 1 suite 285 |  | KeShana Odom 1-512-869-4800 kodom@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 08/28/2020(Private IP - PIP) 08/28/2020(Access) 08/28/2020(WAN Analysis Reporting) |  |  | 09/22/2020 (31914221) 09/18/2020 (31914222) | 01/05/2021 01/11/2021 | 08/28/2020 |  | Completed | N (31914221) N (31914222) N (31914223) | U0101953 |  |  | NSPE0013803418
Completed |  | 6150 TRENTON LN N PLYMOUTH, MN 55442 USA | 5000 MBPS (CQBL2J02) | 05/21/2020: Ready to schedule. Please let us know once you have a date and time to deploy the change. | 10320924 |  | Private IP Port Only (CQBL2J02) | CQBL2J02 | 4000 MBPS | P2198241 |  | BOBLC5XS0001 (CQBL2J02) |  | 5998251 | 72000 | PVC ID : 5998251 VPN Name : UHG-SDWAN Router Name : MN39E01 VRF Name : Vd76602:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.164.75.1 CE Address : 152.164.75.2 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/21/2020 (CQBL2J02) |  |  | 06/16/2020 (CQBL2J02) | 06/16/2020 (CQBL2J02) |  |  |  | N (CQBL2J02) | 05017789 |  | multicast sender | NSPE0013800007
Completed |  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 5000 MBPS (CQBL2J1F) | 05/21/2020: Order Completed on May 21, 2020 | 10320865 |  | Private IP Port Only (CQBL2J1F) | CQBL2J1F | 4000 MBPS | P2308555 |  | BOBLJHRP0001 (CQBL2J1F) |  |  | 2250000 | VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65400 PE IP Address : 152.164.113.173 CE Address : 152.164.113.174 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443141 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/21/2020 (CQBL2J1F) |  |  | 06/16/2020 (CQBL2J1F) | 06/16/2020 (CQBL2J1F) |  |  |  | N (CQBL2J1F) | 05017789 |  | multicast sender | NSPE0013801389
Provisioning Accepted |  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 5000 MBPS (CQBL2JT9) | 05/21/2020: Ready to schedule. Please let us know once you have a date and time to deploy the change. | 10320925 |  | Private IP Port Only (CQBL2JT9) | CQBL2JT9 | 4000 MBPS | P2309944 |  | BOBLJKFG0001 (CQBL2JT9) |  | 6091887 | 2500000 | PVC ID : 6091887 VPN Name : UnitedHealthGroup Router Name : MN3XE01 VRF Name : Vd96545-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65398 PE IP Address : 68.138.99.217 CE Address : 68.138.99.218 QoS - Egress Profile: R12 | [11 empty] | UHT NCC 0017637443141 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/21/2020 (CQBL2JT9) |  |  | 06/15/2020 (CQBL2JT9) | 06/15/2020 (CQBL2JT9) |  |  |  | N (CQBL2JT9) | 05017789 |  | multicast sender | NSPE0013801333
Completed |  | 7383 COUNTY RD COLOGNE, MN 55322 USA | 5000 MBPS (CQBL2J44) | 05/21/2020: Pending logical changes to be made by provisioning. | 10320921 |  | Private IP Port Only (CQBL2J44) | CQBL2J44 | 4000 MBPS | P2308618 |  | BOBLJHT40001 (CQBL2J44) |  | 6086261 | 2500000 | PVC ID : 6086261 VPN Name : UnitedHealthGroup Router Name : MPLS9E01 VRF Name : Vd96554:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65398 PE IP Address : 68.136.41.205 CE Address : 68.136.41.206 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/21/2020 (CQBL2J44) |  |  | 06/16/2020 (CQBL2J44) | 06/16/2020 (CQBL2J44) |  |  |  | N (CQBL2J44) | 05017789 |  | multicast sender | NSPE0013801325
Completed |  | 7383 COUNTY RD COLOGNE, MN 55322 USA | 5000 MBPS (CQBL2JVK) | 05/21/2020: Ready to schedule. Please let us know once you have a date and time to deploy the change. | 10320920 |  | Private IP Port Only (CQBL2JVK) | CQBL2JVK | 4000 MBPS | P2308619 |  | BOBLJHT50001 (CQBL2JVK) |  |  | 2500000 | VPN Name : UnitedHealthGroup Router Name : MZZ9E01 VRF Name : V600583:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65400 PE IP Address : 208.219.130.213 CE Address : 208.219.130.214 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/21/2020 (CQBL2JVK) |  |  | 06/15/2020 (CQBL2JVK) | 06/15/2020 (CQBL2JVK) |  |  |  | N (CQBL2JVK) | 05017789 |  | multicast sender | NSPE0013801319
Completed |  | 7383 COUNTY ROAD 140 COLOGNE, MN 55322 USA | 5000 MBPS (CQBL2J4Z) | 05/22/2020: Order Completed on May 22, 2020 | 10320864 |  | Private IP Port Only (CQBL2J4Z) | CQBL2J4Z | 4000 MBPS | P2198253 |  | BOBLC5X60001 (CQBL2J4Z) |  | 5997743 | 768 | PVC ID : 5997743 VPN Name : UHG-SDWAN Router Name : MZZ9E01 VRF Name : Vd76606:UHGSDWAN Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65023 PE IP Address : 152.161.122.109 CE Address : 152.161.122.110 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 05/22/2020 (CQBL2J4Z) |  |  | 06/16/2020 (CQBL2J4Z) | 06/16/2020 (CQBL2J4Z) |  |  |  | N (CQBL2J4Z) | 05017789 |  | multicast sender | NSPE0013801380
Completed | FL141-08-IM | 13751 METROPOLIS AVE FORT MYERS, FL 33912-7134 US | 50 MBPS (31939097) | 10/27/2020: Order Completed on Oct 27, 2020 | 202920607 | UNITED HEALTHCARE | Private IP - PIP (31939096) WAN Analysis Reporting (31939098) Access (31939097) | 31939096 31939098 31939097 | 10 MBPS (31939096) |  | 1276844965 (Private IP (PIP)) 1276844967 (WAN Analysis Reporting) 1276844881 (Access) | C4023024/ADD (31939096) E4059245/ADD (31939097) | 25.KXGS.520016..UFLG (3193909710247701) | 6125549 | 5500 | PVC ID : 6125549 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65075 PE IP Address : 68.136.219.245 CE Address : 68.136.219.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31939097) | 1000Base-SX (850nm, Multi Mode Fiber) (31939097) | Ethernet | CENTURYLINK (3193909710247701) | 05/21/2020 (3193909710247701) | 07/10/2020 (3193909710247701) | 07/13/2020 (3193909710247701) | 10/27/2020 (VFORCE) (31939097) | 10/27/2020 (VFORCE) (31939097) | DEMARCDET - first floor server room cpe rack mount |  | Deborah Smith 1-239-265-9943 dsmith@wellmed.net | ED KIMUEL RAMOS | kimuel_ramos@optum.com | 632-588-5397 | 10/27/2020(Private IP - PIP) 10/27/2020(WAN Analysis Reporting) 10/27/2020(Access) |  |  | 10/30/2020 (31939096) 10/28/2020 (31939097) | 12/03/2020 12/09/2020 | 10/27/2020 |  | Completed | N (31939096) N (31939098) N (31939097) | U0101953 |  |  | NSPE0013809066
Completed | TX586-01-IM | 316 W BELT LINE RD STE 100 CEDAR HILL, TX 75104-2075 US | 50 MBPS (31938988) | 07/30/2020: FOC date 8/28. | 202920415 | TX586 | WAN Analysis Reporting (31938989) Private IP - PIP (31938987) Access (31938988) | 31938989 31938987 31938988 | 10 MBPS (31938987) |  | 1276595473 (WAN Analysis Reporting) 1276595471 (Private IP (PIP)) 1276595467 (Access) | E4059244/ADD (31938988) C4023023/ADD (31938987) | 46.L1XX.002777..CHTR (3193898878009901) | 6125546 | 5500 | PVC ID : 6125546 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64824 PE IP Address : 152.162.213.53 CE Address : 152.162.213.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (31938988) | 1000Base-SX (850nm, Multi Mode Fiber) (31938988) | Ethernet | TIME WARNER CABLE (3193898878009901) | 07/23/2020 (3193898878009901) | 08/28/2020 (3193898878009901) | 08/03/2020 (3193898878009901) | 08/05/2020 (VFORCE) (31938988) | 08/03/2020 (VFORCE) (31938988) | DEMARCDET - installed below pizza box in tleco rm near the main office CT closet RM VANGALAOFF |  | Emmanuel Udoji 1-214-707-6875 emmanuel_udoji@optum.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 | 08/03/2020(WAN Analysis Reporting) 08/03/2020(Private IP - PIP) 08/03/2020(Access) |  |  | 09/04/2020 (31938988) 09/09/2020 (31938987) | 12/18/2020 12/14/2020 | 08/03/2020 |  | Completed | N (31938989) N (31938987) N (31938988) | U0101953 |  |  | NSPE0013808303
Completed | LA013-01-IM | 3838 N CAUSEWAY BLVD METAIRIE, LA 70002-8194 US | 1 GBPS (31950227) | 06/26/2020: Order Completed on Jun 26, 2020 | 202929405 | UNITED HEALTHCARE | Access (31950227) WAN Analysis Reporting (31950228) Private IP - PIP (31950226) | 31950227 31950228 31950226 | 500 MBPS (31950226) |  | 1276998435 (Access) 1276998441 (WAN Analysis Reporting) 1276998439 (Private IP (PIP)) | E5026033/ADD (31950227) C0196935/ADD (31950226) | 27.KFGX.000383..COXC. (3195022774246001) | 6125796 | 350000 | PVC ID : 6125796 VPN Name : UnitedHealthGroup Router Name : NWO2GE01 VRF Name : V486980:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65393 PE IP Address : 152.176.89.77 CE Address : 152.176.89.78 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (31950227) | 1000Base-LX (1310nm Single Mode Fiber) (31950227) | Ethernet | COX (3195022774246001) | 05/22/2020 (3195022774246001) | 06/23/2020 (3195022774246001) | 06/19/2020 (3195022774246001) | 06/26/2020 (VFORCE) (31950227) | 06/26/2020 (VFORCE) (31950227) | DEMARCDET - 1ST FLR SHARED COMM RM , COX HANDOFF and NID CUST SERVER RM ON THE 23 FLR WALL MOUNTED |  | RIck Tittle 1-504-681-8928 rick.tittle@PeopleHealth.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-990-179-8210 | 06/26/2020(Access) 06/26/2020(WAN Analysis Reporting) 06/26/2020(Private IP - PIP) |  |  | 06/30/2020 (31950227) 07/02/2020 (31950226) | 07/20/2020 07/24/2020 | 06/26/2020 |  | Completed | N (31950227) N (31950228) N (31950226) | U0101953 |  |  | NSPE0013811118
Completed | C1653 | 119 W Tyler St ste 248 Longview, TX 75601-6358 US | 100 MBPS (31975534) | 06/09/2020: Order Completed on Jun 9, 2020 | 202951215 | C1653 | Access (31975534) Private IP - PIP (31975533) WAN Analysis Reporting (31975535) | 31975534 31975533 31975535 | 50 MBPS (31975533) |  | 1278501807 (Access) 1278501813 (Private IP (PIP)) 1278501825 (WAN Analysis Reporting) | E4059352/ADD (31975534) C1132563/ADD (31975533) |  | 6126346 | 30000 | PVC ID : 6126346 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65446 PE IP Address : 208.220.207.93 CE Address : 208.220.207.94 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31975534) | Ethernet |  |  |  |  | 06/09/2020 (CCP) (31975534) 06/09/2020 (CCP) (31975533) | 06/04/2020 (CCP) (31975534) 06/04/2020 (CCP) (31975533) |  |  | Mike Truemner 1-903-323-4513 mtruemner@networkip.net | EDWARD JONES | edward.jones@optum.com | 1-952-219-4357 | 06/09/2020(Access) 06/09/2020(Private IP - PIP) 06/09/2020(WAN Analysis Reporting) |  |  | 06/18/2020 (31975534) 06/22/2020 (31975533) | 06/23/2020 06/29/2020 | 06/09/2020 |  | Completed | N (31975534) N (31975533) N (31975535) | U0101953 |  |  | NSPE0013819118
Completed | NY029-01-IJ | 1311 Mamaroneck Ave ste 240 White Plains, NY 10605-5222 US | 300 MBPS (32035707) | 06/23/2020: Order Completed on Jun 23, 2020 | 202962525 | NY029-01-IJ White Plains NY | Private IP - PIP (32035706) WAN Analysis Reporting (32035708) Access (32035707) | 32035706 32035708 32035707 | 200 MBPS (32035706) |  | 94806923 (Private IP (PIP)) 94806927 (WAN Analysis Reporting) 94806925 (Access) | C5010325/ADD (32035706) E5026280/ADD (32035707) | 32.KFGS.223048..NY (3203570793026702) | 6127497 | 150000 | PVC ID : 6127497 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64819 PE IP Address : 147.225.70.229 CE Address : 147.225.70.230 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32035707) | 1000Base-SX (850nm, Multi Mode Fiber) (32035707) | Ethernet | VERIZON (3203570793026701) VERIZON (3203570793026702) | 06/15/2020 (3203570793026701) 06/12/2020 (3203570793026702) | 06/19/2020 (3203570793026702) | 06/18/2020 (3203570793026702) | 06/23/2020 (VFORCE) (32035707) | 06/23/2020 (VFORCE) (32035707) | DEMARCDET - 1st floor sweet 160 server room wall mounted nid |  | Danielle Maiorana 1-347-909-1344 Danielle_maiorana@uhg.com | Ajai S | ajai@optum.com | 1-952-885-4060 | 06/23/2020(Private IP - PIP) 06/23/2020(WAN Analysis Reporting) 06/23/2020(Access) |  |  | 06/30/2020 (32035706) 06/26/2020 (32035707) | 07/09/2020 07/15/2020 | 06/23/2020 |  | Completed | N (32035706) N (32035708) N (32035707) | U0101953 |  |  | NSPE0013823011
Completed | TX023 | 1311 W President George Bush Hwy Richardson, TX 75080-1153 US | 300 MBPS (32072428) | 08/27/2020: Order Completed on Aug 26, 2020 | 203032661 | TX023-05-IJ Richardson, TX | WAN Analysis Reporting (32072429) Access (32072428) Private IP - PIP (32072427) | 32072429 32072428 32072427 | 150 MBPS (32072427) |  | 94811099 (WAN Analysis Reporting) 94811103 (Access) 94811101 (Private IP (PIP)) | C5010480/ADD (32072427) E5026468/ADD (32072428) | TX/KXFN/339353/LVLC (3207242822568901) | 6128217 | 110000 | PVC ID : 6128217 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64517 PE IP Address : 147.225.75.209 CE Address : 147.225.75.210 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32072428) | 1000Base-SX (850nm, Multi Mode Fiber) (32072428) | Ethernet | LEVEL 3 (3207242822568901) | 07/23/2020 (3207242822568901) | 08/20/2020 (3207242822568901) | 08/19/2020 (3207242822568901) | 08/26/2020 (VFORCE) (32072428) | 08/26/2020 (VFORCE) (32072428) | DEMARCDET - 38 flr row 1 rack 2 rack unit 42 media converter tagged with ckt id |  | JORGE ALVAREZ 1-214-273-8767 jorge_alvarez@optum.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 08/26/2020(WAN Analysis Reporting) 08/26/2020(Access) 08/26/2020(Private IP - PIP) |  |  | 08/31/2020 (32072427) 08/27/2020 (32072428) | 09/09/2020 09/02/2020 | 08/26/2020 |  | Completed | N (32072429) N (32072428) N (32072427) | U0101953 | Jeopardy Notification 1 (07/16/2020) |  | NSPE0013845052
Completed | TX529 | 2563 Sw Grapevine Pkwy Grapevine, TX 76051-7072 US | 100 MBPS (32072336) | 07/30/2020: Circuit delivered. Beas install scheduled for 8/4. | 203032739 | TX529 | Private IP - PIP (32072334) WAN Analysis Reporting (32072337) Access (32072336) | 32072334 32072337 32072336 | 50 MBPS (32072334) |  | 94810835 (Private IP (PIP)) 94810838 (WAN Analysis Reporting) 94810833 (Access) | C1132853/ADD (32072334) E4059694/ADD (32072336) | 81.L1XX.911683..CHTR (3207233679053001) | 6128208 | 30000 | PVC ID : 6128208 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65371 PE IP Address : 147.225.114.1 CE Address : 147.225.114.2 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32072336) | 1000Base-LX (1310nm Single Mode Fiber) (32072336) | Ethernet | TIME WARNER CABLE (3207233679053001) | 06/09/2020 (3207233679053001) | 09/25/2020 (3207233679053001) | 07/30/2020 (3207233679053001) | 08/04/2020 (VFORCE) (32072336) | 08/04/2020 (VFORCE) (32072336) | DEMARCDET - 1st floor IT server room Rack locationRU14 |  | KEVIN JOSLYN 1-952-833-6548 kevin_joslyn@optum.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 08/05/2020(Private IP - PIP) 08/05/2020(WAN Analysis Reporting) 08/05/2020(Access) |  |  | 10/06/2020 (32072334) 10/02/2020 (32072336) | 07/20/2020 07/24/2020 | 08/05/2020 |  | Completed | N (32072334) N (32072337) N (32072336) | U0101953 |  |  | NSPE0013844598
Completed | LA014 | 2633 Napoleon Ave New Orleans, LA 70115-6357 US | 100 MBPS (32086013) | 11/25/2020: Order Completed on Nov 24, 2020 | 203042311 | LA014 | Private IP - PIP (32086012) WAN Analysis Reporting (32086014) Access (32086013) | 32086012 32086014 32086013 | 40 MBPS (32086012) |  | 94811313 (Private IP (PIP)) 94811318 (WAN Analysis Reporting) 94811316 (Access) | C1132900/ADD (32086012) E4059744/ADD (32086013) | LA/KXFN/406163/LVLC (3208601379132102) | 6128439 | 25000 | PVC ID : 6128439 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65374 PE IP Address : 152.183.53.73 CE Address : 152.183.53.74 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32086013) | 1000Base-LX (1310nm Single Mode Fiber) (32086013) | Ethernet | LEVEL 3 (3208601379132102) | 10/19/2020 (3208601379132102) | 12/07/2020 (3208601379132102) | 11/20/2020 (3208601379132102) | 11/24/2020 (VFORCE) (32086013) | 11/24/2020 (VFORCE) (32086013) | DEMARCDET - 4th floor IT room is in room 4. The fiber panel is in the rack to the right and top. |  | Julia Ware 1-504-620-5651 Jware@primarycareplus.com | Solomon Victor | solomon_victor@optum.com | 91-804-670-4304 | 11/24/2020(Private IP - PIP) 11/24/2020(WAN Analysis Reporting) 11/24/2020(Access) |  |  | 12/16/2020 (32086012) 12/14/2020 (32086013) | 12/01/2020 12/07/2020 | 11/24/2020 |  | Scheduled | N (32086012) N (32086014) N (32086013) | U0101953 |  |  | NSPE0013847823
Completed | TX569 | 7461 Airport Fwy Richland Hills, TX 76118-6955 US | 50 MBPS (32110723) | 08/27/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 203051391 | TX569 | Private IP - PIP (32110722) WAN Analysis Reporting (32110724) Access (32110723) | 32110722 32110724 32110723 | 10 MBPS (32110722) |  | 94811619 (Private IP (PIP)) 94811623 (WAN Analysis Reporting) 94811625 (Access) | C4023232/ADD (32110722) E4059833/ADD (32110723) | 81.L1XX.911708..CHTR (3211072379183401) | 6128881 | 5500 | PVC ID : 6128881 VPN Name : UnitedHealthGroup Router Name : RCN3E02 VRF Name : Vh26648-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65368 PE IP Address : 152.162.50.101 CE Address : 152.162.50.102 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32110723) | 1000Base-SX (850nm, Multi Mode Fiber) (32110723) | Ethernet | CHARTER (3211072379183401) | 06/15/2020 (3211072379183401) | 09/30/2020 (3211072379183401) | 08/20/2020 (3211072379183401) | 08/25/2020 (VFORCE) (32110723) | 08/25/2020 (VFORCE) (32110723) | DEMARCDET - 1ST FLOOR SERVER ROOM WALL MOUNTED |  | Khanh Nguyen 1-817-368-6081 knguyen11@wellmed.net | Philip Damasco | philip_damasco@optum.com | 632-790-6235 | 08/25/2020(Private IP - PIP) 08/25/2020(WAN Analysis Reporting) 08/25/2020(Access) |  |  | 10/09/2020 (32110722) 10/07/2020 (32110723) | 12/09/2020 12/15/2020 | 08/25/2020 |  | Completed | N (32110722) N (32110724) N (32110723) | U0101953 |  |  | NSPE0013850632
Completed | TX013 | 1301 W President George Bush Hwy Richardson, TX 75080-1135 US | 50 MBPS (32124890) | 12/01/2020: Order Completed on Nov 30, 2020 | 203062683 | TX023-05-IJ Richardson | Private IP - PIP (32124889) WAN Analysis Reporting (32124891) Access (32124890) | 32124889 32124891 32124890 | 20 MBPS (32124889) |  | 1282530851 (Private IP (PIP)) 1282530863 (WAN Analysis Reporting) 1282530845 (Access) | C4023242/ADD (32124889) E4059857/ADD (32124890) | TX/KXFN/407646/LVLC (3212489016049501) | 6129096 | 13000 | PVC ID : 6129096 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65070 PE IP Address : 206.115.43.37 CE Address : 206.115.43.38 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32124890) | 1000Base-LX (1310nm Single Mode Fiber) (32124890) | Ethernet | LEVEL 3 (3212489016049501) | 10/13/2020 (3212489016049501) | 11/11/2020 (3212489016049501) | 10/15/2020 (3212489016049501) | 11/30/2020 (VFORCE) (32124890) |  | DEMARCDET - RM MDF FLR MAIN BLDG MAIN |  | Nancy Ferrer 1-972-372-1284 nancy.ferrer@optum.com | Sushil Gautam | sushil_gautam@uhc.com | 91-124-309-5736 | 11/30/2020(Private IP - PIP) 11/30/2020(WAN Analysis Reporting) 11/30/2020(Access) |  |  | 11/20/2020 (32124889) 11/18/2020 (32124890) | 12/18/2020 12/24/2020 | 11/30/2020 |  | Completed | N (32124889) N (32124891) N (32124890) | U0101953 |  |  | NSPE0013854125
Completed | UT019-05-IM | 1403 E SEGO LILY DR SANDY, UT 84092-4350 US | 100 MBPS (32147212) | 11/26/2020: Order Completed on Nov 25, 2020 | 203090777 | Pico UT019-01-IM | WAN Analysis Reporting (32147213) Access (32147212) Private IP - PIP (32147211) | 32147213 32147212 32147211 | 50 MBPS (32147211) |  | 1283634871 (WAN Analysis Reporting) 1283634865 (Access) 1283634869 (Private IP (PIP)) | C1133082/ADD (32147211) E4059935/ADD (32147212) | 67.KGGS.006505..CBCL.. (3214721238000401) | 6129501 | 30000 | PVC ID : 6129501 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64833 PE IP Address : 147.225.115.149 CE Address : 147.225.115.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32147212) | 1000Base-SX (850nm, Multi Mode Fiber) (32147212) | Ethernet | COMCAST (3214721238000401) | 10/15/2020 (3214721238000401) | 12/18/2020 (3214721238000401) | 11/24/2020 (3214721238000401) | 11/25/2020 (VFORCE) (32147212) |  | DEMARCDET - basement fire riser room equipment is wall mounted on the south wall |  | Clifton Matthews 1-385-274-3969 cliff.matthews@optum.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-990-179-8210 | 11/25/2020(WAN Analysis Reporting) 11/25/2020(Access) 11/25/2020(Private IP - PIP) |  |  | 12/30/2020 (32147211) 12/28/2020 (32147212) | 12/03/2020 11/25/2020 | 11/25/2020 |  | Completed | N (32147213) N (32147212) N (32147211) | U0101953 |  |  | NSPE0013862895
Completed | TX571-01-IM | 5449 BEAR LN STE 308 CORPUS CHRISTI, TX 78405-4124 US | 50 MBPS (32149981) | 10/19/2020: Order Completed on Oct 19, 2020 | 203093451 | TX571 | Private IP - PIP (32149980) WAN Analysis Reporting (32149982) Access (32149981) | 32149980 32149982 32149981 | 10 MBPS (32149980) |  | 1283717979 (Private IP (PIP)) 1283717981 (WAN Analysis Reporting) 1283717975 (Access) | C4023275/ADD (32149980) E4059940/ADD (32149981) | 36.L1XX.004973..CHTR (3214998179390501) | 6129538 | 5500 | PVC ID : 6129538 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65366 PE IP Address : 152.164.23.233 CE Address : 152.164.23.234 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32149981) | 1000Base-SX (850nm, Multi Mode Fiber) (32149981) | Ethernet | TIME WARNER CABLE (3214998179390501) | 10/08/2020 (3214998179390501) | 10/22/2020 (3214998179390501) | 10/15/2020 (3214998179390501) | 10/19/2020 (VFORCE) (32149981) | 10/19/2020 (VFORCE) (32149981) | DEMARCDET - FLR 1 SUITE 308 IT RM RACK MOUNTED |  | RICK WILLIAMSON 1-210-376-9633 rwilliamson@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 | 10/19/2020(Private IP - PIP) 10/19/2020(WAN Analysis Reporting) 10/19/2020(Access) |  |  | 10/29/2020 (32149980) 10/27/2020 (32149981) | 11/18/2020 11/24/2020 | 10/19/2020 |  | Completed | N (32149980) N (32149982) N (32149981) | U0101953 |  |  | NSPE0013863675
Completed | LA028-02-IM | 120 OCHSNER BLVD GRETNA, LA 70056-5255 US | 50 MBPS (32161322) | 10/08/2020: Order Completed on Oct 8, 2020 | 203104029 | LA028 | Private IP - PIP (32161321) WAN Analysis Reporting (32161323) Access (32161322) | 32161321 32161323 32161322 | 30 MBPS (32161321) |  | 1284135289 (Private IP (PIP)) 1284135291 (WAN Analysis Reporting) 1284135285 (Access) | C4023293/ADD (32161321) E4059973/ADD (32161322) | /ETH/143726//UIF/ (3216132279383001) | 6129734 | 17000 | PVC ID : 6129734 VPN Name : UnitedHealthGroup Router Name : NWO2GE01 VRF Name : V486980:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65389 PE IP Address : 152.164.218.161 CE Address : 152.164.218.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32161322) | 1000Base-SX (850nm, Multi Mode Fiber) (32161322) | Ethernet | SOUTHERN LIGHT (3216132279383001) | 06/17/2020 (3216132279383001) | 08/17/2020 (3216132279383001) | 10/05/2020 (3216132279383001) | 10/08/2020 (VFORCE) (32161322) | 10/08/2020 (VFORCE) (32161322) | DEMARCDET - Main buld 1st Floor MDF room |  | Bonita Augustine 1-504-620-5663 Baugustine@primarycareplus.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-804-670-4304 | 10/08/2020(Private IP - PIP) 10/08/2020(WAN Analysis Reporting) 10/08/2020(Access) |  |  | 09/18/2020 (32161321) 09/16/2020 (32161322) | 10/15/2020 10/21/2020 | 10/08/2020 |  | Completed | N (32161321) N (32161323) N (32161322) | U0101953 |  |  | NSPE0013866855
Completed | FL445-01-IM | 7775 SW 87TH AVE MIAMI, FL 33173-2536 US | 50 MBPS (32169190) | 09/15/2020: Order Completed on Sep 8, 2020 | 203110979 | FL445 | Access (32169190) Private IP - PIP (32169189) WAN Analysis Reporting (32169191) | 32169190 32169189 32169191 | 10 MBPS (32169189) |  | 1284353255 (Access) 1284353259 (Private IP (PIP)) 1284353261 (WAN Analysis Reporting) | E4059994/ADD (32169190) C4023302/ADD (32169189) |  | 6129918 | 5500 | PVC ID : 6129918 VPN Name : UnitedHealthGroup Router Name : 94J9E02 VRF Name : Vh50351:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65364 PE IP Address : 152.183.6.85 CE Address : 152.183.6.86 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32169190) | 1000Base-SX (850nm, Multi Mode Fiber) (32169190) | Ethernet | ATT (3216919079442901) | 08/31/2020 (3216919079442901) |  | 09/03/2020 (3216919079442901) | 09/08/2020 (VFORCE) (32169190) | 09/08/2020 (VFORCE) (32169190) | DEMARCDET - 1ST FLR IT RM RACKMOUNTED |  | TODD VANDERSCHAEGEN 1-813-629-2611 tvanderschaegen@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 09/08/2020(Access) 09/08/2020(Private IP - PIP) 09/08/2020(WAN Analysis Reporting) |  |  | 09/11/2020 (32169190) 09/15/2020 (32169189) | 10/12/2020 10/16/2020 | 09/08/2020 |  | Completed | N (32169190) N (32169189) N (32169191) | U0101953 |  |  | NSPE0013868685
Completed | LA047-01-IM | 3625 HOUMA BLVD METAIRIE, LA 70006-4229 US | 100 MBPS (32169197) | 07/30/2020: Beas install incomplete. Pending LEC correction on SFP card to be MMF. | 203110921 | LA047 | Private IP - PIP (32169196) WAN Analysis Reporting (32169198) Access (32169197) | 32169196 32169198 32169197 | 50 MBPS (32169196) |  | 1284153801 (Private IP (PIP)) 1284153803 (WAN Analysis Reporting) 1284153797 (Access) | C1133379/ADD (32169196) E4059993/ADD (32169197) | 27.KFGX.000384..COXC. (3216919779310401) | 6129919 | 30000 | PVC ID : 6129919 VPN Name : UnitedHealthGroup Router Name : NWO2GE01 VRF Name : V486980:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65369 PE IP Address : 152.164.250.201 CE Address : 152.164.250.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32169197) | 1000Base-SX (850nm, Multi Mode Fiber) (32169197) | Ethernet | COX (3216919779310401) | 06/23/2020 (3216919779310401) | 07/24/2020 (3216919779310401) | 07/23/2020 (3216919779310401) | 08/04/2020 (VFORCE) (32169197) | 08/04/2020 (VFORCE) (32169197) | DEMARCDET - basement telco room Cox rack Acedian port 3 tagged with CKT ID fiber handoff |  | Dawn Gwin 1-504-681-8985 Dawn_gwin@uhg.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 08/04/2020(Private IP - PIP) 08/04/2020(WAN Analysis Reporting) 08/04/2020(Access) |  |  | 08/04/2020 (32169196) 07/31/2020 (32169197) | 07/30/2020 08/05/2020 | 08/04/2020 |  | Completed | N (32169196) N (32169198) N (32169197) | U0101953 |  |  | NSPE0013868385
Completed | UAL11-01-IM | 650 CLINIC DR MOBILE, AL 36688-0001 US | 1 GBPS (32170296) | 07/27/2020: Order Completed on Jul 27, 2020 | 203113031 | AL708 | Private IP - PIP (32170295) WAN Analysis Reporting (32170297) Access (32170296) | 32170295 32170297 32170296 | 500 MBPS (32170295) |  | 1284477817 (Private IP (PIP)) 1284477819 (WAN Analysis Reporting) 1284477813 (Access) | C0198208/ADD (32170295) E5026690/ADD (32170296) | /ETH/143745//UIF/ (3217029679309901) | 6129935 | 350000 | PVC ID : 6129935 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65362 PE IP Address : 152.177.127.233 CE Address : 152.177.127.234 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32170296) | 1000Base-SX (850nm, Multi Mode Fiber) (32170296) | Ethernet | SOUTHERN LIGHT (3217029679309901) | 06/18/2020 (3217029679309901) | 07/24/2020 (3217029679309901) | 07/23/2020 (3217029679309901) | 07/27/2020 (VFORCE) (32170296) | 07/24/2020 (VFORCE) (32170296) | DEMARCDET - main building on the 1st floor in the MDF room tagged with circuit ID |  | Roy Franklin 1-251-272-0856 Roy.Franklin@uniti.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-804-670-4304 | 07/27/2020(Private IP - PIP) 07/27/2020(WAN Analysis Reporting) 07/27/2020(Access) |  |  | 08/26/2020 (32170295) 08/24/2020 (32170296) | 07/30/2020 08/05/2020 | 07/27/2020 |  | Completed | N (32170295) N (32170297) N (32170296) | U0101953 |  |  | NSPE0013869552
Completed | PA120 | 1001 Adams Ave Norristown, PA 19403-2401 US | 50 MBPS (32201333) | 07/02/2020: Order Completed on Jul 2, 2020 | 203051567 | PA120 | Private IP - PIP (32201332) WAN Analysis Reporting (32201334) Access (32201333) | 32201332 32201334 32201333 | 10 MBPS (32201332) |  | 94811376 (Private IP (PIP)) 94811381 (WAN Analysis Reporting) 94811379 (Access) | C4023334/ADD (32201332) E4060084/ADD (32201333) | 11.KFGS.313259..PA (3220133379192701) | 6130541 | 5500 | PVC ID : 6130541 VPN Name : UnitedHealthGroup Router Name : PBYXE04 VRF Name : Vd28902-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65370 PE IP Address : 152.181.230.161 CE Address : 152.181.230.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32201333) | 1000Base-SX (850nm, Multi Mode Fiber) (32201333) | Ethernet | VERIZON (3220133379192701) | 06/23/2020 (3220133379192701) | 06/29/2020 (3220133379192701) | 06/30/2020 (3220133379192701) | 07/02/2020 (VFORCE) (32201333) |  | DEMARCDET - 1st floor room 1.r138 data closet wall mounted,cangoa lable OPAS |  | Andrew Lexa 1-610-550-7935 Andrew.lexa@optum.com | Philip Damasco | philip_damasco@optum.com | 632-790-6235 | 07/02/2020(Private IP - PIP) 07/02/2020(WAN Analysis Reporting) 07/02/2020(Access) |  |  | 07/09/2020 (32201332) 07/07/2020 (32201333) | 07/22/2020 07/28/2020 | 07/02/2020 |  | Completed | N (32201332) N (32201334) N (32201333) | U0101953 |  |  | NSPE0013850704
Completed | TX576 | 1517 S Mccoll Rd Edinburg, TX 78539-3108 US | 50 MBPS (32206000) | 10/30/2020: Order Completed on Oct 30, 2020 | 203147211 | TX576 | Private IP - PIP (32205999) WAN Analysis Reporting (32206001) Access (32206000) | 32205999 32206001 32206000 | 10 MBPS (32205999) |  | 94818704 (Private IP (PIP)) 94818706 (WAN Analysis Reporting) 94818708 (Access) | C4023337/ADD (32205999) E4060093/ADD (32206000) | 38/KRGN/614070//SW (3220600079527801) | 6130631 | 5500 | PVC ID : 6130631 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65443 PE IP Address : 152.162.17.165 CE Address : 152.162.17.166 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32206000) | 1000Base-SX (850nm, Multi Mode Fiber) (32206000) | Ethernet | ATT (3220600079527801) | 10/05/2020 (3220600079527801) | 10/12/2020 (3220600079527801) | 10/28/2020 (3220600079527801) | 11/02/2020 (VFORCE) (32206000) | 10/30/2020 (VFORCE) (32206000) | DEMARCDET - 2nd fl server rm |  | Shawna Malone 1-210-367-6342 shmalone@wellmed.net | Philip Damasco | philip_damasco@optum.com | 632-790-6235 | 10/30/2020(Private IP - PIP) 10/30/2020(WAN Analysis Reporting) 10/30/2020(Access) |  |  | 11/03/2020 (32205999) 10/30/2020 (32206000) | 12/07/2020 12/11/2020 | 10/30/2020 |  | Completed | N (32205999) N (32206001) N (32206000) | U0101953 |  |  | NSPE0013879934
Completed |  | 7383 COUNTY RD COLOGNE, MN 55322 USA | 4000 MBPS (CQBL2QKM) | 07/23/2020: Follow up sent to customer requesting for a date and time to be provided to schedule hotcut. | 10342113 |  | Private IP Port Only (CQBL2QKM) | CQBL2QKM | 4000 MBPS | P2308618 |  | BOBLJHT40001 (CQBL2QKM) |  |  | 2500000 | VPN Name : UnitedHealthGroup Router Name : MPLS9E01 VRF Name : Vd96554:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65398 PE IP Address : 68.136.41.205 CE Address : 68.136.41.206 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 07/27/2020 (CQBL2QKM) |  |  | 07/30/2020 (CQBL2QKM) | 07/27/2020 (CQBL2QKM) |  |  |  | N (CQBL2QKM) | 05017789 |  | remove VPN downgrade port | NSPE0013869474
Completed |  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBL2QKY) | 07/23/2020: Follow up sent to customer requesting for a date and time to be provided to schedule hotcut. | 10342112 |  | Private IP Port Only (CQBL2QKY) EVC/PVC Service (D.12394843.6091888) | CQBL2QKY D.12394843.6091888 | 4000 MBPS | P2309944 |  | BOBLJKFG0001 (CQBL2QKY) |  | 6091888 | 2500000 | VPN Name : UnitedHealthGroup Router Name : MN3XE01 VRF Name : Vd96545-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65398 PE IP Address : 68.138.99.217 CE Address : 68.138.99.218 QoS - Egress Profile: R12 PVC ID : 6091888 | [11 empty] | TIM GUNDERSON 0017637443141 7637442081 TIM_GUNDERSON@OPTUM.COM |  |  |  | 07/27/2020 (CQBL2QKY) |  |  | 07/30/2020 (CQBL2QKY) | 07/27/2020 (CQBL2QKY) |  |  |  | N (CQBL2QKY) N (D.12394843.6091888) | 05017789 P2309944 |  | remove VPN downgrade port | NSPE0013869483
Provisioning Accepted |  | 7383 COUNTY RD COLOGNE, MN 55322 USA | 4000 MBPS (CQBL2QJP) | 08/13/2020: Customer will let us know when changes can be take place after the 15th as unattended after-hours. | 10342111 |  | Private IP Port Only (CQBL2QJP) | CQBL2QJP | 4000 MBPS | P2308619 |  | BOBLJHT50001 (CQBL2QJP) |  | 6086264 6086262 | 2500000 | PVC ID : 6086264,6086262 VPN Name : UnitedHealthGroup Router Name : MZZ9E01 VRF Name : V600583:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65400 PE IP Address : 208.219.130.213 CE Address : 208.219.130.214 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/19/2020 (CQBL2QJP) |  |  | 08/19/2020 (CQBL2QJP) | 07/16/2020 (CQBL2QJP) |  |  |  | N (CQBL2QJP) | 05017789 |  | remove VPN downgrade port | NSPE0013869469
Provisioning Accepted |  | 511 11TH AVE S MINNEAPOLIS, MN 55415 USA | 4000 MBPS (CQBL2QH1) | 08/13/2020: Customer will let us know when changes can be take place after the 15th as unattended after-hours. | 10342110 |  | Private IP Port Only (CQBL2QH1) | CQBL2QH1 | 4000 MBPS | P2308555 |  | BOBLJHRP0001 (CQBL2QH1) |  | 6086392 6086391 | 2250000 | PVC ID : 6086392,6086391 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65400 PE IP Address : 152.164.113.173 CE Address : 152.164.113.174 QoS - Egress Profile: R12 | [11 empty] | TIM GUNDERSON 0017637443000 TIM_GUNDERSON@OPTUM.COM |  |  |  | 08/19/2020 (CQBL2QH1) |  |  | 08/19/2020 (CQBL2QH1) | 07/16/2020 (CQBL2QH1) |  |  |  | N (CQBL2QH1) | 05017789 |  | remove VPN downgrade port | NSPE0013869458
Completed | NY510 | 2805 Veterans Memorial Hwy ste 19 Ronkonkoma, NY 11779-7683 US | 100 MBPS (32449334) | 07/17/2020: Order Completed on Jul 17, 2020 | 203189139 | NY510 | Access (32449334) Private IP - PIP (32449333) WAN Analysis Reporting (32449335) | 32449334 32449333 32449335 | 50 MBPS (32449333) |  | 94820787 (Access) 94820785 (Private IP (PIP)) 94820790 (WAN Analysis Reporting) | E4060807/ADD (32449334) C1144127/ADD (32449333) | 32.KFGS.223298..NY (3244933480001201) | 6176535 | 30000 | PVC ID : 6176535 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65016 PE IP Address : 152.162.57.185 CE Address : 152.162.57.186 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32449334) | 1000Base-SX (850nm, Multi Mode Fiber) (32449334) | Ethernet | VERIZON (3244933480001201) | 07/13/2020 (3244933480001201) | 07/20/2020 (3244933480001201) | 07/17/2020 (3244933480001201) |  |  | DEMARCDET - 1st flr server room rack-mounted tagged |  | Brian Stockfisch 1-810-768-9920 bstockfisch@diplomat.is | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 07/17/2020(Access) 07/17/2020(Private IP - PIP) 07/17/2020(WAN Analysis Reporting) |  |  | 07/27/2020 (32449334) 07/29/2020 (32449333) | 08/07/2020 08/13/2020 | 07/17/2020 |  | Completed | N (32449334) N (32449333) N (32449335) | U0101953 |  |  | NSPE0013888825
Completed | NC062 | 311 Pomona Dr Greensboro, NC 27407-1693 US | 50 MBPS (32280066) | 07/30/2020: Beas install scheduled for 8/4. | 203203709 | NC062 | Private IP - PIP (32280065) WAN Analysis Reporting (32280067) Access (32280066) | 32280065 32280067 32280066 | 30 MBPS (32280065) |  | 94822982 (Private IP (PIP)) 94822988 (WAN Analysis Reporting) 94822986 (Access) | C4023449/ADD (32280065) E4060402/ADD (32280066) | 33.L1XX.807384..CHTR (3228006680139201) | 6175132 | 17000 | PVC ID : 6175132 VPN Name : UnitedHealthGroup Router Name : CHRL9E01 VRF Name : V638950:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65359 PE IP Address : 152.164.147.29 CE Address : 152.164.147.30 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32280066) | 1000Base-SX (850nm, Multi Mode Fiber) (32280066) | Ethernet | TIME WARNER CABLE (3228006680139201) | 07/02/2020 (3228006680139201) | 08/31/2020 (3228006680139201) | 07/29/2020 (3228006680139201) | 08/04/2020 (VFORCE) (32280066) | 08/04/2020 (VFORCE) (32280066) | DEMARCADDR - . DEMARCDET - 1ST Floor Suite B Server Room in the back of the building located on the top of the rack RAD203 Port 5 |  | Justin Dent 1-336-338-1753 JDent@diplomat.is | BRANDON LITTLE | Brandon_little@optum.com | 1-952-687-3694 | 08/04/2020(Private IP - PIP) 08/04/2020(WAN Analysis Reporting) 08/04/2020(Access) |  |  | 09/10/2020 (32280065) 09/08/2020 (32280066) | 08/12/2020 08/18/2020 | 08/04/2020 |  | Completed | N (32280065) N (32280067) N (32280066) | U0101953 |  |  | NSPE0013891976
Completed | MO045-01-IM | 103 CORPORATE LAKE DR STE B COLUMBIA, MO 65203-7290 US | 100 MBPS (32285614) | 09/14/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 203242059 | MO045 | Private IP - PIP (32285613) WAN Analysis Reporting (32285615) Access (32285614) | 32285613 32285615 32285614 | 50 MBPS (32285613) |  | 1288771731 (Private IP (PIP)) 1288771733 (WAN Analysis Reporting) 1288771727 (Access) | C1143264/ADD (32285613) E4060418/ADD (32285614) | 48.KXGS.530897..CTMO (3228561480188401) | 6175166 | 30000 | PVC ID : 6175166 VPN Name : UnitedHealthGroup Router Name : SC99E01 VRF Name : Vf03180:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65357 PE IP Address : 206.115.60.85 CE Address : 206.115.60.86 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32285614) | 1000Base-SX (850nm, Multi Mode Fiber) (32285614) | Ethernet | CENTURYLINK (3228561480188401) | 08/28/2020 (3228561480188401) | 09/08/2020 (3228561480188401) | 09/04/2020 (3228561480188401) | 09/09/2020 (VFORCE) (32285614) | 09/09/2020 (VFORCE) (32285614) | DEMARCADDR - X DEMARCDET - X |  | Kirsten Moloney 1-573-256-4279 kmoloney@diplomat.is | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 09/09/2020(Private IP - PIP) 09/09/2020(WAN Analysis Reporting) 09/09/2020(Access) |  |  | 09/17/2020 (32285613) 09/15/2020 (32285614) | 10/09/2020 10/15/2020 | 09/09/2020 |  | Completed | N (32285613) N (32285615) N (32285614) | U0101953 |  |  | NSPE0013900038
Completed | GA777-16-CM | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 08/13/2020: Hotcut schedule for 8/17 at 10pm CST. | 203284999 | Equinix hub Atlanta Peachtree GA777-04-IJ | Access (32454293) Private IP - PIP (32454292) WAN Analysis Reporting (32454294) | 32454293 32454292 32454294 | 5000 MBPS |  | 1254482815 (Access) 1254482819 (Private IP (PIP)) 1254483061 (WAN Analysis Reporting) | E7001612/REMOVE (32454293) C0186433/REMOVE (32454292) |  | 6130931 6126615 6114536 6126767 | 2500000 | PVC ID : 6130931,6126615,6114536,6126767 VPN Name : UnitedHealthGroup Router Name : 95JXE01 VRF Name : Vc78844-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65138 PE IP Address : 152.187.234.185 CE Address : 152.187.234.186 QoS - Egress Profile: R12 |  |  | Ethernet | [8 empty] | KEVIN ARTS 1-303-478-8532 kevin.arts@broad-path.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 | 08/18/2020(Access) 08/18/2020(Private IP - PIP) 08/18/2020(WAN Analysis Reporting) |  |  | 09/02/2020 (32454293) 09/02/2020 (32454292) | 08/11/2020 | 08/18/2020 |  | Completed | N (32454293) N (32454292) N (32454294) | U0101953 |  | DISCONNECT | NSPE0013908416
Completed | GA777-16-CM | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 07/30/2020: Patching and testing complete. Test and Install management is reviewing order see if at the time of the hot cut they can work the disco to free up the current port and then NOC move the new circuit that has the MVRF configuration to the old port. This will allow the customer to not have to order a new or change the current cross connect. Awaiting feedback from management. | 203284837 | Equinix hub Atlanta Peachtree GA777-04-IJ | Private IP - PIP (32344529) WAN Analysis Reporting (32344531) Access (32344530) | 32344529 32344531 32344530 | 5 GBPS (32344529) |  | 1289233821 (Private IP (PIP)) 1289233823 (WAN Analysis Reporting) 1289233817 (Access) | C0199725/ADD (32344529) E7002001/ADD (32344530) |  | 6175619 6175618 | 1000000 250000 | PVC ID : 6175619,6175618 VPN Name : UnitedHealthGroup,UnitedHealthGroup-ECCMA Router Name : 95JXE01 VRF Name : Vc78844-UnitedHealthGroup,Vh48743-UnitedHealthGroupECCMA Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65138 PE IP Address : v4-152.187.234.185,v6-147.225.75.21 CE Address : v4-152.187.234.186,v6-147.225.75.22 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (32344530) | Ethernet | [8 empty] | KEVIN ARTS 1-303-478-8532 kevin.arts@broad-path.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 | 07/28/2020(Private IP - PIP) 07/28/2020(WAN Analysis Reporting) 07/28/2020(Access) |  |  | 07/27/2020 (32344529) 07/27/2020 (32344530) | 08/11/2020 08/17/2020 | 07/28/2020 |  | Completed | N (32344529) N (32344531) N (32344530) | U0101953 |  |  | NSPE0013906536
Completed | TX479 | 300 Burnett St Fort Worth, TX 76102-2710 US | 500 MBPS (32342490) | 08/27/2020: Order Completed on Aug 21, 2020 | 203279253 | TX479 | Private IP - PIP (32342489) WAN Analysis Reporting (32342491) Access (32342490) | 32342489 32342491 32342490 | 300 MBPS (32342489) |  | 94829314 (Private IP (PIP)) 94829318 (WAN Analysis Reporting) 94829320 (Access) | C5010716/ADD (32342489) E5027048/ADD (32342490) | TX/KXFN/419180/LVLC (3234249078991501) | 6175582 | 180000 | PVC ID : 6175582 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65085 PE IP Address : 206.115.7.105 CE Address : 206.115.7.106 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32342490) | 1000Base-LX (1310nm Single Mode Fiber) (32342490) | Ethernet | LEVEL 3 (3234249078991501) | 07/07/2020 (3234249078991501) | 08/20/2020 (3234249078991501) | 08/18/2020 (3234249078991501) | 08/24/2020 (VFORCE) (32342490) |  | DEMARCDET - 3rd floor, server room, rack N, RMU 45, port 4, SM/LC, tagged with TX/KXFN/419180/LVLC |  | Nathan Staub 1-817-878-3466 staubn@ushealthgroup.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 08/21/2020(Private IP - PIP) 08/21/2020(WAN Analysis Reporting) 08/21/2020(Access) |  |  | 08/31/2020 (32342489) 08/27/2020 (32342490) | 09/30/2020 10/06/2020 | 08/21/2020 |  | Completed | N (32342489) N (32342491) N (32342490) | U0101953 |  |  | NSPE0013907209
Completed | CT187-01-IM | 100 CORPORATE DR STE 111 WINDSOR, CT 06095-2119 US | 100 MBPS (32343037) | 11/03/2020: Order Completed on Nov 2, 2020 | 203282869 | Windsor | Private IP - PIP (32343036) WAN Analysis Reporting (32343038) Access (32343037) | 32343036 32343038 32343037 | 30 MBPS (32343036) |  | 1288878817 (Private IP (PIP)) 1288878819 (WAN Analysis Reporting) 1288878813 (Access) | C1143371/ADD (32343036) E4060563/ADD (32343037) | 20.KGGS.035389..CBCL.. (3234303781042301) | 6175596 | 17000 | PVC ID : 6175596 VPN Name : UnitedHealthGroup Router Name : HLB9E01 VRF Name : V385919:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65352 PE IP Address : 147.225.236.141 CE Address : 147.225.236.142 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32343037) | 1000Base-SX (850nm, Multi Mode Fiber) (32343037) | Ethernet | COMCAST (3234303781042301) | 09/17/2020 (3234303781042301) | 10/19/2020 (3234303781042301) | 10/29/2020 (3234303781042301) | 11/02/2020 (VFORCE) (32343037) | 11/02/2020 (VFORCE) (32343037) | DEMARCDET - 1st floor server room rack mounted in rack 2 labeled w/ comcast CLLI and UNI |  | JENNIFER SACCO 1-800-243-4621 jsacco@diplomat.is | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 11/02/2020(Private IP - PIP) 11/02/2020(WAN Analysis Reporting) 11/02/2020(Access) |  |  | 10/28/2020 (32343036) 10/26/2020 (32343037) | 10/28/2020 11/03/2020 | 11/02/2020 |  | Completed | N (32343036) N (32343038) N (32343037) | U0101953 |  |  | NSPE0013907663
Completed | IA028-01-IM | 10607 AURORA AVE URBANDALE, IA 50322-7927 US | 50 MBPS (32394637) | 07/30/2020: FOC date 8/5. | 203243131 | Urbandale | WAN Analysis Reporting (32394638) Access (32394637) Private IP - PIP (32394636) | 32394638 32394637 32394636 | 10 MBPS (32394636) |  | 1288863221 (WAN Analysis Reporting) 1288863215 (Access) 1288863219 (Private IP (PIP)) | C4023556/ADD (32394636) E4060666/ADD (32394637) | 01.KXGS.536638..NW (3239463780941501) | 6176000 | 5500 | PVC ID : 6176000 VPN Name : UnitedHealthGroup Router Name : PLSHXE01 VRF Name : V588242-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65354 PE IP Address : 147.225.58.145 CE Address : 147.225.58.146 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32394637) | 1000Base-SX (850nm, Multi Mode Fiber) (32394637) | Ethernet | CENTURYLINK (3239463780941501) | 07/24/2020 (3239463780941501) | 08/05/2020 (3239463780941501) | 07/31/2020 (3239463780941501) | 08/05/2020 (VFORCE) (32394637) | 08/05/2020 (VFORCE) (32394637) | DEMARCADDR - X DEMARCDET - X |  | BRIAN STOCKFISCH 1-810-768-9920 bstockfisch@diplomat.is | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 08/05/2020(WAN Analysis Reporting) 08/05/2020(Access) 08/05/2020(Private IP - PIP) |  |  | 08/14/2020 (32394636) 08/12/2020 (32394637) | 08/18/2020 08/12/2020 | 08/05/2020 |  | Completed | N (32394638) N (32394637) N (32394636) | U0101953 |  |  | NSPE0013900239
Completed | NV058-01-IM | 1650 SPRING GATE LN STE 100 LAS VEGAS, NV 89134-6200 US | 100 MBPS (32357896) | 08/06/2020: Beas install scheduled for 8/11. | 203295593 | NV058-02-IJ Catamaran Las Vegas | Private IP - PIP (32357895) WAN Analysis Reporting (32357897) Access (32357896) | 32357895 32357897 32357896 | 50 MBPS (32357895) |  | 1288908241 (Private IP (PIP)) 1288909923 (WAN Analysis Reporting) 1288908237 (Access) | C1143397/ADD (32357895) E4060588/ADD (32357896) | 33.KFGX.002137..COXC. (3235789612847201) | 6175683 | 30000 | PVC ID : 6175683 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64643 PE IP Address : 152.162.155.25 CE Address : 152.162.155.26 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32357896) | 1000Base-LX (1310nm Single Mode Fiber) (32357896) | Ethernet | COX (3235789612847201) | 07/08/2020 (3235789612847201) | 08/05/2020 (3235789612847201) | 08/05/2020 (3235789612847201) | 08/11/2020 (VFORCE) (32357896) | 08/11/2020 (VFORCE) (32357896) | DEMARCDET - 1st flr MDF rm |  | Larry Batson 1-702-242-7222 larry_batson@uhg.com | KELLY BEST | kelly.best@optum.com | 1-702-304-2988 | 08/11/2020(Private IP - PIP) 08/11/2020(WAN Analysis Reporting) 08/11/2020(Access) |  |  | 08/14/2020 (32357895) 08/12/2020 (32357896) | 08/17/2020 08/21/2020 | 08/11/2020 |  | Completed | N (32357895) N (32357897) N (32357896) | U0101953 |  |  | NSPE0013910244
Completed | CA453-01-IM | 1819 ASTON AVE CARLSBAD, CA 92008-7338 US | 100 MBPS (32360474) | 08/07/2020: Beas install scheduled for 8/10. | 203299313 | Carlsbad | Private IP - PIP (32360473) WAN Analysis Reporting (32360475) Access (32360474) | 32360473 32360475 32360474 | 30 MBPS (32360473) |  | 1288923445 (Private IP (PIP)) 1288923447 (WAN Analysis Reporting) 1288923001 (Access) | C1143387/ADD (32360473) E4060574/ADD (32360474) | 11.KFGX.001451..COXC. (3236047480951201) | 6175660 | 17000 | PVC ID : 6175660 VPN Name : UnitedHealthGroup Router Name : SDGGE01 VRF Name : V464391:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65350 PE IP Address : 152.162.36.1 CE Address : 152.162.36.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32360474) | 1000Base-SX (850nm, Multi Mode Fiber) (32360474) | Ethernet | COX (3236047480951201) | 07/31/2020 (3236047480951201) | 08/06/2020 (3236047480951201) | 08/06/2020 (3236047480951201) | 08/10/2020 (VFORCE) (32360474) | 08/10/2020 (VFORCE) (32360474) | DEMARCADDR - 1 DEMARCDET - suite 104 server room customer rack top shelf |  | Rose Feaver 1-760-607-2137 rfeaver@diplomat.is | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 08/10/2020(Private IP - PIP) 08/10/2020(WAN Analysis Reporting) 08/10/2020(Access) |  |  | 08/17/2020 (32360473) 08/13/2020 (32360474) | 09/11/2020 09/17/2020 | 08/12/2020 |  | Completed | N (32360473) N (32360475) N (32360474) | U0101953 |  |  | NSPE0013910382
Completed | CA777-10-CM | 600 W 7TH ST FL 6 LOS ANGELES, CA 90017-3859 US |  | 07/23/2020: Hotcut complete and circuit accepted 7/21. | 203326391 | Equinix Internet Los Angeles | Private IP - PIP (32387527) Access WAN Analysis Reporting (32387529) | 32387527 32387529 | 2 GBPS (32387527) |  | 1254291223 (Private IP (PIP)) 1254291139 1254291225 (WAN Analysis Reporting) | C0186431/NONE (32387527) |  | 6114533 | 2500 | PVC ID : 6114533 VPN Name : UnitedHealthGroup Router Name : LL6XE01 VRF Name : V510590-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65155 PE IP Address : 208.219.143.193 CE Address : 208.219.143.194 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) | Ethernet | [8 empty] | EMAD BHATT 1-952-833-7538 emad@optum.com | EMAD BHATT | emad@optum.com | 1-952-833-7538 | 07/21/2020(Private IP |  |  | 07/16/2020 (32387527) | 07/20/2020 07/20/2020 (6275375.7) | 07/21/2020 |  | Completed Activated/Installed | N (32387527) N N (32387529) | U0101953 |  |  | NSPE0013916449
Completed | OH160 | 7167 E Kemper Rd Cincinnati, OH 45249-1028 US | 200 MBPS (32238876) | 07/22/2020: Order Completed on Jul 22, 2020 | 203183893 | OH160 | Private IP - PIP (32238875) WAN Analysis Reporting (32238877) Access (32238876) | 32238875 32238877 32238876 | 100 MBPS (32238875) |  | 94820547 (Private IP (PIP)) 94820551 (WAN Analysis Reporting) 94820544 (Access) | C5010614/ADD (32238875) E5026885/ADD (32238876) | /KFGS/565098//CB (3223887679974301) | 6131439 | 70000 | PVC ID : 6131439 VPN Name : UnitedHealthGroup Router Name : WYV9E01 VRF Name : V605408:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64636 PE IP Address : 152.183.235.21 CE Address : 152.183.235.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32238876) | 1000Base-SX (850nm, Multi Mode Fiber) (32238876) | Ethernet | CINCINNATTI BELL (3223887679974301) | 06/26/2020 (3223887679974301) | 07/21/2020 (3223887679974301) | 07/22/2020 (3223887679974301) | 07/22/2020 (VFORCE) (32238876) | 07/22/2020 (VFORCE) (32238876) | DEMARCADDR - 2 DEMARCDET - 2 |  | Brian Stockfisch 1-810-768-9920 bstockfisch@diplomat.is | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 07/22/2020(Private IP - PIP) 07/22/2020(WAN Analysis Reporting) 07/22/2020(Access) |  |  | 07/30/2020 (32238875) 07/28/2020 (32238876) | 08/06/2020 08/12/2020 | 07/22/2020 |  | Completed | N (32238875) N (32238877) N (32238876) | U0101953 |  |  | NSPE0013887808
Completed | NC063 | 220 Horizon Dr Raleigh, NC 27615-4928 US | 100 MBPS (32254824) | 07/30/2020: Pending end to end testing and completion of order. | 203200801 | NC063 | WAN Analysis Reporting (32254825) Access (32254824) Private IP - PIP (32254823) | 32254825 32254824 32254823 | 50 MBPS (32254823) |  | 94822955 (WAN Analysis Reporting) 94822953 (Access) 94822949 (Private IP (PIP)) | C1143189/ADD (32254823) E4060316/ADD (32254824) | 26/KRGN/402249//SB (3225482480131601) | 6174579 | 30000 | PVC ID : 6174579 VPN Name : UnitedHealthGroup Router Name : RLGH9E01 VRF Name : V477622:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65360 PE IP Address : 152.164.118.37 CE Address : 152.164.118.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32254824) | 1000Base-SX (850nm, Multi Mode Fiber) (32254824) | Ethernet | ATT (3225482480131601) | 06/29/2020 (3225482480131601) | 07/06/2020 (3225482480131601) | 07/06/2020 (3225482480131601) | 07/30/2020 (VFORCE) (32254824) | 07/30/2020 (VFORCE) (32254824) | DEMARCDET - 1ST FLR SUITE 1 TELCO SERVER RM FIBER JACK |  | Brian Stockfisch 1-810-768-9920 bstockfisch@diplomat.is | BRANDON LITTLE | Brandon_little@optum.com | 1-952-687-3694 | 07/30/2020(WAN Analysis Reporting) 07/30/2020(Access) 07/30/2020(Private IP - PIP) |  |  | 07/15/2020 (32254823) 07/13/2020 (32254824) | 08/14/2020 08/10/2020 | 07/30/2020 |  | Completed | N (32254825) N (32254824) N (32254823) | U0101953 |  |  | NSPE0013891400
Completed | UOK07 | 755 Research Pkwy Oklahoma City, OK 73104-3629 US | 100 MBPS (32457562) | 08/27/2020: Order Completed on Aug 21, 2020 | 203385131 | OK001 Oklahoma City | Private IP - PIP (32457561) WAN Analysis Reporting (32457563) Access (32457562) | 32457561 32457563 32457562 | 50 MBPS (32457561) |  | 94835766 (Private IP (PIP)) 94835763 (WAN Analysis Reporting) 94835761 (Access) | C1144157/ADD (32457561) E4060841/ADD (32457562) | 28.KFGX.101531..COXC. (3245756269192001) | 6176740 | 30000 | PVC ID : 6176740 VPN Name : UnitedHealthGroup Router Name : OKL3E01 VRF Name : Vh53846-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64892 PE IP Address : 206.115.28.217 CE Address : 206.115.28.218 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32457562) | 1000Base-SX (850nm, Multi Mode Fiber) (32457562) | Ethernet | COX (3245756269192001) | 07/14/2020 (3245756269192001) | 08/21/2020 (3245756269192001) | 08/19/2020 (3245756269192001) | 08/20/2020 (VFORCE) (32457562) |  | DEMARCDET - basement telco room next to room beside B00 labeled Cox |  | Lynn McClure 1-405-246-3672 lynn.mcclure@optum.com | Sushil Gautam | sushil_gautam@uhc.com | 1-763-744-2114 | 08/21/2020(Private IP - PIP) 08/21/2020(WAN Analysis Reporting) 08/21/2020(Access) |  |  | 09/01/2020 (32457561) 08/28/2020 (32457562) | 08/24/2020 08/28/2020 | 08/21/2020 |  | Completed | N (32457561) N (32457563) N (32457562) | U0101953 |  |  | NSPE0013930315
Completed | C1598-02-IJ NRECA | 8701 Firethorn Ln Lincoln, NE 68520-1402 US | 50 MBPS (32458267) | 08/27/2020: Order Completed on Aug 24, 2020 | 203386977 | C1598-02-IJ NRECA Lincoln NE | Private IP - PIP (32458266) WAN Analysis Reporting (32458268) Access (32458267) | 32458266 32458268 32458267 | 20 MBPS (32458266) |  | 94835917 (Private IP (PIP)) 94835915 (WAN Analysis Reporting) 94835920 (Access) | C4023638/ADD (32458266) E4060845/ADD (32458267) | 40.L1XX.993795..CHTR (3245826713163401) | 6176752 | 13000 | PVC ID : 6176752 VPN Name : UnitedHealthGroup Router Name : IDCXE03 VRF Name : V560358-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65514 PE IP Address : 147.225.161.5 CE Address : 147.225.161.6 QoS - Egress Profile: R12 | 100Base-TX (32458267) | 100Base-TX (32458267) | Ethernet | TIME WARNER CABLE (3245826713163401) | 07/14/2020 (3245826713163401) | 11/24/2020 (3245826713163401) | 08/18/2020 (3245826713163401) | 08/24/2020 (VFORCE) (32458267) | 08/24/2020 (VFORCE) (32458267) | DEMARCDET - 1st floor, Comm room, Rack Location:D-06 RU-5 |  | Ted Sasse 1-402-483-9264 ted.sasse@nreca.coop | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 08/24/2020(Private IP - PIP) 08/24/2020(WAN Analysis Reporting) 08/24/2020(Access) |  |  | 12/09/2020 (32458266) 12/07/2020 (32458267) | 12/03/2020 12/09/2020 | 08/24/2020 |  | Completed | N (32458266) N (32458268) N (32458267) | U0101953 |  |  | NSPE0013930586
Completed | WA133 | 17930 International Blvd Seattle, WA 98188-4231 US | 400 MBPS (32516469) | 10/02/2020: Order Completed on Oct 2, 2020 | 203478803 | WA133 | Private IP - PIP (32516468) WAN Analysis Reporting (32516470) Access (32516469) | 32516468 32516470 32516469 | 200 MBPS (32516468) |  | 94845635 (Private IP (PIP)) 94845640 (WAN Analysis Reporting) 94845633 (Access) | C5010869/ADD (32516468) E5027394/ADD (32516469) | 04.KXGS.536979..PN (3251646981787301) | 6177614 | 110000 | PVC ID : 6177614 VPN Name : UnitedHealthGroup Router Name : K1B9E01 VRF Name : Vd53143:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65353 PE IP Address : 206.115.110.81 CE Address : 206.115.110.82 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32516469) | 1000Base-LX (1310nm Single Mode Fiber) (32516469) | Ethernet | CENTURYLINK (3251646981787301) | 09/10/2020 (3251646981787301) | 09/18/2020 (3251646981787301) | 09/15/2020 (3251646981787301) | 09/25/2020 (VFORCE) (32516469) |  | DEMARCDET - 1st floor telco room rack mounted ,have to see the end user for access |  | EMILIA RICH 1-763-361-9006 emilia_rich@uhg.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 10/02/2020(Private IP - PIP) 10/02/2020(WAN Analysis Reporting) 10/02/2020(Access) |  |  | 10/13/2020 (32516468) 10/09/2020 (32516469) | 11/12/2020 11/18/2020 | 10/02/2020 |  | Completed | N (32516468) N (32516470) N (32516469) | U0101953 |  |  | NSPE0013946679
Completed | TX591 | 7355 Barlite Blvd ste 301 San Antonio, TX 78224-1340 US | 500 MBPS (32515305) | 10/05/2020: Order Completed on Aug 13, 2020 | 203476405 | TX591 | Private IP - PIP (32515304) WAN Analysis Reporting (32515306) Access (32515305) | 32515304 32515306 32515305 | 200 MBPS (32515304) |  | 94845391 (Private IP (PIP)) 94845396 (WAN Analysis Reporting) 94845389 (Access) | C5010866/ADD (32515304) E5027388/ADD (32515305) | 21.L1XX.991113..CHTR (3251530581784401) | 6177593 | 180000 | PVC ID : 6177593 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64548 PE IP Address : 147.225.169.45 CE Address : 147.225.169.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32515305) | 1000Base-SX (850nm, Multi Mode Fiber) (32515305) | Ethernet | TIME WARNER CABLE (3251530581784401) | 07/21/2020 (3251530581784401) | 10/14/2020 (3251530581784401) | 08/10/2020 (3251530581784401) | 10/13/2020 (VFORCE) (32515305) | 10/13/2020 (VFORCE) (32515305) | DEMARCDET - 1st flr MDF rm adva port 6 |  | Christian Romero 1-210-727-7333 cgromero@samedgrp.com | Amit Shrivastava | amit_shrivastava21@optum.com | 91-804-670-4478 | 08/13/2020(Private IP - PIP) 08/13/2020(WAN Analysis Reporting) 08/13/2020(Access) |  |  | 10/23/2020 (32515304) 10/21/2020 (32515305) | 08/31/2020 09/04/2020 | 08/13/2020 |  | Completed | N (32515304) N (32515306) N (32515305) | U0101953 |  |  | NSPE0013945657
Completed | TX552-04-CM move circuit C4021013 | 4510 MEDICAL CENTER DR STE 311 MCKINNEY, TX 75069-1604 US | 50 MBPS (32447240) | 09/24/2020: LEC move scheduled for tonight at 6pm CST. | 203369099 | TX552 | Access (32447240) Private IP - PIP WAN Analysis Reporting (32447241) | 32447240 32447241 | 10 MBPS |  | 94739266 (Access) 94739264 94739262 (WAN Analysis Reporting) | E4053760/NONE (32447240) |  |  |  |  | 1000Base-SX-850nm (32447240) | 1000Base-SX (850nm, Multi Mode Fiber) (32447240) | Ethernet |  |  |  |  | 08/24/2020 (VFORCE) (32447240) | 08/26/2020 (VFORCE) (32447240) |  |  | MARCO WONG 1-210-762-3623 mwong@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 09/25/2020(Access) |  |  | 09/21/2020 (32447240) | 08/21/2020 08/21/2020 (28227251.1) | 10/01/2020 |  | Completed Activated/Installed | N (32447240) N N (32447241) | U0101953 |  |  | NSPE0013926746
Completed | MA065 | 20 Commerce Way ste 2 Woburn, MA 01801-1057 US | 50 MBPS (32538813) | 09/03/2020: Circuit delivered. Pending scheduling of beas install. | 203362747 | MA065 | Private IP - PIP (32538812) WAN Analysis Reporting (32538814) Access (32538813) | 32538812 32538814 32538813 | 20 MBPS (32538812) |  | 94824991 (Private IP (PIP)) 94824995 (WAN Analysis Reporting) 94824988 (Access) | C4023749/ADD (32538812) E4061150/ADD (32538813) | 95.KFGS.011940..NE (3253881380435501) | 6178033 | 13000 | PVC ID : 6178033 VPN Name : UnitedHealthGroup Router Name : B4W9E01 VRF Name : V598846:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65356 PE IP Address : 206.115.6.209 CE Address : 206.115.6.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32538813) | 1000Base-SX (850nm, Multi Mode Fiber) (32538813) | Ethernet | VERIZON (3253881380435501) | 08/19/2020 (3253881380435501) | 08/26/2020 (3253881380435501) | 09/03/2020 (3253881380435501) | 09/08/2020 (VFORCE) (32538813) | 09/08/2020 (VFORCE) (32538813) | DEMARCDET - NA |  | Brian Stockfisch 1-810-768-9920 bstockfisch@diplomat.is | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 09/09/2020(Private IP - PIP) 09/09/2020(WAN Analysis Reporting) 09/09/2020(Access) |  |  | 09/04/2020 (32538812) 09/02/2020 (32538813) | 09/16/2020 09/22/2020 | 09/09/2020 |  | Completed | N (32538812) N (32538814) N (32538813) | U0101953 |  |  | NSPE0013925431
Completed | TX588 | 4203 E SOUTHCROSS BLVD SAN ANTONIO, TX 78222-3722 US | 100 MBPS (32538296) | 08/06/2020: Circuit delivered. Pending scheduling of beas install. | 203523305 | TX588 | Private IP - PIP (32538295) WAN Analysis Reporting (32538297) Access (32538296) | 32538295 32538297 32538296 | 50 MBPS (32538295) |  | 1294705477 (Private IP (PIP)) 1294705479 (WAN Analysis Reporting) 1294705473 (Access) | C1144540/ADD (32538295) E4061143/ADD (32538296) | 21.L1XX.991133..CHTR (3253829681929201) | 6178003 | 30000 | PVC ID : 6178003 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65042 PE IP Address : 147.225.185.41 CE Address : 147.225.185.42 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32538296) | 1000Base-SX (850nm, Multi Mode Fiber) (32538296) | Ethernet | TIME WARNER CABLE (3253829681929201) | 07/23/2020 (3253829681929201) | 10/16/2020 (3253829681929201) | 08/06/2020 (3253829681929201) | 08/11/2020 (VFORCE) (32538296) | 08/11/2020 (VFORCE) (32538296) | DEMARCDET - 1st Floor storage clawset rack mounted 4 RU rack |  | Christian Romero 1-210-727-7333 cgromero@samedgrp.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 08/11/2020(Private IP - PIP) 08/11/2020(WAN Analysis Reporting) 08/11/2020(Access) |  |  | 10/27/2020 (32538295) 10/23/2020 (32538296) | 09/02/2020 09/09/2020 | 08/12/2020 |  | Completed | N (32538295) N (32538297) N (32538296) | U0101953 |  |  | NSPE0013953542
Completed | TX593 | 9215 Westover Hills Blvd San Antonio, TX 78251-2870 US | 500 MBPS (32568379) | 11/11/2020: Order Completed on Nov 11, 2020 | 203572735 | TX593 | WAN Analysis Reporting (32568380) Access (32568379) Private IP - PIP (32568378) | 32568380 32568379 32568378 | 100 MBPS (32568378) |  | 94848554 (WAN Analysis Reporting) 94848556 (Access) 94848551 (Private IP (PIP)) | C5010931/ADD (32568378) E5027530/ADD (32568379) | 21.L1XX.992567..CHTR (3256837982131401) | 6178623 | 70000 | PVC ID : 6178623 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64779 PE IP Address : 68.136.187.45 CE Address : 68.136.187.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32568379) | 1000Base-SX (850nm, Multi Mode Fiber) (32568379) | Ethernet | TIME WARNER CABLE (3256837982131401) | 09/02/2020 (3256837982131401) | 10/28/2020 (3256837982131401) | 10/28/2020 (3256837982131401) | 11/10/2020 (VFORCE) (32568379) | 11/10/2020 (VFORCE) (32568379) | DEMARCDET - 1ST FLOOR, TELCO RM, WALL RACK MOUNTED |  | Christian Romero 1-210-727-7333 cgromero@samedgrp.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 11/10/2020(WAN Analysis Reporting) 11/10/2020(Access) 11/10/2020(Private IP - PIP) |  |  | 11/06/2020 (32568378) 11/04/2020 (32568379) | 10/22/2020 10/16/2020 | 11/11/2020 |  | Completed | N (32568380) N (32568379) N (32568378) | U0101953 |  |  | NSPE0013960923
Completed | TX589 | 600 Division Ave San Antonio, TX 78214-1350 US | 100 MBPS (32579586) | 08/27/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 203599073 | TX589 | Private IP - PIP (32579585) WAN Analysis Reporting (32579587) Access (32579586) | 32579585 32579587 32579586 | 50 MBPS (32579585) |  | 94849300 (Private IP (PIP)) 94849303 (WAN Analysis Reporting) 94849305 (Access) | C1144676/ADD (32579585) E4061333/ADD (32579586) | 21.L1XX.992617..CHTR (3257958682262001) | 6178855 | 30000 | PVC ID : 6178855 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64863 PE IP Address : 152.183.13.149 CE Address : 152.183.13.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32579586) | 1000Base-SX (850nm, Multi Mode Fiber) (32579586) | Ethernet | TIME WARNER CABLE (3257958682262001) | 07/28/2020 (3257958682262001) | 08/27/2020 (3257958682262001) | 08/21/2020 (3257958682262001) | 08/25/2020 (VFORCE) (32579586) | 08/25/2020 (VFORCE) (32579586) | DEMARCDET - 1st flr comm closet rack mounted |  | CHRISTIAN ROMERO 1-210-727-7333 cgromero@samedgrp.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 08/25/2020(Private IP - PIP) 08/25/2020(WAN Analysis Reporting) 08/25/2020(Access) |  |  | 09/08/2020 (32579585) 09/03/2020 (32579586) | 09/08/2020 09/14/2020 | 08/25/2020 |  | Completed | N (32579585) N (32579587) N (32579586) | U0101953 |  |  | NSPE0013964588
Completed | TX579-01-IM | 1417 N WARE RD MCALLEN, TX 78501 US | 50 MBPS (32603214) | 12/11/2020: Order Completed on Dec 11, 2020 | 203628687 | McAllen | Private IP - PIP (32603213) WAN Analysis Reporting (32603215) Access (32603214) | 32603213 32603215 32603214 | 10 MBPS (32603213) |  | 1296996097 (Private IP (PIP)) 1296996099 (WAN Analysis Reporting) 1296996093 (Access) | C4023813/ADD (32603213) E4061405/ADD (32603214) | 38/KRGN/614137//SW (3260321482427402) 38/KRGN/614087//SW (3260321482427401) | 6179216 | 5500 | PVC ID : 6179216 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65361 PE IP Address : 68.136.199.213 CE Address : 68.136.199.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32603214) | 1000Base-SX (850nm, Multi Mode Fiber) (32603214) | Ethernet | ATT (3260321482427402) ATT (3260321482427401) | 11/24/2020 (3260321482427402) 11/05/2020 (3260321482427401) | 12/02/2020 (3260321482427402) 11/10/2020 (3260321482427401) | 12/09/2020 (3260321482427401) 12/04/2020 (3260321482427402) | 12/10/2020 (VFORCE) (32603214) | 12/10/2020 (VFORCE) (32603214) | DEMARCDET - 1st FLR MDF ROOM SOUTH WALL |  | GABE RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 12/11/2020(Private IP - PIP) 12/11/2020(WAN Analysis Reporting) 12/11/2020(Access) |  |  | 12/11/2020 (32603213) 12/09/2020 (32603214) | 01/07/2021 01/13/2021 | 12/11/2020 |  | Completed | N (32603213) N (32603215) N (32603214) | U0101953 |  |  | NSPE0013971232
Completed | WI054 | 2020 INNOVATION CT DE PERE, WI 54115 US | 500 MBPS (32620870) | 02/11/2021: Circuit delivered. Pending scheduling of beas install. | 203651403 | WI054 | WAN Analysis Reporting (32620871) Access (32620870) Private IP - PIP (32620869) | 32620871 32620870 32620869 | 300 MBPS (32620869) |  | 1297489093 (WAN Analysis Reporting) 1297489087 (Access) 1297489091 (Private IP (PIP)) | C5010975/ADD (32620869) E5027667/ADD (32620870) | 92.L1XX.990527..CHTR (3262087079104801) | 6179522 | 70000 | PVC ID : 6179522 VPN Name : UnitedHealthGroup Router Name : MWA9E01 VRF Name : Vh68954:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65428 PE IP Address : 152.162.157.157 CE Address : 152.162.157.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32620870) | 1000Base-SX (850nm, Multi Mode Fiber) (32620870) | Ethernet | TIME WARNER CABLE (3262087079104801) | 12/17/2020 (3262087079104801) | 02/05/2021 (3262087079104801) | 02/12/2021 (3262087079104801) | 02/17/2021 (VFORCE) (32620870) | 02/17/2021 (VFORCE) (32620870) | DEMARCDET - 1st Fl Room E100 Wall Mounted 7Up Labeled Spectrum |  | JEREMY DASH 1-920-661-4258 jeremy_dash@uhg.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 02/17/2021(WAN Analysis Reporting) 02/17/2021(Access) 02/17/2021(Private IP - PIP) |  |  | 02/16/2021 (32620869) 02/12/2021 (32620870) | 05/14/2021 05/10/2021 | 02/17/2021 |  | Completed | N (32620871) N (32620870) N (32620869) | U0101953 | Jeopardy Notification 1 (12/14/2020) |  | NSPE0013976864
Completed | Sitel Operating Corporation | 5601 N 103rd St Omaha, NE 68134-1006 US | 400 MBPS (32643663) | 02/18/2021: Pending CCR 1893115 for Overture 1400 install, ready for traffic date replanned 2/19/21. Beas installed completed on 2/18. Pending completion of remaining queues including testing for CCR 1893115. Once CCR work is all complete, test and install group will request for tech to be scheduled/dispatched to complete any required work and end to end testing. | 203664123 | Sitel Operating Corporation | Private IP - PIP (32643662) WAN Analysis Reporting (32643664) Access (32643663) | 32643662 32643664 32643663 | 200 MBPS (32643662) |  | 94853065 (Private IP (PIP)) 94853068 (WAN Analysis Reporting) 94853070 (Access) | C5010998/ADD (32643662) E5027716/ADD (32643663) |  | 6179938 | 250000 | PVC ID : 6179938 VPN Name : UHG-ECC Router Name : PLSHXE01 VRF Name : V449266-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65504 PE IP Address : 152.177.64.125 CE Address : 152.177.64.126 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (32643663) | Ethernet |  |  |  |  | 12/15/2020 (CCP) (32643662) 12/15/2020 (CCP) (32643663) | 11/21/2020 (CCP) (32643662) 11/21/2020 (CCP) (32643663) |  |  | CLARK WILLMS 1-305-606-9214 clark.willms@sitel.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 02/22/2021(Private IP - PIP) 02/22/2021(WAN Analysis Reporting) 02/22/2021(Access) |  |  | 02/18/2021 (32643662) 02/16/2021 (32643663) | 02/11/2021 02/17/2021 | 02/22/2021 |  | Completed | N (32643662) N (32643664) N (32643663) | U0101953 | Jeopardy Notification 3 (12/30/2020) |  | NSPE0013979760
Completed | C1530-08-IJ | 11830 Webb Chapel Rd ste 200 Dallas, TX 75234-2784 US | 400 MBPS (32645532) | 09/19/2020: Your order is on track: Provisioning Department accepted the order on Aug 4, 2020 and has begun processing. | 203675799 | C1530-08-IJ | Private IP - PIP (32645531) WAN Analysis Reporting (32645533) Access (32645532) | 32645531 32645533 32645532 | 200 MBPS (32645531) |  | 94853547 (Private IP (PIP)) 94853545 (WAN Analysis Reporting) 94853549 (Access) | C5011000/ADD (32645531) E5027721/ADD (32645532) |  | 6179954 | 200000 | PVC ID : 6179954 VPN Name : UHG-ECC Router Name : RCN9E03 VRF Name : V104327:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65509 PE IP Address : 152.183.178.49 CE Address : 152.183.178.50 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (32645532) | Ethernet | [8 empty] | CLARK WILLMS 1-305-606-9214 clark.willms@sitel.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 08/15/2020(Private IP - PIP) 08/15/2020(WAN Analysis Reporting) 08/15/2020(Access) |  |  | 08/14/2020 (32645531) 08/12/2020 (32645532) | 09/15/2020 09/21/2020 | 08/15/2020 |  | Completed | N (32645531) N (32645533) N (32645532) | U0101953 |  |  | NSPE0013986677
Completed | IL141 | 1370 Busch Pkwy Buffalo Grove, IL 60089-4505 US | 50 MBPS (32646169) | 10/17/2020: Order Completed on Oct 17, 2020 | 203676567 | IL141 | Private IP - PIP (32646168) WAN Analysis Reporting (32646170) Access (32646169) | 32646168 32646170 32646169 | 20 MBPS (32646168) |  | 94853747 (Private IP (PIP)) 94853745 (WAN Analysis Reporting) 94853749 (Access) | C4023867/ADD (32646168) E4061551/ADD (32646169) | /KRGN/127414//LB (3264616982634701) | 6179964 | 13000 | PVC ID : 6179964 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65427 PE IP Address : 68.137.110.57 CE Address : 68.137.110.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32646169) | 1000Base-SX (850nm, Multi Mode Fiber) (32646169) | Ethernet | ATT (3264616982634701) | 08/04/2020 (3264616982634701) | 08/07/2020 (3264616982634701) | 10/13/2020 (3264616982634701) | 10/16/2020 (VFORCE) (32646169) | 10/16/2020 (VFORCE) (32646169) | DEMARCDET - 1st flr network rm. wall mounted |  | BRIAN STOCKFISCH 1-810-768-9920 bstockfisch@diplomat.is | BRANDON LITTLE | emurugan@marchvisioncare.com | 1-952-687-3694 | 10/17/2020(Private IP - PIP) 10/17/2020(WAN Analysis Reporting) 10/17/2020(Access) |  |  | 09/28/2020 (32646168) 09/24/2020 (32646169) | 10/28/2020 11/03/2020 | 10/17/2020 |  | Completed | N (32646168) N (32646170) N (32646169) | U0101953 |  |  | NSPE0013987477
Completed | FL160-05-IM | 3160 Southgate Commerce Blvd Orlando, FL 32806-8549 US | 50 MBPS (32664682) | 10/14/2020: Order Completed on Oct 14, 2020 | 203701057 | UNITED HEALTH GROUP | WAN Analysis Reporting (32664683) Access (32664682) Private IP - PIP (32664681) | 32664683 32664682 32664681 | 10 MBPS (32664681) |  | 94854370 (WAN Analysis Reporting) 94854368 (Access) 94854365 (Private IP (PIP)) | C4023894/ADD (32664681) E4061652/ADD (32664682) | 32.L1XX.994427..CHTR (3266468229896601) | 6180398 | 5500 | PVC ID : 6180398 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65276 PE IP Address : 147.225.212.209 CE Address : 147.225.212.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32664682) | 1000Base-SX (850nm, Multi Mode Fiber) (32664682) | Ethernet | BRIGHT HOUSE (3266468229896601) | 08/28/2020 (3266468229896601) | 12/04/2020 (3266468229896601) | 10/12/2020 (3266468229896601) | 10/14/2020 (VFORCE) (32664682) | 10/14/2020 (VFORCE) (32664682) | DEMARCDET - telco rm rack mounted |  | Glenda Escalante 1-305-301-1513 gescalante@wellmed.net | AIDYL BERT SIMBULAN | aidyl_simbulan@optum.com | 632-462-2465 | 10/14/2020(WAN Analysis Reporting) 10/14/2020(Access) 10/14/2020(Private IP - PIP) |  |  | 12/15/2020 (32664681) 12/11/2020 (32664682) | 10/15/2020 10/09/2020 | 10/14/2020 |  | Completed | N (32664683) N (32664682) N (32664681) | U0101953 |  |  | NSPE0013994231
Completed | TX595-01-IM | 700 AUSTIN AVE WACO, TX 76701-2020 US | 500 MBPS (32688267) | 10/30/2020: Order Completed on Oct 30, 2020 | 203725823 | TX595 | Private IP - PIP (32688266) WAN Analysis Reporting (32688268) Access (32688267) | 32688266 32688268 32688267 | 300 MBPS (32688266) |  | 1299222067 (Private IP (PIP)) 1299222069 (WAN Analysis Reporting) 1299222063 (Access) | C5011228/ADD (32688266) E5028025/ADD (32688267) |  | 6180833 | 180000 | PVC ID : 6180833 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64592 PE IP Address : 147.225.74.17 CE Address : 147.225.74.18 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32688267) | 1000Base-LX (1310nm Single Mode Fiber) (32688267) | Ethernet | YS00 (3268826782838301) | 10/15/2020 (3268826782838301) |  | 10/21/2020 (3268826782838301) | 10/30/2020 (VFORCE) (32688267) | 10/27/2020 (VFORCE) (32688267) | DEMARCDET - main building 1st floor MDF room |  | Larry Ashfield 1-817-878-3395 ashfieldl@ushealthgroup.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 10/30/2020(Private IP - PIP) 10/30/2020(WAN Analysis Reporting) 10/30/2020(Access) |  |  | 11/05/2020 (32688266) 11/03/2020 (32688267) | 12/09/2020 12/15/2020 | 10/30/2020 |  | Completed | N (32688266) N (32688268) N (32688267) | U0101953 |  |  | NSPE0014002624
Completed | C1658-01-IM | 1600 HUNTER RD HANOVER PARK, IL 60133-6767 US | 500 MBPS (32688374) | 08/27/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 203726121 | Insight Distribution Center | Private IP - PIP (32688373) WAN Analysis Reporting (32688375) Access (32688374) | 32688373 32688375 32688374 | 200 MBPS (32688373) |  | 1299307501 (Private IP (PIP)) 1299307503 (WAN Analysis Reporting) 1299307497 (Access) | C5011229/ADD (32688373) E5028027/ADD (32688374) | /KRGN/127456//LB (3268837472533701) | 6180836 | 110000 | PVC ID : 6180836 VPN Name : UHG-ECC Router Name : DNG9E02 VRF Name : Vh77111:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65470 PE IP Address : 152.183.15.37 CE Address : 152.183.15.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32688374) | 1000Base-SX (850nm, Multi Mode Fiber) (32688374) | Ethernet | ATT (3268837472533701) | 08/10/2020 (3268837472533701) | 08/20/2020 (3268837472533701) | 08/21/2020 (3268837472533701) | 08/25/2020 (VFORCE) (32688374) |  | DEMARCDET - emux in 2nd flr mpoe relay rack 1 tray 2 optical port 6 multi mode fiber handoff tagged not extended |  | DEREK JACOBY 1-630-295-7923 derek.jacoby@insight.com | STANIMIR BOSHNAKOV | stanimir_boshnakov@optum.com | 1-763-765-8073 | 08/25/2020(Private IP - PIP) 08/25/2020(WAN Analysis Reporting) 08/25/2020(Access) |  |  | 08/31/2020 (32688373) 08/27/2020 (32688374) | 09/21/2020 09/25/2020 | 08/25/2020 |  | Completed | N (32688373) N (32688375) N (32688374) | U0101953 |  |  | NSPE0014002676
Completed | AZ174-01-IM | 4790 E GRANT RD TUCSON, AZ 85712-2703 US | 50 MBPS (32688711) | 03/11/2021: Circuit delivered. Pending scheduling of beas install. | 203727177 | AZ174 | WAN Analysis Reporting (32688712) Access (32688711) Private IP - PIP (32688710) | 32688712 32688711 32688710 | 10 MBPS (32688710) |  | 1300239871 (WAN Analysis Reporting) 1300239865 (Access) 1300239869 (Private IP (PIP)) | C4023941/ADD (32688710) E4061780/ADD (32688711) |  | 6180839 | 5500 | PVC ID : 6180839 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : Vh97246:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65384 PE IP Address : 152.181.27.113 CE Address : 152.181.27.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32688711) | 1000Base-SX (850nm, Multi Mode Fiber) (32688711) | Ethernet | CENTURYLINK (3268871182948301) | 03/09/2021 (3268871182948301) |  | 03/11/2021 (3268871182948301) | 03/15/2021 (VFORCE) (32688711) | 03/15/2021 (VFORCE) (32688711) | DEMARCDET - FIRST FLOOR CUSTOMERS DATA ROOM , WALL MOUNTED CIENA 3916 MINI OPTICAL PORT # 3 |  | Dean Moen 1-763-553-4889 dean_moen@optum.com | JASON SALAPING | jason_salaping@optum.com | 1-210-862-6784 | 03/15/2021(WAN Analysis Reporting) 03/15/2021(Access) 03/15/2021(Private IP - PIP) |  |  | 03/22/2021 (32688710) 03/18/2021 (32688711) | 04/23/2021 04/19/2021 | 03/15/2021 |  | Completed | N (32688712) N (32688711) N (32688710) | U0101953 | Jeopardy Notification 3 (02/24/2021) |  | NSPE0014003740
Completed | NY033 | 2950 Express Dr S Islandia, NY 11749-1400 US | 100 MBPS (32733855) | 08/27/2020: Your order is on track: Verizon has received a Firm Order Confirmation (FOC) Date for your telco access delivery for Aug 25, 2020 from VERIZON and is now pending loop acceptance. | 203737307 | UNITED HEALTH GROUP | Private IP - PIP (32733854) WAN Analysis Reporting (32733856) Access (32733855) | 32733854 32733856 32733855 | 100 MBPS (32733854) |  | 94856614 (Private IP (PIP)) 94856621 (WAN Analysis Reporting) 94856618 (Access) | C1145514/ADD (32733854) E4061959/ADD (32733855) | 32.KFGS.223537..NY (3273385533843001) | 6181561 | 70000 | PVC ID : 6181561 VPN Name : UnitedHealthGroup Router Name : GS89E01 VRF Name : Va65010:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64553 PE IP Address : 152.183.58.181 CE Address : 152.183.58.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32733855) | 1000Base-SX (850nm, Multi Mode Fiber) (32733855) | Ethernet | VERIZON (3273385533843001) | 08/14/2020 (3273385533843001) | 08/25/2020 (3273385533843001) | 08/21/2020 (3273385533843001) |  |  | DEMARCDET - SERVER ROOM WALLMOUNTED UNIT 3 |  | Jenelle Fleary 1-212-216-6593 jenelle_fleary@uhg.com | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 08/21/2020(Private IP - PIP) 08/21/2020(WAN Analysis Reporting) 08/21/2020(Access) |  |  | 09/03/2020 (32733854) 09/01/2020 (32733855) | 09/22/2020 09/28/2020 | 08/21/2020 |  | Completed | N (32733854) N (32733856) N (32733855) | U0101953 |  |  | NSPE0014006961
Completed | WA112-06-IJ | 8131 W BOSTIAN RD BLDG A WOODINVILLE, WA 98072-5027 US | 50 MBPS (32719898) | 09/14/2020: Order Completed on Sep 10, 2020 | 203750061 | Woodinville | Internet Dedicated Services (32719897) Access (32719898) | 32719897 32719898 | 50 MBPS (32719897) |  | 1301411309 (Internet Dedicated Services) 1301411305 (Access) | C4023976/ADD (32719897) E4061893/ADD (32719898) | 86/KRGN/300922//NWFC/ (3271989883093401) | 6181261 | 0 | PVC ID : 6181261 VPN Name : Internet Router Name : GW1SEA10 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.231.117 CE Address : 204.148.231.118 | 1000Base-SX-850nm (32719898) | 1000Base-SX (850nm, Multi Mode Fiber) (32719898) | Ethernet | FRONTIER (3271989883093401) | 08/13/2020 (3271989883093401) | 09/14/2020 (3271989883093401) | 09/04/2020 (3271989883093401) | 09/10/2020 (VFORCE) (32719898) | 09/10/2020 (VFORCE) (32719898) | DEMARCDET - SL01#SHLF02#PRT ELECTRICAL ROOM OUTSIDE REAR, MPOE#JKSFP-5D#EXTN# |  | SEPI SOLEIMANPOUR 1-425-951-5025 sepideh.soleimanpour@optum.com | SEPI SOLEIMANPOUR | sepideh.soleimanpour@optum.com | 1-425-951-5025 | 09/10/2020(Internet Dedicated Services) 09/10/2020(Access) |  |  | 09/23/2020 (32719897) 09/21/2020 (32719898) | 09/24/2020 | 09/10/2020 |  |  | N (32719897) N (32719898) | U0101953 |  |  | NSPE0014009598
Completed | MD140 | 5275 Westview Dr Frederick, MD 21703-8306 US | 50 MBPS (32489593) | 08/27/2020: Your order is on track: Circuit delivered, we're coordinating the dispatch to install the VZ equipment | 203366553 | MD140 | Private IP - PIP (32489592) WAN Analysis Reporting (32489594) Access (32489593) | 32489592 32489594 32489593 | 20 MBPS (32489592) |  | 94834547 (Private IP (PIP)) 94834554 (WAN Analysis Reporting) 94834549 (Access) | C4023691/ADD (32489592) E4060968/ADD (32489593) | 40.KFGS.304857..CM (3248959381458202) | 6177228 | 13000 | PVC ID : 6177228 VPN Name : UnitedHealthGroup Router Name : RAY3E05 VRF Name : Vh77112-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64599 PE IP Address : 159.24.192.89 CE Address : 159.24.192.90 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32489593) | 1000Base-SX (850nm, Multi Mode Fiber) (32489593) | Ethernet | VERIZON (3248959381458202) | 07/24/2020 (3248959381458202) | 08/26/2020 (3248959381458202) | 08/19/2020 (3248959381458202) | 08/25/2020 (VFORCE) (32489593) |  | DEMARCDET - MAIN SERVER ROOM, 1ST FLR, WALL MOUNTED CANOGA, TAGGED. |  | Melissa Collins 1-410-371-6168 melissa_collins@uhg.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 1-763-744-2114 | 08/25/2020(Private IP - PIP) 08/25/2020(WAN Analysis Reporting) 08/25/2020(Access) |  |  | 09/04/2020 (32489592) 09/02/2020 (32489593) | 08/26/2020 09/01/2020 | 08/25/2020 |  | Completed | N (32489592) N (32489594) N (32489593) | U0101953 |  |  | NSPE0013926384
Completed | TX598 | 1601 E Alton Gloor Blvd Brownsville, TX 78526-3902 US | 50 MBPS (32768803) | 12/14/2020: Order Completed on Dec 14, 2020 | 203796743 | TX598 | WAN Analysis Reporting (32768804) Access (32768803) Private IP - PIP (32768802) | 32768804 32768803 32768802 | 10 MBPS (32768802) |  | 94860880 (WAN Analysis Reporting) 94860876 (Access) 94860873 (Private IP (PIP)) | C4024041/ADD (32768802) E4062093/ADD (32768803) | 95.L1XX.802495..CHTR (3276880383522101) | 6182267 | 5500 | PVC ID : 6182267 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65381 PE IP Address : 152.183.238.185 CE Address : 152.183.238.186 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32768803) | 1000Base-SX (850nm, Multi Mode Fiber) (32768803) | Ethernet | TIME WARNER CABLE (3276880383522101) | 08/19/2020 (3276880383522101) | 12/14/2020 (3276880383522101) | 12/06/2020 (3276880383522101) | 12/10/2020 (VFORCE) (32768803) | 12/10/2020 (VFORCE) (32768803) | DEMARCDET - 1st Floor, Suite 105, MDF, Wallmount rack |  | Ricky Williamson 1-210-951-3129 rwilliamson@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 12/14/2020(WAN Analysis Reporting) 12/14/2020(Access) 12/14/2020(Private IP - PIP) |  |  | 12/23/2020 (32768802) 12/21/2020 (32768803) | 01/14/2021 01/08/2021 | 12/14/2020 |  | Completed | N (32768804) N (32768803) N (32768802) | U0101953 |  |  | NSPE0014024419
Completed | TX601 | 3228 Interstate 30 ste 200 Mesquite, TX 75150-2633 US | 50 MBPS (32777160) | 10/17/2020: Order Completed on Oct 17, 2020 | 203803565 | TX601 | Private IP - PIP (32777159) WAN Analysis Reporting (32777161) Access (32777160) | 32777159 32777161 32777160 | 10 MBPS (32777159) |  | 94861605 (Private IP (PIP)) 94861607 (WAN Analysis Reporting) 94861603 (Access) | C4024056/ADD (32777159) E4062129/ADD (32777160) | 97.L1XX.815535..CHTR (3277716083584901) | 6182515 | 5500 | PVC ID : 6182515 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65150 PE IP Address : 152.162.240.245 CE Address : 152.162.240.246 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32777160) | 1000Base-SX (850nm, Multi Mode Fiber) (32777160) | Ethernet | TIME WARNER CABLE (3277716083584901) | 08/19/2020 (3277716083584901) | 12/11/2020 (3277716083584901) | 10/13/2020 (3277716083584901) | 10/16/2020 (VFORCE) (32777160) | 10/16/2020 (VFORCE) (32777160) | DEMARCADDR - 1 DEMARCDET - 1st floor room 200 rack 4 RU Telco room |  | EMMANUEL UDOJI 1-214-707-6875 eudoji@wellmed.net | MANISH SARKHEL | manish_sarkhel@optum.com | 632-671-2655 | 10/17/2020(Private IP - PIP) 10/17/2020(WAN Analysis Reporting) 10/17/2020(Access) |  |  | 12/22/2020 (32777159) 12/18/2020 (32777160) | 10/22/2020 10/28/2020 | 10/17/2020 |  | Completed | N (32777159) N (32777161) N (32777160) | U0101953 |  |  | NSPE0014026501
Completed | UT027 | 12921 S Vista Station Blvd Draper, UT 84020-2376 US | 500 MBPS (32780503) | 09/14/2020: The Scheduled Facilities Install date for the Telco access delivery has been missed Sep 1, 2020. Our Provisioning Department is following up with CENTURYLINK and will provide an update within 10 Business Days. | 203809497 | UT027 | Private IP - PIP (32780502) WAN Analysis Reporting (32780504) Access (32780503) | 32780502 32780504 32780503 | 300 MBPS (32780502) |  | 94861701 (Private IP (PIP)) 94861703 (WAN Analysis Reporting) 94861699 (Access) | C5011352/ADD (32780502) E5028253/ADD (32780503) | 69.KXGS.544472..MS (3278050383631001) | 6182581 | 180000 | PVC ID : 6182581 VPN Name : UnitedHealthGroup Router Name : SLKC9E01 VRF Name : V661371:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65351 PE IP Address : 206.115.8.69 CE Address : 206.115.8.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32780503) | 1000Base-SX (850nm, Multi Mode Fiber) (32780503) | Ethernet | CENTURYLINK (3278050383631001) | 08/21/2020 (3278050383631001) | 09/01/2020 (3278050383631001) | 09/02/2020 (3278050383631001) | 09/08/2020 (VFORCE) (32780503) | 09/08/2020 (VFORCE) (32780503) | DEMARCDET - NA |  | Jina Kim 1-480-221-0994 jina_kim@uhg.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-804-670-4304 | 09/09/2020(Private IP - PIP) 09/09/2020(WAN Analysis Reporting) 09/09/2020(Access) |  |  | 09/11/2020 (32780502) 09/09/2020 (32780503) | 10/01/2020 10/07/2020 | 09/09/2020 |  | Completed | N (32780502) N (32780504) N (32780503) | U0101953 |  |  | NSPE0014028366
Completed | TX600 | 2822 N Belt Line Rd ste 200 Sunnyvale, TX 75182-9321 US | 50 MBPS (32792920) | 10/20/2020: Order Completed on Oct 20, 2020 | 203814713 | TX600 | Private IP - PIP (32792919) WAN Analysis Reporting (32792921) Access (32792920) | 32792919 32792921 32792920 | 10 MBPS (32792919) |  | 94862689 (Private IP (PIP)) 94862687 (WAN Analysis Reporting) 94862684 (Access) | C4024094/ADD (32792919) E4062211/ADD (32792920) | 97.L1XX.815536..CHTR (3279292083651201) | 6182989 | 5500 | PVC ID : 6182989 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64899 PE IP Address : 206.115.23.57 CE Address : 206.115.23.58 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32792920) | 1000Base-SX (850nm, Multi Mode Fiber) (32792920) | Ethernet | TIME WARNER CABLE (3279292083651201) | 08/20/2020 (3279292083651201) | 12/10/2020 (3279292083651201) | 10/16/2020 (3279292083651201) | 10/20/2020 (VFORCE) (32792920) | 10/20/2020 (VFORCE) (32792920) | DEMARCDET - telco rm mounted in vertical on left wall |  | EMMANUEL UDOJI 1-214-707-6875 eudoji@wellmed.net | MANISH SARKHEL | manish_sarkhel@optum.com | 632-671-2655 | 10/20/2020(Private IP - PIP) 10/20/2020(WAN Analysis Reporting) 10/20/2020(Access) |  |  | 12/21/2020 (32792919) 12/17/2020 (32792920) | 01/12/2021 01/18/2021 | 10/20/2020 |  | Completed | N (32792919) N (32792921) N (32792920) | U0101953 |  |  | NSPE0014030041
Completed | TX575 | 1521 S STAPLES ST CORPUS CHRISTI, TX 78404-3150 US | 50 MBPS (32792880) | 09/15/2020: Order Completed on Sep 14, 2020 | 203820469 | TX575 | WAN Analysis Reporting (32792881) Access (32792880) Private IP - PIP (32792879) | 32792881 32792880 32792879 | 20 MBPS (32792879) |  | 94862903 (WAN Analysis Reporting) 94862900 (Access) 94862905 (Private IP (PIP)) | C4024095/ADD (32792879) E4062212/ADD (32792880) | 36.L1XX.005007..CHTR (3279288083665201) | 6182995 | 13000 | PVC ID : 6182995 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64894 PE IP Address : 206.115.23.45 CE Address : 206.115.23.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32792880) | 1000Base-SX (850nm, Multi Mode Fiber) (32792880) | Ethernet | TIME WARNER CABLE (3279288083665201) | 08/20/2020 (3279288083665201) | 10/05/2020 (3279288083665201) | 09/09/2020 (3279288083665201) | 09/14/2020 (VFORCE) (32792880) |  | DEMARCDET - 3rd flr data room rack location is middle of room |  | GABE RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-804-670-4505 | 09/14/2020(WAN Analysis Reporting) 09/14/2020(Access) 09/14/2020(Private IP - PIP) |  |  | 10/14/2020 (32792879) 10/12/2020 (32792880) | 10/07/2020 10/01/2020 | 09/14/2020 |  | Completed | N (32792881) N (32792880) N (32792879) | U0101953 |  |  | NSPE0014030890
Completed | TX599 | 2138 N Josey Ln ste 102 Carrollton, TX 75006-3036 US | 50 MBPS (32845983) | 11/11/2020: Order Completed on Nov 11, 2020 | 203859699 | TX599 | Private IP - PIP (32845982) WAN Analysis Reporting (32845984) Access (32845983) | 32845982 32845984 32845983 | 10 MBPS (32845982) |  | 94866894 (Private IP (PIP)) 94866890 (WAN Analysis Reporting) 94866892 (Access) | C4024179/ADD (32845982) E4062457/ADD (32845983) | 13/KRGN/456582//FTNC/ (3284598383933501) | 6184130 | 5500 | PVC ID : 6184130 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64721 PE IP Address : 206.115.55.189 CE Address : 206.115.55.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32845983) | 1000Base-SX (850nm, Multi Mode Fiber) (32845983) | Ethernet | FRONTIER (3284598383933501) | 10/07/2020 (3284598383933501) | 11/05/2020 (3284598383933501) | 11/09/2020 (3284598383933501) | 11/11/2020 (VFORCE) (32845983) | 11/11/2020 (VFORCE) (32845983) |  |  | Marco Wong 1-210-762-3623 mwong@wellmed.net | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 11/11/2020(Private IP - PIP) 11/11/2020(WAN Analysis Reporting) 11/11/2020(Access) |  |  | 11/16/2020 (32845982) 11/12/2020 (32845983) | 11/16/2020 11/20/2020 | 11/11/2020 |  | Completed | N (32845982) N (32845984) N (32845983) | U0101953 |  |  | NSPE0014044059
Completed | FL443 | 621 W Brandon Blvd Brandon, FL 33511-5005 US | 50 MBPS (32868151) | 10/14/2020: Order Completed on Oct 14, 2020 | 203874957 | FL443 | Private IP - PIP (32868150) WAN Analysis Reporting (32868152) Access (32868151) | 32868150 32868152 32868151 | 10 MBPS (32868150) |  | 94867506 (Private IP (PIP)) 94867508 (WAN Analysis Reporting) 94867512 (Access) | C4024197/ADD (32868150) E4062514/ADD (32868151) | 65/KRGN/457309//FTNC/ (3286815184017401) | 6184488 | 5500 | PVC ID : 6184488 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64718 PE IP Address : 152.183.27.129 CE Address : 152.183.27.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32868151) | 1000Base-SX (850nm, Multi Mode Fiber) (32868151) | Ethernet | FRONTIER (3286815184017401) | 08/27/2020 (3286815184017401) | 10/16/2020 (3286815184017401) | 10/13/2020 (3286815184017401) | 10/14/2020 (VFORCE) (32868151) | 10/14/2020 (VFORCE) (32868151) |  |  | CHRISTIAN T CAMPBELL 1-813-462-3162 campbell1@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 | 10/14/2020(Private IP - PIP) 10/14/2020(WAN Analysis Reporting) 10/14/2020(Access) |  |  | 10/27/2020 (32868150) 10/23/2020 (32868151) | 10/08/2020 10/14/2020 | 10/14/2020 |  | Completed | N (32868150) N (32868152) N (32868151) | U0101953 |  |  | NSPE0014048358
Completed | C1649 | 3180 IRVING BLVD DALLAS, TX 75247-6235 US | 50 MBPS | 09/14/2020: Order Completed on Sep 12, 2020 | 203927471 | C1649 | Access WAN Analysis Reporting (32909684) Private IP - PIP (32909682) | 32909682 32909684 | 20 MBPS (32909682) |  | 94737350 94737357 (WAN Analysis Reporting) 94737352 (Private IP (PIP)) | C4020947/NONE (32909682) |  | 6099786 | 9000 | PVC ID : 6099786 VPN Name : UHG-ECC Router Name : IAE9E01 VRF Name : V481056:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65412 PE IP Address : 68.138.69.173 CE Address : 68.138.69.174 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Keri Christensen 1-385-743-9634 keri.christensen@niceincontact.com | JOHN BREMSETH | john_bremseth@optum.com | 1-763-553-4895 | 09/12/2020(Private IP |  |  | 09/03/2020 (32909682) | 09/11/2020 (28216071.1) 09/11/2020 | 09/12/2020 |  | Activated/Installed Completed | N N (32909684) N (32909682) | U0101953 |  |  | NSPE0014059225
Completed | IN156 | 5975 Castle Creek Pkwy ste 100 Indianapolis, IN 46250 US | 250 MBPS (32985582) | 10/01/2020: Order Completed on Oct 1, 2020 | 203988659 | IN156 | Private IP - PIP (32985581) WAN Analysis Reporting (32985583) Access (32985582) | 32985581 32985583 32985582 | 200 MBPS (32985581) |  | 94875201 (Private IP (PIP)) 94875207 (WAN Analysis Reporting) 94875204 (Access) | C0203394/ADD (32985581) E0049089/ADD (32985582) | /KRGN/107324//NB (3298558274169102) | 6187649 | 70000 | PVC ID : 6187649 VPN Name : UnitedHealthGroup Router Name : RVDL9E02 VRF Name : V609555:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64698 PE IP Address : 152.183.79.97 CE Address : 152.183.79.98 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (32985582) | 1000Base-T (32985582) | Ethernet | ATT (3298558274169102) ATT (3298558274169101) | 09/10/2020 (3298558274169102) 09/10/2020 (3298558274169101) | 09/15/2020 (3298558274169102) | 09/15/2020 (3298558274169102) | 10/01/2020 (VFORCE) (32985582) | 10/01/2020 (VFORCE) (32985582) | DEMARCDET - 2ND FLR TELCO RM INSIDE SUITE 250 WALLMOUNTED PORT 5 TAGGED WITH CKT ID EXTENDED |  | STEPHEN KLEIN 1-317-806-2035 sklein@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 10/01/2020(Private IP - PIP) 10/01/2020(WAN Analysis Reporting) 10/01/2020(Access) |  |  | 10/07/2020 (32985581) 10/05/2020 (32985582) | 10/20/2020 10/26/2020 | 10/01/2020 |  | Completed | N (32985581) N (32985583) N (32985582) | U0101953 |  |  | NSPE0014079316
Completed | TX606-01-IM | 17045 SAINT EDWARDS DR HOUSTON, TX 77090-3428 US | 50 MBPS (33012604) | 12/31/2020: Circuit delivered. Beas install scheduled for January 5th. | 204012135 | HOUSTON | Private IP - PIP (33012603) WAN Analysis Reporting (33012605) Access (33012604) | 33012603 33012605 33012604 | 10 MBPS (33012603) |  | 1312071391 (Private IP (PIP)) 1312071393 (WAN Analysis Reporting) 1312071387 (Access) | C4024388/ADD (33012603) E4063248/ADD (33012604) | 54.KGGS.029773..CBCL.. (3301260484783301) | 6188436 | 5500 | PVC ID : 6188436 VPN Name : UnitedHealthGroup Router Name : HSJ9E03 VRF Name : V432129:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65185 PE IP Address : 68.136.181.121 CE Address : 68.136.181.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33012604) | 1000Base-SX (850nm, Multi Mode Fiber) (33012604) | Ethernet | COMCAST (3301260484783301) | 09/14/2020 (3301260484783301) | 01/15/2021 (3301260484783301) | 12/30/2020 (3301260484783301) | 01/05/2021 (VFORCE) (33012604) |  | DEMARCDET - 17045 SAINT EDWARDS DR HOUSTON TX |  | TODD VANDERSCHAEGEN 1-813-629-2611 tvanderschaegen@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 01/05/2021(Private IP - PIP) 01/05/2021(WAN Analysis Reporting) 01/05/2021(Access) |  |  | 01/26/2021 (33012603) 01/22/2021 (33012604) | 12/23/2020 12/30/2020 | 01/05/2021 |  | Completed | N (33012603) N (33012605) N (33012604) | U0101953 |  |  | NSPE0014086572
Completed | NY029 | 1311 MAMARONECK AVE WHITE PLAINS, NY 10605-5221 US | 50 MBPS (33013697) | 10/08/2020: Order Completed on Oct 8, 2020 | 204012443 | UNITEDHEALTH GROUP | WAN Analysis Reporting (33013698) Access (33013697) Private IP - PIP | 33013698 33013697 | 10 MBPS |  | 94732276 (WAN Analysis Reporting) 94732274 (Access) 94732270 | E4053500/NONE (33013697) |  |  |  |  | 1000Base-SX-850nm (33013697) | 1000Base-SX (850nm, Multi Mode Fiber) (33013697) | Ethernet | [8 empty] | DANIELLE MAIORANA 1-347-909-1344 danielle_maiorana@uhg.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 10/08/2020(Access) |  |  | 10/12/2020 (33013697) | 10/08/2020 (28209113.1) 10/08/2020 | 10/08/2020 |  | Completed Activated/Installed | N (33013698) N (33013697) N | U0101953 |  |  | NSPE0014086742
Completed | TX597-01-IM | 1303 Mccullough Ave ste 135 San Antonio, TX 78212-5600 US | 50 MBPS (33024323) | 12/17/2020: Order Completed on Dec 17, 2020 | 204017953 | TX597 | Private IP - PIP (33024322) WAN Analysis Reporting (33024324) Access (33024323) | 33024322 33024324 33024323 | 50 MBPS (33024322) |  | 94877152 (Private IP (PIP)) 94877158 (WAN Analysis Reporting) 94877155 (Access) | C4024399/ADD (33024322) E4063299/ADD (33024323) | TX/KXFN/472666/LVLC (3302432384853401) | 6188794 | 5500 | PVC ID : 6188794 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65367 PE IP Address : 68.137.230.249 CE Address : 68.137.230.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33024323) | 1000Base-SX (850nm, Multi Mode Fiber) (33024323) | Ethernet | LEVEL 3 (3302432384853401) | 09/14/2020 (3302432384853401) | 12/11/2020 (3302432384853401) | 12/16/2020 (3302432384853401) | 12/16/2020 (VFORCE) (33024323) | 12/16/2020 (VFORCE) (33024323) | DEMARCDET - 1st floor suite 135 network room fiber wall panal 6 strand port 1 |  | GABE RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 12/17/2020(Private IP - PIP) 12/17/2020(WAN Analysis Reporting) 12/17/2020(Access) |  |  | 12/22/2020 (33024322) 12/18/2020 (33024323) | 10/23/2020 10/29/2020 | 12/17/2020 |  | Completed | N (33024322) N (33024324) N (33024323) | U0101953 |  |  | NSPE0014088402
Completed | TX607 | 11920 Astoria Blvd ste 280 Houston, TX 77089-6097 US | 50 MBPS (33101053) | 10/20/2020: Order Completed on Oct 20, 2020 | 204089293 | TX607 | Private IP - PIP (33101052) WAN Analysis Reporting (33101054) Access (33101053) | 33101052 33101054 33101053 | 10 MBPS (33101052) |  | 94883683 (Private IP (PIP)) 94883681 (WAN Analysis Reporting) 94883685 (Access) | C4024526/ADD (33101052) E4063765/ADD (33101053) | 28/KRGN/750474//SW (3310105385472701) | 6190550 | 5500 | PVC ID : 6190550 VPN Name : UnitedHealthGroup Router Name : HSTN9E02 VRF Name : Vh45943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64911 PE IP Address : 152.164.94.93 CE Address : 152.164.94.94 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33101053) | 1000Base-SX (850nm, Multi Mode Fiber) (33101053) | Ethernet | ATT (3310105385472701) | 09/22/2020 (3310105385472701) | 09/25/2020 (3310105385472701) | 10/15/2020 (3310105385472701) | 10/19/2020 (VFORCE) (33101053) | 10/19/2020 (VFORCE) (33101053) | DEMARCDET - 1ST FLOOR, MPOE ROOM TELCO BOARD, PORT 5 |  | Scott Cannon 1-813-313-4199 scannon1@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 | 10/20/2020(Private IP - PIP) 10/20/2020(WAN Analysis Reporting) 10/20/2020(Access) |  |  | 10/13/2020 (33101052) 10/09/2020 (33101053) | 10/30/2020 11/05/2020 | 10/20/2020 |  | Completed | N (33101052) N (33101054) N (33101053) | U0101953 |  |  | NSPE0014107841
Completed | FL454 | 18900 N TAMIAMI TRL STE 9 NORTH FORT MYERS, FL 33903-7307 US | 50 MBPS (33143948) | 01/28/2021: Per LEC PM: the tech dispatched on this on 01-22-2021 and ran into an issue with bad light levels. This has been referred to engineering for resolution. I have escalated to engineering for an ETA on resolution. | 204123783 | FL454 | Access (33143948) Private IP - PIP (33143947) WAN Analysis Reporting (33143949) | 33143948 33143947 33143949 | 10 MBPS (33143947) |  | 94886845 (Access) 94886841 (Private IP (PIP)) 94886847 (WAN Analysis Reporting) | E4064019/ADD (33143948) C4024574/ADD (33143947) | 25.KXGS.553165..UFLG (3314394885776801) | 6191842 | 5500 | PVC ID : 6191842 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64695 PE IP Address : 68.136.164.17 CE Address : 68.136.164.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33143948) | 1000Base-SX (850nm, Multi Mode Fiber) (33143948) | Ethernet | CENTURYLINK (3314394885776801) | 10/26/2020 (3314394885776801) | 01/26/2021 (3314394885776801) | 01/29/2021 (3314394885776801) | 02/03/2021 (VFORCE) (33143948) | 02/03/2021 (VFORCE) (33143948) | DEMARCDET - 1st floor cabinet wall mounted |  | Todd Vanderschaegen 1-210-780-6809 tvanderschaegen@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 02/03/2021(Access) 02/03/2021(Private IP - PIP) 02/03/2021(WAN Analysis Reporting) |  |  | 02/03/2021 (33143948) 02/05/2021 (33143947) | 12/29/2020 01/04/2021 | 02/03/2021 |  | Completed | N (33143948) N (33143947) N (33143949) | U0101953 |  |  | NSPE0014120053
Completed | NV200 | 6425 Santa Margarita St ste 110 Las Vegas, NV 89118-1802 US | 50 MBPS (33173637) | 02/04/2021: Beas install scheduled for 2/8. | 204160545 | NV200 | Private IP - PIP (33173636) WAN Analysis Reporting (33173638) Access (33173637) | 33173636 33173638 33173637 | 20 MBPS (33173636) |  | 94892274 (Private IP (PIP)) 94892280 (WAN Analysis Reporting) 94892276 (Access) | C4024608/ADD (33173636) E4064135/ADD (33173637) | 53.KXGS.554086..CTRL (3317363786010001) | 6192876 | 13000 | PVC ID : 6192876 VPN Name : UnitedHealthGroup Router Name : LSVG3E01 VRF Name : V460106-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65233 PE IP Address : 152.177.11.61 CE Address : 152.177.11.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33173637) | 1000Base-SX (850nm, Multi Mode Fiber) (33173637) | Ethernet | CENTURYLINK (3317363786010001) | 12/17/2020 (3317363786010001) | 01/06/2021 (3317363786010001) | 01/05/2021 (3317363786010001) | 02/08/2021 (VFORCE) (33173637) | 02/08/2021 (VFORCE) (33173637) | DEMARCDET - back of the north side of the bldg wall and wall mounted not extended suit 101 |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 02/09/2021(Private IP - PIP) 02/09/2021(WAN Analysis Reporting) 02/09/2021(Access) |  |  | 02/15/2021 (33173636) 02/11/2021 (33173637) | 03/17/2021 03/23/2021 | 02/09/2021 |  | Completed | N (33173636) N (33173638) N (33173637) | U0101953 | Jeopardy Notification 3 (01/22/2021) |  | NSPE0014132121
Completed | AZ182 | 7534 E 2nd St ste 102 Scottsdale, AZ 85251-4548 US | 100 MBPS (33187561) | 03/15/2021: Your order is on track: Verizon has received a Firm Order Confirmation (FOC) Date for your telco access delivery for May 7, 2021 from COX and is now pending loop acceptance. | 204172755 | AZ182 | WAN Analysis Reporting (33187562) Access (33187561) Private IP - PIP (33187560) | 33187562 33187561 33187560 | 50 MBPS (33187560) |  | 94893331 (WAN Analysis Reporting) 94893335 (Access) 94893333 (Private IP (PIP)) | C1147529/ADD (33187560) E4064200/ADD (33187561) | 23.KFGX.991975..COXC. (3318756186109701) | 6193195 | 30000 | PVC ID : 6193195 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : Vh97246:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65130 PE IP Address : 68.137.119.97 CE Address : 68.137.119.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33187561) | 1000Base-SX (850nm, Multi Mode Fiber) (33187561) | Ethernet | COX (3318756186109701) | 10/20/2020 (3318756186109701) | 03/19/2021 (3318756186109701) | 03/12/2021 (3318756186109701) | 03/17/2021 (VFORCE) (33187561) | 03/17/2021 (VFORCE) (33187561) | DEMARCDET - 1st flr server rm located on a wall board SAS-k port 2 to demarc panel port 1 |  | Nancy Llanas 1-702-419-9618 nancy_llanas@uhg.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 03/18/2021(WAN Analysis Reporting) 03/18/2021(Access) 03/18/2021(Private IP - PIP) |  |  | 03/30/2021 (33187560) 03/26/2021 (33187561) | 04/21/2021 04/15/2021 | 03/18/2021 |  | Completed | N (33187562) N (33187561) N (33187560) | U0101953 | Jeopardy Notification 1 (03/04/2021) |  | NSPE0014135897
Completed | FL453 | 28959 State Road 54 Wesley Chapel, FL 33543-3218 US | 50 MBPS (33201279) | 01/29/2021: Your order is on track: Request sent to the Local Exchange Carrier (LEC) BRIGHT HOUSE on Dec 2, 2020, waiting for Firm Order Confirmation (FOC) of circuit delivery. | 204186383 | FL453 | Private IP - PIP (33201278) WAN Analysis Reporting (33201280) Access (33201279) | 33201278 33201280 33201279 | 10 MBPS (33201278) |  | 94894166 (Private IP (PIP)) 94894168 (WAN Analysis Reporting) 94894170 (Access) | C4024656/ADD (33201278) E4064260/ADD (33201279) | 81.L1XX.913164..CHTR (3320127986164301) | 6193477 | 5500 | PVC ID : 6193477 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65139 PE IP Address : 147.225.248.137 CE Address : 147.225.248.138 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33201279) | 1000Base-SX (850nm, Multi Mode Fiber) (33201279) | Ethernet | BRIGHT HOUSE (3320127986164301) | 12/02/2020 (3320127986164301) | 01/26/2021 (3320127986164301) | 01/27/2021 (3320127986164301) | 01/29/2021 (VFORCE) (33201279) | 01/29/2021 (VFORCE) (33201279) | DEMARCDET - 1st flr in the server rm wall mounted |  | CHRISTIAN T CAMPBELL 1-813-462-3162 campbell1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 01/29/2021(Private IP - PIP) 01/29/2021(WAN Analysis Reporting) 01/29/2021(Access) |  |  | 02/04/2021 (33201278) 02/02/2021 (33201279) | 04/20/2021 04/26/2021 | 01/29/2021 |  | Completed | N (33201278) N (33201280) N (33201279) | U0101953 | Jeopardy Notification 2 (11/30/2020) |  | NSPE0014140179
Completed | PR518 | 997 CALLE SAN ROBERTO SAN JUAN, PR 00926-2759 PR | 500 MBPS | 10/15/2020: Order Completed on Oct 15, 2020 | 204280239 | PR518 | Private IP - PIP (33285116) Access WAN Analysis Reporting (33285118) | 33285116 33285118 | 150 MBPS (33285116) |  | 1196155629 (Private IP (PIP)) 1196155625 1196155683 (WAN Analysis Reporting) | C5008462/NONE (33285116) |  | 6084883 | 90000 | PVC ID : 6084883 VPN Name : UnitedHealthGroup Router Name : SNJN9E01 VRF Name : Vc13521:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65256 PE IP Address : 68.136.122.77 CE Address : 68.136.122.78 QoS - Egress Profile: R12 | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Enrique Vila-Biaggi, 1-787-274-0996 ejvila@iedifiko.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 10/15/2020(Private IP |  |  | 10/13/2020 (33285116) | 10/21/2020 10/21/2020 (27738465.1) | 10/15/2020 |  | Completed Activated/Installed | N (33285116) N N (33285118) | U0101953 |  |  | NSPE0014167037
Completed | NC068 | 10 Herman Ave Asheville, NC 28803-9110 US | 50 MBPS (33386965) | 11/11/2020: Order Completed on Nov 11, 2020 | 204360937 | NC068 | Private IP - PIP (33386964) WAN Analysis Reporting (33386966) Access (33386965) | 33386964 33386966 33386965 | 30 MBPS (33386964) |  | 94906557 (Private IP (PIP)) 94906564 (WAN Analysis Reporting) 94906560 (Access) | C4024899/ADD (33386964) E4065151/ADD (33386965) | 20/KRGN/400864//SB (3338696580004101) | 6198852 | 17000 | PVC ID : 6198852 VPN Name : UnitedHealthGroup Router Name : CHRL9E01 VRF Name : V638950:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65207 PE IP Address : 152.181.35.65 CE Address : 152.181.35.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33386965) | 1000Base-SX (850nm, Multi Mode Fiber) (33386965) | Ethernet | ATT (3338696580004101) | 10/22/2020 (3338696580004101) | 11/04/2020 (3338696580004101) | 11/03/2020 (3338696580004101) | 11/11/2020 (VFORCE) (33386965) | 11/11/2020 (VFORCE) (33386965) | DEMARCDET - 1ST FL TELCO RM RELAY RACK #2 TAGGED WITH CKTID NOT EXTENDED |  | BRIAN STOCKFISCH 1-810-768-9920 bstockfisch@diplomat.is | BRANDON LITTLE | Brandon_little@optum.com | 1-952-687-3694 | 11/11/2020(Private IP - PIP) 11/11/2020(WAN Analysis Reporting) 11/11/2020(Access) |  |  | 11/13/2020 (33386964) 11/11/2020 (33386965) | 12/03/2020 12/09/2020 | 11/11/2020 |  | Completed | N (33386964) N (33386966) N (33386965) | U0101953 |  |  | NSPE0014193999
Completed | TX574 | 1620 S Padre Island Dr Corpus Christi, TX 78416-1353 US | 50 MBPS (33387014) | 03/15/2021: Order Completed on Mar 15, 2021 | 204361783 | TX574 | Access (33387014) Private IP - PIP (33387013) WAN Analysis Reporting (33387015) | 33387014 33387013 33387015 | 50 MBPS (33387013) |  | 94906359 (Access) 94906363 (Private IP (PIP)) 94906361 (WAN Analysis Reporting) | E4065152/ADD (33387014) C4024900/ADD (33387013) | 36.L1XX.005050..CHTR (3338701487176601) | 6198879 | 17000 | PVC ID : 6198879 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65094 PE IP Address : 147.225.154.69 CE Address : 147.225.154.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33387014) | 1000Base-SX (850nm, Multi Mode Fiber) (33387014) | Ethernet | TIME WARNER CABLE (3338701487176601) | 11/16/2020 (3338701487176601) | 03/23/2021 (3338701487176601) | 03/11/2021 (3338701487176601) | 03/15/2021 (VFORCE) (33387014) | 03/15/2021 (VFORCE) (33387014) | DEMARCDET - 1st FLR IT ROOM WALL MTD |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 03/15/2021(Access) 03/15/2021(Private IP - PIP) 03/15/2021(WAN Analysis Reporting) |  |  | 03/30/2021 (33387014) 04/01/2021 (33387013) | 04/05/2021 04/09/2021 | 03/15/2021 |  | Completed | N (33387014) N (33387013) N (33387015) | U0101953 |  |  | NSPE0014194219
Completed | FL054 | 3100 Sw 145th Ave Hollywood, FL 33027-6610 US | 300 MBPS (33420659) | 12/31/2020: Beas install scheduled for January 4th. | 204393525 | FL054 | Private IP - PIP (33420658) WAN Analysis Reporting (33420660) Access (33420659) | 33420658 33420660 33420659 | 100 MBPS (33420658) |  | 94908753 (Private IP (PIP)) 94908757 (WAN Analysis Reporting) 94908759 (Access) | C5012615/ADD (33420658) E5030482/ADD (33420659) |  | 6200049 | 70000 | PVC ID : 6200049 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65215 PE IP Address : 68.137.96.201 CE Address : 68.137.96.202 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33420659) | 1000Base-SX (850nm, Multi Mode Fiber) (33420659) | Ethernet | CLEC or INDEPENDENT (3342065987415801) | 11/03/2020 (3342065987415801) |  | 01/07/2021 (3342065987415801) | 01/07/2021 (VFORCE) (33420659) | 01/07/2021 (VFORCE) (33420659) | DEMARCDET - NA |  | Jorge Moral 1-954-364-0713 Jorge.moral@optum.com | MANISH SARKHEL | manish_sarkhel@optum.com | 632-671-2655 | 01/07/2021(Private IP - PIP) 01/07/2021(WAN Analysis Reporting) 01/07/2021(Access) |  |  | 01/11/2021 (33420658) 01/07/2021 (33420659) | 01/04/2021 01/08/2021 | 01/07/2021 |  | Completed | N (33420658) N (33420660) N (33420659) | U0101953 | Jeopardy Notification 1 (01/05/2021) |  | NSPE0014206049
Completed | C1661 | 4580 W Post Rd Las Vegas, NV 89118-3926 US | 100 MBPS (33428375) | 02/18/2021: Build is complete and install date is scheduled for Monday, 2/22. | 204425307 | C1661 | Access (33428375) Private IP - PIP (33428374) WAN Analysis Reporting (33428376) | 33428375 33428374 33428376 | 50 MBPS (33428374) |  | 94906550 (Access) 94906547 (Private IP (PIP)) 94906554 (WAN Analysis Reporting) | E4065323/ADD (33428375) C1149011/ADD (33428374) | 33.KFGX.002188..COXC. (3342837586623101) | 6200234 | 30000 | PVC ID : 6200234 VPN Name : UHG-ECC Router Name : LSVG9E03 VRF Name : Vd84509:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65402 PE IP Address : 68.137.119.9 CE Address : 68.137.119.10 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (33428375) | 1000Base-LX (1310nm Single Mode Fiber) (33428375) | Ethernet | COX (3342837586623101) | 10/28/2020 (3342837586623101) | 02/25/2021 (3342837586623101) | 02/22/2021 (3342837586623101) | 02/24/2021 (VFORCE) (33428375) | 02/24/2021 (VFORCE) (33428375) | DEMARCDET - 1st flr server rm on a wall board on the east port 2 of SAS K going to demarc panel port 6 |  | Gino Sullivan 1-636-812-4000 ESullivan@roseint.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 | 02/24/2021(Access) 02/24/2021(Private IP - PIP) 02/24/2021(WAN Analysis Reporting) |  |  | 04/05/2021 (33428375) 04/07/2021 (33428374) | 12/09/2020 12/15/2020 | 02/24/2021 |  | Completed | N (33428375) N (33428374) N (33428376) | U0101953 |  |  | NSPE0014209312
Completed | TX608 | 341 Wheatfield Dr ste 100 Sunnyvale, TX 75182-4639 US | 50 MBPS (33454196) | 12/19/2020: Your order is on track: Verizon has received a Firm Order Confirmation (FOC) Date for your telco access delivery for Dec 18, 2020 from TIME WARNER CABLE and is now pending loop acceptance. | 204448067 | TX608 | Private IP - PIP (33454195) WAN Analysis Reporting (33454197) Access (33454196) | 33454195 33454197 33454196 | 20 MBPS (33454195) |  | 94910850 (Private IP (PIP)) 94910848 (WAN Analysis Reporting) 94910845 (Access) | C4025004/ADD (33454195) E4065429/ADD (33454196) | 21.L1XX.993633..CHTR (3345419687651301) | 6201150 | 13000 | PVC ID : 6201150 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65425 PE IP Address : 68.137.81.225 CE Address : 68.137.81.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33454196) | 1000Base-SX (850nm, Multi Mode Fiber) (33454196) | Ethernet | TIME WARNER CABLE (3345419687651301) | 12/16/2020 (3345419687651301) | 12/17/2020 (3345419687651301) | 12/17/2020 (3345419687651301) | 12/21/2020 (VFORCE) (33454196) | 12/21/2020 (VFORCE) (33454196) | DEMARCDET - CUSTOMER IT ROOM, WALL MOUNT, ETH PORT 3 |  | EMMANUEL UDOJI 1-214-707-6875 emmanuel_udoji@optum.com | SOLOMON VICTOR | solomon_victor@optum.com | 91-804-670-4304 | 12/22/2020(Private IP - PIP) 12/22/2020(WAN Analysis Reporting) 12/22/2020(Access) |  |  | 12/29/2020 (33454195) 12/24/2020 (33454196) | 01/28/2021 02/03/2021 | 12/22/2020 |  | Completed | N (33454195) N (33454197) N (33454196) | U0101953 | Jeopardy Notification 2 (12/15/2020) |  | NSPE0014216572
Completed | TX611 | 416 Village Dr ste A Plano, TX 75094-4648 US | 50 MBPS (33564902) | 01/28/2021: Pending scheduling of beas install. | 204544135 | TX611 | Access (33564902) Private IP - PIP (33564901) WAN Analysis Reporting (33564903) | 33564902 33564901 33564903 | 10 MBPS (33564901) |  | 94917378 (Access) 94917380 (Private IP (PIP)) 94917382 (WAN Analysis Reporting) | E4065893/ADD (33564902) C4025154/ADD (33564901) | 13/KRGN/509304//FTNC/ (3356490288047801) | 6205286 | 5500 | PVC ID : 6205286 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65204 PE IP Address : 147.225.77.65 CE Address : 147.225.77.66 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33564902) | 1000Base-SX (850nm, Multi Mode Fiber) (33564902) | Ethernet | FRONTIER (3356490288047801) | 12/29/2020 (3356490288047801) | 01/28/2021 (3356490288047801) | 01/28/2021 (3356490288047801) | 01/29/2021 (VFORCE) (33564902) | 01/29/2021 (VFORCE) (33564902) | DEMARCDET - 2nd floor telco demarc |  | EMMANUEL UDOJI 1-214-707-6875 emmanuel_udoji@optum.com | JEGIN MIKO DIMAYUGA | jegin_dimayuga@optum.com | 1-631-391-9670 | 01/29/2021(Access) 01/29/2021(Private IP - PIP) 01/29/2021(WAN Analysis Reporting) |  |  | 02/04/2021 (33564902) 02/08/2021 (33564901) | 02/10/2021 02/16/2021 | 01/29/2021 |  | Completed | N (33564902) N (33564901) N (33564903) | U0101953 | Jeopardy Notification 1 (12/23/2020) |  | NSPE0014248923
Completed | TX617 | 8235 S NEW BRAUNFELS SAN ANTONIO, TX 78235-4439 US | 50 MBPS (33581439) | 04/12/2021: Order Completed on Apr 12, 2021 | 204563017 | San Antonio | Private IP - PIP (33581438) WAN Analysis Reporting (33581440) Access (33581439) | 33581438 33581440 33581439 | 10 MBPS (33581438) |  | 1332793837 (Private IP (PIP)) 1332793839 (WAN Analysis Reporting) 1332793833 (Access) | C4025184/ADD (33581438) E4065965/ADD (33581439) | 21.L1XX.993726..CHTR (3358143988308701) | 6205799 | 5500 | PVC ID : 6205799 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64729 PE IP Address : 68.137.139.189 CE Address : 68.137.139.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33581439) | 1000Base-SX (850nm, Multi Mode Fiber) (33581439) | Ethernet | TIME WARNER CABLE (3358143988308701) | 03/12/2021 (3358143988308701) | 04/20/2021 (3358143988308701) | 04/09/2021 (3358143988308701) | 04/12/2021 (VFORCE) (33581439) | 04/12/2021 (VFORCE) (33581439) | DEMARCDET - 1st floor, in the server room IT closet |  | SHAWNA MALONE 1-210-762-3673 shmalone@wellmed.net | vasdudev k | vasdudev.k@optum.com | 91-886-175-8263 | 04/12/2021(Private IP - PIP) 04/12/2021(WAN Analysis Reporting) 04/12/2021(Access) |  |  | 04/29/2021 (33581438) 04/27/2021 (33581439) | 07/30/2021 08/05/2021 | 04/12/2021 |  | Completed | N (33581438) N (33581440) N (33581439) | U0101953 | Jeopardy Notification 2 (03/05/2021) |  | NSPE0014254590
Completed | FL120 | 9045 Strada Stell Ct Naples, FL 34109-4438 US | 50 MBPS (33581602) | 12/16/2020: Order Completed on Dec 15, 2020 | 204564099 | ENT FL120 NAPLES | Private IP - PIP (33581601) WAN Analysis Reporting (33581603) Access (33581602) | 33581601 33581603 33581602 | 20 MBPS (33581601) |  | 94920279 (Private IP (PIP)) 94920286 (WAN Analysis Reporting) 94920281 (Access) | C4025183/ADD (33581601) E4065963/ADD (33581602) | 25.KXGS.565862..UFLG (3358160269276101) | 6205783 | 13000 | PVC ID : 6205783 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65166 PE IP Address : 68.136.61.69 CE Address : 68.136.61.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33581602) | 1000Base-SX (850nm, Multi Mode Fiber) (33581602) | Ethernet | CENTURYLINK (3358160269276101) | 12/04/2020 (3358160269276101) | 12/15/2020 (3358160269276101) | 12/10/2020 (3358160269276101) | 12/15/2020 (VFORCE) (33581602) | 12/15/2020 (VFORCE) (33581602) | DEMARCDET - 1ST FLOOR ,MAIN BUILDING ,PHONE ROOM. RAD205A IS WALL MOUNTED AT THE MPOE TAGGED AND LABELED PORT 4 |  | Jorge Moral 1-954-364-0713 Jorge.Moral@optum.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 | 12/15/2020(Private IP - PIP) 12/15/2020(WAN Analysis Reporting) 12/15/2020(Access) |  |  | 12/24/2020 (33581601) 12/22/2020 (33581602) | 01/20/2021 01/26/2021 | 12/15/2020 |  | Completed | N (33581601) N (33581603) N (33581602) | U0101953 | Jeopardy Notification 1 (12/11/2020) |  | NSPE0014254892
Completed | NY033 | 2950 EXPRESS DR S ISLANDIA, NY 11749-1400 US | 100 MBPS (33599350) | 01/15/2021: Order Completed on Jan 15, 2021 | 204582559 | UNITED HEALTH GROUP | Private IP - PIP WAN Analysis Reporting (33599351) Access (33599350) | 33599350 33599351 | 100 MBPS |  | 94856614 94856621 (WAN Analysis Reporting) 94856618 (Access) | E4061959/NONE (33599350) |  |  |  |  | 1000Base-SX-850nm (33599350) | 1000Base-SX (850nm, Multi Mode Fiber) (33599350) | Ethernet | [8 empty] | Jenelle Fleary 1-212-216-6593 jenelle_fleary@uhg.com | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 | 01/15/2021(Access) |  |  | 01/14/2021 (33599350) | 12/16/2020 (24061917.4) 12/16/2020 | 01/15/2021 |  | Activated/Installed Completed | N N (33599351) N (33599350) | U0101953 |  |  | NSPE0014260872
Completed | C1662 | 41 Alexander Rd Billerica, MA 01821-5045 US | 500 MBPS (33602654) | 02/04/2021: Pending CCR 1896076 beas install, all work complete. Tech scheduled for end to end testing, 2/4. Pending successful testing and completion of order. | 204594641 | C1662 | Private IP - PIP (33602653) WAN Analysis Reporting (33602655) Access (33602654) | 33602653 33602655 33602654 | 200 MBPS (33602653) |  | 94921959 (Private IP (PIP)) 94921963 (WAN Analysis Reporting) 94921965 (Access) | C5012791/ADD (33602653) E5031058/ADD (33602654) |  | 6206833 | 110000 | PVC ID : 6206833 VPN Name : UHG-ECC Router Name : CHTXE03 VRF Name : Vj03572-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65407 PE IP Address : 152.181.178.197 CE Address : 152.181.178.198 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (33602654) | Ethernet |  |  |  |  | 02/01/2021 (CCP) (33602653) 02/01/2021 (CCP) (33602654) | 02/03/2021 (CCP) (33602653) 02/03/2021 (CCP) (33602654) |  |  | Jeremy Colosimo 1-860-919-8534 jcolosimo@wexhealthinc.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 | 02/05/2021(Private IP - PIP) 02/05/2021(WAN Analysis Reporting) 02/05/2021(Access) |  |  | 02/19/2021 (33602653) 02/17/2021 (33602654) | 01/08/2021 01/14/2021 | 02/05/2021 |  | Completed | N (33602653) N (33602655) N (33602654) | U0101953 |  |  | NSPE0014262547
Completed | AZ178 | 15021 W Bell Rd Surprise, AZ 85374-3916 US | 100 MBPS (33630202) | 02/04/2021: Order Completed on Feb 3, 2021 | 204619311 | AZ178 | Private IP - PIP (33630201) WAN Analysis Reporting (33630203) Access (33630202) | 33630201 33630203 33630202 | 50 MBPS (33630201) |  | 94923461 (Private IP (PIP)) 94923463 (WAN Analysis Reporting) 94923459 (Access) | C1150018/ADD (33630201) E4066167/ADD (33630202) | 23.KFGX.992016..COXC. (3363020288727901) | 6207190 | 30000 | PVC ID : 6207190 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : Vh97246:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64702 PE IP Address : 152.162.163.161 CE Address : 152.162.163.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33630202) | 1000Base-SX (850nm, Multi Mode Fiber) (33630202) | Ethernet | COX (3363020288727901) | 11/20/2020 (3363020288727901) | 02/01/2021 (3363020288727901) | 02/02/2021 (3363020288727901) | 02/03/2021 (VFORCE) (33630202) |  | DEMARCDET - ground floor, UHC suite, past receptionist area to door on left to IT/server room, COX demark panel port 16 |  | KIMBERLY A FLICEK 1-612-474-7105 kim.flicek@optum.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 02/03/2021(Private IP - PIP) 02/03/2021(WAN Analysis Reporting) 02/03/2021(Access) |  |  | 05/25/2021 (33630201) 05/21/2021 (33630202) | 02/11/2021 02/17/2021 | 02/03/2021 |  | Completed | N (33630201) N (33630203) N (33630202) | U0101953 |  |  | NSPE0014270771
Completed | AZ176 | 10249 W Thunderbird Blvd Sun City, AZ 85351-3113 US | 100 MBPS (33641329) | 03/03/2021: Order Completed on Mar 3, 2021 | 204629657 | AZ176 | Private IP - PIP (33641328) WAN Analysis Reporting (33641330) Access (33641329) | 33641328 33641330 33641329 | 50 MBPS (33641328) |  | 94924426 (Private IP (PIP)) 94924422 (WAN Analysis Reporting) 94924424 (Access) | C1150047/ADD (33641328) E4066202/ADD (33641329) | 23.KFGX.992017..COXC. (3364132988799401) | 6207515 | 30000 | PVC ID : 6207515 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : Vh97246:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64722 PE IP Address : 206.115.19.69 CE Address : 206.115.19.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33641329) | 1000Base-SX (850nm, Multi Mode Fiber) (33641329) | Ethernet | COX (3364132988799401) | 11/20/2020 (3364132988799401) | 02/25/2021 (3364132988799401) | 02/25/2021 (3364132988799401) | 03/01/2021 (VFORCE) (33641329) | 03/01/2021 (VFORCE) (33641329) | DEMARCDET - Ground floor fire control room racked in customers relay rack conncted to port 2 on patch pannel of Nokia 7210 switch |  | KIMBERLY A FLICEK 1-612-474-7105 kim.flicek@optum.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 03/01/2021(Private IP - PIP) 03/01/2021(WAN Analysis Reporting) 03/01/2021(Access) |  |  | 05/27/2021 (33641328) 05/25/2021 (33641329) | 03/10/2021 03/16/2021 | 03/03/2021 |  | Completed | N (33641328) N (33641330) N (33641329) | U0101953 |  |  | NSPE0014274121
Completed | AZ175 | 3090 N Litchfield Rd Goodyear, AZ 85395-9212 US | 100 MBPS (33656878) | 02/25/2021: Order Completed on Feb 25, 2021 | 204645027 | AZ175 | Private IP - PIP (33656877) WAN Analysis Reporting (33656879) Access (33656878) | 33656877 33656879 33656878 | 50 MBPS (33656877) |  | 94925984 (Private IP (PIP)) 94925982 (WAN Analysis Reporting) 94925987 (Access) | C1150110/ADD (33656877) E4066278/ADD (33656878) | 23.KFGX.992022..COXC. (3365687888846701) | 6208190 | 30000 | PVC ID : 6208190 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : Vh97246:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65116 PE IP Address : 152.164.103.77 CE Address : 152.164.103.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33656878) | 1000Base-SX (850nm, Multi Mode Fiber) (33656878) | Ethernet | COX (3365687888846701) | 11/23/2020 (3365687888846701) | 05/06/2021 (3365687888846701) | 02/23/2021 (3365687888846701) | 02/25/2021 (VFORCE) (33656878) | 02/25/2021 (VFORCE) (33656878) | DEMARCDET - 1st flr server rm mounted on wall board nokia SAS K5 port 2 to demarc panel port 6 |  | KIMBERLY A FLICEK 1-612-474-7105 kim.flicek@optum.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 02/25/2021(Private IP - PIP) 02/25/2021(WAN Analysis Reporting) 02/25/2021(Access) |  |  | 05/17/2021 (33656877) 05/13/2021 (33656878) | 03/10/2021 03/16/2021 | 02/25/2021 |  | Completed | N (33656877) N (33656879) N (33656878) | U0101953 |  |  | NSPE0014278195
Completed | TX633 | 1611 N Belt Line Rd ste A Mesquite, TX 75149-1792 US | 50 MBPS (33762626) | 02/06/2021: Order Completed on Feb 5, 2021 | 204738635 | TX633 | Private IP - PIP (33762625) WAN Analysis Reporting (33762627) Access (33762626) | 33762625 33762627 33762626 | 10 MBPS (33762625) |  | 94933978 (Private IP (PIP)) 94933980 (WAN Analysis Reporting) 94933976 (Access) | C4025408/ADD (33762625) E4066786/ADD (33762626) | 97.L1XX.815755..CHTR (3376262689513201) | 6212487 | 5500 | PVC ID : 6212487 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64677 PE IP Address : 68.137.203.129 CE Address : 68.137.203.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33762626) | 1000Base-SX (850nm, Multi Mode Fiber) (33762626) | Ethernet | TIME WARNER CABLE (3376262689513201) | 12/08/2020 (3376262689513201) | 03/31/2021 (3376262689513201) | 02/01/2021 (3376262689513201) | 02/05/2021 (VFORCE) (33762626) |  | DEMARCDET - 1st flr IT rm wall mounted |  | SHERRY GREEN 1-612-642-7302 sgreen11@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 02/05/2021(Private IP - PIP) 02/05/2021(WAN Analysis Reporting) 02/05/2021(Access) |  |  | 04/09/2021 (33762625) 04/07/2021 (33762626) | 01/27/2021 02/02/2021 | 02/05/2021 |  | Completed | N (33762625) N (33762627) N (33762626) | U0101953 |  |  | NSPE0014312232
Completed | TX619 | 13420 State Highway 249 ste I Houston, TX 77086-3167 US | 50 MBPS (33778357) | 03/16/2021: Order Completed on Mar 16, 2021 | 204755725 | TX619 | Private IP - PIP (33778356) WAN Analysis Reporting (33778358) Access (33778357) | 33778356 33778358 33778357 | 10 MBPS (33778356) |  | 94933968 (Private IP (PIP)) 94933970 (WAN Analysis Reporting) 94933966 (Access) | C4025433/ADD (33778356) E4066869/ADD (33778357) | 199991-ENET-CCF (3377835789504601) | 6213042 | 5500 | PVC ID : 6213042 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65284 PE IP Address : 152.181.36.109 CE Address : 152.181.36.110 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33778357) | 1000Base-SX (850nm, Multi Mode Fiber) (33778357) | Ethernet | CLEC or INDEPENDENT (3377835789504601) | 12/09/2020 (3377835789504601) | 04/19/2021 (3377835789504601) | 03/12/2021 (3377835789504601) | 03/16/2021 (VFORCE) (33778357) | 03/16/2021 (VFORCE) (33778357) | DEMARCDET - Suite 1 wall mounted |  | Christian Campbell 1-813-462-3162 campbell1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 03/16/2021(Private IP - PIP) 03/16/2021(WAN Analysis Reporting) 03/16/2021(Access) |  |  | 04/28/2021 (33778356) 04/26/2021 (33778357) | 04/26/2021 04/30/2021 | 03/16/2021 |  | Completed | N (33778356) N (33778358) N (33778357) | U0101953 |  |  | NSPE0014318616
Completed | C1663 | 6900 S PEORIA ST CENTENNIAL, CO 80112-4137 US | 10 GBPS (33831513) | 02/09/2021: Order Completed on Feb 9, 2021 | 204801737 | UHG- Trizetto | Private IP - PIP (33831512) WAN Analysis Reporting (33831514) Access (33831513) | 33831512 33831514 33831513 | 1 GBPS (33831512) |  | 1341961883 (Private IP (PIP)) 1341961885 (WAN Analysis Reporting) 1341961879 (Access) | C0210882/ADD (33831512) E7002387/ADD (33831513) |  | 6214643 | 550000 | PVC ID : 6214643 VPN Name : UHG-ECC Router Name : EADXE01 VRF Name : Vi90743-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65436 PE IP Address : 68.136.181.93 CE Address : 68.136.181.94 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (33831513) | Ethernet |  |  |  |  | 01/28/2021 (CCP) (33831512) 01/28/2021 (CCP) (33831513) | 01/12/2021 (CCP) (33831512) 01/12/2021 (CCP) (33831513) |  |  | Neil Bower 1-720-515-0434 NEIL.BOWER@TTEC.COM | Neil Bower | NEIL.BOWER@TTEC.COM | 1-720-515-0434 | 02/09/2021(Private IP - PIP) 02/09/2021(WAN Analysis Reporting) 02/09/2021(Access) |  |  | 02/15/2021 (33831512) 02/11/2021 (33831513) | 01/13/2021 01/20/2021 | 02/09/2021 |  | Completed | N (33831512) N (33831514) N (33831513) | U0101953 |  |  | NSPE0014334411
Completed | PA183 | 4000 Chemical Rd ste 100 Plymouth Meeting, PA 19462-1728 US | 50 MBPS (33921414) | 02/09/2021: Order Completed on Feb 9, 2021 | 204824607 | PA183 | Private IP - PIP (33921413) WAN Analysis Reporting (33921415) Access (33921414) | 33921413 33921415 33921414 | 10 MBPS (33921413) |  | 94938780 (Private IP (PIP)) 94938783 (WAN Analysis Reporting) 94938778 (Access) | C4025600/ADD (33921413) E4067364/ADD (33921414) | 11.KFGS.314175..PA (3392141489980402) | 6217615 | 5500 | PVC ID : 6217615 VPN Name : UnitedHealthGroup Router Name : PBYXE01 VRF Name : V486413-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64623 PE IP Address : 152.176.164.189 CE Address : 152.176.164.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33921414) | 1000Base-SX (850nm, Multi Mode Fiber) (33921414) | Ethernet | VERIZON (3392141489980402) | 01/21/2021 (3392141489980402) | 01/29/2021 (3392141489980402) | 02/09/2021 (3392141489980402) |  |  | DEMARCDET - 1st floor main telephone room/wall mounted / nid #2 tagged / not extended /9145e-ve13 |  | Alyssa Cehok 1-716-713-1840 alyssa_cehok@uhg.com | Jose Carlo Ritual | jose_ritual@optum.com | 632-790-6489 | 02/09/2021(Private IP - PIP) 02/09/2021(WAN Analysis Reporting) 02/09/2021(Access) |  |  | 02/09/2021 (33921413) 02/05/2021 (33921414) | 02/17/2021 02/23/2021 | 02/09/2021 |  | Completed | N (33921413) N (33921415) N (33921414) | U0101953 | Jeopardy Notification 3 (01/12/2021) |  | NSPE0014341746
Completed | AZ167 | 9045 E PIMA CENTER PKWY SCOTTSDALE, AZ 85258-4538 US | 50 MBPS (33878341) | 03/25/2021: Beas install scheduled for 3/26. | 204832219 | Scottsdale | Private IP - PIP (33878340) WAN Analysis Reporting (33878342) Access (33878341) | 33878340 33878342 33878341 | 20 MBPS (33878340) |  | 1342698599 (Private IP (PIP)) 1342698601 (WAN Analysis Reporting) 1342698595 (Access) | C4025556/ADD (33878340) E4067242/ADD (33878341) | CA/EVPL/001401/IDTL/VBZ (3387834186432201) | 6215818 | 15000 | PVC ID : 6215818 VPN Name : UnitedHealthGroup Router Name : LSA29E01 VRF Name : V461763:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64633 PE IP Address : 68.138.33.185 CE Address : 68.138.33.186 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33878341) | 1000Base-SX (850nm, Multi Mode Fiber) (33878341) | Ethernet | INDATEL SERVICES, LLC (3387834186432201) | 03/15/2021 (3387834186432201) | 03/15/2021 (3387834186432201) | 03/24/2021 (3387834186432201) | 04/01/2021 (VFORCE) (33878341) | 04/01/2021 (VFORCE) (33878341) | DEMARCADDR - 1ST FLR MDF ROOM DEMARCDET - 1ST FLR MDF ROOM |  | STEVE LEARCH 1-855-351-9517 slearch@diplomat.is | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 | 03/30/2021(Private IP - PIP) 03/30/2021(WAN Analysis Reporting) 03/30/2021(Access) |  |  | 03/09/2021 (33878340) 03/05/2021 (33878341) | 02/02/2021 02/08/2021 | 03/30/2021 |  | Completed | N (33878340) N (33878342) N (33878341) | U0101953 | Jeopardy Notification 1 (03/26/2021) |  | NSPE0014345384
Completed | TX610 | 6907 N Capital Of Texas Hwy Austin, TX 78731-1755 US | 50 MBPS (34028904) | 01/21/2021: FOC date 1/22. | 204965821 | TX610 | Private IP - PIP (34028903) WAN Analysis Reporting (34028905) Access (34028904) | 34028903 34028905 34028904 | 20 MBPS (34028903) |  | 94951330 (Private IP (PIP)) 94951333 (WAN Analysis Reporting) 94951328 (Access) | C4025772/ADD (34028903) E4067817/ADD (34028904) | 32/KRGN/654790//SW (3402890489228201) | 6220761 | 13000 | PVC ID : 6220761 VPN Name : UnitedHealthGroup Router Name : AX39E01 VRF Name : Vd31961:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64679 PE IP Address : 152.177.124.141 CE Address : 152.177.124.142 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34028904) | 1000Base-LX (1310nm Single Mode Fiber) (34028904) | Ethernet | ATT (3402890489228201) | 01/13/2021 (3402890489228201) | 01/22/2021 (3402890489228201) | 01/22/2021 (3402890489228201) | 01/26/2021 (VFORCE) (34028904) | 01/25/2021 (VFORCE) (34028904) | DEMARCADDR - . DEMARCDET - 3930 WALL MOUNTED ON THE SECOND FLOOR JANITOR/TELCO ROOM PORT 7 TAGGED NOT EXT CIENA 3930 PORT 7 |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 01/25/2021(Private IP - PIP) 01/25/2021(WAN Analysis Reporting) 01/25/2021(Access) |  |  | 02/02/2021 (34028903) 01/29/2021 (34028904) | 02/24/2021 03/02/2021 | 01/25/2021 |  | Completed | N (34028903) N (34028905) N (34028904) | U0101953 |  |  | NSPE0014398923
Completed | AL012-02-IJ | 1100 Lee Branch Ln Birmingham, AL 35242-7298 US | 50 MBPS (34107886) | 02/25/2021: Install scheduled 02/26/2021. | 205048059 | AL012-02-IJ Birmingham, AL | Private IP - PIP (34107885) WAN Analysis Reporting (34107887) Access (34107886) | 34107885 34107887 34107886 | 20 MBPS (34107885) |  | 94960107 (Private IP (PIP)) 94960111 (WAN Analysis Reporting) 94960104 (Access) | C4025937/ADD (34107885) E4068247/ADD (34107886) | 20.L1XX.905457..CHTR (3410788612617001) | 6224108 | 13000 | PVC ID : 6224108 VPN Name : UnitedHealthGroup Router Name : ATL29E01 VRF Name : V581602:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64815 PE IP Address : 152.177.167.161 CE Address : 152.177.167.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34107886) | 1000Base-SX (850nm, Multi Mode Fiber) (34107886) | Ethernet | CHARTER (3410788612617001) | 01/26/2021 (3410788612617001) | 05/10/2021 (3410788612617001) | 03/01/2021 (3410788612617001) | 03/03/2021 (VFORCE) (34107886) | 03/03/2021 (VFORCE) (34107886) | DEMARCDET - 1st flr rm 128 wall mounted tagged |  | Dan Jarnigan 1-630-577-3827 Dan.jarnigan@catamaranrx.com | JOSE CARLO RITUAL | jose_ritual@optum.com | 632-790-6489 | 03/03/2021(Private IP - PIP) 03/03/2021(WAN Analysis Reporting) 03/03/2021(Access) |  |  | 05/19/2021 (34107885) 05/17/2021 (34107886) | 06/14/2021 06/18/2021 | 03/03/2021 |  | Completed | N (34107885) N (34107887) N (34107886) | U0101953 |  |  | NSPE0014427622
Completed | TX625 | 6710 Capitol St Houston, TX 77011-4422 US | 50 MBPS (34109323) | 04/01/2021: The rework was completed on 03/26/2021 and technician has already been assigned for 04/02/2021. | 205049241 | TX625 | Private IP - PIP (34109322) WAN Analysis Reporting (34109324) Access (34109323) | 34109322 34109324 34109323 | 10 MBPS (34109322) |  | 94960062 (Private IP (PIP)) 94960064 (WAN Analysis Reporting) 94960066 (Access) | C4025943/ADD (34109322) E4068248/ADD (34109323) | 28/KRGN/751035//SW (3410932391102601) | 6224194 | 5500 | PVC ID : 6224194 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65046 PE IP Address : 152.177.250.137 CE Address : 152.177.250.138 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34109323) | 1000Base-SX (850nm, Multi Mode Fiber) (34109323) | Ethernet | ATT (3410932391102601) | 01/28/2021 (3410932391102601) | 03/24/2021 (3410932391102601) | 04/02/2021 (3410932391102601) | 04/07/2021 (VFORCE) (34109323) | 04/07/2021 (VFORCE) (34109323) | DEMARCADDR - 6710 Capitol St Houston TX DEMARCDET - 2ND FLR,NEW MDF RM CIRCUIT TAGGED FIBER JACK ABOVE CIENA |  | SCOTT CANNON 1-813-695-3652 scannon1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 04/07/2021(Private IP - PIP) 04/07/2021(WAN Analysis Reporting) 04/07/2021(Access) |  |  | 05/03/2021 (34109322) 04/29/2021 (34109323) | 03/10/2021 03/16/2021 | 04/07/2021 |  | Completed | N (34109322) N (34109324) N (34109323) | U0101953 |  |  | NSPE0014428006
Completed | TX626 | 325 W 20th St Houston, TX 77008-2436 US | 50 MBPS (34110146) | 02/13/2021: Order Completed on Feb 12, 2021 | 205050285 | TX626 | Private IP - PIP (34110145) WAN Analysis Reporting (34110147) Access (34110146) | 34110145 34110147 34110146 | 10 MBPS (34110145) |  | 94960131 (Private IP (PIP)) 94960135 (WAN Analysis Reporting) 94960128 (Access) | C4025942/ADD (34110145) E4068250/ADD (34110146) | 28/KRGN/751037//SW (3411014691103601) | 6224187 | 5500 | PVC ID : 6224187 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65370 PE IP Address : 152.177.226.217 CE Address : 152.177.226.218 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34110146) | 1000Base-SX (850nm, Multi Mode Fiber) (34110146) | Ethernet | ATT (3411014691103601) | 01/26/2021 (3411014691103601) | 02/10/2021 (3411014691103601) | 02/11/2021 (3411014691103601) | 02/12/2021 (VFORCE) (34110146) |  | DEMARCDET - 1ST FLR, NETWORK RM, RELAY RACK, 3903, PORT 2 TAGGED W/CKT ID |  | SCOTT CANNON 1-813-695-3652 scannon1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 02/12/2021(Private IP - PIP) 02/12/2021(WAN Analysis Reporting) 02/12/2021(Access) |  |  | 03/02/2021 (34110145) 02/26/2021 (34110146) | 03/10/2021 03/16/2021 | 02/12/2021 |  | Scheduled | N (34110145) N (34110147) N (34110146) | U0101953 |  |  | NSPE0014428288
Completed | TX628 | 4000 Fulton St Houston, TX 77009-4766 US | 50 MBPS (34154299) | 03/18/2021: Circuit delivered. Beas install scheduled for 3/22 between 1pm-5pm CT. | 205093651 | TX628 | Private IP - PIP (34154298) WAN Analysis Reporting (34154300) Access (34154299) | 34154298 34154300 34154299 | 10 MBPS (34154298) |  | 94963086 (Private IP (PIP)) 94963090 (WAN Analysis Reporting) 94963083 (Access) | C4026009/ADD (34154298) E4068429/ADD (34154299) | 28/KRGN/751070//SW (3415429991341301) | 6226118 | 5500 | PVC ID : 6226118 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64546 PE IP Address : 152.183.91.33 CE Address : 152.183.91.34 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34154299) | 1000Base-SX (850nm, Multi Mode Fiber) (34154299) | Ethernet | ATT (3415429991341301) | 03/09/2021 (3415429991341301) | 03/16/2021 (3415429991341301) | 03/17/2021 (3415429991341301) | 03/22/2021 (VFORCE) (34154299) | 03/22/2021 (VFORCE) (34154299) | DEMARCDET - 1ST FLR,TELCO RM,WALL MOUNTED CIENA 3930 , PORTS 1 AND 2 TAGGED WITH CID |  | SCOTT B CANNON 1-813-695-3652 scannon1@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 03/23/2021(Private IP - PIP) 03/23/2021(WAN Analysis Reporting) 03/23/2021(Access) |  |  | 05/05/2021 (34154298) 05/03/2021 (34154299) | 03/11/2021 03/17/2021 | 03/23/2021 |  | Completed | N (34154298) N (34154300) N (34154299) | U0101953 |  |  | NSPE0014447202
Completed | MA710 | 70 INNERBELT RD SOMERVILLE, MA 02143-4461 US | 1 GBPS (34154270) | 02/23/2021: Order Completed on Feb 23, 2021 | 205094675 | Somerville | Private IP - PIP (34154269) WAN Analysis Reporting (34154271) Access (34154270) | 34154269 34154271 34154270 | 500 MBPS (34154269) |  | 1349761761 (Private IP (PIP)) 1349761763 (WAN Analysis Reporting) 1349761757 (Access) | C0212841/ADD (34154269) E5032854/ADD (34154270) |  | 6226078 | 350000 | PVC ID : 6226078 VPN Name : UnitedHealthGroup Router Name : CHTXE03 VRF Name : V637075-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65053 PE IP Address : 68.137.48.233 CE Address : 68.137.48.234 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (34154270) | Ethernet |  |  |  |  | 02/17/2021 (CCP) (34154269) 02/17/2021 (CCP) (34154270) | 02/18/2021 (CCP) (34154269) 02/18/2021 (CCP) (34154270) |  |  | Raffaele Mortillaro 1-978-559-9481 raffaele.mortillaro@optum.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 | 02/23/2021(Private IP - PIP) 02/23/2021(WAN Analysis Reporting) 02/23/2021(Access) |  |  | 03/02/2021 (34154269) 02/26/2021 (34154270) | 03/23/2021 03/29/2021 | 02/23/2021 |  | Completed | N (34154269) N (34154271) N (34154270) | U0101953 |  |  | NSPE0014438670
Completed | TX623 | 720 E Tidwell Rd Houston, TX 77022-1822 US | 50 MBPS (34152197) | 03/25/2021: Circuit delivered. Pending scheduling of beas install. | 205092063 | TX623 | Private IP - PIP (34152196) WAN Analysis Reporting (34152198) Access (34152197) | 34152196 34152198 34152197 | 10 MBPS (34152196) |  | 94963076 (Private IP (PIP)) 94963080 (WAN Analysis Reporting) 94963073 (Access) | C4026001/ADD (34152196) E4068422/ADD (34152197) | 28/KRGN/751068//SW (3415219791333901) | 6226015 | 5500 | PVC ID : 6226015 VPN Name : UnitedHealthGroup Router Name : HSTN9E01 VRF Name : Vi38053:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64654 PE IP Address : 152.176.138.133 CE Address : 152.176.138.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34152197) | 1000Base-SX (850nm, Multi Mode Fiber) (34152197) | Ethernet | ATT (3415219791333901) | 01/29/2021 (3415219791333901) | 03/23/2021 (3415219791333901) | 03/24/2021 (3415219791333901) | 03/30/2021 (VFORCE) (34152197) | 03/30/2021 (VFORCE) (34152197) | DEMARCDET - 1ST FLR,IT ROOM,WALL MOUNTED |  | SCOTT B CANNON 1-813-695-3652 scannon1@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 | 03/30/2021(Private IP - PIP) 03/30/2021(WAN Analysis Reporting) 03/30/2021(Access) |  |  | 05/03/2021 (34152196) 04/29/2021 (34152197) | 03/11/2021 03/17/2021 | 03/30/2021 |  | Completed | N (34152196) N (34152198) N (34152197) | U0101953 |  |  | NSPE0014446703
Completed | MS007 | 3539 Bluecutt Rd Columbus, MS 39705-1324 US | 50 MBPS (34242082) | 03/05/2021: Your order is on track: Provisioning Department accepted the order on Feb 9, 2021 and has begun processing. | 205179251 | UNITED HEALTH GROUP | Access (34242082) Private IP - PIP (34242081) WAN Analysis Reporting (34242083) | 34242082 34242081 34242083 | 10 MBPS (34242081) |  | 94967875 (Access) 94967872 (Private IP (PIP)) 94967878 (WAN Analysis Reporting) | E4068883/ADD (34242082) C4026156/ADD (34242081) | M1/KRGN/826252//SC (3424208218598401) | 6229643 | 5500 | PVC ID : 6229643 VPN Name : UnitedHealthGroup Router Name : T7E9E01 VRF Name : Vj11181:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64552 PE IP Address : 68.137.125.169 CE Address : 68.137.125.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34242082) | 1000Base-SX (850nm, Multi Mode Fiber) (34242082) | Ethernet | ATT (3424208218598401) | 02/09/2021 (3424208218598401) | 03/03/2021 (3424208218598401) | 03/03/2021 (3424208218598401) | 03/10/2021 (VFORCE) (34242082) |  | DEMARCADDR - . DEMARCDET - . |  | Amy Huckaby 1-662-570-6309 amy.huckaby@optum.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 03/10/2021(Access) 03/10/2021(Private IP - PIP) 03/10/2021(WAN Analysis Reporting) |  |  | 03/18/2021 (34242082) 03/22/2021 (34242081) | 03/22/2021 03/26/2021 | 03/10/2021 |  | Completed | N (34242082) N (34242081) N (34242083) | U0101953 |  |  | NSPE0014475732
Completed | IN156 handoff change | 5975 CASTLE CREEK PKWY STE 100 INDIANAPOLIS, IN 46250 US | 250 MBPS (34481535) | 03/26/2021: Hotcut completed 3/18 and circuit accepted. Provisioning opened IT ticket to assist with order completion. | 205416531 | IN156 | WAN Analysis Reporting (34481536) Access (34481535) Private IP - PIP | 34481536 34481535 | 100 MBPS |  | 94875207 (WAN Analysis Reporting) 94875204 (Access) 94875201 | E0049089/NONE (34481535) |  |  |  |  | 1000Base-LX-1310nm (34481535) | 1000Base-SX (850nm, Multi Mode Fiber) (34481535) | Ethernet |  |  |  |  | 03/18/2021 (VFORCE) (34481535) | 03/18/2021 (VFORCE) (34481535) |  |  | STEPHEN KLEIN 1-317-806-2035 sklein@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 | 03/30/2021(Access) |  |  | 03/12/2021 (34481535) | 04/16/2021 (30392333.1) 04/16/2021 | 03/30/2021 |  | Completed Activated/Installed | N (34481536) N (34481535) N | U0101953 |  |  | NSPE0014570732
Completed | CA035 | 425 Market St San Francisco, CA 94105-2532 US | 300 MBPS (34575588) | 03/20/2021: Order Completed on Mar 20, 2021 | 205506305 | UNITED HEALTH GROUP | Private IP - PIP (34575587) WAN Analysis Reporting (34575589) Access (34575588) | 34575587 34575589 34575588 | 200 MBPS (34575587) |  | 94989012 (Private IP (PIP)) 94989017 (WAN Analysis Reporting) 94989010 (Access) | C5014162/ADD (34575587) E5034088/ADD (34575588) |  | 6236833 | 140000 | PVC ID : 6236833 VPN Name : UnitedHealthGroup Router Name : 96FXE02 VRF Name : Vj33744-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64642 PE IP Address : 152.183.206.29 CE Address : 152.183.206.30 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (34575588) | Ethernet | [8 empty] | MIKE PONCE 1-925-246-1343 mike.ponce@uhg.com | SUSHIL Gautam | sushil_gautam@uhc.com | 91-124-309-5736 | 03/19/2021(Private IP - PIP) 03/19/2021(WAN Analysis Reporting) 03/19/2021(Access) |  |  | 03/26/2021 (34575587) 03/24/2021 (34575588) | 04/26/2021 04/30/2021 | 03/20/2021 |  | Scheduled | N (34575587) N (34575589) N (34575588) | U0101953 |  |  | NSPE0014611064
Verizon Restricted

## Cancelled
Customer Summary Status | Site ID | Location - Customer Location Z Full Address | Access Speed | External Comments - Latest | TIN/ProQuest Service Order ID | Location Name | Product (Order ID) | Order ID | Port Speed | COMS Service ID | Service ID | Circuit ID | Telco Circuit ID | PVC ID | Gold CAR | PIP Configlet | TPV LAN Interface | WAN Interface to the CE (Customer Edge) | Customer Handoff | Telco Name (Purchase Order Number) | Telco ASR Sent | Telco FOC Date | Loop Accepted | Dispatch Scheduled (NID) | Dispatch Completion Date | Actual Demarc | Site Contact A | Site Contact Z | Technical Contact Name | Technical Contact Email | Technical Contact Number | Close to Bill | Hotcut Completed Date | VZ Committed Due Date | Requested Due Date | Service Order Billing Complete | Cancel Date | Managed Status | Expedite Flag | BAN | Jeop Notification | Description | Email ID | Request Date
Cancelled | FL038-05-IJ Miami FL | 2960 SW 8TH ST STE 2970 MIAMI, FL 33135-2827 US | 10 MBPS (21456409) | 03/10/2016: 3/10- this order is being cancelled. | 191618987 | FL038-05-IJ Miami FL | Private IP - PIP (21456408) Access (21456409) | 21456408 21456409 | 10 MBPS (21456408) |  | 77842729 (Private IP (PIP)) 77842727 (Access) | C0060824/CANCEL (21456408) C0060824/ADD (21456408) E3013140/CANCEL (21456409) E3013140/ADD (21456409) | 60/KRGN/756106//SB (2145640910550601) | 5637386 | 4000 | PVC ID : 5637386 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64813 PE IP Address : 68.138.141.9 CE Address : 68.138.141.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21456409) | 1000Base-SX (850nm, Multi Mode Fiber) (21456409) | Ethernet | ATT (2145640910550601) | 11/06/2015 (2145640910550601) | 11/25/2015 (2145640910550601) | [5 empty] | Cristy Alfonso 1-305-631-3000 CAlfonso@PCPMedicalGroup.com | ROBERT BENSON | robert_a_benson@optum.com | 1-763-744-2077 | 03/14/2016(Private IP - PIP) 03/14/2016(Access) |  | 03/29/2016 (21456408) 03/25/2016 (21456409) | 03/01/2016 | 03/14/2016 | 03/09/2016 (21456408) 03/14/2016 (21456409) |  | N (21456408) N (21456409) | U0101953 |  |  | NSPE0009573236
Cancelled | UNITED HEALTH GROUP | 415 W 49TH ST HIALEAH, FL 33012-3637 US | 10 MBPS (21445688) | 01/14/2016: 1/14- Order will be cancelled. | 191618983 | UNITED HEALTH GROUP | Private IP - PIP (21445687) Access (21445688) | 21445687 21445688 | 10 MBPS (21445687) |  | 77855881 (Private IP (PIP)) 77855879 (Access) | C0060719/CANCEL (21445687) C0060719/ADD (21445687) E3013074/CANCEL (21445688) E3013074/ADD (21445688) | 60/KRGN/756216//SB (2144568892075802) | 5636500 | 4000 | PVC ID : 5636500 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V545908-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65274 PE IP Address : 159.24.209.225 CE Address : 159.24.209.226 QoS - Egress Profile: G1 | 1000Base-SX-850nm (21445688) | 1000Base-SX (850nm, Multi Mode Fiber) (21445688) | Ethernet | ATT (2144568892075802) | 09/16/2015 (2144568892075802) | 11/12/2015 (2144568892075802) |  | 01/22/2016 (VFORCE) (21445688) |  |  |  | Maritza Puerto 1-305-364-3404 Mpuerto@PCPMedicalGroup.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 01/15/2016(Private IP - PIP) 01/15/2016(Access) |  | 11/23/2015 (21445687) 11/19/2015 (21445688) | 12/10/2015 | 01/18/2016 | 01/13/2016 (21445687) 01/15/2016 (21445688) |  | N (21445687) N (21445688) | U0101953 |  |  | NSPE0009573870
Cancelled | IA005-02-IJ Davenport IA | 200 E 90TH ST DAVENPORT, IA 52806-7340 US | 500 MBPS (21813239) |  | 192201733 | IA005-02-IJ Davenport, IA | Private IP - PIP (21813238) Access (21813239) | 21813238 21813239 | 500 MBPS (21813238) |  | 85826436 (Private IP (PIP)) 85826434 (Access) | C5001476/ADD (21813238) C5001476/CANCEL (21813238) E5002464/ADD (21813239) E5002464/CANCEL (21813239) |  | 5681464 |  | PVC ID : 5681464 | 1000Base-SX-850nm (21813239) | 1000Base-SX (850nm, Multi Mode Fiber) (21813239) | Ethernet |  |  |  |  | 12/07/2015 (VFORCE) (21813239) |  |  |  | Steve Tobin 1-563-529-9127 stobin@estesconstruction.com | TERRY BJORKE | terry_bjorke@optum.com | 1-763-694-7409 | 12/03/2015(Private IP - PIP) 12/03/2015(Access) |  |  | 01/07/2016 | 12/03/2015 | 12/01/2015 (21813238) 12/03/2015 (21813239) |  | N (21813238) N (21813239) | U0101953 |  |  | NSPE0009835476
Cancelled | WV033-02-IJ Dunbar WV | 206 ROXALANA BUSINESS PARK DUNBAR, WV 25064-2727 US | 100 MBPS (21909813) | 05/27/2016: 5/26- Order cancel customer requested | 192335519 | WV033-02-IJ Dunbar WV | Access (21909813) Private IP - PIP (21909812) | 21909813 21909812 | 100 MBPS (21909812) |  | 89524525 (Access) 89524527 (Private IP (PIP)) | E4008317/ADD (21909813) E4008317/CANCEL (21909813) C1030447/ADD (21909812) C1030447/CANCEL (21909812) |  | 5694782 | 1500 | PVC ID : 5694782 VPN Name : UnitedHealthGroup Router Name : PTBXE01 VRF Name : V576619-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64729 PE IP Address : 68.139.222.49 CE Address : 68.139.222.50 QoS - Egress Profile: R12 | 1000Base-SX-850nm (21909813) | 1000Base-SX (850nm, Multi Mode Fiber) (21909813) | Ethernet | [8 empty] | Don Torman 1-800-707-8194 don.torman@briovarx.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 05/31/2016(Access) 05/31/2016(Private IP - PIP) |  | 08/10/2016 (21909813) 08/12/2016 (21909812) | 06/15/2016 | 05/31/2016 | 05/31/2016 (21909813) 05/26/2016 (21909812) |  | N (21909813) N (21909812) | U0101953 |  |  | NSPE0009894157
Cancelled | OH013-02-IJ Avon Lake OH | 33381 WALKER RD AVON LAKE, OH 44012-1463 US | 100 MBPS (21946076) |  | 192445100 | OH013-02-IJ Avon Lake OH | Private IP - PIP (21946075) Access (21946076) | 21946075 21946076 | 50 MBPS (21946075) |  | 91270537 (Private IP (PIP)) 91270535 (Access) | E4008492/CANCEL (21946076) |  | 5699011 |  | PVC ID : 5699011 |  | 1000Base-SX (850nm, Multi Mode Fiber) (21946076) | Ethernet | [8 empty] | Jeff McCarthy 1-440-930-9522 jeff.McCarthy@optum.com | DON OSBORN | donald_r_osborn@optum.com | 1-214-647-4442 | 01/05/2016(Private IP - PIP) 01/05/2016(Access) |  |  | 02/17/2016 | 01/05/2016 | 01/05/2016 (21946075) 01/05/2016 (21946076) |  | N (21946075) N (21946076) | U0101953 |  |  | NSPE0009945921
Cancelled | NJ038-02-IJ Catmaran Cranford | 6 COMMERCE DR STE 302 CRANFORD, NJ 07016-3515 US | 100 MBPS | 01/21/2016: 1/21- Sent email to local contact requesting that he contact engineer to confirm date and time for site survey. | 192495874 | NJ038-02-IJ Catmaran Cranford | Private IP - PIP Access |  | 10 MBPS |  | 91498593 91498591 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Victor Ventura 1-908-603-2199 victorino.ventura@procura-inc.com | EDWARD MCLAUGHLIN | edward.mclaughlin@optum.com | 1-443-853-3646 |  |  |  | 02/26/2016 |  |  |  | N | U0101953 |  |  | NSPE0009959458
Cancelled | OR004-02-IJ Catamaran Portland | 200 SW MARKET ST STE 600 PORTLAND, OR 97201-5719 US | 100 MBPS (22005062) | 06/16/2016: 6/16- Pending cancellation completion. | 192496045 | OR004-02-IJ Catamaran Portland | Private IP - PIP (22005061) Access (22005062) | 22005061 22005062 | 20 MBPS (22005061) |  | 91647248 (Private IP (PIP)) 91647246 (Access) | C1031179/CANCEL (22005061) C1031179/ADD (22005061) E4008751/CANCEL (22005062) E4008751/ADD (22005062) | EL/KEED/839221/ /ELG (2200506212847301) | 5703363 | 10000 | PVC ID : 5703363 VPN Name : UnitedHealthGroup Router Name : HICGE02 VRF Name : V556790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64757 PE IP Address : 152.162.218.93 CE Address : 152.162.218.94 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22005062) | 1000Base-SX (850nm, Multi Mode Fiber) (22005062) | Ethernet | INTEGRA (2200506212847301) | 01/20/2016 (2200506212847301) | 02/24/2016 (2200506212847301) | 06/23/2016 (2200506212847301) |  |  | DEMARCDET - BLDG MAIN,FLR 1ST,RM SERVER |  | Mark Jajou 1-503-265-3412 Mark.jajou@catamaranrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 |  |  | 05/13/2016 (22005061) 05/11/2016 (22005062) | 06/15/2016 | 06/25/2016 | 06/06/2016 (22005061) 06/25/2016 (22005062) |  | N (22005061) N (22005062) | U0101953 |  |  | NSPE0009967826
Cancelled | PA727-02-IJ Catamaran Norristown PA | 1000 ADAMS AVE NORRISTOWN, PA 19403-2402 US | 300 MBPS (22014480) | 02/04/2016: 2/4- Order on hold, waiting for customer confirm if UHG colo with Sonepar. Address 1000 Adams Ave Norristown PA is colloc restricted for customer Sonepar | 192509767 | PA727-02-IJ Catamaran Norristown, PA | Private IP - PIP (22014479) Access (22014480) | 22014479 22014480 | 150 MBPS (22014479) |  | 92076182 (Private IP (PIP)) 92076140 (Access) | C5001614/ADD (22014479) C5001614/CANCEL (22014479) E5002773/CANCEL (22014480) E5002773/ADD (22014480) |  | 5703990 |  | PVC ID : 5703990 |  | 1000Base-LX (1310nm Single Mode Fiber) (22014480) | Ethernet | [8 empty] | John Kelly 1-610-290-7282 john.kelly@procura-inc.com | Jonathan Edwards | jonathan.edwards@optum.com | 1-781-419-8604 |  |  |  | 03/03/2016 | 02/10/2016 | 02/10/2016 (22014479) 02/10/2016 (22014480) |  | N (22014479) N (22014480) | U0101953 |  |  | NSPE0009976492
Cancelled | C1567-02-IJ West - Denver Gas and Electric ECC | 910 15TH ST STE 350 DENVER, CO 80202-3234 US | 600 MBPS (22004805) | 01/28/2016: 1/28- Order approved by provisioning. Order now being sent to design for review. | 192535030 | C1567-02-IJ West - Denver Gas and Electric ECC | Private IP - PIP (22004804) Access (22004805) | 22004804 22004805 | 400 MBPS (22004804) |  | 92493942 (Private IP (PIP)) 92493800 (Access) | C5001637/ADD (22004804) C5001637/CANCEL (22004804) E5002749/ADD (22004805) E5002749/CANCEL (22004805) |  | 5703349 | 20000 | PVC ID : 5703349 VPN Name : UHG-ECC Router Name : DNJ9E01 VRF Name : V473429:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65482 PE IP Address : 147.225.55.157 CE Address : 147.225.55.158 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (22004805) | Ethernet |  |  |  |  | 02/10/2016 (VFORCE) (22004804) 02/10/2016 (CCP) (22004804) 02/10/2016 (CCP) (22004805) |  |  |  | OVIDIO RESENDEZ 1-303-825-2552 ovi-dgeb@qwestoffice.net | SCOTT MOYER | scott_moyer@optum.com | 1-763-744-2154 | 01/31/2016(Private IP - PIP) 01/31/2016(Access) |  |  | 02/16/2016 | 01/31/2016 | 01/29/2016 (22004804) 01/31/2016 (22004805) |  | N (22004804) N (22004805) | U0101953 |  |  | NSPE0009991437
|  | 2960 SW 8TH ST MIAMI, FL 33135 USA | 1.536 MBPS (IQBK9DS9) |  | 8631022 |  | Private IP (IQBK9DS9) EVC/PVC Service (N.10954092.5705496) | IQBK9DS9 N.10954092.5705496 | 10.752 MBPS | P2132381 |  | BCBK9GLL0001 (IQBK9DS9) BCBK9GLL0002 (IQBK9DS9) BCBK9GLL0003 (IQBK9DS9) BCBK9GLL0004 (IQBK9DS9) BCBK9GLL0005 (IQBK9DS9) BCBK9GLL0006 (IQBK9DS9) BCBK9GLL0007 (IQBK9DS9) |  | 5705496 | 4000 | VPN Name : UnitedHealthGroup Router Name : POB3E02 VRF Name : V368211-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64813 PE IP Address : 206.114.79.33 CE Address : 206.114.79.34 QoS - Egress Profile: R12 PVC ID : 5705496 | [11 empty] | CRISTY ALFONSO 0013056313000 CALFONSO@PCPMEDICALGROUP.COM | [5 empty] | 02/02/2016 (IQBK9DS9) | 02/09/2016 (IQBK9DS9) |  | 02/02/2016 (10954092) |  | Y (IQBK9DS9) Y (N.10954092.5705496) | 05017789 P2132381 |  |  | NSPE0010023141
Cancelled | LA007-02-IJ Catamaran Lake Charles LA | 1737D SAM HOUSTON JONES PKWY LAKE CHARLES, LA 70611-5454 US | 100 MBPS | 02/11/2016: 2/11- Order will be cancelled and reissued with correct address. | 192694481 | LA007-02-IJ Catamaran Lake Charles, LA | Access Private IP - PIP |  | 10 MBPS |  | 100484632 100484634 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Jodi Roy 1-337-217-0033 Jodi.roy@briovarx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 |  |  |  | 06/16/2016 |  |  |  | N | U0101953 |  |  | NSPE0010041439
Provisioning Accepted |  |  |  | 03/17/2016: 3/17- Per provisioning this needs to be reissued as change order, to change only the L3 port at the existing circuit. | 8674346 |  | EVC/PVC Service (N.10988900.5718242) | N.10988900.5718242 | [5 empty] | 5718242 5719595 |  | PVC ID : 5718242,5719595 | [11 empty] | TIM GUNNERSON 6512955481 TIM_GUNNERSON@OPTUM.COM | [8 empty] | 03/09/2016 (10988900) |  | N (N.10988900.5718242) | P2135465 |  |  | NSPE0010111708
|  |  |  | 03/17/2016: 3/17- Per provisioning, this needs to be reissued as change order, to change only the L3 port at the existing circuit. | 8674351 |  | EVC/PVC Service (N.10988979.5718290) | N.10988979.5718290 | [5 empty] | 5720598 5718290 |  | PVC ID : 5720598,5718290 | [11 empty] | TIM GUNNERSON 6512955481 TIM_GUNNERSON@OPTUM.COM | [8 empty] | 03/11/2016 (10988979) |  | N (N.10988979.5718290) | P2135482 |  |  | NSPE0010111795
Cancelled | NY361-02-IJ Catamaran Rx | 3030 47TH AVE LONG ISLAND CITY, NY 11101-3433 US | 100 MBPS (22496306) | 10/06/2016: 10/06 - Order Cancelled. Please see 23199129. | 192920772 | NY361-02-IJ Catamaran Rx | Private IP - PIP (22496305) Access (22496306) | 22496305 22496306 | 100 MBPS (22496305) |  | 94036351 (Private IP (PIP)) 94036348 (Access) | C1035454/ADD (22496305) C1035454/CANCEL (22496305) E4010948/CANCEL (22496306) E4010948/ADD (22496306) |  | 5739911 | 4000 | PVC ID : 5739911 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64700 PE IP Address : 152.177.202.181 CE Address : 152.177.202.182 QoS - Egress Profile: R12 | 100Base-FX - MMF (22496306) | 100Base-FX (1310nm, Multi Mode Fiber) (22496306) | Ethernet | VERIZON (2249630614414101) | 06/07/2016 (2249630614414101) | [6 empty] | Bill Downey 1-718-489-9641 Bdowney@salveospecialty.com | David Casanova | david_casanova@optum.com | 1-763-744-1589 |  |  |  | 09/06/2016 | 10/07/2016 | 10/06/2016 (22496305) 10/07/2016 (22496306) |  | N (22496305) N (22496306) | U0101953 |  |  | NSPE0010125086
Cancelled | C1380-05-IJ Convergys Cincinatti Data Center | 229 W 7TH ST FL 6 CINCINNATI, OH 45202-2308 US | 200 MBPS (22412490) | 11/30/2016: 11/29 As per John Sergot, "I have received confirmation to cancel the below orders. Let me know if you have any questions." | 193029241 | C1380-05-IJ Convergys Cincinatti Data Center | Private IP - PIP (22412489) Access (22412490) | 22412489 22412490 | 200 MBPS (22412489) |  | 110017621 (Private IP (PIP)) 110017619 (Access) | C5001921/CANCEL (22412489) C5001921/ADD (22412489) E5003423/CANCEL (22412490) E5003423/ADD (22412490) |  | 5734258 |  | PVC ID : 5734258 | 1000Base-SX-850nm (22412490) | 1000Base-LX (1310nm Single Mode Fiber) (22412490) | Ethernet | [8 empty] | Pat Henry 1-513-723-7692 patrick.henry@convergys.com | SCOTT MOYER | scott_moyer@optum.com | 1-763-744-2154 | 12/01/2016(Private IP - PIP) 12/01/2016(Access) |  | 10/11/2016 (22412489) 10/07/2016 (22412490) | 07/18/2016 | 12/01/2016 | 11/30/2016 (22412489) 12/01/2016 (22412490) |  | N (22412489) N (22412490) | U0101953 | Jeopardy Notification 2 (11/11/2016) |  | NSPE0010234756
Cancelled | NY004-05-IJ New York NY | 168 CENTRE ST FL 5 NEW YORK, NY 10013-3477 US | 100 MBPS (22417531) | 10/24/2016: 10/24 per POC Beth Yepes- cacnel order- infrastructure build out not in UHG 2016 budget- advised OC to Sup to cancel entire order | 193037916 | NY004-05-IJ New York, NY | Private IP - PIP (22417530) Access (22417531) | 22417530 22417531 | 20 MBPS (22417530) |  | 111595375 (Private IP (PIP)) 111595373 (Access) | C1034768/ADD (22417530) C1034768/CANCEL (22417530) E4010523/ADD (22417531) E4010523/CANCEL (22417531) | 32.KFGS.209603..NY (2241753115393101) | 5734569 | 5000 | PVC ID : 5734569 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65039 PE IP Address : 68.139.141.69 CE Address : 68.139.141.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22417531) | 1000Base-SX (850nm, Multi Mode Fiber) (22417531) | Ethernet | VERIZON (2241753115393101) | 04/19/2016 (2241753115393101) | 09/02/2016 (2241753115393101) | [5 empty] | Robert K Cho 1-212-271-0784 rcho@uhc.com | PRADEEP YADAV | pradeep_yadav@optum.com | 91-981-005-9326 | 10/25/2016(Private IP - PIP) 10/25/2016(Access) |  | 10/20/2016 (22417530) 10/18/2016 (22417531) | 11/07/2016 | 10/25/2016 | 10/24/2016 (22417530) 10/25/2016 (22417531) |  | N (22417530) N (22417531) | U0101953 |  |  | NSPE0010247784
Cancelled | AZ038-02-IJ Phoenix AZ | 720 E THUNDERBIRD RD STE 3 PHOENIX, AZ 85022-5396 US | 100 MBPS (22417624) | 06/02/2016: 6/2- PENDING FOC | 193037967 | AZ038-02-IJ Phoenix, AZ | Private IP - PIP (22417623) Access (22417624) | 22417623 22417624 | 10 MBPS (22417623) |  | 111595379 (Private IP (PIP)) 111595377 (Access) | C1034769/ADD (22417623) C1034769/CANCEL (22417623) E4010527/CANCEL (22417624) E4010527/ADD (22417624) |  | 5734576 |  | PVC ID : 5734576 | 1000Base-SX-850nm (22417624) | 1000Base-SX (850nm, Multi Mode Fiber) (22417624) | Ethernet |  |  |  |  | 07/26/2016 (VFORCE) (22417624) |  |  |  | Jennifer A Williams 1-623-707-0050 jennifer.a.williams@optum.com | PRADEEP YADAV | pradeep_yadav@optum.com | 91-981-005-9326 | 06/02/2016(Private IP - PIP) 06/02/2016(Access) |  |  | 05/31/2016 | 06/03/2016 | 06/02/2016 (22417623) 06/02/2016 (22417624) |  | N (22417623) N (22417624) | U0101953 |  |  | NSPE0010247784
|  | 5908 HAMPTON OAKS PKWY TAMPA, FL 33610 USA | 44.736 MBPS (CQBLBQM4) | 08/12/2016: 8/11- Customer hold, Customer hold, waiting on confirmation from Century Link. NEW CFA IS REQUIRED..THERE ARE NOT ANYMORE AVAILABLE DROP PORTS AT TAMPFLXEH88. Cancellation notification email sent, cancellation date 8/31. | 8717075 |  | BACS (Channelized DS3) (CQBLBQM4) | CQBLBQM4 | 44.736 MBPS (CQBLBQM4) | P2016963 |  | AOBK1H2R0001 (CQBLBQM4) | 69/HFGS/305636//GTES/ (CZA10LA9TPX00001) | [6 empty] | FRONTIER (CZA10LA9TPX00001) | 07/13/2016 (CZA10LA9TPX00001) | 08/17/2016 (CZA10LA9TPX00001) | 08/23/2016 (CZA10LA9TPX00001) |  |  |  |  | JOHN SERGOT 0018136309705 JOHN_SERGOT@OPTUM.COM | [5 empty] | 08/19/2016 (CQBLBQM4) | 08/30/2016 (CQBLBQM4) |  |  |  | Y (CQBLBQM4) | 05657353 |  |  | NSPE0010257153
Cancelled | OR004-02-IJ Catamaran Portland | 200 SW MARKET ST STE 600 PORTLAND, OR 97201-5719 US | 100 MBPS (22626958) | 08/17/2016: 8/17- Per John's request order supp'ed to cancel. The project team was notified that this site will be closing. | 193088357 | OR004-02-IJ Catamaran Portland | Private IP - PIP (22626957) Access (22626958) | 22626957 22626958 | 20 MBPS (22626957) |  | 113535103 (Private IP (PIP)) 113535101 (Access) | C1036635/ADD (22626957) C1036635/CANCEL (22626957) E4011768/ADD (22626958) E4011768/CANCEL (22626958) |  | 5751131 | 10000 | PVC ID : 5751131 VPN Name : UnitedHealthGroup Router Name : HICGE02 VRF Name : V556790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64757 PE IP Address : 147.225.218.189 CE Address : 147.225.218.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22626958) | 1000Base-SX (850nm, Multi Mode Fiber) (22626958) | Ethernet |  |  |  |  | 09/30/2016 (VFORCE) (22626958) |  |  |  | MARK JAJOU 1-503-265-3412 mark.jajou@catamaranrx.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 08/18/2016(Private IP - PIP) 08/18/2016(Access) |  | 08/30/2016 (22626957) 08/26/2016 (22626958) | 08/26/2016 | 08/18/2016 | 08/17/2016 (22626957) 08/18/2016 (22626958) |  | N (22626957) N (22626958) | U0101953 |  |  | NSPE0010294305
Cancelled | UMD14-05-IJ Baltimore MD | 2111 VAN DEMAN ST BALTIMORE, MD 21224-6609 US | 50 MBPS (22626767) | 12/08/2016: 12/08 Status: Customer site not ready. Next Action: Customer to advise if they are completing the site work prior to 12/12 or the order will be cancelled. Who owns the next action: Customer Ticket: NA | 193111521 | UMD14-05-IJ Baltimore, MD | Private IP - PIP (22626766) Access (22626767) | 22626766 22626767 | 20 MBPS (22626766) |  | 115121198 (Private IP (PIP)) 115121196 (Access) | C4004219/CANCEL (22626766) C4004219/ADD (22626766) E4011766/CANCEL (22626767) E4011766/ADD (22626767) |  | 5751112 | 4000 | PVC ID : 5751112 VPN Name : UnitedHealthGroup Router Name : BA59E01 VRF Name : V673546:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64935 PE IP Address : 68.137.146.129 CE Address : 68.137.146.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22626767) | 1000Base-SX (850nm, Multi Mode Fiber) (22626767) | Ethernet | [8 empty] | Joanne Sposato 1-443-957-6632 jsposato@spectera.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 12/09/2016(Private IP - PIP) 12/09/2016(Access) |  | 11/04/2016 (22626766) 11/02/2016 (22626767) | 11/03/2016 | 12/09/2016 | 12/09/2016 (22626766) 12/09/2016 (22626767) |  | N (22626766) N (22626767) | U0101953 | Jeopardy Notification 3 (11/29/2016) |  | NSPE0010301088
Cancelled | TX023-05-IJ Richardson | 1301 W PRESIDENT GEORGE BUSH HWY RICHARDSON, TX 75080-1135 US | 200 MBPS (22599787) | 12/12/2016: 12/12 Background: 11/10 Supp to cancel this entire order (22599787). The order will be reissued with the corrected address 1311 President George Bush. Status: reissued as 23423327 which completed on 12/5 Next action: Prov/Dm to complete the sup to cancel entire order for 22599787 Who owns the next action: DM/PRov Ticket: Next update due by : 12/15/2016 | 193125137 | TX023-05-IJ Richardson | Access (22599787) Private IP - PIP (22599786) | 22599787 22599786 | 150 MBPS (22599786) |  | 115870305 (Access) 115870307 (Private IP (PIP)) | E5003715/CANCEL (22599787) E5003715/ADD (22599787) C5002075/ADD (22599786) C5002075/CANCEL (22599786) | 21.L1XX.007148..TWCC (2259978716049501) | 5748578 | 35000 | PVC ID : 5748578 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64517 PE IP Address : 68.139.86.209 CE Address : 68.139.86.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22599787) | 1000Base-SX (850nm, Multi Mode Fiber) (22599787) | Ethernet | TIME WARNER CABLE (2259978716049501) | 08/10/2016 (2259978716049501) | 08/18/2016 (2259978716049501) | 08/16/2016 (2259978716049501) | 11/18/2016 (VFORCE) (22599787) |  | DEMARCDET - 1st floor, Telco Room, MPOE below MTU labeled Verizon Business |  | Martha White 1-214-273-4502 martha1_white@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 12/13/2016(Access) 12/13/2016(Private IP - PIP) |  | 08/25/2016 (22599787) 08/29/2016 (22599786) | 09/21/2016 | 12/13/2016 | 12/13/2016 (22599787) 11/09/2016 (22599786) |  | N (22599787) N (22599786) | U0101953 | Jeopardy Notification 1 (10/26/2016) |  | NSPE0010322068
Cancelled | NJ050-05-IJ | 170 WOOD AVE S ISELIN, NJ 08830-2741 US | 100 MBPS (22599955) | 07/31/2016: 7/31- Pending fiber pull. | 193125180 | NJ050-05-IJ | Private IP - PIP (22599954) Access (22599955) | 22599954 22599955 | 50 MBPS (22599954) |  | 115331580 (Private IP (PIP)) 115331578 (Access) | C1036359/ADD (22599954) C1036359/CANCEL (22599954) E4011553/ADD (22599955) E4011553/CANCEL (22599955) |  | 5748593 | 10000 | PVC ID : 5748593 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V632344:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64585 PE IP Address : 206.115.104.161 CE Address : 206.115.104.162 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22599955) | Ethernet | [5 empty] | 07/13/2016 (CCP) (22599954) 07/13/2016 (CCP) (22599955) |  |  | Matthew Vitale 1-732-623-1099 mvitale@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 |  |  | 08/03/2016 (22599954) 08/01/2016 (22599955) | 09/02/2016 | 08/02/2016 | 08/01/2016 (22599954) 08/02/2016 (22599955) |  | N (22599954) N (22599955) | U0101953 |  |  | NSPE0010322105
Cancelled | M0206-05-IJ East Syracuse | 5015 CAMPUSWOOD DR EAST SYRACUSE, NY 13057-4232 US | 50 MBPS (22600066) | 11/03/2016: 11/2 Sent notice to PM/POC- order on hold for 4+months for site requiremtns need firm ETA for completion. Order is pending review for fianl cancellation. | 193125132 | M0206-05-IJ East Syracuse | Private IP - PIP (22600065) Access (22600066) | 22600065 22600066 | 20 MBPS (22600065) |  | 115909231 (Private IP (PIP)) 115909229 (Access) | C4004135/ADD (22600065) C4004135/CANCEL (22600065) E4011555/ADD (22600066) E4011555/CANCEL (22600066) |  | 5748598 |  | PVC ID : 5748598 | 1000Base-SX-850nm (22600066) | 1000Base-SX (850nm, Multi Mode Fiber) (22600066) | Ethernet | VERIZON (2260006616054701) | 07/14/2016 (2260006616054701) | [6 empty] | Laurie Marinelli 1-315-433-5788 laurie_marinelli@uhc.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 |  |  |  | 08/08/2016 | 11/04/2016 | 11/04/2016 (22600065) 11/04/2016 (22600066) |  | N (22600065) N (22600066) | U0101953 |  |  | NSPE0010326975
Cancelled | AZ032-02-IJ GOODYEAR AZ | 1981 N PEBBLE CREEK PKWY GOODYEAR, AZ 85395-2543 US | 50 MBPS |  | 193141752 | AZ032-02-IJ GOODYEAR, AZ | Access Private IP - PIP |  | 10 MBPS |  | 117847924 117847926 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Jeff Jensen 1-763-744-1651 jeff_jensen@optum.com | JAVIER SEGUI | javier.segui@optum.com | 1-407-541-8143 |  |  |  | 07/22/2016 |  |  |  | N | U0101953 |  |  | NSPE0010344299
|  | 1416 W I65 SERVICE RD S MOBILE, AL 36693 USA | 1.536 MBPS (IQBLB8CN) | 12/01/2016: 11/30 Customer requested sup to cancel entre order. | 8763865 |  | Private IP (IQBLB8CN) EVC/PVC Service (N.11111574.5761532) | IQBLB8CN N.11111574.5761532 | 7.68 MBPS | P2144341 |  | BCBK9Y650001 (IQBLB8CN) BCBK9Y650002 (IQBLB8CN) BCBK9Y650003 (IQBLB8CN) BCBK9Y650004 (IQBLB8CN) BCBK9Y650005 (IQBLB8CN) |  | 5761532 | 1536 | VPN Name : UnitedHealthGroup Router Name : B6S3E01 VRF Name : V546882-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64643 PE IP Address : 199.220.74.245 CE Address : 199.220.74.246 QoS - Egress Profile: R12 PVC ID : 5761532 | [11 empty] | AMANDA BARDWELL 0012514761866 ABARDWELL@NPHC.NET | [5 empty] | 11/01/2016 (IQBLB8CN) | 11/01/2016 (IQBLB8CN) |  | 11/01/2016 (11111574) |  | N (IQBLB8CN) N (N.11111574.5761532) | 05017789 P2144341 |  |  | NSPE0010369802
Cancelled | OH033-02-IJ Dublin OH | 6805 PERIMETER DR DUBLIN, OH 43016-8690 US | 100 MBPS (22697426) | 07/25/2016: 7/24- Per John's request order cancelled. Pending cancellation completion. | 193200202 | OH033-02-IJ Dublin OH | Private IP - PIP (22697425) Access (22697426) | 22697425 22697426 | 50 MBPS (22697425) |  | 121230812 (Private IP (PIP)) 121230810 (Access) | C1037403/CANCEL (22697425) C1037403/ADD (22697425) E4012251/CANCEL (22697426) E4012251/ADD (22697426) |  | 5757589 | 10000 | PVC ID : 5757589 VPN Name : UnitedHealthGroup-TCW Router Name : CMKXE01 VRF Name : V648886-UnitedHealthGroupTCW Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65439 PE IP Address : 68.138.174.1 CE Address : 68.138.174.2 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22697426) | 1000Base-SX (850nm, Multi Mode Fiber) (22697426) | Ethernet | [8 empty] | Kelle O'Donnell 1-320-629-2203 kelle_l_odonnell@uhg.com | TAUOA FALO | tauoa.falo@optum.com | 1-170-224-2765 | 07/25/2016(Private IP - PIP) 07/25/2016(Access) |  | 08/31/2016 (22697425) 08/29/2016 (22697426) | 08/01/2016 | 07/25/2016 | 07/24/2016 (22697425) 07/25/2016 (22697426) |  | N (22697425) N (22697426) | U0101953 |  |  | NSPE0010393616
Cancelled | NY187-02-IJ Farmingdale NY | 931 CONKLIN ST STE C&D FARMINGDALE, NY 11735-2429 US | 100 MBPS (22728830) | 08/04/2016: 8/4- Pending resolution form Production Team. Internal cc ticket created #A201608030087. | 193200169 | NY187-02-IJ Farmingdale, NY | Private IP - PIP (22728829) Access (22728830) | 22728829 22728830 | 50 MBPS (22728829) |  | 121230820 (Private IP (PIP)) 121230818 (Access) | C1037604/ADD (22728829) C1037604/CANCEL (22728829) E4012380/CANCEL (22728830) E4012380/ADD (22728830) |  | 5760873 | 3000 | PVC ID : 5760873 VPN Name : UnitedHealthGroup Router Name : CLK9E01 VRF Name : V486752:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64664 PE IP Address : 152.161.138.173 CE Address : 152.161.138.174 QoS - Egress Profile: G1 | 1000Base-SX-850nm (22728830) | 1000Base-SX (850nm, Multi Mode Fiber) (22728830) | Ethernet | [8 empty] | Sunil Orie 1-800-346-6348 sorie@aciiv.com | JOHN SERGOT | john.sergot@optum.com | 1-763-744-1582 |  |  | 08/04/2016 (22728829) 08/02/2016 (22728830) | 08/05/2016 | 08/10/2016 | 08/10/2016 (22728829) 08/10/2016 (22728830) |  | N (22728829) N (22728830) | U0101953 |  |  | NSPE0010393616
Cancelled | NM007-02-IJ Albuquerque | 2420 COMANCHE RD NE STE A5 ALBUQUERQUE, NM 87107-4754 US | 50 MBPS (22692197) | 09/28/2016: 9/28- Address is removed, order needs to be re-quoted to different LEC | 193200088 | NM007-02-IJ Albuquerque | Private IP - PIP (22692196) Access (22692197) | 22692196 22692197 | 20 MBPS (22692196) |  | 120529746 (Private IP (PIP)) 120529744 (Access) | C4004356/CANCEL (22692196) C4004356/ADD (22692196) E4012229/ADD (22692197) E4012229/CANCEL (22692197) |  | 5756875 |  | PVC ID : 5756875 | 1000Base-LX-1310nm (22692197) | 1000Base-SX (850nm, Multi Mode Fiber) (22692197) | Ethernet | [8 empty] | Linda Manning 1-505-830-1800 lmanning@sironainfusion.com | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 |  |  |  | 07/29/2016 | 10/07/2016 | 09/29/2016 (22692196) 10/07/2016 (22692197) |  | N (22692196) N (22692197) | U0101953 |  |  | NSPE0010388051
Cancelled | FL195-02-IJ Jacksonville | 10401 DEERWOOD PARK BLVD JACKSONVILLE, FL 32256-5007 US | 100 MBPS (22696746) | 08/23/2016: 8/24- Pending cancellation completion. Disconnect FOC date 8/25. | 193200114 | FL195-02-IJ Jacksonville, | Private IP - PIP (22696745) Access (22696746) | 22696745 22696746 | 50 MBPS (22696745) |  | 120529738 (Private IP (PIP)) 120529736 (Access) | C1037382/CANCEL (22696745) C1037382/ADD (22696745) E4012246/CANCEL (22696746) E4012246/ADD (22696746) | 4D/KFFN/002385/LVLC (2269674616751201) | 5757509 | 10000 | PVC ID : 5757509 VPN Name : UnitedHealthGroup-TCW Router Name : JAP3E02 VRF Name : V663962-UnitedHealthGroupTCW Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65440 PE IP Address : 152.183.91.249 CE Address : 152.183.91.250 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (22696746) | 1000Base-SX (850nm, Multi Mode Fiber) (22696746) | Ethernet | LEVEL 3 (2269674616751201) | 06/21/2016 (2269674616751201) | 07/08/2016 (2269674616751201) | 07/18/2016 (2269674616751201) | 07/28/2016 (VFORCE) (22696746) |  | DEMARCDET - BLDG MAIN FLR 1 RM TELCO |  | Kelle O'Donnell 1-320-629-2203 kelle_l_odonnell@uhg.com | TAUOA FALO | tauoa.falo@optum.com | 1-702-242-7654 | 08/26/2016(Private IP - PIP) 08/26/2016(Access) |  | 07/20/2016 (22696745) 07/18/2016 (22696746) | 08/01/2016 | 08/26/2016 | 07/24/2016 (22696745) 08/26/2016 (22696746) |  | N (22696745) N (22696746) | U0101953 |  |  | NSPE0010388051
Cancelled | PA097-02-IJ Havertown PA | 4 RAYMOND DR STE H HAVERTOWN, PA 19083-3188 US | 50 MBPS | 09/22/2016: 9/22- Working on resolving internal issue preventing order submission. | 193200354 | PA097-02-IJ Havertown, PA | Private IP - PIP Access |  | 10 MBPS |  | 121534887 121534885 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Jenny Cleary 1-484-450-0140 jcleary@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 |  |  |  | 10/31/2016 |  |  |  | N | U0101953 |  |  | NSPE0010406080
Cancelled | C1585-02-IJ Johnson Roundtree Premium San Diego | 6160 LUSK BLVD STE 203 SAN DIEGO, CA 92121-2740 US | 50 MBPS (22738815) | 08/31/2016: 8/31- FOC date 11/4. Outstanding issue where COX will terminate circuit has yet to be resolved. (customer placed a new order with different carrier waiting for confirmation to cancel) | 193222554 | C1585-02-IJ Johnson Roundtree Premium San Diego | Private IP - PIP (22738814) Access (22738815) | 22738814 22738815 | 30 MBPS (22738814) |  | 122651490 (Private IP (PIP)) 122651488 (Access) | C4004452/CANCEL (22738814) C4004452/ADD (22738814) E4012420/ADD (22738815) E4012420/CANCEL (22738815) |  | 5761749 |  | PVC ID : 5761749 | 1000Base-SX-850nm (22738815) | 1000Base-SX (850nm, Multi Mode Fiber) (22738815) | Ethernet | [8 empty] | HAU NGUYEN 1-619-719-0014 hnguyen@jrpremium.com | William Goss | william_Goss@optum.com | 1-763-744-1528 | 09/13/2016(Private IP - PIP) 09/13/2016(Access) |  | 11/15/2016 (22738814) 11/11/2016 (22738815) | 08/09/2016 | 09/13/2016 | 09/12/2016 (22738814) 09/13/2016 (22738815) |  | N (22738814) N (22738815) | U0101953 |  |  | NSPE0010420919
Cancelled | C1328-05-IJ Teletech Englewood CO | 9197 S PEORIA ST ENGLEWOOD, CO 80112-5833 US | 1 GBPS (22751847) | 09/22/2016: 9/22- Customer hold, we need space from Teletech for this new install. Sales needs to work with customer to obtain space. Cancellation email sent, cancellation date 9/28. | 193222580 | C1328-05-IJ Teletech Englewood, CO | Private IP - PIP (22751846) Access (22751847) | 22751846 22751847 | 800 MBPS (22751846) |  | 122651494 (Private IP (PIP)) 122651492 (Access) | C0085439/ADD (22751846) C0085439/CANCEL (22751846) E5003952/ADD (22751847) E5003952/CANCEL (22751847) |  | 5762984 | 1700 | PVC ID : 5762984 VPN Name : UHG-ECC Router Name : DNVR9E01 VRF Name : V482035:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65430 PE IP Address : 159.24.196.41 CE Address : 159.24.196.42 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22751847) | Ethernet |  |  |  |  | 08/30/2016 (CCP) (22751846) 08/30/2016 (CCP) (22751847) |  |  |  | KEVIN WALL 1-303-397-8408 kevinwall@teletech.com | William Goss | william_Goss@optum.com | 1-763-744-1528 | 09/23/2016(Private IP - PIP) 09/23/2016(Access) |  |  | 08/17/2016 | 09/23/2016 | 09/23/2016 (22751846) 09/23/2016 (22751847) |  | N (22751846) N (22751847) | U0101953 |  |  | NSPE0010420919
Cancelled | C1380-05-IJ Convergys Cincinatti Data Center | 229 W 7TH ST FL 6 CINCINNATI, OH 45202-2308 US | 500 MBPS (22738985) | 11/30/2016: 11/29 As per John Sergot, "I have received confirmation to cancel the below orders. Let me know if you have any questions." | 193222078 | C1380-05-IJ Convergys Cincinatti Data Center | Access (22738985) Private IP - PIP (22738984) | 22738985 22738984 | 400 MBPS (22738984) |  | 122762090 (Access) 122762092 (Private IP (PIP)) | E5003936/CANCEL (22738985) E5003936/ADD (22738985) C5002177/CANCEL (22738984) C5002177/ADD (22738984) |  | 5761758 | 70000 | PVC ID : 5761758 VPN Name : UHG-ECC Router Name : RVDL9E02 VRF Name : V727152:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65497 PE IP Address : 152.187.231.181 CE Address : 152.187.231.182 QoS - Egress Profile: R12 | 1000Base-SX-850nm (22738985) | 1000Base-SX (850nm, Multi Mode Fiber) (22738985) | Ethernet | [8 empty] | PAT HENRY 1-513-723-7692 patrick.henry@convergys.com | Will Goss | william_Goss@optum.com | 1-763-744-1528 | 12/05/2016(Access) 12/05/2016(Private IP - PIP) |  | 11/21/2016 (22738985) 11/23/2016 (22738984) | 10/13/2016 | 12/05/2016 | 12/05/2016 (22738985) 11/30/2016 (22738984) |  | N (22738985) N (22738984) | U0101953 | Jeopardy Notification 3 (11/21/2016) |  | NSPE0010421749
Cancelled | AZ001-02-IJ PHOENIX AZ | 8027 N BLACK CANYON HWY PHOENIX, AZ 85021-4802 US | 50 MBPS (22753748) | 07/07/2016: 7/7- Order supp'ed to cancel and will be reissued with new address. | 193234200 | AZ001-02-IJ PHOENIX, AZ | Private IP - PIP (22753747) Access (22753748) | 22753747 22753748 | 20 MBPS (22753747) |  | 123815978 (Private IP (PIP)) 123815976 (Access) | C4004469/CANCEL (22753747) C4004469/ADD (22753747) E4012507/CANCEL (22753748) E4012507/ADD (22753748) |  | 5763131 |  | PVC ID : 5763131 | 1000Base-SX-850nm (22753748) | 1000Base-SX (850nm, Multi Mode Fiber) (22753748) | Ethernet | [8 empty] | JENNIFER A WILLIAMS 1-623-707-0050 jennifer.a.williams@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 07/08/2016(Private IP - PIP) 07/08/2016(Access) |  |  | 08/11/2016 | 07/08/2016 | 07/07/2016 (22753747) 07/08/2016 (22753748) |  | N (22753747) N (22753748) | U0101953 |  |  | NSPE0010434992
Cancelled | C1577-03-IJ EXL Services Inc. (AT&T Hosting) NY | 811 10TH AVE NEW YORK, NY 10019-5042 US | 100 MBPS (22754227) | 09/07/2016: 9/9- Customer hold, per this customer address is collocated restricted to AT&T only. If customer wants circuit delivery to floor 16 will need a cancel and reissue as OFFNET (Type 2,3,4)delivery via LEC. LEC loop needed for service to 16th floor AT&T data center - VzB local network cannot deliver. Only VzB presence in building is restricted colo with AT&T on 2nd floor with demarc on 7th floor. Any floor but 16 can be delivered via the 2nd floor. Cancellation email sent, cancellation date 9/23. | 193234522 | C1577-03-IJ EXL Services Inc. (AT&T Hosting) NY | Private IP - PIP (22754226) Access (22754227) | 22754226 22754227 | 50 MBPS (22754226) |  | 124056799 (Private IP (PIP)) 124056797 (Access) | C1037776/CANCEL (22754226) C1037776/ADD (22754226) E4012511/CANCEL (22754227) E4012511/ADD (22754227) |  | 5763175 | 20000 | PVC ID : 5763175 VPN Name : UHG-ECC Router Name : WOR9E02 VRF Name : V661366:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65511 PE IP Address : 68.139.239.217 CE Address : 68.139.239.218 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22754227) | Ethernet | [5 empty] | 08/12/2016 (CCP) (22754226) 08/12/2016 (CCP) (22754227) |  |  | DON EMPSON 1-510-557-8575 don.empson@exlservice.com | Ketul Patel | ketul.patel@exlservice.com | 1-646-712-1497 | 09/13/2016(Private IP - PIP) 09/13/2016(Access) |  | 08/23/2016 (22754226) 08/19/2016 (22754227) | 09/20/2016 | 09/13/2016 | 09/12/2016 (22754226) 09/13/2016 (22754227) |  | N (22754226) N (22754227) | U0101953 |  |  | NSPE0010440151
Cancelled | AZ001-02-IJ Phoenix AZ | 8041 N 24TH AVE PHOENIX, AZ 85021-4842 US | 50 MBPS (22804241) |  | 193261416 | AZ001-02-IJ Phoenix, AZ | Private IP - PIP (22804240) Access (22804241) | 22804240 22804241 | 20 MBPS (22804240) |  | 124982601 (Private IP (PIP)) 124982598 (Access) | E4012822/CANCEL (22804241) |  | 5768189 |  | PVC ID : 5768189 |  | 1000Base-SX (850nm, Multi Mode Fiber) (22804241) | Ethernet | [8 empty] | JENNIFER A WILLIAMS 1-623-707-0050 jennifer.a.williams@optum.com | HARISH KANDPAL | harish_kandpal@optum.com | 91-916-008-4400 | 07/13/2016(Private IP - PIP) 07/13/2016(Access) |  |  | 08/23/2016 | 07/14/2016 | 07/13/2016 (22804240) 07/13/2016 (22804241) |  | N (22804240) N (22804241) | U0101953 |  |  | NSPE0010461599
Cancelled | C1551-07-IJ Florence SC | 160 DOZIER BLVD BLDG 300 FLORENCE, SC 29501-4084 US | 200 MBPS (22804238) | 08/04/2016: 8/4- Customer hold, received confirmation from Level 3 that customer will need to provide LOA because customer located at BCBS. Cancellation notification email sent, cancellation date 9/7. | 193261414 | C1551-07-IJ Florence SC | Private IP - PIP (22804237) Access (22804238) | 22804237 22804238 | 100 MBPS (22804237) |  | 124982617 (Private IP (PIP)) 124982615 (Access) | C5002233/ADD (22804237) C5002233/CANCEL (22804237) E5004056/ADD (22804238) E5004056/CANCEL (22804238) |  | 5768186 |  | PVC ID : 5768186 | 1000Base-LX-1310nm (22804238) | 1000Base-SX (850nm, Multi Mode Fiber) (22804238) | Ethernet | [8 empty] | TONY MILES 1-843-736-1889 tony.miles@pbga.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 | 08/09/2016(Private IP - PIP) 08/09/2016(Access) |  |  | 08/23/2016 | 08/09/2016 | 08/05/2016 (22804237) 08/09/2016 (22804238) |  | N (22804237) N (22804238) | U0101953 |  |  | NSPE0010461599
Cancelled | C1598-02-IJ NRECA Lincoln NE | 8701 FIRETHORN LN LINCOLN, NE 68520-1402 US | 20 MBPS (22843648) | 09/22/2016: 9/22- As per Jessie, IT team is still working on the records change that needs to be done backend. Pending ETA for the issue to be resolved. | 193276163 | C1598-02-IJ NRECA Lincoln NE | Access (22843648) Private IP - PIP | 22843648 | 10 MBPS |  | 94036322 (Access) 94036325 | [5 empty] | 100Base-TX (22843648) | 100Base-TX (22843648) | Ethernet | [8 empty] | ERIC TAYLOR 1-763-744-2082 eric_taylor@optum.com | ERIC TAYLOR | eric_taylor@optum.com | 1-763-744-2082 |  |  |  | 08/31/2016 | 09/28/2016 | 09/28/2016 (22843648) |  | N (22843648) N | U0101953 |  |  | NSPE0010479868
Cancelled | FL145-02-IJ Thonotosassa FL- Wellmed | 10616 MAIN ST THONOTOSASSA, FL 33592-2828 US | 100 MBPS (22915119) | 08/11/2016: 8/11- Production support requested order to be cancelled and reissued so that the LEC reflects Brighthouse and not Frontier. | 193325039 | FL145-02-IJ Thonotosassa, FL- Wellmed | Access (22915119) Private IP - PIP | 22915119 | 10 MBPS |  | 109025930 (Access) 109025932 | E4010463/NONE (22915119) E4013621/CANCEL (22915119) E4010463/REMOVE (22915119) E4013621/ADD (22915119) |  |  |  |  | 100Base-FX - MMF (22915119) | 100Base-TX (22915119) | Ethernet | [8 empty] | MIKE NELSON 1-207-877-7874 minelson@wellmed.net | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 |  |  |  | 09/14/2016 | 08/17/2016 | 08/17/2016 (22915119) |  | N (22915119) N | U0101953 |  |  | NSPE0010520280
Cancelled | C1273-05-IJ Rochester NY ECC | 150 MILE CROSSING BLVD STE 2 ROCHESTER, NY 14624-6209 US | 50 MBPS | 08/09/2016: 8/9- Cancelled per customer's request. | 193338054 | C1273-05-IJ Rochester NY ECC | Private IP - PIP Access |  | 30 MBPS |  | 128953331 128953329 | [5 empty] | 1000Base-T | 1000Base-T | Ethernet | [8 empty] | ANTOINETTE GREEN 1-585-265-8636 antoinette.green@xerox.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 |  |  |  | 09/16/2016 |  |  |  | N | U0101953 |  |  | NSPE0010529786
Cancelled | FL194-02-IJ Tampa FL | 2701 W SAINT ISABEL ST TAMPA, FL 33607-6324 US | 50 MBPS (22953982) | 11/22/2016: Order cancelled as per john_sergot@optum.com request. | 193341229 | FL194-02-IJ Tampa, FL | Private IP - PIP (22953981) Access (22953982) | 22953981 22953982 | 10 MBPS (22953981) |  | 129997659 (Private IP (PIP)) 129997657 (Access) | C4004857/CANCEL (22953981) C4004857/ADD (22953981) E4013763/CANCEL (22953982) E4013763/ADD (22953982) |  | 5783996 | 1500 | PVC ID : 5783996 VPN Name : UnitedHealthGroup Router Name : TAMP3E02 VRF Name : V444060-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64555 PE IP Address : 206.115.21.117 CE Address : 206.115.21.118 QoS - Egress Profile: R12 | 100Base-TX (22953982) | 100Base-TX (22953982) | Ethernet | [8 empty] | Mark Feinberg 1-210-617-4771 MFeinberg@wellmed.net | Ryan Klatt | rylan_klatt@optum.com | 1-763-553-4619 | 11/28/2016(Private IP - PIP) 11/28/2016(Access) |  |  | 11/23/2016 | 11/28/2016 | 11/22/2016 (22953981) 11/28/2016 (22953982) |  | N (22953981) N (22953982) | U0101953 | Jeopardy Notification 1 (09/30/2016) |  | NSPE0010533036
Cancelled | FL145-02-IJ Thonotosassa FL- Wellmed | 10616 MAIN ST THONOTOSASSA, FL 33592-2828 US | 100 MBPS (23009471) | 10/26/2016: 10/26 - reissued correct order: WO 23313550/ SO 193540199 | 193364574 | FL145-02-IJ Thonotosassa, FL- Wellmed | Private IP - PIP (23009470) Access (23009471) | 23009470 23009471 | 100 MBPS (23009470) |  | 132040671 (Private IP (PIP)) 132040669 (Access) | C1043569/ADD (23009470) C1043569/CANCEL (23009470) E4014264/ADD (23009471) E4014264/CANCEL (23009471) |  | 5788363 | 3000 | PVC ID : 5788363 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64672 PE IP Address : 152.161.176.133 CE Address : 152.161.176.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23009471) | 1000Base-SX (850nm, Multi Mode Fiber) (23009471) | Ethernet |  |  |  |  | 11/11/2016 (VFORCE) (23009471) |  |  |  | MIKE NELSON 1-207-877-7874 minelson@wellmed.net | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 |  |  |  | 02/10/2017 | 11/07/2016 | 10/26/2016 (23009470) 11/07/2016 (23009471) |  | N (23009470) N (23009471) | U0101953 |  |  | NSPE0010555783
Cancelled | AZ012-05-IJ Phoenix 100mg | 2222 W DUNLAP AVE PHOENIX, AZ 85021-2818 US | 200 MBPS (23095997) | 09/07/2016: 9/7- AS per LEC: They will not cater MMF Handoff. | 193402397 | AZ012-05-IJ Phoenix 100mg | Private IP - PIP (23095996) Access (23095997) | 23095996 23095997 | 100 MBPS (23095996) |  | 134259747 (Private IP (PIP)) 134259745 (Access) | C5002414/CANCEL (23095996) C5002414/ADD (23095996) E5004500/ADD (23095997) E5004500/CANCEL (23095997) |  | 5796703 |  | PVC ID : 5796703 | 1000Base-LX (23095997) | 1000Base-SX (850nm, Multi Mode Fiber) (23095997) | Ethernet | [8 empty] | Danny Stewart 1-602-293-2973 danny_h_stewart@optum.com | MASROOR KHAN | masroor_khan@optum.com | 1-763-694-7370 | 09/12/2016(Private IP - PIP) 09/12/2016(Access) |  |  | 10/21/2016 | 09/12/2016 | 09/12/2016 (23095996) 09/12/2016 (23095997) |  | N (23095996) N (23095997) | U0101953 |  |  | NSPE0010588320
Cancelled | C1328-05-IJ Teletech Englewood CO | 9197 S PEORIA ST ENGLEWOOD, CO 80112-5833 US | 1 GBPS (23119492) | 11/17/2016: 11/17 cancel and reissue order- LEC confirmed FOC 11/17- will retag ckt at site and update records in CO. Escalating to get order to Beas dispatch asap | 193425743 | C1328-05-IJ Teletech Englewood, CO | Private IP - PIP (23119491) WAN Analysis Reporting (23119493) Access (23119492) | 23119491 23119493 23119492 | 1 GBPS (23119491) |  | 134450148 (Private IP (PIP)) 134450149 (WAN Analysis Reporting) 134450146 (Access) | C0097592/ADD (23119491) C0097592/CANCEL (23119491) E5004551/ADD (23119492) E5004551/CANCEL (23119492) | 1V/KFFN/003330/LVLC (2311949217098201) | 5799535 | 1700 | PVC ID : 5799535 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65430 PE IP Address : 199.220.35.109 CE Address : 199.220.35.110 QoS - Egress Profile: R12 | 1000Base-T (23119492) | 1000Base-SX (850nm, Multi Mode Fiber) (23119492) | Ethernet | LEVEL 3 (2311949217098201) | 10/20/2016 (2311949217098201) | 11/03/2016 (2311949217098201) | 11/02/2016 (2311949217098201) | 12/23/2016 (VFORCE) (23119492) |  | DEMARCDET - 1st floor IDF MMR Row 2 Rack 2, RU12, ADVA ED018 Lan 5 1000BaseSX LC No Auto Tagged |  | DANNY STEWART 1-602-293-2973 danny_h_stewart@optum.com | MASROOR KHAN | masroor_khan@optum.com | 1-763-694-7370 | 11/29/2016(Access) |  | 11/16/2016 (23119491) 11/14/2016 (23119492) | 11/16/2016 11/22/2016 | 11/29/2016 | 11/08/2016 (23119491) 11/08/2016 (23119493) 11/29/2016 (23119492) | Order Canceled | N (23119491) N (23119493) Y (23119492) | U0101953 |  |  | NSPE0010603049
Cancelled | C1425-07-IJ Teletech/Global Grossing Phoenix | 801 S 16TH ST PHOENIX, AZ 85034-4133 US | 1 GBPS (23230014) |  | 193494652 | C1425-07-IJ Teletech/Global Grossing Phoenix | Private IP - PIP (23230013) Access (23230014) | 23230013 23230014 | 800 MBPS |  | 121437622 (Private IP (PIP)) 121437620 (Access) | C0085010/CANCEL (23230013) C0085010/REMOVE (23230013) |  | 5758115 | 350000 | PVC ID : 5758115 VPN Name : UHG-ECC Router Name : WIT9E01 VRF Name : V773343:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65430 PE IP Address : 152.177.159.9 CE Address : 152.177.159.10 QoS - Egress Profile: C13 | 1000Base-LX-1310nm (23230014) | 1000Base-LX (1310nm Single Mode Fiber) (23230014) | Ethernet | [8 empty] | TRAVIS DENT 1-763-744-2265 travis_dent@optum.com | TRAVIS DENT | travis_dent@optum.com | 1-763-744-2265 |  |  | 11/16/2016 (23230013) | 11/04/2016 11/16/2016 | 10/05/2016 | 10/05/2016 (23230013) 10/05/2016 (23230014) |  | N (23230013) N (23230014) | U0101953 |  | Record Change from MMF to SMF | NSPE0010672433
Cancelled | RI001-02-IJ Johnston RI | 1301 ATWOOD AVE JOHNSTON, RI 02919-4900 US | 50 MBPS (23567710) | 01/19/2017: CANCELLED | 193492032 | RI001-02-IJ Johnston, RI | Private IP - PIP (23567709) Access (23567710) | 23567709 23567710 | 20 MBPS (23567709) |  | 139418202 (Private IP (PIP)) 139418200 (Access) | C4005975/ADD (23567709) C4005975/CANCEL (23567709) E4016443/CANCEL (23567710) E4016443/ADD (23567710) |  | 5825156 | 5000 | PVC ID : 5825156 VPN Name : UnitedHealthGroup Router Name : CHT3E04 VRF Name : V425889-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64545 PE IP Address : 152.177.51.61 CE Address : 152.177.51.62 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23567710) | 1000Base-SX (850nm, Multi Mode Fiber) (23567710) | Ethernet | [8 empty] | David Lawley 1-603-629-7751 david_lawley@uhg.com | KYLE HARSMA | kyle_harsma@optum.com | 1-763-553-4195 | 01/23/2017(Private IP - PIP) 01/23/2017(Access) |  | 02/16/2017 (23567709) 02/14/2017 (23567710) | 02/15/2017 | 01/23/2017 | 01/17/2017 (23567709) 01/23/2017 (23567710) |  | N (23567709) N (23567710) | U0101953 |  |  | NSPE0010659360
Cancelled | PA097-02-IJ Havertown PA | 4 RAYMOND DR STE H HAVERTOWN, PA 19083-3188 US | 50 MBPS |  | 193490829 | PA097-02-IJ Havertown, PA | Private IP - PIP Access |  | 10 MBPS |  | 121534887 121534885 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Jenny Cleary 1-484-450-0140 jcleary@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 |  |  |  | 10/31/2016 |  |  |  | N | U0101953 |  | cancelled | NSPE0010633245
Cancelled | MD101-02-IJ Columbia MD | 5585 STERRETT PL COLUMBIA, MD 21044-2608 US | 200 MBPS | 11/04/2016: ORDER CANCELLED. Looks like the address has changed. I will be submitting a new order. This order can be cancelled. - John Sergot | 193522645 | MD101-02-IJ Columbia, MD | Private IP - PIP Access |  | 100 MBPS |  | 141167203 141166621 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Danielle Maiorana 1-952-202-0064 danielle_maiorana@uhg.com | MASROOR KHAN | masroor_khan@optum.com | 1-763-694-7370 |  |  |  | 11/10/2016 |  |  |  | N | U0101953 |  | MD101-02-IJ Columbia MD | NSPE0010701996
Cancelled | PA097-02-IJ Havertown PA | 4 RAYMOND DR STE H HAVERTOWN, PA 19083-3188 US | 50 MBPS | 12/01/2016: Supplement has been created. See Service Order # 193627569. | 193527450 | PA097-02-IJ Havertown, PA | Private IP - PIP Access |  | 10 MBPS |  | 141324893 141324891 | [5 empty] | 100Base-FX - MMF | 100Base-FX (1310nm, Multi Mode Fiber) | Ethernet | [8 empty] | Jenny Cleary 1-484-450-0140 jcleary@axelacare.com | ANUPAM DATT | anupam_datt@optum.com | 1-987-313-9388 |  |  |  | 12/22/2016 |  |  |  | N | U0101953 |  | Havertown - for ess | NSPE0010705596
Cancelled | FL145-02-IJ Thonotosassa FL- Wellmed | 10616 MAIN ST THONOTOSASSA, FL 33592-2828 US | 100 MBPS (23313550) | 11/30/2016: 11/28 Customer has decided to leave handoff as is. cancelling this order. | 193540199 | FL145-02-IJ Thonotosassa, FL- Wellmed | Access (23313550) Private IP - PIP | 23313550 | 10 MBPS |  | 109025930 (Access) 109025932 | E4010463/NONE (23313550) |  |  |  |  | 100Base-FX - MMF (23313550) | 100Base-TX (23313550) | Ethernet |  |  |  |  | 11/04/2016 (VFORCE) (23313550) |  |  |  | MIKE NELSON 1-207-877-7874 minelson@wellmed.net | GLENN MOORE | glenn_moore@optum.com | 1-763-744-0981 | 12/07/2016(Access) |  | 10/25/2016 (23313550) | 12/05/2016 | 12/07/2016 | 12/07/2016 (23313550) |  | N (23313550) N | U0101953 |  |  | NSPE0010717286
|  | 4 RAYMOND DR HAVERTOWN, PA 19083 USA | 1.536 MBPS (IQBLFHWC) | 12/08/2016: Order cancelled. | 8976687 |  | Private IP (IQBLFHWC) EVC/PVC Service (N.11248302.5820416) | IQBLFHWC N.11248302.5820416 | 10.752 MBPS | P2155559 |  | BCBLBFFK0001 (IQBLFHWC) BCBLBFFK0002 (IQBLFHWC) BCBLBFFK0003 (IQBLFHWC) BCBLBFFK0004 (IQBLFHWC) BCBLBFFK0005 (IQBLFHWC) BCBLBFFK0006 (IQBLFHWC) BCBLBFFK0007 (IQBLFHWC) |  | 5820416 | 1512 | VPN Name : UnitedHealthGroup Router Name : PTNGE06 VRF Name : V796021:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64595 PE IP Address : 152.177.38.49 CE Address : 152.177.38.50 QoS - Egress Profile: R12 PVC ID : 5820416 | [11 empty] | JENNY CLEARY 0014844500140 JCLEARY@AXELACARE.COM | [5 empty] | 12/08/2016 (IQBLFHWC) | 12/15/2016 (IQBLFHWC) |  | 12/08/2016 (11248302) |  | N (IQBLFHWC) N (N.11248302.5820416) | 05017789 P2155559 |  |  | NSPE0010786007
Cancelled | C1610-02-IJ Jefferson City | 3222 W TRUMAN BLVD JEFFERSON CITY, MO 65109-5708 US | 100 MBPS (23739930) | 01/19/2017: CANCELLED | 193742119 | C1610-02-IJ Jefferson City | Private IP - PIP (23739929) Access (23739930) | 23739929 23739930 | 30 MBPS (23739929) |  | 152659111 (Private IP (PIP)) 152659109 (Access) | C1049166/CANCEL (23739929) C1049166/ADD (23739929) E4017240/ADD (23739930) E4017240/CANCEL (23739930) |  | 5835210 | 9000 | PVC ID : 5835210 VPN Name : UHG-ECC Router Name : IDCXE03 VRF Name : V864747-UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65530 PE IP Address : 152.164.231.93 CE Address : 152.164.231.94 QoS - Egress Profile: R12 | 1000Base-T (23739930) | 1000Base-T (23739930) | Ethernet | [8 empty] | Mick Bridgins 1-636-812-4000 mick@roseint.com | JAVIER SEGUI | javier.segui@optum.com | 1-407-541-8143 | 01/19/2017(Private IP - PIP) 01/19/2017(Access) |  |  | 02/24/2017 | 01/19/2017 | 01/17/2017 (23739929) 01/19/2017 (23739930) |  | N (23739929) N (23739930) | U0101953 |  | NSPE0010905268; OR 193740897; C1610-02-IJ | NSPE0010905268
|  | 3225 W TRUMAN BLVD JEFFERSON CITY, MO 65109 USA | 1.536 MBPS (IQBLF14D) | 02/20/2017: Status: Sup to cancel 2/13 | 9031611 |  | Private IP (IQBLF14D) EVC/PVC Service (N.11295937.5836820) | IQBLF14D N.11295937.5836820 | 10.752 MBPS | P2159024 |  | BCBLBKC10001 (IQBLF14D) BCBLBKC10002 (IQBLF14D) BCBLBKC10003 (IQBLF14D) BCBLBKC10004 (IQBLF14D) BCBLBKC10005 (IQBLF14D) BCBLBKC10006 (IQBLF14D) BCBLBKC10007 (IQBLF14D) | 48.HCGS.295635..UDMO (IQBLF14D1T9VMB02) | 5836820 | 0 | VPN Name : UnitedHealthGroup Router Name : SC9GE03 VRF Name : V878158:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65530 PE IP Address : 152.161.110.225 CE Address : 152.161.110.226 QoS - Egress Profile: R12 PVC ID : 5836820 |  |  |  | CENTURYLINK (IQBLF14D1T9VMB02) | 02/16/2017 (IQBLF14D1T9VMB02) | 02/24/2017 (IQBLF14D1T9VMB02) | 02/10/2017 (IQBLF14D1T9VMB02) |  |  |  |  | MICK BRIDGINS 0016368124000 MICK@ROSEINT.COM | [5 empty] | 02/10/2017 (IQBLF14D) | 03/23/2017 (IQBLF14D) |  | 02/10/2017 (11295937) |  | N (IQBLF14D) N (N.11295937.5836820) | 05017789 P2159024 |  | NSPE0010914155 | NSPE0010914155
Cancelled | C1610-02-IJ Jefferson City | 3225 W TRUMAN BLVD JEFFERSON CITY, MO 65109-5709 US | 45 MBPS (23796362) | 02/09/2017: 02/09 Background: Jefferson City, MO; New 45/45M PPP; Century Link; No NID; No MNS Status: Pending LOA/CFA from Lease and this might take a week before we can obtain based on their interval. Once LOA is received, we will send request to LEC. Will continue to monitor. Next action: Lease group to provide LOA/CFA Who owns the next action: Lease group / Prov Ticket: NA | 193774811 | C1610-02-IJ Jefferson City | Private IP - PIP (23796361) Access (23796362) | 23796361 23796362 | 45 MBPS (23796361) |  | 154314436 (Private IP (PIP)) 154314434 (Access) | C4006331/ADD (23796361) C4006331/CANCEL (23796361) D3001528/CANCEL (23796362) D3001528/ADD (23796362) |  | 5839144 | 9000 | PVC ID : 5839144 VPN Name : UHG-ECC Router Name : SC9GE04 VRF Name : V882243:UHGECC Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65530 PE IP Address : 68.137.34.113 CE Address : 68.137.34.114 QoS - Egress Profile: R13 |  | DS3 (23796362) | TDM | [8 empty] | MICK BRIDGINS 1-636-812-4000 mick@roseint.com | JAVIER SEGUI | javier_segui@optum.com | 1-407-541-8143 | 02/10/2017(Private IP - PIP) 02/10/2017(Access) |  |  | 02/17/2017 | 02/10/2017 | 02/10/2017 (23796361) 02/10/2017 (23796362) |  | N (23796361) N (23796362) | U0101953 |  | OR 193773804 - C1610-06-IJ | NSPE0010934056
Cancelled | AZ047-02-IJ Tucson | 1669 W INA RD TUCSON, AZ 85704-1982 US | 10 MBPS (23836958) | 02/16/2017: 02/16 Background: TUCSON, AZ; New 10/10M PIP-Eth; Qwest; NID; No MNS Status: Pending loop delivery date. Date issuance will be delayed as per LEC. Next action: LEC to provide loop delivery date Who owns the next action: Qwest Ticket: NA | 193799306 | AZ047-02-IJ Tucson | Private IP - PIP (23836957) Access (23836958) | 23836957 23836958 | 10 MBPS (23836957) |  | 153994484 (Private IP (PIP)) 153994482 (Access) | C0114540/ADD (23836957) C0114540/CANCEL (23836957) E3034053/ADD (23836958) E3034053/CANCEL (23836958) |  | 5841801 | 1500 | PVC ID : 5841801 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64525 PE IP Address : 152.187.218.5 CE Address : 152.187.218.6 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23836958) | 1000Base-SX (850nm, Multi Mode Fiber) (23836958) | Ethernet | [8 empty] | Angel Gillett 1-520-795-6183 angel.gillett@optum.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 |  |  | 05/15/2017 (23836957) 05/11/2017 (23836958) | 03/16/2017 | 02/21/2017 | 02/21/2017 (23836957) 02/21/2017 (23836958) |  | N (23836957) N (23836958) | U0101953 |  | NSPE0010956036; Order Request # 193798792; AZ045-02-IJ Tucson | NSPE0010956036
Cancelled | AZ045-02-IJ Tucson | 1460 W VALENCIA RD TUCSON, AZ 85746-6001 US | 10 MBPS (23836949) | 02/16/2017: 02/16 Background: TUCSON, AZ; New 10/10M PIP-Eth; Qwest; NID; No MNS Status: Pending loop delivery date. Next action: LEC to provide loop delivery date Who owns the next action: Qwest Ticket: NA | 193799307 | AZ045-02-IJ Tucson, | Private IP - PIP (23836948) Access (23836949) | 23836948 23836949 | 10 MBPS (23836948) |  | 154191762 (Private IP (PIP)) 154191760 (Access) | C0113521/ADD (23836948) C0113521/CANCEL (23836948) E3033942/ADD (23836949) E3033942/CANCEL (23836949) |  | 5841807 | 1500 | PVC ID : 5841807 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64522 PE IP Address : 152.161.48.45 CE Address : 152.161.48.46 QoS - Egress Profile: R12 | 1000Base-SX-850nm (23836949) | 1000Base-SX (850nm, Multi Mode Fiber) (23836949) | Ethernet | [8 empty] | Anisa Lopez 1-520-573-0966 anisa.lopez@optum.com | ROB WINSTON | robert.winston@optum.com | 1-443-872-3099 |  |  | 05/01/2017 (23836948) 04/27/2017 (23836949) | 03/16/2017 | 02/21/2017 | 02/21/2017 (23836948) 02/21/2017 (23836949) |  | N (23836948) N (23836949) | U0101953 |  | NSPE0010956036; Order Request # 193798792; AZ045-02-IJ Tucson | NSPE0010956036
Cancelled | VA060-05-IJ | 12018 SUNRISE VALLEY DR STE 400 RESTON, VA 20191-3434 US | 50 MBPS | 04/20/2017: 04/20 Background: Reston, VA; New 20M/50M PIP-Eth; No NID; No MNS Status: Order onhold since 2/21. Customer site not ready. Sent site requirement to John Sergot. Customer to complete site requirement and provide completion date. Next action: OC to submit order. Who owns the next action: OC Ticket: NA | 193810376 | VA060-05-IJ | Access Private IP - PIP |  | 20 MBPS |  | 94139166 94139170 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Jameel Al-Ahmedc 1-571-262-8919 jalahmed@optum.com | Katherine Acain | katherine_acain@optum.com | 632-588-5327 |  |  |  | 03/20/2017 |  |  |  | N | U0101953 | Jeopardy Notification 1 (03/28/2017) | NSPE0010966165 - OR 193806626; RESTON VA; New 20M/50M PIP-Eth; No NID; No MNS | NSPE0010966165
Cancelled | Edison NJ | 333 THORNALL ST EDISON, NJ 08837-2220 US | 50 MBPS | 04/13/2017: 04/13 Background: NJ023-07-IJ; Edison, NJ; New /50M PIP-Ethernet; Verizon ILEC; No NID; No MNS; Status: Order onhold since 03/02. Customer site is not ready. Customer to complete site requirement and provide completion date. Next action: Customer to provide site requirement completion date Who owns the next action: Customer Ticket: NA | 193831323 | Edison NJ | Access Private IP - PIP |  | 20 MBPS |  | 157555056 157555058 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | SCOTT D WAULTERS 1-848-200-3572 swaulters@uhc.com | Herbert Villostas | herbert_villostas@optum.com | 632-790-6516 |  |  |  | 03/14/2017 |  |  |  | N | U0101953 |  | Order Request 193830771 | NSPE0010983820
Cancelled | UNITED HEALTH GROUP | 979 DEL MAR DR THE VILLAGES, FL 32159-7734 US | 10 MBPS (24007977) | 02/22/2017: 02/22 Order cancelled. John decided to not go forward with this order. | 193848057 | UNITED HEALTH GROUP | Private IP - PIP (24007976) WAN Analysis Reporting (24007978) Access (24007977) | 24007976 24007978 24007977 | 5 MBPS (24007976) |  | 158565957 (Private IP (PIP)) 158565958 (WAN Analysis Reporting) 158565955 (Access) | C0115164/CANCEL (24007976) C0115164/ADD (24007976) E3034636/CANCEL (24007977) E3034636/ADD (24007977) |  | 5846774 | 4000 | PVC ID : 5846774 VPN Name : UnitedHealthGroup Router Name : TES9E03 VRF Name : V520368:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65273 PE IP Address : 152.192.125.5 CE Address : 152.192.125.6 QoS - Egress Profile: R12 | 100Base-TX (24007977) | 100Base-FX (1310nm, Multi Mode Fiber) (24007977) | Ethernet | CENTURYLINK (2400797774246001) | 02/21/2017 (2400797774246001) | [6 empty] | Deborah Rosshirt 1-352-674-7160 deborah_rosshirt@uhc.com | RAUL BARLOSO | raul_barloso@optum.com | 632-790-6271 |  |  |  | 04/03/2017 04/07/2017 | 02/22/2017 | 02/22/2017 (24007976) 02/22/2017 (24007978) 02/22/2017 (24007977) | Requested Due Date | N (24007976) N (24007978) N (24007977) | U0101953 |  | NSPE0010995420 Order Request # 193847173 | NSPE0010995420
Cancelled | NY015-07-IJ | 50 FULTON AVE HEMPSTEAD, NY 11550-3686 US | 10 MBPS | 03/16/2017: 03/16 TO BE CANCELLED DUE TO WRONG ADDRESS. AWAITING NEW ORDER. | 193852784 | NY015-07-IJ | Private IP - PIP WAN Analysis Reporting Access |  | 5 MBPS |  | 158622999 158623000 158622997 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Angeo Zuffante 1-516-247-6351 angelo_zuffante@uhc.com | RAUL BARLOSO | raul_barloso@optum.com | 632-790-6271 |  |  |  | 03/21/2017 03/27/2017 |  |  |  | N | U0101953 |  | NSPE0010998718 Order Request # 193851217 | NSPE0010998718
Cancelled | UNITED HEALTHCARE | 3003 N CENTRAL AVE PHOENIX, AZ 85012-2902 US | 50 MBPS (24036020) | 04/10/2017: 04/10 Order cancelled. As per Melissa Chapman, "Yep, we can cancel this." | 193862428 | UNITED HEALTHCARE | Private IP - PIP (24036019) WAN Analysis Reporting (24036021) Access (24036020) | 24036019 24036021 24036020 | 10 MBPS (24036019) |  | 159174509 (Private IP (PIP)) 159174510 (WAN Analysis Reporting) 159174507 (Access) | C4006599/CANCEL (24036019) C4006599/ADD (24036019) E4018372/ADD (24036020) E4018372/CANCEL (24036020) |  | 5848433 |  | PVC ID : 5848433 |  | 1000Base-SX (850nm, Multi Mode Fiber) (24036020) | Ethernet | [8 empty] | Nancy Williams 1-602-282-8208 nancy_j_williams@optum.com | SEENIVASAN B | seenivasan.b@optum.com | 91-804-670-4287 | 04/12/2017(Private IP - PIP) 04/12/2017(Access) |  |  | 03/23/2017 03/29/2017 | 04/12/2017 | 04/11/2017 (24036019) 04/10/2017 (24036021) 04/12/2017 (24036020) | Order Canceled | N (24036019) N (24036021) N (24036020) | U0101953 | Jeopardy Notification 4 (03/31/2017) | Order Request: 193862034 | NSPE0011007448
Cancelled | UMD11-07 | 800 KING FARM BLVD ROCKVILLE, MD 20850-5979 US | 100 MBPS | 04/20/2017: 04/20 Order cancelled. Customer to continue working the site requirements and resubmit the order once the site readiness is completed. | 193873315 | UMD11-07 | Private IP - PIP WAN Analysis Reporting Access |  | 100 MBPS |  | 159353709 159353710 159353707 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | KENNETH R BOHON 1-240-683-5281 kbohon@uhc.com | HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 |  |  |  | 03/27/2017 03/31/2017 |  |  |  | N | U0101953 |  | NSPE0011015417 Order Request # 193872041 | NSPE0011015417
Cancelled | PA012-07-IJ Pittsburgh PA | 1001 BRINTON RD PITTSBURGH, PA 15221-4533 US | 200 MBPS | 03/16/2017: 03/16 Background: PA012-07-IJ PITTSBURGH, PA; New 200M Access Speed PIP Eth; No NID; No MS Status: Site survey 03/20/2017 09:00-12:00 local time Next action: Site visit Who owns the next action: OSPE Ticket: NA | 193915753 | PA012-07-IJ Pittsburgh, PA | Access WAN Analysis Reporting Private IP - PIP |  | 150 MBPS |  | 161382680 161382683 161382682 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Brad Gouza 1-412-501-0625 brad.gouza@optum.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 |  |  |  | 04/11/2017 04/17/2017 |  |  |  | N | U0101953 |  | NSPE0011053107 Order Request 193915560 | NSPE0011053107
Cancelled | CA013-02-IJ UHG - Monarch Irvine | 7 TECHNOLOGY DR IRVINE, CA 92618-2302 US | 1 GBPS (24178595) | 03/30/2017: 03/30 Background: CA013-05-IM Irvine CA; New 1G/1G PIP Eth; AT&T; NID; No MS; Status: Pending loop delivery date Next action: LEC to provide loop delivery date Who owns the next action: AT&T Ticket: NA | 193933772 | CA013-02-IJ UHG - Monarch Irvine | Private IP - PIP (24178594) WAN Analysis Reporting (24178596) Access (24178595) | 24178594 24178596 24178595 | 1 GBPS (24178594) |  | 161740611 (Private IP (PIP)) 161740612 (WAN Analysis Reporting) 161740609 (Access) | C0118741/CANCEL (24178594) C0118741/ADD (24178594) E5006260/CANCEL (24178595) E5006260/ADD (24178595) |  | 5855458 | 700000 | PVC ID : 5855458 VPN Name : UHG-Monarch Router Name : LSA29E01 VRF Name : V966662:UHGMonarch Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65502 PE IP Address : 152.162.56.189 CE Address : 152.162.56.190 QoS - Egress Profile: R1 | 1000Base-SX-850nm (24178595) | 1000Base-SX (850nm, Multi Mode Fiber) (24178595) | Ethernet |  |  |  |  | 05/03/2017 (VFORCE) (24178595) |  |  |  | Santosh Tendolkar 1-949-573-3530 stendolkar@mhealth.com | Pooyan Haghighi | phaghighi@mhealth.com | 1-510-717-2602 | 03/30/2017(Private IP - PIP) 03/30/2017(Access) |  |  | 04/28/2017 05/04/2017 | 03/30/2017 | 03/24/2017 (24178594) 03/24/2017 (24178596) 03/30/2017 (24178595) | Order Canceled | N (24178594) N (24178596) N (24178595) | U0101953 |  | NSPE0011065855 Order Request # 193932880 | NSPE0011065855
Cancelled | UMD14-05-IJ Baltimore MD | 2111 VAN DEMAN ST BALTIMORE, MD 21224-6609 US | 50 MBPS | 08/17/2017: 08/17 Background: UMD14-08-IM Baltimore, MD; New 20M/50M PIP-Eth; No NID; No MS; Status: Staged. Order onhold since 05/09/2017. VZ has conduit path to the building however there are repairs needed the Landlord/private property. VZ will not repair structure on private property. This is the responsibility of landlord or customer. The Conduit is approx 150FT from the VZ manhold to towards the building. Decision to corrected needed repairs need to come from Cust and their landlord. This needs to be completed 08/09. Next action: Will cancel now and reissue later once site is ready Who owns the next action: OM Ticket: NA | 193994039 | UMD14-05-IJ Baltimore, MD | Private IP - PIP Access WAN Analysis Reporting |  | 20 MBPS |  | 164905620 164905618 164905621 | [5 empty] | 100Base-FX - MMF | 100Base-FX (1310nm, Multi Mode Fiber) | Ethernet | [8 empty] | Michael O'Neal 1-301-977-7884 michael_oneal@uhg.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 |  |  |  | 05/03/2017 05/09/2017 |  |  |  | N | U0101953 |  | Order Request 193993058 | NSPE0011112654
|  | 5908 HAMPTON OAKS PKWY TAMPA, FL 33610 USA | 44.736 MBPS (CQBLG262) | 06/22/2017: 06/22 Order cancelled. Customer selling this portion of their business | 9120866 |  | BACS (Channelized DS3) (CQBLG262) | CQBLG262 | 44.736 MBPS (CQBLG262) | P2016963 |  | AOBK1H2R0001 (CQBLG262) | [15 empty] | MELISSA CHAPMAN 0018136309705 EDWARD.MCLAUGHLIN@OPTUM.COM | [6 empty] | 07/24/2017 (CQBLG262) |  |  |  | N (CQBLG262) | 05657353 |  | NSPE0011120680 | NSPE0011120680
Cancelled | CO038-02-IM | 8051 E MAPLEWOOD AVE STE 300 GREENWOOD VILLAGE, CO 80111-4742 US | 20 MBPS (24383783) | 08/24/2017: Cancelled. Will reissue a new order with Comcast. | 194039588 | CO038-02-IM | Access (24383783) Private IP - PIP (24383782) WAN Analysis Reporting (24383784) | 24383783 24383782 24383784 | 10 MBPS (24383782) |  | 167229246 (Access) 167229248 (Private IP (PIP)) 167229249 (WAN Analysis Reporting) | E3038873/CANCEL (24383783) E3038873/ADD (24383783) C3012888/CANCEL (24383782) C3012888/ADD (24383782) |  | 5867859 | 3000 | PVC ID : 5867859 VPN Name : UnitedHealthGroup Router Name : DNJXE01 VRF Name : V469377-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64773 PE IP Address : 152.162.83.165 CE Address : 152.162.83.166 QoS - Egress Profile: R12 | 1000Base-T (24383783) | 1000Base-SX (850nm, Multi Mode Fiber) (24383783) | Ethernet |  |  |  |  | 09/21/2017 (VFORCE) (24383783) |  |  |  | Mike Landauer 1-303-749-1169 mlandauer@cnichs.com | MOHAMMED HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 |  |  |  | 06/08/2017 06/14/2017 | 08/24/2017 | 08/24/2017 (24383783) 08/23/2017 (24383782) 08/23/2017 (24383784) | Order Canceled | N (24383783) N (24383782) N (24383784) | U0101953 |  | NSPE0011153141 Order Request # 194038545 | NSPE0011153141
Cancelled | C1616-01-IM | 304 E CARSON AVE LAS VEGAS, NV 89101-5903 US | 1.5 MBPS (24392736) | 05/18/2017: Cancelled | 194052652 | C1616-01-IM | Private IP - PIP (24392735) WAN Analysis Reporting (24392737) Access (24392736) | 24392735 24392737 24392736 | 1.5 MBPS (24392735) |  | 167749374 (Private IP (PIP)) 167749375 (WAN Analysis Reporting) 167749372 (Access) | C0121298/ADD (24392735) C0121298/CANCEL (24392735) D1085944/ADD (24392736) D1085944/CANCEL (24392736) |  | 5868231 | 1000 | PVC ID : 5868231 VPN Name : UHG-ECC Router Name : LSVG9E03 VRF Name : V100938:UHGECC Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65518 PE IP Address : 152.162.230.149 CE Address : 152.162.230.150 QoS - Egress Profile: R12 |  | DS1 (24392736) | TDM | [6 empty] | DEMARCADDR - NA DEMARCDET - NA |  | Jason Stauss 1-206-274-7952 jstauss@revenueadvantage.com | Travis Dent | travis.dent@optum.com | 1-763-744-2265 | 05/24/2017(Private IP - PIP) 05/24/2017(Access) |  |  | 06/01/2017 06/07/2017 | 05/24/2017 | 05/18/2017 (24392735) 05/18/2017 (24392737) 05/24/2017 (24392736) | Order Canceled | N (24392735) N (24392737) N (24392736) | U0101953 |  | NSPE0011164146 Order Request # 194052504 | NSPE0011174976
Cancelled | FL147-05-IM OCALA FL | 2800 E SILVER SPRINGS BLVD STE 201 OCALA, FL 34470-7057 US | 4.6 MBPS (24604699) | 06/01/2017: 06/01 Background: FL218-01-IJ Ocala, FL; New 4.608 3xT1 PIP MLPPP; CTL; No NID; No MS; Status: Loop delivery date 06/08/2017 Next action: LEC to deliver Who owns the next action: CTL Ticket: NA | 194141181 | FL147-05-IM | Private IP - PIP (24604698) WAN Analysis Reporting (24604700) Access (24604699) | 24604698 24604700 24604699 | 4.6 MBPS (24604698) |  | 171832609 (Private IP (PIP)) 171832610 (WAN Analysis Reporting) 171832607 (Access) | C0122571/ADD (24604698) C0122571/CANCEL (24604698) N1037053/CANCEL (24604699) N1037053/ADD (24604699) N1037054/CANCEL (24604699) N1037054/ADD (24604699) N1037055/CANCEL (24604699) N1037055/ADD (24604699) |  | 5879996 | 2500 | PVC ID : 5879996 VPN Name : UnitedHealthGroup Router Name : AUB3E02 VRF Name : V341993-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64696 PE IP Address : 68.136.187.205 CE Address : 68.136.187.206 QoS - Egress Profile: R12 |  | DS1 (24604699) | TDM | [8 empty] | PETER MARESKA 1-813-486-7037 peter_mareska@uhg.com | JOHN ROTHSTEIN | john_l_rothstein@optum.com | 1-763-744-1556 | 06/05/2017(Private IP - PIP) 06/05/2017(Access) |  | 06/15/2017 (24604698) 06/13/2017 (24604699) | 06/20/2017 06/26/2017 | 06/05/2017 | 06/02/2017 (24604698) 06/02/2017 (24604700) 06/05/2017 (24604699) | Order Canceled | N (24604698) N (24604700) N (24604699) | U0101953 |  |  | NSPE0011237479
Cancelled | UNITED HEALTH CARE | 8880 CAL CENTER DR SACRAMENTO, CA 95826-3222 US | 50 MBPS (24855667) | 07/06/2017: 0706 Order supped to cancel as per customer request. | 194265305 | UNITED HEALTH CARE | Access (24855667) Private IP - PIP (24855666) WAN Analysis Reporting (24855668) | 24855667 24855666 24855668 | 20 MBPS (24855666) |  | 177859927 (Access) 177859929 (Private IP (PIP)) 177859930 (WAN Analysis Reporting) | E4021476/ADD (24855667) E4021476/CANCEL (24855667) C4007926/ADD (24855666) C4007926/CANCEL (24855666) |  | 5890968 | 7000 | PVC ID : 5890968 VPN Name : UnitedHealthGroup Router Name : SCM3E03 VRF Name : V447827-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65185 PE IP Address : 208.220.222.161 CE Address : 208.220.222.162 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24855667) | 1000Base-SX (850nm, Multi Mode Fiber) (24855667) | Ethernet |  |  |  |  | 07/27/2017 (VFORCE) (24855667) |  |  |  | EMILY LIVAICH 1-916-403-0677 emily.livaich@uhc.com | MOHAMMED HUMAYUN RAFI | humayun_rafi@optum.com | 91-804-920-3530 | 07/10/2017(Access) 07/10/2017(Private IP - PIP) |  |  | 08/11/2017 08/17/2017 | 07/11/2017 | 07/10/2017 (24855667) 07/06/2017 (24855666) 07/06/2017 (24855668) | Order Canceled | N (24855667) N (24855666) N (24855668) | U0101953 | Jeopardy Notification 1 (07/06/2017) |  | NSPE0011328554
| TX363-05-IM HARLINGEN TX | 3809 W BUSINESS 83 HARLINGEN, TX 78552 USA | 1.536 MBPS (IQBLH6SL) | 08/17/2017: 08/17 Background:TX363-05-IM HARLINGEN, TX; NEW 7XT1 PIP MLPPP; NO MNS Status: Order onhold 08/14. Site Contact refuse service, stating this is for cancellation. Next action: Customer to verify if this is needed Who owns the next action: Customer Ticket: NA | 9231931 |  | Private IP (IQBLH6SL) EVC/PVC Service (N.11464398.5898877) | IQBLH6SL N.11464398.5898877 | 10.752 MBPS | P2171542 |  | BCBLB3LC0001 (IQBLH6SL) BCBLB3LC0002 (IQBLH6SL) BCBLB3LC0003 (IQBLH6SL) BCBLB3LC0004 (IQBLH6SL) BCBLB3LC0005 (IQBLH6SL) BCBLB3LC0006 (IQBLH6SL) BCBLB3LC0007 (IQBLH6SL) |  | 5898877 | 2420 | VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64924 PE IP Address : 152.164.41.89 CE Address : 152.164.41.90 QoS - Egress Profile: R12 PVC ID : 5898877 | [11 empty] | DAVID GOMEZ 0012108626784 DGOMEZ@WELLMED.NET | [5 empty] | 08/23/2017 (IQBLH6SL) | 08/23/2017 (IQBLH6SL) |  | 08/23/2017 (11464398) |  | N (IQBLH6SL) N (N.11464398.5898877) | 05650532 P2171542 |  | NSPE0011394378 CW 194311209 | NSPE0011394378
Cancelled | CA013-02-IJ UHG - Monarch Irvine | 7 TECHNOLOGY DR IRVINE, CA 92618-2302 US | 500 MBPS (24992454) | 08/31/2017: Cancell order due to LEC (Charter) Service Order # 194339616 has no service in area dna declined order. Order replaced with New LEC (Cox) order new service order 194423573 | 194339616 | CA013-02-IJ UHG - Monarch Irvine | Private IP - PIP (24992453) WAN Analysis Reporting (24992455) Access (24992454) | 24992453 24992455 24992454 | 300 MBPS (24992453) |  | 180993438 (Private IP (PIP)) 180993439 (WAN Analysis Reporting) 180993436 (Access) | C5003426/ADD (24992453) C5003426/CANCEL (24992453) E5007471/ADD (24992454) E5007471/CANCEL (24992454) |  | 5900154 | 1500 | PVC ID : 5900154 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65010 PE IP Address : 152.164.63.225 CE Address : 152.164.63.226 QoS - Egress Profile: R12 | 1000Base-SX-850nm (24992454) | 1000Base-SX (850nm, Multi Mode Fiber) (24992454) | Ethernet | [8 empty] | AMIR SEMNANIAN 1-949-923-3392 asemnanian@mhealth.com | Ranjit Adhikari | ranijt_adhikari@optum.com | 1-763-744-1957 |  |  |  | 09/05/2017 09/11/2017 | 08/30/2017 | 08/30/2017 (24992453) 08/30/2017 (24992455) 08/30/2017 (24992454) | Order Canceled | N (24992453) N (24992455) N (24992454) | U0101953 |  | NSPE0011411625 Order Request # 194339247 Site Name: CA013-08-IM | NSPE0011411625
Cancelled | TX356-01-IM Mesquite TX | 200 W KEARNEY ST MESQUITE, TX 75149-3471 US | 1.5 MBPS (25015181) | 08/31/2017: 08/31 Background: TX356-01-IM Mesquite, TX; New 1.5Mbps PIP-MLPPP; ATT; No NID; No MS; Status: Order needs to be reissued as 7xT1. Next action: to be cancelled and reissued Who owns the next action: Sales Ticket: NA | 194354219 | TX356-01-IM Mesquite, TX Wellmed | Private IP - PIP (25015180) WAN Analysis Reporting (25015182) Access (25015181) | 25015180 25015182 25015181 | 1.5 MBPS (25015180) |  | 181507891 (Private IP (PIP)) 181507892 (WAN Analysis Reporting) 181507889 (Access) | C0126563/ADD (25015180) C0126563/CANCEL (25015180) D1088070/ADD (25015181) D1088070/CANCEL (25015181) |  | 5901838 | 900 | PVC ID : 5901838 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : V991844-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 64617 PE IP Address : 152.176.87.77 CE Address : 152.176.87.78 QoS - Egress Profile: R12 |  | DS1 (25015181) | TDM | [8 empty] | SONIA GARZA 1-210-421-1702 SGarza@wellmed.net | Rizwan Anugula | rizwan.anugula@optum.com | 91-804-670-4280 | 09/01/2017(Private IP - PIP) 09/01/2017(Access) |  | 08/30/2017 (25015180) 08/28/2017 (25015181) | 09/12/2017 09/18/2017 | 09/02/2017 | 09/01/2017 (25015180) 09/01/2017 (25015182) 09/01/2017 (25015181) | Order Canceled | N (25015180) N (25015182) N (25015181) | U0101953 | Jeopardy Notification 1 (09/01/2017) | NSPE0011416861 Order Request # 194348100 | NSPE0011416861
Cancelled | TX361-02-IJ Houston TX | 8888 INTERCHANGE DR HOUSTON, TX 77054-2512 US | 50 MBPS (25141540) | 11/03/2017: 11/02 Reissued under Service Order # 194688266 with urgency. | 194410736 | TX361-02-IJ Houston, TX | Private IP - PIP (25141539) Access (25141540) WAN Analysis Reporting (25141541) | 25141539 25141540 25141541 | 10 MBPS (25141539) |  | 183529376 (Private IP (PIP)) 183529374 (Access) 183529377 (WAN Analysis Reporting) | C4008279/ADD (25141539) C4008279/CANCEL (25141539) E4022470/CANCEL (25141540) E4022470/ADD (25141540) |  | 5908267 | 7000 | PVC ID : 5908267 VPN Name : UnitedHealthGroup Router Name : HSTN3E03 VRF Name : V112143-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65231 PE IP Address : 152.183.24.177 CE Address : 152.183.24.178 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25141540) | 1000Base-SX (850nm, Multi Mode Fiber) (25141540) | Ethernet | [8 empty] | Jason Engel 1-303-594-1125 jason_engel@uhg.com | JEREMIAH LASCANO | jeremiah_lascano@optum.com | 632-588-5331 |  |  | 10/17/2017 (25141539) 10/13/2017 (25141540) | 09/25/2017 09/29/2017 | 11/09/2017 | 11/01/2017 (25141539) 11/09/2017 (25141540) 11/01/2017 (25141541) | Cancelled | N (25141539) N (25141540) N (25141541) | U0101953 | Jeopardy Notification 5 (11/01/2017) | NSPE0011453620 Order Request # 194402025 | NSPE0011453620
Cancelled | UWI29-11-IM Green Bay WI | 3100 AMS BLVD GREEN BAY, WI 54313-9700 US | 200 MBPS (25172852) | 08/25/2017: 08/25 Background: UWI29-11-IM Green Bay, WI; New 100M/200M PIP-E; TWC; NID; No MS; Status: Reissued under NSPE0011534881 Order Request 194447806 / Service Order # 194447070 - with 200M/500M Speed. Pending loop delivery date. Requested NDMT for late receipt of FOC. Next action: Pending cancellation confirmation from customer Who owns the next action: Customer Ticket: NA | 194423403 | UWI29-11-IJ Green Bay | Access (25172852) WAN Analysis Reporting (25172853) Private IP - PIP (25172851) | 25172852 25172853 25172851 | 100 MBPS (25172851) |  | 184238527 (Access) 184238530 (WAN Analysis Reporting) 184238529 (Private IP (PIP)) | E5007749/CANCEL (25172852) E5007749/ADD (25172852) C5003526/CANCEL (25172851) C5003526/ADD (25172851) |  | 5909641 | 30000 | PVC ID : 5909641 VPN Name : UnitedHealthGroup Router Name : MWAGE03 VRF Name : V112553:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64990 PE IP Address : 68.138.90.89 CE Address : 68.138.90.90 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25172852) | 1000Base-SX (850nm, Multi Mode Fiber) (25172852) | Ethernet | [8 empty] | Daniel Bartlett 1-763-744-1815 daniel_l_bartlett@optum.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 |  |  | 11/27/2017 (25172852) 11/29/2017 (25172851) | 09/28/2017 10/04/2017 | 09/01/2017 | 09/01/2017 (25172852) 09/01/2017 (25172853) 09/01/2017 (25172851) | Order Canceled | N (25172852) N (25172853) N (25172851) | U0101953 |  | NSPE0011518318 Order Request # 194421941 | NSPE0011518318
Cancelled | UWI29-11-IJ Green Bay | 3100 AMS BLVD GREEN BAY, WI 54313-9700 US | 500 MBPS (25209525) | 09/28/2017: 09/28 Order cancelled as per Melissa Chapman's request | 194447806 | UWI29-11-IJ Green Bay | Private IP - PIP (25209524) WAN Analysis Reporting (25209526) Access (25209525) | 25209524 25209526 25209525 | 200 MBPS (25209524) |  | 184941505 (Private IP (PIP)) 184941506 (WAN Analysis Reporting) 184941503 (Access) | C5003552/CANCEL (25209524) C5003552/ADD (25209524) E5007822/CANCEL (25209525) E5007822/ADD (25209525) |  | 5911410 | 140000 | PVC ID : 5911410 VPN Name : UnitedHealthGroup Router Name : MWA9E01 VRF Name : Va27144:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64990 PE IP Address : 152.177.52.113 CE Address : 152.177.52.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25209525) | 1000Base-SX (850nm, Multi Mode Fiber) (25209525) | Ethernet | [8 empty] | DANIEL BARTLETT 1-763-744-1815 daniel_l_bartlett@optum.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 09/29/2017(Private IP - PIP) 09/29/2017(Access) |  | 12/06/2017 (25209524) 12/04/2017 (25209525) | 11/02/2017 11/08/2017 | 09/29/2017 | 09/28/2017 (25209524) 09/28/2017 (25209526) 09/29/2017 (25209525) | Order Canceled | N (25209524) N (25209526) N (25209525) | U0101953 | Jeopardy Notification 2 (09/20/2017) | NSPE0011534881 Order Request # 194447070 | NSPE0011534881
Cancelled | TX340-04-IM Kingsville TX | 1311 GENERAL CAVAZOS BLVD KINGSVILLE, TX 78363 USA | 1.536 MBPS (IQBLJM8Z) | 12/01/2017: 12/01 Background: TX340-04-IM Kingsville, TX; New 7XT1 PIP MLPPP; SWB; No NID; No MS Status: Cancelling order as per customer request. Next action: NA Who owns the next action: NA Ticket: NA | 9273629 |  | Private IP (IQBLJM8Z) EVC/PVC Service (N.11495963.5912077) | IQBLJM8Z N.11495963.5912077 | 10.752 MBPS | P2174851 |  | BCBLB7LG0001 (IQBLJM8Z) BCBLB7LG0002 (IQBLJM8Z) BCBLB7LG0003 (IQBLJM8Z) BCBLB7LG0004 (IQBLJM8Z) BCBLB7LG0005 (IQBLJM8Z) BCBLB7LG0006 (IQBLJM8Z) BCBLB7LG0007 (IQBLJM8Z) |  | 5912077 | 1512 | VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65225 PE IP Address : 152.187.4.81 CE Address : 152.187.4.82 QoS - Egress Profile: R12 PVC ID : 5912077 | [11 empty] | RICK WILLIAMSON 0012109513129 RWILLIAMSON@WELLMED.NET | [5 empty] | 12/01/2017 (IQBLJM8Z) | 12/15/2017 (IQBLJM8Z) |  | 12/01/2017 (11495963) |  | N (IQBLJM8Z) N (N.11495963.5912077) | 05650532 P2174851 |  | NSPE0011537344 CW 194446951 | NSPE0011537344
Cancelled | CA250-02-IM Irvine CA | 4 TECHNOLOGY DR IRVINE, CA 92618-5314 US | 1 GBPS (25271898) | 10/19/2017: 10/19 Background: CA250-02-IM Irvine, CA; New 100M/1G PIP-E; Cox; NID; No MS; Status: Customer advise they will have Site Access on 11/15. Will cancel now and reissue this order once customer is ready. Next action: Cancel order Who owns the next action: OC Ticket: NA | 194484496 | UnitedHealth Group- Monarch | Access (25271898) Private IP - PIP (25271897) WAN Analysis Reporting (25271899) | 25271898 25271897 25271899 | 100 MBPS (25271897) |  | 190644310 (Access) 190644312 (Private IP (PIP)) 190644313 (WAN Analysis Reporting) | E5007957/CANCEL (25271898) E5007957/ADD (25271898) C0128851/ADD (25271897) C0128851/CANCEL (25271897) |  | 5914482 | 70000 | PVC ID : 5914482 VPN Name : UHG-Monarch Router Name : LSA29E02 VRF Name : V976456:UHGMonarch Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65505 PE IP Address : 199.220.98.105 CE Address : 199.220.98.106 QoS - Egress Profile: R1 | 1000Base-SX-850nm (25271898) | 1000Base-SX (850nm, Multi Mode Fiber) (25271898) | Ethernet | [8 empty] | POOYAN HAGHIGHI 1-510-717-2602 phaghighi@mhealth.com | SANTOSH TENDOLKAR | stendolkar@mhealth.com | 1-562-382-7377 |  |  |  | 10/16/2017 10/20/2017 | 10/25/2017 | 10/25/2017 (25271898) 10/22/2017 (25271897) 10/22/2017 (25271899) | Cancelled | N (25271898) N (25271897) N (25271899) | U0101953 | Jeopardy Notification 4 (10/16/2017) | NSPE0011559687 Order Request # 194483146 | NSPE0011559687
Cancelled | TX371-02-IM San Benito TX | 850 W US HIGHWAY 77 SAN BENITO, TX 78586-4319 US | 50 MBPS (25456627) | 10/05/2017: 10/05 Background: TX371-02-IM San Benito, TX; New 10M/50M PIP-E; NID; SX MMF; No MNS; Status: Loop delivery date 01/18/2018 Next action: LEC to deliver Who owns the next action: TWC Ticket: NA | 194570357 | UHG- TX371 Wellmed | Private IP - PIP (25456626) WAN Analysis Reporting (25456628) Access (25456627) | 25456626 25456628 25456627 | 10 MBPS (25456626) |  | 193856388 (Private IP (PIP)) 193856389 (WAN Analysis Reporting) 193856386 (Access) | C4008824/CANCEL (25456626) C4008824/ADD (25456626) E4023902/CANCEL (25456627) E4023902/ADD (25456627) |  | 5922859 | 5500 | PVC ID : 5922859 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65279 PE IP Address : 199.220.215.173 CE Address : 199.220.215.174 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25456627) | 1000Base-SX (850nm, Multi Mode Fiber) (25456627) | Ethernet | [8 empty] | Luis Casas 1-956-455-5057 luisecasas@yahoo.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 10/06/2017(Private IP - PIP) 10/06/2017(Access) |  | 01/29/2018 (25456626) 01/25/2018 (25456627) | 02/20/2018 02/26/2018 | 10/07/2017 | 10/06/2017 (25456626) 10/06/2017 (25456628) 10/06/2017 (25456627) | Order Canceled | N (25456626) N (25456628) N (25456627) | U0101953 |  | NSPE0011616624 Order Request # 194568114 | NSPE0011616624
Cancelled | TX342-05-CM CORPUS CHRISTI TX | 1701 S STAPLES ST CORPUS CHRISTI, TX 78404 USA | 1.536 MBPS (IQBLJ3XH) | 11/03/2017: 11/03 Order cancelled as per customer''s request. | 9316271 |  | Private IP (IQBLJ3XH) EVC/PVC Service (N.11532417.5923956) | IQBLJ3XH N.11532417.5923956 | 10.752 MBPS | P2178767 |  | BCBLCC2K0001 (IQBLJ3XH) BCBLCC2K0002 (IQBLJ3XH) BCBLCC2K0003 (IQBLJ3XH) BCBLCC2K0004 (IQBLJ3XH) BCBLCC2K0005 (IQBLJ3XH) BCBLCC2K0006 (IQBLJ3XH) BCBLCC2K0007 (IQBLJ3XH) |  | 5923956 | 1536 | VPN Name : UnitedHealthGroup Router Name : SAJGE01 VRF Name : V145769:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65116 PE IP Address : 152.164.147.209 CE Address : 152.164.147.210 QoS - Egress Profile: R12 PVC ID : 5923956 | [11 empty] | RICK WILLIAMSON 0012109513129 RWILLIAMSON@WELLMED.NET | JEBIN GEORGE | JEBIN.GEORGE@OPTUM.COM | 0918046704595 |  |  | 11/08/2017 (IQBLJ3XH) | 11/08/2017 (IQBLJ3XH) |  | 11/08/2017 (11532417) |  | N (IQBLJ3XH) N (N.11532417.5923956) | 05650532 P2178767 |  | NSPE0011627738 CW 194584184; Note: We are moving from Legacy platform to VRD because VRD cannot accommodate 7xT1. So we are installing an entirely NEW order. No need to reuse loop. Please install entirely new loops. Disconnection Request for the existing Legacy Circuit will be submitted by the account team. Existing Circuit ID C0119588 access N1036322 N1036323 and N1036324; (sales to submit a disconnection request once new install is complete) | NSPE0011627738
Cancelled | UIL55-17-IM Lawrenceville IL | 1001 JEFFERSON ST LAWRENCEVILLE, IL 62439-2435 US | 100 MBPS (25510478) | 12/21/2017: 12/21 Background: UIL55-17-IM Lawrenceville, IL; New 50M/100M PIP-Eth; Frontier; SX MMF; NID; No MNS; Status: Awaiting special construction cost approval from customer. Looking other alternatives; Shared LEC NID is not available; LEC uses 24f or 48f fiber strand details. Customer may directly coordinate with OSP Eng. Travis Cox RAVIS.COX@FTR.COM and and ISP Eng. Jay Johns JAY.JOHNS2@FTR.COM regarding the technical details. Next action: PI sup Who owns the next action: Account Team Ticket: NA | 194587673 | UIL24-17-IJ | Private IP - PIP (25510477) WAN Analysis Reporting (25510479) Access (25510478) | 25510477 25510479 25510478 | 50 MBPS (25510477) |  | 194682667 (Private IP (PIP)) 194682668 (WAN Analysis Reporting) 194682665 (Access) | C1061086/CANCEL (25510477) C1061086/ADD (25510477) E4024057/ADD (25510478) E4024057/CANCEL (25510478) |  | 5924140 | 4000 | PVC ID : 5924140 VPN Name : UnitedHealthGroup Router Name : PLVXE01 VRF Name : V669152-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64764 PE IP Address : 152.183.7.229 CE Address : 152.183.7.230 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25510478) | 1000Base-SX (850nm, Multi Mode Fiber) (25510478) | Ethernet | [8 empty] | Sandra Cary 1-618-943-8000 Sandra_Cary@UnitedHealthone.com | JAVIER SEGUI | javier.segui@optum.com | 1-407-541-8143 | 12/22/2017(Private IP - PIP) 12/22/2017(Access) |  |  | 11/15/2017 11/21/2017 | 12/22/2017 | 12/22/2017 (25510477) 12/22/2017 (25510479) 12/22/2017 (25510478) | Cancelled | N (25510477) N (25510479) N (25510478) | U0101953 |  | NSPE0011627577 Order Request # 194583961 | NSPE0011627577
Cancelled | FL219-02-IM Stuart FL | 2151 SE FEDERAL HWY STUART, FL 34994-4514 US | 50 MBPS (25591506) | 11/03/2017: 11/02 Cancelled. Reissued under NSPE0011710499 Order Request # 194688844 Service Order # 194690281 | 194623108 | FL219-02-IM | Private IP - PIP (25591505) WAN Analysis Reporting (25591507) Access (25591506) | 25591505 25591507 25591506 | 10 MBPS (25591505) |  | 196007110 (Private IP (PIP)) 196007111 (WAN Analysis Reporting) 196007108 (Access) | C4008959/CANCEL (25591505) C4008959/ADD (25591505) E4024299/ADD (25591506) E4024299/CANCEL (25591506) |  | 5927328 | 5500 | PVC ID : 5927328 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64886 PE IP Address : 152.164.65.133 CE Address : 152.164.65.134 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25591506) | 1000Base-SX (850nm, Multi Mode Fiber) (25591506) | Ethernet |  |  |  |  | 11/30/2017 (VFORCE) (25591506) |  |  |  | MIKE NELSON 1-210-951-3126 minelson@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 11/10/2017(Private IP - PIP) 11/10/2017(Access) |  |  | 11/28/2017 12/04/2017 | 11/10/2017 | 11/02/2017 (25591505) 11/02/2017 (25591507) 11/10/2017 (25591506) | Cancelled | N (25591505) N (25591507) N (25591506) | U0101953 | Jeopardy Notification 2 (10/31/2017) | NSPE0011669595 Order Request # 194622882 | NSPE0011669595
Cancelled | FL038-05-IJ Miami FL | 2960 SW 8TH ST STE 2970 MIAMI, FL 33135-2827 US | 50 MBPS (25689870) | 11/27/2017: Reissued under Order Request # 194737838 Service Order # 194737933 | 194676152 | FL038-05-IJ Miami FL | Private IP - PIP (25689869) WAN Analysis Reporting (25689871) Access (25689870) | 25689869 25689871 25689870 | 10 MBPS (25689869) |  | 197430034 (Private IP (PIP)) 197430035 (WAN Analysis Reporting) 197430032 (Access) | C4009179/ADD (25689869) C4009179/CANCEL (25689869) E4024783/CANCEL (25689870) E4024783/ADD (25689870) |  | 5931276 | 4000 | PVC ID : 5931276 VPN Name : UnitedHealthGroup Router Name : POBXE03 VRF Name : V632425-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65255 PE IP Address : 152.162.6.221 CE Address : 152.162.6.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25689870) | 1000Base-SX (850nm, Multi Mode Fiber) (25689870) | Ethernet | [8 empty] | CRISTY ALFONSO 1-305-631-3000 calfonso@pcpmedicalgroup.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 11/29/2017(Private IP - PIP) 11/29/2017(Access) |  |  | 12/12/2017 12/18/2017 | 11/29/2017 | 11/27/2017 (25689869) 11/27/2017 (25689871) 11/29/2017 (25689870) | Cancelled Managed | N (25689869) N (25689871) N (25689870) | U0101953 |  | NSPE0011696665 Order Request # 194670727 | NSPE0011696665
Cancelled | NV095-02-IM Henderson, NV | 3157 SAINT ROSE PKWY STE 200 HENDERSON, NV 89052-3500 US | 3 MBPS (25878031) | 12/04/2017: 12/04 Background: NV095-02-IM Henderson, NV; New 2xT1 3.072M MLPPP; CTL; No NID; No MNS; Status: Pending address confirmation Next action: To be provisioned Who owns the next action: Prov Ticket: NA | 194773653 | NV095-02-IM | Private IP - PIP (25878030) WAN Analysis Reporting (25878032) Access (25878031) | 25878030 25878032 25878031 | 3 MBPS (25878030) |  | 201700260 (Private IP (PIP)) 201700261 (WAN Analysis Reporting) 201700258 (Access) | C1064652/CANCEL (25878030) C1064652/ADD (25878030) N1041292/CANCEL (25878031) N1041293/CANCEL (25878031) N1041293/ADD (25878031) N1041292/ADD (25878031) |  | 5939928 | 1500 | PVC ID : 5939928 VPN Name : UnitedHealthGroup Router Name : RTO3E01 VRF Name : Vb30675-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65230 PE IP Address : 152.176.223.29 CE Address : 152.176.223.30 QoS - Egress Profile: R12 |  | DS1 (25878031) | TDM | [8 empty] | Nestor Romo 1-702-750-3727 nestor_romo@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 12/07/2017(Private IP - PIP) 12/07/2017(Access) |  |  | 12/22/2017 12/29/2017 | 12/08/2017 | 12/07/2017 (25878030) 12/07/2017 (25878032) 12/07/2017 (25878031) | Cancelled | N (25878030) N (25878032) N (25878031) | U0101953 |  | NSPE0011765273 Order Request # 194773465 | NSPE0011765273
Cancelled | NV095-02-IM Henderson, NV | 3175 SAINT ROSE PKWY STE 200 HENDERSON, NV 89052-3507 US | 3 MBPS (25900404) | 12/14/2017: 12/11 Customer requested to cancel this request | 194785151 | 3175 ST ROSE PARKWAY, SUITE 200 | Private IP - PIP (25900403) WAN Analysis Reporting (25900405) Access (25900404) | 25900403 25900405 25900404 | 3 MBPS (25900403) |  | 202279120 (Private IP (PIP)) 202279121 (WAN Analysis Reporting) 202279118 (Access) | C1064980/ADD (25900403) C1064980/CANCEL (25900403) N1041341/CANCEL (25900404) N1041341/ADD (25900404) N1041340/ADD (25900404) N1041340/CANCEL (25900404) |  | 5941059 | 1500 | PVC ID : 5941059 VPN Name : UnitedHealthGroup Router Name : RTOGE06 VRF Name : Vb31977:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65230 PE IP Address : 199.220.97.217 CE Address : 199.220.97.218 QoS - Egress Profile: R12 |  | DS1 (25900404) | TDM | [8 empty] | NESTOR ROMO 1-702-750-3727 nestor_romo@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 12/15/2017(Private IP - PIP) 12/15/2017(Access) |  | 12/22/2017 (25900403) 12/20/2017 (25900404) | 12/28/2017 01/03/2018 | 12/15/2017 | 12/11/2017 (25900403) 12/11/2017 (25900405) 12/15/2017 (25900404) | Cancelled | N (25900403) N (25900405) N (25900404) | U0101953 |  | NSPE0011773486 Order Request # 194784816 | NSPE0011773486
Cancelled | AL016-05-IM Tuscaloosa, AL | 305 PAUL W BRYANT DR E TUSCALOOSA, AL 35401-2055 US | 100 MBPS (25941358) | 01/18/2018: 01/12 Reissued under Service Order # 194808999 | 194808999 | AL016-05-IM | WAN Analysis Reporting (25941359) Private IP - PIP (25941357) Access (25941358) | 25941359 25941357 25941358 | 20 MBPS (25941357) |  | 203522872 (WAN Analysis Reporting) 203522871 (Private IP (PIP)) 203522869 (Access) | E4025989/CANCEL (25941358) E4025989/ADD (25941358) C1065219/ADD (25941357) C1065219/CANCEL (25941357) |  | 5942857 | 10000 | PVC ID : 5942857 VPN Name : UnitedHealthGroup Router Name : B6S9E01 VRF Name : Vb34594:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64651 PE IP Address : 152.162.50.21 CE Address : 152.162.50.22 QoS - Egress Profile: R12 | 1000Base-SX-850nm (25941358) | 1000Base-SX (850nm, Multi Mode Fiber) (25941358) | Ethernet | [8 empty] | Ava Tidwell 1-205-345-4566 atidwell@nphc.net | Jason Salaping | jason_salaping@optum.com | 1-612-916-7253 |  |  | 01/19/2018 (25941358) 01/23/2018 (25941357) | 01/29/2018 01/23/2018 | 01/18/2018 | 01/12/2018 (25941359) 01/12/2018 (25941357) 01/18/2018 (25941358) | Cancelled | N (25941359) N (25941357) N (25941358) | U0101953 |  | NSPE0011789247 Order Request # 194808658 | NSPE0011789247
Cancelled | NY078-07-IM Flushing, NY | 13602 ROOSEVELT AVE FLUSHING, NY 11354-5510 US | 50 MBPS | 03/15/2018: Background: NY078-07-IM Flushing, NY; New 10M/50M PIP-Eth; No NID; No MNS; (Existing C1023310) Status: Pending Site readiness (EUCR) and return of signed ROE. , VZ working on run from man hole to MPOE. Sent FF to customer and OPSE on ETA for work completion. STAGED12/29/17 -- ROE SENT TO CUST 02/08/18. ... Next action: Completion of site works/Order submission | 194844452 | UNITEDHEALTH GROUP | Access Private IP - PIP WAN Analysis Reporting |  | 10 MBPS |  | 205270427 205270429 205270430 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | KEVIN CANTOR 632-588-5331 kevin_cantor@optum.com | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 |  |  |  | 01/22/2018 01/26/2018 |  |  |  | N | U0101953 |  | NSPE0011813855 Order Request # 194844266 | NSPE0011813855
Cancelled | VA729-02-IM Ashburn, VA | 44480 HASTINGS DR ASHBURN, VA 20147-6043 US | 1 GBPS (26108638) | 01/30/2018: 01/30 Background: VA729-02-IM Ashburn, VA; New 500M/1G PIP-Eth; VzB; No NID; No MNS; Status: Order reissued under Service Order ID 194927993 Next action: NA Who owns the next action: NA Ticket: NA | 194888306 | VA729-02-IM | Private IP - PIP (26108637) WAN Analysis Reporting (26108639) Access (26108638) | 26108637 26108639 26108638 | 500 MBPS (26108637) |  | 207365861 (Private IP (PIP)) 207365862 (WAN Analysis Reporting) 207365859 (Access) | C0136149/ADD (26108637) C0136149/CANCEL (26108637) E5009598/ADD (26108638) E5009598/CANCEL (26108638) |  | 5949511 | 35000 | PVC ID : 5949511 VPN Name : UnitedHealthGroup Router Name : WA39E01 VRF Name : V452868:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64918 PE IP Address : 206.115.120.13 CE Address : 206.115.120.14 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (26108638) | Ethernet | [8 empty] | Edward Jones 1-719-425-4044 Edward.jones@optum.com | Edward Jones | Edward.jones@optum.com | 1-719-425-4044 |  |  |  | 02/22/2018 02/28/2018 | 01/30/2018 | 01/30/2018 (26108637) 01/30/2018 (26108639) 01/30/2018 (26108638) | Cancelled | N (26108637) N (26108639) N (26108638) | U0101953 |  | NSPE0011845805 Order Request # 194886990 | NSPE0011845805
Cancelled | UMN9E-02-IM Chaska, MN | 1707 W CREEK LN CHASKA, MN 55318-1891 US |  | 02/20/2018: 02/20 Cancelled and reissued under TIN 9452415 | 194906446 | Chaska Data Center ICM T1 | Private IP - PIP (26143687) Access (26143688) | 26143687 26143688 | 200 MBPS (26143687) |  | 208192491 (Private IP (PIP)) 208192489 (Access) | C1066649/CANCEL (26143687) C1066649/ADD (26143687) E5009729/CANCEL (26143688) E5009729/ADD (26143688) | fs73c 73c 0002 (I0039003.MIN) | 5951008 | 50000 | PVC ID : 5951008 VPN Name : UHG-OFE Router Name : MZZ9E01 VRF Name : Vb77349:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64987 PE IP Address : 68.137.199.77 CE Address : 68.137.199.78 QoS - Egress Profile: C1 |  | 1000Base-LX (1310nm Single Mode Fiber) (26143688) | Ethernet | [8 empty] | TOM KRENN 1-763-744-3141 tom_krenn@optum.com | TOM KRENN | tom_krenn@optum.com | 1-763-744-3141 |  |  | 02/20/2018 (26143687) 02/20/2018 (26143688) | 02/15/2018 | 02/21/2018 | 02/20/2018 (26143687) 02/21/2018 (26143688) |  | N (26143687) N (26143688) | U0101953 |  | NSPE0011857372 Order Request # 194902050 C1 | NSPE0011857372
Cancelled | UMN9D-02-IM Plymouth, MN | 6150 TRENTON LN N PLYMOUTH, MN 55442-3240 US |  | 02/20/2018: 02/20 Cancelled and reissued under TIN 9452471 | 194906471 | UNITED HEALTH GROUP | Private IP - PIP (26143693) Access (26143694) | 26143693 26143694 | 200 MBPS (26143693) |  | 208192494 (Private IP (PIP)) 208192492 (Access) |  |  | 5951007 |  | PVC ID : 5951007 |  | 1000Base-LX (1310nm Single Mode Fiber) (26143694) | Ethernet | [8 empty] | TOM KRENN 1-763-744-3141 tom_krenn@optum.com | TOM KRENN | tom_krenn@optum.com | 1-763-744-3141 |  |  |  | 02/15/2018 | 02/20/2018 | 02/20/2018 (26143693) 02/20/2018 (26143694) |  | N (26143693) N (26143694) | U0101953 |  | NSPE0011857372 Order Request # 194902050 C1 | NSPE0011857372
Cancelled | Partial Disconnect of LD PRI | 10801 WALKER ST CYPRESS, CA 906305043 USA | 0 KBPS (OQBLK3J5) | 02/06/2018: SPM request cancel tin for partial disco- order no longer needed. OM to submit sup to cancel | 9418640 |  | Dedicated Long Distance (OQBLK3J5) | OQBLK3J5 | 0 KBPS (OQBLK3J5) | N5920164 |  | IBBH947D0024 (OQBLK3J5) IBBH947D0025 (OQBLK3J5) IBBH947D0026 (OQBLK3J5) IBBH947D0027 (OQBLK3J5) IBBH947D0028 (OQBLK3J5) IBBH947D0029 (OQBLK3J5) IBBH947D0030 (OQBLK3J5) IBBH947D0031 (OQBLK3J5) IBBH947D0032 (OQBLK3J5) IBBH947D0033 (OQBLK3J5) IBBH947D0034 (OQBLK3J5) IBBH947D0035 (OQBLK3J5) IBBH947D0036 (OQBLK3J5) IBBH947D0037 (OQBLK3J5) IBBH947D0038 (OQBLK3J5) IBBH947D0039 (OQBLK3J5) IBBH947D0040 (OQBLK3J5) IBBH947D0041 (OQBLK3J5) IBBH947D0042 (OQBLK3J5) IBBH947D0043 (OQBLK3J5) IBBH947D0044 (OQBLK3J5) IBBH947D0045 (OQBLK3J5) IBBH947D0046 (OQBLK3J5) IDBH947D0048 (OQBLK3J5) | [15 empty] | SUSAN WAGNER 0017147616459 | [5 empty] | 02/13/2018 (OQBLK3J5) | 02/13/2018 (OQBLK3J5) |  |  |  | N (OQBLK3J5) | 05118490 |  | NSPE0011801542 | NSPE0011801542
Cancelled | CA269-02-IJ Los Angeles, CA; New 10M/50M PIP-Eth | 1902 MARENGO ST STE 200 LOS ANGELES, CA 90033-1382 US | 50 MBPS (26313303) | 02/26/2018: 02/26 Order cancelled as per customer request. | 195004749 | Optum RX | Private IP - PIP (26313302) WAN Analysis Reporting (26313304) Access (26313303) | 26313302 26313304 26313303 | 10 MBPS (26313302) |  | 212853201 (Private IP (PIP)) 212853202 (WAN Analysis Reporting) 212853199 (Access) | C4010617/ADD (26313302) C4010617/CANCEL (26313302) E4027814/ADD (26313303) E4027814/CANCEL (26313303) |  | 5958285 | 8 | PVC ID : 5958285 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65092 PE IP Address : 152.187.47.213 CE Address : 152.187.47.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26313303) | 1000Base-SX (850nm, Multi Mode Fiber) (26313303) | Ethernet | [8 empty] | Salina Yip 1-323-227-4646 salina.yip@briovarx.com | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 02/28/2018(Private IP - PIP) 02/28/2018(Access) |  |  | 07/05/2018 07/11/2018 | 02/28/2018 | 02/26/2018 (26313302) 02/26/2018 (26313304) 02/28/2018 (26313303) | Cancelled | N (26313302) N (26313304) N (26313303) | U0101953 |  | NSPE0011923040 Order Request # 195003821 | NSPE0011923040
Cancelled | UNJ23-02-IM Newark, NJ | 2 GATEWAY CTR NEWARK, NJ 07102-5005 US | 50 MBPS | 03/17/2018: Order cancelled 3/1 per Customer's request | 195046580 | UNITED HEALTHCARE | Access WAN Analysis Reporting Private IP - PIP |  | 10 MBPS |  | 216012203 216012206 216012205 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Ryan Cameron 1-404-308-5876 RyanE.Cameron@am.jll.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  |  | 03/27/2018 04/02/2018 |  |  |  | N | U0101953 |  | NSPE0011946646 Order Request # 195044160 | NSPE0011946646
Cancelled | CA269-04-IM Irwindale, CA | 4900 RIVERGRADE RD STE E100 IRWINDALE, CA 91706-1401 US | 50 MBPS (26376990) | 04/12/2018: UHG request cancellation of order; ROE will not be signed. | 195048120 | Optum RX | Access (26376990) WAN Analysis Reporting (26376991) Private IP - PIP (26376989) | 26376990 26376991 26376989 | 10 MBPS (26376989) |  | 216149772 (Access) 216149775 (WAN Analysis Reporting) 216149774 (Private IP (PIP)) | E4028171/ADD (26376990) E4028171/CANCEL (26376990) C4010746/ADD (26376989) C4010746/CANCEL (26376989) |  | 5962566 | 7000 | PVC ID : 5962566 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65092 PE IP Address : 152.187.70.17 CE Address : 152.187.70.18 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26376990) | 1000Base-SX (850nm, Multi Mode Fiber) (26376990) | Ethernet |  |  |  |  | 12/17/2018 (VFORCE) (26376990) |  |  |  | Paul Kelsey 1-949-929-9934 paul.kelsey@am.jll.com | JASON SALAPING | jason_salaping@gmail.com | 1-210-862-6784 | 04/16/2018(Access) 04/16/2018(Private IP - PIP) |  |  | 07/24/2018 07/30/2018 | 04/16/2018 | 04/16/2018 (26376990) 04/12/2018 (26376991) 04/12/2018 (26376989) | Cancelled | N (26376990) N (26376991) N (26376989) | U0101953 | Jeopardy Notification 2 (04/10/2018) | NSPE0011948957 Order Request # 195047654 | NSPE0011948957
Cancelled | FL243-02-IM Fort Meyers, FL | 10650 METRO PKWY STE 100 FORT MYERS, FL 33966-1107 US | 50 MBPS (26419014) | 05/17/2018: 05/08 Cancelled. | 195072600 | FL243-02-IM Fort Myers, FL | Private IP - PIP (26419013) WAN Analysis Reporting (26419015) Access (26419014) | 26419013 26419015 26419014 | 50 MBPS (26419013) |  | 217105295 (Private IP (PIP)) 217105296 (WAN Analysis Reporting) 217105293 (Access) | C4010913/ADD (26419013) C4010913/CANCEL (26419013) E4028581/ADD (26419014) E4028581/CANCEL (26419014) |  | 5964979 | 5000 | PVC ID : 5964979 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65081 PE IP Address : 152.176.20.93 CE Address : 152.176.20.94 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26419014) | 1000Base-SX (850nm, Multi Mode Fiber) (26419014) | Ethernet |  |  |  |  | 05/17/2018 (VFORCE) (26419014) |  |  |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | SUSHIL GAUTAM | sushil_gautam@uhc.com | 1-612-855-7475 | 05/22/2018(Private IP - PIP) 05/22/2018(Access) |  |  | 05/10/2018 05/16/2018 | 05/22/2018 | 05/08/2018 (26419013) 05/08/2018 (26419015) 05/22/2018 (26419014) | Cancelled | N (26419013) N (26419015) N (26419014) | U0101953 | Jeopardy Notification 3 (04/24/2018) | NSPE0011963735 Order Request # 195069050 | NSPE0011963735
Cancelled | FL273-02-IM Lutz, FL | 15953 N FLORIDA AVE LUTZ, FL 33549-8102 US | 50 MBPS (26445422) | 03/21/2018: Background: FL273-02-IM Lutz, FL; New 10M/50M PIP-Eth; Frontier; NID; No MNS; Status: ASR 03/14, Pending FOC Next action: Circuit delivery Who owns the next action: Frontier | 195089563 | FL273-02-IM Lutz, FL | Access (26445422) Private IP - PIP (26445421) WAN Analysis Reporting (26445423) | 26445422 26445421 26445423 | 50 MBPS (26445421) |  | 218294553 (Access) 218294555 (Private IP (PIP)) 218294556 (WAN Analysis Reporting) | E4028864/CANCEL (26445422) E4028864/ADD (26445422) C4011110/CANCEL (26445421) C4011110/ADD (26445421) |  | 5966479 | 5000 | PVC ID : 5966479 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65082 PE IP Address : 152.161.222.181 CE Address : 152.161.222.182 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (26445422) | 1000Base-SX (850nm, Multi Mode Fiber) (26445422) | Ethernet |  |  |  |  | 04/25/2018 (VFORCE) (26445422) |  |  |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | SUSHIL GAUTAM | sushil_gautam@uhc.com | 1-612-855-7475 |  |  |  | 04/23/2018 04/27/2018 | 03/27/2018 | 03/27/2018 (26445422) 03/23/2018 (26445421) 03/23/2018 (26445423) | Cancelled | N (26445422) N (26445421) N (26445423) | U0101953 |  | NSPE0011977573 Order Request # 195088932 | NSPE0011977573
Cancelled | FL220 Orlando, FL | 5142 CLARETON DR STE 160 AGOURA HILLS, CA 91301-4528 US | 1 GBPS (26626218) |  | 195212369 | Aguora Hills--5142 | Access (26626218) | 26626218 |  |  | 204765015 (Access) | [5 empty] | 1000Base-T (26626218) | 1000Base-T (26626218) | Ethernet | [8 empty] | Franz Schiffman 1-818-665-3474 franz.schiffmann@delphi.com | CHRISTINE DELHOUGNE | christine.delhougne@delphi.com | 3-525-018-2205 |  |  |  | 05/23/2018 | 04/16/2018 | 04/16/2018 (26626218) |  | N (26626218) | U0167179 |  | NSPE0012031781; Order Request # 195169894 | NSPE0012047631
Cancelled | Pharr, TX | 1100 W SAM HOUSTON BLVD PHARR, TX 78577-5104 US | 50 MBPS (26710652) | 10/04/2018: Background: Pharr, TX 10M/50M PIP-Eth TWC NID No MNS Status: Order supped to cancel due to incorrect address. Customer agreed to re-issue order using address: 1104 W SAM HOUSTON BLVD, PHARR, TX 78577-5104. | 195298033 | Location18801835863 | WAN Analysis Reporting (26710653) Access (26710652) Private IP - PIP (26710651) | 26710653 26710652 26710651 | 10 MBPS (26710651) |  | 94518427 (WAN Analysis Reporting) 94518425 (Access) 94518429 (Private IP (PIP)) | C4011825/ADD (26710651) C4011825/CANCEL (26710651) E4030500/CANCEL (26710652) E4030500/ADD (26710652) |  | 5977577 | 5000 | PVC ID : 5977577 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64914 PE IP Address : 152.176.181.249 CE Address : 152.176.181.250 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26710652) | 1000Base-SX (850nm, Multi Mode Fiber) (26710652) | Ethernet |  |  |  |  | 10/30/2018 (VFORCE) (26710652) |  |  |  | JASON OZER 1-121-095-1325 jozer@wellmed.net | KATHERINE ACAIN | katherine_acain@optum.com | 1-763-744-2114 | 10/10/2018(Private IP - PIP) 10/10/2018(Access) |  | 09/19/2018 (26710651) 09/17/2018 (26710652) | 08/06/2018 07/31/2018 | 10/10/2018 | 10/04/2018 (26710653) 10/10/2018 (26710652) 10/04/2018 (26710651) | Cancelled | N (26710653) N (26710652) N (26710651) | U0101953 |  | NSPE0012066631 Order Request # 195266125 | NSPE0012066631
Cancelled | AZ073-02-IM Phoenix, AZ | 7910 W THOMAS RD PHOENIX, AZ 85033-4830 US | 10 MBPS (26817396) | 05/15/2018: UHG request cancel order | 195398367 | AZ073-02-IM | Private IP - PIP (26817395) WAN Analysis Reporting (26817397) Access (26817396) | 26817395 26817397 26817396 | 10 MBPS (26817395) |  | 94524359 (Private IP (PIP)) 94524364 (WAN Analysis Reporting) 94524362 (Access) | C0144199/ADD (26817395) C0144199/CANCEL (26817395) E3053136/ADD (26817396) E3053136/CANCEL (26817396) |  | 5981069 | 5500 | PVC ID : 5981069 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : V880743:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65024 PE IP Address : 68.139.248.189 CE Address : 68.139.248.190 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26817396) | 1000Base-SX (850nm, Multi Mode Fiber) (26817396) | Ethernet |  |  |  |  | 06/13/2018 (VFORCE) (26817396) |  |  |  | JASON ENGEL 1-130-359-4112 jason_engel@uhg.com | KEVIN CANTOR | kevin_cantor@optum.com | 1-763-744-2114 |  |  | 05/30/2018 (26817395) 05/25/2018 (26817396) | 06/19/2018 06/25/2018 | 05/21/2018 | 05/14/2018 (26817395) 05/14/2018 (26817397) 05/21/2018 (26817396) | Cancelled | N (26817395) N (26817397) N (26817396) | U0101953 |  | NSPE0012103837 Order Request # 195385965 | NSPE0012103837
Cancelled |  | 13655 RIVERPORT DR MARYLAND HEIGHTS, MO 63043-4812 US | 200 MBPS (26873291) |  | 195473023 | UMO15-08-IJ Maryland Heights | Internet Dedicated Services (26873290) Access (26873291) | 26873290 26873291 | 100 MBPS (26873290) |  | 94526136 (Internet Dedicated Services) 94526139 (Access) | [5 empty] | 1000Base-T (26873291) | 1000Base-T (26873291) | Ethernet | [8 empty] | Robert Skebo 1-314-592-7082 robert_skebo@uhg.com | VAISHNA PRIYA | vaishna@optum.com | 1-612-763-2114 | 05/16/2018(Internet Dedicated Services) 05/16/2018(Access) |  |  | 06/26/2018 | 05/16/2018 | 05/16/2018 (26873290) 05/16/2018 (26873291) |  | N (26873290) N (26873291) | U0101953 |  | NSPE0012126272 Order Request # 195472363 | NSPE0012126272
Cancelled | TX422-02-IM Dallas, TX | 3199 W CAMP WISDOM RD DALLAS, TX 75237-2603 US | 50 MBPS (26895256) | 05/31/2018: 05/31 Background: TX422-02-IM Wellmed Dallas, TX; New 10M/50M PIP-Eth; AT&T; NID; No MNS; Status: Pending loop delivery date. Escalation ticket has been raised. Next action: Circuit delivery Who owns the next action: AT&T Ticket: C201805314006 | 195503923 | TX422-02-IM Wellmed | Private IP - PIP (26895255) WAN Analysis Reporting (26895257) Access (26895256) | 26895255 26895257 26895256 | 10 MBPS (26895255) |  | 94530153 (Private IP (PIP)) 94530158 (WAN Analysis Reporting) 94530155 (Access) | C4012399/ADD (26895255) C4012399/CANCEL (26895255) E4032031/ADD (26895256) E4032031/CANCEL (26895256) |  | 5982978 | 5500 | PVC ID : 5982978 VPN Name : UnitedHealthGroup Router Name : RCN3E02 VRF Name : V454456-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64811 PE IP Address : 68.138.4.157 CE Address : 68.138.4.158 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26895256) | 1000Base-SX (850nm, Multi Mode Fiber) (26895256) | Ethernet |  |  |  |  | 06/15/2018 (VFORCE) (26895256) |  |  |  | Lizdeli Guerrido 1-210-762-3635 lguerrido@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 1-763-744-2114 | 06/07/2018(Private IP - PIP) 06/07/2018(Access) |  |  | 06/28/2018 07/04/2018 | 06/07/2018 | 06/06/2018 (26895255) 06/06/2018 (26895257) 06/07/2018 (26895256) | Cancelled | N (26895255) N (26895257) N (26895256) | U0101953 |  | NSPE001213 Order Request # 195502865 | NSPE0012133138
Cancelled | Sandy, UT | 1403 E SEGO LILY DR SANDY, UT 84092-4350 US | 20 MBPS (26915561) | 08/02/2018: Order cancelled | 195549425 | Pico UT019-01-IM | Private IP - PIP (26915560) WAN Analysis Reporting (26915562) Access (26915561) | 26915560 26915562 26915561 | 10 MBPS (26915560) |  | 94532630 (Private IP (PIP)) 94532633 (WAN Analysis Reporting) 94532628 (Access) | C3018724/CANCEL (26915560) C3018724/ADD (26915560) E3053638/ADD (26915561) E3053638/CANCEL (26915561) |  | 5983732 | 5500 | PVC ID : 5983732 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64833 PE IP Address : 152.177.134.77 CE Address : 152.177.134.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26915561) | 1000Base-SX (850nm, Multi Mode Fiber) (26915561) | Ethernet |  |  |  |  | 08/14/2018 (VFORCE) (26915561) |  |  |  | Darrick Porter 1-801-870-4617 darrick@bigtreeconst.com | GLENN MOORE | glenn_moore@optum.com | 1-176-374-4098 | 08/07/2018(Private IP - PIP) 08/07/2018(Access) |  |  | 08/22/2018 08/28/2018 | 08/07/2018 | 08/02/2018 (26915560) 08/02/2018 (26915562) 08/07/2018 (26915561) | Cancelled | N (26915560) N (26915562) N (26915561) | U0101953 | Jeopardy Notification 1 (07/05/2018) | NSPE0012138640 Order Request # 195544133 | NSPE0012138640
Cancelled | West Valley, UT | 4071 S 4000 W WEST VALLEY, UT 84120-4143 US | 20 MBPS (26915539) | 06/07/2018: Cust request cancel order | 195549481 | UT021-01-IM Pico | Private IP - PIP (26915538) WAN Analysis Reporting (26915540) Access (26915539) | 26915538 26915540 26915539 | 10 MBPS (26915538) |  | 94532471 (Private IP (PIP)) 94532475 (WAN Analysis Reporting) 94532477 (Access) | C3018723/CANCEL (26915538) C3018723/ADD (26915538) E3053637/ADD (26915539) E3053637/CANCEL (26915539) |  | 5983731 | 5500 | PVC ID : 5983731 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64847 PE IP Address : 152.162.97.53 CE Address : 152.162.97.54 QoS - Egress Profile: R12 | 1000Base-SX-850nm (26915539) | 1000Base-SX (850nm, Multi Mode Fiber) (26915539) | Ethernet |  |  |  |  | 06/19/2018 (VFORCE) (26915539) |  |  |  | Jason Magid 1-203-494-5904 Jason_Magid@uhg.com | DAVID CASANOVA | david_casanova@optum.com | 1-176-374-4158 | 06/11/2018(Private IP - PIP) 06/11/2018(Access) |  |  | 07/02/2018 07/06/2018 | 06/11/2018 | 06/07/2018 (26915538) 06/07/2018 (26915540) 06/11/2018 (26915539) | Cancelled | N (26915538) N (26915540) N (26915539) | U0101953 |  | NSPE0012138749 Order Request # 195544733 | NSPE0012138749
Cancelled | Remove removed WAN reporting and ETM. No other changes. | 505 N BRAND BLVD GLENDALE, CA 91203-1906 US | 7.7 MBPS (27109849) | 07/12/2018: Order Cancelled Background: Remove removed WAN reporting and ETM. No other changes. | 195918449 | UNITED HEALTH-GLENDALE | Private IP - PIP (27109848) WAN Analysis Reporting (27109850) Access (27109849) | 27109848 27109850 27109849 | 7.7 MBPS (27109848) |  | 87492503 (Private IP (PIP)) 87499336 (WAN Analysis Reporting) 87495772 (Access) | C0129539/NONE (27109848) N3009901/NONE (27109849) N3009902/NONE (27109849) N3009899/NONE (27109849) N3009903/NONE (27109849) N3009900/NONE (27109849) |  | 1977560 |  | PVC ID : 1977560 |  | DS1 (27109849) | TDM | [8 empty] | John Sergot 1-763-744-3000 john_sergot@uhc.com | John Sergot | john_sergot@uhc.com | 1-763-744-3000 |  |  | 06/20/2018 (27109848) 06/20/2018 (27109849) | 07/10/2018 07/18/2018 | 07/20/2018 | 07/09/2018 (27109848) 07/09/2018 (27109850) 07/20/2018 (27109849) | Cancelled | N (27109848) N (27109850) N (27109849) | U0101953 |  | NSPE0012190409 Order Request # 195910067 | NSPE0012190409
Cancelled | UT016-02-IM Draper, UT | 13961 S MINUTEMAN DR STE 330 DRAPER, UT 84020-8086 US | 50 MBPS (27381434) | 08/09/2018: Background: UT016-02-IM Draper, UT; New 20M/50M PIP-Eth; XO Comm; NID; No MNS; Status FOC 8/30 | 196245621 | UT016-02-IM | Private IP - PIP (27381433) WAN Analysis Reporting (27381435) Access (27381434) | 27381433 27381435 27381434 | 20 MBPS (27381433) |  | 94554835 (Private IP (PIP)) 94554832 (WAN Analysis Reporting) 94554830 (Access) | C4013613/CANCEL (27381433) C4013613/ADD (27381433) E4034809/ADD (27381434) E4034809/CANCEL (27381434) |  | 5997016 | 13000 | PVC ID : 5997016 VPN Name : UnitedHealthGroup Router Name : SLY9E01 VRF Name : V400098:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65058 PE IP Address : 68.139.245.165 CE Address : 68.139.245.166 QoS - Egress Profile: R12 | 100Base-FX (27381434) | 100Base-FX (1310nm, Multi Mode Fiber) (27381434) | Ethernet |  |  |  |  | 08/23/2018 (VFORCE) (27381434) |  |  |  | Geronimo Arbutante 1-612-274-3897 garbutante@savvysherpa.com | TONY EPPERSON EPPERSON | tony.epperson@optum.com | 1-131-231-5561 | 08/20/2018(Private IP - PIP) 08/20/2018(Access) |  | 09/11/2018 (27381433) 09/07/2018 (27381434) | 09/10/2018 09/14/2018 | 08/20/2018 | 08/17/2018 (27381433) 08/17/2018 (27381435) 08/20/2018 (27381434) | Cancelled | N (27381433) N (27381435) N (27381434) | U0101953 |  | NSPE0012283729 Order Request # 196233575 | NSPE0012283729
Cancelled | ENT NH011 Portsmouth | 170 COMMERCE WAY PORTSMOUTH, NH 03801-3226 US | 50 MBPS (27514937) | 10/18/2018: 10/18 - Background: ENT NH011 Portsmouth, NH; New 10M/50M PIP-Eth; FirstLight/Oxford Networks; NID; No MNS; Status: Per customer cancel order as of 10/16. | 196601425 | ENT NH011 Portsmouth | Private IP - PIP (27514936) WAN Analysis Reporting (27514938) Access (27514937) | 27514936 27514938 27514937 | 10 MBPS (27514936) |  | 94561140 (Private IP (PIP)) 94561142 (WAN Analysis Reporting) 94561138 (Access) | C4013931/ADD (27514936) C4013931/CANCEL (27514936) E4035653/ADD (27514937) E4035653/CANCEL (27514937) |  | 6001640 | 5500 | PVC ID : 6001640 VPN Name : UnitedHealthGroup Router Name : CHTXE03 VRF Name : V637075-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64808 PE IP Address : 68.138.241.197 CE Address : 68.138.241.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27514937) | 1000Base-SX (850nm, Multi Mode Fiber) (27514937) | Ethernet |  |  |  |  | 01/15/2019 (VFORCE) (27514937) |  |  |  | Beth Nault 1-603-422-9017 Beth.Nault@optum.com | Charlie Evangelio | charlie_evangelio@optum.com | 632-588-3409 | 10/18/2018(Private IP - PIP) 10/18/2018(Access) |  | 11/08/2018 (27514936) 11/06/2018 (27514937) | 10/17/2018 10/23/2018 | 10/18/2018 | 10/16/2018 (27514936) 10/16/2018 (27514938) 10/18/2018 (27514937) | Cancelled | N (27514936) N (27514938) N (27514937) | U0101953 |  | NSPE0012332737 | NSPE0012332737
Cancelled | CA769-03-IM Downey, CA | 11525 BROOKSHIRE AVE STE 300 DOWNEY, CA 90241-4982 US | 50 MBPS (27533596) | 05/29/2019: 5/29Background: CA769-03-IM Downey, CA; New 20M/50M PIP-Eth; (TWC); NID; No MNS; 898 Status: Customer requested to have order cancelled Next Action: Pending cancellation | 196624995 | CA769-03-IM | Private IP - PIP (27533595) WAN Analysis Reporting (27533597) Access (27533596) | 27533595 27533597 27533596 | 20 MBPS (27533595) |  | 94561657 (Private IP (PIP)) 94561655 (WAN Analysis Reporting) 94561653 (Access) | C4014118/ADD (27533595) C4014118/CANCEL (27533595) E4035748/ADD (27533596) E4035748/CANCEL (27533596) |  | 6002299 | 13000 | PVC ID : 6002299 VPN Name : UnitedHealthGroup Router Name : LSA29E01 VRF Name : V461763:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64836 PE IP Address : 152.177.64.253 CE Address : 152.177.64.254 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27533596) | 1000Base-SX (850nm, Multi Mode Fiber) (27533596) | Ethernet |  |  |  |  | 06/07/2019 (VFORCE) (27533596) |  |  |  | Sean Igarta 1-714-443-4534 Sean.Igarta@applecaremedical.com | Ranjit Adhikari | ranjit_adhikari@optum.com | 1-763-744-1957 |  |  | 03/06/2019 (27533595) 03/04/2019 (27533596) | 01/11/2019 01/17/2019 | 05/29/2019 | 05/28/2019 (27533595) 05/28/2019 (27533597) 05/29/2019 (27533596) | Cancelled | N (27533595) N (27533597) N (27533596) | U0101953 |  | NSPE0012337028 Order Request # 196623691 | NSPE0012337028
Cancelled | TX410-06-IM Kyle, TX | 830 KOHLERS XING KYLE, TX 78640 USA | 1.536 MBPS (IQBLNJ9T) | 12/13/2018: 12/13 Background: TX410-06-IM Kyle, TX; New 10.5M MLPPP; (Frontier); No NID; No MNS; Status: SCON received; Customer will not proceed with order. Pending cancellation Next action: Pending Cancelation | 9710466 |  | Private IP (IQBLNJ9T) EVC/PVC Service (N.11836564.6011123) | IQBLNJ9T N.11836564.6011123 | 10.752 MBPS | P2205521 |  | BCBLDF3F0001 (IQBLNJ9T) BCBLDF3F0002 (IQBLNJ9T) BCBLDF3F0003 (IQBLNJ9T) BCBLDF3F0004 (IQBLNJ9T) BCBLDF3F0005 (IQBLNJ9T) BCBLDF3F0006 (IQBLNJ9T) BCBLDF3F0007 (IQBLNJ9T) | 13/HCGS/684927//FTNC/ (IQBLNJ9TSZXWMB02) | 6011123 | 7200 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64794 PE IP Address : 68.139.118.69 CE Address : 68.139.118.70 QoS - Egress Profile: R12 PVC ID : 6011123 |  |  |  | SW BELL - SAN ANTONIO ATT (IQBLNJ9TSZXWMB02) | 10/16/2018 (IQBLNJ9TSZXWMB02) | 12/03/2018 (IQBLNJ9TSZXWMB02) | 11/20/2018 (IQBLNJ9TSZXWMB02) |  |  |  |  | JASON OZER 0012109513251 JOZER@WELLMED.NET | [5 empty] | 05/07/2019 (IQBLNJ9T) | 04/24/2019 (IQBLNJ9T) |  | 04/24/2019 (11836564) |  | N (IQBLNJ9T) N (N.11836564.6011123) | 05017789 P2205521 |  | NSPE0012377633 CW 196926487
Cancelled | TX423-01-IM Floresville, TX | 100 WILSON DR FLORESVILLE, TX 78114 US | 50 MBPS (27702084) | 11/15/2018: 11/15 Background: TX423-01-IM Floresville, TX; New 10M/50M PIP-Eth; (Frontier); NID; No MNS Status: Customer is not going through with Frontier Scon. An Amendment is required before a new order is placed with Spectrum. Next action: circuit delivery. | 197191351 | TX423-01-IM | Access (27702084) Private IP - PIP (27702083) WAN Analysis Reporting (27702085) | 27702084 27702083 27702085 | 10 MBPS (27702083) |  | 94570899 (Access) 94570896 (Private IP (PIP)) 94570894 (WAN Analysis Reporting) | E4036971/ADD (27702084) E4036971/CANCEL (27702084) C4014357/ADD (27702083) C4014357/CANCEL (27702083) | c5txu txn 0003 (I0011693.SNA) | 6008226 | 5500 | PVC ID : 6008226 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64724 PE IP Address : 199.220.141.253 CE Address : 199.220.141.254 QoS - Egress Profile: R12 |  | 100Base-FX (1310nm, Multi Mode Fiber) (27702084) | Ethernet |  |  | 11/05/2018 (I0011693.SNA) |  | 11/26/2018 (VFORCE) (27702084) |  |  |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 |  |  |  | 11/01/2018 11/07/2018 | 11/15/2018 | 11/15/2018 (27702084) 11/12/2018 (27702083) 11/12/2018 (27702085) | Cancelled | N (27702084) N (27702083) N (27702085) | U0101953 |  |  | NSPE0012401656
Cancelled | FL367-02-IM Davenport, FL | 9302 NORTH BLVD W DAVENPORT, FL 33837 US | 10 MBPS (27722132) | 10/11/2018: Background: FL367-02-IM Davenport, FL, US; New 10M/10M PIP-Eth; (Frontier); NID; No MNS Status: Order in jeopardy due to customer building still under construction, ECD is 01/02/2019. Order will need to be cancelled and re-issued once phone room is ready. | 197214103 | FL367-02-IM | Private IP - PIP (27722131) WAN Analysis Reporting (27722133) Access (27722132) | 27722131 27722133 27722132 | 10 MBPS (27722131) |  | 94570235 (Private IP (PIP)) 94570242 (WAN Analysis Reporting) 94570237 (Access) | C0152813/ADD (27722131) C0152813/CANCEL (27722131) E3058939/CANCEL (27722132) E3058939/ADD (27722132) |  | 6008845 | 5500 | PVC ID : 6008845 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64740 PE IP Address : 152.162.113.5 CE Address : 152.162.113.6 QoS - Egress Profile: R12 | 100Base-TX (27722132) | 100Base-TX (27722132) | Ethernet | [8 empty] | Todd VanDerSchaegen 1-813-629-2611 anderschaegen@wellmed.net | Vasudev K | vasudev.k@optum.com | 91-886-175-8263 | 10/16/2018(Private IP - PIP) 10/16/2018(Access) |  |  | 11/05/2018 11/09/2018 | 10/16/2018 | 10/12/2018 (27722131) 10/12/2018 (27722133) 10/16/2018 (27722132) | Cancelled | N (27722131) N (27722133) N (27722132) | U0101953 | Jeopardy Notification 1 (10/11/2018) | NSPE0012403854 Order Request # 197199017 | NSPE0012403854
Cancelled | TX086 San Antonio, TX | 6200 NORTHWEST PKWY SAN ANTONIO, TX 78249-3348 US | 1 GBPS (27752502) | 11/29/2018: 11/29Background: UTX34-08-IJ San Antonio, TX; New 400M/1G PIP-Eth; (TWC); NID; No MNS; Status: Order cancelled Next action: Order closure | 197241323 | UTX34-08-IJ San Antonio | Private IP - PIP (27752501) WAN Analysis Reporting (27752503) Access (27752502) | 27752501 27752503 27752502 | 400 MBPS (27752501) |  | 286124289 (Private IP (PIP)) 286124291 (WAN Analysis Reporting) 286124285 (Access) | C0152959/ADD (27752501) C0152959/CANCEL (27752501) E5014346/ADD (27752502) E5014346/CANCEL (27752502) |  | 6009503 | 250000 | PVC ID : 6009503 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64608 PE IP Address : 152.162.238.205 CE Address : 152.162.238.206 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27752502) | 1000Base-SX (850nm, Multi Mode Fiber) (27752502) | Ethernet |  |  |  |  | 11/14/2018 (VFORCE) (27752502) |  |  |  | Carlos Lozano 1-210-474-5223 carlos_lozano@optum.com | CLIFFORD REMIGIO | clifford_remigio@optum.com | 1-612-790-6518 | 11/09/2018(Private IP - PIP) 11/09/2018(Access) |  |  | 11/08/2018 11/14/2018 | 11/09/2018 | 11/07/2018 (27752501) 11/07/2018 (27752503) 11/09/2018 (27752502) | Cancelled | N (27752501) N (27752503) N (27752502) | U0101953 | Jeopardy Notification 3 (11/01/2018) | NSPE0012408985 Order Request # 197232095 | NSPE0012414186
Cancelled | C1629-12-IM Dallas, TX | 1950 N STEMMONS FWY DALLAS, TX 75207-3134 US | 10 GBPS (27803134) | 10/18/2018: 10/18 - Background: C1629-12-IM Dallas, TX; New 2G/10G IDS; VzB; No NID; No MNS; Status: Pending re-issue order from sales.10G IDE order United Health Care order will need to be cancel and reissue for Direct To Service Edge (D2SE) Layer 2 Aggregation: yes (not acceptable). Account Team advised. | 197280371 | TX777-05-IJ Student Resources Internet T1 | Internet Dedicated Services (27803133) Access (27803134) | 27803133 27803134 | 2 GBPS (27803133) |  | 286762491 (Internet Dedicated Services) 286762487 (Access) | E7000722/CANCEL (27803134) |  | 6010666 |  | PVC ID : 6010666 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (27803134) | Ethernet | [8 empty] | MATTHEW ADAMS 1-763-553-4616 matthew_adams@optum.com | MATTHEW ADAMS | matthew_adams@optum.com | 1-763-553-4616 |  |  |  | 10/31/2018 | 10/19/2018 | 10/19/2018 (27803133) 10/19/2018 (27803134) |  | N (27803133) N (27803134) | U0101953 |  | NSPE0012418945 Order Request # 197246067 | NSPE0012418945
Cancelled | ALH GA026 Atlanta, GA | 3200 WINDY HILL RD SE ATLANTA, GA 30339-5640 US | 300 MBPS (27823573) | 10/24/2018: 10/24 - Background: ALH GA026 Atlanta, GA; New 200M/300M PIP-Eth; VzB; NID; No MNS; Status: Per customer please cancel order. Supped to cancel submitted. | 197300201 | ALH GA026 Atlanta | Private IP - PIP (27823572) WAN Analysis Reporting (27823574) Access (27823573) | 27823572 27823574 27823573 | 200 MBPS (27823572) |  | 94574173 (Private IP (PIP)) 94574176 (WAN Analysis Reporting) 94574170 (Access) | C5006204/ADD (27823572) C5006204/CANCEL (27823572) E5014541/CANCEL (27823573) E5014541/ADD (27823573) |  | 6011210 | 90000 | PVC ID : 6011210 VPN Name : UnitedHealthGroup Router Name : CPZXE03 VRF Name : V599438-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64698 PE IP Address : 152.164.7.185 CE Address : 152.164.7.186 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (27823573) | Ethernet |  |  |  |  | 11/08/2018 (CCP) (27823572) 11/08/2018 (CCP) (27823573) | 11/18/2018 (CCP) (27823572) 11/18/2018 (CCP) (27823573) |  |  | LEIGH KELLER (Nation) 1-404-406-3919 Leigh.Nation@optum.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 10/26/2018(Private IP - PIP) 10/26/2018(Access) |  | 11/16/2018 (27823572) 11/14/2018 (27823573) | 11/02/2018 11/08/2018 | 10/26/2018 | 10/24/2018 (27823572) 10/24/2018 (27823574) 10/26/2018 (27823573) | Cancelled | N (27823572) N (27823574) N (27823573) | U0101953 |  | NSPE0012424835 Order Request # 197263279 | NSPE0012424835
Cancelled | UMNEA-04-IM Saint Paul, MN | 515 EATON ST SAINT PAUL, MN 55107-2495 US | 1.5 MBPS (27876584) | 12/06/2018: Cancelled due to incorrect address. Reissued under NSPE0012561584 Order Request # 197718091 Service Order # 197718251 | 197336341 | UMNEA-04-IM | Private IP - PIP (27876583) WAN Analysis Reporting (27876585) Access (27876584) | 27876583 27876585 27876584 | 1.5 MBPS (27876583) |  | 94579031 (Private IP (PIP)) 94579029 (WAN Analysis Reporting) 94579034 (Access) | C0153830/CANCEL (27876583) C0153830/ADD (27876583) D1096393/CANCEL (27876584) D1096393/ADD (27876584) | 1373c uhj 0079 (I0039589.MIN) | 6012774 | 768 | PVC ID : 6012774 VPN Name : UnitedHealthGroup Router Name : MZZ3E01 VRF Name : V338870-UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 64564 PE IP Address : 152.161.168.157 CE Address : 152.161.168.158 QoS - Egress Profile: R12 |  | DS1 (27876584) | TDM |  |  | 11/08/2018 (I0039589.MIN) | [5 empty] | EDWARD JONES 1-719-452-4044 edward.jones@optum.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 12/06/2018(Private IP - PIP) 12/06/2018(Access) |  | 12/03/2018 (27876583) 11/29/2018 (27876584) | 12/18/2018 12/24/2018 | 12/11/2018 | 12/06/2018 (27876583) 12/06/2018 (27876585) 12/06/2018 (27876584) | Cancelled | N (27876583) N (27876585) N (27876584) | U0101953 |  | NSPE0012447654 Order Request # 197336257 | NSPE0012447654
Cancelled | FL367-02-IM Davenport, FL | 2380 NORTH BLVD W DAVENPORT, FL 33837-8924 US | 50 MBPS (27869436) | 11/15/2018: 11/15 Background:Customer no longer need circuit. Status: Pending Completed cancel. | 197337515 | FL367-02-IM new address | Private IP - PIP (27869435) WAN Analysis Reporting (27869437) Access (27869436) | 27869435 27869437 27869436 | 10 MBPS (27869435) |  | 94577404 (Private IP (PIP)) 94577406 (WAN Analysis Reporting) 94577402 (Access) | C4014595/CANCEL (27869435) C4014595/ADD (27869435) E4037697/ADD (27869436) E4037697/CANCEL (27869436) |  | 6012424 | 5500 | PVC ID : 6012424 VPN Name : UnitedHealthGroup Router Name : TAM29E01 VRF Name : Vc07436:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64740 PE IP Address : 152.187.37.121 CE Address : 152.187.37.122 QoS - Egress Profile: R12 | 100Base-TX (27869436) | 100Base-TX (27869436) | Ethernet |  |  |  |  | 11/30/2018 (VFORCE) (27869436) |  |  |  | TODD VANDERSCHAEGEN 1-813-629-2611 anderschaegen@wellmed.net | VASUDEV K | vasudev.k@optum.com | 91-763-744-2114 |  |  |  | 11/22/2018 11/28/2018 | 11/15/2018 | 11/13/2018 (27869435) 11/13/2018 (27869437) 11/15/2018 (27869436) | Cancelled | N (27869435) N (27869437) N (27869436) | U0101953 | Jeopardy Notification 3 (11/02/2018) | NSPE0012444229 Order Request # 197325485 | NSPE0012444229
Cancelled | TX023-05-IJ Richardson, TX | 1311 W PRESIDENT GEORGE BUSH HWY RICHARDSON, TX 75080-1153 US | 500 MBPS (27913910) | 11/01/2018: 11/01 - Background: TX023-05-IJ Richardson, TX; New 300M/500M PIP-Eth; (TWC); NID; No MNS; Off-net Build 75bd Status: No change pending FOC date. Escalation ticket raised. | 197387925 | TX023-05-IJ Richardson, TX | Private IP - PIP (27913909) WAN Analysis Reporting (27913911) Access (27913910) | 27913909 27913911 27913910 | 300 MBPS (27913909) |  | 94581438 (Private IP (PIP)) 94581433 (WAN Analysis Reporting) 94581435 (Access) | C5006292/CANCEL (27913909) C5006292/ADD (27913909) E5014777/ADD (27913910) E5014777/CANCEL (27913910) |  | 6013732 | 180000 | PVC ID : 6013732 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64517 PE IP Address : 206.115.4.213 CE Address : 206.115.4.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27913910) | 1000Base-SX (850nm, Multi Mode Fiber) (27913910) | Ethernet |  |  |  |  | 07/09/2019 (VFORCE) (27913910) |  |  |  | Jorge Alvarez 1-214-273-8767 jorge_alvarez@optum.com | CLIFFORD REMIGIO | clifford_remigio@gmail.com | 632-790-6518 | 11/06/2018(Private IP - PIP) 11/06/2018(Access) |  |  | 01/31/2019 02/06/2019 | 11/06/2018 | 11/02/2018 (27913909) 11/02/2018 (27913911) 11/06/2018 (27913910) | Cancelled | N (27913909) N (27913911) N (27913910) | U0101953 |  | NSPE0012462372 Order Request # 197386709 | NSPE0012462372
Cancelled | NJ139-02-IM Pine Brook, NJ | 19 CHAPIN RD PINE BROOK, NJ 07058-9385 US | 50 MBPS |  | 197420225 | NJ139-02-IM | Access WAN Analysis Reporting (27940026) Private IP - PIP (27940024) | 27940024 27940026 | 50 MBPS (27940024) |  | 216862108 216862111 (WAN Analysis Reporting) 216862110 (Private IP (PIP)) | C4012748/NONE (27940024) |  | 5984366 | 5000 | PVC ID : 5984366 VPN Name : UnitedHealthGroup Router Name : WOR9E02 VRF Name : V757943:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64850 PE IP Address : 68.138.74.9 CE Address : 68.138.74.10 QoS - Egress Profile: R12 | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Steven Ambrosino 1-516-220-4505 sambrosino@ambrosinocorp.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  | 10/24/2018 (27940024) | 11/02/2018 (22827971.1) 11/02/2018 | 10/26/2018 | 10/26/2018 (27940024) 10/26/2018 (27940026) | Order Canceled Cancelled | N N (27940026) N (27940024) | U0101953 |  | NSPE0012470259 Order Request # 197414323 | NSPE0012470259
Cancelled | TX444-02-IM Cedar Park, TX | 11901 W PARMER LN STE 300 CEDAR PARK, TX 78613-7654 US | 50 MBPS (27989134) | 12/27/2018: 12/27Background: TX444-02-IM Cedar Park, TX; New 10M/50M PIP-Eth; (TWC); NID; No MNS; Status: Cancelling request. Next action: Cancel order | 197477889 | TX444-02-IM | Access (27989134) WAN Analysis Reporting (27989135) Private IP - PIP (27989133) | 27989134 27989135 27989133 | 10 MBPS (27989133) |  | 94583641 (Access) 94583647 (WAN Analysis Reporting) 94583644 (Private IP (PIP)) | E4038412/ADD (27989134) E4038412/CANCEL (27989134) C4014853/ADD (27989133) C4014853/CANCEL (27989133) |  | 6015943 | 5500 | PVC ID : 6015943 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64583 PE IP Address : 152.164.233.129 CE Address : 152.164.233.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (27989134) | 1000Base-SX (850nm, Multi Mode Fiber) (27989134) | Ethernet |  |  |  |  | 07/12/2019 (VFORCE) (27989134) |  |  |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 | 12/31/2018(Access) 12/31/2018(Private IP - PIP) |  | 03/26/2019 (27989134) 03/28/2019 (27989133) | 02/12/2019 02/18/2019 | 12/31/2018 | 12/31/2018 (27989134) 12/24/2018 (27989135) 12/24/2018 (27989133) | Cancelled | N (27989134) N (27989135) N (27989133) | U0101953 |  | NSPE0012484679 Order Request # 197467281 | NSPE0012484679
Cancelled | TX423-05-IM Floresville, TX | 100 WILSON DR FLORESVILLE, TX 78114 USA | 1.536 MBPS (IQBLN4NF) | 05/01/2019: 5/1Background: Floresville, TX; New 7xT1 MLPPP; (AT&T); Single NID; No MNS; Status: Loop delivered. > Still pending line testing of circuit 3 and 5 > Issue is between FTR and ATT; > Escalated to 2nd level for resolution | 9743894 |  | EVC/PVC Service (N.11880512.6020829) Private IP (IQBLN4NF) | N.11880512.6020829 IQBLN4NF | 10.752 MBPS | P2208482 |  | BCBLDKG60001 (IQBLN4NF) BCBLDKG60002 (IQBLN4NF) BCBLDKG60003 (IQBLN4NF) BCBLDKG60004 (IQBLN4NF) BCBLDKG60005 (IQBLN4NF) BCBLDKG60006 (IQBLN4NF) BCBLDKG60007 (IQBLN4NF) | 13/HCGS/688338//FTNC (IQBLN4NFSEZWMB01) | 6020829 | 7200 | PVC ID : 6020829 VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64724 PE IP Address : 152.164.58.157 CE Address : 152.164.58.158 QoS - Egress Profile: R12 |  |  |  | ATT (IQBLN4NFSEZWMB01) | 11/26/2018 (IQBLN4NFSEZWMB01) | 04/01/2019 (IQBLN4NFSEZWMB01) | 05/09/2019 (IQBLN4NFSEZWMB01) |  |  |  |  | JASON OZER 2109513251 0012109513251 JOZER@WELLMED.NET | [5 empty] | 05/09/2019 (IQBLN4NF) | 05/01/2019 (IQBLN4NF) |  | 05/01/2019 (11880512) |  | N (N.11880512.6020829) N (IQBLN4NF) | P2208482 05017789 |  | NSPE0012527482 CW 197600787 | NSPE0012527482
Cancelled | Test Only Elk River, MN | 14100 BUSINESS CENTER DR NW ELK RIVER, MN 55330-4654 |  | 12/05/2018: 12/5 Background: Test Elk River, MN; IDE 10Gige Burstable Select 2G; (VzB) Status: Pending provisioning Next action: Pending FOC Who owns the next action: SD | 9743890 |  | Internet Dedicated (U337754) | U337754 | [19 empty] | TERESA DYAR 7636947431 TERESA_N_DYAR@OPTUM.COM | [6 empty] | 01/15/2019 (U337754) |  | 12/13/2018 (U337754) |  | N (U337754) |  |  | NSPE0012523993 CW 197470493 | NSPE0012523993
Cancelled | NY025-02-IJ Brooklyn NY | 30 FLATBUSH AVE BROOKLYN, NY 11217-1121 US | 20 MBPS | 02/06/2019: 2/6Background: NY025-02-IJ Brooklyn NY; New 10M/20M PIP-Eth; (VzT); No NID; No MNS; Status: Site not ready. Pending CRD. EUCR sent 12/18. Sent another follow up to customer. Next action: Order to be submitted to Provisioning | 197672079 | NY025-02-IJ Brooklyn NY | Access WAN Analysis Reporting Private IP - PIP |  | 10 MBPS |  | 94591747 94591751 94591744 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Wali Omarkheil 1-516-306-5957 wali_u_omarkheil@uhc.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 |  |  |  | 01/09/2019 01/15/2019 |  |  |  | N | U0101953 |  | NSPE0012546514 Order Request # 197669585 | NSPE0012546514
Cancelled | NJ139-02-IM Pinebrook, NJ | 19 CHAPIN RD PINE BROOK, NJ 07058-9385 US | 50 MBPS | 12/16/2018: 12/16 Background: NJ139-02-IM Pinebrook, NJ; New 50M/50M PIP-Eth; (Vzt); No NID; No MNS; Status: Pending Site Survey to be rescheduled Next action: To reschedule ESS | 197707899 | NJ139-02-IM | WAN Analysis Reporting Private IP - PIP Access |  | 50 MBPS |  | 302528343 302528341 302528337 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | MICHAEL P. JOHNSON 1-952-202-6900 michael_johnson1@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  |  | 01/07/2019 01/01/2019 |  |  |  | N | U0101953 |  | NSPE0012558382 Order Request # 197707083 | NSPE0012558382
Cancelled | VA732 Ashburn, VA | 21583 MEGAWATT DR ASHBURN, VA 20147 US | 1 GBPS | 12/27/2018: 12/27Background: VA732 Ashburn, VA; New 300M/1G PIP-Ethernet; (VzT); Single NID; No MNS; Rangingwire Data Center Status: Customer and data center confirmed address is correct. Sent another email to OSP. Next action: Submit to provisioning | 197800587 | VA732 | Access WAN Analysis Reporting Private IP - PIP |  | 300 MBPS |  | 94600354 94600352 94600349 | [5 empty] | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Paul Nacamuli 1-425-201-7094 paul_nacamuli@optum.com | EDWARD JONES | edward.jones@optum.com | 1-719-425-4044 |  |  |  | 01/28/2019 02/01/2019 |  |  |  | N | U0101953 |  | NSPE0012585161 Order Request # 197796991 | NSPE0012585161
Cancelled | GA777-04-IJ Atlanta, GA - Equinix hub Peachtree | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US | 10 GBPS (28260795) | 01/02/2019: 1/2Background: GA777-04-IJ Equinix hub Atlanta GA Peachtree; New 2G/10G IDS Burstable; (VzB); No NID; No MNS; Status: Pending Provisioning approval Next action: Pending FOC | 197804091 | Equinix hub Atlanta Peachtree GA777-04-IJ | Internet Dedicated Services (28260794) Access (28260795) | 28260794 28260795 | 10 GBPS (28260794) |  | 306218883 (Internet Dedicated Services) 306218879 (Access) | E7000846/CANCEL (28260795) |  | 6027701 |  | PVC ID : 6027701 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (28260795) | Ethernet | [8 empty] | Alan Kroth 1-952-833-7895 alan@optum.com | Alan Kroth | alan@optum.com | 1-952-833-7895 |  |  |  | 01/15/2019 | 01/03/2019 | 01/03/2019 (28260794) 01/03/2019 (28260795) |  | N (28260794) N (28260795) | U0101953 |  | NSPE0012587114 Order Request # 197803209 | NSPE0012587114
Cancelled | TX423-01-IM Floresville, TX | 100 WILSON DR FLORESVILLE, TX 78114 US | 50 MBPS (28292549) | 01/17/2019: 1/17Background: TX423-01-IM Floresville, TX; New 10M/50M PIP-Ethernet; (Frontier); NID; No MNS; Status: Cancelled. Pending CPE retrieval. Reissued under SO 197855283 with TWC Next action: Order closure Who owns the next action: SD | 197840191 | TX423-01-IM | Private IP - PIP (28292548) Access (28292549) WAN Analysis Reporting (28292550) | 28292548 28292549 28292550 | 10 MBPS (28292548) |  | 293227701 (Private IP (PIP)) 293227697 (Access) 293227703 (WAN Analysis Reporting) | C4015438/CANCEL (28292548) C4015438/ADD (28292548) E4040066/ADD (28292549) E4040066/CANCEL (28292549) | c5txu txn 0004 (I0011752.SNA) | 6028795 | 5000 | PVC ID : 6028795 VPN Name : UnitedHealthGroup Router Name : SAJ9E01 VRF Name : V613471:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64801 PE IP Address : 152.161.106.221 CE Address : 152.161.106.222 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (28292549) | Ethernet |  |  | 02/11/2019 (I0011752.SNA) | [5 empty] | JASON OZER 1-210-951-3251 jozer@wellmed.net | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 |  |  |  | 02/07/2019 02/13/2019 | 01/17/2019 | 01/04/2019 (28292548) 01/17/2019 (28292549) 01/04/2019 (28292550) | Cancelled | N (28292548) N (28292549) N (28292550) | U0101953 |  | NSPE0012598071 Order Request # 197837063 | NSPE0012598071
Cancelled | NJ777-11-IM Secaucus, NJ |  |  |  | 9792611 |  | Internet Dedicated | [20 empty] | ALAN KROTH 9528337895 ALAN@OPTUM.COM | [10 empty] | N |  |  | NSPE0012599209 CW 197839805 | NSPE0010421332
Cancelled | Whitestone, NY | 15235 10TH AVE WHITESTONE, NY 11357-1233 US | 30 MBPS | 01/10/2019: 1/10Background: Whitestone, NY; New 30M/30M PIP-Ethernet; (VzT); No NID; No MNS; Status: Site survey 01/11/2019 9am to 12noon CST. Access confirmed. Next action: To be submitted to provisioning | 197894855 | CARDINAL HEALTH INC | WAN Analysis Reporting Private IP - PIP Access |  | 30 MBPS |  | 309727721 309727719 309727715 | [5 empty] | 100Base-TX | 100Base-TX | Ethernet | [8 empty] | RALPH MERCADO 1-347-438-2644 ralph.mercado@cardinalhealth.com | BRIAN MCNAMARA | brian.mcnamara01@cardinalhealth.com | 1-614-757-0153 |  |  |  | 02/11/2019 02/05/2019 |  |  |  | N | U0102647 |  | NSPE0012616317 Order Request # 197888573 | NSPE0012616317
Cancelled | TX079-05-IM El Paso, TX | 9999 KENWORTHY ST STE A EL PASO, TX 79924-4413 US | 50 MBPS (28380506) | 06/13/2019: 6/13Background: El Paso, TX; Change order to move Telco Circuit only from suite B to suite A; no other changes; ckt not in use; (TWT) Status: Order onhold due to access issue. > Customer pushed out circuit move to 08/21/2019 Next action: OM to put out of hold; then FOC issuance | 197939699 | TX079-05-IM | Access (28380506) Private IP - PIP WAN Analysis Reporting (28380507) | 28380506 28380507 | 20 MBPS |  | 94570166 (Access) 94570162 94570160 (WAN Analysis Reporting) | E4036994/NONE (28380506) |  |  |  |  | 100Base-TX (28380506) | 100Base-TX (28380506) | Ethernet | [8 empty] | GABRIEL RODRIGUEZ 1-210-833-8929 grodriguez1@wellmed.net | Sahil Tuteja | sahil_tuteja@optum.com | 91-828-567-0647 | 06/17/2019(Access) |  | 03/18/2019 (28380506) | 02/25/2019 02/25/2019 (23980307.1) | 06/17/2019 | 06/17/2019 (28380506) 06/14/2019 (28380507) | Cancelled Order Canceled | N (28380506) N N (28380507) | U0101953 |  | NSPE0012630486 Order Request # 197939389 | NSPE0012630585
Cancelled | Medexpress Pittsburgh, PA | 200 ALLEGHENY CENTER MALL PITTSBURGH, PA 15212-5339 US | 100 MBPS |  | 197963661 | Medexpress | Private IP - PIP WAN Analysis Reporting Access |  | 100 MBPS |  | 94606828 94606833 94606831 | [5 empty] | 1000Base-LX-1310nm | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Thomas Mayernick 1-412-929-5035 thomas.mayernick@medexpress.com | Doug Spencer | douglas.spencer@gdt.com | 1-412-929-5035 |  |  |  | 02/27/2019 03/05/2019 |  |  |  | N | U0101953 |  | NSPE0012636523 Order Request # 197962965 | NSPE0012636523
Cancelled | AZ066 Phoenix, AZ | 5830 N 19TH AVE PHOENIX, AZ 85015-2494 US | 50 MBPS (28431486) | 02/21/2019: 2/21Background: AZ066 Phoenix, AZ; New 20M/50M PIP-Ethernet; (Qwest); Dual NID; No MNS; Status: Order has a Scon of 29k; Customer advised to canl, will re-issue with COX Next action: Pending cancellation | 197993341 | AZ066 | Private IP - PIP (28431485) WAN Analysis Reporting (28431487) Access (28431486) | 28431485 28431487 28431486 | 20 MBPS (28431485) |  | 94609824 (Private IP (PIP)) 94609827 (WAN Analysis Reporting) 94609822 (Access) | C4015706/CANCEL (28431485) C4015706/ADD (28431485) E4040762/CANCEL (28431486) E4040762/ADD (28431486) |  | 6033359 |  | PVC ID : 6033359 | 1000Base-SX-850nm (28431486) | 1000Base-SX (850nm, Multi Mode Fiber) (28431486) | Ethernet |  |  |  |  | 03/26/2019 (VFORCE) (28431486) |  |  |  | Jennie Comer 1-602-336-1966 jennie.comer@optum.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 |  |  |  | 03/05/2019 03/11/2019 | 02/25/2019 | 02/21/2019 (28431485) 02/21/2019 (28431487) 02/25/2019 (28431486) | Cancelled | N (28431485) N (28431487) N (28431486) | U0101953 |  | NSPE0012645654 Order Request # 197993279 | NSPE0012645654
Cancelled | PA138 Philadelphia, PA | 1818 MARKET ST PHILADELPHIA, PA 19103-3638 US | 50 MBPS (28431731) | 02/20/2019: 2/20Background: PA138 Philadelphia, PA; New 30M/50M PIP-Eth; (VzB); Dual NID; No MNS Status: Customer advised ok to cancel order at this time Next action: Pending cancellation | 197995085 | PA138 | Private IP - PIP (28431730) WAN Analysis Reporting (28431732) Access (28431731) | 28431730 28431732 28431731 | 30 MBPS (28431730) |  | 94609742 (Private IP (PIP)) 94609747 (WAN Analysis Reporting) 94609745 (Access) | C4015707/ADD (28431730) C4015707/CANCEL (28431730) E4040765/ADD (28431731) E4040765/CANCEL (28431731) |  | 6033368 | 17000 | PVC ID : 6033368 VPN Name : UnitedHealthGroup Router Name : PBYXE04 VRF Name : Vd03246-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64529 PE IP Address : 152.181.213.85 CE Address : 152.181.213.86 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (28431731) | Ethernet |  |  |  |  | 02/13/2019 (CCP) (28431730) 02/13/2019 (CCP) (28431731) | 02/12/2019 (CCP) (28431730) 02/12/2019 (CCP) (28431731) |  |  | Kim Zirkle 1-952-202-0058 Kim_Zirkle@uhg.com | DAVID JZEN DIMAYUGA | david_dimayuga@optum.com | 632-790-6503 | 02/26/2019(Private IP - PIP) 02/26/2019(Access) |  | 03/05/2019 (28431730) 03/01/2019 (28431731) | 03/05/2019 03/11/2019 | 02/26/2019 | 02/20/2019 (28431730) 02/20/2019 (28431732) 02/26/2019 (28431731) | Cancelled | N (28431730) N (28431732) N (28431731) | U0101953 | Jeopardy Notification 1 (02/14/2019) | NSPE0012646259 Order Request # 197995037 | NSPE0012646259
Cancelled | UPA04 Medexpress Pittsburg, PA | 100 S COMMONS PITTSBURGH, PA 15212-5359 US | 100 MBPS | 01/31/2019: 1/31Background: UPA04 Medexpress Pittsburg, PA; New 100M/100M PIP-Eth; (VzT); Single NID; No MNS Status: Site survey 01/25/2019 1PM to 4PM CST. Awaiting results. Sent email to OSPE. Next action: To be submitted to provisioning | 197987055 | UPA04 Medexpress Pittsburg | WAN Analysis Reporting Access Private IP - PIP |  | 100 MBPS |  | 94609559 94609552 94609554 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Thomas Mayernick 1-412-929-5035 thomas.mayernick@gdt.com | DOUG SPENCER | douglas.spencer@gdt.com | 1-440-817-0322 |  |  |  | 03/08/2019 03/04/2019 |  |  |  | N | U0101953 |  | NSPE0012643651 Order Request # 197986877 | NSPE0012643651
Cancelled | NV124 Optum Care North Las Vegas, NV | 4090 W CRAIG RD NORTH LAS VEGAS, NV 89032-2757 US | 50 MBPS (28458395) | 04/18/2019: 4/17 Background: NV124 Optum Care North Las Vegas, NV; New 10M/50M PIP-Ethernet; (Century Link); Dual NID; No MNS; Status: Foc of 4/23 will be missed - Construction has been pushed out to 5/31 due to Road construction. Next action: Pending Re-Foc Who owns the next action: SD/CenturyLink | 198022655 | NV124 Optum Care | Private IP - PIP (28458394) WAN Analysis Reporting (28458396) Access (28458395) | 28458394 28458396 28458395 | 10 MBPS (28458394) |  | 94610858 (Private IP (PIP)) 94610865 (WAN Analysis Reporting) 94610861 (Access) | C4015768/CANCEL (28458394) C4015768/ADD (28458394) E4040935/CANCEL (28458395) E4040935/ADD (28458395) |  | 6034477 | 5500 | PVC ID : 6034477 VPN Name : UnitedHealthGroup Router Name : LSVG9E03 VRF Name : V569793:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64760 PE IP Address : 147.225.64.213 CE Address : 147.225.64.214 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28458395) | 1000Base-SX (850nm, Multi Mode Fiber) (28458395) | Ethernet |  |  |  |  | 04/26/2019 (VFORCE) (28458395) |  |  |  | Ron Rubin 1-702-877-5081 ron.rubin@optum.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 |  |  | 05/02/2019 (28458394) 04/30/2019 (28458395) | 03/08/2019 03/14/2019 | 04/23/2019 | 04/23/2019 (28458394) 04/23/2019 (28458396) 04/23/2019 (28458395) | Cancelled | N (28458394) N (28458396) N (28458395) | U0101953 |  | NSPE0012653686 Order Request # 198021993 | NSPE0012653686
Cancelled | UPA04 Medexpress Pittsburg, PA | 2500 ALLEGHENY CENTER MALL STE 138 PITTSBURGH, PA 15212-5303 US | 100 MBPS (28490266) | 02/14/2019: 2/14Background: UPA04 Medexpress Pittsburg, PA; New 100M/100M PIP-Eth; (VzB); Dual NID; No MNS Status: Need to change telco. Sent email to account team to reissue with the best telco for this location. Awaiting confirmation from SA. Next action: Pending solution from SA on how to proceed | 198057583 | UPA04 | Private IP - PIP (28490265) WAN Analysis Reporting (28490267) Access (28490266) | 28490265 28490267 28490266 | 100 MBPS (28490265) |  | 316873695 (Private IP (PIP)) 316873697 (WAN Analysis Reporting) 316873691 (Access) | C1084976/ADD (28490265) C1084976/CANCEL (28490265) E4041133/CANCEL (28490266) E4041133/ADD (28490266) |  | 6035629 |  | PVC ID : 6035629 |  | 1000Base-SX (850nm, Multi Mode Fiber) (28490266) | Ethernet | [8 empty] | Thomas Mayernick 1-412-929-5035 thomas.mayernick@gdt.com | DOUG SPENCER | douglas.spencer@gdt.com | 1-440-817-0322 |  |  |  | 03/13/2019 03/19/2019 | 02/19/2019 | 02/15/2019 (28490265) 02/15/2019 (28490267) 02/19/2019 (28490266) | Cancelled | N (28490265) N (28490267) N (28490266) | U0101953 |  | NSPE0012664502 Order Request # 198057491 | NSPE0012664502
Cancelled | TX477-02-IM San Antonio, TX | 6430 BANDERA RD STE 98 SAN ANTONIO, TX 78238-1513 US | 10 MBPS (28562627) | 02/19/2019: Cancelled. Reissued under Order Request # 198157131 SO 198165595 | 198140877 | TX477-02-IM | Private IP - PIP (28562626) WAN Analysis Reporting (28562628) Access (28562627) | 28562626 28562628 28562627 | 10 MBPS (28562626) |  | 94613679 (Private IP (PIP)) 94613683 (WAN Analysis Reporting) 94613676 (Access) | C0161487/ADD (28562626) C0161487/CANCEL (28562626) E3065334/ADD (28562627) E3065334/CANCEL (28562627) |  | 6038377 |  | PVC ID : 6038377 | 100Base-TX (28562627) | 100Base-TX (28562627) | Ethernet |  |  |  |  | 02/22/2019 (VFORCE) (28562627) |  |  |  | GABRIEL RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 1-763-744-2114 | 02/19/2019(Private IP - PIP) 02/19/2019(Access) |  |  | 06/28/2019 07/04/2019 | 02/19/2019 | 02/14/2019 (28562626) 02/14/2019 (28562628) 02/19/2019 (28562627) | Cancelled | N (28562626) N (28562628) N (28562627) | U0101953 |  | NSPE0012686969 Order Request # 198140777 | NSPE0012686969
Cancelled | AZ034 Upgrade Port | 6365 E TANQUE VERDE RD STE 120 TUCSON, AZ 85715-3848 US | 50 MBPS (28577092) |  | 198156339 | AZ034-02-IM | Private IP - PIP (28577091) WAN Analysis Reporting (28577093) Access (28577092) | 28577091 28577093 28577092 | 50 MBPS (28577091) |  | 207124966 (Private IP (PIP)) 207124967 (WAN Analysis Reporting) 207124964 (Access) |  |  | 5949510 |  | PVC ID : 5949510 | 100Base-TX (28577092) | 100Base-TX (28577092) | Ethernet | [8 empty] | Deena Lynn 1-520-901-1415 Deena_Lynn@optum.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 |  |  |  | 03/22/2019 03/22/2019 (20686587.1) | 02/13/2019 | 02/13/2019 (28577091) 02/13/2019 (28577093) 02/13/2019 (28577092) | Cancelled | N (28577091) N (28577093) N (28577092) | U0101953 |  | NSPE0012688695 Order Request # 198147635 | NSPE0012688695
Cancelled | TX477-02-IM San Antonio, TX | 6430 BANDERA RD STE 98 SAN ANTONIO, TX 78238-1513 US | 50 MBPS (28584567) | 04/18/2019: 4/17Background: San Antonio, TX; New 10M/50M PIP-Eth; (TWC); Dual NID; No MNS; 100BD off-net build Status: Pending FOC;ROE and COI Next action: FOC issuance | 198165595 | TX477-02-IM | Private IP - PIP (28584566) WAN Analysis Reporting (28584568) Access (28584567) | 28584566 28584568 28584567 | 10 MBPS (28584566) |  | 321106069 (Private IP (PIP)) 321106081 (WAN Analysis Reporting) 321106061 (Access) | C4016061/ADD (28584566) C4016061/CANCEL (28584566) E4041651/ADD (28584567) E4041651/CANCEL (28584567) |  | 6038974 |  | PVC ID : 6038974 | 1000Base-SX-850nm (28584567) | 1000Base-SX (850nm, Multi Mode Fiber) (28584567) | Ethernet |  |  |  |  | 05/24/2019 (VFORCE) (28584567) |  |  |  | GABRIEL RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 1-763-744-2114 | 04/22/2019(Private IP - PIP) 04/22/2019(Access) |  |  | 07/03/2019 07/09/2019 | 04/22/2019 | 04/19/2019 (28584566) 04/19/2019 (28584568) 04/22/2019 (28584567) | Cancelled | N (28584566) N (28584568) N (28584567) | U0101953 |  | NSPE0012691755 Order Request # 198157131 | NSPE0012691755
Cancelled | UTX52-02-IM Plano, TX | 6653 PINECREST DR PLANO, TX 75024-2924 US | 1 GBPS (28584666) | 02/20/2019: 2/20Background: UTX52-02-IM Plano, TX; New 1G/1G IDS; (Windstream); Dual NID; No MNS Status: Pending FOC Next action: FOC issuance Who owns the next action: SD/Windstream | 198165729 | UTX52-02-IM | Internet Dedicated Services (28584665) Access (28584666) | 28584665 28584666 | 1 GBPS (28584665) |  | 321298291 (Internet Dedicated Services) 321298287 (Access) | C0162156/CANCEL (28584665) C0162156/ADD (28584665) E5016546/CANCEL (28584666) E5016546/ADD (28584666) |  | 6038981 |  | PVC ID : 6038981 | 1000Base-LX-1310nm (28584666) | 1000Base-LX (1310nm Single Mode Fiber) (28584666) | Ethernet | [8 empty] | JOHN CURTISS 1-469-229-6712 jcurtiss@uhcsr.com | JOHN CURTISS | jcurtiss@uhcsr.com | 1-469-229-6712 |  |  |  | 03/26/2019 | 02/26/2019 | 02/26/2019 (28584665) 02/26/2019 (28584666) |  | N (28584665) N (28584666) | U0101953 |  | NSPE0012693354 Order Request # 198161531 | NSPE0012693354
Cancelled | UTX52-02-IM Plano TX | 6653 PINECREST DR PLANO, TX 75024-2924 US | 1 GBPS (28584793) | 03/27/2019: 3/27Background: UTX52-02-IM Plano TX; New 100M/1G PIP-Eth; (TWC); Single NID; No MNS; Data Center Status: Order cancelled. Pending ASR cancellation Next action: Order cancellation | 198165799 | UTX52-02-IM | Access (28584793) Internet Dedicated Services (28584792) | 28584793 28584792 | 1 GBPS (28584792) |  | 314576619 (Access) 314576623 (Internet Dedicated Services) | E5016548/ADD (28584793) E5016548/CANCEL (28584793) C0162172/CANCEL (28584792) C0162172/ADD (28584792) |  | 6038998 |  | PVC ID : 6038998 | 1000Base-LX-1310nm (28584793) | 1000Base-LX (1310nm Single Mode Fiber) (28584793) | Ethernet | [8 empty] | JOHN CURTISS 1-469-229-6712 jcurtiss@uhcsr.com | JOHN CURTISS | jcurtiss@uhcsr.com | 1-469-229-6712 |  |  |  | 04/15/2019 | 03/27/2019 | 03/27/2019 (28584793) 03/26/2019 (28584792) |  | N (28584793) N (28584792) | U0101953 |  | NSPE0012688157 Order Request # 198145127 | NSPE0012688157
Cancelled | AZ066 Phoenix, AZ | 5830 N 19TH AVE PHOENIX, AZ 85015-2494 US | 50 MBPS (28656970) | 03/06/2019: 3/6Background: AZ066 Phoenix, AZ; New 20M/50M PIP-Eth; (Qwest); Dual NID; No MNS Status: Incorrect LEC. Re-issuing order Next action: Cancelling | 198243525 | AZ066 | Private IP - PIP (28656969) WAN Analysis Reporting (28656971) Access (28656970) | 28656969 28656971 28656970 | 20 MBPS (28656969) |  | 324904499 (Private IP (PIP)) 324904501 (WAN Analysis Reporting) 324904495 (Access) | C4016180/CANCEL (28656969) C4016180/ADD (28656969) E4042031/ADD (28656970) E4042031/CANCEL (28656970) |  | 6041023 |  | PVC ID : 6041023 | 1000Base-SX-850nm (28656970) | 1000Base-SX (850nm, Multi Mode Fiber) (28656970) | Ethernet |  |  |  |  | 04/02/2019 (VFORCE) (28656970) |  |  |  | JENNIE COMER 1-602-336-1966 jennie.comer@optum.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 |  |  |  | 05/31/2019 06/06/2019 | 03/06/2019 | 02/28/2019 (28656969) 02/28/2019 (28656971) 03/06/2019 (28656970) | Cancelled | N (28656969) N (28656971) N (28656970) | U0101953 |  | NSPE0012716936 Order Request # 198239739 | NSPE0012716936
Cancelled | ENT FL055 Doral, FL | 1425 NW 82ND AVE DORAL, FL 33126-1507 US | 50 MBPS (28720872) | 07/15/2019: 7/15Background: ENT FL055 DORAL New 10M/50M PIPE (Comcast); Dual NID; No MNS Status: Per customer order to be cancelled | 198306767 | ENT FL055 DORAL | Private IP - PIP (28720871) WAN Analysis Reporting (28720873) Access (28720872) | 28720871 28720873 28720872 | 10 MBPS (28720871) |  | 94621434 (Private IP (PIP)) 94621432 (WAN Analysis Reporting) 94621438 (Access) | C4016349/CANCEL (28720871) C4016349/ADD (28720871) E4042444/ADD (28720872) E4042444/CANCEL (28720872) |  | 6042976 | 5500 | PVC ID : 6042976 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64863 PE IP Address : 199.220.159.45 CE Address : 199.220.159.46 QoS - Egress Profile: R12 | 100Base-TX (28720872) | 100Base-TX (28720872) | Ethernet |  |  |  |  | 07/19/2019 (VFORCE) (28720872) |  |  |  | Eddie Justo 1-954-881-4379 eduardo_justo@uhcsouthflorida.com | Edward Jones | edward.jones@optum.com | 1-719-452-4044 | 07/10/2019(Private IP - PIP) 07/10/2019(Access) |  | 09/05/2019 (28720871) 09/03/2019 (28720872) | 04/15/2019 04/19/2019 | 07/10/2019 | 07/09/2019 (28720871) 07/09/2019 (28720873) 07/10/2019 (28720872) | Cancelled | N (28720871) N (28720873) N (28720872) | U0101953 | Jeopardy Notification 4 (05/02/2019) | NSPE0012737572 Order Request # 198306629 | NSPE0012737572
Cancelled | AZ731-02-IJ Phoenix, AZ | 615 N 48TH ST PHOENIX, AZ 85008-6608 US | 1 GBPS (28865218) | 07/29/2019: 7/29Background: AZ731-02-IJ Phoenix, AZ; New 500M/1G PIP-Eth; Dual NID; No MNS; Status: Order cancelled; Pending equipment retrieval Next action: Order cancellation Who owns the next action: SD | 198458381 | Phoenix _ AZ731-02-IJ | Private IP - PIP (28865217) WAN Analysis Reporting (28865219) Access (28865218) | 28865217 28865219 28865218 | 500 MBPS (28865217) |  | 332265849 (Private IP (PIP)) 332265851 (WAN Analysis Reporting) 332265845 (Access) | C0165213/CANCEL (28865217) C0165213/ADD (28865217) E5017263/CANCEL (28865218) E5017263/ADD (28865218) |  | 6048184 | 350000 | PVC ID : 6048184 VPN Name : UnitedHealthGroup Router Name : PHN13E01 VRF Name : V462916-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64915 PE IP Address : 208.220.203.213 CE Address : 208.220.203.214 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (28865218) | Ethernet |  |  |  |  | 04/30/2019 (CCP) (28865217) 04/19/2019 (CCP) (28865218) | 04/29/2019 (CCP) (28865217) 04/29/2019 (CCP) (28865218) |  |  | Cliff Waldrep 1-480-881-8560 Clifton.Waldrep@avella.com | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 |  |  | 05/29/2019 (28865217) 05/24/2019 (28865218) | 04/22/2019 04/26/2019 | 07/29/2019 | 07/26/2019 (28865217) 07/26/2019 (28865219) 07/29/2019 (28865218) | Cancelled | N (28865217) N (28865219) N (28865218) | U0101953 |  | NSPE0012782723 Order Request # 198454615 | NSPE0012782723
Cancelled | FL752-01-IJ Miami, FL | 50 NE 9TH ST MIAMI, FL 33132-1709 US | 500 MBPS (28865277) | 04/19/2019: The order requires a Verizon Build initiated on Apr 18, 2019 and it is in progress. | 198458483 | UNITED HEALTH GROUP/ TERREMARK | Private IP - PIP (28865276) WAN Analysis Reporting (28865278) Access (28865277) | 28865276 28865278 28865277 | 500 MBPS (28865276) |  | 332271767 (Private IP (PIP)) 332271769 (WAN Analysis Reporting) 332271763 (Access) | C5007106/ADD (28865276) C5007106/CANCEL (28865276) E5017364/ADD (28865277) E5017364/CANCEL (28865277) |  | 6049365 | 250000 | PVC ID : 6049365 VPN Name : UnitedHealthGroup Router Name : 1MJ3E02 VRF Name : Vd39940-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65146 PE IP Address : 152.192.88.157 CE Address : 152.192.88.158 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (28865277) | Ethernet | [8 empty] | EDDY HERNANDEZ 1-786-437-5305 eddy_hernandez@optum.com | Edward Jones | edward.jones@optum.com | 1-719-452-4044 | 04/19/2019(Private IP - PIP) 04/19/2019(Access) |  |  | 04/22/2019 04/26/2019 | 04/20/2019 | 04/19/2019 (28865276) 04/19/2019 (28865278) 04/19/2019 (28865277) | Cancelled | N (28865276) N (28865278) N (28865277) | U0101953 |  | NSPE0012782758 Order Request # 198454691 | NSPE0012782758
Cancelled | WA112 Woodinville, WA | 8107 W BOSTIAN RD WOODINVILLE, WA 98072-6011 US | 50 MBPS (28900127) | 04/09/2019: 4/9Background: WA112 Woodinville, WA; New 50M/50M PIP-Eth; (Frontier); Dual NID; No MNS; Status: Order cancelled due to incorrect address. Next action: Order closure Who owns the next action: Prov | 198494583 | WA112 | Private IP - PIP (28900126) WAN Analysis Reporting (28900128) Access (28900127) | 28900126 28900128 28900127 | 50 MBPS (28900126) |  | 94627030 (Private IP (PIP)) 94627032 (WAN Analysis Reporting) 94627028 (Access) | C4016809/CANCEL (28900126) C4016809/ADD (28900126) E4043589/ADD (28900127) E4043589/CANCEL (28900127) |  | 6049311 |  | PVC ID : 6049311 | 1000Base-SX-850nm (28900127) | 1000Base-SX (850nm, Multi Mode Fiber) (28900127) | Ethernet |  |  |  |  | 06/24/2019 (VFORCE) (28900127) |  |  |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  |  | 05/10/2019 05/16/2019 | 04/10/2019 | 04/08/2019 (28900126) 04/08/2019 (28900128) 04/10/2019 (28900127) | Cancelled | N (28900126) N (28900128) N (28900127) | U0101953 |  | NSPE0012795314 Order Request # 198494489 | NSPE0012795314
Cancelled | Miami, FL | 50 NE 9TH ST FL 4 MIAMI, FL 33132-1709 US | 1 GBPS (28956605) | 04/19/2019: 4/19Background: Miami, FL; New 1G/1G PIP-Eth; VzB; (VzB); Single NID; No MNS; Status: Cancelling order per customer Next action: Order cancelled | 198548035 | Location2775909610 | Private IP - PIP (28956604) WAN Analysis Reporting (28956606) Access (28956605) | 28956604 28956606 28956605 | 1 GBPS (28956604) |  | 94628831 (Private IP (PIP)) 94628837 (WAN Analysis Reporting) 94628833 (Access) | C0165717/ADD (28956604) C0165717/CANCEL (28956604) E5017509/ADD (28956605) E5017509/CANCEL (28956605) |  | 6051031 | 550000 | PVC ID : 6051031 VPN Name : UnitedHealthGroup Router Name : FTLDGE01 VRF Name : V539738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65146 PE IP Address : 152.177.63.177 CE Address : 152.177.63.178 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (28956605) | Ethernet | [8 empty] | EDDY HERNANDEZ 1-786-437-5305 eddy_hernandez@optum.com | EDWARD JONES | edward.jones@optum.com | 1-719-452-4044 | 04/19/2019(Private IP - PIP) 04/19/2019(Access) |  |  | 05/17/2019 05/23/2019 | 04/20/2019 | 04/19/2019 (28956604) 04/19/2019 (28956606) 04/19/2019 (28956605) | Cancelled | N (28956604) N (28956606) N (28956605) | U0101953 |  | NSPE0012810216 Order Request # 198544259 | NSPE0012810216
Cancelled | WA112-02-IM Woodinville, WA | 8025 W BOSTIAN RD WOODINVILLE, WA 98072 US | 50 MBPS (28959561) | 04/24/2019: 4/24Background: WA112-02-IM Woodinville, WA; New 50M/50M PIP-Eth; (Frontier); Dual NID; No MNS; Status: Order cancelled . Next Action: Order cancellation | 198555253 | WA112-02-IM | Access (28959561) Private IP - PIP (28959560) WAN Analysis Reporting (28959562) | 28959561 28959560 28959562 | 50 MBPS (28959560) |  | 336949439 (Access) 336949443 (Private IP (PIP)) 336949445 (WAN Analysis Reporting) | E4043888/CANCEL (28959561) E4043888/ADD (28959561) C4016909/CANCEL (28959560) C4016909/ADD (28959560) |  | 6051088 | 17000 | PVC ID : 6051088 VPN Name : UnitedHealthGroup Router Name : K1B9E01 VRF Name : Vd36333:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64674 PE IP Address : 152.181.114.197 CE Address : 152.181.114.198 QoS - Egress Profile: R12 | 1000Base-SX-850nm (28959561) | 1000Base-SX (850nm, Multi Mode Fiber) (28959561) | Ethernet |  |  |  |  | 08/01/2019 (VFORCE) (28959561) |  |  |  | JASON ENGEL 1-303-594-1125 jason_engel@uhg.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  |  | 05/20/2019 05/24/2019 | 04/24/2019 | 04/24/2019 (28959561) 04/23/2019 (28959560) 04/23/2019 (28959562) | Cancelled | N (28959561) N (28959560) N (28959562) | U0101953 | Jeopardy Notification 1 (04/22/2019) | NSPE0012812010 Order Request # 198550205 | NSPE0012812010
Cancelled | TX410-02-IM Kyle,TX | 830 KOHLERS XING KYLE, TX 78640 US | 50 MBPS (28970154) | 05/13/2019: 5/13Background: Change the handoff to 1000base SX MMF only. no other changes; not active Status: Cancelling order as per customer request. Action Taken: Asked TL Jan Millares to help get this cancelled Next action: Cancellation Who owns the next action: Prov | 198557613 | TX410-02-IM | Access (28970154) Private IP - PIP WAN Analysis Reporting (28970155) | 28970154 28970155 | 10 MBPS |  | 94549529 (Access) 94549526 94549533 (WAN Analysis Reporting) | E4034455/NONE (28970154) | [5 empty] | 1000Base-SX (850nm, Multi Mode Fiber) (28970154) | Ethernet | [8 empty] | Jenna King 1-512-504-7206 JKing@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 1-763-744-1111 |  |  |  | 05/21/2019 05/21/2019 (23252713.1) | 05/22/2019 | 05/22/2019 (28970154) 04/30/2019 (28970155) | Cancelled Order Canceled | N (28970154) N N (28970155) | U0101953 | Jeopardy Notification 2 (04/29/2019) | NSPE0012814326 Order Request # 198557237 | NSPE0012814326
Cancelled | UTN18-05-IJ Brentwood, TN | 8 CADILLAC DR BRENTWOOD, TN 37027-5087 US | 100 MBPS (29074400) | 05/20/2019: Cancelled | 198665387 | UTN18-05-IJ Brentwood TN | Private IP - PIP (29074399) WAN Analysis Reporting (29074401) Access (29074400) | 29074399 29074401 29074400 | 50 MBPS (29074399) |  | 341886119 (Private IP (PIP)) 341886121 (WAN Analysis Reporting) 341886115 (Access) | C1090361/CANCEL (29074399) C1090361/ADD (29074399) E4044554/CANCEL (29074400) E4044554/ADD (29074400) |  | 6054836 | 25000 | PVC ID : 6054836 VPN Name : UnitedHealthGroup Router Name : NSVL3E03 VRF Name : V414602-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64804 PE IP Address : 152.192.109.113 CE Address : 152.192.109.114 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29074400) | 1000Base-SX (850nm, Multi Mode Fiber) (29074400) | Ethernet |  |  |  |  | 06/24/2019 (VFORCE) (29074400) |  |  |  | Marvetta Scott 1-615-493-8940 marvetta.scott@uhc.com | KEITH MANGENE | keith_mangene@optum.com | 1-860-702-8284 |  |  | 06/07/2019 (29074399) 06/05/2019 (29074400) | 06/26/2019 07/02/2019 | 05/20/2019 | 05/17/2019 (29074399) 05/17/2019 (29074401) 05/20/2019 (29074400) | Cancelled | N (29074399) N (29074401) N (29074400) | U0101953 | Jeopardy Notification 2 (05/07/2019) | NSPE0012848023 Order Request # 198661249 | NSPE0012848023
Cancelled | NC057 Fayetteville, NC | 4129 RAEFORD RD FAYETTEVILLE, NC 28304-3359 US | 1.5 MBPS (29074574) |  | 198665581 | NC057 | Private IP - PIP (29074573) WAN Analysis Reporting (29074575) Access (29074574) | 29074573 29074575 29074574 | 1.5 MBPS (29074573) |  | 94632708 (Private IP (PIP)) 94632713 (WAN Analysis Reporting) 94632710 (Access) | C0167322/CANCEL (29074573) C0167322/ADD (29074573) D1099895/CANCEL (29074574) D1099895/ADD (29074574) |  | 6054848 | 900 | PVC ID : 6054848 VPN Name : UnitedHealthGroup Router Name : GNJGE07 VRF Name : V369867:UnitedHealthGroup Encapsulation : PPP Routing Protocol : BGP BGP AS Number : 65036 PE IP Address : 68.139.178.169 CE Address : 68.139.178.170 QoS - Egress Profile: R12 |  | DS1 (29074574) | TDM | [8 empty] | Lisa McNamara 1-952-202-0242 lisa_mcnamara@uhg.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 |  |  | 05/22/2019 (29074573) 05/20/2019 (29074574) | 05/20/2019 05/24/2019 | 04/30/2019 | 04/30/2019 (29074573) 04/30/2019 (29074575) 04/30/2019 (29074574) | Cancelled | N (29074573) N (29074575) N (29074574) | U0101953 |  | NSPE0012848279 Order Request # 198662023 | NSPE0012848279
Cancelled | Carlsbad, CA | 2858 LOKER AVE E CARLSBAD, CA 92010-6666 US | 50 MBPS (29081387) | 05/08/2019: 5/8Background: 50 Mbps / 50 Mbps / Access, Private IP (PIP) / CARLSBAD, CA, US / TIME WARNER CABLE Status: Order onhold due to pending Property Management details > this is a migration order mandated by Verizon > ETL fees needed but UHG isnt willing to pay for it and Sales working on waiving the fees Next Action: Pending FOC Who owns the next action: LEC | 198671151 | Carlsbad | Private IP - PIP (29081386) WAN Analysis Reporting (29081388) Access (29081387) | 29081386 29081388 29081387 | 50 MBPS (29081386) |  | 342431175 (Private IP (PIP)) 342431177 (WAN Analysis Reporting) 342431171 (Access) | C4017193/CANCEL (29081386) C4017193/ADD (29081386) E4044581/CANCEL (29081387) E4044581/ADD (29081387) |  | 6054997 | 40000 | PVC ID : 6054997 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64895 PE IP Address : 152.192.109.29 CE Address : 152.192.109.30 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29081387) | 1000Base-SX (850nm, Multi Mode Fiber) (29081387) | Ethernet | [8 empty] | Nhan Phan 1-760-804-2335 NHANPHAN@optum.com | KEITHLEY HUGGINS | keithleyhuggins@optum.com | 1-770-767-8282 |  |  |  | 09/12/2019 09/18/2019 | 05/09/2019 | 05/07/2019 (29081386) 05/07/2019 (29081388) 05/09/2019 (29081387) | Cancelled | N (29081386) N (29081388) N (29081387) | U0101953 | Jeopardy Notification 2 (05/06/2019) | NSPE0012849452 Order Request # 198666033 | NSPE0012849452
Cancelled | Santa Ana, CA | 3110 W LAKE CENTER DR SANTA ANA, CA 92704-6917 US | 100 MBPS (29081438) | 05/15/2019: 5/16Background: 100 Mbps / 100 Mbps / Access, Private IP (PIP) / SANTA ANA, CA, US / TIME WARNER CABLE / Dual NID / 100bd offnet build Status: Order onhold due to pending Property Management details. > This is a migration mandated by Verizon > ETL fees needed and UHG not willing to pay them; sales working on waiving them Next Action: Pending FOC | 198671265 | Santa Ana | Access (29081438) Private IP - PIP (29081437) WAN Analysis Reporting (29081439) | 29081438 29081437 29081439 | 100 MBPS (29081437) |  | 338548541 (Access) 338548545 (Private IP (PIP)) 338548547 (WAN Analysis Reporting) | E4044577/ADD (29081438) E4044577/CANCEL (29081438) C1090387/CANCEL (29081437) C1090387/ADD (29081437) |  | 6054998 | 25000 | PVC ID : 6054998 VPN Name : UnitedHealthGroup Router Name : LSA29E02 VRF Name : V842045:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64822 PE IP Address : 68.139.38.37 CE Address : 68.139.38.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29081438) | 1000Base-SX (850nm, Multi Mode Fiber) (29081438) | Ethernet |  |  |  |  | 06/14/2019 (VFORCE) (29081438) |  |  |  | Richard Marcus 1-714-445-0404 richard_marcus@optum.com | KEITHLEY HUGGINS | keithleyhuggins@optum.com | 1-770-767-8282 |  |  |  | 09/12/2019 09/18/2019 | 05/21/2019 | 05/21/2019 (29081438) 05/17/2019 (29081437) 05/17/2019 (29081439) | Cancelled | N (29081438) N (29081437) N (29081439) | U0101953 | Jeopardy Notification 3 (05/11/2019) | NSPE0012850274 Order Request # 198669231 | NSPE0012850274
Cancelled | IL134 Moline, IL | 1 KONE CT MOLINE, IL 61265-1337 US | 50 MBPS (29082208) | 05/29/2019: 5/29 Background: IL134 50 Mbps / 10 Mbps / Access, Private IP (PIP) / MOLINE, IL, US / Dual NID / (ATT) Status: Correct address 101 17TH STREET MOLINE IL - To be cancelled and re-issued Next Action: Pending cancelation | 198671321 | IL134 | Private IP - PIP (29082207) WAN Analysis Reporting (29082209) Access (29082208) | 29082207 29082209 29082208 | 10 MBPS (29082207) |  | 94633377 (Private IP (PIP)) 94633375 (WAN Analysis Reporting) 94633379 (Access) | C4017207/ADD (29082207) C4017207/CANCEL (29082207) E4044582/CANCEL (29082208) E4044582/ADD (29082208) | c5a89 a89 0038 (I0184512.CFO) c5ueg d2dp0012 (I0000352.DVP) | 6055017 |  | PVC ID : 6055017 |  | 100Base-TX (29082208) | Ethernet |  |  | 06/10/2019 (I0184512.CFO) 06/10/2019 (I0000352.DVP) |  | 08/12/2019 (VFORCE) (29082208) |  |  |  | Matt Schabowski 1-952-202-0145 matthew_schabowski1@uhg.com | KEVIN CANTOR | kevin_cantor@optum.com | 632-588-5331 |  |  |  | 06/06/2019 06/12/2019 | 05/30/2019 | 05/29/2019 (29082207) 05/29/2019 (29082209) 05/30/2019 (29082208) | Cancelled | N (29082207) N (29082209) N (29082208) | U0101953 | Jeopardy Notification 3 (05/28/2019) | NSPE0012851309 Order Request # 198671243 | NSPE0012851309
Cancelled | TX435 AUSTIN, TX | 3016 GUADALUPE ST AUSTIN, TX 78705-2862 US | 100 MBPS (29263650) | 07/17/2019: 7/17Background: TX435 AUSTIN, TX; NEW 100M/50M PIP-ETH; (FPL); DUAL NID; NO MNS; Status: Order to be cancelled Next Action: | 198861493 | TX435 | Access (29263650) Private IP - PIP (29263649) WAN Analysis Reporting (29263651) | 29263650 29263649 29263651 | 50 MBPS (29263649) |  | 94639651 (Access) 94639648 (Private IP (PIP)) 94639655 (WAN Analysis Reporting) | E4046183/CANCEL (29263650) E4046183/ADD (29263650) C1091423/ADD (29263649) C1091423/CANCEL (29263649) |  | 6059764 | 30000 | PVC ID : 6059764 VPN Name : UnitedHealthGroup Router Name : IAEXE01 VRF Name : Vd39763-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64577 PE IP Address : 68.137.11.129 CE Address : 68.137.11.130 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29263650) | 1000Base-SX (850nm, Multi Mode Fiber) (29263650) | Ethernet | [8 empty] | Celeste Duarte 1-877-470-4608 Celeste.Duarte@avella.com | Solomon Victor | solomon_victor@optum.com | 91-804-670-4304 | 07/19/2019(Access) 07/19/2019(Private IP - PIP) |  |  | 08/27/2019 09/02/2019 | 07/19/2019 | 07/19/2019 (29263650) 07/18/2019 (29263649) 07/18/2019 (29263651) | Cancelled | N (29263650) N (29263649) N (29263651) | U0101953 |  | NSPE0012904149 Order Request # 198855391 | NSPE0012904149
Cancelled | FL417 Jacksonville, FL | 12854 KENAN DR JACKSONVILLE, FL 32258-7400 US | 100 MBPS (29294419) | 09/04/2019: 9/4Background: FL417 JACKSONVILLE, FL / 100 Mbps / 50 Mbps / Access, Private IP (PIP) / LEVEL 3 / dual nid Status: Cancelling request as per customer; equipment retrieval 09/10 too far out. Next Action: Order cancellation | 198912649 | FL417 | Access (29294419) Private IP - PIP (29294418) WAN Analysis Reporting (29294420) | 29294419 29294418 29294420 | 50 MBPS (29294418) |  | 94641008 (Access) 94641006 (Private IP (PIP)) 94641010 (WAN Analysis Reporting) | E4046370/CANCEL (29294419) E4046370/ADD (29294419) C1091597/ADD (29294418) C1091597/CANCEL (29294418) | FL/KXFN/163606/LVLC (2929441957229101) FL/KXFN/163606/LVLC (2929441957229104) | 6060582 | 30000 | PVC ID : 6060582 VPN Name : UnitedHealthGroup Router Name : JAPXE01 VRF Name : Vd46494-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64883 PE IP Address : 68.139.249.97 CE Address : 68.139.249.98 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29294419) | 1000Base-SX (850nm, Multi Mode Fiber) (29294419) | Ethernet | LEVEL 3 (2929441957229101) LEVEL 3 (2929441957229104) | 05/28/2019 (2929441957229101) 09/09/2019 (2929441957229104) | 07/05/2019 (2929441957229101) 10/21/2019 (2929441957229104) |  | 09/10/2019 (VFORCE) (29294419) |  |  |  | Jason Roseberry 1-952-202-1958 jason_roseberry@uhg.com | JASON SALAPING | jason_salaping@optum.com | 632-462-2446 | 09/06/2019(Access) 09/06/2019(Private IP - PIP) |  | 08/21/2019 (29294419) 08/23/2019 (29294418) | 07/16/2019 07/22/2019 | 09/06/2019 | 09/06/2019 (29294419) 08/06/2019 (29294418) 08/05/2019 (29294420) | Cancelled | N (29294419) N (29294418) N (29294420) | U0101953 | Jeopardy Notification 1 (08/02/2019) | NSPE0012913675 Order Request # 198908827 | NSPE0012913675
Cancelled | CIRT0002431 MEMPHIS, TN | 5960 E SHELBY DR MEMPHIS, TN 38141-7602 US | 20 MBPS (29427632) | 07/15/2019: 7/15Background: CIRT0002431 20 Mbps / Access, Internet Dedicated Services / MEMPHIS, TN, US / XO / DUAL NID / NO MNS Status: Cancelling order, customer not ready. CRD 10/01/2019. Action Taken: > ASR cancelled; awating order cancellation complete Next Action: SD to cancel order | 199295613 | Cardinal Health | Internet Dedicated Services (29427631) Access (29427632) | 29427631 29427632 | 20 MBPS (29427631) |  | 1166563357 (Internet Dedicated Services) 1166563353 (Access) | C3024428/ADD (29427631) C3024428/CANCEL (29427631) E3071783/ADD (29427632) E3071783/CANCEL (29427632) |  | 6063644 | 0 | PVC ID : 6063644 VPN Name : Internet Router Name : GW1MEM3 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 204.148.39.141 CE Address : 204.148.39.142 | 100Base-TX (29427632) | 100Base-TX (29427632) | Ethernet |  |  |  |  | 11/21/2019 (VFORCE) (29427632) |  |  |  | Rich Crossley 1-716-583-0633 RCrossley@harvarddruggroup.com | ED SANTANA | g44718@att.com | 1-888-334-7644 | 07/16/2019(Internet Dedicated Services) 07/16/2019(Access) |  |  | 07/25/2019 | 07/16/2019 | 07/10/2019 (29427631) 07/16/2019 (29427632) |  | N (29427631) N (29427632) | U0102647 |  |  | NSPE0012948841
Cancelled | TX431 SAN ANTONIO, TX | 410 W SUNSET RD STE 200 SAN ANTONIO, TX 78209-1736 US | 50 MBPS (29438583) | 06/27/2019: 6/27Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / SAN ANTONIO, TX, US / ATT Status: Order to be cancelled and re-issue > Address should be 430 W SUNSET Next Action: Pending cancellation | 199322831 | TX431 | Private IP - PIP (29438582) WAN Analysis Reporting (29438584) Access (29438583) | 29438582 29438584 29438583 | 10 MBPS (29438582) |  | 94647366 (Private IP (PIP)) 94647371 (WAN Analysis Reporting) 94647368 (Access) | C4018509/CANCEL (29438582) C4018509/ADD (29438582) E4047027/CANCEL (29438583) E4047027/ADD (29438583) |  | 6063869 | 5500 | PVC ID : 6063869 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65088 PE IP Address : 199.220.213.145 CE Address : 199.220.213.146 QoS - Egress Profile: R12 | 1000Base-SX-850nm (29438583) | 1000Base-SX (850nm, Multi Mode Fiber) (29438583) | Ethernet |  |  |  |  | 07/03/2019 (VFORCE) (29438583) |  |  |  | GABRIEL RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 06/28/2019(Private IP - PIP) 06/28/2019(Access) |  |  | 07/26/2019 08/01/2019 | 06/29/2019 | 06/28/2019 (29438582) 06/28/2019 (29438584) 06/28/2019 (29438583) | Cancelled | N (29438582) N (29438584) N (29438583) | U0101953 | Jeopardy Notification 1 (06/26/2019) | NSPE0012957518 Order Request # 199322723 | NSPE0012957518
Cancelled | IL134 Moline, IL | 101 17TH ST MOLINE, IL 61265 USA | 1.536 MBPS (IQBLR91Z) |  | 9963326 |  | Private IP (IQBLR91Z) | IQBLR91Z | 1.536 MBPS (IQBLR91Z) | P2261428 |  | BCBLGKV50001 (IQBLR91Z) BCBLGKV50002 (IQBLR91Z) BCBLGKV50003 (IQBLR91Z) BCBLGKV50004 (IQBLR91Z) BCBLGKV50005 (IQBLR91Z) BCBLGKV50006 (IQBLR91Z) BCBLGKV50007 (IQBLR91Z) | [15 empty] | MATT SCHABOWSKI 0018152070145 MATTHEW_SCHABOWSKI1@UHG.COM | [5 empty] | 08/08/2019 (IQBLR91Z) | 08/02/2019 (IQBLR91Z) |  |  |  | N (IQBLR91Z) | 05650532 |  | NSPE0012996369 CW 199442019 | NSPE0012996369
Cancelled | AZ731-02-IJ PHOENIX, AZ, US | 615 N 48TH ST PHOENIX, AZ 85008-6608 US | 1 GBPS (29718090) | 07/30/2019: 7/30Background: 1 Gbps / 500 Mbps / Access, Private IP (PIP) / PHOENIX, AZ, US Status: Asr sent 7/29 Next Action: Who owns the next action: Prov Team | 199603295 | Phoenix _ AZ731-02-IJ | Private IP - PIP (29718089) WAN Analysis Reporting (29718091) Access (29718090) | 29718089 29718091 29718090 | 500 MBPS (29718089) |  | 1181165059 (Private IP (PIP)) 1181165069 (WAN Analysis Reporting) 1181165051 (Access) | C0172863/CANCEL (29718089) C0172863/ADD (29718089) E5019752/ADD (29718090) E5019752/CANCEL (29718090) |  | 6073840 |  | PVC ID : 6073840 | 1000Base-SX-850nm (29718090) | 1000Base-SX (850nm, Multi Mode Fiber) (29718090) | Ethernet | [8 empty] | CLIFF WALDREP 1-480-881-8560 clifton.waldrep@avella.com | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 |  |  |  | 09/06/2019 09/12/2019 | 07/31/2019 | 07/31/2019 (29718089) 07/31/2019 (29718091) 07/31/2019 (29718090) | Cancelled | N (29718089) N (29718091) N (29718090) | U0101953 |  | NSPE0013049976 Order Request # 199601705 | NSPE0013049976
Cancelled |  |  |  |  | 9975979 |  | EVC/PVC Service Private IP Port Only | [20 empty] | JOHN SERGOT 7637441582 JOHN_SERGOT@OPTUM.COM | [10 empty] | N |  |  | NSPE0013053579 CW 199607879 | NSPE0013053579
Cancelled |  |  |  |  | 9975986 |  | EVC/PVC Service Private IP Port Only | [20 empty] | JOHN SERGOT 7637441582 JOHN_SERGOT@OPTUM.COM | [10 empty] | N |  |  | NSPE0013053586 CW 199607131 | NSPE0013053586
Cancelled |  |  |  |  | 9977340 |  | EVC/PVC Service | [20 empty] | UHT NCC 7637443000 JOHN_SERGOT@UHG.COM | [10 empty] | N |  |  | NSPE0013056462 CW 199614769 | NSPE0013056462
Cancelled | AZ731-02-IJ PHOENIX, AZ | 615 N 48TH ST PHOENIX, AZ 85008-6608 US | 1 GBPS (29726685) | 08/07/2019: 8/7Background: 1 Gbps / 500 Mbps / Access, Private IP (PIP) / PHOENIX, AZ, US / COX Status: Pending Cancellation Next Action: Order cancellation Who owns the next action: SD | 199612445 | Phoenix _ AZ731-02-IJ | Private IP - PIP (29726684) WAN Analysis Reporting (29726686) Access (29726685) | 29726684 29726686 29726685 | 500 MBPS (29726684) |  | 1181829537 (Private IP (PIP)) 1181829539 (WAN Analysis Reporting) 1181829533 (Access) | C0172997/ADD (29726684) C0172997/CANCEL (29726684) E5019798/CANCEL (29726685) E5019798/ADD (29726685) |  | 6074236 |  | PVC ID : 6074236 | 1000Base-SX-850nm (29726685) | 1000Base-SX (850nm, Multi Mode Fiber) (29726685) | Ethernet | [8 empty] | CLIFF WALDREP 1-480-881-8560 clifton.waldrep@avella.com | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 |  |  |  | 09/09/2019 09/13/2019 | 08/12/2019 | 08/02/2019 (29726684) 08/02/2019 (29726686) 08/12/2019 (29726685) | Approved | N (29726684) N (29726686) N (29726685) | U0101953 |  | NSPE0013053913 Order Request # 199612195 | NSPE0013053913
Cancelled | TX493-04-IM | 615 N ZARAGOZA RD EL PASO, TX 79907 USA | 1.536 MBPS (IQBLT8Z3) | 06/03/2020: Order Canceled on Dec 4, 2019 | 10021882 |  | Private IP (IQBLT8Z3) EVC/PVC Service (N.12125169.6083865) | IQBLT8Z3 N.12125169.6083865 | 10.752 MBPS | P2307997 |  | BCBLJG110001 (IQBLT8Z3) BCBLJG110002 (IQBLT8Z3) BCBLJG110003 (IQBLT8Z3) BCBLJG110004 (IQBLT8Z3) BCBLJG110005 (IQBLT8Z3) BCBLJG110006 (IQBLT8Z3) BCBLJG110007 (IQBLT8Z3) |  | 6083865 | 7200 | VPN Name : UnitedHealthGroup Router Name : SAJ3E01 VRF Name : V297173-UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 65030 PE IP Address : 199.220.144.189 CE Address : 199.220.144.190 QoS - Egress Profile: R12 PVC ID : 6083865 | [11 empty] | JASON OZER 0019157793583 2109513251 JOZER@WELLMED.NET | [5 empty] | 12/04/2019 (IQBLT8Z3) | 10/17/2019 (IQBLT8Z3) |  | 10/17/2019 (12125169) |  | N (IQBLT8Z3) N (N.12125169.6083865) | 05017789 P2307997 |  | NSPE0013152308 NSPE0013152308 NSPE0013152352 | NSPE0013152352
Cancelled | NY498 | 161 Canal St New York, NY 10013-4518 US | 50 MBPS (30093885) | 10/21/2019: 10/21Background:50MBPS 10MBPS PIP-E New York, NY Status: Pending Cancel Next action: Order to be cancel'd changing Lecs | 199945961 | NY498 | WAN Analysis Reporting (30093886) Access (30093885) Private IP - PIP (30093884) | 30093886 30093885 30093884 | 10 MBPS (30093884) |  | 94678323 (WAN Analysis Reporting) 94678320 (Access) 94678318 (Private IP (PIP)) | C4019797/CANCEL (30093884) C4019797/ADD (30093884) E4050344/ADD (30093885) E4050344/CANCEL (30093885) |  | 6083773 | 5500 | PVC ID : 6083773 VPN Name : UnitedHealthGroup Router Name : NV89E01 VRF Name : V105387:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64607 PE IP Address : 206.115.40.93 CE Address : 206.115.40.94 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30093885) | 1000Base-SX (850nm, Multi Mode Fiber) (30093885) | Ethernet |  |  |  |  | 10/25/2019 (VFORCE) (30093885) |  |  |  | Alex Ray 1-919-830-9567 Alexander_Ray@UHG.com | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 10/23/2019(Private IP - PIP) 10/23/2019(Access) |  |  | 02/17/2020 02/11/2020 | 10/23/2019 | 10/18/2019 (30093886) 10/23/2019 (30093885) 10/18/2019 (30093884) | Cancelled | N (30093886) N (30093885) N (30093884) | U0101953 | Jeopardy Notification 1 (10/16/2019) | NSPE0013175657 | NSPE0013175657
Cancelled | UMNEA | 513 Eaton St Saint Paul, MN 55107-2474 US | 50 MBPS (30260617) | 12/18/2019: 12/18Background: 50 Mbps / 20 Mbps / Access, Private IP (PIP) / Saint Paul, MN, US / CENTURYLINK Status: CANCELLED - Pending equip retrieval Next Action: n/a Who owns the next action: n/a | 200118073 | UMNEA MN003 | Private IP - PIP (30260616) WAN Analysis Reporting (30260618) Access (30260617) | 30260616 30260618 30260617 | 20 MBPS (30260616) |  | 94689693 (Private IP (PIP)) 94689689 (WAN Analysis Reporting) 94689691 (Access) | C4020090/ADD (30260616) C4020090/CANCEL (30260616) E4051124/ADD (30260617) E4051124/CANCEL (30260617) |  | 6088070 | 13000 | PVC ID : 6088070 VPN Name : UnitedHealthGroup Router Name : MN39E01 VRF Name : V463532:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64564 PE IP Address : 152.161.13.169 CE Address : 152.161.13.170 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30260617) | 1000Base-SX (850nm, Multi Mode Fiber) (30260617) | Ethernet |  |  |  |  | 02/18/2020 (VFORCE) (30260617) |  |  |  | PAUL STORVICK 1-651-528-5315 paul.storvick@uhg.com | Joseph Mark Sanorjo | joseph_sanorjo@optum.com | 632-790-6484 | 12/19/2019(Private IP - PIP) 12/19/2019(Access) |  | 04/17/2020 (30260616) 04/15/2020 (30260617) | 11/25/2019 11/29/2019 | 12/19/2019 | 12/02/2019 (30260616) 12/02/2019 (30260618) 12/19/2019 (30260617) | Cancelled | N (30260616) N (30260618) N (30260617) | U0101953 |  | NSPE0013237705 | NSPE0013237705
Cancelled | NY498 | 161 Canal St New York, NY 10013-4518 US | 50 MBPS (30366516) | 04/30/2020: Charges not approved. Pending cancel completion. | 200141435 | NY498 | Private IP - PIP (30366515) WAN Analysis Reporting (30366517) Access (30366516) | 30366515 30366517 30366516 | 10 MBPS (30366515) |  | 94692340 (Private IP (PIP)) 94692338 (WAN Analysis Reporting) 94692336 (Access) | C4020248/ADD (30366515) C4020248/CANCEL (30366515) E4051557/CANCEL (30366516) E4051557/ADD (30366516) |  | 6090546 |  | PVC ID : 6090546 VPN Name : UnitedHealthGroup Router Name : NV89E02 VRF Name : V101790:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64607 PE IP Address : 68.136.11.185 CE Address : 68.136.11.186 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30366516) | 1000Base-SX (850nm, Multi Mode Fiber) (30366516) | Ethernet | [6 empty] | DEMARCDET - NA |  | Alex Ray 1-919-830-9567 Alexander_Ray@UHG.com | Joseph Sanorjo | joseph_sanorjo@optum.com | 632-790-6484 |  |  | 02/10/2020 (30366515) 02/06/2020 (30366516) | 03/30/2020 04/03/2020 | 04/30/2020 | 04/29/2020 (30366515) 04/29/2020 (30366517) 04/30/2020 (30366516) | Cancelled | N (30366515) N (30366517) N (30366516) | U0101953 | Jeopardy Notification 3 (02/15/2020) | NSPE0013246281 | NSPE0013246281
Cancelled | MA093 | 500 Unicorn Park Dr Woburn, MA 01801-3377 US | 300 MBPS | 11/21/2019: 11/21Background: 300MBS 200MBPS PIP-E Woburn, MA VZT Status: Scon identified for this site. Quote has been provided to the customer pending approval Next action: Pending Scon quote approval Who owns the next action: Customer/OM/Prov | 200178307 | MA093 | WAN Analysis Reporting Private IP - PIP Access |  | 200 MBPS |  | 94695550 94695547 94695552 | [5 empty] | 1000Base-SX-850nm | 1000Base-SX (850nm, Multi Mode Fiber) | Ethernet | [8 empty] | Brian Meehan 1-781-305-2385 Bmeehan@equia.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 |  |  |  | 12/09/2019 12/03/2019 |  |  |  | N | U0101953 |  | NSPE0013258711 | NSPE0013258711
Cancelled | NY498 | 161 CANAL ST NEW YORK, NY 10013 USA | 1.536 MBPS (IQBLVKJJ) | 06/03/2020: Order Canceled on Dec 24, 2019 | 10044252 |  | EVC/PVC Service (N.12152542.6089993) Private IP (IQBLVKJJ) | N.12152542.6089993 IQBLVKJJ | 10.752 MBPS | P2309526 |  | BCBLJJXR0001 (IQBLVKJJ) BCBLJJXR0002 (IQBLVKJJ) BCBLJJXR0003 (IQBLVKJJ) BCBLJJXR0004 (IQBLVKJJ) BCBLJJXR0005 (IQBLVKJJ) BCBLJJXR0006 (IQBLVKJJ) BCBLJJXR0007 (IQBLVKJJ) |  | 6089993 | 5520 | PVC ID : 6089993 VPN Name : UnitedHealthGroup Router Name : HLB9E01 VRF Name : V385919:UnitedHealthGroup Encapsulation : MLPPP Routing Protocol : BGP BGP AS Number : 64607 PE IP Address : 152.181.42.221 CE Address : 152.181.42.222 QoS - Egress Profile: R12 | [11 empty] | ALEX RAY 9198309567 0012129415823 ALEXANDER_RAY@UHG.COM | [5 empty] | 12/24/2019 (IQBLVKJJ) | 12/19/2019 (IQBLVKJJ) |  | 12/23/2019 (12152542) |  | N (N.12152542.6089993) N (IQBLVKJJ) | P2309526 05017789 |  | NSPE0013257096 | NSPE0013257096
Cancelled | TX546 | 1901 W William Cannon Dr Austin, TX 78745-5371 US | 50 MBPS (30390258) | 01/08/2020: 1/8Background: 50 Mbps / 50 Mbps / Access, Private IP (PIP) / Austin, TX, US / TIME WARNER CABLE Status: Pending FOC Pending pole permits before construction can begin Next Action: FOC Issuance Who owns the next action: prov/lec | 200248675 | TX546 | WAN Analysis Reporting (30390259) Access (30390258) Private IP - PIP (30390257) | 30390259 30390258 30390257 | 50 MBPS (30390257) |  | 94702653 (WAN Analysis Reporting) 94702655 (Access) 94702658 (Private IP (PIP)) | C4020285/ADD (30390257) C4020285/CANCEL (30390257) E4051646/CANCEL (30390258) E4051646/ADD (30390258) |  | 6091022 | 5500 | PVC ID : 6091022 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65416 PE IP Address : 68.137.176.77 CE Address : 68.137.176.78 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30390258) | 1000Base-SX (850nm, Multi Mode Fiber) (30390258) | Ethernet |  |  |  |  | 01/20/2020 (VFORCE) (30390258) |  |  |  | RICK WILLIAMSON 1-210-951-3129 rwilliamson@wellmed.net | Stanimir Boshnakov | stanimir_boshnakov@optum.com | 1-763-765-8073 | 01/14/2020(Private IP - PIP) 01/14/2020(Access) |  |  | 03/25/2020 03/19/2020 | 01/14/2020 | 01/13/2020 (30390259) 01/14/2020 (30390258) 01/13/2020 (30390257) | Cancelled | N (30390259) N (30390258) N (30390257) | U0101953 | Jeopardy Notification 1 (11/01/2019) |  | NSPE0013284021
Cancelled | for moved order 197185299 | 9999 KENWORTHY ST STE A EL PASO, TX 79924-4413 US | 50 MBPS (30412503) | 02/19/2020: 2/19Background: LEC circuit moved order Status: Order pending cancelation Next action: cancelled Who owns the next action: customer | 200269051 | TX079-05-IM | Access (30412503) Private IP - PIP WAN Analysis Reporting (30412504) | 30412503 30412504 | 20 MBPS |  | 94570166 (Access) 94570162 94570160 (WAN Analysis Reporting) | E4036994/NONE (30412503) |  |  |  |  | 100Base-TX (30412503) | 100Base-TX (30412503) | Ethernet | [8 empty] | GABRIEL RODRIGUEZ 1-210-833-8929 grodriguez1@wellmed.net | Sahil Tuteja | sahil_tuteja@optum.com | 91-828-567-0647 | 02/20/2020(Access) |  |  | 01/29/2020 01/29/2020 (23980307.2) | 02/20/2020 | 02/20/2020 (30412503) 02/20/2020 (30412504) | Cancelled Order Canceled | N (30412503) N N (30412504) | U0101953 | Jeopardy Notification 4 (01/18/2020) |  | NSPE0013292217
Cancelled | IN710-01-IM | 731 W HENRY ST INDIANAPOLIS, IN 46225-1114 US | 1 GBPS (30197772) | 11/22/2019: 11/22Background: 1 Gbps / 500 Mbps / Access, Private IP (PIP) / INDIANAPOLIS, IN, US / LIGHT TOWER Status: Loop delivered at the wrong address > options will be coordinated with LCON and PCC EMULATED NID and customer to extend Demark from LEC Demark to Cx demark > Cancel and Re-issue if the cx does not want to extend circuit Next Action: confirmation on the address issue Who owns the next action: customer/ OM Next update due by:11/25/2019 | 200052885 | IN710-01-IM | Private IP - PIP (30197771) WAN Analysis Reporting (30197773) Access (30197772) | 30197771 30197773 30197772 | 500 MBPS (30197771) |  | 1202159385 (Private IP (PIP)) 1202159387 (WAN Analysis Reporting) 1202159381 (Access) | C0176785/CANCEL (30197771) C0176785/ADD (30197771) E5021095/CANCEL (30197772) E5021095/ADD (30197772) |  | 6086574 | 35000 | PVC ID : 6086574 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64584 PE IP Address : 152.183.245.209 CE Address : 152.183.245.210 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30197772) | 1000Base-SX (850nm, Multi Mode Fiber) (30197772) | Ethernet | [6 empty] | DEMARCDET - 2ND FLR RM RR 217 09 MRV 606 PORT 5 |  | Stephen Klein 1-317-806-2035 Sklein@equian.com | Edward Stiles | edward.stiles@optum.com | 1-763-361-7959 | 11/26/2019(Private IP - PIP) 11/26/2019(Access) |  | 12/09/2019 (30197771) 12/05/2019 (30197772) | 11/14/2019 11/20/2019 | 11/26/2019 | 11/22/2019 (30197771) 11/22/2019 (30197773) 11/26/2019 (30197772) | Cancelled | N (30197771) N (30197773) N (30197772) | U0101953 | Jeopardy Notification 1 (11/21/2019) | NSPE0013212631 | NSPE0013212631
Cancelled | TX537 | 800 N Bishop Ave ste 2 Dallas, TX 75208-4203 US | 50 MBPS (30564044) | 12/05/2019: 12/5Background: 50 Mbps / 10 Mbps / Access, Private IP (PIP) / Dallas, TX, US Status: Pending Cancel Next Action: Who owns the next action: Prov Team | 200435825 | TX537 | Private IP - PIP (30564043) WAN Analysis Reporting (30564045) Access (30564044) | 30564043 30564045 30564044 | 10 MBPS (30564043) |  | 94719303 (Private IP (PIP)) 94719305 (WAN Analysis Reporting) 94719307 (Access) | C4020534/ADD (30564043) C4020534/CANCEL (30564043) E4052510/ADD (30564044) E4052510/CANCEL (30564044) |  | 6094742 | 5500 | PVC ID : 6094742 VPN Name : UnitedHealthGroup Router Name : IAE9E01 VRF Name : V501266:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65410 PE IP Address : 68.138.44.221 CE Address : 68.138.44.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (30564044) | 1000Base-SX (850nm, Multi Mode Fiber) (30564044) | Ethernet | [8 empty] | MARCO WONG 1-214-493-4068 mwong@wellmed.net | MANISH SARKHEL | manish_sarkhel@optum.com | 91-120-671-2655 | 12/04/2019(Private IP - PIP) 12/04/2019(Access) |  |  | 01/03/2020 01/09/2020 | 12/04/2019 | 12/02/2019 (30564043) 12/02/2019 (30564045) 12/04/2019 (30564044) | Cancelled | N (30564043) N (30564045) N (30564044) | U0101953 | Jeopardy Notification 1 (12/02/2019) |  | NSPE0013341303
Cancelled | TARRYTOWN, NY |  | 1 GBPS | 12/07/2019: Background: TOSA Status: Pending Cancellation > will monitor the diso related SO# 200301373 Next action: Disco completed then Cancellation Who owns the next action: disco team | 200435829 |  | Access Private IP - PIP |  | 1 GBPS |  | 57546618 57546619 | [6 empty] | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Patrick Hermanto Patrick Hermanto 1-914-909-1837 patrick.hermanto@alere.com | Tony epperson | tony.epperson@alere.com | 1-312-315-5612 |  |  |  | 01/01/2020 |  |  |  | N | U0101953 |  | TOSA | NSPE0013326255
Cancelled | AZ032 | 1981 N Pebble Creek Pkwy Goodyear, AZ 85395-2543 US | 50 MBPS (30845200) | 02/13/2020: 2/13-Status Cancelation is complete however order is still reflecting in PAM | 201634987 | AZ032-02-IJ GOODYEAR, AZ | Private IP - PIP (30845199) WAN Analysis Reporting (30845201) Access (30845200) | 30845199 30845201 30845200 | 10 MBPS (30845199) |  | 94741234 (Private IP (PIP)) 94741236 (WAN Analysis Reporting) 94741232 (Access) | C4021190/ADD (30845199) C4021190/CANCEL (30845199) E4054086/ADD (30845200) E4054086/CANCEL (30845200) |  | 6101665 |  | PVC ID : 6101665 | 1000Base-SX-850nm (30845200) | 1000Base-SX (850nm, Multi Mode Fiber) (30845200) | Ethernet | [8 empty] | Vicki West 1-602-735-0390 vicki.west@optum.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 | 01/24/2020(Private IP - PIP) 01/24/2020(Access) |  |  | 04/17/2020 04/23/2020 | 01/24/2020 | 01/23/2020 (30845199) 01/23/2020 (30845201) 01/24/2020 (30845200) | Cancelled | N (30845199) N (30845201) N (30845200) | U0101953 |  |  | NSPE0013450096
Cancelled |  | 511 11TH AVE S MINNEAPOLIS, MN 55415-1537 US |  | 01/24/2020: Your order is on track: Provisioning Department accepted the order on Jan 24, 2020 and has begun processing. | 201893801 | 511 | Access (30935286) Private IP - PIP WAN Analysis Reporting (30935287) | 30935286 30935287 | 500 MBPS |  | 337301365 (Access) 337301409 337301411 (WAN Analysis Reporting) | [6 empty] | 1000Base-LX (1310nm Single Mode Fiber) (30935286) | Ethernet | [8 empty] | Scott Mccrady 1-612-800-6534 scott.mccrady@cologix.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 | 01/28/2020(Access) |  |  | 02/24/2020 02/24/2020 (26386541.1) | 01/28/2020 | 01/28/2020 (30935286) 01/28/2020 (30935287) | Cancelled Requested Due Date | N (30935286) N N (30935287) | U0101953 |  |  | NSPE0013481099
Cancelled |  | 511 11TH AVE S MINNEAPOLIS, MN 55415-1537 US |  | 02/06/2020: Order Canceled on Feb 6, 2020 | 201978537 | 511 | Private IP - PIP (30967429) Access WAN Analysis Reporting (30967431) | 30967429 30967431 | 500 MBPS (30967429) |  | 337301409 (Private IP (PIP)) 337301365 337301411 (WAN Analysis Reporting) | C0167608/NONE (30967429) |  | 6051867 | 250000 | PVC ID : 6051867 VPN Name : UHG-OFE Router Name : MN39E01 VRF Name : Vc13322:UHGOFE Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65483 PE IP Address : 68.138.244.229 CE Address : 68.138.244.230 QoS - Egress Profile: G1 |  | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Scott Mccrady 1-612-800-6534 scott.mccrady@cologix.com | WILLIAM GOSS | william_goss@optum.com | 1-763-744-1528 |  |  | 01/31/2020 (30967429) | 02/07/2020 02/07/2020 (26386541.2) | 02/06/2020 | 02/06/2020 (30967429) 02/06/2020 (30967431) | Cancelled Order Canceled | N (30967429) N N (30967431) | U0101953 |  |  | NSPE0013490523
Cancelled | TX013 | 1301 W President George Bush Hwy Richardson, TX 75080-1135 US | 300 MBPS (31110560) | 06/11/2020: Pending cancel complete. | 202094437 | TX023-05-IJ Richardson | Private IP - PIP (31110559) WAN Analysis Reporting (31110561) Access (31110560) | 31110559 31110561 31110560 | 150 MBPS (31110559) |  | 94756653 (Private IP (PIP)) 94756658 (WAN Analysis Reporting) 94756655 (Access) | C5009232/CANCEL (31110559) C5009232/ADD (31110559) E5023717/ADD (31110560) E5023717/CANCEL (31110560) |  | 6108387 |  | PVC ID : 6108387 | 1000Base-SX-850nm (31110560) | 1000Base-SX (850nm, Multi Mode Fiber) (31110560) | Ethernet |  |  |  |  | 07/09/2020 (VFORCE) (31110560) |  |  |  | JORGE ALVAREZ 1-214-273-8767 jorge_alvarez@optum.com | JOHN RICHARD RAYMUNDO | john_raymundo@optum.com | 632-588-5392 |  |  | 05/13/2020 (31110559) 05/11/2020 (31110560) | 05/05/2020 05/11/2020 | 06/12/2020 | 06/10/2020 (31110559) 06/10/2020 (31110561) 06/12/2020 (31110560) | Cancelled | N (31110559) N (31110561) N (31110560) | U0101953 |  |  | NSPE0013530406
Cancelled | IL137-01-IM | 1000 E Warrenville Rd ste 200 Naperville, IL 60563-3574 US | 300 MBPS (31341708) | 06/30/2020: Order Canceled on Jun 30, 2020 | 202314639 | IL137 | Private IP - PIP (31341707) WAN Analysis Reporting (31341709) Access (31341708) | 31341707 31341709 31341708 | 200 MBPS (31341707) |  | 94774531 (Private IP (PIP)) 94774528 (WAN Analysis Reporting) 94774526 (Access) | C5009523/CANCEL (31341707) C5009523/ADD (31341707) E5024485/ADD (31341708) E5024485/CANCEL (31341708) |  | 6113520 |  | PVC ID : 6113520 | 1000Base-SX-850nm (31341708) | 1000Base-SX (850nm, Multi Mode Fiber) (31341708) | Ethernet |  |  |  |  | 01/08/2021 (VFORCE) (31341708) |  |  |  | Gregg Gustafson 1-312-919-0017 gregg_gustafson@uhg.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 | 06/30/2020(Private IP - PIP) 06/30/2020(Access) |  | 07/09/2020 (31341707) 07/07/2020 (31341708) | 08/03/2020 08/07/2020 | 06/30/2020 | 06/30/2020 (31341707) 06/30/2020 (31341709) 06/30/2020 (31341708) | Cancelled | N (31341707) N (31341709) N (31341708) | U0101953 |  |  | NSPE0013597965
Cancelled |  | 425 Market St San Francisco, CA 94105-2532 US | 300 MBPS (31423783) | 10/22/2020: Order Canceled on Oct 22, 2020 | 202393781 | UNITED HEALTH GROUP | Private IP - PIP (31423782) WAN Analysis Reporting (31423784) Access (31423783) | 31423782 31423784 31423783 | 200 MBPS (31423782) |  | 94778905 (Private IP (PIP)) 94778907 (WAN Analysis Reporting) 94778909 (Access) | C5009668/ADD (31423782) C5009668/CANCEL (31423782) E5024810/ADD (31423783) E5024810/CANCEL (31423783) |  | 6115403 |  | PVC ID : 6115403 |  | 1000Base-SX (850nm, Multi Mode Fiber) (31423783) | Ethernet |  |  |  |  | 04/10/2020 (CCP) (31423782) 04/10/2020 (CCP) (31423783) | 04/24/2020 (CCP) (31423782) 04/24/2020 (CCP) (31423783) |  |  | Elizabeth Hasychak 1-415-547-5291 elizabeth.hasychak@optum.com | SUSHIL KUMAR | sushil_gautam@uhc.com | 1-612-855-7475 |  |  | 04/23/2020 (31423782) 04/21/2020 (31423783) | 05/01/2020 05/07/2020 | 10/22/2020 | 10/21/2020 (31423782) 10/21/2020 (31423784) 10/22/2020 (31423783) | Cancelled | N (31423782) N (31423784) N (31423783) | U0101953 |  |  | NSPE0013627167
Cancelled | TX057 | 12668 Silicon Dr San Antonio, TX 78249-3411 US | 100 MBPS (31429625) | 03/31/2020: Your order is on track: Cancel Request submitted and is in progress. | 202405013 | ENT TX057 SAN ANTONIO | WAN Analysis Reporting (31429626) Access (31429625) Private IP - PIP (31429624) | 31429626 31429625 31429624 | 50 MBPS (31429624) |  | 94779220 (WAN Analysis Reporting) 94779216 (Access) 94779213 (Private IP (PIP)) | C1104662/ADD (31429624) C1104662/CANCEL (31429624) E4057225/ADD (31429625) E4057225/CANCEL (31429625) |  | 6115486 |  | PVC ID : 6115486 | 1000Base-SX-850nm (31429625) | 1000Base-SX (850nm, Multi Mode Fiber) (31429625) | Ethernet | [8 empty] | Antonio M Arellano 1-210-270-4808 Tony.Arellano@uhc.com | Sushil Gautam | sushil_gautam@uhc.com | 91-124-309-5736 | 04/01/2020(Private IP - PIP) 04/01/2020(Access) |  |  | 05/08/2020 05/04/2020 | 04/01/2020 | 03/31/2020 (31429626) 04/01/2020 (31429625) 03/31/2020 (31429624) | Cancelled | N (31429626) N (31429625) N (31429624) | U0101953 |  |  | NSPE0013630212
Cancelled | TX013 | 1301 W President George Bush Hwy Richardson, TX 75080-1135 US | 50 MBPS (31429527) | 06/06/2020: Order Canceled on Jun 6, 2020 | 202406193 | TX023-05-IJ Richardson | Private IP - PIP (31429526) WAN Analysis Reporting (31429528) Access (31429527) | 31429526 31429528 31429527 | 20 MBPS (31429526) |  | 94779022 (Private IP (PIP)) 94779024 (WAN Analysis Reporting) 94779026 (Access) | C4022300/CANCEL (31429526) C4022300/ADD (31429526) E4057223/CANCEL (31429527) E4057223/ADD (31429527) |  | 6115480 |  | PVC ID : 6115480 | 1000Base-SX-850nm (31429527) | 1000Base-SX (850nm, Multi Mode Fiber) (31429527) | Ethernet |  |  |  |  | 07/09/2020 (VFORCE) (31429527) |  |  |  | Nancy Ferrer 1-972-372-1284 nancy.ferrer@optum.com | Sushil Gautam | sushil_gautam@uhc.com | 91-124-309-5736 | 06/05/2020(Private IP - PIP) 06/05/2020(Access) |  | 07/21/2020 (31429526) 07/17/2020 (31429527) | 05/04/2020 05/08/2020 | 06/06/2020 | 06/05/2020 (31429526) 06/05/2020 (31429528) 06/05/2020 (31429527) | Cancelled | N (31429526) N (31429528) N (31429527) | U0101953 |  |  | NSPE0013629853
Cancelled |  | 2700 Midwest Dr Onalaska, WI 54650-8763 US | 100 MBPS (31438304) | 05/25/2020: Order Canceled on May 21, 2020 | 202416025 | UNITED HEALTH GROUP | Private IP - PIP (31438303) WAN Analysis Reporting (31438305) Access (31438304) | 31438303 31438305 31438304 | 50 MBPS (31438303) |  | 94779223 (Private IP (PIP)) 94779230 (WAN Analysis Reporting) 94779226 (Access) | C1104697/CANCEL (31438303) C1104697/ADD (31438303) E4057270/CANCEL (31438304) E4057270/ADD (31438304) |  | 6115742 |  | PVC ID : 6115742 | 1000Base-LX-1310nm (31438304) | 1000Base-LX (1310nm Single Mode Fiber) (31438304) | Ethernet |  |  |  |  | 03/19/2021 (VFORCE) (31438304) |  |  |  | Nick Frank 1-608-783-8842 nick_frank@uhg.com | Sushil Gautam | sushil_gautam@uhc.com | 91-124-309-5736 |  |  |  | 05/05/2020 05/11/2020 | 05/21/2020 | 05/20/2020 (31438303) 05/20/2020 (31438305) 05/21/2020 (31438304) | Cancelled | N (31438303) N (31438305) N (31438304) | U0101953 |  |  | NSPE0013631981
Cancelled | CT039-10-IJ | 185 Asylum St Hartford, CT 06103-3408 US | 500 MBPS (31497757) | 05/07/2020: Pending cancel completion. | 202475747 | CT039-10-IJ UHG hartford | WAN Analysis Reporting (31497758) Access (31497757) Private IP - PIP (31497756) | 31497758 31497757 31497756 | 400 MBPS (31497756) |  | 94781922 (WAN Analysis Reporting) 94781926 (Access) 94781924 (Private IP (PIP)) | C5009744/ADD (31497756) C5009744/CANCEL (31497756) E5025042/ADD (31497757) E5025042/CANCEL (31497757) |  | 6117226 | 250000 | PVC ID : 6117226 VPN Name : UnitedHealthGroup Router Name : SMF9E01 VRF Name : V455688:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65153 PE IP Address : 152.177.117.153 CE Address : 152.177.117.154 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) (31497757) | Ethernet |  |  |  |  | 06/11/2020 (CCP) (31497756) 06/11/2020 (CCP) (31497757) | 06/09/2020 (CCP) (31497756) 06/09/2020 (CCP) (31497757) |  |  | Keith Mangene 1-860-702-8284 keith_mangene@optum.com | PHILIP JOSEPH DAMASCO II | philip_damasco@optum.com | 632-790-6235 | 05/07/2020(Access) |  | 05/14/2020 (31497756) 05/12/2020 (31497757) | 06/03/2020 05/28/2020 | 05/07/2020 | 05/07/2020 (31497758) 05/07/2020 (31497757) 05/07/2020 (31497756) | Cancelled | N (31497758) N (31497757) N (31497756) | U0101953 |  |  | NSPE0013651314
Cancelled | TX428 | 5627 University Hts bldg B San Antonio, TX 78249-3582 US | 100 MBPS (31559039) | 04/22/2020: Your order is on track: Cancel Request submitted and is in progress. | 202530703 | TX428 | Private IP - PIP (31559038) WAN Analysis Reporting (31559040) Access (31559039) | 31559038 31559040 31559039 | 50 MBPS (31559038) |  | 94784268 (Private IP (PIP)) 94784271 (WAN Analysis Reporting) 94784265 (Access) | C1105266/CANCEL (31559038) C1105266/ADD (31559038) E4057909/CANCEL (31559039) E4057909/ADD (31559039) |  | 6118414 |  | PVC ID : 6118414 | 1000Base-SX-850nm (31559039) | 1000Base-SX (850nm, Multi Mode Fiber) (31559039) | Ethernet |  |  |  |  | 05/26/2020 (VFORCE) (31559039) |  |  |  | JASON STEN 1-913-323-1014 jason.r.sten@optum.com | JASON SALAPING | jason_salaping@gmail.com | 632-462-2446 |  |  |  | 05/20/2020 05/26/2020 | 04/22/2020 | 04/21/2020 (31559038) 04/21/2020 (31559040) 04/22/2020 (31559039) | Cancelled | N (31559038) N (31559040) N (31559039) | U0101953 |  |  | NSPE0013671675
Cancelled | CA459 | 9055 Las Tunas Dr ste 120 Temple City, CA 91780-1813 US | 50 MBPS (31569760) | 05/07/2020: Cancel complete. | 202539237 | CA459 | Private IP - PIP (31569759) WAN Analysis Reporting (31569761) Access (31569760) | 31569759 31569761 31569760 | 10 MBPS (31569759) |  | 94784543 (Private IP (PIP)) 94784538 (WAN Analysis Reporting) 94784540 (Access) | C4022499/CANCEL (31569759) C4022499/ADD (31569759) E4057934/CANCEL (31569760) E4057934/ADD (31569760) |  | 6118559 |  | PVC ID : 6118559 | 1000Base-SX-850nm (31569760) | 1000Base-SX (850nm, Multi Mode Fiber) (31569760) | Ethernet |  |  |  |  | 02/03/2021 (VFORCE) (31569760) |  |  |  | MIKE WANG 1-626-833-3986 Southland46@gmail.com | AVINASH CHIB | avinash_chib@optum.com | 91-124-622-8720 | 05/07/2020(Private IP - PIP) 05/07/2020(Access) |  |  | 08/26/2020 09/01/2020 | 05/07/2020 | 05/06/2020 (31569759) 05/06/2020 (31569761) 05/07/2020 (31569760) | Cancelled | N (31569759) N (31569761) N (31569760) | U0101953 |  |  | NSPE0013673671
Cancelled | CA777-08-IM | 900 N ALAMEDA ST LOS ANGELES, CA 90012-2904 US | 50 MBPS | 04/20/2020: Your order is on track: Provisioning Department accepted the order on Apr 20, 2020 and has begun processing. | 202638133 | C1648 | WAN Analysis Reporting (31646333) Private IP - PIP (31646331) Access | 31646333 31646331 | 50 MBPS (31646331) |  | 94737713 (WAN Analysis Reporting) 94737706 (Private IP (PIP)) 94737708 | C4020946/NONE (31646331) |  | 6099782 | 13000 | PVC ID : 6099782 VPN Name : UHG-ECC Router Name : LSA29E01 VRF Name : Ve47055:UHGECC Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65420 PE IP Address : 68.139.92.201 CE Address : 68.139.92.202 QoS - Egress Profile: R12 |  | 1000Base-LX (1310nm Single Mode Fiber) | Ethernet | [8 empty] | Keri Christensen 1-385-743-9634 keri.christensen@niceincontact.com | JOHN BREMSETH | john_bremseth@optum.com | 1-763-553-4895 |  |  | 04/21/2020 (31646331) | 04/29/2020 (28216073.1) 04/29/2020 | 04/21/2020 | 04/21/2020 (31646333) 04/21/2020 (31646331) | Cancelled Order Canceled | N (31646333) N (31646331) N | U0101953 |  |  | NSPE0013713516
Cancelled | Tx423-06-IM | 100 WILSON DR FLORESVILLE, TX 78114-2858 US | 50 MBPS (31654381) | 05/15/2020: Your order is on track: Cancel Request submitted and is in progress. | 202644641 | Floresville | Private IP - PIP (31654380) WAN Analysis Reporting (31654382) Access (31654381) | 31654380 31654382 31654381 | 10 MBPS (31654380) |  | 1264211657 (Private IP (PIP)) 1264211659 (WAN Analysis Reporting) 1264211653 (Access) | C4022596/ADD (31654380) C4022596/CANCEL (31654380) E4058240/CANCEL (31654381) E4058240/ADD (31654381) |  | 6120003 |  | PVC ID : 6120003 | 1000Base-SX-850nm (31654381) | 1000Base-SX (850nm, Multi Mode Fiber) (31654381) | Ethernet |  |  |  |  | 05/27/2020 (VFORCE) (31654381) |  |  |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | AIDYL BERT SIMBULAN | aidyl_simbulan@optum.com | 632-462-2465 |  |  |  | 06/01/2020 06/05/2020 | 05/15/2020 | 05/15/2020 (31654380) 05/15/2020 (31654382) 05/15/2020 (31654381) | Cancelled | N (31654380) N (31654382) N (31654381) | U0101953 |  |  | NSPE0013715623
Cancelled | TX481-04-IM | 4323 N JOSEY LN CARROLLTON, TX 75010-4633 US | 50 MBPS (31666160) | 07/22/2020: Order Canceled on Jul 22, 2020 | 202657021 | TX481 | Access (31666160) Private IP - PIP (31666159) WAN Analysis Reporting (31666161) | 31666160 31666159 31666161 | 10 MBPS (31666159) |  | 1264860213 (Access) 1264860221 (Private IP (PIP)) 1264860229 (WAN Analysis Reporting) | E4058292/CANCEL (31666160) E4058292/ADD (31666160) C4022615/ADD (31666159) C4022615/CANCEL (31666159) |  | 6120190 |  | PVC ID : 6120190 | 1000Base-SX-850nm (31666160) | 1000Base-SX (850nm, Multi Mode Fiber) (31666160) | Ethernet |  |  |  |  | 08/21/2020 (VFORCE) (31666160) |  |  |  | LIZDELI GUERRIDO 1-210-762-3635 lguerrido@wellmed.net | AIDYL BERT SIMBULAN | aidyl_simbulan@optum.com | 632-462-2465 | 07/22/2020(Access) 07/22/2020(Private IP - PIP) |  | 09/04/2020 (31666160) 09/09/2020 (31666159) | 07/02/2020 07/09/2020 | 07/22/2020 | 07/22/2020 (31666160) 07/21/2020 (31666159) 07/21/2020 (31666161) | Cancelled | N (31666160) N (31666159) N (31666161) | U0101953 |  |  | NSPE0013718629
Cancelled |  | 180 Peachtree St Ne Atlanta, GA 30303-1760 US | 200 MBPS (31798511) | 05/15/2020: Your order is on track: Cancel Request submitted and is in progress. | 202797201 | Location19591680438 | Private IP - PIP (31798510) WAN Analysis Reporting (31798512) Access (31798511) | 31798510 31798512 31798511 | 150 MBPS (31798510) |  | 94796895 (Private IP (PIP)) 94796898 (WAN Analysis Reporting) 94796893 (Access) | C5010022/ADD (31798510) C5010022/CANCEL (31798510) E5025707/ADD (31798511) E5025707/CANCEL (31798511) |  | 6122525 |  | PVC ID : 6122525 | 1000Base-LX-1310nm (31798511) | 1000Base-LX (1310nm Single Mode Fiber) (31798511) | Ethernet | [8 empty] | Kevin Arts 1-303-478-8532 Kevin.Arts@broad-path.com | Vaishna Priya | Vaishna@optum.com | 91-804-670-4313 |  |  |  | 06/17/2020 06/23/2020 | 05/15/2020 | 05/13/2020 (31798510) 05/13/2020 (31798512) 05/15/2020 (31798511) | Cancelled | N (31798510) N (31798512) N (31798511) | U0101953 |  |  | NSPE0013770719
Cancelled | TX341-02-IM | 1313 E Alton Gloor Blvd Brownsville, TX 78526-3909 US | 50 MBPS (31807815) | 06/06/2020: Order Canceled on Jun 6, 2020 | 202802889 | TX341-02-IM | WAN Analysis Reporting (31807816) Access (31807815) Private IP - PIP (31807814) | 31807816 31807815 31807814 | 20 MBPS (31807814) |  | 94797391 (WAN Analysis Reporting) 94797393 (Access) 94797395 (Private IP (PIP)) | C4022824/ADD (31807814) C4022824/CANCEL (31807814) E4058823/CANCEL (31807815) E4058823/ADD (31807815) |  | 6122675 |  | PVC ID : 6122675 | 1000Base-SX-850nm (31807815) | 1000Base-SX (850nm, Multi Mode Fiber) (31807815) | Ethernet |  |  |  |  | 08/04/2020 (VFORCE) (31807815) |  |  |  | Joe Garza 1-956-292-4488 JGarza3@homecaredimensions.com | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 06/05/2020(Private IP - PIP) 06/05/2020(Access) |  |  | 07/09/2020 07/02/2020 | 06/06/2020 | 06/04/2020 (31807816) 06/05/2020 (31807815) 06/04/2020 (31807814) | Cancelled | N (31807816) N (31807815) N (31807814) | U0101953 |  |  | NSPE0013772600
Cancelled | TX348-02-IM | 6344 Davis Blvd North Richland Hills, TX 76180-4762 US | 50 MBPS (31859367) | 06/08/2020: Order Canceled on Jun 8, 2020 | 202853167 | TX348-02-IM | Private IP - PIP (31859366) WAN Analysis Reporting (31859368) Access (31859367) | 31859366 31859368 31859367 | 10 MBPS (31859366) |  | 94800739 (Private IP (PIP)) 94800737 (WAN Analysis Reporting) 94800743 (Access) | C4022899/CANCEL (31859366) C4022899/ADD (31859366) E4059010/ADD (31859367) E4059010/CANCEL (31859367) |  | 6123650 |  | PVC ID : 6123650 | 1000Base-SX-850nm (31859367) | 1000Base-SX (850nm, Multi Mode Fiber) (31859367) | Ethernet | [8 empty] | Brittany Malkey 1-817-918-2384 bmalkey@homecaredimensions.com | ED KIMUEL RAMOS | kimuel_ramos@optum.com | 632-588-5397 | 06/08/2020(Private IP - PIP) 06/08/2020(Access) |  |  | 10/12/2020 10/16/2020 | 06/08/2020 | 06/05/2020 (31859366) 06/05/2020 (31859368) 06/08/2020 (31859367) | Cancelled | N (31859366) N (31859368) N (31859367) | U0101953 |  |  | NSPE0013790001
Cancelled | TX356-06-IM | 200 W KEARNEY ST MESQUITE, TX 75149-3471 US | 50 MBPS (31868891) | 05/21/2020: Order Canceled on May 21, 2020 | 202862295 | TX356-01-IM Mesquite, TX Wellmed | Private IP - PIP (31868890) WAN Analysis Reporting (31868892) Access (31868891) | 31868890 31868892 31868891 | 20 MBPS (31868890) |  | 1272961025 (Private IP (PIP)) 1272961027 (WAN Analysis Reporting) 1272961021 (Access) | C4022918/CANCEL (31868890) C4022918/ADD (31868890) E4059042/CANCEL (31868891) E4059042/ADD (31868891) |  | 6123923 |  | PVC ID : 6123923 | 1000Base-SX-850nm (31868891) | 1000Base-SX (850nm, Multi Mode Fiber) (31868891) | Ethernet |  |  |  |  | 08/05/2020 (VFORCE) (31868891) |  |  |  | JASON OZER 1-210-951-3251 jozer@wellmed.net | KATHERINE ACAIN | katherine_acain@optum.com | 632-588-5327 | 05/21/2020(Private IP - PIP) 05/21/2020(Access) |  |  | 10/05/2020 10/09/2020 | 05/21/2020 | 05/20/2020 (31868890) 05/20/2020 (31868892) 05/21/2020 (31868891) | Cancelled | N (31868890) N (31868892) N (31868891) | U0101953 |  |  | NSPE0013792194
Cancelled | UWI05 | 2700 Midwest Dr Onalaska, WI 54650-8763 US | 100 MBPS (31931941) | 06/23/2020: Order Canceled on Jun 23, 2020 | 202914331 | UNITED HEALTH GROUP | Access (31931941) Private IP - PIP (31931940) WAN Analysis Reporting (31931942) | 31931941 31931940 31931942 | 50 MBPS (31931940) |  | 1273692323 (Access) 1273692331 (Private IP (PIP)) 1273692343 (WAN Analysis Reporting) | E4059224/CANCEL (31931941) E4059224/ADD (31931941) C1131624/ADD (31931940) C1131624/CANCEL (31931940) |  | 6125430 |  | PVC ID : 6125430 | 1000Base-LX-1310nm (31931941) | 1000Base-LX (1310nm Single Mode Fiber) (31931941) | Ethernet |  |  |  |  | 03/19/2021 (VFORCE) (31931941) |  |  |  | Nick Frank 1-608-783-8842 nick_frank@uhg.com | Sushil Gautam | sushil_gautam@uhc.com | 91-124-309-5736 | 06/23/2020(Access) 06/23/2020(Private IP - PIP) |  |  | 10/12/2020 10/16/2020 | 06/23/2020 | 06/23/2020 (31931941) 06/19/2020 (31931940) 06/19/2020 (31931942) | Cancelled | N (31931941) N (31931940) N (31931942) | U0101953 |  |  | NSPE0013807592
Cancelled | TX349-02-IM | 6513 Smithfield Rd ste C North Richland Hills, TX 76182-4683 US | 50 MBPS (31934411) | 08/27/2020: Your order is on track: Cancel Request submitted and is in progress. | 202916807 | TX349-02-IM | Private IP - PIP (31934410) WAN Analysis Reporting (31934412) Access (31934411) | 31934410 31934412 31934411 | 10 MBPS (31934410) |  | 94800598 (Private IP (PIP)) 94800801 (WAN Analysis Reporting) 94800596 (Access) | C4022989/CANCEL (31934410) C4022989/ADD (31934410) E4059231/ADD (31934411) E4059231/CANCEL (31934411) |  | 6125482 |  | PVC ID : 6125482 | 1000Base-SX-850nm (31934411) | 1000Base-SX (850nm, Multi Mode Fiber) (31934411) | Ethernet | [8 empty] | James Tate 1-817-217-7620 Rdelossantos@homecaredimensions.com | ED KIMUEL RAMOS | kimuel_ramos@optum.com | 632-588-5397 | 08/27/2020(Private IP - PIP) 08/27/2020(Access) |  | 10/09/2020 (31934410) 10/07/2020 (31934411) | 12/22/2020 12/29/2020 | 08/27/2020 | 08/26/2020 (31934410) 08/27/2020 (31934412) 08/27/2020 (31934411) | Cancelled | N (31934410) N (31934412) N (31934411) | U0101953 |  |  | NSPE0013807661
Cancelled | GA777-16-CM | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 06/23/2020: Order Canceled on Jun 23, 2020 | 202962289 | Equinix hub Atlanta Peachtree GA777-04-IJ | WAN Analysis Reporting (31990387) Access (31990386) Private IP - PIP (31990385) | 31990387 31990386 31990385 | 5 GBPS (31990385) |  | 1254483061 (WAN Analysis Reporting) 1254482815 (Access) 1254482819 (Private IP (PIP)) | C0186433/NONE (31990385) E7001612/NONE (31990386) |  | 6114536 6126615 6126767 | 2500000 | PVC ID : 6114536,6126615,6126767 VPN Name : UnitedHealthGroup Router Name : 95JXE01 VRF Name : Vc78844-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65138 PE IP Address : 152.187.234.185 CE Address : 152.187.234.186 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (31990386) | Ethernet | [8 empty] | EMAD BHATT 91-952-833-7538 emad@optum.com | EMAD BHATT | emad@optum.com | 91-804-670-4757 |  |  | 06/10/2020 (31990385) 06/10/2020 (31990386) | 07/15/2020 (6999783.7) 07/15/2020 | 06/23/2020 | 06/22/2020 (31990387) 06/23/2020 (31990386) 06/22/2020 (31990385) | Cancelled | N (31990387) N (31990386) N (31990385) | U0101953 |  | ADD ECCMA VPN | NSPE0013810924
Cancelled | TX479 | 300 Burnett St Fort Worth, TX 76102-2710 US | 500 MBPS (32058977) | 07/13/2020: Order Canceled on Jul 13, 2020 | 203019211 | TX479 | Private IP - PIP (32058976) WAN Analysis Reporting (32058978) Access (32058977) | 32058976 32058978 32058977 | 300 MBPS (32058976) |  | 94810344 (Private IP (PIP)) 94810347 (WAN Analysis Reporting) 94810349 (Access) | C5010472/ADD (32058976) C5010472/CANCEL (32058976) E5026445/CANCEL (32058977) E5026445/ADD (32058977) |  | 6127948 |  | PVC ID : 6127948 | 1000Base-LX-1310nm (32058977) | 1000Base-LX (1310nm Single Mode Fiber) (32058977) | Ethernet |  |  |  |  | 08/03/2020 (VFORCE) (32058977) |  |  |  | Nathan Staub 1-817-878-3466 staubn@ushealthgroup.com | AMIT SHRIVASTAVA | amit_shrivastava21@optum.com | 91-804-670-4478 |  |  |  | 11/11/2020 11/17/2020 | 07/13/2020 | 07/09/2020 (32058976) 07/09/2020 (32058978) 07/13/2020 (32058977) | Cancelled | N (32058976) N (32058978) N (32058977) | U0101953 |  |  | NSPE0013840730
Cancelled | IN710 | 650 W Henry St Indianapolis, IN 46225 US | 1 GBPS (32110753) | 09/03/2020: Pending cancel completion. | 203049273 | IN710 | Private IP - PIP (32110752) WAN Analysis Reporting (32110754) Access (32110753) | 32110752 32110754 32110753 | 500 MBPS (32110752) |  | 94811534 (Private IP (PIP)) 94811532 (WAN Analysis Reporting) 94811536 (Access) | C0197829/ADD (32110752) C0197829/CANCEL (32110752) E5026564/ADD (32110753) E5026564/CANCEL (32110753) | 187461-ENET-CCF (3211075368159401) 187461-ENET-CCF (3211075368159402) | 6128882 |  | PVC ID : 6128882 | 1000Base-SX-850nm (32110753) | 1000Base-SX (850nm, Multi Mode Fiber) (32110753) | Ethernet | LIGHT TOWER (3211075368159401) LIGHT TOWER (3211075368159402) | 06/15/2020 (3211075368159401) 08/28/2020 (3211075368159402) | 07/23/2020 (3211075368159401) 09/28/2020 (3211075368159402) | 07/22/2020 (3211075368159401) 09/15/2020 (3211075368159402) | 07/24/2020 (VFORCE) (32110753) |  | DEMARCDET - 3rd floor South carrier COLO carrier cage rack AC59 |  | Stephen Klein 1-317-806-2035 SKlein@equian.com | ED STILES | edward.stiles@optum.com | 1-763-361-7959 | 09/15/2020(Private IP - PIP) 09/15/2020(Access) |  | 08/03/2020 (32110752) 07/30/2020 (32110753) | 07/27/2020 07/31/2020 | 09/15/2020 | 08/26/2020 (32110752) 08/26/2020 (32110754) 09/15/2020 (32110753) | Cancelled | N (32110752) N (32110754) N (32110753) | U0101953 |  |  | NSPE0013849989
Cancelled | LA047-01-IM | 3625 HOUMA BLVD METAIRIE, LA 70006-4229 US | 100 MBPS (32161262) | 06/18/2020: Order Canceled on Jun 18, 2020 | 203103907 | LA047 | Private IP - PIP (32161261) WAN Analysis Reporting (32161263) Access (32161262) | 32161261 32161263 32161262 | 50 MBPS (32161261) |  | 1284059365 (Private IP (PIP)) 1284059367 (WAN Analysis Reporting) 1284059281 (Access) | C1133359/CANCEL (32161261) C1133359/ADD (32161261) E4059971/ADD (32161262) E4059971/CANCEL (32161262) |  | 6129733 |  | PVC ID : 6129733 | 1000Base-SX-850nm (32161262) | 1000Base-SX (850nm, Multi Mode Fiber) (32161262) | Ethernet | [8 empty] | Dawn Gwin 1-504-681-8985 Dawn_gwin@uhg.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 |  |  |  | 12/21/2020 12/28/2020 | 06/18/2020 | 06/18/2020 (32161261) 06/18/2020 (32161263) 06/18/2020 (32161262) | Cancelled | N (32161261) N (32161263) N (32161262) | U0101953 |  |  | NSPE0013866581
Cancelled | WI054-01-IM | 2020 INNOVATION CT DE PERE, WI 54115 US | 500 MBPS (32205633) | 07/21/2020: Order Canceled on Jul 21, 2020 | 203146785 | WI054 | WAN Analysis Reporting (32205634) Access (32205633) Private IP - PIP (32205632) | 32205634 32205633 32205632 | 300 MBPS (32205632) |  | 1281588161 (WAN Analysis Reporting) 1281588155 (Access) 1281588159 (Private IP (PIP)) | C5010582/ADD (32205632) C5010582/CANCEL (32205632) E5026768/ADD (32205633) E5026768/CANCEL (32205633) |  | 6130624 |  | PVC ID : 6130624 | 1000Base-LX-1310nm (32205633) | 1000Base-LX (1310nm Single Mode Fiber) (32205633) | Ethernet |  |  |  |  | 12/04/2020 (VFORCE) (32205633) |  |  |  | Jeremy Dash 1-920-661-4258 Jeremy_dash@uhg.com | BRANDON LITTLE | brandon_little@optum.com | 1-952-687-3694 |  |  |  | 08/10/2020 08/04/2020 | 07/21/2020 | 07/20/2020 (32205634) 07/21/2020 (32205633) 07/20/2020 (32205632) | Cancelled | N (32205634) N (32205633) N (32205632) | U0101953 |  |  | NSPE0013879809
Cancelled | GA777-16-CM | 180 PEACHTREE ST NW ATLANTA, GA 30303-1760 US |  | 06/25/2020: New change order submitted to provisioning to add additional VPN to circuit. Pending logical changes to be deployed before order can be scheduled for hotcut. | 203163217 | Equinix hub Atlanta Peachtree GA777-04-IJ | Private IP - PIP (32218167) WAN Analysis Reporting (32218169) Access (32218168) | 32218167 32218169 32218168 | 5 GBPS (32218167) |  | 1254482819 (Private IP (PIP)) 1254483061 (WAN Analysis Reporting) 1254482815 (Access) | C0186433/NONE (32218167) E7001612/NONE (32218168) |  | 6130931 6114536 | 2500000 | PVC ID : 6130931,6114536 VPN Name : UnitedHealthGroup Router Name : 95JXE01 VRF Name : Vc78844-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65138 PE IP Address : 152.187.234.185 CE Address : 152.187.234.186 QoS - Egress Profile: R12 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (32218168) | Ethernet | [8 empty] | KEVIN ARTS 1-303-478-8532 kevin.arts@broad-path.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 |  |  | 06/26/2020 (32218167) 06/26/2020 (32218168) | 07/22/2020 07/22/2020 (6999783.8) | 07/02/2020 | 07/02/2020 (32218167) 07/02/2020 (32218169) 07/02/2020 (32218168) | Cancelled | N (32218167) N (32218169) N (32218168) | U0101953 |  |  | NSPE0013883268
Cancelled | NC068 | 10 Herman Ave Asheville, NC 28803-9110 US | 50 MBPS (32241728) | 07/23/2020: Pending cancel completion. | 203189027 | NC068 | Private IP - PIP (32241727) WAN Analysis Reporting (32241729) Access (32241728) | 32241727 32241729 32241728 | 30 MBPS (32241727) |  | 94821065 (Private IP (PIP)) 94821069 (WAN Analysis Reporting) 94821067 (Access) | C4023390/ADD (32241727) C4023390/CANCEL (32241727) E4060288/ADD (32241728) E4060288/CANCEL (32241728) | 20/KRGN/400803//SB (3224172880004101) 20/KRGN/400803//SB (3224172880004102) | 6174437 |  | PVC ID : 6174437 | 1000Base-SX-850nm (32241728) | 1000Base-SX (850nm, Multi Mode Fiber) (32241728) | Ethernet | ATT (3224172880004101) ATT (3224172880004102) | 06/29/2020 (3224172880004101) 07/16/2020 (3224172880004102) | 07/10/2020 (3224172880004101) 07/24/2020 (3224172880004102) | 07/10/2020 (3224172880004101) 07/24/2020 (3224172880004102) | 07/21/2020 (VFORCE) (32241728) |  | DEMARCDET - 1ST FLR,SERVER RM SHELF MOUNTED TAGGED NOT EXT |  | Brian Stockfisch 1-810-768-9920 bstockfisch@diplomat.is | Brandon Little | Brandon_little@optum.com | 1-952-687-3694 | 07/24/2020(Private IP - PIP) 07/24/2020(Access) |  | 07/21/2020 (32241727) 07/17/2020 (32241728) | 08/07/2020 08/13/2020 | 07/24/2020 | 07/13/2020 (32241727) 07/13/2020 (32241729) 07/24/2020 (32241728) | Cancelled | N (32241727) N (32241729) N (32241728) | U0101953 |  |  | NSPE0013888918
Cancelled | MO048 | 601 W Nifong Blvd Columbia, MO 65203-6804 US | 50 MBPS (32255673) | 07/09/2020: Customer action required, engineering is advising they cannot get a response from the local contacts. Follow up sent to customer, pending response back. | 203205413 | MO048 | Private IP - PIP (32255672) WAN Analysis Reporting (32255674) Access (32255673) | 32255672 32255674 32255673 | 10 MBPS (32255672) |  | 94823524 (Private IP (PIP)) 94823530 (WAN Analysis Reporting) 94823528 (Access) | C4023414/CANCEL (32255672) C4023414/ADD (32255672) E4060317/CANCEL (32255673) E4060317/ADD (32255673) |  | 6174605 |  | PVC ID : 6174605 | 1000Base-SX-850nm (32255673) | 1000Base-SX (850nm, Multi Mode Fiber) (32255673) | Ethernet | [8 empty] | Kasey May 1-573-256-4279 kmay@Diplomat.is | BRANDON LITTLE | Brandon_little@optum.com | 1-952-687-3694 | 07/13/2020(Private IP - PIP) 07/13/2020(Access) |  |  | 08/19/2020 08/25/2020 | 07/13/2020 | 07/10/2020 (32255672) 07/10/2020 (32255674) 07/13/2020 (32255673) | Cancelled | N (32255672) N (32255674) N (32255673) | U0101953 |  |  | NSPE0013892305
Cancelled | WA112-06-IJ | 8107 W BOSTIAN RD WOODINVILLE, WA 98072-6011 US | 50 MBPS (32448945) | 08/13/2020: Order canceled. | 203370913 | WA112 | Internet Dedicated Services (32448944) Access (32448945) | 32448944 32448945 | 50 MBPS (32448944) |  | 1290410205 (Internet Dedicated Services) 1290409641 (Access) | C4023624/CANCEL (32448944) C4023624/ADD (32448944) E4060805/ADD (32448945) E4060805/CANCEL (32448945) |  | 6176525 |  | PVC ID : 6176525 | 1000Base-SX-850nm (32448945) | 1000Base-SX (850nm, Multi Mode Fiber) (32448945) | Ethernet | [8 empty] | Sepi Soleimanpour 1-425-951-5025 sepideh.soleimanpour@optum.com | sepideh soleimanpour | sepideh.soleimanpour@optum.com | 1-425-951-5025 |  |  |  | 09/15/2020 | 08/13/2020 | 08/11/2020 (32448944) 08/13/2020 (32448945) |  | N (32448944) N (32448945) | U0101953 |  |  | NSPE0013927019
Cancelled | TX547 | 19500 IH 10 W BLDG 1 SAN ANTONIO, TX 78257-9509 US | 1 GBPS (32689225) | 09/14/2020: Order Canceled on Aug 31, 2020 | 203728241 | SAN ANTONIO | Private IP - PIP (32689224) WAN Analysis Reporting (32689226) Access (32689225) | 32689224 32689226 32689225 | 500 MBPS (32689224) |  | 1300205865 (Private IP (PIP)) 1300205867 (WAN Analysis Reporting) 1300205861 (Access) | C0200824/CANCEL (32689224) C0200824/ADD (32689224) E5028029/ADD (32689225) E5028029/CANCEL (32689225) |  | 6180846 |  | PVC ID : 6180846 | 1000Base-SX-850nm (32689225) | 1000Base-SX (850nm, Multi Mode Fiber) (32689225) | Ethernet | [8 empty] | JASON OZER 1-210-951-3251 jozer@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  | 02/24/2021 (32689224) 02/22/2021 (32689225) | 12/31/2020 01/06/2021 | 08/31/2020 | 08/27/2020 (32689224) 08/28/2020 (32689226) 08/31/2020 (32689225) | Cancelled | N (32689224) N (32689226) N (32689225) | U0101953 |  |  | NSPE0014004158
Cancelled | TX603-01-IM | 2728 TX 337 LOOP NEW BRAUNFELS, TX 78132 US | 50 MBPS (32778438) | 08/27/2020: Customer action required, pending site readiness. Per LEC, building not ready. | 203807453 | New Braunfels | Private IP - PIP (32778437) WAN Analysis Reporting (32778439) Access (32778438) | 32778437 32778439 32778438 | 10 MBPS (32778437) |  | 1304088781 (Private IP (PIP)) 1304088783 (WAN Analysis Reporting) 1304088777 (Access) | C4024057/CANCEL (32778437) C4024057/ADD (32778437) E4062131/ADD (32778438) E4062131/CANCEL (32778438) |  | 6182535 | 5500 | PVC ID : 6182535 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65441 PE IP Address : 147.225.49.93 CE Address : 147.225.49.94 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32778438) | 1000Base-SX (850nm, Multi Mode Fiber) (32778438) | Ethernet | [8 empty] | Rick Williamson 1-210-951-3129 rwilliamson@wellmed.net | RODERICK MUSHATT | roderick.mushatt@optum.com | 1-331-725-0303 |  |  |  | 09/30/2020 10/06/2020 | 08/31/2020 | 08/31/2020 (32778437) 08/31/2020 (32778439) 08/31/2020 (32778438) | Cancelled | N (32778437) N (32778439) N (32778438) | U0101953 |  |  | NSPE0014027705
Cancelled | TX547 | 19500 IH 10 W BLDG 1 SAN ANTONIO, TX 78257-9509 US | 1 GBPS (32867248) | 01/07/2021: Pending cancel completion per customer's request. | 203875703 | SAN ANTONIO | Private IP - PIP (32867247) WAN Analysis Reporting (32867249) Access (32867248) | 32867247 32867249 32867248 | 500 MBPS (32867247) |  | 1306091703 (Private IP (PIP)) 1306091705 (WAN Analysis Reporting) 1306091699 (Access) | C0202433/ADD (32867247) C0202433/CANCEL (32867247) E5028592/CANCEL (32867248) E5028592/ADD (32867248) |  | 6184446 | 180000 | PVC ID : 6184446 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64710 PE IP Address : 152.176.232.117 CE Address : 152.176.232.118 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32867248) | 1000Base-SX (850nm, Multi Mode Fiber) (32867248) | Ethernet | [8 empty] | JASON OZER 1-210-951-3251 jozer@wellmed.net | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 |  |  | 01/06/2021 (32867247) 01/04/2021 (32867248) | 05/19/2021 05/25/2021 | 01/08/2021 | 01/06/2021 (32867247) 01/06/2021 (32867249) 01/08/2021 (32867248) | Cancelled | N (32867247) N (32867249) N (32867248) | U0101953 | Jeopardy Notification 2 (01/06/2021) |  | NSPE0014048133
Cancelled | IN710 | 650 W Henry St Indianapolis, IN 46225 US | 1 GBPS (32877577) | 09/14/2020: Order Canceled on Sep 3, 2020 | 203885503 | IN710 | Private IP - PIP (32877576) WAN Analysis Reporting (32877578) Access (32877577) | 32877576 32877578 32877577 | 500 MBPS (32877576) |  | 94719903 (Private IP (PIP)) 94719906 (WAN Analysis Reporting) 94719909 (Access) | C5008714/NONE (32877576) E5022087/NONE (32877577) |  | 6094787 | 90000 | PVC ID : 6094787 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64584 PE IP Address : 68.139.33.69 CE Address : 68.139.33.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (32877577) | 1000Base-SX (850nm, Multi Mode Fiber) (32877577) | Ethernet | [8 empty] | Stephen Klein 1-317-806-2035 Sklein@equian.com | EDWARD STILES | edward.stiles@optum.com | 1-763-361-7959 |  |  |  | 10/13/2020 10/13/2020 (28083517.2) | 09/03/2020 | 09/03/2020 (32877576) 09/03/2020 (32877578) 09/03/2020 (32877577) | Cancelled | N (32877576) N (32877578) N (32877577) | U0101953 |  |  | NSPE0014051137
Cancelled | CA177 | 6601 CENTER DR W STE 200 LOS ANGELES, CA 90045-1585 US | 500 MBPS (33089214) | 10/28/2020: Order Canceled on Oct 28, 2020 | 204085365 | CA177 | Internet Dedicated Services (33089213) Access (33089214) | 33089213 33089214 | 500 MBPS (33089213) |  | 1313882843 (Internet Dedicated Services) 1313882839 (Access) | C5011884/CANCEL (33089213) C5011884/ADD (33089213) E5029219/ADD (33089214) E5029219/CANCEL (33089214) |  | 6190305 | 0 | PVC ID : 6190305 VPN Name : Internet Router Name : GW10LAX9 VRF Name : XXX Encapsulation : ETHERNET PE IP Address : 157.130.242.249 CE Address : 157.130.242.250 | 1000Base-SX-850nm (33089214) | 1000Base-SX (850nm, Multi Mode Fiber) (33089214) | Ethernet | [8 empty] | Kate Tarr 1-424-439-6649 catherine.tarr@uhc.com | Kate Tarr | catherine.tarr@uhc.com | 1-424-439-6649 |  |  |  | 10/30/2020 | 10/28/2020 | 10/15/2020 (33089213) 10/28/2020 (33089214) |  | N (33089213) N (33089214) | U0101953 |  |  | NSPE0014106940
Cancelled | TX584-01-IM | 125 E GRUBB DR MESQUITE, TX 75149 US | 100 MBPS (33144164) | 10/15/2020: Order Canceled on Oct 15, 2020 | 204132837 | MESQUITE | Private IP - PIP (33144163) WAN Analysis Reporting (33144165) Access (33144164) | 33144163 33144165 33144164 | 50 MBPS (33144163) |  | 1318453739 (Private IP (PIP)) 1318453741 (WAN Analysis Reporting) 1318453735 (Access) | C1147382/ADD (33144163) C1147382/CANCEL (33144163) E4064018/ADD (33144164) E4064018/CANCEL (33144164) |  | 6191845 | 45000 | PVC ID : 6191845 VPN Name : UnitedHealthGroup Router Name : RCN3E02 VRF Name : Vh26648-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64798 PE IP Address : 152.162.107.37 CE Address : 152.162.107.38 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33144164) | 1000Base-SX (850nm, Multi Mode Fiber) (33144164) | Ethernet | [8 empty] | KHANH NGUYEN 1-817-918-2920 knguyen11@wellmed.net | CHARLIE EVANGELIO | charlie_evangelio@optum.com | 632-588-3409 |  |  |  | 11/05/2020 11/11/2020 | 10/15/2020 | 10/15/2020 (33144163) 10/15/2020 (33144165) 10/15/2020 (33144164) | Cancelled | N (33144163) N (33144165) N (33144164) | U0101953 |  |  | NSPE0014123085
Cancelled |  | 9045 E PIMA CENTER PKWY SCOTTSDALE, AZ 85258-4538 US | 50 MBPS (33254152) | 10/13/2020: Order Canceled on Oct 13, 2020 | 204251857 | Scottsdale | Private IP - PIP (33254151) WAN Analysis Reporting (33254153) Access (33254152) | 33254151 33254153 33254152 | 20 MBPS (33254151) |  | 1322256991 (Private IP (PIP)) 1322256993 (WAN Analysis Reporting) 1322256987 (Access) | C4024743/ADD (33254151) C4024743/CANCEL (33254151) E4064489/CANCEL (33254152) E4064489/ADD (33254152) |  | 6194940 |  | PVC ID : 6194940 | 1000Base-SX-850nm (33254152) | 1000Base-SX (850nm, Multi Mode Fiber) (33254152) | Ethernet | [8 empty] | Steve Learch 1-855-351-9517 slearch@diplomat.is | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 |  |  |  | 11/18/2020 11/24/2020 | 10/13/2020 | 10/13/2020 (33254151) 10/13/2020 (33254153) 10/13/2020 (33254152) | Cancelled | N (33254151) N (33254153) N (33254152) | U0101953 |  |  | NSPE0014156040
Cancelled | AZ167 | 9045 E PIMA CENTER PKWY SCOTTSDALE, AZ 85258-4538 US | 50 MBPS (33297304) | 11/02/2020: Order Canceled on Nov 2, 2020 | 204291955 | Scottsdale | Private IP - PIP (33297303) WAN Analysis Reporting (33297305) Access (33297304) | 33297303 33297305 33297304 | 20 MBPS (33297303) |  | 1323591631 (Private IP (PIP)) 1323591633 (WAN Analysis Reporting) 1323591627 (Access) | C4024795/CANCEL (33297303) C4024795/ADD (33297303) E4064669/CANCEL (33297304) E4064669/ADD (33297304) |  | 6196046 | 15000 | PVC ID : 6196046 VPN Name : UnitedHealthGroup Router Name : PHN19E01 VRF Name : V515309:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64633 PE IP Address : 152.181.227.69 CE Address : 152.181.227.70 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33297304) | 1000Base-SX (850nm, Multi Mode Fiber) (33297304) | Ethernet | [8 empty] | STEVE LEARCH 1-855-351-9517 slearch@diplomat.is | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 |  |  |  | 12/03/2020 12/09/2020 | 11/02/2020 | 10/30/2020 (33297303) 10/30/2020 (33297305) 11/02/2020 (33297304) | Cancelled | N (33297303) N (33297305) N (33297304) | U0101953 |  |  | NSPE0014170712
Cancelled | C1661 | 4580 W POST RD LAS VEGAS, NV 89118-3926 US | 50 MBPS (33308466) | 10/16/2020: Order Canceled on Oct 16, 2020 | 204301587 | Las Vegas | Private IP - PIP (33308465) WAN Analysis Reporting (33308467) Access (33308466) | 33308465 33308467 33308466 | 20 MBPS (33308465) |  | 1323771297 (Private IP (PIP)) 1323771299 (WAN Analysis Reporting) 1323771293 (Access) | C4024805/ADD (33308465) C4024805/CANCEL (33308465) E4064717/CANCEL (33308466) E4064717/ADD (33308466) |  | 6196273 |  | PVC ID : 6196273 | 1000Base-LX-1310nm (33308466) | 1000Base-LX (1310nm Single Mode Fiber) (33308466) | Ethernet | [8 empty] | Gino Sullivan 1-636-812-4000 ESullivan@roseint.com | VAISHNA PRIYA | vaishna@optum.com | 91-988-619-5805 | 10/16/2020(Private IP - PIP) 10/16/2020(Access) |  |  | 11/24/2020 12/02/2020 | 10/16/2020 | 10/15/2020 (33308465) 10/15/2020 (33308467) 10/16/2020 (33308466) | Cancelled | N (33308465) N (33308467) N (33308466) | U0101953 |  |  | NSPE0014173794
Cancelled | AZ184 | 21300 N John Wayne Pkwy ste 123 Maricopa, AZ 85139-8978 US | 100 MBPS (33394178) | 12/03/2020: Per customer's request pending cancel completion. | 204369527 | AZ184 | Private IP - PIP (33394177) WAN Analysis Reporting (33394179) Access (33394178) | 33394177 33394179 33394178 | 50 MBPS (33394177) |  | 94906487 (Private IP (PIP)) 94906491 (WAN Analysis Reporting) 94906485 (Access) | C1148804/ADD (33394177) C1148804/CANCEL (33394177) E4065178/ADD (33394178) E4065178/CANCEL (33394178) | c5nt5 532 0004 (I0029090.PHX) | 6199051 | 30000 | PVC ID : 6199051 VPN Name : UnitedHealthGroup Router Name : PHN19E02 VRF Name : Vh97246:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65076 PE IP Address : 68.137.166.101 CE Address : 68.137.166.102 QoS - Egress Profile: R12 |  | 1000Base-SX (850nm, Multi Mode Fiber) (33394178) | Ethernet |  |  | 12/08/2020 (I0029090.PHX) | [5 empty] | KIMBERLY A FLICEK 1-612-474-7105 kim.flicek@optum.com | VASUDEV K | vasudev.k@optum.com | 91-886-175-8263 | 12/08/2020(Private IP - PIP) 12/08/2020(Access) |  | 12/10/2020 (33394177) 12/08/2020 (33394178) | 12/04/2020 12/10/2020 | 12/08/2020 | 12/02/2020 (33394177) 12/01/2020 (33394179) 12/08/2020 (33394178) | Cancelled | N (33394177) N (33394179) N (33394178) | U0101953 |  |  | NSPE0014196630
Cancelled | WI019 | 102 JAY ST LA CROSSE, WI 54601-4381 US | 50 MBPS (33453499) | 01/21/2021: FOC date 2/3. | 204446319 | WI019 | Private IP - PIP (33453498) WAN Analysis Reporting (33453500) Access (33453499) | 33453498 33453500 33453499 | 30 MBPS (33453498) |  | 94911033 (Private IP (PIP)) 94911035 (WAN Analysis Reporting) 94911038 (Access) | C4025003/ADD (33453498) C4025003/CANCEL (33453498) E4065427/CANCEL (33453499) E4065427/ADD (33453499) |  | 6201147 | 17000 | PVC ID : 6201147 VPN Name : UnitedHealthGroup Router Name : DNG3E03 VRF Name : Vi75464-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65046 PE IP Address : 68.137.81.121 CE Address : 68.137.81.122 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33453499) | 1000Base-SX (850nm, Multi Mode Fiber) (33453499) | Ethernet | [8 empty] | Steve Fletschock 1-715-858-5329 steven_fletschock@uhg.com | SUSHIL KUMAR | sushil_gautam@uhc.com | 91-896-855-7475 | 01/25/2021(Private IP - PIP) 01/25/2021(Access) |  | 01/25/2021 (33453498) 01/21/2021 (33453499) | 02/19/2021 02/25/2021 | 01/25/2021 | 01/25/2021 (33453498) 01/25/2021 (33453499) | Scheduled | N (33453498) N (33453500) N (33453499) | U0101953 | Jeopardy Notification 1 (01/14/2021) |  | NSPE0014253966
Cancelled | AZ167-01-IM | 9045 E Pima Center Pkwy Scottsdale, AZ 85258-4538 US | 50 MBPS (33478992) | 12/02/2020: Order Canceled on Dec 2, 2020 | 204471877 | Scottsdale | Private IP - PIP (33478991) WAN Analysis Reporting (33478993) Access (33478992) | 33478991 33478993 33478992 | 20 MBPS (33478991) |  | 94912549 (Private IP (PIP)) 94912547 (WAN Analysis Reporting) 94912552 (Access) | C4025037/CANCEL (33478991) C4025037/ADD (33478991) E4065523/CANCEL (33478992) E4065523/ADD (33478992) |  | 6202075 |  | PVC ID : 6202075 | 1000Base-SX-850nm (33478992) | 1000Base-SX (850nm, Multi Mode Fiber) (33478992) | Ethernet | [8 empty] | STEVE LEARCH 1-855-351-9517 slearch@diplomat.is | LARRY WALSH | larry_l_walsh@optum.com | 1-317-715-7773 |  |  |  | 12/15/2020 12/21/2020 | 12/02/2020 | 12/02/2020 (33478991) 11/25/2020 (33478993) 12/01/2020 (33478992) | Cancelled | N (33478991) N (33478993) N (33478992) | U0101953 |  |  | NSPE0014225326
Cancelled | IN022-02-IJ | 1050 PATROL RD JEFFERSONVILLE, IN 47130-7750 US | 200 MBPS (33668387) | 11/30/2020: Order Canceled on Nov 30, 2020 | 204657817 | IN022-02-IJ Catamaran Jeffersonville | Private IP - PIP (33668386) WAN Analysis Reporting (33668388) Access (33668387) | 33668386 33668388 33668387 | 100 MBPS (33668386) |  | 1336057727 (Private IP (PIP)) 1336057729 (WAN Analysis Reporting) 1336057723 (Access) | C5012820/CANCEL (33668386) C5012820/ADD (33668386) E5031171/CANCEL (33668387) E5031171/ADD (33668387) |  | 6208596 | 50000 | PVC ID : 6208596 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 68.137.29.197 CE Address : 68.137.29.198 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (33668387) | 1000Base-LX (1310nm Single Mode Fiber) (33668387) | Ethernet | [8 empty] | Matt McQueary 1-812-924-4105 willis.mcqueary@optum.com | BRIAN LADD | brian.ladd@optum.com | 1-331-223-7121 |  |  |  | 01/07/2021 01/13/2021 | 11/30/2020 | 11/25/2020 (33668386) 11/25/2020 (33668388) 11/30/2020 (33668387) | Cancelled | N (33668386) N (33668388) N (33668387) | U0101953 |  |  | NSPE0014281597
Cancelled | IN022-02-IJ | 1050 PATROL RD JEFFERSONVILLE, IN 47130-7750 US | 200 MBPS (33668445) | 12/01/2020: Order Canceled on Nov 30, 2020 | 204657923 | IN022-02-IJ Catamaran Jeffersonville | Private IP - PIP (33668444) WAN Analysis Reporting (33668446) Access (33668445) | 33668444 33668446 33668445 | 100 MBPS (33668444) |  | 1336338009 (Private IP (PIP)) 1336338011 (WAN Analysis Reporting) 1336338005 (Access) | C5012821/CANCEL (33668444) C5012821/ADD (33668444) E5031172/ADD (33668445) E5031172/CANCEL (33668445) |  | 6208592 | 50000 | PVC ID : 6208592 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 68.137.24.17 CE Address : 68.137.24.18 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (33668445) | 1000Base-LX (1310nm Single Mode Fiber) (33668445) | Ethernet | [8 empty] | Matt Willis McQueary 1-812-924-4105 willis.mcqueary@optum.com | BRIAN LADD | brian.ladd@optum.com | 1-630-417-1013 |  |  |  | 01/07/2021 01/13/2021 | 11/30/2020 | 11/26/2020 (33668444) 11/25/2020 (33668446) 11/30/2020 (33668445) | Cancelled | N (33668444) N (33668446) N (33668445) | U0101953 |  |  | NSPE0014281839
Cancelled | IN022-02-IJ | 1050 PATROL RD JEFFERSONVILLE, IN 47130-7750 US | 200 MBPS (33677810) | 12/17/2020: Order Canceled on Dec 16, 2020 | 204665639 | IN022-02-IJ Catamaran Jeffersonville | Private IP - PIP (33677809) WAN Analysis Reporting (33677811) Access (33677810) | 33677809 33677811 33677810 | 100 MBPS (33677809) |  | 1336441593 (Private IP (PIP)) 1336460283 (WAN Analysis Reporting) 1336441589 (Access) | C5012830/CANCEL (33677809) C5012830/ADD (33677809) E5031188/ADD (33677810) E5031188/CANCEL (33677810) |  | 6208954 | 50000 | PVC ID : 6208954 VPN Name : UnitedHealthGroup Router Name : WYV9E02 VRF Name : V578728:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 147.225.29.125 CE Address : 147.225.29.126 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (33677810) | 1000Base-LX (1310nm Single Mode Fiber) (33677810) | Ethernet | [8 empty] | Matt McQueary 1-812-924-4105 willis.mcqueary@optum.com | BRIAN LADD | brian.ladd@optum.com | 1-331-223-7121 |  |  |  | 01/08/2021 01/14/2021 | 12/16/2020 | 12/15/2020 (33677809) 12/15/2020 (33677811) 12/16/2020 (33677810) | Cancelled | N (33677809) N (33677811) N (33677810) | U0101953 |  |  | NSPE0014284840
Cancelled | IN022-02-IJ | 1050 PATROL RD JEFFERSONVILLE, IN 47130-7750 US | 200 MBPS (33677725) | 12/17/2020: Order Canceled on Dec 17, 2020 | 204665721 | IN022-02-IJ Catamaran Jeffersonville | WAN Analysis Reporting (33677726) Access (33677725) Private IP - PIP (33677724) | 33677726 33677725 33677724 | 100 MBPS (33677724) |  | 1336441215 (WAN Analysis Reporting) 1336441209 (Access) 1336441213 (Private IP (PIP)) | C5012829/CANCEL (33677724) C5012829/ADD (33677724) E5031189/CANCEL (33677725) E5031189/ADD (33677725) |  | 6208953 | 50000 | PVC ID : 6208953 VPN Name : UnitedHealthGroup Router Name : CMKXE01 VRF Name : V625245-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64785 PE IP Address : 147.225.10.141 CE Address : 147.225.10.142 QoS - Egress Profile: R12 | 1000Base-LX-1310nm (33677725) | 1000Base-LX (1310nm Single Mode Fiber) (33677725) | Ethernet | [8 empty] | Matt McQueary 1-812-924-4105 willis.mcqueary@optum.com | BRIAN LADD | brian.ladd@optum.com | 1-331-223-7121 |  |  | 02/03/2021 (33677724) 02/01/2021 (33677725) | 01/14/2021 01/08/2021 | 12/17/2020 | 12/15/2020 (33677726) 12/17/2020 (33677725) 12/15/2020 (33677724) | Cancelled | N (33677726) N (33677725) N (33677724) | U0101953 |  |  | NSPE0014284840
Cancelled | TX610 | 6907 N Capital Of Texas Hwy Austin, TX 78731-1755 US | 50 MBPS (33732051) | 01/14/2021: Order Canceled on Jan 14, 2021 | 204710261 | TX610 | Private IP - PIP (33732050) WAN Analysis Reporting (33732052) Access (33732051) | 33732050 33732052 33732051 | 10 MBPS (33732050) |  | 94931481 (Private IP (PIP)) 94931486 (WAN Analysis Reporting) 94931479 (Access) | C4025360/CANCEL (33732050) C4025360/ADD (33732050) E4066643/ADD (33732051) E4066643/CANCEL (33732051) |  | 6211425 |  | PVC ID : 6211425 | 1000Base-SX-850nm (33732051) | 1000Base-SX (850nm, Multi Mode Fiber) (33732051) | Ethernet | [8 empty] | JASON OZER 1-210-951-3251 jozer@wellmed.net | JOSEPH MARK SANORJO | joseph_sanorjo@optum.com | 632-790-6484 | 01/14/2021(Private IP - PIP) 01/14/2021(Access) |  |  | 01/14/2021 01/20/2021 | 01/14/2021 | 01/11/2021 (33732050) 01/11/2021 (33732052) 01/14/2021 (33732051) | Cancelled | N (33732050) N (33732052) N (33732051) | U0101953 |  |  | NSPE0014303619
Cancelled | C1663 | 6900 S PEORIA ST CENTENNIAL, CO 80112-4137 US | 5 GBPS (33818653) | 12/17/2020: Order Canceled on Dec 17, 2020 | 204617705 | UHG- Trizetto | Private IP - PIP (33818652) WAN Analysis Reporting (33818654) Access (33818653) | 33818652 33818654 33818653 | 1 GBPS (33818652) |  | 1335081983 (Private IP (PIP)) 1335081985 (WAN Analysis Reporting) 1335081979 (Access) | C6000062/CANCEL (33818652) C6000062/ADD (33818652) E6001586/ADD (33818653) E6001586/CANCEL (33818653) |  | 6214400 |  | PVC ID : 6214400 |  | 10GBase-LR / LAN PHY (1310nm, Single Mode Fiber) (33818653) | Ethernet | [8 empty] | Neil Bower 1-720-515-0434 NEIL.BOWER@TTEC.COM | Neil Bower | NEIL.BOWER@TTEC.COM | 1-720-515-0434 |  |  |  | 01/12/2021 01/19/2021 | 12/17/2020 | 12/17/2020 (33818652) 12/17/2020 (33818654) 12/17/2020 (33818653) | Cancelled | N (33818652) N (33818654) N (33818653) | U0101953 |  |  | NSPE0014316525
Cancelled | TX636 | 2111 Fort Worth Hwy Weatherford, TX 76086-4834 US | 50 MBPS (33900979) | 01/05/2021: Order Canceled on Jan 5, 2021 | 204860109 | TX636 | Private IP - PIP (33900978) WAN Analysis Reporting (33900980) Access (33900979) | 33900978 33900980 33900979 | 10 MBPS (33900978) |  | 94939601 (Private IP (PIP)) 94939603 (WAN Analysis Reporting) 94939399 (Access) | C4025563/CANCEL (33900978) C4025563/ADD (33900978) E4067260/ADD (33900979) E4067260/CANCEL (33900979) |  | 6216990 | 5500 | PVC ID : 6216990 VPN Name : UnitedHealthGroup Router Name : RCN9E03 VRF Name : V112738:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 64778 PE IP Address : 68.138.38.221 CE Address : 68.138.38.222 QoS - Egress Profile: R12 | 1000Base-SX-850nm (33900979) | 1000Base-SX (850nm, Multi Mode Fiber) (33900979) | Ethernet | [8 empty] | KHANH NGUYEN 1-817-918-2920 knguyen11@wellmed.net | BRANDON LITTLE | emurugan@marchvisioncare.com | 1-952-687-3694 | 01/05/2021(Private IP - PIP) 01/05/2021(Access) |  |  | 02/04/2021 02/10/2021 | 01/05/2021 | 12/23/2020 (33900978) 12/23/2020 (33900980) 01/05/2021 (33900979) | Cancelled | N (33900978) N (33900980) N (33900979) | U0101953 |  |  | NSPE0014353226
Cancelled | TX587 | 2414 MEMORIAL PKWY PORTLAND, TX 78374-3208 US | 50 MBPS (33980776) | 03/17/2021: Order Canceled on Jan 23, 2021 | 204919371 | TX587 | Access (33980776) Private IP - PIP (33980771) WAN Analysis Reporting (33980794) | 33980776 33980771 33980794 | 10 MBPS (33980771) |  | 1344843819 (Access) 1344843823 (Private IP (PIP)) 1344843825 (WAN Analysis Reporting) | E4067601/ADD (33980776) E4067601/CANCEL (33980776) C4025694/CANCEL (33980771) C4025694/ADD (33980771) |  | 6219456 |  | PVC ID : 6219456 | 1000Base-SX-850nm (33980776) | 1000Base-SX (850nm, Multi Mode Fiber) (33980776) | Ethernet |  |  |  |  | 03/17/2021 (VFORCE) (33980776) |  |  |  | GABE RODRIGUEZ 1-210-974-6678 grodriguez1@wellmed.net | JASON SALAPING | jason_salaping@optum.com | 1-210-862-6784 | 01/22/2021(Access) 01/22/2021(Private IP - PIP) |  |  | 02/17/2021 02/23/2021 | 01/23/2021 | 01/22/2021 (33980776) 01/21/2021 (33980771) 01/20/2021 (33980794) | Cancelled | N (33980776) N (33980771) N (33980794) | U0101953 |  |  | NSPE0014379017
Cancelled | TX642 | 2327 N Riverside Dr Fort Worth, TX 76111-2904 US | 50 MBPS (34258419) | 03/11/2021: Pending cancel completion, per customer's request. | 205193237 | TX642 | Private IP - PIP (34258418) WAN Analysis Reporting (34258420) Access (34258419) | 34258418 34258420 34258419 | 10 MBPS (34258418) |  | 94967916 (Private IP (PIP)) 94967914 (WAN Analysis Reporting) 94967912 (Access) | C4026188/ADD (34258418) C4026188/CANCEL (34258418) E4068999/CANCEL (34258419) E4068999/ADD (34258419) |  | 6230177 | 5500 | PVC ID : 6230177 VPN Name : UnitedHealthGroup Router Name : RCN9E01 VRF Name : V570955:UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65082 PE IP Address : 152.162.41.149 CE Address : 152.162.41.150 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34258419) | 1000Base-SX (850nm, Multi Mode Fiber) (34258419) | Ethernet | [8 empty] | EMMANUEL UDOJI 1-214-707-6875 emmanuel_udoji@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 03/12/2021(Private IP - PIP) 03/12/2021(Access) |  | 06/23/2021 (34258418) 06/21/2021 (34258419) | 07/01/2021 07/08/2021 | 03/12/2021 | 03/09/2021 (34258418) 03/12/2021 (34258419) | Scheduled | N (34258418) N (34258420) N (34258419) | U0101953 |  |  | NSPE0014479938
Cancelled | NV190 | 8410 W Warm Springs Rd ste 10 Las Vegas, NV 89113-3624 US | 50 MBPS (34409977) | 03/22/2021: Order Canceled on Mar 22, 2021 | 205339649 | NV190 | Private IP - PIP (34409976) WAN Analysis Reporting (34409978) Access (34409977) | 34409976 34409978 34409977 | 10 MBPS (34409976) |  | 94978001 (Private IP (PIP)) 94978007 (WAN Analysis Reporting) 94978003 (Access) | C4026445/CANCEL (34409976) C4026445/ADD (34409976) E4069588/ADD (34409977) E4069588/CANCEL (34409977) |  | 6233238 | 5500 | PVC ID : 6233238 VPN Name : UnitedHealthGroup Router Name : LSVG3E01 VRF Name : V460106-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65295 PE IP Address : 68.136.148.125 CE Address : 68.136.148.126 QoS - Egress Profile: R12 | 1000Base-SX-850nm (34409977) | 1000Base-SX (850nm, Multi Mode Fiber) (34409977) | Ethernet |  |  |  |  | 03/29/2021 (VFORCE) (34409977) |  |  |  | DAVID RUCKDASCHEL 1-702-243-8580 david.ruckdaschel@optum.com | RIZWAN ANUGULA | rizwan.anugula@optum.com | 91-804-670-4280 | 03/22/2021(Private IP - PIP) 03/22/2021(Access) |  |  | 04/08/2021 04/14/2021 | 03/22/2021 | 03/10/2021 (34409976) 03/10/2021 (34409978) 03/22/2021 (34409977) | Cancelled | N (34409976) N (34409978) N (34409977) | U0101953 | Jeopardy Notification 1 (03/09/2021) |  | NSPE0014535232
Verizon Restricted

## Data Complete
Order Received | VzB POC | UHG PO # | LOCATION | PRODUCT | NPA/ NXX | VzB ORDER | griid | PDM | ACCESS TYPE Type 1=On net Type 3=Off net | TIN | SERVICE NUMBER | CKT SPEED | PVC ID | GOLD CAR | VzB CKT ID | LEC CKT ID | T1/DS3 ID | ASR SENT | TELCO DUE (FOC) | TELCO COMPLETE | REQUESTED DUE DATE | VzB DUE | VzB COMPLETE | AS NUMBER | UHT Engineer | CONFIGLET SENT | ACTIVATION SCHEDULED | ORDER SUBMISSION COMMENTS | ORDER STATUS COMMENTS | Todays Date | COMPLETE | ACTIVATION PROBLEMS -Y/N | Days Since VzB Complete | Days from VzB Complete to Customer Activation
2010-04-15 | Melissa | MN053-44-IJ | Elk River- VCC 12 (firm-ready to slot) | Muxed DS3 |  | CDR201004160053 approved IQBJC74F IZA0SY4Y min I30036 (clsd) disco OQBJMSLH |  | Jennifer Sleight | on-net | 4289851 | P1747290 | bacs | na | na | AOBKB1M60001 | Demarc. 1st fl Room 800. Bay 808.An shelf 10 jack 14. 3x-73c-llm8-0012 |  |  |  |  | bpdd | 6/4/2010 disco due 11/29 | 2010-06-03 | [5 empty] | 4/22- order in design 4/30- order sent to local design and ops for site survey 5/6 - sonet work completed, sent for dispatch for term loop to test to. 5/12- circuit tested well ETE pending orders to be stepped and closed 6/3- order closed, need to get T1 orders to slot against it. 11/- order is now being discoed. 11/29- disco complete
2010-04-15 | Melissa | MN053-44-IJ | Elk River- CVP (firm- ready to slot) | Muxed DS3 |  | CDR201004160055 Approved IQBJC741 IZA0SY9E min I30038 (clsd) disco OQBJMSLK |  | RUSSO, CHRISTINA M | on-net | 4290526 | P1747295 | bacs | na | na | AOBKB0510001 | 3x-73c-llm8-0014 |  |  |  |  | bpdd | 6/4/2010 disco due 11/29 | 2010-07-22 | [5 empty] | 4/22- order in design 5/6 pending LD interconnect portion with local network, 5/13- still working interconnection issue, escalating. 5/17-pending disco order of min-o26508 to open facilities due date 5/17 5/20 disconnect order complete, prov will move foward with design 6/9- local x-conns made, unable to test to loop. Troubleshooting 6/17- tech is having troublet getting access to terminate and tag circuit. Melissa is working on coordinating access. 6/24- ETE test is set for 6/25 7/1- ETE test did not happen, Melissa escalating. 7/15- CLR mux/routing reviewed and down loaded, All patching and/or mux requirements complete. Verified CFA matches ICAT review complete/sending to install. Pending install dates. 7/22- order closed 11/- order is now being discoed. 11/29-complete 11/29
2010-04-15 | Melissa | UMN03-23-IJ | Eagan, MN- CVP back up (firm-ready to slot) | Muxed DS3 |  | CDR201004150056 Approved IQBJDNJ8 IZA0T0KG min I30067 new cdr (for offnet) CDR201004280042 disco OQBJMSLJ |  | RUSSO, CHRISTINA M | off-net | 4291339 new tin 4302045 | P1749718 | bacs | na | na | AO BKB7B1 0001, | 3x-73c-uf0-0052 Qwest 15/HFGS/045969//NW |  | 2010-05-13 | 2010-06-03 |  | bpdd | 6/16/2010 disco due 11/29 | 2010-07-12 | [5 empty] | submitted on 4/21 4/29- re-issued new order for offnet access 5/6- new order in prov and is being designed 5/13- order designed through local portion, sending ASR to Qwest 5/20-pending LEC FOC of 6/3 6/9- Qwest called to test on 6/3, we weren't ready on our side. Having LOS in our network. Once we get that resolved we will work with Qwest and accept the loop 6/16- LD portion is being worked so we can test through 6/24- LD wiring should complete today 7/1- LD wiring did not complete, escalating 7/12- order completed. 11/- order is now being discoed. 11/29- disco complete
2010-08-04 | Melissa | UMN99-40-IJ | Plymouth, MN | IPV4/Ipv6 stacked Internet T1 |  | u292053 IQBJJ571 |  |  |  | 4443448 |  |  |  |  | u292053 | 15/HCGS/218582//NW DEMARC LOC: LOWER LVL MPOP CAB 2,SLOT 7/14 DEMARC LOC Continued: Extended Wire (Yes or No): no Jack Type: 66BK,POS 2 |  | 2010-08-30 | 2010-09-14 | 2010-09-14 | bpdd | 2010-09-13 | 2010-09-15 |  |  |  | 11/8 at 2pm Central not completed, not IPv6, need reprovision and internal wiring needed to be checked |  | 8/9 order submitted 8/12- order in design 8/26- supped order to change name to Pacific Healthcare so IP addresses can be assigned 9/1- pending LEC FOC of 9/14 9/15 closed to bill activation script sent 12/8 pending MUX completion- being escalated 12/21 circuit turned up
2010-08-23 | Melissa | NY068-01-IJ | New York, NY | Sub-rate DS3 pip with and Dcar |  | CDR201008230072 IQBJJ883 NYC-I0299443 |  |  |  | 4473617 | P1780336 |  | 1952647 |  | BCBKFRN80001 | 32.HFGS.650707..NY | 0CK62N | 2010-09-30 | 2010-12-10 |  | bpdd | 2010-10-13 |  | 65266 | (763) 744-1886, steve_betsinger@uhc.com |  |  |  | 9/8- order in provisioning 9/23- escalating for prov pick up 9/30 ASR sent requesting dd of 10/5 10/7- LEC put ASR on hold indicating that LCON was not available for access. Called and spoke to Martin who said building is not yet ready and directed me to Dan Ward. Per John building won't be ready until week of 10/18 and we need to extend to 40th floor 10/13- pending building readiness. 10/21- Per Dan Ward building is now ready, working with LEC to try and pull in dd. ticket RB20101021015 10/28- per LEC Fiber needs to be pulled and spliced from 7th to 40th floor and flashwave equipment needs to be placed. Delivery for equipment is 3 weeks. Melissa is trying to escalate that. 11/18- fiber and equipment placed. Pending design, ran into IOF facilites. This is escalated to Carole Rice and we are hoping to delivery today complete/activated
2010-11-01 | Melissa | M0352-04-IJ | Metairie, LA | New 2xT1, 3072 |  | IQBJMW69 |  |  |  | 4582042 | P1798830 | 2048 | 1975820 | 3mg | BC BKG1R2 0001, BC BKG1R2 0002, | L2/HCGS/621757//SC DEMARC LOC: 26TH FLR SUIT 2600 TELCO RM/QD MT DEMARC LOC Continued: 2,SLOT 2 Extended Wire (Yes or No): No L2/HCGS/621758//SC |  |  | 2010-11-17 |  | bpdd | 2010-12-02 |  | 64582 | (860) 702-6323, dave_marquis@uhc.com |  |  |  | 11/2- order sent to Robb F to assign OM 11/11- pending LEC FOC of 11/17 11/18- missed loop DM20101118005 for circuit 2 12/8 hotcut rescheduled to 12/16 per request 12/16 completed
2010-12-02 | Rose | UTX43-01-DJ, | Plano TX | Disconnect Internet T1 |  | U137050 |  |  |  |  | U137050 |  |  |  | MGBHWGJT0001 | [13 empty] | complete
2010-11-23 | Rose |  | Braintree MN | Disconnect PIP T1 |  | OQBJNKC4 |  |  |  |  | P1397558 |  |  |  | BCBJCTWV0001 | [13 empty] | disconnect complete 12/23/10
2010-12-08 | Rose |  | Overland park, KS | disconnect PIP OC3 |  | OQBJNY33 |  |  |  |  | P1425573 |  |  |  | BCBJFPR20001 | [13 empty] | disconnect due date 1/6/11- pending
2010-12-10 | Rose | UNY21-01-DJ | New York | Disconnect Nx2T1 |  | OQBJNY38 | [8 empty] | BCBJ2CL30001-2 | [13 empty] | complete
2010-12-10 | Rose | TX053-01-DJ | Addison TX | Disconnect Nx2T1 |  | OQBJNY50 | [8 empty] | BCBJS2M50001-2 | [13 empty] | complete
2010-12-10 | Rose | C1343-01-DJ | Nashville TN | Disconnect Nx2T1 |  | OQBJN47C |  |  |  |  | P1374995 |  |  |  | BCBH91TH0001-2 | [13 empty] | complete
2010-12-10 | Rose | UCA10-04-DJ, | Cypress, CA | disconnect DS3 |  | OQBJN1FQ |  |  |  |  | P1350700 |  |  |  | BCBH77290001 | [13 empty] | complete
2010-12-10 | Rose | UCA10-04-DJ, | Cypress, CA | disconnect DS3 |  | OQBJN1FR |  |  |  |  | P1555070 |  |  |  | BCBJSHW10001 | [13 empty] | complete
2010-10-08 | Melissa | UNY24-05-CJ | New York | Upgrade from 6xT1to 8xT1, 12288 |  | IQBJLY2L OQBJL244 NYC-I0301397 |  |  |  | 4550718 | P1792773 (In) P1748908 (out) | 12288 | 1911904 | 3600 | BCBKGLPF0001-0008 (in) BCBKB5TW0001-6 (out) | 13-56w-1pe-0011 13-56W-1PE-0012 Demarc is 8th floor, computer room, VZB krone blk #1, position #3, extended to RJ48X jack(0011). Position #4, extended to RJ48X jack(0012). |  |  | 2010-11-05 |  |  | 2010-11-09 |  | 64782 | (860) 702-6323, dave_marquis@uhc.com |  | scheduling for 5pm EST on 12/1 | completed on 12/6 | 10/21- order submitted and is being designed 10/28- pending local tail delivery of 11/5, dispatch set up for Friday, 10/29 11/11- there was a question on the local design, that is cleared up. ETE test set for 11/12 11/15- order ready to schedule for hotcut, informed Dave Marquis
2010-10-15 | Melissa | UNH03-05-CJ | Nashua, NH | Upgrade port from 4xT1 to 6xT1, 9216 |  | IQBJL8F9 OQBJL9TY IQBJP0P1 |  |  |  | 4562110 | P1794568 (in) P1812355 | 9216 |  | 4608 | BCBJT7590001-4 (out) BC BKGP10 0001-0006(in) | 84/HCGS/331952//NH/ 84/HCGS/331953//NH/ |  |  | 2010-11-12 |  | bpdd | 2010-11-24 |  | 64848 | 860/702-7396, mark_l_mullally@uhc.com |  |  |  | 10/21- order in OE 10/28- ASR sent pending LEC response 11/4- pending LEC FOC of 11/12 12/8 scheduled 12/21/10 1/3/11 pending reschedule rescheduled to 1/19/11 rescheduled to 2/2/11 rescheduled to 2/9 due to weather
2010-11-22 | Rose | IL059-05-CJ | Rockford IL | Upgrade to 6144 4XT1 |  | IQBJNH7P/ OQBJNKX1 |  |  |  | 4605035 | P1802598 P1562035 | 6144 |  | 2048 | BCBKG9XK0001-4 | /HCGS/603015//LB |  |  | 2010-12-15 |  | bpdd | [5 empty] | completed on 02/04 |  | 12/16 loop delivered pending MUX completion 1/3/11 hotcut ready to schedule
2011-01-04 | NA | PA014-02-DJ | Churchhill PA | disco |  | OQBJPN83 |  |  |  | na | P1613121 |  |  |  | BCBJX17Y0001-2 | [6 empty] | 2011-02-03 | [6 empty] | completed 2/7
2010-12-22 | NA | OH063-01-DJ | Blue Ash OH | disco |  | NSPE0004105829 OQBJPRR7 |  |  |  | na |  |  |  |  | BCBJ20TD0001 | [6 empty] | 2011-01-24 | [6 empty] | disconnect complete 1/26/11
2011-01-03 | NA | MS010-01-DJ | Ridgeland MS | disco |  | NSPE0004105779 OQBJPXHW |  |  |  | na |  |  |  |  | BCBJ6P4W 0001 | [6 empty] | 2011-02-03 | 2011-02-07 | [5 empty] | completed 2/7
2011-01-28 | NA | M0352-01-DJ | Metairie, LA | disco |  | NSPE0004149225 | [8 empty] | BCBH88H60001 | [13 empty] | disconnected on 3/1
2011-02-22 | Katrina | AZ006-05-CJ | Phoenix, AZ | Upgrade to full port 44736, DS3 |  | CQBJQ9Y5 |  | 4734600 | P1753778 |  |  |  | BCBKCGBD0001 | [5 empty] | expedite customer requested 3/3 |  |  | 65269 | (702) 303-7293, tauoa.falo@uhc.com |  | scheduled for 11pm Eastern, 10pm Central 9pm Mountain on 3/3 Bridge Number: 866-819-9840 Passcode: 3365052 |  | completed 3./3
2010-10-07 | Melissa | ME007-05-CJ | South Portland, ME | Upgrade port and add Multicast receiver |  | IQBJL1HK OQBJL3H7 |  | 4552769 | P1793073 (in) P1760254 (out) | 6xT1, 9216 | 1926050 | 2048 | Bcbkcwb70001-0003 (out) BCBKGL7J0001-006 (in) | 82/HCGS/316574//ME/ DEMARC LOC: BLDG MAIN,FLR MAIN,RM MPOE DEMARC LOC Continued: 1ST FLR. TELCO RM MOUNT NO.3 POS.1 OF 4 82/HCGS/316575//ME/ 1st flr. telco rm mount no.3 pos.2 of 4 82/HCGS/316576//ME/ 1st flr. telco rm mount no.3 pos.3 of 4 | 0CLSDL; 428830287; 0CLSDP; 260890287; 0CLSDK; 815810287; 0CLSDQ; 941790287; 0CLSDM; 41930287; 0CLSDN; 675310287 |  | 2010-11-02 |  | bpdd | 2010-11-09 |  | 65149 | 763/694-7409 terry_bjorke@uhc.com |  | sheduled for 11/18 at 5:30pm Central |  | 10/13- pending OM to write and submit order 10/21- order submitted pending design and ppwk update 10/28- pending LEC FOC of 11/2 11/4- order ready to schdule
2011-02-08 | Katrina | HI005-02-DJ | HONOLULU HI | disco |  | OQBJQVWJ |  |  | P1688342 |  |  |  | BCBJ6R1Y0001 | [6 empty] | 2011-03-08 | 2011-03-10 | [5 empty] | 2/21- disco due on 3/8. disco complete 3/10
UTX49-02-IJ C1333-05-IJ | TX038-05-IJ San Antonio TX | 5859 FARINON DR SAN ANTONIO, TX 78249-3460 US | Gig UNI Optical, MMF LC 100M, I will throttle down to 50M | 50 MBPS | 100 MBPS (21656820) | 191884960 | 21656819 21656820 |  | 4000 | PVC ID : 5664069 VPN Name : UnitedHealthGroup Router Name : SAJXE01 VRF Name : V543614-UnitedHealthGroup Encapsulation : ETHERNET Routing Protocol : BGP BGP AS Number : 65044 PE IP Address : 152.176.58.21 CE Address : 152.176.58.22 QoS - Egress Profile: R12 | C1027141/ADD (21656819) E4007185/ADD (21656820) | 31/KRGN/651668//SW (2165682018846901) | DEMARCADDR - 5859 FARINON DR SAN ANTONIO TX DEMARCDET - 1ST FLR STE 100 INSIDE ELECTRICAL RM WALL MT HANDOFF TRAY#POS3 | AT&T - ATT | 10/14/2015 (2165682018846901) | 10/29/2015 (2165682018846901) | 11/30/2015 | 11/09/2015 (21656819) 11/05/2015 (21656820) | 11/20/2015 |  | DAVID CASANOVA | 1-763-744-1589 | david_casanova@optum.com
2011-02-08 | Katrina | TX053-04-DJ | ADDISON TX | disco |  | OQBJQ1GM |  |  | P1478536 |  |  |  | BCBJK2YH0001-0003 | [6 empty] | 2011-03-09 | 2011-03-11 | [5 empty] | 2/21- disco due on 3/9 disco complete 3/11
2011-02-17 | Katrina | MN053-50-CJ | Elk River, MN | Add dyanmic CAR to UHG-IPTF and UnitedHealthGroup VPNs |  | VDDS 5494055 and 5494058 |  |  |  |  | 1817128 1817132 |  | w0v78421 | [5 empty] | bpdd |  |  | 64693 | (763) 694-7333, skbrown1@uhc.com |  |  |  | 3/10- order is complete and DCAR is enabled.
2011-02-17 | Katrina | UMN99-44-CJ | Plymouth MN | Change - Change Egress profile to R12 & add dynamic CAR | [6 empty] | 1815622 (pending change) and 1739612 |  | bcbj50sn0001 | [8 empty] | 64693 | (763) 694-7333, skbrown1@uhc.com |  |  |  | 2/25- R12 on both, pending PVC 1815622 provisioning for DCAR enable. 3/10- DCAR enabled for both pvcs
2010-08-30 | Melissa | IN045-07-IJ | Indianapolis, IN | 10mg subrate Ds3 |  | CDR201008300077 IQBJKGFN S/O 4640276 ind I12215 |  | 4483926 | P1781600 | 10mg | 1954113 | 6144 | BCBKFT850001 | HFGS/105025//NB | 0CK80V | 2010-09-30 | 2010-11-22 |  | bpdd | 2010-12-27 | 2011-01-03 | 65230 | (763) 744-1886, steve_betsinger@uhc.com |  |  |  | 9/8- pending prov approval, esclaating 9/13/10 prov approved 9/23- pending prov worked. Escalating 9/30- ASR sent out requesting dd of 10/15 10/6- Lec came back with dd of 11/22. Seeing if we can better that. Opened better telco due date ticket of DB20101007024 10/11- Per ART- spoke with Joan (AT&T Rep) and she said that the FOC will be pushed on 11/22/2010 due to a construction schedule that has an ECD of 11/17/2010 10/20- Per AT&T , she said that there's a 37 Business Day interval for the contruction and that it may include the following: * Reconfigure/Rewire Existing MUX * Translation Work * Backplane Wiring * Install Plugs * Install Customer Premise Equipment as determined by the OSPE during site Visit * Place less than 2,500 ft. of Fiber and Conduit * Order and Install New Central Office Equipment 12/16 FOC 12/27/10 1/3/11 circuit ready for activation script sent
2010-11-09 | Melissa | UCA79-05-IJ | Glendale, CA | 7680 - 5xT1 |  | IQBJM37Z LSA-I115427 | on-net | 4588812 | P1800208 | 7680 |  | 2048 | BC BKG45H 0001 BC BKG45H 0002 BC BKG45H 0003 BC BKG45H 0004 BC BKG45H 0005 | [5 empty] | bpdd | 2010-12-09 |  | 64744 | 763-744-1763, jason_a_feulner@uhc.com |  |  |  | 11/11- sent to provisioning 11/18- order designed in network, sent for site survery ( and possible install) on 11/19. 12/8 pending loop delivery 12/16 pending cable pairs 1/3/11 pending redesign 1/11/11 ready for activation
2017-12-16 | Rose | HI005-04-IJ | Honolulu HI | New 2xT1, 3072 |  | IQBJPB0S |  | 4654317 | P1808130 | 3mg |  | 1152 | BCBKHPTY0001-2 | 18/HCGS/103901/TWCS |  |  | 2011-01-24 |  | bpdd |  | 2011-01-25 | 65009 | Terry Bjorke 763/694-7409, terry_bjorke@uhc.com |  |  |  | 1/26/11 ready to schedule DEMARC: 7th flr suite 725 comp rm. smjk panel wj023 pos 1 of 4 rj48c labeled wit h both ckt id's CKT.2 DEMARC: 7th flr suite 725 comp rm. smjk panel wj035 pos 1 of 4 rj48c labeled wit h both ckt id's
2010-12-10 | v | NA | Bluffdale, UT | disco DSL account K0239370 |  | NSPE0004220694 INQ2011022800590 order order number 11726694 | [14 empty] | 2011-03-22 | [5 empty] | DSL disconnect account K0239370 which is under master account Y1825712. 3/10- e-mailed for an update 3/21- disco due 3/22. 3/14- Melissa confirming disco completed
2011-02-18 | Katrina | C1425-02-DJ | Phoenix, AZ | disco |  | OQBJQ8Z6 |  |  | P1493907 |  |  |  | BCBJL44R0001 | [5 empty] | bpdd | 2011-03-16 | 2011-03-18 | [5 empty] | disconnect due 3/16 disco complete 3/18
2011-03-22 | Melissa | NY077-04-CJ | Latham, NY | upgrade Gold CAR, |  | looking glass job id 28429 order 426666 |  | n/a | P1605195, | 6mg |  | 4608 | BCBJW7HN0001-4 | [5 empty] | bpdd after 9pm eastern | 9/22 10pm Eastern | [6 empty] | cold car change complete
2010-08-18 | Melissa | n/a | Elk River FQDN elr04.uhgiptf.globalipcom.com | FQDN |  | n/a |  | n/a | [10 empty] | bpdd | [7 empty] | 8/18- order submitted 8/19- TFN 8774795854 is now active to IPT TERM 1996537999@elr03.uhgiptf.globalipcom.com with svc no. N6316899 - pending discussion with UGH and Mike Lee to determine SBC location before we proceed further
2010-08-18 | Melissa | n/a | Elk River FQDN elr03.uhgiptf.globalipcom.com | FQDN |  | n/a |  | 4441237 | [18 empty] | 8/18- order submitted 8/19- elr04.uhgiptf.globalipcom.com under corp id 92948679. service number: N6317217 created IP term. pointed tfn 8774795855 to ip term 1996637999@elr04.uhgiptf.globalipcom.com.
2010-08-18 | Melissa | n/a | Trumbull, CT FQDN (tbl02.uhgiptf.globalipcom.com) | FQDN |  | n/a |  | 4441242 | [18 empty] | 8/18- order submitted 8/19- URI User/Name 1993037999 already exist please provide a new URI User to activate the IP Term. 9/15-Created 8004 service (IPdomain), IP Termination and pointed Toll Free number 8774795856., pending SBC capacity decision
2011-01-03 | NA | UCA89-04-IJ | Concord CA | New 3xT1 4.5mg |  | IQBJPSLL |  | 4672542 | P1810842 |  |  | 960 | BCBKHW5H0001-3 | 86/HCGS/733099//PT 86/HCGS/733100//PT 86/HCGS/733101//PT |  |  |  | 2011-01-26 | bpdd |  |  | 64609 | Jason Feulner 763-744-1763, jason_a_feulner@uhc.com |  |  |  | loops installed 1/27/11 DMARC SHELF 8 X 4 @ 0.1 SHELF 8 X 3 ready for activation activated with Jason 1/31
2011-02-16 | Katrina | n/a | disco DSL | disco DSL account K0240490 |  | NSPE0004196057 INQ2011031001238 | [12 empty] | bpdd |  | 2011-03-18 | [5 empty] | discoed on 3/18
2011-02-14 | Katrina | n/a | PITTSBURGH | DSL disco |  | INQ2011022800826 Request 11837494 |  |  | K0225752 |  |  |  | U49163 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | SAINT CHARLES | DSL disco |  | INQ2011022800826 |  |  | K0240655 |  |  |  | U77337 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | CONYERS | DSL disco |  | INQ2011022800826 |  |  | K0241433 |  |  |  | U78498 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | WEST VALLEY CITY | DSL disco |  | INQ2011022800826 |  |  | K0239663 |  |  |  | U75847 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | BARTLETT | DSL disco |  | INQ2011022800826 |  |  | K0236468 |  |  |  | U70756 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | IRVINE | DSL disco |  | INQ2011022800826 |  |  | K0245806 |  |  |  | U84431 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | DULUTH | DSL disco |  | INQ2011022800826 |  |  | K0230333 |  |  |  | U58670 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | BOLINGBROOK | DSL disco |  | INQ2011022800826 |  |  | K0236364 |  |  |  | U70550 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | HOFFMAN ESTATES | DSL disco |  | INQ2011022800826 |  |  | K0240494 |  |  |  | U77087 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | MATTESON | DSL disco |  | INQ2011022800826 |  |  | K0239983 |  |  |  | U76337 | [6 empty] | 2011-03-28 | 2011-03-28 | [5 empty] | disco complete 3/28
2011-02-14 | Katrina | n/a | 12588 FORT ST, DRAPER, UT 840209362 | DSL disco |  | 11572040 | [6 empty] | U49712 | due 3/16 | [5 empty] | 2011-03-16 | 2011-03-16 | [5 empty] | disco complete 3/16
2011-02-14 | Katrina | n/a | 1830 N 500 W, LEHI, UT 840431034 | DSL disco |  | 11572040 | [6 empty] | U64001 | due 3/16 | [5 empty] | 2011-03-16 | 2011-03-16 | [5 empty] | disco complete 3/16
2011-02-14 | Katrina | n/a | 3287 W 6735 S, WEST JORDAN, UT 840846922 | DSL disco |  | 11572040 | [6 empty] | u64064 | due 3/16 | [5 empty] | 2011-03-16 | 2011-03-16 | [5 empty] | disco complete 3/16
2011-02-14 | Katrina | n/a | 1200 E 6200 S, SALT LAKE CITY, UT | DSL disco |  | 11572040 | [6 empty] | u66558 | due 3/16 | [5 empty] | 2011-03-16 | 2011-03-16 | [5 empty] | disco complete 3/16
2011-02-14 | Katrina | n/a | 1048 WALDEN WOOD DR, MURRAY, UT | DSL disco |  | 11572040 | [6 empty] | u64072 | due 3/16 | [5 empty] | 2011-03-16 | 2011-03-16 | [5 empty] | disco complete 3/16
2011-02-23 | Katrina | C1207-01-DJ, | Columbus, GA | disco |  | NSPE0004212491 OQBJRB23 | [6 empty] | bcbjgjsm0001 | [6 empty] | 2011-03-24 | 2011-03-18 | [5 empty] | disco complete 3/28
2011-02-23 | Katrina | UCT15-03-CJ | Rocky Hill, CT | change encapsulation to PPP |  | CQBJRCXF |  | 4736041 |  |  |  |  | BCBH7R7T0001 | [5 empty] | bpdd |  |  | 64878 | (860) 702-6323, dave_marquis@uhc.com |  | completed 4/4 |  | 2/25- sent to OM group. 3/10- order is with provisioning 3/23- ready to schdule, e-mailed Dave for a date. 3/24- mux needed prior to cut. Working with provisioning. 3/31- schduled for 4/4 4/4- hotcut completed.
2011-02-23 | Katrina | UFL68-06-CJ | Oldsmar, FL | change encapsulation to PPP |  | CQBJRCW5 |  | 4736119 |  |  |  |  | BCBH3H6B0001 | [5 empty] | bpdd |  |  | 64878 | (860) 702-6323, dave_marquis@uhc.com |  | scheduled 3/23 at 10pm Central, Richard Slinkard and Bruce Kirsh bridge 866-819-9840 pcode 3365052 |  | 2/25- sent to OM group. 3/10- order has been with provisioning since 3/1, opened ticket C201103100146 3/14- order is now ready for hotcut 3/16- hotcut schduled for 3/23 3/14- hotcut complete, pending order closure order completed 3/25
2010-10-28 | Melissa | C1475-05-CJ | Atlanta, GA | Upgrade to 4xT1, 6144 |  | IQBJMMGM OQBJMRCR (old) IQBJR0ZZ / OQBJR0YP |  | 4573759 | P1796884 (in) P1661064 (out) | 6mg | 1799678 | 4608 | BCBJ29NG0001-3 (out) BCBKJ3KR0001--0004 (in) | 38/HCGS/901226//SB |  |  | 2010-11-18 |  | bpdd | 2010-11-29 |  | UHGECC 65505 | 763-553-4657 nicholas_cooper@uhc.com |  | scheduled for Friday 4/8 at 6am central 866-819-9840 leader pcode 3365052 |  | 10/28- sent to OM 11/4- pending provisioning pick up 11/12- pending LEC FOC of 11/18 11/29 hotcut ready to schedule 3/24- order did not complete Sunday. Switch port needed to be changed on our network. Provisioning is working on that 3/31- switch port corrected and order re-schduled. 4/8- completed
2011-02-04 | Katrina | US08-6-CJ | Overland Park | OC3 circuit BCBKF4BR.0001 re-home from Provider Edge (PE) router SC9ES01 in St. Louis, MO to IDCGE03 in Independence, MO. |  | CDR201103040011 IQBJRLZ6 OQBJRQ46 kan-C12556 |  | 4708836 New tin 4749872 | P1786085 |  | 1964063 |  | BCBKF4BR0001 (out) BCBKJV880001 (in) | 74/OBGS/904170/SW | [5 empty] | 2011-03-11 | 2011-04-07 |  |  |  | scheduled for 4/2 at 9pm bridget 866-819-9840 pcode 3365052 | OC3 circuit BCBKF4BR.0001 re-home from Provider Edge (PE) router SC9ES01 in St. Louis, MO to IDCGE03 in Independence, MO. FOR QUESTIONS ON ORDERS/HCUS ISSUE, PLEASE CONTACT/SEND NOTICE TO OS, MARK ADRIAN RUIZ-MARK.A.RUIZ@VERIZONBUSINESS.COM. OR customer facing Implemantation: katrina Okolie/Katrina.Okolie@rentacenter.com. | 3/4- CDR provided, new Tin issued 3/24- order now ready to schdule.x 3/31- hotcut schduled for this weekend. 4/7- hotcut completed.
2011-02-09 | Katrina | UMN99-43-CJ | Plymouth MN | upgrade from 600mb to full gig and change the minimum commit to 300M / Gig E Burstable Port |  | Tin 4719953 Site/PID: u210681 /748686 4781246 /min-C31421 |  | 4719953 |  |  |  |  | u210681 W0S30534/gx-nsb-jcfg-0001 | [5 empty] | bpdd | 2011-05-16 |  |  |  |  | completed 4/4 |  | 3/10- order is supped with correct info and is with provisioning to work Tcoms order placed for local portion rdd is 4/5 3/24 order schduled for 3/30 at 10pm Central 3/31- Jimmy asked to push date to following week. Now schduled for 4/6
2011-02-09 | Katrina | MN053-49-CJ | Elk River MN | Please upgrade from 600mb to full gig and change the minimum commit to 200M / Gig E Burstable Port |  | tin 4720758 Site/PID: u248769 /748714 |  | 4720758 |  |  |  |  | u248769 W0U37210 appearance | [5 empty] | bpdd | 2011-05-16 |  |  |  |  | scheduled for 4/7 at 10pm 866-819-9840 pcode 3365052 |  | 3/10- order is supped with correct info and is with provisioning to work 3/16- Provisioning is working 3/24- Per provisioning this was already at 1 gig, confirming. 3/31- There is no physical work needed. we only have to change the service policy on the gateway router at time of activation. Ready for upgrade
2011-03-01 | SA disco | C1494-01-DJ | STATEN ISLAND,NY | disco |  | OQBJRHP5 |  |  | P1707752 |  |  |  | BCBJ77K90001 | [7 empty] | 2011-04-01 | [5 empty] | 3/1 sent to SA disconnect. 3/10- disco is due 3/30 disco complete 4/1
2011-03-31 | Melissa | OH006-04-CJ | Dayton, OH | upgrade gold CAR to 2048 |  | Job 29129, order 440828 |  |  | P1562156 |  |  |  | BCBJS1BS0001-0003 | [8 empty] | 65277 | (763) 744-2077, robert_a_benson@uhc.com |  |  |  | completed
2011-02-11 | Katrina | UVA04-06-CJ | Roanoke, VA | upgrade Gold CAR, change cos to R12 and protocol to PPP |  | CQBJRCN5 (encap change) |  | 4719587 encap change 4735855 |  |  |  | Upgrade to 24576 | BCBH2JVX0001 | [5 empty] | bpdd |  |  | 64759 | (763) 744-2077, robert_a_benson@uhc.com |  | scheduled for 8pm Eastern on 4/1 bridge 866-819-9840 pcode 3365052 |  | gold car upgraded and R12 added. Pending encapsulation change. That is with provisioning 3/10- it looks like this is ready for hotcut for the encapsulation change. Melissa is verifying and then will schdule. 3/16- encapsualation change is ready to schedule. E-mailed engineer for time and date. 3/24- requested for 4/1 3/31- schdeuled for 4/1 4/1- completed.
2011-02-09 | Katrina | UMN03-26-CJ | Eagan MN | Please upgrade from 600mb to full gig |  | Tin 4721318 u211574 min-C31443 |  | 4721318 |  |  |  |  | u211574 PLBJKJTR0001 | gx-73c-w7y-0001 |  |  |  |  | bpdd | 2011-05-16 | [6 empty] | 3/10- order is supped with correct info and is with provisioning to work 3/16- Provisioning is working 3/24- over to TI to order equipment. 3/31- this order is ready for upgrade 4/16- upgrade completed with Jimmy.
2011-03-15 | katrina | AZ126-03-IJ | Scottsdale (8322 East McDowell Rd, Suites 101 - 103) | subrate DS3 15000 |  | NSPE0004262478 CDR201103170014 IQBJRZFT |  | 4772726 | P1826205 |  |  | 1280 | BCBKJ2WG0001 |  | 0CNCTP |  |  |  | bpdd |  |  | 65141 | 763/744-1847, donald_r_osborn@uhc.com |  |  |  | 3/24 CDR obtianed, order send and is with provisioning 3/31- NDMT ticket C201103280177 4/7- escalating for provisioning pickup. 4/21- per John Sergot please close order 4/27- order cancelled
2011-03-18 | Catherine M. Stewart 800-903-1526 ext 5927 | C1426-09-IJ | Boston, MA | install 1 FB Please add to Summary Account: 617 815-1323 731 |  | NSPE0004272467 | [12 empty] | bpdd | 2011-04-01 | [6 empty] | Order Number: N5XE5730 Date Due: 04-01-11 (earliest available) Billing Telephone Number: 617-247-1939 4/5- e-mail sent to John Tech could not get access to install this line they are coming back out on 04-08-11 4/13- 2 additional numbers added, due 4/15 two additional numbers are: 617-247-6040, 6041 4/15 completed
2011-04-15 | Melissa | UMO21-04-CJ | Springfield, MO | Upgrade God CAR to 2048 | [8 empty] | BCBJRLWS0001-0004 | [9 empty] | 763-744-1847, donald_r_osborn@uhc.com |  |  |  | completed on 4/15
2011-03-21 | SA disco | N045-01-DJ | Indianapolis IN | disconnect |  | NSPE0004274141 OQBJR1N2 |  |  | P1623299, |  |  |  | BCBJYW5B0001-4 | [5 empty] | bpdd | 2011-04-20 | [6 empty] | disco completed
2011-03-21 | SA disco | UCA79-04-DJ | GLENDALE CA | disconnect |  | NSPE0004285285 OQBJR4DB | [6 empty] | BCBJD7H90001-5 | [5 empty] | bpdd | 2011-04-21 | [6 empty] | due date 4/21 for disco
2011-04-18 | Verizon CC | C1524-02-IJ | Franklin Lakes NJ | 1 POTS line |  | NSPE0004350979 | [13 empty] | 2011-04-25 | [6 empty] | Order Number: N6LN26271 Date Due: 2011-04-25 Billing Telephone Number: 2018915456 Circuit ID or Telephone Number: 201 891-5456 completed
2011-03-07 | katrina | UAZ126 | Phoenix, AZ (scottsdale) | 3072, 2xT1 |  | NSPE0004239882 IQBJRMC1 |  | 4752198 | P1823589 |  | 2025575 | 1280 | BCBKJWD80001-0002 | 14/HCGS/425138//MS DEMARC LOC: 1ST FLR RISER RM, SHELF 1, SLOT 3 OF 4 14/HCGS/425139//MS DEMARC LOC: 1ST FLR RISER RM, SHELF 1, SLOT 4 OF 4 | 0CM7Z1 0CM7Z2 |  | 3/28/2011 New 4/7 |  | bpdd | 2011-04-15 | 2011-04-11 | 65141 | 763/744-1847, donald_r_osborn@uhc.com |  |  |  | 3/10-in design, pending MFS CFA 3/15- LEC FOC for 3/28 3/31- per LEC building is not yet ready, sent note to John S to follow up 4/6- new LEC FOC for 4/7 4/11- ORDER READY FOR ACTIVATION SCRIPT SENT 4/22- site will not be opening, John will disconnect.
2010-12-02 | Rose | C1488-04-IJ | Edina MN | New OC3 |  | IQBJPF2C |  | 4655876 | P1809039 | OC3 |  | 128k | BCBKHR9M0001 | 15/OBGS/042616//NW Demarc: fiber distribution panel suite 130 fiber lnd 8 pair 29 and 30 not extended, tagged Lcon: GENE RANDOL 952-830-7415 Singlemode, concatenated |  |  | 2011-03-21 | 2011-03-31 |  | 2011-03-18 | 2011-03-31 | should be 65522- UHGECC | Matt Seymour matt_f_seymour@uhc.com 763-744-0840 |  |  |  | 1/26 FOC 3/21/11 3/24- Qwest missed loop delivery. Defective fiber at cust prem. qwest missed loop tkt C201103220613, s/w Becky and was told that it's still being jeopd due to the deffective fiber that is alreadyexisting going to customer's prem. They may have a maintenance crew go out to the prem to check if there is already a need for a new install or just fix the existing fiber. 3/31- Qwest delivered, we are working on testing through our network. 4/6- order completed and activation notice sent.
2010-12-15 | NA | AU507-01-IJ | Melbourne Australia | New 5xE1 |  | 4729086 (port) 4729092 (bearer) |  | 4654311 | 10240K | 10240K | 2017032 | 6144K | W0X83226 (port) W0X83221, (e1) | SERVICE CIRCUIT ID: 33CB O3RB NP003, 33CB O3RB NP004, 33CB O3RB NP005 33CB O3RB NP006, 33CB O3RB NP007 |  |  |  | 2011-02-14 | bpdd |  | 2011-02-15 | 65264 | Steve Betsinger (763) 744-1886, steve_betsinger@uhc.com |  | 5/5 at 7pm Central |  | local loop order sent to OPUS pending FOC 3/2- order is now ready for activation Activated with Steve on 5/5
2011-01-05 | NA | UIL11-06-IJ | Chicago IL | T1 PIP |  | IQBJPSXR |  | 4673029 | P1810947 |  |  | 614K | BCBKHW990001 | 13-bvt-bjk-0006 |  |  |  | 2011-01-27 | bpdd |  |  | 64583 | Dan Skripka 763-744-1575, daniel_j_skripka@uhc.com |  |  |  | 1/27/11 loop insta;lled DMARC 18th floor demarc block 1651 pos #6 crossconnected to the SBC Tie cable to the net pop pair #11 of 16 customer responsible for extending the circuit ready for activation 4/22- John thought it would be working
2011-03-07 | katrina | UAZ125 | Phoenix, AZ ((9130 West Thomas Rd, Suites A107-109) | 3072, 2xT1 |  | IQBJRMHL |  | 4752665 | P1823641 |  |  | 1280 | BCBKJWHF0001-0002 | 14/HCGS/425101//MS 14/HCGS/425102//MS DEMARC LOC: 1ST LFR MAIN IT NE CORNER OF BLDG LOCK BOX COMBO 6127 SHLF#1 SLOT 1 and 2 OF 8 | 0CM73K 0CM73L |  | 2011-03-25 | 2011-03-18 | bpdd | 2011-04-04 | 2011-03-22 | 65142 | 763/744-1847, donald_r_osborn@uhc.com |  |  |  | 3/10- order is with provisioning 3/16- LEC FOC for 3/25 3/31- order is now ready for activation, sent script
2011-03-15 | katrina | AZ125-03-IJ | Phoenix, AZ ((9130 West Thomas Rd, Suites A107-109) | subrate DS3 15000 |  | NSPE0004262376 CDR201103170015 IQBJRZFS PHX-I0020073 |  | 4772658 | P1826204 |  | 2029717 | 1280 | BCBKJ2WF0001 | 3X-W5J-BCK-0240 (5/27) |  | 2011-04-24 |  |  | bpdd |  |  | 65142 | 763/744-1847, donald_r_osborn@uhc.com |  |  |  | 3/16- pending CDR. 3/24- CDR obtained, order submitted 3/31- wrong CDR listed on order, escalating to get corrected. Ticket A201103290123 4/7 -escalating with provisioning for pick up. 4/21- provisioning has, I think an ASR went out on it, but I can't find it. confirming. 4/27- ASR sent, pending FOC, FOC anticipated 5/2 5/5- per john order is to be cancelled 5/10- order cancelled
2011-02-08 | Katrina | TN041-07-IJ | Franklin, TN | New 10 mg subrate DS3 |  | CDR201102080014 IQBJQR10 Downgrade CQBJSVCF |  | 4711480 downgrade tin 4816465 | P1817737, | 10mg | 2016650 | 1280 | BCBKJDXK0001 | ATT T4/HFGS/820994//SC demarc: 1st flr data room wall mount pos b1 blu tag extended: NO Level 3 BBPH4618 | 0CMX01 |  | ATT 3/31/2011 Level 3, 4/5 |  | bpdd | 2011-04-16 | 2011-04-11 | 65173 | 715-841-7731, sonja_d_mroczynski@uhc.com |  | downgrade scheduled for 5:30 PM, CT on 5/9 866-819-9840 3365052 |  | t C201102240049 - This is a meet point order, which utilizes 2 carriers for access. A valid ASR submitted to Level 3 on 3/4/11. Provisioning is waiting for a response from Level 3 with their FOC/LOA/CFA (usually minimum 5 business days) so they can then transmit the second ASR to AT&T/Bell South. The 2nd ASR is prepped and sitting in “Hold” status dependent on the info from Level 3. 3/24- ATT FOC is 3/31, Level 3 is 4/5 4/7- both carriers delivered, testing through our network. 4/11- assigned to NILO, ROCHELLE 4/12- activated with Sonja. Accidently ordered as a full DS3, working on crediting the difference and placing a downgrade order. 5/10- order downgraded to correct speed
2011-03-16 | katrina | UTN13-06-CJ | Kingsport, TN | 6144, Add 1 T1 to existing 3xT1 and upgrade gold CAR to 3072 |  | NSPE0004264180 IQBJSQ4D OQBJSQ1Z |  | 4772812 | P1393092 (out) P1831935 (in) |  | 1568154 | 3072 | BCBJCHPX0001-3 (out) BCBKKGY90001-0004 (in) | 50.HCGS.435406..UIMN (ckt 1) old 50.HCGS.435407..UIMN (ckt 2) odl 50.HCGS.435408..UIMN (ckt 3) 1ST FLOOR TELCO EQUIPMENT ROOM SLOT 1 OF 2 |  | 2011-04-14 | 2011-04-26 |  | bpdd |  |  | 64921 multicasting reciever | (763) 744-1575, daniel_j_skripka@uhc.com |  | scheduled for 5./18 at 9am Central |  | order sent to Katrina for port upgrade, gold car upgrade schduled via looking glass, job 581249, scheduled to complete 3/17 3/24- gold car upgradeed, tin submitted, pending orderpro ticket? 4/7- escalated on automation issue 4/14- ASR send for 4/26 due date. 4/21- pending 4/26 due date. 4/27- late loop ticket B201104270099 5/2- order ready for upgrade, script sent 5/17- scheduled for May 18th. 5/18- completed May 18th with Dan
2011-02-09 | Katrina | UAL10-05-CJ | Birmingham, AL | Upgrade from 2xT1 to 4xT1, 6144 |  | IQBJQ6MM OQBJQ6MD |  | 4713624 | P1820311 (in) P1488153 (out) |  |  |  | BCBKJMYL0001-004 (in) BCBJLP680001-2 (out) | A3/HCGS/424413//SC A3/HCGS/424414//SC DEMARC LOC: 3RD FL MM2 SL4AND 3 |  | 2011-03-04 | 2011-03-18 |  | bpdd | 2011-03-25 |  | 64733 | 91 9873139388, anupam_datt@uhc.com |  |  |  | 3/10- pending LEC FOC of 3/18 3/24- LEC delivered, order ready for upgrade. Sent note to enginner to request date/time 4/18- requested for 4/27 5/5- Anupam pushed out again, pending hotcut date from UHG 5/18- hotcut completed
2011-02-11 | Katrina | C1414-05-CJ | Salt Lake City, UT | Upgrade from 4xT1 to 5xT1, 7680 |  | IQBJQ55L OQBJQ541 |  | 4720012 | P1820228 (in) P1471610 (out) |  | 1618590 | 5520 | BCBKJMSR0001-0005 (in) BCBJKCDH0001-4 | 64/HCGS/197791//MS DEMARC LOC: 1ST FL PHN RM RM 109 CAB 2 SLOT 2 OF 4 |  |  | 2011-03-14 | 2011-03-14 | bpdd |  |  | 65439 | 763-744-1999 jon_langemak@uhc.com |  |  |  | pending LEC FOC of 3/14 for the new circuit. 3/16- upgrade is now ready to schedule. Hotcut completed in April
2011-04-15 | SA disco | UTX17-03-DJ | SAN ANTONIO TX | disconnect |  | NSPE0004347179 OQBJSXFM | [6 empty] | BCBH4TS60001 | [6 empty] | 2011-05-16 | 2011-05-16 | [5 empty] | disco completed 5/16
2011-04-15 | SA disco | C1518-02-DJ | Columbus, OH | disconnect |  | NSPE0004347207 OQBJSVCS | [6 empty] | BCBKDPPG0001 | [6 empty] | 2011-05-11 | 2011-05-11 | [5 empty] | disco completed 5/11
2011-04-15 | SA disco | C1488-02-DJ | Edina, MN | disconnect |  | NSPE0004347349 OQBJSYP5 | [6 empty] | BCBJ6DF50001 | [6 empty] | 2011-05-16 | 2011-05-16 | [5 empty] | disconnect completed 5/16
2011-04-27 | Melissa | na | New FQDN- ELR |  |  |  |  | 4832168 | [18 empty] | tin completed
2011-05-10 | VZ core | UDC04-04-DJ | Washington DC | disco pots line 202-737-0417 |  | NSPE0004409960 Order Number: C0BH32257 Date Due: 5-12-11 Billing Telephone Number: 202 737-0415 Circuit ID or Telephone Number to be disconnected: 202 737-0417 | [20 empty] | completed 5/12
2011-04-18 | SA disco | WI012-04-DJ | WAUSAU WI | disconnect |  | NSPE0004350356 OQBJSW94 | [6 empty] | BCBJBBWW0001-2 | [6 empty] | 2011-05-18 | 2011-05-18 | [5 empty] | disco completed 5/18
2011-01-28 | katrina | UWA05-05-IJ | Seattle, WA | 1536 T1 |  | IQBJQDJN |  | 4694373 | P1814933 | 1536 |  |  | BCBKH66B0001 | 74/HCGS/500950 /PN DEMARC LOC: bsmt lvl 'g' mn telco closet,multi mnt 3, slot 4/4 DEMARC LOC Continued: Extended Wire (Yes or No): no | 0CMS87 |  |  |  | bpdd | 2011-02-24 | 2011-02-14 | 64562 | (763) 744-1886, steve_betsinger@uhc.com |  |  |  | per John activated
2011-03-21 | SA disco | C1386-03-DJ | GURGAON India | disconnect |  | NSPE0004274086 s/o 4786981, | [6 empty] | w0v36120 | [5 empty] | bpdd | 2011-05-20 | 2011-05-26 | [5 empty] | disco completed 5/26
2011-03-21 | SA disco | JP501-02-DJ | Tokyo Japan | disconnect |  | NSPE0004274365 s/o 4787834 |  | 4783825 |  |  |  |  | W0W60808 | [5 empty] | bpdd | 2011-05-27 | 2011-05-22 | [5 empty] | disconnect completed 5/22
2011-05-05 | SA disco | AZ125-02-DJ | Phoenix | disconnect |  | OQBJTMPK NSPE0004398626 |  |  | P1823641, |  |  |  | BCBKJWHF0001-0002 | [6 empty] | 2011-05-26 | 2011-05-26 | [5 empty] | disconnect completed on 5/26
2011-05-05 | SA disco | AZ126-02-DJ | Scottsdale | disconnect |  | OQBJTMR8 NSPE0004398654 |  |  | P1823589 |  |  |  | BCBKJWD80001-0002 | [6 empty] | 2011-05-26 | 2011-05-26 | [5 empty] | disconnect completed on 5/26
2011-06-01 | Melissa | M0361-06-CJ | Atlanta, GA | Upgrade Gold CAR to 15000 |  | Job 31350 | [5 empty] | 15000 | BCBJ6K6B0001 | [13 empty] | Melissa submitted in looking glass to complete 6/1 at 10pm Central. Completed 6/1
2010-01-20 | katrina | UMD10-07-CJ | Elkridge, MD | Upgrade from 4xT1 to 6xT1, 9216 |  | IQBJR0YD OQBJR0YF |  | 4769046 | P1665366 (old) P1826530 (new) |  | 1669075 |  | BCBJ3K6K0001-0004 | 38/HCGS/986283//CM 1st flr. telco rm cab 1 slot 26 38/HCGS/986284//CM GND,RM 0,UTIL-RM,SHLF 1,POS 27 |  | 2011-04-07 | 2011-05-09 |  | bpdd | 2011-04-18 | 2011-06-03 | 64617 | 91 9873139388, anupam_datt@uhc.com |  | 6/3 at 10pm Central 866-819-9840 pcode 3365052 |  | circuit is disconnected, we can not upgrade. 3/15- John Provided circuit BCBJ3K6K0001-0004, sent to Katrina for Upgrade 3/24- order now submitted and is with provisioning to work 3/31- provisioning has and is working, pending aSR for new loops (held up because of capacity issues), records ASR sent on existing loops 4/7- still pending capactiy escalating 4/8- capacity issue taken care of, ASR sent 4/7 requesting 4/13. Pending LEC repsonse 4/11- pending FOC date of 4/19 4/21- no loops, opened ticket B201104210093, turns out the tech was not given access. Order supped 4/27- new FOC date is for 5/9 5/5- Anupam pushed activation again, waiting for new date 5/25 activation scheduled for 5/31 completed on 6/3 with Anupam
2011-05-05 | SA disco | AZ004-02-DJ | Phoenix | disconnect |  | OQBJTP3F NSPE0004398641 |  |  | P1731693, |  |  |  | BCBJ9WBV0001 | [6 empty] | 2011-06-02 | 2011-06-02 | [5 empty] | disconnect completed on 6/2
2011-06-20 | Melissa | MN053-54-CJ | ELR- new PVC for Raven | [7 empty] | 2065597 | 3000 | bcbjww2n0001 | [5 empty] | bpdd | 2011-06-27 |  | Raven 64693 | 763-744-1921 or nick_heintzelman@uhc.com |  |  | 6/20- entered into VDDS, pending provision 6/23- pending BFD approval before l3 6/27- configlet sent to engineer and John.
2011-06-20 | Melissa | MN053-55-CJ | ELR- new PVC for Raven | [7 empty] | 2065622 | 3000 | w0v78421 | [5 empty] | bpdd | 2011-06-27 |  | Raven- 64693 | 763-744-1921 or nick_heintzelman@uhc.com |  |  | 6/20- entered into VDDS, pending provision 6/23- pending BFD approval before l3 6/27- configlet sent to engineer and John.
2011-05-10 | Katrina | II601-03-DJ | Mumbai,India | disconnect |  | NSPE0004411571 4821349, 4821351 |  | 4859571 |  |  |  |  | W0V70141 | [7 empty] | 2011-06-09 |  |  |  |  | disconnect completed on 6/9
2011-05-10 | Katrina | UIX50-14-DJ | Gurgaon India | disconnect |  | 4822591 |  | 4864689 |  |  |  |  | w0u82837 | [7 empty] | 2011-06-30 |  |  |  |  | 6/30 circuit discoed
2011-02-23 | Katrina | UCA56-01-IJ | Costa Mesa to ELR | Oc12 private line ELR end to terminate on DWDM ring, unportected. |  | NSPE0004210316 CDR201102230084 s/o 4777236 MIN I31432 LSA I117348 (FOC 5/20) LA ER2147569673 (oc12 card on oc48.je @ n6v,01 & ljd,02 ) clsd ER 2147569673 for capacity @ n6v,01 & ljd,02 (oc12 card) clsd IQBJTKJ3 |  | 4750622 |  |  |  |  | W0Y07923, LSA handoff o3-8sh-ljd-0001 | MN end o3-73c-llm8-0003 Fl 1 Room MDF 700. Verizon Cabinet Vam shelf 11 pos 3a. Tagged with both local and LD ckt id. ATT 13/ODGS/575548//PT DMARC 1st flr, serv rm relay rack 100.01 rack #8 panel 1 port 1 |  |  | 2011-06-03 |  | bpdd | 2011-07-13 | 2011-06-30 |  | Jim Moskalik 763/744-1588 jim_moskalik@uhc.com |  |  | 2/25 pending CDR. 3/7 orde needed to be re-issued as opt 1, that is done and the order is now with OE 3/24- Pending ROADM and OC12 cards, due 4/8. aSR also sent to Bell for Costa Mesa portion, pending response 4/7- Min end- CLR built, site survey completed and facilites are present. Escalating ASR out to Bell, no clean ASR yet. OC12 cards installed on CA side. testing 4/14- ATT came back saying the system wasnt' valid, we are following up with them to get this cleared up. 4/19- AT&T came back with FOC of 6/3, 5/19- pending LEC FOC, out to both LSA and MIN for patching. 5/25, all LD work complete, MIN end sched for 5/25, LA end stepped to dispatch. 6/3- no dmarc information from LEC yet will get on 6/6, retesting between LA and Irvine hub , MN end tested well tagged at dmarc. CLR needs to be updated. 6/9- loop delivered, NDMT C201106090022 for order testing and closure. 6/5- sent back to re-engineer on CA end, we could not test between our nodes. Min end pending LD wiring. 6/15- escalated for dispatch on MN and LA end 6/30- pending removal of AT&T loop order can then be closed
2011-06-13 | Verizon Core | C1340-05-IJ | White Plains NY | New pots line Please extend and tag in MDF room in ste 240 |  | NSPE0004498530 Order Number: N2XD4968 Date Due: 2011-06-20 Billing Telephone Number: 9146816017 Circuit ID or Telephone Number: 914 681-6017 | [6 empty] | Circuit ID or Telephone Number: 914 681-601 | [5 empty] | bpdd | 2011-06-20 | [5 empty] | completed 6/20
2011-03-15 | katrina | AU527-01-IJ | Sydney, Australia | 2048k E1 |  | NSPE0004498530 Order Number: N2XD4968 Date Due: 2011-06-20 Billing Telephone Number: 9146816017 Circuit ID or Telephone Number: 914 681-6017 |  | 4769853 |  |  |  | 512 | W0Y10513 bearer W0Y11437 | 12CL O2QA NP001 |  |  |  |  | bpdd | 2011-05-19 | 2011-05-19 | 65193 multicasting reciever | (763) 744-1886, steve_betsinger@uhc.com |  |  | 3/16- pending globalink 3/14- globalink obtained, order submitted and is with provisioning, pending request to PTT 3/31- LCON validated order ASR sent to PTT requesting 5/10 4/7- pending PTT response. 4/11-OPTUS: SITE SURVEY COMPLETED. FIBRE WORKS WILL BE SCHEDULED WITH THE CUSTOMER WITHIN THE NEXT 2 WEEKS. 4/21- OPTUS UPDATE: -04/18 FIBRE WORKS COMPLETED TODAY. INSTALL WILL BE ARRANGED EITHER THIS WEEK OR NEXT DEPENDANT ON TECH WORKLOAD. ORDER ON TRACK TO MEET SCHEDULED COMPLETION DATE. 4/27- VMAIL LEFT FOR LCON, TECHS AWAITING CALL BACK TO ARRANGE INSTALL DATE. 5/5- tech's still waiting on LCON 5/10- local loop delivered, pending ops side. schduled for 5/18 , , 5/19- order completed and ready for activation 6/3- Per John they may disconnect
2011-05-20 | Katrina | II745-02-DJ | Pune , India | disconnect |  | 4829147 4829157 |  | 4873232 |  |  |  |  | W0V36111 | [5 empty] | bpdd | 2011-06-24 | 2011-07-04 |  |  |  |  | 5/23- disconnect sent to Katrina to process. 5/25- tin sent for disco 6/3- ORDER SEND TO TTML FOR DISCONNECTION ( 3 XE1) ON 24-JUN-2011 6/30- local tail discoed, we are discoing our elements disco completed 7/4
2011-05-20 | SA disco | UMN60-01-DJ | Duluth, MN | disconnect |  | NSPE0004443760 OQBJT59L |  |  | P1412480 |  |  |  | BCBJDTC10001-8 | [5 empty] | bpdd | 2011-06-16 | 2011-06-16 |  |  |  |  | disconnect due on 6/16 6/16- soft disco done, pending order closure disco completed 6/16
2011-05-26 | Katrina | UGR02-02-DJ | Taunusstrasse 9 WIESBADEN GERMANY | disconnect |  | NSPE0004457262 S/O 4836928 |  | 4885333 |  |  |  |  | W0R58587 | [5 empty] | bpdd | 2011-06-30 | [5 empty] | 6/30- lcon verified, forwarding to the telco team to place ptt disco PTT disco set for 8/31 disco complete 7/7
2011-06-08 | SA disco | C1328-05-DJ | Englewood, CO | disconnect |  | NSPE0004489636 NSPE0004504940 OQBJVMFM |  |  | P1490404 |  |  |  | BCBJLV670001 | [5 empty] | bpdd | 2011-07-05 | 2011-07-05 |  |  |  |  | disco complete 7/5
2011-06-24 | SA disco | PA004-01-DJ | Huntingdon Valley, PA | disconnect |  | NSPE0004537701 OQBJV5F6 | [6 empty] | BCBJS1350001 - 0005 | [5 empty] | bpdd | 2011-07-21 | 2011-07-07 |  |  |  |  | 6/27- order sent to SA disco 6/30- disco due 7/21 Order Number: D9GP00644 Date Due: 2011-07-07 Billing Telephone Number: 2159381530
2011-06-30 | core disco | UNY27-06-DJ | Melville, NY | disco |  | NSPE0004552364 | [6 empty] | 631-755-1359 | [6 empty] | 2011-07-01 | 2011-07-01 |  |  |  |  | Order Number: D1HN0316 Date Due: 2011-07-01 Billing Telephone Number: 631 755-1359 Circuit ID or Telephone Number: 631 755-1359 completed
2011-04-05 | Katria | NV064-03-IJ | Pahrump | 12288 8xT1 |  | NSPE0004315985 IQBJSJ72 |  | 4802586 | P1830571 |  |  | 2048 | BCBKKCPX0001-0008 | 16/HCGS/501756//NV 16/HCGS/501757//NV 16/HCGS/501758//NV 16/HCGS/501759//NV 16/HCGS/501760//NV 16/HCGS/501761//NV 16/HCGS/501762//NV 16/HCGS/501763//NV DMARC OUTSIDE EAST WALL 1.1 | 0CNK10; 0CNK11; 0CNK12; 0CNK13; 0CNK1V; 0CNK1W; 0CNK1X; 0CNK1Z; | 2011-04-12 | 2011-04-25 | 2011-05-04 | bpdd | 2011-05-02 | 2011-06-01 | 65144 | (702) 303-7293, tauoa.falo@uhc.com | scheduled for 2pm Central, noon Pacific on 6/28 866-819-9840 pcode 3365052 |  | send to provisioning 4/6, pending pick up. 4/14- pending port assingnments for circuits 2 and 3. 4/15- LEC FOC for 4/25 4/27- LEC missed delivery, said dispatch is set for today 5/5- LEC delivered 5/4, testing 5/10- unable to loop NIU on circuits 5 and 8, investigating 5/19- opened NDMT ticket B201105190115, patching verified, needs to be tested. 5/25- Created a manula ticket for ckt 2 G K027563-800-332-1321, since it was'nt able to run ping test as i was not a ble to loop the smjk also 6/1- order ready for activation, let engineer know. 6/23- scheduled for activation on 6/28 6/28- complete with Tau on 6/28
2011-07-12 | Melissa | DC045-06-CJ | Washington, DC | Upgrade Gold CAR to 1280 | [8 empty] | BCBJ7KL80001 | [5 empty] | bpdd |  | 2011-07-12 |  |  |  |  | completed 7/12
2011-06-06 | SA disco | UIA17-01-DJ | WATERLOO IA | disconnect |  | NSPE0004479923 OQBJVH8Q | [6 empty] | BCBJYSKJ0001-4 | [5 empty] | bpdd | 2011-07-06 | 2011-07-06 |  |  |  |  | disconnect due 7/6 Soft disco done, pending order closure disco completed 7/6
2011-06-24 | Core disco | PA004-03-DJ | Huntingdon Valley, PA | disco pots |  | NSPE0004536605 | [6 empty] | 215-938-1530 | [5 empty] | bpdd | [6 empty] | completed
2011-05-11 | Katrina | ON517-02-IJ | 5500 N Service Rd. BurlingtonBurlington, ONT Canada | New 3072, 2xT1 |  | Globalink 1016472 NSPE0004413863 S/O 4827126 (port) 4831080 (bearer) |  | 4859740 |  |  | 2059443 | 1280 | W0Y34798 | 05DHAT245446BLCA 05DHAT245447BLCA 14/HFGS/974915//MS DEMARC INFO: 5TH FL, ROOM 501, COMPUTER RM, PAIRGAIN SLOT 2 OF 2 LOOP LEFT UP A/Z END: NO IF YES, WHERE EXACTLY: N/A |  |  | 2011-07-06 | 2011-07-06 |  | 2011-08-08 | 2011-07-06 | Unitedhealthgroup 65130 | 763/694-7409, terry_bjorke@uhc.com | activated |  | 5/31- need valid LCON and floor/suite, requested information from John Sergot. 6/3- order sent to Bell Canada 6/11- bell canada due 6/21 6/23- "Unfortunately, this order was not completed yesterday. Your customer is not ready for service; their room is not ready yet. Please, send us ... an email requesting a new due date with a minimum of 5 business days." 6/.30 Bell Canada is now due 7/6. They were instructed to drop the line at the DMARc. 7/8- order is now ready for activation. scheduled for 7/19 at 2pm central. circuit is now activated
2011-06-30 | SA disco | C1458-02-DJ | Brookfield, WI | disco |  | OQBJWBLR |  |  | P1593641, |  |  |  | bcbjv7640001 | [6 empty] | 2011-07-18 | 2011-07-18 |  |  |  |  | completed 7/18
2011-05-05 | Katrina | UVA01-03-IJ, | Richmond, VA | new PIP T1 |  | NSPE0004398875 IQBJTR47 |  | 4854554 | P1838871 | 1536 |  | 1280 | BCBKK1D40001 | 48/HCGS/828366//CV DEMARC LOC: GND,RM TEL,TEL-CLOSET,SHLF 2,POS 9 DEMARC LOC Continued: Extended Wire (Yes or No): No | 0CN0MD |  | 2011-06-21 | 2011-06-21 | bpdd | 2011-06-23 | 2011-06-21 | 64623 | (763) 744-1886, steve_betsinger@uhc.com | scheduled for 7/14 at 11am Central 866-819-9840 pcode 3365052 |  | pending LEC on 5/31, possible hyperlink capacity issue, opened B201105250095 ticket 5/15- Hyperlink ticket now complete. 6/3- LEC attempted to deliver, but LCON not aware of order, asked John S to reach out to him and let us know when we can re-dispatch. 6/11- pending new LEC FOC of 6/21 6/22- LEC delivered and we are testing. 6/23- order complete. scheduled for 7/18 at 1pm Central, cut did not go, might be inside wiring issue 7/20- per Steve it's operational
2011-05-20 | Katrina | USC03-03-IJ | Columbia, SC | New 1536, T1 |  | NSPE0004443336 IQBJT4LJ B201106090131 |  | 4873823 | P1841893 | 1536 | 2053132 | 1280 | BCBKK6JL0001 | 34/HCGS/429428//SB DEMARC LOC: 1ST FL TELCO RM MM1 POS 3 DEMARC LOC Continued: Extended Wire (Yes or No): YES |  |  |  | 2011-06-09 | bpdd | 2011-06-20 | 2011-06-21 | 64575 | (763) 744-1886, steve_betsinger@uhc.com | scheduled for 7/13 at 8pm Central 866-819-9840 pcode 3365052 |  | 5/23- order sent to Katrina to process. 6/3- pending LEC delivery of 6/10 6/11- LEC delivered, need to test and complete. B201106090131 6/16- couldn't test to hard loop. Checkign x-cons in our network. Appears to be an issue with the CFA 6/21- order completed, informed engineer scheduled for 7/13 at 8pm Central, hotcut didn't go, seeing loop telco ticket opened 7/18- Steve verified circuit is now up
2011-05-04 | Katrina | NY078-02-IJ | Flushing< NY | 2xT1 pip |  | NSPE0004395961 IQBJTQL3 NYC I0306860 (clsd) |  | 4854047 | P1838552 | 3072 |  | 1536 | BCBKK0SR0001-0002 | 32.HCGS.685844..NY 32.HCGS.685845..NY DEMARC LOC: DMARC BASEMENT CELLAR TELCO ROOM RJ48C SLOT 3 OF 4 TAQGGED DEMARC LOC Continued: NOTEXTEND Extended Wire (Yes or No): Yes | 0CNZ3W; 0CNZ3X; | 2011-05-12 | 2011-05-24 | 2011-05-24 | 2011-05-26 | 2011-06-06 | 2011-06-03 | 65132 | 763-744-1556, john_l_rothstein@uhc.com | 7/25 at 7am Cental |  | pending LEC FOC of 5/24 5/25- LEC delivered, can't connect in our network because of capacity. Pending capacity planning 6/3- order now ready for activation scheduled for 7/25 at 7am central. Completed on 7/25 with John
2011-05-04 | Katrina | IA021-02-IJ | Des Moines, IA | new PIP T1 |  | NSPE0004395256 IQBJTQDN |  | 4854033 | P1838524 | 1536 |  | 960 | BCBKK0NT0001 | 32/HCGS/083748//NW DEMARC LOC: first floor main telco room mount # 2 slot 12 of 14 | 0CNZ2W | 2011-05-12 | 2011-05-27 |  |  | 6/6/ | 2011-05-22 | 65134 | 91 91600 84400, harish_kandpal@uhc.com | requested for 8:30am Central on 7/28 |  | 5/10- order ops approved, pending provisioning pick up 5/19- pending LEC FOC of 5/27 6/3- order now ready for activation, script sent 7/21- requested timelslot at 8:30am Central on 7/28 8/4- UHG engineer didn't show on the bridge, but our layer 3 sees the interface up and was able to ping the router
2011-06-30 | SA disco | UNY27-05-DJ | Melville, NY | disco |  | NSPE0004552823 OQBJWHNL |  |  | P1583551, |  |  |  | BCBJVGRC0001-2 | [6 empty] | 2011-07-28 | [5 empty] | completed 7/28
2010-12-17 | NA | UK535-02-IJ | Potters Bar UK | new E1 |  | 4730235 |  | 4660325 | 4730235 | 1984K |  | 320 | W0X83773 | DEMARK UKD072CW (PPC 81 HIGH ST, POTTERS BAR, EN6 5AS) CIRCUIT IS PRESENTED ON BT NTE CWSS 51D BT CIRCUIT ID : MXWB 206666 RJ45 PORT 1. |  |  |  |  | bpdd | 2011-03-03 | 2011-02-18 | 65146 | Sonja Mroczynski 715/841-7731, sonja_d_mroczynski@uhc.com | completed on 8/11 |  | 1/26/11 pending FOC date asr sent pending FOC 2/18- Order BCOMed and ready for activation Sonja needed to reschedule. Pending new date and time 8/11- activated with Sonja
2011-04-13 | Melissa/Katrina | C1463-06-IJ | Aurora, CO (SunGard) | New 45M Burstable Internet OC3 |  | CDR201104140055 u302630 IQBJTFF5 dnv-I27047 pending er 2147570797 for capacity (clsd) ndmt C201106030095 |  | 4825376 |  |  |  |  | u302630 | o2-cny-h0t8-0001 105.0.4.1, shelf 9, ports 1a(VZ tx) and 1b(VZ rx) DEMARC LOC-Z 1st fl co/lo rm relay rack 108.0.4.1 ports 1a & 1b |  |  | 2011-06-20 | 2011-06-21 |  | 2011-07-14 |  |  | hau.phan@ingenix.com | completed on 8/9 |  | 4/14- pending CDR 4/21- order with provisioning 5/5- pending new OC48 ring, order going through funding 5/19- new capacity now installed, order designed, need to step for node work 5/20- node work done, NLI verifying 6/3- Site work at Sungard complete. Pending patch at DNJ ticket C201106020613 6/11- pendign ETE testing and ping tested, send to operations for 6/9 6/15- need tech at other end to ping test, that will be done 6/20. 6/21- order ready for activation, sent e-mail to engineer 8/11- activation completed on 8/9
2011-04-13 | Melissa/Katrina | C1426-10-IJ | Boston MA (SunGard) | New 45M Burstable Internet OC3 |  | CDR201104150064 NSPE0004339649 u303252 IQBJTKLL \bst-I75439 (clsd) pendign ER 2147572293 (clsd 6/16) ndmt C201107070059 |  | 4832591 |  |  |  |  | u303252 | o2-vyi-cix-0002 | [5 empty] | 2011-07-28 | 2011-07-23 |  | hau.phan@ingenix.com | completed on 8/9 |  | 4/14- pending CDR and address clarification 4/21- CDR approved and order sent to Katrina 5/10- provsioning is working 5/24- ER 2147572293 (FOTS) opened (RFT 8/22) 6/3- pending ER for OC48 shelf in boston, ER is due 8/22, equipment shippped and received. 6/11- not all eqruipment is at the hub, still pending some equpment. 6/15- Equipment now installed, topology built, sent to operations for testing. 6/16- ER is now closed. Site survey now scheduled for 6/22 6/23- site survey rescheduled to 6/29 6/30- site survey didn't happen escalating to get tech back out 7/8- Site survey work and work at Sungard work complete, sent out for node work, escalating. 7/13- node work done, dispatched for ETE testing, that is schduled for 7/14 7/18- local order closed, pending LD order wiring NDMT ticket C201107070059 7/23- order now ready for activation 8/11- activation completed on 8/9
2011-05-31 | Katrina | C1342-05-IJ | Connextions- Orlando FL- Sec CFA 3600 eCommerce Place | PIP Ds3 |  | CDR201106090045 IQBJVXGY C201106230106 orl I13369 (clsd) |  | 4907096 | P1847491 |  | 2065220 |  | BCBKLKY20001 | 58/HFGS/703962//SB DEMARC: 1st floor main telco room relay rack 01101.1a shelf 1a position 9 Extended (Y/N): NO Tagged (Y/N): YES | 0CPDSS | 6/23/2011 mfs 6/29 SBC | 7/29 SCB | 6/29 (MFS) | bpdd | 8/2 (as or 6/21) |  | UHGECC 65413 | matt_f_seymour@uhc.com 763-744-0840 | activated on 8/16 |  | 6/9- John provided new CFA 6/14- CDR approved and order sent to Katrina 6/23- ops approved on 6/17, pending provisioning pickup. 6/30- ASR sent, pending response 7/8- Clarification on ASR. Openeed NDMT ticket C201107070201 to get more information 7/14- clarification cleared, pending FOC, we should have that by 7/15. 7/20- per John client needs middle of Aug 7/27- AT&T verified a clean ASR, out for facilities check. 7/28- FOC recieved for 7/29 8/1- LEC delivered, need testing C201108020041 8/4- LEC tested, order ready for activation 8/16- order activated
2010-01-28 | Katrina | UK534-02-IJ | OXFORD, UK | 20mg Ehternet PIP |  | s/o 4751696 Globalink 906956 NEW GLOBALINK ID AS 1010618 circuit 6110553 |  | 4697918 |  |  |  |  | W0X94791, | OM5066900 DMARC BUSINESS PARK SOUTH - JOHN SMITH DRIVE OXFORD OXFORDSHIRE UK OX4 2RU TERMINATION: "ETH RJ45 SERVER ROOM,IT DEPARTMENT/GROUND FLOOR OX42RU003 CABLE & WIRELESS CIRCUIT REFERENCE :P0663810A BT CIRCUIT REFERENCE :ONEA904738 |  |  | 2011-06-28 | 2011-06-30 | bpdd | 2011-05-27 | 2011-08-08 | 65147 | 715/841-7731, sonja_d_mroczynski@uhc.com | completed 8/15 |  | 3/2 AS PER PTT FOC BY 29TH MARCH, 3/24 it looks to be a 5/2 PTT due date, but we will know more end of next week 3/31- Still no FOC, asked to follow up with PTT 4/1- BT ORDER IS PROGRESSING. BT HAVE ADVISED THAT CABLE @ EXHANGES ARE REQUIRED ALONG WITH UPGRADE FOR EXCHANGE AND THIS IS NOT TO COMPLETE UNTIL SEPTEMBER 2011. REQUEST HAS BEEN MADE FOR ORDER BEING RE ROUTED IF THERE ARE AVAILABLE CAPACITY AT OTHER NODES 4/7 asking C&W for further updates. 4/11 I HAVE SPOKEN WITH BT AND ON THE CURRENT ORDER WE ARE AWAITING FOR CORE ROUTE CABLE WHICH WILL NOT BE SCHEDULED FOR COMPLETION UNTIL AUGUST/SEPTEMBER 20, 11 THEY HAVE BEEN CHECKING ALTERNATE ROUTES TO ESTABLISH WHETHER AN EXTENDED REACH CIRCUIT WOULD BE AN OPTION . THERE IS NO OPTION FOR EXTENDED REACH SO I AM CURRENTLY CHASING OUR C&W PLANNER TO PROVIDE UPDATE ON ANY OTHER OPTIONS FOR CHANGING OR C&W SIDE AND WE ARE CURRENTLY CHECKING SPACE AND CAPACITY FOR OTHER OPTIONS , 4/21- Siva got BT pricing. We may go the BT route. Determining if there are C&W cancellation charges. 4/27- Siva said to go ahead with BT, regardless of cancellation charges. 5/5- UPDATE FROM C & W ------------------------- NEW ORDER HAS BEEN PLACED WITH BT , FOC OF 26TH MAY HAS BEEN ISSUED AND REQU EST HAS BEEN MADE FOR ECD FOR EXTERNALS TO BE ISSUED C&W ARFS DATES HAVE BEE N SET AS 9TH JUNE , We are also looking at going direct to bT. 5/10- we are staying with C&W, likely delivery of mid june. 5/25- C&W is expected to complete June 28th. Order is progressing with BT. . Awaiting BT install and subsequent fit&test. 6/11- BT expected June 21, C&W June 28th 6/15- pending BT install of 6/21 6/30 C&W handed over circuit, we are doing patching on our side. Patching expected to complete Friday 7/1 7/8- Patching complete, pending PVC, requested update 7/11- ete failed issue with BT having the auto negotiate enabled, escalating with BT/openreach 7/20- still chasing after openreach/BT 7/27- ETE test scheduled for 7/29 8/3- ETE rescheduled to 8/4 (tech ran out of time on 7/29, office was closing) 8/8 order ready for activation 8/15- activation completed wtih Sonja.
2011-03-25 | Kathleen Reagan B end | II517-02-IJ | Hyderabad, India | PIP 3xE1 |  | 4796829- port 4796832 - access | [5 empty] | 1280 | W0Y16220 W0Y16216 W0Y16217 W0Y16218 |  |  |  | 2011-06-15 |  |  | 2011-06-13 | 2011-06-13 | 65139 | 91 98100 59326, pradeep_yadav@uhc.com | activated on 8/16 |  | kathleen sent to get SOF, pending SOF 4/7- SOF sent to UHG for signature. 4/21- order sent to PTT, pending due date. 5/19- Circuit implementation is underway, we expect to handover it over by 20-Jun 6/16- circuit is ready for activation 7/20- per john they will activation early Aug 8/11- Was unable to bring up circuit. India PM is working on it. 8/16- circuit activated with Harish
2011-05-05 | Katrina | AZ008-02-IJ | 4425 East Cotton Center Blvd. Phoenix | PIP DS3 |  | CDR201105080001 NSPE0004409363 IQBJTR42 PHX-I0020331 (5/27 clsd) NDMT C201105190116 (clsd) |  | 4855808 | P1838870 | 44736 |  | 27648 | BCBKK1D10001 | 14/HFGS/974915//MS Demarc: 1st floor server room rr 010200.01 shelf 1 NUI slot 1 of 3 | 0CN0MB | 2011-05-13 | 2011-07-14 | 2011-07-15 |  | 2011-08-10 | 2011-07-20 | 65132 | 763-744-1847, donald_r_osborn@uhc.com | completed 8/18 |  | ASR sent 5/13 requesting 6/3 FOC, pending LEC response. Opened ndmt ticket C201105190116 5/25- order went to funding: pending FOC due to FUNDING issue--ORDER DELAYED FOR AQCB FUNDING. AQCB ID NUMBER AZ1101228. VTA AND SPECIAL CONSTRUCTION INFORMATION WILL BE PROVIDED WHEN KNOWN; 6/3- Supped ASR for new VTA, pending Qwest to assign a PM. 6/11- PM is scheduling a site survey 6/16- Project Manager Assigned (QWEST)has already responded;as per email,--We completed the site survey on 6/8 and I held the kick off call on 6/13.We have established a target date of 7/14/11 to deliver the circuit.We will place our new equipment in an existing rack and use DC power at the site. There are no customer requirements for this build.I will work to get the FOC to VB next week. 6/30- LEC FOC of 7/14 recieved. 7/18- per Qwest they didn't have access supping for re-dispatch, this will affect the due date 7/20-order is now ready for activation 8/17- tag and locate ticket opened, 2011081630179 8/18- activation completed with Don
2011-06-06 | Neha- ordered B end | PH501-02-IJ | Phillippines | 10M subrate DS3 |  | s/o 4843267 | [5 empty] | 2048 | W0Y40995 (wilpak) | [5 empty] | bpdd | 2011-08-17 | 2011-08-17 | UnitedHealthgroup 65141 | 919873139388 , anupam_datt@uhc.com | activated on 8/17 |  | 6/6- order sent to neha, GLs need to be raised and SOF generated. 6/15- SOF given to Siva to have UHG sign, pending order invo. 6/23- CALLED JASON VALDERAMA @ +639209078083 AND THE PHONE NUMBER IS UNREACHABLE 7/8- order is now validated with LCON and is moving. Should know more from the PTT in 10 days 7/13- order to PTT, pending FOC 7/20- pending internal cable pull set to complete 7/23, we will ask PTT when they can deliver 7/27- DS3 modem install to happen on 7/28, PTT test that day, hopefully will hand off to verizon for testing on 7/28 8/4- power, grounding and A/C should be now done on the site, pending PTT delivery 8/11- DS3 - 24HR BERT WAS COMPLETED SUCCESSFULLY, order to Verizon for building/testing 8/17- activated
2011-08-02 | VZ Core | UNY29-04-DJ | Flushing NY | disco pots |  | NSPE0004648290 | [6 empty] | 718-661-0981 | [12 empty] | Order Number: D1BE3291 Date Due: 2011-08-02 Billing Telephone Number: 7186610981 Circuit ID or Telephone Number: 7186610981 ,completed
2011-08-15 |  | MA035-03 | CHELMSFORD MA | disco pots |  | NSPE0004684049 | [6 empty] | 978-250-7407 | [12 empty] | Order Number: D5CD4978 Date Due: 2011-08-17 Billing Telephone Number: 9782507407 Circuit ID or Telephone Number: 978 250-7407 completed
2011-02-28 | Melissa |  | Quebec, Canada | 1536, T1 |  | Globalink 914411 4767269 port 4767270 DSl |  | 4731112 |  | 1536 | 2022590 | 256 | W0Y01894 (port) W0Y01895 (ds1) | 05DHAT243000BLCA DMARC: 2ND FLOOR, SUITE 200, TELECOM ROOM, SIJ POS #1 OF 2 |  |  | 2011-03-16 |  | bpdd | 2011-04-06 | 2011-03-18 | 65272 | 920-636-2664, daniel_l_bartlett@uhc.com | activated with Dan on 8/23 |  | 5/27- pending Globalink 6/3- Per Liz this will be ordered in-country, pending SOF and information from UHG. 2/28 order placed on US side. 3/8- Pending FOC of 3/16 3/18- order now ready for activation 8/23- activated with Dan.
2011-03-18 | katrina | AZ009-02-IJ | Phoenix (1 E. Washington) | Full PIP DS3 44736 |  | NSPE0004272370 CDR201103230060 IQBJR359 phx I20113 (clsd) NDMT C201106090134 |  | 4775019 | P1827257 |  | 2030880 | 4608 | BCBKJ4Y80001 | Time Warner (to customer prem) 56/HFGS/106610/TWCS Basement (MPOE) Main Telco Room wallmounted Cisco 310ma T3 card No. 1 Port No. 2 Rear connector Qwest (mid portion) 14/HFGS/974865//MS |  |  | Time Warner 4/18 Qwest 5/4 |  | bpdd | 2011-05-09 | 2011-06-27 | 65140 | 763-744-1847, donald_r_osborn@uhc.com | activated wth Don on 8/23 | City Pairs: PMB - RTO. MUX Message: H-SOJ334. F & E Circuit ID: N/A. Site Code: PMB. Entrance Comments: CITY 1: Approved for (1) DS3 using Local to the DRVYAZNO collocation. TIME WARNER to extend circuit from DRVYAZNO to the customer premise. Populate VTA on ASR with BLANK months for QWEST. Populate VTA on ASR with 12 months for TIME WARNER TELECOM OF ARIZONA, LLC-AZ. RFA approval based on terms provided in CDR (12 mos. term, MRC $2230), if the term or price changes, a new approval will be required. If you are contacted by the CAP and/or LEC and special construction and/or a change in the VTA is required, please contact CIP/AE immediately. Note, if there is not an alternate access path available, construction could take from 90 to 120 days. Any changes to the explicit ordering instructions provided above must be referred back to CIP/AE via the 711/WRKGRP3 process for review and re-approval. TCOMS/Circuit ID: phx I20113 / 3x-w5j-541-0018. City 2: Site Code: RTO. Entrance Comments: Terminate to PIP. | pending CDR. 3/23- CDR number received, sent to Katrina and Amber. 3/24- order submitted, CDR correction needed. E-mailed Katrina 3/31- ASR was sent to TW01 to request for LOA/CFA for QWEST, local order created, pending ASR with LOA from TW01 to Qwest. 4/5- opened NDMT ticket C201104050142 4/7- pending LOA from Tw01 to sent request to Qwest. 4/11- ASR sent to Qwest, pending response. 4/12- pending TW FOC of 4/18 and Qwest FOC of 5/4 4/14- also pending facilites between 2 of our internal nodes. Sent over to order equipment. 4/21- pending local loops. MFS capacity ER 2147570932 (RFT 5/19) 5/5- pending TW piece, order wtill be supped to Time Warner 5/10- Equipment will be installed by 5/13 and Initial testing wil l begin by 5/16 5/19- Capacity equipment placed and ER closed, working on node work now.\ 5/25- pending mux and testing with time warner 6/3- Ckt pre-tested today. Ckt Tested OK 100% Issues/Pending: -Pending ETMS: 2011060215492 for dispatch to clear LOS Plan of Action: -Once tech called in for ETMS: 2011060215492, troubleshoot to clear LOS -Follow up with Qwest (MS03) for End-to-End testing 6/11- Pending CFA verification, opened NDMT C201106090134 6/16- -Qwest is seeing LOS at Time Warner CFA as they are not wire yet -requested change order to provisioner for Qwest to terminate at the Time Warner CFA 6/23- Qwest fixed wiring on 6/21, circuit now tested, pending BMIS ticket BMIS ticket S2046755 to complete the HBW-Commit-Date 7/28- Per John this will go mid august 8/23- activated
2011-04-27 | Katrina | UFL74-06-CJ | Tampla, FL | Change encapsulation to PPP |  | NSPE0004379211 IQBJTNKR OQBJTNKQ CDR201105170038 |  | 4847838 | P1838112 (in) P1338957 (out) |  | 1528408 |  | BCBKKYYJ0001 (in) BCBH7D9S0001 (out) | [6 empty] | 2011-07-05 |  | 64749 | (860) 702-6323, dave_marquis@uhc.com | completed with Dave on 8/24 |  | 4/28- order sent to Katrina 5/5- order to OE 5/10- ops approved on 5/9, pending provisioning pick up 5/19- needed CDR, cdr created, re-sending back to provisioning 5/25- records ASR sent to the LEC 6/3- pending lec response to our records ASR and local work for ds3 to aub 6/11- order is ready to schdule for encapsulation change 8/17- scheduled for 8/24 8/24- completed with Dave
2011-05-19 | Katrina | GY507-02-IJ | Berlin, Germany | new 2048 E1 |  | 4828472 e-cost 6181904 |  | 4871192 |  |  |  | 1280 | W0Y33796 | 46G/30000/30000/864 |  | 2011-07-01 | 2011-08-16 | 2011-08-22 |  | 2011-09-01 |  | UnitedHealthGroup65133 | 763/694-7409, terry_bjorke@uhc.com | per Terry it is activated |  | 6/3- order with provisioning, wrong lcon listed, placing supp, per john vpn may be changed from Raven. 6/11- per LCON, pending lease agreement, he asked us not to order the local loop 6.16- MR. BAUMEISTER (LCON) IS ON VACATION THIS WEEK AND HE DID NOT HEAR ANYTHING YET on the lease SO HE ASKED Verizon TO SEND HIM AN EMAIL AND HE WILL REPLY. E-mail sent to LCON, pending his reply 6/29- LCON confirmed order and lease was signed. Pending landlord consturction program, so it can be determined where the dmarc will be. Pending that before local tail delivery 7/8- Pending PTT delivery date requesting 8/12, but pending confirmation. 7/20- pending PTT delivery of 8/16 7/28- people are moving 8/31, need the week before 8/4- pending LEC delivery of 8/16 8/17- PTT delivered, pending internal work, set for 8.19 8/23- per Terry circuit is active
2011-06-01 | Katrina | CNI01 | 5515 North Service Road / Suite 203 , Burlington, Ontario | New 3072, 2xT1 |  | Globalink 1020737 s/o: 4839256 / 4839262 |  | 4887381 |  |  |  |  | W0Y39364-65 (DS1) W0Y39363 (port) | 05DHAT246279BLCA |  |  |  |  | bpdd | 2011-08-24 | 2011-08-19 | UnitedHealthGruop 65013 | 763/694-7409, terry_bjorke@uhc.com | activated by Terry on 8/19 |  | 6/3- sent to Katrina to process 6/11- order is with provisioning 6/16- order sent to bell canada, pending date. 6/23- there was a question on the suite. Sent clarification back to Canada 6/24- Per James Ward they will dispatch on 6/28 7/8- followed up with James on where we are with this. 7/13- pending correct LCON from UHG. 7./18- new LCON received, passed to provisioning 7/27- LCOn is out of office until 8/8, alternate LCOn received and verified. That info passed onto BC. 8/1- BC delivery set at 8/5 8/16- terry requested to move VPN to Unitedhealthgroup and change aSN to 65013 8/17- one T1 down- tested to soft loop by BC, asked Terry to check inside wiring. 8/19- Terry verified that the port is up and working
2011-06-22 | Katrina | N/a | Private Wireless Gateway- EVDO |  |  | NSPE0004538530 s/o 4860110 4860094 |  | 4928668 |  |  |  |  | minnetonka-mn_p1408290 | [5 empty] | bpdd | 2011-07-28 | [5 empty] | pending info from Siva/Mike 6/27- order sent to Katrina 7/8- order is with provisioning 7/13- wrong paperwork turned in, corrected. 7/27- order progressing and sent to wireless 8/4- ready for activation
2011-06-13 | B end | PH501-04-IJ | Phillippines | 5xE1 |  | 4843298 4843308 | [5 empty] | 2048 | W0Y41014 W0Y41008 (bearer) | [5 empty] | expedite 8/1 | 2011-09-01 |  | 65141 | 919873139388 , anupam_datt@uhc.com |  |  | SOF sent to UHG, pending order numbers. 6/30- pending validation with lcon 7/8- order validated with LCON, expedite requested. 7/13- order to PTT, pending date from PTT 7/20- pending internal cable pull set to complete 7/23, we will ask PTT when they can deliver 7/27- pending cable pull which is to complete 7/29 8/11- 5XE1 - SINCE WE WERE NOT ALLOWED BY THE BUILDING ADMIN TO PROVISION NEW CABLES, WE TRACED HOUSELINE USING THE EXISTING TIECABLE. - INSTALLED MODEM AT UHC BUT UPON TESTING MODEM WONT SYNC. 8/17- PTT delievered, PVC built, pending x-conns on our side. 8/25- (PTT) ARE JUST WAITING FOR THE FINAL TEST ON THE LAST 2 E1. 9/1- order is now ready for activation 9/8- John sent a disco order
2011-07-07 | Katrina | AU527-01-DJ | Sydney Australia | disco |  | s/o 4859786 |  | 4937715 |  |  |  |  | W0Y10513 | [5 empty] | bpdd | 2011-08-31 | 2011-09-01 |  |  |  |  | order sent to Katrina 7/13- order to provisioning 7/20- pending disconnect confirmation from LCON Victor Chang 7/25- pending response from e-mail sent to victor chang 8/4- early term charges of $3150, pending UHG approval 8/11- UHG approved charges, disco date set at 8/31 9/1 disco complete
2011-08-02 | SA disco | UNY29-02-DJ | Flushing NY | disco |  | NSPE0004648339 OQBJXR06 |  |  | P1583397 |  |  |  | BCBJVGC40001-2 | [6 empty] | 2011-09-06 | 2011-09-06 |  |  |  |  | disco completed on 9/6
2011-08-15 | beth | UCN22-03-DJ | Burlington, Ontario Canada | Disconnect 3xT1 |  | s/o: 4885479 port s/o: 4885480 |  | 4991251 |  |  | 1680036 |  | w0t59399 | [5 empty] | bpdd | 2011-08-30 | 2011-08-25 |  |  |  |  | 8/18- SENT TO TELUS TO DISCONNECT 3XDS1S W0T59396 W0T59397 W0T59398 8/25- order will be discoed 8/30 9/8- order discoed
2011-08-19 | B end | CN504-01-IJ | British Columbia | 1536, T1 | [7 empty] | 1024 | [6 empty] | bpdd |  |  | UnitedHealthGroup-65125 | (702) 303-7293, tauoa.falo@uhc.com |  |  | 9/13- per John cancel this order
2011-08-15 | Beth | UUK02-03-DJ | MAIDENHEAD BERKSHIRE | disconnect |  | 4885619 |  | 4991669 |  |  |  |  | W0T84197 | [5 empty] | bpdd | [6 empty] | 8/18- order sent to provisioning 8/25- order validated need to send to LEC 9/1- pending response from the LEC 9/15- still pending response from the LEC. 9/22- circuit now disconnected
2011-08-15 | SA disco | MA035-02-DJ | CHELMSFORD MA |  |  | NSPE0004683881 OQBJXXLB | [6 empty] | BCBKBCKJ0001 | [5 empty] | bpdd | 2011-09-15 | [5 empty] | disco due on 9/15- soft disco done, pending order closure disco completed on 9/15
2011-09-15 | Beth | TX102-05-IJ | San Antonio | 1536, T1 |  | NSPE0004760301 IQBJYWBB |  | 5033824 | P1870221 |  | 3215048 | 128 | BCBKMYJL0001 | 31/HCGS/694105//SW | 0CQD2B | 2011-09-21 | 2011-09-29 |  | bpdd | 2011-10-12 |  | UHG-ECC 65408 | 763-744-2154, scott_moyer@uhc.com |  |  | 9/22- FOC 9/29, cancelled by John
2011-09-21 | Melissa- Looking Glass | PA012-04-CJ | Pittsburgh | Gold CAR Upgrade from 9Meg to 12000 |  | Job 46949 | [5 empty] | 12288 | BCBJX4PL0001 | [5 empty] | bpdd |  |  |  | 763-744-0951, steve_groebe@uhc.com |  |  | entered in looking glass to complete 9/22 at 10pm CDT.
2011-06-01 | Katrina | C1526-02-IJ | 8424 S PARK CIR, 140, changed 6/27 to 8403 SouthPark Circle, Suite 655 Orlando, FL 32819 Connextions- Orlando FL | PIP DS3 |  | CDR201106010041 NSPE0004476021 IQBJVPJ2 C201106160145 new CDR with corrected address. CDR201106270070 New order ORL-I0013408 (due 7/14) |  | 4892745 | P1845974 | 44736, | 2061226 | 12000 | BCBKLGSF0001 | 58/HFGS/703944//SB | 0CPBXR | 6/13 supped 6/24 New address sent 7/7 | MFS due 7/14 AT&T due 8/23 |  | bpdd | 2011-07-26 |  | UHGECC- 65408 | 763-744-1999 jon_langemak@uhc.com |  |  | 6/16- ASR sent to the LEC,pending clarification NDMT C201106160145 6/27- UHG changed address on order, pending new CDR request CDR201106270070 6/28 - tin supped with new address. 6/30 new address sent to provisioning, pending ASR 7/8- new ASR with address sent 7/7 requesting 7/21, pending response 7/13- LEC FOC received for 8/23. Escalating mfs portion of circuit...needs redesign NDMT ticket C201107130062 7/18- As per Field tech, local order ORL-I13408 was a duplicate order, as it was wired under order orl-I13345. NDMT ticket C201107180131 to better the LEC FOC date. 7/21-per Liza, there is job required (she said that there is no JOB CODE) for this order and the Estimated COmpletion Date is 08/16/2011. The job required are fiber slicing and placement of equipment to the node, additional to the existing ring. 7/27- Circuit tested clean from the router to the hand-off to Bell. Pending/Issues: Loop delivery from Bell due on 8/23 8/25- LEC pending equipment. escalated ndmt C201107180131. AT&T Test Center, he said it will not be completed today because they still waiting to turn up and node work. Talked to Daytra/Ap Rep, she said that they are not able to get the equipment in time. As of 08/18 still waiting parts to arrive on 09/06 and they cannot ship any date sooner. As of 08/22 optical build order are waiting on batteries to be shipped to power shelves. 9/1- Talked to Buddy/AT&T Test Center, he said that it is still not completed. The ring has not been turned up yet, there are still node works to be done because they are still waiting for the cards (no estimated time of arrival). 9/8- As per AT&T, Closed and turned up today 09/08 / ASR has been completed. seeing LOS we need to troubleshoot. opened C201109080178 9/12- CFA mismatch, change pon IQBJVPJ26R8PMB03 sent 9/15- pending CFA change for 09/20, escalating that with AT&T 9/21- order complete. Activation scheduled for 7am Central on 9/23 9/27- activated with Matt
2011-09-30 | Core | NY057-02-DJ | QUEENS NY | disco |  | NSPE0004804007 | [6 empty] | 718-559-0380 | [5 empty] | bpdd | [6 empty] | already discoed under D1GD1376
2011-06-13 | Katrina | C1340-04-IJ | White Plains, NY | 3072, 2 x T1 |  | NSPE0004501948 IQBJVXG2 |  | 4906451 | P1847493 |  |  | 128 | BCBKLKY30001-0002 | 32.HCGS.692019..NY 32.HCGS.692020..NY DEMARC LOC: GND,RM W,TEL-CLOSET,SHLF W,POS 1 DEMARC LOC Continued: Extended Wire (Yes or No): Yes Jack Type: RJ48C | 0CPDST 0CPDSV | 2011-06-20 | 2011-07-01 | 2011-06-29 | bpdd | 2011-07-14 | 2011-06-29 | UHGECC- 65493 | Leon_L_Betterman@uhc.com 763-744-1587 |  |  | Sent to Katrina on 6/13 6/16- tin created 6/23- pending LEC delivery of 7/1 7/8- LEC complete. Sent Engineer information Leon activated on 10/10
2011-09-06 | Beth | C1395-05-IJ | West Des Moines, IA | 7680, 5 x T1 |  | NSPE0004736202 IQBJYQLK |  | 5021386 | P1869063 |  |  | 5008 | BCBKMV0J0001-0005 | 32/HCGS/084745//NW | 0CQCNS; 0CQCNR; 0CQCNV; 0CQCNT; 0CQCNW; |  | 2011-10-17 | 2011-09-30 | bpdd | 2011-10-06 |  | UHGECC- 65489 | 763-744-2082 eric_taylor@uhc.com |  |  | ops approved on 9/14, pending ASR 9-22- pending LEC dd of 10/17, needs eng job to put repeater bay in CO, due 10/4, that pushes our commit date to 10/24 9/29- per Qwest Latest Update from our center. Pushing to bring them in for you. Typically work load permitting the field will try to get these by ptd which is 9 -30 10-4- ready for activation, engineer informed.
2011-09-12 | SA disco | UNV04-02-DJ | LAS VEGAS | disco |  | NSPE0004750500 OQBJYR8G | [6 empty] | BCBKGWH60001 and BCBKGWH60002 | [5 empty] | bpdd | 2011-10-10 | [5 empty] | disco completed on 10/10
2011-10-06 | Melissa | UWI34-06-CJ | Brookfield WI | gold car upgrade | [7 empty] | Upgrade to 1280 | BCBJYNLG0001-4 | [5 empty] | bpdd | [6 empty] | completed 10/13
2011-07-05 | Katrina | C1528-02-IJ | Charolette, NC | New 44736, DS3 |  | NSPE0004572908 CDR201107050065 IQBJWMR9 chr I5802 (closed) |  | 4937322 |  |  |  | 9216 | BCBKLXPC0001 | 22/HFGS/403566//SB |  | 2011-09-30 | 2011-10-11 |  | bpdd | 2011-10-18 |  | UNGECC 65407 | 763-744-1999 jon_langemak@uhc.com | activation completed on 10/17 | activation completed on 10/17 | 7/8- CDR approved and order sent to Katrina 7/13- ASR sent to internal MFS, pending LEC ASR for handoff info 7/21- ER # 2147573855 add ds3 crds/ AFL is scheduled to complete their work on 08/07/11. I hope to complete the OPS portion of connectorizing and testing by 08/12/11. NDMT ticket open for ASR cannot be sent yet due to Pending Local Tiedown. Tiedown will be provided once ER is completed. Expecting to complete the ER by 8/10/2011. 8/11- cable pull completed. ops hoping to have their portion worked by early next week. 8/17- ER date pushed to 8/26, ER is in Held due to strike. 8/26- ER now has a date of 8/25. 9/1- ER pushed to 9/7, equipment with ops and is ready to install. 9/8- ER now closed. order designed 9/15- pending LEC FOC of 9/30, new commit date of 10/18 9/22- all ld patching and mux complete, pending LEC delivery on 9/30 10/5- CDD was improved from 10/18/ to 10/12. Order is with Install Tech for Pending Completion of the order. scheduled activation on Monday the 17th at 11am activation completed with Eric
2010-03-01 | katrina | IR511-01-IJ | Letterkenny, Ireland | 44736, DS3 - Dynamic Port |  | Globalink 914795 circuit 5052523 S/O: 4790282 |  | 4776226 |  |  |  | 6144 Dynamic CAR | W0Y12673 | Enet EN01099 LKY_6325_TN10/ENET PATCH PANEL PORT 1, BNC HANDOFF |  | 2011-09-23 | 2011-09-20 |  | bpdd |  |  | 64943 | (763) 694-7333, skbrown1@uhc.com | scheduled for 11am on 10/20 failed. Resched for 10/27 at noon central. | activated with Steve Brown on 10/27 | pending information on diversity from john Elmore 3/24- diversity requirement received and order submitted 3/31- order now in provisioning. Epedite ticket opened. 4/7- tech information valideted with onsite contact. Request sent to telco team to send ASR. Escalation opened. No formal escalations in Ireland, but we will do best effort and escalate our side after PTT delivery 4/8- request sent to PTT, pending response. 5/5- PTT working with LCON on site survey 5/10- pending Wayleave agreement. Melissa seeing who the Wayleave is with. 5/19- MATTHEW ERSKINE CONTACTED ENET MATTHEW IS NOW GOING TO WORK ON GETTING THE,WL SIGNED BY THE LANDLORD AND ALSO ADVISED THAT HE HAS CONTACTED THE IDA FOR,US TO CARRY OUT OUR WORKS WITHIN THE PARK. 6/2- pending wayleave agreement 6/11- still pending wayleave 8/4- local real estate person is working on agreement. Should be done by 8/5 8/17- found out wayleave should be done this week. 9/1- wayleave complete, pending confirmation with enet , 9/7- following up with Enet on status of wayleave 9/15- PTT circuit is due 9/23 9/21- tail delivered, we are building our network and testing 9/29- network x-cons completed on 9/28, pending Layer 3 10/6- DMARC terminated, asking when we can close the orders. 10/7- order ready for activaion, let enginer know
2011-08-05 | Beth | NV068-02-IJ | Las Vegas, NV | 1536, T1 |  | IQBJXL7P lsv I1418 (clsd) |  | 4978474 | P1860320 |  | 2545339 | 1280 | BCBKMB1Y0001 | 50.HCGS.619482..CTRL | 0CPZ7T | 2011-08-15 | 2011-08-29 | 2011-08-30 | bpdd | 2011-09-01 | 2011-08-30 | UnitedHealthGroup- 65144 | (702) 303-7293, tauoa.falo@uhc.com | requested Mon 10/24 at 3pm central. | completed with Tauoa on 10/24 | LEC FOC for 8/29 8/30 ready for activation
2011-09-15 | core | NY068-04-IJ | New York, NY | POTS line |  | Order Number: N1PX9087 Date Due: 2011-10-12 Billing Telephone Number: 2123025173 Circuit ID or Telephone Number: 212 302-5173 NSPE0004762578 Circuit ID or Telephone Number: 212 302-5173 | [12 empty] | bpdd | 2011-12-29 | [5 empty] | request completed on 10/14. Asked for binding post info
2011-10-27 | Melissa | UNJ20-04-CJ | East Windsor, NJ | gold car upgrade 1228 |  | job 50769 |  |  | P1536327 |  |  | 1228 | BCBJP9GC0001-3 | [5 empty] | bpdd |  |  |  | 763-744-1886, steve_betsinger@uhc.com |  |  | completed on 10/27
2011-08-18 | Beth | C1518-04-IJ | Teleperformance Columbus OH | PIP DS3 |  | CDR201108180096 (approved 8/18) IQBJX2PV |  | 4997294 | P1863984 |  | 2712155 | 9216 | BCBKMJ630001 | 13/HFGS/105883/TWCS Demarc: 1st Flr Computer Rm Blue TW Telecom Cabinet Marked X3001 (DSX Panel) Pos ition 7 Demarc verified via ASR information. Extended: N Tagged: Y | 0CP464 | 2011-08-24 | 2011-09-07 |  | bpdd | 2011-09-28 | 2011-10-10 | UHGECC- 65516 | 763-744-2154, scott_moyer@uhc.com |  | completed with Scott on 10/21 | 8/18- cdr created, order sent to Beth 10/25- ASR sent, pending response 9/1- pending FOC for 9/7, new committed date is 9/28 9/15- time warner loop accepted, pending TPTA mux 9/22- escalting on TPTA mux, trouble ticket S2712386 9/29- still pending ticket 10/6- ticket resolved, mux written, mux will be wired 10/11. trying to better that. 10/10 order ready for activation ,
2011-08-22 | SA disco | UNC16-13-DJ, | Greensboro NC | disco OC12 |  | NSPE0004701127 Request 15185044 u197442 OQBJX5YJ (comp) gnb O1008 | [6 empty] | PLBJFRD70001/O2-FK5D-KYMF-0001 U197442 | PLBJFRD70001/ gnb o2-fk5d-kymf-0001 |  |  |  |  | bpdd | 2011-09-22 | 2011-11-03 |  |  |  |  | 9/29= disco is past due, internet never worked it. Escalated to mgr to have them work it. 10/5- local order opened up, pending disco asr to AT&T 10/13- disco should have completed on the 11th under LEC order CX83F3M3 10/20-soft disco complete. Escalating for order completion 10/27- escalating further for order completionc 11/3- disco completed
2011-10-14 | Core | UVA01-04-IJ | Richmond, VA | New POTs line |  | NSPE0004841256 Order Number: N0QM20103 | [6 empty] | 8042721074 | 8042721074 |  |  |  |  | 91 9873139388 anupam_datt@optum.com | 2011-10-28 | 2011-10-28 |  |  |  |  | completed on 10/28- JOANNE L FOX, 215 466-5398,OPB JOHN SERGOT 763 744-1582,RQST INSTL POTS LINE,ONSITE CONTACT SHAWN MCDONALD 804 267-5333,OR JOHN SERGOT 763 744-1582,TAG & TERM @ DEMARC & EXTEND TO MDF ROOM,WFA COMPLETION,VER XX PLACD TAG @ DMARK, SUB NOT IN THE BUILDNG ADVSD JP DESK ST 20
2011-09-30 | Centralized disco | OH085-02-DJ | CANFIELD OH | disco |  | NSPE0004804034 OQBJZD9V | [6 empty] | BCBJ7N6R0001-0003 | [5 empty] | bpdd | 2011-10-27 | 2011-10-27 |  |  |  |  | disco completed on 10/27
2011-06-20 | Neha- ordered B end | AU526-01-IJ | LILYFIELD, Australia | 2048 E1 |  | S/O 4855749 bearer 4861971 encapsulation s/o 4926249 | [5 empty] | 1024 | W0Y47225 (Wilpak) |  |  | 2011-07-15 | 2011-09-20 |  | bpdd | 2011-10-04 | 2011-09-15 | 65142 | (763) 744-1886, steve_betsinger@uhc.com | scheduled for 11/8 at 1pm Central. | activated with Steve. | 6/23- pending order info and SOF from Neha 7/13- order opened, pending tech validation with lcon 7/20- Local loop order sent to Telstra, requesting 8/24 date. 7/27- Still pending FOC date from Telstra. 7/28- Order is on hold pending Commercial Works Quote approval. Commercial Works Quote document attached for a total of $3636.15 Please respond within 10 business days to avoid order being withdrawn due to no response. In the meantime the order is HELD all work has ceased and the TCD provided is now no longer valid. 8/11- UHG approved charges, telstra told to proceed. 8/17- pushing telstra for delivery date. 8/25- Telstra delivery date is 9/20, need 10 days for building/testing on our side. Expected delivery date would be 10/4. Melissa needs to reach out to Ravi tio better that. 9/15- order is now ready for activation 10/20- new order issued for encapsulation change 10/26- encaupsulation is changed and order is ready for activation.
2011-09-06 | Beth | NY015-03-IJ | Hempstead, NY | 1536, T1 |  | NSPE0004736283 IQBJYRTY |  | 5024003 | P1869382 |  | 3075035 | 1280 | BCBKMWLK0001 | 32.HCGS.706366..NY P2 DEMARC=BLDG MAIN BSMT TELCO CAGE | 0CQC4G | 2011-09-15 | 2011-10-14 | 2011-10-14 | bpdd | 2011-11-01 | 2011-10-27 | UnitedHealthGroup- 65145 | (860) 702-6323, dave_marquis@uhc.com | scheduled for 11/09/2011 4:00 PM Central | activation completed with Dave | asr sent on 9/15 9/22- LEC FOC for 9/27 9/29=- Order has been jeop due to per TELCO the tech talked t o LCON Susana refused the circuit. They doesn't want the service 10/6- pending ASR supp to send the LEC back out. 10/13- New LEC FOC 10/14 10/20- LEC delivered, pending order closure. 10/27- testing completed, escalating for order closure 11/9-activation complete.
2011-09-15 | Beth | UTN21-01-IJ | Brentwood, TN | 44736, DS3 |  | NSPE0004762512 CDR201109150064 IQBJYWG9 | [5 empty] | 1280 | BCBKMYLP0001- | NV/HFFS/258584/ /TQW / DEMARC: B1.1.3 shelf 3 jack3, tagged not extended. |  | 2011-09-20 | 2011-10-17 | 2011-10-18 | bpdd | 2011-10-31 | 2011-11-03 | UnitedHealthGroup- 65110 | 715/841-7731, sonja_d_mroczynski@uhc.com |  | activated with Sonja on 11/4 | 9/22- ASR sent pending LEC FOC 9/29- escalating for FOC C201109290165 10/6- LEC due date is 10/17 10/20- LEC delivered, testing. C201110190199 10/27- Pending dispatch in MEJ and NAA sites scheduled 10/28/2011. 11/3- found LOS while testing with XO, pending vendor meet schduled for today. 11/4- fixed issue with XO and activated with Sonja
2011-09-15 | Beth | TX007-01-IJ | San Antonio | 1536, T1 |  | NSPE0004762740 IQBJYWJL |  | 5033814 | P1870288 |  | 3215052 | 1280 | BCBKMYMD0001 | 31/HCGS/694107//SW DEMARC LOC: 4TH FLOOR STE 400 TELCO BACKBOAR DEMARC LOC Continued: D CAB #1 SLOT #2 Extended Wire (Yes or No): NO | 0CQD4D |  | 2011-09-29 | 2011-09-27 | bpdd | 2011-10-12 | 2011-09-27 | UnitedHealthGroup- 65113 | 715/841-7731, sonja_d_mroczynski@uhc.com | Requested Date 11/10/2011 02:00:00 PM Central Time * Conference Bridge * 866-819-9840 Conference Pass Code 3365052 | activation on 11/10 with Sonja | 10/6- order ready for activation, engineer assigned 11/10- activated
2011-09-21 | Beth | UMD43-07-CJ | Frederick, MD | change encapsulation to PPP |  | NSPE0004777710 CDR201109260027 IQBJY8Z3 OQBJZDH5 |  | 5043964 |  |  |  | 12288 | BCBKM5BJ0001 (in) BCBH54980001 (out) | [5 empty] | bpdd | 2011-11-14 |  | UnitedHealthGroup- 64694 | (763) 744-1575, daniel_j_skripka@uhc.com | scheduled for 11/04/2011 4:00 PM Central Time | completed with Dan on 11/4 | CP88 record change asr pon IQBJY8Z3XATQMB01 has been transmitted, records change due 10/21. 10/27 ready to schedule for encapsulation change.
2011-10-14 | Core | NJ005-03-IJ | Newark, NJ | New POTs line |  | NSPE0004841295 Order Number:n8yg13351 | [6 empty] | Circuit ID or Telephone Number: 9736450296 | [5 empty] | bpdd | 2011-11-07 | [5 empty] | Per Eugene in Management office this line was refused. Order has been canned. Please straighthen with landlord and send new request for line if needed. Order has been canned. 11/4- new due date on 11/7 11/10- order completed on 11/7
2011-10-26 | Core | MA023-03-IJ | Wakefield, MD | 1 POTS line |  | NSPE0004873503 N5KE9315 | [6 empty] | 781 246-1960 | 781 246-1960 |  |  |  |  | bpdd | 2011-11-09 | [5 empty] | completed 11/9 BOB SELLERS 781-557-3082 ALT JOHN SERGOT 763-744-1582 PL TAG AT BLDG DEMARC AND RUN JACK,(DOE*) OPB JOHN SERGOT 763-744-1582 NSPE0004873503 OPB NSPE0004873503,246-1960, HH, 11-07, 00:30,WAW DMARC MN TELCO PER J MCLEAN VER CODE XX
2011-04-18 | Katrina | C1524-01-IJ, | Franklin Lakes, NJ | 4608 3xT1 |  | NSPE0004350948 IQBJS2TJ |  | 4828922 | P1834258 |  |  | 1536 | BCBKKNJL0001-0003 | /HCGS/450962//NJ GND,RM 3,TEL-CLOSET,SHLF 8,POS 13,3RD FLR CMP RM /HCGS/450963//NJ GND,RM W,TEL-CLOSET,SHLF W,POS 1,CMP /HCGS/450964//NJ GND,RM 3,TEL-CLOSET,SHLF 8,POS 14,3RD FLR CMP RM |  | 2011-04-22 | 2011-05-05 | 2011-05-05 |  | 2011-05-17 |  | UHCECC 65495 | 763-744-2082 eric_taylor@uhc.com |  |  | 5/5- lec delivered we are testing 5/10- local loops tested, pending Layer 3 testing 5/17- order ready for activtion, informed uhg engineer
2011-07-20 | Katrina | UT020-03-IJ | Provo, UT | 1536, T1 |  | NSPE0004609064 IQBJWZ1V |  | 4953397 | P1855777 |  | 2331377 | 1280 | BCBKL3B80001 | 64/HCGS/199972 /MS DEMARC LOC: mn flr telco cab 2 slot 3 of 8 DEMARC LOC Continued: Extended Wire (Yes or No): no |  |  | 2011-08-10 | 2011-08-03 | bpdd | 2011-08-17 | 2011-08-03 | UnitedHealthGroup 65235 | (763) 744-1886, steve_betsinger@uhc.com |  |  | 7/20- order sent to Katrina 7/27- pending ASR, NDMT B201107270054 8/4- order is now complete and ready for activation 10/21- activation didn't go on 10/20. extended dmarc issues. Need to reschedule.
2011-07-20 | Katrina | UNE13-03-IJ | Lincoln, NE | 1536, T1 |  | NSPE0004609236 IQBJWZ2P |  | 4953429 | P1855782 |  | 2331379 | 1280 | BCBKL3CF0001 | NE/HCGS/104512/ /WINW DEMARC LOC: BLDG 1,FLR 1,RM TELCO DEMARC LOC Continued: DEMARC:3RD FLR TELCO ROOM SLOT 1 OF 2 RJ48C TAGGED |  | 2011-07-25 | 2011-08-10 |  | bpdd | 2011-08-17 | 2011-08-17 | UnitedHealthGroup 64893 | (763) 744-1886, steve_betsinger@uhc.com |  |  | 7/20- order sent to Katrina 7/27- ASR sent, requesting delivery from lec of 8/10, pending FOC. 8/4- pending 8/10 FOC 8/11- LEC didn't deliver, opened NDMt B201108110038 for late loop delivery 8/18- lec delivered- order closed and ready for activation.
2011-07-20 | Katrina | UTN06-03-IJ | Memphis, TN | 1536, T1 |  | NSPE0004609318 IQBJW0KV |  | 4953668 | P1855827 |  | 2339128 | 1280 | BCBKL3FL0001 | 20/HCGS/106243/TWCS DEMARC LOC: BLDG 1,FLR 1,RM TELCO DEMARC LOC Continued: 1ST FLR. TELCO RM. RELAY 001.W1.01 PANEL WJ003 POSITION 1 Extended Wire (Yes or No): No |  | 2011-07-26 | 2011-08-11 | 2011-08-18 | bpdd | 2011-08-18 | 2011-08-18 | UnitedHealthGroup 64556 | (763) 744-1886, steve_betsinger@uhc.com |  |  | 7/20- order sent to Katrina 7/27- ASR sent requesting 8./11 delivery date 8/4- pending LEC delivery 8/11 8/18- order ready for activation, engineer informed.
2011-08-18 | Beth | C1093-05-IJ | Secaucus, NJ | 7680, 5 x T1 |  | IQBJX19Q |  | 4996791 | P1863919 |  | 2712086 | 128 | BCBKMJ2G0001-0005 | HCGS/458560//NJ DEMARC LOC: GND,RM CAGE13,TEL-CLOSET,SHLF 11,POS 19 /HCGS/458561 /NJ DEMARC LOC: GND,RM CAGE13,TEL-CLOSET,SHLF 11,POS 21 /HCGS/458562 /NJ DEMARC LOC: GND,RM CAGE13,TEL-CLOSET,SHLF 11,POS 23 /HCGS/458563 /NJ DEMARC LOC: GND,RM CAGE13,TEL-CLOSET,SHLF 11,POS 25 /HCGS/458564 /NJ DEMARC LOC: GND,RM CAGE13,TEL-CLOSET,SHLF 11,POS 22 | 0CP43N; 0CP43Q; 0CP43R; 0CP43P; 0CP43S; | 2011-09-21 |  |  | bpdd | 2011-10-05 | 2011-10-05 | UHGECC- 65423 | 763-744-2154, scott_moyer@uhc.com |  |  | 8/18- beth is processing, in strike area, likely wont' come in until early next year. 9/1- FOC date for 12/30 9/8- FOC date moved in to 9/21 9/22- spoke with Carol of VZT, advised customer not ready. Tech spoke with LCON Lynn Quinn but she's not associated on United Healthcare and she's doesn't know anything about the order. Please supp with valid LCON and new due date. 9/29- pending FOC from the LEC on supp 10/5=- order ready for activation, engineer informed. 11/2- tag and locate ticket opened. 2011110118379 11/11- circuit now re-terminated 11/21- per John You can move the below order to the completed tab. I will be submitting a disconnect for these circuits and we will be installing a new DS3.
2011-09-16 | Beth | FL001-02-IJ, | Inspiris, Melbourne, FL | 1536, T1 |  | NSPE0004765089 IQBJZDPW |  | 5056166 |  |  |  | 1280 | BCBKM7HS0001 | 58/HCGS/780607//SB DEMARC LOC: BLDG MAIN,FLR 1,RM TELCO DEMARC LOC Continued: FIRST FLOOR, EQUIPMENT BACKBOARD, MM1/3, RJ48C, Extended Wire (Yes or No): No |  |  | 2011-10-18 | 2011-10-19 | bpdd | 2011-10-26 | 2011-10-20 | UnitedHealthGroup | (860) 702-6323, dave_marquis@uhc.com |  |  | LEC foc is for 10/18 10/20- LEC delivered, testing ready for activation, engineer notified.
2011-09-15 | Beth | TN008-01-IJ | Franklin, TN | 9216, 6xT1 |  | NSPE0004762111 IQBJYWL1 | 5033820 | P1870329 |  | 3233728 | 2048 | BCBKMYNW0001-0006 | T4/HCGS/848870//SC T4/HCGS/848871//SC T4/HCGS/848872//SC T4/HCGS/848873//SC T4/HCGS/848874//SC T4/HCGS/848875//SC Demarc: 2nd flr cust telco rm mm1 pos. 2,3, 2nd flr cust telco rm mm2 pos. 1,2,3,4 RJ48x tagged and not extended. LCON is aware where the demarc is. LCON:DAVE CONNERLY/615-523-5576 | 0CQD6C; 0CQD6D; 0CQD6F; 0CQD6G; 0CQD6H; 0CQD6J |  | 2011-10-11 | 2011-10-12 | bpdd | 2011-10-18 | 2011-10-12 | UnitedHealthGroup- 65115 | 715/841-7731, sonja_d_mroczynski@uhc.com |  | Saonja activated on Monday 11/14 | pending 10/11 FOC 10/6- LEC delivered, pending DMARC for all loops. Testing. Order now ready for activation, informed engineer
2011-10-26 | Core | MD028-02-IJ, | Bel Air MD | 1 POTS line |  | NSPE0004873479 Order Number: N1BH68871 | [5 empty] | Billing Telephone Number: 4105692340 Circuit ID or Telephone Number: 410 569-2340 | Billing Telephone Number: 4105692340 Circuit ID or Telephone Number: 410 569-2340 |  |  |  |  | bpdd | 2011-11-11 | 2011-11-16 |  |  |  |  | completed 11/16 DONNESSA X VICTOR, 800 315-4477,CONTACT: TOMARA HARRIS 202 738 3732,PLEASE TAG IN BUILDING DEMARC.,SECONDARY CONTACT: JOHN SERGOT 763-744-1582,WFA COMPLETION,VER XX PLACED X-CONNECT,LOC PR-174,TAGGED ST 30
2011-11-17 | Beth | C1532-01-IJ | Cedar Rapids, IA | 4608, 3xT1 |  | NSPE0004930321 IQBJ025H | 5126979 | P1886448 |  | 3389096 | 4144 | BCBKN1YY0001-0003 | 34/HCGS/067235 /NW 1ST FLR DATA CENTER/CAB R5 CAT 3/SL 14 OF 28 34/HCGS/067236 /NW 1ST FLR DATA CENTER/CAB R5 CAT 3/SL 15 OF 28 34/HCGS/067237 /NW 1ST FLR DATA CENTER/CAB R5 CAT 3/SL 16 OF 28 | 0CQ443 0CQ442 0CQ441 |  |  | 2011-11-30 | bpdd | 2011-12-16 | 2011-12-01 | UHG-ECC 65461 | 763-553-4657, nicholas_cooper@uhc.com |  |  | 11/17- order sent to beth. 12/1- order complete, engineer informed.
2/1/2011 re-issued 7/5 | Katrina | NV064-02-IJ | Pahrump, NV | New Subrate DS3, 10M |  | IQBJWKJX LSV I0001362 (closed) | new tn 4935256 | P1817104 | 10mg | 2015776 | 2048 | BCBKLWPS0001 | 16/HFGS/501067//NV 1st floor phone room mount 1 slot 2. Not Ext | 0CMW4T |  | 2011-11-02 | 2011-11-04 | 2011-11-04 | 2011-08-19 | 2011-11-08 | 65144 | (702) 303-7293, tauoa.falo@uhc.com | scheduling for 11/28 at 10pm Central | activated with Tau on 11/28 | 6/3- per John AT&T has contract, site survey. 9/2 site ready date. 7/5 order sent to Katrina to re-process now that AT&T has a site ready date 7/17- pending ASR NDMT C201107140154 7/27- ticket needed to be opened for ASR generation 8/3- FOC Received date 8/3/2011. FOC Date: 09/02/2011 per LEC ORD NBR: C21074730 9/1- tech didnt' get accesss, needed to supp order, sent supp for 9/7 9/8- No FOC back from the LEC on our supped ASR. opened ticket C201109080043 9/15- ASR rejected for valid CCEA. asked for that information 9/21- AT&T came back with an 11/2 date, saying it was pending an access ring. Opened ticket C201109220145 to get better info and to escalate for better due date. 9/28- this went to build with AT&T. I need to get the PM name and I will go to them and ask them why this is out to build. Build Detail: Code 65 involves (1) reconfigure/rewire existing MUX, (2) translation work, (3) backplane wiring, (4) install plugs, (5) install CPE as determined by outside plant engineer during the site visit, (6) place greater than 2500 ft of fiber and conduit, (7) order and install new central office equipment, (8) trenching, (9) install new manhole and (10) permits for right-of-way. 10/12- order was supped for new LCON. Old LCON is no longer iwth the company. 10/20- FOC for 11/2, Melissa is checking to see if AT&T has new lcon. 10/26- AT&T has new LCON and is passing to BIC engineer 11/7- LEC delivered, we are pushing to close our order. Loop testing ticket C201111070065 11/8- order now ready for activation, engineer informed.
2011-07-20 | Katrina | NY008-03-IJ | Rochester, NY | 1536, T1 |  | NSPE0004609266 IQBJWZ20 roc I4999 (closed) | 4953460 | P1855785 |  | 2331382 | 1280 | BCBKL3CJ0001 | T-42687 demarc: 1ST FLR SLOT2 POS4 enclosure, tagged, extended to 3RD FLR SRVR RM TO A SMJK LOOPBACK SPLIT E |  | 2011-08-11 | 8/10 (MFS) | 2011-08-11 | bpdd | 2011-08-17 | 2011-08-11 | UnitedHealthGroup 65194 | (763) 744-1886, steve_betsinger@uhc.com |  | ******Activation Complete****** customer Steve asked me to test the smartjack and i tested clean he said that we can complete our side as plug and play since we tested the smartjack clean he will have their tech to check their inside wiring. I will complete DTAC side as plug and play. | 7/20- order sent to Katrina 7/27- order designed on local network, pending ASR for last mile 8/4- local portion complete, pending 8/11 fOC 8/17- order complete and ready for activation, engineer notified.
2011-08-05 | Beth | TX102-01-IJ | WellMed, San Antonio, TX | 44736, DS3 |  | CDR201108050105 IQBJXMY1 sna I8430 | 4978801 | P1860560 |  | 2548237 | 2048 | BCBKMCDN0001 | 31/HFGS/652096//SW Demarc: 1st floor, suite 125 (IT room), Cab 1 slot 1 | 0CP0G9 | 2011-08-16 | 2011-08-25 | 2011-08-25 | bpdd | 2011-09-22 | 2011-09-09 | UnitedHealthGroup- 65122 | (763) 744-2077, robert_a_benson@uhc.com |  | John confirmed active on 12/2 | 8/26- LEC delivered local order, we are testing 9/1- Pending Mux completion scheduled 09/02 9/8- was unable to see AT&T loop at customer prem, dispatched to check cabling, dispatch due 9/8 9/15- order ready for activation, engineer notified
2011-08-16 | beth | UNJ06-07-IJ | Basking Ridge- NJ | 44736, DS3 |  | CDR201108180085 IQBJX2P2 njy I132166 (closed) | 4997113 | P1863986 |  |  | 12000 | BCBKMJ670001 | /HFGS/067232//NJ Demarc: Flr 1 Main Telco Room DSX Position C Tagged. Not extended. | 0CP466 |  | 2011-10-20 | 2011-10-20 | bpdd | 2011-11-17 | 2011-10-20 | UnitedHealthGroup-Raven AS 65120 | Terry_Bjorke@uhc.com, 763-694-7409 |  | activation completed on 11/28 | 8/16- sent to Matt for CDR. 8/17- CDR created and sent to beth for processing 8/25- order in provisioning, pending ASR 9/1- pending FOC for 9/9 9/8- order due date pushed to 10/12, pending capacity, open slot on OC system was found and sent to provisioner. opened ticket C201109080119 9/15 LEC didn't deliver. LCON EDWARD NAUGIN NOT AWARE OF ORDER 9/22- esclating for ASR supp 9/29- new LEC delivery 10/7, node work being done 10/5- tested through local network, LEC delivery 10./7 10/13- Edward didn't respond to the LEC. changed LCON, supped order 10/20- LEC delivered, trying to better commit date. ticket C201110200076 opened. order ready for activation, engineer notified.
2011-09-06 | Beth | UTX45-02-IJ | San Antonio, TX | 44736, DS3 |  | CDR201109060060 NSPE0004736370 IQBJYRVR sna I8495 (closed) | 5024530 | P1869395 |  |  | 2048 | BCBKMWL10001 | 31/HFGS/652129//SW Demarc: BLDG MAIN FLR 1 RM TELCO Main Tel RM ATT relay rack 2 shelf 2 slot 1 Extended: N |  |  | 2011-10-03 |  | 2011-10-03 | 10/26/2011 new 12/22 moved back to 11/15 | 2011-11-08 | UnitedHealthGroup-65122 | (763) 744-2077, robert_a_benson@uhc.com | sched for 11/18, might already be active | per John completed. | 9/12- order was submitted by Beth 9/15- ASR sent 9/30- LEC FOC is for 10/3 10/6- loop accepted pending mux. Opened ndmt ticket C201110060146 10/13- mux is held for capacity, trying to better date. LEC deliverd. 10.20- ticket C201110200092 opened to get mux completed. 10/27- mux is scheduled to be wired today. asking to have order closed early. 11/3- path ready, went through testing. found rolled cables those were fixed on 11/2 11/8- order now ready for activation, engineer informed.
2011-09-15 | Beth | TN013-01-IJ | Brentwood | 9216, 6xT1 |  | NSPE0004762653 5033809 IQBJYWC6 |  | P1870243 |  |  | 2048 | BCBKMYKF0001-0006 | T4/HCGS/848795//SC T4/HCGS/848796//SC T4/HCGS/848797//SC T4/HCGS/848798//SC T4/HCGS/848799//SC T4/HCGS/848800//SC DEMARC: 1ST FL TEL RM,MM2SL1 1ST FL TEL RM,MM2SL2 1ST FL TEL RM,MM3SL2 1ST FL TEL RM,MM2SL4 1ST FL TEL RM,MM3SL1 1ST FL TEL RM,MM2SL3 RJ48X tagged not extended |  | 2011-09-21 | 2011-10-04 | 2011-10-04 | bpdd | 2011-10-12 | 2011-10-05 | UnitedHealthGroup- 65116 | 715/841-7731, sonja_d_mroczynski@uhc.com | requested 11/22/2011 1:00 PM, CT | activatied with Sonja | Pending LEC FOC of 10/4 10/6- order is now ready for activtion 12/1- sonja confirmed they were active.
2011-09-16 | Beth | AZ005-02-IJ | 2025 North 3rd Street, suite 170 Phoenix | 4608 3 xT1 |  | NSPE0004764450 IQBJY3Q4 | 5043313 | P1872062 |  | 3234478 | 1280 | BCBKM2TL0001-003 | 14/HCGS/430430 /MS DEMARC LOC: 1st floor main it shelf#4 slot 2 of 28 14/HCGS/430429 /MS DEMARC LOC: 1st floor main it shelf#4 slot 1 of 28 14/HCGS/430431 /MS DEMARC LOC: 1st floor main it shelf#4 slot 3 of 28 | 0CQHLH 0CQHLF 0CQHLG |  | 2011-09-29 |  | bpdd | 2011-10-19 | 2011-09-30 | UnitedHealthGroup- 64648 | 763-694-7370, masroor_khan@uhc.com | 11/08/2011 8:00 AM Central Time / GMT 14:00 bridge 866-819-9840 pcode 3365052 | per John completed. | 10/6- order ready for activation, engineer assigned 10/27- activation scheduled. 11/17- nobody joined the activaion on the 8th. Is this working? No response from engineer.
2011-10-19 | Beth | TN026-04-IJ | 1208 Pointe Centre Drive Suite 230 Chattanooga, TN | 3072 2xT1 |  | NSPE0004852218 | 5079771 | P1880826 |  | 3313226 | 2752 | BCBKNL5S0001-0002 | T1/HCGS/827773//SC 2ND FLOOR, SUITE 230 TELCO ROOM DUALMOUNT 1, SLOT 2, RJ48X T1/HCGS/827774//SC 2ND FLOOR SUITE 230 TELCO ROOM DUA | 0CQWWS; 0CQWWT; |  | 2011-11-09 | 2011-11-10 | bpdd | 2011-11-16 |  | UnitedHealthGroup- 64674 | 763-694-7409, terry_bjorke@uhc.com |  | per Terry this is up and operational as of 11/18 | 10/27- order with provisioning, pending ASR 11/3- pending FOC for 11/9 11/10- order complete- engineer informed.
2011-11-02 | Core | UMD17-04-IJ | COLLEGE PARK, MD | 1 POTS line |  | NSPE0004890109 Order Number: N1BH69694 Date Due: 2011-11-17 Circuit ID or Telephone Number: 301 220-0191 | [5 empty] | Billing Telephone Number: 3012200191 | Circuit ID or Telephone Number: 301 220-0191 | [5 empty] | 2011-11-17 | [5 empty] | order complete 11/17- NICHELLE X NIXON, 800 540-6960,OPB JOHN SERGOT 763 744-1582 NSPE0004890109,SITE CONTACT MARGARET AYALA 301 441-3855 OR JOHN SERGOT 763 744-1582,WFA COMPLETION,VER XX TAGGED AT DMARK ST 20
2011-11-03 | Core | MD002-02-IJ | Columbia, MD | 1 POTS line |  | NSPE0004895927 | [5 empty] | 443 285-0632 | 443 285-0632 |  |  |  |  | bpdd | 2011-11-16 | [5 empty] | order completed 11/16
2011-11-17 | Core | MD017-02-IJ | Boulevard Dundalk, MD | Pots line |  | NSPE0004928822 Order Number: N3LH77880 Date Due: 2011-11-30 | [5 empty] | 4102822005 | Circuit ID or Telephone Number: 410 282-2005 | [5 empty] | 2011-11-30 | [5 empty] | completed on 11/30
2011-11-21 | Melissa | AZ005-04-CJ | Pheonix, AZ | upgrade gold car to 2752 |  |  |  | P1872062 |  |  |  | BCBKM2TL0001-003 | [7 empty] | 2011-11-30 |  |  |  |  | gold car upgraded on 11/30
2011-11-21 | core | MD002-01-DJ | Columbia MD | disco pots |  | NSPE0004944677 Order Number: D2DP13446 | [5 empty] | 443-285-0632 | Billing Telephone Number: 443.285.0632 |  |  |  |  | bpdd | Date Due: 11*29*2011 | [5 empty] | disco complete 11/29
2011-10-05 | Beth | C1475-07-CJ, | Atlanta, GA | Upgrade to 6xT1, 9216 |  | NSPE0004814849 IQBJZQ02 OQBJZT02 | 5064155 | P1877013 P1826542 (out) |  | 1799678 | 5500 | BCBKNC4T0001-0006 BCBKJ3KR0001-0004 (out) | DEMARC LOC: SUIT 1400, , DEMARC LOC Continued: DEMARC FOR CIRCUIT 38/HCGS/922596//SB IS SLOT 4, 38/HCGS/922597//SB slot 3. Both located at the 14th floor, suite 1400 tel room, mm1, rj48c | 0CQQ2G; 0CQQ2D; 0CQQ2F; 0CQQ2B; 0CQQ19; 0CQQ2C; | 2011-11-04 |  |  | bpdd | 2011-11-08 |  | UHGECC- 65505 | 763-744-0840 matt_f_seymour@uhc.com | completed with Matt on 12/2 |  | orderpro submitted, pending OE 10/20- LEC FOC for 2 new T1s is 10/31 11/3- records needed to be updated, supp was send, new FOC is 11/4 11/8- ready for hotcut, let engineer know 11/17- scheduled for 11/21 12/1- matt requested re-schedule, sched for 12/2 12/5- completed 12/2 with Matt
2011-10-28 | SA disco | UAZ59-02-DJ | Phoenix, AZ | disconnect |  | NSPE0004879501 OQBJ0GR9 | n/a |  |  |  |  | BCBH9KBP0001 | [5 empty] | bpdd | 2011-11-28 | [5 empty] | disco completed 11/28
2011-10-28 | SA disco | UAZ58-03-DJ | 4601 E. Hilton Ave, Phoenix, AZ | disconnect |  | NSPE0004879502 OQBJ0FDW | n/a |  |  |  |  | BCBJB8RM0001-8 | [5 empty] | bpdd | 2011-11-23 | [5 empty] | disco complete 11/23
2011-10-28 | SA disco | C1395-02-DJ | Des Moines, IA | disconnect |  | NSPE0004879503 OQBJ0C3L | n/a | P1428676 |  |  |  | bcbjfy8c0001 | [5 empty] | bpdd | 2011-11-28 | [5 empty] | disco complete 11/28
2011-11-01 | Beth | C1496-06-IJ | Tucson, AZ | 9216, 6xT1 |  | NSPE0004887506 IQBJ0M00 |  | P1883467 |  | 3355289 | 6000 | BCBKNTDM0001-0006 | 57/HCGS/106930/TWCS 57/HCGS/106931/TWCS 57/HCGS/106932/TWCS 57/HCGS/106933/TWCS 57/HCGS/106934/TWCS 57/HCGS/106935/TWCS DMARC info ckt 1:1st flr. telco rm. rj48c shelf 3 slot 1 ckt 2:1st flr . telco rm. rj48c shelf 3 slot 2 ckt 3:1st flr. telco rm. rj48c shelf 3 sl ot 3 ckt 4:1st flr. telco rm. rj48c shelf 3 slot 4 ckt 5:1st flr. telco r m. rj48c shelf 3 slot 5 ckt 6:1st flr. telco rm. rj48c shelf 3 slot 6 tag and not extended | 0CQ1F2; 0CQ1F3; 0CQ1F4; 0CQ1F5; 0CQ1F6; 0CQ1F7; |  | 2011-11-21 | 2011-11-22 | bpdd | 2011-11-30 |  | UHG-ECC- 65470 | 763-553-4657, nicholas_cooper@uhc.com |  | per john active 12/9 | 11/18- 11/21 FOC date 11/28- order closed and ready for activation. 12/7- passed configlet to nick last week, pending activation.
2011-11-04 | SA disco | C1456-03-DJ | Topeka, KS | disco |  | NSPE0004897640 OQBJ0Q3P | [5 empty] | BCBJV1BC0001 | [5 empty] | bpdd | 2011-12-01 | [5 empty] | completed 12/1
2011-11-15 | Melissa | MN053-59-CJ | ELK RIVER MN | PVC add to UHG-MA |  |  | n/a |  |  | 3478146 | 1004 | w0v78421 | [8 empty] | UHG-MA 65098 | tim gunderson |  |  | 11/16- asked John for DLCI and ASN info 11/23- info provided. 11/30- PVC created Order Number: 7186405 PVC ID: 3478146 , reequested layer 3 build. 12/7- layer 3 build complete and sent to John
2011-11-20 | Core | MD002-01-DJ | New York, NY | disco pots |  | NSPE0004958179 Order Number: D2HF5680 | [6 empty] | Billing Telephone Number: 212 221-0814 Circuit ID or Telephone Number: 212 221-0814 | [5 empty] | Date Due: 12-02-2011 | [5 empty] | completed 12/2
2011-09-06 | Beth | C1396-03-IJ | Tampa Bay, FL | 7680, 5 x T1 |  | NSPE0004736222 IQBJYQL5 | 5023021 | P1869077 |  | 3029041 | 5008 | BCBKMV1B0001-0005 | 69/HCGS/413882//GTES DEMARC LOC: dmarc info: 1st flr serv rm, sh 1, slot 1 of 4 rj48x 69/HCGS/413883//GTES DEMARC LOC: dmarc info: 1st flr serv rm, sh 1, slot 2 of 4 rj48x 69/HCGS/413884//GTES DEMARC LOC: dmarc info: 1st flr serv rm, sh 1, slot 3 of 4 rj48x 69/HCGS/413885//GTES DEMARC LOC Continued: w/opener, non ext, tagged, 69/HCGS/413886//GTES DEMARC LOC: dmarc info: 1st flr serv rm, sh 2, slot 1 of 4 rj48x DEMARC LOC Continued: w/opener, non ext, tagged | 0CQCPW; 0CQCPZ; 0CQCPT; 0CQCPV; 0CQCPX; |  | 2011-09-29 | 2011-09-29 | bpdd | 2011-10-06 | 2011-09-30 | UHGECC- 65488 | 763-744-2082 eric_taylor@uhc.com | troubleshooting sched for 12/2 at 3pm | activated with Eric on 12/2 | 9/15- ASR sent, pending response 9/22- LEC FOC 9/29, pending hyperlink capacity 9/29- pending LEC delivery, hyperlink done and tcoms order closed 10/6- order ready for activation, engineer informed 11/29- ticket sent out to show circuit 2 and prove dmarc 9810 from 11/28 12/1 - still having issues with the 2nd circuit. Troubleshooting call sched for 12/2 at 3pm Central
2011-10-14 | Beth | NJ005-02-IJ | Newark, NJ | 3072, 2xT1 |  | NSPE0004841180 IQBJZ5JG NJY-I0133164 (closed) | 5078270 | P1880234 |  | 3312499 | 1536 | BCBKNKTM0001-0003 | /HCGS/462344//NJ DEMARC LOC: BSMT , RM telco, TEL RM , RJ21X, LP Y, CAB N, RCK, POS, rack DEMARC LOC Continued: 5 positio Extended Wire (Yes or No): No | 0CQV61; 0CQV62; | 2011-11-02 | 2011-11-15 | 2011-11-15 | bpdd | 2011-11-17 | 2011-11-17 | UnitedHealthGroup-65107 | 763-744-1556, john_l_rothstein@uhc.com | john verified circuit came up for him on 12/7 |  | sent to beth on 10/14 10/27- order with provisioning, pending ASR. 11/2- aSR sent, pending FOC ticket B201111030043 11/8- FOC date is for 11/15 11/17- lec delivered, not able to loop smjack, ticket 2011111700577 11/28- order ready for activation, john informed.
2011-10-24 | Beth | UMO21-06-CJ | Springfield, MO | 9216, 6xT1, upgrade current 4xT1 |  | NSPE0004864625 IQBJ0BCR OQBJ0FGD SMO- I3920 | 5087195 | P1541386 (out) P1881191 (in) |  | 1673619 | Upgrade to 4608 | BCBJRLWS0001-4 (out) BCBKNMSV0001-0006 (in) | 84/HCGS/037661//SW DEMARC LOC: 1ST FLOOR SERVER ROOM, MM 2 SLOT DEMARC LOC Continued: 14 Extended Wire (Yes or No): NO 84/HCGS/037662//SW DEMARC LOC: 1ST FLOOR SERVER ROOM, MM 2 SLOT DEMARC LOC Continued: 15 Extended Wire (Yes or No): NO 84/HCGS/037663//SW DEMARC LOC: 1ST FLOOR SERVER ROOM, MM 2 SLOT DEMARC LOC Continued: 18 Extended Wire (Yes or No): NO 84/HCGS/037664//SW DEMARC LOC: 1ST FLOOR SERVER ROOM, MM 2 SLOT DEMARC LOC Continued: 19 Extended Wire (Yes or No): NO 84/HCGS/037665//SW DEMARC LOC: 1ST FLOOR SERVER ROOM, MM 2 SLOT DEMARC LOC Continued: 20 84/HCGS/037666//SW DEMARC LOC: 1ST FLOOR SERVER ROOM, MM 2 SLOT DEMARC LOC Continued: 9 Extended Wire (Yes or No): NO |  | `11/7 | 2011-11-17 |  | bpdd | 2011-11-28 |  | UnitedHealthGroup 64630 | 763-744-1847, donald_r_osborn@uhc.com | completed on 12/7 |  | pending os sumission 11/3- pending pip capcity at CRJ, provisioniner is looking for other pip switches 11/10- Will need to install new loops instead since we can't approve it on the original path due to capacity constraints. Pending LEC FOC 11/17 11/17- ready for hotcut. Informed engineer. 12/16- complted on 12/7
2011-10-26 | Beth | MA023-02-IJ | Wakefield, MD | 9216, 6 x T1 |  | NSPE0004873206 IQBJ0DCJ BST-I0077232 (due 11/15) | 5092238 | P1881614 |  | 3317077 | 6144 | BCBKNNL50001-0006 | 95.HCGS.432005..NE DEMARC LOC: 1st flr telco rm rj48x #3 pos 1 of 8 tagged both ids not 95.HCGS.432006..NE DEMARC LOC: 1st flr telco rm rj48x #3 pos 2 of 8 tagged both ids not 95.HCGS.432009..NE DEMARC LOC: 1st flr telco rm rj48x #3 pos 3 of 8 tagged both ids not 95.HCGS.432010..NE DEMARC LOC: 1st flr telco rm rj48x #3 pos 4 of 8 tagged both ids not 95.HCGS.432011..NE DEMARC LOC: 1st flr telco rm rj48x #3 pos 5 of 8 tagged both ids not 95.HCGS.432079..NE DEMARC LOC: 1st flr telco rm rj48x #3 pos 6 of 8 tagged both ids not | 0CQX0T; 0CQX0W; 0CQX0S; 0CQX0V; 0CQX0Z; 0CQX0X; |  | 2011-11-21 | 2011-11-17 | bpdd | 2011-11-23 |  | UnitedHealthGroup- 65103 | (860) 702-6323, dave_marquis@uhc.com | Per Dave active on 12/6 |  | 11/2- FOC for 5 circuits of 11/21, openened ticket B201111030054 to get FOC on 6th circuit 11/10- all circuits now FOCd for 11/21 12/1- all circuits testing clean, pending order closure 12/5- order completed, engineer notified 12/6- dave activated.
2011-11-10 | SA disco | UMN99-41-DJ | Protected 10Gb between Elk River MN and Plymouth MN on the old Verizon ring. | disco |  | NSPE0004914524 s/o 4946326 | [5 empty] | WOV31917 | [5 empty] | bpdd | 2011-12-08 | [5 empty] | disco due on 12/8 12/15- disco not complete. Escalating 12/22- completed.
2011-11-15 | SA disco | VT010-02-DJ | COLCHESTER VT | disco |  | OQBJ0X4W NSPE0004921977 | [5 empty] | BCBJ1BB70001 | [5 empty] | bpdd | 2011-12-15 | [5 empty] | disco completed 12/15
2011-11-18 | SA disco | C1383-02-DJ | ROCKY MOUNT | disco |  | NSPE0004933902 OQBJ1JBB |  | P1414425 |  |  |  | BCBJDX8R0001 | [6 empty] | due 12/19 | [5 empty] | disco completed 12/19
2011-11-18 | SA disco | C1268-01-DJ | JACKSONVILLE FL | disco |  | NSPE0004933963 OQBJ04NJ |  | P1306145 |  |  |  | BCBH4JBB0001 | [6 empty] | 2011-12-19 | [5 empty] | disco completed 12/19
2011-11-18 | SA disco | C1268-01-DJ | JACKSONVILLE FL | disco |  | NSPE0004933963 OQBJ04NK |  | P1691830 |  |  |  | BCBJ61400001 | [6 empty] | 2011-12-19 | [5 empty] | disco completed 12/19
2011-11-21 | SA disco | C1093-02-DJ | SECAUCUS NJ | disco |  | NSPE0004937170 OQBJ09HR | [5 empty] | BCBKMJ2G0001-0005 | [6 empty] | 2011-12-21 | [5 empty] | disco complete 12/22
2011-08-15 | Neha- ordered B end | II745-07-IJ | PUNE, INDIA | E3-dport |  | 4891293 |  |  |  |  | 9216 | W0Y66519 | THE DEMARK LOCATION: (.) circuit id 20294265578 FLOOR / ROOM: CUSTOMER SERVER ROOM RACK NUMBER MODULE NUMBER LAST MILE CABLING COPPER / FIBER: 10 MTRS DETAILS PTT MUX FROM WHERE SERVICE IS PROVIDED LOCATION CUSTOMER SERVER ROOM ID PUNE_UNITEDHC_01(172.22.164.149) DS3 1-8-1 PUNE_ITMC_XDM6 I1 P4 (W) & I3 PORT 4 (PROT) J2- TUG 200 |  | 2011-10-18 | 2011-10-18 |  | bpdd | 2011-10-28 | 2011-10-27 | UnitedHealthGroup- 65177 | 91-9873139388/9810059326 anupam_datt@uhc.com | scheduled for 7am Central on 1/6 |  | 8/15- sent to Neha for ordering. 9/1- Order logged with TCOM, waiting for FOC 9/22- PTT delivery 11/29 9/29- PROVISIONING GOING ON IN PTT NETWORK FOC 10TH OCT 2011 10/13- clarifying with India on PTT delivery date 10/20- ETE testing being performed. 10/27- order now ready for activation. completed.
2011-09-16 | Beth | AZ002-05-IJ | Phoenix | 4608 3 xT1 |  | NSPE0004764336 IQBJY3QD PHX I20979 loc 07 | 5043233 | P1872052 |  | 3234479 | 1280 | BCBKM2S60001-003 | 13-cpz-aji-0001 13-cpz-aji-0002 13-cpz-aji-0003 extended and tagged the 3 T1 Circuits from the POP in the Basement of 3033 N Central to the 3003 N Central 8th Floor Telco Closet on the Vz Krone Block. | 0CQHKR 0CQHKP 0CQHKQ | 2011-09-27 | 2011-10-20 |  | bpdd | 11/8/2011 moved to 12/2, lcon not aware |  | UnitedHealthGroup- 64676 | 763-694-7370, masroor_khan@uhc.com |  |  | 9/29- ASR sent 10/6- order on-net, pending delivery of 10/10. stepped to field. 10/13- LCON not aware of the floor it needed to teminate on. Per john terminate to 8th. Order supped. 10/26- new site survey schedueld for today 10/27- rescheduled, no tech time. tech will go back out on 10/28. 11/3- circuits installed on 10/28, coudln't test End to end on all 3 T1s. Node work all checked, re-testing ETE today. 11/11- order supped saying lcon is aware and to terminate to main floor. 11/17- escalating for local loop delivery 12/1- Testing circuits from the LD Network, Unable to test to hardloop on circuit 0003, Stepping order Back opdz h2h testing. testing is set for 12/1 12/7- local ETE testing complete. pending testing of LD order. B201112070082 12/14- order closed, still issues with circuit 2, setting up a vendor meet. 12/29- second vendor meet set up for noon central on 12/30
2011-12-02 | SA disco | C1532-02-DJ, | Cedar Rapids | disco |  | NSPE0004961642 OQBJ1PPV | [5 empty] | BCBKN1YY0001-0003 | [5 empty] | bpdd | 2012-01-03 | [5 empty] | circuit disconnected on 1/3
2012-01-04 | Melissa | UCT09-40-CJ | Trumbull | upgrade gold car to 10 mg | [7 empty] | BCBKBRKV0001 | [12 empty] | completed
2011-10-05 | Beth | C1520-05-IJ | Los Angeles, CA | 44736, DS3 with DCAR |  | CDR201110050066 NSPE0004818112 IQBJZWV4 lsa I120830 (closed) | 5065406 | P1878151 |  | 3285793 | 12000 | BCBKNF0X0001 | 3X-OWB-OWB-1551 DS3 #24----2.Where is the DMARC? 4TH MUX ROOM 2 OWB-BX DSX3 2.3.R.7--How was DMARC left? UNLOOPED/NORMAL--Type of terminatio n? DSX3--Circuit labeled at the DMARC? YES---- | 0CQSR5 | 2011-10-31 |  |  | bpdd | 2011-11-30 | 2011-11-17 | UHGECC- 65498 | 763-744-2082, eric_taylor@uhc.com |  |  | 10/7- submitted 10/31- on-net sonet work being done. FOC 10/31 10/27- pending local ete sched for 10/27 11/3- per tech, order needs re-design. 11/8- local loops delivered, testing ticket C201111080079 11/11- Local piece completed, pending testing and order closure] 11/15- "seeing LOF at FUJI48 16.12. 2:4.4.1 (TCOMS Loc1), only able to see loop until RTO TBM-48 SAE DS3 1, troubles hooting other TIDs, checking for alarms & xcons 11/17- order completed and ready for activation. Engineer notified. 1/5- per john will disco and order an oc3
2011-10-26 | Beth | M0352-07-CJ | Metairie , LA | 6144, upgrade existing 2xT1 to 4xT1 |  | NSPE0004871083 IQBJ0BF3 OQBJ0FHL | 5087464 | P1798469 (out) P1881206 (in) |  | 1975920 | 2048 | BCBKNMTP0001-0004 (in) BCBKG05N0001-2 (out) | L2/HCGS/627975//SC DEMARC LOC: 26th fl, COMP RM QMT 4 SLOTS 3 L2/HCGS/627976//SC DEMARC: 26th flr computer rm quadmnt 4 slot 4 rj48c tagged both ids not extended | 0CQXDX; 0CQXDW; 0CQXDZ; 0CQXDV; |  | 2011-11-21 |  | bpdd |  |  | UnitedHealthGroup 64943 | 91 98100 59326, pradeep_yadav@uhc.com | scheduled for 10:30am on 1/13. |  | 11/3- order sent to ops on 10/31, pending help desk ticket Tkt #: S3164958 11/10- pending 11/21 foc 11/30 ready for upgrade. 1/13- hotcut completed.
2011-10-31 | Beth | C1402-02-IJ | customer LOA Denver 1. ACCU-Ring Access Provider: AT&T METRO 2. ACCU-Ring Circuit #: ACEC803231ATI 3. CFA Assignment: • SCID: R4820 • Bandwidth: STS1 • Time Slot: 34W • A Loc: DNVRCOMDH01 (Access Provider) • Z Loc: DNVRCOMDN42 (Customer Location) | PIP DS3 |  | NSPE0004883925 CDR201110310032 IQBJ0M05 |  | P1883468 |  |  | 27000 | BCBKNTDN0001 | 10/CSZZ/011739//TPM Demarc: 6 FLR CUST DATA RM 060601.10 SHELF 5 SLOT 8 DS3 NIU Extended: N Tagged: |  | 2011-11-30 | 2011-12-29 | 2011-12-22 | bpdd | 2012-01-05 | 2012-01-04 | UHG-ECC 65475 | 763-553-4657, nicholas_cooper@uhc.com |  |  | 11/2- CDR approved. 11/10- with prov, pending ASR. C201111100142 11/16- escalating for ASR, there might be IOF issues on our local network 11/30-issue with design that was fixed on 11/30. ASR out and accepted by the LEC. Requesting 12/7 install date 12/7- pending FOC, asked provisioning to call LEC. 12/15- changed slto assign on 12/9, supped asr, pending response. btdd C201112190129 12/22-- LEC delivered. DLR delivered. Mux scheduled for 12/29. 1/4- order ready for activation, engineer informed. activated on 1/13
2011-12-22 | Beth | AZ005-05-CJ | Pheonix, AZ | Upgrade to 9216, 6xT1 |  | NSPE0005014549 IQBJ2CFJ OQBJ2FS8 | 5192580 | P1896048 (in) |  | 3234478 | 2752 | BCBKM2TL0001-003 (out) BCBKPMLB0001-0006 (in) | 14/HCGS/432455 /MS DEMARC LOC: 1st flr telco room/shlf 4 slt 5-28 DEMARC LOC Continued: Extended Wire (Yes or No): no 14/HCGS/432456 /MS DEMARC LOC: 1st flr telco room/shlf 4 slt 6-28 DEMARC LOC Continued: Extended Wire (Yes or No): no 14/HCGS/432457 /MS DEMARC LOC: 1st flr telco room/shlf 4 slt 7-28 DEMARC LOC Continued: |  |  |  | 2012-01-10 | bpdd |  |  | UnitedHealthGroup-64648 | 763-694-7370, masroor_khan@uhc.com |  |  | 12/29 order in OE. 1/5- ASR sent pending FOC 1/12- ready for hotcut Engineer informed. Completed with Masroor on 1/17
2011-12-23 | Core | DE003-03-IJ | Newark, DE | install 1 POTS line |  | NSPE0005015421 | [6 empty] | Order Number: n0cq54941 Date Due: 01-10-12 Billing Telephone Number: 302 738-5436 941 Circuit ID or Telephone Number: 302 738-5436 | [11 empty] | completed ZEIGLER, APRIL M.800 700-8297 EXT 3153,TOM TOMEI 302 420-5833 JOHN SERGOT 763 744-1582 TG TRM DMRC RN LNE INSTL JCK,OPB JOHN SERGOT 763 744-1582,WFA COMPLETION,VER XX DT GOOD TAG AND LOCATED ST 20
2011-08-10 | Beth | ON517-05-CJ | Burlington, Ontario | Change - Upgrade port to 3xT1 and Gold CAR |  | Globalink 1034105, circuit 6306337 port s/o 4889321 bearer s/o 4889322 & 4889324 disco s/o is 4959877 OQBJ10TP | 4996415 |  |  |  | 2752 | W0Y34798 | 05DHAT246916BLCA |  |  | 2011-09-14 |  | bpdd | 2011-11-10 |  | UnitedHealthGroup- 65130 | 763/694-7409, terry_bjorke@uhc.com |  |  | order now is with provisioning 9/1-0 order is being worked with provisioning 9/8- escalated with provisioning 9/14 due date from BC 9/22- ready for upgrade, engineer notified 11/2- per Terry AT&T circuit came in and this upgrade might be cancelled? 11/17- supp to cancel upgrade submitted. 11/28- pending confirmation from beth that order was supped to cancel. 12/5- A new TIN has been created and submitted to the OS as of 12/2/11. The TIN Number is UNITEDHEALTH GROUP - TIN 5145601/. disco s/o is 4959877 ( W0Y65616 ). I have cancelled both port s/o 4889321; bearer s/o 4889322. 12/7- disconnect bearer in ISD queue. 12/14- followed up with provisioning on bearer cancel. 12/21- provisioning is working cancel on the beaer 12/29- disco reqeuest for bearer sent to BC 1/5- bearer is discoed, upgrade cancelled.
2011-11-30 | SA disco | NV064-01-Dj | Pahrump NV |  |  | NSPE0004954585 OQBJ1GYT |  | P1830571 |  |  |  | BCBKKCPX0001-008 | [5 empty] | bpdd | [6 empty] | disco completed on 1/16- will credit back to 12/30
2011-12-02 | Beth | UIR01-07-DJ | Letterkenny IR | disco |  | NSPE0004961661 s/o 4963147 | 5146796 |  |  |  |  | w0s28730 | [5 empty] | bpdd |  | 2012-01-18 |  |  |  |  | 12/7- beth created tin. 12/15- tev sent to matthew, pending confirmation to proceed. 12/22- asr sent requesting disco on 1/30 12/29- still pending TEV from LCON. 1/5- request sent to enet and software cross connects deleted. 1/12- local loop set to disco on 2/4 1/18- disco completed
2011-12-09 | Beth | UTN13-08-CJ | Kingsport, TN | 9216, Add 2 T1s to existing 4xT1 upgrade CAR to 4608 |  | IQBJ1ZMY OQBJ12LK | 5156180 | P1893082 (in) P1831935 (out) |  | 1568154 | 4608 | BCBKKGY90001-0004 (out) BCBKPFXJ0001-0006( in) | 50.HCGS.785972.. DEMARC LOC: 1ST FLOOR TELCO ROOM, SLOT 1 OF 4, PRIMARY GAS PROTECTION ONLY, RJ48 C,TAGGED BOTH CKT IDS, as requested Extended Wire (Yes or No):No UIMN 50.HCGS.767973..UIMN DEMARC LOC: 1ST FLOOR TELCO ROOM, SLOT 2 OF 4, PRIMARY GAS PROTECTION ONLY, RJ48 C,TAGGED BOTH CKT IDS, placed where requested Extended Wire (Yes or No):No |  |  | 2011-01-09 |  | bpdd |  |  | UnitedHealthGroup- 64921 | 763/694-7370, masroor_khan@uhc.com | scheduled on 1/20 at noon central |  | pending tin sumission by om/os, beth 12/22- order is with provisioninng. 12/29- FOC for 1/9 1/5- circuits delivered and order is ready for encapsulation change. 1/20- change sched for 1/20 at noon central completed with Masroor on 1/23
2011-12-13 | SA disco | UAZ44-08-DJ | Phoenix | disco |  | NSPE0004986520 OQBJ1XZ2 | [5 empty] | BCBH1K280001 | [5 empty] | bpdd | 2011-01-11 | [5 empty] | disco completed on 1/11
2011-12-13 | SA disco | UTN0705-DJ | BRENTWOOD, TN | disco |  | NSPE0004986660 OQBJ1XZ8 | [5 empty] | BCBJ6T6B0001-4 | [5 empty] | bpdd | 2011-01-11 | [5 empty] | disco completed on 1/11
2011-08-22 | Beth | UTN07-08-IJ | Brentwood, TN | PIP DS3 with Dport and Dcar |  | CDR201108240031 IQBJX96K s/o 4889396 | 4999199 | P1865718 |  | 2855166 | 2048 | BCBKMM9S0001 | T4/HFGS/821128//SC | 0CP7D4 | 2011-11-04 |  |  | bpdd | 2011-11-17 | 2012-12-06 | UnitedHealthGroup-64523 | 715-841-7731, sonja_d_mroczynski@uhc.com | activatied 12/6 with Sonja. Need to downgrade to 10 mg. |  | ops approved on 9/1 9/8- pending ASR. Opened ticket C201109080122 for ASR 9/15- escalating with LEC for FOC 9/22- pending DLR from level 3 in order to send out out ASR to AT&T. L3 due 10/7 , we should get DLR on 10/4 10/6- aSR sent to AT&T, requesting 10/10, pending response 10/13- According to ATT that there's a pending job on the mux. They stated that the ECD (Estimated Calculated DATE) is 10/27/2011. 10/20- pending LEC delivery of 11/17 11/16- Local loop delivered, attempting to get dmarc info. Issue with network wiring that is being addressed. 12/1- all testing complete. Pending AT&T to remove soft loop at customer premise 12/6- activated with Sonja, need to throttle port down to 10mg | x
2011-12-22 | Beth | SC012-03-IJ | Columbia/SC | 1536, T1 |  | NSPE0005014492 IQBJ2CD6 | 5193270 | P1896044 |  |  |  | BCBKPMK60001 | 34/HCGS/430939//SB DEMARC LOC: MM2 SLOT 1 1ST FLR MAIN TELCO RM DEMARC LOC Continued: Extended Wire (Yes or No): No | 0CRKPL |  |  |  | bpdd | 2012-01-24 | 2012-01-10 | UnitedHealthGroup-65229 | 715-891-8592, sonja_d_mroczynski@uhc.com | completed on 1/31 with Sonja |  | 12/29 order in OE. 1/5- LEC FOC 1/17 1/20- ready for activation, engineer informed. 1/31- completed with Sonja
2011-04-15 | Katrina | UNY13-05-CJ | Albany, NY | 7680, Upgrade from 3xT1 to 5xT1 |  | NSPE0004346999 IQBJS7RF OQBJS7RD | 4829928 | P1835314 (in) P1432493 (out) |  | 1590983 |  | BCBJF9YT0001-3 | 34.HCGS.684672..NY DEMARC LOC: GND,RM 1,TEL-CLOSET,SHLF 1,POS 1 DEMARC LOC Continued: Extended Wire (Yes or No): Yes 34.HCGS.684674..NY DEMARC LOC: GND,RM 1,TEL-CLOSET,SHLF 1,POS 3 DEMARC LOC Continued: Extended Wire (Yes or No): Yes |  | 2011-05-05 | 2011-06-13 | 2011-06-15 |  | 2011-06-24 |  |  | 91 9873139388, anupam_datt@uhc.com | completed 1/30 with Anupam |  | 6/11- pending LEC delivery of 6/13 6/16- LEC delivered we are testing. NDMT B201106170015 6/20- order now ready to schdule informed Anupam 6/30- order is scheduled for 7/8 7/13- New ckts. 0004 - 0005 did not come up. DTAC was not able to loop up the CSU or S/J on both ckts. Opened tkts. 2011070902463 = 004, AND 2011070902536 = 0005. Had to roll back. This will need to be re-scheduled. 7/20- ready for re-schedule. Informed Anupam 8/16- cut did not go, no valid change control by UHG. 9/8- cut did not go, new T1s didn't come up. seeing AIS from customer. Need to re-schedule with someone on site. 9/29- sched for 9/30 10/6- sched for 10/13 at 5pm 10/10- didn't have support for 10/13, asked Anupam for another date. 10-20- rescheduled again for 10/28 10/28- Anupam couldn't get on-site person for this date, need to re-sched. 11/10- issue with on-site wiring, need to re-schedule. Per cable vendor they need another 200 ft pulled, John is checking into it. 12/29- Anupam asked to re-schedule Albany 1/25- rescheduled for 1/30
2012-01-11 | core | PA001-02-IJ | ,Philadelphia,PA | 1 POTS line |  | NSPE0005053874 | [6 empty] | Order Number: N0CQ55521 Date Due: 2012-01-27 Billing Telephone Number: 2152716190 Circuit ID or Telephone Number: 215 271-6190 |  |  |  |  | bpdd | 2012-01-27 | 2012-01-27 |  |  |  |  | completed ZEIGLER, APRIL M.800 700-8297 EXT 3153,SHAUN LEONARD 215 983-1197 JOHN SERGOT 763 744-1582 TAG IN BLDG DMRC,WFA COMPLETION,VER XX DT GD TO DEMARC-PER SHANE,WTG ON ENG TO PROVIDE TO EXTEND ST 20
2011-10-19 | Beth | TN027-04-IJ | 1206 Pointe Centre Drive Suite 230 Chattanooga, TN | 3072 2xT1 |  | NSPE0004852213 IQBJZ5N0 | 5081009 | P1880289 |  | 3312527 | 2752 | BCBKNKWM0001-0002 | T1/HCGS/827771//SC DEMARC LOC: T1/HCGS/827772//SC demarc for both ckts 2nd flr telco rm/mm 1 slot 1 & 2/48x/tagged/not ext | 0CQV8J; 0CQV8H; | 2011-10-26 | 2011-11-08 | 2011-11-09 | bpdd | 2011-11-17 |  | UnitedHealthGroup- 65237 | 763-694-7409, terry_bjorke@uhc.com | Per John complered on 2/10 |  | sent to beth on 10/19 10/27- FOC due on 11/8 11/10- order completed 11/9, engineer informed.
2011-11-22 | Beth | C1093-07-IJ | Wipro Secaucus, NJ | 44736, DS3 |  | CDR201111220011 IQBJ06GG NSPE0004939834 NJY I0133431 (closed) | 5129613 |  |  |  | 128 | BCBKN27W0001 | : /HFGS/067415//NJ DEMARC LOC: BLDG MAIN;FLR 1;RM 7972 GROUND FLR CAGE 13 RR NO 9 DSX NO DEMARC LOC Continued: 1 POS B1-7 |  |  | 2011-12-27 |  | bpdd | 2011-01-20 | 2012-01-06 | UHG-ECC 65440 | scott_moyer@uhc.com; 763-744-2154 | completed with Scott on Friday 8/10 |  | telco FOC is 12/27 12/29- LEC delivered, testing. Opened better commit date of C201112290038
2012-01-10 | Beth | IL016-04-CJ | Aurora, IL | Add 1 T1 to existing bundle, 6144 |  | NSPE0005049648 IQBJ2ZQK OQBJ22Z1 | 5213406 | P1901061 (in) P1774603 (out) |  | 1945139 | 2048 | BCBKD5T80001-0003 (out) BCBKPYL40001-0004 | / /HCGS/632626//LB DEMARC LOC: FLR 1 IT CAB 2 SLOT 6 OF 8 |  |  | 2012-02-08 |  | bpdd |  |  | UnitedHealthGroup- 65253 | sonja_d_mroczynski@uhc.com, 715/841-7731 | completed with Sonja on 2/15 |  | 1/20 OE Is working order. 1/26- FOC for 2/8 2/10- order ready for upgrade, engineer informed. 2/15- completed with Sonja
2012-01-10 | Beth | OH085-03-IJ | Canfield, OH | PIP T1 1536 |  | NSPE0005050321 IQBJ2WNC | 5213276 |  |  | 3975100 | 512 | BCBKPW7K0001 | 92/HCGS/210081//OB DEMARC LOC: WALL PANEL 1 JACK 2 DEMARC LOC Continued: Extended Wire (Yes or No): YES EW Reason/Location:WALL PANEL 1 JACK 2 Jack Type: RJ48C DMARC Labeled IXC (Yes or No): No DMARC Labeled LEC (Yes or No): Yes | 0CRQ19 | 2012-01-16 | 2012-01-26 |  | bpdd | 2012-02-02 | 2012-01-26 | UnitedHealthGroup- 65136 | (763) 744-2077, robert_a_benson@uhc.com | completed with Robert on 2/10 |  | FOC date is 1/26 1/26-lec delivered and pending order testing closure 2/2- order ready for activation, engineer informed. 2/8- scheduled for 2/10
2012-01-24 | SA disco | KS001-02-DJ | WICHITA | disco |  | NSPE0005090505 OQBJ27QJ | [5 empty] | BCBJS00B0001-0003 | [5 empty] | bpdd | 2012-02-23 | [5 empty] | disco complete
2012-01-24 | SA disco | OH009-05-DJ | WESTERVILLE | disco |  | OQBJ3CBD |  | P1543498 |  |  |  | BCBJRRKV0001-6 | [5 empty] | bpdd | 2012-02-23 | [5 empty] | disco complete
2012-01-25 | SA disco | UAZ57-05-DJ | PHOENIX AZ | disco |  | NSPE0005094001 OQBJ3DW3 | [5 empty] | BCBJ19BM0001-0004 | [5 empty] | bpdd | 2/.22 | [5 empty] | disco complete
2012-01-30 | SA disco | UAZ02-06-DJ | PHOENIX AZ | disco |  | NSPE0005105411 OQBJ3GZW | [5 empty] | BCBH3JFG0001 | [5 empty] | bpdd | 2012-02-29 | [5 empty] | disco complete
2012-02-15 | B end | IR503-02-IJ | Dublin, Ireland | E1 2024 MD5 encryption UHGVERbgpbqZyofa | [6 empty] | 1024 | [6 empty] | bpdd |  |  | UnitedHealthGrop-65086 | 763-744-1556, john_l_rothstein@uhc.com |  |  | 2/16- pending SOF 3/5- Cancel per John.
2011-03-23 | Melissa | n/a | ROADM and subtended Sonet |  |  | S/O 1: 4816363 (DMS Wave) MIN-I31661 pending ER 2147565054 ROADM Facility prep so 2: 4790209 (hub) pending local order MIN-I31560 FOTS ER for new subtended OC48.j2 2147565055 | 4476349 |  |  |  |  | W0Y28557 (radm) | r4-llm8-jcfg-0002 roadm | [11 empty] | pending migration orders, see migration tab
2012-02-15 | Core | MD002-04-IJ | Columbia, MD | pots |  | NSPE0005155699 | [18 empty] | Order Number: N3BH98466 Date Due: 2012-02-29 Billing Telephone Number: 4103120429 508 Circuit ID or Telephone Number: 410 312-0429 completed
2010-12-15 | NA | AU516-01-IJ | Adelaide Australia | new E1 |  | 4729193 port 4731367 carrier | 4657487 | 4731367 | E1 |  | 512K | W0X83262 port W0X84794 carrier | 55DY O5PS NP001 |  |  |  |  | bpdd | 2011-02-14 |  | 65171 | Steve Betsinger (763) 744-1886, steve_betsinger@uhc.com |  |  | 2/22- order enabled and ready for Plug and play.
2011-06-29 | in country B end | AU501-01-IJ | Sydney, Australia | 2048 E1 |  | s/o 4865474 |  |  |  |  | 512 | W0Y52068 |  |  | 2011-07-26 | 2011-08-31 |  | bpdd |  |  | UnitedHealthGroup 65193 | (763) 744-1886, steve_betsinger@uhc.com |  |  | 6/29- Siva sent to B end rep for processing 7/13- pending Globalink. 7/26- Request sent to Telstra, requesing 9/7, pending response 8/11- testra delivery date is 8/31 9/1- circuit is ready fro activation
2012-01-04 | Beth | UIX51-01-DJ | Garguon | disco |  | 4991432 | 5203225 |  |  |  |  | w0x83342 | [12 empty] | needs to go through b end 1/26- order processed on the B end and sent to process. 2/2- pending TECV 2/10- PTT WILL DISCONNET THE CKT W.E.F. 4TH MARCH 2012 3/15- Melissa is verifying the circuit is disconnected and billing has ceased.
2012-02-02 | SA disco | disco old DWDM | Plymouth | disco |  | NSPE0005120359 OQBJ3NXV MIN C0027691 | [5 empty] | bcbj50sn0001 | [5 empty] | bpdd | 2012-02-29 | [5 empty] | 3/8 disconnected
2012-02-07 | SA disco | FL001-02-DJ, | Melbourne, FL | disco |  | NSPE0005132248 OQBJ3T57 | [5 empty] | BCBKM7HS0001 | [5 empty] | bpdd | 2012-03-08 | [5 empty] | disco completed on 3/8
2012-02-07 | SA disco | C1520-02-DJ, | Los Angeles CA | disco |  | OQBJ3W3G | [5 empty] | BCBKNF0X0001 | [5 empty] | bpdd | 2012-03-07 | [5 empty] | disco completed on 3/7
2012-02-07 | SA disco | C1411-01-DJ | Cedar Knolls NJ | disco |  | NSPE0005132284 OQBJ34HC | [5 empty] | BCBJH9JM0001 | [5 empty] | bpdd | 2012-03-12 | [5 empty] | disco completed on 3/12
2012-02-29 | Core | MD029-02-IJ | Salisbury,MD | 1 POTS line |  | NSPE0005199126 | [11 empty] | bpdd | [6 empty] | Order Number: N2DP19424 Date Due: 03/12/12 Billing Telephone Number: 410.677.3161 completed
2011-10-27 | SA disco | M0352-02-DJ | METAIRIE LA | disconnect |  | NSPE0005132251 OQBJ3XV6 | n/a | P1798830 |  |  |  | BCBKG1R20001 BCBKG1R20002 | [5 empty] | bpdd | 2011-11-23 | 2012-03-08 |  |  |  |  | disco completed on 3/8
2011-12-23 | Beth | DE003-02-IJ | Newark, DE | 3072, 2xT1 |  | NSPE0005015396 IQBJ2ZKM | 5192682 | P1900991 |  | 4085154 | 1280 | BCBKPYJH0001-0002 | 11/HCGS/486220//DS DEMARC LOC: GND,RM na,TEL RM ,RJ48C,LP Y,CAB N,MNTG 1,SLOT 7,na 11/HCGS/486222//DS DEMARC LOC: GND,RM na,TEL RM ,RJ48C,LP Y,CAB N,MNTG 1,SLOT 6,na | 0CRRX9 0CRRZB |  | 2012-02-06 | 2012-02-01 | bpdd | 2012-02-10 | 2012-02-02 | UnitedHealthGroup-65094 | 715-891-8592, sonja_d_mroczynski@uhc.com | completed with Sonja on 3/19 |  | 1/5- pending order submission by beth. 1/6- ticket needed to add S3695881 1/17- tin submittd 1/20- order with provisioning, working on getting optimal path FOC is 2/2 2/2- order ready for activation, engineer informed. 3/19- activation completed with Sonja.
2012-02-28 | Core | NY051-03-IJ | Albany, NY | 1 POTS line |  | NSPE0005194997 | [11 empty] | bpdd | 2012-03-15 | [5 empty] | Order Number: N2FB5077 Date Due: 2012-03-15 Billing Telephone Number: 5184625086 Circuit ID or Telephone Number: 518 462-5086 completed
2011-06-24 | Katrina new order B end. | UK534-03-IJ | OXFORD, UK | 4Mbps Ethernet internet |  | s/o : 4947011 | [5 empty] | W0Y93401 | Open reach ONEA807755. YDEMARC IS GROUND FLOOR COMMS ROOM FIRST CAB ON LEFT HANDSIDE OF COMMS ROOM ADVA BOX HALF WAY DOWN RJ45 LOOPBACK LEFT ON |  |  | 2011-01-23 |  | bpdd | 2011-02-16 | 2012-01-18 |  | jimmie_l_skaggs@uhc.com | activated with Jim on 3/14 |  | 8/17- new tin issued, pending order...keeping pip open in case UHG needs it. 8/25- internet needs to be processed via B end. 9/1- SOF sent to john sergot 11/16- -new order progressing and is expedited. 12/1- CUTOMER SIDE:158.43.24.162/30 GATEWAY:158.43.24.161. AW FOC DATE TO BE SET, local loop install requested for 1/10. 12/7- PTT planning phase/site survey complete. No exess construction. Pending FOC, which we should have in 7 days. 12/14- still pending FOC. We should have something 12/16 12/21- PTT FOC is 1/23 1/12- BT tail is delivered, LCON has equipment plugged in and local ETE test is set for 1/13 1/17- order ready for activation, trying to get activation nfo so I can send to Jimmie. activated with Jim on 3/14
2011-09-07 | Beth | PH501-01-DJ | Phillippines 5x E1 disco | disco |  | NSPE0004740339 S/O 4950309 / 4951184 | 5025897 |  |  |  |  | W0Y41014 W0Y41008 | [12 empty] | 10/20 disconnect order progressed 11/2- pending ETF charges approval 12/7- pending TEV validation with LCON 12/21- e-mail has been sent to Jason, no response. Need to validate before disco can move forward. 1/20- tecv complete 2.2- sent to PTT to proceed 2/10- circuit is disconnected, pending order closure 3/13- escalating for order closure 3/20- escalating further for order closur 3/22 - disco complete
2011-09-28 | B end | PP502-02-IJ | Phillippines Bill will go to the US. Bill in US Dollar. | Ethernet 100 Mbps |  | s/o 4937407 (port), 4937415 | new tin 5087299 |  |  |  | 33792 | W0Y89090 (port) W0Y89088 (access) |  |  | 2011-12-15 |  |  | bpdd |  |  | UnitedHealthGroup-65111 | 919873139388 , anupam_datt@uhc.com | completed with Anupam on 3/23 |  | 12/27- no new news from PTT, on leave and freeze. 1/12- RTA ALREADY APPROVED BY MERALCO. KICK-OFF MEETING/JOINT STAKING/WORK PERMIT ACQUISITION - JAN 16-17 PROJECT IMPLEMENTATION - TO COMMENCE JAN 18. TARGET COMPLETION WI THIN 5 DAYS (BEST SCENARIO). TAKE NOTE THAT THIS IS ALSO DEPENDENT ON THE AP PROVAL OF THE BA. TESTING COMMISSIONING - JAN 25 ( 1 DAY) >>>> AS OF YESTERDAY, DATA CENTER IS NOT YET READY. PER JONG CHICO (CONTACT), THIS WILL BE READY BY END OF FEBRUARY OR A LITTLE BIT EARLIER. NOTE THAT BAYAN'S FOC (FIBER OPTIC CABLE) CAN ONLY BE INSTALLED UP TO THE BUILDING'S MDF OR FLOOR TTC WHERE UHG IS LEASING UNTIL DATA CENTER IS READY. 1/26- AS PER ISD, PTT CAN COMPLETE THEIR PART WITHIN 3-5 DAYS ONCE THE SERVER ROOM IS READY. THEY ARE ACTUALLY DOING THEIR WORK OUTSIDE OF THE BUILDING. HENCE, HE IS ASKING LPM IF THE END OF FEB IS THE EARLIEST TENTATIVE DATE. WAITING FOR RESPONSE FROM LPM 2/2- UPDATES BASED ON THE JOINT STAKING BETWEEN BAYAN AND UHG. UHG WANTS TO START THE PERMIT PROCESSING ON JAN. 30,2012 JAN. 30 - PERMIT ACQUISITION (3 TO 5 DAYS APPROVAL) JAN. 31 TO FEB 4 - MOBILIZATION/PULL OUT OF LOGISTICS @ WAREHOUSE, PREPARATI ON OF OTHER LOGISTICS FEB. 9-13 - CLIENT PREFERRED SCHEDULE "FOC INSTALLATION" DATA CENTER IS NOT YET READY (STILL ON-GOING RENOVATION). UHG EQUIPMENT IS NOT YET INSTALLED. EQUIPMENT RACK INSTALLATION IS EXPECTED AFTER FEB. 15 FOC WILL BE INSTALLED UP TO THE CEILING OF THE DATA CENTER ONLY AND TO BE CONTINUED UPON/SPLICED WHEN THE EQUIPMENT RACK IS FIXED . Per John MDF is ready 2/.21, circuits can terminate prior to that. 3/1- JUST TO UPDATE YOU ON THE STATUS. OUR CONTRACTOR CAN'T PROCEED W/ THE TERMINATION OF FOC @ UHG DATA CENTER THIS WEEK BECAUSE THE INSTALLATION OF EQUIPMENT RACK FOR BAYAN & OTHER TELCO IS NOT YET COMPLETED. WE WILL JUST WAIT FOR THEIR ADVISE 3/12- UPDATE FROM THE PTT: ER WAS INSTALLED LAST FRIDAY (CONFIRMED BY XIN NETWORKS). OUR CONTRACTOR WOR K PERMIT APPROVED STARTING TODAY. TODAY'S ACTIVITIES: 1. PULLING OF FOC TO THE DESIGNATED LOCATION/EQUIPMENT RACK 2. ODF INSTALLATION 3. FOC TERMINATION 4. FOC COMMISSIONING AND TESTING 5. QA PRELIMINARY TESTING MARCH 13 ONWARDS 1. INSTALLATION OF POWER SUPPLY & MUX 2. INITIAL COMMISSIONING____ 5. LINK INITIAL TESTING 3. MUX LINK UP___________________6. LINK E2E TESTING 4. LINK PROVISIONING_____________7. LINK ENDORSEMENT 03/12/2012 04:44:10 TORNO, TEDDY JASON G. (1) UPDATE FROM THE PTT: EQUIPMENTS WERE INSTALLED. YOUR CUSTOMER HAS ANOTHER ISSUE, THERE'S NO AC OU TLET IN THE NEWLY INSTALLED EQUIPMENT RACK. PLEASE ADDRESS THIS CONCERN TO U HG. TO HELP YOU ON THIS, I AM COORDINATING THIS CONCERN TO ROBAL SEPULCHRE/U HG PM. I ALSO SPOKE WITH XIN NETWORKS/ALEX SANTOS. HE CONFIRMED THAT POWER STRIP WI LL BE READY TODAY. OUR FOC CONTRACTOR IS ON SITE AND THEY WILL CONFIRM THE A C SUPPLY AVAILABILITY. KEEP YOU POSTED. 3/15- PTT is working on fiber cable. Hoping to have ready for activation by 3/20 3/21- PTT is hoping to get equipment active tonight, then can proceed with testing.
2012-02-02 | SA disco | disco old DWDM | Plymouth | disco |  | NSPE0005120359 OQBJ3NXW | [5 empty] | bcbj7h2l0001 | [5 empty] | bpdd | 2012-02-29 | 2012-03-23 |  |  |  |  | completed 3/23
2012-02-15 | SA disco |  | Internet disco |  |  | NSPE0005221405 Request 19342820 | [5 empty] | - U306891 | [12 empty] | disconnect cancelled.
2012-02-15 | SA disco |  | Internet disco |  |  | NSPE0005221405 Request 19342820 | [5 empty] | K0520561 - U309373 | [12 empty] | The bill cease date is 03/16/2012. The physical disconnection is in progress. The site has been admined down as of 3/26/2012.
2011-10-27 | Beth | C1475-09-IJ | Wipro, Atlanta | 44736, DS3 |  | nspe0004875232 CDR201110270040 (CDR approved) IQBJ0JW2 atl I74530 | 5090769 | P1882712 |  |  | 9000 | BCBKNRM50001 | 3x-cpz-35p-0006 Demarc is 14th floor Wipro data room network RR rack. Hard left on ckt loc2 for testing. LCON is Carlo. | 0CQ0J1 |  | 2011-11-23 |  | bpdd | 2011-02-20 |  | UHC-ECC 65505 | 763-553-1783 matt_f_seymour@uhc.com |  |  | 11/3- sent to prov on 11/2 11/10- on-net being designed, pending capacity Capacity between 6cn to cpz 11/16- capacity found and local order being designed. 12/1- issue with local ring. Order went back to engineering to find capacity 12/15- capacity found, sent for ETE test on the lcoal portion on 12/16. 12/22- issue with Add-drops are not correct @ 55P STS1:9 is droping to 5:3. All STS1^s are one for one @ 55P. Please verify that CLR is correct andif-is correct add-drop, back to provisioning 12/29- local ETE test scheduled for today 1/5- issue with testing. 1/12- ETE testing rescheduled for today 1/20- it appears there are still issues with LOS...checking 1/24- ready for activation, engineer informed.
2012-02-08 | Beth | UNJ20-05-IJ | East Windsor, NJ | 4608, 3 x T1 |  | IQBJ3Z4F | 5246501 | P1907244 |  | 5009076 | 640 | BCBKRFGJ0001-003 | /HCGS/467594//NJ DEMARC LOC: BSMT 1,RM 1,TEL RM ,RJ48C,LP N,CAB N,RCK 1,POS 11,rj48c pos DEMARC LOC Continued: 11 /HCGS/467595//NJ DEMARC LOC: BSMT 1,RM 1,TEL RM ,RJ48C,LP N,CAB N,RCK 1,POS 10,rj48c pos DEMARC LOC Continued: 10 /HCGS/467596//NJ DEMARC LOC: BSMT 1,RM 1,TEL RM ,RJ48C,LP N,CAB N,RCK 1,POS 12,rj48c pos DEMARC LOC Continued: 12 |  |  | 2012-03-13 |  | bpdd | 2012-03-05 | 2012-03-15 | UnitedHealthGroup- 64927 | 91 91600 84400, harish_kandpal@uhc.com | scheduled- 04/04/2012 12:00 PM Central Time / GMT 17:00 Techs: Daniel Lewis and Matt Lawrence Sarte. Bridge 866-819-9840 and 3365052 |  | 2/16- ordr with provisioning. In design 2/23- per john S= Just found out the suite and building are incorrect on this order. Please have this changed to 50 Millstone Road, Building 100, suite 100, East Windsor, NJ 08520 3/8- FOC date for 3/13 3/15- order is ready for activation 3/29- scheduled for 4/4
2011-12-15 | B end | SP504-02-IJ | Barcelona, Spain bill in country | E1 2048 |  | 4995920 |  |  |  |  | 1280 | W0Z14768 | 08100002247275- The circuit is delivered in customer room.(CPD customer). Alcatel equipment 1540 Litespan.HW-loop in 120 Ohmios.(RJ45). |  |  | 2012-03-29 |  | bpdd | 2012-04-02 | 2012-03-05 | UnitedHealthGroup-65095 | 91 9810059326 pradeep_yadav@uhc.com | completed by pradeep on 4/13 |  | 2/2- SOF returned from UHG, with UK to process order 2/.10- ASR sent to PTT, pending response 2/16- PTT tail is due 3/29 3/5- order ready for activation- engineer informed.
2012-02-27 | SA disco | na | 10 gig disco Eagan and Elk River | 10 gig disco |  | NSPE0005211906 5018115 | [5 empty] | W0V77422 | [5 empty] | bpdd | 2012-03-27 | 2012-03-27 |  |  |  |  | discoed on 3/27
2012-02-27 | SA disco | na | 10 gig disco Eagan and Elk River | 10 gig disco |  | NSPE0005211906 5018114 | [5 empty] | W0V77421 | [5 empty] | bpdd | 2012-03-27 | 2012-03-27 |  |  |  |  | discoed on 3/27
2012-02-27 | SA disco | na | 10 gig disco Eagan and Elk River | 10 gig disco |  | NSPE0005211906 5018116 | [5 empty] | W0V77423 | [5 empty] | bpdd | 2012-03-27 | 2012-03-27 |  |  |  |  | discoed on 3/27
2012-02-27 | SA disco | na | 10 gig disco Eagan and Elk River | 10 gig disco |  | NSPE0005211906 5018117 | [5 empty] | W0V77424 | [5 empty] | bpdd | 2012-03-27 | 2012-03-27 |  |  |  |  | discoed on 3/27
2012-02-27 | SA disco | na | 10 gig disco Eagan and Elk River | 10 gig disco |  | NSPE0005211906 5018118 | [5 empty] | W0V77425 | [5 empty] | bpdd | 2012-03-27 | 2012-03-27 |  |  |  |  | discoed on 3/27
2012-02-27 | SA disco | na | 10 gig disco Eagan and Elk River | 10 gig disco |  | NSPE0005211906 5018119 | [5 empty] | W0V77426 | [5 empty] | bpdd | 2012-03-27 | 2012-03-27 |  |  |  |  | discoed on 3/27
2012-03-01 | SA disco | TN011-03-DJ | NASHVILLE TN | disco |  | NSPE0005213248 OQBJ4VB4 | [5 empty] | BCBJFYNY0001 | [5 empty] | bpdd | 2012-04-02 | 2012-04-07 |  |  |  |  | disconnect completed as 4/7
2012-03-06 | Beth | C1541-01-IJ changed to C1215-01-IJ. | Customer Elation Bloomington, MN | 9216, 6xT1 |  | IQBJ4WLG | 5275813 | P1912797 |  |  | 4000 | BCBKRYD80001-0006 | 15/HCGS/227521 /NW main level back of wharehouse cab 5 slot 3/4 15/HCGS/227522 /NW main level back of wharehouse cab 5 slot 4/4 15/HCGS/227523 / NW main level back of wharehouse cab 6 slot 1/4 15/HCGS/227524 /NW main level back of wharehouse cab 6 slot 2/4 15/HCGS/227525 /NW main level back of whare house cab 6 slot 3/4 15/HCGS/227526 /NW main level back of wharehouse cab 6 slot 4/4 |  |  | 2012-03-14 |  | bpdd | 2012-03-30 | 2012-03-23 | UHGECC- 65525 | matt_f_seymour@uhc.com 763-744-0840 | activated on 3/30 |  | 3/21- local loops delivered, escalated for loop testing and closure B201203210059
2011-09-22 | Beth | UNY24-05-IJ | New York, NY | Dport DS3 (15 mg) |  | NSPE0004780137 CDR201109230018 IQBJZC82 nyc I309880 (closed) | 5043859 | P1874147 |  | 3242998 | 4096 | BCBKM68P0001 | 32.HFGS.653709..NY Demarc: 8th flr mdf room next to mux nl7737 slot 1 of 3 tagged not extended. | 0CQLN4 |  |  |  | bpdd | 2012-03-13 | 2012-03-22 | UnitedHealthGroup-64782 | (860) 702-6323, dave_marquis@uhc.com | completed with Dave marquis on 4/10 |  | in local design, pending capacity on local network, pending ASR to LEC, Associated ER 2147578067 for capacity between 56w & por (RFT 11/07) 10-13- core indicated customer telco room isn't ready. Asked John about it. 10/19- order supped to the LEC 10-27- another supp required. dmarc is on 8th floor and this was asked to terminate to first floor 11/2- Customer requirements needed. Power. Sent information to john. VZB-Core portion pending IOF ER ER2147578775 RFT 1/24. ER is currently in Equip Shipped queue. Equip is in backorder and ETA is 11/8 11/11- still pending power from UHG, IOF build is in process. equipment shipped 11/17- no change in status on power, equipment is pending install for IOF. 12/1- PNDING er ER2147578775 AND POWER, ops has equipment, ER is being pushed. pending ops install. 12/7- pending SFP modules Request sent for VP Approval for PO.. These parts have a 12-14 week lead time 12/.15- got temp sfps Self test of the FW4100 ES had been completed for both sites.Awaiting the revision laser cards to complete the system turn up test. 12/21- FUJI VENDOR SHIPMENT FOR REV 1.1 IS NOT SCHEDULED UNTIL MARCH. Procurement has been working with the vendor to try to improve this date, but it’s a matter of raw material availability. At this point, since no improvement is being seen in their shipments Testing has been completed using temporary cards, once the correct lasers are received, it shouldn’t take too long to complete final testing and close the ER. 12/29- still pending cards... 1/12- CURRENT SHIP DATE 3/23/12 FOR FUJITSU VENDOR PO #8500160968 for SFP modules and cards. 3/8- Equipment for ring installed. Alarming done, pending further testing and ER closure, then order can go to provisioning. 3/15- ER complete, CLR updated, Sonet and node work being done. 3/21- node work complete, local ETE testing complete from 2 nodes. 3/29- order closed/engineer informed. 4/11- order activated with Dave Marquis on 4/10
2011-11-15 | Beth | UMN99-41-CJ | PLYMOUTH MN | Please change the encapsulation to Frame Relay and add a new PVC (Gold CAR = 1004) to VPN UHG-MA for the below circuit. |  | NSPE0004923059 IQBJ1MM4 OQBJ1QMZ | 5138636 | new P1890250 |  | new MA pvc 3520288 |  | BCBH7R4R0001 BCBKN8P00001-0005 (new) | [9 empty] | tim gundersen | rescheduled for 04/04/2012 6:00 PM Central Time / GMT 23:00 866-819-9840 pcode 33650 Christian Marco Canero and Jose Sulit |  | Beth is working on the tin 12/6- OE is working the tin 12/7- order over to provisioning 12./15- ready to shedule for encapsulation change. Rescheduled for 4/4 4/10-hotcut completed, building other PVC. 4/17- new configlet given to John.
2011-10-14 | Beth | UCO16-05-IJ | Colorado Springs | subrate DS3 with Dport and DCAR |  | NSPE0004842598 CDR201110190023 IQBJZ27Z | 5077494 | P1879646 |  | 3298396 | 1280 | BCBKNJTB0001 | 67/HFGS/102891/TWCS Demarc: 1st Flr Equipment Rm TW Cab on Position 1 Not ext. Tagged. | 0CQVK8 | 2011-11-08 | 2011-11-28 |  | bpdd | 2011-12-06 |  | UnitedHealthGroup- 64899 | 763-744-1575, Daniel _j_skripka@uhc.com | per john activated |  | cdr provided on 10/19 10/27 sent to ops on 10/21, escalating for pick up. Ticket C201110270175 11/2- issue with port assignment, escalating with management 11/10- pending FOC of 11/28 12/1- Pending demarc Action Taken: Paula/Qwest verified that the order was completed on 11/28/11. . Waiting for the DEMARC. ticket C201111290626 12/7- PTA recieved from Qwest, will test wtih them on 12/7 12/15- issue with testing, LOS. sent back to design to review. Escalating. 12/22- redesign done, needed to order a loop from time warner, not qwest. esclating new asr. 1/5- escating for FOC with TW 1/12- TW delivered May need to send TWTC out to LOCATE AND TAG.ON THE DSX frame. . -will call TW to request tag and locate -will resend cabling dsp once TW tag & locate dsp is done -Vzb network pretested -will test ckt e2e once patching is complete 11/17- order ready for activation, engineer informed.
2011-11-30 | Beth | TX016-02-IJ | McAllen, TX | 1536, T1 |  | NSPE0004954083 IQBJ1K85 | 5144719 | P1889859 |  | 3497074 | 1280 | BCBKN74R0001 | 38/HCGS/626511 /SW DEMARC LOC: 16TH FLR TELCO RM BB QUAD MNT POS 2, R DEMARC LOC Continued: J48C |  |  | 2012-01-10 | 2012-01-10 | bpdd | 2012-01-23 | 2012-01-11 | UnitedHealthGroup- 65096 | (91) 9810059326 , pradeep_yadav@uhc.com |  |  | 11/30- beth confirmed reciept 12/8- pending 12/14 FOC 12/15- AT&T held- order has been jeop'd -for the customer not ready. As per the customer has not signed the lease contract 1/12- order ready for activation, engineer informed.
12/13/2011 All info obtained 1/5 | Beth | MN011-02-IJ | Chaska, MN MDF 800 area (not ordered protcted) | 1Gig Internet Burstable 200mg commit |  | u313034 iqbj2qxk / i32849-min (closed) | 5189348 |  |  |  |  | u313034 | PLBKPT450001 / gx-73c-m6l7-0001 LOC Z DMARC- 1ST FL MDF800 ROOM BAY AJ807 FIBER PANEL FB3 |  |  |  |  | bpdd | 2012-03-07 | 2012-03-07 |  | u309696 | completed 4/19 with jim. |  | 12/14- pending approval doc, etc from Matt. 12/16- approvals received from Matt. Pending tin 1/5 All info obtained and order submitted by beth. 1/11- order in IDE design 1/20- order sent for site survey, pending CCR #: 1045770 (gig e card, rft 3/26, pending equipment install) and CCR #: 1045771 (SMTU card) 1/26- still pending cards, shipped. 2/2- CCR #: 1045770 (topol comp, pending closure) CCR (cards installed, pending topol and closrue) 2/10- CCR 1045770 is completed , 1045771 Pending CCR testing and completion (CCR now complet) 2/16- testing completed at Cologne. Pending LD completion, set for 2/20 3/7- order is ready for activation. Jimmie is informed.
2011-12-20 | Beth | MN039-08-IJ | Eden Prairie, MN | 6144, 4 x T1 |  | NSPE0005007234 IQBJ2DYR | 5198101 | P1896525 |  |  | 5520 | BCBKPND30001-0004 | 15/HCGS/226586//NW DEMARC LOC: 2nd fl excercise rm cab 3 slot 1 of 4 15/HCGS/226587//NW DEMARC LOC: 2nd fl excercise rm cab 3 slot 1 of 4 15/HCGS/226588//NW DEMARC LOC: 2nd fl excercise rm cab 3 slot 3 of 4 DEMARC LOC Continued: Extended Wire (Yes or No): no 15/HCGS/226589//NW DEMARC LOC: 2nd fl excercise rm cab 3 slot 4 of 4 |  |  | 2012-01-17 |  | bpdd | 2012-01-26 | 2012-01-16 | UnitedHealthGroup-65276 | 763-744-1556, john_l_rothstein@uhc.com |  |  | 12/22- pending tin creation by beth 1/5- ASR sent, pending response 1/12- LEC FOC for 1/12 1/16- order ready fro activation, enginneer informed
2012-01-11 | Beth | MI006-02-IJ | Southfield, MI | PIP 3072 2xT1 |  | NSPE0005054227 IQBJ2WM1 | 5212921 | P1900322 |  | 3975126 | 1280 | BCBKPW670001 | /HCGS/555803//MB /HCGS/555804//MB DEMARC LOC: MAIN PH.RM.,SHELF2 SLOT5OF7 DEMARC LOC: MAIN PH.RM.,SHELF2 SLOT5OF7 | 0CRQ1X 0CRQ1Z | 2012-01-17 | 2012-02-01 | 2012-01-26 | bpdd | 2012-02-08 | 2012-02-16 | UnitedHealthGroup- 65092 | masroor_khan@uhc.com 763-694-7370 | activation completed with Masroor on 4/26 |  | FOC for 2/1 2/2- LEC delivered, tested, pending issue with port assignments 2/8- B201202080054, escalated for issue with port assignments 2/16- order tested, pending closure. Escalated B201202160034 3/8- order closed on 2/16, engineer informed. activation completed with Masroor on 4/26
2012-01-18 | Beth | TX003-02-IJ | Sugarland TX | 44736, DS3 |  | NSPE0005073208 CDR201201190036 IQBJ236Y | 5220134 |  |  |  | 12288 | BCBKP1J30001 | 28/HFGS/745184//SW Demarc: 1st floor, Demarc room, no ext, 1ds3 jack panel 1, slot #4. Extended: no Tagged: yes |  |  | 3/21/2012 new 4/13 |  | bpdd | 2012-05-08 | 2012-04-16 | UnitedHealthGroup- 65088 | (91) 9810059326 , pradeep_yadav@uhc.com | Per John, activated on 4/18 |  | pending CDR pending FOC for sugarland tel, then we need to send ASR to Windstream 2.2- still pending FOC from Sugarland. 2/8- DLR received from Windstream, no FOC. Escalating 2/17- needed to send meet point ASR. Sent requsting 2/27 for dd, pending FOC FOC date for 3/21. 3/22- per lec backboard and rack is needed. Melissa will get more details. 3/29- new LEC FOC is 4/13 4/10- BCD C201204100056 4/19- ready for activation/engineer informed.
2011-06-01 | Katrina | UK527-01-IJ | Coventry, UK | PIP 10mg ethernet |  | Gobalink Opportunity ID 1016492, circuit id 6166597. NSPE0004466632 4836694 New s/o 4841921 | 4885981 |  |  | 2422034 |  | W0Y40352 | ETHA00139754/ETHC00139755/ONEA705208 DEMARCATION INFORMATION : FE LOCATION : ZEND FLOOR : GRND ROOM : COMMS CABINET : CUST ODF PANEL : POS : BACK OF CAB IN THE MIDDLE |  | 2011-06-15 | 2011-08-30 | 2011-09-06 | bpdd | 2011-09-23 |  | 65129 | 715/841-7731, sonja_d_mroczynski@uhc.com | completed with Sonja on 5/7 |  | 6/11- order is with provisioning 6/16- order sent over to PTT< pending date. 6/30- per KCI unable to get a hold of the lcon, sent an alternate contact. 7/8- escalated to find out where KCI is with this. 7/12- need correct phone number for Lcon, e-mailed John s., got correct number and passed to telco team. 7/13- pending fOC from BT 7/20- still pending FOC from BT 7/27- site survey complete, BT should have delivery date soon 8/4- job is out of planning should have a delivery date next week. PLANNING HAS NOW BEEN COMPLETED FOR YOUR ETHERWAY WITH SERVICE ID ETHA001397, 54 BEING PROVIDED UNDER ORDER NO 1-8208783173. 8/11- BT delivery date is 8/30 , 8/17- BT will be testing on 8/17 8/25- BT FOC date is set for 8/30, due date set to 9/7 9/1- LEC delviered we are testing 9/8- order is ready fro activation, informed engineer.
2012-03-05 | Beth | UMN20-05-CJ | International Falls, MN | upgrade port to Upgrade to 9216, 6xT1 Upgrade CAR to 2048 add UHGVERbgpbqZyofa |  | IQBJ4Y9G OQBJ4Z9K | 5276299 | P1913413 (in) P1796539 (out) |  |  |  | BCBKGWMJ0001-4 (out) BCBKR0ST0001-0006 (in) | 23/HCGS/483988//CZUC/ DEMARC LOC: 1st fl comm rm single mnt niu 23/HCGS/483990//CZUC/ DEMARC LOC: 1st fl comm rm single mnt niu |  |  | 2012-03-29 |  | bpdd | 2012-04-05 |  | UnitedHealthCare-64596 | (763) 744-2077, robert_a_benson@uhc.com | hotcut completed on 5/5 with Robert |  | 3/15- order with provisioning 3/22- FOC 3/29 4/11- ready for upgrade/engineer informed. 4/19- need to re-schedule this layer 3 system issue during the cutover. Our leads are already working with Tier 3 and they have opened a ticket shown below. The customer accepted to back it out instead and their existing 4 T1s are up and running as well as their BGP. Ticket # CR113711 completed 5/5
2012-03-12 | SA disco | RI007-02-DJ | Lincoln RI | disco |  | NSPE0005236537 OQBJ41F9 | [5 empty] | BCBKCHP60001-2 | [5 empty] | bpdd | 2012-04-12 | [5 empty] | disco complete 4/12
2012-03-19 | SA disco | na | eagan (unuable circuit on roadm) |  |  | NSPE0005261173 OQBJ47YV | [5 empty] | BCBKL7GY0001 | [5 empty] | bpdd | 2012-04-18 | 2012-04-25 |  |  |  |  | disco complete 4/25
2012-04-17 | core | UNJ20-03-DJ | East Windsor, NJ | diso POTS |  | NSPE0005356648 | [5 empty] | 609 490-9857 | [6 empty] | 2012-04-19 | [5 empty] | Order Number: D4YG48198 Date Due: 2012-04-19 Billing Telephone Number: 609 490-9857 Circuit ID or Telephone Number: 609 490- completed
2012-03-27 | Beth | CT003-07-CJ | Windsor, CT | Upgrade to 8xT1, 12288 |  | IQBJ5MTT OQBJ5QMR | 5300734 | P1724776 (out) |  |  | upgrade to 6144 | BCBJ9C2S0001-0006 (out) BCBKR92H0001-0008 (in) | FA/HCGS/778719 /SN DEMARC LOC: 1ST FL TELCO ROOM 14PK 1 SLOT 12 DEMARC LOC Continued: 12 FA/HCGS/778718 /SN DEMARC LOC: 1ST FL TELCO ROOM 14PK 1 SLOT 9 |  |  | 2012-04-27 |  | bpdd |  |  | UnitedHealthGroup-64673 | (860) 702-6323, dave_marquis@uhc.com | hotcut completed on 5/10 with Masroor |  | LEC is due 4/27 5/30 ready for upgrade, engineer ifnormed.
2011-09-16 | Beth | UNC17-05-IJ | Cary NC | 1536, T1 |  | NSPE0004765505 IQBJZDP9 RAL- I8580 CQBJ09JC dmarc move RAL-C8580 | 5057453 TIN 5132539 dmarc move | P1874350 |  |  | 1280 | BCBKM7H30001 | 13-bggv-hzdh-0002 UNITED HEALTHCARE//FL 1 RM TELCO MX2820 1.1.4:1.1.1 Aisle.Bay.Shelf:DS3.Card.Trib Start DEMARC Information: CFA: 3H-BGGV-BB5Y-0032, SLOT 18 |  | 2011-10-04 |  |  | bpdd | 2011-10-26 | 2011-10-20 | UnitedHealthGroup- 65108 | (763) 744-1886, steve_betsinger@uhc.com | completed with Don on 5/10 |  | on-net. Site survey sched for 10/14 10/20- circuit terminated. Tech left vmail with lcon to show him where circuit is. Ready for activation. 11/17- opened tag and locate ticket and send order to trminate circuit to lobby dmarc. 12/7- dmarc move with local ops. pending access. 12/15- tech scheduled to go out on 12/16 12.21- Ok I have been on site for quite awhile, No one at United Health Care seems to know anything about this circuit. The LCON escorted me to the 2nd floor telco room and this circuit is not there and the 1st floor Telcom room is controlled by building maintenance. I called Clark the build maintenance man ans was unable to reach him. I also called the property management group and they stated that this would need to go thru Clark for entrance. So this needs to be set up inadvance and there needs to be more info in the ticket as to what all corresponding ckt ID^s are and exactly where the ckt is to be moved to and from. As I stated no one here knows anything about it or where they want it. 2/2- tech is set for dispatch on 2/3 2/7- Arrived on site & building maintenance man Clark Suttle let me intothe 1st floor telco room. I located the ckt id: 13-bggv-hzdh-0002/bcbkm7h30001 was dropped off on port 1 of the DSXpanel. The customer contact Dave Pasternak stated that they had delive red a 66 block with 8 RJ-45 jacks to the back wall and that all I needed to do was run / extend the cable over there & that he would take it from there.I extended the ckt there, labeled it, tie wrasped it up & advised Dave & Tammy as well as Sue.
2011-10-10 | Beth | 1530-01-IJ | Dallas, TX | 44736, DS3 |  | CDR201110100049 NSPE0004826089 IQBJZ0HR dal I86076 (closed) DAL C86076 dal-C86076 (closed) | 5068375 | P1878936 |  | 3312499 | 3000 | BCBKNHK70001 | 14/HFGS/882175//SW DEMARC LOC: 1ST FLR, TELCO CAGE DEMARC LOC Continued: DS3_DSX,RR4, PNL1, POS 4 Extended Wire (Yes or No): No |  | 2011-11-02 | 2011-11-18 | 2011-11-17 | bpdd | 2011-12-02 |  | UHGECC- 65489 | 763-744-2082 eric_taylor@uhc.com | complted with Eric on 5/10 |  | 10/20- pending ASR. 10/27- escalated on ASR C201110270171 11/3- ASR out, pending FOC. MFS portion of loop due 11/11 11/7- pending FOC of 11/18 11/17- LEC delivered, we are working on testing, completing our network. C201111170056 12/1- had to go back to design. design done on 11/29 12/2- A TCOMS change order has been crea ted, dal-C86076, to move it off parent ckt o5-nrc-gwd-0002, as per field te ch, "there's no patching at site IAE because the DS3 at IAE is embedded on a local OC12." Also, a change MUX RTAN160 to change handoff at IAE. Sent em ail to NLI to review TCOMS asap, complete the sonet work and step for dispa tch. 12/7- esclalating with NLI 12/13- node work and install work being done and local change 12/29- had to re-dispatch for local node work since tech thought this was a hotcut. 12/29- order is now ready for activation. Engineer informed on 1/3 1/10- changed gold car to 18 mg.
11/3,all info obtained 11/8 | Beth | UMN99-40-IJ | Plymouth Service Type IDE 10GigE Burstable Select 1G Inet approval 8MQPUCPU CS bid script# 147741 SMF/LC connector | 10 gig Burstable select IDE |  | NSPE0004912241 u311943 IQBJ1XTT /min-I32765 | 5126385 |  |  |  |  | PLBKPD6D0001 / u311943 | jy-nsb-jcfg-0001 dmarc 106.11.2.VAM 2 port 1 (built as protected | [5 empty] | 2012-04-23 |  |  |  | completed with Jim on 5/12 |  | 12/1- order needs to be supped for service type, Beh is working with OS on Supp 12/7- product type corrected with IDE provisioning. 12/15- order with local provisioning. 12/22- site survey done, pending CCR #: 1041304, 10g card add to 7100 roadm, due 2/29. CCR in approved status and pending equipment shipment. 12/29- still pending card shipment 1/12- card shipped, pending install. 1/20- RMREMARKS :I installed the cards at JCFG 7/10 and fibered them to A 15 and B 15. their was already a Y cable so I used port 3 and fibered to Vam 7.0Q.1l:5 which goes to vam 7.0M.FB1A:5.. Pending CCR testing closure 1/26- CCR is complete local order ete tested. 2/2- pending LD network, asked for ETA 2/10- current date for LD network readiness is 2/17 3/7- checking on status of LD build 3/15- escalating for status on build 3/20- build compltete, LD order designed and sent for patching. 3/16- all patching complete. Sent to test and insatall 3/29- testing through LD and local, sending for ping test. 4/30 order ready for activation, mitch may not want to turn this one up.
2012-02-28 | Beth | NY051-02-IJ | Albany, NY | 9216, 6xT1 MD5 encryption UHGVERbgpbqZyofa |  | IQBJ4RKG | 5268119 | P1911918 |  | 5014750 | 4608 | BCBKRV6M0001-0006 | 34/HCGS/729856 /NY DEMARC LOC: GND,RM pbx,TEL RM ,RJ48C,LP Y,CAB N,MNTG 2,SLOT 10, 34/HCGS/729857 /NY DEMARC LOC: GND,RM pbx,TEL RM ,RJ48C,LP Y,CAB N,MNTG 2,SLOT 12, 34/HCGS/729858 /NY DEMARC LOC: Floor 1, pbx/telco rm., slot 1 of 4, mounting #3 34/HCGS/729859 /NY DEMARC LOC: GND,RM pbx,TEL RM ,RJ48C,LP Y,CAB N,MNTG 3,SLOT 2of4 34/HCGS/729860 /NY DEMARC LOC: GND,RM pbx,TEL RM ,RJ48C,LP Y,CAB N,MNTG 3,SLOT 3of4, 34/HCGS/729861 /NY DEMARC LOC: GND,RM pbx,TEL RM ,RJ48C,LP Y,CAB N,MNTG 3,SLOT 4of4, |  |  |  | 2012-03-31 | bpdd | 2012-03-28 | 2012-03-28 | UnitedHealthcare-65083 | (987) 313-9388, anupam_datt@uhc.com | completed with Anupam on 2/14. |  | 3/6- informed John that we need an in-state lcon, pending that to place the order. 3/7- John provided new LCON 3/22- LEC delivered, we are testing. 3/29- order ready for activation, enginer informed
2012-04-05 | SA disco | C1475-01-DJ | Wipro, Atlanta | disco |  | NSPE0005323544 OQBJ5016 |  | P1877013 |  |  |  | BCBKNC4T0001-0006 | [5 empty] | bpdd | 2012-05-03 | 2012-05-03 |  |  |  |  | disco completed on 5/3
2010-03-29 | Melissa | UUK04-03-IJ | Maidenhead England | PIP Ds3 | na | GL Job Id. 812349 Port: 4532768 | 4266532 |  | 44736 | 1906399 | 12288 | W0W76572 (port) | Y0501509A FLOOR : 1ST FLOOR ROOM : MDF R$OOM CABINET : CAB 4 ODF PANEL : C&W BNC PANEL POS : PORT 1 |  | 2010-04-14 |  |  | bpdd | 2012-01-15 | 2012-04-17 | 65150 |  | activated with Sonja on 5/15 |  | 1/5- pending PTT delivery. Melissa has reached out to get an ETA on PTT delivery 2/10- pending FOC date to be set 2/16- FIBRE SERVICES UPDATE - RISK ASSESSMENTS AND METHOD STAETMENTS HAVE BE, , EN ACCEPTED BY THE CUSTOMER AND THE SUPPLY CHAIN ARE IN THE PROCESS OF CONFI, , RMING ACCESS 3/6- RISK ASSESSMENTS AND METHOD STATEMENTS ACCEPTED BY THE CUSTOMER. AWAITING CONFIRMAITON OF DATE CONSTRUCTION WILL BE ABLE TO ATTEND SITE 3/15- Fiber services was to complete their work on 3/13, Melissa is double checking on that. 3/20- Fiber services work pushed.MUX COMMISIONING HAS BEEN MOVED TO 26/03 AND FINAL TESTING BEEN MOVED TO 27/03. 3/29- LEC reached LCON WHO HAS CONFIRMED ACCESS 30/03. (SITE CONTACT ON THE DAY WILL BE RITESH 01628 587 377) 4/5- the local end test to test the cckt is scheduled on 12th of April . 4/11- local end test complete. pending ping testing. 4/17- ******** PING TEST COMPLETED ************** POSTED AT: CE SITE LOOPBACK DEVICE: HARD LOOP SENDING 1000, 4470-BYTE ICMP ECHOS TO 206.115.90.13 SUCCESS RATE IS 100 PERCENT (1000/1000): 0XABCD MIN/AVG/MAX = 4/9/152 MS 0X1111 MIN/AVG/MAX = 4/10/116 MS 0X0000 MIN/AVG/MAX = 4/8/128 MS LOOPBACK REMOVED: NO order ready for activation, John informed.
2011-09-07 | B end- SOF | UUK04-06-IJ | Maidenhead, UK | 20Mb Ethernet |  | 4969564 |  |  |  | 3930101 | 2048 | W0Y67746 (bearer) W0Y67749 (NNI) W0Z04077 (port) | 2C00764474 / EAFE00764241/ONEA908274 DEMARCATION INFORMATION: FE LOCATION:"A-END FLOOR:"1ST ROOM:"I3 SERVER ROOM CABINET:"SER 5 |  |  | 2012-03-22 |  | bpdd | 2012-04-09 | 2012-04-03 | UnitedHealthGroup-Raven 64723 | (763) 744-1886, steve_betsinger@uhc.com | resheduled for 2pm on 5/17 |  | Siva sent to b end to create SOF 12/1- sof obtained, pending order info. 12/29- order with provisioning, need to correct LCON 1/5- ORDER SUBMITTED TO C & W FOR 20MB/20 MB TYPE 4 NNI TRANSPARENT 1/12- still pending BT FOC, BT usually takes 10 b days to provide this. 1/20- updated lcon, update back from C&W is that standard leadtime is 60 w days, job should be out of planning in 20 w days. 1/26- pending FOC date 2/8- pending tail delivery date 2/16- peding tail delivery date of 3/20 3/7- Awaiting Tail installation date / expected 22nd march . Due to this moving the service delivery date to 9th april. 3/29- Verizon will be dispatching to site on 4/2 to test 4/11- order ready for activation, engineer informed.
2012-02-01 | Beth | CA015-02-IJ | San Diego, CA | 44736, DS3 |  | CDR201202020019 IQBJ3PD6 snd I18030 clsd) | 5237835 |  |  | 5006322 | 26992 | BCBKP9FC0001 | 19/HFGS/529107//PT demarc info: mezzanine mpoe relay rack 101.01 panel 1 jack 1 wiri ng not extended (wiring not needed) demarc was tagged and labeled |  |  |  | 2012-03-07 | bpdd | 2012-03-19 | 2012-03-09 | unitedhealthgroup- 65087 | 763-694-7370, masroor_khan@uhc.com | per Masroor complete. |  | 2/8- order with provisioning, pending ASR. 2/17- ASR sent to LEC, pending FOC 3/8- loop accepted on 3/7. Pending order closure 3/12- ready for activation, engineer informed
2011-03-15 | katrina | AU528-01-IJ | Deakin, Australia | 2048k E1 |  | Globalink 919869, Globalink circuit 5057163 s/o 4785659 | 4772132 |  |  |  | 512 | W0Y10678, | N6003253L extended to coms room |  |  | 2011-05-05 |  | bpdd | 2011-05-19 | 2011-05-25 | 65148 multicasting reciever | (763) 744-1886, steve_betsinger@uhc.com |  |  | 3/16- pending globalink 3/14- globalink obtained, order submitted and is with provisioning, pending request to PTT 3/31- LCON not aware of order, sent note to John S 4/12- CATEGORISED AS A CAT 4METRO AND THE TCD PROVIDED = 05/05/2011 THE DESIGN HAS BEEN COMPLETED AND ORDER THE IS NOW PENDING EXTERNAL/LINE BUILD STAGE 4/14- FOC confirmed for May 5th 5/5 pending FFS approval, sent to UHG - John 5/10- FFS approved, Melissa sent back. Pending info back from PTT 5/19- local loop delivered, ops is checking cross connects, we are seeing it down/down. Troubleshooting 5/25- no updates from ops, send an e-mail for status 6/3- order now BCOMed and ready for activation
2012-03-07 | in country B end | II745-03-DJ | Pune India |  |  | 5025904 / 5025921 | [5 empty] | W0X83357 | [5 empty] | bpdd | 2012-05-14 | 2012-05-28 |  |  |  |  | B end is working on disconnect. Disco due on 5/14 5/17- path removed, pending order closure 5/23- disconnect completed on 5/18
2012-04-10 | Beth | IA021-05-IJ | Des moines IA | 3072, 2xT1 MD5 Encryption UHGVERbgpbqZyofa |  | Smartform 159721558 NSPE0005333700 IQBJ55D0 | 5328594 | P1920499 |  | 5034547 | 2048 | BCBKSKY20001-002 | 32/HCGS/085963//NW DEMARC LOC: 1st flr tele demarc mt# 1 slot# 3 of 14 DEMARC LOC Continued: Extended Wire (Yes or No): no 32/HCGS/085964//NW DEMARC LOC: 1st flr tele demarc mt# 2 slot# 10 of 14 DEMARC LOC Continued: Extended Wire (Yes or No): no | 0CSMBB 0CSMBC |  | 2012-04-30 |  | bpdd | 2012-05-07 | 2012-05-03 | Unitedhealthgroup-65134 | 91 91600 84400, harish_kandpal@uhc.com | per Harish port activated on 5/10 |  | 4/10- submitted to OM 4/19- FOC for 4/30 5.3- ready for activation, engineer informed.
2012-04-17 | SA disco | UTN14-02-DJ | ,Knoxville,TN | disco 2xT1 |  | NSPE0005355844 OQBJ6BW3 | [5 empty] | BCBJCD2K0001-2 | [5 empty] | bpdd | 2012-05-17 | 2012-05-21 |  |  |  |  | disco completed 5/21
2012-04-17 | SA disco | UNY24-02-DJ | New York, NY | disco |  | NSPE0005356910 OQBJ590Z |  | P1792773 |  |  |  | BCBKGLPF0001-0008 | [5 empty] | bpdd | 2012-05-17 | 2012-05-21 |  |  |  |  | disco completed 5/21
2012-04-17 | SA disco | UNJ20-02-DJ | East Windsor, NJ | disco |  | NSPE0005356915 OQBJ59GS | [5 empty] | BCBJP9GC0001 -3 | [5 empty] | bpdd | 2012-05-17 | 2012-05-21 |  |  |  |  | disco completed 5/21
2012-05-03 | Core | MA003-03-IJ | Cambridge,MA | POTS |  | NSPE0005413708 | [11 empty] | bpdd | [6 empty] | Order Number: N5PC6405 Date Due: 2012-05-10 Billing Telephone Number: 6172250910 completed KENDALL PRESS INSTLL TO BLDG DMRK TAG W TN CNTCT DOUG DOWNIE CBR 781 420 0830 OR JOHN SERGOT CBR 763 744 1582 OPB DOUG DOWNIE NI,225-0910, HH, 05-10, 00:30,WBB DTOK TAGGED LOC PER DOUGVER CODE XX
2012-02-07 | Beth | UFL75-05-CJ | Miami | Upgrade port to 6xT1, 9216 |  | IQBJ3TNK OQBJ3XF4 | 5243665 | P1906056 (in) |  |  | Upgrade Gold CAR to 4608 | BCBKGWSF0001-4 (out) BCBKRBYN0001-0006 | 60/HCGS/433044//SB 60/HCGS/433045//SB Demarc Info: 3rd flr,telco rm,cab 1,slot 5 and 6, rj48x, tagged and not extended. |  |  |  | 2012-03-01 | bpdd | 2012-03-07 |  | UnitedHealthGroup- 64860 | (860) 702-6323, dave_marquis@uhc.com | upgrade completed on 5/22 |  | 2/8- order with OE 2/16- ASR sent pending resonse 3/8- ready for upgrade. Engineer informed.
2012-02-14 | B end | GY509-02-IJ | Munich, Germany | 10M Ethernet md5 encryption UHGVERbgpbqZyofa |  | s/o 5029271 |  |  |  |  | 1280 | W0Z29203 | ODF PANEL:" POS:"HU 7 INTERNAL CABLING:" FIBRE RACK:" BLOCK:" FIBRES:"RJ45 PORT 1 PRESENTATION:"ON MNET MODEM XTU402051 LOOPBACK PLUG DELIVERED:"YES |  |  | 2012-05-07 |  | bpdd | 2012-05-18 | 2012-05-15 | UnitedHealthGrop-65084 | 763-694-7409, Terry_Bjorke@uhc.com | activated on 5/22 with Andrew/Terry. |  | 2/16- pending SOF 3/16- SOF received. 3/29- order generated 4/11- PTT FOC is May 7th, PTT did not accept expedite. Our commit date is May 11th. WE will work to see if we can better the date. 5/3- AW TAIL - NEW FOC IS 14TH OF MAY because of inhouse cabling 5/15- order ready for activation, engineer informed.
2012-03-16 | Beth | UMN08-08-IJ | Minnetonka Lab- ICM | PIP ICM s replacing FR circuit ZABJ2RMG0001- 128k |  | IQBJ46ZP MIN-I33151 | 5287762 |  |  | 5021553 | 128 | BCBKR3620001 | 15/HCGS/227617//NW DEMARC LOC: main telco/floor b2/shelf 1 slot 1 of 7 on 66 blk DEMARC LOC Continued: |  |  | 2012-04-03 | 2012-03-29 | bpdd | 2012-04-10 | 2012-04-03 | ASN 65300 UnitedHealthCare-IDN need to change to unitedhealthgroup-lab | 763-744-1587, Leon_L_Betterman@uhc.com | activated on 5/24 |  | 3/16- UHG ordered 3/22- FOC for 4/3 3/29 - LEC delivered, we will esclate for closure. 4/11- order ready for activtion, engineer informed. 5/23- need to move to the unitedhealthgroup-lab vpn. Disco placed on old PVC. Need to build neew pvc once disco completes. 5/24 activated
4/2/1012 | SA disco | MN053-08-DJ, | 14100 Business Center Drive ELK RIVER MN | Disconnect OC3 |  | NSPE0005306971 OQBJ5TQY |  | P1637848 |  |  |  | BCBJ07WN0001 | [5 empty] | bpdd | 2012-05-01 | 2012-05-23 |  |  |  |  | disco due on 5/1 esclaating for disco 5/17- -no tickets filed by customer -breaking all xcons -DNG, RVG & MPW 883/unwire dispatches sent through mux manager 5/23- order still open, escalating further order discoed on 5/23 .
2012-05-02 | SA disco | MN053-09-DJ | ELR to Costa mesa pt to pt | disco |  | NSPE0005412894 5058338 | [5 empty] | W0Y07923 | [6 empty] | 2012-05-31 | [5 empty] | disco due on 5/31 5/30- order cancelled per UHG request.
2011-08-18 | B end | CN501-01-IJ | Burnaby, British Columbia, Canada | New 2xT1 for Canada |  | 4967637 (port) 4967644 (bearer) | 5173693 |  |  | 4145036 | 2048 | W0Z04136 (bearer) W0Z04137 (bearer) W0Z04138 (port) | Telus 55/DHXS/323095/000/BCTC/000 55/DHXS/323096/000/BCTC/000 DEMARC INFO: HDSL BOX 3 2ND FLOOR SERVER ROOM MOUNTED ON THE WALL ACROSS THE DOOR LOCAL CONTACT: JUDY GAGE - 6042932584 HARD LOOP LEFT ON SITE |  |  | 2012-01-19 |  | bpdd | 2012-02-10 | 2012-01-26 | UnitedHealthGroup- 65144 | (702) 303-7293, tauoa.falo@uhc.com |  |  | 8/18- siva will forward to B end for processing 9/10 pending SOF 12/1- SOF obtained, pending order info 12/15- order submitted, with provisioning 12/21- order sent to telus on 12/19, pending FOC date 12/28- Telus set to install on 1/17 with a 1/19 FOCx 1/20- ping tested, but unsure of local loop delivery, checing wtih delivery management 1/26- order ready for activation, engineer informed.
2011-08-19 | B end | CN512-01-IJ | Victoria, British Columbia | 1536, T1 |  | s/o: 4967601 port s/o: 4967602 hicap | 5174001 |  |  |  | 1280 | W0Z06291 (port) W0Z06290 (DS1) | PTT: TELUS 6045492253 DEMARC INFO: SERVER ROOM, SINGLE SLOT PAIR GAIN INTERFACE RJ45 |  |  | 2012-02-01 |  | bpdd | 2012-02-01 | 2012-02-01 | UnitedHealthGroup-65144 | (702) 303-7293, tauoa.falo@uhc.com |  |  | order pending B end SOF 12/1- SOF obtianed, pending order info. 12/15- order submitted, with provisioning 12.19- still with provisioning, updated lcon 12/31- escalating with provisioning. 1/5- order sent to telus (PTT) pending delivery dates back. 1/12- TELUS INSTALLATION DATE MONDAY, JANUARY 30, 2012 SERVICE DUE DATE WEDNESDAY, FEBRUARY 01, 2012 (FOC) 1/31- order ready for activation, engineer informed on 2.2
2012-05-04 | Core | DC002-02-IJ | Washington, DC | New POTS line |  | NSPE0005416483 | [18 empty] | Order Number: N2DP32860 Date Due: 2012-05-24 Billing Telephone Number: 2028425436 Circuit ID or Telephone Number: 202 842-5436 completed 5/24
2012-03-23 | Beth | UVA01-05-IJ | Richmond, VA | , New 2 x T1 encryption UHGVERbgpbqZyofa |  | IQBJ5CWK | 5294124 | P1916029 |  | 5023378 | 1280 | BCBKR55G0001-002 | 48/HCGS/832380 /CV DEMARC LOC: BSMT 1,RM 1,TEL RM ,RJ48C,LP Y,CAB N,SHELF 2,SLOT 3,sh 2/sl DEMARC LOC Continued: 3 48/HCGS/832381 /CV DEMARC LOC: BSMT telc,RM telco,TEL RM ,RJ48C,LP Y,CAB Y,shelf-2,SHELF DEMARC LOC Continued: 02,SLOT 02,jk-2 |  |  | 2012-04-06 | 2012-04-06 | bpdd | 2012-04-16 | 2012-04-12 | UnitedHealthGroup-64623 | (763) 694-7370, masroor_khan@uhc.com | completed on 6/4 |  | 4/11- LEC delivered, we are working on testing. 4/19- order ready for activation, engineer informed. 5/14- BCBKR55G0002 is up/up ckt 1 is up/down. We tried to troubleshoot it but there is no customer tech on site. customer extended the dmarc. As per customer He will reschedule it for the next turn up 5/17- masroor requested to troubleshoot on 6/4 6/4- completed with Masroor.
2012-04-03 | Beth | CO035-04-IJ | Denver, CO | 3072, 2xT1 MD5 Encryption UHGVERbgpbqZyofa |  | NSPE0005321229 IQBJ5YJ5 DNV- I28659 Smartform 159049141 | 5316501 | P1919022 |  | 5029601 | 1280 | BCBKSGK40001-0002 | 13-cny-anr-0004 13-cny-anr-0005 Dmarc for both circuits are extended as follows:----CKT - 0004 for VZ POP on MEZ level xcond from CAC slot 1 to PR 6 & 31 of 50PR riser to MPOE in Bsmt, xcond in MPOE from 50 PR to PR 3 of Cust (United Healt h) 66 block, cust block is extended to thier suite on 11th floor (Suite 1100), terminates in customer server rm to Jack 3 of customer panelleft hard loop in jack for testing purposes.----CKT - 0005 for VZ POP on MEZ level xcond from CAC slot 4 to PR 3 & 28 of 50PR riser to MPOE in Bsmt, xcond in MPOE from 50 PR to PR 5 of Cust (United Health) 66 block, cust block is extended to thier suite on 11th floor (Suite 1100), terminates in customer server rm to Jack 5 of customer panel, left hard loop in jack for testing purposes | 0CSKH5; 0CSKH6 |  | 2012-04-27 |  | bpdd | 2012-05-04 | 2012-05-04 | UnitedHealthGroup-65242 | 91 91600 84400, harish_kandpal@uhc.com | completed with masroor on 6/6 |  | 4/11- order with provisioning, pending AS. 4/19- FOC 4/.27 5/3- local loops delviered, pending order closure 5/10- order ready for activation, engineer informed.
2012-04-05 | Beth | UTX34-06-IJ | San Antonio, TX | DS3 with Dport and Dcar MD5 Encryption UHGVERbgpbqZyofa |  | Smartform 159716329 CDR201204100013 NSPE0005333663 IQBJ55B5 | 5330668 | P1920481 |  | 5034552 | 40256 | BCBKSKX90001 | 42/HFGS/106223/TWCS Demarc:1st floor data center back wall below TW telecom ds1 smartjack chassis, p os 3 of 4 on ds3 jack | 0CSL9X |  | 2012-05-02 | 2012-05-02 | bpdd | 2012-05-29 | 2012-05-18 | Unitedhealthgroup-64608 | 763-744-1556, john_l_rothstein@uhc.com | completed on 6/5 |  | 4/10- submitted to OM 4/19- FOC for 5/2 5/3- LEC delivered, escalating for order closure 5/17- escalating further for order closure C201205170057 5/23- order closed on 5/18 6/5 completed with John R.
2012-05-23 | Core | PA001-04-IJ | PHILADELPHIA PA | pots line |  | NSPE0005472769 | [11 empty] | bpdd | 2012-06-01 | [5 empty] | Order Number: N3HC76290 Date Due: 06-01-12 Billing Telephone Number:215 467-5689 New Telephone Number:215 467-5689 completed on 6/1- no dmarc provided.
2012-05-24 | Beth | CA049-02-IJ | Carlsbad, CA | T1, 1536 |  | smartform 174512608 NSPE0005479378 IQBJ7G9W SND-I18485 | 5402163 | P1928925 |  | 5074331 | 1280 | BCBKS6CR0001 | [5 empty] | bpdd |  |  |  | 763-744-1575, daniel_j_skripka@uhc.com | UnitedHealthGroup-65068 |  | 5/24- beth sent an e-mail, need a MLN that is in state. 5/31- pending FOC 6/4- will supp to cancel, this is being replaced by a 2xt1 6/7- Melissa confirmed order is cancelled.
2012-05-24 | Melissa | PA012-05-CJ | pittsburgh, PA | change error detection to CRC32 | [7 empty] | BCBJX4PL0001 | [10 empty] | completed with Anupam on 6/7 |  | completed with Anupam on 6/7
2012-01-06 | Beth | C1520-07-IJ | Los Angeles | PIP 155520, OC3- SMF LC connector |  | CDR201201060037 NSPE0005040999 IQBJ2XPJ Lsa I122428 (clsd) | 5211110 | P1900571 |  | 5000789 | 40000 | BCBKPXM90001 | o2-8sh-owb-0063 DMARC? OWB-CC LGX 5.5.G.7.A.3/4 (4TH FLOOR MDF ROOM)--How was DMARC left? UNLOOPED/NORMAL--Type of termination? LGX (LC)--C ircuit |  |  |  |  | bpdd | 2012-04-17 | 2012-03-27 | UHGECC- 65488 | 763-744-2082, eric_taylor@uhc.com | completed with Eric on 6/12 |  | 1/11- pending CDR approval 1/11- CDR approved, sent to beth 1/26- order in local design 2/2- needed a location update, back to local design 2/10- sent to ops for site survey 3/8- Local loop deliver and local order closed. Tested, pending order closure. Opened ticket C201203080055 to better CDD and close order. 3/15- escalated, new ticket C201203150057 3/22- issues with Ping test. Tech is troubleshooting 3/29- order ready for activation, engineer informed. 6/12- completed with Eric
2012-01-20 | Beth | AZ007-02-IJ | Tuscon, AZ | 44736, DS3 |  | CDR201201200053 IQBJ25KG TUS I6782 | 5221217 | P1902238 |  | 5001025 | 18432 | BCBKP1090001 | 16/HFGS/706256//MS DMARC informat ion is 2nd floor 2259 wall mount 1st cabinet slot 1 of 3. | 0CRTM7 |  | 2012-05-31 | 2012-05-31 | bpdd | 2012-06-07 | 2012-05-31 | UnitedHealthGroup- 64882 | (763) 744-2077, robert_a_benson@uhc.com | completed with Robert on 6/14 |  | 1/26- pending CDR approval 1/27- order submitted. 2/2- per time warner PLEASE SUP TO CANCEL. TW CANNOT DELIVER A DS3 TO THIS ADDRESS 9040 S. RITA RD, TUCSON AZ. THE BUILDING ONLY HAS AN ETHERNET RING. NO SONET AT THIS TIME. THANKS" Melissa is checking on altrnate carriers 2/10- we will be using Qwest, ASR sent requesting 2/23 2/17-needed to supp ASR for 12 month term, prov issueing supp 3/6- The circuit needs to be delivered to 9030 South Rita Road, not 9040 South Rita Road. Faulk Electric cross connects at 9030 to existing fiber for the final mile to UHG at the 9040 building. The circuit orders placed listed 9040 South Rita Road since this is the address of the UHG facility. In order to gain access to 9030 South Rita Road which is owned by a large government contractor, they require 48 hour notice to set up building access.. Thre is a Qwest special construction. They have assigned a PM and kicked off the project yesterday. Pending timeline from them. 3/15- per Qwest: Our fiber Techs are going out on 3/19 to verify the fiber path. We are hoping there is an existing structure that can be used for this project. 3/15- john asked for supp to chang the address again to 9040 South Rita 3/22- supp sent to LEC asking to deliver to 9040. Pending FOC. 3/29- still pending FOC, escalating 4/11- esclalated further on FOC. There are power site requirements, getting additional info on that. 4/17- power requiements complete update on progress of the fiber issue and FOC 5/3- fOC for 5/31, better due date ticket C201202230110 5/17- pending 5/31 FOC 5/31- lEC delivered, pending testing. 6/6- order ready for activation, engineer informed.
2012-02-16 | Beth | MN053-62-IJ | Elk River, MN | PIP ICM s replacing FR circuit ZABJ2V7G0001- 384k |  | IQBJ40ST IZA0VZNR | 5279922 |  |  | 5019453 | 128 | BCBKR1GT0001 | 15/HCGS/227550//NW DEMARC LOC: mn lvl mdf rm cab 2 slot 14 of 14 |  |  | 2012-03-27 |  | bpdd | 2012-04-03 |  | UnitedHealthCare-IDN- 64680 | 763-744-1587, Leon_L_Betterman@uhc.com | activated with Leon on 6/13 |  | 3/8- need to be cancelled and re-issued to go off-net 3/22-LEC delivered. Working on closing our order. B201203220099 3/29- ready for activation. Engineer infomred.
2012-02-16 | Beth | MN053-54-IJ | Elk River, MN | PIP ICM s replacing FR circuit AZABJ2WKX0001- 384k |  | IQBJ4GGT IZA0VWUX | 5261973 |  |  | 5012590 | 128 | BCBKRPY90001 | 15/HCGS/227469//NW DEMARC LOC: mn lvl mdf rm cab 2 slot 13 of 14 |  |  | 2012-03-23 |  | bpdd | 2012-04-03 |  | UnitedHealthCare-IDN- 64680 | 763-744-1587, Leon_L_Betterman@uhc.com | activated with Leon on 6/13 |  | 3/8- need to be cancelled and re-issued to go off-net 3/22-LEC delivered. Working on closing our order. 4/2- order ready for activation, engineer informed.
2012-02-16 | Beth | UCT09-41-IJ | Trumbull, CT | PIP ICM s replacing FR circuit ZABJ2YR20001- 384k |  | IQBJ4T47 IZA0VYYS BRP-I1443 | 5258121 |  |  | 5015693 | 128 | BCBKRXH20001 | 13-3DN-HMG1-0015 Demarc Structure LD: BLDG Demarc Structure LV: MAIN Demarc Elevation LD: FL Demarc Elevation LV: 1 |  |  | 2012-03-26 |  | bpdd | 2012-04-03 |  | UnitedHealthCare-IDN- 64675 | 763-744-1587, Leon_L_Betterman@uhc.com | activated with Leon on 6/14 |  | pending lec delivery 3/26 3/29- order ready for activation, Engineer informed.
2012-02-16 | Beth | UCT09-42-IJ | Trumbull, CT | PIP ICM s replacing FR circuit ZABJ2RMG0001- 384k |  | IQBJ4ZDQ IZA0VZIQ BRP-I1444 | 5258010 |  |  | 5079408 | 128 | BCBKR0V90001 | 13-3DN-HMG1-0016 |  |  | 2012-03-23 |  | bpdd | 2012-04-03 |  | UnitedHealthCare-IDN- 64675 | 763-744-1587, Leon_L_Betterman@uhc.com | activated with Leon on 6/14 |  | pending lec delivery 3/23 4/2- order ready for activation, engineer informed.
2012-05-09 | SA disco |  | Las Vegas |  |  | NSPE0005430461 OQBJ638F | [5 empty] | BCBKMB1Y0001 | [5 empty] | bpdd | 2012-06-06 | 2012-06-06 |  |  |  |  | disco completed on 6/6
2012-06-04 | core | UNY13-05-DJ | Albany, NY | disco |  | NSPE0005506638 | [5 empty] | 518-452-0383 | [5 empty] | bpdd | [6 empty] | Order Number: D2DP5126 Date Due: 2012-06-07 Billing Telephone Number: 5184520383 Circuit ID or Telephone Number: 5184520383 completed
2012-06-08 | core | PA001-01-DJ | Philadelphia PA | disco pots |  | NSPE0005522633 | [5 empty] | 215-271-6190 | Order Number:D3HC76795 Date Due:06-11-12 Billing Telephone Number: 215 271 6190 Disconnect Telephone Number: D3HC76795 |  |  |  |  | bpdd | [6 empty] | Order Number:D3HC76795 Date Due:06-11-12 Billing Telephone Number: 215 271 6190 Disconnect Telephone Number: D3HC76795 bill completed on 6/11
2012-05-07 | Beth | FR501-04-IJ | Irvine, CA | 6144, 4xT1 |  | Smartform 165838358 NSPE0005425259 IQBJ60BW (cancel) IQBJ65TT 9reissue) lsa I124225 | 5376685 | p1926897 |  |  | 2048 | BCBKS2J60001-0004 | 13/HCGS/816851//PT DEMARC LOC: 2.1, SHELF 3, SLOT 1, BUILT-IN 13/HCGS/816852//PT DEMARC LOC: 2.1, SHELF 2, SLOT 2, BUILT-IN 13/HCGS/816853//PT DEMARC LOC: 2.1, SHELF 3, SLOT 3, BUILT-IN 13/HCGS/816854//PT DEMARC LOC: 2.1, SHELF 3, SLOT 4, BUILT-IN |  |  | 2012-05-30 |  | bpdd | 2012-06-06 |  | unitedhealthgroup-65085 | 919873139388 , anupam_datt@uhc.com | activated with anupam |  | beth placed tin on 5/9. Per John they may need active by first week of June. 5/17- ASR sent, pending response 5/23- FOC for 5/30 5/30- lec delivered, opened ticket to get circuits tested and order closed B201205310047 6/6- order ready for activation, engineer informed.
2012-05-16 | Beth | UCO12-03-IJ | Colorado Springs, CO | 1536, T1 MD5 encryption UHGVERbgpbqZyofa |  | Smartform 173735687 NSPE0005468221 IQBJ7CVY | 5397824 | P1928122 |  | 5067373 | 1280 | BCBKS4Y20001 | 26/HCGS/633637//MS DEMARC LOC: 1ST FLR, SOUTH PH RM, CAB 3, DUAL MOUNT #2, SLOT 2 |  |  | 2012-06-07 | 2012-06-07 | bpdd | 2012-06-14 | 2012-06-07 |  | 91 9873139388, anupam_datt@uhc.com | unitedhealthgroup-64760 |  | 5/16- submitted to OM 5/23- order to provisioning, pending ASR 5/31- FOC for 6/7 6/7- still pending LEC delivery as of 10am on 6/7 6/14- order closed 6/7 engineer informed.
2012-02-09 | Beth | CA016-02-IJ | Irvine, CA | Dport/DCAR DS3 MDF encrayption |  | CDR201202100006 IQBJ3YLB lsa I122721 | 5247830 | P1906953 |  |  | 9216 | BCBKRDVN0001 | 13/HFGS/586555//PT |  |  | 2012-06-14 |  | bpdd |  |  | UnitedHealthGroup- 65085 | 919873139388 , anupam_datt@uhc.com |  |  | 2/16- pending local facility check 3/7- needed to go through new local re-design because of Cfa change 3/15- local design changed, order to ops 3/22- LEC rejected ASR for LCON. . John talked to Tony and he agreed to be lcon. Order will be supped. 3/29- order supped, escalaiting for ASR 4/10- LEc needs lcon that can accept site requirements. Supping order iwth that infomation. 4/19- order supped with lcon, pendign LEC response, asking provisioning to follow up. 4/23- LEC came back wtih 6/14 FOC date. btdd is C201204230043. 5/3- escalated the ticket 5/11-code 38 which includes the following. >Reconfigure/Rewire Existing Mux >Translation Work >Backplane Wiring >Install Plugs >Install Customer Premise Equipment as Determined by the OSPE during the site visit >Place Less than 2,500 ft. of Fiber and Conduit >Order and Install New Central Office Equipment 5/11- Requested confirmation if dates will need to be negotiated due to customer delay- customer has not indicated where the equipment is to be placed. Customer needs to identify location where MPOE is to be placed. Customer also to provide backboard, power, ground and path from MPOE to the equipment location. Per Network PM, dates will need to be renegotiated. 5/16- FOC date 6/14 6/6- fOC isn't valid- Eric Carter completed the site requirements last weekend. melissa reached out to eric to see if the site visit has been schduled with the LEC field person so the site can be certified as ready and the order can progress. 6/14- LEC hasn't issued FOC, so we can't escalate for a better date yet, but we are pushing for the FOC. Per LEC Based on customer delay caused on site requirement s new ECD of the job is scheduled on 6/26/12 and new DD should be 7/3/12.
2012-02-22 | Beth | HI005-05-IJ | Honolulu. HI | DS3 with Dport and Dcar MD5 Encryption UHGVERbgpbqZyofa |  | CDR201202220055 IQBJ4T64 - reissue IQBJ5NGV | 5260902 |  |  | 5025669 | 9216 | BCBKR97Y0001 | 18/HFGS/105422/TWCS Demarc:7th flr suite 725. server room..Backboard at the right hand wall.. 2 position shelf.. labelled EE006 position 2. tagged with both ID's not extended as requested by the customer to be in the 7th floor instead of 1st floor as the minimun point of entry | 0CR8H2 |  | 2012-06-08 | 2012-06-11 | bpdd | 2012-06-15 | 2012-06-11 | UnitedHealthCare-65009 | 763-694-7409, Terry_Bjorke@uhc.com | activated on 06/19/2012 2:00 PM Central Time |  | 3/6- pending Globalink pricing. 3/8- order with OE 3/15- ASR sent to the LEC requesting a 3/29 due date 3/22- still pending FOC 3/29- needed to cancel and re-issue for city pairs. New IQBJ5NGV 4/11- pending FOC, escalating for FOC. 4/12- per TW the conduit is clogged, informed john. Also trying to get more detial from the LEC. 5/3- Per TW- Also please be advised that there is no building demarc in Hawaii as we do maximum point of entry. If you do not want us to extend to the customer, then you wil l need to specify where in the building you want us to hand the circuit off at a nd then we will have to get the building to approve of said demarc that is not i n the customer suite 5/10- asked john for AT&T cicuit ID so we can supp our ASR with that information 5/16- FOC received for 6/8 6/11- opened missed loop ticket C201206110020 6/14- order closed 6/11 informed engineer 6/19- activated with Terry
2012-05-15 | SA disco | UTN06-02-DJ | Memphis | disco |  | OQBJ67XC | [5 empty] | BCBKL3FL0001 | [5 empty] | bpdd | 2012-06-14 | 2012-06-14 |  |  |  |  | disco completed on 6/14
2012-05-15 | SA disco | IA021-02-DJ | Des Moines | disco |  | NSPE0005448078 OQBJ68SK | [5 empty] | BCBKK0NT0001 | [5 empty] | bpdd | 2012-06-14 | 2012-06-14 |  |  |  |  | disco completed on 6/14
2012-06-08 | core | C1543-03-IJ | Irving TX | new pots |  | NSPE0005523691 | [6 empty] | Order Number: I1806021 Date Due: 06/20/12 (access hours between 8 am and 5 pm) Billing Telephone Number: 972 929-7202 Circuit ID or Telephone Number: 9729297292 |  |  |  |  | bpdd |  | 2012-06-20 |  |  |  |  | Order Number: I1806021 Date Due: 06/20/12 (access hours between 8 am and 5 pm) Billing Telephone Number: 972 929-7202 Circuit ID or Telephone Number: 9729297292 completed on 6/20
2012-06-14 | Beth | CA016-07-CJ | Irvine, CA | Upgrade from 4xT1 to 8xT1, 12288 |  | Smartform is 182511053 NSPE0005542172 | 5430238 |  |  |  | 3071 | BCBKS2J60001-4 | [5 empty] | customer paid expedite |  |  | unitedhealthgroup-65085 | 919873139388 , anupam_datt@uhc.com |  |  | 6/21- per John cancel
2012-06-04 | SA disco | UNY13-03-DJ | Albany, NY | disco |  | NSPE0005506792 OQBJ7RC9 |  | P1835314 |  |  |  | BCBKKR7G0001-05 | [5 empty] | bpdd | 2012-06-25 | [5 empty] | disconnect due on 6/25 disconnect completed on 6/25
2012-05-09 | SA disco |  | (Eagan 1 gig on DWDM | disco |  | NSPE0005431601 OQBJ7TW4/min-O31443. | [5 empty] | U211574 | gx-73c-w7y-0001 | [5 empty] | 2012-06-08 | [5 empty] | disco due on 6/8, billing ceased, pendign physical disco 6/28- circuit is physically disconnected.
2012-05-17 | SA disco | UCO16-02-DJ, | Colorado Springs, CO | disco |  | NSPE0005459322 OQBJ7PKZ |  | P1405660 |  |  |  | BCBJDB1B0001 | [6 empty] | 2012-06-19 | 2012-06-19 |  |  |  |  | disco completed on 6/19
2012-06-04 | Beth | NY013-03-IJ | Hamilton, NJ | 1536 T1 with md5 encryyption UHGVERbgpbqZyofa |  | Smartform 179251119 NSPE0005510159 IQBJ7S3J | 5415579 | P1931421 |  | 5081607 | 1280 | BCBKTBWC0001 | /HCGS/473081//NJ DEMARC LOC: GND,RM t,TEL RM ,RJ48C,LP Y,CAB N,RCK 1,POS 4, | 0CS3XF |  | 2012-06-22 |  | bpdd | 2012-06-29 | 2012-06-29 | UnitedHealthGroup-65240 | 763-694-7370, masroor_khan@uhc.com | completed with anupam on 7/12 |  | 6/4 submitted to OM 6/7 tin created, pending om submission 6/14- FOC for 6/22, our commit date is 6/29 6/29- order ready for activation, engineer informed.
2012-06-05 | SA disco | UVA01-03-DJ | Richmond, VA | disco |  | NSPE0005512708 OQBJ7TVH |  | P1838871 |  |  |  | bcbkk1d40001 | [5 empty] | bpdd | 2012-07-05 | [5 empty] | disco completed 7/5
2012-02-10 | Beth | CT003-05-IJ | Windsor, CT | Dport/DCAR DS3 |  | CDR201202100050 hrt I14731 IQBJ37NN | 5253780 |  |  | 5011235 | 4096 | BCBKRKYD0001 | HFGS/710738//SN DEMARC: 1st floor telco room 12 pad multi mount slot 1 bnc conn ecto rs. |  |  | 2012-10-22 |  | bpdd | 2012-10-29 | 2012-07-10 | UnitedHealthGroup- 64673 | (860) 702-6323, dave_marquis@uhc.com | per keith this is up and active as of 7/13 |  | 4/19- Requested the latest update from the engineer- per him job will be issued by the end of this week. 5/3- There is no change as the engineer job was issued last week and is still trying to have the ECD improved; There is still a job in the CO that is required. 5/11- escalating for more info 5/16- no new status. Asking to get the following answers: 1. Where are we with the engineering? The job was issued in April 2. Are they able to better to 5/31? 3. Are customer requirements still pending? 5/23- LEC status:5/18: On track. There is CO work and construction job required. Engineers are working hard to improve the ECDs. The best scenario is that order could be delivered in June, but please have in mind, that this is not confirmed at this time. 5/31- no change in LEC status. 6/6- requested order to be placed as hot esclation with ATT to be discussed on calls. pending results of that escalation 6/14- per LEC Design date is scheduled 9/5. 7/5- fiber splicing is complete, but they are saying that there is site requirements (power) that are needed. We have reached out to get more infomration from AT&T on that. 7/11- order ready for activation. Engineer informed.
2012-03-20 | B end | II521-02-IJ | Hyderabad India | 20M subrate DS3 with encryption UHGVERbgpbqZyofa |  | 5051507 |  |  |  | 5072782 | 6144 | W0Z39250 (port) | BTL 1357547S |  |  |  |  | bpdd | 2012-07-27 | 2012-07-11 | UnitedHealthgroup-65079 | 919160084400, harish_kandpal@uhc.com | activation completed |  | SOF received, pending order numbers. 5/10- ASR sent to the PTT pending response. 5/17- ORDER HAS BEEN ACK BY PTT HOWEVER, THE COMMERCIAL APPROVAL IS PENDING FROM THEIR SALES. FOLLOW-UP STARTED WITH PTT -SALES 5/31- SCOPE OF WORK: PTT HAS 900MTRS OF FIBER PULLING AND APPR0X 70 MTRS OF TRENCHING WORK. CALLED UP GIRDHAR TO SCHEDULE VISIT BUT NO RESPONSE ON PHONE CALL. 6/5- CUSTOMER ARRANGED ROW PERMISSION FOR PTT OSP WORK AND PTT WILL ALIGN LOCAL TEAM FOR FIBER PULLING SHIRTLY. NOTE: THE OSP WORK ACROSS BUSINESS PARK ROAD CAN BE ARRIED IN WEEKEND ONLY . PTT HAS SHARED 9TH JULY AS RFS DATE 6/14- OSP WORK IS NEAR COMPLETION AND PTT WILL PLAN FOR FIBR TERMINATION AND MUX INSTALLATION IN NEXT 2-3 DAYS. HARDWARE(MUX,RACK, BATTERIES ETC) IS DELIVERED AT SITE. 6/20- Melissa asked about the mux integration and status. 6/28-It looks like the PTT engineer should have done the internal cabling today and they should have performed ETE loopback testing. It also sounds like they are starting the logical provisioning process. 7/5- line is in loop back testing. Dispatch set for 7/9 7/9- Ping test completed. 7/11- order ready for activation, engineer informed.
2012-06-25 | core | MD021-03-IJ | Towson, MD | Pots line |  | NSPE0005574094 | [6 empty] | Order Number: N4BH07509 Date Due: 2012-07-06 Billing Telephone Number: 4103370234 Circuit ID or Telephone Number: 410 337-0234 |  |  |  |  | bpdd | [6 empty] | Order Number: N4BH07509 Date Due: 2012-07-06 Billing Telephone Number: 4103370234 Circuit ID or Telephone Number: 410 337-0234 7/11 - Per technician there was no access to the location. Please provide a date when someone will be available and an onsite name and number. 7/23- john cancelled this request.
2012-05-09 | SA disco |  | Plymouth 1 gig on DWDM | disco |  | NSPE0005431601 Request 20833278 is min - O32473 | [5 empty] | U210681 | gx-73c-jcfg-0001 | [5 empty] | 2012-06-08 | 2012-07-15 |  |  |  |  | disco due on 6/8, billing ceased, pendign physical disco 7/12- patches removed at nsb. Pending other patch removal and order removal. 7/15- disco completed and order closed
2012-05-15 | SA disco | UMN99-43-DJ | Plymouth MN 1 gig roadm | disco internet |  | request 20981509 cfo-O156623 / min-O32522 | [5 empty] | U306803 | [6 empty] | 2012-06-14 | [5 empty] | 5/17- sent to SA disco, pending date back. 5/31- disconnect due on 6/14 6/6- made sure order was assigned to correct disco queue 6/14- disco due today 6/20- escalating for disco. 7/12- order physically discoed
2012-05-16 | Beth | C1542-02-IJ | Connextions, Centennial CO | 44736, DS3 no MD5 encyption |  | smartform 170758389 dnv I28753 IQBJ7B10 | 5397352 | P1927940 |  | 5066378 | 12288 | BCBKS4MF0001 | 24/HFGS/601609//MS Demarc: 1st floor telco room top of south wall port 2 tagged not extended |  |  | 2012-06-14 |  | bpdd | 2012-07-06 | 2012-06-26 | UHGECC-65530 | matt_f_seymour@uhc.com 763-744-0840 | completed 7/20 with matt |  | 5/22- order sent to provisioning 5/31- ASR sent, pending response. 6/7- FOC date is 6/14. CDD is 7/6. 6/14- lec delivered, pending order closure 6/21- local loop delivered, but issue in our network this has a CFA mismatch at 85d site. oc48.fg:3 is not tied to CFA alv01:78..... oc48.fg:3 is actually tied to CFA alv01:99....either CFA needs corrected/change d or vz design needs changed....if CFA is to be kept at 85d site, then alv01:78 needs tied/designed to oc48.6k ring, sts 30....redispatch once clr or cfa has be en corrected, thx. working with provisioning to correct. 6/26- order completed, engineer infomed 7/19- activation failed, Matt had inside wiring checked, asked about opening a ticket. Melissa reached out to the install team leads to open a ticket. 7/20- Matt confirmed BGP is up.
2012-06-15 | SA disco | C1418-01-DJ | Edina MN | disconnect |  | NSPE0005547155 OQBJ77KZ | [5 empty] | bcbjkc6n0001 | [5 empty] | bpdd | 2012-07-12 | 2012-07-12 |  |  |  |  | disco completed on 7/12
2012-06-15 | SA disco | UIN04-02-DJ | Indianapolis, IN | disconnect |  | OQBJ74ZQ NSPE0005547158 | [5 empty] | BCBKGVP00001-008 | [5 empty] | bpdd | 2012-07-12 | 2012-07-12 |  |  |  |  | disco completed on 7/12
2012-06-25 | SA disco | CO035-01-DJ | Denver, CO | disconnect |  | NSPE0005580845 OQBJ8QTB |  | P1689583 |  |  |  | BCBJ6V210001 | [5 empty] | bpdd | 2012-07-24 | 2012-07-24 |  |  |  |  | disco completed 7/24
2012-04-23 | Melissa |  | Elk River move bcbklrsx0001 OC12 to SR 1 (llm8,06) SMF/LC |  |  | Smartform 165732752 NSPE0005420492 CQBJ631Z min- C33335 | 5381084 |  |  |  |  | bcbklrsx0001 | o3-nsb-llm8-0001 new dmarc The demark is as follows per the CCR remarks. At LLM8,06 I patchedslot 4 port 1 to our left patch panel port 8. (161.AJ.1L:8 VAM 161.OA.FB6A:8) | [11 empty] | 5/10- needed to re-submit smartfom. 5/17- order over to local provisioning 5/23- escalating with provisioning 5/31- pending CCR 1077973, smtmu card add on UHG roadm from nsb,04 and llm8,06 6/5- RFT on CCR is 8/5, but ops is targeting mid week on CCR install, which may move the dates forward 6/14- CCR completed testing, pending closure, set for 6/22, design complete and order stepped 6/20- new dmarc terminated and tested, pending ETE testing and order closure 6/28- DMARC is now moved. Engineer informed.
2012-06-13 | beth | PA012-05-CJ | Pittsburgh, PA | Change - encapsulation TO PPP |  | smartform 189619753 CDR201206210034 NSPE0005566600 CQBJ8VTP | 5440294 | P1614150 |  |  |  | BCBJX4PL0001 | [5 empty] | bpdd |  |  |  |  | completed with Anupam on 7/31 |  | 6/14- pending tin from Beth 6/21- smartform sent to beth. 6.29- order jepped back to OM, informed beth 7/5- order appears to be ready to schdule for the change. Melissa is confirming that. 7/12- encapsulation change is ready to schedule. 8/2- completed with Anupam on 7/31
2012-06-19 | Beth | UCA20-07-CJ | Chico, CA | 44736, Upgrade to full port and change encapsluation from frame to PPP |  | smartform 189617362 CDR201206190021 NSPE0005560009 CQBJ8TV2 | 5441000 | P1303599 |  | 1498153 | 10800 | bcbh35lm0001 | [5 empty] | bpdd |  |  | unitedhealthgroup-64532 | 0091 98100 59326 , Pradeep_yadav@uhc.com | completed with Anupam on 7/31 |  | 6/29- order jepped back to beth 7/4- order is with provisioning. 7/12- ASR went to the lEc to update records, pending response. 7/19- ready to schedule.
2012-06-25 | Beth | GA003-02-IJ | Duluth, GA | 44736, DS3 md5 encryption UHGVERbgpbqZyofa |  | smartform 189622995 CDR201206260061 NSPE0005580825 IQBJ8NH0 ATL I76622 | 5448172 |  |  |  | 22000 | BCBKTXGG0001 | [5 empty] | bpdd |  |  | unitedHealthgroup-65053 | 8607028284, Keith_mangene@uhc.com |  |  | 6/29- pending provisioning pickup 7/5- ASR sent to the LEC, pending response 7/12- pednign local CFA assisngment. CFA appeared to be in use. They are dispatching to check. 7/19- CFA issue appears to be resolved. Asked provisioning to send out a new ASR 7/26- new CFA issued, appears to be LOS acorss it. Techs are troubleshooting 8/2- escalated with provisioning on CFA issue 8/3- john asked for order to be cancelled, asked that beth supp toc ancel 8/9- order is cancelled
2012-06-26 | change | WA020 | mercer island Network Optimization | change PE to SEJGE03 |  | smartform 189625772 NSPE0005592367 CQBJ80PR | 5465377 |  |  |  |  | BCBKGWXD0001-0004 | [5 empty] | bpdd |  |  |  | masroor | completed with masroor on 7/31 |  | 7/5- pending tin from Beth 7/12- order with provisioning, pendign hyperlink issue 7/19- order is ready for pE change 8/1- completed with masroor on 7/31
2012-07-23 | Core | MD031-02-IJ | Baltimore, MD | pots |  | NSPE0005656663 | [6 empty] | Order Number: N4BH09637 Date Due: 2012-08-01 Billing Telephone Number: 4106630867 379 Circuit ID or Telephone Number: 410 663-0867 | [11 empty] | Order Number: N4BH09637 Date Due: 2012-08-01 Billing Telephone Number: 4106630867 379 Circuit ID or Telephone Number: 410 663-0867
2012-03-20 | B end | II523-02-IJ | Noida India | 20M subrate DS3 with encryption UHGVERbgpbqZyofa |  | 5051503 |  |  |  | 5078820 | 6144 | W0Z39249 | BTL 1356739S |  |  |  |  | bpdd | 2012-07-27 | 2012-07-11 | UnitedHealthgroup65078 | 919810059326, pradeep_yadavl@uhc.com | completed on 8/9 with pradeep. |  | 5/3- question with LCON, Melissa verified and informed that this should be delviered to the building dmarc 5/10- ASR sent to the PTT pending response. 5/17- ORDER HAS BEEN ACK BY PTT HOWEVER, THE COMMERCIAL APPROVAL IS PENDING FROM THEIR SALES. FOLLOW-UP STARTED WITH PTT -SALES 5/31- @ REC'D FROM ISD: THE CUSTOMER SITE IS NOT CONNECTED ON PTT NETWORK. PTT HAS TO CARRY OUT FIBER ROLL OUT, RACK/MUX INSTALLATION AND IT WILL TAKE ATLEAST 4-5 WEEKS. INDIA PTT DOESN'T OFFER PAID EXPEDITE BUSINESS CASE. This could be impacted if the customer site is not ready. 6/6- PTT is telling us RFS is July 9th. 6/14- OSP WORK IS IN PROGRESS AND FIBR WORK IS LIKELY TO COMPLETED BY THIS WEEKEND MUX,RACK ETC DELIVERED AT SITE AND PTT WILL ALIGN TEAM FOR MUX INSTALLATION INTEGRATION BY NEXT WEEK. 6/20- AS PER UHC TEAM (DINESH KANIAL) POWER SOCKETS WILL BE ARRANGED BY TOMORROW MORNING. 6/18- LOGICAL PROVISIONING OF LOCAL LOOP IS COMPLETE AND PTT WILL SCHEDULE INTERNAL WIRING TASK SHORTLY. ASKED MR. VIVEKANAND OJHA TO SHARE DISTANCE B/W TELCO RACK AND UHC ROUTER SO THAT PTT ENGINEER AND CABLE ARE ARRANGED . 7/5- LINE UNDER LOOPBACK TEST. RESULTS WILL BE AVAILABLE BY TOMORROW 7/9- ping testing complete. pending order closure. 7/11- order ready for activation, engineer informed.
2012-04-04 | Beth | AU507-04-CJ | Melbourne Australia | move from the existing MDF room on the 25th floor to the new MDF room on the 25th floor. |  | Smartform 159645036 NSPE0005333382 5076970 | 5329387 |  |  |  |  | 5 x E1 W0X83226 (port) W0X83221, (e1) | [12 empty] | 4/10- submitted to OM 4/19- pending Om submission 5/3- new Ecost needed, infomed Siva 5/10- escalating with Siva for ecost 5/17- e-cost received and forwarded to Beth and her backup 5/23- e-cost isn't approved, pushing siva to get it approved. 6/6- order submitted and accepted, moved to provisioning. 6/14- escalating for provisioning pickup 6/20- per LCON I AM AT THE UNDERSTANDING THAT THE VERIZON CIRCUIT HAS ALREADY BEEN MOVED? THERE WAS A TECH FROM OPTUS HERE EARLY LAST WEEK WHO MOVED OUR AT&T CIRCUIT, AND I HAVE CHECKED THE VERIZON CONNECTION HAS ALSO BEEN MOVED TO OUR NEW MDF 6/28- OPTUS DOES NOT HAVE AN ORDER TO MOVE THE CIRCUIT AND AS FAR AS OPTUS IS AWARE THE CIRCUIT HAS NOT BEEN MOVED. 7/5- followed up with Australia ops to find out how to proceed. 7/12- lcon not responding, askied for new lcon from john. 7/18- followed up with John on LCON 7/26- LCON is certain the circuit has moved 8/3- per john order should be cancelled. Sent note to beth to supp to cancel 8/8- order cancelled.
2012-04-17 | Beth | UNE50-06-IJ | Omaha, NE | DS3 with Dport and Dcar MD5 Encryption UHGVERbgpbqZyofa |  | smartform 160895973 CDR201204170036 NSPE0005364560 IQBJ6CCP | 5337473 | P1921529 |  | 5038937 | 6144 | BCBKSN110001 | 21.HFGS.071273..COXC DEMARC: 2nd floor co mmon room, cox wall rack 3 pos. MFP, Mod 1 Jack 1 | 0CSNKP |  | 2012-06-05 | 2012-05-30 | bpdd | 2012-06-04 | 2012-05-30 | Unitedhealthgroup-64756 | 0091 98100 59326, pradeep_yadav@uhc.com | per Keith this is completed. |  | 4/19- submitted to OM. 5/3- ASR sent, pending FOC C201205020090 5/10- FOC 6/5. As per COX lec, We had to order a 4100ES and DS3 cards to deliver this circuit 5/17- The ECD for services is 06-05-12; this date i s due to required equipment being ordered/installed, design, and timeline r equirements. Sherrie/COX Carrier Project Manager provided the timeline below: ETA Equipment Arrival: 3 Weeks ETA Equipment Install: 4 Weeks C ircuit Completion and ready for test/acceptance 5/23- still pending LEC delivery of 6/5 7/10- need to reschedule due to cabling problems. 7/19= pradeep reached out asking for a schedule since the circuit did not come up for him. Melissa asked if Monday 7/23 at 3pm central would work 7/25- issue with customer extended demarc. asked customer to provide hardloop at demarc but unable to get hold a tech onsite. They will reschedule the activation. 8/1- need to re-schedule with a vendor meet. Targeting 8/7 at 6pm Central. 8/7- per keith this is completed.
2012-06-08 | Beth | C1335-01-DJ | PHILIPPINES | disco |  | 5087290 | 5429175 |  |  |  |  | W0P23687 | [5 empty] | bpdd |  | 2012-08-08 |  |  |  |  | 6/14- pending tin from Beth 6.29- pending lcon validation; CALLED RAUL NUMBER AND ITS RING NO ANSWER. SENT EMAIL INSTEAD - RAULCABALLEGAN@TELETECH.COM 7/5- order sent to the PTT for disconnection, pending response from PTT. 7/11- STILL PENDING response from PTT 7/19- Melissa reached out to our Phillippines folks on the status of the PTT request. 7/26- ORDER STATUS MOVED TO CFOC PER ISD, DISC DATE IS 2 AUGUST 8/2- as of 9:30 am order isn't discoed yet 8/8- order is now disconnected.
2011-06-20 | Katrina | MN053-53-IJ | ELR - MDF800- DWDM access with card and path diversity | OC12 pip |  | CDR201106160057 MDF800 - 511 11th Ave - MZZ MIN A0031868 NSPE0004538383 IQBJV8VC MIN I32010 min A31868 (closed) | 4919226 | P1850147 |  | 2215739 | 300MB | BCBKLWN10001 | o3-73c-llm8-0004 Demarc MDF room 800VAM 361.BD.1l:8.tx 361.BD.1l:8.rx VAM 361.BA.FB6A:8.tx 361.BA.FB6A:8.rx server room 3 |  |  | 2011-08-11 |  | 2011-10-01 | 2011-09-23 | 2012-01-27 | UHG-IPTF VPN 65165 | 763-744-1921 or nick_heintzelman@uhc.com | activated with Steve on 8/14 |  | 6/27- capacity approved and order sent to Katrina. 6/30 tin submitted 7/8- had some issues with CDR. Order is now with OE. 7/13- re-send to provisioning with correct connector type 7/20- in LD provisioning, pending PIP port to be unblocked. NDMT C201107220013 7/27- order now progressed and is over with local engineering 8/4- node work being done 8/9- patch and labels completed at 511/20 and NSB04. 8/15- C201108120609 for testing 8/30- local tested well. 9/1- working on ld testing 9/13- Tested clean from 73c to a loop provided by NLI at the Z end 9/15-need dispatch at 511 to check cards, cards keep switching to protect. 9/21- need to redesign on the local side due to the protection isssue 9/29- card installed to resolve protection issue, pending ER closure and tcoms closure then we can re-test. 10/3- ER completed 10/5- issue with HS assignments, sent back to provisioning 10-/13- ETE testing is scheduled for today. 10/14 tested clean demark is 10.29.2.6/12 working and 10.29.4.6/12 protect 10/27- issue with local design on new roadm. ops and TI reviewing 11/2- design done SFPs located, sonet work done node work done at 511/20 11/8 - additional node work is set for today. 11/11- Local piece done, LD going through re-design 12/7- need testing tagging on ELR end. 12/14- local order closed, pending LD order closure. C201112190146 12/29- order is ready for testing, pushing CDD of 1/31. Asking install to test early. 1/26- LD mux scheduled for todday 1/27- order ready for activation 8/14- BGP established.
2012-05-03 | Beth | MA003-02-IJ | Cambridge, MA | 3072, 2xT1 |  | smart form 165475118 NSPE0005416049 IQBJ607J re-issue IQBJ673J | 5379198 | P1927288 |  | 5062446 | 1280 | BCBKS00R0001-0002 | 95.HCGS.445175..NE DEMARC LOC: FLR 10,RM tel,TEL CLOSET ,RJ48X,LP N,CAB N,JCK e,JCK e, 95/HCGS/445176 /NE DEMARC LOC: FLR 10,RM tel,TEL CLOSET ,RJ48X,LP N,CAB N,JCK w,JCK w, |  |  | 2012-06-05 | 2012-06-05 | bpdd | 2012-06-12 | 2012-06-05 | unitedhealthgroup-65076 | 715/841-7731, sonja_d_mroczynski@uhc.com | 8/15 sonja said it's active |  | sent to OM on 5/4 5/10- OM created tin, pending oS submsision 5/17- Cancel and re-issue request forwarded to OE. Provided capacity (CFA and SCFA) as signed by the system has a different Sales City, searched CAMEO for a valid 3h c apacity for the state of this order but the CFA's for BST is under different POP 5/23- FOC for 6/5 6/6- order ready for activation, engineer informed. 8/14- activation failed, Telco ticket 2012081422631 - to have tech dispatch do a head to head test on the circuit 8/15- per Sonja circuit is active.
2012-08-02 | Melissa | C1495-05-CJ | Pittsburg, PA | change ASN | [7 empty] | BCBJ8FDG0001 | [5 empty] | bpdd |  |  | UHG-Ecc- change to 65410 | (763)553-4895 john_bremseth@uhc.com | scheduled 08/09/2012 6:00 PM Central Time |  | completed.
2011-09-07 | B end- SOF | UK526-04-IJ | London, UK (optum) | 8Mb Ethernet |  | 4969565 |  |  | 8mg | 3965100 | 2048 | W0Z04078 | ETHC01501482/ETHA01501483/ONEA308351 dmarc SERVER/COMMS ROOM IN RECEPTION AREA. |  |  | 4/ |  | bpdd | 2012-05-04 | 2012-05-18 | UnitedHealthGroup - 65160 | (763) 744-1886, steve_betsinger@uhc.com | requested 8/23/2012 12:30:00 PM Central Time, bridge will be 866-819-9840 pcode 3365052. |  | 1/12- pending ASR. 1/20- tail ordered/bt/openreach 1/26- pendng access for site survey 2/2- contact changed to SHAZAD_ASGHAR@UHC.COM 044 0162858733 passed info to BT 2/10- FOC date is March 13th 3/15- FOC date pushed out THE DELAY IN THE DELIVERY OF YOUR ORDER FOR ETHERWAY WITH SERVICE ID ETHA01501483 BEING PROVIDED UNDER ORDER NO 1-10507754505 HAS NOW BEEN RESOVLED. THE DELAY WAS DUE TO ACCESS FOR FIBRE REQUIRED. YOUR NEW COMPLETION PLANNED DATE IS NOW 12/04/2012 AND CONTRACTUAL DELIVERY DATE IS NOW April 12th, 2012 4/11- pending tail delivery for 4/12 4/17- BT could not deliver, they could not get a hold of Shazad, correct number passed to BT, (01628 407 507), pending new date from BT 5/3- PASSED THIS ON TO OPEN REACH FOR THEM TO ADVISE WHAT EXACTLY HAPPENED IN THIS INSTANCE. OPEN REACH HAVE ADVISED THAT THE FIBRE WORKS HAVE BEEN COMPLETED AND CIRCUIT IS NOW READY FOR FIT AND TEST, SO THE DMU SHOULD BE IN TOUCH WITH THE SITE CONTACT TO MAKE THE NECESSARY ARRANGEMENTS. 5/10- Fiber works have been completed and BT has passed to the fit and test team, who should be reaching out to the local contact to schedule a final test appt. per Shaz they delivered the circuit yesterday 5/16- AW LOCAL END TEST / TASK SCHEDULED ON 17TH OF MAY 2012 5/18- order ready for activation
2012-07-18 | SA disco | CT003-02-DJ | Windsor, CT | disconnect |  | NSPE0005642038 OQBJ9FNW | [5 empty] | BCBKR92H0001-8 | [5 empty] | bpdd | 2012-08-20 | [5 empty] | 7/19- order sent to SA disco, assigned. 7/23- disco is due on 8/20 8/23- disconnect completed
2012-06-04 | Beth | CA049-02-IJ | Carlsbad, CA | 3072 2xT1 MD5 UHGVERbgpbqZyofa |  | smartform 178909481 NSPE0005507078 IQBJ7T3D SND- I18508 | 5418849 | P1931591 |  | 5081963 | 1280 | BCBKTCF80001-0002 | 19/HCGS/609194//PT DEMARC LOC: NIU @ 1.1 SHELF 1 SLOT/JK 7 19/HCGS/609195//PT DEMARC LOC: NIU @ 1.1 SHELF 1 SLOT/JK 8 |  |  | 2012-07-19 | 2012-07-20 | bpdd | 2012-07-26 | 2012-07-23 | UnitedHealthGroup-65068 | 763-744-1575, daniel_j_skripka@uhc.com |  |  | 6/4 submitted to OM 6/7 tin created, pending om submission 6/13- FOC date of 6/22 6/28- : spoke with Debbie,there was no facilities on the designated mux locati on, they are working with the Lcon to determine a new location.End user is aware of t he issue. they need a new CFA and a supp for new due date 7/5- mux should now be complete. Redispatching the LEC. 7/12- supped asr to CHANGE LCON TO JOHN BATIS: 619-665-4339. JBATIS@BINGHAM-CONSTRUCTION.COM. ALSO, PLEASE PUSH THE DUE DATE TO 7/30/2012 7/19- LEC FOC for 7/19, LEC had not delivered as of 1pm Central. Commited date of 7/26 7/23- order ready for activation, engineer informed.
2012-06-26 | Beth | CA049-06-IJ | Carlsbad, CA | 4xT1, 6144 |  | smartform 189625784 NSPE0005592279 IQBJ8R29 | 5455231 | P1936583 |  | 5095229 | 3072 | BCBKT06Y0001 | 19/HCGS/609723//PT 19/HCGS/609724//PT 19/HCGS/609725//PT 19/HCGS/609726//PT Ckt1-mpoe, 1.1 jack10,RJ48C tagged not ext. Ckt1-mpoe, 1.1 jack8, RJ48C tagged not e xt. Ckt1-mpoe, 1.1 jack7, RJ48C tagged not ext. Ckt1-mpoe, 1.1 jack9, RJ4 8C tagged not ext. |  |  | 2012-07-20 |  | bpdd | 2012-07-27 | 2012-07-26 | UnitedHealthGroup-65068 | 763-744-1575, daniel_j_skripka@uhc.com |  |  | 7/5- aSR sent pending FOC 7/20 FOC date 7/20 and 7/27 commit 7/26- AT&T missed delivery, mised ticket B201207200076 8/2- order ready for activation 7/26, engineer informed.
2011-11-30 | B end | CN502-05-IJ | Dundas, Ontario | 10mbps Ethernet |  | 5028737 - PORT 5028738 - ACCESS |  |  |  | 5079120 | 1536 | W0Z29749 (port) W0Z29748 (access) | 01/KFFN/100013/000/ROG Demark Main Floor Telco Room Raisecom Media Converter | [5 empty] | 2012-07-16 | 2012-06-14 | UnitedHealthGroup- 65154 | 920-661-6798, daniel_l_bartlett@uhc.com | 8/31, per Terry B the circuit is up and operational. |  | SOF sent to John on 12/9, updated SOF on 1/12. 2/16- SOF recieived 3/7- pending order number information from B end. 3/21- order created and sent to provisioning 3/29- note sent to LCON Matt, from Justin Ryan at VZ. I KNOW YOU ALREADY APPROVED THIS SITE ADDRESS, BUT THE TELCO IS COMING BACK REPORTING A DESCREPENCY... PLEASE CONFIRM THAT THE ADDRESS IS 4 INNOVATION DR., DUNDAS AND NOT FLAMBOROUGH. I REALIZE THEY ARE IN THE SAME AREA BUT WENEED TO CONFIRM THAT IT IS IN FACT DUNDAS. 4/11- order sent to PTT for local loop, pending FOC. 4/12- FOC date May-23 5/29- Telco construction delay has pushed the FOC date out to May-30. 5/31- pending update on telco delivery 6/4- 6/04 - Circuit delivered May-31; Demark Main Floor Telco Room Raisecom Media Converter; estimated Verizon hand-off date Jun-7 6/6- pending order closure 6/14- order still not closed, I think we can activate it, but Melissa is checking with the B end. 6/20- order closed and ready for acitvation. 7/5- actvation failed, we will need to re-schedule with Rogers on the phone. 7/11- checking up to see where Rogers is with this downgrade. 7/18- Rogers is done with downgrade and order is ready to schdule again. Reached out to Dan/Terry to re-schedule. 8/31, per Terry B the circuit is up and operational.
2012-06-28 | Beth | C1545-01-IJ | Warminster, PA | 44736, DS3 no MD5 encyption |  | smartform 189625798 CDR201206290014 NSPE0005592447 IQBJ8R1H | 5456011 |  |  | 5092026 | 128 | BCBKT0540001 | 11/HFGS/107467//PA DEMARC: 1st floop main telco room, t3 shelf #1 slot #2 Extended (Y/N): 1st floor server cage cabinet #2 Tagged (Y/N): tageged with both ID |  |  | 2012-08-02 |  | bpdd | 2012-08-16 | 2012-08-22 | UHG-ECC-65408 | 763-553-4895 john_bremseth@uhc.com | requested for 8/30 at 3pm Cetnral. |  | 6/29- submitted to Beth 7/5- order with provisioning, pending ASR 7/12- FOC for 8/2 8/2- LEC delivered, pending order closure 8/8- esclaating for order closure 8/15- created DMUX to have the terminal unwire the LEC facilities from the WBDXC port. 8/23- order ready for activation, engineer infomed.
2012-06-29 | Beth | TX017-05-IJ | Corpus Christi | 3072, 2xT1 md5 encryption UHGVERbgpbqZyofa |  | smartform 189625806 NSPE0005592862 IQBJ8R0G | 5455233 | P1936558 |  | 5092024 | 1536 | BCBKT05T0001-0002 | 34/HCGS/625781//SW DEMARC LOC: 9TH FLOOR TELCOM RM CAB 1 SLOT 3 34/HCGS/625782//SW DEMARC LOC: 9TH FLOOR TELCOM RM CAB 1 SLOT 4 |  |  | 2012-07-12 | 2012-07-10 | bpdd | 2012-07-19 | 2012-07-10 | UnitedHealthGroup-65052 | 763-744-1847, donald_r_osborn@uhc.com | completed with Don on 8/23 |  | 6/29- submitted to Beth 7/5- 7/12 FOC date, commit date is 7/19 7/12- order ready for activation, engineer informed.
2012-07-23 | Beth | C1546-02-IJ | Harrisburg, PA | 1536, T1 no encryption |  | smartform 189643336 NSPE0005655451 IQBJ9QR3 | 5491115 | P1942955 |  | 5135083 | 128 | BCBKVGWH0001 | 13/HCGS/552577//PA DEMARC LOC: 1st flr util rm, shf 1, slt 2, pos 2 rj48c tgd nt xtnd |  |  | 2012-08-13 |  | bpdd | 2012-08-20 | 2012-08-13 | uhg-ecc- 65491 | 7637443196 justin_smith@uhc.com | activated with justin on 8/.29 |  | 7/23- submitted to Beth. 8/2- FOC 8/13, commit date is 8/20 8/15- order closed. Engineer infomed. 8/29- activated with Justin.
2012-08-03 | SA disco | CA016-02-DJ | irvine CA | disconnect |  | NSPE0005698756 OQBJ9009 | [5 empty] | BCBKS2J60001-4 | [5 empty] | bpdd | 2012-09-04 | 2012-09-06 |  |  |  |  | disco complete 9/6
2012-08-07 | Beth | C1491-02-IJ | Neenah, WI | 44736, DS3 no MD5 encyption |  | Smartform 189676785 CDR201208080009 NSPE0005711107 IQBKBRBP | 5511154 | P1949068 |  | 5176944 | 3072 | BCBKVYD60001 | [5 empty] | bpdd |  |  | UHG-ECC- 65533 | 65533 |  |  | 8/9- with OM/OS 8/14- pending CDR lease approval, these can take up to 30 days. 8/28- TIN NOW SUBMITTED. 8/29- order sent to provisioning 8/31- john cancelled order, will resubmit with new address.
2011-06-20 | Katrina | MN053-52-IJ | ELR - MDF700- DWDM access with card and path diversity | OC12 pip |  | CDR201106220049 - MDF700 - 6182nd Ave - MWA NSPE0004538322 IQBJV8SL min I31943 (closed) min A31881 ER 2147565054 s/o 4886096 | 4917968 | P1850132 |  |  | 300MB | BCBKLRSX0001 | o3-nsb-llm8-0001 VAM 361.BA.FB6A:5.tx 361.BA.FB6A:5.rx Server room 3 | 0CPJVF | 2011-07-07 | pending |  | 2011-10-01 | 2011-09-23 | 2011-10-10 | UHG-IPTF VPN 65165 | 763-744-1921 or nick_heintzelman@uhc.com | per steve this is active and running as of 9/5 |  | 6/27- capacity approved and order sent to Katrina. 6/30 tin submitted 7/8- order over to local engineering 7/20- clarification with local that it needs to go to old system. NDMT C201107220023 to supp local order and step back for processing 7/27- local order now has correct information and is proceeding 8/16- stepped for node work, scheduled for 8/16 8/17- Per Joel, tech clr needs to be redesigned, prov working with joel on redesign 8/25- redesign not needed. Node work being done today. 9/1- node work completed 9/7- stepped for ETE testing. scheduled for 9/8. Opened ndmt C201109080112 9/15- redesigned to correct MDF. Pendign dispatch 9/16- node work scheduled for 9/19 9/21- local piece completed, pending a network groom on the LD network that we can't do until 9/30. I am pushing to have patches done that same night, but we won't hit the 10/1 date. 9/29- groom will be done tonight and ops will wire mux tomorrow. 10/5- NDMT ticket C201110060040 to better the commit date. 10/10- ready for activation, engineer informed. 8/14 tag and locate requested. 8/22- still trying to prove the path
| Beth |  | Quality metric | Customer is using existing Cisco 1841 from old circuit u256245 and will be installing 20M Internet Ethernet � Tiered |  | u318313 SAR ID: 1-1J23IMB Conf code: 021JND-0011 Inquiry ID: 0030644VZTSAXXX f&e 5108122 | 5441145 | P1938004 (in) |  |  |  | u318313 | [5 empty] | bpdd | [6 empty] | 7/9- order pre-sales approved, beth can now submit tin 7/19- pending SAR from Matt 7/24- SAR came back Special Construction required: yes Special Construction case: 2012-620266 Special Construction cost: $3781 7/26-asking beth to supp order 8/2- ASR sent 8/9- pending FOC 8/23- pending approval of construction charges. 9/6- order is cancelled, customer will not pay chargees
2012-06-21 | SA disco | MN053-10-DJ | ELR 1Gig ISP (elk river) | disconnect |  | NSPE0005567093 OQBJ9H5S/min-O27551 | [5 empty] | U248769 | [6 empty] | 2012-07-05 | [5 empty] | 6/29- escalating for a response 7/5- This was issued with dd 7/21 order 21879644 7/25- billing ceased on 7/21, disco prov will start on 7/27 8/3- disco orders created, pending being worked 8/9- x-conns being removed. Pending order closure 8/14- still pending order closure 8/23- order closed
2012-07-24 | Beth | USP02-02-DJ | BARCELONA SPAIN | disconnect |  | 5121084 (access) 5121083 | 5508912 |  |  |  |  | E1- MCI - W0S09721 E1- MCI - W0S09723 | [5 empty] | bpdd | 2012-09-06 | [5 empty] | 7/25- sent to beth 8/14 pending lcon from John. 8/23- order over to provisioning. 8/29- x-connects removed, pending order closure 9/6- asked provisioner to close orders. 9/6 disco completed
2012-08-10 | SA disco | UNE50-05-DJ | Omaha NE | disconnect |  | NSPE0005723416 OQBKBCGZ | [5 empty] | BCBJHKKM0001-4 | [5 empty] | bpdd | 2012-09-10 | [5 empty] | disco completed on 9/12
2012-08-16 | beth | C1491-05-IJ | Neenah, WI | 6144, 4xT1 |  | smartform 189681288 NSPE0005746509 IQBKBGHM | 5520843 | P1947562 |  | 5164961 | 1536 | BCBKVSDT0001 | 41/HCGS/123194//WT 41/HCGS/123195//WT 41/HCGS/123196//WT 41/HCGS/123197//WT |  |  | 2012-08-31 |  | bpdd | 2012-09-10 |  | UHGECC- 65533 | 65533 |  |  | 8/16- submitted to beth 8/23- order is with provisioning and they are designing. FOC date 8/31 9/6- order installed, john will issue disco and we will order to new address.
2012-08-17 | SA disco | UOK01-02-DJ | OKLAHOMA CITY OK | disconnect |  | NSPE0005751510 OQBKBGYQ | [5 empty] | BCBJS1200001-6 | [5 empty] | bpdd | 2012-09-17 | [5 empty] | 9/20 disco complteted
2012-08-17 | SA disco | C1520-04-DJ | Los Angeles, CA | disconnect |  | NSPE0005751472 OQBKBL1Y | [5 empty] | bcbkfjml0001 | [5 empty] | bpdd | 2012-09-13 | [5 empty] | 9/20 disco complteted
2012-08-28 | Beth | C1203-03-IJ | Troy, MI | 44736, DS3, no MD5 encryption. |  | smartform 189688518 CDR201208280041 NSPE0005789251 IQBKBS80 | 5536167 | P1949590 |  | 5180102 | 128 | BCBKVY7H0001 | [5 empty] | bpdd |  |  | UHG-ECC-TCW- 65202 | 763/744-1587 Leon_L_Betterman@uhc.com |  |  | 8/28 submitted to Beth 9/6- order sent to provisioning, pending pick up. 9/14- ASR came back saying LCON wants it on their own SCID. Melissa asking John about that 9/14- tin is now supped to cancel.. 9/20 - order cancelled.
2012-08-31 | Beth | C1550-02-IJ | Columbia, SC | 44736, DS3 |  | smartform 189693036 CDR201209040024 NSPE0005810873 |  |  |  |  | 9216 | [6 empty] | bpdd |  |  | UHG-ECC-TCW- 65203 | 763/744-1587, Leon_L_Betterman@uhc.com |  |  | 9/4- sent to Beth. 9/5- John sent a cancel, will re-issue with CFA 9/20 oder cancelled.
2012-09-14 | Core | UMD17-02-DJ | College Park, MD | disco pots |  | NSPE0005853154 | [18 empty] | 4732 Cherry Hill Rd., College Park, MD 20740 was already disconnected per Request Id: NSPE0005807879. The order number is D4BH12493 and was completed on 09-11-12.
2012-09-14 | core | UMD91-02-DJ | Baltimore, MD | disco pots |  | NSPE0005853106 | [11 empty] | bpdd | [6 empty] | Telephone number 410 685-3820 was disconnected on 09-11-12 with Request Id: NSPE0005807876. Your order confirmation is provided below. Order Number: D4BH12508 Date Due: 2012-09-11 Billing Telephone Number: 410685073 209 Circuit ID or Telephone Number: 410 685-3820
2012-05-03 | Beth | IL004-02-IJ | Chicago, IL | 6144, 4xT1 |  | smartform 165439872 NSPE0005425198 IQBJ62V8 | 5379182 | P1926350 |  | 5057098 | 2000 | BCBKS1FG0001-0004 | /HCGS/640147//LB DEMARC LOC: LOWER LEVEL #5 NETPOP, FIBER, SLT#5 /HCGS/640148//LB DEMARC LOC: LOWER LEVEL 5 NETPOP, FIBER, SLT#14 /HCGS/640149//LB DEMARC LOC: LOWER LEVEL 5 NETPOP, FIBER, SLT#16 /HCGS/640150//LB DEMARC LOC: LOWER LEVEL 5 NETPOP, FIBER, SLT#25 |  |  | 2012-05-25 | 1900-03-01 | bpdd | 2012-06-06 | 2012-06-01 | unitedhealthgroup-64943 | (763) 744-1575, daniel_j_skripka@uhc.com |  |  | sent to oM on 5/8 5/17- ASR sent to LEC, pending response 5/23- pending LEC FOC of 5/25. 5/31- LEC delivered, but we only have dmarc infor for 2 of the 4. opened ticket B201205310048 6/6- order ready for activation, engineer informed.
2012-05-11 | Beth | MN011-05-IJ | Chaska OC3 PIP Ecc- line side protected SMF/LC connector MDF 800 |  |  | Smart form 168977725 NSPE0005439120 CDR201205230051 IQBJ7K89 min - I33378 (closed0 | 5396008 |  |  | 5077160 | 80Mb | BCBKS7V90001 | o2-73c-m6l7-0001 Space(SP) Chaska #2 Room MDF800 T7100 1.1.1:2.5.1 Demarc: 1st floor, MDF800, rack-aj807 panel fb3 jack 4 extended, Not extended, | [5 empty] | 2012-08-28 | 2012-08-23 | UHG-ECC 65462 | 763-744-2154 scott_moyer@uhc.com |  |  | submitted to OM on 5/11 5/17-pending tin from OM 5/29- CDR approved. Order submitted to OS. 5/31- order with oe for keying 6/6- order with local provisioning 6/14- pendgin CCR# 1081249 - pending capacity 511/m6l7,02 SMTU cards 6/.20- cards shipped RFT on this is 8/21 6/25- pedning expansion bay at 511 on the UHG ROADM. CCR 1080507. pending shipment 6/28- CCR 1081249 shipped for SMTU cards, following up with ops. Also pending 511 bay expansion. 7/12- melissa following up on Bay 7/18- tellabs bay has arrived, asking for anticipated install date and rft date 7/19 CCR 1081249 SMTMu card add as 511,20 and M6L7,02 The cards are installed at M6L7,02 (Chaska) but is waiting on CCR 1080507 at 511. This supports pending order: TCOMS i33378- we have to verify if we have the side panels. 7/24- Dan Schmidt out in 8 hrs today on building the new cabinet. He assembled it and has it in place for mounting. As we cannot core drill till after hours I will stay tonight and mount the cabinet. Activities left: Mount bay, Run and terminate 3 A power and 3 B power feeds to include after hour Mastars for PDF work, Build Timing/Control cables, Build out fiber guide, Install NIC cables from Roadm to Vams for future ckts, Provision new bay In software, and test. 7/26- Have rack mounted in place and have started on power. Hope to have power to bay by end of week. 8/1- asked phil for update on Bay 8/9- bay is complete. SMTU cards are installed, order designed and sent for node work 8/14- node work being done around the ring. 8/22- ETE testing scheduled for 8/22 8/23- order ready for activation, engineer informed.
2012-06-25 | Beth | MD021-02-IJ | Towson, MD | 10M ethernet type 2 (vzt) access with md5 encryption UHGVERbgpbqZyofa |  | SAR confirmation code is: 021ACO-001 inquiry id is: 0029994VZTSAXXX smartform 189628549 NSPE0005612748 IQBJ828V (EA) IQBJ834D (port) | 5467801 |  |  |  | 3072 | EDBKT6WG0001 (EA0 BCBKT67P0001 (port) | 38.KEGS.301387..CM SUITE ND FL DATA RM RELAY RACK TAGGED W ID REPAIR |  |  | 2012-09-10 | 2012-09-10 | bpdd | 2012-09-17 | 2012-09-19 | unitedHealthgroup-65067 | 715-841-7731, sonja_d_mroczynski@uhc.com | activated on 9/19 |  | 6/26- pending inetinquiry from matt. 7/5 pending info from Siva and Matt 7/9- submitted to Beth. 7/12- order with provisioning, pending ASR. 7/16- Per Jim Meyer they need this by the end of August- 7.19- melissa spoke with the engineer and they had not yet heard back on the site requrements. 7/26- interduct is placed. but we need to know the length. Joe is workng wtih commnet on that. 8/2- FOC is for 9/10, trying to better that. Construction eccd is 8/27, pending Jumper, trying to find out when jumper will arrirve. 8/9- unable to better due date. Received notice from Regional and was advised that outside plant engineering (OSPE) has already released the engineering work order (EWO) to construction and has provided an estimate completion date (ECD) of the build of 8/27/12. 8/14- Received notice from Regional and was adv ised that the ECCD for 8/27/12 remains firm and no DD improvement is possib le until build completes. Was advised further to have ticket stepped to Reg ional after the EWO to check if they can better the DD 8/23- Build still in progress and is on track to meeting the ECCD of 8/27/12. Will pursue better DD improvement after build completes. 8/28- checking to see if build completed. 9/6- build completed and core is attempting to delviery circuit by 9/7 9/13- lec delivered, pendinng cpe shipment and dispatch. Thank You. Your ticket number is: C201209130055 9/19 order completed and activated.
2012-06-25 | Beth | UIL11-05-IJ | Chicago, IL | 3072, 2 x T1 md5 encryption UHGVERbgpbqZyofa |  | Smartform 189622954 NSPE0005580730 IQBJ8NGK cfo I0160443 (clsd) | 5448162 | P1935885 |  | 5091187 | 1280 | BCBKTXF00001-0002 | 13-BVT-BJK-0010 and 13-BVT-BJK-0011 The demarc will be the 18th floor netpop pairs 10 and 60 of 100 to the ATT netpo p. |  |  | 2012-07-16 |  | bpdd | 2012-07-23 | 2012-08-03 | unitedHealthgroup-64583 | 763-694-7370, masroor_khan@uhc.com |  |  | 6/29- pending provisioning pickup 7/5- on-net FOC for 7/16, or commit date is 7/23 7/19- local loop delivered, pending testing and order closure. Opened loop testing ticket B201207190054 8/2- circuits not testting clean working with telco on testing head to head. 8/9- order ready for activation, engineer informed.
2012-07-11 | Beth | CA165-05-CJ | Sacramento, CA | Upgrade to 4xT1, 6144 Gold CAR to 3072 |  | smartform 189630593 NSPE0005620716 IQBJ8302 OQBJ86CSA | 5471816 | P1639971 (out) P1939112 (in) |  |  | upgrade to 3072 | BCBJ1CXV0001-0002 (out) BCBKT6550001-0004 (in) | 18/HCGS/563783//PT DEMARC LOC: 1.1 MPOE SHELF 3X9 RJ48C HANDOFF DEMARC LOC Continued: HANDOFF PANEL 1 POS 1 18/HCGS/563783//P DEMARC LOC: 1.1 MPOE SHELF 3X10 RJ48C HANDOFF DEMARC LOC Continued: HANDOFF PANEL 1X2 |  |  | 2012-08-03 |  | bpdd |  |  | UnitedHealthGroup-65185 | 91 - 98100 59326, pradeep_yadav@uhc.com | completed on 9/26 |  | 7/12- order submitted to OE. 7/19- order in provisioning 7/26- FOC for 8/3 on new loop 8/9- order ready for hotcut. Engineer informed.
2012-08-24 | Beth | MN022-02-IJ | Minnetonka, MN | 4 x T1 6144 with MD5 UHGVERbgpbqZyofa |  | smartform 189689262 NSPE0005793992 IQBKBVW8 | 5539036 | P1949810 |  |  |  | BCBKV0PH0001 | [5 empty] | bpdd |  |  | UnitedHealth Group-65049 | 764-744-1556 john_l_rothstein@uhc.com |  |  | 8/29- sent to Beth. 9/6- order to provisioning, pending ASR 9/13- john requested that order be cancelled. 9/20- followed up with Beth on cancellation 9/27- order verified as cancelled.
2012-05-03 | Beth | OH085-05-IJ | Canfield, OH | 3072, 2xT1 |  | smartform 165154951 NSPE0005412877 IQBJ606P | 5379224 | P1926130 |  | 5056436 | 640 | BCBKS00D0001-0002 | 92/HCGS/210292//OB DEMARC LOC: ATT CAB SHELF 1 SLOT 6 OF 14 92/HCGS/210293 DEMARC LOC: ATT CAB 1 SHELF 1 SOT 5 OF 14 |  |  | 2012-06-01 | 2012-06-01 | bpdd | 2012-06-06 | 2012-06-01 | unitedhealthgroup-65136 | (763) 744-2077, robert_a_benson@uhc.com |  |  | Sent to OM on 5/3 5/10- OM created tin, pending oS submsision 5/17- LEC FOC 6/1 6/6- order ready for activaion, engineer informed.
2012-05-16 | Beth | C1543-02-IJ | Connextions, Irving TX | 44736, DS3 no MD5 encyption |  | Smartform 170750441 IQBJ7BRF | 5397652 | P1927877 |  | 5066318 | 10000 | BCBKS4JF0001 | 12/HFGS/303884//GTEC Demarc info: 1st floor data room, verizon equ ip rack, t3 dsx shlf, jack 5 of 12; |  |  | 2012-09-13 | 2012-09-20 | bpdd | 2012-09-24 | 2012-09-20 |  | matt_f_seymour@uhc.com 763-744-0840 | UHGECC-65529 |  | 6/26- LEC FOC isn't until 9/17. This project entails a substantial build with 2700 ft of fiber and the placement of a mux 6/28- we are trying to better the FOC but WE CAN NOT BETTER THE DATE AT THIS TIME** THERE IS AN OSP WORK ORDER PLACE & SPLICE 3000 FEET OF FOC. TENT EISD 8/29. THERE IS A COEI WORK ORDER TO INSTALL FW4100 AND DSX PANEL AT CUST ESTIMATED COMPLETION DATE IS 9/6. THERE IS ALSO A COEI WORK ORDER THAT IS NID ONLY AT PREMISE ESTIMATED EISD IS 9/6. 7/12- Notes detail that construction has not started and no material has been received on any of the WO's.. melissa is asking that this be added to the escalation list. 7/19- this order is just being processed and material requested. We have 0 of 43 items received with a material need date of 8/8. 7/26-12 wo iss 6/21 OSP wo 5639-3F0A0HB apprvd 6/22, ready for splicing. COEI wo 5639-3TNA0TA WOAPP 7/9 MND 8/8 pending matl 1/43 items rcvd, ssd 7/26-8/8 4 pics no info, EISD TBD. COEI wo 5639-3T0A0EF NID ONLY job. 8/1- The status has not changed. Latestnotes in AAIS: "wo iss 6/21 OSP wo 5639-3F0A0HB apprvd 6/22, ready for splicing, ECD TBD. COEI wo 5639-3TNA0TA WOAPP 7/9 MND 8/8 pending matl 2/48 items rcvd, ssd 7/26-8/8 4 pics no info, EISD TBD. Dates cannot be improve d at this time. 8/9- Current status; Work Order 5639-3F0A0HB ready for splicing, Estimated Ccompletion Date To Be Determined. COEI .wo 5639-3TNA0TA WOAPP pending matl 22/48 items rcvd, ssd 7/26-8/8, EISD TBD 8/13- OSP wo 5639-3F0A0HB splicing 8/9. COEI wo 5639-3TNA0TA WOAPP, pending m atl 47/48 items rcvd, Estimated In-Service Date To Be Determined pending co mpletion of Outside Plant WO 8/23- OSP WO complete 8/10. COEI WO has an expected completion date of 8/30. 8/28- OSP WO complete 8/10. COEI WO has an expected completion date of 8/30. 9/5- CLR issued and dates improved to proper intervals: WOT - 9/10 PTD - 9/12 DD - 9/13 9/13- there was an issue with the jack, order redesigned and ASR sent. Gave core the new assignment info . Tyring to push this for completion 9/20 - FOC date today (due to redesign to new jack), we ping tested to the new CFA
2012-06-19 | Beth | TN040-05-CJ | Knoxville, TN | 6144, 4xT1 Add 1 T1 to existing 3xT1 bundle |  | Smartform 189619857 NSPE0005591940 IQBJ8VM1 OQBJ8YDT | 5453595 | P1588204 (out) P1937320 (in) |  |  |  | BCBJVTLR0001-3 BCBKT19W0001-0004 (in) | T2/HCGS/836866//SC Demarc info: 2FLR TLCO RM, MM1, POS9¦JT |  |  | 2012-09-06 |  | bpdd |  |  |  | masroor | completed with masroor on 9/28 |  | 6/29- tin submitted to beth 7/5- order is with OE 7/12- provisioning is designing, pending Asr 7/19- FOC for the new loop is 7/25 7/26- LEC did not deliver, missed loop ticket of B201207260055 8/2- tech has no access at the site the tech has been dispatched 7/25, they try to contact the lcon but the lcon cannot be reached. supped and new FOC date is 8/16 8/20- john requested lcon change. 8/23- Reissue PON IQBJ8VM1604RMB04 sent with a new due date and LCON per customer. 8.28- new lEC foc is 9/6 9/20- order ready for hotcut. Enginner informed.
2012-06-29 | Beth | UNJ22-05-CJ | Newark, NJ | upgrade to 7680 5 xT1 |  | smartform 189628595 NSPE0005606364 IQBJ8YK5 OQBJ817T | 5465423 | P1438023 (out) P1938004 (in) |  | 1601821 | upgrade to 3072 | BCBJGR0Y0001-4 (out) BCBKT30W0001-0005 (in) | /HCGS/474791//NJ DEMARC LOC: BSMT telc,RM bsmt,TEL RM ,RJ48C,LP Y,CAB N,SHELF 1,POS 24, DEMARC LOC Continued: |  |  | 2012-08-29 |  | bpdd | 2012-08-03 |  | unitedhealthgroup-65447 | 763-694-7370, masroor_khan@uhc.com | hotcut completed 8/1 with masroor |  | FOC for new loop is 7/27 8/2- tech missed delivery due to no ID, supping for re-dispatch. 8/15- new FOC is 8/29 8/28- order is ready for upgrade. Engineer informed.
2012-05-11 | Beth | UMD97-02-IJ | Baltimore, MD | 100 mg type 2 Ethernet Handoff 100Base-TX (FastE) RJ45 jack type, CAT6 shielded copper cable |  | SAR 020QEL-001 Smart form 174043732 NSPE0005471401 Inet pEr 06051201 IQBJ7XC4 (port) IQBJ7T8N (EACS) | 5399367 |  |  | 5083631 | 30000 (30 mg) | BCBKTDL10001 EDBKTCKH0001 | 38.KFGS.300334..CM DEMARC: data point date center relay rack r2 c1 4 position 37 not extended BEAS installed at United Health cage in main data room. Rad installed in cabinet J-2, la beled. |  |  | 2012-08-16 |  | bpdd | 2012-09-05 | 2012-09-05 | unitedhealthgroup-65071 | 715/841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 10/2 |  | 5/17- pending approvals from matt 5/22- SAR received, order sent to OM. 5/23- pending PER, informed matt 6/6- PER provided and order is with om. 6/14- ASR sent, LEc ENGINEER HAS CONTACTED LCON, PENDING LCON RESPONSE/AVAILABILIT ON HOLD FOR SITE SURVEY NO SUP REQUIRED AT THIS TIME 6/20- still pending site survey, per Jim nobody from LEC has called him. opened ticket C201206200071 6/21- engineer is waiting for the customer to callback. Please have the LCON contact Eng Otto Hart at 410-393-0022. 7/11- ASR rejected saying jim has not contacted otto, Melissa Called Jim and left a vmail to confirm. Spoke to Dave. Need to see if he is the lcon 7/18- Jim responsed and said Dave should be the LCON order is being supped. 7/26- Dave and Otto have spoken. ASR has not been supped yet. Escalating for supp on ASR. 8/1 ASR has been supped 8/8- FOC is for 8/16 8/22- LEC did not deliver, opening ticket for missed loop 8/28- LEC delivered, dispatch opened for BEAS install 9/6- order ready for activation, engineer informed.
2012-03-28 | Beth | MN011-02-IJ | Chaska Internet-add protection |  | Bid ID 158903 IP Capacity Inquiry #8SJLC9XG Smartform 174515549 NSPE0005474823 CQBJ70L0 / min-c32849 | 5399933 |  |  |  |  | u313034 | gx-73c-m6l7-0001 |  |  |  |  | bpdd |  |  |  |  | completed 9/27 with Jim |  | pending BID approval, following up with Matt on that. 4/27- bid approved, need smart form. Asked matt and Siva to work on that in melissa's absence. 5/10-smartform submitted to OM 5/17- pending tin from beth 5/31- pending OS submission 6/6- assigned to Alcinda in UUnet provisioning, 6/30- per local provisioning protection is done via the SFP cards that are in place. i am addressing that with engineering and ops 6/25- provisiong is understanding we need to add line side protection, SMTU cards needs to be ordered. Rudy is working with Bryan Brayman on that. 6/28- pending by in 511 for protection. bay is on backorder. 7/5- melissa asked about an update on the bay 7/11- pending update on bay. 7/18- Bay is in from tellabs, pending dates on project completion. 7/24- cabinet for bay is installed, Activities left: Mount bay, Run and terminate 3 A power and 3 B power feeds to include after hour Mastars for PDF work, Build Timing/Control cables, Build out fiber guide, Install NIC cables from Roadm to Vams for future ckts, Provision new bay In software, and test. 8/8- bay is addeded, pendign smtmu paired card add (511,20 and m6l7,02) . 1092534 is the CCR, pending shipment. 8/14- Cards shipped on 8/13 8/22- cards shipped, pending equipment sign off and installation by ops, due 8/24. 8/.28- cards are now scheduled for 8/30 9/6- escalating for install of cards. 9/13- cards installed, order now stepped to engineering 9/19- ready to scedule hotcut to add protection. Informed John. 9/26-requested for 9/27 completed 9/27 with Jim
2012-09-17 | Beth | CN502-02-DJ | DUNDAS ON | disconnect | 5142276 | 5573356 |  |  |  |  | W0W57103-6 | [5 empty] | bpdd | 2012-10-04 | 2012-10-04 |  |  |  |  | 9/17- sent to Beth to process TELUS ORDER#: D4340-6647-48-12 TELUS CIRCUIT#: 55DHXS224248000ABGT000 EFFECTIVE STOP BILLING DATE: OCTOBER 4, 2012 10/4 disco completed.
2012-09-19 | Core | TX142-03-IJ | , Boerne, TX - Wellmed | pots | NSPE0005868152 | [6 empty] | Order Number: I2636058 Date Due: 2012-09-28 Billing Telephone Number: 8302493419 |  |  |  |  | bpdd | [6 empty] | Order Number: I2636058 Date Due: 2012-09-28 Billing Telephone Number: 8302493419
2012-09-28 | core | C1361-03-DJ, | HARRISBURG PA | disconnect | NSPE0005909468 | [5 empty] | POTS# 717-671-6931 | Order Number: I2636058 Date Due: 2012-09-28 Billing Telephone Number: 8302493419 |  |  |  |  | bpdd | [6 empty] | Order Number: I2636058 Date Due: 2012-09-28 Billing Telephone Number: 8302493419
2012-08-31 | SA disco | C1380-01-DJ | Cincinnati, OH | disconnect | NSPE0005807744 OQBKB182 | [5 empty] | bcbjdm5s0001 | [5 empty] | bpdd | 2012-10-04 | 2012-10-08 |  |  |  |  | disco completed 10/8
2012-08-31 | SA disco | CA049-02-DJ | CARLSBAD CA | disconnect | NSPE0005807750 OQBKB19W | [5 empty] | BCBKTCF80001-0002 | [5 empty] | bpdd | 2012-10-04 | 2012-10-08 |  |  |  |  | disco completed 10/8
2012-09-07 | SA disco | C1491-03-DJ | NEENAH WI | disconnect | NSPE0005825887 OQBKB4DS | [5 empty] | BCBKVSDT0001-0004 | [5 empty] | bpdd | 2012-10-04 | 2012-10-08 |  |  |  |  | disco completed
2012-09-14 | Beth | UK526-03-DJ | LONDON UK | disco | S/O: 5135988 5135989 | 5558110 |  |  |  |  | W0X31607 (E1) W0X,31608 (E1) W0X31609, (Port) | [5 empty] | bpdd |  | 2012-10-11 |  |  |  |  | circuit disconnected
2012-09-25 | Core | MD036-02-IJ | 1800 Washington Blvd. (Montgomery Park), Baltimore, MD | Pots | NSPE0005890636 | [6 empty] | Order Number: N2DP38897 Date Due: 10/10/2012 Billing Telephone Number: 410-2447384 |  |  |  |  | bpdd | [6 empty] | Order Number: N2DP38897 Date Due: 10/10/2012 Billing Telephone Number: 410-2447384
2012-09-25 | Core | MD034-01-IJ | 351 W. Camden Street Baltimore MD 21201 | Pots | NSPE0005890675 | [6 empty] | Order Number: N2DP38904 Date Due: 10/04/2012 Billing Telephone Number: 410-244-0891 |  |  |  |  | bpdd | [6 empty] | Order Number: N2DP38904 Date Due: 10/04/2012 Billing Telephone Number: 410-244-0891
2012-05-30 | B end | CN516-02-IJ | Montreal, Ontario, Canada | 3072 2xT1 MD5 UHGVERbgpbqZyofa | 5112297 / 5112289 | 5505240 |  |  |  | 1808 | W0Z67807 (port) W0Z67805 (bearer) W0Z67806 (bearer) | Telus 55DHXS247154000ABGT000 55DHXS247156000ABGT000 TELUS CKT ID#:55DHXS247156 INT: SERIAL0/5/1/0/1/26:1 TELUS CKT ID#:55DHXS247154 INT: SERIAL0/5/1/0/1/27:1 |  |  |  | 2012-10-10 | bpdd | 2012-10-23 | 2012-10-23 | unitedhealthgroup-65069 | 763-694-7409, tbjorke@uhc.com | per terry active on 10/29? |  | 5/30- siva sent for SOF. 6/14- Pending uhg requested changed on SOF 7/6- still pending corrected SOF 7/13- corrected SOF sent to UHG 7/25- SOF received by Verizon 8/1- Melissa checking on SOF status 8/8:order validated w/ customer; customer moving beginning of Oct; order placed w/ Telus 8/3/2012:order rec'd on 8/2; PO# CN516-02-IJ; order submitted to system on 8/3 8/8- pendign FOC from Telus 8/140 still pending FOC from Telus 8/23- still pending telus date. 8/28- Telus FOC date is 10/10 10/4- per Canada PM: There was supposed to be a site visit on Oct 1 and there should be another site visit tomorrow. As of today, our provisioner advises that we are still tracking towards an Oct 10 FOC date. 10/5- because the site was not ready when they went on site on Oct 1. Also, Telus was not able to contact the site contact Andrea Linehin at 514-856-4370. It goes directly to voicemail and they have tried several times. The phone number for Elisabeth Wishart 514-940-0313 ends up on a voice mail of Monica Limba. Please can you provide another site contact? 10/8- per john The site contact Andrea has been working off site the last couple days, but will be back in the office on 10/9. 10/10- Melissa asked about a new FOC date 10/23- Order is ready for activation. .
2012-09-07 | Beth | UNC01-03-IJ | Wilmington, NC | 1536, T1 with MD5 encryption UHGVERbgpbqZyofa | smartform 189695630 NSPE0005831581 IQBKB4QF | 5552308 | P1952149 |  | 5200160 | 1280 | BCBKV4T00001 | 28/HCGS/412649//SB demarc is: 1st flr telco rm, quad melt 2nd slot rj48C, not extended, |  |  | 2012-09-25 |  | bpdd | 2012-10-02 | 2012-10-02 | unitedhealthgroup-64607 | 91 91600 84400, harish_kandpal@uhc.com | completed with keith on 11/6 |  | FOC date for 9/25, commit date for 10/2 9/27- LEC delivered, pending testing and closure 10/4- order ready for activation, engineer informed.
2012-07-26 | Beth | UMN46-02-IJ | Elk River SR 3 | PIP OC3 155250, OC3 Single Mode fiber, LC connector on ROADM frame encapsulation | Smartform 189662554 NSPE0005671054 CDR201207300027 IQBJ9Q4Y MIN I33589 | 5498703 | P1943146 |  | 5135631 | 44992 | BCBKVG370001 | o2-73c-llm8-0003 . The demark is the first floor server room 1, bay AO161, shelf FB6, jack A6, labeled. |  |  |  |  | 2012-10-24 | 2012-10-03 |  | UHG-ECC-TCW - 65200 need to change to UHG-ECC-TCW | 763/744-1587,,Leon_L_Betterman@uhc.com | completed with leon on 11/1 |  | 7/26- submitted to OM 8/2- Order with provisioning. 8/9- order with local provisioning 8/14- pending CCR # :1094000 (FOTS 73c-511 equipped with oc3 ) pendign shipment. 8/23- equipment shipped, pending equipment install due 8/31 8/29- pending equipment install sched fo r8/31 9/6- card installs set for today. 9/13-there was a timing issue with some of thesee cards, phil has this set for 9/20. I will ask if he can pull these in. 9/20- CCR now closed, prder steppedx 9/27- protect path needed to be added to design, order sent to field for testing. 10/4- order ready for activation engineer infromed
2012-07-26 | Beth | UMN46-01-IJ | Elk River SR 3 | PIP OC3 155250, OC3 Single Mode fiber, LC connector on ROADM frame encapsulation | smartform 189662380 NSPE0005671074 CDR201207300028 IQBJ9Q4T min I33603 (closed) | 5495180 | P1943143 |  | 5135629 | 44992 | BCBKVG340001 | o2-73c-llm8-0004 demarc sr3 customer ba361 fb6 port 3 LC patch panel. |  |  |  |  | 2012-10-06 | 2012-08-30 | 2012-09-06 | UnitedHealthGroup-TCW - 65307 | 763/744-1587,,Leon_L_Betterman@uhc.com | complted with leon on 10/29 |  | 7/26- submitted to OM 8/2- Order with provisioning. 8/9- pending CCR 1092773 OC3 card/SFPs add oc192.uhr3 (511,20 and llm8,07) . Equipment shipped on 8/9 8/14- CCR 1092773 closed. Order designed and node work being done 8/23 node work still being done. 8/29- order tested, pending closure, need CLR updated. DMARC posted. 9/6- order ready for activation, need to change vpn. 9/13- engineer informed that orde ris ready for activation
2012-05-15 | Beth | MN053-67-IJ | Elk River SR 1 10gig Lan PHY protected end link order- B- (llm8,06) terminate to 511 router MN33E01 |  | so: 5068101 MIN- I33379 | 5394336 |  |  |  | W0Z47164 | jy-llm8-511-0001 Bay 1, Shelf 2 (PS2), Slot 6 (Deg A) and 11 (Deg B) at site LLM8,06. VAM 161.0A.FB6A:9.tx | [6 empty] | 2012-08-01 | 100mg UHG-IPTF / 100 mg UnitedHealthGroup / 3mg UnitedHealthGroup-Raven |  | activate by steve end of october |  | 5/23- order is over to provisioning. 5/30- had to supp order to change Z end of endlink to 511. 5/31- supp being processed. 6/7- pending CCR #: 1080083 - 10g card add - RFT is 8/15. funding approved, pending card shipment. 6/14- shipment set for 6/20 6/21- shipment hasn't happened yet, following up. 6/28- this is likely related to the 511 bay add 7/19- per Phil Bay is arrived, reaching out to pM for intalll and RFT dates. 7/26- this is not related to the new bay. circuit is RFC tested, pending tcoms order closure 8/1 order closed
2012-05-15 | Beth | MN053-67-IJ | Elk River PIPO 2.5 mg port.- - (llm8,06) terminate to 511 terminate to router MN33E01 |  | IQBJ7Y0T | 5425384 | P1932463 | unitedhealthgroup 5189840 uhg-iptf 5189860 Raven 5189862 | 3mg | BOBKTFPX0001 | n/a |  |  |  |  | bpdd | 2012-09-05 | 2012-09-20 | ASN 65165 100mg United health group and ugh-iptf, 3mg Raven ASN 65165 |  | activate by steve end of october |  | pending card install in PE router-then order can be placed. The present activation date for MN3 is 7/17/2012 7/9- Card install is ready. port MN33E01.7B.0. This port is ready for traffic. Still pending 10 gig x-conn info for ordering. 7/26- order can now be placed. Termination info in LGX 113.5.9:25 113.5.9:26 Attempted to place tin, but am getting an error, ticket is open. 8/1- tin placed. 8/9- remarketing approved order with port info. 8/14- order with provisioning- pending mux new port doesn't have mecca info 8/22- mux created HLTK159 on scheduled status, September 5 8/28- mux completed X-connect is in and labeled fom 113.5.9 jks 25/26 to 113.06.09 jacks 15/21. sent to install. 9/6- pending configlets and BFD approval. 9/13- order pending ping test. configlets approved. 9/20- escalating for ping testing. 9/27- pipo closed, engineer informed.
2012-08-20 | Beth | CA049-04-IJ | Sacramento, CA | 3072, 2xT1 with MD5 encryption UHGVERbgpbqZyofa | smartform 189684827 NSPE0005767908 IQBKBK3Z | 5528460 | P1948327 | 5170742 | 1536 | BCBKVTK90001-0002 | 18/HCGS/564210//PT DEMARC LOC: SHELF 4 SLOT 6 18/HCGS/564211//PT DEMARC LOC: SHELF 4 SLOT 3 |  |  | 2012-09-12 | 2012-09-11 | bpdd | 2012-09-19 |  | UnitedHealth Group-65154 | 702-303-7293, tauoa.falo@uhc.com | completed with Tauoa on 10/11 |  | 8/22- sent to beth. 8/23- OS is working order 8.29- FOC 9/12, commit 9/19 9/13- order complete, engineer informed.
2012-09-11 | Deepa | na | 8220 SAN PEDRO DR NE ALBUQUERQUE, NM | currently homed to VzB PE router DNJES06 in Denver, CO. Request re-homing to AQHGE01 in Albuquerque, NM. | smartform 189712762 |  | P1589151 |  |  | BCBJVV660001 – 0002 | [8 empty] | 65232 |  |  |  | 11/7- this circuit was disconnected on 11/06/2012
2012-09-18 | Core | NY004-03-IJ | New York NY | New pots | NSPE0005862990 | [5 empty] | Order Number: N2LV4877 Date Due: 2012-10-10 Billing Telephone Number: 2122190363 Circuit ID or Telephone Number: 212 219-0363 |  |  |  |  | bpdd | [6 empty] | Order Number: N2LV4877 Date Due: 2012-10-10 Billing Telephone Number: 2122190363 Circuit ID or Telephone Number: 212 219-0363
2012-09-28 | SA disco | C1361-01-DJ | HARRISBURG PA | disconnect | NSPE0005909403 OQBKCTTW |  |  |  |  | BCBJCLRK0001 | [5 empty] | bpdd | 2012-10-29 | [5 empty] | disco completed 10/31
2012-09-28 | SA disco | na | AURORA IL | Disconnect Vzb DSL 128K | NSPE0005910247 |  |  |  |  | 100-404-432 U42047 | [5 empty] | bpdd | 2012-10-25 | [5 empty] | disco due on 10/25
2012-09-28 | SA disco | na | SHOREWOOD IL | Disconnect Vzb DSL 128K | NSPE0005910247 |  |  |  |  | 103-441-537 U70537 | [5 empty] | bpdd | 2012-10-25 | [5 empty] | disco due on 10/25
2012-09-28 | SA disco | na | SANDY UT | Disconnect Vzb DSL 128K | NSPE0005910247 |  |  |  |  | 100-993-160 U75439 | [5 empty] | bpdd | 2012-10-25 | [5 empty] | disco due on 10/25
2012-09-28 | SA disco | na | HOMEWOOD IL | Disconnect Vzb DSL 128K | NSPE0005910247 |  |  |  |  | 103-439-748 U78820 | [5 empty] | bpdd | 2012-10-25 | [5 empty] | disco due on 10/25
2012-09-28 | SA disco | UCA15-01-DJ | AGOURA HILLS CA | disconnect | NSPE0005909572 OQBKCTK4 |  |  |  |  | bcbh9hf50001 | [5 empty] | bpdd | 2012-10-29 | [5 empty] | disco completed 10/31
2012-09-28 | SA disco | UIL20-02-DJ | CHICAGO IL | disconnect | NSPE0005909778 OQBKCWPM |  |  |  |  | BCBJ7N5Y.0001-0006 | [5 empty] | bpdd | 2012-10-25 | [5 empty] | disco complete 10/29
2012-10-11 | Core | UMD27-03-DJ | Overlea MD | disconnect POTs | NSPE0005955869 | [10 empty] | bpdd | [6 empty] | Order Number: c4bh55673 Date Due: 2012-10-16 Billing Telephone Number: 4108829600 Circuit ID or Telephone Number: 4108824917
2012-05-04 | B end | FR501-04-IJ | Nanterre, France | 2048, E1 with md5 UHGVERbgpbqZyofa | fE 5099191 |  |  |  | 1536 | W0Z61034 | 0028PSA8 |  | 2012-07-17 | 2012-08-14 | 2012-09-11 | bpdd | 2012-09-25 | 2012-09-19 | unitedhealthgroup-65075 | 763-744-1847, donald_r_osborn@uhc.com |  |  | 5/10- pending SOF 7/5- per john SOF is in UHG's hands as of 7/4 7/13- per John Siva had the SOF as of Monday 7/9 7/19- Tech validation done on 7/17, ASR sent to PTT, pending response. 7/26- FOC date is Aug 14th 8/1- per conversation with LCOn, they wish to have the tail delivery pushed to September 4th due to the holiday. Confirmaing with Europe PM. 8/8- ACCORDING TO THE FT'S NOTES, THE CUSTOMER CONFIRMED A TAIL DELIVERY AT AUGUST 09TH 8/13- THE TAIL COULDN'T BE DELIVERED BY FT DUE TO THE MISSING WIRING IN THE CUSTOMER'S SITE. ALSO, THE CUSTOMER CONFIRMS THAT THE WIRING WILL BE COMPLETED AT THE FIRST WEEK OF SEPTEMBER. MR PATRICK MATHEY +33 1 64 62 41 91/+33 6 72 27 75 52 /PMATHEY@TRSERVICES.FR WILL TAKE CARE OF THE WIRING. 9/6- WIRING SCHEDULED ON 6TH SEP,ASKED TELCO TEAM TO DELIVER THE TAIL ON 7TH SEP 9/13- telco complete, pending ckt build, testing scheduled for 9/17 9/19- order ready for acitvation, engineer informed.
2012-08-28 | Beth | NM024-05-IJ | Farmington, NM | 4608 3 x T1 MD5 encryption UHGVERbgpbqZyofa | smartform 189688488 NSPE0005789005 IQBKBS8M | 5536218 | P1949582 | 8933091 | 1536 | BCBKVY640001-0003 | 54/HCGS/036463//MS DEMARC LOC: mn it - 1st flr - cab 1- slot 4 of 4 54/HCGS/036464//MS DEMARC LOC: 1st flr telco it mnt#1 slot 5 of 8 54/HCGS/036465//MS DEMARC LOC: 1st flr telco it mnt#1 slot 6 of 8 |  |  | 2012-09-18 | 2012-09-12 | bpdd | 2012-09-25 | 2012-09-21 | UnitedHealth Group-65189 | 715-841-7731, sonja_d_mroczynski@uhc.com |  |  | 8/28 submitted to Beth 9/6- FOC is for 9/18, our date is 9/25 9/14- circuits delivered on 9/12, taking errors on all circuits, troubleshooting 9/20- circuits tested well, pending configlets. 9/27- order completed, engineer informed.
2012-09-04 | Beth | C1491-05-IJ | Neenah, WI | 6144, 4 x T1 no MD5 encryption | smartform 189693464 NSPE0005814410 IQBKB9BW | 5549982 | P1953145 | 5207466 | 1536 | BCBKV60H0001-0004 | 41/HCGS/123346//WT DEMARC LOC: 5TH FLOOR TELCO CLOSET, DEMARC LOC Continued: SHELF 3 SLOT 1 OF 14 41/HCGS/123347//WT DEMARC LOC: 5TH FLOOR TELCO CLOSET, SHELF 3 SLOT 2 DEMARC LOC Continued: 3 SLOT 3 OF 14 41/HCGS/123348//WT DEMARC LOC Continued: 3 SLOT 2 OF 14 DEMARC LOC: 5TH FLOOR TELCO CLOSET, SHELF 3 SLOT 3 41/HCGS/123349//WT DEMARC LOC: 5TH FLOOR TELCO CLOSET, SHELF 3 SLOT |  |  | 2012-10-05 | 2012-10-02 | bpdd | 2012-10-08 | 2012-10-03 | UHGECC- 65533 | 763-744-2082, eric_taylor@uhc.com | requested for 3:30pm on Monday the 15th |  | 9/4- submitted to Beth 9/13- pending om submission 9/20- provisioning has, pending ASR submission 9/27- FOC for 10/5 10/4- order ready for activation, engineer informed
2012-09-05 | Beth | TX038-02-IJ | San Antonio | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189694430 CDR201209060054 NSPE0005822155 IQBKB5WG | 5549994 | P1952410 | 5202682 | 10800 | BCBKV5FD0001 | 31/HFGS/652311//SW DEMARC: 1st floor elect rm 125 ds3 cabinet 2 slot 3 tagged not extended |  |  | 2012-10-02 |  | bpdd | 2012-10-25 | 2012-10-08 | unitedhealthgroup-65154 | 702-303-7293, tauoa.falo@uhc.com | 11/07/2012 2:00 PM Central Time |  | 9/6 submitted to Beth. 9/14- order sent to ops. Pending provisioning approval 9/20 FOC 10/2 with our commit date to 10/25 10/4- lec delivered, issue with Los at cfa , troubleshooting 10/11- order completed, engineer informe.d
2012-09-24 | SA disco | UIL11-02-DJ | Chicago IL | disco | NSPE0005885055 OQBKCMSJ |  |  |  |  | BCBKHW990001 | [5 empty] | bpdd | 2012-10-24 | 2012-10-26 |  |  |  |  | disconnect due on 10/26
2012-10-09 | IBBJG75L0001 | disconnect | Agoura Hills, CA |  | NSPE0005944722 OQBKC7KG |  |  |  | IBBJG75L0001 - 0024 service N5982797 | [19 empty] | 10/11 order with disconnect group- pending order 11/9- disco completed
2012-09-07 | beth | C1550-04-IJ | Columbia, SC secondary CFA of NC139G OC192 83 CLMASCSNKAR CLMASCOSKAA | DS3 no MD5 encroyption | smartform 189695590 CDR201209100033 NSPE0005831699 IQBKB637 | 5552299 | P1952647 |  | 9216 | BCBKV5V20001 | 34/HFGS/401364//SB demarc : FIRST FLOOR TELCO ROOM RELAY RACK 15 PORT 4 |  |  | 2012-10-04 | 2012-10-05 | bpdd | 2012-11-13 | 2012-11-09 | UHG-ECC-TCW- 65203 | 763/744-1587, Leon_L_Betterman@uhc.com | activated wth Leon on 11/13 |  | 9/14- order sent to provisioning 9/20- FOC for 10/4, pending commit date 9/27- ticket C201209270049 for commit 10/4- pendign Lec delivery 10/10-= LEC delivered, commit 9/26, escalating for testing and completion 11/7 we are working on fiedl cross connects, pushing to have this completed by 11/13 11/9- PRE TEST RESULTS: VZB pre-tested good & clean NEXT ACTION: End-to-End test will be done w/ AT&T 11/9- order completed and ready for activation, engineer informed.
2012-05-15 | Beth | MN011-06-IJ | Chaska MDF 700 10gig Lan PHY protected end link order- terminate to 511- SMF LC connector proteccted |  | smartform 170573483 NSPE0005453825 so: 5068853 MIN- I33387 | 5391962 |  |  |  | W0Z48442 | jy-m6l7-511-0001 Demarc at m6l7,01 is 7100 patch panel LEFT pos 3. THis equals customer VAM AK,707.FB3 A3 (pos 3) | [11 empty] | sent to OM 5/23- order to provisioning 5/30- oder rejected for info, sent email to oE and prov.supped order to terminate at 511 versus 73c 5/31- order written between cologne and Minneapolis, need cologne end changed to chaska, workign with oe provisioning 6/6- new local order opened to terminate at 511 node. 6/14- pending CCR #: 1080958 10g card add (m6l7,01 and 511,20, funding approved, pending shipment. capacity to be available 7/11 6/20- still pending card shipment. 6/21- cards shipped. 6/28- I think this might be held up due to the bay expansion in 511. Bay is backordered. melissa is checking with Phil on this. 7/19- per Phil Bay is arrived, reaching out to pM for intalll and RFT dates. 7/26- This is not related to the bay expansion at 511. Cards are installed. Order is being RFC tested now. 8/1- order closed. 511 hand off is LGX 113.5.9:27 113.5.9:28 (Aisle.Bay.Shelf:Jack)
2012-05-15 | Beth | MN011-06-IJ | Chaska MDF700 PIPO order terminate to router MN3GE01 |  | IQBJ7X4C | 5423825 | P1932297 | 5209867 unitedhealthgroup 5212513 - UHG-IPTF |  | BOBKTD960001 | [8 empty] | UnitedHealth Group and UHG-IPTF 100mg ASN 65074 |  |  |  | pending card install in PE router-then order can be placed. The present activation date for MN3 is 7/17/2012 7/9- MN3GE01), is still in process. We are decomming a card from another site and will be installing it in this new router. The date is TBD but most likely will be mid-August (subject to change). The reason I cannot give you a firm date is due to the fact that the decom is still in process but more importantly, we may run into transport issues but will not know until the start testing. 8/14 card install is still pending 8/22- card should be available by the end of this week. 8/28- followed up with engineering on card install. 9/6 card is in MN3GE01.1A.0. sent order to provisioning wtih card info 9/13- order is sent for mux and ready for install review 9/19- ticket to icat for pick up B201209190090, spoke to rep, he wil get it assigned. 9/26- rebuilt PVCs, asked for prebuild again. 9/27- sent for ping testing. 10/4- order completed, engineer informed.
2012-09-25 | Beth | UWA05-05-IJ | Seattle, WA | 2xT1 3072 with md5 UHGVERbgpbqZyofa | smartform 189706436 NSPE0005897191 IQBKCMNJ | 5574069 | P1955062 | 5210333 | 1536 | BCBKWB1V0001-0002 | 74/HCGS/510510//PN 74/HCGS/510511//PN |  |  |  |  | bpdd | 2012-10-23 | 2012-10-18 | Unitedhealthgroup-64562 | 763/694-7370, masroor_khan@uhc.com | completed on 11/14 with masroor |  | 9/27- pending ASR 10/4- FOC for 10/16, commit 10/23 11/8- order ready for activtaion- Masroor placed request.
2012-09-25 | Beth | UVA01-07-CJ | Richmond, Va | Upgrade to 3xT1 4608 with md5 UHGVERbgpbqZyofa | smartform 189706458 NSPE0005897425 IQBKCPRK OQBKCS1W | 5574311 | P1916029 (out) P1955390 (IN) |  | upgrade to 1536 | BCBKR55G0001-2 (out)BCBKWCTN0001-3 (in) | 48.HCGS.980887..CV DEMARC LOC: BSMT 1,RM 1,TEL RM ,RJ48C,LP Y,CAB N,SHELF 2,SLOT 5, |  |  | 2012-10-22 | 2012-10-22 | bpdd |  |  | Unitedhealthgroup-64623 | 763/694-7370, masroor_khan@uhc.com | hotcut completed 11/16 |  | 9/27- pending tin submission by om 10/4- order with provisonning 10/11- pending capacity, esclating with provsiiooning 11/8- order ready for hotcut. Engineer informed.
2012-05-15 | Beth | MN053-68-IJ | Elk River SR 3 10gig Lan PHY protected end link order- through NSB- (llm8,07) router MZZGE01 at Cologne. |  | so: 5068828 MIN-I33355 CCR 1085041 min-C33355 | 5396111 |  |  |  | W0Z47185 | jy-llm8-73c-0001 dmarc VAM 361.BD.1l:9 |  |  | 2012-08-29 |  |  |  | 2012-08-01 |  |  |  |  | 5/23- order is over to provisioning. 5/31- order being worked by local design 6/7- pending CCR #: 1080086- sent e-mail to system engineer to review. 6/14- pending funding approval for transponder card 6/21- equipment received at the terminal. 6/28- pending equipment install 7/12- FOC set to 8/29. TGTM cards have been installed at LLM8,07 (SR3) used splitter set 2 and term ckt to Roadm Vam patch panel (LEFT) pos 9. THis feeds to customer FDP BA 361.FB6 A9 LC. PLease add this to the CLR. per Phil cards are installed and he had to build them on the roadm 7/19- CCR is complete. Asking provisioning to proceed with design 7/20- CCR 1085041 TGTM 10gig Card add at nsb and 73c with Splitter shelf. At nsb this calls for the first cards in port shelf 3. I am working to turn up this new shelf and prep for ckt hand offs. ETA late next week. At 73c the card have been sent to the site and should be completed late next week. This supports pending order: TCOMS i33355 7/24- Cards are in and fibered at 73c. As I stated below I still have some prep work for the new shelf at nsb.Will have to see if I can find time to get to nsb around mid week. All the provisioning is completed today in the 7100. (paths built). Just need to build out the Y/Splitter shelf’s at nsbAnd install fiber from the Roadm to Vams for ckt drops 8/1- CCR complete, pending order closure 8/9- RFC test completed, pending correction on design at 73 c to this going to T7100 14.21.1:4.16.1 8/15- order closed. loop at the far end. The demark is the first floor, LGX 10.27.4.3 & 9.
2012-05-15 | Beth | MN053-68-IJ | Elk River SR 3 PIPO 2.5 mg port- through NSB- (llm8,07) terminate to MZZGE01 at 73c cologne. |  | IQBJ72RQ (replacement IQBKCY5T ) | 5430195 |  | Order Number: 9191207 PVC ID: 5212868 Order Number: 9191218 PVC ID: 5212870 Order Number: 9191228 PVC ID: 5212873 |  | BOBKWHD00001 | [6 empty] | 2012-10-31 | 2012-11-12 | 100mg United health group and ugh-iptf, 3mg Raven ASN 65165 |  |  |  | pending card install in PE router-then order can be placed. The present activation date for MZZ is 8/7/2012 8/6- card is installed. Port is MZZGE01.1A.0 8/15- orderpro ticket opened. Can't submit x-connection order 8/23- able to submit tin 8/28- order created and sent to provisioning 9/6- following up with provisioning on pick up. 9/13- escalating further for prov pick up 9/.20- order is with provisioning, pending the pot to be unblocked. 9/.27- escalating with OE, order was keyed incorrectly 10/10- order keyed by OE, provisioning has it and mux is being written 11/7- order tested and just needs to be closed Melissa is pushing for order closure 11/14- order ready for activtion, engineer informed..
2012-03-13 | Beth | CA167-02-IJ | San Jose, CA | 44736, DS3 with dport and dcar and UHGVERbgpbqZyofa encryption | CDR201203130020 IQBJ44CV OAK I0010114 is in opdk | 5283326 |  |  | 1536 | BCBKR25S0001 | 86/HFGS/577962//PT Dmarc: mpoe closet level 1 yellow tags ye |  |  | 2012-04-04 |  | bpdd | 2012-04-27 | 2012-04-24 | UnitedHeatlhgroup65154 changed by dan to asn 65080 on 11/20 | 702-303-7293, tauoa.falo@uhc.com | completed with Don on 11/20 |  | 3/22- FOC 4/4 4/11- leC missed delivery opened late loop ticket. 4/19- lec delivered, C201204190037, ready for testing and closure 5/3- ready for activation, engineer informed.
2011-08-25 | Beth | C1246-04-IJ | El Segundo, CA- sec CFA customer provided acccess. | 9216, 6 x T1 | NSPE0004710104 IQBJYDVQ lsa I120248 6hr loc 75 LSA-C120248 | 5002417 | p1866556 configlet is under p1866556-2819537 |  | 128 | BCBKMMDN0001-0006 | x1-vrp-6hr-0001 dmarc 3h-6hr-pfc-0015 Slot 22 x1-vrp-6hr-0002 dmarc 3h-6hr-pfc-0015 Slot 16 x1-vrp-6hr-0003 dmarc 3h-6hr-pfc-0015 Slot 4 x1-vrp-6hr-0004 dmarc 3h-6hr-pfc-0015 Slot 5 x1-vrp-6hr-0005 dmarc 3h-6hr-pfc-0015 Slot 8 x1-vrp-6hr-0006 dmarc 3h-6hr-pfc-0015 Slot 10 | 0CP6TJ; 0CP6TK; 0CP6TN; 0CP6TL; 0CP6TH; 0CP6TM; |  |  |  | bpdd | 2011-09-22 | 2011-11-02 | UHGECC-65433 | scott_moyer@uhc.com; 763-744-2154 |  |  | need to cancel and re-sissue, collo with Savis 9/15- supped order to correct sec CFA 9/21- 8sh,01 completely out of dacs ports, estimated time frame for dacs,looking at end of October,2011., pending 3p-8sh-pfc-0089 parent order A120462 10/27- lsa A120462 order closed. 11/2- order local delivered, pending testing and closure. opened ticket B201111020148, order closed and ready for activation. John submitted a disconnect via the VEC 11/16
2012-05-15 | Beth | MN011-07-IJ | Chaska MDF 800 10gig Lan PHY protected end link order- through NSB terminating to Cologne, need different shevles at nsb and Chaska on the roadm from mdf 800 |  | S/O: 5105171 MIN-I33590 | 5480845 |  |  |  | W0Z66371 | jy-m6l7-73c-0001 THe Vam demarc info at m6l7,02 is: 7100 SC patch panel 1.1.1r:3 this takes it to customer LC patch panel: AK.807.FB3 B:3. i | [11 empty] | pending OCNE approval 6/28- OCNE approval received, pending pricing 7/19- per conversation between matt and Rich, we won't be using the ld network because of the cost. 7/24- order placed. 7/26- order in provisioning. 8/1- confirmed ring id with provisioning and routing 8/9- sent for site survey on CCR CCR #: 1092653 and and CCR #: 1092530 (transponder/OADM cards), pending shipment 8/14- CCR cards shipped. Phil verified he has the cards 8/22- pendign card installs, set for the end of this week. 8.28- card installs set for 8/30. 8/31- cards installed, pending testing and closure 9/6- all node work done, sent for RFC testing. 9/13- issue with switchover at testing. Y cable needs to be removed, melissa is talking to Phil about this. 9/19- y cable removed from design, stepped for patching. handoff at 73c T7100 14.21.1:4.3.1 10/4- order closed, rfc testing complete
2012-05-15 | Beth | MN011-07-IJ | Chaska MDF800 PIPO order terminate to MZZGE02 |  | IQBKCPXD | 5493889 | P1955436 | 5210727 5210728 |  | BOBKWCW20001 | see above | [6 empty] | 2012-11-14 | 100mg United health group 65074 and 100mg UHG-IPTF 65074 |  | brought up by Steve on 11/14 |  | pending card install in PE router-then order can be placed. The present activation date for MZZ is 8/7/2012 8/6- Card is installed. Port MZZGE02.1A.0 9/26- tin submitted 10/4- escalating with provisioning for pick up 10/10- provisioning has and they are working it 11/7- mux written and set to be worked, Melissa is esclating on themux 11/14- We are testing, waiting for customer to admin up the router to see if the port is fibered up correctly. Steve was able to bring up interface.
2012-07-26 | Beth | UMN47-01-IJ | Chaska mdf 800 | PIP OC3 155250, OC3 Single Mode fiber, LC connector on ROADM frame encapsulation | smartform 189662694 NSPE0005671205 CDR201207290002 IQBJ9PKG min-I33626 | 5495001 | P1942659 | 5154821 | 44992 | BCBKVGCL0001 | o2-73c-m6l7-0002 demark is MDF700, VAM AK.707.FB3:A4 |  |  |  |  | bpdd (september) | 2012-11-07 | 2012-09-27 | UnitedHealthGroup-TCW- 65323 | 763/744-1587,,Leon_L_Betterman@uhc.com | requested for 11/9 at 10am |  | 7/26- submitted to OM 8/2- pending prov ticket 8/9- provisioning dissapproved, pending re-ops approval 8/14- order over to local provisioning 8/23- pending roadm transponder cards CCR 1095680, site survey being performed. Pending equjipment shipment 8/28- equipment installed, pending CCR closure. 9/6- CCR revision occurred pending equipment install, reaching out to Phil on Date. 9/13- ccr completed, order stepped out for sonet work. 9/20- all local node work completed, pending ld work at 511., ticket 2012092101 9/27- local order is closed, pending testing and closure of ld order, dmarc posted 9/28- order tested clean. closing order. ready for activtion, engineer informed.
2012-08-03 | B end | PH501-03-DJ | PHILIPPINES | disconnect | 5127106 |  |  |  |  | W0Y40995 | [5 empty] | bpdd | 2012-11-15 | 2012-11-16 |  |  |  |  | 8/6- send to B end team to process. 8/14 escalating with B end for process. 8/23- pending contract expiry date, ETF and the notice period of their service 8/29 - escating with billing on the above information 9/6- billng verification done, order to validation wtih LCon 9/13- still pending tech verification, sent to contact Jason 9/20- re-sent jasn't info to tech validation 9/27- pending TEV from Jason 10/4- asked john for an alternate onsite contacet 10/11- fup with John on site contact. 11/7- ORDER MOVED TO CFOC STATUS TERMINATION DATE : 11/15/2012 11/14- order moved to install to close 11/160 disco completed
2012-11-12 | Core | UMA05-03-DJ | Medford MA | disco pots | NSPE0006072484 | [5 empty] | 781-391-2014 |  |  |  |  | bpdd | [6 empty] | Order Number: D5FR9200 Date Due: 2012-11-16 Billing Telephone Number: 781 391-2014 627 Disconnect Telephone Number: 781 391-2014
2012-04-03 | Beth | UKS08-08-IJ | Overland Park, KS | 50 MBPS Ethernet MD5 Encryption UHGVERbgpbqZyofa type 4 ethernet | Project ID: CP23155.00 Smartform 160301894 Per #: 04101203 SAR ID:1-1HKJN8N_1-1HKL6JM ORDER IQBJ7BFV EA IQBJ7BFW EF | 5340406 | P1927818 EA P1927819 EF | VDDS Order Number: 8122761 PVC ID: 5066263 | 20000 | EDBKSP5L0001 (EA) BCBKS4FH0001 (EF) | 74/KQGN/904549//SW Demarc Info: 1ST FLOOR LAN ROOM CUSTOMER RELAY RACK 1 SHELF 1 WESTELL PANEL POSITION 1 TAGGED ON BOTH SIDES ERS/ERS NOT EXTENDED. . |  |  | 2012-08-07 |  | bpdd | 2012-08-24 | 2012-08-22 | UnitedHealthGroup-64905 | 763-744-1575, daniel_j_skripka@uhc.com | activated with Dan on 11/27 |  | l no response on our ASR. opened ticket C201206060047 6/14- escalating with AT&T for status. 6/20- stilll no response from AT&T 6/21- we had to transmit to a different NCsc SW02. That ASR has been transmitted. 6/28- AT&T netowrk has to issue the job for design and approval in order to establish a provisioning interval. They have 7 to 10 days after notification to kick-off the project and begin that process. 7/5- still pending AT&T job 7/12- per AT&T- there will be an infrastructure build required to splice new fiber and equipment in order to establish the facilities to work the service you have ordered. The ECD for the work to complete is 8/6/12. Your estimated service delivery date is 8/16/12. Your formal FOC will not be ready for a week or so. Once it is available, I will provide it to you. 7/18- still pending formal FOC 7/24-The ASC is working to issue your FOC now. Your FOC DD will be 8/7/12. You should be receiving your FOC within the next few days. You may follow-up with the ASC if you do not. 8/1- pending LEC FOC of 8/7, pending flow marketing approval 8/8- Called AT&T and spoke with Becky, LEC loop has been completed on 8/7/2012 but no DEMARC information indicated on there system. Called AT&T ENOC and was ad vised they will call back as soon as they have the information (state impacted b y the strike). 8/15- CPE installed and RFC test done, pending order closure 8/22- order ready for activation, no prebuld done, melissa requested.
2012-03-29 | Beth | UIL44-10-IJ | Moline, IL | DS3 with Dport and Dcar MD5 Encryption UHGVERbgpbqZyofa | NSPE0005302542 IQBJ5TKR dvp I206 (closed) | 5306454 | P1918374 | 5028918 | 6288 | BCBKSDJ80001 | /HFGS/808117//LB Demarc: relay rack 0003 panel 1 slot 1 | 0CSJJ3 |  | 2012-07-13 |  | bpdd | 2012-07-19 | 2012-07-18 | UnitedHealthGroup-64584 | 763-694-7409, tbjorke@uhc.com | completed 11/26 |  | 5/17- LEC didn't deliver, pending build 65, trying to get more info. Ticket C201205100078 FOC pushed to 7/2, we are trying to better that. 5/23- per AT&T there is still a pending job code 65 with no ECD. 5/31- escalating fo rupdate. 6/6- i called and spoke to Steve of centurylink and as per him the ICO is still pen ding with the contruction job on the end user and he said that plant test is on 6/29/2012.. i called and spoke to Dee of ATT she said that as per the notes the customer is pending with the site visit. melissa called LCON to see if he's heard from AT&T 6/14- still pending site visit, asked john to reach out to lcon as well. Per lcon, he hasn't heard from the lec. C201206060058 is ask lec to call lcon 6/20- escalating with the LEc. 6/28- escalating further to find out on the LCON site visit 7/2- site visit was done 6/29. FOC for 7/2 7/5- LEC revised their FOC to 7/13 7/18- it appears we did not get ELA from the lEC. asked to follow up and see if LEC delivered. 7/25- order is ready for activation, engineer informed. 9/14- activation failed, customer needs to check inside wriing. 11/7- rescheduled for 11/26
2012-10-24 | SA disco | UCA89-01-DJ | CONCORD CA | disconnect | OQBKDX6N |  | P1361241 |  |  | total disconnect for P1361241 BC BH81LH 0001 BC BH81LH 0002 BC BH81LH 0005 | [5 empty] | bpdd | 2012-11-21 | [5 empty] | 11/5- sent to SA disco 11/6- disconnect due on 11/21 disco completed 11/21
2011-12-08 | B end | IN518-02-IJ | Bangalore, India | 2048, E1 | 4976202 |  |  | 5104220 | 1536 | W0Z06773 | 0008001054807 |  |  | 2012-07-14 |  | bpdd | 2012-07-30 | 2012-07-11 | UnitedHealthGroup- 65220 | (91) 9810059326 , pradeep_yadav@uhc.com |  |  | 3/29- THE WORK IS STILL IN PROGRESS AT THE SITE. THE BIGGEST CHALLENGE FACED BY THE PTT IS FOR THE ROW PERMISSION (PERMISSION REQUIRED FROM GOVERNMENT AUTHORITIES FOR THE FIBER PULLING ACTIVITY. THIS PERMISSION IS BEING STOPPED BY THE GOVERNMENT AUTHORITIES TIME TO TIME DUE TO SOME CIVIL WORK. PTT IS NEGOTIATING AND WORKING WITH THE AUTHORITIES IN GETTING THIS APPROVED. AS A RESULT, THE PROJECT IMPLEMENTATION WILL TAKE SOME TIME.PTT HAS INITIATED TO IMPLEMENT THE CIRCUIT ON LBR. THE NEW EXPECTED DELIVERY DATE IS OF 20 APRIL 2012. 4/17-IMPLEMENTATION WORK IS IN PROGRESS AT THE SITE. HOWEVER, THERE ARE SOME DEPENDENCIES AT THE CUSTOMER END WHICH NEEDS TO BE RESOLVED BY THE CUSTOMER. -> INDOOR EARTHING FOR TRANSMISSION RACK IS NOT AVAILABLE AT THE CUSTOMER LOCATION. -> OUTDOOR EARTHING FOR LBR POLE IS NOT AVAILABLE AT THE CUSTOMER LOCATION. -> UPS SUPPLY IS NOT AVAILABLE IN THE SERVER ROOM FOR OUR EQUIPMENTS.HAVE ASKED THE CUSTOMER TO PROVIDE THE ABOVE REQUIREMENT FOR THE INSTALLATION OF THE CIRCUIT. ORDER IS ON HOLD DUE TO CUSTOMER DEPENDENCIES. 5/17- per John still pending ups 5/31- per John another week or 2 on the UPS. 6/6- still pending customer UPS 6/14- STILL PENDING UPS 6/20- still pending UPS. 6/27- UPS should now be in place per john. india pm has asked pTT to move forward with implementation work. new revised FOC is July 14th. 7/11-CIRCUIT TESTING HAS BEEN COMPLETED. PING TEST HAS BEEN COMPLETED. CIRCUIT DELIVERED. ORDER CLOSED.
2012-10-02 | Deepa | FL050-02-IJ | West Melbourne, FL | 4608 3xT1 with md5 UHGVERbgpbqZyofa | smartform 189711108 NSPE0005920039 IQBKCWL3 | 5583302 | P1956785 | 5212178 | 1536 | BCBKWF6P0001-0003 | 58/HCGS/784556 /SB DEMARC LOC: 1FL COM RM 1#2 58/HCGS/784557//SB 58/HCGS/784558//SB |  |  |  |  | bpdd | 2012-11-15 | 2012-11-14 | unitedhealthgroup-65037 | 860-702-8284 Keith_mangene@uhc.com | activated with Keith on 12/3 |  | 10/4- order with provisoning 10/11- pending ASR escalating 11/8- LEC delivered on 11/1. order is still held for Need to place conduit and back board , which melissa is figuring out. We may ned to supp to remov it 11/15- order ready for activation, engineer informed.
2012-09-06 | Beth | GA008-02-IJ | Atlanta, GA | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189694768 CDR201209070030 NSPE0005825159 IQBKB71M atl I77339 (closed) | 5550068 | P1952848 | 5206201 | 22000 | BCBKV6CB0001 | 38/HFGS/708015//SB |  |  | 2013-01-08 |  | bpdd | 2012-01-15 |  | unitedhealthgroup-65043 | 860-702-8284 Keith_mangene@uhc.com |  |  | 9/7- order sent to Beth 9/14- pending OS submission 9/20- ASR sent, pending FOC 9/27- address clarification from the LEC. Working with provisioner 10/4- address still not validing provisioner is working on this. Melissa asked if any further info is needed. 10/10- escalating on address validation issues 11/7-clarifiation on suite. per john C 600. order supped. 11/14- supp sent to clarify sutie and saying to terminate to dmarc. Requested date from the LEC is 11/29 11/15- LEC FOC 1/8, better telco due date ticket opened C201211140073 11/21- Called AT&T spoke with Barbara, has job code 35. Great possibility that job will be completed on December.ECD 12/26. Pending Milestones: Reconfigure/rewire existing MUX Translation work Backplane wiring Install plugs Install CPE as determined by the OSPE (outside plant engineer) during site visit Place less than 2,500 ft of fiber and conduit Order and install new central office (CO) equipment 11/29- Pending AT&T build job with cod e 35, placing fiber and equipment, ECD 12/26, Due date scheduled for 1/8 11/30- per john cancel the order.
2012-10-12 | Deepa | TX007-05-IJ | 5835 Callaghan Road Suite 400, San Antonio, TX | 3072 2xT1 with md5 UHGVERbgpbqZyofa | IQBKDCYK | 5599281 | P1960074 | 5219757 | 1536 | BCBKWM770001 BCBKWM770002 | 31/HCGS/700072//SWDEMARC LOC: 4TH FLR SUIT 400, CAB#2, SLOT#3, DEMARC LOC Continued: SLOT#3, TAGGED 31/HCGS/700073//SW DEMARC LOC: 4TH FLR SUIT 400, CAB#2, SLOT#3, DEMARC LOC Continued: SLOT#3, TAGGED |  |  | 2012-11-16 |  | bpdd | 2012-11-27 | 2012-11-15 | unitedhealthgroup-65113 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 12/5 |  | 10/26/2012: Order is with provisioning. Waiting for FOC date. 11/02/2012: Order with provisisioner 11/8- Called ATT, spoke with Lisa, as per her, order was not completed, the tech lost access yesterday at the customer site. As per her, there are no notes if the tech will be dispatching again at the customer site. -775 added reques ting to place the order in HCUS due to issues with access 11/15- new FOC 11/16 11/21- order ready for activaiton, engineer informed.
2012-09-12 | Beth | C1551-01-IJ | FLORENCE, SC | 44736, DS3 with md5 to TCWVERbgpajs9tbxp | smatform 189697982) CDR201209120038 NSPE0005842709 IQBKB9GS flo-I201 (closed) | 5557167 | P1953191 | 5207504 | 22000 | BCBKV62H0001 | 32/HFGS/400246//SB DEMARC:1st floor data room relay rack 2 ds3 jack no 18 Fiber Mode (MMF/SMF): |  |  | 2012-11-26 |  | bpdd | 2012-12-05 | 2012-11-27 | UnitedHealth Group-TCW-65043 | 860-702-8284 Keith_mangene@uhc.com | activated with Keith on 12/6 |  | 9/20- ASR sent to the LEC, pending FOC 9/27- FOC 11/9, commit 11/16 11/8- order is not going on the ring. Also went into hcus for dmarc termination. Asked to supp to have terminated to mpoe. This will push out the date of 11/9/ 11/15- fOC 11/26, CDD for 12/5 11/29- order ready for activation. Engineer infomed.
2012-10-24 | SA disco | NM024-02-DJ | FARMINGTON NM | disconnect | OQBKFDDB |  | P1669372 |  |  | BCBJ3W8H0001 | [6 empty] | 2012-12-03 | [5 empty] | 11/5- sent to SA disco 11/9- disconnect due on 12/3 12/6- disco complete
2012-10-11 | Deepa | DE003-05-CJ | Newark, DE | upgrade to 4608 3xT1 | smartform 189716417 NSPE0005956759 IQBKC75M OQBKC9H2 | 5597576 | P1900991 (out) P1959610 (in) |  | upgrade to 1536 | BCBKPYJH0001-0002 (out) BC BKWMDD0001 -0003 (in) | 11/HCGS/700105 /DS DEMARC LOC: GND,RM mdf,TEL RM ,RJ48C,LP Y,CAB N,MNTG #2,SLOT 2,extended DEMARC LOC Continued: to 2nd floor d Extended Wire (Yes or No): Yes |  |  |  |  | bpdd |  |  | unitedhealthgroup-65094 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 12/10 |  | 10/26/2012: Order is with provisioning. Waiting for FOC date. 11/9 new loop delivered annd order is ready to schedule for hotcut
2012-07-25 | Beth | NY077-06-CJ | Latham, NY | Upgrade to 9216, 6xT1 | Smartform 189662938 NSPE0005670658 IQBJ9S1H OQBJ9S1L | 5498729 | P1605195 (out) P1943663 (in) | 1740288 | 4608 | BCBJW7HN0001-4 (out) BCBKVH170001-0006 (in) | 34.HCGS.751337..NY DEMARC LOC: GND,RM 1,UTIL RM ,RJ48C,LP Y,CAB N,MNTG 2,SLOT 5, 34.HCGS.751338..NY DEMARC LOC: GND,RM 1,UTIL RM ,RJ48C,LP Y,CAB N,MNTG 2,SLOT 6, |  |  | 2012-08-21 |  | bpdd |  |  | UnitedHealthGroup-65222 | (987) 313-9388, anupam_datt@uhc.com | completed on 12/11 |  | 7/26- submitted to beth 8/2- order over to provisioning 8/9- ASR sent, pendng response 8/14- FOC for the new loop is 8/21 8/23- Lec delivered and order is ready for hotcut engineer informed.
2012-11-05 | Deepa | KS003-04-IJ | Overland Park , KS | 12288 8xT1 t with MD5 UHGVERbgpbqZyofa | smartform 189738428 NSPE0006055879 IQBKFL5N | 5628133 | P1966721 | 5233566 | 9216 | BCBKW9270001-0008 | 74/HCGS/944080//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 11. 74/HCGS/944081//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 12. 74/HCGS/944082//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 13. 74/HCGS/944083//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 14. 74/HCGS/944084//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 15 74/HCGS/944085//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 16. 74/HCGS/944086//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 17. 74/HCGS/944087//SW DEMARC LOC: FLR 2, EQ RM, SH 1, SL 18. |  | 2012-11-29 | 2012-12-06 |  | bpdd |  |  | unitedhealthgroup-65041 | 763/694-7409, terry_bjorke@uhc.com | completed with Terry on 12/12 |  | 11/7- order sent to OM. 11/15- esclating for OM submit 11/21- order in design, pending handoff 11/29- asr sent, pending foc. 12/6- order ready for activation. Engineer informed.
2012-09-14 | Beth | C1203-04-IJ | Troy, MI secondary cfa of NSCDR1/STS1/7/TROYMIATH01/TROYMIMNK03 | 44736, DS3 with md5 UHGVEReccstr82tcW | smartform 189701496 CDR201209190020 NSPE0005869143 IQBKCFK9 | 5563664 | P1954093 | 5208701 | 128 | BCBKV8ST0001 | demarc: 1st floor main telco rm.,relay rack1 shelf 1 slot 3 extended: No tagged:Yes Lec order: C2904275911 Lec ckt ID: /HFGS/314601//MB |  |  |  |  | bpdd |  | 2012-11-06 | UHG-ECC-TCW- 65202 | 763/744-1587,,Leon_L_Betterman@uhc.com | activated with Leon on 12/6 |  | 9/20- pending submission by the om 9/27- ASR sent pending FOC 10/4 Asked provisioner to supp asr with secondary cfa 10/11- ASR supped, pending FOC 11/6- order ready for activation, John informed.
2012-12-03 | ILEC | PA016-03-DJ | 300 Oxford Drive Monroeville PA | disco pots | NSPE0006142045 | [5 empty] | Order Number:D0HC21560 Date Due: 12-07-12 Billing Telephone Number: 412 373-0340 783 Disconnect Telephone Number: 412 373-0340 |  |  |  |  | bpdd
2011-10-24 | Beth | C1489-08-IJ | Connextions, Jeffersonville, IN on CFA 81DGL OC12 3 JFVLIN01 UTTPINBIH00 | 44736, DS3 | CDR201110240018 IQBJ0J7F lou I455 (closed) | 5085699 | P1882805 | 3355308 | 12000 | BCBKNRS70001 | / /HFGS/105604//NB / 03052012 K1/HFGS/105604//NB Demarc: 1st flr server rm, shelf 2 slot 3 Extended(Y/N): no New FOC K1/HFGS/105604//NB Demarc st flr server rm shelf slot not exten ded and it s tagged |  |  | 2012-08-31 |  | bpdd | 2012-09-11 | 2012-09-05 | UHG-0ECC-65513 | 763-744-0840 matt_f_seymour@uhc.com |  |  | 2/16- This is a MULTI-EC ASR between NB01 and SC02. The one that has FOC on 3/5 is for NB01.We are waiting for FOC now from SC02. 3/8- FOC for both carriers was 3/5. Missed, opened ticket C201203080028 3/15- AT&T tested and we have dmarc but they are saying the ASR is held for CNR. Melissa is escalating for clarification. 3/21- AT&T required a supp saying the sec CFA wasn't ready, we vrifid it was, suppeed the order, the new due date is 4/9 4/10- AT&T is still saying the SCFA isn't ready and won't be until August. Asked Provisioning to call and get more informaiton. 4/17- FOC RCVD DATE: 04172012 TELCO DUE DATE: 04302012 LEC ORD NBR: C2902584888, opened BCD ticket C201204190026 5/3- no LEC delivery. LEC STATUS: Emailed the AP rep/Janice for status assistance and clarification. Anotification was received regarding an error to SCID and seen at the main billing order notes that there is a customer not ready ,there is a problem with fibe ring at the customer.Pending response. 5/17- still pending response from Connextions/ATT 5/31- LEC FOC is 6/5 asked AT&T to match their orders to the 6/5 dates 6/6- AT&T didn't deliver and jepped orer again- SCFA has a problem the upgrade didn't go through due to the riders on the OC12. Informed John and asked if we shoudl have another call. 6/28- will be having a call next week.with ATT. 7/5- per AT&T they will be installing new fiber. They asked us to supp our order out to 7/.27 7/11- asking provisioning to supp the order to 7/27 7/18- order is FOC'd for 7/27, commit date is 8/3 8/1- LEC asked us to push the FOC date to 8/31: called and spoke with Theresa, provi ded that they have moved the due date to 08/31/12 because the Channel failc ity assignment that we requested will not be availiable until the end ofthe month. 8/13- we attempted to call the lec and they couldn't pull up the ring order to refer if it's closed. 9/5- delviery and dmarc conrimed on 9/4, need to test and close. our due date is 9/11 9/13- order closed and ready for activation, engineer informed.
2012-11-20 | Nyrone | GA008-05-IJ | Atlanta, GA (backup) | 3072 2 xT1 with MD5 UHGVERbgpbqZyofa | smartform 189751142 NSPE0006105395 IQBKFQ0T atl I78122 | 5648336 | P1967764 | 5237220 | 1536 | BCBKXC0V0001-0002 | 38/HCGS/941199//SB 38/HCGS/941200//SB Demarc 6th floor insurance telco room mm2 slot 1 & 2 rj48c tagged not extended |  | 2012-11-29 | 2012-12-14 |  | bpdd | 2012-12-19 | 2012-12-14 | unitedhealthgroup-65043 | 860-702-8284 Keith_mangene@uhc.com | completed with Keith on 12/21 |  | 11/20- send to om 11/29- ASR sent pending FOC 12/6- FOC for 12/14, commit date set for 12/19 12/19- order ready for activation, engineer informed.
2012-11-12 | Nyrone | UK535-01-DJ | Potters Bar UNITED KINGDOM | disco E1 | NSPE0006072565 s/o: 5171769 | 5637515 |  |  |  | W0X83773 | [5 empty] | bpdd | [6 empty] | 11/13- sent to Nyrone 11/15- order to TEV 11/29- CONFIRMED CEASE DATE 27/12/2012 CUSTOMER OWN REF: 5171769 12/28- order disconnected.
2012-09-26 | Beth | CT012-05-CJ | Rocky Hill, CT | Upgrade to 6xT1, 9216 with md5 UHGVERbgpbqZyofa | smartform 189708964 NSPE0005908081 IQBKCSVL OQBKCWVB hrt- I0015161 (completed) | 5577761 | P1738508 (out) P1956030 (IN) | 1898837 | upgrade to 4608 | BCBJ99MC0001-4 (out) BCBKWD170001-6 (in) | /HCGS/782167//SN DEMARC LOC: 4TH FL 14 PACK 4 POS 1 /HCGS/782168//SN DEMARC LOC: 4TH FL TELCO RM 14 PACK 4 POS 2 |  |  | 2012-12-05 | 2012-12-04 | bpdd |  |  | unitedhealthgroup-65152 | 860-702-8284 Keith_mangene@uhc.com | requeseted for 5pm central on 1/2. |  | 9/28-sent to OM 10/4- order sent to provisioning, pending pick up 10/11- escalating for proviisoning pick up 11/8- capacity found, pending ASR. Escalating. 11/15- escalating further for aSR 11/21 FOC for 12/5 12/6- LEC delivered, pending testing. B201212060051 12/10- ready for hotcut. Engineer informed. Completed with Keith on 1/2
2012-09-18 | Beth | AZ012-02-IJ | Tricare Phoenix | 44736, DS3 with md5 TCWVERbgpajs9tbxp | smartform 189701686 CDR201209190043 NSPE0005870463 IQBKCJXW PHX I22315 (closed) | 5565372 | P1954731 | 5209537 | 22000 | BCBKV95S0001 | 23.HFGS.205289..COXC Demarc: ds3 module 2 green Not extended |  |  |  |  | bpdd | `12/26 | 2013-12-28 | UnitedHealth Group-TCW -65426 | 860-702-8284 Keith_mangene@uhc.com | activated with Keith on 1/7 |  | 9/19- submitted to beth. 9/20 pending submission to om 9/27= pending FOC of LEC ASR PON: IQBKCG62FFJSMB01 10/4- pending tie down from cox to issue asr to quest 10/11- local order in redesgin, pending DSX modules, need this infor for tie down 11/8- Email sent to jim.adrean@cox.com to follow up as to when LOA/CFA can be issued for prov to proceed in transmitting asr to lec QWEST. Pending response back. 11/15- COX delivered to customer site, still pending Qwest middle portion ASR, melissa is escalating on that. 11/21- we finally got ths co from cox. sending to access engineering to approve. melissa escalating 11/29- esclating further with provisioning 12/12- removed quest from the design and connecting directly with cox, the local loop that is in place. Working mux message internally. 12/18- mux released, CDD is set to 12/26. Disconnect mux to be worked on 12/19 to allow space for our wiring, we will schedule that on the 10th. 12/27- issue with wiring the mux. Tech couldn't locate equipment. Setting up conf call with tech and provisioning to locate assigments 1/3- Customer will troubleshoot issue and will contact Project Manager for another schedule.. was able to identify the problem, and it's with the customer saw the loop from their demarc but when they face it on the customer direction they cannot see the loop. they need more time to check.
2012-11-12 | Nyrone | UAG01-01-DJ | BUENOS AIRES ARGENTINA | disco E1 | NSPE0006072519 S/O: 5171766 | 5637114 |  |  |  | W0R79102 | [5 empty] | bpdd | [6 empty] | 11/12- sent to Nyrone 11/15- to provisoning 11/29- WE HAVE REQUESTED THIS DISCONNECTION TO TELEFONICA EFFECTIVE 12/28/2012 1/3- followed up on status of disco 1/4- disco completed.
2012-12-03 | Nyrone | CO008-05-IJ | Tricare Colorado Springs CO Backup | 9216, 6xT1 with MD5 TCWVERbgpajs9tbxp | smartform 189759644 NSPE0006147447 IQBKF699 | 5660506 | P1971559 | 9439921 | 4608 | BCBKXM300001-0006 | 26/HCGS/634725 /MS DEMARC LOC: inside terminal, 1st flr, main telco room, cab (b), slot 6/8 26/HCGS/634722 /MS inside terminal, 1st flr, main telco room, cab (b), slot 3/8 26/HCGS/634724 /MS inside terminal, 1st flr, main telco room, cab (b), slot 5/8 26/HCGS/634723 /MS inside terminal, 1st flr, main telco room, cab (b), slot 4/8 26/HCGS/634721 /MS inside terminal, 1st flr, main telco room, cab (b), slot 2/8 26/HCGS/634720 /MS inside terminal, 1st flr, main telco room, cab (b), slot 1/8 |  |  |  | 2012-12-27 | bpdd | 2012-01-07 | 2012-12-27 | UnitedHealth Group-TCW - 65040 | (763) 744-1575, daniel_j_skripka@uhc.com | activated with Dan on 1/16 |  | 12/6- pending om submit 12/13- order with provisioning, pending ASR 12/19- esclating with provsioning for pick up 12/28- order ready for activation, engineer informed.
2012-11-27 | Nyrone | TX012-02-IJ | Wellmed Taft, TX | 10752, 7xT1 with MD5 UHGVERbgpbqZyofa | smartform 189755274 NSPE0006125464 IQBKFYB7 | 5653356 | P1969102 | P1969102 | 1536 | BCBKXG5T0001-0007 | 12/HCGS/608944//GTEC 1ST FLR LAN RM HTUR HOUSING LABELED(E)SLOT 1 NORTHWALL 12/HCGS/608945//GTEC label e SLOT 2 12/HCGS/608946//GTEC label e SLOT 3 12/HCGS/608947//GTEC label f slot 4 12/HCGS/608948//GTEC label f slot 1 12/HCGS/608949//GTEC label f slot 2 12/HCGS/608950//GTEC 1ST FLR LAN ROOM HTUR HOUSING LABELED (F) SLOT 3 NORTHWALL |  | 2012-11-30 | 2012-01-02 |  | bpdd |  |  | unitedhealthgroup-65034 | Deven Patterson 763-744-0696 deven_patterson@uhc.com | completed with Deven on 1/16 |  | 11/28- sent to OM. 12/6- FOC for 12/12, commit 12/19 12/13- Per LEC, the LCON is not in the office when the tech went to the customer location, they met someone named Helen and she did not give the tech an access to install the circu it because she is not aware. LEC needs a better LCONand new due date 12/19- new FOC for 1/2 1/4- called SW80 and talekd to Debbie, per her, the T3 is not yet ready that's why the t1 cannot be completed. Also, per Verizon, customer is not yet ready and need to push the due date 1/10- order is now ready for activation, pendign dmarc.
2012-06-14 | Beth | UMD11-05-IJ | Rockville, mD | Pip DS3 with md5 encryption UHGVERbgpbqZyofa | smartform 182848355 CDR201206140079 NSPE0005544426 IQBJ73ZT CQBKGWXF (to correct port speed) | 5429377 | P1933226 | 5086048 | 4608 | BCBKTHTL0001 | 23/HFGS/011559//CD Demarc:1st FL Main telephone RM rack 2 shelf 5 DSX3 Jack 1 Demarc Match and LCON | 0CS6RD |  | 2012-08-17 |  | bpdd | 2012-08-24 | 2012-08-20 | unitedhealthgroup-64855 | 0091 98100 59326 , Pradeep_yadav@uhc.com | completed 1/4 with Pradeep |  | 6/14- send to OM 6/21- ASR sent ENGINEER HAS CONTACTED LCON, PENDING LCON RESPONSE/AVAILABILIT ON HOLD FOR SITE SURVEY NO SUP REQUIRED AT THIS TIME 6/29- Site visit was set for 6/27, pending requiements and perhaps FOC 7/2- BLDG. MGMT. NEEDS TO PROVIDE POWER(15AMP TWIST-LOCK) FOR THE PLACEMENT OF THE NEW EQUIPMENT.CUSTOMER TO PROVIDE PATH WITH PULL-STRING TO MAIN TELCO ROOM 7/12- FOC for 8/17, Melissa trying to see if site requiremetns are done 7/19- trying to better FOC of 8/17 - C201207160005. Per LEC Order was released to construction on 7/13/12. Will send email to construction to see if we are able to better the due date. Will follow up. 7/26- no better FOC, melissa reachd out to john to see if site requirments are done 8/2- checking on site requirements again 8/9- site requirments are complete, pending FOC of 8/17 8/15- pending FOC 8/17 8/23- local loop installed, pending customer router. 8/28- order ready for activation, engineer informed.
2012-09-06 | Beth | C1549-02-IJ | Neenah, WI change to sec CFA 02D34 OC12 11 APPLWI01 NANHWICEH05 | 44736, DS3 no MD5 encyption | smatform 189694770 CDR201209070050 NSPE0005826399 IQBKB710 new smartform 189749718 new CDR CDR201211190090 IQBKF5FD | 5552309 New tin 5646157 | P1971008 | 5259063 | 3072 | BCBKXL100001 | [5 empty] | bpdd |  |  | unitedhealthgroup-65533 | 763-744-2082, eric_taylor@uhc.com |  |  | 9/14- pending OM submission 9/20 still pending lease approval 10/4- CDR approved, ASR sent 10/11- Per AT&T Called ATT and spoke toBarbara. According to her this has a job code 42(42 business day intervals). Job will complete on Nov. 27 (estimated completion date). And the design date is scheduled on Nov.28.There is a major build required to support this install at the customer premise. The LCON needs to be informed that the LEC engineering team/BIC Engineer should be reaching out to them to coordinate the initial site visit to determine the customer's requirements within the next 10 business days. 11/7- per AT&T they said customer wanted it on a private ring. Checking with Deepa to see what happened. also checking in with John, 11/9- per john waiting back to hear from engineer 11/14- Followed up with John if he wants it on the rign 11/16- john changed order to LOA/cfa 11/21- pending tin submit on new loa 11/29- pending CDR for tin submit, asked PCM for approval 12/5- PCM now approved, pending LD Review 12/12- ASR out, pending FOC 12/18- sent LOA over. pending FOC 12/27- lEC is saying channel 11 is busy, Melissa is double checking with provisioning/LEC 12/28- order supped with correct secondary CFA, pending FOC 1/9- Per John cancel order.
2012-09-24 | beth | II601-02-DJ | mumbai-ind | disco | S/O: 5174442 (port) S/O: 5174444 |  |  |  |  | w0x83355 (port) W0X83487/W0X83488 (Bearer) | [5 empty] | bpdd | 2013-01-08 | 2013-01-08 |  |  |  |  | 9/24- sent to B end team to process. 10/4- OM team needs to enter disco 11/2- per om this needs to be processed via the b end, sent back over to the b end. 11/15- escalating with B end. 11/19- Disconnection request has been raised under OVI # 1-1131153681 11/21- TEV done order progressing 12/6- pendign FOC date 12/12- ORDER MOVED TO CFOC STATUS TERMINATION DATE : 01/06/2013 1/9- disco completed, pending order closure. order in ANOC disco completed 1/8
2013-01-09 | Core | PA055-02-DJ | 600 North 2nd Street Suite 500, Harrisburg PA 17101 |  | disco POTS |  | NSPE0006267687 |  |  |  | POTS – 717-232-2227 |  |  |  |  | bpdd | [6 empty] | Order Number: D0HC22936 Date Due: 01-15-13 Billing Telephone Number:717 232-2227 895 Disconnect Telephone Number: 717 232-2227
2012-10-12 | Deepa | SC012-05-IJ | Columbia, SC | 12288, 8xT1 with md5 UHGVERbgpbqZyofa | IQBKDPRY NSPE0005961412 | 5599277 | P1961064 | 5222496 | 1536 | BCBKWP3R0001-0008 | 34/HCGS/432567//SB 34/HCGS/432568//SB 34/HCGS/432569//SB 34/HCGS/432570//SB 34/HCGS/432571//SB 34/HCGS/432572//SB 34/HCGS/432574//SB demarc info: 1ST FLR MPOEMM 1 SLT 8MM 1 SL T 9MM 1 SLT 10 MM 1 SLT 11 MM 1 SLT 11 MM 1 SLT 13 MM 1 SLT 14M M 2 SLT 2JT=RJ48Ctaggednot extended |  |  | 2012-12-06 | 2012-12-05 | bpdd | 2012-12-06 | 2012-12-05 | unitedhealthgroup- 65229 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja 1/14 |  | 10/26/2012: Order is with provisioning. Waiting for FOC date.1 11/9- pending DS3 Waiver, Melissa sent. Order sent for 17 standard B day interval 11/15 FOC for 11/27, commit for 12/4 11/29- LEC delivered, taking errors on ckt 4:34/HCGS/432570//SB, dispatching lEc to prove dmarc 12/6- order ready for activation, engineer informed 12/17- ETMS TICKET 2012121501149 need to dispatch tech to prove tru demarc on ckts 2 circuits are UP and running,Customer will check cabling issue on the remaining circuits
2012-10-24 | Deepa | UIL11-07-CJ | 200 West Madison, Chicago IL 60606, United States | upgrade to 4608 3xT1 | smartform 189725412 OQBKD72D IQBKD53B CFO I162032 | 5614212 | P1935885 (out) P1963525 (in) | 5091187 | upgrade to 4608 | BCBKTXF00001-0002 (out) BCBKW3WM0001-0003 (in) | 13-BVT-BJK-0015 18TH VERIZONNET POP PIARS 15 65 OF 100 T O ATT NET POP on a SMJKI |  |  |  |  | bpdd |  |  | unitedhealthgroup-64583 | 763/694-7370, masroor_khan@uhc.com | completed with Masrooor on 1/17 |  | 11/2/2012 Order is being processed. 11/21- FOC for 11/27 12/6- order is ready fro hotcut. Engineer infomed.
2012-12-10 | Nyrone | FL700-02-IJ | Jacksonville | 10752 7xT1 with MD5 UHGVERbgpbqZyofa | smartform 189762464 NSPE0006169972 IQBKGKKJ | 5664977 | P1974298 | 9439921 | 4608 | BCBKXTXC0001-0007 | 52/HCGS/770405 /SB DEMARC LOC: 1ST FL SUITE MPOE BK/BRD QD/MT SL 2 52/HCGS/770404 /SB DEMARC LOC: 1ST FL SUITE MPOE BK/BRD DEMARC LOC Continued: QD/MT SLOT2 52/HCGS/770403 /SB DEMARC LOC: 1ST FL SUITE MPOE BK/BRD ML/MT SLOT 14 52/HCGS/770402 /SB DEMARC LOC: 1ST FL SUITE MPOE BK/BRDML/MT SLOT 13 52/HCGS/770401 /SB DEMARC LOC: 1ST FL SUITE MPOE BK/BRD ML/MT SLOT 12 52/HCGS/770400 /SB DEMARC LOC: 1ST FL SUITE MPOE BK/BRD 52/HCGS/770399//SB 1ST FL SUITE MPOE BK/BRD ML/MT SLOT 10 ¦JT=RJ48C |  |  | 2013-01-11 | 2013-01-10 | bpdd | 2013-01-18 | 2013-01-15 | unitedhealthgroup-65032 | 860-702-8284 Keith_mangene@uhc.com | keith verified everything came up on 1/23 |  | 12/13 order with om 12/19- asked that tin be submitted 12/28- order with provisioning, asr created and needs to be sent 1/3- escalating on ASR. 1/11- lec delivered , CDD is 1/18, pending order testing and closure 1/170- order ready for activation, engineer informed
2012-09-13 | B end | UK508-02-IJ | Gloucestershire, UK | 10Mb Ethernet with md5 UHGVERbgpbqZyofa and SOO Letterkenny - circuit ID W0Y12673 | 5143590 |  |  |  | 3072 | W0Z80796 | CWW ORDER REFERENCE: Q5114121-1-1 CWW CIRCUIT REFERENCE : T0564171A TERMINATION: GROUND FLOOR, TRANSPORT ROOOM, EXSTG 4.14 CW CAB 2[MUX:BS20NT841 PORT: 01-14-04]-PRESENTATION: ETH RJ45 |  |  |  |  | bpdd | 2012-12-21 | 2012-11-26 | unitedhealthgrou-65064 | 715-841-7731 sonja_d_mroczynski@uhc.com | Sonja confirmed active on 1/17 |  | 9/13- siva sent to B end to process. 9/26- returned SOF sent to B end. 9/27- asking for order status 10/2-= tech validation done, pending ordering of local tail. 10/4- ORDER SUBMITTED TO C&W FOR 10MB TYPE 5 C&W REF: OM5114121 10/11- pending FOC from C&W 11/6- - Please be advised that we are waiting for the FOC date from the ptt. The service delivery is currently estimated to be 21st Dec 2012 but a lot of it depends on the Tail installation date back 11/12- tail installed and order is progressing. 11/15- e-mailed Barkha about local end test 11/20- dispatch sent to ops for ETE test. 11/26- order now ready for activation, engineer informed.
2012-06-21 | Melissa | n/a | DWDM disconnect |  | MIN-O28197 s/o 5207188 | 5666180 |  |  |  | rw-nsb-w7y-0001 / W0S25529 | [7 empty] | 2013-01-23 |  |  |  |  | pending site survey by ops. 7/12- nsb/llm8 site survey complete. 7/16- I have done Elk River, 511, and NSB. Just need to do Eagan and Plymouth. 8/15- phil is still pending site surveys at plymouth and eagan. 9/6- all site surveys done, pending a couple circuits that phil sees. melissa needs to check them. 11/7- pending meeting with jamie, he has some concerns on the subtended ring. 12/5- we are changing the ring to public. 12/27- working with OE on getting tin assinged. 1/23- order closed, circuit billing ceased
2012-09-17 | Beth | NY004-02-IJ | New York | 4608 3 x T1 with md5 UHGVERbgpbqZyofa | smartform 189701506 NSPE0005869192 IQBKCD8J | 5564745 | P1954016 | 5208469 | 3072 | BCBKV8ML0001-0003 | 32.HCGS.758982..NY BASEMENT TELCO RM RJ48C SLOT 1 OF 4 TAGGED NOT EXT 32.HCGS.758983..NY BASEMENT TELCO RM SLOT 2 OF 4 RJ48C TAGGED NOT EXTENDED 32.HCGS.758987..NY BASEMENT TELCO RM SLOT 3 OF 4 RJ48C TAGGED NOT EXT |  |  | 2012-01-02 | 2013-01-15 | bpdd | 2013-01-15 | 2013-01-21 | unitedhealthgroup-65039 | (91) 9810059326 , pradeep_yadav@uhc.com | per pradeep active on 2/1 |  | 9/20- pending submission by om. 9/27- pending address validation 10/4 Provisioner cannot validate the address of this order in their tool so he tried to validate to address using the main listed #. However, the address that he got has different street #. Please advise if “168 CENTRE ST NEW YORK NY 10013” is the same with this one that he got “183 CENTRE MANHATTAN NY 10013”. 10/8- Per John- The correct address is 168 CENTRE ST, NEW YORK NY 10013, United States The # provided is for our site contact, but that person is not on site. This is a new site for us and we do not have any services on site today. 10/11- ASR sent, pending FOC 11/7- FOC due to copper build, expedite was not accepted. 11/29- pending FOC of 12/3 12/5- date was pushed to 1/2 because of Sandy, trying to find a way to get it in earlier 12/12- per john he needs them by 01/04 at the latest. trying to pull commit in, ticket B201212120052 1/3- LEc didn't delvier, lcon told them to deliver to the 5th floor and there is no riser cable, we are trying to see if it will help to terminate to mpoe. 1/9- need to do pair recovery, no good pairs in the mpoe. tech is dispatching on 1/10 to see if he can recover pairs. 1/16- local circuits delivered, taking errors in QRS pattern for ckt 2 1/21- order ready for activation, engineer informed
2012-08-03 | Beth | CT039-07-IJ | Hartford, CT | 100M type 1 ethernet with md5 UHGVERbgpbqZyofa SMF LC connector type | Per #: 08031212 Project ID: CP25647.00 smartform 189675603 NSPE0005702508 IQBKBGVP (access)/IQBKBGWG(flow) HRT-I15175 ccr 1114850 (closed) 1112869 | 5510414 | P1947691 (access) P1947697 (flow) | 5166040 | 30m | EDBKVSLW0001 (access) BCBKVSMM0001 ( flow) | ea-rxo-rxo-0011 made cross conect from ISG400 Port 1 to customer^s fiber panel on backboard in building telco room T1. Using fibers 3&4 in customer^s fiber riser to their data room. This fiber panel in telco room is our demarc. |  |  |  |  | bpdd | 2012-01-04 | 2013-01-24 | UnitedHealthGroup-65153 | 860-702-8284 Keith_mangene@uhc.com | completed with Keith on 2/4 |  | 9/27 1101902 shipped, 1101917. shipped and ipak created 10/4- 1101902 is engineeing complete, pending ops install. 1101917. is recieved, pending install. 10/10- CCR 1101902 ( Install Overture ISG1400, equipped with OC3 SFPs) pending trunk path, No TPTA capacity. CDR201209190012 re-approved opt2. Mux Message H-TNC910, dependent on two prereq D messages. CCR 1101917. (Reconfigure Fujitsu FLM600 ) dispatch out, scheduled for 10/15 11/7- order supped with Tower 1 Pending CCR completion > Pending local order step to operations > Pending End to end dispatch 11/14- redesign needed for city place 1, completed, order sent for site survey 11/21- new CCR opened for overture. RFT isnt' until 12/.28. We are requesting vp escalation. 11/29- new overture shipped. 12/5- overture prebuild completed and pending install. 12/12- pending overture trunk build 12/18- mux scheduled for trunk 12/27- issue with SNM assingment, pending overture install 1/2- pending ais errors between local and ld network, we can't dispatch the overture until this is cleared. 1/9-overture installed and pingable, working on completeing ER, need rfc test and order closure 1/16- local circuit installed and dmarc notes. pending rfc testing, there was an issue with snm that is now reasolved., send back to ops for testing. 1/23- RFC testing completed, pending ticket for order closure 1/30- order ready for activation, engineer informed.
2012-09-24 | B end | II525-01-IJ | Bangalore, India | 100M ethernet with md5 UHGVERbgpbqZyofa Melbourne - circuit ID W0X83226 | 5174463 (port) 5174464 (access) |  |  | 5294560 | 45000 | W0Z93382 (port) W0Z93383 (access0 | 0008001414312 DEMARK INFO:DP/MDF/PATCH PANEL/JACK PANEL PORT DETAILS* XL HEATH_JP NAG AR PH3 L2 EOS PORT 1 |  |  |  |  | bpdd |  |  | unitedhealthgroup-65038 | (987) 313-9388, anupam_datt@uhc.com | completed with Anupam on 2/12 | 10/4- pending SOF 10/8- SOF generated. 11/7- followed up with Siva on SOF signature 11//16- Siva has sof? 11/21 pending TEV 11/29- need lcon e-mail for RAMESH GANESHAN 12/6- order sent to group to send request to PTT 12/12- pending FOC- requested date Feb 15th from PTT 12/18- pending pTT request. 12/27- 1. AS PER PTT; PHYSICAL WORK HAS BEEN COMPLETED... 2. PROVISIONING ALSO COMPLETED FROM PTT END... 3. NEXT WEEK WE WILL BE INITIATING THE E2E TEST... 1/3- 24 hour test completed, pending order closure 1/9- order ready for activation, engineer inofrmed.
2012-09-18 | Beth | CO008-02-IJ | Tri care Colorado Springs | 44736, DS3 with md5 TCWVERbgpajs9tbxp | smartform 189701508 CDR201209190025 NSPE0005869316 IQBKCG62 | 5564962 | P1954410 | 5209128 | 10000 | BCBKV9F10001 | 74/KQGN/904680//SW DEMARC: FIRST FLOOR FIRE CONTROL ROOM NORT H WALL CABINET 2 SLOT 2 OF 3 TAGGED AND NOT EXTENDED |  |  | 2013-01-25 | 2013-01-25 | bpdd | 2013-01-25 | 2013-01-25 | UnitedHealth Group-TCW -65040 | 763-744-1575, daniel_j_skripka@uhc.com | completed with dAn on 2/13 | 10/11- fup with CDR group on VTA supp 11/8- order in hcus Order was placed on HCUS with the remarks: Until now where not yet clear where to replace the circuit since the building is just a shell as of now, though the LEC is trying to contact several people to know where it should be, the customer needed to be informed regarding this. and ask their advise when willthe circuit be terminated. Plus the requested due date is tomorrow. Please supp customer location is not yet ready. 11/9- Per john he wants to leave at bulding dmarc. order supped, 11/15- no FOC from the lec, Field engineer is going out to do a site survey Friday.. Conduit is existing and pull tape is there. Might need backborad and power. 11/19- john forwarded Sarah mdF layout, she will forward to FE. 11/29- equipment will now be placed in mpoe. firm project shecule to come out on Monday 12/3. Delivery likely won't be until end of Jan. 12/6- current timeline Major Milestones: (May be adjusted due to backlog and volume issues) Site Visit Completed = 11/26/2012 Internal kick off call =12/3/2012 Equipment Engineering and Network Designs issued by = 12/13/2012 Material Availability = 12/31/2012 Fiber job complete = 1/17/2012 Service install, test and turn up (estimated) completed by = 1/25/2012 12/27- all milestones on track 1/3- per century link: Materials are in transit or getting ready to ship out. There are a couple of items I am requesting escalations on to see when they will arrive. 1/8- Per Century link Power and ground are still needed on site. This may affect the FOC date. 1/9- per Dan Ward power and grounding are now there, informed Century link 1/16- fup with Sarah on FE report. 1/23- Service install, test and turn up (estimated) completed by = 1/25/2012 , this is for the build, FOC will be issued later.
2012-03-29 | Beth | UWI05-02-IJ | Onalaska, WI | DS3 with Dport and Dcar MD5 Encryption UHGVERbgpbqZyofa | NSPE0005302533 IQBJ5TLQ smartform 157703832 mad I279 (closed) | 5306462 |  | 5028920 | 8000 | BCBKSDKL0001 | 50/HFGS/182521//CYWI/ Demarc: 1st flr lan rm 4500 terminal 2nd oc3 | 0CSJKG |  |  |  | bpdd | 2012-06-20 | 2012-07-27 | UnitedHealth Group-64680 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 2/11 | 4/11- ASR sent to Windstream to get tie down for AT&T. Pending response. 4/19- escalating for FOC C201204190042 5/3- further escalated for FOC 5/10- escalating, it looks like prov sent another ASR and it's in incomplete status 5/17- prov was pending CFA from other carrier WI16 has been transmitted and is escalated as expedite, im just waiting for FOC. 5/23- both Windstream and AT&T loops are in, issue with CFA. Pending response from Widnstream. Asking for escalation. 5/31- Windstream required a new ASR. no accepting the ACTL, escalting 6/6- escalated further and asked that we escalate further with widnstream 6/14- FOC was issued for 6/13, no delivery, escaltion ticket C201206140606 6/20- issue with the LEC CFA with centruylink. Escalating. 6.27- per Centurylink, they are still working on the facility part of the order 7/5- escalating with centruylink on CFA and facility issue. 7/11- asked for Beth's management's assistance in the escalaation 7/18- escalating further for windstream CFA issue 7/19- Windstream has agreed to redesign the circuit. They are saying 4 b days for that. 1 day for design and 3 days for dispatch. 7/25- Per Centruylink, they are not designed to the new CFA. Escalting further 8/1- order ready for activation, engineer informed.
2012-07-24 | Beth | UOR02-05-CJ | Tigard, OR | Upgrade to 9216, 6xT1 | Smartform 189650394 NSPE0005660954 OQBJ9QF5 IQBJ9MKD | 5491115 | P1405675 (out) P1942175 (in) |  | Upgrade to 6000 | BCBJDB170001-5 (out) BCBKVFJL0001-0006 (in) | 43/HCGS/499830//FTNC/ Demarc1st flr telco room shelf 1 slot 8 of 28 tagged not extended. |  |  | 2012-09-11 |  | bpdd | 2012-09-13 | 2012-09-13 | UnitedHealthGroup- 64902 | 91 91600 84400, harish_kandpal@uhc.com | completed 9/28 | 7/24- submittted to beth 7/26- tin created, pending OS submission 8/2- order with provisioning 8/9- ASR sent pending FOC. 8/15 Frontier jepped ASR asking for a suite 8/23- escalating with provisioning on ASR. 8/29- there wwas an issue with the address, we are using 7632, Frotier cleared all errors on the ASR, we should have FOC in the next couple of days. 9/6- FOC for 9/11 9/13- order ready for upgrade engineer informed.
2012-09-28 | Deepa | UNJ08-07-IJ | Basking Ridge | 100M ethernet with md5 UHGVERbgpbqZyofa | IQBKD313 (EACS) IQBKD46H (flow) | 5610791 | SAR ID: 1-1KR7Y7Z Type 2 : Verizon Telecom Confirmation Code: 022KSH-001 002 firm order Expiration Date: 2/14/2013 No special construction | 5226767 | 44992 | EDBKW2PS0001 BCBKW3DP0001 | .KFGS.301373..NJ DEMARC:FL1 TELCO ROOM RACK MOUNTED BEAS Demark is 1st floor telco room, mounted on backboard, Overture Port 1 tagged not extended |  |  | 2013-01-28 | 2013-01-18 | bpdd | 2013-02-04 | 2013-01-31 | unitedhealthgroup-64541 | 763-744-1556 john_l_rothstein@uhc.com | per john circuit was up on 2/25 | 10/4- pending approvals from Matt 10/10- Matt requested SAR SAR 1-1KR7Y7Z. , pending approval 10/16- SAR received back 11/8- ASR sent, pending response 11/15- PER LEC ENGINEER HAS CONTACTED LCON, PENDING LCON RESPONSE/AVAILABILIT ON HOLD FOR SITE SURVEY NO SUP REQUIRED AT THIS TIME 11/21- lcon has not heard from anyone. melissa asking to escalatie with lec 11/29- engineer is Donavan # 9734225145. 11/6- suppring order to remvoe from CNR. 12/13- this is associated wth a major build. 12/18- donovan left edward a vmail to schedule site visit on 12/13 12/27- still pending site visit. 1/3- Andew is the engineer assigned to this, he visited the site today and they are compiling the site information. 1/9- FOC 1/28, commit 2/4 1/24- loop delivered, BEAS installed, RFC tested, access order closed, pending ticket to close port order. 1/30- EACS closed, RFC test completed, pending closure 2/7- order ready for activation, engineer informed.
2012-10-11 | Deepa | IN015-04-IJ | Lafayette, IN | 3072 2xT1 with md5 UHGVERbgpbqZyofa | smartform 189716369 NSPE0005956649 IQBKC6RK | 5597575 | P1959309 | 5217769 | 1536 | BCBKWLTG0001-0002 | 31/HCGS/647637//FTNC/ 31/HCGS/647638//FTNC/ dmarc shelf 1 slot 6 shelf 1 slot 5 |  |  | 2012-12-21 |  | bpdd | 2013-12-31 | 2013-12-31 | unitedhealthgroup-65168 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 2/26 | 10/26/2012: Order is with provisioning. Waiting for FOC date. 11/8- lec missed delivery- Received a call from Robin @ 765-414-7582 of Frontier She said there is no access to the demarc The person onsite don't know the demarc, it is locked and don't have keys. Robin tried to call the lcon SUSAN SIGLER @ 765-269-2233 but is unassigned numbe 11/15- new FOC received 11/28, new commit 12/5 11/29- per tech number 523-3031 didn't have access to the dmarc. 12/6- asked to have order supped 12/13- ASR supped to redispatch 12.18- new FOC 12/21 12/27- LEC delivered, but not testing well. Frontier is checkign their wiring. 1/3- order ready for activation, engineer informed.
2012-10-24 | Deepa | UMA25-06-IJ (CANCELLED) | 70 INNERBELT RD, SOMERVILLE MA 02143, United States to 109 BROOKLINE AVE, BOSTON MA 02215, United States | 10 gig Metro Private line | 5164581 • BST-I80911 CCR #: 1115644 (ROADM) T7BA-T7AF Degree Add + MS15 3cm 1115134 (ROADM CARD) | 5617242 | pending |  |  | W0Z91013 | / JX-IBR-CIX-0001 |  |  |  |  | bpdd | [5 empty] | 12/13- osp had a call to determine how to support this. Yes. . We are going to use a combination of the Sungard and existing shared ROADM systems to support this requirement. Sean Murphy is evaluating the four existing CCRs to determine which he will keep so we can move the project forward. 12/18- pending build CCR #: 1115134 (ROADM CARD) TGTME T7AF @ cix T7AN @ ibr RFT 2/6 CCR #: 1115644 (ROADM) T7BA-T7AF Degree Add + MS15 3cm RFT 3/22 will try and better due dates. 12/28- bay shipped, pending shipment of cards, trying to get director approval to improve build dates. 1/10- we shoujld have an idea of install dates on the equipment from ops late next week. 1/16- pending update from ops expected 1/18 1/24- Op’s is currently working on finishing the VP escalation( delay encountered due to missing equipment ) this week for another project. Once they complete that project they will begin work on these CCR’s and the Op’s group is saying they will need 8 days to complete their CCR queues, which would be 2/6 and then it will take a week for the CCR to be worked through the remaining queues to close the CCR’s. So at this point we are looking at 2/13/13. As always if there is any opportunity to improve those dates I will push the groups to do so 1/30 - fup with PM to see if ops has started work 2/7- i believe ops is supposed to begin work on 2/8. 2/13- order needs to be cancelled. DId we see that from John? 2/18/13 - Order Supp'd to Cancel in OrderPro 2/21: Order has been canceled.
2012-10-10 | Deepa | UFL75-09-IJ | Miami, FL | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189715310 CDR201210100058 NSPE0005949999 IQBKC5CH | 5596051 | P1959097 | 5216866 | 22000 | BCBKWK7B0001 | 60/HFGS/760351//SB 2520DEMARC: 3rd floor, telephone room relay, rack 03.0100.01 p anel 3, position. Tagged and not extended. , |  |  | 2012-12-28 | 2013-12-27 | bpdd | 2012-01-04 | 2013-01-04 | unitedhealthgroup-64860 | 91 91600 84400, harish_kandpal@uhc.com | per harish complete on 2/28 | 10/11- pendign om submit 11/8- Pending loop delivery due on 12/28/2012 to E2E test order with AT&T. 11/15- still pending LEC delivery 11/21- pending LEC delivery12/28 1/3- Lec delivered, pending order closure. 1/10- order ready for activation. Engineer informed
2012-09-25 | Beth | TX023-05-IJ | 1311 President George Bush Tollway Richardson, TX | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189705766 CDR201209250072 NSPE0005893862 IQBKCMM1 dal-I0090057 new smartform 189766488 new cdr CDR201212170048 new NSPE0006198928 new IQBKGJNY | 5572454 new tin 5673723 | P1955450 | 5280413 | 22000 | 44736, DS3 with md5 UHGVERbgpbqZyofa | 50/HFGS/882895//SWDL Demarc: 1st flr,telco closet walmount E panel 1, position 3 and 4, rj48x, not e xtended. |  |  | 2013-01-17 | 2013-01-18 | bpdd | 2013-02-04 | 2013-01-18 | unitedhealthgroup-64517 | 763-744-1847, donald_r_osborn@uhc.com | completed on 3/4 with Don. | 9/25- submitted to oM 10/4- ASRs sent, pending FOC GT10 CLARIFICATION RETURNED FROM LEC NOT QUALIFIED FOR REQUESTED SERVICE DUE TO EXCESSIVE DB LOSSPLEASE CANCEL ASR. , sent over to CDR for new path 11/7- CNR cleared, still pending FOC, esclating with prov for fup 11/15- CCR #:1107073 for ds3 cards, RFT 11/27. escalating further for FOC C201211150034. Pon has a pending foc, I called the lec and spoke with Lisa and as per her, the pon has a pending job due to lack of ds3 capacity. And they already sent out an information about the job to Janet Wilson and sw60 is waiting for the reply of janet regarding this. 11/21- called janet and left vmail 11/29- this is tied to the other Richardson build. no site requirement, need to place equipment with splicing and need co equipemnt. 12/6- pending dS3 ports in CO, asking to have this escalated. 12/13- pending foc 12/18- Melissa realized she ordered to the 1301 address, not the 1311 address, new order being placed with an internal expedite 1/9- order placed on hold for backboard or shelf 1/10- per john back board in place. order supped, FOC date of 1/17 1/24- order closed, engineer informed. 2/20 - Received IVUE Conf for Activation date of Mar 4th @ 5:00PM CT -
2012-09-28 | Beth | UWI29-05-IJ | Green Bay, WI on secondary CFA of N50AMO OC12 1 GNBYWIGBH00 GNBYWI11 | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189709308 CDR201209280056 NSPE0005909369 IQBKCY68 | 5578524 | P1957548 | 5212886 | 22000 | BCBKWHFB0001 | 41/HFGS/101000//WT Demarc: 1st flr telco rm relay rack 3 dsx shelf 1 position 5 |  |  | 2013-01-24 |  | bpdd | 2013-01-31 | 2013-01-24 | unitedhealthgroup-64990 | 715-841-7731 sonja_d_mroczynski@uhc.com | sonja turned up on 3/5 | 10/4-Om submitted 10/11- provisioning has and is working 11/8- provisioning has and is pending FOC 11/15 FOC for 11/20, escalating for CDD C201211190027 11/20- pending mux, escalating, per John, no need to esclalate this one, Dan Bartlett needs to discuss the mux. he turned away the LEC yesterday. 11/29- need to re-issue ASR. 12/6- ASR issued on the first, pending foc 12/13- LEC came back and asked for a re-issue asr, asking prov for that 12/18- LEC ASR sent on 12/13. pending response 12/27- asking provisioning to escalate on ASR. 1/3- the SCFA provided on the LOA/CFA (attached) isn’t working per the LEC. Sent to John. 1/9- FOC for 1/24 1/24- lec not delivered as of 1pm CST. 1/30- order closed, engineer informed
2012-09-18 | Beth | UFL73-04-IJ | Jacksonville, FL | 3072, 2xT1 with MD5 encryption UHGVERbgpbqZyofa | smartform 189700790 NSPE0005864571 IQBKCCWK | 5563305 | P1953775 | 5208089 | 2048 | BCBKV7430001-0002 | 52/HCGS/769603//SB DEMARC LOC: 4TH FLOOR EQUIPMENT ROOM QUAD MOUNT # DEMARC LOC Continued: 2 SLOT 1 52/HCGS/769604//SB DMARC 4th floor equiptment room quad mount 2 slot 2 , RJ48C. Not extended |  |  | 2012-10-17 | 2012-10-17 | bpdd | 2012-10-24 | 2012-10-19 | unitedhealthgroup-64742 | 91 91600 84400, harish_kandpal@uhc.com | completed on 3/1 with harish. | 9/20- pending submission by om. 9/27escalating for ASR B201209270072 10/4- ASR sent. foc will be received within 3 days. thanks, 10/4- FOC 10/17, commit 10/24 11/8- order ready for activation, engineer informed. 11/29- per harish need to reschedule. wiring issues at the site.
2013-02-15 | Ken | UMN99-42-CJ | Plymouth, MN | Downgrade from 10Gb to 1GB | NSPE0006425943 |  |  |  |  | U311943 | jy-nsb-jcfg-0001 |  |  |  |  | bpdd | [5 empty] | 2/14 - Downgrade from 10Gb to 1Gb. 2/18 - Customer requests put on HOLD until they decide how to move forward with this order - Confirmed Out order pending 'Go Ahead' 3/7- order not valid, UHG will place a new 1 gig circuit and disco this one once this one.
2012-10-12 | Deepa | VA060-05-IJ | Reston, VA | 44736, DS3 with md5 UHGVERbgpbqZyofa | IQBKC88J | 5599301 | P1959861 | 5219303 | 4608 | BCBKWMV30001 | 23/HFGS/011790//CD DEMARC=MAIN TELCO 1ST FL . DSX PNL.1, JK.4 EXTENDED TO 4TH FL. LAN RM. OPN COAX 1 2 TAGGED VZB |  |  | 2012-01-30 |  | bpdd | 2013-02-06 | 2013-02-06 | unitedhealthgroup-65176 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 3/7 | 10/26/2012: Order is with provisioning. Waiting for FOC date. 11/02/2012: ASR Sent.Pending FOC Date. 11/9- There are end user contingincies. Trying to get the details. 11/15 forwarded John EU requirements 11/16- per john they are doing the site requirements 11/29- site requirements are now complete. order supped 12/6- per LEC site not ready VZ:E/U:,JAMEEL ALAHMED,571-262-8919 PATH;APPROVAL FROM BUILDING MANAGEMENT FOR ANY AND ALL VERIZON NEEDS TO ACCOMPLISH TO PROVIDE SERVICE TO THE CUSTOMER.;,SPACE FOR THE DS3 HA,SEE COMPLETE EUCR IN EWPTS, Melissa informed John 12/13- per Cathy they did decide to go to mpoe. asked to have order supped. Site is now ready 12/18- escalating with provisioning on supp 12/27- FOC for 1/30= trying to better due date. LEC order is with construction 1/2- The due date is still set for the EWO to complete is 1/22/12. Once the ewo is completed then we will be able to work with dispatch to better the date. 1/10- Pending DLR from LEC to schedule MUX H-TNT678 DLRD: 01242013 1/16- patching send to field, pending lec delivery of 1/30. CRDD is 2/6 1/30- lec not yet delivered 2/7- order ready for actiation, engineer informed.
2012-11-05 | Deepa | TN027-07-CJ | Chattanooga, TN | upgrade to 4608, 3xT1 | smartform 189738388 NSPE0006056099 IQBKFLXX OQBKFMQ9 | 5628138 | P1880289(out) P1966648 (in) |  | upgrade to 3072 | BCBKNKWM0001-2 (out) BCBKW9YL0001-0003 | T1/HCGS/829062//SC Demarc: 1ST FLR SERVER RM QUAD MT POS 2 RJ48X EXT WRNG N-NOT ORDERED |  |  | 2012-12-10 |  | bpdd |  |  | unitedhealthgroup-65237 | 763/694-7409, terry_bjorke@uhc.com | completed wih Terry on 3/12 | 11/7- order sent to OM. 11/15- esclating for OM submit 11/21- order to provisioning 11/29- FOC for 12/10 12/13- order ready for hotcut, engineer informed.
2012-11-05 | Deepa | C1246-05-IJ | El Segundo, CA | 44736, DS3, with MD5 encryption UHGVEReccgas4Usp9 | smatform 189738496 CDR201211130021 NSPE0006056346 IQBKFMS0 lsa-I127226 | 5628266 | P1966952 | 5235212 | 128 | BCBKXBGG0001 | 3x-8sh-6hr-0015 - Dmarc is the DSX3 at RR.2.2.3:20 - Savis makes all x-connects from the transport room. |  |  | 2012-11-27 |  | bpdd | 2012-01-07 | 2013-01-18 | uhg-ecc-65458 | scott_moyer@uhc.com; 763-744-2154 | completed with Scott on 3/12 | 11/12- LOA needed for CDR approval. Informed John. 11/14- lOA obtained and new CDR created, pending tin submission 11/21- order on-net sent to ops. On-net completion set for 11/27 11/29- order sent to re-design per tech comments 12/6- oder re-designed , send for dispatch 12/13- question on design again. escalating with provisioning 12/19- design issue esolved. Field tech working on cross connects 12/28- local loop delivered, asked to have order tested. C201212280006 1/3 the order is on TENT status due to pending for MUX HTOY149: revision. Provisioning is working on it 1/10- eslcalting on mux design 1/16- mux complete, sent to install for testing. 1/18- order ready for activation, engineer informed.
2012-10-03 | Deepa | UNJ20-05-CJ | East Windsor, NJ | upgrade port to 6144 4xT1 | smartform 189712038 NSPE0005926670 IQBKCYKX OQBKCZXJ New Order Nos IQBKHQ4Z OQBKHXH9 | 5584683 New Tin 5720923 | P1957381 (in) |  | upgrade to 3072 | BCBKRFGJ0001-3 (out) BCBKWG4S0001-0004 (in) | .HCGS.802138..NJ BSMT tel,RM tel,TEL RM ,RJ48C,LP Y,CAB N,RCK 1,SLOT 20,rj48c |  |  | 2012-10-25 |  | bpdd |  |  | unitedhealthgroup-64927 | 91 91600 84400, harish_kandpal@uhc.com | completed with harish on 3/11 | 10/3- sent to OM. 10/4- pending oM submit 10/11- order with provisoning, pending ASR 11/8- ASR sent, LEC is asking for clarification, 11/15- escalating for details on clarification 11/21- B201211210014 for missed foc 10/25 11/27- ready to schedule for hotcut. Engineer informed. 2/19 - Called Customer (J. Sergot and requested Activation (Upgrade) date - Pending response - 3/1- DESIGN IS NOT YET COMPLETED ON THE TIME OF THE CUT HYP TEAM CREATED MECCA TICKET TO RESOLVE THE ISSUE 3/7- rescheduled
2012-10-24 | Deepa | CA047-02-IJ | 34800 BOB WILSON DR, SAN DIEGO CA 92134, United States | 4608 3xT1 with mdf encryption UHGVEReccstr82tcW | NSPE0006012238 IQBKD2LT SND-I0018927 | 5614195 | P1962530 | 5224997 | 3072 | BCBKW1VL0001-0003 | 19/HCGS/612836//PT DEMARC LOC: CCB BK 24 POS 48 19/HCGS/612837//PT DEMARC LOC: CCB BK 25 POS 55 19/HCGS/612838//PT DEMARC LOC: ccb block 25 position 56 DEMARC LOC Continued: |  |  | 2012-12-05 |  | bpdd | 2012-12-12 | 2012-12-13 | UnitedHealth Group-TCW - 65393 | 860-702-8284 Keith_mangene@uhc.com |  | 11/2/2012 Order is being processed 11/9- ASR sent to MFS so we can get CFA to send to aT&T 11/15- clarification on address, supping order 11/21- escalating ASR 11/29- FOC for 12/5, commit 12/12 12/6- LEC delivered, Called ATT to get the demarc for the 3rd CKT. Spoke with Perry, according to her she can't find the demarc, tester will find dmarc and test 12/13-order completed, engineer informed.
2012-12-18 | Nyrone | HI003-03-IJ | Tricare Honolulu | 3072, 2xT1 with md5 TCWVERbgpajs9tbxp | smartform 189769056 NSPE0006208768 IQBKGVM9 | 5677066 | P1977282 | 5300321 | 2048 | BCBKX0Y00001-0002 | 82.HCGS.111866..HAWT 8th flr mechanical room backboard shelf 2 positions 1 rj48c tagged and not extended 82.HCGS.111867..HAWT 8th flr mechanical room backboard shelf 2 positions 2 rj48c tagged and not extended |  | 2013-01-08 | 2013-01-16 | 2013-01-16 | bpdd | 2013-01-23 | 2013-01-23 | UnitedHealth Group-TCW - 65363 | 763-744-2077 robert_a_benson@uhc.com |  | 12/28- pending globalink from Siva 1/3- tin submitted. 1/11- ASR sent on 1/8 PON: IQBKGVM9XEZSMB01 VER: 01 sent to HW10 validated address and CFA at cameo once accepted foc can be received within 3BD 1/16- LEC delviered, pending testing and closure CDD 1/23 1/25- order closed , Robert informed.
2012-12-12 | Nyrone | FL070-02-IJ | Jacksonville | 44736, DS3 with MD5 UHGVERbgpbqZyofa | Smartform 189777410 CDR201301070036 NSPE0006257624 IQBKGY66 | 5690310 | P1978317 | 5306960 | 9216 | BCBKX2R20001 | 52/HFGS/703494//SB Demarc: 1st flr equip rm. rr1 panel 1 jack 4 |  |  | 2013-02-14 | 2013-02-14 | bpdd | 2013-02-27 | 2013-02-27 | unitedhealthgroup-65031 | 860-702-8284 Keith_mangene@uhc.com | keith accepted circuit on 3/19 per e-mail. | 12/13 need good lcon 1/4- John provided LCON 1/7- order submitted 1/10- order in provisioning, pending ASR. 1/17- escalating on ASR 1/24- pending LOA from fibernet TO XCONECT WITH AT&T, due 1/25 1/30- FOC date is 2/14, asked to have commit set C201301300044 2/15- LEC not yet delivered. 2/20- Loop delivered. Pending MUX completion on 2/27/2013 2/27- order complete, engineer informed.
2013-02-25 | Melissa | C1396-04-CJ | Tampa | ASN change |  |  |  | 3029041 |  | BCBKMV1B0001-0005 P1869077 | [5 empty] | bpdd |  |  | UHGECC- 65498 | eric taylor | completed 3/19 with Eric | 3/7- pending hotcut
2012-10-15 | Deepa | UWI28-05-IJ | 2725 MALL DR, EAU CLAIRE WI 54701, United States | 44736 DS3 with mdf encryption of UHGVERbgpbqZyofa | IQBKD2H7 | 5610788 | P1962467 | 5224966 | 22000 | BCBKW1SG0001 | 42/HFGS/100242//WT demarc: 1ST FLR SERVER ROOM DS3 SHELF 1 JACK 1 |  |  | 2013-02-01 | 2013-02-01 | bpdd | 2013-02-08 | 2013-02-04 | unitedhealthgroup-64534 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 3/19 | 11/2/2012 Order is being processed. 11/02/2012: Order is with provisioning. 11/8- esclating for provisioning pick up 11/15- FOC for 12/26- CODE 37; 8891637 SPLC FIBER AND PLC EQUIP PREM, NO CO WORK, asking for commit\ 12/6- Base on ATT spreadsheet job ECD is still 12/19, job issued to construction. 12/13- per lec customer needs to place twistlock. per Sonja that won't be installed until after freeze 1/16- new FOC for 2/1, pending commit 1/24- Mux HTOD750 has been scheduled. CDD of 2/08/2013 has been set 2/19- Ready for activation
2012-10-24 | Deepa | UNY26-05-CJ | New York, NY | Upgrade to 6144 4xT1 | smartform 189725880 NSPE0006013041 IQBKD54F OQBKD71L | 5614391 | P1640361 (out) P1963529 (in) | 1778324 | upgrade to 3072 | BCBJ1DLC0001-2 (out) BCBKW3WY0001-0004 (in) | 32.HCGS.762446..NY DEMARC LOC: FLR 6 DEMARC LOC Continued: 32.HCGS.762448..NY DEMARC LOC: FLR 6 DEMARC LOC Continued: |  |  | 2012-11-27 |  | bpdd | 2012-12-02 |  | unitedhealthgroup 64752 | (91) 9810059326 , pradeep_yadav@uhc.com |  | 11/9- Foc for new loops 11/27. 11/29- C/NR. They tried to dispatch yesterday but the LCON refused to give them an access, and they tried to call the LCON today but it was just a voicemail. They are requesting for an alternative LCON, sent note to johnn 12/5- Robert Cho is correct LCOn, needs a call a day before FOC. order supped 12/13- lec delivered, not testing well Added 898. please verify wiring and optioning. Taking errors to QRS pattern from the wbdxc 12/18- new loops tested. order ready for upgrade. Engineer informed. 2/12- supp to cancel submitted once complete, disco can be placed. 2/13 TIN SUPPED TO CANCEL 3/7- order cancelled, disco can be submitted 3/11- Disco was submitted on 2/15, order # OQBKJF7X, due 3/14 disconnect order completed on 3/14
2013-02-20 | Ken | FL063-02-IJ | Pembroke Park, FL | 1536, T1 with MD5 UHGVERbgpbqZyofa | smartform 189813822 NSPE0006458252 IQBKJN34 | 5761643 | P1991509 |  | 1280 | BCBKYV750001 | 60/HCGS/447863//SB |  | 2013-03-04 | 2013-03-15 |  | bpdd | 2013-03-22 |  | unitedhealthgroup- 65030 | 763/694-7370, masroor_khan@uhc.com |  | 2/25- submitted to OM 3/7- FOC for 3/15, commit 3/22 3/13- John submitted cancel.
2013-02-20 | Ken | FL063-02-IJ | Pembroke Park, FL | 1536, T1 with MD5 UHGVERbgpbqZyofa | smartform 189813822 NSPE0006458252 IQBKJN34 | 5761643 | P1991509 |  | 1280 | BCBKYV750001 | 60/HCGS/447863//SB |  | 2013-03-04 | 2013-03-15 |  | bpdd | 2013-03-22 |  | unitedhealthgroup- 65030 | 763/694-7370, masroor_khan@uhc.com |  | 2/25- submitted to OM 3/7- FOC for 3/15, commit 3/22 3/13- John submitted cancel.
2013-02-14 | Ken | n/a | Elk River, MN | disconnect | Proquest NSPE0006420238 5225435 |  |  |  |  | W0Y07923 | [5 empty] | bpdd | 2013-03-06 | 2013-03-19 |  |  |  | 2/14 - Disco Order Submitted - 2/25- disco due on 3/6 3/7 order is pdis status 3/13- ticket opened to get order to closed. 3/20- order disconnected on 3/19
2012-04-04 | Beth | UTN18-07-IJ | Brentwood, TN | DS3 with Dport and Dcar MD5 Encryption UHGVERbgpbqZyofa | smartform 159706657 CDR201204100004 NSPE0005333070 IQBJ54FL | 5328415 | P1920258 | 5050123 | 10752 | BCBKSKJB0001 | C9BPTGF7 - Demarc: 1st fl electric room 247.28 panel 2 jack 10 extended: No | 0CSL01 |  | 2012-06-06 | 2012-06-08 | bpdd | 2012-06-22 | 2012-06-08 | UnitedHealthGroup-64804 | 763/694-7370, masroor_khan@uhc.com |  | 4/10- submitted to OM 4/19- pending provisioning approval, escalation C201204190049 5/.3- provisioning has, pending issueing ASR 5/10- escalating for ASR C201205100056 • Order is still pending LOA from LC20 • Once the LOA is provided then provisioner will send ASR to SW80 • Provisioner is sending a ff-up email to Valerie Sykora of Level 3 and asked for an updates. 5/17- CALLED LEVEL 3 AND SPOKE WITH KARLOS NETWORK BUILD WHICH IS NOT SCHEDULED TO COMPLETED 05/25/2012 VENDOR FOC DATE OF 06/06. SEND EMAIL TO DAN FROM LEVEL 3 ASKING FOR INFORMATION ON THE ORDER. PUTTING TICKET ON WORKING AND PROVIDE UPDATE ON 05/18/2012 5/23- no improvement on FOC of 6/6 6/6- LEC still has not delivered as of 4pm Central 6/14- order closed on 6/8, engineer informed.
2011-11-10 | beth | M0331-08-IJ | Austin, TX | 3072, 2xT1 | NSPE0004913634 IQBJ0XXD | 5117424 | P1885545 |  | 1280 | BCBKNYRH0001-0002 | 32/HCGS/686596//SW DEMARC LOC: CAB 5 SLT 8 DEMARC LOC Continued: Extended Wire (Yes or No): YES EW Reason/Location:3RD FL SERVER RM Jack Type: RJ48C 32/HCGS/686597//SW DEMARC LOC: MAIN TELCO CAB 5 SLT 11 | 0CQ3ZG 0CQ3ZF |  |  |  | 12/27/2011 no access new foc 1/9 | 2012-01-04 | 2013-01-16 | UnitedHealthGroup- 65102 | 763-744-1847, donald_r_osborn@uhc.com | completed with Don on 3/22 | 12/1- order with proisioning, issue with address valdating with AT&T systems, escalating 12/7- supped order with building 1 12/15- pending LEC foc of 12/27 12/29- LCON wasn't available to give LEC access, order needed to be supped, new commit date is 1/20. new FOC is 1/9 1/4- telco delivered, testing. B201201050076 1/6 ready for activation, engineer informed.
2012-10-03 | Deepa | UGA09-05-CJ | Norcross, GA | upgrade port to 10752 7xT1 | smartform 189711952 NSPE0005926598 IQBKC3BQ OQBKC5C2 | 5586997 | P1579050 (out) P1958585 (in) | 1668541 | upgrade to 4608 | BCBJT5PH0001-6 (out) BCBKWJ9J0001 -0007 (in) | 38/HCGS/939633//SB . Demarc: STE 300 TELCO RM MM#2 SLOT 9 RJ48C |  |  | 2012-12-24 |  | bpdd |  |  | unitedhealthgroup-64578 | 91 91600 84400, harish_kandpal@uhc.com | completed with Harish on 3/22 | 10/3- sent to OM. 10/10- submitted by OM 10/11- pending OE 11/8- order needed to be supped to cancel and re-issue. 11/15- ordet put on hold, not able to get a hold of the lcon, melissa also left the lcon a message. 11/21- new foc for 11/29 11/29- as of 2pm central, lec had not delivered yet 12/6- Per Coreen of ATT, LCON wasn't able to provide access during the dispatch yesterday, tagged as missed appointment, asked to have order supped 12/13- new FOC for 12/24 12/27- LEC missed delivery, ticket B201212270040 12/31- loop delivered, opened testing ticket B201212310010 1/3- order ready for upgrade engineer informed.
2013-01-30 | Ken | na | Chaska MDF 800 LLM8, 06. | 10 gig pl move Plymouth end to Elk River SR1 | 5222471 MIN - C31985 (closed) CCR 1135315 (closed) | 5739811 |  |  |  | W0Y51076 | JX-JCFG-M6L7-0002 new JX-LLM8-M6L7-0008 |  |  |  |  | bpdd | 2013-03-17 | 2013-03-17 |  |  | Steve was going to try and activate on 3/20 | 2/7- sent to os group to work 2/14: Ops approved 2/13 2/19 - Being Provisioned - 2/28- asking local design about CDRs 3/7 CCR 1135315. ROADM Transponder Card / OADM Card Adds , equipment received, stepped for site survey 3/13- new cards installed and loops for testing placed in ELR 3/20- new link ready for activation
2013-01-30 | Ken | na | Chaska MDF 700 LLM8, 07 | 10 gig move Plymouth end to Elk River SR3 | 5222459 MIN- C31984 (closed) CCR 1135299 (closed) | 5735459 |  |  |  | W0Y51078 | JX-JCFG-M6L7-0001 new JX-LLM8-M6L7-0007 |  |  |  |  | bpdd | 2013-03-17 | 2013-03-17 |  |  | Steve was going to try and activate on 3/20 | 2/7- sent to os group to work 2/14: Ops approved 2/13 2/19 - Being Provisioned - 2/28- asking local design about CDRs 3/7 CCR 1135315. ROADM Transponder Card / OADM Card Adds , equipment received, stepped for site survey 3/13- new cards installed and loops for testing placed in ELR 3/20- new link ready for activation
2012-10-22 | Deepa | UMD10-05-CJ | Elkridge, MD | upgrade to 10752 7xT1 | smartform 189725534 NSPE0006013068 IQBKD5TH OQBKD5SM BLT I29891 | 5614186 | P1826530 (out) P1963444 (in) | 1669075 | upgrade to 4608 | BCBKJ3L70001-6 (out) BCBKW3P50001-0007 (in) | 38.HCGS.981811..CM DEMARC LOC: GND flr TEL RM SHELF 1,SLOT 7,not extd.per lcon. DEMARC LOC Continued: |  |  | 2012-11-08 |  | bpdd | 2012-11-30 |  | unitedhealthgroup-64926 | (987) 313-9388, anupam_datt@uhc.com | completed with Anupam on 3/25 | 11/9- FOC for 11/8, loops not yet delviered 11/15- LEC delivered, pendign closure 11/21- order ready for upgrade. Engineer informed.
2012-11-12 | Deepa | USC03-05-IJ | 107 Westpark Blvd., Columbia SC | 3072 2xT1 with MD5 UHGVERbgpbqZyofa | smartform 189742372 NSPE0006071938 IQBKFL4Y | 5643434 | P1966707 | 5233563 | 1536 | BCBKW92N0001-0002 | 34/HCGS/432672//SB SBData room suite 110 multi mt 1 position 1 RJ4 8C not extended 34/HCGS/432672//SB SBData room suite 110 multi mt 1 p osition 2 RJ48C not extende |  | 2012-11-29 | 2012-12-12 | 2012-12-13 | bpdd | 2012-12-14 | 2012-12-14 | unitedhealthgrou-64575 | 763/694-7370, masroor_khan@uhc.com | completd with Masroor on 3/25 | 11/15- pending tin from om 11/21- pending ASR 11/29- ASR sent, pending foc 12/6- FOC date for 12/12. commit date of 12/14. 12/13- LEC delivered, testing 12/19- order ready for activation, engineer informed.
2012-10-15 | Deepa | UMO21-05-IJ | 1930 W BENNETT ST, SPRINGFIELD MO 65807, United States | 44736 DS3 | IQBKDY25 | 5610785 | P1961775 | 5223571 | 22000 | BCBKWY9X0001 | 84/HFGS/020571//SW DEMARC: 1st flr telco cab DSX panel 1 pos 4 not ext. |  |  | 2012-11-13 |  | bpdd | 2012-12-12 | 2012-11-30 | unitedhealthgroup-64630 | (987) 313-9388, anupam_datt@uhc.com | completed with Anupam on 3/26 | 10/26/2012: Order is with provisioning. Pending FOC. 11/02/2012: FOC recived 11/13/2012. 11/7- pending mux. 11/15- LEC delivered, trying to find different equipment to replace the existing equipment which is keeping the MUX unschedulable 11/21- new mux done, order sent to install 11/29- mux complete, sent to install for test and closure. 12/6- order ready for activation, engineer informed.
2012-09-24 | Beth | UTN13-05-IJ | Kingsport, TN | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189705760 CDR201209250070 NSPE0005893676 IQBKCPYM | 5572452 | P1955450 | 5210733 | 9216 | BCBKWCXD0001 | 50.HFGS.798847..UIMN Demarc: 3f computer room tagged:Yes |  |  | 2012-11-26 | 2012-12-13 | bpdd | 2013-01-23 | 2013-01-25 | unitedhealthgroup-64921 | 763/694-7370, masroor_khan@uhc.com | enabled with Masroor on 3/28 | 9/25- submitted to oM 9/27- pending tin submission 10/4- provisioning has and is working 10/11- escalating for pip port capacity 11/8- FOC for 11/26, asked Deepa to open a commit date ticket 11/15- escalating for CDD ticket C201211150031 11/29- CFA is busy, Sprint is checking with lease vendor. We got a CNR on 11/27 12/6- we supped for new CFA. LEC waiting for facilities, internal transport before completed, ETA 12/14/2012 12/13- This order is in jeopardy due to a pending order to install the transport. Therefore this order can not be engineered until the new facility is installed. No ECD at this time." This install is on the LEC side. 12/18- LEC delivered, we need to test on our side. 12/27- escalating for testing 1/3- orde rwill test on 1/4 1/4- roder did not test, esclaating 1/10-mux is needed. 1/16- wiring scheduleing, commit 1/23. 1/24-pending order closure, escalating 1/29- order is ready for activation, engineer informed.
2012-09-21 | Beth | UMD14-05-IJ | Baltimore, MD | 6144, 4xT1 with md5 UHGVERbgpbqZyofa | smartform 189704334 NSPE0005888351 IQBKCJXX | 5570729 | P1954732 | 5209538 | 4608 | BCBKV95T0001-0004 | 38.HCGS.981402..CM DEMARC LOC: BLDG MAIN 1st flr telco room cabinet 1 slot 1, rj48c 38.HCGS.981403..CM DEMARC LOC: BLDG MAIN, Ground flr telco rm mounting 1 slot 2 rj48c 38.HCGS.981404..CM DMARC=GND,RM 1,TEL RM ,RJ48C,LP N, CAB N,MNTG 1,SLOT 3 . 38.HCGS.981405..CM DEMARC LOC: BLDG MAIN/TELco RM ,RJ48C,MNTG 1,SLOT 4, |  |  | 2012-11-06 |  | bpdd | 2012-11-13 | 2012-11-27 | united healthgroup- 64935 | (987) 313-9388, anupam_datt@uhc.com | completd with Anupam on 3/28 | 9/27- pending ASR 10/4- asr sent, pending response 10/11- escalating for FOC B201210110052 11/8- LEC delivered, pending order closure 11/15- escalating for order closure 11/20- retest the circuit and still getting errors in qrs pattern and for circuit #3 38 .HCGS.981404..CM. unable to loop smjk. TT opened 11/29- order ready for activation, didn't get all damrc info from the lec. 12/5- got other dmarc and sent to anupam. we are working to schedule for next week. 2/21 - - Order ready for acitvation.
2012-10-12 | Deepa | WI011-05-IJ | Wausau, WI | 44736, DS3 with md5 UHGVERbgpbqZyofa | IQBKDFDP CDR201210120063 | 5599282 | P1960380 | 5220284 | 25000 | BCBKWNR60001 | 39/HFGS/660667/FTNC telco rm north wall rj48c |  |  | 2013-01-10 | 2013-01-11 | bpdd | 2013-01-17 | 2013-01-17 | unitedhealthgroup-65284 | 715-841-7731 sonja_d_mroczynski@uhc.com | completed with Sonja on 3/28 | 10/26/2012: Order is with provisioning. Waiting for FOC date. 11/02/2012: ASR Sent.Pending FOC Date. 11/2- ASR sent requesting 11/20, pending FOC, ticket B201211090004 11/15- escalating to upper management for FOC.\ Called Lec for foc and as per the rep foc went out last 11/05 however the foc didn’t went in on our system, I’ll have the foc details on this and I will proceed on this 1. FOC will be for 11/20, commit will be for 11/27 11/21- opening up missed FOC for 11/20 11/29- LEC delivered, they require a supp for testing. escalating. 12/6- per lec no supp needed, pending foc date 12/13- escalting with provisionign on asr issue, foc is 12/17, need to update foc. 12/18- escalating further with provisioning, frontier is now saying they need a supp. 12/27- frontier is now sending another CNR, asking for that information. 1/3- escalating why the order is in CNR 1/10- DLR obtained from frontier, pending mux. supposed to complete 1/11, Melissa following up ontaht. 1/16- LEC delivered, we are testing on our side. 1/24- order complete 1/17, engineeer informed.
2012-09-07 | Beth | MS010-05-CJ | Ridgeland, MS | Upgrade port and Gold CAR to 6144, 4 x T1 and 3072 | smartform 189695484 NSPE0005830610 IQBKJRHJ OQBKJRHH | 5552307 | P1776302 (out)_ P1992050 (in) |  | 4608 | BCBKFBWX0001-002 (out) BCBKV60X0001-0004 (in) | M1/HCGS/435105//SC DEMARC LOC: 1ST FLR TELCO, PANELBOARD, DUEL MT DEMARC LOC Continued: SLOT 1 M1/HCGS/435106//SC -1st flr telco panel dual mount slot 2 rj48c not e xt taggedsent |  |  | 2012-10-19 |  | bpdd | 2012-10-23 |  | unitedhealthgroup- 64713 | 763/694-7370, masroor_khan@uhc.com | masroor accepted all on 4/3 | 11/20- We are still having problems testing the new circuits. We are taking QRS errors and need to test head to head with AT&T. 11/28- Bill CO TUPLMSMAK41 Ticket #: 2012111705373 -per him he already checked their wiring/optionings and they were all good -retested the ckt but took immediate errors to smjk on Qrs patterns -he monitored the ckt and he's also seeing errors -per him ckt passes first on Jackson CO (JCSNMSCPK43) then on their CO w/c is the Tupeulo Co (TUPLMSMAK41) -per Bill, he will coordinate w/ jackson Co to isolate where the trouble is comi ng from,and they will call us back for further testing.. 12/5- order ready for upgrade. Engineer informed. 12/12- activation failed, we could loop the smjk but not the csu. Customer to have vendor check inside wiring. 3/7- original order was cancelled because it took so long for re-schedule. new order issued, Melissa is asking if this is ready to schedule. 3/13- asked masroor for re-schedule.
2012-05-31 | Beth | UMA07-07-IJ | Waltham, MA | Pip DS3 with md5 encryption UHGVERbgpbqZyofa | Smartform 177832933 CDR201205310053 NSPE0005498705 IQBJ7MTDC bst I79411 | 5411232 | P1930222 | 5078641 | 6144 | BCBKS8CH0001 | 95.HFGS.640438..NE 2nd floor telphone room adc channel position 1 of 4 tag both id not exten ding. |  |  | 2012-10-04 | 2012-11-01 | bpdd | 2012-10-30 | 2012-11-02 | unitedhealthgroup-64930 | 91 - 98100 59326, pradeep_yadav@uhc.com | completed with Pradeep on 4/3 | 7/26- Micheal Hart 781-376-8170. is the engineer. I told him karen is now aware and they can reach out to her to schedule the site survey. he said they would reach out to her and try and get out there early next week. 8/1- I spoke to micheal, They did the site survey on 7/31 and a mux will need to be placed. There is an existing rack, so no customer site requirements at this time. he said he just needs to change the order status so the ASR will update. 8/9- LEC FOC for 9/24. BTDD ticket C201208090006 . commit 10/1 8/14- build with Fiber placing and splicing, Equipment Placed and installed. Facility available date is 9/17. 8/23- Plant materials has been ordered as per update by regional. Facility available date is 9/17. Next update: ticket on hold 8/30 as OSP build has not yet started 8/30 still pending OSP build 9/6- Pending CXM Dispatch. 9/13- talked to engineering, power is needed for a wall mounted mux. They can't place the mux in the existing cabinet, it would put too much stress on the existing rectifier, so they are goign to wall mount it in the mux, power just needs to be provided. 9/20-pending power for the new mux. Customer needs to provide power. 10/4- per john power should have completed last week, ASR PON IQBJ7MTDG1YRMB01 WAS SUPPED TO PUSH OUT DUE DATE TO 10/22 REQUIRED BY LEC 10/10- pending FOC on 10/22 date, per Mike H The 1st order per SR 02117H-001 with PON IQBJ7MTDG1YRMB01 (MCI request) is associated with SO# C5XC8261 and has a FOC of 11/02/2012. 11/7- order completed and engineer informed.
2012-10-04 | Deepa | AZ008-05-IJ | 4425 East Cotton Center Blvd. Phoenix, AZ | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189712870 CDR201210050033 IQBKC5F4 | 5597568 | P1959126 | 5216910 | 22000 | BCBKWK790001 | 14/HFGS/975439//MS 1st flor server Room rr 200 shelf 5 position 1 of 3 |  |  | 2012-12-28 | 2013-01-29 | bpdd | 2012-01-07 | 2013-01-29 | unitedhealthgroup-65154 | 702-303-7293, tauoa.falo@uhc.com | completed with Tauoa on 4/4 | 11/16- per e-mail from Qwest PM; CenturyLink field engineer, Stephanie Embry, will be in touch with Jason Nelson to set up a time for the site visit. Stephanie will need access to the main telco room in the building to verify the fiber count and equipment cabling. Once we have that information, I can set a timeline for getting the service turned up. 11/21- site survey happened on 11/20, Melissa asking pm about results 11/29- Melissa followed up with Judy to see about project schdule on AQCB. 12/6- Melissa will ask pm again per call to century link said order still on design still waiting for facility. none ECD as of the moment 12/13- LEC status: as per CenturyLink project manager: Today is just the inst all of the shelf and card, another tech will complete the test and turn-up. still on track of the due date 12/28. FOC 12/28 1/3- LEC missed delivery- Called Judy Lewis(Project Manager) and asked for the order status for this PON:IQBKC5F4D9MSMB01.As per Judy,design has been comleted and she will verify this one today.Once verified,she will sent out dispatch and will delivered the loop toVZN.ETA for Loop delivery is early next week 1/10- e-mailed Judy lewis at Century link las, lec status is LEC status: Order is in Engineering-Hold; Order in AQCB status = Waiting for "Funding Code" no change on status 1/16- as per CenturyLink project manager: The technician is at t he location today to turn up the higher level OC3 circuit and I am pushing the DS3 design to get it completed so we can get it turned up after the tes ting is done on the OC3. The testing usually takes about 48 hours to compl ete, the tech will let me know when his work is completed 1/24- there was an issue turning up the OC3 with the fiber pairs, they were defective, this was resolved and they are working on getting a tech out to trun up the Ds3 today or tomorrow. 1/30- order ready for activation, engineer informed.
2012-10-04 | Deepa | AZ009-05-IJ | 1 East Washington Phoenix, AZ | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189713058 CDR201210050044 NSPE0005935640 IQBKC29L | 5588455 | P1958573 | 5215319 | 9216 | BCBKWJ8V0001 | 56/HFGS/108979/TWCS Demarc: 7th Flor, Customer Server Room, Wall mounted, Ds3 Niu Shelf #1, Slot1 Tagged and Labelled: Yes |  |  |  |  | bpdd | 2012-12-06 | 2012-12-05 | unitedhealthgroup-65140 | 702-303-7293, tauoa.falo@uhc.com | completed with Tauoa on 4/4 | 10/5 sent to OM 10/11 order with provisioning 11/7- asr sent, pending FOC. 11/15 per lec end user didn't allow access for lec site survey. Melissa called LCON and he said he allowed them access yesterday, they apparently needed to visit again to check fiber connections. Erroneous HCUS, supping to remove and re-dispatch tech. 11/21- time warner put the order back in hold saying no access. Tech Wesley called john at (602) 255-8307. Melissa also called John to see if he heard from Time warner 11/29- order supped to re-dispatch 12/6- order ready for actiation, engineer informed
2012-05-29 | Beth | TX013-02-IJ | 1301 W PRESIDENT GEORGE BUSH HWY Richardson, TX | Pip DS3 with md5 encryption UHGVERbgpbqZyofa | Smartform 176769392 CDR201205300014 NSPE0005492114 IQBJ7K0H ATT fiber CDR CDR201207310016 dal I89223 | 5409957 |  | 5076929 | 12288 | BCBKS7NK0001 | SW60/SBC/C586199 1ST FLOOR MAIN TELCO CLOSET WALL MOUNT PANEL 1 PORT 7 AND 8 |  |  | 2013-01-22 | 2013-01-16 | bpdd | 2013-02-01 | 2013-01-16 | unitedhealthgroup-65070 | 763-694-7370, masroor_khan@uhc.com | Masroor accepted the circuit on 4/8 | 8/28- ammendment recieved, order supped with new cdr 9/10- ticket resolved and order sent to provisioning, pushing to have them pick up 9/20- ASR sent to AT&T, pending FOC. 9/27- escalating for FOC 10/4- added to executive escaltion, AT&T is saying scid is full, we are escaltating with them. 10/10- ATT is escalating internally, on the executive escalation list 11/7- Pre-test on LD and LOCAL hand offs are clean and good. Pending/ Issues: LEC Loop Delivery Date is on 11.16.2012 Will do the end to end test once LEC loop stepped to completion 11/14- still pending LEC deliver on 11/16 11/21- missed loop C201210160024. Received notice from our ATT OMC management POC and was advised that this order is held up due to a new OC12 installation. At this time they are escalating to have the equipment be shipped the soonest possible time so that they can move this order forward to completion, escalating with AT&T and asked to have this added to the VP list 11/29-ATT OMC leadership and was advised that the OC12 installation has been tagged an ECD of 12/21/12 however they are escalating this order to have the ECD be given an improved DD to area managers level at this time. 12/5- site is pending site requirements. Power and Backboard, Per john the engineer is working on it and there is no ETA. 12/12- Still pending site requirements. The engineer is working with Donald Osborne/UHC and Donald is aware of the requirements. From the information I received, the requirements for the address at 1301 is below. Donald also relayed to the engineer that the site requirements might not be completed before year end.” 1301 W President George Bush Hwy: 1 - L5-15R Twist-lock Outlet 1/16- order ready for activation, engineer informed. 2/20 - Customer requested Mar 4th @ 5pm CT activation - Submitted IVue Request Form for Mar 4th, 5PM CT Activation
2012-10-24 | Deepa | C1414-05-IJ | 1355 S 4700 W, , SALT LAKE CITY UT 84104, United States | 44736 DS3 with mdf encryption of UHGVEReccgas4Usp9 | smartform 189725788 IQBKD2LN | 5614191 | P1962527 | 5224995 | 128 | BCBKW1VJ0001 | 64/HFGS/137676//MS Demarc: FL 1 BLDG MAIN STE SEELCON |  |  | 2013-03-05 | 2013-03-05 | bpdd | 2013-03-12 | 2013-03-06 | uhgecc- 65457 | scott_moyer@uhc.com; 763-744-2154 | per Scott Active on 4/5 | 12/28- have provided the requisite information on the build requirements to the FieldEngineer.\He will establish the site survey with the end user and supply me with the necessary documentation once survey has been completed. This build requires placement of equipment at end user location. 1/10- following up with Centurylink pM. 1/15- per LEC PM I m trying to get a call together to expedite this project because we found existing equipment that might work for this circuit. I ll update further when I know more. 1/24- per lEC PM: the multiplexer is installed. We are currently running power but this is running into problems we hope to have them resolved quickly. The job is still on track for the completion date. melissa trying to find out completion date. 1/24- per lec pm We had assumed that the end user s closet had the correct power, but found that the power had actually been brought in from another room on a different floor ofthe building. We have had to order additional equipment and we have expedited that order. We should receive the equipment next week. I have already asked t he building manager to provide AC power for the new equipment. This was requested on another customer s job. 2/1- per john power will be in late next week. 2/7- pending update from Centurylink. Added to the VP list. 2/13- power is in and order supped 2/17 - Order Supp'd for BPDD - 2/19- FOC is 3/05/2013 2/27- commit date is 3/12
2013-02-26 | b end | UUK04-06-DJ | MAIDENHEAD UK | Disconnect 20M circuit | SR # 1-1168548205 s/o 5232318 |  |  |  |  | w0z04077 W0Y67746 (bearer) (bearer) W0Y67749 (NNI) W0Z04077 (port)) | [5 empty] | bpdd | 2013-04-01 |  |  |  |  | circuits will be cancelled April 1st. 4/3- disconnected as of 4/1
2012-10-03 | Deepa | UCA89-09-CJ | Concord,, CA | upgrade port to 6144 4xT1 | smartform 189711950 NSPE0005926475 IQBKJJLS OQBKJKCC OAK C0009358 | 5584626 new tin 5746972 | P1990279 (in) | 1997436 | upgrade to 3072 | BCBKHW5H0001-3 (out) BCBKYTHH0001-0004i(in) | 86/HCGS/775259//PT DEMARC LOC: NIU AT MPOE O.1, SHELF 10, SLOT 12 DEMARC LOC Continued: SLOT 12 |  |  |  |  | bpdd |  |  | unitedhealthgroup-64611 | 91 91600 84400, harish_kandpal@uhc.com | completed 4/5, order closed 4/10 | 10/3- sent to OM. 10/4- pending oM submit 10/11- pending OE 11/8- LEC delivered, pending dmarc info 11/15- order ready for upgrade, engineer informed. 2/15 - Encapsulation needs to be changed to MLPPP - 2/21 - Order being pushed thru Internal Expedite process - Requesting a 3/06 Install date - 2/17- new orders sent to provisioning 2/27- pending prov pick up 3/7- confirming if ready to re-shedule 3/13- pending hyperlink ticket for capacity 2013031302820 4/10 order completed, pending clossure
2012-10-10 | Deepa | UFL68-05-IJ | Oldsmar, FL | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189715240 CDR201210100048 NSPE0005949420 IQBKC3WK | 5596042 | P1958743 | 5215864 | 22000 | BCBKWKL10001 | 69/HFGS/305506//GTES Demarc: 1/f server room, verizon bay, labelled as verizon-02, jack 3, not ext |  |  | 2012-12-17 |  | bpdd | 2012-12-24 | 2013-01-04 | unitedhealthgroup-64660 | 91 91600 84400, harish_kandpal@uhc.com | completed with Pradeep on 4/10 | 10/11- order sent tp provisioning\ 11/8- site engineer contacted lcon with no response. 11/15- order place on hold for no return call from the Local contact Melissa also called and left a voicemail from the local contact asking if he has heard from anyone from Verizon. Also informed John S. Alternate contact is Cory Smiton at 813-818-5518. 11/20- ASR supped pending FOC 11/29- escalating for FOC. 12/6- issue with CFA on ASR. Escalating with provisioning 12/13- LEC FOC 12/17, asked to have commit set C201212130032 12/14- DM asked to have mux scheduled. 12/17- commit date set to 12/24 12/18- lec didn't deliver, late access loop ticket opened 12/27- pending network ticket on our side. LEC delivered, need dmarc notes 1/3- vendor meet at colo complete. Cabling is now done as per field tech. He asked to place comments below on this order for future reference: TMP DSX3 xconns have now been completed between VZB and VZT CFA FOT-200/01/JK14.. actual assignment within VZB node is Vert 22D/ jack #4 which is an in-house tie cable to VZT telecomm closet @ CXR 201 Panel 5 / JK4.... Panel 5/ JK4 is then xconn'd to CXR 201/ Sh.1/ JK14 (FOT-200 G5-2). Panel has now been tagged in VZB node above Vert 22D 1/10- order ready for activation, engineer informed.
2012-10-24 | Deepa | NJ050-05-CJ | 170 WOOD AVE S, ISELIN NJ 08830 2704, United States | upgrade to 10752 7xT1 | smartform 189725720 OQBKD5RX IQBKD41N | 5614187 | P1506377 (out) P1963230 (in) | 1644135 | 3072 | BCBJM08H0001-3 (out) BCBKW29L0001-0007 (in) | /HCGS/803093 /NJ DEMARC LOC: FLR 3RD DEMARC LOC Continued: Extended Wire (Yes or No): No /HCGS/803092 /NJ DEMARC LOC: FLR 3RD DEMARC LOC Continued: HCGS/803091 /NJ DEMARC LOC: FLR 3RD /HCGS/803094 /NJ DEMARC LOC: GND,RM tlc,TEL RM ,RJ48C,LP N,CAB N,SHELF 1,POS 18,dmarc |  |  | 2012-11-27 |  | bpdd | 2012-12-04 |  | unitedhealthgroup- 64585 | (91) 9810059326 , pradeep_yadav@uhc.com | completed on 4/11 with Pradeep. | 11/2/2012 Order is with provisioning. 11/15- FOC is for 11/27, commit is for 12/4 11/29- LEC delivered, pending testing. 12/6- order is ready for hotcut. Engineer informed
2012-06-04 | Beth | UIN05-03-IJ | Indianapolis, IN | 1536, T1 | Smartform 178984662 NSPE0005507188 IQBJ7VGG IND- I13541 | 5418794 | P1931722 | 5082131 | 1280 | BCBKTCNC0001 | /HCGS/744739//NB DEMARC LOC: FIRST FLOOR TELCOROOM SHELF 2 SLOT 6 DEMARC LOC Continued: SLOT 6 | 0CS4D1 |  | 2012-06-22 |  | bpdd | 2012-06-29 | 2012-06-20 | UnitedHealthGroup-64776 | 763-694-7370, masroor_khan@uhc.com |  | 6/4 submitted to OM 6/7 tin created, pending om submission 6/14- FOC for 6/22, our commit date is 6/29
2012-06-22 | Beth | C1544-01-IJ | Eden Prairie | 6144, 4xT1 | smartform 189621296 NSPE0005575118 IQBJ8K20 MIN I33469 | 5444263 | P1935139 | 5089634 | 1536 | BCBKTV6R0001-0004 | 15/HCGS/229071//NW DEMARC LOC: 1ST FLR MPOP - CABINET 1 - SLOT 1 OF 8 DEMARC LOC Continued: 15/HCGS/229073 /NW DEMARC LOC: 1ST FLR MPOP - CABINET 3 - SLOT 3 OF 4 15/HCGS/229072 /NW DEMARC LOC: 1ST FLR MPOP - CABINET 3 - SLOT 2 OF 4 15/HCGS/229074 /NW DEMARC LOC: 1ST FLR MPOP - CABINET 3 - SLOT 4 OF 4 DEMARC LOC Continued: |  |  | 2012-07-16 | 2012-07-10 | bpdd | 2012-07-23 | 2012-07-11 | UHGECC-65468 | nicholas_cooper@uhc.com |  | 6/29- Tie down infor provided, pending ASR to the LEC> 7/5- LEC FOC for 7/16. our commit date is 7/23 7/12- order closed and ready for activation, engineer informed.
2012-10-03 | Deepa | UNC17-07-IJ | Cary, NC | 3072, 2xT1 with md5 UHGVERbgpbqZyofa | smartform 189712962 NSPE0005934442 IQBKC3CR RAL I9155 | 5588478 | P1958596 (in) | 5215332 | 1536 | BCBKWJ960001-0002 (in) | 13-bggv-hzdh-0005 13-bggv-hzdh-0006 Room telco rm DSX1 1.1.5:4.tx DSX1 1.1.5:6. Hard loop left at demarc |  |  | 2012-11-16 |  | bpdd | 2012-12-13 | 2012-12-11 | unitedhealthgroup-65108 | 214-647-4442 don_r_osborne@uhc.com | completed with Don on 4/15 | 10/5 sent to OM 10/11- ASR sent, pending FOC 11/8- order in in HCUS because of no response from the LCON. Per LCON she wasn't called, need to set up another call 11/15 order sent for re-dispatch. 11/21- order set for dispatch today. Tech john miles couldn't get a hold of TAMMY AULT @ 919-677-5993 . melissa is also reaching out to her 11/29- tech re-dispatched 12/6- circuits delivere, pending testing and closure 12/13- order ready for activation, engineer informed.
2013-02-04 | Ken | SG501-02-IJ | 5736714singapore | disconnect | 5220902 |  |  |  |  | W0W40030 | [6 empty] | 2013-04-15 | 2013-04-10 |  |  |  | RFS DATE: FEB 28, 2013 SINGTEL LAST BILL DATE: MARCH 21, 2013 3/28- pending wiring removal 4/30 disconnect complete, pending order closure 4/10- escalating for disconnect closure 4/18- verified order was discoed and backdated to the 10th
2012-10-10 | Deepa | FL054-05-IJ | Miramar, FL | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189715308 CDR201210100057 NSPE0005949781 IQBKC4L2 | 5596050 | P1958932 | 5215987 | 22000 | BCBKWKXX0001 | SB04/ATT/CQ76 T4B9 1st floor telco room suite 100 westel cabinet prov 1 and 2 tagged not extended |  |  |  |  | bpdd | 2012-12-04 | 2012-12-05 | unitedhealthgroup-65215 | 91 91600 84400, harish_kandpal@uhc.com | completed with Harish on 4/18 | 10/11- pendign om submit 11/8- LEC delivered, pending order closure 11/15- escalating for orde rclosure. 11/27 commit date. C201211150039 11//29- there appears to be some trouble with testing with AT&T, Melissa escalating with install 12/6- order ready for activation, engineer informed.
2012-10-24 | Deepa | ULA06-05-IJ | Baton Rouge, LA | 3072 2xT1 with MD5 UHGVERbgpbqZyofa | smartform 189725372 NSPE0006012219 IQBKD41Z | 5614216 | P1963233 | 5225847 | 2688 | BCBKW29S0001-0002 | L0/HCGS/386462//SC L0/HCGS/386463//SC 7TH FLOOR TELCO ROOM,QUAD MOUNT SLOT 3Q UAD MOUNT SLOT 4,TAGGEDJT |  |  | 2012-11-21 |  | bpdd | 2012-11-30 | 2012-12-04 | unitedhealthgroup 64712 | (91) 9810059326 , pradeep_yadav@uhc.com | activated with Pradeeep on 4/24 | 11/9- ASR sent, pending FOC 11/15- FOC for 11/21. commit for 11/30 11/29- lec delivered, issues with testing 12/6- order ready for activation, engineer informe.d
2012-09-10 | Beth | MI008-01-IJ | Ann Arbor, MI | 1536, T1 with MD5 encryption UHGVERbgpbqZyofa | smartform 189695698 NSPE0005832455 IQBKB9NC | 5552258 | P1952100 | 5199800 | 1280 | BCBKV6410001 | /HCGS/567230//MB DEMARC LOC: INSTLL SMT JK LOWER LEVEL TELCO RM DEMARC LOC Continued: TELCO RM SHF 3 SLOT 1 OF 7 |  |  | 2012-10-02 |  | bpdd | 2012-10-05 | 2012-10-04 | unitedhealthgroup-65045 | 763/694-7409, terry_bjorke@uhc.com |  | 9/14- provisioning has order and is working it. 9/20 SUPP TO CANCEL: IQBKB4JDA ORDER AUTO OPS APPROVED WITH AN I25 NODE WHICH IS DECOMMISSIONED, UNABLE TO FIND CAPACITY AT THE SAME POP. New order IQBKB9NC 9/17- FOC for 10/2, commit 10/5 10/4- order ready for activatin, engineer informed.
2013-03-11 | Ken | KY010-04-IJ | Louisville, KY- need April 9th, people moving in on the 26th. | 12288, 8xT1 md5 encryption UHGVERbgpbqZyofa | smartform 189824168 NSPE0006521911 IQBKJ6LW | 5781445 | P1994991 | 5339132 | 10000 | BCBKY3TM0001-0008 | K1/HCGS/419573//SC DEMARC LOC: 3RD FLR ELECTRIC RM CAB#5 SLOT 2 K1/HCGS/419574//SC DEMARC LOC: 3RD FLR ELECTRIC ROOM CAB#5 SLOT 3 K1/HCGS/419575//SC DEMARC LOC: 3RD FLR ELECTRIC RM CAB#5 SLOT 4 K1/HCGS/419576//SC DEMARC LOC: 3RD FLR TELCO CLOSET CAB#5 SLOT 1 K1/HCGS/419577//SC DEMARC LOC: 3RD FLR TELCO CLOSET CAB#4 SLOT 1 K1/HCGS/419578//SC DEMARC LOC: 3RD FLR TELCO CLOSET CAB#4 SLOT 2 K1/HCGS/419579//SC DEMARC LOC: 3RD FLR TELCO CLOSET CAB#4 SLOT 3 K1/HCGS/419580//SC DEMARC LOC: 3RD FLR TELCO CLOSET CAB#4 SLOT 4 |  | 2013-03-25 | 2013-04-08 | 2013-03-25 | bpdd | 2013-04-09 | 2013-04-09 | unitedhealthgroup-65021 | 763/694-7409, terry_bjorke@uhc.com | Per Terry active on 4/26 | 3/14- Order with OE 3/20- escalting with provisioning on ASR. 3/25- ASR sent 3/28- FOC for 4/8, commit for 4/9 4/10- order ready for activation, engineer informed. 4/25- 7 or the 8 T1s are active, working on getting the last one opeational
2012-10-22 | Deepa | UNC24-05-CJ | Charlotte, NC | upgrade to 4608 3xT1 | CW: 189725524 OQBKD5QG IQBKD406 | 5614178 | P1796679 (out) |  | upgrade to 1536 | BCBKGWWT0001-2 (out) BCBKW29C0001-0003 (in) | 22/HCGS/491132//SB 5th floor main phone room mm1 slot 4 RJ48c tagged not extended |  |  | 2012-11-21 |  | bpdd |  |  | unitedhealthgroup- 64926 | (987) 313-9388, anupam_datt@uhc.com | 5/6/2013 06:00:00 PM Central Time | 11/9- FOC for new loop is 11/21 11/29- lec delivered, need loops tested. 12/4- order is now ready for hotcut. Engineer informed. 5/6- hotcut completed Customer Name / Number: Anupum Datt 987-313-9388
Disconnect |  |  | ELR to Trumbull EPL | disconnect | NSPE0006629528 s/o 5254105 MIN-O0028898 (clsd) BRP-O0000891 |  |  |  |  | W0V64266 | [5 empty] | bpdd | 2013-04-28 |  |  |  |  | 4/19- pending LEC 4/25- disco due 4/28 5/3- disco completed on 4/29
2012-06-19 | Beth | UCA92-04-CJ | Santa Ana, CA | Change - encapsulation TO PPP | CW: 189625754 NSPE0005592030 CDR201206290008 CQBJ819K | 5453480 |  |  |  | bcbjglv30001 | [8 empty] | unitedHealthgroup-64822 |  |  | 6/29- tin submitted to beth 7/5- order is still with OM/Os 7/12- pending provisioning pick up. 7/19- there is a flow through error, esclating with OE 7/26- escalating with prov and OE 8/2- order re-marketing approved. 8/9- encapsulation change is now ready to schdule
2012-11-19 | Nyrone | OH006-05-CJ | Dayton, OH | Upgrade to 4xT1, 6144 | smartform 189750516 NSPE0006100826 OQBKFRJ4 IQBKFQZQ | 5648326 | P1562156 (out) P1967749 (in) |  | upgrade to 3072 | BCBJS1BS0001-003 (out) BCBKXCY60001-0004 (in) | 98/HCGS/227555//OB DEMARC LOC: SH 5 SL 1 OF 4 IN THE 4TH FL TELCO CL DEMARC LOC Continued: TELCO CLOSET |  | 2012-12-04 | 2012-12-17 |  | bpdd |  |  | unitedhealthgroup-65277 | 763-744-2077 robert_a_benson@uhc.com |  | 11/20- sent to OM 11/29- with provisioning, pending asr 12/6- pending FOC for 12/17 12/19- order ready for upgrade. Engineer informed. 5/7- John asked to have order cancelled 5/8- order cancelled
2012-07-24 | ShaRita | NM020-05-CJ | Albuquerque , NM | Upgrade to 12288, 8xT1 | Smartform 189650694 NSPE0005695001 IQBJ9YLP (in) OQBJ95QM (out) | 5507506 | P1945206 (in) |  | Upgrade to 4608 | BCBJVV660001 -2 BCBKVLJ40001-0008 | 54/HCGS/036275//MS DEMARC LOC: MAIN TELCO ROOM 1ST FLR CAB #3 SLOT 1 OF 14 54/HCGS/036276/ /MS DEMARC LOC: MAIN TELCO ROOM 1ST FLR CAB #3 SLOT 2 OF 14 54/HCGS/036277//MS DEMARC LOC: MAIN TELCO ROOM 1ST FLR CAB #3 SLOT 3 OF 14 54/HCGS/036279//MS DEMARC LOC: MAIN TELCO ROOM 1ST FLR CAB #3 SLOT 5 OF 14 54/HCGS/036280//MS DEMARC LOC: MAIN TELCO ROOM 1ST FLR CAB #3 SLOT 6 OF 14 |  |  | 2012-09-04 |  | bpdd |  |  | UnitedHealthGroup- 65232 | 91 - 98100 59326, pradeep_yadav@uhc.com |  | 7/24- pending smartform ticket 8/2- submitted to OM 8/9- order with OE 8/14- provisoning has it and is working on it. 8/23- Records ASR sent to lec PON IQBJ9YLPULFJMB02 Install ASR sent to lec PON IQBJ9YLPULFJMB04 Once accepted, FOC will be received in 3 BDs. 8/29- FOC for new circuits is 9/4 9/6- order ready for hotcut, engineer informed. 5/10- hotcut completed on 6/11/12. pradeep yadav @9810059326 confirms that circuit is up and processing t raffic and accepts this circuit.
2012-09-26 | ShaRita | UPA08-05-CJ | Johnstown, PA | upgrade 4xT1, 6144 | CW: 189797566 NSPE0006374298 IQBKH4L2 OQBKH5C0 smartform 189709078 NSPE0005908160 IQBKCSPS OQBKCWQN | re-issue 5734653 5577764 | P1955998 (in) P1734777 (out) | 1894690 | upgrade to 4608 | BCBJ92PM0001-2 (out) BCBKYL2T0001 -4 (in) | ckt 3 = 14/HCGS/708510 /PA ,C6FQ80975 / AC052418 DMARC=2ND FLR TELCO RM HSE A SLOT 15 OF 28 RJ48CTAGGED. NOT EXTENDED ckt 4 = 14/HCGS/708511 /PA ,C6FQ80976 / AC052419 DMARC=2ND FLR TELCO RM HSE A SLOT 18 OF 28 RJ48CTAGGED. NOT EXTENDED |  |  |  |  | bpdd |  |  | unitedhealthgroup-64554 | 763-744-1556 john_l_rothstein@uhc.com |  | 9/28-sent to OM 10/4- order sent to provisioning, pending pick up 10/11- provisioning has pending ASR 11/8- ready for upgrade 2/4- didn't go, need to change encapsulation to MLPPP, 2/14 - OS is supping order to 2/27/13 - Pending Confirmation - 2/15- order is to provisioning to change encapsulation 2/19-Order in process with provisoning 2/21: Requested update from provisoning. 2/27- ASR sent on 2/26, should be ready to schedule once ASR is acceppted 3/7- order ready to re-schedule, informed John 4/18- ticket opened for dispatch on the address issues 2013041812449 4/22- order ready to re-schedule. Informed John. 5/17- Customer, John Rothstein, confirmed that circuits are up and running properly. Notes in our system show order as completed. Notes from 5/6 Called customer (John Rothstein) and he confirmed that all 4T1 are UP.Vdds file completed and send email to requesting to supp the order. (MARTILLANO,MONROE)
2012-10-04 | ShaRita | UAZ54-05-CJ | Tucson, AZ | upgrade to 4608 3xT1 | CW: 189712946 NSPE0005934527 IQBKD1MG OQBKD1MJ | 5588456 | P1958597 (in) P1396026 (out) |  | upgrade to 3072 | BCBJCP120001-2 (out) BCBKWJ970001-003 (in) | 16/HCGS/736030 /MS DEMARC LOC: 1st flr mn 'it' Extended To 6th flr telco mnt 1 slot 1 of 1 DEMARC LOC Continued: Extended Wire (Yes or No): yes Jack Type: rj48c |  |  |  |  | bpdd |  |  | unitedhealthgroup-64584 | 702-303-7293, tauoa.falo@uhc.com | they provisioned these on 3 new loops, cut happened, but only up on 1 of the 3, Tauoa was going to get the cable vendor out to wire up the other 2 to bring the entire port up. We then can upgrade the gold car | 10/5 sent to OM 10/11- order with provisioning 11/8- SUPP TO CANCEL ORDERS: IQBKC3CSA / OQBKC4BNA SUPP TO CANCEL AND REISSUE REASON: THE ORDER WILL BE CANCELLED AND REISSUED SINCE IT WAS OPS APPROVED USING BLENDED PATH CAPACITY YET PRIOR SENDING THE ASR WHEN WE CHECKED THE CAPACITY PROVIDED BY AE IT WAS NO LONGER SPARE SO WE ASKED THEM 11/15- ready for upgrade engineer informed. 5/17- hotcut completed 5/8/2013. Customer Name / Number: Tauoa Falo @ 702-303-7293
2013-01-11 | B end | AK002-03-IJ | Elmendorf AFB, Alaska- Tricare | 3072, 2xT1 PIP md5 TCWVERbgpajs9tbxp | Smartform 189793398 ecost opportunity 1119750 NSPE0006351548 BEARER S/O 5219300 port s/o 5219297 IQBKH2X1 | 5721427 |  | 5336720 | 1280 | W1A14238 (Ds1) W1A 14239 (ds1) (port) | GCI T1'S CKT ID'S: HC/157642 HC/157643 demarc shown below: Second Floor Comm Room BASE HOSPITAL BUILDING ROOM 2A-107 RJ48x JACKS on side of rack. Labeled with GCI and Verizon circuit numbers. |  | 2013-02-25 | 2013-03-14 | 2013-03-14 | bpdd | 2013-03-20 | 2013-03-20 | UnitedHealth Group-TCW - 65443 | (763) 744-1575, daniel_j_skripka@uhc.com |  | 1/14- send to OM 1/24- pending globalink 1/30- ecost received, order submitted to OM 2/7- order sent by OM 2/13 - Being Provisioned - Pending FOC req DD 4/11/2013 2/20- TICKET S6799258 to correct Z Location 2/28- escalating with provisioning on ASR status 3/4- Request sent to GCI on 2/25 3/7- GCI FOC is 3/14 3/20- order ready for activation, engineer informed.
2013-01-17 | B end | CN520-06-IJ | Toronto, Ontario, Canada | 6144 4xT1 UHGVERbgpbqZyofa | MLPPP PORT: 5249135 MLPPP BEARER: 5249136 | 5801981 |  | 5350042 | 4608 | W1A26870 (port) bearers W1A26866 W1A26867 W1A26868 W1A26869 | 02/DHXX/013863/UCN/001 02/DHXX/013865/UCN/001 02/DHXX/013867/UCN/001 02/DHXX/013869/UCN/001 DMARC ON 27TH FLOOR SUITE 2700. SERVER ROOM WALL MOUBNTED SLOT 1 OF 4 POS PAIRGAIN 2 OF 4, 3 OF 4 AND 4 OF 4. |  |  |  | 2013-04-26 | bpdd | 2013-05-18 | 2013-04-26 | UnitedHealth Group-64593 | 763/694-7409, terry_bjorke@uhc.com | requested 5/13 at 5pm Central | 1/17- siva sent over for SOF 3/22- Siva sent SOF to John 3/26- signed SOF over to B end. 3/29- Siva asked if we wanted to bill in country, John is pending a response. 4/3- orders now in process, lcon is turning our tev calls down because the aT&T circuit was installed, asked John to intervene. 4/10- TEV done, pTT request sent 4/18- PTT due date is 4/26, site visit is set up for today 4/25- pending PTT delivery 4/26 4/26- order ready for activation, engineer informed.
2013-02-06 | ShaRita | NY020-02-IJ | Rye Brook, NY *** | 12288, 8xT1 with MD5 UHGVERbgpbqZyofa | proquest 189799746 NSPE0006387650 IQBKHY05 | 5732224 | P1985715 | 5325553 | 4608 | BCBKYJF10001-0008 | 32.HCGS.774625..NY DEMARC LOC: FLR 3,RM hall,TEL CLOSET ,RJ48C,LP Y,CAB Y,5,MNTG 14pck,SLOT DEMARC LOC Continued: 1/14, 32.HCGS.774626..NY DEMARC LOC: FLR 3,RM hall,TEL CLOSET ,RJ48C,LP Y,CAB Y,5,MNTG 14pck,SLOT DEMARC LOC Continued: 2/14, 32.HCGS.774627..NY DEMARC LOC: FLR 3,RM hall,TEL CLOSET ,RJ48C,LP Y,CAB Y,5,MNTG 14pck,SLOT DEMARC LOC Continued: 3/14, 32.HCGS.774628..NY DEMARC LOC: FLR 3,RM hall,TEL CLOSET ,RJ48C,LP Y,CAB Y,cab 5,MNTG DEMARC LOC Continued: 14pck,SLOT 4/14, 32.HCGS.774632..NY DEMARC LOC: FLR 3,RM telco,TEL CLOSET ,RJ48C,LP Y,CAB Y,5,OTHER 1,SLOT DEMARC LOC Continued: 5, 32.HCGS.774633..NY DEMARC LOC: FLR 3,RM tel cl,TEL CLOSET ,RJ48C,LP Y,CAB Y,5,MNTG 5,SLOT DEMARC LOC Continued: 6, 32.HCGS.774634..NY DEMARC LOC: FLR 3,RM closet,TEL CLOSET ,RJ48C,LP Y,CAB Y,5,OTHER 1,SLOT DEMARC LOC Continued: 7, 32.HCGS.774635..NY DEMARC LOC: BLDG 6 3fl telco rm |  |  | 2013-04-16 |  | bpdd | 2013-04-23 | 2013-04-18 | UnitedHealth Group- 64557 | pradeep | pradeep activated on 4/25 | 2/7- sent to provisioning 2/6 2/14 escalating with provisioning for pick up 2/20: Pending FOC 2/25- VZ Outside Plant Engineer unable to schedule Site Survey as LCON (Tom Giantomidis) is on Vacation.Also, please confirm specific building the LCON is in. The name is not listed in the Main building. 3/7- order supped saying lcon is back from vk, pending ops approval 3/13- LEC came back, per customer building number is 6. John verified it is building 6. Melissa asked Ken to supp order 3/20- ASR supped with info 3/28- escalating with provisioning to get ASR supped 4/3- esclating another level for ASR supp 4/5- FOC for 4/16, CRDD for 4/23...need to clear DMARC to make sure it terminates to mpoe and not the 3rd floor 4/18- lec delivered pending testing
2013-02-27 | ShaRita/Melissa | Na | Eagan node removal from ROADM | node removal from ring. | SO: 5232562 MIN-C31661 CCR 1143103 | 5771014 |  |  |  | W0Y28557 | RW-LLM8-JCFG-0002 |  |  |  |  | bpdd | [5 empty] | 3/4- order submitted. 3/7- order in provisioning 3/20- order escalated in local design 3/28- all orderes off the node, asked local design to proceed. 4/3- decom CCR opened, Ops will need to schedule the MASTARS for the removal of the Roadm at w7y,05 location... 4/10-new CCRs needed- Equipment Definition queue stepped on CCRs 1144716 (card removal) and 1144708. fiber testign complete and pending spicing 4/18- fiber cut happnened on 4/17,pending equipment pick up 4/25- Phil is workign with Unisys on date to pick up equipment 5/2- cards removed, pending CCR closure 5/9- Per phil, he is getting the equipment from Unisys on 5/15 5/17- order completed
2013-04-01 | VEC |  | El Segundo | disconnect (the credit will be split until 12/12/12 (our original disconnect was submitted on 11/12/12) and then full credit from 12/12/12 until these circuits are disconnected) | NSPE0006601635 OQBKK8DL |  | P1866556 |  |  | BCBKMPP00001 BCBKMPP00002 BCBKMPP00003 BCBKMPP00004 BCBKMPP00005 BCBKMPP00006 | [5 empty] | bpdd | 2013-05-01 |  |  |  |  | disconnect due on 5/1 5/3- disco not complete, pushing to get this disconnected 5/7- disconnect completed
|  |  | ELR to Trumbull EPL | disconnect | NSPE0006629528 s/o 5254105 MIN-O0028898 (clsd) BRP-O0000891 |  |  |  |  | W0V64266 | [5 empty] | bpdd | 2013-04-28 |  |  |  |  | 4/19- pending LEC 4/25- disco due 4/28 5/3- disco completed on 4/29
2013-05-07 | ShaRita | C1395-07-IJ | Fiserv 4400 Westown Parkway, Des Moines | 44736 DS3 with md5 UHGVEReccgas4Usp9 | smartform 189869776 CDR201305090048 NSPE0006762449 | 5877771 |  |  | 35000 | [6 empty] | bpdd |  |  |  | 763-744-2082 eric_taylor@uhc.com |  | 5/9- sent to OM 5/16- customer requested to cancel order
2013-03-07 | VEC |  | FRONTIERMEDEX MITCHELDEAN UK | disconnect | NSPE0006466504 5234443 | 5771907 |  |  |  | W0Y54562 | [5 empty] | bpdd | 2013-04-26 |  |  |  |  | disconnect due on 4/26 5/2- pushing to get disco order closed 5/9- disco will complete on 5/13
2012-09-28 | ShaRita | TN040-07-CJ | Knoxville, TN | Upgrade port to 7680, 5xT1 | CW: 189710424 NSPE0005915096 IQBKCVFG OQBKCX68 | 5581368 | P1956496 (in) P1937320 (out) |  | upgrade to 4608 | BCBKT19W0001-4 (out) BCBKWFP50001-5 (in) | T2/HCGS/837112//SC DEMARC 2nd floor telco room mm1 pos 11 rj48c tagged not extended. closing ticket, |  |  |  |  | bpdd |  |  |  | 763/694-7370, masroor_khan@uhc.com | Requested 5/15/2013 05:30:00 PM Central Time bridge 866-819-9840 pcode 3365052 | 10/4- order with OE 10/11- pending capacity for provsioning approval 11/8- order ready for upgrade. Engineer informed. 11/29- order had to be sent back to provisioning, new path is not good 12/6- CHANGE ASR SENT. THIS IS A REQUEST TO AT&T TO CHANGE THE C FA SLOT FROM 06 TO 02 12/13- order ready for upgrade. engineer informed. 5/22- *** COMPLETED, CIRCUIT IS UP/UP AND ERROR FREE *** Customer Accepted CIRCUIT UP : yes Customer Name / Number: Masroor Khan - 952-201-1673
2012-09-25 | ShaRita | NY040-05-CJ | New York, NY | Upgrade from 4 x T1 to 6xT1, 9216 | CW: 189705869 NSPE0005894231 IQBKCPTF OQBKCQ66 | 5572886 | P1955408 (in) |  | upgrade to 4608 | BCBJ8T760001-4 BCBKWCVM0001-0006(in) | 32.HCGS.758583..NY DEMARC LOC: 14th flr tel rm slot 1/2 32.HCGS.758585..NY 14th flr tel rm slot 2/2 RJ48c |  |  | 2012-10-25 | 2012-10-25 | bpdd |  |  | Unitedhealthgroup-65159 | 763/694-7370, masroor_khan@uhc.com | Requested date 5/16 at 6pm CST | 9/27- pending tin submission by om 10/4- order with provisonning 10/11- FOC for 10/25 due to copper build. Pending commit. Trying to escalate for better FOC 11/7- order ready for upgrade, engineer informed 5/8- activation scheduled 5/16 6pm cst HOTCUT COMPLETED, CIRCUIT IS UP/UP AND ERROR FREE Customer Accepted CIRCUIT UP : YES Customer Name / Number: Masroor Khan - 763/694-7370
2012-10-24 | ShaRita | UOH09-05-CJ | 9050 CENTRE POINTE DR, WEST CHESTER OH 45069 4874, United States | upgrade to 12288 8xT1 | CW: 189725900 OQBKFB1G IQBKD707 | 5614193 | P1536785 (out) P1964035 (in) | 1668650 | upgrade to 3072 | BCBJRBDF0001-6 (out) BCBKW4RX0001-0008 | 17/HCGS/106131/TWCS suite 400 smartjack wj 007 position 4ckt 17/HCGS/106132/TWCS suite 400 smartjack wj003 position 1 |  |  | 2012-11-29 |  | bpdd |  |  | unitedhealthgroup- 64621 | (91) 9810059326 , pradeep_yadav@uhc.com | requested 5/20/2013 05:30:00 PM Central Time 866-819-9840 pcode | 11/2/2012 Order is being processed 11/5- sent DS3 waiver over to OS 11/9- FOC for 11/21 11/15- asking for commit B201211150061 11/29- mistken this one for a NJ order, this one haws an FOC for 11/29 12/6- order ready for hotcut. Engineer informe.d 5/22- *** HOTCUT COMPLETED *** *** CIRCUIT IS UP/UP AND ERROR FREE *** Customer Accepted CIRCUIT UP : Y Customer Name / Number:Keith Manzene / 8607028284
2012-09-17 | ShaRita | KS003-01-IJ | 10895 Grandview Drive - Suite 200 Overland Park | 20M type 4 ethernet with md5 UHGVERbgpbqZyofa | SAR AR ID:1-1KA6ME3_1-1KAA2W2 IQBKDZJX (EACS) IQBKFBQY (flow) | 5600626 | P1961846 (access) | 5228498 | 4608 | EDBKW0F10001 (acess) BCBKW51N0001 (flow) | 74/KQGN/904680//SW Dmarc:2nd Floor, Customer Suite Data Room, Shelf 1 Port 2 Pos 3 West Pannel, Tagged and Labeled Hand-off: Electrical UNI Speed: 100M EVC Speed: 20M Priority Data Auto-Neg settings: Off Duplex settings: Full Duplex |  |  | 2013-01-23 |  | bpdd | 2013-02-01 | 2013-02-12 | unitedhealthgroup-65041 | 763/694-7409, terry_bjorke@uhc.com | terry confirmed active on 5/23 | 11/15- ASR sent on 11/13. 12/13 date requested. pending FOC. CPE ORDERED ON NSAP # 10584155 11/29- still no FOC, asked prov to follow up. 12/6- per AT&T they are currently waiting for KO notification from NSS PM. I expect to receive KO at the end of this week or early next week. 12/12- After the KO I/Robert will be able to provide you with the scope of work and tentative timeline. Please note that FOC is provided few days before construction completion. 12/14- MAJOR build – building new handoff on customer prem (placing Cisco ME-3400-24), splicing required. Preliminary network completion date 2/28/12 Preliminary service delivery date – 3/21/12 12/18- pending major build, we are asking for a better date if possible 12/27- Per AT&T- that network will be completed on 1/14/13, so we have enough time to complete this order till the end of January. 1/16-new Prj Mgr handling this is Matus Karahuta. i have asked assistance for updates if they have finished they're network build. pending response. please be guidedthat after netwrok build it usually takes them 7- 10 days before they can deliver loop to customer. 1/24- LEC FOC 1/23 and LEC delivered, BEAS install scheduled for 1/25, commite date is for 1/30 1/30- BEAS install resched for 1/30, when LCON is available. 2/7- Replaced and configured cpe at customer site. IPAT was able to ping and certify beas. B&E provided loop but test set detected loss of frames and loss of sequence. Left hard loop on port one for B&E to complete remote RFC 2/15- order ready for acitvation, engineer informed.
2013-01-22 | ShaRita | MD740-02-IJ | Baltimore, MD | 44736, DS3 with MD5 UHGVERbgpbqZyofa | CW: 189788170 CDR201301230040 NSPE0006327365 IQBKHJK6 blt-I30344 (complete) | 5711530 | P1982105 | 5320843 | 1536 | BCBKX99L0001 | 3x-7yc-3ai-0005 Room node Floor(FL) 3 dsx3ja 14.4.7:2.tx/rx Labeled dsx3 panel. Demark per CLR. |  | 1/28/2013 supp 1/31 | 2013-04-30 |  | bpdd | 2013-05-09 |  | UnitedHealth Group-65020 | 702-303-7293, tauoa.falo@uhc.com | terry confirmed active on 5/23 | -They are now communicating to field engineer for site survey. 3/7- needed ASR supp, pending FOC 3.13- escalating on ASR. continues to have errors 3/20- working wtih director and SME on ASR issues 3/21- order is collo restricted, in talking to John, they are collocated with level 3. trying to work with site contact to get CFA, but the number we have for him is RNA. sent e-mail to account manager to get CFA 3/28- pending info from level 3 4/3 per level 3 “We do not issue LOA’s for other carriers to terminate circuits into the L3 collocation area. If Axolotl is bringing in a circuit from Verizon, then it should be designed to the Verizon cabinet in the Leased Transport Area and they should provide tie down/DLR to Axolotl. Axolotl would then need to order a cross connect from L3 and provide the tie down info from VZ in the documentation. Working with provisioning on this 4/10- lec is asking for spot clli again. 4/18- redesigned to on-net, pending install. on net foc is 4/30. 4/25- Local circuit delviered, pending testing 5/2 MUX HTRR579-E dispatches complete // pending completion of MUX a nd bne testing
2013-02-06 | ShaRita | UCA35-07-IJ | San Francisco, CA | 44736 DS3 with MD5 UHGVERbgpbqZyofa | CW: 189799810 CDR201302060036 NSPE0006387880 IQBKHY2R SNF I0061723 | 5732233 | P1985745 | 5326685 | 22000 | BCBKYJG00001 | 3X-COU-42M-0003 |  | 2013-02-11 | 2013-02-25 |  | bpdd |  |  | UnitedHealth Group- 64642 | (987) 313-9388, anupam_datt@uhc.com | scheduled for Monday, 5/22, at 8am CST bridge# 866-878-8630 pass code 6653710 | 2/7- order with Oe 2/14: FOC for 2/25/2013 3/7- no access, supped for Lcon 3/13- followed up with provisioning on local order with new contacts. 3/20- escalating for dispatch with new contact 3/28- tech going on site to do survey today 4/3- customer paid cable pull required, this order will require a customer coordinated/paid coax cable pull from customer^s server rm on 15th fl to verizon pop on B-2 level... bldg riser vendor for loc2/42m is IMG @ 877-611-8908, 4/10- pending word from uHG on where we nee dto terminate to B2 level or 15th floor 4/18- supped to terminate to 15th floor pending dispatch. site survey set for today 4/25- per tech there is no cable from verizon pop to the 15th floor. 5/2- Cable should be in 5/3, order supped 5/17- Loop dropped and the router shows normalized. End to end testing will be done once local order, SNF I61723 / 3x-cou-42m-0003, has been closed and completed. 5/20- ready for activation 5/27- Antonette Pagayonan (05/27/2013 8:23 AM) +++++ACTIVATION COMPLETED+++++ Circuit is up and running. Pradeep accepted the circuit. Datt, Anupam 4155475133 of UnitedHealthGroup.
2013-01-16 | ShaRita | C1553-02-IJ | Hartford, CT | 4608 3xT1 with md5 UHGVEReccgas4Usp9 | smartform 189782810 NSPE0006296623 IQBKHDYX | 5701137 | P1981459 | 5320048 | 128 | BCBKX8DT0001-003 | /HCGS/782912//SN C-LEVEL CABINET CJ27 CUSTOMER /HCGS/782913//SN single cabinet, 12 pack slot 5, terminated to rj48c /HCGS/782914//SN C LEVEL CABINET CJ27 NUMBER 16, 12 P |  | 2013-01-29 | 2013-02-12 | 2013-02-12 | bpdd | 2013-02-15 | 2013-02-12 | uhg-ecc 65405 | 763-553-4895 john_bremseth@uhc.com | completed with Keith on 6/3 | 1/16- Sent to OM 1/23- order with provisioning, pending asr 1/30- FOC 2/13- commite 2/15 2/14:ready for activation, engineer informed
2013-04-12 | B end | C1521-01-DJ | Building No. A-2,DLF Ltd, SEZ Silokhera Gurgaon INDIA 122002 | disconnect | NSPE0006653856 s/o: 5258464 , 5258465 | 5827939 |  |  |  | w0x41360 |  |  |  | 2013-05-31 |  | bpdd | 2013-05-31 |  |  |  |  | 4/19- order sent to provisioning 4/25- TEV done and order sent to PTT 5/3- pending provisioning task 5/9- escaalting with provisioning 5/16- disco date is 5/31 6/6- disconnect completed
2012-11-02 | B end | II702-07-IJ | 5th,6th & 7th Floor, Building# 14, Sundew Properties, SEZ Raheja Mindspace, HI-TECH City Hyderabad, india | Ethernet 150 Mbps 1 with MD5 UHGVERbgpbqZyofa site of origin W0Y12673 | 5182429 - 5182430 PORT & ACCESS | n/a | n/a | 5309001 | 33792 | W0Z96959 (port) W0Z96958 (access) | CARRIER NAME : TATA COMM(FORMERLY VSNL) 1000BASE-TX ckt id 091HYDE1143007567661 |  |  |  |  | bpdd | 2013-03-28 | 2013-03-28 | unitedhealthgroup-65158 | 1 91600 84400, harish_kandpal@uhc.com | activated with harish on 4/26 | 11/7- pending SOF. 1/3- order was entered as 100 mg, we are confirming with Neha that it should be 150mg 1/10- following up with Neha on change 1/16- TEV complete and order sent to PTT for processing. 1/24- FOC DATE WILL BE SHARED BY THE PTT IN THE NEXT WEEK. 1/28- PTT FOC DATE = 14-15 MARCH 2013 2/14- CUSTOMER SITE IS NOT READY (SERVER ROOM READINESS IS AWAITED). IMPLEMENTATION WORK HAS BEEN KEPT ON HOLD. AS PER THE LCON, SITE IS EXPECTED TO BE READY BY MARCH END. PTT WILL TAKE 4 -5 WEEKS TO COMPLETE THE INSTALLATION ONCE THE SITE IS READY 3/7- we are now getting word that the site won't be ready until end of April 3/28- this was confused with the other Hyderabad site. this one is now ready for activation.
2012-06-08 | B end | SW505-03-IJ | Stockholm, Sweden | 2xE1, 4096 with md5 encryption UHGVERbgpbqZyofa | FE 5098424 and 5098425 |  |  | 5153780 | 1024 | W0Z60681-2 (bearer) W0Z60683 (port) | FB7652272 FB7652275 6th floor server |  |  | 2012-08-06 |  | bpdd | 2012-08-28 | 2012-08-28 | unitedhealthgroup-64515 | 763/694-7409, terry_bjorke@uhc.com | activated with Terry on 6/11 | 6/14- pending SOF 7/6- signed SOF sent to Siva 7/26- order over to provisioning 8/1- PTT due date of 8/6 8/8- TAIL DELAYED TO 13TH OF AUGUST DUE TO LCON ON VACATION 8/28- order ready for activation, engineer informed. 11/7- attempted to activate mid oct with issues. B end PM ffollowed up and circuits were re-tested clean on 11/6, pending new activation date from Terry.
2012-09-04 | ShaRita | NM023-05-IJ | Albuquerque, NM | 44736, DS3 with MD5 encryption UHGVERbgpbqZyofa | smartform 189693402 CDR201209050014 NSPE0005813785 IQBKB3RC abq-I7591 (closed) ABQ C7591 | 5546018 | P1951922 | 5197361 | 9216 | BCBKV4D90001 | 54/HFGS/964922//MS DEMARC LOC: MAIN PHONE ROOM 1ST FLOOR EAST WALL MT 1 SLOT 1 OF 3 DMARC Labeled MCI (Yes or No): yes |  | 2012-10-26 | 4/30 (tentative) | 2013-03-27 | bpdd | 2013-03-27 | 2013-04-25 | unitedhealthgroup-65190 | 763.553.4801, sonja_d_mroczynski@uhc.com | activated w/ Sonja Mroczynski 763 553 4801 on 6/11 | 12/27- still no FOC, working on the FOC. Per Century link The end user wants them to use a different type of power source. They will have to reorder the equipment. The date of the DS3 might be pushed out from the date of 1/25 1/9- Century link in the process of installing the equipment but no power was found. I've been told that the end user won't have the L5-15R in place until mid February. Century link will work on getting a FOC with a 2-22 due date. 1/23- per Sonja pending ETA on power, once we have ETA on power VErizon will have to supp the order to Century link 2/27- per Sonja power was in 2/25, per Centurylink tenative duedate for this order is 04/30 3/7- WAITING FOR ON OC3 SCID TO BE TURNED UP. ANY QUESTIONS CONTACT PROJECT MANAGER DEANE DIEZ 602 630-1118 EMAIL DEANE.DIEZ@CENTURYLINK.COM. 3/13- follow up with PM on status 3/20- still pending OC3 SCID. sent e-mail to deane for status. 3/28- Centurylink deliverd on 3/27, we never got formal FOC. working to get our order completed out. 4/2- testing with centurylink 4/3- testing not sucessful Created new ETMS: 2013040309988 for vendormeet 4/10- Change local ABQ C7591 - 3x-bl2s-vyb-0016 created and stepped to PRRS with remarks: the local is needed to be re-designed because the CFA used is defective on LEC side. 4/17- redesign done, pending ASR 4/25- new local loop is in. We are wrokign on testing the circuit, order complete, engineer informed.
2013-05-07 | Scott/Melissa |  |  | DDOS Mitigation from 2G to 10G Mitigation. | u309696 | 5882585 | [9 empty] | bpdd | 2013-07-04 |  |  |  |  | sent to Scott Moritz 5/22- order sent to provisioning due date is 7/4 completed on 6/7
2013-04-12 | ShaRita | ID003-02-IJ | 205 E Watertower Lane, Meridian, ID | 6144 4xT1 UHGVERbgpbqZyofa | CW: 189849433 NSPE0006653826 IQBKLHDG | 5825515 | P2004122 | 5349701 | 3072 | BCBK0NDL0001-004 | 34/HCGS/639733//MS 34/HCGS/639734//MS 34/HCGS/639735//MS 34/HCGS/639736//MS | 0CW1HP 0CW1HM 0CW1HL 0CW1HN |  | 2013-05-07 |  | bpdd | 2013-05-10 |  | unitedhealthgroup-65285 | plus 632-588-4651 noemi.joy_gomez@uhc.com | activation completed with Noemi 6/25 | 4/19- pending ASR 4/25- FOC 5/7- commit 5/10
2013-01-30 | ShaRita | FL751-01-IJ | Miami, FL | 44736, DS3 MD5 UHGVERbgpbqZyofa | smartform 189794444 CDR201301300065 NSPE0006358179 IQBKHTMH | 5723753 | P1984231 | 5323535 | 8896 | BCBKYF560001 | Level 3 BCHN3249 dmarc CFA MMR TC-03-07 PNL 4 POS 5IN 17OUT |  | 2013-02-06 | 2013-02-27 | 2013-02-27 | bpdd | 2013-03-18 | 2013-03-15 | UnitedHealth Group-64561 | 763-744-0981 glenn_moore@uhc.com | completed with Glenn on 6/25 | 2/7- ASR Sent, pending FOC 2/14: FOC 2/27/2013 2/28- no ELA for lec delivery, C201302280611 3/7- lec delivered, pending testing 3/13- C201303130047 for loop testing, mux scheduled 3/20- order ready for activation, engineer informed.
2013-05-22 | ShaRita | C1545-04-CJ | 65 Steamboat Dr. Warminster , PA 18974 | insite circuit move from cage area to data center on the same floor, approximately 80 feet | smartform 189883531 NSPE0006832795 CQBKMVC1 | 5900310 | P1936565 | 5092026 | 128 | BCBKT0540001 | 11/HFGS/107467//PA |  | 2013-06-03 | 2013-06-19 |  | bpdd | 2013-07-15 |  | UHG-ECC-65406 | Site Contact: Jim Quinn, 267-960-3879 |  | 5/30- order in OE 6/6- Order number C6FQ96159; pending FOC of 6/19 6/13- pending FOC date of 6/19 6/20- pending confirmation loop was delivered 6/27- order closed. Customer, Jim Quinn, confirmed circuit was moved.
2013-05-14 | ShaRita | none | 1355 S 4700 W SALT LAKE CITY UT 84104-4433 | disconnect | NSPE0006774745 OQBKMFFR |  |  |  |  | bcbkjmsr0001-0005 | [5 empty] | bpdd | 2013-06-13 |  |  |  |  | disconnect due on 6/13
2013-05-14 | ShaRita | none | 301 N HURSTBOURNE PKWY LOUISVILLE KY 40222 | disconnect | NSPE0006774878 OQBKMDM9 |  |  |  |  | bcbj92my0001 | [5 empty] | bpdd | 2013-06-13 |  |  |  |  | disconnect due on 6/13 soft disconnect done 6/12
2013-05-14 | ShaRita | none | 250 N PATRICK BLVD BROOKFIELD WI 53045-5826 | disconnect | NSPE0006774791 OQBKMFF8 |  |  |  |  | bcbjynlg0001-0004 | [5 empty] | bpdd | 2013-06-12 |  |  |  |  | disconnect due on 6/12
2013-05-14 | ShaRita | none | 8550 UNITED PLAZA BLVD BATON ROUGE LA 70809 | disconnect | NSPE0006774849 OQBKMFGL |  |  |  |  | bcbkf10s0001 | [5 empty] | bpdd | 2013-06-12 |  |  |  |  | disconnect due on 6/12 soft disconnect done on 6/12
2013-06-11 | ShaRita | none | 4400 Chatterson #205 Victoria British Columbia CN V8X5J2 | disconnect | NSPE0006892240 5290225 5290227 | 5931682 |  |  |  | W0Z06291 (port) W0Z06290 (access) | [5 empty] | bpdd | 2013-08-11 | 2013-06-19 |  |  |  | pending disconnect date 6/20- disconnect completed 6/19
2013-05-14 | ShaRita | none | 5955 ZEAMER AVE ELMENDORF AFB AK 99506-3702 | disconnect | NSPE0006774686 5276808 OQBKMK4T |  |  |  |  | W1A14238 W1A13406 | [5 empty] | bpdd | 2013-06-13 | 2013-06-20 |  |  |  | disconnect due on 6/13 6/20- disconnect completed
2013-05-23 | ShaRita | none | 44 South Broadway White Plains, NY 10601 | disconnect | NSPE0006818670 OQBKMTJW |  | P1644190 | 1782345 | 9216 | BCBJ1PYX0001-0008 | [5 empty] | bpdd | 2013-06-19 |  |  |  |  | disco due on 6/19 6/20- soft disconnected completed 6/19 6/24- disconnect completed
2012-11-19 | ShaRita | OH085-08-CJ REQUEST CANCELLED | Canfield, OH | Upgrade to 3xT1, 4608 | CW: 189749746 NSPE0006099326 OQBKFRCL IQBKFPV3 | 5646161 | P1926130 (out) P1967489 (in) |  | upgrade to 1536 | BCBKS00D0001-2 (out) BCBKXCF30001 -0003 | 92/HCGS/210738//OB DEMARC LOC: CAB1 SH1 SL11, WALL PNL #2 PORT 3, DEMARC LOC Continued: PORT 3, EXT TO 1ST FL MDF RO2 |  | 2012-11-30 | 2012-12-14 | 2012-12-14 | bpdd |  |  | unitedhealthgroup- 65136 | 763-744-2077 robert_a_benson@uhc.com |  | 11/19- send to oM 11/21- in oe 11/29- with provisioning, pending asr 12/13- LEC deliverd, pending testing 12/19- order ready for upgrade. Engineer informed. 6/13- per customer request order has been supp'ed to cancel 6/20- pending completion of cancellation 6/25- cancel completed
2012-09-24 | ShaRita | UUT05-05-IJ | Salt Lake City, UT | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189705722 CDR201209250064 NSPE0005893503 IQBKCMKT SLC I0009879 | 5572298 | P1955056 | 5210312 | 22000 | BCBKWB1B0001 | 64/HFGS/137666//MS demarc: MAIN BLDG MAIN FLR DSX3 NIU RACK MT |  |  | 2013-01-16 | 2013-01-17 | bpdd | 2013-01-16 | 2013-01-17 | unitedhealthgroup-64762 | 763/694-7370, masroor_khan@uhc.com | Requested Date 6/19/2013 6:30PM Central Time bridge bridge 866-819-9840 pcode 3365052 Activation completed 6/26 | 9/25- submitted to oM 9/27- provisioning has and is working 10/4-EV28 PON IQBKCMKTI4JSMB01 and MS01 PON IQBKCMKTI4JSMB02 have been sent. Now awaiting LEC FOC for MS01 PON. 10/11- ASR penidng FOC from Quest. Per Qwest working on design 11/8- Lec deliverd, pending field cross connects . Deepa filed better commit date ticket. C201210190613 for better commit 11/15- needed to re-dsign to new local ring, new local order opeened. 11/21- new tie down recieved, need ASR sent 11/29- pending ld patching on our side. 12/6- LD patching set for today. 12/13- 892 dispatch at site SLY was incomplete. Per field tech Don Condie, there need to have a disconnect MUX MSG for HRUY064 because the local connection that MUX MSG RTPG200 is trying to use is still connected to the first MUX. email sent to provisioner Perry Carlos, team lead Yoly Bernadas asking them to review the MUX MSG and do the necessary revisions 12/18- escalating wth provisioning on mux revisions 12/27- poending disco order to free up equipment. Per Remarks:Pending unwiring for DTQE904 SLY ¦ working ¦ 12/27/12 1/3- Pending patching at site SLY, sched 1/3/13 1/9- pending mux again, escalating with prov 1/16- all patching complete in our network, testing almoest complete. 1/24- order complete, engineer informed
2013-04-02 | ShaRita | FL039-02-IJ | 415 West 49th Street, Hialeah, FL | 1536 T1 with mD5 encryption UHGVERbgpbqZyofa | smartform 189841960 NSPE0006606995 IQBKK6YK | 5812142 | P2002553 | 5347453 | 1376 | BCBK0J1W0001 | 60/HCGS/448945//SB Demarc: BCBK0J1W00010001=cab2, slot1, telco room, first flo or, RJ48C, tagged, not ext |  | 2013-04-10 | 2013-04-23 | 2013-04-24 | bpdd | 2013-04-30 | 2013-05-01 | unitedhealthgroup-65274 | 763.553.4801, sonja_d_mroczynski@uhc.com | per Robert Bensen activated on 7/3 | 4/2- submit to OM 4/11- ASR sent, pending FOC 4/25- LEC delivered, we are testing commit 4/30 5/2- order ready fro activation, engineer informed.
2012-10-03 | ShaRita | UNY14-05-IJ | Islandia, NY | 44736, DS3 with md5 UHGVERbgpbqZyofa | smartform 189711890 CDR201210030051 NSPE0005926141 IQBKCX22 | 5584690 | P1957178 | 5212531 | 12896 | BCBKWGT90001 | 32.HFGS.656003..NY DEMARC LOC: BLDG MAIN 2ND FLOOR MDF ROOM. WALL MOUNTED DMX GROUP B SLOT DEMARC LOC Continued: 1,TAGGED WITH CKT ID. LCON SAO |  |  | 2013-04-05 | 2013-04-05 | bpdd | 2013-04-12 | 2013-04-12 | unitedhealthgroup-64553 | 763-744-1556 john_l_rothstein@uhc.com | Requested Date 7/5/2013 6:30PM Central Time bridge 866-878-8630 pcode 6653710 | 11/21- LEC due date pushed to 02/04. need to fidn out why 11/29- per core, NY and NJ still in disaster recovery. All BTDD requests have to be VP to VP escalations 12/13- Currently waiting for the DLR to be received, expecting on 12/26. 12/18- still pending DLR 12/27- Still pending for tne LEC DLR expected date 12/28. 1/3- Apparently lec DLR isn't due until 1/24, FOC date is 2/4/2013 1/18- As per LEC, customer TELCO room is not yet ready and there will be a construction for this. The suggested DD is 03/13/2013. 1/24- new FOC is 3/13. pending dlr to schedule wiring. 1/30 FOC 3/13, pending DLR DLR date of 3/5/2013 2/27- per LEC conduit is needed. trying to get details on where conduit is needed. 3/6- sent conduit requirements to John. RECCD= 3/27/13.CNR.CONDUIT NOT DUE TO COMPLETE END OF MONTH NEW DD 4/5/13 - 3/13- FOC received for 4/5, C201303130024 for commit date 3/20- FOC 4/5, pending DLR to schedule MUX. ETA for DLR is 03/29/2013. 4/3- esclating for DLR/mux 4/10- peding testing with lec, pending lec cable for testing 4/17- order is ready for activation 7/5- Ckt is up and passing traffic. John accepts the ckt.
2013-06-11 | Sa disconnect | none | 7067 N. Mariposa Street, Fresno, CA | disconnect | NSPE0006891190 OQBKM6JR |  |  |  |  | BCBK04PH0001 | [5 empty] | bpdd | 2013-06-26 |  |  |  |  | 6/11- send to SA disco and needs to be credited. This was installed in error and is a duplicate of BCBK04XG0001 disconnect due date on 6/26 6/27- soft disconnect completed 6/27 7/3- disconnect completed 6/28
2012-11-19 | ShaRita | PA012-05-IJ | Pittsburg, PA | 44736, DS3 with MD5 UHGVERbgpbqZyofa | smartform 189750538 CDR201211200007 NSPE0006100878 IQBKFQQG | 5648338 | P1967697 | 5237100 | 27m | BCBKXCWL0001 |  |  | 2013-12-18 |  |  | bpdd |  |  | unitedhealthgroup-65225 | (987) 313-9388, anupam_datt@uhc.com |  | 1/31 - Supp'd order to chg LCON to MARTIN KLABNIK – 4125010620 - Now in Prov - 2/17 - Order Supp'd to change LCON to Ben Fortune at 412-501-0696 - 2/21: Pending FOC ASR supped with new LCON. 2/28- pending FE site visit for FOC. Build is required 3/13- per lec PM At this time, the outside field eng is wait on customer to decide where the MUX needs to be installed in the build they want service 3/20- per LEC At this time, the outside field eng is wait on customer to decide where the MUX needs to be installed in the build if they want service 4/3- tried FE Fred at 412-237-2292, to see about site visit 4/10- Melissa trying to find out details of the ticket for the site visit 4/18- need verification on mux and ticket process from uhg 4.25- UHG still trying to find site access contact 5/22- Still waiting for UHG to provide site access contact 5/29- Still waiting for UHG to provide site access contact 6/6- Still waiting for UHG to provide site access contact 6/13- Still waiting for UHG to provide site access contact 6/19- Advised customer that order will be cancelled if site access contact is not provided by COB 6/21- Once a site contact is provided order then should be re-issued. 6/27- Pending completion of cancellation. 7/2- Cancelled completed 7/2
2013-05-14 | ShaRita | none | 3100 SW 145TH AVE MIRAMAR FL 33027 | disconnect | NSPE0006721630 OQBKMGK1 |  |  |  |  | BCBJXX6N0001-0008 | [5 empty] | bpdd | 6/6/2013 6/26/2013 |  |  |  |  | disconnect due on 6/6; escalated to disconnect management , grooms order G0165663 needs to be cancelled grooms order completed; disconnect due 6/26 6/20- pending due date of 6/26 6/27- soft disconnect on 6/26 7/3- disconnect completed on 6/28
2013-04-29 | ShaRita |  | Connextions 8403 SouthPark Circle Orlando, FL 32819 | moved from the 1st floor to the 2nd floor, Connextions is moving their MDF room. | smartform 189869740 NSPE0006762259 CQBKMKQ0 | 5884913 5876046 | P1845974 | 2061226 | 12288 | BCBKLGSF0001 | 58/HFGS/703944//SB |  | 2013-05-22 | 2013-09-10 |  | bpdd | 2013-09-17 |  |  |  |  | 5/9- sent to OM 5/16- order with om 5/22- pending provisioning approval 5/23- customer requested move be done asap 5/29- Pending FOC date of 9/10. The order number for this move is CYFPHNL5. Per AT&T, this order requires major equipment replacement. 6/6- Pending FOC date of 9/10 6/13- Pending FOC date of 9/10 6/20- Pending FOC date of 9/10 7/3- customer requested to cancel. cancel completed
2013-01-30 | ShaRita | ME007-05-IJ | South Portland, ME | 20M Ethernet with copper handoff MD5 UHGVERbgpbqZyofa type 4 access with Fairpoint. | SAR 1-1N4E8JH ProQuest 189797786 NSPE0006375852 IQBKH3YN Access order # : IQBKH3HW | 5730159 | P1987030 (EACS) | 5328298 | 12288 | BCBKYLTV0001 (port) EDBKYLLB0001 (EACS) | 10/VLXP/078148/22/MJD/ Demarc info : 1st floor utility room telco back board and the hand off is in por t a |  | 2013-02-12 | 2013-05-03 | 2013-05-07 | bpdd | 2013-05-10 | 2013-05-30 | UnitedHealth Group-65149 | 763/694-7409, terry_bjorke@uhc.com |  | 3/7- ASR supped with engineer info to see if that will work, pending response 3/12- LEC acceppted supp 3/20- following up with fairpoint on ASR status 3/21- According to Fairpoint, the engineer spoke with the contractor. The contractor has not had time to go to the job site. They hope to do that today 3/28- FOC recieved for 5/3. BTDD ticket: C201303270041 4/10- pending 5/3 FOC, commit 5/10 5/8- LEC confirmed delivered on 5/7, pending BEAS install, sent for BEAS install 5/17- per dispatch, LEC needs to change config at handoff. from dmarc via 220 ft extension to cust data room overture installed in rack #3 we can green up the line to equipment. from cable going into equip back to dmarc we cannot clear alarms on LEC side. need LEC to test w BEAS group, once this is done successfully ipat will be able to ping and verify box which has been configured. 5/22- Beas installed and pingable. pending ETE testing 5/29- ready for activation / pending configs
2011-12-14 | ShaRita | old C1408-04-IJ, new UCO31-01-IJ | Centennial, CO | 60Mb ethernet PIP Multi-mode fiber handoff | NSPE0005016429 IQBJ2CP5 (EA) IQBJ4K18 (flow) DNV-I28222 trunk dnv a28297 scotts is222977 | 5191320 | P1910724 |  | 0 | EDBKPMR10001 (EA) BCBKRSKH0001 (Flow) | EDBKPMR10001 EACS ea-7f8-7f8-0009 . Dmarc is as follows:--1st floor telco/meet-me room--ADC 6000 fiber patch panel 106.5.7:7 VZ TX 106.5.7:8 VZ RX: 100 base fx MM SC connectors, tagged/w circuit id |  |  |  |  | bpdd | 2012-04-26 | 2012-05-03 | UnitedHealthGroup-64899 |  |  | 12/14- pending approval doc, etc from Matt. 12/22- pending approvals, matt is pending handoff info. 12/29- order sent to provisioning, pending approval 1/5 pending ccr 1043251 to order oc3 cards for oc48.fx (rft 1/31) pending ccr 1043257 to order oc3 cards for oc48.9aa (rft 1/31 1/11- ops did a site survey for the ccr and were told by Via West the customer is actually moving their equipment to the other Via WQest site 11900 E CORNELL AVE(tcoms bldg d7m)..order to csre to have order verified. 1/12- cage is moving, not building, re-sent order. pending ccr 1043251 (rft 1/31 equipm ship ) to order oc3 cards for oc48.fx pending ccr 1043257 (rft 1/31 equip ship) to order oc3 cards for oc48.9aa Overture CR is CCR 1043247 (rft 3/22). Per Via West customer name is known to them as Probuild 1/20 - 1043257 cards installed, Overture CR is CCR 1043247 equipment shipped 2/2- 1043257 completed 1043247 pending install Overture will be going in 106.02.11 with handoff being off ADC 6000 panel in the same relay rack at this Via West Data Center facility. Customer will need to order x-connect from Via West between the Vz demarc at relay rack 106.02 to their colo cage. C RR is for MM fiber hand off and the connector type at the Vz hand off will be SC connectors. 2/10- escalating to find out status of trunk 2/16- need a via west ticket number in order to dispatch 3/7- still pending a via west ticket . Melissa is working with Dianne from Via West. 4/11- supped for west ticket WEST TICKET # 1402610. 4/17- order RFC tested, pending flow and order closure. 5/3- ready for activation, engineer infomed
2012-10-12 | ShaRita | UOK04-05-IJ | Oklahoma City, OK | 3072 2xT1 with md5 UHGVERbgpbqZyofa | IQBKC86G | 5599283 | P1959841 | 5219286 | 2048 | BCBKWMT60001-0002 | 97/HCGS/936581 /SW DEMARC LOC: 7TH FLR TELCO CLOSET-MM #3-SLOT DEMARC LOC Continued: #3-SLOT #3-RJ48C |  |  |  |  | bpdd |  |  | unitedhealthgroup-64636 | 763-744-1556 john_l_rothstein@uhc.com |  | 10/26/2012: Order is with provisioning. Waiting for FOC date. 11/01/2012: All testing complete and circuit ready for activation.
2013-01-23 | ShaRita | UKS05-05-IJ | Overland Park | 20M ethernet with MD5 UHGVERbgpbqZyofa handoff RJ45 - Copper type 4 (we can't offer an electfcal handoff on type 4, customer will have to order converter to convert from Optical to electrical | SAR 1-1MYQ0P3 new SAR SAR 1-1NP2MCB Smartform 189805334 NSPE0006416470 IQBKKD4X (port) IQBKKD4T (EACS) | 5741377 | P1996363 (port) P1996362 (EACS) | 5340452 | 12896 | BCBKY6KH0001 (port) EDBKY6KF0001 (EACS) | DMARC: 2nd floor telco closet position 2 port. 74/KQGN/904754//SW Overture dmarc Demark: 2ND FLOOR TELCO CLOSET WEST TELCO WALL TELCO BOARD PORT 1 ON OVERTURE. |  |  |  |  | bpdd | 2013-04-18 | 2013-04-16 | UnitedHealth Group-64870 | 763/694-7409, terry_bjorke@uhc.com |  | 1/24- pending approval SAR from Matt 2/7- SAR approved 2/13- sent to OM. 2/14: In process downstream, pending OS 2/20: MRV code corrected, moving forward 2/21 - TIN submitted to OE for processing - 2/25- SAR id handoff not matching customer requested. Asking Matt for new SAR. 2/27- pending new SAR, informed Terry we can't support electrical handoff 3/19- SAR is now approved again, tin re-submitted 3/20- order with provisioning 3/28- asked provisining to pick this up 4/3- esclating again for provisioning pick up 4/8- Per LEC FOC will be ON 4/11/2013 still waiting for VLAN 4/10- pending lec deliviery, no formal foc issued 4/18- order ready for activation, engineer infromed.
2013-01-24 | ShaRita | KY010-02-IJ | Louisville, KY | 44736, DS3 MD5 UHGVERbgpbqZyofa | smartform 189789898 CDR201301240081 NSPE0006334903 IQBKHL6N | 5716804 | P1982693 | 5321888 | 40256 | BCBKYB8R0001 | BCHG4054 (level 3) K1/HFGS/450861//SC AT&T to customer Demarc: 1st fl pulsecom telco room, wall-mounted jack 1 |  | 1/29/2013 6/11/2013 | 5/30/2013 6/20/2013 7/5/2013 |  | bpdd | 6/6/2013 re-commit date 6/24/2013 | 2013-07-10 | UnitedHealth Group-65021 | 763/694-7409, terry_bjorke@uhc.com | activated with Terry on 7/12 | 3/4- tent FOC for 4/19- per AT&T JOB NUMBER = TBD,NEED TO ENGZ FIBER AND PL EQUIP DDD/BPD UNDER EVAL 3/20- AT*T issued a CNR stating that a better lcon was needed. Melissa reached out to Michelle Jarboe at 502-426-4800 x 192 to see if she was aware of the order, Tim wood alternate 502-426-4800 ext 363. 3/28- formal FOC received for 4/19 - JOB NUMBER = TBD,NEED TO ENGZ FIBER AND PL EQUIP DDD/BPD UNDER EVAL 4/3- asked to have ASR supped for LCOn 4/10- CNR cleared, pending 4/19 FOC 4/25- supped to change lcon. 4/25- fOC for 5/30 JOB 35L02008N 5/22- pending FOC date of 5/30 5/29- loop delivered on 5/28 but but cannot test it end-to-end because of an issue with CFA between level 3 and AT&T. Pending Issues: was told by Level 3 that their CFA with AT&T is at a bad port (8 0047/T3TIE/1/LSVLKYWE/LSVLKYWEWA2). notified provisioner if he can request AT&T to have it moved to the next available port without sending out a new ASR. awaiting his response 6/6- escalating with level 3, they are saying the CFA is in use, but we show it open on our side. 6/13- pending FOC date of 6/20; awaiting loop delivery before circuit can be tested end to end 6/20- Pending confirmation loop was delivered 6/27- order is escalated; pending FOC 6/28- pending FOC date of 7/5; VzB network has already been pre-tested clean and good for this order. We are awaiting for the LEC loop delivery to have this tested end-to-end. 7/3- pending FOC date of 7/5
2013-04-09 | ShaRita | FL038-02-IJ | 2960 SW 8th Street, Miami, FL | 3072 2xT1 with MD5 UHGVERbgpbqZyofa | smartform 189848454 NSPE0006647726 IQBKLG8Q | 5824297 | P2004059 | 5349560 | 1536 | BCBK0NBF0001-0002 | 60/HCGS/449093//SB 1st floor server room multimount 3 slot 4, tagged not extended 60/HCGS/449094//SB 1st floor server room multimount 4 slot 1, tagged not extended | 0CW1FZ | 2013-04-17 | 2013-04-30 |  | bpdd | 2013-05-07 | 2013-05-01 | unitedhealthgroup-65262 | 763.553.4801, sonja_d_mroczynski@uhc.com | activated with Sonja on 7/15 | 4/2- asked John to clarify suite and lcon phone number 4/9- John provided corrected address 4/10- sent to OM. 4/19- ASR sent. Pending FOC 4/19-- FOC 4/30, commit 5/7 5/2- order ready for activation, engineer informed.
2013-04-04 | ShaRita | C1556-02-IJ | Connextions 4809 East Thistle Landing Drive, phoenix | 44736 DS3 with MD5 encyption of UHGVEReccgas4Usp9 | smartform 189845347 CDR201304080047 NSPE0006629703 IQBKK8G6 (canc) phx I23030 IQBKL3CY (re-issue) | 5816115 | P2009013 | 5355601 | 12288 | BCBK0YG00001 | 14/HFGS/975595//MS DEMARC LOC: DEMARC:1ST FLOOR MAIN IT DATA ROOM SHELF:1 SLOT:1/3 DMARC Labeled MCI (Yes or No): yes |  | 2013-04-13 | 2013-04-26 | 2013-05-15 | bpdd | 2013-05-22 |  | uhg-ecc - 65496 | 763-744-0840 matt_f_seymour@uhc.com | per Matt circuit is up on 7/16. | 4/11- local order issued, pending tie down to send ASR to Centurylink 4/19- FOC for 4/26, pending commit date 4/30 pushing for commit date 5/2- LEC ASR is now held, it appears the order had to go back into redesign, melissa is investigating. 5/9- order re-designed, pending new asr 5/17- loop delivered, pending testing 5/22- Loop delivered. pending mux. issue with open channel. Coordinating with operations and provisioning 5/29- Ready for activation
2013-06-26 | ShaRita | none REQUEST TO CANCEL | Miami, FL | 44736, DS3 md5 encryption UHGVERbgpbqZyofa change terremark handoff | CQBKNMWH MIA-C36435 | 5951895 | P1995221 | 5338777 | 10800 | BCBKY39N0001 | 3X-2ET-DNGL-0081 to Loc Z demark: 2nd floor; Terremark west Meet-Me-Room; dsx3 panel; rr NAPMIA.2BX78.105.02.11 10. |  |  |  |  | bpdd | 2013-07-10 |  | unitedhealthgroup-65146 | 763.553.4801, sonja_d_mroczynski@uhc.com | need to re-request once handoff is changed with Terremark. | 6/27- submitted tin to OE as internal expedite 7/3- pending local order 7/11- order requested to be cancelled. Per Terremark customer can use slot 10.
2013-02-07 | B end | UK526-06-CJ | London, UK | Upgrade port 20M and Gold CAR letterkenny SOO W0Y12673 - letterkenny. | s/o 5254467 and 5254453 |  |  |  | upgrade 3072 | w0z04078 W1A28021 (EA) | ONEA614993 |  |  | 2013-07-05 |  | bpdd | 2013-07-24 | 2013-07-10 | UnitedHealth Group- 65160 | 715-841-7731 sonja_d_mroczynski@uhc.com | activated on 7/16 with Sonja. | 2/7- sent for SOF 2/14: pending SOF 3/20- SOF signed and returned to b end. 3/26- Siva sent new SOF to uhg, the first one had wan analysis and managed services, needed to be corrected. 4/19- per John SOF is back with VZ. Melissa will follow up 5/2- order sent to BT for 100mg tail, pending date 5/9- still pending response from BT 5/17- pending site survey 5/22- pending FOC, expected 5/24 5/28- Please be informed the installation date by 3rd party provider is set to 5th July 2013. Once the circuit is completed by 3rd party provider we can plan completion of remaining tasks which are hardware, software cross connect and local end testing. 5/30-Per BT openreach- WE ARE CURRENTLY WAITING FOR FIBRE ESTIMATES TO BE RAISED ON THIS CIRCUIT SURVEY RESULTS HAVE SINCE BEEN PROVIDED AND NO COSTS ARE APPLICABLE. 6/13- PTT FOC 7/5 6/20- pending PTT FOC of 7/5 7/3- Per PTT, external fiber engineers have arrranged access w/ customer for Friday 5th of July for fiber work- splicing/jointing. Fit & test to be arranged once fiber work completes. 7/11- ready for activation-scheduled.\
2012-09-11 | ShaRita | na | Santa Fe, NM 2904 Rodeo Park Dr E | currently homed to VzB PE router WITGE01 in Wittman, AZ. Request re-homing to AQHGE01 in Albuquerque, NM. | CW: 189712760 NSPE0005949495 CQBKC9GV | 5596048 | P1637895 |  |  | BCBJ07YW0001 – 0005 | [8 empty] | unitedhealthgroup- 65188 | Dan Stripka | completed with Dan on 7/18 | 11/7 pending mux. Followed up with provisioning 11/8- order is ready to be schduled.
2013-05-30 |  |  | DDOS removoval from Lenexa | [18 empty] | per Scott Moritz DDOS removed
2013-04-12 | ShaRita | C1554-02-IJ | SourceHOV 1250 14 Mile Road, Troy, MI secondary CFA of SCDR1/OC48/013/TROYMIMN/TROYMIFJH03 | 44736 DS3 with MD5 encyption of UHGVEReccstr82tcW | smartform 189849303 CDR201304120038 NSPE0006652669 IQBKLLLN DET-I0028649 | 5825323 | P2004676 | 5350475 | 128 | BCBK0PF80001 | /HFGS/314899//MB Demarc: Main telco rm relay rack 1 shelf 2 slot 6 Extended(Y/N): n Tagged (Y/N): y | 0CW1ZG | 4/24/2013 6/06/2013 | 2013-06-20 | 2013-06-20 | bpdd | 2013-07-19 | 2013-07-02 | UHG-ECC-TCW- 65204 | 763-744-1587 leon_l_betterman@uhc.com | completed with Leon on 7/19 | 4/19- sent to provisioning on 4/17, pending pick up 4/25- ASR sent, pending FOC 5/2- clarification back from the ASR on the sec CFA 5/9- escalating with provisioning on the ASR 5/17- need new CFA from UHG 5/22- supp'ed order to reflect revised CFA, NSCDR1/OC48/STS/013/TROYMIFJH03/TROYMIMN 5/29- need revised CFA from UHG 6/6- FOC 6/20 6/13- Issue with cross connect. Will proceed on testing the circuit once issue is fixed and mux is completed, still pending FOC for 6/20 6/20- Pending confirmation from AT&T loop delivered 6/27- dispatch for local order I0028649 at site Troy, MI, disp is already completed. pending dispatch for the LOS as per ATT, at site I9701, TROY MI, dispatch schedule is today, 06272013. will continue testing with ATT once dispatch is completed. 7/3- Ready for activation; customer notified.
2013-06-11 | ShaRita | none | 9900 West 109th Street Overland Park, KS 66210 | disconnect | NSPE0006891657 OQBKNDRN |  | P1578488 |  |  | BCBJT4TC0001-0002 |  |  |  |  | bpdd | 2013-07-10 | 2013-07-10 |  |  |  |  | disconnect due date on 7/10 7/12- disconnect completed
2013-06-11 | ShaRita | none | 10895 Grandview Drive Suite 200 Overland Park, KS 66219 | disconnect | NSPE0006891600 OQBKM81W |  | P1966721 |  |  | BCBKW9270001-0008 |  |  |  |  | bpdd | 2013-07-10 | 2013-07-12 |  |  |  |  | disconnect due date on 7/10 7/12- disconnect completed
2013-06-11 | ShaRita | none | 6545 Flying Cloud Drive Eden Prairie, MN 55344 | disconnect | NSPE0006891749 OQBKM88N |  | P1896525 |  |  | BCBKPND30001-0004 |  |  |  |  | bpdd | 2013-07-11 | 2013-07-15 |  |  |  |  | pending disconnect date disconnect due on 7/11 7/12- soft disconnect completed 7/15- disconnect completed
2013-06-11 | ShaRita | none | 9300 Tech Center Drive 2nd Floor Sacrame NTO, CA 95826 | disconnect | NSPE0006892121 OQBKM7WJ |  | P1739242 |  |  | BCBKBCVN0001 |  |  |  |  | bpdd | 2013-07-11 | 2013-07-15 |  |  |  |  | disconnect due on 7/11 7/15- disconnect completed
2013-06-11 | ShaRita | none | 11490 Xeon Street NW Suite 200 Coon Rapids, MN 55448 | disconnect | NSPE0006892313 OQBKM9T5 |  | P1659671 |  |  | BCBJ23HK0001-0002 |  |  |  |  | bpdd | 2013-07-11 | 2013-07-16 |  |  |  |  | pending disconnect date disconnect due on 7/11 7/12- soft disconnect completed 7/16- disconnect completed
2013-06-11 | ShaRita | none | 14100 Business Center Drive Elk River, MN 55330 | disconnect | NSPE0006892384 OQBKM886 |  | P1601585 |  |  | BCBJWW2N0001 |  |  |  |  | bpdd | 2013-07-11 | 2013-07-16 |  |  |  |  | pending disconnect date disconnect due on 7/11 7/16- disconnect completed
2013-06-11 | ShaRita | none | 14100 Business Center Drive Elk River, MN 55330 | disconnect | NSPE0006892397 5292776 |  |  |  |  | W0V78421 |  |  |  |  | bpdd | 2013-07-11 | 2013-07-15 |  |  |  |  | pending disconnect date disconnect due on 7/11 7/15- disconnect completed
2013-06-11 | ShaRita | none | 6150 Trenton Lane Plymouth, MN 55442 | disconnect | NSPE0006892418 OQBKM6XV |  | P1866603 |  |  | BCBKMPSR0001 |  |  |  |  | bpdd | 2013-07-11 | 2013-07-15 |  |  |  |  | disconnect due on 7/11 7/12- disconnect completed 7/15- disconnect completed
2013-06-11 | ShaRita | none | 6150 Trenton Lane Plymouth, MN 55442 | disconnect | NSPE0006892432 OQBKM6X2 |  | P1860947 |  |  | BCBKMC0L0001 |  |  |  |  | bpdd | 2013-07-11 | 2013-07-16 |  |  |  |  | disconnect due on 7/11 7/16- disconnect completed.
2013-06-11 | ShaRita | none | Nobel House - Siskin Drive - Middle March Office Village Conventry United Kingdom CV3 4JF | disconnect | NSPE0006892468 5289812 | 5931606 |  |  |  | W0Y40352 |  |  |  |  | bpdd | 2013-08-09 | [5 empty] | disco completed on 7/12
2013-06-11 | ShaRita | none | 9900 West 109th Street Overland Park, KS 66210 | disconnect | NSPE0006891657 OQBKNDRN |  | P1578488 |  |  | BCBJT4TC0001-0002 |  |  |  |  | bpdd | 2013-07-10 | 2013-07-17 |  |  |  |  | disconnect due date on 7/10 7/17- disconnect completed
2013-03-12 | ShaRita | FL752-02-IJ | Miami, FL | 44736, DS3 md5 encryption UHGVERbgpbqZyofa | smartform 189824236 CDR201303120032 NSPE0006522122 IQBKJ7XH MIA-I0036041 (comp) | 5782176 | P1995221 | 5338777 | 10800 | BCBKY39N0001 | 3X-2ET-DNGL-0081 Loc Z demark: 2nd floor; Terremark west meet-me-room; dsx3 panel; rr NAPMIA.2BZ81.106.00.01:14. |  |  | 2013-03-28 |  | bpdd | 2013-04-25 | 2013-03-27 | unitedhealthgroup-65146 | 763.553.4801, sonja_d_mroczynski@uhc.com | need to re-term | 3/14- order in OE 3/20- Local portion due 3/28 3/28- order delivered and ready for activation, engineer informed.
2013-05-09 | ShaRita | CA005-03-IJ | 7067 N. Mariposa Street, Fresno, CA | 1536, T1 with MD5 encryption UHGVERbgpbqZyofa | smartform 189872638 NSPE0006780035 IQBKMGVZ | 5880587 | P2011464 | 5359056 | 1024 | BCBK04PH0001 | 88/HCGS/529814 /PT DEMARC LOC: NI IN SLOT 1 OF 2 SLOT MOUNT AT MPOE DEMARC LOC Continued: AT MPOE Extended Wire (Yes or No): YES EW Reason/Location:PNL 1, JK 3, 1ST FLR Jack Type: RJ48C DMARC Labeled IXC (Yes or No): Yes DMARC Labeled LEC (Yes or No): Yes |  | 5/21/213 | 2013-06-05 | 2013-06-03 | bpdd | 2013-06-12 | 2013-06-06 | UnitedHealth Group- 65289 | 91 91600 84400, harish_kandpal@uhc.com | Requested Date 7/19/2013 5:30PM Central Time bridge 866-819-9840 pcode 3365052 | 5/14- sent to OM 5/22- pending FOC date of 6/5 5/29- pending FOC date of 6/5 6/6- order completed, activation notice sent 7/19- (07/19/2013 5:16 PM) ******************Activation Completed******************* Customer: Keith Nange- 8607028284
2013-06-05 | ShaRita | IL004-05-CJ | 200 East Randolph St, #5301, Chicago, iL 60601 | Upgrade existing 4xT1 to 6xT1, 9216 | smartform 189892236 NSPE0006875210 IQBKM509 OQBKM8G9 | 5925633 5931409 | P1926350 (out) P2016456 (in) | 5057098 | 3072 | BCBKS1FG0001-0004 (out) BCBK1G6C0001-0006 (in) | /HCGS/660718 /LB DEMARC LOC: BASEMENT NETPOP SLOT 3 OF 14 Jack Type: 66BLK /HCGS/660719 /LB DEMARC LOC: BASEMENT NETPOP SLOT 11 OF14 Jack Type: 66BLK |  | 2013-06-18 | 2013-07-05 | 2013-07-05 | bpdd | 2013-07-11 | 2013-07-08 | unitedhealthgroup-64943 | 763-744-1575, daniel_j_skripka@uhc.com | hotcut completed on 7/25 with Dan. | 6/6- sent to ShaRita 6/13- order resubmitted correctly as in/out on 6/11; sent to OE 6/20- pending FOC date of 7/3 6/27- pending FOC date of 7/3 7/3- pending CORRECT foc date of 7/5 7/8- order ready for hotcut. Engineer informed.
2013-06-12 | ShaRita | IA021-05-CJ | 1089 Jordan Creek Parkway, Des Moines, IA 50266 | Upgrade from 2xT1 to 3xT1, 4608 | smartform 189896406 NSPE0006904301 IQBKM8F1 OQBKM9CS | 5935073 | P1920499 (out) P2017011 (in) | 5034547 | 2.048 no upgrade | BCBKSKY20001-002 (out) BCBK1H4R0001-0003 (in) | 1st floor telco/elec room, mount 2, slot 3/14 lcon/jackie said vendor to extend. 32/HCGS/088472 /NW |  | 2013-06-20 | 2013-07-05 | 2013-06-27 | bpdd | 2013-07-12 |  | unitedhealthgroup-65134 | 91 91600 84400, harish_kandpal@uhc.com | hotcut complete with Harish on 7/26 | 6/20- ASR sent; awaiting LEC to provide FOC date 6/28- Loop was delivered 6/27. Testing compeleted and ready to schedule hotcut. Customer notified.
2012-10-03 | ShaRita | UFL71-05-CJ | Maitland, FL | Upgrade port to 7680 5xT1 with md5 UHGVERbgpbqZyofa | CW: 189711940 NSPE0005926370 IQBKCYFM OQBKCZTM | 5584698 | P1957295 (in) P1529034 (out) |  | upgrade to 3072 | BCBJPSRH0001-4 (out) BCBKWG1R0001-0005 (in) | 50.HCGS.122068..UFLG per century link delivered. demarc 2nd floor unit 200 rj48c not extended sl ot 11 of 12.closing ticket. , |  |  |  |  | bpdd |  |  | unitedhealthgroup-64611 | 91 91600 84400, harish_kandpal@uhc.com | 7/25/2013 09:30:00 PM Central Time / Conference bridge 866-878-8630 pass code 6653710 | 10/3- sent to OM. 10/4- pending oM submit 10/7 Om submitted 10/11- pending provisoning pick up 11/12- order is ready for upgrade trying to get dmarc info. 11/15- esclating for dmarc 11/21- order ready to schedule, engineer informed 7/25- COMPLETED, CIRCUIT IS UP/UP AND ERROR FREE Customer Accepted CIRCUIT UP : YES Customer Name / Number: Keith Mangene 860 702 8284
2012-10-24 | ShaRita | UTX28-05-CJ | 1333 WEST LOOP S, HOUSTON TX 77027 9116, United States | upgrade to 10752 7xT1 | CW: 189725936 IQBKD41S OQBKD5SD | 5614208 | P1685166 (out) P1963231 (in) | 1576470 | upgrade to 3072 | BCBJ6G670001-0003 (out) BCBKW29R0001-0007 | 28/HCGS/897942//SW DEMARC LOC: 5TH FLR MPOE TELCO. CAB-9/SL 28/HCGS/897943//SW DEMARC LOC: 5TH FLR MPOE TELCO RM. CAB-9/SL 28/HCGS/897944//SW DEMARC LOC: 5TH FLR MPOE TELCO. CAB-9/SL 28/HCGS/897945//SW DEMARC LOC: 5TH FLR MPOE CAB-1 SLOT-14 |  |  | 2012-11-21 |  | bpdd |  |  | unitedhealthgroup-64687 | (91) 9810059326 , pradeep_yadav@uhc.com | 5/22- Pending customer confirmation. AFTER TELCO FIX something on the t1, it went up pls see stats below; circuit ready for hotcut can ping across but 1 leg is down, dtac open etms ticket to prove the demarc and check the niu at site. crossed 1 working versus the non working and serial interface @ pe side for ckt no 3 came up and ckt 4 went down, looks like a wic card issue but when we placed the 3rd t1 to the spare port on the new wic wont avail, we need to make sure that existing t1 is good ticket 2013050900169 | 11/2/2012 Order is with provisioning. 11/9- FOC fo 11/21 11/29- lec delivered, pending testing 12/6- order ready for hotcut. Engineer informed. \
2013-06-17 | Melissa | none | Medecision ds3 | disconnect | NSPE0006917218 OQBKNBJ4 |  |  |  |  | BCBKCCW50001 |  |  |  |  | bpdd | 2013-07-17 | 2013-07-19 |  |  |  | disconnect due on 7/17 7/25- disconnect completed 7/19
2013-05-30 | ShaRita | FL027-02-IJ | 591 Oak Commons Blvd Kissimmee FL | 10752 7xT1 md5 UHGVERbgpbqZyofa | smartform 189887702 NSPE0006849312 IQBKMWHW | 5909575 | P2014180 | 5362831 | 1536 | BCBK1BN80001 BCBK1BN80002 BCBK1BN80003 BCBK1BN80004 BCBK1BN80005 BCBK1BN80006 BCBK1BN80007 | 50/HCGS/141709//UFLG 1ST FLR TELCO RM BACKBOARD, SLOT 9 OF 28 50/HCGS/141710//UFLG 1ST FLR TELCO RM BACKBOARD, SLOT 15 OF 28 50/HCGS/141711//UFLG 1ST FLR TELCO RM BACKBOARD, SLOT 11 OF 28 50/HCGS/141712//UFLG 1ST FLR TELCO RM BACKBOARD, SLOT 12 OF 28,RJ48C 50/HCGS/141713//UFLG 1ST FLR TELCO RM BACKBOARD, SLOT 13 OF 28 50/HCGS/141714//UFLG 1ST FLR TELCO RM BACKBOARD, SLOT 14 OF 28 50/HCGS/141715//UFLG 1ST FLR TELCO RM BACKBOARD, SLOT 15 OF 28, RJ48C |  | 2013-06-03 | 2013-06-14 |  | bpdd | 2013-06-21 | 2013-06-18 | unitedhealthgroup-64919 | 214-647-4442 donald_r_osborn@uhc.com | completed with Don on 8/6 | 5/31- submitted to OE 6/6- pending FOC of 6/14 6/13- pending FOC date of 6/14 6/18- ready for activation, engineer informed.
2013-04-23 | ShaRita | UMD92-07-CJ | 6220 Old Dobbin Lane , Columbia, MD | upgrade to a full DS3 port, add dport/dcar | CW: 189865033 CDR201305010035 NSPE0006728703 IQBKL13X OQBKL3BB | 5849563 | P2008570 (in) P1653191 (out) |  |  | BCBJ2FBL0001 (out) | [5 empty] | bpdd |  |  | UnitedHealth Group | 91 - 98100 59326, pradeep_yadav@uhc.com | 08/02/2013 10:00 PM Central Time / Conference bridge 866-878-8630 pass code 6653710 | 5/1- sent to OM. 5/16- ready for hotcut 8/2- Customer: Pradeep Yadav cb # +91 9810059326 Remarks/Comments: circuit is up and processing traffic and Pradeep Yadav cb # +91 9810059326 accepted the ckt. Status: COMPLETED
2013-02-27 | ShaRita/Melissa | UMN99-43-IJ | Address: 6150 Trenton Lane N PLYMOUTH MN USA 55442 | 750M port commit on 1Gig-Ethernet access protected and on ring, SMF- LC connector | smartform 189836754 NSPE0006587022 u323983 IQBKLJMX / PLBK0NNV0001 - TENT status Local order has already received DLR/CLR, order step code: OPRE 5257595 / W1A29094 - CSCH 5258132 / W1A29283 - CSCH MIN- I34587 / gx-nsb-jcfg-0002 -- clsd RFC test CCR #: 1146837 (complete) CFO A163527 (clsd) CFO I0164002 (complete) cfo a164043 (clsd) cfo a164044 (clsd) cfo a164045 (clsd) min-a34680 (clsd) min-a24681 (clsd) | 5807096 |  |  |  | u323983 | gx-nsb-jcfg-0002Tagged with circuit id and order number. Demark is ifbasement (flr 0) MDF room, row 7.0M panel fb1 Jack A6 |  |  |  |  | bpdd | 2013-07-09 | 2013-07-09 |  |  |  | 4/10- pending design 4/18- working with provisioning on design 5/2- Cards installed, pending port orders and backhaul piece. 5/9- ROADM transponder cards are in place in Plymouth, Chicago side complete, pending backhaul and plymouth install, CDD set to 7/9/2013 5/17- CCR 1146837 complete. 5/22- all node work complete, pending rFC and ETE testing. 5/30- RFC testing set for this evening 6/6- RFC testing completed, Mux reviewed; expectations are to complete the mux this week. then we can test through the whole circuit 6/13- pending 892 dispatch at the DNG and MNE sites. MNE is scheduled today while DNG is set for tomorrow. Once all patchings are complete BNE will proceed on testing the ckt. 6/20- Dispatches are completed. All cross connects have been made. No red alarms on all of the NE's. Router is synced with the circuit. Working with Mitch on access for an ETE test date 6/27- Dispatch is still working with Mitch on access for ETE test date 7/3- Testing failed. BnE says the problem is with the Long Distance network. The loop in Chicago could not be tested. The local network is good. BnE is going to do some further trouble shooting. 7/9- order ready for activation/ Jim and Mitch informed. 8/8- activation completed 8/7 Completed Activation and testing, IN and OUT Bound was good, and Vendor Phillip accepted all services.
2013-04-12 | ShaRita | C1555-02-IJ | SourceHOV 1250 14 Mile Road, Troy, MI secondary CFA of SCDR1/OC48/21/TROYMIFJH03/TROYMIMN | 44736 DS3 with MD5 encyption of UHGVEReccgas4Usp9 | Smartform 189849371 CDR201304120041 NSPE0006652918 IQBKLLLS DET I28650 (clsd) | 5825460 | P2004679 | 5350477 | 128 | BCBK0PGB0001 | /HFGS/314945//MB | 0CW1ZJ | 2013-06-06 | 2013-06-11 |  | bpdd | 2013-07-01 | 2013-06-13 | UHG-ECC - 65414 | 763-744-2121 ryan_baker@uhc.com |  | 4/19- provisioning is designing 4/25- pending ASR 5/2- escalating for ASR 5/9- clarification came back on our request SCFA1 INVALID - SUPP TO CORRECT TROYMIMNK0 IS NOT ON THE SCID SCDR1 5/17- order currently on hold. Awaiting customer to provided a revised CFA. The CLLI: TROYMIMNK0 is not under SCID: SCDR1. 5/22- supp'ed order to reflect revised CFA, NSCDR1/OC48/STS/021/TROYMIFJH03/TROYMIMN 5/29- need revised CFA from UHG 6/6- escalated to DS3 provisioning for assistance with the rejected CFAs 6/13-ready for activation, engineer informed
2012-09-11 | ShaRita | na | Albuquerque, NM 8801 Horizon Blvd Northeast | currently homed to VzB PE router WITGE01 in Wittman, AZ. Request re-homing to AQHGE01 in Albuquerque, NM. | CQBKDZJN |  | P1637726 |  |  | BCBJ07M60001-4 | [9 empty] | Dan Stripka | circuit will be discoed, order is cancelled. | 11/7- escalating for mux so we can schedule hotcut 11/8 - order is in cord status and ready for hotcut.
2013-04-02 | ShaRita | FL046-02-IJ | 7800 SW 24th Street, Miami, FL | 1536 T1 with mD5 encryption UHGVERbgpbqZyofa | smartform 189842065 NSPE0006607804 IQBKK6WF | 5812216 | P2002534 | 5347433 | 1376 | BCBK0J0G0001 | 60/HCGS/448986//SB demarc info for this completed order.1st fl, server rm, cab 1, slot 4, tagged, not ext, rj48c.- |  | 2013-04-12 | 2013-04-25 |  | bpdd | 2013-05-02 | 2013-04-26 | unitedhealthgroup-65265 | 763.553.4801, sonja_d_mroczynski@uhc.com | sonja confirmed complete on 8/5 | 4/2- submit to OM 4/11- pending ASR. 4/19- FOC 4/25, commit 5/2 4/25- LEC hasn't delivered yet 5/2- order is ready for activation, engineer informed.
2013-03-19 | ShaRita | FL047-02-IJ | 9100 S Dadeland Blvd, Suite 1250 Miami, FL | 44736, DS3 md5 encryption UHGVERbgpbqZyofa | smartform 189830128 CDR201303190058 NSPE0006551568 IQBKKHTV MIA-I0036082 media converters CCR #:1144568 | 5790971 | P1996910 | 5341198 | 10800 | BCBKY7N40001 | 3X-2ET-IZG-0001 conduit to customer data room--x --ADC 1-U , 12-pos fiber panel.--x--1 feet SM fibers --x--5-Module Omnitron media convertershelf. slot 1. Extended to 14 th floor AC/Electrical room. MM fiber FDP x 2 feet MM fibers to media converter shelf slot 1. It has a SM<-->MM media converter card. |  |  | 4/8/13 6/3/13 | 2013-05-28 | bpdd | 2013-05-03 | 2013-05-28 | unitedhealthgroup-64528 | 763.553.4801, sonja_d_mroczynski@uhc.com | completed with Bob Bensen on 8/9 | 3/19- sent to OM 3/20- order sent to OS 3/28- FOC for 4/8, commit date 5/3 4/11- site survey completed. Need a new pair of media converter to extend DS3 to 14th floor, data room. Please reflect the floor number on the order. Lcon is Ken Glancy 305-670-8438 ext 1045. need multi mode media converters, two SC fiber terminating panel. Length of trunk fiber cable is pending. Customer needs to get a new 2" conduit. He will notify me once it is in. 4/25- media convereters shipped, called Ken to see on conduit status 5/2- pending media converter install of 5/9 5/9- conduit is now in place. Fiber cable pull is proceeding, fiber is ordered. 5/17- Order was supp for new customer's due date to 6/3. This was due to customer's conduit. Pending CCR #:1144568 - fad/rft date provided - 05/21/13. The equipment installation schedule of dispatches are mostly on 5/31. pending cable pull. 5/22- Pending FOC date of June 3rd 5/29- Ready for activation
2012-11-07 | B end | CN501-04-CJ | Burnaby, BC | 4608 3xT1 - Add 1 T1 to existing 2xT1 | 5296379 | 5944764 | P1938004 (out) |  | upgrade to 2048 | W0Z04136 (bearer) W0Z04137 (bearer) W0Z04138 (port) | 55/DHXS/329593/000/BCTC/000 LABELED DEMARC:BOX 2 CIRCUIT 2 IN SERVER ROOM |  |  |  |  | bpdd | 2013-07-12 | 2013-07-15 | unitedhealthgroup-65144 | 702-303-7293, tauoa.falo@uhc.com | completed with Tauoa on 8/12. | 11/15- pending SOF 1/23- SOF with UHG 6/17- SOF with Verizon, processing 7/11- checking with Canada rep on order numbers. 7/12- FOC date is 7/12 for new local loop 7/18- Telus delivered loop and order is ready to schedule for hotcut. Engineer informed.
2012-09-11 | ShaRita | TX143-02-IJ | Pleasanton, TX | 10752, 7 x T1 with MD5 UHGVERbgpbqZyofa | CW: 189697978 NSPE0005842604 IQBKB9GT | 5557154 | P1953192 | 5207505 | 1536 | BCBKV62J0001-0007 | 31/HCGS/702882//SW cabinet 1, slot 1 31/HCGS/702883//SW cabinet 1 slot 2 31/HCGS/702884//SW cabinet 1 slot 2 31/HCGS/702885//SW cabinet 1, slot 4 31/HCGS/702886//SW cabinet 2 slot 3 31/HCGS/702887//SW cabinet 2 slot 2 31/HCGS/702888//SW cabinet 2 slot 3 Both located at the New telco room first floor, rj48c, not extended | 5/30/2013 7/2/2013 | 4/10/2013 6/24/2013 7/19/2013 |  |  | bpdd | 2013-08-01 | unitedhealthgroup-65042 | Deven Patterson 763-744-0696 deven_patterson@uhc.com |  | Deven activated on 8/12 | 4/3- FOC for 4/10 4/10- order held again for conduit 4/17- trying to get a copy of site requirements 4/25- still workign through conduit issue 5/17- order currently on hold due to customer not ready. per At&t testing center, customer needs conduit from serving pedestal to new backboard. 5/-22- order currently on hold due to customer not ready. per At&t testing center, customer needs conduit from serving pedestal to new backboard. spoke with lcon via email and phone and advised that order cannot proceed until site requirement is completed. 5/30- lcon advised that site requirements have been completed. ASR re-issued 5/30. 6/6- pending FOC of 6/24; spoke with At&t tech and he volunteered to go by the site to confirm if necessary requirements have been completed to avoid jepping pending FOC date 6/13- pending FOC of 6/24; customer spoke with At&t tech to clarify the site requirements for the conduit. 6/20- pending FOC of 6/24 6/27- telco not delivered; conduit placed in wrong location per tech 7/3- pending new FOC date of 7/19 7/11- pending new FOC date of 7/19 7/18- pending confirmation loop was delivered 7/24- dispatched scheduled for 7/29 at 11am at terminal for test assist 8/1- ready for activation; customer notified.
2013-05-30 | ShaRita | none | 777 BAY STREET TORONTO - ONTARIO TORONTO - ON M5G2C8 | disconnect | NSPE0006841850 5288262 port 5288263 access | 5922779 |  |  |  | Port W0V14323 Bearer W0W17895 |  |  |  |  | bpdd |  | 2013-08-06 |  |  |  | pending disconnect date 6/6- John provided a local contact to Sharita pending disconnect due date of 8/6 (standard interval) 8/8- disconnect completed
2013-06-13 | ShaRita | none | Wiesbaden Germany | disconnect | NSPE0006900473 5291942 5291944 | 5934777 |  |  |  | W0V46233 |  |  |  |  | bpdd | 2013-08-13 | 8/7/213 |  |  |  | disconnect being processed disconnect due date 8/13 8/8- disconnect completed
2013-07-03 | ShaRita | none | Horizon Blvd NE Albuquerque, NM 87113 | disconnect | NSPE0006990672 OQBKN0L1 |  |  |  |  | BCBJ07M60001-0004 |  |  |  |  | bpdd | 2013-07-31 |  |  |  |  | 7/3- submitted to Sadisconnect 7/11- pending request CQBKDZJN (rehome) to be cancelled first before disconnect can be requested. 7/18- disconnect due on 7/31 8/1- soft disconnect completed 8/8- disconnect completed
2013-07-03 | ShaRita | none | 1624 Westgate Circle Suite 175 Brentwood, TN 37027 | disconnect | NSPE0006990846 OQBKNV1M |  |  |  |  | BCBKMYKF0001-0006 |  |  |  |  | bpdd | 2013-07-31 | 2013-08-02 |  |  |  | 7/3- submitted to Sadisconnect 7/11- disconnect due on 7/31 8/1-pending soft disconnect 8/8- disconnect completed
2013-07-03 | ShaRita | none | 840 N. Telshor Suite AB Las Cruces, NM 88011 | disconnect | NSPE0006990998 OQBKNV1N |  |  |  |  | BCBKV0R40001-0002 |  |  |  |  | bpdd | 2013-07-31 | 2013-08-02 |  |  |  | 7/3- submitted to Sadisconnect 7/11- disconnect due on 7/31 8/1- soft disconnect completed 8/8- disconnect completed
2013-07-03 | ShaRita | none | 840 N. Telshor Suite AB Las Cruces, NM 88011 | disconnect | NSPE0006990998 OQBKNV1P |  |  |  |  | BCBJ2MKW0001 |  |  |  |  | bpdd | 2013-07-31 | 2013-08-02 |  |  |  | 7/3- submitted to Sadisconnect 7/11- disconnect due on 7/31 8/1-pending soft disconnect 8/8- disconnect completed
2013-07-03 | ShaRita | none | 10052 Mesa Ridge Place Suite 200 San Diego, CA 92121 | disconnect | NSPE0006991084 OQBKNV1Q |  |  |  |  | BCBJRHYW0001-0002 |  |  |  |  | bpdd | 2013-07-31 | 2013-08-02 |  |  |  | 7/3- submitted to Sadisconnect 7/11- disconnect due on 7/31 8/1- soft disconnect completed 8/8- disconnect completed
2013-01-11 | Neha-B end | AU534-02-IJ | Brisbane, Australia | 2048 E1 with MD5 UHGVERbgpbqZyofa | s/o 5259541 OVI 1-1155954135 GL 7190524 BEARER ORDER: 5267113 |  |  |  | 1536 | W1A29925 | optus circuit id CCT ID: 44QJ O4WF NP002 Demarcation is temporarily mounted on Level 14 Comm Rack, Comms Room, Rack 1, RU 1, Jack 2, and will be moved back to Rack 2 when customer relocates. |  |  |  | bpdd | 2013-08-02 | 2013-07-25 | UnitedHealth Group-65036 | 763-744-1556 john_l_rothstein@uhc.com | Noemie accepted on 7/25 | 5/23- per John lease is signed........melissa will let the teams know 5/30- optus has been informed to proceed with order 6/6- Melissa is following up to see if we have received a date from Optus 6/13- Melissa asked ops team to follow up with Optus to see where they are in the design process. 6/20- LATEST UPDATE FROM OPTUS: THE ORDER IS DELAYED DUE TO CUSTOMER SITE IS NOT READY. THE CUSTOMER CONTACT, ALLISON, ADVISED OPTUS ENGINEER TO CONTACT THE SITE MA NAGER, SHANE, AND CHECK IF THE SITE IS READY. SHANE ADVISED THE COMMS ROOM I S UNDER CONSTRUCTION BUT THE COMMS RACK IS PROBABLY A FEW WEEKS AWAY YET. SHANE ADVISED HANDOVER IS THE 8TH AUGUST AT THIS STAGE 6/27- Order on hold, customer site not ready. Informed Optus that comms room will be ready on July 8th and to aim to deliver shortly after this date 7/11- have delivered the circuit according to customer’s request: Demarcation is temporarily mounted on Level 14 Comm Rack, Comms Room, Rack 1, RU 1, Jack 2, and will be moved back to Rack 2 when customer relocates. testing 7/18- pending soft loop from Optus for ping testing. 7/19- RECEIVED A CALL FROM MARK OF OPTUS AND SAYS A LOOP WAS PROVIDED AT THE FARTHEST POINT FACING VERIZON NETWORK. UNABLE TO SEE THE LOOP, INTERFACE STATUS DOWN/DOWN. NEED TO ENGAGE AUSTRALIA FOPS TEAM TO CHECK LAYER 1 7/25- order accepted and turned up by UHG, pending order closure 8/1- Melissa pushing for bearer order closure. All work complete. 8/8- escalating for order closure 8/14- orders now closed
2012-07-19 | ShaRita | na | Trumbull, CT (ICM change for diversity) | please re-route circuit BCBKRXH20001 to make it diverse from BCBKR0V90001, we need access and pop diversity. | CW: 189635101 NSPE0005648901 CQBJ9J58 | 5484021 |  |  |  | BCBKRXH20001 | [5 empty] | bpdd |  |  |  | completd with peter on 8/14 | Requested Date: 08/14/2013 12:00 AM Central Time brige 866-878-8630 pcode 6653710 | 7/26- order sent to provisioning 8/2- prov dissapproved, workign with OS to resbumit 8/9- they are saying they can't provide pop diversity, Melissa is investigating 8/14- will move forward wthout pop diverisity, re-marketing approving order. 8/23- provisioning has the order and is working 8/28- ready to schdule.
2013-07-11 | B end | UK750-02-IJ | SunGard Availability Services Ltd C/O Global Switch 2 , 3 Nutmeg Lane, London, , E14 2AX,UK- 11th floor / Area 7-Verizon Rack | 50M Ethernet with md5 encryption UHGVERbgpbqZyofa SOO to Letterkenny - circuit ID W0Y12673 move to new dmarc | OVI 1-1215298991 s/o: 5307283 new 5317509 |  |  |  | 15360 | W1A31298 |  |  |  |  | bpdd | 2013-08-12 | 2013-08-08 | unitedhealthgroup- 65020 | 763/694-7370, masroor_khan@uhc.com |  | 7/11- ovi order initiated 7/18- VMAIL LEFT FOR PAUL ASH ACCORDING TO HIS VMAIL HIS OOH UNTIL THE 18TH TEV EMAIL SENT pending TEV 7/25- ASR sent to PTT, pending date 8/1- this is on-net. Prep work for move done at the node. Asking B end when tech can dispatch to custoemr site to move the circuit 8/8- circuit moved to the correct location, pending order closure 8/14- order closed
2013-02-26 | ShaRita | UMN99-43-IJ | Plymouth, MN ECC | 155520 OC3 with MD5 UHGVEReccgas4Usp9 Fiber SMFLC connector | CW: 189814944 NSPE0006464836 CDR201303010037 IQBKJXF5 MIN I34424 | 5764107 | P1993005 | 5335502 | 90000 | BCBKYY740001 | o2-73c-jcfg-0002 |  |  |  |  | bpdd |  |  | UHG-ECC - 65532 | 763-7442154 scott_moyer@uhc.com | completed with Scott on 8/19 | 3/7- order over to local provisioning 3/13- order sent to ops for install 3/20- order was engineered to the wrong ring. Phil and Rudy are working together on this. 3/25- CCR #:1140044 for SFP cards on ROADM ring. 3/28- CCR rejected, working with local design and planning. 4/2- pending CCR 1140044 for SFP cards, cards are shipped and with ops. phil called STeve B to get access to install them 4/10- CCR comlete. asked to have order progressed 4/18- Issued CCR # 1146711 for OC3 Multi-rate SFP at jcfg,01. Existing SFP is MM GigE which does not support multi-rate. CCR expedited 4/.25-new cards shipped and pending install. 5/2- oc3 sfp SM installed by CCR. This is fiber to 7100 Patch Panel at jcfg,01 : 7.0Q.1L:7 This is tied to Customer LC patch panel 7.0M.FB1A:7 5/17- Pending end to end testing once Local order MIN I0034424 is completed. 5/20- Ready for activation
2013-05-20 | ShaRita | UTX43-05-IJ | 2301 West Plano Parkway, Ste 300, Plano, TX 75075 | 44736, DS3 md5 encryption UHGVERbgpbqZyofa | smartform 189877681 CDR201305200050 NSPE0006803335 IQBKMJK2 | 5887245 | P2011780 | 5359666 | 3072 | BCBK05BD0001 | 12/HFGS/304180//GTEC Demarc: 1st floor vz cabinet, shelf 45, jack 5 of 6, | 6/25/13 5/29/13 | 2013-07-29 | 2013-07-15 |  | bpdd | 2013-07-31 |  | UnitedHealth Group- 64750 | 214-647-4442 donald_r_osborn@uhc.com | customer attempting PNP on 8/21 8/22- per Donald We got the circuit up last night as a plug and play with no issues | 5/21- sharita submitted tin 5/30- ASR sent; LEC ENGINEER HAS CONTACTED LCON, PENDING LCON RESPONSE/AVAILABILIT ON HOLD FOR SITE SURVEY 6/6- Pending confirmation from LEC if still pending response/availability fromc customer for site survey 6/13- Escalated to provisioning lead to assist with current status of site survey 6/20- Spoke with lcon and tech and was advised site survey has been completed. Advised provisioning to send ASR to request FOC date. 6/27- pending FOC date of 7/29 7/3- pending FOC date of 7/29 7/11- pending FOC date of 7/29 7/18- Lec delivered 7/15, wiring mux being scheduled. 7/25- Pending end to end testing to complete Per LEC they are seeing a LOS. Awaiting dispatch for test assist to check for the cabling. Will continue testing once tech is onsite. 8/1- ready for activation; customer notified.
2012-11-19 | B end | II519-02-IJ | Hiteccity 2, Building H06, Gachibowli Village, Hyderabad Hyderabad, india ** | 150 Ethernet mb access with 100 mb port with MD5 UHGVERbgpbqZyofa and letterkenny SOO W0Y12673 | s/o: 5297258 (port) s/o: 5297259 (access) |  |  | 5381646 | 29.776m need to change to 50m | W1A44771 (port) W1A44772 (access) | TTSL 0004001302213 - PTT CKT ID |  |  |  |  | bpdd | 2013-08-16 | 2013-08-09 | unitedhealthgroup-65035 | 91 91600 84400, harish_kandpal@uhc.com | completed with Harish on 8/27\ | 5/22- order will be re-issued once site is ready. Expected June 1 6/6- followed up with Varun on site readiness and order re-issueing 6/13- Varun had a conference call this week with Harish for confimation. New orders will be issued Monday 6/20- site confirmed ready on 6/10 6/27- TEV completed and order sent to PTT. Awaiting FOC date to be provided. 7/3- Awaiting PTT to provide FOC date 7/4- Server room appears to still be not ready. Site survey scheduled; pending update. 7/9- PTT WILL INITIATE THE FIBER WORK IN THE NEXT WEEK. RACK + MUX WILL BE DISPATCHED TO THE CUSTOMER SITE TOMORROW. FOC DATE = 30 JULY 2013 7/11- Mike K agreed to go with the linear path for 1 week, expected PTT delivery of 7/23-7/25 7/18- verifying interbuilding permissions have been received. 7/25- PERMISSION STILL AWAITED FROM THE SEZ MANAGER FOR THE INCAMPUS BUILDING WORK. ONCE THE PERMISSIONS ARE APPROVED BY THE SEZ MANAGEMENT, WE CAN GET THE FIBER WORK COMPLETED IN 2-3 DAYS' TIME. 8/1- SEZ permission granted and fiber work done last weekend, circuit installed Wed. PTT had encountered some errors during testing. Configuration changes are in progress at PTT end to resolve this. We have scheduled an engineer tomorrow at the site to re-start the test. 8/6- testing complete, pvc and prebuild for ping testing now happeniong. 8/8- ping testing complete, pending GLP configs. 8/9- ready for activation, engineer informed.
2013-07-10 | ShaRita | TX073-02-IJ REQUEST TO CANCEL | 103 Thousand Oaks Blvd, Georgetown, TX 78628 | 10752 7xT1 with MD5 UHGVERbgpbqZyofa | Smartform 189918533 NSPE0007014067 IQBKNY28 | 5973160 | P2023676 | 5374396 | 1536 | BCBK1W7Y0001-0007 | 12/HCGS/614708//GTEC 12/HCGS/614709//GTEC 12/HCGS/614710//GTEC 12/HCGS/614711//GTEC 12/HCGS/614712//GTEC 12/HCGS/614713//GTEC 12/HCGS/614714//GTEC | 2013-07-17 | 2013-07-26 |  | bpdd | 2013-08-02 |  | unitedhealthgroup- 65291 | 210-877-7919 chris_spoor@uhc.com |  | 7/11- order in provisioning 7/18- FOC date for 7/26 7/25- pending FOC of 7/26 8/1- FOC date missed due to site not ready; customer site needs conduit. Awaiting ASR to be re-issued for a new due date 8/8- order supp'ed to cancel per customer request 8/14- pending cancellation to be completed 8/22- cancel completed
2013-07-29 | ShaRita | none | medecision, old ring 14100 BUSINESS CENTER DR NW ELK RIVER MN 55330 | disconnect | NSPE0006917218 OQBKPKPJ | 6003978 |  | 1893317 |  | EDBJ91060001 |  |  |  |  | bpdd | 2013-08-15 | 2013-08-19 |  |  |  | 7/29- requested to have access disconnected asap/submitted to disconnect group 8/8- pending disconnect due 8/15 8/14- pending disconnect due 8/15 8/22- disconnect completed
2013-08-13 | ShaRita | none | 8501 LASALLE RD BALTIMORE MD 21286 | disconnect | NSPE0006466484 OQBKPW5P |  |  |  |  | EDBKJRVS0001 |  |  |  |  | bpdd | 2013-08-27 |  |  |  |  | 8/13- submitted disconnect 8/22- pending disconnect due date of 8/27 8/29- soft disconnect completed 8/30- disconect completed.
2013-06-07 | ShaRita | MI028-02-IJ | 950 Trade Centre Way, Ste 320, Kalamazoo MI 49002 | 3072 2xT1 with md5 UHGVERbgpbqZyofa | smartform 189892806 NSPE0006880331 IQBKM2ZJ GRR I0039142 / 13w7l nzbs0001 | 5926204 | P2015969 | 5364976 | 1536 | BCBK1FJ20001-0002 | /HCGS/578534//MB MB1st flr east terminal shelf 1 slot 4 of 14 not ext tagged rj48c /HCGS/578535//MB 1st flr east terminal shelf 1 slot 5 o f 14 not ext tagged rj48c |  | 2013-06-13 | 2013-06-26 | 2013-06-24 | bpdd | 2013-07-03 | 2013-06-28 | unitedhealthgroup-64924 | 214-647-4442 donald_r_osborn@uhc.com | activated by Keith on 9/3 | 6/13- order approved by provisioning; awaiting ASR to be sent to LEC 6/20- FOC is scheduled for 6/26 6/27- awaiting confirmation loop was delivered 6/28- ready for activation; customer notified
2012-07-24 | ShaRita | none | 9100 Shelbyville Rd Louisville, KY 40222 | disconnect | NSPE0007075450 OQBKPLHP |  |  |  |  | BCBKY3TM0001-8 |  |  |  |  | bpdd | 2013-08-22 | 2013-08-26 |  |  |  | 7/25- submitted disconnect to sadisconnect 8/1- escalated to team lead to have order entered 8/8- awaiting due 8/22 8/14- awaiting due date of 8/22 8/22- pending soft disconnect 8/23- soft disconnect complete
2012-07-24 | ShaRita | none | 2950 Expressway Dr St Suite 240 Islandia NY 11749 | disconnect | NSPE0007075559 OQBKPLHK |  |  |  |  | BCBKGWW70001-4 |  |  |  |  | bpdd | 2013-08-22 | 2013-08-26 |  |  |  | 7/25- submitted disconnect to sadisconnect 8/1- escalated to team lead to have order entered 8/8- awaiting due 8/22 8/14- awaiting due date of 8/22 8/22- soft disconnect done
2012-07-24 | ShaRita | none | 1331 17th St Suite 1100 Denver CO 80201 | disconnect | NSPE0007075645 OQBKPLHM |  |  |  |  | BCBKSGK40001-2 |  |  |  |  | bpdd | 2013-08-22 | 2013-08-26 |  |  |  | 7/25- submitted disconnect to sadisconnect 8/1- escalated to team lead to have order entered 8/8- awaiting due 8/22 8/14- awaiting due date of 8/22 8/22- pending soft disconnect
2012-07-24 | ShaRita | none | 425 Market St- IPT San Franciso CA 94105 | disconnect | NSPE0007075975 OQBKPLJV |  |  |  |  | BCBH35LR0001 |  |  |  |  | bpdd | 2013-08-22 | 2013-08-26 |  |  |  | 7/25- submitted disconnect to sadisconnect 8/1- escalated to team lead to have order entered 8/8- awaiting due date to provided 8/14- awaiting due date of 8/22 8/22- pending soft disconnect 8/23- soft disconnect completed
2013-07-30 | ShaRita | none | 300 Southborough Drive Suite 100 South Portland ME 04106 | disconnect | NSPE0007098924 OQBKPLJW |  |  |  |  | BCBKGL7J0001-6 |  |  |  |  | bpdd | 2013-08-22 | 2013-08-26 |  |  |  | 7/31- submitted disconnect to sadisconnect 8/8- pending disconnect due date 8/22 8/14- pending disconnect due date 8/22 8/22- soft disconnet done
2012-07-24 | ShaRita | none | 8403 South Pk Circle Suite 655 Orlando FL 32819 | disconnect | NSPE0007075821 OQBKPLJT |  |  |  |  | BCBKLGSF0001 |  |  |  |  | bpdd | 2013-08-22 | 2013-08-27 |  |  |  | 7/25- submitted disconnect to sadisconnect 8/1- escalated to team lead to have order entered 8/8- awaiting due date to provided 8/14- awaiting due date of 8/22 8/22- pending soft disconnect 8/23- soft disconnect completed 8/27- disconnected completed
2013-05-13 | ShaRita | UMA25-05-IJ | Sungard 20 Overland Street, Suite A , Boston, MA 02215 actual address is 109 Brookline Ave, lit bldg ID is cix | Ethernet Access Type 1. 1G access, 1 gig port (john will throttle down to 100mg) Multimode with LC connector (SX Optic) MD5 encryption UHGVERbgpbqZyofa | iNet is CP32761.00, PER 05201311 Smartform 189877214 CDR201305210036 NSPE0006806871 IQBKMJ9J port IQBKMJ63 access BST I82392 CCR #: 1154893 (MEDIA CONVERTER) rft 7/8 CCR #: 1149679 (CARD ADD) complete BST I82392 / ea-cix-3cm-0002 | 5888361 | P2011906 | 5359785 | 3008 | BCBK05WM0001 EDBK05TG0001 | ea-cix-3cm-0002 demark: inside coo lo room verizon business cabinet, 122a.2.1, media converter shelf slot 1 |  |  |  |  | bpdd | 2013-07-15 | 2013-07-23 | UnitedHealth Group- 64944 | 763-744-1999 jon_langemak@uhc.com | Scheduled for 8/26/2013 09:00:00 PM Central Time Conference Bridge 866-878-8630 Conference Pass Code 6653710 | 5/21- sent to OM. 5/22- customer agreed to have us order the x-conn from Sungard, order in local provisioning 5/29- pending CCR 1154893 / Current RFT - 7/8 CCR is for installing Omnitron Media Converter to convert from Gig-E Single Mode to Multi Mode 850nm at VeriCenter/SunGard (cix,16) 109 BROOKLINE AVE, BOSTON MA, MC is pending shipment 6/6- pending CCR 1154893 / Current RFT - 7/8- equipment is shipped 6/13- pending CCR 1154893 / equipment is installed, built is telephony, pending closure. 6/20- pending CCR 1154893 / media converter scheduled for installation 7/1 / Current RFT - 7/8, equipment set to install on 6/20 6/27- pending CCR 1154893 / media converter scheduled for installation 7/1 / Current RFT - 7/8 7/3- CCR # : 1154893 Construction Complete; pending testing 7/11- build complete, pending cross connects. 7/18-node work set for today 7/24- ready for activation; customer notified
2013-06-19 | ShaRita | C1425-04-IJ | 801 S. 16th Street, Phoenix, AZ****Hoping to have by end of July. | 100M ethernet with md5 UHGVEReccgas4Usp9 | CP33743.00 PER 06241307 smartform 189905724 NSPE0006949009 IQBKNHB4 (port) IQBKNGZW (access) phx-I23288 ¦ea-bfn8-bfn8-0009 CCR#: 1162624 (oc3 cards for oc48.jc at loc 2.) complete ccr 1162486 (re-card overture) (RFT 7/19) phx A0023305 | 5948785 | P2018820 | 5369444 | 40000 | BCBK1MD40001 EDBK1L570001 | ea-bfn8-bfn8-0009 VZB DMARC: 1st Floor TeleTech Colo BFN8 Rack 14.1 Shelf 3 RJ45 Jack 1.1 - (Not 2.1 per CLR) Tagged: I23288 EA-BFN8-BFN8-0009 EDBK1L570001 HANDOFF TYPE: Electrical |  | 2013-07-23 |  | bpdd | 7/30/2013 9/12/2013 | 2013-08-23 | UHGECC - 65430 | 763-7442154 scott_moyer@uhc.com | 09/03/2013 1:00 PM Central Time bridge 866-864-4993 pass code 6446099 | 6/27- pending ethernet approval. 7/3- pending FAD date of 7/23 7/11-Pending OC3 and overture cards. CCRs due 7/23, with an anticipated delivery date of 7/30 7/18- CCR # 1162486 pending access to install cards 7/25- CCR#: 1162624 status ALL WORK COMPLETE; CCR # 1162486 having issues getting on site to install the cards: Customer Access : delay into customer site has prevented timely dispatch/completion for a order work. RFT will be reset once CCR completes the TCC queue. 8/1- Awaiting CCR # 1162486 to complete & the local tcoms engineered. 8/8- pending date and time of dispatch to install BEAs 8/14- RFT has been set for 8/22 on CCR # 1162486; date is trying to be improved 8/22- pending beas installation; dispatch scheduled for 8/22
2013-07-12 | ShaRita | FL117-02-IJ | 979 Del Mar (Spanish Springs) The Villages, FL 32159 | 3072 2 x T1 with MD5 UHGVERbgpbqZyofa | Smartform 189921606 NSPE0007026807 IQBKN07W | 5977468 | P2024237 | 5375060 | 1536 | BCBK1X650001-0002 | 50.HCGS.145651..UFLG 1st flr telephone equipment room housing 1 slot 3 of 4 RJ48C not ext tagged labeled and grounded. 50.HCGS.145652..UFLG 1st flr telephone equipment room housing 1 slot 4 of 4 RJ48C not ext tagged labeled and grounded. | 7/18/13 8/9/13 | 7/29/13 9/3/13 | 2013-08-13 | bpdd | 2013-08-05 |  | unitedhealthgroup- 65273 | 715-841-7731 sonja_d_mroczynski@uhc.com | sonja confirmed actiated on 9/10 | 7/12 order submitted. 7/18- order approved; requested status on when ASR would be issued 7/25- pending FOC date of 7/29 8/1- site not ready; building is still under construction. Awaiting ASR to be re-issued for a new due date. 8/8- customer advised site will be ready next week; advised provisioning to re-issue ASR 8/14- pending new FOC date of 9/3 8/22- tech was able to loop smjk on ckt 2 but not on ckt 1; awaiting confirmation from LEC that both T1s are completed on telco side 8/29- trouble ticket open; currently issue with testing. per LEC order is still open in their system for install of 9/3 and they are not able to accept any trouble tickets until this has been completed. requested provisioning to call to close order with lec; awaiting response 9/5- done running the Layer 1 for the 2nd CKT. However we had created a trouble ticket to LEC for the 1st CKT as we were unable to loop up any device.
2013-01-11 | ShaRita | CA750-02-IJ | Fremont, CA | 44736, DS3 with MD5 UHGVERbgpbqZyofa | CW: 189781306 NSPE0006309390 CDR201301140015 IQBKHCQ6 | 5703055 | P1981248 | 5320183 | 1536 | BCBKX7210001 | 86/HFGS/578590//PT 1st flr data center att cage shelf 1 slot 3 ds3 ni u tagged, not extended. no |  | 2013-01-24 | 2013-02-11 |  | bpdd | 2013-03-07 |  | UnitedHealth Group-65029 | 702-303-7293, tauoa.falo@uhc.com | 09/10/2013 7:00 PM Central Time 866-878-8630 6653710 | 1/14- issue validating address for cdr. Ticket S6583183 1/24- ASR sent, pending FOC 1/30- still pending FOC 2/7- FOC for 2/11, asking for commit date. 2/14: Lec delivered, pending VZ commit of 3/7, order being tested 2/20: Loop delivered, mux complete, pending BNE reveiw and testing. 2/28- loop in circuit outside of our network, working with AT&T to resolve. 3/7- called ATT at 800 517 2520 opt 2 opt 3 and was assisted by Josh. he break the l oop at the CFA but we are seeing a loop. he said that he needs to open a ticket at thier CO to check where they are connected. Asked him if we could do a vendor meet instead but he insisted that he needs to verify first the location and whe re they are connected to us. he gave me TT uf043263 for reference and he said th at he will call us back 3/13- asked install to escalate with AT&T on the testing issues 3/20- AT&T order is back with their engineering. Asked our install group to escalate this wtih AT&T 3/28- still seems to be an issue at the CFA, esclating this to producation support 4/3- new ASR went out to correct CFA issue, escalating with provisioning on CNR issue 4/10- trying to determine an open CFA with the LEC. 4/18- new CFA foc for today 4/25- seeing a loop up. David (ATT tester) said that he will dispatch to their colo to check and call me back once he has a hold of a tech. 5/2- pending mux Jason Ferran (09/10/2013 7:58 PM) ***************************Activation Complete****************************** Customer Tauoa still accepted the circuit.
2013-04-02 | ShaRita | FL042-02-IJ | 1064 Lake Sumter Landing , The Villages Florida | 3072 2xT1 with MD5 UHGVERbgpbqZyofa | smartform 189842130 NSPE0006608178 IQBKK6LJ | 5812228 | P2002485 | 5347369 | 1536 | BCBK0JW10001-0002 | 50.HCGS.138469..UFLG DEMARC LOC: 1ST FLR TELCO, SLOT 3 OF 4, RJ48C, T/L, NOT EXT-GETO NOT POPULA TED 50.HCGS.138470..UFLG DEMARC LOC: 1ST FLR TELCO, SLOT 4 OF 4, RJ48C, T/L, NOT EXT-GETO NOT POPULA TED |  | 2013-04-26 |  |  | bpdd | 2013-05-03 | 2013-05-01 | unitedhealthgroup-64519 | 763.553.4801, sonja_d_mroczynski@uhc.com | scheduled for 9/6/2013 03:00:00 PM Central Time | 4/2- submit to OM 4/11- address validation issues, provided onsite phone number for address 4/19- Address now validated, ASR is being sent 4/25- there might be a facility issue, so FOC for 4/26 will be good.
2012-11-19 | ShaRita | M0111-05-IJ | Kingston, NY | 44736, DS3 with MD5 UHGVERbgpbqZyofa | smartform 189750536 CDR201211200005 NSPE0006100850 IQBKFTLC | 5648335 | P1968299 | 5241560 | 30M | BCBKXD300001 | 33.HFGS.656810..NY DMARC: main bldg mpop 103 wall mounted Extended : n Tagged : y LEC order number C1HM9029 |  | 2012-12-06 | 2013-05-23 | 2013-05-23 | bpdd | 2013-05-31 | 2013-05-30 | unitedhealthgroup-64662 | (91) 9810059326 , pradeep_yadav@uhc.com | activated with Pradeep on 9/17 | 1/17- pending site requirements, twist lock and clearning of cabinet area 1/24- Melissa checking with john on site requirements 2/12- order supped indicating site requirements are complete. 2/19- pending FOC 2/27- LEC is saying building is not ready. per pradeep power won't be in until 3/9 3/13- power is in and order is supped.spoke to FE and informed him that power is there, he informed me that electronics need to be placed and he needs help with access 3/20- Melissa asked Pradeep about trouble ticket for access. 3/21- CC# C10643814 for access to the access the MDF on March 29th and April 1st – 4rd 4/2- Core needs more time to install electronics. Asked Pradeep to extend the ticket until 4/9. Expected delivery date is 4/29. Asked to have ASR supped. 4/10- core working on test and turn up of equipment 4/18- lec foc is now 5/23 4/25- IOF build is required on this order and IOF is waiting on sonet ring NhL403 to be turned up and that is scheduled for 5-15, per IOF nodes and posting deign are in progress 5/2- pending 5/23 FOC 5/17- pending FOC for 5/23 5/22- pending FOC date of 5/23 5/29- pending end to end testing 5/30- ready for activation / pending configs 5/31- config ready, informed engineer ready for activation.
2013-06-05 | ShaRita | FL118-02-IJ CANCEL COMPLETE | 1049 Sumter Landing The Villages, FL 32162 | 44736, DS3 md5 encryption UHGVERbgpbqZyofa | Smartform 189890730 NSPE0006864611 CDR201306040065 IQBKMZZB gai-I149 / 3X-FSLF-SSH-0097 | 5919165 | P2015089 | 5364118 | 1536 | BCBK1C610001 | 3X-FSLF-SSH-0097 | 2013-07-12 | 2013-07-31 |  | bpdd |  |  | UnitedHealthGroup-64900 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com |  | 6/6- awaiting order to be assigned to provisioning 6/13- ASR sent; awaiting LEC to provide FOC date 6/20- Upon checking order ASR for LEC still not transmitted. ASR being sent to LEC for FOC date. 6/27- Local order GAI I149 closed on 06/25/2013. Awaiting Level 3 to provide FOC date 7/3- LC20 ASR stuck in transmitted status. Trouble ticket open; pending resolution. Once issue resolved will submit ASR to get a FOC date asap. 7/11- a FOC date of 7/8 was provided in system but working to confirm if this was correct or an error. Pending LEC conformation. 7/18- the July 8th date was to have the cross connects completed with level 3. There are four different LECs involved on this order. issue with validating address to LEC. this issue has been escalated to get resolved asap. 7/25-issue with ASR, asking provisioning to re-transmit 8/1- Pending: dispatch for mux HTXQ209; awating confirmation that loop was delivered as scheduled, 7/31 8/8- supp'ed to cancel order per customer request. 8/14- pending cancellation to be completed 8/29- pending cancellation to be completed 9/5- awaiting disconnect for ASR; due date 9/12. pending cancellation to be completed 9/10- cancel completed
2013-02-27 | ShaRita/Melissa |  | New Cologne ROADM node |  | 5274382 MIN- C34713 CCR # : 1154005 | reissue 5807214 | RW-LLM8-73C-0001 | [7 empty] | bpdd | [5 empty] | 3/7- pending OM. 4/3- pending Eagan roadm decommision 5/16- order sent to provisioning 5/22- order pending CCR 1154005 for ROADM node 5/29- Pending CCR#: 1154005 / No FAD date yet- pending fiber chracterization testing. 6/6- Pending CCR#: 1154005 / No FAD date yet. Equipment package was designed and shipped. 6/13- Pending CCR#: 1154005 / No FAD date yet. Equipment received (Facility Prep). Phil will be looking at this next week or so. 6/20- Still pending CCR#: 1154005 / No FAD date yet. Equipment received (Facility Prep). 6/27- Still pending CCR#: 1154005 / No FAD date yet. Equipment received (Facility Prep). 7/3- Still pending CCR#: 1154005 / No FAD date yet. Equipment received (Facility Prep). 7/11- working with phil on getting equipment installed by end of July 7/18- equipment will be powered up tonight, then Phil will put cards in and prep for cutting in. Node will be ready to cut in by end of July, looking at a 3-4 hour outage to cut the node in. 7/25- Ready to cut into the system. Working with customer to set up a date/time, since there will be down time. There is a call set up on Monday. 8/1- order currently on hold; awaiting a date and time to cut the new node into the network 8/8- PER OPS TECH, PHIL R. - CUSTOMER CAME BACK WITH A DATE OF 8/29 AT 10PM TO CUT NODE IN. 8/14- pending cutover 8/22- pending cutover 8/29- pending cutover at 10pm 9/5- node cut into network , there is a concern with some fiber, so we are doing maintenacne on this. Working with John Lagemak...looking at Thursday the 12th. 9/12- maintenance being done today
2013-06-07 | ShaRita | NC004-02-IJ | 3131 RDU Center Drive, Suite 200, Morrisville, NC 27560****** | 44736, DS3 md5 encryption UHGVERbgpbqZyofa | smartform 189892841 CDR201306070038 NSPE0006880401 IQBKM4W6 | 5930095 | P2016259 | 5365395 | 10800 | BCBK1GS50001 | 63/HFGS/542144//FTNC | 6/25/2013 7/18/2013 | 7/19/2013 9/10/2013 estimated 9/13/2013 |  |  | bpdd | 2013-07-26 | 2013-09-12 | unitedhealthgroup-65288 | 860-702-8284 keith_mangene@uhc.com | activated with Keith on 9/23 | 6/13- ASR sent; awaiting FOC date to be provided 6/20- CNR received from LEC. ASR re-issued; awaiting LEC to provide FOC date 6/27- Awaiting LEC to provide FOC date 6/27- Escalated to provisioning lead, ASR returned from LEC and needs to be re-issued ASAP 7/3- awaiting LEC to provide FOC date 7/11- ASR invalid asked provisioning to update and re-issue 7/18- ASR sent 7/25- Mux sheduled for today, 7/25. Awaiting confirmation if loop was delivered on 7/19. 8/1- LEC just informed that there is a project within the last two weeks that has been approved. There is equipment needed to be ordered and installed. Vendor has ship dates later in August that LEC is working to try to improve. 8/8- LEC status pending build completion; a new FOC date has been tagged by ATT for 9/10 due to ATT requiring a build on their side to support this install. ordered/ship dates have been improved for parts. a couple of items tagged estimate ship dates later this month but working to improve dates but most of the equipment should be delivered this month. LEC needs all equipment received before they can work an ECD for the build to be completed. 8/14- pending LEC build completion ; pending estimated FOC date of 9/10 8/22- pending LEC build completion ; pending estimated FOC date of 9/10 8/28- pending LEC build completion; pending estimated FOC date of 9/10 9/5- awaiting LEC to provide exact FOC date; estimated FOC date is 9/10 9/12- pending FOC date of 9/13
2013-08-12 | ShaRita | none | 5450 Tech Center Drive Colorado Springs, CO | disconnect | NSPE0007148630 OQBKPZSG |  |  |  |  | BCBKS4Y20001 |  |  |  |  | bpdd | 2013-09-11 |  |  |  |  | 8/12- submitted disconnect to sadisconnect 8/22- pending disconnect due date of 9/11 8/29- pending disconnect due date of 9/11 9/11- pending soft disconnect 9/13- disconnect complete
2013-08-12 | ShaRita | none | 3800 Avenue of the Cities Suite 200 Moline, IL 61265 | disconnect | NSPE0007148372 OQBKP08F |  |  |  |  | BCBJCMPW0001 |  |  |  |  | bpdd | 2013-09-11 | 2013-09-12 |  |  |  | 8/12- submitted disconnect to sadisconnect 8/22- awaiting disconnect due date 8/29- pending disconnect due date of 9/11 9/5- pending disconnect due date of 9/11 9/12- pending soft disconnect 9/12- disco complete
2013-08-12 | ShaRita | none | 1305 Stephenson Hwy Troy, MI 48038 | disconnect | NSPE0007148520 OQBKP354 |  |  |  |  | BCBKV8ST0001 |  |  |  |  | bpdd | 2013-09-11 | 2013-09-12 |  |  |  | 8/12- submitted disconnect to sadisconnect 8/22- awaiting disconnect due date 8/29- pending disconnect due date of 9/11 9/5- pending disconnect due date of 9/11 9/12- pending soft disconnect 9/12- disco complete
2013-03-12 | ShaRita | IL059-05-CJ | Rockford, IL | 7680 5xT1, Add 1 T1 to exsiting 4xT1 upgrade MD5 UHGVERbgpbqZyofa | CW: 189826330 NSPE0006533091 IQBKKCKP OQBKKDCY | 5785122 | P1802598 (out) P1996052 (in) |  | Upgrade to 4608 | BCBKG9XK0001-4 (out) BCBKY5WG0001-0005 (in) | /HCGS/656453//LB Demarc: 1ST FLR, IT RM, OPTI RACK # 3, SLOT 28, RJ48C, TAGGED NOT EXT. |  | 2013-03-29 | 2013-04-10 |  | bpdd |  |  | unitedhealthgroup-65278 | 763-744-2077 robert_a_benson@uhc.com | resheduled 9/23 at 7:30PM CST 866-878-8630 6653710 | 3/14- order with OM 3/20- order sent to provisioning 3/28- escalating with provisioning for pick up 4/3- LEC FOC for new loop is 4/10 4/10- order now ready for hotcut. Engineer informed.
2013-02-26 | B end | II523-08-IJ | Oxygen Blvd - Tower D Floors Ground through 3 Plot No. 7, Sec 144 Noida, Uttar Pradesh India. 201304 Noida, India | 150MB Ethernet-The Interface Type will be:- SFP-GE-S (1000 Base-SX-SFP (DOM) md5 encryption UHGVERbgpbqZyofa SOO to Letterkenny - circuit ID W0Y12673 | OVI : 1-1155431162 S/O 5274709 5274710 (access) |  |  |  | 34368 | W1A35637 (port) W1A35638 (access) | tata provider |  |  |  | bpdd | 2013-09-30 | 2013-09-28 | unitedhealthgroup- 65078 | 91 - 98100 59326, pradeep_yadav@uhc.com | activated with Pradeep on 9/28 | n. 7/11- pending customer server room readiness 7.18- AS WE NEED TWO ROUTES FOR OFC CABLE ENTRY AND EXIT AND CUSTOMER HAS STILL NOT FINALIZED ALTERNATE PATH. PENDING WITH CUSTOMER. 7/25- building management is not allowing PTT to do work, Pradeep is aware. 7/30- Still pending building management permission so PTT can access the site to do work. 8/1- folllowing up with Pradeep on BMO permission for PTT access. 8/8- verifying if tata got access. 8/12- last mile provider to work on the site between 16- 18 August. UHG Has request for access permission for the Tech who will be working to complete the installation. 8/20- the cable was only partially pulled and 20 mtrs section remains, since UHG wasn’t able to arrange permission from estate management. UHG needs to obtian permission for this remaining section 8/29- FIBER CABLE TERMINATED AND FIBER WORK COMPLETED. ASKED CUSTOMER TO ARRANGE UPS POWER POINTS FOR RACK + NON ELECTRICAL EARTHING POINT. 9/5-PTT TEAM GOT ACCESS AND INSTALLED MUX AT SITE .CUSTOMER DELAYED UPS POWER SUPPLY FOR RACK/MUX. CHECKING WITH PTT FOR MUX INTEGRATION ACTIVITY 9/12- access has been arranged for 13th Sep, 11:00AM to 5:00PM for the SFP installation and fiber patch cord extension 9/19- The circuit is under logical provisioning stage at ptt end, in which they are allocating BW to physical ports at UHG and VZ pop physical ports.This activity will be completed in another couple of days and after that we will be performing a loopback test on circuit to check its healthiness, followed by service handover. 9/26- LINE HAS BEEN PUT ON E2E STABILITY TEST, TEST RESULTS WILL BE AVAILABLE BY TOMORROW SAME TIME. AFTER IT'S SUCCESSFULLY PASSED, CKT IS GOOD FOR ACTIVATION RM RAISED
2013-08-20 | ShaRita | none | 20 Grenfell Road Maidenhead UK SL6 1EH | disconnect | NSPE0007180603 5331977 5331978 | 6029667 |  |  |  | w0u33654 w0S09405 |  |  |  |  | bpdd | 2013-10-21 | 2013-09-23 |  |  |  | 8/22- order submitted to provisioning 8/29- pending lcon verfication process to be completed 9/5- asked John for a new lcon to complete verification process; lcon provided has yet to respond 9/12- lcon replied; awaiting disconnect due date 9/18- awaiting disconnect date of 10/21 9/25- disconnect completed on 9/23
2013-08-09 | SA disconnect | na | Plymouth, MN | disconnect U311943 OQBKQ84V min-O32765 | NSPE0007155363 IORDER:34487312 |  |  |  |  | U311943 | jy-nsb-jcfg-0001 PLBKPD6D0001 |  |  |  | bpdd | 2013-09-16 | 2013-09-24 |  |  |  | 8/13- sent to SA disconnect 8/22- SA disconnect requesting a LOD for disconnect request 8/29- Melissa asked John if he could submit via the VEC. SA disco needs LOD in order to process. 9/5- pending disconnect due date of 9/16 9/18- requested an update from SAdisconnect on completion of request 9/25- disco completed ITEMS is showing disco on U order. no more work required.
2013-09-04 | ShaRita | none | Unitech World Cyber Park Sector 39 Haryana Gurgaon India India 122001 | disconnect | NSPE0007241188 5341297 5342009 | 6047636 |  |  |  | w0u54956 |  |  |  |  | bpdd | 2013-11-08 | 2013-09-18 |  |  |  | 9/5- confirmed lcon information with John 9/12- local cease order placed with PTT 9/18- order disconnected but s/o 5341297 still open. Requested that order be closed out as well. 9/25- disconnect completed
2013-07-31 | ShaRita | C1556-04-CJ PENDING CANCELLATION | Connextions 4809 East Thistle Landing Drive Phoenix, AZ 85044 | move bcbk0yg00001 to new data room. | smartform 189943558 NSPE0007123165 CQBKPVCV | 6006897 | P2009013 | 5355601 | 12288 | bcbk0yg00001 |  | 2013-08-12 | 2013-08-28 |  | bpdd | 2013-09-05 |  |  | Technical Contact: Matt Seymour matt_f_seymour@uhc.com 763-744-0840 |  | 8/8- order submitted to order entry 8/14- pending LEC to provide FOC date 8/22- pending FOC date of 8/28 8/29- Per LEC, CNR sent 8/28 due to bad lcon; asked Mr. Sergot for an alternate lcon 9/5- order currently on hold, awaiting Jose (Connextions) to advise how to move forward 9/12- order currently on hold, awaiting Jose (Connextions) to advise how to move forward 9/18- received HCUS (hold customer) Escalation Level 5 Notification sent - Order to be submitted for cancellation 9/25- order supped to cancel; customer needs to work with LEC (Centurylink) and building owner to have demarc moved
2013-06-17 | ShaRita | TX175-02-IJ | 14141 Southwest Freeway, Sugarland, TX 77478- end of Sept | 44736 ds3 with md5 UHGVERbgpbqZyofa | Smartform 189899339 CDR201306170045 NSPE0006918911 IQBKNBKF HOU I48538 / 3x-6l9-lyw-0061 | 5938324 | P2017506 | 5367170 | 22000 | BCBK1J1D0001 | 19/HFGS/170165/TWCS Demarc information: C Level E lectrical/Telco room in the TW cabinet C3001 DS3-1 | 2013-08-14 | 2013-08-15 | bpdd | 2013-08-21 | 2013-08-20 | unitedhealthgroup-65114 | 214-647-4442 donald_r_osborn@uhc.com | activated with Don on 10/4 | 6/20- ASR sent; awaiting LEC to provide FOC date 6/27- Pending dipatch on HOU I0048538 scheduled on 6/28 7/3- Still pending LOA/CFA from lec TW01 7/11- Pending LEC (TW01) to provide LOA/CFA so ASR can be sent for LEC SW70. Awaiting response from LEC in regards to LOA/CFA. 7/18- issuing ASR 7/25- redesigning as meet point is not in AT&T systems 8/8- HSTNTXBUH00 not a valid CLLI for AT&T, shoudl provide to Time Warner, escalating with provisioning 8/14- Pending confirmation that loop was delivered as scheduled on 8/14 8/22- ready for activation; engineer notified
2013-06-17 | ShaRita | TX175-02-IJ second DS3 | 14141 Southwest Freeway, Sugarland, TX 77478- end of Sept | 44736 ds3 with md5 UHGVERbgpbqZyofa | smartform 189899767 CDR201306170047 NSPE0006918973 IQBKNBK8 HOU I48537 / 3x-6l9-lyw-0060 | 5938364 | P2017517 | 5367183 | 22000 | BCBK1J1S0001 | 19/HFGS/170207/TWCS Demarc: 4th floor MDF room dsx 3002 slot 1 Extended(Y/N): Y | 2013-07-03 | 2013-08-16 | 2013-08-20 | bpdd | 2013-09-30 | 2013-09-26 | unitedhealthgroup-65114 | 214-647-4442 donald_r_osborn@uhc.com | Don will plug and play on 10/3 | 6/20- ASR sent; awaiting LEC to provide FOC date 6/27- ASR has not been able to be issue. Per provisioner, order has not been designed because there is no ds3capacity between or at 6l9 - lyw 7/3- escalated to provisioning for a recent update; pending response. 7/11- LEC ASR has been sent requesting for LOA/CFA. 7/18- ASR accepted; awaiting LEC to provide FOC date 7/25 Requested provisioning team lead to escalate in obtaining the LOA/CFA 8/1- ASR accepted by Time Warner (LEC); awaiting LEC to provide FOC date 8/8- awaiting FOC date to be provided; still no design or update from the city operations from TIme Warner, need design to send ASR to AT&T 8/14- pending FOC date of 8/16 8/16- loop delivered by TIme Warner (LEC) on 8/20; however we are waiting for the LOA/CFA from TW01 since the provided tiedown and ACTL is invalid from ATT side 8/29- escalate this to TW Manager to ask assistance so they can prioritize in providing the revised LOA/CFA so we can move forward processing this order. 9/5- escalated to provisioning management to step in to resolve the LOA/CFA issue with TW 9/12- provisioning team is pushing to get issue with LOA/CFA resolved. 9/18- escalated to order management senior manager as well as 4th level provisioning manager to get the CNR rejections from the LEC corrected ASAP 9/25- received an ASR completion notification yesterday end of shift from AT&T . Order will now be step into BNE for testing . 9/26- ready for activation, engineer informed 10/10- activation completed with Donald and failed plug n play on 10/4
2013-06-18 | ShaRita | WA002-05-IJ | 20021 120th Ave NE, Bothell, WA 98011 | 6144, 4xT1 with md5 UHGVERbgpbqZyofa | smartform 189899281 NSPE0006923460 IQBKNBSJ | 5938556 | P2017565 | 5367210 | 3072 | BCBK1J3R0001 BCBK1J3R0002 BCBK1J3R0003 BCBK1J3R0004 | 86/HCGS/540285 /FTNC shelf 3, slot 6/frontier control, no coordinated testing w/centurylink requested Jack Type: rj48c 86/HCGS/540286//FTNC/ shelf 3, slot 7/frontier control, no coordinated testing w/centurylink requested Jack Type: rj48c 86/HCGS/540287 /FTNC shelf 3, slot 8/frontier control, no coordinated testing w/centurylink requested Jack Type: rj48c 86/HCGS/540288 /FTNC shelf 3, slot 9/frontier control, no coordinated testing w/centurylink requested Jack Type: rj48c | 2013-06-24 | 2013-07-09 | 2013-07-09 | bpdd | 2013-07-16 | 2013-07-10 | unitedhealthgroup-65282 | 763-744-2077 robert_a_benson@uhc.com | 9/30/2013 02:00:00 PM Central Time. Conference Bridge 866-692-3158 Conference Pass Code 9236734 | 6/20- ASR sent; pending LEC to provide FOC date 6/27- pending FOC date of 7/9 7/3- pending FOC date of 7/9 7/10- ready for activation; customer notified
2013-01-14 | ShaRita | FL018-02-IJ | Tampa, FL | 10752 7xT1 with MD5 UHGVERbgpbqZyofa | Smartform 189782142 NSPE0006290870 IQBKHH2M | 5701029 | P1982002 | 5320724 | 1536 | BCBKX95D0001-0007 | 69/HCGS/426533//GTES LOCATED IN DATA ROOM SH 1 POS 3 OF 8 NONEXTENDED 69/HCGS/426534//GTES LOCATED IN DATA ROOM SH 1 POS 4 OF 8 NONEXTENDED 69/HCGS/426535//GTES DIMAR LOCATED IN DATA ROOM SH 1 POS 5 OF 8 NONEXTENDED 69/HCGS/426536//GTES DIMAR LOCATED IN DATA ROOM SH 1 POS 6 OF 8 NONEXTENDED 69/HCGS/426537//GTES DEMARC LOC: DIMAR LOCATED IN DATA ROOM SH 1 POS 7 OF 8 NONEXTENDED DEMARC LOC Continued: TAGGED WITH OPENER 69/HCGS/426538//GTES LOCATED IN DATA ROOM SH 1 POS 8 OF 8 NONEXTENDED 69/HCGS/426539//GTES LOCATED IN DATA ROOM SH 1 POS 8 OF 8 NONEXTENDED | 2013-02-14 |  |  | bpdd | 2013-02-21 | 2013-02-21 | UnitedHealth Group-65027 | 214-647-4442 donald_r_osborn@uhc.com | 9/30/2013 01:00:00 PM Central Time bridge 866-819-9840 pcode 3365052 | 1/15- send to OM 1/24 order with provisioning, pending ASR. 1/30- escalating for ASR 2/7- escalting further for ASR 2/14: Pending FOC 2/20: LOOP TESTED ON CKT 1,2,3,6,AND 7, PENDING LOOP ON CKT 4 AND 5 FLAGGED AS TELCO NOT DELIVER - 2/25- order ready for activation, engineer informed.
2013-08-07 | ShaRita | NY051-05-CJ | 22 Corp Woods 5th floor, Albany, NY 12211 | 12288, Upgrade from 6xT1 to 8xT1 | Smartform 189949763 NSPE0007155051 IQBKPYMV OQBKPZXC | 6018812 | P1911918 (out) P2031296 (in) | 5014750 | 4608 | BCBKRV6M0001-6 (out) BCBK2DW80001-8 (in) | 34.HCGS.796899..NY DEMARC LOC: rj48c mt#4 slot 3/8 flr 1 telco rm,ext to flr 5 idf rm,jck DEMARC LOC Continued: 11/12 on top of server rack,both ids.lcon 34.HCGS.796901..NY DEMARC LOC: rj48c mt#4 slot 4/8 flr 1 telco rm,ext to flr 5 idf rm,jck DEMARC LOC Continued: 12/12 on top of server rack,both ids.lcon |  | 2013-09-09 | 2013-09-09 | bpdd | 2013-09-16 | 2013-09-09 | unitedhealthgroup-65083 | 987-313-9388 anupam_datt@uhc.com | Hotcut requested for 09/26/2013 5:00 PM Central Time. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 8/13- sent to ShaRita 8/14- order submitted to Order Entry 8/22- order being reveiwed by provisioning 8/29- pending FOC date of 9/9 9/5- pending FOC date of 9/9 9/9- order ready for hotcut; engineer notified
2013-09-04 | ShaRita | none | 12500 Aprapahoe Road Centennial CO 80112 | disconnect | NSPE0007243331 OQBKQ4V9 OQBKQ4YY |  |  |  |  | BCBKRSKH0001 EDBKPMR10001 |  |  |  |  | bpdd | 2013-10-03 | 2013-10-07 |  |  |  | 9/4- order sent to SA disconnect 9/12- disconnect set for 10/3 9/18- disconnect set for 10/3 9/25- disconnect set for 10/3 10/9- disconnect completed 10/7
2013-09-04 | ShaRita | none | 2301 West Plano Parkway Plano TX 75075 | disconnect | NSPE0007243392 OQBKQ40Y |  |  |  |  | BCBJG7C10001-0007 |  |  |  |  | bpdd | 2013-10-03 | 2013-10-07 |  |  |  | 9/4- order sent to SA disconnect 9/12- pending disconnect due date of 10/3 9/18- pending disconnect due date of 10/3 9/25- disconnect set for 10/3 10/9- disconnect completed 10/7
2013-09-04 | ShaRita | none | 7700 France Ave S. Ste 525 Edina MN 55435 | disconnect | NSPE0007243554 OQBKQ42F |  | P1809039 |  |  | BCBKHR9M0001 |  |  |  |  | bpdd | 2013-10-03 | 2013-10-07 |  |  |  | 9/4- order sent to SA disconnect 9/12- pending disconnect due date of 10/3 9/18- pending disconnect due date of 10/3 9/25- disconnect set for 10/3 10/9- disconnect completed 10/7
2013-09-04 | ShaRita | none | 6860 West 115th St Overland Park KS 66211 | disconnect | NSPE0007243577 OQBKQ44D |  |  |  |  | BCBKJV880001 |  |  |  |  | bpdd | 2013-10-03 | 2013-10-07 |  |  |  | 9/4- order sent to SA disconnect 9/12- pending disconnect due date of 10/3 9/18- pending disconnect due date of 10/3 9/25- disconnect set for 10/3 10/9- disconnect completed 10/7
2013-09-06 | ShaRita | none | 4745 Haven Point Blvd Indianapolis IN 46280 | disconnect | NSPE0007249650 OQBKQ82N |  | P1781600 |  |  | BCBKFT850001 |  |  |  |  | bpdd | 2013-10-03 | 2013-10-07 |  |  |  | 9/10- order sent to SA disconnect 9/18- pending disconnect date of 10/3 9-25- pending disconnect date of 10/3 10/3- pending disco date of today 10/9- disconnect completed
2013-02-01 | ShaRita | FL032-04-IJ | Fort Pierce, FL | 10752, 7xT1 with MD5 UHGVERbgpbqZyofa | ProQuest 189797890 NSPE0006376511 IQBKHXND | 5730239 | P1985237 | 5324987 | 1536 | BCBKYHP20001-0007 | Jack Type: RJ48C 60/HCGS/447354//SB 1RST FLR CUST EQUIP RM MM#4 SLOT 4 60/HCGS/447355//SB 1RST FLR CUST EQUIP RM MM#4 SLOT 5 60/HCGS/447356//SB 1RST FLR CUST EQUIP RM MM#4 SLOT 6 ¦JT=RJ48C 60/HCGS/447357//SB 1RST FLR CUST EQUIP RM MM#4 SLOT 60/HCGS/447358//SB 1RST FLR CUST EQUIP RM MM#4 SLOT 8 ¦JT=RJ48C 60/HCGS/447359//SB 1RST FLR CUST EQUIP RM MM#4 SLOT 9 60/HCGS/447360//SB 1RST FLR CUST EQUIP RM MM#4 SLOT 10 | 4/15/2013 5/30/2013 7/5/2013 | 2013-07-05 |  | bpdd | 4/22/2013 7/12/2013 | 2013-07-12 | UnitedHealth Group- 65017 | 214-647-4442 donald_r_osborn@uhc.com | Activation has been scheduled for 10/14/2013 1pm CST/2PM EST. Conference bridge 866-878-8630 pass code 6653710 | 3/7- LEC due 4/15, commit 4/22 4/18- : Per Jon(ATT-Manager), The BIC engineer updated the service orde r on 4/15 rescinding the BIC readiness of the customer. The BIC stated that the customer is still not ready as they need to place conduit. The order w ill remain held and no job will be issued until the site has been declared as BIC ready by the engineer. 4/25- e-mailed BIC engineer on site requirements 4/26- site requirements e-mailed to UHG, pending response. 5/8- still pending site requirements 5/17- pending FOC of 5/30 5/22- pending FOC date of 5/30 5/30- Pending confirmation that loop was delivered 6/5- Customer confirmed that back board is now ready; provisioning is working on rejected ASR. 6/13- ASR sent; awaiting LEC to provide FOC date 6/20- Per LEC, due date pushed out to 7/5 because of pending job to build facilities and ECD is 7/5. Earlier due date has been requested by provisioning; pending response. 6/27- Pending splicing work to be completed. Work could take a full week to complete. ECD complete date 7/5. 7/3- Pending splicing work to be completed. At the moment there is a missed RID not sure if this affect the 7/5 due date. 7/11- circuits delivered, pending testing. 7/12- order ready for activation, engineer informed.
2013-01-14 | ShaRita | FL015-02-IJ | Sebastian, FL | 10752 7xT1 with MD5 UHGVERbgpbqZyofa | smartform 189782158 NSPE0006290808 IQBKHH2N | 5700723 | P1982003 |  | 1536 | BCBKX95F0001-0007 | 60/HCGS/446587//SB 1FL TELCO MM4#3 ¦JT=RJ48C 60/HCGS/446588//SB 1FL TELCO MM4 #1 ¦JT=RJ48C 60/HCGS/446589//SB 1FL TELCO MM4#4 ¦JT=RJ48C 60/HCGS/446590//SB 1FL TELCO MM5 #3 ¦JT=RJ48C 60/HCGS/446591//SB DEMARC LOC: 1FL TELCO MM5#2 60/HCGS/446592//SB DEMARC LOC: 1FL TELCO MM4 #2 60/HCGS/446593//SB 1FL TELCO MM5 #1 ¦JT=RJ48C | 2013-01-25 | 2013-02-08 | 2013-02-12 | bpdd | 2013-02-15 | 2013-02-12 | UnitedHealth Group-65028 | 214-647-4442 donald_r_osborn@uhc.com | This has been rescheduled for 10/15/2013 3PM Central Time/4PM Eastern Time. Conference bridge 866-878-8630 pass code 6653710. . | 1/15- send to OM 1/24 order with provisioning, pending ASR. 1/30- FOC 2/8- commit 2/15 2/14: circuit ready for activation, engineer informed.
2013-05-21 | ShaRita | C1485-05-IJ | 6200 Shingle Creek Parkway Brooklyn Center, MN 55430 | 44736, DS3 md5 encryption UHGVEReccgas4Usp9 | smartform 189878649 CDR201305210056 NSPE0006808829 IQBKMLRH min-I34719 / 3X-73C-P7T-0621 AQCB MN13S5593 | 5890131 | P2012205 | 5360080 | 3072 | BCBK06FJ0001 | 15/HFGS/047174//NW Demarc information: 1st floor mpop ds3 niu shelf 3 slot 1, not extended; | 2013-06-03 | estimated 8/10/13 (TBD) 8/30/13 | 2013-08-29 | bpdd | 2013-09-09 | 2013-09-26 | UHG-ECC 64750 changed by Erik on 10/2 to 65494 | 214-647-4442 donald_r_osborn@uhc.com | Requested for 10/10/2013 4:30 PM Central Time. Bridge 866-819-9840 pcode 3365052 | 6/27- PM assigned and working with lcon 7/3- Pending timelines from project manager 7/11- Pending AQCB 7/18- Internal kick off call =7/2/2013 Equipment Engineering Network Designs issued by = 7/8/2013 Material Availability = 7/26/2013 Service install, test and turn up (estimated) completed by =8/10/2013 (TBD) 7/25- awaiting PM to provide ship dates for the equipment; once we have dates we will work with customer to get dates for the night cuts 7/29-Qwest upgrade/hotcut set for 9 pm on 8/28. 8/1- pending Qwest upgrade/hotcut set for 9 pm on 8/28. 8/8- pending Qwest upgrade/hotcut set for 9 pm on 8/28. 8/16- pending Qwest upgrade/hotcut set for 9 pm on 8/28. 8/22- pending Qwest upgrade/hotcut set for 9 pm on 8/28. 8/29- hotcut completed; pending FOC of 8/30 9/5- loop delivered; awaiting mux to be reassigned for revisions that are needed 9/12- R-mux RUBS143 created by Prov for requested changes sent out disptches for cabling on the new mux pending dispatch completions 9/19- escalated to 3rd level provisioning management for assistance with mux issue 9/25- Dispatches has been sent for MPX & MZZ site. MPX is already completed and for the MZZ dispatch is due on 09/25. Will monitor those dispatches so we can have order tested ASAP. 9/26- ready for activation, engineer informed.
2013-08-15 | E44525-12679 E44525-13019 (disco) | 1 PRI 40 DIDs | 4600 Sheridan Street - Suite 300 HOLLYWOOD, FL 33021 | 6025802 | NSPE0007178236 IX Plus Acct/BAN: 8604096012X16 Local Order/AM#: 14343917 | New range 954-744-7429-7468 obus 4DY40155 prwea n1wc0001 |  |  | 60/HCGS/452632//SB | 2013-09-04 | 2013-09-04 |  |  |  |  | 8/19- sent to local GRD. 8/29- FOC for 9/4 \ 9/5- delivered, ready for activation- Demarc: 3RD FL SUIT 300 MM#1 SLT#3 RJ48C to be disconnected Disconnect Order Type: FULL Intrada Order #: 4506211 Company Name: UNITED HEALTH CARE IX Plus Acct/BAN: 8604096012X16 Local Order/AM#: 14343917 CRDD: 10/07/13
2013-09-10 | ShaRita | none | 9900 Bren Rd E Minnetonka, MN | disconnect | NSPE0007258784 OQBKQ681 |  |  |  |  | ZABJ2FHT0001 |  |  |  |  | bpdd | 2013-10-03 | 2013-10-11 |  |  |  | 9/10- order sent to SA disconnect 9/18- pending disconnect date of 10/3 9-25- pending disconnect date of 10/3 10/3- pending disco date of today 10/9- soft disconnect completed 10/16- disconnect completed
2013-09-10 | ShaRita | none | 48 Monroe Tpke Trumbull CT | disconnect | NSPE0007258820 OQBKQ699 |  |  |  |  | ZABJ2RMG0001 |  |  |  |  | bpdd | 2013-10-09 | 2013-10-16 |  |  |  | 9/10- order sent to SA disconnect 9/18- pending disconnect date of 10/9 9/25- pending disconnect date of 10/9 10/9 - soft disconnect completed 10/16- disconnect completed
2013-09-10 | ShaRita | none | 48 Monroe Tpke Trumbull CT | disconnect | NSPE0007258840 OQBKQ7KF |  |  |  |  | ZABJ2YRS0001 |  |  |  |  | bpdd | 2013-10-09 | 2013-10-11 |  |  |  | 9/10- order sent to SA disconnect 9/18- pending disconnect date of 10/9 9/25- pending disconnect date of 10/9 10/9- soft disconnect completed 10/16- disconnect completed
2013-09-10 | ShaRita | none | 14100 Business Center Dr NW | disconnect | NSPE0007258879 OQBKQ7HV |  |  |  |  | ZABKMMC30001 |  |  |  |  | bpdd | 2013-10-09 | 2013-10-11 |  |  |  | 9/10- order sent to SA disconnect 9/18- pending disconnect date of 10/9 9/25- pending disconnect date of 10/9 10/9 - soft disconnect completed 10/16- disconnect completed
2013-09-10 | ShaRita | none | 14100 Business Center Dr NW | disconnect | NSPE0007258884 OQBKQ7L3 |  |  |  |  | ZABKMMC40001 |  |  |  |  | bpdd | 2013-10-09 | 2013-10-11 |  |  |  | 9/10- order sent to SA disconnect 9/18- pending disconnect date of 10/9 9/25- pending disconnect date of 10/9 10/9 - soft disconnect completed 10/16- disconnect completed
2013-02-01 | ShaRita | FL016-02-IJ | Port ST Lucie | 10752, 7xT1 with MD5 UHGVERbgpbqZyofa | ProQuest 189798592 NSPE0006381214 IQBKH3HF | 5732222 | P1987021 | 5327239 | 1536 | BCBKYLK00001-0007 | 60/HCGS/447640//SB DEMARC LOC: 1ST FLR SERVER RM, MM 3, JCK 3 60/HCGS/447641//SB DEMARC LOC: 1ST FLR MOUNT1 JACK3 TAGGED-GND 60/HCGS/447655//SB DEMARC LOC: 1ST FLR SERVER RM MOUNT3 JACK4 TA 60/HCGS/447656//SB DEMARC LOC: 1ST FLR SERVER RM MOUNT3 JACK3 TA 60/HCGS/447657//SB DEMARC LOC: 1ST FLR SERVER RM MOUNT3 JACK2 TA 60/HCGS/447658//SB DEMARC LOC: 1ST FLR SERVER RM MOUNT3 JACK1 TA 60/HCGS/447659//SB DEMARC LOC: 1ST FLR SERVER RM MOUNT4 JACK4 TA |  | 2013-03-22 | 2013-03-22 | bpdd | 2013-03-29 | 2013-04-15 | UnitedHealth Group- 65091 | 763-744-1847, donald_r_osborn@uhc.com | Activation scheduled for 10/21/2013 01:00:00 PM Central Time. Conference bridge 866-878-8630 pass code 6653710 | 2/7- address validation issue, ticket S6747148 2/14: Order in process 2/20: In Provisioning - 2/28- 3/22- FOC, 3/29- commit- Accordin g to Debbie/ATT, Theres a Job- 3E854083N,and that's the reason we have th is 3/22 dd. They need to place fibers. 3/7- according to Erika/ATT, The job has not started yet as they have to ensure all thin gsneeded was already available (equipts etc). the have an ECD of 3/20 for the placing of fibers 3/13- followed up to find out about status of job. 3/20- Accordingto Koreen,The Estimated completion date of the order is 3/22. We dont haveany update yet regarding the completion of job to place fiber 3/28- LEC delivered on 3/22, pending order testing and closure 4/3- escalating fpr mux and testing, order past due 4/10- mux scheduled for 4/15 4/18- order ready for activation, engineer informed.
2013-07-26 | ShaRita | FL118-05-IJ | 1049 Lake Sumter Landing, The Villages, FL | 12288, 8xT1 with MD5 UHGVERbgpbqZyofa | smartform 189935248 NSPE0007088271 IQBKPCV4 | 5996847 | P2026625 | 5378233 | 1536 | BCBK13WL0001-8 | 50.HCGS.146735..UFLG 1st floor telco room, RJ48X with an open plug, housing #1 slot 10 of 13, t agged and labelled , not extended 50.HCGS.146736..UFLG 1st floor telco room, RJ48X with an open plug, housing #1 slot 11 of 13, t agged and labelled , not extended 50.HCGS.146737..UFLG 1st floor telco room, RJ48X with an open plug, housing #1 slot 12 of 13, t agged and labelled , not extended 50.HCGS.146738..UFLG 1st floor telco room, RJ48X with an open plug, housing #1 slot 13 of 13, t agged and labelled , not extended 50.HCGS.146739..UFLG 1st floor telco room, RJ48X with an open plug, housing #2 slot 1 of 7, tag ged and labelled , not extended 50.HCGS.146732..UFLG 1st floor telco room rj48x with an open plug housing 2 slot 2 of 7, tagge d, not extended 50.HCGS.146733..UFLG 1st floor telco room rj48x with an open plug housing 2 slot 3 of 7, tagge d, not extended 50.HCGS.146734..UFLG 1st floor telco room rj48x with an open plug housing 2 slot 4 of 7, tagge d, not extended | 2013-07-31 | estimated 10/11/13 (TBD) | 2013-10-08 | bpdd | 2013-10-18 | 2013-10-16 | unitedhealthgroup- 64900 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | scheduled for 10/21 at 6pm CST 866-819-9840 pcode 3365052 | 7/26- submitted to ShaRita 8/1- order approved by provisioning; ASR sent to LEC 8/8- order CNR- special construction (order numbers N494823,N494824, N494825 for the special construction); it will take 11 business days to identify the special construction quote. 8/14- awaiting special construction quote to be provided from LEC 8/22- per Dave(FL03 Manager), A JEP has been sent. This circuit is now held for ICB with a possible due date of 10/11 8/29- per LEC, no special construction charges needed; supp'ing order to match intial FOC date of 10-11 because that is the due date that engineers can meet due to facility issues. 9/5- ASR supp to push due date per LEC; awaiting LEC to provide FOC date 9/12- per LEC the PON is already forwarded to the manager of engineering for the FOC date; awaiting LEC to provide FOC date. 9/19- Still pending exact FOC date. Per LEC there is an ongoing escalation on their backend to provide a FOC on this one. 9/25- pending FOC date of 10/11 10/3 pending foc 10/11 10/10- loop delivered; pending testing to be completed 10/16- ready for activation; engineer notified
2013-09-04 | ShaRita | MA023-05-IJ | 100 Quannapowitt Parkway, Suite 405 Wakefield, MA 01880 | 44736, DS3 with mds UHGVERbgpbqZyofa | smartform 189971909 CDR201309040019 NSPE0007242056 IQBKQYVG | 6046741 | P2036184 | 5391837 | 12288 | BCBK2R210001 | 95.HFGS.641489..NE DEMARC LOC: 1st floor main telco room, adc box 1 pos 3 DEMARC LOC Continued: Extended Wire (Yes or No): Yes Jack Type: RJ48X | 2013-09-06 | 2013-09-24 |  | bpdd | 2013-10-18 | 2013-09-30 | unitedhealthgroup-65230 | 763-744-2077 robert_a_benson@uhc.com | Robert confirmed came up with pnp on 10/25 | 9/4- Sent to ShaRita 9/5- awaiting provisioning approval 9/12- pending FOC date of 9/24 9/18- pending FOC date of 9/24 9/25- loop delivered; pending 892 dispatch at site CHT - working 9/26 **pending MUX COMPLETION **Will do a pre-test once MUX is completed 10/2- ready for activation, engineer informed.
2013-09-25 | ShaRita | none | 5975 Castle Pkwy North Drive Suite 150 Indianapolis, IN 46250 | disconnect | NSPE0007325418 OQBKRQBQ |  | P1931722 |  |  | BCBKTCNC0001 |  |  |  |  | bpdd | 2013-10-21 | 2013-10-23 |  |  |  | 9/25- sent to sadisconnect 10/4- disconnect due 10/21 10/10- disconnect due 10/21 10/16- disconnect due 10/21 10/23- disconnect completed
2013-09-25 | ShaRita | none | 2929 E Corona Rd Tucson, AZ 85756 | disconnect | NSPE0007325454 OQBKRRFL |  | P1883467 |  |  | BCBKNTDM0001-6 |  |  |  |  | bpdd | 2013-10-21 | 2013-10-23 |  |  |  | 9/25- sent to sadisconnect 10/4- disconnect due 10/21 10/10- disconnect due 10/21 10/16- disconnect due 10/21 10/23- disconnect completed
2013-09-04 | ShaRita | none | 131 Leichhardt St Spring Hill Australia QN 4000 | disconnect | NSPE0007241614 5341355 | 6047843 |  |  |  | w0x83286 w0x85340 |  |  |  |  | bpdd | 2013-11-05 | 2013-10-23 |  |  |  | 9/5- confirmed office is closed; will proceed with John as lcon 9/12- order accepted; pending lcon verification to be completed 9/18- PTT DISCO REQUEST SENT TO TELSTRA 9/25- pending disconnect to be completed; standard interval 11/5 10/10- pending disconnect to be completed; standard interval 11/5 10/17- pending disconnect to be completed; standard interval 11/5 10/23- disconnect completed
2013-09-30 | ShaRita | KS008-02-IJ CANCEL REQUEST | 7100 College Blvd. Overland Park, KS 66210 ** high visibility project | 44736, DS3 md5 encryption UHGVERbgpbqZyofa | Smartform 189999894 CDR201309300037 NSPE0007348444 IQBKR00H kan I15237 | 6078668 | P2043366 | 5408927 | 10800 | BCBK27680001 |  |  |  |  | bpdd |  |  | unitedhealthgroup- 65093 | tauoa.falo@uhc.com 702-242-7654 |  | 10/4- pending OM submit 10/10- awaiting ASR to be sent to LEC SBC (SW20); capacity now found on local system to design 10/14- John requested to cancel. 10/16- order supp'ed to cancel; awaiting cancellation completion 10/23- cancel completed
2013-10-11 | ShaRita | na CANCEL REQUEST | 4425 East Cotton Center Blvd. Phoenix AZ USA 85040 | VPN / PVC add | NSPE0007403423 |  |  |  |  | BCBKK1D10001 |  |  |  |  | bpdd |  |  | unitedhealthgroup-TCW 65358 | keith Mangene |  | 10/14- sent to ShaRita 10/16- working to complete request 10/23- unable to add an extra VPN to these circuits, because they are PPP. • The Multi-VRF QoS features are not supported on Private IP ports using PPP, MLPPP, ATM or HDLC encapsulations.
2013-10-15 | ShaRita | na CANCEL REQUEST | 100 Northfield Drive WINDSOR CT USA 06095 | VPN / PVC add | NSPE0007408452 |  |  |  |  | bcbkrkyd0001 |  |  |  |  | bpdd |  |  | unitedhealthgroup-TCW-65365 | keith Mangene |  | 10/14- sent to ShaRita 10/16- working to complete request 10/23- unable to add an extra VPN to these circuits, because they are PPP. • The Multi-VRF QoS features are not supported on Private IP ports using PPP, MLPPP, ATM or HDLC encapsulations.
2013-09-23 | ShaRita | GA015-03-IJ | 4875 Riverside Drive, Macon, GA 31210 | 1536, T1 | smartform 189990702 NSPE0007317793 IQBKRJ70 | 6066962 | P2039996 | 5402992 | 1280 | BCBK21H40001 | 46/HCGS/615153 /SB 1ST FLR MAIN TELCO RM MM3 SLT 3 | 2013-09-25 | 2013-10-03 | 2013-10-02 | bpdd | 2013-10-15 | 2013-10-07 | unitedhealthgroup- 64668 | 91 - 98100 59326, pradeep_yadav@uhc.com | Requested Date 10/25/13 3:00 PM, CT 866-819-9840 pcode 3365052 | 9/25- ASR sent to LEC; awaiting FOC date to be provided 10/4- LEC delivered, pending testing 10/10- ready for activation; engineer notified
2013-10-15 | core | UMD07-06-DJ | 2811 LORD BALTIMORE DR,WOODLAWN,MD | disconnect | NSPE0007408166 Order Number: D8B206809 Billing Telephone Number: 410 M55 - 1082 458 Circuit ID or Telephone Number: 38.HCGA.374501..CM |  |  |  |  | 38.HCGA.374501..CM | Billing Telephone Number: 410 M55 - 1082 458 Circuit ID or Telephone Number: 38.HCGA.374501..CM |  |  |  | bpdd | 2013-10-24 |  |  |  |  | Order Number: D8B206809 Date Due: 10-24-13 Billing Telephone Number: 410 M55 - 1082 458 Circuit ID or Telephone Number: 38.HCGA.374501..CM
2012-10-16 | ShaRita | UCA28-06-IJ | Carlsbad, CA | 50M ethernet with md5 encryption UHGVERbgpbqZyofa | SAR ID 1-1KUZSWZ. SR ID: 130942. SAR Expiration Date: 04/19/2013 IQBKD9BQ (eacs) IQBKFC40 (port) | 5614400 | P1964410 (eacs) P1964951 (port) | 5229289 | 25000 | EDBKW5HR0001 (eacs) BCBKW63C0001 (port) | 19/KQGN/528379//PT Demarc info : 1st floor data room rack mounted 101.01 dc tower port 1 ack 1 Overture Demarc is in customer server room bay 101.3 top of the rack port #1. lcon has been shown where it is. |  | 3/11/13 (estimated) |  | bpdd |  | 2013-05-02 | unitedhealthgroup-64895 | 763-744-1575, daniel_j_skripka@uhc.com | activated with Dan on 10/31 | 12/13- "There is a major infrastructure build underway to provide facilities for the circuit you have ordered. The build requires installing new fiber and equipment. The ECD for the build to complete is 2/27/13. The estimated service delivery date you may share with your customer is 3/11/13. You formal FOC will not be available until the infrastructure build has completed." 1/10- asking for update on build 1/24- pending EU contact to engineer to set up site visit 1/30- order supped for 3/30, earliest date due to build 2/7- checking if site visit has been set up 2/27- asking about site visit again 3/7- Per LEC: Due to the delay with the site visit, the ECD forthe network build has been adjusted to 4/15/13. Your ESD is 4/24/13. Your formal FOC will be issued a few days after the network build actually completes, melissa called boththe lcon and the FE to see if site survey was completed 3/13- let john know we need a new lcon, john provided Site Contact: Sean McCarley Site Contact Work: (760) 804-2238 3/20- spoke to Cesar Delgado, they just need to go on site and install equipment . Sean is on PTO until 4/8. Melissa asked Cesar to go when Sean is back from PTO 4/10- equipment is being installed this week. 4/17- called Cesar to follow up on equipment install. 4/25- the ECD for the network build has been adjusted to 4/15/13. Your ESD is 4/24/13. Your formal FOC will be issued a few days after the network build actu ally completes." 5/2- order ready fro activation, pending configlet.
10/'21 | ShaRita | AZ008-10-IJ | 4425 East Cotton Center Blvd, Phoenix, AZ 85040 | 3072 2xT1 with md5 TCWVERbgpajs9tbxp | smartform 190023559 NSPE0007428658 IQBKSJC2 | 6117710 | P2046992 | 5414974 | 1536 | BCBK3G440001-2 | 14/HCGS/445323//MS 14/HCGS/445324//MS | 2013-10-23 | 2013-11-05 |  | bpdd | 2013-11-12 |  | unitedhealthgroup-tcw 65358 | 860-702-8284 keith_mangene@uhc.com |  | 10/24- ASR sent, once accepted, we'll be receiving its FOC in 3 business days 10/31- pending FOC date of 11/5 11/1- supp to cancel per request from John.
2013-07-30 | Melissa | IQBKNW8T | MINDSPACE-K. RAHEJA IT P HYDERABAD INDIA 500081 | disconnect | s/o 5334236 |  |  | 1893321 |  | w0w53663 |  |  |  |  | bpdd | 2013-10-28 | 2013-10-28 |  |  |  | 7/31- submitted disconnect to order entry 8/8- disconnect needs to be worked via B end. Sent to Varun 8/14- Apac disconnect has it assigned and is working 8/20- followed up with Apac disco group for order numbers. 8/29- disco due on 10/28 10/31- circuit disconnected and billing triggered.
2013-07-30 | Melissa | B-end | MINDSPACE-K. RAHEJA IT P HYDERABAD INDIA 500081 | disconnect | s/o 5334242 |  |  | 1893317 |  | w0w53649 |  |  |  |  | bpdd | 2013-10-28 | 2013-10-28 |  |  |  | 7/31- submitted disconnect to order entry 8/8- disconnect needs to be worked via B end. Sent to Varun 8/14- Apac disconnect has it assigned and is working 8/20- followed up with Apac disco group for order numbers. 8/29- disco due on 10/28 10/31- circuit disconnected and billing triggered.
2013-09-06 | ShaRita | NY058-02-IJ CANCEL REQUEST | 13 Cornell Rd , Latham, NY 12110 | 44736 DS3 mds UHGVERbgpbqZyofa | smartform 189974702 CDR201309060036 NSPE0007255434 IQBKQ2C4 | 6048766 | P2037055 | 5393069 | 10800 | 5393069 |  | 2013-09-10 | estimate 12/16 |  | bpdd |  |  | unitedhealthgroup-65129 | 987-313-9388 anupam_datt@uhc.com |  | 9/12- ASR issued; special construction required. Awaiting quoted to be provided. 9/18- FACILITIES ARE NOT AVAILABLE. OUR BEST ESTIMATE DATE IS 12/16/2013. A FOC WILL BE SENT WHEN AN ACTUAL DUE DATE HAS BEEN DETERMINED. 9/25- special constructions charges provided to customer; NY01 returned with a CNR remarks: LEC FACILITIES ARE NOT AVAILABLE. OUR BEST ESTIMATE DATE IS 12/16/2013. A FOC WILL BE SENT WHEN AN ACTUAL DUE DATE HAS BEEN DETERMINED. 10/3- Ammendment needs to be signed, PCM is working on that. 10/10- FACILITIES ARE NOT AVAILABLE. OUR BEST ESTIMATE DATE IS 12/16/2013. A FOC WILL BE SENT WHEN AN ACTUAL DUE DATE HAS BEEN DETERMINED, ammendment is in process. 10/16- FACILITIES ARE NOT AVAILABLE. OUR BEST ESTIMATE DATE IS 12/16/2013. A FOC WILL BE SENT WHEN AN ACTUAL DUE DATE HAS BEEN DETERMINED, ammendment is in process. 10/23- customer requested to cancel order; order supp'ed to cancel 10/30- cancel complete
2013-04-26 | ShaRita | CANCEL REQUEST | move the Chaska internet service (circuit ID u313034 ) to a diverse gateway router backhauling to stl3 | move | CDR201305160028 IP capacity Inquiry is 94GT3V7W smartform 189917553 NSPE0007009099 IQBKN396 /PLBK10MP0001 – OPS Approved STL I20965 /gx-p48-bmj0-0006 – closed MIN C34935 /gx-511-m6l7-0001 – pending hotcut | 5972735 | P1899332 |  |  | u313034 | PLBKPT450001 / gx-73c-m6l7-0001 |  |  |  | bpdd | 2013-09-23 |  |  |  | customer will have to hotcut after freeze | pending backhaul approvals from Matt 6/20- back haul approvals done. Melissa is working on the order. 6/27- CDR approved. Melissa still working on order. 7/11- order submitted to order entry 7/18- Path orders issued. 7/25- Pending CCR 1167096 for the Fuji 9500 ROADM system installed in St. Louis with one new Muxponder ring between sites p48/09NE2 and bmj0/01 RFT date is 8/23. ops has equipment pending an install date. 8/1- some node work done on the new ring, pending further equipment installation, set for 8/9, Transmission date on new ring 8/23. 8/8- pending completion of equipment installation scheduled for 8/9 for the St. Louis ROADM transponder cards 8/14- equipment install date moved to 8/14 8/22- due to technician workload, card install moved to 9/5 8/29- roadm transponder cards are now in place in St. louis; workng on x-connects and testing for the St. Louis portion of the circuit 9/5- St. louis portion of the order RFC tested and closed, pending LD connections between STL and MSP. 9/10- sent out a dispatch in bgw for mux IQBKQZFW and IQBKQZGC to check the crossconnect and patching going to tcoms STL I20965 and MIN C34935; awaiting confirmation dispatch was completed 9/19- pending distpatch Number: IQBKQZGC-XCN Site: SC9 Address: 9869 MEEKS BLVD ST LOUIS MO Schedule: 9/19/2013 9/25- hotcut sched monday 10pm we need to sent out ft to run the rfc test and layer 3 ping test on monday if the rfc test and layer 3 ping test is successful order will endorsed to BnE D S3/OC3/OC12 activation team 10/30- cancel request completed
2013-07-12 | ShaRita | UNJ22-04-CJ | 100 MULBERRYST,BLDG4 Newark NJ 07102 | 9216, 6xT, upgrade from 5xT1 | smartform 189924003 NSPE0007039466 IQBKN4LP OQBKN58K | 5983372 | P1938004 (out) P2024995 (in) | 1601821 | 4480 | BCBK10PG0006-0006 | /HCGS/815232//NJ DEMARC LOC: BSMT ,RM telco,TEL RM ,RJ48X,LP Y,CAB N,RCK 1,SLOT 1, Jack Type: RJ48C | 2013-07-26 | 2013-08-05 | 2013-08-05 | bpdd | 2013-08-14 | 2013-08-14 | unitedhealthgroup- 65447 | 763-694-7370 masroor_khan@uhc.com | 10/31/2013 05:30:00 PM Central Time 866-819-9840 pcode 3365052 | 7/18- order submitted to order entry 7/25- order approved by provisioning. Awaiting ASR to be sent to LEC. 8/1- awaiting FOC date of 8/5 8/8- loop delivered; pending end to end testing 8/14- unable to loop niu; pending dipatch to terminal to check wiring and optioning should be set to esf/b8zs 8/19- order ready for hotcut, engineer informed.
2013-05-13 | ShaRita | UCO32-05-IJ | Sungard 3431 N. Windsor Drive Aurora, CO 80011 | Ethernet Access Type 1. 1G access, 1 gig port (john will throttle down to 100mg) Multimode with LC connector (SX Optic) MD5 encryption UHGVERbgpbqZyofa | iNet CP32818.00, PER 05211320 CDR201305150046 NSPE0006785104 IQBKMJ4Z port IQBKMJY9 access DNV I30446 / ea-h0t-890d-0001 (clsd) CCR 1154891 | 5885282 | P2011869 | 5359761 | 3008 | BCBK05RT0001 EDBK05K20001 | eah0t890d 0001 VZB DMARC: H0T8 3rd party room, RR.105.0.4.1 shelf 9 port 2tx/rx LC connectors m ultimode fiber. Tagged loop with TCOMS and Netpro cir ids. HANDOFF TYPE: Optical |  |  |  | bpdd | 2013-08-26 | 2013-06-21 | UnitedHealth Group- 64948 | 763-744-1999 jon_langemak@uhc.com | John confirmed active on 11/8 | 5/21- pending 1 gig inet per 5/22- order with local design 5/29- CCR 1154891 Project is routing through flow process to order, fund, and install. 6/6- CCR shipment complete for system upgrade, current RFT is 8/7 6/13- pending CCR 1154891, eqipment installed, oc48.mh upgraded to a oc192. Order designed and stepped to ops. 6/20- CCR completed, TCOMS (I0030446). Pending path validation. Hardloop left for remote RFC test once path is built. pending x-connects at node h0t8, 02. 6/25- local order is closed ETE completed. Ready for activation, engineer informed.
2013-10-24 | Melissa | MN053-10-CJ | 14100 Business Center Drive, Elk River, MN | Add 1Gb VLAN to Verizon circuit BOBKWHD00001 with md5 ECCmaVERskb243QB | Order Number: 10024809 PVC ID: 5417303 (Automated Pre-Build) |  |  |  |  | BOBKWHD00001 |  |  |  |  | bpdd |  | 2013-11-07 | DLCI 31 UnitedHealth Group-ECCMA- 65165 | Steve Brown Ph: +1.763.694.7333 skbrown1@uhc.com | per Steve active on 11/12 | 10/31- PVC built and configlet requested. 11/7- configelt sent to Steve
2013-08-07 | ShaRita | FL064-03-IJ CANCEL COMPLETE | 2735 W. State Rd 434, Suite 1031, Longwood, FL 32779 | 10752 7xT1 with md5 UHGVERbgpbqZyofa | smartform 189946984 NSPE0007139569 IQBKPWN4 ORL I0014545 13tes ns7v0001 | 6016095 | P2030775 | 5383603 | 1536 | BCBK2C0L0001-0007 | 10.HCGS.149168..UFLG 10.HCGS.149169..UFLG 10.HCGS.149170..UFLG 10.HCGS.149171..UFLG 10.HCGS.149172..UFLG 10.HCGS.149173..UFLG 10.HCGS.149174..UFLG | 2013-09-10 | 9/20/2013 10/25/2013 |  | bpdd |  |  | unitedhealthgroup-64529 | Deven Patterson 763-744-0696 deven_patterson@uhc.com |  | 8/29- provisioning had issues with customer address. Asked Mr. Sergot if could proceed with valid address of 2735 State St Immokalee, FL 32779; awaiting response 9/5- awaiting LEC to provide a FOC date 9/12- address valid as: 2735 W SR 434 LONGWOOD FL 32779; ASR re-issued and awaiting LEC to provide FOC date 9/18- sent an email to provisioning requesting to contact LEC for a FOC date.; awaiting response. 9/19- FOC: 9/20/13, lec: 800-871-3388, AS PER LISA, 7 CIRCUITS WILL BE INSTALLED ON 9/20/13 STATED ON THERE NOTE. 9/25- tech advised he would not have access to site until the 24th; supp'ed order with new due date of 10/29. awaiting new FOC date to be provided. 10/4- access was available on 9/24, trying to pull date in. pending supped asr 10/9- pending FOC date of 10/25 10/17- pending FOC date of 10/25 10/23- pending FOC date of 10/25 10/31- order on customer hold; awaiting confirmation if order will be cancelled, but waiting on the official email. 11/1- john requested supp to cancel. 11/6- cancel complete
2013-08-07 | ShaRita | FL065-02-IJ CANCEL COMPLETE | 3927 Rosewood, Orlando, FL 32808 | 10752 7xT1 with md5 UHGVERbgpbqZyofa | Smartform 189946916 NSPE0007139475 IQBKPWMZ | 6016026 | P2030762 | 5383587 | 1536 | BCBK2CY30001-0007 | 58/HCGS/787170//SB 58/HCGS/787171//SB 58/HCGS/787172//SB 58/HCGS/787173//SB 58/HCGS/787174//SB 58/HCGS/787175//SB 58/HCGS/787176//SB | 2013-08-13 | 2013-10-25 |  | bpdd | 2013-11-11 |  | unitedhealthgroup-65018 | Deven Patterson 763-744-0696 deven_patterson@uhc.com |  | 8/29- pending FOC date of 10/25 9/5- pending FOC date of 10/25 9/12- pending FOC date of 10/25; no facilities on site 9/19- pending FOC date of 10/25; no facilities on site 9/25- pending FOC date of 10/25 10/2- pending FOC date 10/25 10/10- pending FOC date of 10/25 10/16- There are 8 orders answered to the EWO that will provide service to UHG. It appears that the DOT permit was received on 10-7 and that construction is waiting for the approval of the City permit. The ECD: 10-18 and current due date of 10-25 will not be met due to not receiving the City permit, and the copious amount of construction work needing to be scheduled and worked afterwards. An ECD will not be given by construction until all the permit approvals are received. After the City permit approval the EWO will be scheduled to be worked by the contractor first: which includes 4 bores, breaking up a sidewalk, placing conduit and cable. Then TELCO work(62+hrs) will be scheduled including: splicing, turn up of a system 10/23- Update from ATT: Service order CYBMP846 is a part of a group of 8 orders at 3927 Rosewood Way which are held to a construction work order. We do have all permits required for this work to proceed. Our construction CMC job scheduler has assigned an ECD of 10/31 and an ESD of 11/07 for this work. LEC will not be able to meet this 10-25 due date for this service order. 10/31- pending estimated service delivery of 11/7 11/1- john requested supp to cancel. 11/6- cancel complete
2013-06-27 | ShaRita | C1557-02-IJ | 2220 Campbell Creek, Richardson, TX 75082 | 44736, DS3 with MD5 UHGVEReccgas4Usp9 | smartform 189915922 NSPE0006997764 IQBKNW8T DAL I92583 / 3x-dif-d03-0190 | 5970068 | P2023137 | 5373882 | 18000 | BCBK1WC90001 | 14/HFGS/883141//SW | 7/10/2013 9/6/2013 | 9/4/2013 9/24/2013 |  | bpdd | 9/12/2013 re-commit date 10/7 | 2013-10-15 | UHG-ECC - 65455 | 763-744-0840 matt_f_seymour@uhc.com | Scheduled for 11/15/2013 02:00:00 PM Central Time Bridge 866-692-3158 pass code 9236734 | 7/8- Siva sent to ShaRita on 7/5, ShaRita processing. 7/11- waiting for local redesign from our local pop to lec node, first cfa was busy 7/18- FOC 9/4, facility build 7/25- Pending FOC date of 9/4 8/1- Pending FOC date of 9/4 8/8- Pending FOC date of 9/4 8/14- Pending FOC date of 9/4 8/22- Pending FOC date of 9/4 8/29- Pending FOC date of 9/4 9/5- order currently on hold, tech went out for the dispatch but site is under constrution and no power 9/12- pending FOC date of 9/24 9/19- pending FOC of 9/14 9/25- advised provisioning team to confirm no power at site with LEC; awaiting response. per customer their is power. The telco rack AT&T installed last week has the power they requested on the original site requirements document. Verizon should be checking directly with AT&T, not with Cory as he doesn't know what equipment is getting installed. 10/4- Per BIC engineer fiber is spliced into the equipment. order supped for new LCOn and ealist due date of 10/25 10/3- ASR SENT: PON IQBKNW8THHTTMB02 Ver 04 for LEC SW60 (AT&T) sent today 10/2/2013 ---FOC date of 10/15/2013 with LEC order number C497207. BTDD ticket C201310040014 10/10- order approved to be added to the VP list; LEC loop delivery - FOC date of 10/15 10/15- ready for activation, customer informed.
2013-08-28 | ShaRita | FL062-03-IJ | 2020 Flamingo Drive Bartow, FL 33830 | 7xT1 10752 with mds UHGVERbgpbqZyofa | NSPE0007219117 Smartform 189966351 IQBKQNN1 | 6038764 | P2034132 | 5389480 | 1536 | BCBK2LN70001-0007 | 69/HCGS/429941/ /GTES/ MAIN PHONE RM SHELF 2 X 8 TAGGED NON EXT 69/HCGS/429942/ /GTES/ MAIN PHONE RM SHELF 4 X 8 TAGGED NON EXT 69/HCGS/429943/ /GTES/ MAIN PHONE RM SHELF 3 X 8 TAGGED NON EXT 69/HCGS/429944/ /GTES/ MAIN PHONE RM SHELF 5 X 8 TAGGED NON EXT 69/HCGS/429945/ /GTES/ MAIN PHONE RM SHELF 6 X 8 TAGGED NON EXT 69/HCGS/429946/ /GTES/ MAIN PHONE RM SHELF 7 X 8 TAGGED NON EXT |  | 2013-09-16 | 2013-09-16 | bpdd | 2013-09-23 | 2013-09-23 | unitedhealthgroup-65019 | 210-877-7969 Deven_Patterson@uhc.com | Rescheduled for 11/14/2013 04:30:00 PM Central Time 866-819-9840 pcode 3365052 | 8/29- awaiting provisioning to submit ASR 9/5- ASR sent; awaiting LEC to provide FOC date. 9/12- pending FOC date of 9/16 9/19- order ready for activation; engineer notified
2013-10-10 | ShaRita | IA021-07-CJ | 1089 Jordan Creek Parkway, 3rd Fl, Des Moines, IA 50266 | 6144 4xT1 add 1 T1 to existing 3xT1 bundle | Smartform 190015629 NSPE0007401805 IQBKSFRC (in) OQBKSGRY (out) | 6114971 | P2046410 (in) P2017011 (out) |  | 2048 | BCBK3FPS0001-4 (in) BCBK1H4R0001-3 (out) | 32/HCGS/085963//NW 32/HCGS/085964//NW 32/HCGS/088472//NW 32/HCGS/089136//NW DEMARC LOC: 1st flr mn telco rm mnt#2 slt 4/14 | 2013-10-21 | 2013-11-07 |  | bpdd | 2013-11-14 |  | unitedhealthgroup- 65134 | 91 91600 84400 harish_kandpal@uhc.com | Requested Date 11/15/2013 06:00:00 PM Central Time bridge 866-819-9840 pcode 3365052 | 10/14- sent to ShaRita 10/17- pending audit form from Siva before order is submitted 10/23- pending FOC date of 11/7 10/31- pending FOC date of 11/7 11/1- ready for hotcut, engineer informed.
2013-10-24 | ShaRita | MN011-06-CJ | Address: 1707 West Creek Lane Chaska MN USA 55318 | Please place an order to upgrade the 1Gig, circuit ID u313034, from 200Mb to 1GIG port- billng change only. | smartform 190037903 NSPE0007481346 | 6127868 | u313034 |  |  | u313034 |  |  |  |  | bpdd | 2014-01-14 | 2013-11-11 |  | Jim Skaggs. |  | 11/6- order progressed; assigned to provisioner 11/13- Site u313034 is Up and Billable for AlterNet charges as of 11/11/2013 . Site u313034 is Up and Billable for Line charges as of 11/11/2013 .
2013-10-16 | ShaRita | none | 106 Farmers Aly Kalamzoo MI | disconnect | NSPE0007408907 OQBKSCJT |  | P1705608 |  |  | BCBJ72RV0001-4 |  |  |  |  | bpdd | 2013-11-14 | 2013-11-18 |  |  |  | 10/16- sent to sadisconnect 10/24- pending disconnect date of 11/14 10/31- pending disconnect date of 11/14 11/6- pending disconnect date of 11/14 11/14- pending soft disconnect 11/20- disconnect completed
2013-10-16 | ShaRita | none | 3701 Boardman-Canfield Road Canfield, OH 44406 | disconnect | NSPE0007408742 OQBKSHL3 |  |  |  |  | BCBKPW7K0001 |  |  |  |  | bpdd | 2013-11-14 |  |  |  |  | 10/16- sent to sadisconnect 10/24- pending disconnect date of 11/14 10/31- pending disconnect date of 11/14 11/6- pending disconnect date of 11/14 11/14- pending soft disconnect 11/20- disconnect completed
2013-10-16 | ShaRita | none | 3701 Boardman-Canfield Road Canfield, OH 44406 | disconnect | NSPE0007408742 OQBKSHL4 |  |  |  |  | BCBKS00D0001-2 |  |  |  |  | bpdd | 2013-11-14 |  |  |  |  | 10/16- sent to sadisconnect 10/24- pending disconnect date of 11/14 10/31- pending disconnect date of 11/14 11/6- pending disconnect date of 11/14 11/14- pending soft disconnect
2013-10-16 | ShaRita | none | 20021 120th Ave NE Ste 200 Bothell, Washington 98011 | disconnect | NSPE0007408763 OQBKSHFY |  |  |  |  | BCBJS1080001-5 |  |  |  |  | bpdd | 2013-11-14 |  |  |  |  | 10/16- sent to sadisconnect 10/24- pending disconnect date of 11/14 10/31- pending disconnect date of 11/14 11/6- pending disconnect date of 11/14 11/14- pending soft disconnect 11/20- disconnect completed
2013-10-22 | ShaRita | MD740-05-CJ Cancel Request | 300 West Lexington BALTIMORE MD USA 21201 | inside move to the 3rd floor | Smartform 190024811 NSPE0007434926 CQBKSL2Z | 6119115 | P1982105 | 5320843 | 1536 | BCBKX99L0001 | 3X-7YC-3AI-0005 | 2013-10-28 | 2013-11-11 |  | bpdd | 2013-11-12 | 2013-11-19 |  |  |  | 10/24- order submitted to Order Entry 10/31- pending FOC date of 11/11 11/6- According to NLI this ckt was never delivered to a 1st floor location. The install order delivered the ckt to this 3rd floor demarc at 3ai,loc 02: 3rd floor node room, DSX3 14.4.7:2.; awaiting customer on how to proceed 11/13- awaiting customer feedback on how to proceed 11/20- customer advised order could be cancelled. cancelled completed 11/19.
2013-11-14 | ShaRita | none | 1 Main Street Cambridge, MA 02142 | disconnect | NSPE0007520759 |  |  |  |  | BCBKS00R0001-2 |  |  |  |  | bpdd | [5 empty] | 11/14- order sent to sadisconnect 11/20- per sadisconnect: John, Per our records the circuit id on the attachment was not installed or was cancelled before installation was completed. Please contact billing regarding any billing issues/questions that you may have. The reach number is 800 937-6000 or send a new email to customercare@verizon.com.
2013-11-01 | ShaRita | FL116-03-IJ | 2617 West Torch Lake Dr , The Villages, FL 32162 | 3072 2xT1- with md5 UHGVERbgpbqZyofa | Smartform 190037826 NSPE0007480978 IQBKSW7V | 6129281 | P2049889 | 5419530 | 1536 | BCBK3N3J0001-2 | 50.HCGS.154760..UFLG DEMARC LOC: ONT 1ST FL TELCO ELECTRICAL ROOM SLOT 4 POST 1 50.HCGS.154761..UFLG DEMARC LOC: ONT 1ST FL TELCO ELECTRICAL ROOM SLOT 4 POST 2 Jack Type: RJ48X WITH OUT PLUG PER CINDY VERIZON | 2013-11-04 | 2013-11-14 | 2013-11-13 | bpdd | 2013-11-21 | 2013-11-15 | unitedhealthgroup-65286 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | 11/25/2013 06:00:00 PM Central Time Conference Bridge 866-878-8630 Conference Pass Code 6653710 | 11/6- pending FOC date of 11/14 11/13- loops delivered; pending testing 11/15- ready for activation; enigeer notified
2013-10-24 | ShaRita | M0206-05-IJ | 5015 Campuswood Dr. (DeWitt), East Syracuse, NY 13057 | 7680 5xT1 md5 encryption UHGVERbgpbqZyofa Install in NEW MDF room as old MDF is going away | smartform 190028477 NSPE0007447599 IQBKSLVP | 6120332 | P2047691 | 5415910 | 3072 | BCBK3JGP0001-5 | 36.HCGS.802968..NY rj48C, 1st flr server rm, cab 1 slot 6 of 14, tagged not ext 36.HCGS.802969..NY 1st flr server rm, cab 1 slot 7 of 14, tagged not ext 36.HCGS.802970..NY rj48c, 1st flr server rm, cab 1 slot 8 of 14, tagged not ext CABINET # 1 SLOT 8 36.HCGS.802971..NY rj48c, 1st flr server rm, cab 1 slot 9 of 14, tagged not ext 36.HCGS.802972..NY rj48c, 1st flr server rm, cab 1 slot 10 of 14, tagged not ext Jack Type: RJ48X | 10/24/2013 11/12/2013 | 11/7/2013 12/02/2013 | 2013-11-21 | bpdd | 2013-11-27 | 2013-11-27 | unitedhealthcare-64548 | 987-313-9388 anupam_datt@uhc.com | Requested Date 12/4/2013 01:00:00 PM Central Time bridge 866-819-9840 pcode 3365052 | 10/31- pending FOC date of 11/7 11/6- pending FOC date of 11/7 11/13- per customer site under construction will not be ready until November 25st. Pending new FOC date 12/2 11/20- pending FOC date of 12/2 11/26- loop delivered; pending testing 11/27-order ready for activation 12/4- Per Anupam, I was able to turn up the new circuits successfully. All T1’s and BGP is up and the circuit looks good. This is to confirm the acceptance of this circuit and the contact information is as below. Name – Anupam Datt Cell No – 91 9873139388
2013-05-28 | B end | PH504-02-IJ | Science Hub Tower #3, McKinley Hill Cyberpark, cPhilippines | 100M ethernet soo Melbourne - circuit ID W0X83226 md5 UHGVERbgpbqZyofa | 1-1204650450 : 5292157 & 5292158. |  |  |  | 30720 | W1A43066 (port) W1A43067 (access) | carrier BAYAN TEL | 2013-07-03 |  |  | bpdd |  | 2013-12-01 | unitedhealthgroup-64925 | plus 632-588-4651 noemi.joy_gomez@uhc.com | activated on 12/5 with Noemi | 10/10- Per Patrick, . The MDF handover has been postponed one week until 10/18. It will take about 2 weeks for the PTT to delvier post MDF readiness and then we need 5-10 days to do physical work, that brings us to an expected ready date of 11/8. 10/.17- ID CARDS AND PERMIT ARE RELEASED. AGREED WITH UHC GENERAL CONTRACTOR TO START FOC LAYING TOMORROW. FYI, UHC DATA EQUIPMENT IS NOT YET MOUNTED. THEIR CONTRACTOR WILL FIX IT TOMORROW WHILE OUR CONTRACTOR DOES THE FOC INSTALLATION. 10/24- FIBER OPTIC CABLE INSTALLATION STARTED LAST FRIDAY 18 OCT TARGET COMPLETION OF FIBER CABLE INSTALLATION IS OCT 24 . Mux should have been installed on 10/23 10/31- Issue was found during end to end testing. Today, PTT is on early knock off, Tomorrow Nov 01 is Phils Public Holiday . Next corrective action will be perform by Nov 04. I will closely work with PTT to get the circuit hand over to VZB sooner than Nov 08. 11/5- HW ARE NOW INSTALLED ON QUE FOR THE PATCHING OF FIBER 11/7- loop in place with testing between ptt and vzb. 24 hour test. 11/14-issues found with the path between Verizon and PTT while testing, needed to groom to a new path, that grooming is complete and dispatch is scheduled for initital testing. 11/21- LAST TESTING (30MINS AGO), LINK IS STILL WITH ERRORS THOUGH MUCH BETTER NOW THAN THE PREVIOUS ISOLATIONS. OUR NOC & FE ARE CURRENTLY DOING ANOTHER ISOLATION (REPLACED PORT AT MK2 & UHC, REROUTED TO BETTER SHORTEST PATH). HOPE WE CAN BE ABLE TO RESOLVE THE PROBLEM TONIGHT. 12/1- ready for acitvation
2013-11-07 | ShaRita | UCA08-05-CJ | 8840 Complex Drive, San Diego CA 92123 | Upgrade to 6144, new 4xT1 | smartform 190045735 NSPE0007511358 IQBKS5S5 (in) OQBKS5ZR (out) | 6142074 | P1796758 (out) P2051743 (in) | 1974302 | 2048 | BCBKGW1R0001-2 (out) BCBK3VV80001-4 (in) | 19/HCGS/618726//PT RJ48C ON MOUNT 3X3 TAGGED OK TO LEAVE TO LEAVE AT MPOE DAVE 19/HCGS/618727//PT RJ48C ON MOUNT 3X4 TAGGED Jack Type: RJ48C | 2013-11-13 | 2013-12-03 | 2013-12-03 | bpdd | 2013-12-10 | 2013-12-03 | unitedhealthgroup-64883 | 987-313-9388 anupam_datt@uhc.com | Hotcut scheduled for Dec 11th, Wednesday, at 5:00 PM PST. Conference bridge: 866-692-3158 pass code: 9236734 | 11/7- Melissa has order and is working 11/13- ASR sent; FOC will be received after 3BD 11/20- pending FOC date of 12/3 12/4- ready for hotcut; engineer notified
2013-10-03 | ShaRita | AK010-02-IJ | 310 K Street, Anchorage, Alaska. 99501 | 3072 2xT1- with MD5 TCWVERbgpajs9tbxp | GL id 1155792 circuit 7393409 smartform 190012415 NSPE0007393561 New smartform 190015752 NSPE0007401861 access 5364665 port 5364664 IQBKSCBP | 6109476 | P2045994 | 5423041 | 768 | MGBK3DWH0001/0002 W1A72823 access W1A72836 port | GCI 2XT1 CIRCUIT ID'S HC--/161675 HC--/161676 ACS LOCAL LOOP SERVICE CKT ID: 46.UHDA.011595..GCI DMARC: 7TH FLR SERVER RM TAGGED AND LABELED ON 110 BLOCK.....TIE CABLE POSN 43/44 45/46... | 2013-10-17 | 2013-11-18 | 2013-11-18 | bpdd | 2013-12-16 | 2013-11-25 | UnitedHealth Group-TCW - 65446 | 763-744-1575, daniel_j_skripka@uhc.com |  | 10/4- pending Globalink pricing. 10/10- GL pricing received, Melissa submitted to ShaRita 10/14- Melissa Resubmitted as opt 1 10/16- order approved by provisioning; pending request to LEC 10/23- Order processing is completed from GCI; pending FOC 11/18 10/31- pending FOC 11/18 11/6- pending FOC 11/18 11/13- pending FOC 11/18 11/20- loop delivered; pending testing
2013-11-14 | E47349-13558 | Please Port Main Number 361-853-3995 to the below circuits on 12/6/13 if possible. | 2634 Gollihar - Suite C CORPUS CHRISTI, TX 78415 VTNS Site ID: TX182 | 6145743 | NSPE0007530849 | Existing Circuit ID: prtxunyb60001 LEC ID: 34/HCGS/626957//SW TIN 5871541 DID Range = 361-445-3203 thru 3222 outpulsing 5-xxxx. | [7 empty] | 11/15- sent to SA Mac. 12/3- We have FOC for 12/06 . What time did you want to schedule the port? We have been approved. port 12/06 5pm Ct bridge: 866-860-5032 pc 6607777
2013-12-02 | E46376-13657 | disconnect of services that were never turned up | 1118 S. Orange Ave / Suite 201 Orlando, FL 32806 VTNS Site ID: FL026 |  | acct 8604099039 INTRADA ORDER #: 4545131 COMPANY NAME: UNITED HEALTH CARE IX PLUS ACCT/BAN: 8604099039 LOCAL ORDER/AM #: 14479535 | VzB Circuit ID: prtes n4fj0001 LEC Circuit ID: 58/HCGS/787805//SB VzB DID's: Reservation ID = 10354915 Range = 407-454-5584/5623 Qty numbers = 40 DEMARC LOC: 2ND FLR STE 201 TELCO RM.CAB1 SLT4 | [7 empty] | 12/3- LD discos is processing. Assigned to BERNARDO JACOBE 12/3-disconnect due 12/9
2013-11-07 | ShaRita | none | 1821 Rutherford Lane Ste 300 Austin, TX | disconnect | NSPE0007498799 OQBKS783 |  |  |  |  | BCBJB42F0001 |  |  |  |  | bpdd | 2013-12-05 | 2013-12-09 |  |  |  | 11/8- order sent to sadisconnect 11/14- pending disconnect due date of 12/5 11/20- pending disconnect due date of 12/5 12/5- pending disconnect 12/9- disconnect completed
2013-11-07 | ShaRita | none | 6200 Shingle Creek Parkway Brooklyn Center, MN 55430 | disconnect | NSPE0007498812 OQBKS8GH |  |  |  |  | BCBJ13V30001-2 |  |  |  |  | bpdd | 2013-12-05 | 2013-12-09 |  |  |  | 11/8- order sent to sadisconnect 11/14- pending disconnect due date of 12/5 11/20- pending disconnect due date of 12/5 12/5- pending disconnect 12/9- disconnect completed
2013-11-07 | ShaRita | none | 2858 Loker Ave Carlsbad, CA 92009 | disconnect | NSPE0007498839 OQBKS8HG |  |  |  |  | BCBKKDYR0001 |  |  |  |  | bpdd | 2013-12-05 | 2013-12-09 |  |  |  | 11/8- order sent to sadisconnect 11/14- disconnect order number yet not received; sent a follow up email to sadisconnect 11/15- disconnect due 12/5 11/20- pending disconnect due date of 12/5 12/5- pending disconnect 12/9- disconnect completed
2013-10-15 | ShaRita | IL061-02-IJ | 9550 W. Higgins Road - Suite 1100, Rosemont, IL 60019 | 4xT1, 6144 md5 encryption UHGVERbgpbqZyofa | smartform 190017581 NSPE0007408342 IQBKSDQP | 6113233 | P2046247 | 5413673 | 2048 | BCBK3FDK0001-4 | /HCGS/665225//LB DEMARC LOC: 1ST FL TELCO RM ORANGE 66 BLOCK PO DEMARC LOC Continued: BLOCK POS. 33 Jack Type: 66BLK /HCGS/665226//LB DEMARC LOC: 1ST FL TELCO RM ORANGE 66 BLOCK PO DEMARC LOC Continued: BLOCK PO. 37 Jack Type: 66BLK /HCGS/665227//LB DEMARC LOC: 1ST FL TELCO ROOM ORANGE 66 BLOCK PO DEMARC LOC Continued: S 38 Jack Type: 66BLK /HCGS/665228//LB DEMARC LOC: 1ST FL TELCO RM ORANGE 66 BLOCK PO DEMARC LOC Continued: BLOCK POS. 39 Jack Type: 66BLK | 2013-10-21 | 2013-10-31 | 2013-10-29 | bpdd | 2013-11-07 | 2013-11-01 | unitedhealthgroup-65056 | 763-744-2077 robert_a_benson@uhc.com | Activation scheduled for 1/3/2014 02:00:00 PM Central Time. Conference bridge: 866-878-8630 pass code 6653710 | 10/15- sent to ShaRita 10/17- order submitted to order entry 10/23- pending FOC date 10/31 10/31- loop delivered; pending testing 11/1- ready for activation -engineer informed. 1/2- Per Robert, We can cancel the conference call. The config was plug and play. The 4xT1’s are up, the multilink circuit is up, and I have BGP learned routes.
2013-10-15 | ShaRita | WA041-02-IJ | 15325 SE 30th Place, Eastgate Office Park, Bellvue, WA 98007 | 6xT1, 9216 md5 encryption UHGVERbgpbqZyofa | smartform 190017579 NSPE0007408268 IQBKSDN8 | 6113226 | P2046243 | 5413668 | 4608 | BCBK3FC30001-6 | 74/HCGS/515987//PN DEMARC LOC: 2nd fl telco multi mount 2 slot 8 of 8 Extended To 2nd fl data room patch panel jack 7 74/HCGS/515988//PN DEMARC LOC: 2nd fl telco multi mount 1 slot 1 of 8 Extended To 2nd fl data room patch panel jack 8 74/HCGS/515989//PN DEMARC LOC: 2nd fl telco multi mount 1 slot 3 of 8 Extended To 2nd fl data room patch panel jack 9 74/HCGS/515990//PN DEMARC LOC: 2nd fl telco multi mount 1 slot 3 of 8 Extended To 2nd fl data room patch panel jack 7 74/HCGS/515991//PN DEMARC LOC: 2nd fl telco multi mount 1 slot 4 of 8 Extended To 2nd fl data room patch panel jack 11 74/HCGS/515992//PN DEMARC LOC: 2nd fl telco multi mount 1 slot 7 of 8 Extended To 2nd fl data room patch panel jack 12 Jack Type: rj48c | 2013-10-23 | 2013-11-14 | 11/5/2013 11/12/2013 | bpdd | 2013-11-12 | 2013-11-22 | unitedhealthgroup-65057 | 763-744-2077 robert_a_benson@uhc.com |  | 10/15- sent to ShaRita 10/17- order submitted to order entry 10/23- ASR transmitted; FOC in 3 business days 10/31- customer requested to have have the circuits installed in room N206 on the second floor; supp'ed order to reflect change. Awaiting for FOC date to be provided. 11/6- pending loop for circuit 5 11/13- pending testing; TICKET created to lec to check the circuit. Checked all parameters on Verizon's part and all good. This is for ckt 2. Other circuits are good. Will monitor this and escalate if needed. 11/20- t3 ticket is still open and has been escalated. T3 is working with Centurylink to resolve issue with circuit. 11/25- ready for activation; engineer notified
2013-10-10 | ShaRita | TX090-02-IJ | 6363 NORTH STATE HWY 161 Irving, TX 75038 | 3072 2xT1 with md5 UHGVERbgpbqZyofa | smartform 190012463 NSPE0007393731 IQBKR83F | 6106340 | P2045373 | 5412370 | 768 | BCBK3CXW0001-2 | 50/HCGS/141319//SWDL DEMARC LOC: 1ST FLR TELCO RM (NXT TO SERV ELE) CAB DEMARC LOC Continued: ELE) CAB 2 SLOT 1 RJ48C 50/HCGS/141320//SWDL DEMARC LOC: 1ST FLR TELCO RM (NXT TO SERV ELE) CAB DEMARC LOC Continued: ELE) CAB 2 SLOT 2 RJ48C | 2013-10-29 | 2013-11-01 | 2013-10-31 | bpdd | 2013-11-08 | 2013-10-31 | unitedhealthgroup- 65093 | 763-744-1575, daniel_j_skripka@uhc.com |  | 10/10- sent to ShaRita 10/17- Order has not been ops approved due to we are pending capacity. Follow up email has been sent to Access Engineer (AE) team for the capacity assistance. 10/23- Awaiting for another capacity to be provided as per Telco Rep AT&T sport center group. The address SPORT Buildout, OOFBNP is the corresponding SPEC code. LEC advised that it needs to be affiliated to the Northlake wire center. This request has been referred to area planner. 10/31- pending FOC date of 11/1 11/6- ready for activation; engineer notified
2013-04-16 | B end | UUK03-05-IJ | 3rd fl Beaufort House, Cricket Field Road, Uxbridge Middlesex | 20M ethernet UHGVERbgpbqZyofa SOO Letterkenny - circuit ID W0Y12673 | 5287853 | n/a | n/a | 5368388 | 12288 | W1A41046 | 2C01192971/2C01192974 /EAFE01192358 Dmarc FLOOR : 3RD ROOM : SUITE 1 CABINET : CAB 2 ODF PANEL : N/A POS : VODAPHONE ADVA 150CC SHELF |  |  |  | bpdd | 2013-10-22 | 2013-10-08 | unitedhealthgroup- 64949 | 763/694-7409, terry_bjorke@uhc.com | Requested Date 11/21/2013 12:30:00 PM Central Time bridge 866-819-9840 pcode 3365052. | 5/30- pending order numbers 6/6- following up with B end on order numbers 6/13- orders created TEV E-MAIL SENT TO CUSTOMER. 6/20- order sent to the ptt, pending response. 6/27- awaiting PTT to provide FOC date 7/3- PTT FOC not provided yet, will be provided on 11/7/2013. 7/11- following up on FOC 7/18- FOC for 8.27 8/1- pendign PTT delivery on 8/27 8/29- still pending fiber...issue with access: AS PER UPDATE VODAFONE ARE WAITING FOR CUSTOMER TO ACCEPT RISK ASSESSMENTS AND METHOD STATEMENTS ACCESS IS BOOKED DIRECTLY WITH SITE CONTACT 9/5-Vodaphone is pushing BT for an update on the above. 9/12-BT ORDER IN CUSTOMER DELAY AS OF 28/08. CUSTOMER ACCESS DEPENDENT ON DETAILED RAMS. OLO TEAM WERE ASKED ON 09/03 TO RE-ISSUE RAMS(RISK ASSESSMENTS AND METHOD STATEMENTS) TO LISA.TOLMIE@I3INNOVUS.COM AS PER VERIZON REQUEST, sent again on 9/8 9/26- CUSTOMER HAS APPROVED RAMS AND BT FIT AND TEST HAS BEEN BOOKED FOR 24/09/2013, circuit provisioning in process. 9/27- 26/09 - BT (BRITISH TELECOM) COMPLETED 9/24 VF (VODAFONE) ARFS (ADVISED READY FOR SERVICE) AMENDED TO 10/1.. VF (VODAFONE) FINAL TESTING SCHEDULED FOR FRIDAY 9/27. ACCESS AGREED. 9/30- Please be informed Vodafone has handed the circuit over to VzB today. At the moment we are validating dispatch for local and test and end to end test. 10/2- dispatching to customer site on 10/4 to test ETE 11/21- Customer/MS IE Contact: Terry Bjorke 7636947409 Account Team/PM Contact: Melissa R Chapman Comments/New route and/or new port info: New Install completed. Circuit is UP/UP and error free. Terry Bjorke confirms applications are up and processing traffic, and accepts this circuit.
2013-11-14 | ShaRita | none | 5710 Olenander Drive, Suite 206 Wilmington, NC 28403 | disconnect | NSPE0007520487 OQBKTCTJ |  |  |  |  | BCBKV4T00001 |  |  |  |  | bpdd | 2013-12-12 | 2013-12-17 |  |  |  | 11/14- order sent to sadisconnect 11/20- pending disconnect due date of 12/12 12/5- pending disconnect due date of 12/12 12/11- pending disconnect due date of 12/12
2013-11-14 | ShaRita | none | 8345 Lenexa Drive Lenexa, KS 66214 | disconnect | NSPE0007520686 OQBKTPTV kan-O9863 |  |  |  |  | u220554 PLBJMN920001 | o2-6xc-cyx7-0001 |  |  |  | bpdd | 2013-12-12 | 2013-12-18 |  |  |  | 11/14- order sent to VZB FULL DISCO OPTION 4 11/20- pending disconnect due date of 12/12 12/5- pending disconnect due date of 12/12 12/11- pending disconnect due date of 12/12
2013-11-25 | ShaRita | none | 2025 North 3rd Street Suite 170 Phoenix, AZ 85004 | disconnect | NSPE0007555709 OQBKTKX6 |  |  |  |  | BCBKPMLB0001-6 |  |  |  |  | bpdd | 2013-12-19 | 2013-12-23 |  |  |  | 11/25- order sent to sadisconnect 12/5- pending disconnect due date of 12/19 12/11- pending disconnect due date of 12/19 12/19- pending disconnect completion 12/23- disconnect completed
2013-11-25 | ShaRita | none | 1064 Lake Sumter Landing The Villages, FL 32162 | disconnect | NSPE0007564990 OQBKTM78 |  |  |  |  | BCBK0JW10001-2 |  |  |  |  | bpdd | 2013-12-24 | 2013-12-27 |  |  |  | 11/25- order sent to sadisconnect 12/5- pending disconnect due date of 12/24 12/11- pending disconnect due date of 12/24 12/19- pending disconnect due date of 12/24 12/27- disconnect completed
2013-11-20 | ShaRita | none | 1 Main Street Cambridge, MA 02142 | disconnect | NSPE0007550088 OQBKTLZ8 |  | P1927288 |  |  | BCBKS3GC0001-2 |  |  |  |  | bpdd | 2013-12-19 | 2013-12-23 |  |  |  | 11/20- order sent to sadisconnect 12/5- pending disconnect due date of 12/19 12/11- pending disconnect due date of 12/19 12/19- pending disconnect completion 12/23- disconnect completed
2013-11-20 | ShaRita | none | 8345 Lenexa Drive Lenexa, KS 66214 | disconnect | NSPE0007550116 OQBKTL01 KAN-O0011161 |  |  |  |  | BCBJ27620001 | 3X-6XC-CYX7-0004 |  |  |  | bpdd | 2013-12-19 | 2013-12-23 |  |  |  | 11/20- order sent to sadisconnect 12/5- pending disconnect due date of 12/19 12/11- pending disconnect due date of 12/19 12/19- pending disconnect completion 12/23- disconnect completed
2013-11-20 | ShaRita | none | 8800 Grand Oaks Circle Tampa, FL 33637 | disconnect | NSPE0007550223 OQBKTL10 |  |  |  |  | BCBKKYYJ0001 |  |  |  |  | bpdd | 2013-12-19 | 2013-12-31 |  |  |  | 11/20- order sent to sadisconnect 12/5- pending disconnect due date of 12/19 12/11- pending disconnect due date of 12/19 12/19- pending disconnect completion 12/31- disconnect completed
2013-11-25 | ShaRita | none | 315 Eisenhower Pkwy - Suite 305 Ann Arbor, MI 48108 | disconnect | NSPE0007564926 OQBKTM6J |  |  |  |  | BCBKV6410001 |  |  |  |  | bpdd | 2013-12-24 | 2014-01-02 |  |  |  | 11/25- order sent to sadisconnect 12/5- pending disconnect due date of 12/24 12/11- pending disconnect due date of 12/24 12/19- pending disconnect due date of 12/24 1/2- disconnect completed
2013-11-14 | ShaRita | none | 5701 Katella Avenue Cypress, CA 90630 | disconnect | NSPE0007523307 NSPE0007548309 OQBKTJ1N | 6150267 |  |  |  | IBBJHC0Y0001-0238 IBBJHC0Y0215-0238 |  |  |  |  | bpdd | 2013-12-23 | 2013-12-31 |  |  |  | 11/14- order sent to sadisconnect 11/20- customer and Melissa confirmed this should be a partial disconnect. Request resubmitted by John and submitted to SADedicatedCSS-request 12/5- pending disconnect due date of 12/23 12/11- pending disconnect due date of 12/23 12/19- pending partial disconnect due date of 12/23 12/31- disconnect complete
2013-12-12 | ShaRita | none | 3rd Floor Beaufort House/Cricket Field Road UxBridge Middlesex, United Kingdom UK UB81QG | disconnect | NSPE0007628323 s/o 5402467 | 6173168 |  |  |  | W0V96974 |  |  |  |  | bpdd | 2014-02-14 | 2014-01-02 |  |  |  | 12/19- disconnect submitted 12/30- pending disconnect completion; standard interval due date 2/14. 1/2- disconnect complete
2012-09-21 | B end | IR503-04-IJ | Dublin Irlenad | E1 2048 with md5 UHGVERbgpbqZyofa SOO to Letterkenny - circuit ID W0Y12673 | s/o 5163628 |  |  | 5328277 | 1536 | W0Z89332 | eircom DPL2113092 |  | 2012-12-22 |  | bpdd | 2012-01-13 |  | united healthgroup- 65086 | 763/694-7409, terry_bjorke@uhc.com |  | 12/27- pending customer coms room. 1/3- still pending coms room 1/9- still pending comms room 1/16- per local contact, pending landlord signature from uHG 2/7- Per John, lease should be signed this week. 2/27- per John lease is with UHG legal 3/12- per john everything will be completed by 3/22. 3/19- Current status is that we are still waiting for comments back from VHI on the sublease. The business has a meeting with them on March 26, which means the lease will not be signed on March 22. We are now looking at a mid-April date for lease execution. 5/17- Order currently on hold. Waiting for customer to provide the signed lease. 6/6- still pending signed lease 7/25- pending signed lease. 1/2- order cancelled
2013-05-29 | B end | PH503-02-IJ | 8th-9th Flr, Calyx Centre, Cebu I.T. Park, Apas, Cebu City, Phillippines | 100M ethernet soo Melbourne - circuit ID W0X83226 md5 UHGVERbgpbqZyofa | 1-1204650121 SO: 5292125 & 5292126 |  |  |  | 21504 | W1A43047 (port) W1A43048 (access) | carrier BAYAN TEL | 2013-07-03 | 2013-08-20 |  | bpdd |  | 2013-12-20 | unitedhealthgroup-64937 | plus 632-588-4651 noemi.joy_gomez@uhc.com |  | 10). We will try and push it to meet your 10/18 and 10/28 dates, but that is no guarantee 10/10- New MDF date of 10/13, asking to pass along to PTT 10/15- CUSTOMER EQUIPMENT RACK IS NOT YET INSTALLED AS OF OCT 14. THERE WAS AN EARTHQUAKE YESTERDAY AND STILL EXPERIENCING AFTERSHOCKS TODAY. OUR CONTRACTOR WILL COORDINATE W/ THE LCON. AS OF YESTERDAY. ALL EMPLOYEES IN CEBU IT PARK WERE ADVISED NOT TO WORK. 10/24- pending mux ready date of 10/28 10/31- PTT COMPLETED ODF & FIBER OPTIC CABLE TERMINATION AT CUST SITE LAST 29 OCT PTT WAITING ADVISE FROM CUSTOMER FOR THE EQUIPMENT INSTALLATION OCT 31- PTT ON EARLY KNOCK OFF, NOV 01- PHILIPPINES PUBLIC HOLIDAY 11/7- still pending customer rack. 11.14- Patrick confirmed customer rack is in Cebu and will be installed over the weekend. Melissa checking to see if PTT can begin work Monday. 11/21- EDWIN MANCIA ADVISED OUR CONTRACTOR TO MOVE THE ACTIVITY ON shcduled for 11/20 BECAUSE THERE ARE UHC CONTRACTORS WORKING INSIDE THE DATA CENTER. working with edwin on another date 12/5- INSERTION OF SFP AT VITRO SWITCH AND TRANSMISSION PORT IS ON PROGRESS. PTT NEW RFS DATE : 10 DEC 2013 12/12-ISSUE WAS FOUND DUE TO THE MUX EQUIPMENT INSTALLED AT CUSTOMER SITE PTT WILL SHIP SPARE UNIT FROM MANILA TO CEBU, EXPECTED ETA OF SPARE MUX WILL BE DEC 13 AFTERNOON 1/2- IVUE ACTIVATION COMPLETED 12/18/2013 10:00 PM CENTRAL TIME Customer Contact: Noemi Joy Gomez (+63918-9850-985) Comments/New route and/or new port info: Change / Hot Cut completed. Circuit is UP/UP and error free. Noemi confirms applications are up and processing traffic, and accepts this circuit.
2013-12-30 | ShaRita | TX090-05-CJ | 6363 NORTH STATE HWY 161 Irving, TX 75038 | 6144, upgrade from 2xT1 to 4xT1 md5 UHGVERbgpbqZyofa | smartform 190096756 NSPE0007677484 IQBKVC62 OQBKVDSB | 6186588 | P2058882 | 5412370 | 3072 | BCBK4D8S0001-4 | 50/HCGS/142813//SWDL DEMARC LOC: 1ST FLR TELCO RM CAB 3 SLOT 3 RJ48C DEMARC LOC Continued: RJ48C 50/HCGS/142815//SWDL DEMARC LOC: 1ST FLR TELCO RM CAB 3 SLOT 4 RJ48C DEMARC LOC Continued: RJ48C | 2014-01-07 | 2014-01-23 | 2014-01-20 | bpdd | 2013-01-30 | 2014-02-21 | unitedhealthgroup- 64873 | 763-744-1575, daniel_j_skripka@uhc.com | activated with Dan on 1/31 | 1/2- order submitted to order entry 1/9- ASR submitted; awaiting LEC to provide FOC date 1/16- pending FOC date of 1/23 1/21- ready for hotcut; customer notified
2013-11-14 | b-end | none | Oxygen Blvd- Tower D Floors Ground thru 3 Plot No 7 Sec 144 Noida Uttar Pradesh 201304 | disconnect | NSPE0007521233 5386329 |  |  |  |  | w0z39249 |  |  |  |  | bpdd | 2014-02-07 | 2014-01-30 |  |  |  | 11/14- disconnect submitted to B-end 11/20- pending disconnect due date of 1/14 12/5- pending disconnect due date of 1/14 12/11- pending disconnect due date of 1/14 12/19- pending disconnect due date of 1/14 1/2- pending disconnect due date of 1/14 1/-16- disconnect date moved to 2/7- PTT DATE OF DISCONNECTION IS 17-JAN-2014 1/29- circuit disconnected; requested order to be closed 2/6- disconnect complete
2014-01-02 | ShaRita | none | 400 N Pennsylvania Ave Suite 550 Roswell, NM 88201 | disconnect | NSPE0007684646 OQBKVG6D |  |  |  |  | BCBJ1L620001 |  |  |  |  | 2013-01-03 | 2014-01-30 | 2114-02-03 |  |  |  | 1/2- order submitted to sadisconnect 1/9- pending disconnect of 1/30 1/16- pending disconnect of 1/30 1/22- pending disconnect of 1/30 1/29- pending disconnect of 1/30 2/6- disconnect complete
2014-01-02 | ShaRita | none | 1225 Eye Street Washington, DC 20050 | disconnect | NSPE0007684685 OQBKVJ6Q |  |  |  |  | BCBJ7KL80001 |  |  |  |  | 2013-01-03 | 2014-01-30 | 2014-02-03 |  |  |  | 1/2- order submitted to sadisconnect 1/9- emailed sadisconnect requesting disconnect request be submitted 1/16- pending disconnect of 1/30 1/22- pending disconnect of 1/30 1/29- pending disconnect of 1/30 2/6- disconnect complete
2014-01-02 | ShaRita | none | 130 West 2nd St 4th Floor Dayton, OH 45402 | disconnect | NSPE0007684767 OQBKVJ50 |  |  |  |  | BCBJS1BS0001-3 |  |  |  |  | 2013-01-03 | 2014-01-30 | 2014-02-03 |  |  |  | 1/2- order submitted to sadisconnect 1/9- emailed sadisconnect requesting disconnect request be submitted 1/16- pending disconnect of 1/30 1/22- pending disconnect of 1/30 1/29- pending disconnect of 1/30 2/6- disconnect complete
2014-01-02 | ShaRita | none | 22 Corp Woods Albany, NY12211 | disconnect | NSPE0007684832 OQBKVJ7D |  |  |  |  | BCBK2DW80001-8 |  |  |  |  | 2013-01-03 | 2014-01-30 | 2014-02-03 |  |  |  | 1/2- order submitted to sadisconnect 1/9- emailed sadisconnect requesting disconnect request be submitted 1/16- pending disconnect of 1/30 1/22- pending disconnect of 1/30 1/29- pending disconnect of 1/30 2/6- disconnect complete
2014-01-02 | ShaRita | none | 5015 Campuswood Drive Suite 107 East Syracuse, NY 13057 | disconnect | NSPE0007684913 OQBKVD10 |  |  |  |  | BCBJP1NK0001-4 |  |  |  |  | 2013-01-03 | 2014-01-30 | 2014-02-03 |  |  |  | 1/2- order submitted to sadisconnect 1/9- emailed sadisconnect requesting disconnect request be submitted 1/16- pending disconnect of 1/30 1/22- pending disconnect of 1/30 1/29- pending disconnect of 1/30 2/6- disconnect complete
2014-01-02 | ShaRita | none | 400 N Pennsylvania Ave Suite 550 Roswell, NM 88201 | disconnect | NSPE0007684967 OQBKVDZP |  |  |  |  | BCBKVY630001-2 |  |  |  |  | 2013-01-03 | 2014-01-30 | 2014-02-03 |  |  |  | 1/2- order submitted to sadisconnect 1/9- pending disconnect of 1/30 1/16- pending disconnect of 1/30 1/22- pending disconnect of 1/30 1/29- pending disconnect of 1/30 2/6- disconnect complete
2013-05-15 | ShaRita | TN041-06-IJ | 1021 Windcross Ct. Franklin, TN 37067-2678 | 100M ethernet md5 encryption UHGVERbgpbqZyofa | approved iNet is CP32672.00, PER 05161302 smartform 189879395 NSPE0006818796 IQBKMP2F port IQBKMNB8 access SAR 1-1PA9JK7 Confirmation #ME202018 Exp date 9/18/13 | 5894078 | P2012817 | 5361511 | 44992 | BCBK07800001 edbk064j0001 | T4/KQGN/822172//SC VZB DMARC: Data Center Room Equipment Cabinet R21 Position 36, tagged, not ext ended. HANDOFF TYPE: ELEC | 2013-07-15 | 2013-07-15 |  | bpdd | 2013-07-22 | 2013-07-24 | QOS profile G12 unitedhealthgroup- 65173 | 214-647-4442 donald_r_osborn@uhc.com |  | 2/19- Kevin Mangene confirmed complete 5/15- Sent to Lori for inet and SAR. 5/21- pending SAR approval from AT&T 5/23- sent to Sharita 5/30- awaiting order to be assigned to provisioning 6/6- ASR sent; awaiting FOC date to be provided (8-10 BDs for Type 4) 6/13- Pending FOC date of July 15th 6/20- Pending FOC date of 7/15 6/27- Pending FOC date of 7/15 7/3- pending FOC date of 7/15 7/11- pending FOC date of 7/15 7/18- Dispatch scheduled for 2013-07-18 10:30:00.0 to install BEAS/NID and testing, question on handoff. 7/24- ready for activation; customer notified
2013-11-21 | ShaRita | HI750-02-IJ | 1132 Bishop Street, Suite 611, Honolulu, Hawaii 96813 | 12288 8xT1 t md5 UHGVERbgpbqZyofa | smartform 190070193 NSPE0007584677 IQBKTQFW | 6160999 | P2054748 | 5426291 | 6000 | BCBK33600001-8 | 82.HCGS.114798..HAWT Ckt1: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 1 pos 2 82.HCGS.114799..HAWT Ckt2: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 1 pos 3 82.HCGS.114800..HAWT Ckt3: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 1 pos 4 82.HCGS.114801..HAWT Ckt4: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 1 pos 5 82.HCGS.114802..HAWT Ckt5: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 1 pos 6 82.HCGS.114803..HAWT Ckt6: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 1 pos 7 82.HCGS.114804..HAWT Ckt7: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 1 pos 8 82.HCGS.114805..HAWT Ckt8: located inside room telco/elctro room at the 6th floor diamond head side. consecutively shelf 2 pos 1 of 4 shelf 2 1 of 4 Jack type rj48c not extended. Customer advised tech where circuit should be installed. he was guided by the customer. | 2013-12-16 | 12/26/2013 1/30/2014 | 2014-01-30 | bpdd |  | 2014-02-07 | unitedhealthgroup- 65290 | 763/694-7409, terry_bjorke@uhc.com |  | 12/2- order entered in Proquest, may need to get special approval. Sent to ShaRita 12/5- order submitted; pending provisioning approval. This request has been sent to Area Planner for capacity review. 12/12- awaiting confirmation from provisioning if capacity was approved from area planner 12/19- pending FOC date of 12/26 1/2- order on hold; pending site readiness CUSTOMER WILL NEED TO INSTALL A BACKBOARD AT THE DESIRED DEMARC LOCATION AND THEN HT WILL NEED TO RUN CABLE TO THE BACKBOARD. 1/9- order being supp'ed to have circuits installed in the 6th floor MDF, per John's request 1/16- Pending FOC date of 1/30 1/22- pending FOC date of 1/30 1/29- pending FOC date of 1/30 2/6- We were able to escalate dispatches on circuit 1 to 5 and 7 and was completed today; we got a best possible patching dispatch scheduled for circuits 6 and 8. Coordinating with Hawaiian LEC to test the other circuits to verify continuity up to the demarc. 2/6- ready for activation customer notifed 2/6- Terry confirmed circuit up
2014-01-15 | ShaRita | none | 9700 Bissonnet Avenue Suite 2500 Westwood Technology Center Houston, TX 77036 | disconnect | NSPE0007729401 OQBKVS19 |  |  |  |  | BCBH5W1X0001 |  |  |  |  | 2014-01-15 | 2014-02-13 | 2014-02-18 |  |  |  | 1/16- order submitted to sadisconnect 1/22- pending disconnect due date of 2/13 2/6- pending disconnect due date of 2/13 2/18- disconnect completed
2013-11-21 | B End | CN525-02-IJ | 1435 40th Avenue NE, Calgary, Alberta | 10M ethernet md5 UHGVERbgpbqZyofa RJ45 interface | 5405178 Port 5405179 Access |  |  |  | 1536 | [5 empty] | bpdd |  | 2014-02-17 | unitedhealthgroup- 64764 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com |  | 12/2- pending SOF 12/5- new SOF signed 12/12- pending order numbers 1/9- reaching out to B end account manager for order numbers. 1/16- BUILD IS NECESSARY. BUILD CHARGE CAD 5731.20 IS APPROVED BY CUSTOMER informed Telus to proceed on 1/10, pending dates. 1/27- pending lease, conduit. 1/28- John requested order to be cancelled. 2/6- pending order cancel completion 2/17- cancel complete
2013-08-07 | ShaRita | FL028-02-IJ | 6092 S Federal Hwy, Stuart FL 34997 | 10752 7xT1 with md5 UHGVERbgpbqZyofa | smartform 189948643 NSPE0007148829 IQBKPWQC | 6016137 | P2030784 | 5383623 | 1536 | BCBK2C0V0001-0007 | 60/HCGS/456610 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456611 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456612 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456613 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456614 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456615 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456616 /SB 1st fl cpu rm qdfr rj48x not extended lablelled | 8/15/2013 9/30/2013 1/16/2014 | 10/15/2013 10/18/2013 2/4/2014 | 2014-02-05 | bpdd | 2014-02-10 | 2014-02-07 | unitedhealthgroup-64556 | Deven Patterson 763-744-0696 deven_patterson@uhc.com | Activation scheduled for 2/26/2014 05:00:00 PM Central Time. Conference: 866-692-3158 pass code: 9236734 | 10/23- Order on customer hold; per ATT rep, their tech went on the customer's site last 10/18 but Lcon Charles needs to have a meeting with their engineer to know the requirements that needs to provide before they will do the order. They are also requesting to sup the order with a new due date once the customer is ready. 10/31- customer, Kevin Buckley, spoke with field tech to discuss conduit. tech will request BIC engineer to provide a drawing of were conduit is acutally needed. 11/6- Field tech provided 2 choices for conduit and termination of their facilities; awaiting customer to confirm which route will be taken. BIC Engineer will be providing the drawings AFTER we decide which option the customer prefers. 11/13- currently awaiting LEC to provide customer a BIC package. 11/20- per LEC PM BIC package will be sent to customer tomorrow, November 21st 11/26- awaiting customer to provide date conduit will be placed 12/5- customer, Kevin Buckley, is waiting to get approval from the landlord and hope to have that by the end of the week so he can have my contractor start next week on the conduit. Once he gets the approval he will provide an update. 12/11- order on hold; customer awaiting landlord approval to place conduit 12/19- pending site readiness 1/2- pending site readiness 1/9- customer received approval from the landlord and once he get the schedule from contractor doing the work he will provide update. The contractor is estimating 3 days to do the job. 1/16- requested new FOC date from LEC; conduit scheduled for install Wednesday January 15, 2014 through Friday January 17, 2014. 1/22- pending FOC date of 2/4 1/29- pending FOC date of 2/4 2/6- circuit delivered; pending testing 2/7- ready for activation; customer notifed 2/26- activation completed
2014-01-08 | B end | IR507-02-IJ | 5/9 South Frederick St. 3rd floor, Dublin 2, IRL | E1 2048 MD5 UHGVERbgpbqZyofa | OVI# 1-1273634284, Oppty: 1-L10DYI |  |  |  | 1536 | [5 empty] | bpdd |  |  | unitedhealthgroup-64950 | James Nalo Office +6(02)5884741/63 9297700576 aj_nalo@uhc.com |  | 1/21- pending SOF 2/20- Per John order is cancelled……
2013-08-07 | ShaRita | FL028-02-IJ | 6092 S Federal Hwy, Stuart FL 34997 | 10752 7xT1 with md5 UHGVERbgpbqZyofa | smartform 189948643 NSPE0007148829 IQBKPWQC | 6016137 | P2030784 | 5383623 | 1536 | BCBK2C0V0001-0007 | 60/HCGS/456610 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456611 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456612 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456613 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456614 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456615 /SB 1st fl cpu rm qdfr rj48x not extended lablelled 60/HCGS/456616 /SB 1st fl cpu rm qdfr rj48x not extended lablelled | 8/15/2013 9/30/2013 1/16/2014 | 10/15/2013 10/18/2013 2/4/2014 | 2014-02-05 | bpdd | 2014-02-10 | 2014-02-07 | unitedhealthgroup-64556 | Deven Patterson 763-744-0696 deven_patterson@uhc.com | Activation scheduled for 2/26/2014 05:00:00 PM Central Time. Conference: 866-692-3158 pass code: 9236734 | 10/23- Order on customer hold; per ATT rep, their tech went on the customer's site last 10/18 but Lcon Charles needs to have a meeting with their engineer to know the requirements that needs to provide before they will do the order. They are also requesting to sup the order with a new due date once the customer is ready. 10/31- customer, Kevin Buckley, spoke with field tech to discuss conduit. tech will request BIC engineer to provide a drawing of were conduit is acutally needed. 11/6- Field tech provided 2 choices for conduit and termination of their facilities; awaiting customer to confirm which route will be taken. BIC Engineer will be providing the drawings AFTER we decide which option the customer prefers. 11/13- currently awaiting LEC to provide customer a BIC package. 11/20- per LEC PM BIC package will be sent to customer tomorrow, November 21st 11/26- awaiting customer to provide date conduit will be placed 12/5- customer, Kevin Buckley, is waiting to get approval from the landlord and hope to have that by the end of the week so he can have my contractor start next week on the conduit. Once he gets the approval he will provide an update. 12/11- order on hold; customer awaiting landlord approval to place conduit 12/19- pending site readiness 1/2- pending site readiness 1/9- customer received approval from the landlord and once he get the schedule from contractor doing the work he will provide update. The contractor is estimating 3 days to do the job. 1/16- requested new FOC date from LEC; conduit scheduled for install Wednesday January 15, 2014 through Friday January 17, 2014. 1/22- pending FOC date of 2/4 1/29- pending FOC date of 2/4 2/6- circuit delivered; pending testing 2/7- ready for activation; customer notifed
2014-02-19 | ShaRita | none | 200-3333 Boulvevard Cote-Vertu Montreal, Canada PQ H4R2NI | disconnect | NSPE0007850859 5438186 5438187 | 6268966 |  |  |  | W0Y01894 |  |  |  |  | 2014-02-19 | 2014-04-22 | 2014-03-03 |  |  |  | 2/19- submitted disconnect request 2/27- ORDER TO DISCONNECT SENT TO TELCO (BELL) on 2/24 3/6- disconnect complete
2014-01-28 | ShaRita | none | 2904 Rodeo Park E Suite 300A Santa Fe, New Mexico 87505 | disconnect | NSPE0007774011 OQBKV120 |  |  |  |  | BCBJ07YW0001-5 |  |  |  |  | 2014-01-29 | 2014-02-27 | 2014-02-27 |  |  |  | 1/28- order submitted to sadisconnect 2/6- pending disconnect due date of 2/27 2/20- pending disconnect due date of 2/27 2/27- soft disconnect completed 3/6- disconnect complete
2013-12-06 | ShaRita | TN008-03-IJ | 113 Seaboard Ln Suite B-200, Franklin, TN 37067 | 20M PIP E RJ45, copper handoff md5 UHGVERbgpbqZyofa | Service Order 190076099 Order Request id 190075087 20156193 access 20156192 port |  |  | 5427609 | 10800 | E3000579 access C5000121 port | NV/L2XX/998711/ /TQW /ELK VZB DMARC: Customer backboard Data Room 2nd Flr Suite B 200 on cat 5 jack with XO ckt ID. | 12/11/2013 1/9/2014 | 2014-02-06 | 2014-02-06 | bpdd | 2014-02-13 | 2014-02-14 | unitedhealthgroup- 65115 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | scheduled for 3/18/2014 08:00:00 PM Central Time. Conference bridge: 866-692-3158 Pass code: 9236734 | 12/9- ShaRita submitted order. 12/11- ASR submitted; awaiting LEC to provide FOC date 12/19- awaiting LEC to provide FOC date 1/2- escalated to provisioning for feedback on FOC date 1/9- issue resolved and ASR re-sent 1/16- awaiting LEC to provide FOC date 1/22- Per LEC,XO, is saying that they went to the customer site to do a survey but the LCON Carla Powel is not aware of any service being delivered and is not going to allow any work by XO until she has details of what has been ordered. 1/28- pending FOC date of 2/6 2/6- loop delivered; pending testing 2/14- ready for activation; customer notified
2014-03-10 | ShaRita | HI015-02-IJ | 1132 Bishop Street, Suite 400, honolulu, HI | 20mg Ethernet with RJ45 handoff md5 UHGVERbgpbqZyofa extend to 4th floor telco room | OPP #O-0963891 |  |  |  | 8000 | [5 empty] | bpdd |  |  | UnitedHealthGroup-65290 | 763-694-7409 terry_bjorke@optum.com |  | 3/13- no ethernet capability in honolulu, checking to see if UHG can do TDM.
2014-02-11 | ShaRita | none | Letterkenney Business Park Lisnenan Letterkenney Co Donegal Ireland | disconnect | NSPE0007818733 5438000 | 6268963 |  |  |  | w0y12673 | [5 empty] | 2014-04-22 | 2014-03-21 |  |  |  | 2/11- waiting for Melissa to confirm if this is B-end 2/19- submitted disconnect request 2/27- CEASE SENT TO ENET 3/6- pending disconnect completion; standard interval due date 4/22 3/20- pending disconnect completion 3/24- disconnect completed 3/21
2014-02-19 | ShaRita | none | 4336 Equity Drive Columbus, OH | disconnect | NSPE0007850527 OQBKWK6D |  |  |  |  | BCBK2N1W0001 |  |  |  |  | 2014-02-19 | 2014-03-19 | 2014-03-21 |  |  |  | 2/19- order submitted to Sadisconnect 2/27- pending disconnect due date of 3/19 3/6- pending disconnect due date of 3/19 3/12- pending disconnect due date of 3/19 3/20- soft disconnect complete; pending hard disconnect 3/21- disconnect complete
2014-02-19 | ShaRita | none | 6150 Trenton Lane North Plymouth, MN 55442 | disconnect | NSPE0007850562 OQBKWK6F |  |  |  |  | BCBH92PC0001 |  |  |  |  | 2014-02-19 | 2014-03-19 | 2014-03-21 |  |  |  | 2/19- order submitted to Sadisconnect 2/27- pending disconnect due date of 3/19 3/6- pending disconnect due date of 3/19 3/12- pending disconnect due date of 3/19 3/20- soft disconnect complete; pending hard disconnect 3/21- disconnect complete
2014-02-19 | ShaRita | none | 1021 Windcross Court Franklin, TN 37067 | disconnect | NSPE0007850591 OQBKWK6G |  |  |  |  | BCBKJDXK0001 |  |  |  |  | 2014-02-19 | 2014-03-19 | 2014-03-21 |  |  |  | 2/19- order submitted to Sadisconnect 2/27- pending disconnect due date of 3/19 3/6- pending disconnect due date of 3/19 3/12- pending disconnect due date of 3/19 3/20- soft disconnect complete; pending hard disconnect 3/21- disconnect complete
2014-01-22 | ShaRita | AR003-02-IJ | 1 Allied Drive, Suite 2210, Little Rock AR | 9216, 6xT1 MD5 UHGVERbgpbqZyofa | Smartform 190120231 NSPE0007761328 IQBKVW71 | 6222917 | P2061821 | 5438621 | 1536 | BCBK4MP50001-6 | 63/HCGS/092930//SW DEMARC LOC: 14 SLOT MOUNT MUX CAB 2ND FLOOR SERVER ROOM 63/HCGS/092931//SW DEMARC LOC: 14 SLOT MOUNTING MUX RACK 2ND FLOOR DATA SERVER ROOM 63/HCGS/092932//SW DEMARC LOC: 2ND FLOOR DATA SERVER ROOM 14 SLOT MOUNT MUX RACK 63/HCGS/092933//SW DEMARC LOC: 2ND FLOOR DATA SERVER ROOM MUX RACK 14 SLOT MOUNTING 63/HCGS/092934//SW DEMARC LOC: 2ND FLOOR DATA SERVER ROOM MUX RACK 14 SLOT MOUNTING 63/HCGS/092935//SW DEMARC LOC: 2ND FLOOR DATA SERVER ROOM MUX RACK 14 SLOT MOUNTING Jack Type: RJ48C | 2014-01-27 | 2014-02-06 | 2014-02-12 | bpdd | 2014-02-13 | 2014-02-18 | unitedhealthgroup-64947 | 214-647-4442 donald_r_osborn@uhc.com | Activation scheduled for 3/17/2014 09:00:00 AM Central Time. Conference: 866-692-3158 pass code: 9236734 | 1/29- pending FOC date of 2/6 2/6- pending confirmation from LEC that circuit was delivered 2/7- Per LEC the circuits were not installed due to bad weather on this area. No tech is scheduled to work this out today still because of bad weather. Will follow up next week. 2/12- loop delivered; pending testing 2/18- escalated to provisioining to complete testing 2/20- ready for activation; customer notified
2014-02-19 | ShaRita | UFL88-08-CJ | 5908 Hampton Oaks Pkwy Tampa, FL 33610 | upgrade the following circuit in Tampa to 100M Circuit ID # BCBKYSWR0001 | smartform 190166232 INET 02241412 SAR 1-1UO7L8K, confirmation code 027QPM-001, exp 6/29/14. NSPE0007867584 CQBKWR4N access CQBKWR4P port | 6277901 | P1989898 port P1989674 access | 5331690 |  | EDBKYSJC0001 BCBKYSWR0001 | 69/KEGS/701213//GTES (access) Demarc Info: 1st Flr. rack-mounted, Rack 0193.08, mounting position 23B 69/VLXP/002430//GTES (virtual) installed the beas in the vzb rack shelf 3. tagged with circuit id. | 2014-03-03 | 2014-03-31 | 2014-03-31 | bpdd | 2014-04-14 | 2014-04-01 |  |  | Cutover scheduled for Monday, April 7th at 9:30pm CST/10:30pm EST. Conference: 866-692-3158 pass code: 9236734 | 2/20- pending approval for BAU 2/27- order submitted to order entry 3/6- ASR submitted; awaiting LEC to provide FOC date. 3/12- awaiting LEC to provide FOC date. 3/20- ASR encountered internal errors that have now been resolved; awaiting LEC to provide FOC date. 3/27- FOC date 3/31 4/1- ready for hotcut; customer notified
2014-01-21 | ShaRita | FL160-02-IJ | 3160 southgate Commerce Blvd, Orlando, FL 38206 | 10752 7xT1 MD5 UHGVERbgpbqZyofa | smartform 190122316 NSPE0007761362 IQBKVW61 | 6222886 | P2061814 | 5438615 | 1536 | BCBK4MPT0001-7 | 58/HCGS/788312//SB DEMARC LOC: 1FLR, STE-34, TELCO RM, CAB#1, SDEMARC LOC Continued: CAB#1, SLOT#8, TAG&GRD, NOT EXT 58/HCGS/788313//SB DEMARC LOC: 1FLR, STE-34, TELCO RM, CAB#1, SDEMARC LOC Continued: LOT#9, TAG&GRD, NOT EXT 58/HCGS/788314//SB DEMARC LOC: 1FLR, STE-34, TELCO RM, CAB#1, SDEMARC LOC Continued: LOT#10, TAG&GRD, 58/HCGS/788315//SB DEMARC LOC: 1FLR, STE-34, TELCO RM, CAB#1, S DEMARC LOC Continued: LOT#11, TAG&GRD, 58/HCGS/788316//SB DEMARC LOC: 1FLR, STE-34, TELCO RM, CAB#1, S DEMARC LOC Continued: LOT#12, TAG&GRD, 58/HCGS/788317//SB DEMARC LOC: 1FLR, STE-34, TELCO RM, CAB#1, S DEMARC LOC Continued: LOT#12, TAG&GRD, 58/HCGS/788318//SB DEMARC LOC: 1FLR, STE-34, TELCO RM, CAB#1, S DEMARC LOC Continued: LOT#14, TAG&GRD, | 2014-01-27 | 2/7/2014 3/3/2014 | 2014-02-27 | bpdd | 2014-02-14 | 2014-03-05 | unitedhealthgroup-65276 | 763-744-0981 glenn_moore@uhc.com |  | 1/29- pending FOC date of 2/7 2/6- pending FOC date of 2/7 2/18- order was placed on hold. Per telco rep, LCON is unavailable and they want to confirm the exact demarc. Requested a new due date. 2/20- pending new FOC date of 3/3 2/27- pending FOC date of 3/3 3/5- circuit ready for activation; customer notified
2013-11-21 | B End | SP504-04-IJ | Carrer del Cister 2 Barcelona 08022 Spain | 10M ethernet SOO to Letterkenny W0Y12673,md5 UHGVERbgpbqZyofa | s/o 5395175 OVI# 1-1274079001, Oppty: 1-L1K6WC |  |  |  | 3072 | W1A83113 | BCN/BCN/LE-157542 FLOOR:"1 ROOM:"COMMS CABINET:" ODF PANEL:" POS:"PANEL 1 POS 2 |  | 2013-02-24 | 2014-12-17 | bpdd | 2014-04-07 | 2014-01-06 | unitedhealthgroup- 65095 | 981-005-9326 pradeep_yadav@uhc.com |  | 12/2- signed SOF returned from UHG and sent for processing 12/12- COLT COMMITTED DATE IS FEBRUARY THE 24TH BUT THEY ARE DOING THEIR BEST TO DELIVER BY MID JANUARY. PLEASE, COULD YOU CONFIRM IF WE CAN DELIVER ASAP OR WE SHOULD WAIT UNTIL THE CDDD, PLEASE 1/2- awaiting confirmation that loop has been delivered and end to end testing completed 1/9- order ready but not closed due to currency. order ready for activation. engineer informed. 2/20- per B end currency is updated and billing should reflect correctly.
2014-03-11 | ShaRita | none | 3803 North Elm Street Greensboro, NC 27455 | disconnect | NSPE0007918165 OQBKW0BQ OQBKW0BY |  |  |  |  | BCBK1J5F0001 EDBK1DBN0001 |  |  |  |  | 3/10/2014 (standard 30 business days) | 2014-04-09 | 2014-04-14 |  |  |  | 3/11- order submitted to Sadisconnect 3/20- pending disconnect due date of 4/9 3/27- disconnect due date 4/9 4/3- due date 4/9 4/9- soft disconnect complete; pending hard disconnect 4/16- disconnect complete
2014-03-11 | ShaRita | none | 3803 North Elm Street Greensboro, NC 27455 | disconnect | NSPE0007918165 OQBKW0BN |  |  |  |  | BCBJ1G8B0001 |  |  |  |  | 3/10/2014 (standard 30 business days) | 2014-04-09 | 2014-04-14 |  |  |  | 3/11- order submitted to Sadisconnect 3/20- pending disconnect due date of 4/9 3/27- disconnect due date 4/9 4/3- due date 4/9 4/10- soft disconnect complete; pending hard disconnect 4/16- disconnect complete
2014-03-12 | ShaRita | none | 9395 S John Young Parkway Orlando, FL 32819 | disconnect | NSPE0007925475 OQBKW3QD |  |  |  |  | BCBK0W7M0001-0008 |  |  |  |  | 3/14/2014 (standard 30 business days) | 2014-04-10 | 2014-04-14 |  |  |  | 3/12- order submitted to Sadisconnect 3/20- pending disconnect due date of 4/10 3/27- disconnect due date 4/10 4/3- due date 4/10 4/10- pending soft disconnect; sent follow up email 4/16- disconnect complete
2014-03-12 | ShaRita | none | 2240 CAMPBELL CRK RICHARDSON, TX 75082 | disconnect | NSPE0007925493 OQBKW3F0 |  |  |  |  | BCBK0J5V0001-0008 |  |  |  |  | 3/14/2014 (standard 30 business days) | 2014-04-10 | 2014-04-14 |  |  |  | 3/12- order submitted to Sadisconnect 3/20- pending disconnect due date of 4/10 3/27- disconnect due date 4/10 4/3- due date 4/10 4/10- soft disconnect complete; pending hard disconnect 4/16- disconnect complete
2014-02-19 | ShaRita | C1561-02-IJ | 960 Macarthur Blvd. Mahwah, NJ 07495 | 50mg PPP RJ45 MD5 UHGVEReccgas4Usp9 | request 190160098 Service Order(s) [ 190169515 ] has been created for Order Request 190168352 access 20217157 port 20217156 |  |  | 5446976 | 10000 | Access E4000492 port C1002753 | .KEGS.309225..NJ Demark basement telco room, Overture 400 mounted in customers router rack, electrical port 1 tagged not extended, loop left on port 1. | 2014-02-26 | 2014-04-02 | 2014-04-02 | bpdd | 2014-04-09 | 2014-04-07 | UHGECC | 763-744-2265 travis_dent@optum.com | scheduled for 7pm CST Thursday, April 17th. Bridge: 866-692-3158 Pass code: 9236734 | 2/20- pending credit approval 2/27- pending site requirements to be completed; forwarded John EUCR form 3/6- pending site requirements to be completed; awaiting LEC to provide FOC date as well 3/12- pending FOC date of 4/2 3/20- pending FOC date of 4/2 3/27- FOC date 4/2 4/3- circuit delivered; pending testing 4/9- ready for activation; customer notified
2014-03-27 | B-end | none | Carrer del Cister, 2 Barcelona Spain 08022 | disconnect | NSPE0007950682 5460825 |  |  |  |  | w0z14768 |  |  |  |  | 3/21/2014 (standard 60 business days) | 2014-04-24 | 2014-04-24 |  |  |  | 3/27- disconnect submitted 4/3- disconnect due date 4/24 4/10- disconnect completion date 4/24 4/17- disconnect completion date 4/24 4/24- disconnect complete
2014-03-24 | ShaRita | none | 690 Asylum Street / North Plaza C-Level HARTFORD CT 06115 | disconnect | NSPE0007962481 OQBKXB8G |  |  |  |  | BCBKX8DT0001 |  |  |  |  | 3/21/2014 (standard 30 business days) | 2014-04-21 | 2014-04-23 |  |  |  | 3/24- order submitted to Sadisconnect 3/24- disconnect due date 4/21 4/3- due date 4/21 4/9- due date 4/21 4/17- due date 4/21 4/23- disconnect complete
2014-03-11 | ShaRita | none | JP Laurel National Highway Lipa City, Batangas 4721 Phillippines | disconnect | NSPE0007918426 5449107 | 6301220 |  |  |  | w0r46789 |  |  |  |  | 3/10/2014 (standard 60 business days) | 2014-05-12 | 2014-04-22 |  |  |  | 3/11- submitted disconnect request 3/20- LL DISCO REQUEST SENT TO PTT, PENDING ACK & EFFECTIVE DISCO DATE 3/27- THIS IS ACKNOWLEDGED. WILL PROVIDE THE QID REFERENCE ONCE DONE.. STOP BILL DATE: APRIL 19, 2014 4/3- pending disconnect due date from PTT 4/9- STOP BILL DATE: APRIL 19, 2014 4/22- disconnect completed
2014-02-12 | ShaRita | none | Unitech World Cyber Park Gurgaon 124980 IND | disconnect | NSPE0007825401 5444366 |  |  |  |  | w0z05855 | [5 empty] | 2014-04-26 | 2014-04-22 |  |  |  | 2/11- waiting for Melissa to confirm if this is B-end 2/19- request submitted to B-end for disconnect 2/27- Circuit- W0Z05855 Contract Expiry- Already Expired Last Bill Date- 14-Apr-14 Notice Period- 60 days 3/6- TEV IS OVER WITH LCON(PRADEEP YADAV) . ACCESS LINE DISCO ORDER SUBMITTED TO PTT 3/12- CUSTOMER-VZ LAST BILL DATE IS 14-APR-14. LOCAL LOOP WILL ALSO DISCONNECT ON SAME DATE. 3/20- pending disconnect completion 3/27- pending disconnect date 4/14 4/17- pending disconnect completion, There are still some pending ISD and fops task. 4/23- disconnect complete
2014-03-05 | Melissa | MN011-24-IJ | 1707 West Creek Lane, Chaska, MN 55318 | Add vrf to existing circuit PIP BOBKTD960001 384k | quote id 190183097 Order Number: 10156171 PVC ID: 5452983 (Automated Pre-Build) |  |  |  | 384 | [5 empty] | bpdd | n/a | 2014-03-10 | UnitedHealthGroup-IDN- 65400 | 763-744-0840 matt_f_seymour@optum.com |  | 3/6- melissa is working on order 3/10- PVC and configlet created. 4/24- per Steve B activated.
2014-03-12 | ShaRita | VA016-05-CJ | 3130 Fairview Park Drive Falls Church, VA 22042 | Upgrade port 3xT1, 4608 | NSPE0007935749 CWOrderID= 190192603 IQBKW2S8 OQBKW3DF | 6311341 | P2068824 | 1661775 | Upgrade to 1536 | BCBJPRCT0001-2 (out) BCBK44280001-3 (in) | 36.HCGS.001833..CD DEMARC LOC: Basement,Mtr,TEL RM,RJ48X,Y,N,SHELF,1,SLOT,16,Taged, DEMARC LOC Continued: Extended Wire (Yes or No): No Jack Type: RJ48C | 2014-03-18 | 2014-04-03 | 2014-04-03 | bpdd | 2014-04-10 | 2014-04-03 | unitedhealthgroup-64550 | 987-313-9388 anupam_datt@optum.com | Hotcut rescheduled for Wednesday, 5/1 at 730pm CST. Bridge: 866-878-8630 Pass code: 6653710 | 3/11- sent to ShaRita 3/20- pending FOC date of 4/3 3/27- FOC date 4/3 4/3- FOC date 4/3 4/3- ready for hotcut; customer notified
2014-03-25 | ShaRita | none | 113 Seaboard Ln Suite B- 200 Franklin TN | disconnect | NSPE0007970896 OQBKXFYJ |  |  |  |  | BCBKMYNW0001-0006 |  |  |  |  | 3/25/2014 (standard 30 business days) | 2014-04-24 | 2014-04-28 |  |  |  | 3/25- order submitted to Sadisconnect 3/27- sent email to Sadisconnect to process request 4/3- due date 4/24 4/9- due date 4/24 4/17- due date 4/24 4/23- pending soft disconnect; due date 4/24 5/1- disconnect complete
2014-01-15 | B End | none | Hiteccity 2 Building #H09 Gachibowli Village, Hyderabad Andhra Pradesh 500001, India | disconnect | NSPE0007724228 5418824 |  |  |  |  | w0z39250- 5072782 |  |  |  |  | 2014-01-14 | 2014-04-15 | 2014-04-26 |  |  |  | 1/16- request submitted to APAC disconnects 1/22- pending disconnect due date of 4/15 CONTRACT EXPIRY - CONTRACT EXPIRED ETF (IF APPLICABLE) - NOT APPLICABLE CUSTOMER NOTICE PERIOD - 60 DAYS LAST BILL DATE - 15-MAR-2014 2/6- pending disconnect due date of 4/15 3/3- last bill date will be march 15 4/3- PTT SERVICE REQUEST NUMBER IS SR_17669351 DATE OF DISCONNECTION IS 18-APR-2014 4/9- DATE OF DISCONNECTION IS 18-APR-2014 4/17- DATE OF DISCONNECTION IS 18-APR-2014 4/24-billing triggered. 5/1- disconnect complete
2014-02-17 | ShaRita | C1395-08-IJ | 4400 Westown Parkway West Des Moines, IA 50266-6756 | 100M - Needs to be 50M Ethernet RJ45 handoff MD5 UHGVEReccgas4Usp9 access type 1 | Service Order(s) [ 190167827 ] has been created for Order Request 190166558 access 20216199 port 20216198 DSM I0001071 ea-lpv6-lpv6-0012 |  |  | 5446755 | 1536 | C1002747 E4000484 | ea-lpv6-lpv6-0012 building lpv6 loc 1 building 7 basement floor telco room ISG5K 100.1.3:1.3 |  |  |  | bpdd | 2014-03-10 | 2014-04-02 | UHGECC- 65487 | 763-744-2082 eric_taylor@optum.com | activation scheduled for 5/7 at 5pm CST Bridge: 866-878-8630 Pass code: 6653710 | 2/20- pending credit approval 2/27- sent email to provisioning to approve order as soon as possible and to submit ASR to LEC 3/6- Site survey set for 3/7 3/12- Tech pending confirmation of design before being dispatched. Couldn't find assigned BEAS 3/20- BEAS wired up, pending testing 3/27- BEAS wired up, pending testing 4/3- ready for activation; customer notified
2014-03-27 | ShaRita | MN053-72-IJ | 14100 Business Center Drive, Elk River(SR 3) to 1707 West Creek Lane, Chaksa MDF 700 (m6l7,01) Single mode fiber hand off, SC connector type | Verizon 10Gb ROADM circuit between Elk River, MN SR#(LLM8/07) and Chaska, MN MDF700 (M6L7, 01). It will be 10Gb LAN Phy unprotected circuits. Single mode fiber hand off, SC connector type. | NSPE0007989775 s/o 5461608 MIN-I35625 CCR#1204885 (complete) | 6337287 |  |  |  | W1B07116 | JX-LLM8-M6L7-0010 Demarc: M6L7,01 Customer MDF-700 room LC Fiber panel: ak707. FB3. A5 loopback and tagged with both ckt id. Demarc: LLM8,07 Customer SR3 room LC Fiber panel: A0361. FB6 E1 loopback and tagged with both ckt id. |  |  |  | bpdd | 2014-06-25 | 2014-04-23 |  | Steve Brown | Steve confirmed active on 5/15/2014 | 4/2- being reviewed by local provisioning 4/10- PENDING CCR#1204885 WITH FAD DATE OF 05/12/14 CURRENT QUEUE/OWNER : EQUIP RECD / OPS-I MATERIALS ARE EXPECTED TO DELIVER BY FRI 4/11/2014 VIA FEDEX 4/17- CCR 1204885 complete , circuit dmarced, pending RFC testing 4/23- order closed to billing
2014-03-27 | ShaRita | MN053-73-IJ | 14100 Business Center Drive, Elk River(SR 1) , llm8,06 to 1707 West Creek Lane, Chaksa MDF 800 Single mode fiber hand off, SC connector type | Verizon 10Gb ROADM circuit between Elk River, MN SR 1 (llm8,06) and Chaska, MN MDF800 (m6l7, 02). It will be 10Gb LAN Phy unprotected circuits. Single mode fiber hand off, SC connector type. | NSPE0007989775 S/O PORT: 5460696 MIN-I35623 CCR #: 1204525 | 6338310 |  |  |  | W1B06892 | JX-LLM8-M6L7-0009 Demarc: M6L7,02 MDF-800 room Customer LC fiber panel: AJ807 FB3 B7 Loopback and tagged with both ckt id Demarc: LLM8,06 SR1 room Customer LC patch panel: A0161 FB6 B4 Loopback and tagged with both ckt id |  |  |  | bpdd | 2014-06-24 | 2014-04-23 |  | Steve Brown | Steve confirmed active on 5/15/2014 | 4/2- CCR #: 1204525 created 10g card add on roadm.bb (llm8,06 and m6l7,02) , RFT 5/8 4/10- CHECKED PENDING CCR# 1204525 FOR LOCAL ORDER MIN-I35623 CURRENT QUEUE/OWNER : EQUIP RECD / OPS-I GLOBAL TRACKING STATUS : ENGINEERING COMPLETE WITH RFT DATE: 05/08/2014 4/17- transponder card installed and dmarc posted, pending CCR closure after certification and testing, circuit design and testing 4/23- order closed to billing
2014-05-08 | ShaRita |  | 4425 E COTTON CENTER BLVD, PHOENIX, AZ 85040 | remove the WAN analysis feature | order request 190268070 Service Order 190268123 has been Submitted for Provisioning 20295756 port | [9 empty] | bpdd | 2014-05-19 | 2014-05-14 |  |  |  | 5/8- request submitted to provisioning 5/14- request completed
2014-04-07 | ShaRita | none | 1001 Winstead Drive / Suite 200 CARY NC USA 27513 | disconnect | NSPE0008018698 OQBKXN7W |  |  |  |  | BCBJLPM40001 - 6 |  |  |  |  | 4/11/2014 (standard 30 business days) | 2014-05-07 | 2014-05-09 |  |  |  | 4/7- order submitted to Sadisconnect 4/10- disconnect due date 5/7 4/17- disconnect due date 5/7 4/23- disconnect due date 5/7 5/1- disconnect due date 5/7 5/8- soft disconnect complete 5/14- disconnect complete
2014-04-07 | ShaRita | none | 500 Enterprise Drive ROCKY HILL CT USA 06067 | disconnect | NSPE0008019290 OQBKXN8C |  |  |  |  | BCBKWD170001-6 |  |  |  |  | 4/11/2014 (standard 30 business days) | 2014-05-07 | 2014-05-12 |  |  |  | 4/7- order submitted to Sadisconnect 4/10- disconnect due date 5/7 4/17- disconnect due date 5/7 4/23- disconnect due date 5/7 5/1- disconnect due date 5/7 5/8- soft disconnect complete 5/14- disconnect complete
2014-04-07 | ShaRita | none | 2800 Hutton Ave FARMINGTON NM USA 87402 | disconnect | NSPE0008019423 OQBKXQYX |  |  |  |  | BCBKVY640001-3 |  |  |  |  | 4/11/2014 (standard 30 business days) | 2014-05-07 | 2014-05-09 |  |  |  | 4/7- order submitted to Sadisconnect 4/10- disconnect due date 5/7 4/17- disconnect due date 5/7 4/23- disconnect due date 5/7 5/1- disconnect due date 5/7 5/8- soft disconnect complete 5/14- disconnect complete
2014-04-14 | ShaRita | none | L7, 70 Pirie Street Adelaide Australia SA 5000 | disconnect | NSPE0008042552 5469511 | 6382770 |  |  |  | W0X83262 |  |  |  |  | 4/16/2014 (standard 60 day interval) |  | 2014-05-09 |  |  |  | 4/14- disconnect submitted 4/17- order accepted; moved to provisioning 4/23- EMAILED AUSTRALIA PROVISIONING ASKING FOR AN UPDATE. 5/1- pending Field Operations task 5/8- Order moved to PTT 5/14- disconnect complete
2013-10-23 | ShaRita | USC05-05-IJ | 2 Independence Point Suite 100 Greenville, SC 29615 | 100Mb Type 4 Premium Ethernet Access MRC - $2,352 (provided by AT&T), SAR for both options is 1-1S4PY7I, CONFIRM, exp date 1/5.iNet CP37314.00, PER 10231311. RJ45 handoff md5 encryption UHGVERbgpbqZyofa | Smartform 190027175 NSPE0007442302 IQBKSLQS (EACS) IQBKSLY7 (PORT) | 6120069 | P2047720 | 5415951 | 44992 | BCBK3JHL0001 EDBK3JDD0001 | 30/KQGN/401218//SB VZB DMARC: FIRST FLOOR MAIN DATA ROOM, IN TELCO RACK 8TH SPACE FROM FLOOR. LABELED AND MARKED FOR CUSTOMER | 2013-10-24 | 2013-12-09 | 2014-01-06 | bpdd | 2014-01-13 | 2014-01-10 | unitedhealthcare-64908 | 763/694-7409, terry_bjorke@uhc.com |  | 11/26- Per AT&T, Order has a major build, build ecd is 11/30/13 with an foc of 12/9/13. Also, awaiting customer site readiness; sent pending requirement to John 12/5- awaiting customer site readiness 12/11- awaiting site readiness, Per John, The requirements will need to wait until after our network freeze. The work should be complete by the middle of Feb. 12/19- pending site readiness 1/2- Per LEC circuit has been delivered. Requested a tag and locate, customer unable to find circuit. 1/9- Beas installation scheduled for 1/10 1/10- ready for activation; engineer notified
2014-05-06 | B end | PH510-01-IJ | Building O, UP North Science and Techno Park, Commonwealth, Quezon City, Philippines Building ) | 100M Ethernet Fiber SX Handoff SOO to W0X83226 Melbourne MD5 UHGVERbgpbqZyofa |  |  |  |  | 30000 | [5 empty] | bpdd |  |  | UnitedHealthGroup-65260 | plus 632-588-4651 noemi.joy_gomez@uhc.com |  | 5/12- pending SOF 5/16- SOF provided to UHG to sign, need to correct address 5/19 revised SOF sent to UHG 5/20- per john cancel
2013-11-26 | ShaRita | UWI28-07-IJ | 2725 Mall Drive, Eau Claire, WI 54701 | 150mg PIP E Multimode Fiber LC handoff md5 UHGVERbgpbqZyofa | Request id 190067528 order number 190067769 20153488 access 20153487 port |  | 190067769 | 5425315 | 22000 | C5000166 port E4000235 access | 42/OBGS/100091//WT 3rd Bay from entrance Door. Middle shelf, labeled VZB. Patched to Southwall fiber panel | 2013-12-24 | 2014-02-18 | 2014-02-18 | bpdd | 2014-02-25 | 2014-03-14 | unitedhealthgroup- 64534 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | ShaRita is checking on SFP card activation scheduled for 5/27 at 3pm CST bridge 866-692-3158 pass code 9236734 | 12/2- Siva submitted via RD 12/5- order submitted; pending provisioning approval 12/12- unable to OPS-Approve due to stuck issue. IT is aware of this issue and is currently fixing it. Until this is resolved, that's the only time we can work on the order. Will assign the provisioner once the issue is resolved. 12/19- still stuck 1/2- pending FOC date of 2/18 1/9- pending FOC date of 2/18 1/16- pending FOC date of 2/18 1/22- pending FOC date of 2/18 1/29- pending FOC date of 2/18 2/6- pending FOC date of 2/18 2/20- loop delivered; pending BEAS install and RFC testing 2/27- dispatch for mux message HUGB556 at site DNG, is complete, however as per tech notes: Will need to investigate the LD x-connect on FUDNGGIL-0036. 3/6- cross connect issue resolved; escalated to BNE to complete testing of circuit 3/12- beas installation/rfc testing dispatch scheduled for 3/13
2014-04-14 | ShaRita | none | L7, 70 Pirie Street 5430 Data Court /Suite 200 ANN ARBOR MI USA 48108 | disconnect | NSPE0008042618 OQBKXV6W |  |  |  |  | BCBJ62XH0001-8 |  |  |  |  | 4/16/2014 (standard 30 business day interval) | 2014-05-14 | 2014-05-19 |  |  |  | 4/14- order submitted to Sadisconnect 4/23- disconnect due date 5/14 5/1- disconnect due date 5/14 5/8- disconnect due date 5/14 5/14- sent email to provisioning asking when soft disconnect will done; pending response 5/22- disconnect complete
2013-10-24 | ShaRita | MN011-07-IJ | Address: 1707 West Creek Lane Chaska MN USA 55318 Technical contact: Jimmie Skaggs | order for a new 10G internet circuit with a 1G port/commit. Please provision on ROADM SMF/LC to MSP3 protected line side. 2 fiber, terminate to m6l7/01, mdf700. IP Capacity Inquiry #9CWQEX9Q | smartform 190033040 NSPE0007463990 bid SFDC Opportunity ID O-0864524 u327321 Engagement Script ID: ES-00113453 IQBKVKF4 CCR# 1195074 MIN I35469 | 6126309 |  |  |  | u327321 PLBK4HHN0001 | jx-73c-m6l7-0001 DEMARC VIA Y CABLE: AJ807 FB3 B-5 ( This is a LC customer patch panel B Row set 5). THis is M6l7,02 (MDF-800) main floor. |  |  |  | bpdd | 2014-02-14 | 2014-03-28 |  | Jim Skaggs. |  | 11/20- the firm order request was sent out Thursday, November 14, 2013. Comments: We can support this 10GigE at MSP3 with router upgrade and card install. Please allow 8-10 weeks for completion once firmed order is received. 12/5- pending augmenting card to the existing router 12/5- order can not be done as port only and needs a complex solutions bid. Working with Matt B on that. 12/11- order on hold pending approvals 12/19- order on hold pending approvals 12/31- order on hold pending approvals 1/2- Received approvals from the complex bid; approval ES-00113453. Requesting order be removed from hold. 1/9- Fiber panel info: MSP3 Panel: 1 Channel: 27/28 MSP3:12.42:1 12.42 1/16- pending card augmentation and GW outer info 1/23- This order has been assigned to GW3.MSP3 GigabitEthernet3/0/0. No longer waiting for a card augment. 1/29- waiting for the card augment and EPL portion is being provisioned. 2/6- waiting for the card augment and EPL portion is being provisioned. pending CCR to be created. 2/18- pending CCR# 1195074. waiting for the equipment to be delivered by this week and then installed. Once installed will begin working on the builds. 2/20- Transponder cards installed, Phil is working on provisioning them into the ROADM systen 2/21- sup requested to change mdf to 800 2/27- moved cards to m6l7,02 3/6- provisioning is working on resolving issue with path 3/12- pending MUX, patch wire between the port and the local network 3/20- MUX revised and wired. dispatch complete. need to ping test. 3/27- ping test scheduled tonight, March 27th at 7pm CST with customer 4/3- ready for activation; customer notified
2014-05-21 | ShaRita | none | 5515 North Service Road / Suite 203 Burlington ONTARIO CANADA L7L 6G4 | disconnect | NSPE0008175120 5488413 5488414 | 6438529 |  |  |  | W0Y39363 (port) W0Y39364, W0Y39365 |  |  |  |  | 5/23/2014 (standard 60 calendar days) | 2014-07-21 | 2014-05-29 |  |  |  | 5/22- submitted to OE 5/29- disconnect complete
2014-05-08 | ShaRita | none | 41 Rue Des Fontanot / 6th Floor NANTERRE FRANCE FRANCE 92000 | disconnect | NSPE0008126811 s/o 5483747 s/o 5483740 | 6426347 |  |  |  | W0V57558 W0V57559 W0V57560 |  |  |  |  | 5/9/2014 (standard 60 business days) | 2014-07-13 | 2014-05-26 |  |  |  | 5/8- submitting request for disconnect to OE 5/14- disconnect submitted to provisioning 5/22- pending disconnect 5/29- disconnect complete
2014-02-25 | Melissa | n/a | Letterkenney Business Park / Lisnenan LETTERKENNY / CO. DONEGAL IRELAND |  | NSPE0007872109 INQ2014031102129 |  | 5451647 |  |  | W0T52119 / UIE200380 | [5 empty] | 2014-05-24 | 2014-05-25 |  |  |  | 4/29- disco due on 5/24 5/29- disco completed 5/24
2014-03-03 | ShaRita | AK010-05-CJ | 310 K Street - 7th Floor, Anchorage, AK 99501 | Upgrade to 4608, 3xT1 | Ecost Circuit: 7564156 smartform 190186324 NSPE0007916853 5449843 5449844 5449845 IQBKW1XJ | 6300188 | P2045994 | 5423041 | 768 | MGBK3DWH0001/0002 MGBK3DWH0003 W1A72823 access W1A72824 access W1A72836 port | GCI T1 Circuit id: HC/165362 DEMARC IS AT THE SERVER ROOM PATCH PANEL 8, TAGGED AND LABELED | 2014-03-17 | 2014-04-04 | 2014-04-02 | bpdd | 2014-05-13 | 2014-04-03 | UnitedHealth Group-TCW 65446 | 860-702-8284 keith_mangene@uhc.com | Cutover rescheduled for 5/30 at 6pm CST. Conference bridge information will be: Conference Bridge: 866-878-8630/international dial-in 001-203-369-8013 Conference Pass Code: 6653710 | 3/6- circuit ids validated from John. Melissa working on order 3/12- order submitted to provisioning, was pending ecost 3/20- pending PTT to provide FOC date 3/27- FOC date 4/4 4/3- FOC date 4/4 4/9- ready for cutover; customer notified
2014-03-12 | ShaRita | n/a | 10400 Business Center Dr, Elk River, MN SR3 | New 10 Gig Protected appearance between ELR Server Room 3 (LLM8/07) and 511 (511/20.) | NSPE0007962955 S/O: 5457036 MIN-I35610 ccr 1203861 | 6322236 |  |  |  | W1B05870 | jx-llm8-511-0001 |  |  |  | bpdd | 2014-06-18 | 2014-04-22 |  |  | requested for 6/5 at 10pm central | 3/20 Melissa created tin 3/27-order over to local design 4/3- pending ccr 1203861 current queue I-Pak Created / RE,Equip Recd / OPS-I with rft date of 05/05/14. 4/10- pending ccr 120386 rft date of 05/05/14. 4/17- ccr complete; pending node work to be complete before proceeding with end to end testing 4/22- order closed to billing
2014-03-12 | ShaRita | n/a | 10400 Business Center Dr, Elk River, MN SR3 to MN33E01 (511) | PIPO Port change BOBKTFPX0001 to Y-CABLE drop side FDB demark: Y-Cable 113.04.A1 set 3 F ports SR 3 | CQBKX5KM | 6406035 | P1932463 | [12 empty] | requested for 6/5 at 10pm central | 4/28- tin submitted 5/8- pending hotcut
2014-03-12 | ShaRita | n/a | 10400 Business Center Dr, Elk River, MN SR1 | New 10 Gig Protected appearance between ELR Server Room 1 (LLM8/06) and Cologne (73c.) | NSPE0007962955 S/O: 5457056 MIN-I35609 ccr 1203856 | 6322678 |  |  |  | W1B05846 | JX-LLM8-73C-0001 |  |  |  | bpdd | 2014-06-18 | 2014-04-17 |  |  |  | 3/20 Melissa created tin 3/27-order over to local design 4/3- pending ccr 1203856 current queue I-Pak Created / RE, Equip Recd / OPS-I with rft date of 05/05/14. 4/10- pending ccr 1203856 rft date of 05/05/14. 4/17- ccr complete; RFC testing scheduled for today 4/22- order closed to billing
2014-03-12 | ShaRita | n/a | 10400 Business Center Dr, Elk River, MN SR1 change to Y-CABLE drop side FDB demark: Demarc: FDB 10.26.2, jacks 3/9 | pipo change BOBKWHD00001 Colgone to SR1 | CQBKX5KS | 6410324 | P1957529 | [13 empty] | 4/30- tin sumbiteed 5/8- pending mux work 5/14- pending hotcut
HOT & ESCALATED 1/30/2014 | HOT & ESCALATED ShaRita | C1356-05-IJ | 9180 Commerce Circle, Highlands Ranch, CO 80129 | 200M ethenet, RJ45 handoff with MD5 UHGVEReccgas4Usp9 94 Ethernet shaping | Service Order(s) [ 190134050 ] has been created for Order Request 190133283 20190201 access 20190197 port | 190134050 |  | 5440920 | 10000 | E5000069 access C5000523 port | 24/KXGS/119371//ACSO 1st floor data room , cage # 66 , century link rack , shelf 1 , optical port 4. ****Verizon/BEAS DMARC**** = BEAS IS RACK MOUNTED IN VERIZON CABINET #1 OF 6 IN CAGE 66 IN RELAY RACK UNIT34 all is labeled | 2/3/2014 3/28/2014 | 3/11/2014 4/28/2014 | 2014-04-28 | bpdd | 3/18/2014 6/2/2014 | 2014-06-02 | UHG-ECC-65502 | 763-744-2082 eric_taylor@uhc.com | ****ACTIVATION FAILED AND BEING ESCALATED TO BE RESOLVED**** scheduled for 6/3 at 6pm CST Conference Bridge 866-692-3158 Pass code 9236734 | 2/6- ASR submitted, awaiting LEC to provide FOC date 2/20-pending FOC date of 3/11 2/27- pending FOC date of 3/11 3/6- pending FOC date of 3/11 3/12- circuit not delivered; LEC advised that there is a redesign needed. Pending new FOC date to be provided. 3/20- Asked John to confirm handoff type. Centurylink tech went out to install on this and was told by the end user they wish to have a single mode fiber handoff. 3/27- John confirmed to move forward with electrical handoff; awaiting LEC to provide FOC date 4/3- pending FOC date; escalated per John's request 4/10- per John supp order to change handoff to SMF LC 4/17- pending FOC date 4/23- FOC date 4/28 5/1- circuit delivered; pending beasinstallation/rfc testing 5/8- email sent to dispatch to schedule beas installation/rfc testing asap 5/14- pending demarc extension then tech will be re-dispatched for beas installation 5/22- pending demarc extension then tech will be re-dispatched for beas installation 5/28- demarc extension completed; escalating to get a date for bea installation. John advised that end user needs service up Friday, BEAS scheduled for Monday. 6/2 6/2- ready for activation; customer notified
2014-03-27 | B-end | none | 9th Floor /Block B LAXMI CYBER CITY Kondapur Hyderabad India | disconnect | NSPE0007962400 5459905 5459906 |  |  |  |  | W0Y16220 W0Y16216 W0Y16217 W0Y16218 |  |  |  |  | 3/21/2014 (standard 60 business days) | 2014-06-23 | 2014-06-02 |  |  |  | 3/27- disconnect submitted 4/3disconnect due date 6/23 4/10- disconnect completion date 6/23 4/17- disconnect completion date 6/23 4/18- disco due 5/21 4/23- PENDING Field operations 5/1- pending Field operations 5/8- pending Field operations 5/14- pending Field operations 5/22- WAITING FOR RELATED ORDER TO BE READY FOR DISCONNECTION S/O: 5459906 5/28- PROGRESSED TO ANOC STATUS TO TRIGGER BILLING. 6/2- disconnect complete
2013-11-13 | ShaRita | PA012-07-IJ | 1001 Brinton Road , Pittsburgh, PA 15221 | New 100M Ethernet type 2 premium with Multimode fiber LC connector, MD5 UHGVERbgpbqZyofa SAR is 1-1SEE1DF (100BaseFX), approval 026VWI-001, exp 3/18/14, iNet CP38005.00 PER 11131309. | smartform 190052106 NSPE0007531864 EACS IQBKS939 port IQBKS95Z | 6146246 | P2052376 EACS P2052391 PORT | 5423021 | 30000 | EDBK3XSC0001 EACS BCBK3XS40001 PORT | 15/KEGS/306998 /PA VZB DMARC: basement fiber demarc, mounted in rack 102.09 HANDOFF TYPE: Electrical | 2013-11-18 | 12/24/2013 1/9/2014 | 2014-01-09 | bpdd | 2014-01-28 | 2014-01-22 | unitedhealthgroup-65225 | 987-313-9388 anupam_datt@uhc.com | Activation rescheduled for 6/11 at 930 pm CST Bridge Number: 866-692-3158 pass code: 9236734 | 11/20- ASR submitted; awaiting LEC to provide FOC date 11/26- awaiting LEC to provide FOC date 12/5- pending FOC date of 12/24 12/11- pending FOC date of 12/24 12/19- order on hold; customer will not allow access for placing or splicing until 1/3 1/3- Order on hold due customer's unavailability. customer will not allow access for placing or splicing until 1/3 1/9- Order on hold due customer's unavailability 1/16- beas installation scheduled for 1/22 at 830am EST 1/22- ready activation; customer notifed
2013-10-03 | ShaRita | UMO15-07-IJ | 13655 Riverport Drive, Maryland Heights, MO 63043 | 100M Type 4 Premium Ethernet Access Multi-mode handoff (SX) with MD5 UHGVERbgpbqZyofa | smartform 190004392 NSPE0007366076 IQBKR4C9 EACS IQBKR40H PORT | 6095067 | P2044399 EACS P2044560 PORT | 5410702 | 30000 | EDBK29X30001 EACS BCBK298B0001 PORT | 41/KRGN/703406//SW DMARC: first florr electric phone room by the loading doc TELCO BOARD handoff:-media pannel pos 1 and 2 multimode. | 2013-10-09 | 2013-11-07 | 2013-11-19 | bpdd | 2013-11-22 | 2013-11-22 | unitedhealthgroup- 64678 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | Activation rescheduled for 6/5 at 2pm CST Bridge Number: 866-692-3158 pass code: 9236734 | 10/4- sent to OM. 10/10- ASR sent; awaiting LEC to provide FOC 10/16- pending FOC date of 11/7 10/23- pending FOC date of 11/7 10/31- pending FOC date of 11/7 11/6- pending FOC date of 11/7 11/14- received feedback from customer and also spoke with dispatch tech. supp'ed order to reflect correct equipment, AC. And advised tech to install overture in the MDF room if it will not cause any delays. If it will cause delays asvised to install at the MPOE as we do all other orders unless requested otherwise from UHG. 11/20- dispatch to install beas scheduled for 2013-11-22 3pm 11/22- ready for activation; customer notified
2014-05-08 | ShaRita | none | 4 Gateway Center / Suite 400 / 100 Mulberry Street NEWARK NJ USA 07102 | disconnect | NSPE0008125693 OQBKYB8S |  |  |  |  | BCBK10PG 0001-6 |  |  |  |  | 5/9/2014 (standard 30 business days) | 2014-06-09 | 2014-06-11 |  |  |  | 5/8- disconnect submitted to Sadisconnect 5/14- pending disconnect 5/22- pending disconnect 5/29- pending disconnect 6/5- pending disconnect due date 6/9 6/12- disconnect complete
2014-01-22 | ShaRita | TN017-02-IJ | 7105 Moores Lane, Brentwood, TN 37027 *customer needs early April" | 50M Ethernet MD5 UHGVERbgpbqZyofa RJ45 handoff, dport DCAR | Order Request # 190121034 Service Order ID : 190122192 20183133 access 20183132 port |  |  | 5438541 | 11056 | C5000464 port E4000358 access | T4/KQGN/822967//SC VZB DMARC: installed overture in cust 1st flr comp/telco room rack mounted HANDOFF TYPE: Electrical | 1/30/2014 2/28/2014 | 6/25/2014 5/16/2014 | 2014-05-16 | bpdd | 2014-06-10 | 2014-06-04 | unitedhealthgroup-64911 | 214-647-4442 donald_r_osborn@uhc.com | scheduled for 6/17 at 12pm CST | 2/27- still pending ASR transmission; pending SAR info 3/6- ASR submitted; awaiting LEC to provide FOC date 3/13- awaiting LEC to provide FOC date; Per latest update from the assigned AT&T Rep. Kelly, she is still waiting on downstream to send dates for the scope work involved. This may take some time. The Engineer has to check facilities and see what needs to be done. FOC will be sent as soon as she gets it. 3/20- Per LEC ,still waiting on dates (scope of work involve) from TSC group. According to LEC, this process normally takes 2 weeks and it has only been one week. 3/27- FOC date 6/25; LEC has to place 2000 feet of fiber 4/3- FOC date 6/25 Scope of work: Complex build to place approximately 6.4 kf of fiber, several splices required, place equipment, test and turn up. ECD=5/1, ESD=6/25. The CDDD=6/25 which is the FOC date. 4/10- FOC date 6/25; ticket open in attempt to improve date 4/17- FOC date 6/25; Closely monitoring this order for possible improvement of FOC. As per AT&T PM, We are still pending permit approval. there’s a lot involved with this job. The 5/23 ESD is an improvement in the due date and is based on receiving the permit. 4/9: ECD=5/16, tentative ESD=5/23 based on approval of city permit for lane closures. We also have environmental issues at this location. We may be required to pump and haul our waste water out of these manholes to another location for storage and testing prior to disposal 4/23- Estimated complete date 05/16; estimated service delivery 05/23 due date improvement. pending permit approval for lane closures. 5/1- tentative due date improve 05/23 still depends on the permit approval 5/8- pending FOC date 5/16 5/14- pending FOC date 5/16 5/16- circuit delivered; pending demarc extension prior to beas installation 5/22- escalating for BEAS install 5/28- extension completed; pending date for beas installation 6/4- ready for activation; customer notified
2014-02-28 | B End | UIR01-09-CJ, | Letterkenney Business Park / Lisnenan LETTERKENNY / CO. DONEGAL IRELAND | add dport and upgrade to 70mg | s/o 5463059 |  |  |  |  | W1A68428 |  |  |  |  | bpdd |  |  |  | none listed |  | 3/6- pending SOF 3/27- SOF over to B end. Pending order info. 4/3- order validated and sent to provisioning 4/17- ASKED CUSTOMER FOR MAINTANANCE WINDOW AND ASKED ALSO SARKA IF ITS PORT UPGRA DE TO 100 AND DYNAMIC PORT TO 60 WITH DCAR 4/24- escalting with B end. 5/8- confirming ready to schedule, pat moran. Anupam is the enginner 5/14- pat Moran is working on a change window. 5/22- still working on window. May have to credit the 700 after hours fee 5/29- we will work on crediting after hours fee, Melissa is verifying when this is re-scheduld hotcut completed 6/2
2014-04-07 | B-end | none | Commerzon e K Raheja Private Ltd Survey No 144 & 145 Off. Airport Road / Yerwada Pune India India 411 006 | disconnect | NSPE0008018641 s/o 5492158 |  |  |  |  | w0y66519 |  |  |  |  | 4/11/2014 (standard 60 calendar days) | 2014-08-25 | 2014-06-15 |  |  |  | 5/21- sent a follow up email to APAC termination 5/22- OVI order has been raised for this disconnect order, however we are waiting for billing advise in order to proceed raising F&E disconnect order. 5/29- all info to billing pending disconnect set date 6/5- PTT LAST BILL DATE: 1-JULY-2014 6/11- circuit disconnected; ASR closed 6/18- disconnect complete
2014-05-08 | ShaRita | none | Joachimstal er Str 10-12, Berlin, Germany | disconnect | NSPE0008127143 5482632 | 6426349 |  |  |  | W0Y33796 |  |  |  |  | 5/9/2014 (standard 60 business days) | 2014-07-14 | 2014-06-16 |  |  |  | 5/8- submitting request for disconnect to OE 5/14- pending disconnect 5/22- pending disconnect 5/29- pending disconnect 6/5- pending disconnect due date 7/14 6/12- pending disconnect due date 7/14 6/18- disconnect complete
2014-05-21 | ShaRita | none | 3431 N. Windsor Drive Aurora, CO 80011 | disconnect | NSPE0008174839 OQBKYM4K |  |  |  |  | BCBJYSJ60001 |  |  |  |  | 5/23/2014 (standard 30 business days) | 2014-06-19 | 2014-06-23 |  |  |  | 5/21- disconnect submitted to Sadisconnect 5/29- disconnect due date 6/19 6/5- disconnect due date 6/19 6/11- disconnect due date 6/19 6/18- emailed provisioning to complete soft disconnect 6/24- disconnect complete
2014-05-21 | ShaRita | none | 4203 Town Center Boulevard Eldorado Hills, CA 95762 | disconnect | NSPE0008174938 OQBKYRRH |  |  |  |  | BCBJ20PF0001 |  |  |  |  | 5/23/2014 (standard 30 business days) | 2014-06-19 | 2014-06-23 |  |  |  | 5/21- disconnect submitted to Sadisconnect 5/29- sent email to Sadisconnect requesting order information 6/5- disconnect due date 6/19 6/11- disconnect due date 6/19 6/18- emailed provisioning to complete soft disconnect 6/24- disconnect complete
HOT & ESCALATED 11/26/2013 | HOT & ESCALATED ShaRita | IL016-05-IJ | 4205 Westbrook Drive, Aurora IL 60504 | 20M PIP E RJ45, copper handoff md5 UHGVERbgpbqZyofa | Request id 190072950 service order number Id 190074263 20155561 access 20155560 port |  |  | 5427118 | 4608 | C5000155 port E3000598 access | /HFGS/809316//LB DMARC Info: L5pk is the new patch panel in bay 1.04.shelf 3 ports 11/12 it is labeled with the circuit id both the jx and the W. | 1/15/2014 2/28/2014 5/8/2014 | 4/17/2014 5/1/2014 5/22/2014 | 2014-05-22 | bpdd |  |  | unitedhealthgroup- 65253 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | activation scheduled for July 8th at 8pm CST Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 3/20- pending FOC date of 5/1 3/27- FOC date 5/1 4/3- FOC date 5/1 4/10- FOC date 5/1 4/17- new lcon needed; Received email from Matus. Lec supervisor, that This order is not on track with due date 5/1. Order remains on hold because customer is unresponsive. To move forward with order, They need good LCON. Please send supp with good LCON contact information so the BIC engineer can contact LCON without trouble. Will address this issue. 4/24- provisioning is coordinating with ATT regarding the latest status of the order 5/1- new FOC requested. As per AT&T Lec, Order was on hold because the contact information for customer was not correct. This caused delay for their OSP department. Per network PM, this issue has been cleared and they are in touch with the LCON. However, delay is still there and supp is needed to clear the CN/R. I asked for the specific delay that it had caused the order, he responded with this, “Delay was caused because of the wrong contact information for your LCON. Our BIC engineer could not reach LCON. This situation caused delay in the plan of work of our OSP department. We’ll need supp to schedule new due date for circuit delivery.” 5/8- pending FOC date 5/14- FOC date 5/22 5/22- FOC date 5/22 5/28- circuit delivered; currently we are troubleshooting an LOS (loss of signal) issue and then we will dispatch for the beas installation, we have a tech scheduled to look a the LOS issue. Once LOS is resolved beas installation and end to end testing 6/5- escalating to have beas installation scheduled ASAP, likely to dispatch on 6/6 6/10- ready for activation
2014-06-04 | ShaRita | none | 10 Tara Blvd, Nashua NH 03062 | disconnect | NSPE0008221855 OQBKYZQ7 |  |  |  |  | BCBKH1V70001-6 |  |  |  |  | 6/9/2014 (standard 30 calendar days) | 2014-07-10 | 2014-07-07 |  |  |  | 6/4- disconnect submitted to Sadisconnect 6/11- disconnect due 7/10 6/18- disconnect due 7/10 6/25- disconnect due 7/10 7/3- disconnect due 7/10 7/9- disconnect complete
2014-06-04 | ShaRita | none | 1118 S. Orange Ave, Suite 201, Orlando FL 32806 | disconnect | NSPE0008221091 OQBKY0JN |  |  |  |  | BCBK2CJW0001-7 |  |  |  |  | 6/4/2014 (standard 30 calendar days) | 2014-07-03 | 2014-07-08 |  |  |  | 6/4- disconnect submitted to Sadisconnect 6/11- disconnect due 7/3 6/18- disconnect due 7/3 6/25- disconnect due 7/3 7/3- disconnect due 7/3 7/9- disconnect complete
2014-05-29 | ShaRita | none | 201 Pennsylvani a Avenue / 3rd Floor CHARLEST ON WV USA 25302 | disconnect | NSPE0008198374 OQBKY1DH OQBKY7WN |  |  |  |  | BCBJF9570001-2 |  |  |  |  | 5/30/2014 (standard 30 calendar days) | 6/30/2014 7/2/2014 | 2014-07-07 |  |  |  | 5/29- disconnect submitted to Sadisconnect 6/5- sent follow up email to Sadisconnect to move forward with request 6/11- disconnect due 6/30 6/18- emailed Sadisconnect manager to request the correct order number for disconnect request; order number provided was for a different request. order number OQBKY7WN disconnect due date 7/2 6/25- disconnect due 7/2 7/2- soft disconnect complete, 7/2 7/9- disconnect complete
2014-05-29 | ShaRita | none | 5701 Katella Avenue CYPRESS CA USA 90630 | disconnect | NSPE0008198342 OQBKY1DH |  |  |  |  | BCBJ9TPG0001 |  |  |  |  | 5/30/2014 (standard 30 calendar days) | 2014-06-30 | 2014-07-08 |  |  |  | 5/29- disconnect submitted to Sadisconnect 6/5- sent follow up email to Sadisconnect to move forward with request 6/11- disconnect due 6/30 6/18- disconnect due 6/30 6/25- disconnect due 6/30 7/2- soft disconnect complete, 7/1 7/9- disconnect complete
2014-03-24 | ShaRita | TX038-05-IJ | 5859 Farinon Drive, San Antonio, TX 78249 | 100mg ehernet with dport john will throttle down to 15mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd extend to floor 1 mdf | SFDC Opportunity ID O-0976291 Quote ID: 190210564 Order Request [ 190211533 Service Order(s) [ 190213522 20244423 access 20244422 port | 190213522 |  | 5461700 | 5008 | E4000647 C1003782 | 31/KQGN/651997//SW | 2014-03-28 | 2014-06-16 |  | bpdd |  |  | UnitedHealthGroup-65044 | 860-702-8284 keith_mangene@optum.com |  | 3/25- pending MDF room info 4/2- pending site requirements; sent to John 4/10- pending site readiness; FOC date 6/16 4/17- pending site readiness; FOC date 6/16 4/23- pending site readiness; FOC date 6/16 5/1- pending site readiness 5/8- pending site readiness 5/14- pending site readiness 5/22- pending site readiness 5/29- pending site readiness 6/5- pending site readiness 6/11- pending site readiness 6/19- pending site readiness 6/25- pending site readiness 7/2- per John sounds like this order will be cancelled, as this site will be closing. Pending official cancellation 7/8- order supped to cancel per instruction from John. Order complete cancelled.
2014-03-05 | ShaRita | UGA09-05-IJ | 3720 Davinci Court, Norcross GA 30092 | 50 mg Ethernet dport, John will throttle down to 20. rJ45 copper handoff md5 UHGVERbgpbqZyofa | The Quote ID is 190182474. Service Order(s) [ 190186578 ] has been created for Order Request 190184524 20228464 access 20228463 port | 190186578 |  | 5453002 | 5392 | E4000561 C1003289 | 38/KQGN/611574//SB VZB DMARC: 3rd fl server rm, Overture400 on telco backboard below HANDOFF TYPE: Electrical | 3/10/2014 5/6/2014 6/3/2014 | 4/28/2014 5/20/2014 6/25/2014 | 2014-06-23 | bpdd | 5/5/2014 7/11/2014 | 2014-06-30 | unitedhealthgroup-64578 | 91 91600 84400 harish_kandpal@optum.com | scheduled 7/17/2014 8:00:00 PM Eastern Time Bridge Number: 866-692-3158 Passcode: 9236734 | 3/6- melissa is working on order 3/12- pending LEC to provide FOC date 3/20- pending site survey to be scheduled 3/27- pending confirmation from LEC that site survey has been completed 4/3- asked John for a contact that is able to make decisions in regards to the order with the LEC BIC engineer 4/10- LEC PM is working with BIC engineer for updates 4/17- FOC date 4/28 4/23- FOC date 4/28 5/1- loop not delivered; customer is not ready. As per AT&T, the pull string broke and they were unable to pull their fibers thru the customer’s conduit. End user will need to have this fix before they can proceed. 5/6- conduit issue resolved; pending new FOC date 5/8- new FOC date 5/20 5/14- FOC date 5/20 5/22- Per LEC received call from field advising that end user now needs a pull string in conduit to complete turn-up. Please advise when end user will have pull string so we can complete turn-up. 5/28- waiting on John to advise that pull string is in place in conduit 6/5- pull string is in place; pending FOC 6/25 6/11- FOC date 6/25 6/18- FOC date 6/25 6/25- FOC date 6/25 6/26- circuit delivered pending beas on 6/30 between 8am and 12:10pm 7/2- ready for activation; customer notified
2014-06-10 | ShaRita | none | 14100 Business Center Drive ELK RIVER MN USA 55330 | disconnect | NSPE0008236250 s/o 5501099 s/o 5501100 |  |  |  |  | W0Z47185 W0Z47164 |  |  |  |  | 6/10/2014 (standard 30 calendar days) | 2014-07-09 | 2014-07-16 |  |  |  | 6/9- disconnect submitted VZB FULL DISCO OPTION 1 AND 2 6/18- disconnect due date 7/9 6/25- disconnect due date 7/9 7/3 -disconnect due date 7/9 7/9- sent follow up email to provisioning for update. update: TCOMS order 5501099 is for MIN O0033355 and 5501100 is for MIN O0033379 that have 7/11 FOC. We will work them on 7/11 7/17- disconnect completed
2014-06-03 | ShaRita | none | 2 Independen ce Point / Suite 100 GREENVIL LE SC USA 29615 | disconnect | NSPE0008211041 OQBKYYRD |  |  |  |  | BCBJ28KY0001 |  |  |  |  | 6/3/2014 (standard 30 calendar days) | 2014-07-02 | 2014-07-16 |  |  |  | 6/3- disconnect submitted to Sadisconnect 6/11- disconnect due 7/2 6/18- disconnect due 7/2 6/25- disconnect due 7/2 7/2- pending soft disconnect on order 7/9- there was a provisioning delay on order; emailed provisioning asking when soft disconnect will be completed, pending response. 7/16- disconnect complete
2014-05-21 | ShaRita | none | 15 Blue Street / Suite 3 / Level 1 NORTH SYDNEY AUSTRALIA AUSTRALIA NSW 2060 | disconnect | NSPE0008175244 5488331 | 6438533 |  |  |  | W0W11910 |  |  |  |  | 5/23/2014 (standard 60 calendar days) | 2014-07-21 | 2014-07-10 |  |  |  | 5/22- submitted to OE 5/29- pending LCON verification 6/5- A/W TERMINATION. 6/11- A/W TERMINATION. 6/18- A/W TERMINATION. 6/25- Order will be disconnected on July 4th 7/3- Order will be disconnected on July 4th 7/10- email sent to assigned provisioner regarding the ASSOCIATED BEARER DISCO S/O: 5496906 for this order. Once The bearer is close will disconnect SO: 5488331 7/10- disconnect complete
2014-03-24 | ShaRita | UOH09-05-IJ | 9050 CENTRE POINTE DR, West Chester, OH 45069 | 100mg ehernet with dport john will throttle down to 15mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd extend to Floor 4 MDF | SFDC Opportunity ID O-0976410 Quote ID: 190211584 Order Request [ 190212900 ] Service Order(s) [ 190213787 20244561 access 20244560 port cin-I0008162 | 190213787 |  | 5461734 | 5008 | E4000651 C1003807 | c5-2df-2df-0017 17/OBGS/107963/TWCS | 2014-04-01 | 2014-06-06 |  | bpdd | 2014-06-13 | 2014-07-09 | UnitedHealthGroup-64621 | 860-702-8284 keith_mangene@optum.com |  | 3/25- pending MDF room info 4/2- being reviewed by local provisioning 4/10- pending FOC date 4/17- PM informed they found that we need to complete an augment for capacity. The operations manager has placed an est. 4/30/2014 completion date on this circuit. 4/23- Pending augment for capacity 5/1- As per TW telecom, order is currently in Jeopardy status due to inventory issue. There is an equipment they need that they are still waiting for available stocks. Karen our PM assign is working to get that equipment ASAP. 5/8- requested an update from LEC on their inventory issue; pending response 5/14- tw telecom has received the approval on the PA and has ordered the required equipment. Operations manager is currently looking at a 6/6/2014 completion date; asked provisioning to confirm if 6/6 is the estimated FOC date. Pending response 5/22- FOC date 6/6 5/28- FOC date 6/6 6/5- FOC date 6/6 6/12- pending confirmation if circuit was delivered or missed 6/18- circuit delivered 17/OBGS/107963/TWCS is located on positions 1&2 on the brand new TW fiber panel on the fourth floor. MUX dispatch was cancelled due to some patching issue with LEC. Apparently there was some confusion with the demarc. Our provisioner already sent an email to the customer project manager to have it reviewed. They already had it forwarded to their Field Ops team. 6/25- Called TW Telecom to check the status of tag and located and foud out that it was done. However there's still an issue with the demarc that it is why they have to go out again on site to finish the job. 7/2- TW Tech went out to tag and locate circuit and had to move the handoff at 312 PLUM ST CINCINNATI, OH 45202 7/8- order supped to cancel per instruction from John; pending cancellation completion
2014-04-25 | ShaRita | NY025-02-IJ | 30 Flatbush Ave., Brooklyn, NY 11217 New site need by end of June | 1536, T1 MD5 UHGVERbgpbqZyofa | SFDC Opportunity ID O-1005150 Quote ID: 190255870 order request id 190255911 Service Order(s) [ 190260127 ] has been created for Order Request 190255911 20285293 access 20285292 port | 190260127 |  | 5475121 | 1280 | C0001474 D1003603 | 32/HCGS/824366 /NY P2 DEMARC=RJ48C SLOT 1OF 2 SUB BASEMENT INSIDE TELEPHONE ROOM LCON=LARRY DOUGLAS PHONE=646 423-3718 JACK TYPE=RJ48C | 4/30/2014 6/24/2014 | 6/18/2014 8/12/2014 7/15/2014 | 2014-07-15 | bpdd | 6/23/2014 8/15/2014 | 2014-07-17 | unitedhealthgroup-65259 | 763/694-7370, masroor_khan@uhc.com | Per Masroor, activated on 7/21 | 4/25- pending quote from Siva 4/29- sent to ShaRita 5/1- pending FOC date 5/8- FOC date 6/18 5/14- FOC date 6/18 5/22- FOC date 6/18 5/29- FOC date 6/18 6/5- FOC date 6/18 6/12- FOC date 6/18 6/18- asked provisioning to confirm with LEC if circuit was installed 6/25- FOC date 8/12 due to COPPER PLACING;PLACE AND SPLICE 2W HDSL 7/2- FOC date 8/12. Escalation ticket created This order is currently in circuit design. Email sent to regional o see if order can be improved 7/9- Current status: The circuit install is scheduled for 7/15 commitment date. We will see if this can be dispatched before then but we cannot be for sure that can happen. Next step: Tet and turn up of the DS1. 7/16- circuit delivered. ready for activation. customer notified
2013-12-10 | ShaRita | NJ023-02-IJ | 333 Thornall Street, Edison, NJ 08837 | 3072, 2xT1 md5 UHGVERbgpbqZyofa | Service Order 190079847 Request Id 190078109 access 20157874 port 20157873 |  |  | 5428303 | 1280 | N1000548,N1000547 access C3000498 port | .HCGS.821491..NJ DEMARC LOC: BLDG MAIN telco sh 1 pos 1 DEMARC LOC Continued: Extended Wire (Yes or No): N Jack Type: RJ48C .HCGS.821492..NJ DEMARC LOC: BLDG MAIN telco sh 1 pos 2 DEMARC LOC Continued: Extended Wire (Yes or No): No Jack Type: RJ48C | 2013-12-13 | 2013-12-27 | 2013-12-27 | bpdd | 2014-01-03 | 2013-01-03 | unitedhealthgroup- 65298 | 763/694-7370, masroor_khan@uhc.com |  | 12/11- request submitted; pending provisioning appproval 12/19- pending FOC date of 12/27 1/2- loop delivered; pending testing 1/3- circuit ready for activation; engineer notified
2014-06-05 | ShaRita | NJ023-05-CJ | 333 Thornall Street, Edison, NJ 08837 | Change - Upgrade port 4608, 3xT1 Add 1 T1 to existing bundle | O-0889964 Quote ID: 190316737 Order Request 190326741 Order Request 190326741 / In order Service Order 190333993 Order Request 190333994/ Out order Service Order 190333986 20354820 in 20354819 in 20354867 out 20354866 out | 190333993 in 190333986 out |  | 5494439 | 1300 | N1003819,N1003818,N1003817 in access C0003658 in port N1000548,N1000547 access C3000498 port | .HCGS.828398..NJ DEMARC LOC: Ground,mn,TEL RM,RJ48C,N,N,OTHER,na,OTHER,na,1st fl sj 8p15 DEMARC LOC Continued: hbl 1 p4 no ex Extended Wire (Yes or No): No Jack Type: RJ48C HCGS.828399..NJ DEMARC LOC: Ground,mn,TEL RM,RJ48C,N,N,OTHER,na,OTHER,na,1st fl mn telco DEMARC LOC Continued: sj 8 p16 hbl Extended Wire (Yes or No): No Jack Type: RJ48C .HCGS.828400..NJ DEMARC LOC: Ground,mn,TEL RM,RJ48C,N,N,OTHER,na,OTHER,na,1st fl sj 9p16 DEMARC LOC Continued: hbl 1 p 6 no e Extended Wire (Yes or No): No Jack Type: RJ48C | 6/20/2014 6/30/2014 | 2014-07-11 | 2014-07-11 | bpdd | 2014-07-08 | 2014-07-15 | unitedhealthgroup- 65298 | 763/694-7370, masroor_khan@uhc.com | scheduled for 7/22 at 6pm CST Conference Bridge 866-878-8630 pass code 6653710 | 6/10- pending ticket S9673337 6/19- ShaRita is working on submitting order request to provisioning 6/25- confirmed to provisioning that we want to reuse existing access and install new. Provisioning is working on re-design and re-submission of ASR to LEC for FOC date 7/2- FOC date 7/11 7/9- FOC date 7/11 7/15- ready for activation. customer notified
HOT & ESCALATED 5/6/2014 | HOT & ESCALATED ShaRita | AZ002-05-IJ | 3003 Central Ave, Phoenix, AZ 85012 | Upgrade to 4xT1, 6144 | CW order ID 190286749 NSPE0008170721 IQBKYN6G (in) OQBKYP53 (out) PHX-I0024193 | 6440362 | P2076609 (in) P1872052 (out) | 3234479 | 1376 | BCBKM2S60001-003 out BCBK5P0J0001-0004 in | 13-W5J-AJI-0001Extended the T1 from 4U3,3033 N Central, Basement, Krone Jack Pair 13 to the Customer in AJI, 3003 N Central, Suite 800, Server Room, Rack 1, Ver izon Router Shelf 38, T1 # 4, Hard Looped & Tagged.---- | 2014-05-30 | 2014-06-13 |  | bpdd |  | 2014-07-15 | unitedhealthgroup-64676 | 763/694-7370, masroor_khan@optum.com | Wednesday, July 23, 2014 7:00 Conference Bridge 866-878-8630 pass code 6653710 | 5/20- sent to ShaRita 5/22- ShaRita is working submitting order 5/29- order submitted; pending provisioning approval 6/5- FOC date 6/13 6/12- FOC date 6/13 6/18- missed loop ticket has been opened. Escalated to provisioning to provide an expected delivery date asap 6/25- tech went onsite to extend circuit 6/26- dispatch for cross connects scheduled for 6/27 7/2- dispatch rescheduled for tomorrow for cross connects; ESCALATED TO UPPER MANAGEMENT 7/10- provisioining completed the redesign. management escalated to have circuit delivered and tested 7/16- circuit ready for activation; customer notified
2014-02-17 | ShaRita | AZ018-02-IJ | 4129 E. Van Buren St Phoenix, AZ 85008 | 100M - Needs to be 50M Ethernet RJ45 handoff MD5 UHGVERbgpbqZyofa | request 190158235 order id 190166464 Service Order(s) [ 190167772 ] has been created for Order Request 190166464 access 20216136 port 20216135 |  |  | 5446752 | 10000 | access E4000483 port C1002825 | 14/KXGS/124240//ACSO VZB DMARC: rack 4, ru 40. HANDOFF TYPE: Optical | 2014-02-28 | 2014-03-28 | 2014-03-18 | bpdd | 2014-04-04 |  | unitedhealthgroup-65014 | 860-702-8284 keith_mangene@optum.com | activated with Tauoa on 7/25 | 2/20- pending credit approval 2/27- sent email to provisioning to approve order as soon as possible and to submit ASR to LEC 3/6- pending FOC date of 3/28 3/12- pending FOC date of 3/28 3/20- circuit delivered; pending beas installation 3/27- tech not able to find circuit during beas dispatch;tag and locate requested from Century Link 4/3- waiting for customer to extend demarc from 2nd floor to 3rd floor since LEC can only deliver up to the MPOE 4/10- Security provided access to the 2nd fl common area electrical rm located behind the elevators. The correct 3750 in this room already has customers on it. A new cat5 cable will have to be run from this rm to the customers mdf, approx 200 feet through the ceiling and terminated behind rack 4. Once this is done by end user we will install the beas. 4/17- order on hold due to customer requirements 4/23- order on hold due to customer requirements 5/1- Pending customer extension. 5/8- Pending customer extension. 5/14- requested tag and locate for customer 5/22- end user was able to locate circuit; Pending customer requirements. Security provided access to the 2nd fl common area electrical rm located behind the elevators. The correct 3750 in this room already has customers on it. A new cat5 cable will have to be run from this rm to the customers mdf, approx 200 feet through the ceiling and terminated behind rack 4. It's extended. 5/28- pending date for beas installation 6/3- ready for activation; customer notified
2014-06-20 | ShaRita | none | 3803 North Elm Street Greensboro NC 27455 | disconnect | NSPE0008281657 OQBKZCQY |  |  |  |  | bcbh5y9y0001 |  |  |  |  | 6/20/2014 (standard 30 calendar days) | 2014-07-17 | 2014-07-22 |  |  |  | 6/21- disconnect submitted VZB FULL DISCO OPTION 1 AND 2 6/26- pending order number and disconnect due date 7/3- disconnect due date 7/17 7/9- disconnect due date 7/17 7/17- pending soft disconnect 7/23- disconnect complete
2014-06-20 | ShaRita | none | 2725 Mall Drive EAU CLAIRE WI USA 54701 | disconnect | NSPE0008281729 OQBKZGFT |  |  |  |  | bcbjdphh0001 |  |  |  |  | 6/20/2014 (standard 30 calendar days) | 2014-07-17 | 2014-07-21 |  |  |  | 6/21- disconnect submitted VZB FULL DISCO OPTION 1 AND 2 6/26- pending order number and disconnect due date 7/3- disconnect due date 7/17 7/9- disconnect due date 7/17 7/17- pending soft disconnect 7/18- soft disconnect issued 7/23- disconnect complete
2014-06-20 | ShaRita | none | 2725 Mall Drive EAU CLAIRE WI USA 54701 | disconnect | NSPE0008281729 OQBKZCR6 |  |  |  |  | BCBKW1SG0001 |  |  |  |  | 6/20/2014 (standard 30 calendar days) | 2014-07-17 | 2014-07-23 |  |  |  | 6/21- disconnect submitted VZB FULL DISCO OPTION 1 AND 2 6/26- pending order number and disconnect due date 7/3- disconnect due date 7/17 7/9- disconnect due date 7/17 7/17- pending soft disconnect 7/23- disconnect complete
2014-06-20 | ShaRita | none | 2441 Warrenville Road LISLE IL USA 60532-3642 | disconnect | NSPE0008281758 OQBKZC5R |  |  |  |  | bcbj0jkt0001 |  |  |  |  | 6/20/2014 (standard 30 calendar days) | 2014-07-17 | 2014-07-22 |  |  |  | 6/21- disconnect submitted VZB FULL DISCO OPTION 1 AND 2 6/26- pending order number and disconnect due date 7/3- disconnect due date 7/17 7/9- disconnect due date 7/17 7/17- soft disconnect issued 7/23- disconnect complete
2014-06-03 | ShaRita | none | 6150 Trenton Lane Plymouth MN 55442 | disconnect | NSPE0008216561 Request 49641436 u292053 OQBKZKKD |  |  |  |  | u292053 |  |  |  |  | 6/3/2014 (standard 30 calendar days) | 2014-07-03 | 2014-07-23 |  |  |  | 6/3- disconnect submitted to VZB FULL DISCO OPTION 4 6/6- disconnect due 7/3 6/11- disconnect due 7/3 6/8- disconnect due 7/3 6/18- disconnect due 7/3 6/25- disconnect due 7/3 7/3- disconnect due 7/3 7/9- There’s a system issue for this order. Ticket has been escalated. 7/17- Order will be completed on Friday, 7/18/2014. 7/23- disconnect complete
2014-03-24 | ShaRita | UTX10-05-IJ | 5800 Granite Parkway, Plano TX 75024 | 100mg ethernet with dport john will throttle down to 50mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd extend to Floor 9 MDF | SFDC Opportunity ID O-0976289 Quote ID: 190207220 order request 190212844 Service Order(s) [ 190213755 20244541 access 20244540 port DAL I0094967 | 190213755 |  | 5461732 | 5008 | E4000653 C1003843 | c5dif l8x 0001 14/OBGS/874712//SW 9th fl server room telco backboard labeled with both ck ids. | 2014-04-04 | 2014-04-18 | 2014-05-08 | bpdd | 4/25/2014 6/27/2014 |  | UnitedHealthGroup-64539 | 860-702-8284 keith_mangene@optum.com | 7/29 at 9pm CST Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 3/25- pending MDF room info 4/2- pending order to be stepped to local provisioning 4/10- requested an alternate lcon from John 4/17- FOC date 4/18 4/23- loop not delivered, AT&T having issues with fiber. Signals that are leaving the ATM switch is not reaching the premise. Engineers are working on it but no ETA yet. 5/1- per ATT Manager, the job to extend fiber was completed. Escalating to LEC for FOC date. 5/8- fiber issue has been completed, pending new FOC date from LEC 5/14- circuit delivered; pending demarc extension from telco closet to MDF room 5/22- pending demarc extension from telco closet to MDF room 5/28- pending demarc extension from telco closet to MDF room, interduct should be installed 5/30. 6/5- demarc extension completed; pending beas installation and end to end testing 6/10- need access to install beas, Donald Osborne will need to open access ticket but is OOO til 6/16 6/18- pending beas installation to be scheduled 6/26- ready for activation; customer notified
2014-04-29 | ShaRita | C1346-06-IJ | Connextions- 3534 Mercy Dr, Orlando, FL 32808, changed to 3600 E Commerce Place | 100mg Ethernet with RJ45 handoff | opp id O-1007831 Quote ID: (190256587) Order Request 190257680 Service Order 190259914 has been Submitted for Provisioning 20291607 port 20291608 access new Quote ID: 190280628 new order Request 190281235 New Service Order 190281244 20305592 access 20305591 port | 190259914 |  | 5477401 | 30000 | C1005119 E4001011 | 58/KQGN/702111//SB Demarc: 1st floor telco room relay rack 01101.1A unit 1 Cienna 3930 handoff on port 1 tagged with ckt id and not extended | 2014-05-19 | 6/27/2014 6/19/2014 | 2014-06-19 | bpdd | 2014-07-07 | 2014-06-26 | Connextions- 65220 (will be migrated to UnitedHealthGroup) | 407-926-2400 x10390 jose.hanachi@connextions.com | Thursday, July 31, 2014 6:00 AM-7:00 AM Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 5/1- pending order submission 5/8- pending FOC date 5/14- Per LEC correct address is 3600 E Commerce Place. Order will have to be cancelled and reissued with correct address. 5/22- pending FOC date 5/29- FOC date 6/27 6/5- FOC 6/27 6/12- improved new FOC 6/19 6/18- pending confirmation circuit delivered 6/25- circuit delivered; beas installation completed. pending RFC testing 7/2- ready for activation; customer notified
2014-04-29 | ShaRita | TX169-06-IJ | Connextions- 2220 Campbell Creek, Richardson, TX 75082 | 100mg Ethernet with RJ45 handoff | opp id O-1007831 Quote ID: (190256587) Order Request 190257680 Service Order 190259896 has been Submitted for Provisioning 20291598 access 20291597 port Quote ID O-1052296 (change) Quote ID: 190350515 (change) Service Order(s) [ 190355433 ] has been created for Order Request 190354080 20372366 port | 190259896 190355433 |  | 5477393 5477394 | 30000 | C1004787 E4000903 | 14/KQGN/879997//SW VZB DMARC: 1st fl server room RR.3 rack position 43 labeled with both ids HANDOFF TYPE: Electrical | 2014-05-07 | 2014-05-23 | 2014-05-23 | bpdd | 2014-06-02 | 2014-06-06 | Connextions- 65228 (will be migrated to UnitedHealthGroup) | 407-926-2400 x10390 jose.hanachi@connextions.com | can turn up when needed Activations scheduled on July 31st from 12am CST to 4am CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | ticket S9430258 ssrc-escalation-request@one.verizon 5/1- pending order submission 5/8- pending FOC date 5/14- FOC date 5/23 5/22- FOC date 5/23 5/29- circuit delivered; pending beas installation and end to end testing 6/5- beas installed; pending end to end testing 6/12- circuit ready for activation; customer notified 6/18- notification was not sent to customer last week. although circuit is ready for activation there is an issue that provisioning has to resolve for failed PVC. escalating to have issue resolved 6/25- change order being submitted to remove PVC 7/3- change order submitted to remove 2nd PVC; pending provisioning approval 7/9- Opened defect 5912 to fix issue in Op-EVC-Assign-Design-In-VDDS task. 7/17- issue escalated to provisioning and defect ticket escalated 7/30- PVC issue resolved 7/31- activation completed
2014-04-29 | ShaRita | FL037-06-IJ | Connextions- 9395 S John Young Pkwy, orlando, FL 32819 | 100mg Ethernet with RJ45 handoff | opp id O-1007831 Quote ID: (190256587) Order Request 190257680 Service Order 190259955 has been Submitted for Provisioning access 20291626 port 20291625 change opp id O-1053410 change Quote ID: 190362347 change Order Request 190370129 Service Order(s) [ 190373244 ] has been created for Order Request 190370129 20389680 port | 190259955 190373244 |  | 5477403 5477404 | 30000 | C1004781 E4000907 | 58/KQGN/702068//SB DEMARC LOC: 1ST FLR DATA CENTER WALL MOUNT TAG'D | 2014-05-06 | 2014-06-04 | 2014-06-04 | bpdd | 6/11/2013 6/20/2014 |  | Connextions- 65229 (will be migrated to UnitedHealthGroup) | 407-926-2400 x10390 jose.hanchi@connextions.com | can turn up when needed Activations scheduled on July 31st from 12am CST to 4am CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 5/1- pending order submission 5/8- pending FOC date 5/14- FOC date 6/4 5/22- FOC date 6/4 5/29- FOC date 6/4 6/5- circuit delivered; asked John to confirm demarc: 1st Floor Data Center. 6/12- asked Jose to confirm demarc 6/18- Jose confirmed demarc; Order is pending for line testing and then will be stepped for beas installation 6/25- pending beas installation and rfc testing. a change order will have to be submitted to correct the PVC issue once order is completed 7/2- pending beas installation and rfc testing. 7/9- beas dispatch scheduled for 7/10 7/17- ready for activation. change order submitted to remove 2nd PVC; pending provisioning approval 7/24- Ticket S9898071 was requested to fix the issue in vdds. 7/31- Activation complete
2013-11-07 | ShaRita | UCA56-07-IJ | 3515 Harbor Blvd Costa Mesa, CA 92626 | 100M access, 100M port (john wil throttle to 60 afte install) Rj45 interface. Md5 UHGVERbgpbqZyofa 100Mb Type 4 Premium Ethernet Access | smartform 190045879 NSPE0007512038 IQBKS8C6 EACS IQBKS84V PORT | 6142387 | P2052133 EACS P2052274 PORT | 5423270 | 18000 | EDBK3WS30001 BCBK3W4G0001 | 13/KQGN/587647//PT 13/KQGN/588334//PT DMARC: 1st floor data room relay rack 100.01, rack A customer handoff panel 12 tagged not extended. | 12/20/2013 1/15/2014 | 1/7/2014 2/20/2014 | 2014-02-21 | bpdd | 2014-01-14 | 2014-02-26 | unitedhealthgroup-64906 | 763-744-1575, daniel_j_skripka@uhc.com | Activation schedule for Monday, August 4th at 7pm CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 11/12- order being worked by Ethernet Cell 11/14- Ethernet Cell working on order to submit to Order Entry 11/20- ASR submitted; pending LEC to provide a FOC date 11/26- pending FOC date of 1/7/14 12/5- pending FOC date of 1/7/14 12/11- pending FOC date of 1/7/14 12/19- pending FOC date of 1/7/14 1/2- pending FOC date of 1/7/14 1/9- update from LEC, this circuit can't be turned up as the customer is not ready. No ETA and their order remarks doesn't have anything but asking us to contact our account manager and get this issue fixed with the customer. Requesting more specifics from LEC; pending response. 1/16- Site has been ready since 11/21- EVC ASR was submitted. Awaiting new FOC date. 1/22- per LEC could take up to 16 business days before receiving FOC date 1/29- pending new FOC date of 2/20 2/6- pending new FOC date of 2/20 2/17- pending FOC date of 2/20 2/20- awaiting confirmation if circuit was installed as scheduled for today, 2/20 2/27- ready for activation; customer notified
2014-03-07 | B end | PH550-01-IJ | 8F, MGO Bld., cor. Legaspi Dela Rosa st. , Makati City, Metro Manila, Philippines address changed 4/27 to IDC BLDG CENTER DANNY FLORO ST. BAGONG ILOG PASIG CITY | 1Gb PIP access rate limited to 100Mb with dport/car md5 UHGVERbgpbqZyofa Hand Off - Multi-Mode fiber with LC connector 850 SX Optics Pat confirmed they can take SMF/LC on 7/10 | OVI which is 1-1290311424 5515110 - Port 5515168 - Access |  |  | 5505541 | 10Mb | W1B26074 (access) W1B26059 (port) | MW01-072014-86032 PLDT CABLE TAG AT CUST CAB./EPLDT REF:SO#13086-A PLDT DIRECT FIBER XCONNECT CABL ONLY FR VZB POP & CUST COLO CABINETR | 2014-07-15 | 2014-08-06 | 2014-08-04 | bpdd | 2014-10-13 | 2014-08-07 | UnitedHealthGroup-65272 | 763-694-7333 skbrown1@uhc.com | activated with Steve on 8/11 | 3/10- pending SOF 3/14- Sof sent to John, dport not available in the Philippines. 3/18- SOF corrections made and sent, pending UHG signature 4/8 - pending LCON who can answer qustions and veification of the address. 4.10- new LCON passed onto B end 4/17- pat moran trying to set up a call with LCOn and our verification team 4/24- Call set up fo 8:30pm Central this evening 5/6- pending ecost and new SOF for address change. 5/12- new SOF sent to John with new address. 7.10 new order generated ASR being sent with SMF/LC connector type. Pat confirmed UHG can acctp 7/24- CHASING PTT FOR RFS DATE 7/31- PTT RFS DATE: AUG 06 2014 BEST EFFORT - AUG 01 2014 8/7- ready for activation, engineer informed
2014-07-02 | ShaRita | none | 1001 BRINTON ROAD PITTSBUR GH PA USA 15221 | disconnect | NSPE0008323740 OQBKZQW8 |  | P1614150 |  |  | BCBJX4PL0001 |  |  |  |  | 7/2/2014 (standard 30 calendar days) | 2014-07-31 | 2014-08-06 |  |  |  | 7/3- disconnect submitted to Sadisconnect 7/9- pending order number for disconnect 7/16- disconnect due date 7/31 7/24- disconnect due date 7/31 7/31- ready to disconnect; pending soft disconnect 8/6- disconnect complete
2014-07-02 | ShaRita | none | 131 Morristown Road Basking Ridge NJ 07920 | disconnect | NSPE0008323774 OQBKZQZK |  | P1863986 |  |  | bcbkmj670001 |  |  |  |  | 7/2/2014 (standard 30 calendar days) | 2014-07-31 | 2014-08-05 |  |  |  | 7/3- disconnect submitted to Sadisconnect 7/9- pending order number for disconnect 7/16- disconnect due date 7/31 7/24- disconnect due date 7/31 7/31- ready to disconnect; pending soft disconnect 8/6- disconnect complete
2014-07-02 | ShaRita | none | 9180 Commerce Circle Highland Ranch, CO 80129 | disconnect | NSPE0008323637 OQBKZQWJ |  | P1660738 |  |  | BCBJ271J0001 |  |  |  |  | 7/2/2014 (standard 30 calendar days) | 2014-07-31 | 2014-08-05 |  |  |  | 7/3- disconnect submitted to Sadisconnect 7/9- pending order number for disconnect 7/16- disconnect due date 7/31 7/24- disconnect due date 7/31 7/31- ready to disconnect; pending soft disconnect 8/6- disconnect complete
2014-04-29 | ShaRita | NC002-06-IJ | Connextions- 8333 Forest Point Blvd, Charlotte, NC 28273 | 100mg Ethernet with RJ45 handoff | opp id O-1007831 Quote ID: (190256587) Order Request 190257680 Service Order 190259898 has been Submitted for Provisioning 20291616 access 20291615 port QUOTE ID O-1052294 (change) Quote ID: 190350432 (change) Service Order(s) [ 190355394 ] has been created for Order Request 190354066 20372386 port | 190259898 190355394 |  | 5477399 5477400 | 30000 | C1004764 E4000905 | 22/KQGN/402124//SB VZB DMARC: 1 st server room r.r 1 pos 17 | 2014-05-06 | 2014-06-12 | 2014-06-04 | bpdd | 2014-06-19 |  | Connextions- 65223 (will be migrated to UnitedHealthGroup) | 407-926-2400 x10390 jose.hanchi@connextions.com | can turn up when needed Activations scheduled on July 31st from 12am CST to 4am CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 5/1- pending order submission 5/8- pending FOC date 5/14- FOC date 6/12 5/22- FOC date 6/12 5/29- FOC date 6/12 6/5- circuit delivered; asked John to confirm demarc FIRST FLOOR SERVER ROOM UNIT 2 RACK MOUNTED PORT 1 RJ 45 100 M FULL DUPLEX AUTO NEG DISABLED TAGGED WITH CKT ID. VLAN ID 18. 6/12- asked Jose to confirm demarc 6/18- although circuit is ready for activation there is an issue that provisioning has to resolve for failed PVC. escalating to have issue resolved 6/25- change order being submitted to remove PVC 7/3- change order submitted to remove 2nd PVC; pending provisioning approval 7/10- sent follow up email to provisioning to reveiw and approve order asap 7/17- helpdesk ticket to have order OPS approved was resolved. sent follow up to provisioning request to proceed with removal of PVC 7/24- Defect ticket 6457 was filed to fix the fall out issue. 7/31- activation complete
2014-04-29 | ShaRita | CO005-06-IJ | Connextions- 10730 E Briarwood Ave, Centennial, CO 80112 | 100mg Ethernet with RJ45 handoff | opp id O-1007831 Quote ID: (190256587) Order Request 190257680 Service Order 190259897 has been Submitted for Provisioning 20291641 access 20291640 port change Quote# O-1053411 change Quote ID: 190362450 change Order Request 190370028 Service Order(s) [ 190372794 ] has been created for Order Request 190370028 20389056 port | 190259897 190372794 |  | 5477405 5477406 | 30000 | C1004757 E4000908 | 24/KXGS/127007//ACSO VZB DMARC: FIRST FLOOR MAIN IT , WALL MOUNTED NEXT TO CIENNA 3916 DMARC all is labeled HANDOFF TYPE: ELECTRICAL | 2014-05-06 | 2014-06-04 | 2014-06-04 | bpdd | 6/11/2013 6/20/2014 |  | Connextions- 65225 (will be migrated to UnitedHealthGroup) | 407-926-2400 x10390 jose.hanchi@connextions.com | can turn up when needed Activations scheduled on July 31st from 12am CST to 4am CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 5/1- pending order submission 5/8- pending FOC date 5/14- FOC date 6/4 5/22- FOC date 6/4 5/29- FOC date 6/4 6/5- circuit delivered; asked John to confirm demarc 1st flr main telephone Rm, electric port 2 6/12- asked Jose to confirm demarc 6/18- Jose confirmed demarc; Order is pending for line testing and then will be stepped for beas installation 6/26- emailed provisioning to move forward with order for beas installation and rfc testing. a change order will have to be submitted to correct the PVC issue once order is completed 7/2- pending beas installation and rfc testing. 7/9- beas dispatch and rfc testing completed. sent email to provisioning requeting order be closed 7/17- ready for activation. change order submitted to remove 2nd PVC; order accepted by provisioning, ticket created for system error 7/31- activation complete
2014-05-16 | ShaRita | M0289-05-IJ | 170 Parkway West, Duncan, SC 24334 | PIP DS3 Install in new MDF room 205, md5 UHGVERbgpbqZyofa | SFDC Opportunity ID O-1022175 Quote ID: 190286266 Order Request 190287039 Service order id 190296034 20322429 access 20322428 port | 190296034 |  | 5485889 | 6144 | C4000181 D3000157 | 30/HFGS/401412//SB Main Bldg. Ground Flr. TELCO Room 206 [PORTS 1 AND 2 OF PATCH PANEL] | 2014-05-30 | 6/18/2014 8/5/2014 | 2014-08-05 | bpdd | 2014-08-12 | 2014-08-06 | unitedhealthgroup-65259 | robert_a_benson@optum.com 763-744-2077 |  | 5/20- sent to ShaRita 5/22- ShaRita is working submitting order 5/29- pending OPS approval 6/5- asr is on HOLD, waiting for LOA/CFA from Level 3 6/12- FOC date 6/18 6/19- there are 2 lec involved; 6/18 was FOC date from Level 3. We are pending our circuit delivery date from AT&T. asked provisioner to contact LEC to request the latest status on FOC date. 6/25- FOC date 8/5. Per ATT General Escalations List.. “6/25- job code A35, job required to place and splice fiber and place equipment, ECD 7/29, due date is scheduled for 8/5”. We have a BTDD ticket C201406240047 7/2- FOC date 8/5 7/9- FOC date 8/5 7/16- FOC date 8/5 7/24- FOC date 8/5 7/31- FOC date 8/5 8/6- ready for activation
2014-03-12 | ShaRita | FL751-05-IJ | 11300 NW 25 ST Miami, FL 33172 | 50M - Will throttle down to 20M Ethernet RJ45 handoff md5 UHGVERbgpbqZyofa | SFDC Opportunity ID O-0966120 quote id 190189558 Service Order(s) [ 190190618 ] has been created for Order Request 190189650 20231566 access 20231565 port MIA I0037153 | 190190618 |  | 5453964 | 10800 | C1003370 port E4000576 access | c5mia dqn 0008 60/OBGS/750794//SB VZB DMARC: first floor of Telefonica data center cabinet F28 position | 3/25/2014 5/2/2014 | 4/29/2014 5/16/2014 5/27/2014 | 2014-05-27 | bpdd | 5/6/2014 5/30/2014 | 2014-07-03 | unitedhealthgroup-64561 | 763-744-0981 glenn_moore@Optum.com | Activation rescheduled for 8/12 at 8pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 3/13- order is in process. 3/20- internal issue; pending resolution from ticket due to error 3/27- ASR submitted 4/3- pending FOC date from LEC 4/10- There is a build required for this order and based on the ECD of this build, the preliminary FOC is 4/30/14 at this time. The FOC will be sent once the build is completed and this should happen in mid-April. 4/17- FOC date 4/29 4/23- FOC date 4/29 5/1- pending new FOC date due to lcon not providing access 5/6- new FOC date 5/16 5/14- FOC date 5/16 5/22- Correct FOC date 5/27 5/28- circuit delivered; pending beas installation and end to end testing 6/5- access approved by end user; pending beas installation and end to end testing 6/11- beas installation scheduled for tomorrow, 6/13 6/18- BEAS installation and RFC Testing was completed last Friday, 6/13/2014. This order needs another dispatch for trouble shooting 6/25- The BEAS is now pingable; pending RFC testing 7/2- escalated to provisioning to close order asap if testing has been completed successfully 7/8- ready for activation; customer notified.
2013-11-22 | ShaRita | AZ008-12-IJ | 4425 East Cotton Center Blvd. Phoenix, AZ 85040 | 100M ethernet, RJ45 interface md5 UHGVERbgpbqZyofa | Request id 190063988 order number 190067688 20153384 access 20153383 port |  |  | 5425291 | 10800 | E4000177 access C1000775 port | 14/KXGS/123888//ACSO DMARC Info: Demarc is 1st Flr Main MDF rm mounted on backboard port ckt is tagged not extended | 2013-12-05 | 2014-03-19 | 2014-03-19 | bpdd | 2014-03-31 | 2014-03-31 | unitedhealthgroup- 65132 | 702-242-7654 tauoa.falo@uhc.com | Activation rescheduled for 8/8 at 8pm CST Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 1/2- LEC is working to schedule the site survey with the local contact on this order. This project needs equipment and/or fiber to provide service. CenturyLink personnel will contact us if there is difficulty or lack of response in scheduling the site visit. Please allow approximately 10 business days for site visit scheduling/ completion and subsequent contact for the project kickoff call. 1/9- pending response from LEC project manager on if site visit has already been scheduled or done. 1/16- Per Project Manager, Your order will be processed as a ‘flow thru’ order as soon as facilities are available. Currently United Healthcare has another order with another carrier that is currently in progress. Once their initial order completes, I will release your order to our Provisioning Center to be worked with standard dates. So for now order 20153384 will be placed on hold. As an FYI - their other order does require new equipment so they are looking at approximately 45 days to complete once it gets started. At the moment their initial order is ‘held’ while the end customer’s Corporate office approves of their site requirements. 1/22- order on hold 1/30- order on hold until intial order with other carrier completes. awaiting feedback from LEC if there are site requirements pending. 2/6- order on hold until intial order with other carrier completes. Per Project Manager, there are no site requirements. requested LEC to provide order information for other order; awaiting feedback 2/18- order still on hold. escalated to provisioning team lead to contact LEC in regards to other order; awaiting feedback. 2/20- order still on hold until intial order with other carrier complete. 2/27- escalated to provisioning to reach out to LEC to provide the latest status 3/6- escalated to 4th level escalation provisioning to provide status of order asap, Melissa Also reached out to LEC PM. Acocording to CL PM, the AQCB completed and provisioning is working on issued a due date. Due date will be 7-10 b days from when it's issued. 3/12- pending FOC date of 3/19 3/20- pending confirmation from LEC that circuit has been delivered 3/27- circuit delivered; beas installation scheduled for 3/27 4/1- ready for activation; customer notified
2014-06-10 | ShaRita | n/a | 8534 Concord Center Drive Englewood, CO 80112 | change from copper to fiber in order to extend at cust prem via SCID NCABU1 | Smartform 190316684 NSPE0008241135 CQBKY6N9 | 6469509 | P2039269 | 5400343 | 128 | BCBK2YWB0001 | 24/HCGS/745972//MS new DMARC_LOC=DATACENTER FIRST FLR NIU SHELF 1 SLOT 3 OF 28 EXTENDED=NO | 2014-06-27 | 2014-07-11 | 2014-08-04 | bpdd | 2014-08-21 | 2014-08-13 | UHGECC- 65521 | 763-744-2082 eric_taylor@uhc.com |  | 6/10-submitted to ShaRita 6/12- ShaRita is working on order submission to OE 6/18- order submitted to OE; OE is reviewing order request with team lead before submitting to provisioning 6/25- John confirmed circuit could be moved anytime; pending ASR submission 7/2- FOC date 7/11 7/9- FOC date 7/11 7/17- CL is working on the order to submit the cross connect jumper from the customers collocation over to Verizon carrier cabinet 7/24- circuit 24/HCGS/745972//MS has moved to SCID NCABU1 , we are asking CL about next steps 7/31- CL will provide an NIU on the circuit and work on an internal order, DD Monday but will work ASAP once order gets in. 8/4- Per CL circuit is reterminated. Pending testing of circuit and closing of order 8/14- order complete
2014-04-15 | ShaRita | AZ750-02-IJ | 3033 N 3rd Ave, Phoenix, AZ 85013 | 100M ethernet, RJ45 handoff MD5 UHGVERbgpbqZyofa | SFDC Opportunity ID O-0999056 Quote ID: 190241921 Order Request 190244304 Service Order(s) [ 190257634 access 20283406 port 20283405 | 190257634 |  | 5474565 | 10000 | C1004564 E4000838 | BCSC0608 Dmarc: Beas 1400 in the Cabinet top RU | 2014-04-30 | 2014-05-29 | 2014-05-29 | bpdd | 2014-06-05 | 2014-07-24 | unitedhealthgroup-64907 | 702-242-7654 tauoa.falo@uhc.com | Activation scheduled for Tuesday, 8/19 at 8pm CST Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 4/24- pending order submission; sharita needs to complete site questionnaire with technical contact 5/1- pending FOC date 5/8- FOC date 5/29 5/14- FOC date 5/29 5/22- FOC date 5/29 5/29- FOC date 5/29; pending confirmation circuit was installed 6/5- circuit delivered; asked John to confirm demarc Demarc info cabinet ff114 rmu 29 port number 2. 6/12- asked Tauoa to confirm demarc 6/18- Beas dispatch in complete. Order has been placed in jeopardy status due to NO POWER, it won't be available until mid July, this will have to be re-scheduled once customer confirms power is available. Supp order for new due date once customer has completed requirements. 6/25- pending end user to provide power 7/2- pending end user to provide power 7/9- John confirmed that temporary power is in place; pending date for beas installation 7/16- beas installation scheduled for 7/22 7/24- dispatch incomplete. IPAT CANNOT SEE HARD LOOP PROVIDED AT LEC HANDOFF AT CUST PREM ON ELECTRICAL RJ-45 PORT 2! REFER TO LEC TO WORK WITH BNE TO CLEAR PATH. 7/25- ready for activation; customer notified
2014-06-20 | ShaRita | TX028-03-IJ | Connextions- 5150 Regent Blvd, Irving, TX 75063 | 100M Ethernet RJ45 handoff | O-1046276 Quote ID: 190336647 Order Request 190337474 Service Order(s) [ 190342369 ] has been created for Order Request 190337474 20360621 access 20360620 port | 190342369 |  | 5495639 | 30000 | C1006246 E4001310 | 12/KEGS/701874//GTEC VZB DMARC: 1st flr server room, verizon relay rock shelf number 3, NID 3 | 2014-06-26 | 2014-08-01 | 2014-08-01 | bpdd | 2014-08-08 | 2014-08-04 | Connextions- 65226 | 407-926-2400 x10390 jose.hanchi@connextions.com | Activation scheduled for Tues, 8/19 at 2am CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 6/25- order submitted to provisioning 7/2- ASR submitted; pending FOC date 7/9- pending FOC date 7/17-pending FOC date 7/24- FOC date 8/1 7/31- FOC date 8/1 8/6- ready for activation; customer notified
2014-06-19 | ShaRita | FL156-02-IJ | 611 Druid E. Road, Suite 511, Clearwater, FL 33756 | 10752, 7xT1 MD5 UHGVERbgpbqZyofa | Smartform 190286749 NSPE0008286483 IQBKZDP6 | 6480339 | P2080175 | 5495936 | 1536 | BCBK50940001-0007 | 69/HCGS/433988//GTES DEMARC LOC: 1st floor telco room shelf 2 1 in 8 position shelf 69/HCGS/433989//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 2 in 8 position shelf 69/HCGS/433990//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 3 in 8 position shelf 69/HCGS/433991//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 4 in 8 position shelf 69/HCGS/433992//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 5 in 8 position shelf 69/HCGS/433993//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 6 in 8 position shelf 69/HCGS/433994//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 7 in 8 position shelf Jack Type: RJ48X | 2014-06-27 | 2014-07-18 | 2014-07-18 | bpdd | 2014-07-25 | 2014-07-25 | UnitedHealthGroup | 763-744-0981 glenn_moore@uhc.com | Activation scheduled for 8/15 at 12pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 6/18- pending opp id from Siva 6/25- ShaRita is working on submitting order to order entry 7/2- FOC date 7/18 7/9- FOC date 7/18 7/16- FOC date 7/18 7/18- circuit delivered; pending confirmation from John if we can proceed with end to end testing. Our tech has called the LEC and spoke with Melissa from VZB test center. She told him that circuits have been extended to suite 511, field tech was unable to use the conduit because it does not go out to termination and so they used the existing cable. The local contact agreed and aware of it, Bryan Hovell at 727-215-2527. 7/25- ready for activation; customer notified
2014-08-06 | ILEC | FL750-08-IJ | 9310 Florida Palm Drive Tampa, FL 33619 | Please place an order to install a new POTS line for the below location. We are requesting copper only, we do not want the fios service. | NSPE0008442759 Order Number: I3786927 Date Due: 2014-08-12 (8a-12p arrival) telephone Number: 8136304181 Circuit ID or Telephone Number: 8136304181 | [15 empty] | completed and dmarc sent
2013-11-21 | B End | AU535-02-IJ | 437 Williamstown Road Port Park, Melbourne Australia | 10M ethernet SOO to Melbourne - circuit ID W0X83226,md5 UHGVERbgpbqZyofa | 1-1296496955 5469902 (port) / 5469903 (access) |  |  |  | 6144 | W1B09873 (port) / W1B09874 (access) | Optus MVA 33CB G3P5 IPA002 A END DEMARCATION: GD LEVEL, DATA HALL D, REAR RACK 82, RI 33, POER 1 ON THE ISA CARD | 2014-04-24 | 2014-06-11 | 2014-06-23 | bpdd | 2014-07-17 |  | unitedhealthgroup- 65118 | plus 632-588-4651 noemi.joy_gomez@uhc.com | activated with noemi on 8/26 | 6/2- LATEST FROM OPTUS: "SITE SURVEY HAS ALREADY BEEN COMPLETED. WE ARE CURRENTLY WAITING FOR SITE ACCESS APPROVAL TO DO THE INSTALLATION OF TELECOMMUNICATIONS EQUIPMENT. IF THERE ARE NO UNFORESEEN ISSUES FROM THIS POINT ONWARDS, WE SHOULD BE ABLE TO MEET 11/06/2014." 6/12- still pending site access. 6/19- OPTUS ADVISES THAT SERVICE FINAL INSTALL AND TESTING HAVE BEEN SCHEDULED. IT SHOULD BE COMPLETED WITHIN THE NEXT FEW BUSINESS DAYS. 6/26- optus delivered tail on 6/24, we working on ethernet ete testing 7/10- escalating to get ETE testing complete. 7/14- pending site access from UHG to get ETE testing scheduled. 7/15-pending x-connect from dmarc to rack before ETE testing. Onsite contact is working on this. 7/22- Since Avy nor the customer could confirm correct rack details for me, the tech made some enquiries with the data centre and they got back to me saying Optus line G3P5 G3P5 EBB110 has been delivered to rack D82. He also sent an email to 3 customer contacts last Friday requesting access be granted for me for Monday or Tuesday this week- yet nobody has replied yet. Pending access 7/24- Customer has reached out to his DC to have a cross connect implemented to another rack. This may take another week or so. 7/31 - checking with field tech if he has heard from customer 8/7- following up with field tech to see if customer has x-conn completed. 8/14- still pending cross connext from customer 8/18- cross connect is complete. Access is being arranged for technician from Wednesday morning 9am-1pm 8/20- ready for activation, noemi asked to schedule for Tuesday the 26th at 3pm local time.
HOT 6/26/2014 | ShaRita | C1563-01-IJ | 5215 West Wiley Post Way, Suite 200, Salt Lake City, UT 84116 need mid August. | 44736, DS3 with md5 UHGVEReccgas4Usp9 | O-1049454 Quote ID: 190347215 Order Request 190350553 Service Order(s) [ 190351140 ] has been created for Order Request 190350553 20368196 access 20368195 port slc I10984 | 190351140 |  | 5496664 | 18000 | C4000218 D3000200 | 3x-vrp-xng-0356 64/HFGS/137956//MS DEMARC provided by MS01(QWEST):2nd Flr. Sever Room, C-Link Cabinet 1,shelf 3, slot 11 of 24 | 7/14/2014 8/7/2014 | 7/30/2014 8/12/2015 | 7/30/2014 8/15/2015 | bpdd | 2014-08-06 | 2014-08-18 | uhg-ecc 65416 | 763-7442154 scott_moyer@optum.com |  | 6/26- pending opp id from Siva 6/30- sent to Sharita 7/2- order submitted, pending provisioning approval 7/10- pending design on local network before ASR can be transmissted to CL/Qwest 7/16- asr transmitted and sent to QWEST now waiting for FOC. lec has 5 BD sla to issue foc from asr sent date 7/24- FOC date 7/30 7/31- circuit delivered, pending end to end testing 8/6- Design has been revised to different ring. A change ASR being submitted to change the CFA. 8/14- BNE to proceed completing this order once we have corected the wiring 8/18- ready for activation; customer notified
2014-06-24 | ShaRita | UCA99-07-CJ | 4365 Executive Drive #500, San Diego, CA 92120 | upgrade to 7680, 5xT1 | Smartform 190344703 NSPE0008301941 IQBKZHCJ OQBKZLJV | 6485004 |  | 1580927 |  | BCBJD0XJ0001-2 (out) BCBK515X0001-5 (in) | 13-H52-BJM-0009 13-H52-BJM-0010 13-H52-BJM-0011 from Field Tech: All 3 circuits are extended to the building demarc at mpoe on the 2nd floor telco room. Customer needs to contact their leasing agent to get a hold of Horizon to extend all 3 circuits to their suite from the 2nd floor telco rm. Cir. 13 -j0f-bjm-0012 top 110 block East wall 15 001312 001411 Left note for contractor, Horizon. Hard loops left on bp at 2nd floor mpoe. | 2014-07-07 | 7/23/2014 7/29/2014 |  | bpdd | 2014-07-30 | 2014-07-31 | unitedhealthgroup- 64942 | 987-313-9388 anupam_datt@uhc.com |  | 6/26 submitted to ShaRita 7/2- order submitted to Order Entry 7/10- FOC date 7/23 7/17- FOC date 7/23 7/24- New FOC date of 7/29 due to SUP hat was sent to EV28 to cancel PON, changing of primary CFA due to Node A66 is for future decom. The reason for the change of CFA is that the first CFA use has a NODE a66 that is for future decom. 7/31- circuits delivered and tested. ready for hotcut; customer notified Notes from Field Tech: All 3 circuits are extended to the building demarc at mpoe on the 2nd floor telco room. Customer needs to contact their leasing agent to get a hold of Horizon to extend all 3 circuits to their suite from the 2nd floor telco rm. Cir. 13 -j0f-bjm-0012 top 110 block East wall 15 001312 001411 Left note for contractor, Horizon. Hard loops left on bp at 2nd floor mpoe.
2014-06-03 | ShaRita | WA041-07-IJ | 15325 SE 30th Place, Bellvue, WA 98007 | 50mg EthernetRJ45 connector installed MPOE MD5 UHGVERbgpbqZyofa | opp id O-1034828 Quote ID: 190311155 Order Request 190311536 Service Order 190315397 20340359 access 20340358 port | 190315397 |  | 5489814 | 10mg | C1005810 E4001182 | 74/KXGS/407313//ACSO DEMARC INFO: 3rd floor, telco room, port 1, Tagged with CKT ID | 2014-06-10 | 2014-06-24 | 2014-06-20 | bpdd | 2014-07-01 | 2014-07-25 | unitedhealthgroup- 65057 | robert_a_benson@optum.com 763-744-2077 | Activation scheduled for 8/21 at 3pm CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 6/11- pending FOC 6/18- FOC 6/24 6/25- circuit delivered; pending beas installation and RFC testing 7/2- pending customer demarc extension 7/9- pending customer demarc extension 7/16- John confirmed extension complete. Pending date for beas installation 7/24- beas installation scheduled for 7/24 7/28- ready for activation; customer notified
2014-02-17 | ShaRita | CA123-02-IJ | 3215 Prospect Park Drive Rancho Cordova, CA 95670 | 100M - Needs to be 50M Ethernet RJ45 handoff MD5 UHGVERbgpbqZyofa | request 190158252. Service Order(s) [ 190168297 ] has been created for Order Request 190166635 20216566 access 20216565 port |  |  | 5446765 | 10000 | access E4000485 port C1002739 | 18/KQGN/517501//PT DMARC: FLR 1 Telco Rm 1.1 panel 1 jack 5 tagged with circuit ID | 2014-02-25 | 2014-04-08 | 2014-04-03 | bpdd | 2014-04-15 | 2014-04-09 | unitedhealthgroup- 64787 | 860-702-8284 keith_mangene@optum.com | Activation rescheduled for 8/14 at 1030pm CST. Bridge Number: 866-692-3158 Passcode: 9236734 7/23 at 10pm CST Bridge Number: 866-692-3158 Passcode: 9236734 Activation failed: Deven advised that he will just contact Sharita for re-schedule. they have power issues at site and Greg will work on it | 2/20- pending credit approval 2/27- asr sent; awaiting LEC to provide FOC date 3/6- awaiting LEC to provide FOC date 3/12- awaiting LEC to provide FOC date; per LEC, expect FOC date within this week. 3/20- Awaiting AT&T PM to follow up the schedule of site survey and customer room readiness. Received email response from LEC PM stating that he has informed the network about the relationship between United Healthcare and Dignity Health and also that the Dignity Health LCON is valid. The site visit however did not take place yet. According to him, the construction was fortunately able to continue without the site visit, however the order will not be able to complete without a site survey and customer being room ready. Also, he mentioned that they still need to make sure that customer is room ready and that will be the last pillar of the build phase and we will be able to proceed to provisioning soon after their room readiness is confirmed and hoping that the site visit can take place as soon as possible. 3/26- FOC date 4/8 4/3- FOC date 4/8 4/9- circuit ready for activation; customer notified
2014-04-29 | ShaRita | UFL68-07-IJ | 601 Brooker Creek Blvd, Oldsmar, FL 34677 | 100mg ethernet with RJ45 handoff MD5 UHGVERbgpbqZyofa | SFDC Opportunity ID O-1007464 Quote ID: 190255791 Order Request 190256254 Order Request 190257680 Service Order(s) [ 190260131 ] has been created for Order Request 190256254 access 20285314 port 20285313 |  |  | 5475126 | 44184 | C1004602 E4000854 | 69/KEGS/702333//GTES Demarc: 1st flr, MDF rm, verizon rack MS9, tagged, not extended | 2014-05-01 | 2014-07-01 | 2014-05-29 | bpdd | 2014-07-09 | 2014-06-12 | unitedhealthgroup-64615 | 91 91600 84400 harish_kandpal@optum.com | Activation scheduled for 8/27 at 6pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 4/29- sent to ShaRita 5/1- pending FOC date 5/8- FOC date 7/1; pending build on LEC side 5/14- FOC date 7/1 5/22- FOC date 7/1 5/29- FOC date 7/1 6/5- FOC date 7/1 6/12- ready for activation; customer notified
2014-06-05 | ShaRita | NJ023-05-CJ | 333 Thornall Street, Edison, NJ 08837 | Change - Upgrade port 4608, 3xT1 Add 1 T1 to existing bundle | O-0889964 Quote ID: 190316737 Order Request 190326741 Order Request 190326741 / In order Service Order 190333993 Order Request 190333994/ Out order Service Order 190333986 20354820 in 20354819 in 20354867 out 20354866 out | 190333993 in 190333986 out |  | 5494439 | 1300 | N1003819,N1003818,N1003817 in access C0003658 in port N1000548,N1000547 access C3000498 port | .HCGS.828398..NJ DEMARC LOC: Ground,mn,TEL RM,RJ48C,N,N,OTHER,na,OTHER,na,1st fl sj 8p15 DEMARC LOC Continued: hbl 1 p4 no ex Extended Wire (Yes or No): No Jack Type: RJ48C HCGS.828399..NJ DEMARC LOC: Ground,mn,TEL RM,RJ48C,N,N,OTHER,na,OTHER,na,1st fl mn telco DEMARC LOC Continued: sj 8 p16 hbl Extended Wire (Yes or No): No Jack Type: RJ48C .HCGS.828400..NJ DEMARC LOC: Ground,mn,TEL RM,RJ48C,N,N,OTHER,na,OTHER,na,1st fl sj 9p16 DEMARC LOC Continued: hbl 1 p 6 no e Extended Wire (Yes or No): No Jack Type: RJ48C | 6/20/2014 6/30/2014 | 2014-07-11 | 2014-07-11 | bpdd | 2014-07-08 | 2014-07-15 | unitedhealthgroup- 65298 | 763/694-7370, masroor_khan@uhc.com | scheduled for 7/22 at 6pm CST Conference Bridge 866-878-8630 pass code 6653710 | 6/10- pending ticket S9673337 6/19- ShaRita is working on submitting order request to provisioning 6/25- confirmed to provisioning that we want to reuse existing access and install new. Provisioning is working on re-design and re-submission of ASR to LEC for FOC date 7/2- FOC date 7/11 7/9- FOC date 7/11 7/15- ready for activation. customer notified 7/23- cutover completed. pending disconnect of out order. 7/30- pending disconnect 8/28- disconnects completed
2014-07-21 | ShaRita | none | 4875 Riverside Drive Macon GA 31210 | disconnect | NSPE0008380854 OQBKZ0JT |  |  |  |  | bcbk21h40001 |  |  |  |  | 7/22/2014 (standard 30 calendar days) | 2014-08-21 | 2014-08-26 |  |  |  | 7/21- disconnect submitted to Sadisconnect 7/31- disconnect due date 8/21 8/6- disconnect due date 8/21 8/14- disconnect due date 8/21 8/21- disconnect due date 8/21 8/26- disconnect complete
2014-07-21 | ShaRita | none | 4205 Westbrook Drive Aurora IL USA 60504 | disconnect | NSPE0008381741 OQBKZ8RK |  |  |  |  | BCBKPYL40001-4 |  |  |  |  | 7/22/2014 (standard 30 calendar days) | 2014-08-20 | 2014-08-22 |  |  |  | 7/21- disconnect submitted to Sadisconnect 7/31- escalated to disconnect group management requesting that order be processed ASAP 8/6- disconnect due date 8/20 8/14- disconnect due date 8/20 8/21- soft disconnect complete, pending disconnect completion 8/22- disconnect complete
2014-07-25 | ShaRita | UCA08-05-CJ | 8840 Complex Drive, San Diego CA 92123 | 7680 5xT1 upgrade from 4xT1 | Smatform 190391509 NSPE0008405953 IQBKZ3QW (in) OQBKZ5CW (out) | 6525873 | P2083824 (in) P2051743 (out) |  | 4000 | BCBK3VV80001-4 (out) BCBK58XN0001-0005 (in) | 19/HCGS/622539//PT DEMARC LOC: NIU AT THE 1.1 MPOE ON QUAD MOUNT #2 DEMARC LOC Continued: MOUNT #2 SLOT 4 Jack Type: RJ48C | 2014-07-31 | 2014-08-18 | 2014-08-15 | [5 empty] | Hotcut requested for 8/28 at 730pm CST Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 7/31- order submitted; pending provisioning approval. 8/6- FOC date 8/18 8/14- FOC date 8/18 8/21- circuit delivered; ready for hotcut. Customer notified
2014-03-24 | ShaRita | UTN07-05-IJ | 10 Cadillac Drive , Brentwood, TN | 100mg ehernet with dport john will throttle down to 10mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd | SFDC Opportunity ID O-0975869 Quote ID: 190204555 Order Request [ 190205270 ] Service Order(s) [ 190208364 ] has been created for Order Request 190205270 access 20240431 port 20240430 | 190208364 |  | 5460108 | 5008 | E4000631 C1003718 | T4/KRGN/821559//SC DMARC: 2nd floor suite 200 server room relay rack 2 tagged on A ciena 3930 | 2014-04-07 | 5/6/2014 7/16/2014 | 2014-07-16 | bpdd | 5/13/2014 7/25/2014 | 2014-07-25 | UnitedHealthGroup-64523 | 860-702-8284 keith_mangene@optum.com |  | 4/23- FOC date 5/6 5/1- FOC date 5/6 5/8- pending customer to provide new conduit 5/14- pending customer to provide new conduit 5/22- pending customer to provide new conduit 5/28- pending customer to provide new conduit, conduit should be installed Thursday or Friday 6/7 6/5- order supp'ed for new due date 6/10- pending FOC date 6/18- provisioning reached out with the PM from ATT working on this one, currently they are working in getting this foc’d. 6/26- pending FOC date 7/2- FOC date 7/16 7/9- FOC date 7/16 7/16- circuit delivered, John confirmed demarc 2ND FLOOR,SUITE 200,SERVER ROOM,RR02,CIENA. pending dispatch date for beas installation 7/24- bea dispatch complete; pending end to end testing 7/25-ready for activation; customer notified
2014-08-01 | ShaRita | none | 777 108th Avenue NE / Suite 2040 BELLEVUE WA USA 98004 | disconnect | NSPE0008428525 OQBK0CSZ |  |  |  |  | P1639351 / BCBJ1BVJ0001-2 |  |  |  |  | 8/4 (standard 30 calendar days) | 8/25/2014 8/28/2014 | 2014-09-02 |  |  |  | 8/4- disconnect submitted to Sadisconnect 8/7- pending order information 8/14- disconnect due date 8/25 8/21- disconnect due date 8/25 8/28- correct disconnect due date 8/28 9/3- disconnect complete
2014-08-18 | ShaRita | NJ777-03-IJ | 800 Secaucus Road, Seacaucus, NJ 07094 | 1G internet circuit with 100M commit. Port only release CFA | O-1078647 Quote ID: 190426132 order request 190428424 Service Order(s) [ 190433206 ] | [15 empty] | 8/14- there was a question on where to meet with equinix. We will be meeting them at 755 Secaucus per Steve B, this will requrie an access loop 8/21- it was decided to order a local loop into 800 secaucus, order sent to ShaRita 8/29- pending cancellation confirmation from John 9/3- order cancelled
2014-06-02 | ShaRita | none | 13 Cornell Rd Latham, NY 12110 | inside move to 2nd floor MDF | smartform 190306002 NSPE0008213859 CQBKY3H5 port CQBKY3H6 access | 6455052 | P2049885 EACS P2049901 PORT | 5419536 | 10800 | EDBK3N210001 EACS BCBK3N370001 PORT | 34.KEGS.026057..NY Demarc is: 2nd floor room 209, wall mounted. | 2014-06-18 | 2014-07-08 | 2014-07-08 | bpdd | 2014-07-29 | 2014-07-08 |  | 987-313-9388 anupam_datt@uhc.com / Chris Frank 5183134811 | Hotcut scheduled or 9/3 at 8pm CST Bridge Number: 866-692-3158 Pass code: 9236734 | 6/2- change order submitted to ShaRita 6/5- confirming with provisioning if request is a change or in/out 6/11- order submitted to OE 6/18- emailed provisioning to review and approve order asap 6/25- FOC date 7/8 7/2- FOC date 7/8 7/9- ready for activation; customer notified
2013-10-23 | ShaRita | NY058-06-IJ | 13 Cornell Rd Latham, NY 12110 | 20M ethernet md5 encryption UHGVERbgpbqZyofa FastE interface 20Mb Type 2 Premium Ethernet Access MRC - $1,401 (provided by Verizon) SAR 1-1SEE3ER, approval 026OYJ-001, exp 2/25/14, | smartform 190028224 NSPE0007446657 IQBKSW65 EACS IQBKSW85 PORT | 6125184 | P2049885 EACS P2049901 PORT | 5419536 | 10800 | EDBK3N210001 EACS BCBK3N370001 PORT | 34.KEGS.026057..NY VZB DMARC : basement telco area wallmount HANDOFF TYPE: RJ48C | 2013-11-05 | estimate 2/14 4/30/2014 | 2014-04-29 | bpdd | 5/7/2014 5/12/2014 | 2014-04-29 | unitedhealthcare-65129 | 987-313-9388 anupam_datt@uhc.com | Hotcut scheduled or 9/3 at 8pm CST Bridge Number: 866-692-3158 Pass code: 9236734 | ruction charges provided to account team/customer; awaiting customer to approve charges; pending estimated FOC date of 02/18/2014. 12/5- special construction charges provided to account team/customer; awaiting feedback from account team. Pending estimated FOC date of 02/18/2014. 12/11- Received PCM VP approval that Verizon can waive the special construction charge if the customer agrees to a 3 year term on the circuit; pending amendment draft. 12/19- UHG has the amendment, and they are reviewing for execution. 1/2- Awaiting UHG to return amendment 1/9- Awaiting UHG to sign/return amendment 1/16- Contract received back from UHG but still pending counter signature 1/23- awaiting feedback from LEC on what the next steps are to move forward since contract has been returned 1/29- Followed up with LEC regarding with the special construction quote. The contract is with VZB and we are waiting for their signature, after that it will be forwarded to VZT and they have to counter sign it. We should be good to go after this. The contract should be completed by end of this week. 2/6- order is currently on standstill until issue with contract status has been resolved. a ticket has been opened and escalated to resolve issue. 2/18- estimated FOC date of 4/30 2/27- estimated FOC date of 4/30 3/6- pending FOC date of 4/30; also asked provisioning to confirm with LEC if customer is pending an site requirements. Pending response from LEC. 3/12- pending site requirements; forwarded to John 3/20- pending FOC date of 4/30; site requirements forwarded to John, Per John site requirements are complete. 3/27- FOC date 4/30 4/3- FOC date 4/30 4/10- FOC date 4/30 4/17- FOC date 4/30 4/23- FOC date 4/30 5/1- ready for activation customer notified
2014-06-20 | ShaRita | AZ043-03-IJ | Connextions- 4809 E. Thistle Landing Dr., Phoenix AZ 85044 | 100M Ethernet RJ45 handoff | O-1046270 Quote ID: 190336291 Order Request 190336597 Service Order(s) [ 190342284 ] has been created for Order Request 190336597 20360573 access 20360572 port | 190342284 |  | 5495595 | 30000 | C1006245 E4001307 | 14/KXGS/124859//ACSO DMARC: 1st floor west side of building telco | 2014-06-25 | 2014-07-10 | 2014-07-10 | bpdd | 2014-07-17 | 2014-08-22 | Connextions- 65227 | 407-926-2400 x10390 jose.hanchi@connextions.com | Activation scheduled for Monday, September 3rd at 2am CST Bridge Number: 866-692-3158 Pass code: 9236734 | 6/25- order submitted to provisioning 7/2- FOC date 7/10 7/9- FOC date 7/10 7/16- circuit delivered. Beas installation scheduled for Monday 7/21 7/24- beas installation incomplete. Asked customer to confirm and check to the customer port 1-1 if it is tagged as 14/KXGS/124859//ACSO. 7/31- tech went out and was able to locate the circuit. Per customer (Alex), there was a power outage last week , the electrical outlets used for the equipment are currently not working. Our Facility Manager is working with the Property Manager to get those outlets fixed, and bring back online the equipment that is currently turned off. I'll keep you updated as to when those outlets are fixed. 8/6- per Alex, outlet issue resolved. pending demarc extension before we are able to schedule beas installation 8/14- Jose informed demarc does not have to be extended. pending scheduling of beas installation 8/21- beas dispatch scheduled for today, August 21st 8/22- ready for activation ; customer notified
2014-01-17 | ShaRita | UFL88-06-IJ | 5908 HAMPTON OAKS PKWY, Tampa, FL | 100M ethernet, RJ45 handoff MD5 UHGVERbgpbqZyofa | Order Request # 190116213 Service Order(s) [ 190116488 ] 20180117 access 20180116 port | 190116488 |  | 5437291 | 30M | E4000335 access C1001942 port | 69/KEGS/702037//GTES DMARC Info:1st floor collo area. Vzb rack 9207 shelf 4 | 2013-01-22 | 2014-02-24 | 2014-02-24 | bpdd | 3/3/2014 3/31/2014 | 2014-07-29 | unitedhealthgroup-65033 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com |  | Both Cabinets, Power are ready! There is a call with the client to discuss the remaining tasks. 5/14- Technician will be going out to install the BEAS at Hampton oaks on 5/20. UHG will then order connextion from there to Palm Drive. 5/22- CenturyLink is working with the Retail side to get the orders and paperwork processed. As soon as that is completed we can have the tech install the Beas in Hampton Oaks." 5/29- Pending CL retail contract with the customer. No ETD yet. 6/5- Pending CL retail contract with the customer. No ETD yet. 6/11- CenturyLink wholesale just reached out to their Retail Sales and on Connextion customer and they have not gotten back a signed order yet>> they were thinking they should see it this week> Will update when we have confirmation Connextions has sent back the signed order. 6/18- CL is working on extension, contract signed 6/25- CL is working on extension, contract signed, per John should be extended the week of the 11th, we will have to escalate to put BEAS in, since UHG is getting pressure to get this in 7/2- CL should be done with extension next week 7/9- Pending CL to complete demarc extension 7/16- John confirmed handoff will not be changed; Per CL on Tampa>> I have spoken to our engineering and the electronics that can’t support copper terminations between the address LOCs is exhaust> I am working with our transport engineer to see if there is a potential groom which can be done to support> I don’t have confirmation back yet>> 7/25- Per CL, they have found facilities and have been told that they already have XC to the Verizon circuit in Hampton Oaks. 7/25- Per Century Link, Can we get a tech out to Hampton Oaks today to complete and tag circuit? They have their side ready. 7/28- Demarc information is 1st floor collo area. Vzb rack 9207 shelf 4. Tagged with circuit id and order number. 7/29- ready for activation; customer notified
2014-06-19 | ShaRita | CA079-03-IJ | 30 W Valley Blvd, Alhambra, CA 91803 | 1536, T1 MD5 UHGVERbgpbqZyofa | O-1046256 Quote ID: 190336159 Order Request 190336385 Service Order(s) [ 190341769 ] has been created for Order Request 190336385 20360263access 20360262 port | 190341769 |  | 5495503 | 1376 | C0003818 D1005293 | 13/HCGS/853025//PT DEMARC LOC: MOUNT-2,SLOT-1 30-1.1 W.VALLEY DEMARC LOC Continued: W.VALLEY Extended Wire (Yes or No): YES EW Reason/Location:SERVER ROOM Jack Type: RJ48C | 2014-06-26 | 2014-07-08 | 7//7/2014 | bpdd | 2014-07-11 | 2014-07-11 | UnitedHealthGroup- 65207 | plus 632-588-4651 noemi.joy_gomez@uhc.com | completed with Noemi on 9/15/2014 | 6/18- pending opp id from Siva 6/25- order submitted to provisioning 7/2- FOC date 7/8 7/9- circuit delivered; pending end to end testing 7/16- ready for activation. Customer notified
2014-08-01 | ShaRita | none | 9009 Corporate Lake Drive / West Lake Corp Center TAMPA FL USA 33634 | disconnect | NSPE0008428030 OQBK0DB0 |  |  |  |  | BCBJKL0G0001-8 |  |  |  |  | 8/4 (standard 30 calendar days) | 2014-09-02 | 2014-09-04 |  |  |  | 8/4- disconnect submitted to Sadisconnect 8/7- pending order information 8/21- disconnect due date 9/2 8/27- disconnect due date 9/2 9/3- soft disconnect complete. Pending disconnect 9/10- disconnect complete
2014-08-01 | ShaRita | none | 5800 Granite Parkway / Suite 900 PLANO TX USA 75024 | disconnect | NSPE0008428062 OQBK0DHL |  |  |  |  | BCBJ7L590001 |  |  |  |  | 8/4 (standard 30 calendar days) | 2014-09-02 | 2014-09-04 |  |  |  | 8/4- disconnect submitted to Sadisconnect 8/7- pending order information 8/14- disconnect due date 9/2 8/21- disconnect due date 9/2 8/27- disconnect due date 9/2 9/3- soft disconnect complete. Pending disconnect 9/10- disconnect complete
2014-08-01 | ShaRita | none | 200 W Madison Street / Suite 3440 / 34th Floor CHICAGO IL USA 60606 | disconnect | NSPE0008428259 OQBK0B38 |  |  |  |  | P1963525 / BCBKW3WM0001-3 |  |  |  |  | 8/4 (standard 30 calendar days) | 2014-09-02 | 2014-09-04 |  |  |  | 8/4- disconnect submitted to Sadisconnect 8/7- pending order information 8/14- disconnect due date 9/2 8/21- disconnect due date 9/2 8/27- disconnect due date 9/2 9/3- soft disconnect complete. Pending disconnect 9/10- disconnect complete
2014-08-07 | ShaRita | none | 3515 Harbor Blvd / 1st Floor of University Bldg COSTA MESA CA USA 92626 | disconnect | NSPE0008442920 OQBK0DHC |  |  |  |  | BCBJCTY10001 |  |  |  |  | 8/7 (standard 30 calendar days) | 2014-09-04 | 2014-09-10 |  |  |  | 8/7- disconnect submitted to Sadisconnect 8/14- disconnect due date 9/4 8/21- disconnect due date 9/4 8/27- disconnect due date 9/4 9/3- disconnect due date 9/4 9/10- disconnect complete
2014-08-07 | ShaRita | none | 13655 Riverport Drive / P.O. Box 2560 MARYLAND HEIGHTS MO USA 63043-8560 | disconnect | NSPE0008443663 OQBK0DZL |  |  |  |  | BCBH3R4J0001 |  |  |  |  | 8/7 (standard 30 calendar days) | 2014-09-04 | 2014-09-09 |  |  |  | 8/7- disconnect submitted to Sadisconnect 8/14- disconnect due date 9/4 8/21- disconnect due date 9/4 8/27- disconnect due date 9/4 9/3- disconnect due date 9/4 9/10- disconnect complete
2014-08-07 | ShaRita | none | 13655 Riverport Drive / P.O. Box 2560 MARYLAND HEIGHTS MO USA 63043-8560 | disconnect | NSPE0008443663 OQBK0DZM |  |  |  |  | BCBJC2YV0001 |  |  |  |  | 8/4 (standard 30 calendar days) | 2014-09-04 | 2014-09-10 |  |  |  | 8/7- disconnect submitted to Sadisconnect 8/14- disconnect due date 9/4 8/21- disconnect due date 9/4 8/27- disconnect due date 9/4 9/3- disconnect due date 9/4 9/10- disconnect complete
2014-03-12 | ShaRita | n/a | Chaska mdf 800 change circuit BOBKWCW20001 | MDF800 -Change request for circuit W0Z66371 (jy-m6l7-73c-0001) to stop circuit at Cologne (73c) eliminating Verizon shared ROADM (ROADM.AA) from the circuit path. | NSPE0007962955 5456777 MIN- C33590 CCR # : 1203311 | 6325820 |  |  |  | W0Z66371 | JY-M6L7-73C-0001 Demarc: AJ807, FB3 B-6 |  |  |  | bpdd | 2014-05-09 | 2014-04-10 |  |  | scheduling for 5/20 at 10pm central | 3/20 Melissa created tin 3/27- CHECKED PENDING CCR # : 1203311 FOR LOCAL MIN- C33590 CURRENT QUEUE/OWNER : WAREHOUSE EQUIP SHIP / PMMO, I-PAK CREATED / RE RFT DATE: 05/01/2014 LATEST REMARKS; SYSTEM PLAN APPROVED ON 03/27/2014 4/3- PENDING CCR # : 1203311 ; RFT DATE: 05/01/2014 4/10- PENDING CCR # : 1203311 ; RFT DATE: 05/01/2014 4/16- order closed to billing
2014-03-12 | ShaRita | n/a | Chaska mdf 800 change circuit BOBKWCW20001 PIPO change order to new handoff DEMARC: FDB: 10.26.2 jacks:2/8 | MDF800 -Change request for circuit W0Z66371 (jy-m6l7-73c-0001) to stop circuit at Cologne (73c) eliminating Verizon shared ROADM (ROADM.AA) from the circuit path. terminate to MZZGE01 GW: HKQ/MZZGE01.1A.0.1 | CQBKXZ7T | 6395094 |  |  |  | BOBKWCW20001 | DEMARC: FDB: 10.26.2 jacks:2/8 | [8 empty] | scheduling for 5/20 at 10pm central | 4/22- tin submiteted FDB: 10.26.2 jacks:2/8 5/8- pending hotcut
2014-08-01 | ShaRita | NJ777-02-IJ | 800 Secaucus Road, Seacaucus, NJ 07094 | 1G will throttle down to 500M SMF LC connector give tie down info to Equinix for x-conn. BGP advertisement-interval set to 0. BFD Enabled. Line is provided by equinix, so no protection is provided by Verizon. Optic - GE-L 1310 | Smartform 190411452 NSPE0008449080 inquiry 9N5M3LPY IQBK0G8X | 6552380 | P2085909 | 5512713 | 20M | BOBK6D7K0001 | [6 empty] | 2014-08-22 | UnitedHealthGroup- 65239 | 763-694-7333 skbrown1@optum.com | activated with Steve Brown on 9/19. | 8/5 lori needs to process BAU 8/11- order is with ShaRita 8/14- ShaRita working on submitting tin to OE 8/21- account team provided the assigned L3 port, pending provisioning approval 8/25- LOA given to UHG and order closed
2014-08-18 | ShaRita | none | 4425 East Cotton Center Blvd. Phoenix AZ USA 85040 | disconnect | NSPE0008476811 OQBK0MLV |  | P1838870 |  |  | BCBKK1D10001 |  |  |  |  | 8/15 (standard 30 calendar days) | 2014-09-11 | 2014-09-15 |  |  |  | 8/19- disconnect submitted to Sadisconnect 8/21- pending order number 8/27- disconnect due date 9/11 9/3- disconnect due date 9/11 9/10- disconnect due date 9/11 9/15- disconnect complete
2014-08-18 | ShaRita | none | 4425 East Cotton Center Blvd. Phoenix AZ USA 85040 | disconnect | NSPE0008476811 OQBK0MLV |  | P1959126 |  |  | BCBKWK790001 |  |  |  |  | 8/15 (standard 30 calendar days) | 2014-09-11 |  |  |  |  | 8/19- disconnect submitted to Sadisconnect 8/21- pending order number 8/27- disconnect due date 9/11 9/3- disconnect due date 9/11 9/10- disconnect due date 9/11 9/15- disconnect complete
2014-08-18 | ShaRita | none | 3720 Davinci Court, Norcross, GA 30092 | disconnect | NSPE0008476859 OQBK0MMK |  | P1958585 |  |  | BCBKWJ9J0001-0007 |  |  |  |  | 8/15 (standard 30 calendar days) | 2014-09-11 | 2014-09-13 |  |  |  | 8/19- disconnect submitted to Sadisconnect 8/21- pending order number 8/27- disconnect due date 9/11 9/3- disconnect due date 9/11 9/10- disconnect due date 9/11 9/15- disconnect complete
2014-07-02 | ShaRita | none | 1707 West Creek Lane Chaska MN USA 55318 | disconnect | NSPE0008323602 Request 51752867 |  |  |  |  | u313034 |  |  |  |  | 7/2/2014 (standard 30 calendar days) | 2014-07-31 |  |  |  |  | 7/3- disconnect submitted to VZB FULL DISCO OPTION 4 7/10- pending order number for disconnect 7/16- disconnect due date 7/31 7/24- disconnect due date 7/31 7/31- pending disconnect completion 8/7- escalated to provisioning to complete disconnect 8/14- LOD sent to disconnect group to have all services disconnected; pending disconnect completion 8/20- pending disconnect completion. requested provisioning to provide disconnect due date 8/27- confirmed billing has stopped but still pending disconnect completion in system 9/3- confirmed billing has stopped but still pending disconnect completion in system 9/10- billing has stopped but order still pending in disconnect Que 9/16- confirmed that all services are disconnected and off the ring.
2014-04-07 | ShaRita | CO007-02-IJ | 385 Interlocken Crescent, Suite 200, Broomfield, CO 80021 | 100mg ethernet RJ45 handoff md5 UHGVERbgpbqZyofa | SFDC Opportunity ID O-0990306 Quote ID: 190225783 Service Order(s) [ 190241389 ] has been created for Order Request 190239157 20269110 access 20269109 port dnv-I31828 | 190241389 |  | 5470428 | 4000 | C1004471 E4000807 | c5-cny-cny-0018 BCSJ9275 VZB DMARC: parking lot telco 01.01.35 ports 13 and 14 tagged not extended handoff: SMF connector type : SC | 2014-05-09 | 2014-06-06 | 2014-06-04 | bpdd | 2014-06-11 | 2014-08-11 | unitedhealthgroup-64938 | 214-647-4442 donald_r_osborn@uhc.com |  | 5/8- TCOMS order has been generated and we are just waiting for the CFA to use on the ASR. 5/14- pending FOC date 5/22- pending FOC date; email received from Level 3 having issues with the system. IT is trying to resolve. 5/28- FOC date 6/6 6/5- circuit delivered; awaiting John to confirm if demarc will be extended Demarc: PRKNG LOT TELCO 01.01.35. 13/14 6/10- circuit delivered; asked Jamie to confirm if demarc will be extended Demarc: PRKNG LOT TELCO 01.01.35. 13/14 6/18- pending customer to extend circuit to MDF room 6/25- pending customer to extend circuit to MDF room 7/2- demarc extended; pending dispatch date for beas installation and rfc testing 7/10- Dispatch has been done in our tiedown and as per our VZB tech Bruce, DLR from Level 3 needs to be revised as it is incorrect. Issue already relayed to Level 3’s manager and is working on it. Also, Bruce informed Level 3’s tech for actions that needs to be taken so this could be resolved properly. Once done, we’ll proceed for beas installation. 7/16- The MUX issue in our tie down has been resolved but we currently have a defect ticket open. Designer assigned filed it as we are encountering issue in Lport. With that, we still can’t step order for BEAS installation. 7/24- Defect ticket - 6238 still pending resolution. Escalated to provisioning for resolution asap. 7/31- pending beas installation to be scheduled 8/6- pending customer to schedule beas installation 8/14- ready for activation customer notified
2014-05-19 | ShaRita | UNC16-10-IJ | 3803 N. Elm Street, Greensboro, NC 27455 | 200mg ethernet port on 300mg access. MMF with LC connector MD5 UHGVERbgpbqZyofa | quote : O-1023188 Quote ID: 190286998 Order Request 190299670 Service Order 190299785 20325039 access 20325038 port | 190299785 |  | 5486500 | 90000 | C1005402 E5000198 | 24/KRGN/400434//SB Demarc is 2nd fl, data rm, RR-300.02. This is an AT&T rack but is where te cus/John Rothstein requested it be installed. | 2014-06-09 | 7/11/2014 7/25/2014 8/11/2014 |  | bpdd | 7/18/2014 8/8/2014 | 2014-08-14 | unitedhealthgroup-64535 | John Rothstein 763-744-1556 john_l_rothstein@optum.com |  | 5/20- pending PCM error before submitting to ShaRita, ticket S9554922, per John may need to be ordered to a specific POP, Melissa is going to talk to Lori 5/29- order submitted to ShaRita 6/5- This order is for pending ASR due to system issue, provisioning already forwarded this to our support team & still waiting for the resolution. 6/12- pending FOC 6/18- FOC 7/11 6/25- FOC 7/11 7/2- FOC 7/11 7/9- tech attempted to deliver circuit on 7/8 but was not able to gain access due to lcon wasa on vacation and back up\Apryle Stallings had no work order to allow field tech access to the premise. customer provided new local contact. requested LEC to return to deliver circuit. pending new delivery date 7/16- FOC date 7/25 7/24- FOC date 7/25 7/31- requested new due date due to no access provided. New FOC 8/11 8/6- FOC date 8/11
2014-07-08 | ShaRita | TX214-02-IJ | 1250 Mockingbird Lane, Suite 550, Dallas, TX 75247 | 7xT1, 10752 MD5 UHGVERbgpbqZyofa | Smatform 190370610 NSPE0008356808 IQBKZW1Z | 6507533 | P2082688 | 5501483 | 1536 | BCBK56NR0001-0007 | 14/HCGS/146877//SW DEMARC LOC: 2ND FLR MAIN PHN RM MM CAB1,SLO DEMARC LOC Continued: CAB1,SLOT 2 14/HCGS/146878//SW DEMARC LOC: 2ND FLR MAIN PHN RM MM CAB1,SLO DEMARC LOC Continued: CAB1,SLOT 3 14/HCGS/146879//SW DEMARC LOC: 2ND FLR MAIN PHN RM MM CAB1,SLOT DEMARC LOC Continued: 4 14/HCGS/146880//SW DEMARC LOC: 2ND FLR MAIN PHN RM MM CAB1,SLO DEMARC LOC Continued: CAB1,SLOT 5 14/HCGS/146881//SW DEMARC LOC: 2ND FLR MAIN PHN RM MM CAB1,SLO DEMARC LOC Continued: CAB1,SLOT 6 14/HCGS/146882//SW DEMARC LOC: 2ND FLR MAIN PHN RM MM CAB1,SLO DEMARC LOC Continued: CAB1,SLOT 7 14/HCGS/146883//SW DEMARC LOC: 2ND FLR MAIN PHN RM MM CAB1,SLO DEMARC LOC Continued: CAB1,SLOT 8 Jack Type: RJ48C | 7/22/2014 8/13/2014 | 8/8/2014 8/29/2014 | 2014-08-21 | bpdd |  | 2014-08-26 | unitedhealthgroup-65249 | 210-877-7919 chris_spoor@optum.com |  | 7/10- pending approval to process 7/17- order submitted to OE 7/24- FOC date 8/8 7/31- FOC date 8/8 8/6- FOC date 8/8 8/14- order supp'ed for new FOC date and to change lcon. FOC date 8/29 8/21- FOC date 8/29 8/27- ready for activation; customer notified
2014-09-01 | B end | n/a | CISTER 2 Barcelona | disconnect related to upgrade | 5509518 |  |  |  |  | W1A83113 |  |  |  |  | bpdd | [5 empty] | 9/4- billing ceased, pending hard disconnect. 9/25- circuit in DISC status
2014-05-19 | ShaRita | FL750-02-IJ | 9310 Florida Palm Drive, Tampa FL 33619 | 1 gig access and port, (John will throttle down to 400mg) MMF LC Connector MD5 UHGVERbgpbqZyofa | SFDC O-0327502 Quote ID: 190286875 Order Request 190287050 Service Order 190296053 20322459 access 20322458 port | 190296053 |  |  | 30000 | C0002685 E5000193 |  | 2014-06-11 |  |  | bpdd |  |  | unitedhealthgroup-65033 | 702-242-7654 tauoa.falo@optum.com |  | 5/20- submitted to ShaRita 5/22- ShaRita is working submitting order 5/29- ASR submitted; pending FOC 6/5- Prov. still working on the pending ASR transmission due to system issue 6/11- system issue resolved. ASR submitted, pending FOC 6/18- Pending VZ presence in florida palm 6/25- Pending VZ presence in florida palm, could be a couple months 7/2- Pending VZ presence in florida palm, could be a couple months 7/10- per Robin, pending contract still, then build will start 7/16- Gaining access to this Centurylink Data center is currently in legal. 7/24- Contract to get access/presence is still in legal. 7/31-Contract to get access/presence is still in legal. 8/6- Contract to get access/presence is still in legal. 8/14- CL excutives to meet on 8/26 on this to make a decision 8/20- CL excutives to meet on 8/26 on this to make a decision 8/27- expected to receive feedback on decision in about 2 weeks 9/3- Still in discussions. More meetings scheduled for next week. 9/10- Still in discussions. We are working towards an Agreement…trying to outline and identify the ILEC locations and where there are centers for both CTL and VZ…. 9/17- Still in discussions. 9/18- John asked to cancel 9/19- order cancelled
2014-05-06 | B end | PH509-01-IJ | Building N, UP North Science and Techno Park, Commonwealth, Quezon City, Philippines building N | 100M Ethernet Fiber SX Handoff SOO to W0X83226 Melbourne MD5 UHGVERbgpbqZyofa | 5512865 (port) 5512866 (access) |  |  |  | 30000 | W1B25254 (port) W1B25255 (access) |  | 2014-07-15 |  |  | bpdd |  | 2014-10-02 | UnitedHealthGroup-65261 | plus 632-588-4651 noemi.joy_gomez@uhc.com | per John when they plugged in on 10/3 the circuit came up. | 8/14- AS PER LCON NALO, ARNAL JAMES A [AJ_NALO@OPTUM.COM] WE ARE EXPECTING MDF HANDOVER ON AUG. 30. BUT THERE WON'T BE ANY EQUIPMENT INSTALLATION TIL THE 5TH OF SEPT. 8/21- FS RESULTS PROVIDED, SITE PRE-REQUISITES STILL NOT AVAILABLE. FOC INSTALLATION REQUIRES AERIAL CABLING AND POLE ATTACHMENT, RTA PERMIT APPLICATION ALREADY FILED, TENTATIVE RTA RELEASE ON AUG. 30, FOR FOLLOW-UP. SEPARATE MEETING W/ UHG, PLDT TEAMS FOR THE LOCAL REQUIREMENTS CONDUCTED LAST AUG. 18. 8/28- pending RTA permit and site readiness 9/4- advised back office that we need to proceed with the order and not use an alternate carrier, per John PLDT is working on arial cabling 9/11- from PLDT PER COORDINATION W/ UHG'S CONTRACTOR, WORK PERMIT WAS APPROVED BY UPA ADMIN (APMC) YESTERDAY AFTERNOON. OUR CUSTNET2 TEAM WILL NOW PROCEED W/ THE CABLING WORKS. WILL KEEP YOU POSTED ONCE FURTHER DEVELOPMENTS ARE AVAILABLE. NEW TARGET RFS FOR UHG WILL BE EARLIEST BY OCT. 6. PLEASE ALSO SEE ATTACHED FILE FOR PHOTOS TAKEN IN UHG THIS TUE, SEP. 9 DURING OUR TEAM'S VISIT AND COORDINATION W/ UHG'S CONTRACTORS - DON PIN (ELECTRICAL/STRUCTURED CABLING CONTRACTOR) AND JLL (UHG PM). 9/18- It looks like PLDT is waiting for the site to have permanent power supply and UPS in place before they can proceed. Asked John for dates 9/22- We just received an advise fr PLDT that customer’s issue has been resolved. This is now pending PTT to complete their mapping & waiting to kick off 24 hrs BERT. 9/25- BERT testing to begin 9/26, then once complete can hand to Verizon 10/2- circuit delviered., tested and configliet built. pending activation
2014-09-09 | ShaRita | none | Via Cristoforo Colombo 163 / 6th Floor ROME ITALY USA 00147 |  | NSPE0008553486 5548030 | 8001338 |  |  |  | w0v97474 |  |  |  |  | 9/9/2014 (standard 60 business days) | 2014-11-10 | 2014-09-29 |  |  |  | 9/9- disconnect submitted to provisioning 9/10- lcon verification complete. Disconnect request submitted to PTT. 9/17- pending disconnect 9/25- pending disconnect 10/2- disconnect complete
2014-04-15 | ShaRita | UWI29-05-IJ | 3100 AMS Blvd, green bay WI 54313 Needs to be provisioned out of the GNBYWI11 POP (Ridge CO) | 155520, OC3 MMF connector | CW Order (ID : 190259557) CDR201404160024 IQBKX514 IQBKYBDS 5483577 | 6411635 | P2074355 | 5478106 | 44992 | BCBK5KHB0001 BCBK5LTT0001 W1B14855 | 41/OBGS/100215//WT LEC ORD: C2901648458 / Tracking ticket: WY013769 Ckt : 41/OBGS/100215//WT Tester: Erik (800-982-7144 opt 6) =================================================================== ADDRESS: 3100 AMS BLVD GREEN BAY WI 54313 Demarc: 1st Floor Telco RM ¦ Bay 3 ¦ Shelf 1 ¦ Ports 3 & 4 Tagged: Yes / Both IDs Extended: No | 5/22/2014 8/19/2014 | 7/17/2014 9/3/2014 | 2014-08-28 | bpdd |  | 2014-09-11 | unitedhealthgroup-64990 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | Activation scheduled for 10/2 at 1pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 4/17- pending CDR, currently with lease group. CDR201404160024 5/1- pending CDR 5/8- order submitted to provisioning; pending capacity check 5/14-pending lease/clr design, Once received for LOA/CFA, ASR will be send to WT33. 5/22- received LOA/CFA from Lease Group. ASR sent pending FOC date 5/28- Called LEC/WT33 // ASR PON: IQBKYBDSPQQUMB01 to follow up for the ETA for the FOC// advise that the enginnering still reviewing the ASR and once they done they will release a FOC for this request. 6/5- FOC date 7/17 6/12- FOC date 7/17 6/18- FOC date 7/17 6/25- FOC date 7/17 7/2- FOC date 7/17 7/9- FOC date 7/17 7/17- Per ATT they are still having issue with splicing. Provisioning requested an ECD. 7/24- LEC Status: Splicing is complete on this project. Checking if the order can be designed now. Once design is complete, LEC will deliver loop. There's an existing missed loop ticket open, B201407170020. 7/31- Per LEC design is still working on order. It had to go back to the construction team. Now it back in design. We are doing our best to complete it ASAP. 8/6- Per ATT, “Central Office work is successfully completed. The next step is to dispatch a technician to install an equipment at the premise. 8/14- LEC was not able to gain acces, order supp'ed for new due date. Pending new FOC 8/20- Pending FOC date 9/3 8/27- FOC date 9/3 9/3-circuit delivered. LOS seen by US Signal from our handoff. Sent TCA dispatch to check our cabling 9/10- As per Shannon of Lease, US signal will be ready 9/11/14 to test with our network 9/15- ready for activation; customer notified
2014-03-24 | ShaRita | NC004-05-IJ | 3131 RDU Center Drive , Morrisville, NC 27560 | 100mg ehernet with dport john will throttle down to 20mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd extend to Floor 2 MDF type 4 can not be extended | SFDC Opportunity ID O-0976415 Quote ID: 190212935 order request ID is 190214353 Service Order 190214539 20246317 access 20246316 port | 190214539 |  | 5463513 | 5008 | E4000656 C1003871 | 26/KQGN/401234//SB VZB DMARC: 2nd floor it room, wall mounted and customer will extend to their equipment HANDOFF TYPE: Electrical | 2014-04-02 | 2014-07-02 | 2014-07-02 | bpdd | 2014-07-10 | 2014-07-31 | UnitedHealthGroup-65288 | 860-702-8284 keith_mangene@optum.com | Activation scheduled for 10/8 at 8pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 4/10- pending site requirements, forwarded to John. FOC date 7/2 4/17- pending site requirements, forwarded to John. FOC date 7/2 4/23- pending site requirements, forwarded to John. FOC date 7/2 5/1- pending site requirements 5/8- pending site requirements 5/14- pending feedback from AT&T, on Monday tech will go to site to confirm if the (2) 1 ½” inner ducts are sufficient 5/22- ATT confirmed that work could be completed with the (2) 1 ½” inner ducts; site is ready; FOC date 7/2 5/28- FOC date 7/2 6/5- FOC date 7/2; pending complex build- ecd: 6/23 6/12- FOC date 7/2; pending complex build- ecd: 6/23 6/18- FOC date 7/2; pending complex build- ecd: 6/23 6/25- FOC date 7/2 7/2- circuit delivered; pending confirmation from John if demarc will be extended. ATT delivered the ckt already, demark: 2nd floor server room, wall mount. 7/16- pending confirmation if demarc will be extended 7/24- customer confirmed demarc. pending date for installation of beas equipment. 7/31- ready for activation; customer notified
2014-08-18 | ShaRita | NJ777-03-IJ | 800 Secaucus Road, Seacaucus, NJ 07094 address changed to 165 HALSEY ST, Newark on 8/28 | 1G internet circuit with 100M commit. Port only release CFA | new quote 190444136 new Order Request 190445707 New work orders 20471247 (access) 20471246 (port) NJY I143738 new order njy-I143867 |  |  |  |  | Access E5000443 port C1008919 | gx-1mk-1mk-0025 fs-1mk-1mk-0206 |  |  |  | bpdd | 2014-09-05 | 2014-10-08 |  |  |  | 8/14- there was a question on where to meet with equinix. We will be meeting them at 755 Secaucus per Steve B, this will requrie an access loop 8/21- it was decided to order a local loop into 800 secaucus, order sent to ShaRita 8/29- order cancelled and re-issued to Newark 9/10- pending node work 9/18- provisioning is working to get system issue resolved with order this week to prevent delay on order. Melissa and Siva are escalating 9/25- pending provisioning to provide LOA 10/2- LOA provided to customer, pending confirmation from customer that the circuit has been extended so that we may proceed with router test. 10/8- order closed to be billing
2014-08-01 | ShaRita | TX777-03-IJ | 1950 North Stemmons Freeway Suite 3050, Dallas TX 75207 | 1G internet circuit with 100M commit. Port only release CFA Dallas 07 | O-1078648 Quote ID: 190414724 Service Order(s) [ 190423597 ] has been created for Order Request 190420959 20440509 20440508 Internet Dedicated Services dal i96520 |  |  |  |  | Port C1008919 access E5000443 | gx1mk 1mk 0025 |  |  |  | bpdd | 2014-08-27 | 2014-10-03 |  | jon_langemak@optum.com |  | 8/11 ticket T0111160 pricing error 8/14- order submitted to ShaRita 8/21- pending provisioning and approval and update from provisioning on meeting that took place for final decision from planning, product marketing and access pricing teams on site availability for PIP router. 8/27-provisioning issues with the port assignment 9/3- interenet port assigned, designed from our pop to Equinix pop. need to dispatch to see what fibers are available. 9/8- CFA given to UHG. 9/10- testing of our network schedued for 9/12 9/18- working on final testing and closing of order. IP addressing provided 9/25- circuit is up for the customer. pending closing of order. 10/2- pending closing of order 10/8- order closed
2014-08-01 | ShaRita | TX777-02-IJ | 1950 North Stemmons Freeway Suite 3050, Dallas TX 75207 | 1G PIP will throttle down to 500M SMF LC connector give tie down info to Equinix for x-conn. BGP advertisement-interval set to 0. BFD Enabled. Line is provided by equinix, so no protection is provided by Verizon. Optic - GE-L 1310 | O-0528961 Quote Id 190400899 Order Request: 190415014 Service Order(s) [ 190420630 ] has been created for Order Request 190415014 20437815 access 20437814 port |  |  | 5509806 | 20M | C1008574 E5000403 | Tie Down: Cage: 21020 Router: 9O4XE01 Panel: PP:0000:175665 TX/RX: 27/28 |  |  |  | bpdd | 2014-08-29 | 2014-09-11 | UnitedHealthGroup- 65246 | 763-694-7333 skbrown1@optum.com | Activation scheduled for 10/3 at 11am CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 8/5- pending NSS 8/11- order sent to ShaRita 8/14- order submitted to provisioning 8/21- pending provisiong and approval and update from provisioning on meeting that took place for final decision rom planning, product marketing and access pricing teams on site availability for PIP router. 8/27- provisioning issues with the port assignment 8/28- LOA sent to John Tie Down: Cage: 21020 Router: 9O4XE01 Panel: PP:0000:175665 TX/RX: 27/28 9/3- pending closing of order 9/10- MUX dispatch/completion (escalated) 9/11- trouble with port coming up. ticket with Equinox
2014-08-04 | ShaRita | C1564-02-IJ | 2300 W Plano Parkway, Plano, tX 75075 expedited for 9/1 | 50M Ethernet Optical MMF LC MD5 UHGVEReccgas4Usp9 | SFDC #O-1076074 Quote 190407280 Service Order(s) [ 190415592 Order Request 190411008 20432532 access 20432531 port dal I0096431 |  |  | 5508502 | 1536 | C1008409 port E4001698 access | ea-d43-d43-0073 FACILITIES LOCATED AT: Address: 2300 W PLANO PKWY PLANO, TX 75075-8427 Designator: Building K Space(SP) data cntr FACILITY ASSIGNMENT: ISG5K Aisle: 00BD Bay: 31 Shelf: 9 Card: 2 Port: 1 |  | 2014-08-21 | 2014-08-21 | 9/8/2014 Expedite | 2014-08-28 | 2014-08-27 | UHGECC - 65451 | 763-744-2265 travis_dent@optum.com | Activation rescheduled for 10/13 at 10pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 8/7 -submitted to ShaRita as an expedite. 8/14- waiting for John to confirm building 8/21- John confirmed circuits for Dell will go into K2; provisioning approved, card in shaed beas is already mm card. no ccr work necessary stepped to opre for install 8/27- ready for activation; customer notified
2014-09-10 | ShaRita | none | 6363 N State Hwy 161 - Corporate Centre II IRVINE TX USA 75038 |  | NSPE0008564286 OQBK04BG |  |  |  |  | BCBK4D8S0001-0004 |  |  |  |  | 9/10/2014 (standard 30 business days) | 2014-10-09 | 2014-10-13 |  |  |  | 9/15- order sent to Sadisconnect 9/18- pending disconnect due date 10/9 9/25- pending disconnect due date 10/9 10/2- pending disconnect due date 10/9 10/8- soft disconnect done, pending hard disconnect 10/13- disconnect complete
2014-09-10 | ShaRita | none | 901 5th Avenue / Suite 1500 SEATTLE WA USA 98164 |  | NSPE0008572203 OQBK06NW |  |  |  |  | BCBKH66B0001 |  |  |  |  | 9/15/2014 (standard 30 business days) | 2014-10-09 | 2014-10-13 |  |  |  | 9/15- order sent to Sadisconnect 9/25- pending disconnect due date 10/9 10/2- pending disconnect due date 10/9 10/8- soft disconnect done, pending hard disconnect 10/13- disconnect complete
2014-03-24 | ShaRita | UTN18-05-IJ | 8 Cadillac Drive, Brentwood, TN 37027 | 100mg ehernet with dport john will throttle down to 20mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd | SFDC Opportunity ID O-0975884 Quote 190204657 Rev. 0 Order Request [ 190205229 ] Service Order(s) [ 190208392 ] has been created for Order Request 190205229 access 20240424 port 20240423 |  |  | 5460107 | 5008 | E4000630 C1003716 | T4/KQGN/823082//SC DMARC Info: 4th Floor Server Rm, Rack 2, mounted. | 4/7/2014 5/19/2014 | 5/6/2014 6/10/2014 | 5/6/2014 6/9/2014 | bpdd | 2014-05-13 | 2014-06-12 | UnitedHealthGroup-64804 | 860-702-8284 keith_mangene@optum.com | Activation scheduled for 10/16 at 6pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 3/24- order submitted 3/27- order submitted to provisioning 4/3-Order is still in pending ASR transmission status due to info needed from the SAR file. 4/10- pending FOC date 4/17- pending FOC date 4/23- There is a build on this order; pending build details from LEC and FOC date 5/8- circuit delivered; pending beas installation/rfc testing 5/14- beas installed; pending end to end testing 5/22- AT&T delivered 10M circuit instead of 100M. ASR sent to AT&T; pending new FOC date 5/28- escalating to provisioning to submit the ASR and then escalate to LEC for a new FOC date 5/29- We received an FOC of 6/10 but we are still coordinating this with the LEC to improve the FOC date. 6/5- FOC date 6/10 6/10- ready for activation; customer notified
2014-09-04 | ShaRita | C1564-05-IJ | 2300 W Plano Parkway, Plano, TX 75075 building K2 | 200M ethernet with handoff 1000 Base-SX optical LC, MD5 UHGVEReccgas4Usp9 | O-1090507 Quote ID: 190456510 Order Request 190456691 Service Order 190463338 Service Order(s) [ 190463338 ] has been created for Order Request 190456691 20490653 access 20490652 port dal I96622 |  |  |  | 1536 | C1009277 E5000462 | ea-d43-d43-0074 Customer is demarc building K2 floor 1st room telco |  |  |  | bpdd | 2014-10-03 | 2014-09-30 | UHG-ECC-65449 | 763-744-2265 travis_dent@optum.com | Activation scheduled for 10/20 at 6pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 9/4-sent to ShaRita 9/10- order submitted, pending provisioning approval 9/18- no existing nni's with capacity. Pending circuit design by provisioning, likely will need to engineer for build. 9/22- pending CCR 1228006 gig-e card install in overture 5100 , current Ready date of 10/14 9/25- Site survey complete no cable pull required...Pending ccr with an RFT Dates: Current: 10/14/2014, card recieved and scheduled for install on 9/26 10/2- ready for activation, customer notified
2014-07-28 | ShaRita | UKS08-10-CJ | 6860 West 115th Street Overland Park, KS 66211 | upgrade from 50mg to 100 mg ethernet | Smatform 190394863 NSPE0008419250 OQBKZ889 (out) OQBKZ896 (out) IQBKZ89X (in access) IQBKZ898 (in port) | 6532862 | P1927818 (out) P1927819 (out) P2084840 (in) P2084843 (in) | 5506767 | 30000 | BCBK6B040001 (in) EDBK6B000001 (in) EDBKS4D50001 (out) BCBKS4FH0001 (out) | 74/KQGN/905530//SW | 8/12/2014 9/17/2014 | 9/12/2014 9/17/2014 | 2014-09-17 | bpdd | 2014-10-24 | 2014-09-23 | unitedheatlhgroup- 64905 | 763-744-1556 john_l_rothstein@optum.com | activation scheduled Wednesday, October 22, 2014 8:00 PM-9:00 PM. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 8/1- ShaRita is working 8/6- pending provisioning approval 8/14- pending FOC 8/21- FOC date 9/12 8/27- FOC date 9/12 9/3- FOC date 9/12 9/10- FOC date 9/12 9/17- circuit installed; pending demarc confirmation from John 9/25- ready for hotcut; customer notified
2014-05-20 | B End- Marc | SP504-06-IJ | Carrer del Cister 2 Barcelona 08022 Spain | 30M ethernet SOO Letterkenny - circuit ID W0Y12673 MD5 UHGVERbgpbqZyofa No Dport | OVI# 1-1324015505 s/o 5509501 (processed as upgrade) RELATED DISCONNECT ORDER ON S/O; 5509518 |  |  | 5498406 | 3072 | W1B24093 disco W1A83113 | BCN/BCN/LE-1. | 2014-06-30 | 2014-08-18 |  | bpdd | 2014-09-09 |  | unitedhealthgroup-65095 | 981-005-9326 pradeep_yadav@optum.com | completed Aug 27th | 5/20- Marc pulling pricing for 30mb, 50mb & 100mb ? 5/29- checking with Marc on pricing, John says to go with 30mg 6/4- pricing provided and SOF being generated 6/18- SOF signed and sent to Marc 6/25- order in OE, let them know to update lcon information 7/30- order in Barcelona is ready for hotcut. Can you please provide time and date? Please note we need 3 working days’ notice to schedule all parties and 5 days in case of out-of-hours 5pm-9am (750 USD single charge would apply of ooh as well).
2014-06-20 | ShaRita | NC001-03-IJ | Connextions- 4601 Corporate Drive NW, Concord, NC 28027 | 100M Ethernet RJ45 handoff | O-1046272 Quote ID: 190336411 Order Request 190337454 Service Order(s) [ 190342772 ] has been created for Order Request 190337454 20361218 access 20361217 port | 190342772 |  | 5495590 | 30000 | C1006441 E4001308 | NC/VLXP/635205/ /WINS/ DMARC: Metronid located in main telco room, suite 115. Approx. 4 feet from back wall in a rack, in the middle isle, sitting beside a hatteras 408 | 2014-07-01 | 9/19/2014 9/24/2014 | 2014-09-24 | bpdd | 2014-09-26 | 2014-10-17 | Connextions- 65221 | 407-926-2400 x10390 jose.hanchi@connextions.com | 10/20 at 3pm CST Bridge Number: 866-692-3158 Passcode: 9236734 | 7/9- pending FOC date, Per LEC PM we should receive FOC by 7/15/14. 7/17- FOC date 9/19. BTDD Ticket to be filed 7/24- FOC date 9/19. PM Kelli, There is not a fiber build, there is an Outside Plant work order to splice & test fibers that is in progress before it can move to our transport engineering group to do their portion. She will notify & send notification once VLAN has been assigned. It will be a couple of weeks before that is available. 7/31- FOC date 9/19 8/6- FOC date 9/19 8/21- FOC date 9/19 8/27- FOC date 9/19 9/3- FOC date 9/19 9/10- FOC date 9/19 9/17- BNE tech Arjay called wind stream (LEC) per conversation circuit is not yet turned up, it is not completed yet. Will try monitor if early loop delivery would be possible. Note: Foc date 09/19 9/25- circuit delivered; pending scheduling of beas installation and end to end testing 10/2- We are done with the line testing for this order. And we are now in the process of stepping this order to the dispatch team (RNC), however we encountered error in provisioning the MV-Lan of this circuit, and we created a CC ticket for this (A201409300065). Advised by Prod Support to contact the GTNOC to open up a ticket for this to do a master reboot of the box. The ticket number from GTNOC is 2014093020052. Called them today around 10:40AM and spoke with a rep, as per him this ticket is already assigned to a tech, but there is no ETA. Once this issue will be resolved and we are able to provision the MV-lan we can then proceed in scheduling a beas installation. 10/8- The LEC has now installed the missing SPF card. BEAS is scheduled for install 10/13 10/16- Line test passed with LEC (Windstream), we are now stepping order to have BEAS installation rescheduled. (ESCALATED) 10/20- ready for activation, customer notified. activaton completed.
2014-09-19 | ShaRita | none | 1001 Winstead Drive / Suite 200 CARY NC USA 27513 |  | NSPE0008598025 OQBK08RH |  |  |  |  | BCBKWJ960001-2 |  |  |  |  | 9/22/2014 (standard 30 business days) | 2014-10-16 | 2014-10-21 |  |  |  | 9/19- order sent to Sadisconnect 9/25- disconnect due date 10/16 10/2- disconnect due date 10/16 10/8- disconnect due date 10/16 10/15- soft disconnect complete. Pending hard disconnect. 10/21- disconnect complete
2014-09-19 | ShaRita | none | 400 Mann Street / Suite 901 CORPUS CHRISTI TX USA 78401 |  | NSPE0008598051 OQBK08R4 |  |  |  |  | BCBKT05T0001-2 |  |  |  |  | 9/22/2014 (standard 30 business days) | 2014-10-16 | 2014-10-20 |  |  |  | 9/19- order sent to Sadisconnect 9/25- disconnect due date 10/16 10/2- disconnect due date 10/16 10/8- disconnect due date 10/16 10/15- soft disconnect complete. Pending hard disconnect. 10/20- disconnect complete
2014-09-19 | ShaRita | none | 3900 McCarty Lane Lafayette IN USA 47904 |  | NSPE0008598178 OQBK08RM |  |  |  |  | BCBKWLTG0001-2 |  |  |  |  | 9/22/2014 (standard 30 business days) | 2014-10-16 | 2014-10-20 |  |  |  | 9/19- order sent to Sadisconnect 9/25- disconnect due date 10/16 10/2- disconnect due date 10/16 10/8- disconnect due date 10/16 10/15- soft disconnect complete. Pending hard disconnect. 10/20- disconnect complete
2014-08-26 | ShaRita | C1409-04-IJ | 200 Arlington Street, Chelsea, MA 02150 | 50M Ethernet 1000 Base-SX - Optical LC UHGVEReccgas4Usp9 | O-1089752 Quote ID: 190460563 Order Request 190462257 Service Order(s) [ 190464903 ] has been created for Order Request 190462257 20494643 access 20494642 port |  |  | 5519886 | 1536 | E4001968 C1009109 | 95.KFGS.003497..NE DMARC Info: MAIN BLDG FLR 3rd RM TELCO customer Address:200 ARlington CHE MA 02150 | 2014-09-11 | 2014-09-24 | 2014-09-24 | bpdd | 2014-10-01 | 2014-09-24 | UHG-ECC-65450 | 763-744-2265 travis_dent@optum.com | activation scheduled Friday, October 24, 2014 8:00 PM-9:00 PM Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 8/28- pricing error 9/4- escalating on ticket T0206973 for pricing error 9/10- pending provisioning approval 9/16- FOC date for 9/24 9/24- circuit ready for activation; customer notified
2014-09-11 | ShaRita | URI44-04-CJ | Connextions, 70 Royal Little dr, Providence RI 02904 | 100M upgrade from 50M need to disco BCBK1SJS0001 | SFDC# O-1100740 Quote ID: 190472032 Order Request 190472491 Service Order 190480265 20513718 access 20513717 port |  |  | 5523510 | 30mg | C1009381 E4002050 | 85.KEGS.013875..NE DMARC Info: first floor server room rack 2 mounted just above the conoga perkins for this order | 2014-09-19 | 2014-10-21 | 2014-10-21 | bpdd | 2014-11-14 | 2014-10-24 | Connextions-65233 | 407-926-2400 x10390 jose.hanchi@connextions.com | activation COMPLETE for Oct 30th at 1030am CST Bridge Number: 866-692-3158 Passcode: 9236734 | 9/18- pending lcon verification 9/25- order on hold, pending site readiness. Requirements forwarded to Jose. 10/2- FOC date 10/21 10/8- FOC date 10/21 10/15- FOC date 10/21 10/23- circuit delivered. Pending beas installation 10/27- ready for activation; customer notified 10/30- Activation completed, customer accepted circuit
2014-09-25 | B end | UIX50-07-IJ | Unitech World (Cyber Park) - Sector 39, Building B - 14th, Gurgaon, Haryana 122001 | 300M Ethernet Optical MMF LC connector MD5 UHGVERbgpbqZyofa SOO to Letterkenny - circuit ID W0Y12673 |  |  |  |  | 16320 | [5 empty] | bpdd |  |  | unitedhealthgroup-64896 | 763-744-2081 tim_gunderson@uhc.com |  | 9/30- pending SOF 10/10- updated SOF with UHG 10/28- per John Cancel
2012-11-02 | ShaRita | UCA92-05-IJ | Santa Ana, CA | 100M access ethernet with 50M port with MD5 UHGVERbgpbqZyofa Type 4. Handoff MMF/LC | SAR Id is 1-1LAF731 confirmation 132030 expiration 05/18/2013 smartform 189754742 Request ID: CP27729.00 iNet Per #: 11081207 NSPE0006121729 IQBKFYW0 EACS IQBKFZW1 Port | 5651927 | P1969305 (EACS) P1969628 (port) | 5255961 | 22000 | EDBKXHGX0001 (EACS) BCBKXH1G0001 (port) | 13/KRGN/578046//PT DMARC: 2nd floor data room, relay rack 200.07 optical port number 1 on cisco | 11/30/2012 3/12/2013 | 3/7 (estimated) 7/29/13 (estimated) 9/13/13 estimated 5/13/2014 | 2014-05-14 | bpdd | 2014-06-16 | 2014-06-17 | unitedhealthgroup-64822 | 763-744-1575, daniel_j_skripka@uhc.com | Activation rescheduled for 11/03 at 7pm CST. Conference Bridge: 866-692-3158 Conference Pass Code: 9236734 | 2/14- order on hold; pending site readiness. 2/20- order on hold; pending site readiness. Customer, Daniel, advised that Arien Heinrich from Comnet is on site this week to trace the entire path this week, and will be contacting him to arrange a time to meet with Blake, LEC PM. 2/27- will contact Daniel March 3rd to see if site is ready 3/6- Arien Heinrich from Comnet confirmed the innerduct path issues have been resolved. Blake and Arien are planning the final walkthrough the end of this week or early next week. 3/12- customer advised site is ready; pending new FOC date from LEC 3/20- pending LEC to provide FOC date 3/27- asked provisioning to check with LEC to confirm when FOC date will be received; pending response. 4/3- currently we are waiting for a revised ECD (expected complete date) which has no ETA at the moment lec would have to check everything again since order has been on hold for long, he said that it would take another week or 2 for an update in regards with the ECD." 4/10- Revised ECD is 4/23/14, FOC is going to be available after that date. 4/17- Pending FOC date 4/23- Pending FOC date 5/1- escalated to provisioning in regards to pending FOC date 5/8- FOC date 5/13 5/14- circuit delivered; pending beas installation/rfc testing 5/22- requested to have a new beas for ac power as per advise by the provisioner; coordinating with the CPE coordinator in regards with the new BEAS for AC power, right now we are awaiting ETA on the CPE 5/28- pending date for installation of beas 6/5- beas installation incomplete due to an IP address conflict on our network. once issue resolved will redispatch 6/11- IP address issue resolved; pending dispatch to be rescheduled 6/17- ready for activation; customer notified
2014-10-15 | ShaRita | none | 1950 North Stemmons Freeway Suite 3050, Dallas TX 75207 | VLAN add | O-1122444 Quote ID: 190545516 Change order submitted, Service Order(s) [ 190568714 ] has been created for Order Request 190568632. 20579874 port |  |  | 5509806 |  | C1008574 |  |  |  |  | bpdd | 2014-11-05 | 2014-11-04 |  |  | hotcut scheduled 11/11 at 10pm CST Bridge Number: 866-692-3158 Passcode: 9236734 | 10/16-scheduling a call with Steve b to understand what is needed 10/23- change order required to add vlan tagging. 10/29- This order is with the VRD Change Order Support team because of a task that encountered an error. 11/6- ready for hotcut; customer notified
2014-10-06 | ShaRita | none | 1333 West Loop South / Park Towers / 11th floor HOUSTON TX USA 77027 |  | NSPE0008648664 OQBK1JCN |  |  |  |  | p1963231 BCBKW29R0001-7 |  |  |  |  | 10/3/2014 (standard 30 business days) | 2014-10-30 | 2014-11-04 |  |  |  | 10/8- pending disconnect due date of 10/30 10/15- pending disconnect due date of 10/30 10/23- pending disconnect due date of 10/30 10/30- awaiting soft disconnect 11/6- disconnect complete
2014-10-06 | ShaRita | none | 48 Monroe Turnpike TRUMBULL CT USA 06611 |  | NSPE0008648759 OQBK1JP8 |  |  |  |  | BCBKRXH20001 |  |  |  |  | 10/3/2014 (standard 30 business days) | 2014-10-30 | 2014-11-03 |  |  |  | 10/8- pending disconnect due date of 10/30 10/15- pending disconnect due date of 10/30 10/23- pending disconnect due date of 10/30 10/30- awaiting soft disconnect 11/6- disconnect complete
2014-10-06 | ShaRita | none | 48 Monroe Turnpike TRUMBULL CT USA 06611 |  | NSPE0008648759 OQBK1JQB |  |  |  |  | BCBKR0V90001 |  |  |  |  | 10/3/2014 (standard 30 business days) | 2014-10-30 | 2014-11-06 |  |  |  | 10/8- pending disconnect due date of 10/30 10/15- pending disconnect due date of 10/30 10/23- pending disconnect due date of 10/30 10/30- awaiting soft disconnect 11/6- disconnect complete
2014-10-10 | ShaRita | none | 3803 North Elm Street GREENSB ORO NC USA 27455 |  | NSPE0008673049 OQBK1QM7 |  |  |  |  | BCBKJSBL0001 |  |  |  |  | 10/10/2014 (standard 30 business days) | 2014-11-06 | 2014-11-07 |  |  |  | 10/14- submitted to Sadisconnects 10/23- pending disconnect due date of 11/6 10/30- pending disconnect due date of 11/6 (per John's request disconnect asap) 11/6- escalated to have disconnect completed asap 11/13- disconnect complete
2014-06-20 | ShaRita | IN001-03-IJ | Connextions- 200 Patrol Rd., Jeffersonville, IN 47130 | 100M Ethernet RJ45 handoff | O-1046273 Quote ID: 190336600 Service Order(s) [ 190342868 ] has been created for Order Request 190337564 20361298 access 20361297 port lou I688 | 190342868 |  | 5495631 | 30000 | C1006274 E4001320 | c5-d4d-gm89-0008 TELCO CKT ID: /OBGS/101184//NB DMARC: first floor telco board lgx terminal positions 13 and 14 tagged | 2014-07-24 | 10/2/2014 10/10/2014 | 2014-11-04 | bpdd | 2014-10-09 | 2014-11-11 | Connextions- 65222 | 407-926-2400 x10390 jose.hanchi@connextions.com | Activation scheduled for Nov. 19 at 10am CST Bridge Number: 866-692-3158 Passcode: 9236734 | 7/17- CCR resolution date is 7/25... still no ASR sent. 7/24- CCR complete; ASR submitted. Pending FOC. 7/31- provisioning has ticket open due to error when ASR submission. 8/6- pending FOC date (escalate to provisioning) 8/14- pending FOC date (Escalated to 5th level) 8/21- pending FOC date, build for AT&T (CO going to prem) which estimated time is 10/13. 8/27- FOC date 10/2 9/3- FOC date 10/2 9/10- FOC date 10/2 9/17- FOC date 10/2 9/25- FOC date 10/2 10/2- pending confirmation circuit was delivered 10/8- ****This order is a multi LEC order with 2 LECS both from AT&T. Pending Loop delivery ICSC:SC02 FOC:10/10. ****The DD was moved to 10/10/14 on Order C2902666421 NB01 because the due date on order C4FCG1V8 SC02 was set for 10/10/14 As those two orders ( A LOC in KY and Z LOC in IN)) were submitted to deliver one Sonnet service to End User, both orders needs to be turned up the same date because of the testing process. DD on order C2902666421 was just aligned with DD of KY order.****** 10/15- missed loop, LEC Status :Low light levels in fiber pending update from the tech assigned. 10/23- ESCALATED. The AT&T technician encountered excessive signal lost on the fibers during test and turn up. Escalation has been sent to splicing group for dispatch to clear the fibers. We are waiting to hear ETA on fiber repair . 10/29- Escalated AT&T construction is still working on resolving the fiber issue that was discovered during the testing phase of the installation. 11/6- The 09:00 AM dispatch scheduled for today had to be canceled due to a priority 1 ticket. The dispatcher is checking to reschedule the dispatch for the first available date. 11/11- ready for activation, customer notified
2014-10-15 | ShaRita | none | MPLS - BCBJGGP10001, we want to add UHGECC VPN and remove Connextions 3534 MERCY DR , orlando FL | Change | CQBHKR5Z | 8074488 |  | 1592612 | 20000 | BCBJGGP10001 | [8 empty] | Leon Betterman |  | 10/16- pending CDR 10/23- waiting for John to provide date and time for cutover to reflect new VPN. Gold Car upgraded to 20mg 10/29- waiting for John to provide date and time for cutover to reflect new VPN. Gold Car upgraded to 20mg
2014-09-08 | ShaRita | UFL88-08-IJ | 5908 HAMPTON OAKS PKWY, TAMPA, FL 33610 slot 11 | New muxed DS3 | NSPE0008558361 CDR201409100048 IQBK02HC | 8004433 | P2089146 |  |  | AOBK6MKF0001 | LEC ORDER: CGC4273386109 69/HFGS/305817//GTES Demarc: Century Link pop gte-1 mounting space 16 g7 3 ( high speed hand off-OC12) Extended(Y/N): N Tagged (Y/N): Y secCFA 101M/OC48/23/TAMPFLXEH88/TAMRFLIYW01 | 9/16/2014 9/19/2014 10/2/2014 | 9/26/2014 10/15/2014 | 2014-10-15 | bpdd | 2014-10-20 | 2014-10-16 |  | Trevor Lewellen - trevor.lewellen@connextions.com – 407-963-9537 |  | 9/9- Sent to ShaRita. 9/10- Pending CDR to be approved before order can be submitted to Order Entry 9/17- ASR submitted, pending FOC date 9/18- LEC FOC for 9/26 9/25- John requested to change slot. Order supp'ed, pending new FOC date. provisioning created tkt regarding asr issue. will monitor cc tkt for resolution. 10/2- Order re-supp'ed to change slot to 47. pending new FOC date 10/8- FOC date 10/15 had to move to slot 23.....per call with Verizon and CL. 10/16- circuit delivered, pending end to end testing. 10/23- ready for activation, customer notified
2014-10-15 | ShaRita | none | 3131 RDU Center Drive - Suite 200 MORRISVIL LE NC USA 27560 |  | NSPE0008688563 OQBK1TL9 |  |  |  |  | bcbk1gs50001 |  |  |  |  | 10/17/2014 (standard 30 business days) | 2014-11-12 | 2014-11-19 |  |  |  | 10/16- submitted to Sadisconnects 10/23- pending disconnect due date of 11/12 10/29- pending disconnect due date of 11/12 11/6- pending disconnect due date of 11/12 11/13- soft disconnect done 11/20- disconnect complete
2014-10-27 | ShaRita | none | 7100 College Blvd OVERLAND PARK KS USA 66210 |  | NSPE0008722502 OQBK10S3 |  |  |  |  | BCBK3CX80001 to 4 |  |  |  |  | 10/24/2014 (standard 30 business days) | 2014-11-20 | 2014-11-25 |  |  |  | 10/27- submitted to Sadisconnects 11/6- disconnect due date 11/20 11/13- disconnect due date 11/20 11/20- awaiting soft disconnect 11/26- disconnect complete
2014-10-27 | ShaRita | none | 170 Parkway West DUNCAN SC USA 29334 |  | NSPE0008722574 OQBK10V5 |  |  |  |  | BCBJTXS00001 |  |  |  |  | 10/24/2014 (standard 30 business days) | 2014-11-20 | 2014-11-25 |  |  |  | 10/27- submitted to Sadisconnects 11/6- disconnect due date 11/20 11/13- disconnect due date 11/20 11/20- awaiting soft disconnect 11/26- disconnect complete
2014-10-21 | ShaRita | none | 6150 Trenton Ln Plymouth MN 55442 |  | NSPE0008703662 OQBK1VJZ |  |  |  |  | P1890250 BCBKN8P00001-0005 |  |  |  |  | 10/21/2014 (standard 30 business days) | 2014-11-19 | 2014-11-24 |  |  |  | 10/21- submitted to Sadisconnects 10/29- pending disconnect due date 11/19 11/6- pending disconnect due date 11/19 11/13- pending disconnect due date 11/19 11/20- soft disconnect completed, pending disconnect completion 11/26- disconnect complete
2014-10-20 | ShaRita | none | 15325 SE 30th Place BELLVUE WA USA 98007 |  | NSPE0008703831 OQBK1YDD |  |  |  |  | BCBK3FC30001-6 |  |  |  |  | 10/21/2014 (standard 30 business days) | 2014-11-19 | 2014-11-24 |  |  |  | 10/29- pending disconnect due date of 11/19 11/6- pending disconnect due date of 11/19 11/13- pending disconnect due date of 11/19 11/20- soft disconnect completed, pending disconnect completion 11/26- disconnect completed
2014-10-21 | ShaRita | none | 8 Cadillac Drive BRENTWO OD TN USA 37027 |  | NSPE0008703547 OQBK1VHZ |  |  |  |  | BCBKSKJB0001 |  |  |  |  | 10/21/2014 (standard 30 business days) | 2014-11-20 | 2014-11-24 |  |  |  | 10/21- submitted to Sadisconnects 10/29- pending disconnect due date of 11/20 11/6- pending disconnect due date of 11/20 11/13- pending disconnect due date of 11/20 11/20- soft disconnect completed, pending disconnect completion 11/26- disconnect completed
2014-11-10 | ShaRita | none | 3100 Lake Center Drive SANTA ANA CA USA 92704 |  | NSPE0008771824 OQBK2CKW |  |  |  |  | BCBJGLV30001 |  |  |  |  | 11/7/2014 (standard 30 business days) | 2014-12-04 | 2014-12-04 |  |  |  | 11/10- submitted to Sadisconnects 11/13- pending disconnect due date 12/4 11/20- pending disconnect due date 12/4 11/26- pending disconnect due date 12/4 12/4- soft disconnect done. Pending disconnect completion 12/11- disconnect complete
2014-11-10 | ShaRita | none | 11300 NW 25th Street MIAMI FL USA 33172 |  | NSPE0008771869 OQBK2CMC |  |  |  |  | BCBKYF560001 |  |  |  |  | 11/7/2014 (standard 30 business days) | 2014-12-04 | 2014-12-04 |  |  |  | 11/10- submitted to Sadisconnects 11/13- pending disconnect due date 12/4 11/20- pending disconnect due date 12/4 11/26- pending disconnect due date 12/4 12/4- soft disconnect done. Pending disconnect completion 12/11- disconnect complete
2014-08-27 | ShaRita | C1565-01-IJ | 2501 S State Hwy 121, Lewisville, tX 75067 Building 5 suite 500 75067 | 50M Ethernet 1000 Base-SX - Optical LC UHGVEReccgas4Usp9 | O-1090507 Quote ID: 190444279 Order Request 190445500 Service Order(s) [ 190448485 ] 20471316 access 20471315 port |  |  | 5515598 | 1536 | E4001846 C1008752 | 12/KFGS/700571//GTEC DMARC Info: ISG400 installed on first floor, MDF room, RR NIDH01R1, shelf 22, tagged with both ID's, not extended. beas is pingable and ready for remote certification and RFC testing. there is no loop. handoff to customer is single mode LC fiber port 0.1 | 2014-08-29 | 10/16/2014 10/10/2014 |  | bpdd | 2014-10-23 | 2014-10-27 | UHG-ECC-65488 | 763-744-2082 eric_taylor@optum.com | activation rescheduled for 12/16 at 730pm CST Bridge Number: 866-878-8630 pass code: 6653710 | 8/28- submitted to ShaRita 9/3- pending FOC 9/10- FOC date 10/16 9/17- FOC date 10/16 9/25- FOC date 10/16 10/2- FOC date 10/16 10/8- LEC pulled FOC date in to 10/10 10/15- circuit delivered, pending demarc extension 10/23- lcon confirmed NID and BEAS will be next to each other. pending scheduling of beas installation
2014-09-10 | ShaRita | FL106-02-IJ | 2627 WEST TORCH LAKE DRIVE, The Villages, FL 32163 | 3072 2xT1 md5 UHGVERbgpbqZyofa | O-1099470 Quote ID: 190467765 Order Request 190467860 Service Order(s) [ 190476961 ] has been created for Order Request 190467860 20510665 access 20510664 port |  |  | 5522526 | 1536 | C1009360 N1005895,N1005896 | 25.HCGS.262310..UFLG 25.HCGS.262309..UFLG DEMARC LOC: 1st flr rear of bldg electrical room port 1,2 RJ 48X with open plug Tagged with ckt ids not extended DEMARC LOC Continued: No Extended Wire (Yes or No): No Jack Type: rj48c | 2014-09-19 | 2014-10-01 |  | bpdd | standard 10/3 | 2014-10-08 | unitedhealthgroup-64901 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@optum.com | activation rescheduled for12/17 at 2pm CST Bridge Number: 866-692-3158 pass code: 9236734 | 9/11- order sent to ShaRita 9/17- order submitted to provisioning 9/25- FOC date 10/1 10/2- pending confirmation from LEC that circuit was installed 10/8- circuit ready for activation, customer notified
2014-12-04 | ShaRita | none | Dallas 1950 North Stemmons Freeway Suite 3050, Dallas TX 75207 | downgrade to 500mg | SFDC# O-0958374 Quote ID: 190664665 Order Request 190665118 Service Order(s) [ 190671027 ] has been created for Order Request 190665118 20664834 port |  |  |  |  | C1008574 |  |  |  |  | 2014-12-19 | 2014-12-18 |  |  |  | scheduled for 12/18 at 10pm CST Bridge Number: 866-692-3158 Passcode: 9236734 | 12/4- need to submit downgrade 12/11-ready for hotcut, customer notified
2014-10-21 | Bend | none | 3333 Cote Vert, St. Laurent / Suite 710 MONTREAL CANADA H4R 2N1 |  | NSPE0008703587 s/o: 5573586 port s/o: 5573587 access | 8078367 |  |  |  | W0Z67807 (port) W0Z67805 W0Z67806 |  |  |  |  | 10/21/2014 (standard 30 business days) | 2014-12-22 |  |  |  |  | 10/21- pending provisioning approval 10/29- ORDER TO DISCONNECT SENT TO TELCO (TELUS) OCT 24TH 2014 HERE ARE YOUR ORDER DETAILS: 1. TELUS ORDER : D4340-1637-48-14, TELUS CIRCUIT #: 55DHXS247154000ABGT000 2. TELUS ORDER : D4340-1638-48-14, TELUS CIRCUIT# : 55DHXS247156000ABGT000 PSI FOX: 2153996 FOR BOTH ORDERS STOP BILL DATE: 22/12/2014
2014-11-26 | ShaRita | none | 8333 Forest Point Blvd. Charlotte NC USA 28273 |  | NSPE0008822392 OQBK23VH |  |  |  |  | BCBKLCKX0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2015-01-05 | 2015-01-07 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- escalated to Sadisconnects to process request ASAP 12/17- pending disconnect due date 1/5 1/8- disconnect complete
2014-11-26 | ShaRita | none | 70 Royal Little Drive PROVIDEN CE RI USA 02904 |  | NSPE0008822494 OQBK2WRV |  |  |  |  | BCBK1SJS0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-23 | 2014-12-26 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- pending disconnect due date 12/23 12/17- pending disconnect due date 12/23 1/8- disconnect complete
2014-11-26 | ShaRita | none | 2220 Campbell Creek RICHARDS ON TX USA 75082 |  | NSPE0008822497 OQBK2T7Z OQBK2T76 |  |  |  |  | BCBK0K450001 EDBK0KPN0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-24 | 2014-12-29 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- pending disconnect due date 12/24 12/17- pending disconnect due date 12/24
2014-11-26 | ShaRita | none | 9395 John Young Parkway - Headquarter s ORLANDO FL USA 32819 |  | NSPE0008822480 OQBK2T78 |  |  |  |  | BCBK00J00001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-24 | 2014-12-30 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- pending disconnect due date 12/24 12/17- pending disconnect due date 12/24 1/8- disconnect complete
2014-11-26 | ShaRita | none | 910 15th Street - Suite 350 Denver CO USA 80202 |  | NSPE0008822462 OQBK2T74 OQBK2T8V |  |  |  |  | BCBK2FPH0001 EDBK2DXD0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-24 | 2015-01-05 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- escalated to Sadisconnects to process request ASAP 12/17- order issued, pending disconnect due date 1/8- disconnect complete 1/5
2014-11-26 | ShaRita | none | 5150 Regent Blvd IRVING TX USA 75063 |  | NSPE0008822464 OQBK2W42 |  |  |  |  | BCBKS7520001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-23 | 2014-12-26 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- pending disconnect due date 12/23 12/17- pending disconnect due date 12/23 1/8- disconnect complete
2014-11-26 | ShaRita | none | 4601 Corporate Drive NW - Building 1 CONCORD NC USA 28027 |  | NSPE0008822283 OQBK2T72 |  |  |  |  | MGBJ0GSW0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-24 | 2014-12-24 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/17- order issued, pending disconnect due date 1/8- disconnect complete 12/24
2014-11-26 | ShaRita | none | 5749 San Felipe HOUSTON TX USA 77057 |  | NSPE0008822196 OQBK2PQG |  |  |  |  | BCBK3RYM0001-2 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-24 | 2014-12-24 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending disconnect due date 12/24 12/17- pending disconnect due date 12/24 1/8- disconnect complete 12/24
2014-11-26 | ShaRita | none | 1003 Broad Street / Bldg C / Suite 300 JOHNSTO WN PA USA 15907 |  | NSPE0008822124 |  | P1955998 |  |  | BCBKWD0C0001-4 |  |  |  |  | 11/26/2014 (standard 30 business days) |  | 2013-02-08 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- escalated to Sadisconnects to process request ASAP 12/17- disconnect was completed 2/8/13
2014-11-12 | ShaRita | none | 3100 AMS Blvd GREEN BAY WI USA 54313 |  | NSPE0008784692 OQBK2FF2 |  |  |  |  | BCBH7WT20001 |  |  |  |  | 11/14/2014 (standard 30 business days) | 2014-12-11 | 2014-12-11 |  |  |  | 11/12- submitted to Sadisconnects 11/20- pending disconnect due date 12/11 11/26- pending disconnect due date 12/11 12/4- pending disconnect due date 12/11 12/11- pending soft disconnect 12/17- disconnect complete
2014-11-12 | ShaRita | none | 3100 AMS Blvd GREEN BAY WI USA 54313 |  | NSPE0008784692 OQBK2FF3 |  |  |  |  | bcbkwhfb0001 |  |  |  |  | 11/14/2014 (standard 30 business days) | 2014-12-11 | 2014-12-11 |  |  |  | 11/12- submitted to Sadisconnects 11/20- pending disconnect due date 12/11 11/26- pending disconnect due date 12/11 12/4- pending disconnect due date 12/11 12/11- pending soft disconnect 12/17- disconnect complete
2014-11-12 | ShaRita | none | 1208 Point Center Drive / Suite 230 CHATTANO OGA TN USA 37421 |  | NSPE0008784803 OQBK2FTS |  |  |  |  | BCBKNL5S0001-2 |  |  |  |  | 11/14/2014 (standard 30 business days) | 2014-12-11 | 2014-12-11 |  |  |  | 11/12- submitted to Sadisconnects 11/20- pending disconnect due date 12/11 11/26- pending disconnect due date 12/11 12/4- pending disconnect due date 12/11 12/11- pending soft disconnect 12/17- disconnect complete
2014-11-12 | ShaRita | none | 13 Cornell Road - 2nd Floor LATHAM NY USA 12110 |  | NSPE0008784612 OQBK2FF4 |  |  |  |  | BCBK21HW0001-8 |  |  |  |  | 11/14/2014 (standard 30 business days) | 2014-12-11 | 2014-12-11 |  |  |  | 11/12- submitted to Sadisconnects 11/20- pending disconnect due date 12/11 11/26- pending disconnect due date 12/11 12/4- pending disconnect due date 12/11 12/11- pending soft disconnect 12/17- disconnect complete
2014-11-14 | ShaRita | none | 1525 NW 98th Court Doral, FL 33172 |  | NSPE0008791040 OQBK2F33 |  |  |  |  | BCBK2SYD0001-4 |  |  |  |  | 11/14/2014 (standard 30 business days) | 2014-12-11 | 2014-12-11 |  |  |  | 11/12- submitted to Sadisconnects 11/20- pending disconnect due date 12/11 11/26- pending disconnect due date 12/11 12/4- pending disconnect due date 12/11 12/11- pending soft disconnect 12/17- disconnect complete
2014-04-15 | B end | IT508-02-IJ | Via Cornelio Magni 15 , 00147 Rome Italy | 10M ethernet sooo Letterkenny - circuit ID W0Y12673 MD5 UHGVERbgpbqZyofa | s/o 5493954 |  |  | 5490020 | 3072 | W1B18665 |  |  | 2014-10-20 | 2014-10-20 | bpdd | 2014-11-27 | 2014-11-07 | unitedhealthgroup-65263 | 763-694-7409 terry_bjorke@optum.com | terry accepted the circuit 1/15/2015 | 6/12- order sent to telecom italia 6/20- pending ptt of 7/8 7/10- following up with B end OM on access line install 7/14- pending major build. FOC for 10/17.....need to escalate. 7/23- Marc is checking on Colt for local acccess and pricing. Should be available in 3-4 days. 7/29- To use COLT would increase the charges: One time +€375.00 to: €2,375.00 Monthly: +€192.79 to: €5,018. 8/11- Pls be aware that the customer site is not ready until the end of August as it is in renovation. As the lcon confirmes the site is ready , Telecom will schedule a new survey. 8/14- PTT is still working on outside fiber works while customer space is being built. Pending update from PTT.dy date. 8/21- PTT is working on outside fiber works, but can't commit to a timeline until the site survey is completed once the site is ready. 8/28- following up to see if ptt can do the site survey 9/2- Per John site is ready to go. 9/4- per onsite contact, site was ready 9/3. Advised ops. 9/11- pending date from PTT 9/18- TELECOM CONFIRMED US THE 7TH OF NOVEMBER AS FOC BUT THEY ARE TRYING TO DELIVER THIS CIRCUIT WITHIN THE 20TH OF OCTOBER 9/25- pending telco delivery 10/2- pending delivery for 10/20 10/23- checking for line delivery 10/30- line delivered on 20th october, testing to be completed – in attached configuration information for your router configuration 11/6- PVC built, circuit ete testing scheduled for 11/7. 11/7- order closed and engineer informed.
2014-11-26 | ShaRita | none | 4809 East Thistle Landing Drive PHOENIX AZ USA 85044 |  | NSPE0008822490 OQBK22QT port OQBK22QV access |  |  |  |  | BCBK0MNS0001 EDBK0KNL0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-31 | 2014-01-14 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- escalated to Sadisconnects to process request ASAP 12/17- pending disconnect due date 12/31 1/8- pending disconnect 1/14- disconnect complete
2014-12-12 | ShaRita | none | 1155 Gregory Street TAFT TX USA 78390 |  | NSPE0008864210 OQBK251M |  |  |  |  | BCBKXG5T0001-7 |  |  |  |  | 12/12/2014 (standard 30 business days) | 2015-01-08 | 2014-01-08 |  |  |  | 12/12- submitted to Sadisconnects 12/17- pending order number 12/26- pending disconnect due date of 1/08 1/8- pending disconnect due date of 1/08 1/8- disconnect complete
2014-12-12 | ShaRita | none | 8840 Complex Drive SAN DIEGO CA USA 92123 |  | NSPE0008864148 OQBK25X0 |  |  |  |  | BCBK58XN0001-5 |  |  |  |  | 12/12/2014 (standard 30 business days) | 2015-01-08 | 2014-01-08 |  |  |  | 12/12- submitted to Sadisconnects 12/17- pending order number 12/26- pending disconnect due date of 1/08 1/8-pending disconnect due date of 1/08 1/14- disconnect complete
2014-08-08 | ShaRita | CT006-02-IJ | 4 Research Parkway, Shelton, CT 06484 | 200 mg PIP(John will throttle to 100mg) 1000 Base SX LC connector terminate to 5th floor MDF room MD5 UHGVERbgpbqZyofa | O-1079738 Quote ID: 190414793 Order Request 190415630 Service Order(s) [ 190421543 ] has been created for Order Request 190415630 20438617 access 20438616 port |  |  | 5509949 | 21680 | E5000376 C1008297 | /KRGN/709753//SN DMARC Info: Beas is installed in the lower level main telco room. Tagged with Verizon and frontier's ckt id's. The customer has a fiber in place to his mdf room on the 5th floor. | 2014-08-14 | 2014-09-03 | 9/3/2014 9/22/2014 | bpdd | 9/10/2014 1/14/2104 | 2014-01-12 | unitedhealthgroup - 65244 | 214-647-4442 Donald_r_osborn@optum.com | ACTIVATION SCHEDULED 1/16 at 7am CST bridge: 866-692-3158 pass code: 9236734 | 9/17- LEC NTI CLLI issue resolved, pending new FOC date 9/25- circuit delivered; pending customer demarc extension (per Verizon tech, Customer new floor in building is under construction will not be ready for a least a month. Customer will need to get fiber from AT&T demarc to their data room. Handoff from AT&T may be multi mode please check if customer will need single mode or multi mode from At&T to data room) 10/2- pending customer demarc extension (per Verizon tech, Customer new floor in building is under construction will not be ready for a least a month. Customer will need to get fiber from AT&T demarc to their data room. Handoff from AT&T may be multi mode please check if customer will need single mode or multi mode from At&T to data room) 10/8- John confirmed MMF for site. Pending MDF room to be complete. 10/15- Pending MDF room to be complete 10/23- per John MDF room will be completed in December 10/29- per John MDF room will be completed in December 11/6- per John MDF room will be completed in December 11/13- per John MDF room will be completed in December 11/20- per John MDF room will be completed in December 11/26- per John MDF room will be completed in December 12/4- per John MDF room will be completed in December, anticpated 12/24. 12/11- per John MDF room will be completed in December, anticpated 12/24. 12/17- per John MDF room will be completed in December, anticpated 12/24. 12/25- demarc complete, pending scheduling of beas installation 1/8- beas installation scheduled for Friday, Jan 8th
2014-12-17 | ShaRita | none | 300 Galleria / # 401 SOUTHFIE LD MI USA 48034 |  | NSPE0008873167 OQBK2570 |  |  |  |  | BCBKPW670001 -2 |  |  |  |  | 12/16/2014 (standard 30 business days) | 2015-01-14 | 2015-01-14 |  |  |  | 12/17- submitted to Sadisconnects 12/26- pending disconnect due date of 1/14 1/8-pending disconnect due date of 1/14 1/14- soft disconnect complete, pending disconnect completion 1/20- disconnect complete
2014-11-26 | ShaRita | none | 4601 Corporate Drive NW - Building 1 CONCORD NC USA 28027 |  | NSPE0008822283 OQBK22P4 port OQBK22P5 access |  | P1881715 |  |  | BCBKNNSJ0001 EDBKM69P0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-31 | 2015-01-20 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- escalated to Sadisconnects to process request ASAP 12/17- order issued, pending disconnect due date 1/8- Prov ticket. Unable to perform HD 1/14- All issues resolved, and it is now ready for disco. Pending disconnect completion 1/20- disconnect complete
2014-11-26 | ShaRita | none | 200 Patrol Road JEFFERSO NVILLE IN USA 47130 |  | NSPE0008822477 OQBK2WWM port OQBK2WWQ access |  |  |  |  | BCBKNFCK0001 EDBKM7SF0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | 2014-12-24 | 2015-01-14 |  |  |  | 11/26- submitted to Sadisconnects 12/4- pending order number 12/11- escalated to Sadisconnects to process request ASAP 12/17- pending disconnect due date 12/24 1/8- pending disconnect 1/14- sent follow up email to provisioning, Order is still pending related TCOMS completion from NLI group. 1/16- disconnect complete
2014-08-26 | ShaRita | CT820-02-IJ | 690 Asylum Ave, Hartford, CT 06155 | 1G PIP 1000 Base-SX LC MD5 UHGVERbgpbqZyofa | O-1089573 Quote ID: 190441388 Service Order(s) [ 190448260 ] has been created for Order Request 190442738 20472870 access 20472869 port |  |  | 5515701 | 45000 | E5000420 C0006673 | /KRGN/709776//SN demarc: c level data center cabinet cj-19 position 6 tagged | 8/29/2014 9/25/2014 10/13/2014 | 9/24/2014 10/7/2014 10/22/2014 | 2014-10-14 | bpdd | 10/7/2014 11/7/2014 12/26/2014 | 2014-12-19 | UnitedHealthGroup- 65219 | 763-744-2077 robert_a_benson@optum.com | activated with Robert Benson | 8/26- pending opp id 8/28- pending lcon verification 9/3- pending FOC 9/10- FOC date 9/30 9/16- FOC revised to 9/24 9/25- due to access not granted, order supp'ed for new FOC date. 10/2- FOC date 10/7 10/8- working with customer and lcon to obtain access to site to allow LEC to install circuit 10/15- circuit delivered, pending demarc confirmation from John 10/23- pending demarc extension 10/29- pending demarc extension 11/6- pending demarc extension 11/13-pending demarc extension 11/20- pending demarc extension 11/26- pending demarc extension 12/4- pending demarc extension 12/11- pending demarc extension 12/12- Per John the extentsion is now completed, ShaRita is scheduling the BEAS. 12/17- Beas installation scheduled for 12/19
2014-03-24 | ShaRita | UOH01-05-IJ | 9200 Worthington Road, Westerville OH 43082 | 100mg ehernet with dport john will throttle down to 50mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd extend to Floor 1 MDF | SFDC Opportunity ID O-0976284 Quote ID: 190207216 Order Request [ 190212895 ] Service Order(s) [ 190213778 20244535 access 20244534 port | 190213778 |  | 5461730 | 5008 | E4000648 C1003789 | 94/KQGN/201133//OB DEMARC LOC: 1ST FLOOR TELCO ROOM TO PORT 4 DEMARC LOC Continued: ON THE EXTENSION SHELF | 2014-04-02 | 2014-04-30 | 2014-05-06 | bpdd | 2014-05-07 | 2014-10-09 | UnitedHealthGroup-64619 | Don Osborn | Activation scheduled for 11/11 at 9pm CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 5/28- pending demarc extension due next week 6/5- advised John LEC won't extend on Type 4 ciruits 6/10- John requested to change handoff on this from RJ45 to SMF/LC for dmarc extenstion. 6/18- informed John that for type 4 orders customer is responsible for Media Converter, customer should complete that first. If demark extension is needed customer should complete that first. 6/25- pending demarc extension 7/2- pending demarc extension; Matt is working with Don for resolution 7/7- Don asked if we could place the IDF. . We cannot go the IDF route, if we tried we’d end up doing as much work as re-ordering the service, and we still may find its not feasible. there are two options the customer has. Cancel and re-order with optical or purchase and install media converters. 7/16- per Don, no estimated date media converter will be in place 7/24- pending media converters to be put in place 7/31- Pending media converters 8/6- awaiting John to advise what different route will be taken 8/14- Per Don, he put in the request to have 2” conduit installed with pull strings as requested by AT&T. Work should be completed prior to 8/27. 8/20- Pull string should be ready 8/27 8/27- Pull string work was pushed out to next week. 9/3- pending pull string work, Per John work should be completed Monday 9/8 9/10- conduit/pull string work complete. pending AT&T to move the jumpers 9/17- Pending scheduling of beas installation 9/25- beas installation scheduled for Sept 26th 10/2- Tech is unable to locate the part that was signed out by another tech (he no longer works with Verizon) Current techician is currently working to locate missing parts. Once tech has parts, we can redispatch for BEAS installation. THis is already escalated. 10/9- Beas installation complete. Escalated to provisioning to close order asap. 10/15- Ready for activation customer notified. An ETMS ticket 2014101509303 for a filed tech dispatch at the customer prem to swing the Beas connection from port 1 to port 2. 10/23- Verizon’s, ETMS ticket, has been referred back and cancelled. Issue has been clarified. We talked to an ATT tech and was told that there was a mistake on circuit tagging. Port 1 is correct and no need to swing the cables. We opened a ticket OE010932 with AT&T to send someone out and have it corrected. As per the tech, dispatch will happen first thing tomorrow.
2014-08-15 | B end | SG503-02-IJ | #07-02 55 Market Street, Singapore, 48941 | 2 x E1 SOO to Melbourne - circuit ID W0X83226 | OVI 1-1360648723 • Port : 5542952 • ether-access : 5542953 |  |  |  | 1024 | W1B36180 (E1) W1B36178 (port) | Starhub SERVICE ID: 1201201095/1201201096 |  |  |  | bpdd | 2014-11-11 | 2014-10-21 | unitedhealthgroup - 65223 | (+91)-80-49203530 humayun_rafi@optum.com | ACTIVATION IS SCHEDULED ON NOVEMBER 5, 11:00 AM SGT - NOVEMBER 4, 9PM US CST GLP ENGINEER ASSIGNED IS MARIA ORRO | 8/21- pending SOF from Varun 8/26- SOF returned from UHG. 9/4- following up with Varun on order information 9/11- TEV COMPLETED WITH THE LCON. CLIENT: OPTUM HEALTH & TECHNOLOGY SINGAPORE PTE LTD ADDRESS: #08-02 55 MARKET ST SINGAPORE 48941 SINGAPORE LOCAL CONTACT FOR SITE ACCESS: SARI ERLANDY (9641 7373) SARI.ERLANDY@AP.JLL.COM working on getting address changed 9/18- PTT starhub has order, pending FOC. 9/25- SITE SURVEY COMPLETED ON 24/9. PTT IS WORKING TO HANDOVER THE CIRCUIT ON 30/09. 10/2- Starhub advised THE NEXT VISIT FOR THE INSTALLATION AND TESTING WILL BE ON TUESDAY 14TH OCT 2014 AT 10AM. i am checking to see if this was due to site access issues. 10/9- pending installation and testing for the 14th 10/16- Starhub dleivered, pending line testing, pvc build and configlet
2014-01-21 | ShaRita | TX092-02-IJ | 1030 Bendsdale, Pleasanton, TX | 10752 7xT1 MD5 UHGVERbgpbqZyofa | smartform 190118086 NSPE0007748576 IQBKVTBL | 6218579 | P2061425 | 5437923 | 1536 | BCBK4LRM0001-7 | 31/HCGS/706108//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#1 31/HCGS/706109//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#2 31/HCGS/706110//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#3 31/HCGS/706111//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#4 31/HCGS/706112//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#2,SLOT#1 31/HCGS/706113//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#2,SLOT#2 31/HCGS/706114//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#2,SLOT#3 Jack Type: RJ48C | 1/23/2014 4/4/2014 5/16/2014 | 1/31/2014 3/31/2014 4/25/2014 5/30/2014 | 2014-06-09 | bpdd | 2/7/2014 4/2/2014 | 2014-06-13 | unitedhealthgroup-65277 | 763-744-0981 glenn_moore@uhc.com | activation scheduled for 7/10 at 2pm CST Bridge Number: 888-656-8232 pass code: 9158384 | 1/22- order approved by provisioning; pending ASR to be submitted to LEC 1/29- pending FOC date of 1/31 2/6- order on hold. LEC advised order should be cancelled and re-issued, customer will not be ready until MAY or JUNE. 2/20- pending new FOC date of 3/31 2/27- pending new FOC date of 3/31 3/6- pending FOC date of 3/31 3/12- pending FOC date of 3/31 3/20- pending FOC date of 3/31 3/27- FOC date 3/31 4/3- requested circuit be delivered to MPOE per John. Pending new FOC date. 4/10- FOC date 4/25 4/17- FOC date 4/25 4/23- FOC date 4/25 5/1- customer not ready; the building contractor is still placing conduit to the pole. It has to be completed first, so they can put the terminal. 5/8- customer not ready; the building contractor is still placing conduit to the pole. It has to be completed first, so they can put the terminal 5/14- requested new FOC date 5/22- FOC date 5/30 5/28- FOC date 5/30 6/5- circuit not delivered due to facilites issues on LEC side. There is a splicing job with an ECD of 6/9 6/11- circuit delivered; dispatch scheduled for 6/11 to verify wiring and optioning. unable to loop up SMJK for circuits BCBK4LRM0003 and BCBK4LRM0005 6/18- ready for activation; customer notified
2014-03-07 | B end | IR507-03-IJ | No. 2 Harbourmaster Dublin Ireland IRL (expedited) | E1 2048 r md5 UHGVERbgpbqZyofa SOO to Letterkenny - circuit ID W0Y12673 | Dublin OVI# 1-1293062194 new SO# 5481011 |  |  | 5484721 | 1536 | W1B13709 | : CIRCUIT COMES OFF VERIZON OVERTURE IECA01EC-0726 ON PORT 1. |  |  |  | bpdd |  | 2014-06-16 | UnitedHealthGroup-64950 | Office +6(02)5884741/63 9297700576 aj_nalo@uhc.com | 6am Central 6/19 Bridge is 866-819-9840 pcode 3365052 | 3/10- pending SOF 3/27- uHG provided signed SOF 4/10- checking on order information 4/17- new quote needed to be created because site is offnet 4/24- no additional charges to UHG, PCM waived, order can now progress. s/o assigned 5/15- TAIL ORDERED FROM EIRCOM, pending PTT delivery date 5/22- pending delivery date from EIRCOM 5/29COMMS ROOM WILL BE READY FOR EIRCOM TO RERETURN TO SITE ON MONDAY 9TH JUNE. SUBJECT TO CONFIRMATION BY THE CUSTOMERS PROJECT MANAGER BEFORE COB NEXT FRIDAY. ONCE THE EIRCOM TECH ATTENDS SITE TO INSTALL THEIR NTU, IT COULD TAKE A COUPLE OF DAYS TO TEST AND HAND OVER THE 6/12- tech expected to go to site friday to complete testing. pushing for friday handover 6/16- ready for activation, engineer informed.
2014-11-04 | ShaRita | VT001-02-IJ | 46 Main Street, Winooski, Vermont 05404 | 7680, 5xT1 MD5 UHGVERbgpbqZyofa | smartform 190595042 NSPE0008758956 IQBK2CYP | 8112855 | P2095390 | 5542351 | 4000 | BCBK64PR0001-0005 | 88/HCGS/932742//VT/ 88/HCGS/932743//VT/ 88/HCGS/932744//VT/ 88/HCGS/932745//VT/ 88/HCGS/932746//VT/ Demarc: ckt 1-4: 2nd flr telco rm, mount #2 pos 1-4, rj48C, tagged not ext ckt 5: 2nd flr telco rm, mount # 3 pos 1, rj48C, tagged not ext | 2014-11-14 | 2014-12-09 | 2014-12-16 | bpdd | 2014-12-09 | 2014-12-16 | Unitedhealthgroup-65186 | 443-853-3646 edward.mclaughlin@optum.com |  | 11/6- ShaRita working on order 11/13- order submitted, pending provisioning approval 11/20- pending FOC date 11/26- pending FOC date. LEC advised that CFA channels are busy and requested a sup to the ASR. 12/9- FOC date 12/9. Fairpoint, who is providing the local loop is on strike in the area. They have issued us a date of 12/9, but there is no guarantees on that because of the work stoppage. 12/11- Circuits were installed but we are waiting for Fairpoint to complete their testing. 4 out of 5 circuits have been completed. They are waiting for the Central Office to complete all the tickets and provide the demarcs.
2014-11-05 | ShaRita | FL158-02-IJ | 10151 Deerwood Park Blvd, Bld 300 Ste 310, Jacksonville, FL 32256 | 10752, 7xT1 MD5 UHGVERbgpbqZyofa | smartform 190601843 NSPE0008772400 O-1100740 IQBK2CZ4 | 8112842 | P2095398 | 5542365 | 2000 | BCBK64P50001-0007 | 52/HCGS/774678//SB DEMARC LOC: 3RD FLOOR TELCO ROM M SLOT 8RJ48 NO DEMARC LOC Continued: 8RJ48 NON EXT 52/HCGS/774679//SB DEMARC LOC: 3RD FLOOR TLCO MM SLOT 9 RJ48C NO DEMARC LOC Continued: RJ48C NON EXT 52/HCGS/774680//SB DEMARC LOC: 3RD FL MAIN TELCO MM SLOT10 RJ48C NN DEMARC LOC Continued: RJ48C NN 52/HCGS/774681//SB DEMARC LOC: 3RD FLOOT MAIN TELCO MM SLOT 11 RJ48C DEMARC LOC Continued: 11 RJ48C NON EXT 52/HCGS/774682//SB DEMARC LOC: 3RD FLORR MAIN TELCO MM SLOT12 R DEMARC LOC Continued: SLOT12 RJ48C 52/HCGS/774683//SB DEMARC LOC: 3RD FLOOT MAIN TELCO MM SLOT13RJ DEMARC LOC Continued: SLOT13RJ48C NON EXT 52/HCGS/774684//SB DEMARC LOC: 3RD FLOR MAN TECO ROOM MM SLOT14 R DEMARC LOC Continued: SLOT14 RJ48C NON EXT | 2014-11-14 | 2014-12-03 | 2014-12-05 | bpdd | 2014-12-12 | 2014-12-12 | unitedhealthgroup-65180 | 763-744-1589 david_casanova@optum.com |  | 11/6- pending Auth code 11/7- sent to shaRita 11/13- order submitted, pending provisioning approval 11/20- FOC date 12/3 11/26- FOC date 12/3 12/4- pending confirmation that circuts were installed 12/11- ready for activation, customer notified
2014-10-21 | ShaRita | WA022-02-IJ | 1111 3rd Ave, Suite 1100, 11th Floor, Seattle, WA 98101 | 7680, 5xT1 MD5 UHGVERbgpbqZyofa | Smartform 190566661 NSPE0008718548 IQBK1463 | 8084080 | P2094529 | 5539353 | 3008 | BCBK621X0001-0005 | 74/HCGS/519354//PN DEMARC LOC: 19th floor main telco room mnt no 4 slot no 1 of 4 74/HCGS/519355 /PN DEMARC LOC: 19th floor main telco room mnt no 4 slot no 2 of 4 74/HCGS/519356 /PN DEMARC LOC: 19th floor main telco room mnt no 4 slot no 3 of 4 74/HCGS/519357 /PN DEMARC LOC: 19th floor main telco room mnt no 4 slot no 4 of 4 74/HCGS/519358 /PN DEMARC LOC: 19th floor main telco room mnt no 6 slot no 4 of 4 Jack Type: rj48c | 2014-11-07 | 2014-11-21 | 2014-11-21 | BPDD | 2014-12-03 | 2014-12-03 | Unitedhealthgroup-65202 | 763/694-7370, masroor_khan@optum.com |  | 10/23- Sent to ShaRita 10/30- pending lcon verfication 11/6- lcon verification completed. order submitted. 11/14- FOC date of 11/21 11/20- FOC date 11/21 11/26- circuit delivered, pending testing 12/3- ready for activation, customer notified
2014-06-19 | ShaRita | WI012-05-IJ | 115 West Wausau Avenue, Wausau WI 54401 | 44736, DS3 MD5 UHGVERbgpbqZyofa | O-1046269 Quote ID: 190336232 Order Request 190336540 Service Order(s) [ 190342019 ] has been created for Order Request 190336540 20360406 access 20360405 port | 190342019 |  | 5495525 | 22000 | C4000215 D3000198 | 39/HFGS/183592//FTNC/ Demarc:telco rm shelf 1 jack 7 r01cfot1 jack 7 Not ext. Tagged. | 2014-07-25 | 2014-08-12 | 2014-08-12 | bpdd | 2014-09-05 | 2014-09-04 | UnitedHealthGroup- 64521 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | Activation failed Customer has two CPE on site and Sonja is not sure what router is connected to the Vz circuit. | 6/18- pending opp id from Siva 6/25- order submitted to provisioning 7/2- pending lease 7/9- pending lease 7/16- pending lease 7/24- pending lease 7/31- ASR submitted; pending FOC 8/6- FOC for 8/12 8/14- pending confirmation of circuit was installed 8/21- circuit delivered. ticket open due to path issue. once ticket resolved pending Mux Scheduling/Design Completion 8/27- provisioning is working with development to fix the mecca issue on order 9/3- pending end to end testing 9/10- circuit ready for activation; customer notified
2014-11-07 | ShaRita | FL066-02-IJ | 13350 Metro Parkway, Suite 301, Fort Myers FL 33901 | 10752, 7xT1 MD5 UHGVERbgpbqZyofa | smartform 190604277 O-1100740 NSPE0008772465 IQBK2C12 | 8112863 | P2095407 |  | 1536 | BCBK64RM0001-0007 | 25.HCGS.263945..UFLG 1ST FLR TELCO RM SLOT 1 OF 8 25.HCGS.263943..UFLG 1ST FLR TELCO RM SLOT 2 OF 8 25.HCGS.263942..UFLG 1ST FLR TELCO RM SLOT 3 OF 8 25.HCGS.263940..UFLG 1ST FLR TELCO RM SLOT 4 OF 8 25.HCGS.263941..UFLG 1ST FLR TELCO RM SLOT 5 OF 8 25.HCGS.263939..UFLG 1ST FLR TELCO RM SLOT 6 OF 8 25.HCGS.263944..UFLG 1ST FLR TELCO RM SLOT 7 OF 8 Jack Type: RJ48C | 2014-11-14 | 2014-11-25 | 2014-11-24 | bpdd | 2014-11-25 | 2014-11-25 | unitedhealthgroup-65181 | 443-872-3099 robert.winston@optum.com |  | 11/7- sent to ShaRita 11/13- order submitted, pending provisioning approval 11/20- FOC date 11/25 11/26- ready for activation, customer notified
2014-08-28 | ShaRita | C1566-02-IJ | 391 Inverness Parkway, Englewood, CO 80112 | 3072 2xT1 | O-1091587 Quote ID: 190452800 Order Request 190456019 Service Order 190462616 Service Order(s) [ 190462616 ] has been created for Order Request 190456019 20490067 access 20490066 port DNV I0032307 |  |  | 5518847 | 128 | C1009035 N1005731,N1005730 | 13-cny-4gh-0003 13-cny-4gh-0004 DEMARC INFO: dmarc for both circuits as follows: 2nd floor MDF02. Circuit id: 13-cny-4gh-0003: RJ48P 1.1.7:3. Circuit id: 13-cny-4gh-0004: RJ48P 1.1.7:6. Tagged w/circuit ids and hard loop left at dmarc. Latysis to drop hard loops when ready to extend circuit to end-user/customer. Extended Wire (Yes or No): NO Jack Type: RJ48P |  |  |  | bpdd | 2014-10-10 | 2014-10-08 | UHG-ECC-65448 | 763-7442154 scott_moyer@optum.com |  | 9/4- order submitted to ShaRita 9/10- order submitted to provisioning. no ASR pon is generated so created helpdesk ticket(T0275484). 9/18- pending site survey completion 9/25- pending end to end testing 10/2- Tuesday, September 30 --unable to deliver circuit att due to end-user/customer information required to deliver circuit to Latysis data center so circuit delivery form can be filled out/completed. Cable and wireless is insufficient customer information. Provided lcon and alternate contact information to tech, LCON : Troy Goulding @ 303-268-1484 and the alternate contact is Bryan Walsh @ 303-268-1495 10/8- ready for activation, customer notifed
2014-08-29 | ShaRita | C1558-05-IJ | 1525 NW 98th Court, Doral, FL 33172 | 50M, will throttle down to 20M handoff 1000 Base-SX Optical LC MD5 UHGVEReccgas4Usp9 | O-1093219 Quote ID: 190452396 Order Request 190452617 Service Order 190462696 Service Order(s) [ 190462696 ] has been created for Order Request 190452617 20490109 access 20490108 port MIA I0037616 MIA I0037621 |  |  | 5518896 | 15M | C1009264 E4001951 | eabjf5bjf50047 eabjf5bjf50048 demarc 318.10panal #1 Module A port 4 |  |  |  | bpdd | 2014-09-25 | 2014-09-22 | UHG-ECC-65526 | 763-7442154 scott_moyer@optum.com |  | 9/3- pending lcon verification. 9/10- order submitted, pending provisioning approval 9/18- provisioned to shared BEAS. Pending site survey and possible ete test if site is ready 9/24- circuit ready for activation; customer notified
2014-06-05 | ShaRita | CA147-02-IJ | 6195 Lusk Blvd, Ste 120, San diego, CA 92121 | 100M, will throttle down to 50M delivered to first floor mdf RJ 45 handoff | opp O-1034859 Quote ID: 190311264 Order Request 190311569 Service Order 190315403 Service Order(s) [ 190315403 ] has been created for Order Request 190311569 20340376 access 20340375 port | 190315403 |  | 5489815 | 1536 | C1005799 E4001183 | 19/KQGN/530482//PT VZB DMARC: Above at@t demarc, rack # 1,middle of the rack. P1. HANDOFF TYPE: ELECTRICAL | 2014-06-09 | 2014-09-10 | 2014-09-11 | bpdd | 2014-09-17 | 2014-09-17 | unitedhealthgroup- 65296 | 702-242-7654 tauoa.falo@optum.com |  | 6/11- pending FOC 6/18- asked John to have lcon contact LEC to schedule site survey 6/25- lcon left voicemail for LEC engineer and will reply back when the site survey has been scheduled 7/2- per lcon, Harold, scheduled for the site survey Tuesday, 7/8 at 11:00am 7/9- site survey completed on 7/8; pending LEC to provide FOC date 7/16- FOC date 9/10 BTDD: C201407150039 infrastructure ECD 8/29/14, complex build, with placing of apx. 2000 feet of fiber, splicing with permits, placing of equipment.” 7/24- FOC date 9/10. infrastructure ECD 8/29/14, complex build, with placing of apx. 2000 feet of fiber, splicing with permits, placing of equipment. 7/31- FOC date 9/10 8/5- FOC date 9/10 8/14- FOC date 9/10 8/20- FOC date 9/10 8/27- FOC date 9/10 9/3- FOC date 9/10 9/10- pending confirmation circuit was installed 9/18- ready for activation; customer notified
2014-05-27 | ShaRita | GA008-05-IJ | 5775 Peachtree Dunwoody Rd NE Suite C600, Atlanta, GA | 100M, John will reduce to 50M, RJ45 handoff MD5 UHGVERbgpbqZyofa terminate in In MDF room in suite C600 | Opportunity ID O-1027377 Quote ID: 190296551 Service Order(s) [ 190299343 ] has been created for Order Request 190297685 20324693 access 20324692 port | 190299343 |  | 5486493 | 9664 | C1005392 E4001074 | 38/KQGN/612572//SB demarc, bldg C, 6th fl, ste 600 server room rack 3, tagged. | 2014-06-02 | 2014-07-30 | 2014-09-04 | bpdd | 2014-08-06 | 2014-09-16 | unitedhealthgroup-65043 | 702-242-7654 tauoa.falo@optum.com |  | 5/29- order submitted to provisioning 6/5- pending FOC date 6/11- pending FOC date 6/18- FOC 7/30 6/25- FOC 7/30 7/2- FOC 7/30 7/9- FOC date 7/30 7/16- FOC date 7/30 7/24- FOC date 7/30 7/31- pending confirmation from LEC if circuit was delivered. 8/6- Complex build to place a Loop EMUX, place and splice fiber, place equipment, dispatch test and turn up. The ECD was 8/5 Per LEC PM, the original ECD was 8/5, the FOC date should have been after the ECD. The construction job remains in progress. LEC PM will escalate for dispatch as soon as the build completes. 8/14- Per LEC PM, New ECD 8/29 - Reason: requires power retrofit; vendor waiting on power shelf. She will escalate for dispatch as soon as the infrastructure build completes. This is being treated with urgency, however they cant move forward without a power shelf. The vendor will advise when it has been received. 8/20- pending build completion, ECD 8/29 8/27- pending build completion, ECD 8/29 9/3- Build is completed. Pending loop completion 9/10- circuit delivered and beas installed. pending end to end testing 9/16- ready for activation, customer notified
2014-08-04 | ShaRita | FL156-02-IJ | 611 Druid E. Road, Suite 511, Clearwater, FL 33756 move to new conduit | 10752, 7xT1 MD5 UHGVERbgpbqZyofa | Smartform 190405430 NSPE0008433245 CQBK0CK0 |  | P2080175 | 5495936 | 1536 | BCBK50940001-0007 | 69/HCGS/433988//GTES DEMARC LOC: 1st floor telco room shelf 2 1 in 8 position shelf 69/HCGS/433989//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 2 in 8 position shelf 69/HCGS/433990//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 3 in 8 position shelf 69/HCGS/433991//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 4 in 8 position shelf 69/HCGS/433992//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 5 in 8 position shelf 69/HCGS/433993//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 6 in 8 position shelf 69/HCGS/433994//GTES DEMARC LOC: 1st floor telco room shelf 2. Slot 7 in 8 position shelf Jack Type: RJ48X | 8/19/2014 8/21/2014 | 9/2/2014 9/4/2014 | 2014-08-29 |  |  | 2014-09-08 | UnitedHealthGroup | 763-744-0981 glenn_moore@uhc.com |  | 8/4- submitted move to ShaRita 8/7- working to submit request to OE 8/14- Provisioning sent the ASR however we received jeopardy from Verizon LEC. They clarified that we don’t need to send out a Move ASR since there are no changes on the demarc or no new demarc. Customer needs to request for maintenance ticket to their Verizon sales person to have the Verizon Technician go out to the site again. 8/21- pending hotcut on 9/2 at 10am EST 8/27- circuit 7 FOC date 9/2 and circuits 1-6 FOC date 9/4. Still escalating to provisioning to get LEC to accept FOC date of 9/2 for all circuits 9/3- tech was out there on Friday and stated: CKT MOVED TO CUSTOMER'S NEW HOUSE CABLE. pending confirmation from John that circuits were moved to the correct location then will proceed with testing and closing of order 9/5- John confirmed cable moved 9/8- circuits tested, order closed
2014-06-09 | ShaRita | MN051-07-IJ | 13625 Technology Dr., Eden Prairie, MN 55344 | 10M, I will throttle down to 5M MD5 UHGVERbgpbqZyofa RJ45 handoff | Opp ID# O-1037265 Quote ID: 190316245 Order Request 190316826 Service Order(s) [ 190319402 ] has been created for Order Request 190316826 20343457 access 20343456 port | 190319402 |  | 5490784 | 1536 | C0003396 E3002395 | 15/KXGS/047184//ACSO The Demarc for the Overture is in building C, Lower level, MDF Room, Row and cabinet H19, U29 of U45 Overture 1400 10/100 port 0.1 tagged with LD and Lec ID and shown to Lcon Chris Hemstad 952/917-7276. | 2014-06-12 | 2014-07-07 | 2014-07-07 | bpdd | 2014-07-14 | 2014-08-12 | unitedhealthgroup- 64880 | 763-744-2081 tim_gunderson@optum.com |  | 6/10-submitted to ShaRita 6/11- order submitted to provisioning 6/18- pending FOC date 6/25- FOC date 7/7 7/2- FOC date 7/7 7/9- circuit delivered; pending confirmation from John if circuit will be extended DEMARC: lower level server room customer rack mounted fast ethernet port 2 7/17- pending demarc extension to building C MDF 7/24- pending demarc extension 7/31- pending demarc extension confirmation 8/6- demarc extended, waiting for bea installation to be scheduled 8/12- ready for activation; customer notified
2014-06-20 | ShaRita | TX028-03-IJ | Connextions- 5150 Regent Blvd, Irving, TX 75063 | 100M Ethernet RJ45 handoff | O-1046276 Quote ID: 190336647 Order Request 190337474 Service Order(s) [ 190342369 ] has been created for Order Request 190337474 20360621 access 20360620 port | 190342369 |  | 5495639 | 30000 | C1006246 E4001310 | 12/KEGS/701874//GTEC VZB DMARC: 1st flr server room, verizon relay rock shelf number 3, NID 3 | 2014-06-26 | 2014-08-01 | 2014-08-01 | bpdd | 2014-08-08 | 2014-08-04 | Connextions- 65226 | 407-926-2400 x10390 jose.hanchi@connextions.com |  | 6/25- order submitted to provisioning 7/2- ASR submitted; pending FOC date 7/9- pending FOC date 7/17-pending FOC date 7/24- FOC date 8/1 7/31- FOC date 8/1 8/6- ready for activation; customer notified
2014-07-08 | ShaRita | TX213-01-IJ | 2821 Lackland Road, Suite 101, Fort Worth, TX 76116 | 7xT1, 10752 MD5 UHGVERbgpbqZyofa | Smatform 190370599 NSPE0008356761 IQBKZW1X | 6507328 | P2082687 | 5501482 | 1536 | BCBK56NP0001-0007 | 14/HCGS/146846//SW DEMARC LOC: 2ND FLR TELCO RM,MULTIMOUNT CAB-1,SL DEMARC LOC Continued: CAB-1,SLOT-05 14/HCGS/146847//SW DEMARC LOC: 2ND FLR TELCO RM,MULTIMOUNT CAB-1,SL DEMARC LOC Continued: CAB-1,SLOT-06 14/HCGS/146848//SW DEMARC LOC: 2ND FLR TELCO RM,MULTIMOUNT CAB- DEMARC LOC Continued: 1,SLOT-07 14/HCGS/146849//SW DEMARC LOC: 2ND FLR TELCO RM,MULTIMOUNT CAB-1,SL DEMARC LOC Continued: CAB-1,SLOT-08 14/HCGS/146850//SW DEMARC LOC: 2ND FLR TELCO RM,MULTIMOUNT CAB-1,SL DEMARC LOC Continued: CAB-1,SLOT-09 14/HCGS/146851//SW DEMARC LOC: 2ND FLR TELCO RM,MULTIMOUNT CAB-1,SL DEMARC LOC Continued: CAB-1,SLOT-10 14/HCGS/146852//SW DEMARC LOC: 2ND FLR TELCO RM,MULTIMOUNT CAB- DEMARC LOC Continued: 1,SLOT-11 Jack Type: RJ48C | 2014-07-21 | 2014-07-28 | 2014-07-28 | bpdd | 2014-08-13 | 2014-07-29 | unitedhealthgroup-65250 | 210-877-7919 chris_spoor@optum.com |  | 7/10- pending approval to process 7/17- order submitted to OE 7/24- FOC date 7/28 7/30- ready for activation; customer notified
HOT & ESCALATED 3/19/2014 | HOT & ESCALATED ShaRita | HI015-02-IJ | 1132 Bishop Street, Suite 400, Honolulu HI | 12288, 8xT1 md5 UHGVERbgpbqZyofa extend to 4th floor telco room | smartform 190204468 NSPE0007967086 IQBKXCPK | 6327632 | P2070287 | 5460767 | 8000 | BCBK472Y0001-0008 | 82.HCGS.115450..HAWT 82.HCGS.115451..HAWT 82.HCGS.115452..HAWT 82.HCGS.115453..HAWT 82.HCGS.115454..HAWT 82.HCGS.115455..HAWT 82.HCGS.115456..HAWT 82.HCGS.115457..HAWT 4TH FLR TELCO RM BKBRD, 8 POS SHELF, POS 1, 2, 3, 4, 5, 6, 7, 8, rj48c, not extended. | 3/31/2014 6/20/2014 | 4/21/2014 6/27/2014 | 2014-04-23 | bpdd |  | 2014-07-03 | UnitedHealthGroup-65290 | 763-694-7409 terry_bjorke@optum.com |  | 3/20- pending sumbit to ShaRita 3/27- order submitted to provisioning 4/3- pending FOC date from LEC 4/10- escalated to provisioning team lead for assistance with clearing the CNR error on ASR 4/17- FOC date 4/21 4/23- FOC date of 4/21 missed; Mssed loop ticket created to escalate loop delivery, 8 circuits. 5/1- circuits delivered; pending mux work and end to end testing 5/8- escalated to provisioning to resolve mux issue asap 5/14- provisioning still working to resolve mux issue 5/22- Capacity has been provided, Request sent to Hawaiit for validation. 5/29- looking for another CFA to replace three specified circuits due to the capacity requested currently have a live circuit riding on them. We already looked for replacements and sent a request to Hawaii Telcom to verify t1 status. 6/5- ASR already prepped; Waiting for advise from GLP which circuits needs CFA replacements. ***This has been escalated*** 6/11- pending MUX completion. 6/18- provisioning team is still working on completing the MUX 6/26- due to testing errors needed to change CFA'S FOR 8 circuits; new FOC date 6/27 7/2- Tech scheduled to go out to work order today. We are unable to test good on circuit 5-7. Dispatch sent to check the wiring and optioning for ckts 5-7. ESCALATED TO UPPER MANAGEMENT 7/9- ready for activation; customer notified
2014-03-05 | ShaRita | UGA09-05-IJ | 3720 Davinci Court, Norcross GA 30092 | 50 mg Ethernet dport, John will throttle down to 20. rJ45 copper handoff md5 UHGVERbgpbqZyofa | The Quote ID is 190182474. Service Order(s) [ 190186578 ] has been created for Order Request 190184524 20228464 access 20228463 port | 190186578 |  | 5453002 | 5392 | E4000561 C1003289 | 38/KQGN/611574//SB VZB DMARC: 3rd fl server rm, Overture400 on telco backboard below HANDOFF TYPE: Electrical | 3/10/2014 5/6/2014 6/3/2014 | 4/28/2014 5/20/2014 6/25/2014 | 2014-06-23 | bpdd | 5/5/2014 7/11/2014 | 2014-06-30 | unitedhealthgroup-64578 | 91 91600 84400 harish_kandpal@optum.com |  | 3/6- melissa is working on order 3/12- pending LEC to provide FOC date 3/20- pending site survey to be scheduled 3/27- pending confirmation from LEC that site survey has been completed 4/3- asked John for a contact that is able to make decisions in regards to the order with the LEC BIC engineer 4/10- LEC PM is working with BIC engineer for updates 4/17- FOC date 4/28 4/23- FOC date 4/28 5/1- loop not delivered; customer is not ready. As per AT&T, the pull string broke and they were unable to pull their fibers thru the customer’s conduit. End user will need to have this fix before they can proceed. 5/6- conduit issue resolved; pending new FOC date 5/8- new FOC date 5/20 5/14- FOC date 5/20 5/22- Per LEC received call from field advising that end user now needs a pull string in conduit to complete turn-up. Please advise when end user will have pull string so we can complete turn-up. 5/28- waiting on John to advise that pull string is in place in conduit 6/5- pull string is in place; pending FOC 6/25 6/11- FOC date 6/25 6/18- FOC date 6/25 6/25- FOC date 6/25 6/26- circuit delivered pending beas on 6/30 between 8am and 12:10pm 7/2- ready for activation; customer notified
2014-03-06 | ShaRita | MN011-25-IJ | 1707 West Creek Lane, Chaska, MN 55318 | 1536 ICM T1 installed via copper at MDF800 | quote id 190183055 Service Order(s) [ 190186606 ] has been created for Order Request 190184520 20228472 access 20228471 port | 190186606 |  | 5453004 | 384 | D1002718 access C1003341 port | 50.HCGS.526014..UDMN main floor mainframe data room TA3000 shelf slot 21 of 22 rj48c tagged not extended | 2014-04-23 | 2014-06-17 | 2014-06-11 | bpdd | 2014-06-24 | 2014-06-12 | UnitedHealthGroup-IDN- 65400 | 763-744-0840 matt_f_seymour@optum.com |  | 3/6- melissa is working on order 3/12- provisioning not able to validate address to submit ASR, provided existing circuit PLBKPT450001/BCBKS7V90001 3/20- provisioning not able to validate address to submit ASR; per John, Century Link is still working on the build. They have orders that are on hold yet because the service is not ready. 3/27- order oh hold due to address validation. Note from John, Sounds like Century Link is still working on the build. They have orders that are on hold yet because the service is not ready. 4/3- order oh hold due to address validation 4/10- order oh hold due to address validation 4/17- requested provisioning to retry submit the ASR, pending feedback if address validation is now clear 4/24- ASR submitted; waiting for FOC date 5/1- pending FOC date; email sent to provisioning requesting update on when FOC date can be expected 5/8- pending FOC date; Per Centurylink there is an internal issue on their part which causes the delay. We asked for an ETA and what is the issue going on, there is no spare feature cable 1 pair and require repeater. 5/14- per LEC their tech went on the customer's site yesterday but Lcon Matt told them that they need an escort in doing the job but customer's(Matt) escort is on vacation. 5/22- asked John to confirm with lcon if escort that will allow tech access is back from vacation 5/28- order supp'ed for new due date now that access can be provided 6/5- pending FOC date 6/11- pending FOC date, provisioning is still working with LEC management regarding the design
2014-01-08 | B end | IR503-02-IJ | Old Naas Road, Dublin 12 / Waverley Office Park , Dublin, Ireland |  | # 1-1274079250, Oppty: 1-L10DXE 5434615 |  |  | 5464664 | 1536 | W1A97105 | DPL2113306 CIRCUIT COMES OFF VERIZON OVERTURE IECA01EC-0 720 ON PORT 1. |  | 2014-03-31 |  | bpdd | 2014-05-15 | 2014-05-05 | unitedhealthgroup-65086 | James Nalo Office +6(02)5884741/63 9297700576 aj_nalo@uhc.com |  | 1/21- pending SOF 2/20 - SOF processed, pending order numbers 3/6- Melissa escalting with B end team for order indo HCUS REASON: CH04 - CUSTOMER HOLD - CUSTOMER NOT READY NEXT STEPS: CUSTOMER AGREED THE CHANGE ON FRIDAY 14 OF MARCH DATE OF NEXT STEPS: 20MAR14 3/14- order in design. 3/20- followed up on status of design 3/27- PTT delivery of 3/31 4/3- EIRCOM UPDATE: ORDER PLACED ON CUSTOMER DELAY. A/W APPT TO GAIN ACCESS TO CUSTOMERS PREMISES TO CHECK EQUIPMENT AS CUST CTC MEGAN O'HANLON IS CURRENTLY UNAVAILABLE. 4/14- circuit tested clean, pvc created , configlet created. verifying if ready for activation 4/24- escalating with B end. 5/5- ready for activation
2013-11-26 | ShaRita | VA016-09-IJ | VA016 (A end) 3130 Fairview Park Drive, Suite 500 Falls Church, VA 22042 NTTA/Verio Data Center (B end) 22451 Shaw Road Sterling, VA 20166 | New 100M private line | NSPE0007593926 CDR201312040009 5398012 WDC I0121646 | 6164854 |  |  |  | W1A84721 | ethf4fbcrw0001 (Sterling) 22451 SHAW RD / STERLING, VA 20166-4319 Main telco room relay rack 101.06 port 3-3 On mux hard wired to first electrical Ethernet handoff in sip panel mounted in the relay rack to the right customer is to extend circuit if needed. 36.KEGS.308382..CD (Falls church) VERIFIED DEMARC: BASEMENT MAIN TELCO RM PLZ RACK 1 CHANNEL 4 PORT OF 5 | 2013-12-10 | 2013-04-24 | 2014-04-21 | bpdd | 2014-05-08 | 2014-04-25 | na | engineer not listed |  | 1/16- order on hold; pending site requirements for Location A, end user at loc A is asking for LOA, Melissa Asked John about that 1/22- pending site requirements for Location A 1/29- order on customer hold; pending site requirements for Location A 2/6- order on customer hold; pending site requirements for Location A. For B location confirming if circuit can be delivered in copper or if a media converter can be installed 2/20- pending site requirements for Location b; also confirmed that Verizon will run a copper twisted pair category 6 cable and terminate to an RJ45 plug. They will locate the RJ45 somewhere in the MPOE where the customer can then extend the circuit over their network to the CPE. 2/27- pending site requirements for Location A, 3130 Fairview Park Drive, Suite 500 Falls Church, VA 22042 3/6- pending FOC date of 4/24 for both ends 3/12- pending FOC date of 4/24 for both ends 3/20- pending FOC date of 4/24 3/27- FOC date 4/24 ***NOTE: Ask John if due date needs to be improved*** 4/3- FOC date 4/24 4/9- FOC date 4/24 4/17- FOC date 4/24 4/23- circuit delivered 4/21 for 3130 Fairview Park Drive, Suite 500 Falls Church, VA. pending loop delivery for 22451 Shaw Road Sterling, VA 20166, FOC date 4/24 5/1- ready for activation; customer notified
2014-01-31 | ShaRita | CA087-02-IJ | 1770 Iowa Ave., Building E, Suite 260 Riverside CA 92507 | 1536, T1 MD5 UHGVERbgpbqZyofa | request id 190167076 Service Order(s) [ 190169443 ] has been created for Order Request 190168316 20217163 access 20217162 port |  | 190169443 | 5446978 | 1376 | D1002346 access C1002988 port | 13/HCGS/848670//PT DEMARC LOC: NIU AT 2.1, SH 1 SLOT 7, SNAP JK 2 POS DEMARC LOC Continued: JK 2 POSITION 1 | 2014-03-03 | 2014-03-14 | 2014-03-12 | bpdd | 2014-03-19 | 2014-03-13 | unitedhealthgroup-64945 | 214-647-4442 donald_r_osborn@uhc.com |  | 2/6- Melissa received order request 2/20- pending approval code for BAU 2/27- sent email to provisioning to approve order as soon as possible and to submit ASR to LEC 3/6- pending FOC date of 3/14 3/12-- pending FOC date of 3/14 3/20- ready for activation; customer notfied
2014-02-25 | ShaRita | VA018-02-IJ | 4426 Costello Way Haymarket, VA 20169 | 1536 T1 MD5 UHGVERbgpbqZyofa | Quote O-0952296 Service Order(s) [ 190173599 ] has been created for Order Request 190172102 20219106 access 20219105 port |  | 190173599 | 5448133 | 1376 | Access D1002389 Port C1002823 | 36.HCGS.001215..CD DEMARC LOC: BSMT LL,RM main,TEL RM ,RJ48C,LP Y,CAB N,SHELF 1,JCK 8, DEMARC LOC Continued: Extended Wire (Yes or No): No Jack Type: RJ48C | 2014-02-28 | 2014-03-12 | 2014-03-07 | bpdd | 2014-03-17 | 2014-03-17 | unitedhealthgroup- 64909 | 214-647-4442 donald_r_osborn@optum.com |  | 2/27- pending order creation 3/6- pending FOC date of 3/12 3/12- circuit delivered; pending testing 3/20- ready for activation; customer notified
2014-01-30 | ShaRita | TX164-02-IJ | 1143 E. Sinton St., Sinton, TX 78287 | 10752 7xT1 MD5 UHGVERbgpbqZyofa | smartform 190134829 NSPE0007794219 IQBKV5NN | 6241834 | P2063342 | 5441665 | 1536 | BCBK4RRJ0001-7 | 34/HCGS/627749//SW DEMARC LOC: 1ST FLR I PH CLOSET, QD MT#3,POS DEMARC LOC Continued: MT#3,POS#1 Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C 34/HCGS/627750//SW DEMARC LOC: 1ST FLR I PH CLOSET, QD MT#3,POS DEMARC LOC Continued: MT#3,POS#2 Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C 34/HCGS/627751//SW DEMARC LOC: 1ST FLR I PH CLOSET, QD MT#3,POS DEMARC LOC Continued: MT#3,POS#3 Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C 34/HCGS/627752//SW DEMARC LOC: 1ST FLR I PH CLOSET, QD MT#3,POS DEMARC LOC Continued: #4 Extended Wire (Yes or No): No EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C 34/HCGS/627753//SW DEMARC LOC: 1ST FLR I PH CLOSET, QD MT#4,POS DEMARC LOC Continued: MT#4,POS#1 Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C 34/HCGS/627754//SW DEMARC LOC: 1ST FLR I PH CLOSET, QD MT#4,POS DEMARC LOC Continued: MT#4,POS#2 Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C 34/HCGS/627755//SW DEMARC LOC: 1ST FLR I PH CLOSET, QD MT#4,POS DEMARC LOC Continued: MT#4,POS#3 Extended Wire (Yes or No): NO EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C | 2014-02-05 | 2/14/2014 3/4/2014 | 2014-02-27 | bpdd | 2/21/2014 3/12/2014 | 2014-03-11 | unitedhealthgroup-65275 | Deven Patterson 763-744-0696 deven_patterson@uhc.com |  | 2/6- pending FOC date of 2/14 2/18- Per ATT, tech dispatched last Friday, 2/14, but the person on the site was not able to provide access. Requested a new due date 2/20- pending new FOC date of 3/4 2/27- pending new FOC date of 3/4 3/6- Per ATT circuit installation still not completed. Dispatch is scheduled for today. 3/7- Circuit delivered; pending testing 3/11- ready for activation; customer notified
2013-03-13 | ShaRita | UFL07-05-IJ | Tampa, FL | 44736, DS3 md5 encryption UHGVERbgpbqZyofa | smartform 189825512 CDR201303130072 NSPE0006529937 IQBKKBGP | 5785025 | P1995779 | 5339498 | 18432 | BCBKY5GK0001 | 69/HFGS/305744/ /GTES/ DEMARC LOC: MPOE: 2ND FLOOR CUST DATA ROOM - SHELF #4 - NIU SLOT 1 OF 1 DEMARC LOC Continued: Extended Wire (Yes or No): No Jack Type: RJ21X | 2013-04-11 | 6/14/2013 reissued 9/20/2013 2/21/2014 | 2014-02-21 | bpdd | 2014-03-14 | 2014-02-28 | unitedhealthgroup-64616 | 763-744-2077 robert_a_benson@uhc.com |  | 11/20- Per LEC, OUR NNI TEAM WENT ON 11/19 TO COMPLETE INSTALL AND THE CUSTOMER CONTACT (ERIC HEATH) STILL HASN'T PROVIDED THE POWER OUTLET NEEDED FOR THEIR EQUIPMENT. ERIC HEATH WILL NOT PROVIDE THE POWER NEEDED UNTIL HE FINDS OUT WHO FROM HIS CORPORATION PLACED THIS ORDER. LEC WILL NOT BE RETURNING TO THIS SITE WITHOUT A PICTURE OF THE NECESSARY POWER BEING COMPLETED. Requested LEC to advise exactly where power is needed; MPOE or the MDF. 11/22- awaiting customer to provide power on the 2nd floor telco closet 11/26- awaiting customer to provide power on the 2nd floor telco closet 12/5- requested LECs field tech information to confirm exactly where power is needed on the 2nd floor 12/12- attempted to reach LEC to discuss site requirements but no answer; asked provisioning to reach out to LEC for tech's management information 12/19- spoke with LEC and was able to provide site requirements form/pictures. pending site readiness 1/2- pending site readiness 1/9- pending site readiness 1/16- pending site readiness 1/22- pending site readiness 1/28- site ready; pending ASR to be resubmitted for new FOC date 2/6- order on hold until customer returns the signed EURC form to LEC advising when their required contingencies are ready 2/18- pending new FOC date of 2/21 2/20- pending new FOC date of 2/21 2/27- loop delivered; pending Mux work completion 3/5- ready for activation; customer notified
2013-11-22 | ShaRita | AZ008-12-IJ | 4425 East Cotton Center Blvd. Phoenix, AZ 85040 | 100M ethernet, RJ45 interface md5 UHGVERbgpbqZyofa | Request id 190063988 order number 190067688 20153384 access 20153383 port |  |  | 5425291 | 10800 | E4000177 access C1000775 port | 14/KXGS/123888//ACSO DMARC Info: Demarc is 1st Flr Main MDF rm mounted on backboard port ckt is tagged not extended | 2013-12-05 | 2014-03-19 | 2014-03-19 | bpdd | 2014-03-31 | 2014-03-31 | unitedhealthgroup- 65132 | 702-242-7654 tauoa.falo@uhc.com |  | 1/2- LEC is working to schedule the site survey with the local contact on this order. This project needs equipment and/or fiber to provide service. CenturyLink personnel will contact us if there is difficulty or lack of response in scheduling the site visit. Please allow approximately 10 business days for site visit scheduling/ completion and subsequent contact for the project kickoff call. 1/9- pending response from LEC project manager on if site visit has already been scheduled or done. 1/16- Per Project Manager, Your order will be processed as a ‘flow thru’ order as soon as facilities are available. Currently United Healthcare has another order with another carrier that is currently in progress. Once their initial order completes, I will release your order to our Provisioning Center to be worked with standard dates. So for now order 20153384 will be placed on hold. As an FYI - their other order does require new equipment so they are looking at approximately 45 days to complete once it gets started. At the moment their initial order is ‘held’ while the end customer’s Corporate office approves of their site requirements. 1/22- order on hold 1/30- order on hold until intial order with other carrier completes. awaiting feedback from LEC if there are site requirements pending. 2/6- order on hold until intial order with other carrier completes. Per Project Manager, there are no site requirements. requested LEC to provide order information for other order; awaiting feedback 2/18- order still on hold. escalated to provisioning team lead to contact LEC in regards to other order; awaiting feedback. 2/20- order still on hold until intial order with other carrier complete. 2/27- escalated to provisioning to reach out to LEC to provide the latest status 3/6- escalated to 4th level escalation provisioning to provide status of order asap, Melissa Also reached out to LEC PM. Acocording to CL PM, the AQCB completed and provisioning is working on issued a due date. Due date will be 7-10 b days from when it's issued. 3/12- pending FOC date of 3/19 3/20- pending confirmation from LEC that circuit has been delivered 3/27- circuit delivered; beas installation scheduled for 3/27 4/1- ready for activation; customer notified
2014-01-15 | ShaRita | UTX44-03-IJ | 4050 Rio Bravo Suite 103, El Paso, TX 79902 | 1536 T1 MD5 UHGVERbgpbqZyofa | Service Order(s) [ 190116677 ] Order Request 190116310 20180211 access 20180210 port |  |  | 5437310 | 464 | D1001708 access C1001969 port | 30/HCGS/628658//SW DEMARC LOC: 1ST FLR,TELCO RM,TELCO BKBRD,CA DEMARC LOC Continued: BKBRD,CAB 1,SLOT 4 Jack Type: RJ48C | 2014-01-21 | 2014-01-30 | 2014-01-29 | bpdd | 2014-02-04 | 2014-02-03 | unitedhealthgroup-64722 | 214-647-4442 donald_r_osborn@uhc.com |  | 1/22- pending FOC date of 1/30 1/29- loop delivered; pending testing 2/3- ready for activation, engineer informed.
2013-12-11 | ShaRita | GA007-02-IJ | 115 Arkwright Landing Macon, GA 31210 | 3072, 2xT1 md5 UHGVERbgpbqZyofa | Service Order 190081113 Request id 190079730 access 20162697 port 20162696 |  |  | 5437310 | 1500 | N1000599 ¦ N1000600 access C3000514 port | 46/HCGS/615352//SB 1ST FLR TELCO RM MM2 SLT 1 46/HCGS/615353//SB 1STFLR TELCO RM MM2 SLT 2 | 2013-12-19 | 2014-01-17 | 2014-01-15 | bpdd | 2014-01-22 | 2014-01-30 | unitedhealthgroup- 65297 | 981-005-9326 pradeep_yadav@uhc.com |  | 12/11- ShaRita submitted order. 12/19- order was not submitted successfully. Called E2EI helpdesk for assistance. Order now pending provisioning approval. 1/2- pending FOC date of 1/17 1/9-pending FOC date of 1/17 1/16- loops delivered; pending testing 1/22- escalated to provisioning team to have circuit testing completed asap 1/29- NOC move was needed needed; order has been re-designed to new ports. pending testing 1/30 ready for activatiobn
2013-12-22 | ShaRita | none | A end: 5908 Hampton Oaks Pkwy, Tampa, FL 33610 on BACS : AOBK1H2R0001/NP0CXFVL0001 channel 26 B end 4601 Corporate Dr NW, Concord, NC 28027 | pt to pt T1 | NSPE0007663791 IQBKT8WM re-issue IQBKVLHD | 6180880 | P2058245 |  |  | MGBK4C000001 NP0CXFVL0001 SLOT 26 | NC/HCGS/127383/ /WINS/ The demarc is 1st flr, data room, mx2820, rj48c, not extended | 2014-01-14 | 2014-01-28 |  | bpdd | 2014-02-04 | 2014-01-28 |  |  |  | 12/24- order submitted to OE 12/31- ASR submitted to LEC; awaiting LEC to provide FOC date 1/16- capacity issue resolved; Re-issue order IQBKVLHD. ASR submitted to LEC; awaiting LEC to provide FOC date 1/22- pending FOC date of 1/28 1/28- ready for activation; customer notified
2013-11-13 | ShaRita | PA012-07-IJ | 1001 Brinton Road , Pittsburgh, PA 15221 | New 100M Ethernet type 2 premium with Multimode fiber LC connector, MD5 UHGVERbgpbqZyofa SAR is 1-1SEE1DF (100BaseFX), approval 026VWI-001, exp 3/18/14, iNet CP38005.00 PER 11131309. | smartform 190052106 NSPE0007531864 EACS IQBKS939 port IQBKS95Z | 6146246 | P2052376 EACS P2052391 PORT | 5423021 | 30000 | EDBK3XSC0001 EACS BCBK3XS40001 PORT | 15/KEGS/306998 /PA VZB DMARC: basement fiber demarc, mounted in rack 102.09 HANDOFF TYPE: Electrical | 2013-11-18 | 12/24/2013 1/9/2014 | 2014-01-09 | bpdd | 2014-01-28 | 2014-01-22 | unitedhealthgroup-65225 | 987-313-9388 anupam_datt@uhc.com |  | 11/20- ASR submitted; awaiting LEC to provide FOC date 11/26- awaiting LEC to provide FOC date 12/5- pending FOC date of 12/24 12/11- pending FOC date of 12/24 12/19- order on hold; customer will not allow access for placing or splicing until 1/3 1/3- Order on hold due customer's unavailability. customer will not allow access for placing or splicing until 1/3 1/9- Order on hold due customer's unavailability 1/16- beas installation scheduled for 1/22 at 830am EST 1/22- ready activation; customer notifed
2013-12-22 | ShaRita | none | A end: 5908 Hampton Oaks Pkwy, Tampa, FL 33610 on BACS : AOBK1H2R0001/NP0CXFVL0001 channel 27 B end 4601 Corporate Dr NW, Concord, NC 28027 | pt to pt T1 | NSPE0007663791 IQBKT87B | 6180886 | P2058334 |  |  | MGBK4C440001 NP0CXFVL0001 SLOT 27 | NC/HCGS/126431/ /WINS/ Demarc: 1st floor data center, mux #1 port 14, not extende d, RJ48C, tagged | 2013-12-30 | 2013-01-17 | 2014-01-13 | bpdd | 2014-01-23 | 2013-01-15 |  |  |  | 12/24- order submitted to OE 12/31- ASR submitted to LEC; awaiting LEC to provide FOC date 1/3- pending FOC date of 1/17 1/16- circuit ready for activation; customer notified
2013-10-29 | ShaRita | TX098-02-IJ | 7077 Highway 6 North Houston, TX 77095 | 6144 4xT1 with md5 UHGVERbgpbqZyofa John changed on 11/4 to 2xT1 | smartform 190033090 NSPE0007463945 new smartform 190040660 NSPE0007492178 IQBKS0TN IQBKS4MP | 6124608 6137004 | P2050701 P2051486 | 5420648 5421621 | 1536 | BCBK3R7D0001-2 BCBK3VB90001-2 | 28/HCGS/907488//SW CAB1 POS1 @ 1ST FLR TEL BOARD EMARC LOC Continued: xtended Wire (Yes or No): No W Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C 28/HCGS/907489//SW CAB1 POS2 @ 1ST FLR TEL DEMARC LOC Continued: Extended Wire (Yes or No): No EW Reason/Location:NO IW AUTHORIZED GROUND OK : Jack Type: RJ48C | 2013-11-12 | 2013-11-27 | 2013-12-23 | bpdd | 2013-12-06 | 2013-12-27 | unitedhealthgroup-64841 | 702-242-7654 tauoa.falo@uhc.com |  | 10/29- sent to ShaRita 10/31- corrected address per customer to 7077 Highway 6 North Houston, TX 77095. awaiting provisioning approval. 11/4- John requested to supp to change to 2xT1 11/6- awaiting ASR to be sent to LEC for FOC date 11/13- cancel/reissue by provisioning REISSUE DETAILED REASON (ORDER WAS AUTO OPS AS BLENDED PATH BUT CAPACITY IS DECOMMED NODE. FOUND CAPACITY BUT DIFFERENT POP. Awaiting LEC to provide FOC date. 11/20- pending FOC date of 11/27 11/26- pending FOC date of 11/27 12/5- order is on hold; per telco, customer needs to provide back board and new due date is required. Per ATT Lcon JULIE NGUYEN=281-387-0749 is already aware and she as made her contractor informed as to where the back board should be place. 12/12- John informed backboard now in place; requesting new FOC date 12/19- awaiting LEC to provide new FOC date 12/30- circuit ready for activation; engineer notified
2013-09-06 | B end - mark Wilson | UIR01-07-IJ | Letterkenny Business Park, Lisnenan, Letterkenny, Co.Donegal. Ierland | 50M ethernet on 100M access LC SMF handoff SOO to Letterkenny - circuit ID W0Y12673 with mds UHGVERbgpbqZyofa 85 percent ethernet shaping | s/o is 5355104 |  |  |  | 6144 | W1A68428 | Enet EN02969 | 2013-10-04 | 2013-11-20 |  | bpdd | 2013-12-31 | 2013-11-27 | unitedhealthgroup-64943 | 860-702-8284 keith_mangene@uhc.com |  | 9/9- Mark is working on SOF. 9/13- SOF sent to UHG. 10/2- KEITH MANGENE CALLED TO SAY THE AIRSPEED CANNOT BE USED FOR THIS IE WIRELESS CARRIER..SO I HAVE REVALIDATED THE GL.AND AWAIT NEW PRCING ETC 10/10- pending Lcon verification 10/17- ASR sent to the PTT, pending response. 10/23- per enet STILL CANNOT FIND A LCON THAT IS AWARE OF WHERE THE CIRCUIT IS TO TERMINATE. CURRENTLY MATTHEW ERSKINE IS INVESTIGATING WHERE THE CIRCUIT IS TO TERMINATE AND WILL REVERT TO E-NET ASAP. 10/31- passed new lcon info to provisoning, asked them to follow up with Enet 11/1- e-net have confirmed that the demarks have been clarified and are processing the order. Awaiting FOC. 11/7- Pending FOC. 11/14- PTT INSTALLATION 11 20 2013 11/27- ready for activation, engineer informed.
2013-10-29 | ShaRita | TX173-02-IJ | 5749 San Felipe, Houston, TX 77057 | 6144 4xT1 with md5 UHGVERbgpbqZyofa John changed on 11/4 to 3072 2xT1 | smartform 190033261 NSPE0007464627 New smartform 190040680 NSPE0007492122 IQBKS0CH | 6124640 6136962 | P2050652 | 5420618 | 1536 | BCBK3RYM0001-2 | 28/HCGS/907308//SW DEMARC LOC: 1ST FLR TELCO RM CAB 1 SLOT 7 28/HCGS/907309//SW DEMARC LOC: 1ST FLR TELCO RM CAB 1 SLOT 6 Jack Type: RJ48C | 2013-11-07 | 2013-11-21 | 2013-11-18 | bpdd | 2013-12-02 | 2014-11-20 | unitedhealthgroup-64834 | 702-242-7654 tauoa.falo@uhc.com |  | 10/29- sent to ShaRita 10/31- awaiting LEC to provide FOC date 11/4- John requested to supp to change to 2xT1 11/6- awaiting ASR to be sent to LEC for FOC date 11/13- pending FOC date of 11/21 11/20- ready for activation; engineer notified
2013-10-17 | ShaRita | FL077-02-IJ | 2191 9th Ave. N. Ste. 110 St. Petersburg, FL 33713 | 10752, 7 x T1 md5 encryption UHGVERbgpbqZyofa | smartform 190019605 NSPE0007416917 IQBKSDZD | 6113773 | P2046310 | 5413736 | 1536 | BCBK3FG50001-7 | 69/HCGS/430747//GTES DEMARC LOC: 1ST FLR TELCO BOARD, SHELF 2 POS 8 OF 14, RJ48X W/OPEN, TAG DEMARC LOC Continued: 2IDS, NOT EXT 69/HCGS/430748//GTES DEMARC LOC: 1ST FLR TELCO BOARD, SHELF 2 POS 9 OF 14, RJ48X W/OPEN, TAG DEMARC LOC Continued: 2IDS, NOT EXT 69/HCGS/430749//GTES DEMARC LOC: 1ST FLR TELCO BOARD, SHELF 2 POS 10 OF 14, RJ48X W/OPEN, DEMARC LOC Continued: TAG 2IDS, NOT EXT 69/HCGS/430750//GTES DEMARC LOC: 1ST FLR TELCO BOARD, SHELF 2 POS 11 OF 14, RJ48X W/OPEN, TAG DEMARC LOC Continued: 2IDS, NOT EXT 69/HCGS/430751//GTES DEMARC LOC: 1ST FLR TELCO BOARD, SHELF 2 POS 12 OF 14, RJ48X W/OPEN, TAG DEMARC LOC Continued: 2IDS, NOT EXT 69/HCGS/430752//GTES DEMARC LOC: 1ST FLR TELCO BOARD, SHELF 2 POS 13 OF 14, RJ48X W/OPEN, TAG DEMARC LOC Continued: 2IDS, NOT EXT 69/HCGS/430753//GTES DEMARC LOC: 1ST FLR TELCO BOARD, SHELF 2 POS 14 OF 14, RJ48X W/OPEN, TAG DEMARC LOC Continued: 2IDS, NOT EXT. Jack Type: RJ48X | 2013-10-24 | 2013-11-04 | 2013-11-04 | bpdd | 2013-11-11 | 2013-11-05 | unitedhealthgroup-65187 | 210-877-7919 chris_spoor@uhc.com |  | 10/17- sent to ShaRita 10/24- awaiting provisioning to send ASR to LEC 10/31- pending FOC date of 11/4
2013-10-10 | ShaRita | KS008-05-IJ | 7100 College Blvd. Overland Park, KS 66210 | 6144 4xT1 with md5 UHGVERbgpbqZyofa | smartform 190012310 NSPE0007393649 IQBKR839 | 6106325 | P2045385 | 5412378 | 1536 | BCBK3CX80001-4 | 74/HCGS/945855//SW DEMARC LOC: UPPER LVL TELCO RM CAB 2 SLOT 6 Jack Type: 48c 74/HCGS/945856//SW DEMARC LOC: UPPER LVL TELCO RM CAB 2 SLOT 2 Jack Type: 48c 74/HCGS/945857//SW DEMARC LOC: UPPER LVL TELCO RM CAB 2 SLOT 8 INSIDE Jack Type: 48c 74/HCGS/945858//SW DEMARC LOC: UPPER LVL TELCO RM CAB 2 SLOT 9 INSIDE Jack Type: 48c | 2013-10-14 | 2013-10-23 | 2013-10-23 | bpdd | 2013-10-30 | 2013-10-23 | unitedhealthgroup- 65093 | 702-242-7654 tauoa.falo@uhc.com |  | 10/10- sent to ShaRita 10/17- pending FOC date of 10/23 10/23- ready for activation; engineer notified
2014-04-02 | ShaRita | CA089-02-IJ | 2050 Main St, STE 850 , Irvine, CA 92614 | 6144, 4 x T1 md5 UHGVERbgpbqZyofa | Opp Id O-0984777 Quote ID: 190220185 Order Request 190235904 Service Order(s) [ 190237976 20267125 access 20267124 port |  |  | 5469103 | 1536 | C1004303 port N1002263 access N1002264 access N1002265 access N1002266 access | 13/HCGS/850290//PT DEMARC LOC: NIU BUILT INTO MUX AND ID'D DEMARC LOC Continued: snap jk#3 pos#3 tagged 13/HCGS/850291//PT DEMARC LOC: NIU BUILT INTO MUX AND ID'D IN MUX DEMARC LOC Continued: snap jk#3 pos#4 tagged 13/HCGS/850292//PT DEMARC LOC: NIU BUILT INTO MUX AND ID'D IN MUX DEMARC LOC Continued: snap jk#3 pos#5 tagged 13/HCGS/850293//PT DEMARC LOC: NIU BUILT INTO MUX AND ID'D IN MUX DEMARC LOC Continued: IN MUX Jack Type: RJ48C | 2014-04-15 | 2014-04-29 | 2014-04-25 | bpdd | 2014-05-02 | 2014-05-12 | unitedhealthgroup-64904 | 763-744-1575, daniel_j_skripka@uhc.com |  | 4/3- pending error to create quote. Ticket S9279049 created 4/10- ticket resolved, quote created, pending credit approval 4/17- FOC date 4/29 4/23- FOC date 4/29 5/1- circuit delivered; incomplete route in BGW defect 2981 5/8- As per provisioning pending resolution regarding incomplete route in BGW 5/13- ready for activation; customer notified
2014-03-05 | ShaRita | UCA10-05-IJ | 5701 Katella, Cypress, CA 90630 | 100mg ehernet with dport john will throttle down to 50mg rJ45 copper handoff md5 UHGVERbgpbqZyofa | quote/order # is 190182429 Service Order(s) [ 190186917 ] has been created for Order Request 190186837 20228650 access 20228649 port lsa-I134892 lsa a134920 lsa a135167 lsa-I135447 |  |  | 5453056 | 15360 | C1003309 port E4000562 access | lsa i134892 (ea-br9h-br9h-0001) lsa a135167 (oh-n6v-br9h-0001) lsa i135447 (ea-br9h-br9h-0002) demarc 1st flr , ISG400 1.2.3a:0.1. |  |  |  | bpdd | 2014-05-02 | 2014-05-14 | unitedhealthgroup-65444 | 763-744-1575 daniel_j_skripka@optum.com |  | 3/6- melissa is working on order 3/12- order submitted; provisioning is working, on-net 3/20- Pending CCRs 1201097 (EBAP STD) Overture ISG1400 @ br9h,01 RFT 4/25 1201100 (CARD ADD) OC3 Card OC48.br b7t,03-br9h,01 RFT 4/11 3/27- Pending CCRs 1201097 (EBAP STD) Overture ISG1400 @ br9h,01 RFT 4/25, equipment shipped. 1203638 (CARD ADD) OTrib Shelf/OC3 Card OC48.br b7t,03-br9h,01 RFT 4/11 4/3- Pending CCRs 1201097 (EBAP STD) RFT 4/25, equipment shipped, topology built, pending equipment install Overture ISG1400 @ br9h,01 1203638 (SYS RECONF) RFT 4/28- , card shipped and recieved TRIB SH/OC3 Card OC48.br b7t,03-br9h,01 4/10- Sonet wk completed on H1D, O1A, & BR (passthru) ring (STS3C), FFP built...step OPIN for tech to compl xconn...t/u. 4/17- Pending CCR 1201097 (EBAP STD) RFT 4/25. CCR 1203638 complete Installed overture at Loc 1 with Lambert. Local contact or anyone on site does not knopw where this Ethernet circuit is going to land. Left a loop plug in pos 1 on the overture and flagged for techs when they find out where they want to land this circuit. currently building trunk 4/23- asked John to verify the demarc with end user because the local order was returned to us requesting for the actual demarc. tcoms order lsa-I134892 is now cancelled and replaced with lsa-I135447 5/1- Pending RFC testing to hardloop due to pending confirmation if VZb will hand off at 1st floor 5/8- Pending RFC testing to hardloop due to pending confirmation if VZb will hand off at 1st floor 5/14- ready for activation; customer notified
2014-03-27 | Melissa | MN053-73-IJ | 14100 Business Center Drive, Elk River | New VLAN on 10G 400meg on existing circuit bobktfpx0001 | Order Number: 10187520 PVC ID: 5463424 |  |  |  |  | bobktfpx0001 |  |  |  |  | bpdd |  | 2014-04-24 | UHG-ECC- 65165 | 763-744-0840 matt_f_seymour@optum.com |  | 4/2- PVC created, configlet requested 4/10- new vlan in place, will send configlets to Matt 4/17 configlet requested 4/24 configlet sent to Matt
2014-03-27 | Melissa | MN053-75-IJ | 14100 Business Center Drive, Elk River | New VLAN on 10G 400meg on existing circuit BOBKWHD00001 | Order Number: 10187517 PVC ID: 5463422 |  |  |  |  | BOBKWHD00001 |  |  |  |  | bpdd |  |  | UHG-ECC- 65165 | 763-744-0840 matt_f_seymour@optum.com |  | 4/2- PVC created, configlet requested 4/10- new vlan in place, will send configlets to Matt 4/17 configlet requested 4/24 configlet sent to Matt
2013-08-07 | ShaRita | FL026-02-IJ | 1118 S Orange Ave, Suite 201, Orlando, FL 32806 | 10752 7xT1 with md5 UHGVERbgpbqZyofa | Smartform 189946934 NSPE0007139407 IQBKPVSF | 6014833 | P2030524 | 5382910 | 1536 | BCBK2CJW0001-0007 | 58/HCGS/787210//SB DEMARC LOC: 2ND FLR STE201 TELCO RM.CAB1 SLT1 58/HCGS/787211//SB DEMARC LOC: 2ND FLR STE201 TELCO RM.CAB1 SLT2 58/HCGS/787212//SB DEMARC LOC: 2ND FLR TELCO RM STE201 CAB1 SLT3 58/HCGS/787213//SB DEMARC LOC: 2ND FLR TELCO STE201 CAB5 SLT4 58/HCGS/787214//SB DEMARC LOC: 2ND FLR TELCO RM.STE201 CAB6 SLT1 58/HCGS/787215//SB DEMARC LOC: 2ND FLR TELCO RM.STE201 CAB6 SLT2 58/HCGS/787216//SB DEMARC LOC: 2ND FLR TELCO RM.STE.201 CAB6 SLT3 Jack Type: RJ48C | 2013-08-16 | 2013-11-04 | 2013-11-04 | bpdd | 2013-11-11 | 2013-11-05 | unitedhealthgroup-64887 | 214-647-4442 donald_r_osborn@uhc.com |  | 10/10- pending FOC date 11/4 10/16- pending FOC date of 11/4 The issue is there arent any more facilities as this customer has exhausted all cable pairs to the cross box. This customer had 7 T1s installed on 8/15 and exhausted their capacity. With this being an install for an additional 7 T1s there isnt capacity. This will require a construction job and ECD of 10/28 is the soonest they can complete it out making your DD 11/4/13. We will not be able to bring in your dates or issue a design until the work order has been completed on 10/28 10/23- pending FOC date 11/4 10/31- pending FOC date 11/4
2013-10-02 | ShaRita | FL083-02-IJ | 260 Wekiva Springs Road, Suite 1000, Longwood, FL 32779 | 10752 7 x T1 md5 encryption UHGVERbgpbqZyofa | smartform 190004098 NSPE0007364560 IQBKR26N | 6095473 | P2044086 | 5409948 | 3072 | BCBK29BY0001-7 | 10.HCGS.152769..UFLG DEMARC LOC: 1ST FLR STE. 1000, ELEC ROOM, CAB 2, SLOT 1 OF 8,RJ48C,T/L,NOT EXT Jack Type: 48C 10.HCGS.152770..UFLG DEMARC LOC: 1ST FLR STE. 1000, ELEC ROOM, CAB 2, SLO T 2 OF 8,RJ48C, T/L,NOT EXT Jack Type: 48C 10.HCGS.152771..UFLG DEMARC LOC: 1ST FLR STE. 1000, ELEC ROOM, CAB 2, SLOT 3 OF 8,RJ48C,T /L,NOT EXT Jack Type: 48C 10.HCGS.152772..UFLG DEMARC LOC: 1ST FLR STE. 1000, ELEC ROOM, CAB 2, SLOT 4 OF 8,RJ48C,T/L,NOT EXT Jack Type: 48C 10.HCGS.152773..UFLG DEMARC LOC: 1ST FLR STE. 1000, ELEC ROOM, CAB 2, SLOT 5 OF 8,RJ48C,T/L,NOT EXT Jack Type: 48C 10.HCGS.152774..UFLG DEMARC LOC: 1ST FLR STE. 1000, ELEC ROOM, CAB 2, SLOT 6 OF 8,RJ48C,T /L,NOT EXT Jack Type: 48C 10.HCGS.152775..UFLG DEMARC LOC: 1ST FLR STE. 1000, ELEC ROOM, CAB 2, SLOT 7 OF 8,RJ48C,T /L,NOT EXT Type: 48C | 2013-10-10 | 2013-10-25 | 2013-10-23 | bpdd | 2013-11-01 | 2013-10-29 | unitedhealthgroup- 65182 | 210-877-7919 chris_spoor@uhc.com |  | 10/4- submitted to OM 10/10- ASR sent; awaiting FOC date to be provided 10/16- pending FOC date of 10/25 10/23- loop delivered; testing completed. Pending ports from DTAC 10/29- ready for activation, engineer informed.
2013-08-07 | ShaRita | FL024-03-IJ | 4740 Exploration Ave, Lakeland, FL 33812 | 10752 7xT1 with md5 UHGVERbgpbqZyofa | smartform 189946898 NSPE0007139352 IQBKPVR2 | 6014677 | P2030520 | 5382913 | 1536 | BCBK2CJN0001-0007 | 69/HCGS/429659//GTES FLASHWAVE-POS-28.1ST FL EQ RM Jack Type: RJ48X 69/HCGS/429660//GTES FLASHWAVE-POS-29.1ST FL EQ RM Jack Type: RJ48X 69/HCGS/429661//GTES FLASHWAVE-POS-30.1ST FL EQ RM Jack Type: RJ48X 69/HCGS/429662//GTES FLASHWAVE-POS-31.1ST FL EQ RM Jack Type: RJ48X 69/HCGS/429663/ /GTES/ FLASHWAVE,POS-24.1ST FL EQ RM Jack Type: RJ48X 69/HCGS/429664/ /GTES/ FLASHWAVE,POS-23.1ST FL EQ RM Jack Type: RJ48X 69/HCGS/429665/ /GTES/ FLASHWAVE,POS-22.1ST FL EQ RM Jack Type: RJ48X | 8/16/2013 9/10/2013 | 8/27/2013 9/19/2013 | 2013-10-23 | bpdd | 2013-09-04 | 2013-10-24 | unitedhealthgroup-64897 | 214-647-4442 donald_r_osborn@uhc.com |  | 9/12- provided new lcon, Kevin Buckley , and supp'ed order for new due date. pending new FOC date of 9/19 9/19- pending confirmation from LEC that loop was delivered as scheduled, 9/19 9/25- a late loop ticket was opened and advised the following Per construction - The flash wave 4100 for this w/ord is to be installed in the field; this is to be completed by COEI. At this time the RTC (release to construction) date is 10/2, the construction start date is 10/7; they are still waiting on materials 10/4- NDMT ticket B201309200608. Per update from Linda McMillan/Logistics - W000686497 - 8600622909 line 10 - tracking request sent to vendor; 8600622933 line 10 - emailed vendor expedite request; 8600622948 line 40 - emailed vendor for status/bssd; 8600714069 - emailed vendor for status/bssd 10/9- pending loop delivery- with ndmt ticket B201309200608, escalating on equipment status 10/17- Order has been referred back to Telco (GT10) designer to redesign the circuit because there is an issue with the inter office facilities. ECD of construction was 10/16; awaiting confirmation from LEC that construction was completed as scheduled 10/23- loop delivered; pending testing to complete 10/24- order ready for activation, engineer informed
2013-08-09 | ShaRita | C1518-04-IJ | 4335 Equity Drive, Columbus OH | 44736 DS3 with mD5 UHGVEReccgas4Usp9 | smartform 189949861 CDR201308130022 NSPE0007155616 IQBKPXPX IQBKQT1F re-issue clm I3332 3x-bgyz-czb-0197 | 6018138 | P2031038 P2035021 re-issue | 5384155 5390479 re-issue | 7500 | BCBK2DF20001 BCBK2N1W0001 | 13/HFGS/108769/TWCS demarc information: 1st floor, network room , tw cabinet # 2, position 9. Tagged and extended. | 8/14/2013 9/4/2013 | 9/3/2013 9/11/2013 | 2013-09-11 | bpdd | 2013-09-26 | 2013-09-23 | UHG-ECC 65516 | 763-7442154 scott_moyer@uhc.com | This is scheduled for 10/11/2013 01:00:00 PM Central Time / Conference bridge 866-878-8630 pass code 6653710. | 8/14- Pending local design to get handoff to issue asr to time warner, this will go from verizon local to Time warner to AT&T to customer. 8/22- pending FOC date of 9/3 8/29- new local design being issued; per LD design change, can not use DS3 pip port @ CMK............CDR APPROVED FOR 1) OPT 2 PIP ORDER CITY PAIRS: CO9 -NOR...LD is approved/enabled from CO9-NOR on TPTA network. ..MUX: H-UAV380 9/5- ASR sent; awaiting LEC to provide FOC date 9/12- awaiting confirmation that loop was delivered as scheduled on 9/11 9/18- loop delivered; pending cross connect dispatch scheduled 9/19 9/23- order complete, engineer informed.
2013-09-23 | ShaRita | NY058-05-IJ | 13 Cornell Rd , Latham, NY 12110 ** need mid Nov | 12228, 8xT1 with MD5 UHGVERbgpbqZyofa | smartform 189990738 NSPE0007317655 IQBKRJ69 ALB I4078 | 6066904 | P2039991 | 5402984 | 9216 | BCBK21HW0001-0008 | ckt 1: 34.HCGS.800552..NY Basement,Tel ar,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,2,, DEMARC LOC Continued: Jack Type: RJ48C ckt 2: 34.HCGS.800553..NY Basement,Tel,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,3,Rj48c slot 3 DEMARC LOC Continued: of 14 in bsmt Jack Type: RJ48C ckt 3: 34.HCGS.800554..NY Basement,Tel ,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,4,Rj48c slot 4 DEMARC LOC Continued: of 14 in mtg# Jack Type: RJ48C ckt 4: 34.HCGS.800555..NY Basement,Tel,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,5,, DEMARC LOC Continued: Jack Type: RJ48C ckt 5: 34.HCGS.800556..NY Basement,Tel,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,6,Rj48c slot 6 DEMARC LOC Continued: of 14 in mtg#2 Jack Type: RJ48C ckt 6: 34.HCGS.800557..NY Basement,Tel,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,7,Rj48c slot 7 DEMARC LOC Continued: of 14 in mtg#2 Jack Type: RJ48C ckt 7: 34.HCGS.800558..NY Basement,Tel,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,8,Rj48c slot 8 DEMARC LOC Continued: of 14 in bsmt Jack Type: RJ48C ckt 8: 34.HCGS.800559..NY Basement,Tel,OPEN AREA,RJ48C,Y,N,MNTG,2,SLOT,9,Rj48c slot 9 DEMARC LOC Continued: of 14 in bsmt Jack Type: RJ48C | 2013-09-25 | 2013-10-15 | 2013-10-14 | bpdd | 2013-10-18 | 2013-10-14 | unitedhealthgroup- 65129 | 987-313-9388 anupam_datt@uhc.com |  | 9/25- awaiting provisioning to send ASR 10/4- blended path, foc for 10/15 on tail circuit, pending foc for x-conect 10/10- cross connect completed 10/7; pending loop delivery of 10/15 10/17- ready for activation; engineer notified
2013-09-18 | ShaRita | C1560-01-IJ | 8534 Concord Center Drive Englewood, CO 80112 | T1 1536 mds UHGVEReccgas4Usp9 | smartform 189985266 NSPE0007300085 IQBKRFGR | 6059680 | P2039269 | 5400343 | 128 | BCBK2YWB0001 | 24/HCGS/745972//MS dmarc 1st flr mn it cab#2 slt 7/14 | 2013-09-23 | 2013-10-07 | 2013-09-30 | bpdd | 2013-10-14 | 2013-10-14 | UHGECC- 65521 | 763-744-2082 eric_taylor@uhc.com |  | 9/18- sent to ShaRita 9/25- ASR sent to LEC; awaiting FOC date to be provided 10/4 local loop delivered, pending testing. 10/10- pending mux work to be completed on 10/15
2013-09-11 | ShaRita | MA003-05-IJ | 1 Main Street Cambridge, MA 02142 | 10M port on 100M ethernet access SM LC connections mds UHGVERbgpbqZyofa | NSPE0007271116 iNet is CP36021.00, PER 09111305. Smartform 189978110 IQBKQ6Z8 eacs IQBKQ7FL port CCR#: 1176338 RFT 10/9 bst I0083394 (clsd) | 6052360 | P2038039 eacs P2038118 port | 5396363 | 2048 | EDBK2WK60001 eacs BCBK2WP90001 port | ea-mst-mst-0007 demarc: 10th floor MDF room vzb fiber panel #1 port 3 & 4 |  |  |  | bpdd | 2013-10-23 | 2013-10-03 | unitedhealthgroup- 65076 | 860-702-8284 keith_mangene@uhc.com | This has been scheduled for 10/16/2013 04:00:00 PM Central Time. Customer no show - waited in the bridge with BNE tech Rachelle Ann Cunignig for 30 minutes. BNE tried calling the customer but only got his VM. This needs to be rescheduled. Conference bridge 866-692-3158 Conference Pass Code 9236734 | 9/11- sent to ShaRita 9/18- CCR Current RFT Date: TBD 9/19- CCR 1176339 for Media converter, not needed. 9/25- CCR #:1176338 (CARD ADD) for overture completed, pending ETE test, set for 9/27 10/2- went to the pop at ^MST^ and fibered out the circuit from the overture card 0, port 3 to the fiber panel leading to the 10 floor using ports 11 & 12. when i got to the customer^s 10th floor reception, the lcon was offsite and said that he will be at the location tomorrow by 1pm and was not able to provide entry to the comp room. a revisit is set for tomorrow by 1pm to resume the test prep for the RFC. 10/10- ready for activation; engineer notified
2013-09-05 | ShaRita | C1558-01-IJ | 1525 NW 98th Court Doral FL 33172 | 6144 4xT1 w mds UHGVEReccgas4Usp9 | smartform 189973309 NSPE0007247861 IQBKQ0H2 MIA I0036597 | 6047894 | P2036664 | 5392366 | 128 | BCBK2SYD0001-4 | 13-MIB-BJF5-0103 dsx 2.17.2l:1.6.1 13-MIB-BJF5-0104 dsx 2.17.2l:1.7.2 13-MIB-BJF5-0105 dsx 2.16.7r:1.3.3 13-MIB-BJF5-0106 dsx 2.16.7r:1.4.1 dmarc Loc 2:UNITED HEALTH GROUP BLDG MAIN FL MAIN RM MPOE, on DSX panel | 2013-09-09 | 2013-10-01 | 2013-09-27 | bpdd | 2013-10-01 | 2013-09-27 | UHGECC- 65526 | 763-553-4895 john_bremseth@uhc.com |  | 9/5- Sent to ShaRita 9/12- ASR issued; awaiting LEC to provide FOC date 9/18- pending FOC date of 9/24 9/25- pending confirmation loop was delivered 9/26- loop not delivered, pending field wiring 10/2- order closed, pending dmarc info.
2013-06-05 | ShaRita | UNC16-12-IJ | 3803 North Elm Street Greensboro, NC 27455 | 300M ethernet md5 encryption type 4 UHGVERbgpbqZyofa Hand Off - Multi-Mode fiber with LC connector. | smartform 189891384 NSPE0006869348 IQBKMZ87 IQBKNBZF CP33257.00, PER 06051308 SAR 1-1PNTZHB, confirmation code CONFIRM, exp date 9/2/13 | 5920347 | P2015167 | 5367835 | 100000 | BCBK1J5F0001 (port) EDBK1DBN0001 (eacs) | 24/KRGN/400334//SB 3rd Floor, relay rack 300.2, not extended HANDOFF TYPE:Optical Multimode Fiber | 2013-07-31 | 2013-08-09 | bpdd | 8/7/13 8/28/13 | 2013-08-22 | 2013-08-22 | unitedhealthgroup-64535 | Steve Brown 763-694-7333 skbrown1@uhc.com | Needs to be rescheduled The sfp was already delivered last 9/09/2013. I had step this order for dispatch already. Now we are waiting on when it will be scheduled and then after that the FT will resume his task in completing out his installation. Thanks! Hope that helps. 866-878-8630 6653710 | 6/6- awaiting order to be assigned to provisioning 6/13- contacted provisioner to have order OPS approved ASAP 6/20- ASR sent; awaiting LEC to provide FOC date 6/27- Advised provisioning that ASR was returned from LEC and needs to be re-issued ASAP 7/3- pending FOC date of 7/31 7/11- pending FOC date of 7/31 7/18- pending FOC date of 7/31 7/25- pending FOC date of 7/31 7/31- order supp'ed for a new FOC date because tech did not gain access to deliver loop; pending LEC to provide new FOC date, need to use Steve Brown for access 8/8- customer requested tech complete install on 8/8; awaiting confirmation from LEC that installation was completed 8/14- pending BEAS install; need to confirm demarc extension before order is stepped for dispatch 8/22- Beas install scheduled for 8/22 8/29- ready for activation; engineer notified
2013-08-07 | ShaRita | NY068-05-IJ | 1 bryant park 40th floor, NY, NY 10110 | 10M ethernet Type 2, SAR 1-1QW747J, confirmation code 02WD8-0001, expiration 12/10/13. No iNet needed. with md5 UHGVERbgpbqZyofa SMF/.LC handoff | Smartform 189948810 NSPE0007149802 IQBKPZDZ access IQBKP1NB port | 6018870 | P2031526 | 5391368 | 2000 | BCBK2FX50001 port EDBK2D9T0001 access | 32.KEGS.024458..NY Demarc : 40th floor,Computer room Rack number 1 verizon Beusiness ISG 4000 port 0.1 Handoff : electrical . | 2013-09-06 | 2013-09-06 | bpdd | 2013-09-13 | 2013-09-11 |  | unitedhealthgroup-65266 | 860-702-8284 keith_mangene@uhc.com |  | 8/8- pending confirmation of handoff from Keith 8/14- order being worked by Ethernet Cell and awaiting to be assigned to an order manager 8/22- awaiting LEC to provide FOC date 8/29- pending FOC date of 9/6 9/5- pending FOC date of 9/6 9/12- ready for activation; engineer notified
2013-08-07 | ShaRita | C1365-05-IJ | 1821 Rutherford Lane / Suite 300, Austin, TX 78754 | 4608 3xT1 with mD5 UHGVEReccgas4Usp9 | smartform 189949855 NSPE0007155255 IQBKPXNF | 6018013 | P2031017 | 5384141 | 128 | BCBK2DD70001-0003 | 32/HCGS/691702 /SW DEMARC LOC: MPOE, 3RD FLR TLCO RM, QUD MNT CB # DEMARC LOC Continued: MNT CB #1, SLT 4 32/HCGS/691703//SW DEMARC LOC: MPOE, 3RD FLR TLCO RM, QUD MNT CB # DEMARC LOC Continued: MNT CB #1, SLT 3 32/HCGS/691704//SW DEMARC LOC: MPOE, 3RD FLR TLCO RM, QUD MNT CB # DEMARC LOC Continued: MNT CB #1, SLT 5 | 2013-08-27 | 2013-08-23 | bpdd | 2013-09-04 | 2013-08-28 |  | UHG-ECC 65484 | 763-7442154 scott_moyer@uhc.com |  | 8/13- sent to ShaRita 8/14- order submitted to Order Entry 8/22- pending FOC date of 8/27 8/29- ready for activation; engineer notified.
2013-05-23 | ShaRita | C1531-05-IJ | 2929 E Corona Road Tucson, AZ 85756 | 44736, DS3 md5 encryption UHGVEReccgas4Usp9 | smartform 189881159 CDR201305230031 IQBKMM7N NSPE0006819484 | 5893730 | P2012567 | 5360494 | 20000 | BCBK063G0001 | 57/HFGS/108503/TWCS demarc: 1st flr data center tw rack, tcsmazwyx1002 jack 3, label n ot extended. | 2013-06-12 | 2013-07-02 | bpdd | 2013-07-09 | 2013-08-13 |  | UHG-ECC- 65470 | 763-744-0840 matt_f_seymour@uhc.com |  | 5/23- sent to Sharita 5/30- pending FOC of 6/12 6/6- pending FOC of 6/12 6/13- loop delivered, pending commit date and testing 6/20- Awaiting for TPTA MUX to be completed, commit date 7/9 6/27- pending dispatches for patching. will proceed to testing once completed. 7/3- tech working to resolve TPTA MUX issue 7/11- Escalated to have TPTA MUX issue completed asap 7/18- TPTA has been cancelled and re-issued. BMIS ticket S7741721 filed for the issue. Requested ticket be escalated. 7/25- New manual mux created, pushing for dispatch on new mux. 8/1- Escalated to have a tech dispatched on new mux asap. 8/8- This order has been escalated to 4th level escalation; tech has to be re-dispatched to confirm cross connects, dual port assignment 8/14- TPTA MUX issue being worked to resolved.
2013-06-05 | ShaRita | UMN47-06-IJ | 1707 W Creek Lane Chaska, MN 55427 mdf800 (tcoms M6L7, 02) | 155.5 Mbps (OC3/STM1) Fiber SMF/LC connector type | Smartform 189891203 NSPE0006868658 CDR201306050060 IQBKM201 min-I34773 / o2-73c-m6l7-0003 CCR 1160374 (card add completed) | 5920724 | P2015980 | 5364987 | 43200 | BCBK1FKJ0001 | o2-73c-m6l7-0003 DEMARC: Space(SP) Chaska #2 Room MDF800 EXTENDED(Y/N): N TAGGED (Y/N): Y FIBER MODE (SMF/MMF): SMF CONNECTOR (SC/LC): LC HAND-OFF (2W/4W):2W |  |  |  | bpdd | 2013-08-20 | 2013-07-16 | UHG-ECC-TCW-65201 | Leon Betterman 763-744-1587 leon_l_betterman@uhc.com |  | 6/6- pending CDR approval, asked John about MDF termination 6/13- created local min-I34773 // First Circuit Id: o2-73c-m6l7-0003 6/20- CCR 1160374 SFP cards / pending capacity 511,20/m6l7,02. Cards shipped 6/27- Pending capacity 511,20/m6l7,02 / working with Leon for a date and time for access to install equipment 7/3- Pending Local order min-I34773 // First Circuit Id: o2-73c-m6l7-0003. Have ran fiber at the chaska MDF 800. Ran from M6L7 shelf 2 slot 5 port 2 to left fiber panel jack 5. Which goes to Bay AJ807 panel FB3A, A-5(jacks 9/10). Left a loop at demark with circuit id's and order number. 7/11- card add complete and CCR closed, working on fiber x-cons/node work 7/18- ready for activation; customer notified.
2013-04-16 | B end | UIX50-05-IJ | Unitech World Cyber Park, Sector 39, Gurgaon-122001 | 100M ethernet UHGVERbgpbqZyofa SOO Letterkenny - circuit ID W0Y12673 100BASE-TX handoff | SO: 5264686 & 5264687 |  |  | 5355043 | 18432 | W1A31791 (port) W1A31792 (access) | PROVIDER : TATA COMM(FORMERLY VSNL) 091NOID1143008210377 Demarc Info: TCL Mux_ GRGN_UNITEDHEALTH_01 (172.22.122.100) FE_card_Slot_7_Port_1 |  | 2013-06-28 | 2013-06-28 | bpdd | 2013-07-19 | 2013-07-11 | unitedhealthgroup- 64896 | 91 - 98100 59326, pradeep_yadav@uhc.com |  | 4/26-SOF with UHG 5/3- order in process. 5/9- request sent to PTT, pending response 5/16- checking with PTT on RFS date 5/22- PTT RFS DATE IS 06/28, commit date 7/19 5/30- PTT RFS DATE IS 06/28; WAITING FOR THE LOCAL LOOP TO BE DELIVERED 6/13- pending ptt delivery 6/27- Pending loop delivery 7/3- pending confirmation that loop was delivered 7/11- order ready for activation, engineer informed.
2013-06-10 | ShaRita | none | Miami, FL | 44736, DS3 md5 encryption UHGVERbgpbqZyofa change terremark handoff | CQBKM5L4 mia-C36041 | 5928357 | P1995221 | 5338777 | 10800 | BCBKY39N0001 | 3X-2ET-DNGL-0081 Loc Z demark: 2nd floor; Terremark west Meet-Me-Room; dsx3 panel; rr NAPMIA.2BX78.105.02.11 10. |  |  |  | bpdd | 2013-06-21 |  | unitedhealthgroup-65146 | 763.553.4801, sonja_d_mroczynski@uhc.com | need to re-request once handoff is changed with Terremark. | 6/10- sharita submited. 6/13- (mia-C36041) local order was created, requesting to redesign using the slot 15 at Terremark. 6/20- Per FT, pair is hard wired and the ring is full. Escalated to provisioning to re-design ring ASAP 6/24- ready for activation; customer notified
2013-06-07 | ShaRita | MI028-02-IJ | 950 Trade Centre Way, Ste 320, Kalamazoo MI 49002 | 3072 2xT1 with md5 UHGVERbgpbqZyofa | smartform 189892806 NSPE0006880331 IQBKM2ZJ GRR I0039142 / 13w7l nzbs0001 | 5926204 | P2015969 | 5364976 | 1536 | BCBK1FJ20001-0002 | /HCGS/578534//MB MB1st flr east terminal shelf 1 slot 4 of 14 not ext tagged rj48c /HCGS/578535//MB 1st flr east terminal shelf 1 slot 5 o f 14 not ext tagged rj48c | 2013-06-13 | 2013-06-26 | 2013-06-24 | bpdd | 2013-07-03 | 2013-06-28 | unitedhealthgroup-64924 | 214-647-4442 donald_r_osborn@uhc.com |  | 6/13- order approved by provisioning; awaiting ASR to be sent to LEC 6/20- FOC is scheduled for 6/26 6/27- awaiting confirmation loop was delivered 6/28- ready for activation; customer notified
2013-05-28 | ShaRita | MI008-05-IJ | 315 E. Eisenhower Pkwy, Ste 305, Ann Arbor, MI 48108 | 3072, 2 x T1 UHGVERbgpbqZyofa | smartform 189883266 NSPE0006831005 IQBKMRCT | 5899431 | P2013148 | 5361392 | 2752 | BCBK08VR0001-0002 | /HCGS/577921//MB /HCGS/577922//MB DEMARC LOC: ITEM #2 IS HDSL2 IN SHLF #1 SLOT 1/8 DEMARC LOC Continued: SLOT 1/8 1ST FLR TELCO RM | 2013-05-29 | 2013-06-12 | 2013-06-07 | bpdd | 2013-06-19 | 2013-06-11 | unitedhealthgroup-65045 | 763/694-7409, terry_bjorke@uhc.com |  | 5/28- submitted to OE. 5/30- with provisioning, pending ASR. 6/6- pending FOC of 6/12 6/13- ready for activation
2013-06-05 | ShaRita | PA006-03-IJ | 700 American Avenue Suite 206 King of Prussia, PA 19406 | 3072 2 x T1 md5 encryption UHGVERbgpbqZyofa | Smartform 189890722 NSPE0006864518 IQBKMZ51 | 5920158 | P2015133 | 5364171 | 1536 | BCBK1C840001 BCBK1C840002 | 11/HCGS/714849//PA BSMT 0,RM 0,UTIL RM ,RJ48C,LP Y,CAB N,SHELF 2,POS 4,RJ48C 11/HCGS/714850//PA BSMT 0,RM 0,UTIL RM ,RJ48C,LP Y,CAB N,SHELF 4,POS 1,RJ48C | 2013-06-10 | 2013-06-18 | 2013-06-17 | bpdd | 2013-06-25 | 2013-06-19 | UnitedHealthGroup-64682 | John Rothstein 763-744-1556 john_l_rothstein@uhc.com |  | 6/6- awaiting order to be assigned to provisioning 6/13- pending FOC date of 6/18 6/20- ready for activation; customer notified
2013-06-10 | ShaRita | none | Miami, FL | 44736, DS3 md5 encryption UHGVERbgpbqZyofa change terremark handoff | CQBKM5L4 mia-C36041 | 5928357 | P1995221 | 5338777 | 10800 | BCBKY39N0001 | 3X-2ET-DNGL-0081 Loc Z demark: 2nd floor; Terremark west Meet-Me-Room; dsx3 panel; rr NAPMIA.2BX78.105.02.11 10. |  |  |  | bpdd | 2013-06-21 |  | unitedhealthgroup-65146 | 763.553.4801, sonja_d_mroczynski@uhc.com | need to re-request once handoff is changed with Terremark. | 6/10- sharita submited. 6/13- (mia-C36041) local order was created, requesting to redesign using the slot 15 at Terremark. 6/20- Per FT, pair is hard wired and the ring is full. Escalated to provisioning to re-design ring ASAP 6/24- ready for activation; customer notified
2012-08-28 | ShaRita | NM026-05-IJ | Roswell, NM | 3072, 2xT1 with MD5 encryption UHGVERbgpbqZyofa | smartform 189688492 NSPE0005789067 IQBKBS8L | 5536194 | P1949581 | 5180080 | 1536 | BCBKVY630001-0002 | 54/HCGS/036632//MS DEMARC LOC: 5th floor telco room 8slot mt slot 4 of 8 54/HCGS/036633//MSDEMARC LOC: 5th floor telco room 8slot mt slot 5 of 8 |  | 2012-09-27 | 2012-09-24 | bpdd | 2012-10-04 | 2012-09-24 | UnitedHealth Group-65186 | 763-744-1575, daniel_j_skripka@uhc.com |  | 8/28 submitted to Beth 9/6- escalating with provisioning for ASR 9/14- ASR sent 9/14 with requested date 9/27 9/20- pending FOC for 9/27 9/27- order ready for a ctivation, engineer informed.
2012-09-14 | B end | CN592-02-IJ | Calgary, Alberta | 10M ethernet with md5 encrpytion UHGVERbgpbqZyofa | 5163662 (port) 5163665 (access) | 5616717 |  | 5163662 | 1536 | W0Z89663 (port) W0Z89662 (access) | Allstream P1211Z01411 DEMARC RACK MOUNTED 3916 CIENA. | 2012-11-05 | 2012-12-11 | 2012-12-10 | bpdd | 2012-12-17 | 2012-12-17 | unitedhealthgrou-65063 | 763-744-1847, donald_r_osborn@uhc.com |  | 9/19- pending sof 9/27- john asked to change the speed to 10mg 10/4- pending SOF 11/8- still pending SOF 11/16- john gave Siva SOF. 11/21- ASR sent to Allstream, pending fOC 11/29- Allstream FOC for 1/16, we did get notice that they will likely send us a new one to better that date. 12/6- FOC is moved up to 12/11 12/12- The circuit is delivered. Just waiting for final tests prior to hand-off. 12/17- order ready for activation, engineer informed.
2013-01-14 | ShaRita | FL011-02-IJ | Winter park, FL | 10752 7xT1 with MD5 UHGVERbgpbqZyofa | Smartform 189782166 NSPE0006290944 IQBKHH2K | 5701092 | P1982000 | 5320723 | 1536 | BCBKX95C0001-0001 | 50.HCGS.130628..UFLG 1ST FL TELCO/DATA RM, SUITE B4, CABINET 1, SLOT 1 OF 8 50.HCGS.130629..UFLG 1ST FL TELCO/DATA RM, SUITE B4, CABINET 1, SLOT 2 OF 8 50.HCGS.130630..UFLG 1ST FL TELCO/DATA RM, SUITE B4, CABINET 1, SLOT 3 OF 8 50.HCGS.130631..UFLG 1ST FL TELCO/DATA RM, SUITE B4, CABINET 1, SLOT 4 OF 8 50.HCGS.130632..UFLG 1ST FL TELCO/DATA RM, SUITE B4, CABINET 1, SLOT 5 OF 8 50.HCGS.130633..UFLG 1ST FL TELCO/DATA RM, SUITE B4, CABINET 1, SLOT 6 OF 8 50.HCGS.130634..UFLG 1ST FL TELCO/DATA RM, SUITE B4, CABINET 1, SLOT 7 OF 8 | 2013-01-25 | 2013-02-11 | 2013-02-12 | bpdd | 2013-02-18 | 2013-02-12 | UnitedHealth Group-65023 | 210-877-7919 chris_spoor@uhc.com |  | 1/15- send to OM 1/24 order with provisioning, pending ASR. 1/30- FOC 2/11- commite 2/18 2/14: Order Complete in systems. Ready for customer. Activation notice sent
2013-04-02 | ShaRita | FL045-02-IJ | 5345 West 20th Ave, Hialeah, FL | 1536 T1 with mD5 encryption UHGVERbgpbqZyofa | smartform 189841986 NSPE0006607112 IQBKK6V2 | 5812198 | P2002528 | 5347428 | 1376 | BCBK0J0B0001 | 60/HCGS/448902//SB dmarc cab2, slot1, telco room, first flo or, RJ48C, tagged, not ext |  | 2013-04-23 | 2013-04-18 | bpdd | 2013-04-30 | 2013-04-19 | unitedhealthgroup-65167 | 763.553.4801, sonja_d_mroczynski@uhc.com |  | 4/2- submit to OM 4/11- FOC 4/23 commit date 4/30 4/25- order ready for activation, engineer informed
2013-04-02 | ShaRita | FL040-02-IJ | 701 NW 57th Ave Suite 150, Miami, FL | 1536 T1 with mD5 encryption UHGVERbgpbqZyofa | smartform 189842025 NSPE0006607292 IQBKK6X6 | 5812165 | P2002551 | 5347452 | 1376 | BCBK0J1T0001 | 60/HCGS/448951//SB DEMARC LOC: 1ST FL STE#150 TELCO RM CAB 2X1 TGD DEMARC LOC Continued: 2X1 TGD | 2013-04-11 | 2013-04-23 | 2013-04-23 | bpdd | 2013-04-30 | 2013-04-23 | unitedhealthgroup-65172 | 763.553.4801, sonja_d_mroczynski@uhc.com |  | 4/2- submit to OM 4/11- FOC 4/23 commit date 4/30 4/25- order ready for activation, engineer informed
2013-04-02 | ShaRita | FL043-02-IJ | 1210 NW 95th Street, Miami, FL | 1536 T1 with mD5 encryption UHGVERbgpbqZyofa | smartform 189842075 NSPE0006607699 IQBKK6XD | 5812188 | P2002541 | 5347442 | 1376 | BCBK0J060001 | 60/HCGS/449023//SB DEMARC LOC: 1FL TEL RM CAB2 SLOT1 | 2013-04-15 | 2013-04-26 | 2013-04-25 | bpdd | 2013-05-03 | 2013-04-25 | unitedhealthgroup-65161 | 763.553.4801, sonja_d_mroczynski@uhc.com |  | 4/2- submit to OM 4/11- pending ASR ticket opened. B201304110043 4/19- FOC 4/26, commit 5/3 4/25- lec delivered, pending testing 5/2- order ready for activation, engineer informed.
2013-02-26 | B end | UK750-02-IJ | SunGard Availability Services Ltd C/O Global Switch 2 , 3 Nutmeg Lane, London, , E14 2AX,UK- 11th floor / Area 7-Verizon Rack | 50M Ethernet with md5 encryption UHGVERbgpbqZyofa SOO to Letterkenny - circuit ID W0Y12673 | 5263335 |  |  |  | 15360 | W1A31298 |  |  |  |  | bpdd |  |  | unitedhealthgroup- 65020 | 763/694-7370, masroor_khan@uhc.com |  | 3/7- pending SOF on B end 3/28- UHG has the SOF to the in country person 4/19- new SOF sent to UHG. Pending signature 4/24- SOF returned to Mark at Verizon 5/2- reached out to John for lcon e-mail 5/22- ready for activation
2015-01-13 | ShaRita | none | 7 Teleport Dr Staten Island, NY 10311 |  | NSPE0008932425 OQBK3MR9 |  |  |  |  | BCBKGRCX0001-2 |  |  |  |  | 1/15/2015 (standard 30 business days) | 2015-02-05 | 2015-02-05 |  |  |  | 1/8- submitted to Sadisconnects 1/14- pending disconnect due date 2/5 1/28- pending disconnect due date 2/5 2/5- soft disconnect complete, pending disconnect completion 2/12- disconnect complete
2015-01-07 | ShaRita | none | 7077 Highway 6 North HOUSTON TX USA 77095 |  | NSPE0008914046 OQBK3F1N |  |  |  |  | BCBK3VB90001-2 |  |  |  |  | 1/7/2015 (standard 30 business days) | 2015-02-05 | 2015-02-05 |  |  |  | 1/8- submitted to Sadisconnects 1/14- pending disconnect due date 2/5 1/28- pending disconnect due date 2/5 2/5- soft disconnect complete, pending disconnect completion 2/12- disconnect complete
2015-01-07 | ShaRita | none | 8101 O Street / 3rd floor LINCOLN NE USA 68510 |  | NSPE0008914058 OQBK3FSS |  |  |  |  | BCBKL3CF0001 |  |  |  |  | 1/7/2015 (standard 30 business days) | 2015-02-05 | 2015-02-05 |  |  |  | 1/8- submitted to Sadisconnects 1/14- pending disconnect due date 2/5 1/28- pending disconnect due date 2/5 2/5- soft disconnect complete, pending disconnect completion 2/12- disconnect complete
11/18/2014 changed 11/20 | ShaRita | LA005-02-IJ | 7305 Florida Blvd suite 7389-100A, Baton Rouge, LA 70806 | 100M will throttle down to 20M Ethernet , Optical, MMF, LC connector, MD5 UHGVERbgpbqZyofa | O-1146712 Quote ID: 190624755 Order Request 190624898 New quote 190629837 New Order Request 190629911 New Service Order 190636951 20635675 access 20635674 port | 190636951 |  | 5544983 | 10mg (9664 not avail) | E4002762 C1013206 | 24.KFGX.000091..COXC. VZB DMARC: server room, wall mounted, close to COX Accedian and the other cox equipment. labeled with the lec ckt id and labeled with Verizon Beas Box | 2014-11-25 | 2015-01-05 | 2015-02-02 | bpdd Standard 1/12/2015 | 1/12/2014 2/17/2015 | 2015-02-11 | unitedhealthgroup-65179 | 763-744-1589 david_casanova@optum.com | 2/17/15 at 2pm CST bridge 866-692-3158 passcode 9236734 | 11/18- Sent to ShaRita 11/20- John requested to add suite number 7389-100A to address. Order re-issued. 11/26- pending FOC date 12/4- FOC date 1/5 12/11- FOC date 1/5 12/17- FOC date 1/5 1/8- COX has confirmed there is a damage to previously existing lines by the building tenants which necessitates construction. Order is currently FOC’D for 2/9/15. Escalated and advised LEC PM that site is opening 2/1. 1/14- pending FOC date 2/9. Per our escalation team, no improvement still. FOC still on target. Will advise if they determine it can be improved as it progresses. 1/21- FOC date 2/9 1/28- FOC date 2/9 2/5- circuit delivered, awaiting scheduling of beas installation (escalated) 2/12- circuit ready for activation, customer notified
2014-12-01 | ShaRita | none | 48 Monroe Turnpike TRUMBULL CT USA 06611 |  | NSPE0008824210 |  |  |  |  | AOBJGWC80001 |  |  |  |  | 11/26/2014 (standard 30 business days) | [5 empty] | 12/1- submitted to Sadisconnects 12/4- The orders to disconnect the requested DS3 circuits listed on the attached LOD are not able to be proceed until the associated DS1 circuits have been removed. Please advise if you wish to proceed with this request., if so please submit an LOD listing all DS1's that are to be disconnected as well. 2/19- informed John this was submitted by Sue and disconnect complete
2014-12-01 | ShaRita | none | 48 Monroe Turnpike TRUMBULL CT USA 06611 |  | NSPE0008824210 |  | P1438722 |  |  | AOBJGS9N0001 |  |  |  |  | 11/26/2014 (standard 30 business days) | [5 empty] | 12/1- submitted to Sadisconnects 12/4- The orders to disconnect the requested DS3 circuits listed on the attached LOD are not able to be proceed until the associated DS1 circuits have been removed. Please advise if you wish to proceed with this request., if so please submit an LOD listing all DS1's that are to be disconnected as well. 2/19- informed John this was submitted by Sue and disconnect complete
2015-01-27 | ShaRita | UCA17-05-IJ | 2300 Main St, Irvine, CA 92614 | 100M, John will throttle down to 60M MD5 UHGVERbgpbqZyofa, Optical, MMF LC | O-1191322 Quote ID: 190785674 Order Request 190785991 Service Order 190794442 20797050 acccess 20797049 port | 190794442 |  | 5563868 | 25M | C1016294 port E4003423 access |  | 2015-02-04 |  |  | BPDD (standard 3/11/2015 |  |  | UnitedHealthGroup-64877 | 763/694-7370, masroor_khan@optum.com |  | 1/28- Submitted to ShaRita 1/29- ShaRita is working on order 2/5- order submitted and approved by provisioning. Awaiting LEC to provide FOC date 2/12- per John cancel order. Order supp'ed to cancel, pending cancellation completion 2/18- order cancelled
2015-01-13 | ShaRita | none | 13621 NW 12th Street SUNRISE FL USA 33323 |  | NSPE0008932392 OQBK3LFJ |  |  |  |  | BCBJ4L0P0001 |  |  |  |  | 1/15/2015 (standard 30 business days) | 2015-02-12 | 2015-02-17 |  |  |  | 1/13- submitted to Sadisconnects 1/20- pending disconnect due date 2/12 1/28- pending disconnect due date 2/12 2/5- pending disconnect due date 2/12 2/12- sent follow up email to provisioning requesting to move forward with soft disconnect 2/18- disconnect complete
2014-03-24 | ShaRita | UOH01-05-IJ | 9200 Worthington Road, Westerville OH 43082 | 100mg ehernet with dport john will throttle down to 50mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd extend to Floor 1 MDF | SFDC Opportunity ID O-0976284 Quote ID: 190207216 Order Request [ 190212895 ] Service Order(s) [ 190213778 20244535 access 20244534 port | 190213778 |  | 5461730 | 5008 | E4000648 C1003789 | 94/KQGN/201133//OB DEMARC LOC: 1ST FLOOR TELCO ROOM TO PORT 4 DEMARC LOC Continued: ON THE EXTENSION SHELF | 2014-04-02 | 2014-04-30 | 2014-05-06 | bpdd | 2014-05-07 | 2014-10-09 | UnitedHealthGroup-64619 | Don Osborn | Activation scheduled for 11/11 at 9pm CST. Conference Bridge: 866-878-8630 Conference Pass Code: 6653710 | 5/28- pending demarc extension due next week 6/5- advised John LEC won't extend on Type 4 ciruits 6/10- John requested to change handoff on this from RJ45 to SMF/LC for dmarc extenstion. 6/18- informed John that for type 4 orders customer is responsible for Media Converter, customer should complete that first. If demark extension is needed customer should complete that first. 6/25- pending demarc extension 7/2- pending demarc extension; Matt is working with Don for resolution 7/7- Don asked if we could place the IDF. . We cannot go the IDF route, if we tried we’d end up doing as much work as re-ordering the service, and we still may find its not feasible. there are two options the customer has. Cancel and re-order with optical or purchase and install media converters. 7/16- per Don, no estimated date media converter will be in place 7/24- pending media converters to be put in place 7/31- Pending media converters 8/6- awaiting John to advise what different route will be taken 8/14- Per Don, he put in the request to have 2” conduit installed with pull strings as requested by AT&T. Work should be completed prior to 8/27. 8/20- Pull string should be ready 8/27 8/27- Pull string work was pushed out to next week. 9/3- pending pull string work, Per John work should be completed Monday 9/8 9/10- conduit/pull string work complete. pending AT&T to move the jumpers 9/17- Pending scheduling of beas installation 9/25- beas installation scheduled for Sept 26th 10/2- Tech is unable to locate the part that was signed out by another tech (he no longer works with Verizon) Current techician is currently working to locate missing parts. Once tech has parts, we can redispatch for BEAS installation. THis is already escalated. 10/9- Beas installation complete. Escalated to provisioning to close order asap. 10/15- Ready for activation customer notified. An ETMS ticket 2014101509303 for a filed tech dispatch at the customer prem to swing the Beas connection from port 1 to port 2. 10/23- Verizon’s, ETMS ticket, has been referred back and cancelled. Issue has been clarified. We talked to an ATT tech and was told that there was a mistake on circuit tagging. Port 1 is correct and no need to swing the cables. We opened a ticket OE010932 with AT&T to send someone out and have it corrected. As per the tech, dispatch will happen first thing tomorrow.
2014-12-12 | ShaRita | none | 5908 HAMPTON OAKS PKWY, TAMPA, FL 33610 | 500MB VPN/VRF for UnitedHealthGroup 300MB VPN/VRF for Connextions | O-0976284 Quote ID: 190678210 IN Service Order(s) [ 190695564 ] has been created for Order Request 190689781 Out Service Order(s) [ 190700621 ] has been created for Order Request 190695785 in 20710317 access in 20710316 port out 20709759 access out 20709758 port | 190695564 in 190700621 out |  |  | 5552638 UnitedHealthGroup 5552639 Connextions | C0028306 port E5000816 access | 69/KFGS/700811//GTES VZB DMARC: Demarc 1st floor telco cage rack 9207 sh6 port 0.1. | 1/8/2015 2/4/2015 | 1/20/2015 2/5/2015 | 1/20/2015 | 2015-01-23 | 1/27/2015 2/18/2015 | 2015-02-10 |  |  | rescheduled 3/2 at 6pm CST bridge 866-692-3158 passcode 9236734 | 12/18- ShaRita is working on order 1/8- capacity issue resolved. ASR submitted, pending FOC date. 1/15- ASR issue cleared, awaiting LEC to provide FOC date 1/21- circuit delivered,BEAS Box installation scheduled tomorrow (01/23/2015). 1/29- due to access issues, beas installation rescheduled for 1/29 2/5- Tech is going to replace the existing SMF cabling with MMF cabling which should correct most of the problem. They also have an SMF SFP that can be placed in the Overture to provide the SMF hand off to the customer. We are looking to have the fiber replaced by Friday COB and turn the order over to the customer by next Wednesday. 2/11- ready for activation, customer notified
2014-10-27 | ShaRita | UCO10-05-IJ | 6465 South Greenwood Plaza, Suite 300, Centennial, CO 80111 | 20mg Ethernet acces and speed, Optical MMF LC connector 3rd Floor MDF room 20 Mb Type 4 Premium Ethernet Access MRC - $803 (provided by CenturyLink) MD5 UHGVERbgpbqZyofa | Opp id O-1130627 Quote ID: 190575539 Service Order(s) [ 190587047 ] has been created for Order Request 190576193 20602302 access 20602301 port |  |  | 5538842 | 5M | C1012254 E3005422 | 24/KXGS/120102//ACSO DMARC Info: 3rd floor serverroom rack 5 of 6 in RU 44 - behind fiber extension panel, all is labeled | 2014-11-05 | 2014-11-19 | 2014-11-17 | bpdd | 11/26/2014 1/22/2015 | 2015-01-15 | Unitedhealthgroup-64736 | 91 91600 84400 harish_kandpal@optum.com | 2/19/15 at 830pm CST bridge 866-692-3158 passcode 9236734 | 10/28- Sent to ShaRita 10/30- working on order submission 11/6- pending FOC date 11/13- FOC date 11/19 11/20- circuit delivered, pending customer's demarc extension 11/26- pending customer's demarc extension 12/4- pending customer's demarc extension 12/11- Circuit will be extended by end of day 12/15. requested to schedule beas install for as soon as possible after the 12/15 date 12/17- pending confirmation from Harish that demarc has been extended 1/8- pending demarc extension, per Harish Unfortunately the circuits are extended to a wrong place and we are working to get them moved out to the appropriate place. Will update you once we have them near to the CPE. 1/14- beas installation scheduled for 1/15 at 3pm 1/16- ready for activation, customer notified
2014-11-04 | ShaRita | n/a | remove the ring Node from SCID NFC32G located at Connextions 4201 Shader Dr Orlando FL 32808 | remove ring node | s/o 5584573 orl - C15126 CCR #: 1235983 | 8106544 |  |  |  | W0R81453 | r2-kzmd-awn-0001 |  |  |  | bpdd | 2015-01-19 | 2014-01-12 |  |  |  | 12/4- Per Bellsouth - We had to do the SI for design and wait for those responses (normal 10 business day interval), then do the firm SI and allow network to start on it and assign a network project manager. In general, the process involves creating and working orders to re-establish and test the SMARTRing without the node that is being removed. Once all of that is completed, then our vendor is engaged to do the equipment removal. It is normally a considerably longer process than the time since I received your request through the end of December. When the network project manager is assigned, I will talk with him or her about your customer’s timeframes. They may be able to talk with and/or visit your customer to understand the issues, timing, any options available for accessing the space for equipment removal even if your customer has vacated, etc. We should know who the network project manager will be within the next couple of days. Things are actually moving a little ahead of normal timeframes. 12/11- pending Bellsouth to complete work 12/17- A pm from Bell South has been established for this. After they review and do a site survey, dates will be established. 1/8- equipment has been removed. order no longer billing on our side. Bell south still has to do the p;ermenant splice. The network project manager received a date of 2/15 for the splicing job this morning and is trying to get that improved. One other factor, though, is that project manager and Carrie shared is that they are still receiving and processing disconnects for other service at that location. The splicing will most likely not take place until all remaining service has been disconnected. The network project manager expects to have an updated date for the splicing by next week and I will make sure you get the info. 1/14- order closed 1/21- ATT has confirmed that they plan to do the permanent splice on 1/30. They were able to pull this in from a targeted date of 2/15. 2/5- splice completed
2015-02-06 | ShaRita | none | 2720 North Tenaya LAS VEGAS NV USA 89128 |  | NSPE0009002431 67067517 OQBK4NN2 |  |  |  |  | U164018 U164019 MGBH4JBR0001-0002 |  |  |  |  | 2/6/2015 (standard 30 business days) | 3/5/2015 3/9/2015 | 2015-03-11 |  |  |  | 2/6- submitted to VZB Full Disco Option 4 2/12- John confirmed to disconnect the entire bundle, pending order information and due date 2/19- provided documentation to disconnect team showing relationship between UHG and Optum. Awaiting confirmation that they will proceed with request. 2/26- pending disconnect due date of 3/5 3/11-disconnect complete
2015-02-10 | ShaRita | none | 48 Monroe Turnpike TRUMBULL CT USA 0661 |  | NSPE0009010077 OQBK39XG |  |  |  |  | BCBKBV0D0001 |  |  |  |  | 2/11/2015 (standard 30 business days) | 2015-03-09 | 2015-03-03 |  |  |  | 2/10- submitted to Sadisconnects 2/12- pending order information/disconnect due date 2/19- pending disconnect due date 3/9 2/26- pending disconnect due date of 3/9 3/5- pending disconnect due date of 3/9 3/10- disconnect complete
2015-02-06 | ShaRita | none | 3817 NW Expressway / Suite 720 OKLAHOM A CITY OK USA 73112-1469 |  | NSPE0009002086 OQBK34YV |  |  |  |  | BCBKWMT60001-2 |  |  |  |  | 2/6/2015 (standard 30 business days) | 2015-03-05 | 2015-03-09 |  |  |  | 2/6- submitted to Sadisconnects 2/12- pending disconnect due date of 3/5 2/19- pending disconnect due date of 3/5 2/26-pending disconnect due date of 3/5 3/5- soft disconnect complete, pending disconnect completion 3/11- disconnect complete
2015-02-06 | ShaRita | none | 2617 W. Torch Lake THE VILLAGES FL USA 32162 |  | NSPE0009002323 OQBK34W0 |  |  |  |  | BCBK3N3J0001-2 |  |  |  |  | 2/6/2015 (standard 30 business days) | 2015-03-04 | 2015-03-06 |  |  |  | 2/6- submitted to Sadisconnects 2/12- pending disconnect due date of 3/4 2/19- pending disconnect due date of 3/4 2/26-pending disconnect due date of 3/4 3/5- soft disconnect complete, pending disconnect completion 3//6- disconnect complete
2015-02-06 | ShaRita | none | 701 Pennsylvani a Avenue / 5th Floor WASHINGT ON DC USA 20004 |  | NSPE0009002396 OQBK343V |  |  |  |  | BCBJ2PBX0001 |  |  |  |  | 2/6/2015 (standard 30 business days) | 2015-03-03 | 2015-03-06 |  |  |  | 2/6- submitted to Sadisconnects 2/12- pending disconnect due date of 3/3 2/19- pending disconnect due date of 3/3 2/26- pending disconnect due date of 3/3 3/5- soft disconnect complete, pending disconnect completion 3/6- disconnect complete
2014-09-25 | ShaRita | MN051-08-IJ | 13625 Technology Dr., Eden Prairie, MN 55344 | 10M, John will throttle down to 5M MD5 UHGVERbgpbqZyofa MMF LC handoff to be installed in the new APOP, terminal name is 13625 Technology Dr Lab. MMF LC | O-1109308 Quote ID: 190500127 Order Request 190501723 Service Order(s) [ 190535113 ] has been created for Order Request 190501723 20553639 access 20553638 port O-1149544 New Quote Quote ID: 190633517 New Order Request 190633943 New Service Order 190637099 20635702 access 20635701 port |  |  | 5529840 5544989 | 1536 | C0011117 E3004884 C0022190 E3005817 | 15/KXGS/047674//ACSO DMARC: first floor data center, customer cabinet AE121, RU 41, labeled with order number and LEC ckt ID | 10/10/2014 11/24/14 1/21/2015 | 12/18/2014 3/9/2015 | 2015-02-17 | bpdd | 12/26/2014 3/16/2015 | 2015-03-06 | unitedhealthgroup-65214 | 952-906-1396 eric_sandberg@optum.com | activation scheduled for 3/17 at 3pm CST. Bridge 866-692-3158 pass code 9236734 | 10/15- order approved by provisioning. ASR submitted, pending FOC date. 10/23- FOC Dec 18th, ShaRita getting information on build 10/29- FOC date 12/18; The FOC date is COMCAST's standard 45 day interval. No build associated. 11/6- FOC date 12/18 11/13- FOC date 12/18 11/20- FOC date 12/18 11/26- order cancelled and reissued to select Qwest as LEC. Pending FOC date 12/4- pending FOC 12/11- pending FOC. per LEC PM, just handed over to them in Project Management they are verifying the LCON and the site survey will be conducted 12/17- site survey completed, LEC PM will reach out to the end user and put together the site requirements needed to provision service. 12/25- Order is pending FOC date. Site survey is already completed. 1/8- Per LEC PM, there are some issues with the order and she has been working with the local contact. Right now there has been no decision as to where the equipment will be placed." 1/14- order on hold, asked John if there has been a a decision made on where the equipment will go 1/21- per John, It will be racked in the lab. The circuits need to be in delivered in the APOP. order supp'ed, pending new FOC date 1/28- FOC date 3/9 2/5- FOC date 3/9 2/12- FOC date 3/9 2/19- Circuit delivered. Awaiting dispatch to provide date of beas installation 2/25- Still awaiting dispatch to schedule beas installation 3/5- beas installation scheduled for 3/6 3/6- ready for activation customer notified
2015-01-27 | ShaRita | WA004-05-IJ | 1633 Westlake Ave North, Seattle, WA 98109 | 3072, 2xT1 MD5 UHGVERbgpbqZyofa, | O-1191054 Order Request 190786034 Quote 190785793 Service Order 190794451 20797094 access 20797093 port | 190794451 |  | 5563871 | 1536 | C1016345 port N1013758, N1013759 access | 74/HCGS/520135//PN lower level telco rm, mt 1, slot 1 of 8 rj48c,tagged & not extended 74/HCGS/520136//PN lower level telco rm, mt 1, slot 2 of 8 rj48c,tagged & not extended | 2/9/2015 2/24/15 | 2015-03-02 | 2015-03-02 | BPDD | 2015-03-06 | 2015-03-03 | UnitedHealthGroup-65046 | 763/694-7370, masroor_khan@optum.com | activation scheduled for 3/18 at 7pm CST. Bridge 866-692-3158 pass code 9236734 | 1/28- Submitted to ShaRita 1/29- ShaRita is working on order 2/5- order submitted and approved by provisioning. Awaiting ASR submission due to internal issue. Ticket has been opened to resolve issue 2/12- ASR submitted, pending FOC date 2/19- provisioning is working with the LEC to find facilities for the order and we have been working with access engineering to give us a new path for this. 2/26- ASR had been sent with DD of 3/2 3/5-ready for activation, customer notified
2015-01-13 | b-end | none | 3 Sheldon Square / Paddington LONDON UK UNITED KINGDOM W2 6PX |  | NSPE0008932448 INQ2015020417214 s/o 5631289 |  |  |  |  | w1a28021 |  |  |  |  | 1/15/2015 (standard 60 days) | 2015-03-13 | 2015-03-13 |  |  |  | 1/13- order submitted to B-end to disconnect 1/22- escalating with EMEA 2/5- EMEA is now processing the disco 2/6- target effective date of 13 MARCH 2015 3/13- disconnect complted.
2015-02-06 | ShaRita | none | 2720 North Tenaya LAS VEGAS NV USA 89128 |  | NSPE0009002420 67067517 OQBK4NNW OQBK4NN0 |  |  |  |  | U111535 U111536 MGBG7TG20001 U111537 MGBG7LTD0001 |  |  |  |  | 2/6/2015 (standard 30 business days) | 3/5/2015 3/9/2015 | 2015-03-11 |  |  |  | 2/6- submitted to VZB Full Disco Option 4 2/12- John confirmed to disconnect the entire bundle, pending order information and due date 2/19- provided documentation to disconnect team showing relationship between UHG and Optum. Awaiting confirmation that they will proceed with request. 2/26- pending disconnect due date of 3/5 3/11- soft disconnect complete, pending disconnect completion 3/12- disconnect complete
2015-02-10 | ShaRita | none | 48 Monroe Turnpike TRUMBULL CT USA 0661 |  | NSPE0009010077 OQBK39XF |  |  |  |  | BCBKCP3V0001 |  |  |  |  | 2/11/2015 (standard 30 business days) | 2015-03-09 | 2015-03-11 |  |  |  | 2/10- submitted to Sadisconnects 2/12- pending order information/disconnect due date 2/19- pending disconnect due date 3/9 2/26- pending disconnect due date of 3/9 3/5- pending disconnect due date of 3/9 3/11- soft disconnect, pending disconnect completion 3/12- disconnect complete
2014-05-27 | ShaRita | FL750-06-IJ | Connextions- 9310 Florida Palm Drive, Tampa FL 33619 | 200M Ethernet RJ54 handoff no md5 Terminate to 1st floor Data Room | SFDC# O-1027815 Quote ID: 190296794 Order Request 190299748 Service Order 190299764 20325025 access 20325024 port SR# 028TNY | 190299764 |  | 5486496 | 90M | C1005401 E5000197 |  |  |  |  | bpdd |  |  | Connextions- 65231 | 407-926-2400 x10390 jose.hanachi@connextions.com |  | 10/8- Had a meeting on October 7th with CL executives and we believe we may be able to come to an agreement but are working on locations. More to come 10/15- Still working on agreement 10/23- Still working on agreement 10/29- Still working on agreement 11/6- Still working on agreement 11/13- still negotiating but expect a draft hopefully early next week. We are at least moving forward. Once agreement is in place build will take about 3 months. 11/20- pending agreement and possibly will not have a completed document before January 1st. Possible but no one moves fast around the holidays…unfortunately. CTLs next internal review is after Thanksgiving. 11/26- pending agreement and possibly will not have a completed document before January 1st. Possible but no one moves fast around the holidays…unfortunately. CTLs next internal review is after Thanksgiving. 12/4- Still working on agreement 12/11- Still working on agreement 12/17- Still working on agreement 1/8- Still working on agreement 1/14- Still working on agreement 1/21- Still working on agreement 1/22- order will be parked and re-initiated once agreement is reached. 3/6- per John waiting confirmation to cancel 3/18- cancel complete
2014-12-10 | ShaRita | replacement for NV750-03-IJ | 7135 S. Decatur Blvd., Las Vegas, NV 89118 | 100mg Ethernet with 1000 Base-LX, Single mode Fiber MD5 UHGVERbgpbqZyofa deliver to MDF on 1st Floor | O-1164012 Service Order(s) [ 190701143 ] has been created for Order Request 190694120 20711294 access 20711293 port lsv I2411 | 190260625 |  | 5552665 | 10000 | C1015367 E4003039 |  |  |  |  | bpdd | 2015-01-05 | 2014-12-31 | UnitedHealthGroup-65267 | 702-242-7654 tauoa.falo@optum.com | activation rescheduled for 3/19 at 5pm CST Bridge: 888-6568232 PC 9158384 | 12/23- order submitted and approved by provisioning. 1/8- ready for activation, customer notified
2014-10-02 | ShaRita | C1273-05-IJ | 150 Mile Crossing Blvd Suite 2, Rochester, NY 14624 | 10M 1000 Base-SX Optical MMF LC connector 10 Mb ) md5 UHGVEReccgas4Usp9 | O-1115295 Quote ID: 190518486 order reqeust id 190535279 Service Order(s) [ 190546106 ] has been created for Order Request 190535279 20560840 access pending cancellation 20560839 port pending cancellation New Order Request 190861544 has been generated for the Quote 190809404 for the Ds3, insitiated 2/25 Service Order(s) [ 190863448 ] 20857679 access 20857678 port | 190546106 |  | 5531353 5572637 | 1536 | C0011297 E3004949 | 22/KFFN/105577/TWCS 1st floor, main colo, Xerox Data Closet, customer Cabinet B10, loose MM Fiber LC connectors, tagged with circuit ID | 2014-10-15 | 2014-11-17 | 2014-11-19 | bpdd | 2014-11-24 |  | uhg-ECC 65479 | 763-744-2082 eric_taylor@optum.com |  | 10/9- John confirmed we can use TWM, pending credit approval. 10/15- order approved by provisioning. ASR submitted, pending FOC date. 10/23- Pending FOC 10/29- FOC date 11/17 11/6- FOC date 11/17 11/13- FOC date 11/17 11/20- circuit delivered, pending testing with Timewarner 11/26- pending demarc confirmation from John, if demarc will be extended or not 12/4- order on hold. pending confirmation if demarc extension is needed 12/11- order on hold. pending confirmation if demarc extension is needed 12/19- sent email informing Jamie/John that this is Type 4 access. Per our agreement with the carrier they will only install at the main point of entrance (MPOE). We were unable to ask them to extend it. 1/8- FOC date for extension 1/15 1/15- demarc moved completed, awaiting beas installation to be scheduled 1/21- Level 3 is requiring a collocation agreement for us (Verizon) to place our BEAS. 1/28- order currently on hold, Informed customer needs to work with XEROX to allow a Verizon tech into their collo to install beas equipment 2/5- order currently on hold,customer is still working with Xerox on allowing Verizon to install beas equipment. Per John, UHG is working on setting up another conference call. 2/12- order currently on hold,customer is still working with Xerox on allowing Verizon to install beas equipment. 2/19- awaiting confirmation from UHG if order will be cancelled and DS3 ordered 2/26-per John, they will need to go with DS3. 3/5- pending ASR submission, escalated to provisioning management (per John, site is closing but pending confirmation to cancel, requested provisioning to hold off on sending ASR) 3/11- per John cancel both ethernet and DS3. Orders supp'ed to cancel, pending cancellation completion 3/19- DS3 order cancel complete. Pending Cancellation of the Ethernet order 3/26- both DS3 and Ethernet order cancel complete.
2014-12-15 | ShaRita | UCO31-05-IJ | 12500 Arapahoe Road, Suite C , Centennial, CO 80112 | 200M, will throtlle down to 100M Optical MMF with LC Connector MD5 UHGVERbgpbqZyofa, terminate to Building demarc | O-1163946 Quote 190678902 Service Order(s) [ 190706187 ] has been created for Order Request 190686246. 20723979 access 20723978 port | 190706187 |  | 5554333 | 80k | C5000722 E5000834 | BCWV1050 DEMARC:1st floor telephone roomextended by customer to c54.1.8 in rack ru 3.labelled | 2015-01-16 | 2015-02-20 | 2015-02-23 | 2015-02-27 | 2015-03-27 | 2015-03-26 | unitedhealthgroup-64894 | 763-744-1556 john_l_rothstein@optum.com | 3/27 at 530am CST Bridge: 866-692-3158 Passcode: 9236734 | 12/18- ShaRita working on order, pending lcon verification 1/8- escalated to provisioning order has been ops approved, pending ASR submission 1/15-issue with engineering codes of the ASR, ticket opened to resolve. Once resolved, ASR will be submitted. escalated to provisioning for assitance to have issue resolved asap. 1/22- FOC date 2/20 1/28- FOC date 2/20 2/5- FOC date 2/20 2/12- FOC date 2/20 2/19- FOC date 2/20 2/26- circuit delivered; John confirmed demarc will have to be extended 3/5- pending customer's demarc extension 3/11- per John, Extension completed yesterday. Pending scheduling of beas installation. 3/19- beas installation scheduled for 3/23 3/26- LCON EDWARD JONES CONFIRMED ACCESS FOR THURSDAY 3/26 3/27- ready for activation, customer notified 3/27- activation complete and circuit accepted
2015-03-04 | ShaRita | none | 901 5th Avenue / Suite 1500 SEATTL E WA USA 98164 |  | NSPE0009072670 OQBK4RWJ |  |  |  |  | BCBKWB1V0001-2 |  |  |  |  | 3/5/15 (standard 30 business days) | 2015-04-02 |  |  |  |  | 3/4- submitted to Sadisconnects 3/11-pending disconnect due date 4/2 3/19- pending disconnect due date 4/2 3/26- pending disconnect due date 4/2 4/1- awaiting provisioning to perform soft disconnect 4/3- soft disconnect complete
2015-03-04 | ShaRita | none | 9200 Worthing ton Road COLUM BUS/WE STERVIL LE OH USA 43082- 8823 |  | NSPE0009072881 OQBK4SH5 |  |  |  |  | BCBJDXYJ0001 |  |  |  |  | 3/5/15 (standard 30 business days) | 2015-04-02 |  |  |  |  | 3/4- submitted to Sadisconnects 3/11- pending disconnect due date 4/2 3/19- pending disconnect due date 4/2 3/26- pending disconnect due date 4/2 4/1- awaiting provisioning to perform soft disconnect 4/3- soft disconnect complete
2015-04-16 | BCC- Core | C1543-03-DJ | 5150 Regent Blvd Irving, TX | disconnect | NSPE0009195006 |  |  |  |  | 972-929-7202 | [10 empty] | 4/16- john sent order to center 4/17- 972-929-7202 was disconnected on 12-30-14 on order # O9143649.
2015-04-01 | ShaRita | C1572-03-IJ | 21 Gregory Dr. Ste 165 South Burlington VT need by june 1 | 100M John will throttle down to 20M, Optical, LC SMF, MD5 UHGVEReccgas4Usp9 | O-1251336 Quote ID: 191009681 Order Request 191009843 Service Order(s) [ 191034918 ] has been created for Order Request 191009843 | 191034918 | [8 empty] | BPDD (standard 5/12/15) |  |  | UHGECC -65437 | 952-974-5838 hau.phan@optum.com |  | 4/1- Order submitted to ShaRita 4/9- pending lcon verification before proceeding with order submission 4/10- per John request, order was cancelled
2015-02-17 | ShaRita | NY707-01-IJ | 210 Westchester Ave, WEST HARRISON , NY 10604 | 1G, John will throttle down to 300M SMF LC MD5 UHGVERbgpbqZyofa. | O-1208626 Quote ID: 190840293 Service Order(s) [ 190849171 ] has been created for Order Request 190840779 20840980 access 20840979 port | 190849171 |  | 5570549 | 1536 | C0039857 E5001018 | 32.KFGS.203885..NY | 2015-02-23 | 2015-04-17 |  | bpdd (standard 3/31/2015) | 2015-04-24 |  | unitedhealthgroup- 65141 | 952-512-8650 mark_dasovic@optum.com |  | 2/19- ShaRita is working on order 2/26- site survey completed, pending site readiness. Asked provisioning to forward EUCR form. 3/5- pending site readiness, customer ready date 3/15. FOC date 4/17 3/11- FOC date 4/17 3/19- asked John to confirm with lcon that site requirements are complete, FOC date 4/17 3/26- pending confirmation from John if site is ready , FOC date 4/17 4/1- John advised that site requirements are not complete. Pending site readiness. 4/9- the conduit is blocked between the building management property and the building management manhole. Since it is on their property they are responsible to unblock it. 4/10- per John request, order supp'ed to cancel 4/14- order complete cancelled
2015-02-24 | ShaRita | NV018-05-IJ | 2720 N Tenya Way, Las Vegas, NV 89128 | 100M Ethernet Electrical RJ45, copper MD5 UHGVERbgpbqZyofa, | O-1216625 Quote ID: 190857940 Order Request 190858125 Service Order(s) [ 190864976 20859542 access 20859541 port | 190864976 |  | 5572783 | 20M | C1018081 E4003707 | 33.KFGX.000894..COXC. 6th floor communications rack 6 | 2015-03-02 | 2015-03-27 | 2015-03-27 | bpdd (standard 4/9) | 2015-04-03 | 2015-04-03 | unitedhealthgroup- 64591 | 702-242-7654 tauoa.falo@optum.com | 4/16 at 7pm CST Bridge: 866-692-3158 Passcode: 9236734 | 2/19- ShaRita is working on order 2/26- received order 2/25, will process order once OVC is completed w/ customer and lcon 3/5- pending FOC date 3/11- FOC date 3/27 3/19- FOC date 3/27 3/26- FOC date today, 3/27 4/1- beas installation scheduled for 4/3 4/6- ready for activation, customer notified
2015-03-24 | ShaRita | MI041-05-IJ | 822 Centennial Way, Lansing, MI 48917 | 4608, 3xT1 MD5 UHGVERbgpbqZyofa | O-1245015 Quote ID: 190976402 Order Request 190976839 Service Order 190985859 20933345 access 20933344 port | 190985859 |  | 5582203 | 1.5Mb | C0045522 N1017985,N1017986, N1017984 | /HCGS/594774//MB (N1017984) DEMARC LOC: MAIN TELCO/SERVER CLOSET SHF 3 SLOT 1 DEMARC LOC Continued: 3 SLOT 1/4. /HCGS/594775//MB (N1017985) DEMARC LOC: MAIN TELCO/SERVER CLOSET SHF 3 SLOT 2 DEMARC LOC Continued: 3 SLOT 2/4. /HCGS/594776//MB ( N1017986) DEMARC LOC: MAIN TERM/SERVER CLOSET SHF 3 SLOT 3/4 DEMARC LOC Continued: SLOT 3/4. Jack Type: RJ48C | 2015-03-27 | 2015-04-08 | 2015-04-06 | BPDD (standard 04/16/2015) | 2015-04-13 | 2015-04-08 | unitedhealthgroup-65258 | 763-744-1589 david_casanova@optum.com | 4/17 at 6am CST Bridge: 866-692-3158 Passcode: 9236734 | 3/26- ShaRita is working on order. 4/1- FOC date 4/8 4/9- ready for activation, customer notified
2015-03-18 | ShaRita | none | 9050 Centerpo inte Center Drive / Suite 400 WEST CHESTE R OH USA 45069 |  | NSPE0009106842 OQBK41TB |  |  |  |  | BCBKW4RX0001-8 |  |  |  |  | 3/18/2015 (standard 30 business days) | 2015-04-16 | 2015-04-20 |  |  |  | 3/19- pending disconnect due date of 4/16 3/26-pending disconnect due date of 4/16 4/1-pending disconnect due date of 4/16 4/9-pending disconnect due date of 4/16 4/16- awaiting provisioning to perform soft disconnect 4/23- disconnect complete
2015-03-18 | ShaRita | none | 7525 SE 24th / Suite 200 MERCE R ISLAND WA USA 98040 |  | NSPE0009106473 OQBK41GT |  |  |  |  | BCBKGWXD0001 -4 |  |  |  |  | 3/18/2015 (standard 30 business days) | 2015-04-16 | 2015-04-20 |  |  |  | 3/19- pending disconnect due date of 4/16 3/26-pending disconnect due date of 4/16 4/1-pending disconnect due date of 4/16 4/9-pending disconnect due date of 4/16 4/16- awaiting provisioning to perform soft disconnect 4/23- disconnect complete
| ShaRita | MN051-19-IJ | 13625 technology drive, Eden prairie, MN 55344 terminate to new APOP | 10M, John will throttle down to 2M handoff Copper RJ45 | O-1189192 Quote ID: 190785443 service order 190791322 20797686 access 20797685 port | 190791322 |  | 5563920 | 1M | C0029615 port E3007225 access | 15/KXGS/047882//ACSO Demarc: Tech installed the Overture in the customers Lower level (OTL) which is the Optom Training Lab. In RRAE121 U39 of u45, Overture 1400 10/100 port #1, tagged with circuit IDs and order information and shown to LCON Dan Todd 763/744-1663, cell 651/336-5681. | 2015-02-03 | 2015-03-20 | 2015-03-25 | BPDD (standard 3/11/2015 | 2015-03-27 | 2015-03-27 | UnitedhealthGroup-Lab-64954 | 214-929-7326 peter_chisholm@optum.com | activation rescheduled for 4/29 at 830pm CST Bridge: 866-878-8630 Passcode: 6653710 | 1/28- Submitted to ShaRita 1/29- ShaRita is working on order 2/5- order submitted and approved by provisioning. awaiting LEC to provide FOC date 2/12- awaiting LEC to provide FOC. Per LEC PROJECT IS GOING THROUGH THE SITE VISIT PROCESS. YOU SHOULD EXP 2/19- awaiting LEC to provide FOC date 2/26- awaiting LEC to provide FOC date. provisioning requested update from LEC PM, pending feedback. asked Sharita to supp to request termination to MPOE. 3/5- awaiting the site survey results. will not receive your FOC until the site requirements have been met if any. 3/11- FOC date 3/20 3/19- FOC date 3/20, awaiting completion notification from LEC 3/26- circuit delivered, pending beas installation 3/27- ready for activation, customer notified
2015-01-23 | ShaRita | MN051-18-IJ | 13625 technology drive, Eden prairie, MN 55344 terminate to new APOP | 10M, John will throttle down to 2M handoff Copper RJ45 | O-1189192 Quote ID: 190785443 order request 190785788 service order 190791343 20797519 access 20797518 port | 190791343 |  | 5563917 | 1M | C0029614 port E3007224 access | LEC CKT ID: 15/KXGS/047877//ACSO DMARC: lower level computer room, cabinet AE121, labeled | 2015-02-03 | 2015-03-19 | 2015-03-20 | BPDD (standard 3/11/2015 | 2015-03-26 | 2015-03-25 | UnitedhealthGroup-Lab-64954 | 214-929-7326 peter_chisholm@optum.com | activation rescheduled for 4/29 at 930pm CST Bridge: 866-878-8630 Passcode: 6653710 | 1/28- Submitted to ShaRita 1/29- ShaRita is working on order 2/5- order submitted and approved by provisioning. awaiting LEC to provide FOC date 2/12- awaiting LEC to provide FOC. Per LEC PROJECT IS GOING THROUGH THE SITE VISIT PROCESS. YOU SHOULD EXPECT TO HAVE AN UPDATE WITHIN 10 BUSINESS DAYS. ONCE THE SITE VISIT IS COMPLETED YOU WILL BE NOTIFIED OF YOUR PROJECT MANAGER'S NAME AND CONTACT # 2/19- awaiting LEC to provide FOC date 2/26- order on hold, Pending Site Survey ¦¦ Received an update from the LEC PM that this project is on hold at the moment. When scheduling the site survey with the LCON, Steve Brown, they advised that this was on hold on their end pending fiber confirmation in the building., asked Sharita to supp to request termination to MPOE. 3/5- awaiting the site survey results. will not receive your FOC until the site requirements have been met if any. 3/11- FOC date 3/19 3/19- FOC date 3/19, awaiting completion notification from LEC 3/20- ready for activation, customer notified
2015-03-05 | ShaRita | FL110-02-IJ | 500 Westshore Blvd., Suite 500, Tampa, FL 33609 | 50M, John will throttle down to 20M Optical MMF, LC UHGVERbgpbqZyofa | Quote: 190890114 Order Request 190900981 Service Order(s) [ 190909770 ] has been created for Order Request 190900981 20909639 access 20909638 port | 190909770 |  | 5579435 | 10M | C4001037 E4003981 | 69/KEGS/703482//GTES VZB DMARC:3RD FLR CUST DATA ROO BACK WEST WALL JUST BELOW CANOGA PERKINS | 2015-03-19 | 2015-04-29 | 2015-04-10 | bpdd | 2015-05-06 | 2015-04-21 | unitedhealthgroup-65286 | 443-853-3646 edward.mclaughlin@optum.com | activation scheduled for 4/29 at 630pm CST Bridge: 866-692-3158 Passcode: 9236734 | 3/11- early site survey scheduled with lcon for Monday, March 16th between 9am and 12pm 3/19- early site survey complete, no site requirements. Allow 21 days for facility build. Pending FOC date 3/26- FOC date 4/29 4/1- FOC date 4/29 4/9- FOC date 4/29 4/16- circuit installed, John confirmed demarc. beas installation scheduled for 4/21 4/21- ready for activation, customer notified
2015-01-27 | ShaRita | WI017-01-IJ | 328 South Front Street, La Crosse, WI | 1G, John will throttle down to 300M MD5 UHGVERbgpbqZyofa, Optical, MMF LC | O-1191548 Quote ID: 190786076 Order Request 190786151 Service Order 190794456 20806899 port 20806900 access | 190794456 |  | 5565372 | 50M | C0029818 E5000963 | CHC00292947 DEMARC: Installed and labeled beas in center bay. 5th floor telco room. | 2015-02-13 | 2015-04-10 | 2015-04-24 | BPDD | 2015-04-17 | 2015-05-01 | UnitedHealthGroup-65168 | 952-512-8650 mark_dasovic@optum.com | activation scheduled for 5/11 at 1pm CST Bridge: 866-692-3158 Passcode: 9236734 | 2/5- ShaRita is working on order, pending order verification with lcon 2/12- order submitted and approved by provisioning. Awaiting ASR submission due to internal issue. Ticket has been opened to resolve issue 2/19- awaiting LEC to provide FOC date 2/26-Received email from Charter (LEC) on 2/25 stating: "This email is to confirm that Charter Communications has approved your Order request. The MRC for this circuit will be $1775.00/mo and the NRC is $500.00 We will respond with Firm Order Commitment date information within 10 business days." 3/5-pending FOC 3/6- Per LEC PM projected completion date for construction of 3/27/2015. FOC date 4/10 3/11- FOC date 4/10 3/19- FOC date 4/10 3/26-FOC date 4/10 4/1- FOC date 4/10 4/9- FOC 4/10 4/16- order still pending circuit delivery. per LEC, fiber splicing is completed and switch installation is scheduled for Friday. 4/23- FOC date 4/24 4/30- circuit delivered, beas installation scheduled for 5/1 at 8am 5/4- ready for activation, customer notified
2015-03-31 | ShaRita | none | 1633 Westlake Ave., North SEATTLE WA USA 98109 |  | NSPE0009148077 OQBK5F5D |  |  |  |  | bcbkvmtf0001 |  |  |  |  | 3/31/2015 (standard 30 business days) | 2015-04-30 |  |  |  |  | 3/31- submitted to Sadisconnects 4/9- pending disconnect due date of 4/30 4/16- pending disconnect due date of 4/30 4/23- pending disconnect due date of 4/30 4/30- soft disconnect complete, pending disconnect completion
2015-03-31 | ShaRita | none | 5775 Peachtree Dunwoody Rd. NE - Suite 600 ATLANTA GA USA 30342 |  | NSPE0009148120 OQBK5GC2 |  |  |  |  | BCBKXC0V0001-2 |  |  |  |  | 3/31/2015 (standard 30 business days) | 2015-04-30 |  |  |  |  | 3/31- submitted to Sadisconnects 4/9- pending disconnect due date of 4/30 4/16- pending disconnect due date of 4/30 4/23- pending disconnect due date of 4/30 4/30- soft disconnect complete, pending disconnect completion
2015-03-31 | ShaRita | none | 6465 South Greenwood Plaza, Suite 300 Centennial CO 80111 |  | NSPE0009148200 OQBK5GDJ |  |  |  |  | BCBKCMC00001-5 |  |  |  |  | 3/31/2015 (standard 30 business days) | 2015-04-30 |  |  |  |  | 3/31- submitted to Sadisconnects 4/9- pending disconnect due date of 4/30 4/16- pending disconnect due date of 4/30 4/23- pending disconnect due date of 4/30 4/30- soft disconnect complete, pending disconnect completion
2014-10-30 | ShaRita | NV080-02-IJ | 9850 Double R Boulevard, Reno, NV 89521 | 100M, will throttle down to 50M 1000 Base-SX MMF LC Connector MD5 UHGVERbgpbqZyofa | O-1133506 Quote ID: 190583633 Order Request 190586387 Service Order(s) [ 190587577 20603055 access 20603054 port | 190587577 |  | 5538903 | 30M | C1012264 E4002550 | 17/KRGN/505413//NV Demarc : 2nd Floor MPOE / Server Room, Ciena 3930 Optical port no. 6 MMF coming off to Jack Panel 1 Port 3 and 4 extended to FLR 1 RM TELCO | 2014-11-06 | 2014-12-09 | 2014-12-09 | bpdd | 12/16/2014 2/7/2015 | 2015-02-11 | Unitedhealthgroup-65204 | 763-744-2077 robert_a_benson@optum.com | activation completed 5/13 Eric Sandberg Customer accepted the circuit | 10/30- pending credit 11/6- pending FOC date 11/13- FOC date 12/9 11/20- FOC date 12/9 11/26- FOC date 12/9 12/4- Construction delayed, splicing delayed - new ECD 12/08. asked LEC when can we expect the loop to be delivered, pending response 12/11- circuit delivered, pending confirmation if demarc extension is needed 12/17- circuit delivered, pending confirmation if demarc extension is needed 1/8-circuit delivered, pending confirmation if demarc extension is needed 1/14- circuit delivered, pending confirmation if demarc extension is needed 1/21- circuit delivered, pending confirmation if demarc extension is needed 1/28- pending confirmation if demarc extension is needed 2/5- pending confirmation if demarc extension is needed 2/12- ready for activation, customer notified
2014-10-09 | B end Varun | PH510-01-IJ | Building O, UP North Science and Techno Park, Commonwealth, Quezon City, Philippines- needs to be ready first week of March. | Please use Globe as last mile provider 100M Ethernet SOO To Melbourne - circuit ID W0X83226 MD5 UHGVERbgpbqZyofa Multimode SX Fiber | SO-5592191 / 5592192 internal change • Port SO : 5672847 • Access SO : 5672848 |  |  |  | 30000 | W1B53388 Port W1B53389 access | PTT is Globe PTT CIRCUIT ID (radio) : IC-AKZ-2909 |  | 2015-03-11 |  | bpdd |  |  |  | Dianne Mariz Concepcion R. Reyes Sr. Voice/Data Network Analyst, Optum Technology Science Hub Tower 1, Campus Ave. cor Turin St. Mckinley Hill Cyberpark, Fort Bonifacio, Taguig City, Philippines, 1634 T +63 02-588-3551 M +63 998-576-5586 drreyes@optum.com |  | 2/26- per Globe: Revised radio plan was submitted to building admin last monday as per plan and got their comment/remarks yesterday. Unfortunately the plan is still subject for revision. On a separate e-mail with building admin and Jaime Lucero I am requesting a joint survey hopefully by today or tomorrow depending on the building admin availability for us to avoid re-mobilization and plan revision. Also, to get their remarks on the same day. Will let you know once i got their confirmation. 3/5- targeted FOC date 3/11 3/12- Local loop delivery via interim solution is now complete. Once customer ckt is up & running via this current PTT solution, are we still on previous arrangement that this service order will be close & internal change order will be submitted to track final set up which is via fiber? Note: fiber solution tentative PTT RFS date- 1st week of May. 3/18- radio solution will be turned up on 3/18, fiber solution should be ready first week of May 3/26- FOC from Globe room to outside plant has been laid already. Waiting for the FOC assignment to be used. We are looking at April 22 handover for the final solution. 4/1- still on track for 4/22 for permenant solution 4/9- pending Globe delivery for 4/22 4/23- Fiber solution insalled and ready for hotcut. 4/30- hotcut should have happened on 4/29. melissa following up to see if completed and what is needed to disconnect the radio solution. 5/1- There is no parallel billing on PTT’s end. I believe it is the same in VZB end since we worked on change (internal order) in tracking the installation of fiber solution. I will now inform Globe to proceed in deactivating their local loop segment via radio.
2015-04-01 | ShaRita | none | 2220 Campbell Creek RICHARDSON TX | disconnect | NSPE0009176333 OQBK5QFT |  |  |  |  | BCBK1WC90001 |  |  |  |  | 4/10/15 (standard 30 business days) | 2015-05-07 | 2015-05-13 |  |  |  | 4/10- submitted to Sadisconnects 4/15- pending disconnect due date of 5/7 4/23- pending disconnect due date of 5/7 4/30- pending disconnect due date of 5/7 5/7- awaiting provisioning to perform soft disconnect 5/13- disconnect complete
2015-03-18 | ShaRita | none | 5908 Hampton Oaks Pkw TAMPA FL USA 33610 | disconnect | NSPE0009106634 Order Number:190985027 Service Order : 190988647 20934323 access 20934322 port | 190988647 |  |  |  | E4000335 access C1001942 port |  |  |  |  | 3/18/2015 (standard 30 business days) | 4/16/2015 5/21/2015 | 2015-05-08 |  |  |  | 3/18- submitted to Sadisconnects 3/26- provided service instance ids to disconnect to progress request. Pending order information and due date. 4/1- order in disapproved status, preventing provisioning to submit ASR. Provisioning working to resolve. 4/9- Order issue is still not resolved on ticket T1466525. Ticket has been escalated 4/15- ASR sent to LEC requesting disconnect with due date of 4/22 4/23- unable to close order, having issue with the disconnect PVC. Ticket created. 4/30- This will still be scheduled for dispatch by RNC, the task is auto-complete. Once the dispatch was completed, your order will also be completed. Dispatch scheduled for 5/4. 5/7- provisioning sent follow up email to dispatch requesting them to complete dispatch request in system. Once the dispatch tech completed the tast,prder will autocomplete 5/8- disconnect complete
2013-11-22 | ShaRita | AZ009-07-IJ | 1 E. Washington, Phoenix, AZ 85040 may change to fiber check what to change to MMF, needs to extend 7 floors | 100M ethernet type 4, RJ45 interface md5 UHGVERbgpbqZyofa | Request id 190064162 order number 190067740 20153398 access cancelled 20153397 port cancelled New quote Quote ID: 190342285 Order Request 190347304 New Service Order 190348132 20366352 access 20366351 port change order to have WAN Interface to the CE (Customer Edge) changed to 1000Base-SX (850nm, Multi-Mode Fiber) Service Order(s) [ 191132842 ] has been created for Order Request 191132676 (CANCELLED) | 190067740 190348132 191132842 |  | 5425293 5496357 | 10800 | E4000173 access C1000764 port C1006381 port E4001337 access | 14/KXGS/123881//ACSO DEMARC: Basement Parking lot Telco rm. Wallmounted Extended to patch panel port 1. CISCO 3750 Fast Ethernet Port 1. 23.KFGX.990102..COXC. VZB DMARC: 7TH FLOOR, MDF ROOM BACK BOARD MOUNTED ON THE WALL TAGGED AND LABELLED WITH CIRCUIT ID HANDOFF TYPE: Fiber | 12/4/2013 6/27/2014 | 1/2/2014 8/4/2014 | 12/27/2013 8/4/2014 | bpdd | 1/13/2014 4/7/2014 8/11/2014 new | 2014-09-10 | unitedhealthgroup- 65140 | 702-242-7654 tauoa.falo@uhc.com | activation rescheduled for 5/21 at 7pm CST Bridge: 866-692-3158 Passcode: 9236734 | If the customer wants fiber from CTL, order needs to be supped to change the interface then a new ASR will be sent to CTL. This will require another standard interval before LEC can deliver the circuit. 6/18- per request from Tauoa handoff order supp'ed to change LEC handoff to MMF 6/25- working with Matt, SA, for request for optical handoff 7/2- new order install submitted for optical handoff; pending FOC date 7/9- FOC date 8/4 7/16- FOC date 8/4 7/24- FOC date 8/4 7/31- FOC date 8/4 8/6- beas installation scheduled for 8/8 8/14- tech scheduled for beas installation today, August 14th. Our technician will be bringing 45/60 feet of fiber patch cord to the customer location. It will take approximately 2 hrs. to run the fiber and connect to the BEAS box. 8/20- Pending tech redisptach. Beas dispatch was complete but will we have to redispatch tech to site to conference in LEC (COX) to change the settings in the box and match it with the settings that COX has. 8/27- tech was redispatached ran multi mode fiber from the lec handoff to the cust fiber patch panel on floor p1 mpoe. he moved the mm sfp to port 6 on the beas. ran a multi mode fiber jumper from the cust 7th fl fiber patch pnl to the beas. Pending MAC test with COXC (re test) 9/3- issue resolved, box is now pingable with stable response. pending end to end testing and closing of order 9/10- circuit ready for activation; customer notified 5/1- change order submitted to have WAN Interface to the CE (Customer Edge) changed to 1000Base-SX (850nm, Multi-Mode Fiber). 5/4- customer requested to cancel the change order to avoid having to deliver new access, instead he will ship site contact LH gbic to the site and will use SM fiber cabling.
2015-02-25 | ShaRita | none | phoenix-az -NEED TO ADD MULTICASTING | Migrate to UnitedHealthcare VPN from Connextions VPN | NSPE0009079961 Order Request # 190895580 20877811 port | 190896339 |  | 5495595 |  | C1006245 |  |  |  |  | 2015-05-08 |  |  | 64940 |  | 5/8 at 730pm CST Bridge: 866-692-3158 Passcode: 9236734 | 3/5- sharita working on order 3/6- requested submitted to provisioning, ready for hotcut customer notified
2015-02-25 | ShaRita | none | charlotte-nc - NEED TO REMOVE VRF | Migrate to UnitedHealthcare VPN from Connextions VPN | Quote 190952164 Service Order(s) [ 190958930 ] has been created for Order Request 190953487 (IN) 20915809 access 20915808 port Service Order(s) [ 190965420 ] has been created for Order Request 190959835 (OUT) 20918961 access 20918960 port 4/21 Order Request 191088720 Quote 191026601 Service Order(s) [ 191089030 21004520 port | 191089030 |  |  |  | C1004764 | [7 empty] | 64922 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@optum.com | hotcut requested for 5/15/2015 at 930PM CST | 3/5- sharita working on order 3/6- advised customer that circuit was ordered with VRF feature and will have to be removed to have VPN Connextions removed before replacing with VPN UnitedHealthGroup. 3/19- change submitted 3/26- pending FOC date 4/1- FOC date 4/13 4/9- awaiting PIP product manager to confirm if removing VRF queuing can be done without installing new access 4/16- received confirmation that MVRF with PVC level queing can be completed as a change. pending cancellation of the in/out 4/21- order submitted to add multicasting, change VPN to UnitedHealthGroup, and change AS to 64922 has been submitted. hotcut scheduled for 5/15 at 930pm CST
2015-02-25 | ShaRita | none | richardson-tx NEED TO ADD MULTICASTING and REMOVE VRF | Migrate to UnitedHealthcare VPN from Connextions VPN | NSPE0009079961 Order Request # 190895580 20877805 port | 190896263 |  | 5477394 |  | C1004787 |  |  |  |  | 2015-03-27 |  |  | 64918 |  | 3/27 at 530pm CST Bridge: 866-692-3158 Passcode: 9236734 | 3/5- sharita working on order 3/6- requested submitted to provisioning, ready for hotcut customer notified 3/27- hotcut completed to change VPN to UnitedHealthGroup, AS to 64918, and enable MD5 password UHGVERbgpbqZyofa 4/1- Melissa now working on order to add multicasting. 4/9- melissa working on order to add multicasting 4/16- received confirmation that MVRF with PVC level queing can be completed as a change 4/23- awaiting change order from Melissa to add multicasting
2015-02-25 | ShaRita | none | irving-tx NEED TO ADD MULTICASTING | Migrate to UnitedHealthcare VPN from Connextions VPN | NSPE0009079961 Order Request # 190895580 20877802 port | 190896264 |  | 5495639 |  | C1006246 |  |  |  |  | 2015-04-10 |  |  | 64920 |  | 4/10 at 530pm CST Bridge: 866-692-3158 Passcode: 9236734 | 3/5- sharita working on order 3/6- requested submitted to provisioning, ready for hotcut customer notified
2015-03-05 | ShaRita | none | centennial-co NEED TO REMOVE VRF | Migrate to UnitedHealthGroup VPN from Connextions VPN MD5 password UHGVERbgpbqZyofa AS 64939 multicasting BFD | NSPE0009267872 Order Request # 191176442 21070438 | 191184983 |  | 5477405 |  | C1004757 |  |  |  |  | 2015-03-27 |  |  | 64939 |  | 5/29 at 630pm CST Bridge: 866-692-3158 Passcode: 9236734 | 5/14- ready for hotcut, customer notified
2015-03-05 | ShaRita | none | orlando-fl_c1004781 NEED TO REMOVE VRF | Migrate to UnitedHealthGroup VPN from Connextions VPN MD5 password UHGVERbgpbqZyofa AS 64932 multicasting BFD | Order Request # Service Order(s) [ 191243841 ] has been created for Order Request 191243500 | 191243841 |  | 5477403 |  | c1004781 |  |  |  |  | 2015-06-05 |  |  | 64932 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | 6/5 at 530pm CST Bridge: 866-692-3158 Passcode: 9236734 | 6/4- ready for hotcut, customer notifed
2015-02-25 | ShaRita | none | jeffersonville-in | Migrate to UnitedHealthcare VPN from Connextions VPN | NSPE0009079961 Order Request # 190895580 20877808 port | 190896340 |  | 5495631 |  | C1006274 |  |  |  |  | 2015-04-17 |  |  | 64917 |  | rescheduled for 4/24 at 1030pm CST Bridge: 866-692-3158 Passcode: 9236734 | 3/5- sharita working on order 3/6- requested submitted to provisioning, ready for hotcut customer notified
2015-03-05 | ShaRita | none | concord-nc | Migrate to UnitedHealthGroup VPN from Connextions VPN MD5 password UHGVERbgpbqZyofa AS 64923 multicasting BFD | NSPE0009267872 Order Request # 191176442 21074035 | 191184982 |  | 5495590 |  | c1006441 |  |  |  |  | 2015-06-19 | 2015-06-26 |  | 64923 |  | 6/19 at 630pm CST Bridge: 866-692-3158 Passcode: 9236734 | 5/21- ready for hotcut, customer notified
2015-03-05 | ShaRita | none | orlando-fl_c1005119 | Migrate to UnitedHealthGroup VPN from Connextions VPN MD5 password UHGVERbgpbqZyofa AS 64933 multicasting BFD | NSPE0009332593 Order Request # 191240872 191241419 21136741 | 191241419 |  | 5481354 |  | c1005119 |  |  |  |  | 2015-07-10 |  |  | 64933 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | 7/10 at 530pm CST Bridge: 866-692-3158 Passcode: 9236734 | 6/4- ready for hotcut, customer notifed
2015-02-03 | ShaRita | FL120-02-IJ | 9045 Strada Stella Ct, Naples, FL 34109 | 7680, 5xT1 | CW Order (ID : 190799802 NSPE0008991778 IQBK32FL | 8231641 | P2102545 | 5566764 | 1536 | BCBK7T0Y0001-0005 | 25.HCGS.265945..UFLG DEMARC LOC: 1ST FLR ELEC RM, SL 6 OF 13, RJ48C, PRIM PROT ONLY, T/L/G, NOT EXT 25.HCGS.265946..UFLG DEMARC LOC: 1ST FLR ELEC RM, SL 7 OF 13, RJ48C, PRIM PROT ONLY, T/L/G, NOT EXT 25.HCGS.265947..UFLG DEMARC LOC: 1ST FLR ELECTRICAL RM, SL 8 OF 13, RJ48C, SOLID STATE PRIM PROT ONLY, T/L/G, NOT EXT 25.HCGS.265948..UFLG DEMARC LOC: 1ST FLR ELECTRICAL RM, SL 9 OF 13, RJ48C, SOLID STATE PRIM PROT ONLY, T/L/G, NOT EXT 25.HCGS.265949..UFLG DEMARC LOC: 1ST FLR ELEC RM, SL 10 OF 13, RJ48C, PRIM PROT ONLY, T/L/G, NOT EXT Jack Type: RJ48C | 2015-02-12 | 2015-02-24 | 2015-02-24 | bpdd | 2015-03-06 | 2015-02-25 | UnitedHealthGroup-65166 | 443-853-3646 edward.mclaughlin@optum.com |  | 2/3- sent to ShaRita 2/5- ShaRita is working on order 2/12- order submitted and approved by provisioning. Awaiting LEC to provide FOC date. 2/19- FOC date 2/24 2/26- ready for activation, customer notified
2015-04-01 | ShaRita | none | 2720 N Tenaya Way Las Vegas, NV 89128 | disconnect | NSPE0009176277 mci20416 |  |  |  |  | mci20416/ K0019443 |  |  |  |  | 4/10/15 (standard 30 business days) | 2015-05-07 | 2015-05-22 |  |  |  | 4/13- submitted to Sadisconnects 4/16- pending order and due date information 4/23- pending disconnect due date of 5/7 4/30- pending disconnect due date of 5/7 5/7- pending disconnect completion, due date 5/7 5/14- disconnect group sent an email to our provisioning team to have this completed. 5/22- disconnect complete
2015-04-16 | ShaRita | none | 2300 Main Street IRVINE CA USA 92614 | disconnect | NSPE0009194159 OQBK5WCL |  |  |  |  | bcbjglrp0001 |  |  |  |  | 4/17/15 (standard 30 business days) | 2015-05-14 | 2015-05-19 |  |  |  | 4/16- submitted to Sadisconnects 4/23- sent follow up email to disconnect group to process order request asap, pending due date and order information 4/23- pending disconnect due date of 5/14 4/30- pending disconnect due date of 5/14 5/7- pending disconnect due date of 5/14 5/14- soft disconnect complete, pending disconnect completion 5/21- disconnect complete
2015-04-16 | ShaRita | none | 5150 Regent Blvd IRVING TX USA 75063 | disconnect | NSPE0009194405 OQBK5TL8 |  |  |  |  | BCBKS4JF0001 |  |  |  |  | 4/17/15 (standard 30 business days) | 2015-05-14 | 2015-05-19 |  |  |  | 4/16- submitted to Sadisconnects 4/23- pending disconnect due date of 5/14 4/30- pending disconnect due date of 5/14 5/7- pending disconnect due date of 5/14 5/14- soft disconnect complete, pending disconnect completion 5/21- disconnect complete
2015-04-16 | ShaRita | none | 1201 K Street / Suite 1020 SACRA MENTO CA USA 95814 | disconnect | NSPE0009195064 OQBK5V0T |  |  |  |  | bcbh8s3b0001 |  |  |  |  | 4/17/15 (standard 30 business days) | 2015-05-14 | 2015-05-18 |  |  |  | 4/16- submitted to Sadisconnects 4/23- sent follow up email to disconnect group to process order request asap, pending due date and order information 4/23- pending disconnect due date of 5/14 4/30- pending disconnect due date of 5/14 5/7- pending disconnect due date of 5/14 5/14- soft disconnect complete, pending disconnect completion 5/21- disconnect complete
2015-05-05 | ShaRita | n/a | orlando-fl_bcbjggp10001-1592612 | request to have the following circuit migrated from UHGECC to Connextions-Wellpoint VPN | NSPE0009246140 Order Number: 10632986 PVC ID: 5598595(Automated Pre-Build) |  |  |  |  | bcbjggp10001 | [7 empty] | new Connextions-Wellpoint 65001 |  |  | 5/5- sent to ShaRita 5/7- ShaRita working on order 5/7- melissa added second PVC, per request from engineering
2014-05-20 | ShaRita | C1551-07-IJ | 160 North Dozier Blvd, Bldg 300, Florence, SC 29501 | 10M Ethernet access and port RJ45 handoff MD5 TCWVERbgpajs9tbxp | Opportunity ID O-1023946 Quote ID: 190288495 Order Request 190288742 Service Order 190295999 20322412 access 20322411 port | 190295999 |  | 5485879 | 7680 | C0002812 E3002206 | gnb_I1612 - c4-bd7w-bd7w-0142 flo I233 - c4-6zk-hp5v-0019 32/HFGS/400279//SB DMARC Info: Data room 1st fl 1st rack tagged not extended | 2014-05-30 | 2014-07-03 | 2014-07-03 | bpdd | 9/26/2014 12/1/2014 | 2014-12-18 | UnitedHealth Group-TCW -65449 | 214-647-4442 donald_r_osborn@optum.com | troubleshooting scheduled for 5/30 at 930 CST Bridge: 866-692-3158 Passcode: 9236734 | 7/31- pending demarc extension 8/6- pending demarc extension 8/14- demarc extended; pending scheduling of beas installation 8/27- provisioning is working with production support to clear the TPTA mux issue 9/3- Order still with pending TPTA mux. Expected to be resolved 9/5. 9/10- pending cabling onsite, scheduled for Thursday, 9/11 (escalated) 9/17- working to have the MUX completed this week (escalated) 9/25- Order still with pending completion for Mux message HULT228. We have t to replace a OPC card before Mux msg HULT228 will complete. Pending ETA on the replacement card. (escalated) 10/2- Order still with pending completion for Mux message HULT228 due to a card replacement needed.We have escalated to Transport and getting the ETA of this. Due to no capacity for re-routing the circuit. 10/8- New update on the replacement card -- The card has been replaced and the Tier 2 GTNOC team is performing updates. According to the Tier 2 tech working on it. It may take 2 days to complete the work. 10/16- Mux msg HULT228-O is now completed. Pending scheduling of beas installation. 10/23- beas installation complete. Had to install anda 400 on temp power. Customer is aware. customer requested to have tech redispatched to switch over to the new outlet. Cusotmer requested to hold off order closure until permanant power is in. 10/29- pending customer to place new outlet 11/6- new outlet installed. dispatched rescheduled for 11/10. 11/13- Outlet swing issue on this order had been resolved. trouble ticket opened and escalated by provisioning unable to provision the access circuit and pvc 11/20- ready for activation, customer notified
2014-10-27 | ShaRita | UCA89-05-IJ | 2300 Clayton Rd, Suite 1000, Concord, CA 92108 | 20mg Ethernet acces and speed, Optical MMF LC connector, 10th floor MDF room. with 20 Mb Type 4 Premium Ethernet Access MRC - $1,229 (provided by AT&T) MD5 UHGVERbgpbqZyofa | Opp Id O-1130621 Quote ID: 190571645 Order Request 190572229 Service Order(s) [ 190587030 ] has been created for Order Request 190572229 20594116 access 20594115 port | 190587030 |  | 5537261 | 5392 | C1011511 E3005329 | 86/KRGN/574399//PT 86/KRGN/575404//PT the Beas box is installed in the 10th floor server room rack 2 right below AT&T fdp patch panel 1. Connected Beas box fiber 0.6 to att fdppannel 1 port 3. | 11/3/2014 1/7/15 4/14/15 | 12/2/2014 5/5/15 | 2015-05-05 | BPDD 12/10/2014 Standard | 12/9/2014 5/12/15 | 2015-05-12 | unitedhealthgroup-64609 | 91 91600 84400 harish_kandpal@optum.com | 5/29 at 6pm CST Bridge: 866-868-8630 Passcode: 6653710 | 1/21- pending conduit, per LEC PM was advised that the quickest way to resolve this would be if the end user/customer contact their property manager directly to find out and to also make arrangements regarding having the fiber jumpers placed. 1/28- order on hold, penidng conduit. requested LEC to provide more information on conduit issue, pending feedback. 2/5- order on hold, pending conduit. 2/12- order on hold, pending conduit. per LEC PM, We had a field technician out on the site and the customer still needs to have Riser Co. place fiber to suite. Please confirm and provide an ECD for customer readiness. 2/19- order on hold, pending conduit. 2/26- order on hold, pending conduit. Per John, They are in the process of scheduling with the riser company. 3/5-order on hold, pending conduit. (per John supposed to have meeting yesterday) 3/11-order on hold, pending conduit. 3/19- order on hold, pending conduit. 3/26- order on hold, pending conduit. 4/1-order on hold, pending conduit. Agreement with procurement group at UHG pending signature. 4/9- order on hold, pending conduit. Agreement with procurement group at UHG pending signature. 4/14- received confirmation from John that work is complete, pending new FOC date 4/23- Per LEC PM awaiting customer needs to work with their riser company to have the AT&T provided fiber cable placed. They requested that to be done by 4/24/15. Waiting confirmation from John that this is complete. 4/30- FOC date 5/5 5/7- circuit delivered, pending confirmation from from Harish where demarc was extended in order to schedule beas installation 5/12-ready for activation, customer notified
3/10/2015 revised 3/13 | ShaRita | GA777-04-IJ | 56 Marietta St , Atlanta, GA 30303 Per Matt 180 Peachtree St. Steve will send John a note to change the order. We will provide tie-down information only, no access circuit. Customer provided access | 1G, John will throttle down to 500M UHGVERbgpbqZyofa SMF LC | Quote O-1231816 Quote ID: 190933459 Order Request 190945564 Submitted, Service Order(s) [ 190960574 20917104 access 20917103 port CHANGE ORDER COMPLETE TO CHANGE VLAN FROM 1 TO 150 PER CUSTOMER REQUEST Service Order(s) [ 191467300 ] has been created for Order Request 191310979 order 21299780 | 190960574 |  | 5580133 | 20Mb | E5001144 C1019330 | customer provided access FACIILITIES ASSIGNMENT: Verizon Cage 20936, Cabinet 0000, CP:0000:181367 /Panel 4: Ports 1 & 2 – SMF with SC connectors |  |  |  | bpdd (standard 4/24/2015) | 2015-04-24 | 2015-04-21 | unitedhealthgroup-65138 | 763-694-7333 skbrown1@optum.com | activation requested for 6/4 at 7am CST Bridge: 866-692-3158 Passcode: 9236734 | 3/12- Pending ammended order from John 3/19- ShaRita is working on order 3/20- ShaRita submitted 3/26- pending provisioning approval 4/2- Provisionining created trouble ticket because there is an issue preventing the correct path to flow correctly in system. 4/9- order being escalated to development for system issue. 4/16- Provisioning is still working on the MUX but was able to provide the LOA to customer. 4/21- ready for activation, customer notified
2015-05-26 | melissa | n/a | 14100 Business Center Drive, Elk River, MN 55330. | add a VLAN, UnitedHealthGroup-ECCMA, | [5 empty] | BOBKTFPX0001 | [10 empty] | 5/28- VPN added
2015-05-05 | Melissa | MN053-21-CJ | 14100 Business Center Drive, Elk River, MN 55330. | remove the RAVEN VPN | Order Number: 10651543 PVC ID: 5212873 |  |  |  |  | Verizon MPLS VPN: UHG-Raven ID bobkwhd00001-5212873 | [10 empty] | 5/28- Raven VPN removed
2015-05-05 | Melissa | MN053-21-CJ | 14100 Business Center Drive, Elk River, MN 55330. | remove the RAVEN VPN | Order Number: 10651546 PVC ID: 5189862 |  |  |  |  | Verizon MPLS VPN: UHG-Raven ID bobktfpx0001-5189862 | [10 empty] | 5/28- Raven VPN removed
2015-04-20 | ShaRita | RI007-02-IJ | 24 Albion Road, Lincoln, RI 02865- hub order | 100M, John will throttle down to 50M Optical LC SMF Md5 UHGVERbgpbqZyofa | O-1284487 Quote ID: 191086123 Order Request 191086345 Service Order(s) [ 191088888 ] New Quote ID: 191100615 for multi service Order Request 191100846 (cancelled) 21034224 access 21034223 port | 191088888 |  | 5595878 | 1.5M | C1020549 E4004504 | 85.KFGS.004397..NE 1st fl, server rm, data rm, MDF#1, tagged w/id and repair# | 2015-05-01 | 2015-05-29 | 2015-05-29 | bpdd 6/1 Standard | 2015-06-05 | 2015-06-01 | unitedhealthgroup-64891 | 763-744-1949 anthony_flesher@optum.com | 6/5 at 8am CST Bridge: 866-808-3655 Passcode: 7356498 | 4/23- Matt indicated order needed to be multi service. Asked John to confirm. 4/30- submitted order to provisioning 5/7- pending FOC date, ASR submitted 5/1 requesting 6/2, SR 02BLXU-001 SITE SURVEY COMPLETED:04/30/2015 5/14- pending FOC date (SLA for VZT 10 business days). will open escalation ticket if FOC not obtained by LEC (VZT) 5/26- FOC 5/29 6/4- circuit ready for activation, customer notified
2015-04-30 | ShaRita | none | 200 Patrol Road JEFFER SONVILL E IN USA 47130 | disconnect | NSPE0009235070 OQBK51WN |  |  |  |  | BCBKNRS70001 |  |  |  |  | 4/30/15 (standard 30 business days) | 2015-05-28 |  |  |  |  | 4/30- submitted to Sadisconnects 5/7- sent follow up email to disconnect group, pending order info and due date 5/14- pending disconnect due date of 5/28 5/26- pending disconnect completion 6/4- disconnect complete
2015-01-14 | ShaRita | CO820-02-IJ | 6300 Diagonal HighWay, Boulder, CO 80301 terminating at Century link Denver Main at 931 14th Street, Denver, CO reorder to Boulder on pulbic access | 100M, John will throttle down to 50M, Optical, MMF LC Connector on secondary CFA PDWI0/31-LGSS/199,200/ DNVRCOMA/ DNVRCOMAHGO | O-1182089 Quote ID: 190780173 Order Request 190785375 Service Order 190794405 20803662 access cancelled 20803661 port cancelled Quote ID: 190855432 Order Request 190855976 (public access) Service Order(s) [ 190856285 ] 20848832 access 20848831 port | 190794405 190856285 |  | 5565124 5571407 | 15M | E4003439 access E4003648 access C1017959 port | BCXD7213 BLDG 23, fl 1, rm D531 - to BLDG MAIN, FL DATACENTER, RM-MEETM | 2/26/2015 3/4/2015 | 3/25/2015 5/22/15 | 2015-03-19 | BPDD (standard 3/11/2015 EXPEDITE (3/13/15) | 2015-04-01 | 2015-06-11 | unitedhealthgroup-65217 | 763-744-2077 robert_a_benson@optum.com | scheduled for 6/11 at 11pm CST Bridge: 866-878-8630 Pass code: 6653710 | 2/26- order submitted and approved by provisioning. Provisioning working on submitting ASR to LEC 3/5- Customer confirmed to deliver to Bldg 23; Fl 1; Room D531. ASR already supped with updated Demarc info. Pending FOC date. 3/11- Awaiting LEC to provide FOC 3/12- FOC is 3/25, but according to Level 3, they should be able to deliver sooner 3/19- Level 3 confirmed circuit delivered, requested provisioning to work with them to have completion notice sent ASAP 3/26- order on hold, awaiting confirmation from John if demarc will be extended or if order will be cancelled. 4/1- awaiting end user to extend demarc 4/9- order on hold, pending demarc extension 4/16-order on hold, pending demarc extension 4/23- pending Tag-and-locate (RE: PN:2084883266874801// 1007BDQS), Line testing with Level 3 (RE: PON 2084883266874801 … ), beas dispatch (** DISPATCH REQUEST - URGENT**…) 4/29- Order has been supped to change hand off. ASR will be disconnected and will submit a new one with the correct hand off. 5/7- pending FOC date for handoff change. L3 design and engineering still working to determine FOC. 5/13- The date was set for the Standard 7 days. Due date 5/22. However, we will work to complete sooner than that. The port has been assigned and this is making its way to the field. 5/22- FOC date 5/22 5/26- circuit delivered, pending testing with LEVEL 3 (escalated) 5/28- beas installation scheduled for 5/29 6/4- Per Level 3, customer needs to put in request to have extension moved from port 9 to port 12. Port moved 6/4. Asking BNE to test 6/11- ready for activation, customer notified
2014-10-30 | ShaRita | PA028-02-IJ | 4 Walnut Grove Drive, Horsham, PA 19044 | 200M, will throttle down to 150M 1000 Base-SX MMF LC Connector MD5 UHGVERbgpbqZyofa No NID | O-1133505 Quote ID: 190583437 Order Request 190586545 Service Order(s) [ 190587688 20621887 access 20621886 port |  |  | 5543162 | 36M (35 available) | C5000644 E5000666 | 11.KFGS.302898..PA DMARC Info: 1ST FLR, DATA CNTR, FIBER RACK 4, BOTTOM | 11/24/2014 1/6/15 | 12/29/2014 1/14/2015 | 2014-01-14 | bpdd | 1/6/2015 1/30/2014 | 2015-01-14 | Unitedhealthgroup-65205 | 763-744-2077 robert_a_benson@optum.com |  | 10/30- pending credit 11/6- ShaRita working on order 11/13- site survey scheduled for 11/14 at 8am 11/20- pending ASR submission ***BMIS ticket T0708524 still pending resolution*** 11/26- still pending FOC date due to system issue 12/4- Issue with LEC system still not yet resolved. The issue is escalated to the highest level 12/11- FOC date 12/29 12/17- FOC date 12/29 1/8- lcon was on vacation and unavailable to provide access for circuit delivery, pending new FOC date. 1/14- Plant Test Date - 01/13/2015 (Techs visit for pre testing installations and turn up) Due Date - 01/14/2015 (Due date for circuit installation) 1/16- ready for activation customer notified
2015-03-23 | ShaRita | C1573-01-IJ | 1 National Life Dr, Montpelier, VT 05604 need by june 1 | 100M, John will Throttle down to 20m MD5 UHGVEReccgas4Usp9 Optical, SMF LC National Life Telecom room Rack NL-00304 extended to SOV Switches | O-1244560 Quote ID: 190971856 Order Request 190982436 Service Order(s) [ 190995712 20942775 access 20942774 port | 190995712 |  | 5583300 | 1536 | E4004102 C1019210 | 88/KQGN/316542/00/MJD/ Demarcation Info- National Life Telecom Room (LEC transport area) MetroNId in Rack#5, extended 20' to Rack#2 where Overture ISG1400 is mounted. Unit is tagged with all information. The State of Vermont was also onsite and ran their cable to the comb-block which extends to SOV data room. Cable is plugged into port1 but customer has not installed equipment yet. | 2015-04-03 | 2015-04-28 | 2015-04-30 | BPDD (standard 5/4/2015) | 2015-05-11 | 2015-05-06 | UHGECC- 65436 | 952-974-5838 hau.phan@optum.com |  | 3/26- ShaRita is working on order. 4/1-pending FOC date 4/9- per customer request, order supp'ed to change handoff to electrical/RJ45. Pending FOC date 4/16- FOC date 4/28 4/23-FOC date 4/28 4/30- circuit delivered 5/6- ready for activation, customer notified
2014-10-30 | ShaRita | PA024-02-IJ | 7350 Tilghman Street, Allentown PA 18106 | 100M Ethernet 1000 Base-SX MMF LC Connector MD5 UHGVERbgpbqZyofa NID | O-1133502 Quote ID: 190583419 Order Request 190586553 Service Order(s) [ 190587701 20616812 access 20616811 port | 190587701 |  | 5542288 | 36M (35 available) | C1012922 E4002650 | 11.KFGS.302888..PA 3RD FLR LAN RM WALL MOUNTED TAGGED WITH ORDER NUMBER NOT EXTENDED | 2014-11-14 | 2014-12-19 | 2015-01-20 | bpdd | 1/2/2015 2/11/2015 | 2015-01-29 | Unitedhealthgroup-65281 | 763-744-2077 robert_a_benson@optum.com | completed with Bob on 6/23 | 10/30- pending credit 11/6- ShaRita working on order 11/13- site survey completed and requirements forwarded to lcon and John. Order submitted pending provisioning approval. 11/20- ASR submitted, but there is a system issue that was encountered preventing ASR to be sent to regional. The issue is causing delay with getting FOC date. 11/26- still pending FOC date due to system issue 12/4- system issue resolved. order is now with engineering for review. Pending FOC date. 12/11- order on hold, pending site requirements 12/17- pending site requirements 1/8- pending site requirements 1/14- pending site requirements 1/21- circuit delivered, pending demarc confirmation from John 1/28- John confirmed demarc, beas installation scheduled for 1/30 2/5- ready for activation, customer notfied
2015-05-22 | ShaRita | C1246-05-IJ | 200 North Nash Street El Segundo, CA 90245 | Copper, RJ45 100mg Ethernet circuit | O-1312023 Quote ID: 191219968 Order Request 191220053 Service Order 191234448 created for Order Request 191220053 21142817 access 21142816 port | 191234448 |  | 5608004 | 50M | E4005069 C1021656 | ea6hr 6hr 0028 demarc per CLR 1st floor colo R 2.2.5c:0.4. Labeled ckt ID on the Overture and on the hard loop with a red Vz tag. |  |  |  | BPDD (Standard 7/13) | 2015-06-12 | 2015-06-12 | uhg-ecc-65458 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 5/28- ShaRita working on order 6/4- order submitted to provisioning, pending ASR submission to LEC 6/11- pending RFC testing 6/18- ready for activation, customer notified
2015-05-18 | ShaRita | UFL73-05-CJ | 10151 Deerwood Park Blvd. Suite 420/Build, Jacksonville, FL 32256 | Upgrade from 2xT1 to 3xT1 | O-1307438 CW order id 191200585 NSPE0009283869 IQBK57TQ | 8361229 | P2111314 (in) P1953775 (out) | 5208089 | No change | BCBKV7430001-2 out BCBK8KT50001-0003 in | 52/HCGS/775462//SB DEMARC LOC: 4TH FL, ST 420, SERVER RM, QMT1, SLt 1 | 2015-05-28 | 2015-06-09 | 2015-06-09 | BPDD | 2015-06-16 | 2015-06-09 | unitedhealthcare- 64742 | 91 91600 84400 harish_kandpal@optum.com | hotcut scheduled 6/19 | 5/26- order submitted to provisioning 5/28- pending FOC date 6/4- FOC date 6/9 6/11- ready for hotcut, customer notified
2015-05-05 | ShaRita | none | 1311 President George Bush Tollway RICHAR DSON TX USA 75080 | disconnect | NSPE0009246439 OQBK52SV |  |  |  |  | BCBJW13T0001 |  |  |  |  | 5/6/2015 (standard 30 business days) | 2015-06-04 | 2015-06-08 |  |  |  | 4/30- submitted to Sadisconnects 5/7- pending order info and due date 5/14- pending disconnet due date 6/4 5/26- disconnect due date 6/4 6/4- pending disconnect completion 6/11- disconnect complete
2015-04-30 | ShaRita | none | 48 Monroe Turnpike TRUMB ULL CT USA 06611 | disconnect | NSPE0009234498 OQBK5ZGM OQBK5ZGH OQBK5ZGJ OQBK5ZGK OQBK5ZGL |  |  |  |  | AOBJGV7P0001 and T1s IBBJG5BG0001,IBBJ2HM50001,IBBJ2HNW0001,IBBJ2HPR0001 |  |  |  |  | 4/30/15 (standard 30 business days) | 2015-05-28 | 2015-06-08 |  |  |  | 4/30- submitted to Sadisconnects 5/7- pending disconnect due date of 5/28 5/14- pending disconnect due date of 5/28 5/26- disconnect due date of 5/28 5/28- pending disconnect of OQBK5ZGM now that the ACTIVE DS1 RIDERS are disconnected 6/11- disconnect complete
2015-04-20 | ShaRita | RI007-02-IJ | 24 Albion Road, Lincoln, RI 02865- hub order | 100M, John will throttle down to 50M Optical LC SMF Md5 UHGVERbgpbqZyofa | O-1284487 Quote ID: 191086123 Order Request 191086345 Service Order(s) [ 191088888 ] New Quote ID: 191100615 for multi service Order Request 191100846 (cancelled) 21034224 access 21034223 port | 191088888 |  | 5595878 | 1.5M | C1020549 E4004504 | 85.KFGS.004397..NE 1st fl, server rm, data rm, MDF#1, tagged w/id and repair# | 2015-05-01 | 2015-05-29 | 2015-05-29 | bpdd 6/1 Standard | 2015-06-05 | 2015-06-01 | unitedhealthgroup-64891 | 763-744-1949 anthony_flesher@optum.com | 6/5 at 8am CST Bridge: 866-808-3655 Passcode: 7356498 | 4/23- Matt indicated order needed to be multi service. Asked John to confirm. 4/30- submitted order to provisioning 5/7- pending FOC date, ASR submitted 5/1 requesting 6/2, SR 02BLXU-001 SITE SURVEY COMPLETED:04/30/2015 5/14- pending FOC date (SLA for VZT 10 business days). will open escalation ticket if FOC not obtained by LEC (VZT) 5/26- FOC 5/29 6/4- circuit ready for activation, customer notified
2015-03-10 | ShaRita | GA777-02-IJ | 56 Marietta St NW 6th Floor, Atlanta, GA, 30303-2885 release CFA so Equinix can extend. 1000 based LX (SMF/LX). Hub ATL17 - RNH Order | 1G Internet Ethernet circuit with 500mb commit rate. 1000 based LX (SMF/LX). | O-1227523 Smartform 190921269 NSPE0009097156 9UGPNE4Z u330623 | 8301195 |  |  |  |  | customer provide access Tiedown: Equinix Info: UUNET: PP:0000:200063 Cage 60026, Cab 0000 Channel: 31/32 | [5 empty] | 2015-06-11 |  | Site contact is Luke Martin, Phone: (763) 744-1692 Luke_Martin@optum.com | Per conversation with Paul, this is an internet circuit. You can call into our hotline, 24-7, to activation your circuit, at 866 829 9719 for circuit activation. | 3/13- IP Capacity Inquiry #9UGPNE4Z- ATL17 will require card augment (sfp). Please allow 2-4 weeks to complete. Working on order 3/19- ShaRita is working on order 3/23- ShaRIta submitted. 3/26- pending entrance facility assignment from capacity. ATL17 will require card augment (sfp). Please allow 2-4 weeks to complete. 4/1- ATL17 will require card augment (sfp). Please allow 2-4 weeks to complete. 4/9- ATL17 will require card augment (sfp). Please allow 2-4 weeks to complete. 4/16- Provided customer LOA. Awaiting customer to order the cross connect to Equinix and once completed to send us the completion notice for patching and testing. 4/23- order on hold, awaiting customer to confirm cross connect to Equinix is complete 4/30-order on hold, awaiting customer to confirm cross connect to Equinix is complete 5/7-order on hold, awaiting customer to confirm cross connect to Equinix is complete 5/14- order on hold, awaiting customer to confirm cross connect to Equinix is complete 5/26- order on hold, awaiting customer to confirm cross connect to Equinix is complete 6/4- per Pat circuit is extended. Informed provisioning to proceed with patching and testing 6/11- ready for activation
2015-02-05 | ShaRita | CA777-01-IJ | Equinix 445 North Douglas Street, El Segundo, CA 90245 cahnged to 600 W 7th St, 6th floor, Los Angeles CA 90017-3859 on 2/6 | 1G, John will throttle down to 500M Single-Mode fiber with LC connector, Optic - GE-L 1310, MD5 UHGVERbgpbqZyofa. BGP advertisement-interval set to 0 BFD Enabled Dyanmic CAR Enabled Dyanmic Port Enabled Line Protection AS Override Off Optic - GE-L 1310 | O-1199996 Quote ID: 190806713 new Quote ID: 190806866 Order Request 190816465 NSPE0009010201 Service Order(s) [ 190830911 20829782 access 20829781 port | 190830911 |  | 5568742 | 20Mb | E5000995 C1017878 | customer provided access FACIILITIES ASSIGNMENT: Verizon Cage 500, Cabinet 0000, PP:0000:181368 / Panel 3: Ports 07 & 08 – SMF with SC connectors |  |  |  | bpdd (standard 3/23/2015) | 2015-03-23 | 2015-04-23 | UnitedHealthGroup-65155 | 763-694-7333 skbrown1@optum.com | activation requested | 2/10- sent to ShaRita 2/12- ShaRita working to submit order 2/19- order submitted, pending provisioning approval. Sent follow up email to provisioning 2/26- provisioning is currently working on building path 3/5- provisioning working on repath of order 3/11- Due to system issue preventing path to appear correctly in system, provisionining had to issue a trouble ticket. BGW Ticket T1312993 3/19- pending logical port assignment, VDDS ticket T1386912 3/26- provisioning is checking to see if another port can be opened, current port is blocked 4/1-provisioning still working on TT so that she can write MUX message, but was able to provide LOA for customer 4/16- Mux Message: H-UVT296 was written, no dispatch is needed since equipment is already pre-wired. LOA already provided to customer. Order is ready for testing and closure 4/23- GLP had to Requery and Deploy the Configs for the new port so that provisioning can complete the NOC move on the Transport ckt under Legacy Provisoining Actions 4/23- ready for activation, customer notified
2015-05-28 | ShaRita | n/a | Connextions- St Louis VPN add | VPN Add | Smartform 191233951 NSPE0009327800 EA: ORDER CQBK6FBV SERVICE P1836931 EF: ORDER CQBK6FBX SERVICE P1840324 | 8372263 | P1836931 P1840324 |  |  | BCBKK3WW0001-2050478 |  |  |  |  | BPDD | 2015-06-18 | 2015-06-17 | UHGECC-65409 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 5/29- submitted to ShaRita 6/4- order submitted to provisioning 6/11- provisioning working on order 6/18- escalating with provisioning 6/25- ready for cutover to add VPN
2015-05-19 | ShaRita | none | 4809 E Thistle Landing Drive PHOENI X AZ USA 85044 | disconnect | NSPE0009286475 OQBK56LF |  |  |  |  | bcbk0yg00001 |  |  |  |  | 5/6/2015 (standard 30 business days) | 2015-06-17 | 2015-06-22 |  |  |  | 5/19- submitted to Sadisconnects 5/27- disconnect due date 6/17 6/4- disconnect due date 6/17 6/11- disconnect due date 6/17 6/25- disconnect complete
2015-05-19 | ShaRita | none | 8333 Forest Point Blvd Charlotte , NC 28273 | disconnect | NSPE0009286539 OQBK56L3 |  |  |  |  | BCBKLXPC0001 |  |  |  |  | 5/6/2015 (standard 30 business days) | 2015-06-18 | 2015-06-22 |  |  |  | 5/19- submitted to Sadisconnects 5/27- disconnect due date 6/18 6/4- disconnect due date 6/18 6/11- disconnect due date 6/18 6/25- disconnect complete
2015-04-30 | ShaRita | none | 48 Monroe Turnpike TRUMB ULL CT USA 06611 | disconnect | NSPE0009234498 OQBK550Q OQBK550L OQBK550M OQBK550N OQBK550P |  |  |  |  | AOBJY39S0001 and T1s IBBJ6N850001 IBBJ6N870001 IBBJ6N880001 IBBJ6N9D0001 |  |  |  |  | 4/30/15 (standard 30 business days) | 2015-06-03 | 2015-06-18 |  |  |  | 4/30- submitted to Sadisconnects 5/7- John will resubmit LOD once the 800#s and calling plans has been unlinked. 5/14- waiting for the final terms to be removed , ticket needed 5/26- pending disconnect due date 6/3 6/4- soft disconnect completed 6/3, pending disconnect completion 6/11- sent follow up email to provisioning to complete disconnect asap 6/17- provisioning complete, now able to proceed with soft disconnect 6/25- disconnect complete
4/28/2015 all info received 5/5 | ShaRita | VA723-01-IJ | UHG - Equinix DC2 Cage 02730, 21715 Filigree Court, AShburn VA 20147 terminate to Equinix 2nd Floor MMR BFD enabled. Meeting at 21721 Filigree Court building id 9OZ | 1G port only, John will throttle down to 200M Optical MMF LC | O-1291150 Needs to go BAU CW order id 191143704. Inquiry ID: 9W8NRU8S NSPE0009263308 IQBK53TD | 8356264 | P2110594 |  | 1.5M | BOBK8JY10001 |  |  |  |  | BPDD | 2015-06-09 | 2015-05-29 | UnitedHealthGroup-65059 | 763-744-3052 mitch_preble@optum.com | 6/25/2015 They do not have Single mode, they will reschedule the activation | 4/30- pending if this will be port only or if access will need to be ordered. 5/5- UHG said to go with port only, Matt is working on Inet, Melissa requested Auth code. 5/11- submitted to ShaRita 5/14- order submitted to provisioning 5/26- pending MUX work, pending LOA approval before release 5/28- LOA sent 5/29- order complete
2015-05-29 | ShaRita | none | 8333 FOREST POINT BLVD CHARLOTTE NC | disconnect | NSPE0009309031 OQBK59P3 | [5 empty] | BCBKK73F0001 |  |  |  | 5/27/2015 (standard 30 business days) | 2015-06-25 | 2015-06-29 |  |  |  | 5/29- submitted to Sadisconnects, pending order information and due date 6/11- disconnect due date 6/25 6/25- soft disconnect complete 7/2- disconnect complete
2015-05-29 | ShaRita | none | 200 PATROL RD JEFFERSONVILLE IN | disconnect | NSPE0009309041 OQBK59PW | [5 empty] | BCBKJRN30001 |  |  |  | 5/27/2015 (standard 30 business days) | 2015-06-25 | OQBK59P3 |  |  |  | 5/29- submitted to Sadisconnects, pending order information and due date 6/11- disconnect due date 6/25 6/25- soft disconnect complete 7/2- disconnect complete
2015-04-30 | Bend | none | 41 Rue Des Fontanot - 4th Floor NANTER RE FRANCE 92000 | disconnect | NSPE0009235212 5684299 |  |  |  |  | W1B31940 |  |  |  |  | 4/30/15 (standard 60 calendar days) | 2015-06-30 | 2015-06-30 |  |  |  | 4/30- order being submitted to bend disconnect team 5/14- pending TEV with local contact 5/26- TEV complete, disconnect due date 6/30 6/5- disconnect due date 6/30 6/11- disconnect due date 6/30 7/2- circuit disconnected
2015-03-23 | ShaRita | C1575-01-IJ | 14500 W. 105 Street, Lenexa, KS 66215 need by june 1- state of vermont | 100M, John will Throttle down to 20m MD5 UHGVEReccgas4Usp9 Optical, SMF LC First floor, Telco Rm 110 extended to First floor, Customer Cabinet Rm 121 | O-1244393 Quote ID: 190971455 Order Request 190982503 Service Order 190990921 20936343 access 20936342 port | 190990921 |  | 5582560 | 1536 | C1019182 E4004085 | BCXJ9591 Dmarc is 1st floor / room 110 / cabinet 5 / pnl 7. Tagged | 2015-03-27 | 2015-05-12 | 2015-04-16 | BPDD (standard 5/4/2015) | 5/19/2015 5/20/2015 | 2015-05-13 | UHGECC-65464 | 952-974-5838 hau.phan@optum.com | 7/13 at 7pm CST bridge 866-878-8630 pass code 6653710 | 3/26- ShaRita is working on order. 4/1-pending FOC date 4/9- FOC date 5/12 4/16- FOC date 5/12 4/23- circuit delivered, awaiting John to confirm if demarc will have to be extended 4/30- John confirmed to install beas at the demarc, pending beas installation 5/7- Installed and configured beas but unable to ping beas. There is a problem thru LVL3. B&E opened a tkt with LVL3. Dmarc is 1st floor / room 110 / cabinet 5 / pnl 7. Tagged. Dispatch complete. Pending resoloution of ticket with level 3, testing, and completion of order. 5/13- ready for activation, customer notified
2015-02-06 | ShaRita | CA777-02-IJ | Equinix 600 W 7th St, 6th floor, Los Angeles CA 90017-3859 on 2/6 | Internet 1G Ethernet circuit with 500mb commit rate. SMF with LC. | O-1201005 Quote ID: 190814425 Order Request 190816460 NSPE0009010196 Service Order(s) [ 190830908 20829749 access 20829748 port | 190830908 |  | 5568740 |  | E5000994 C1018051 | customer provide access FACIILITIES ASSIGNMENT: Verizon Cage 230, CP:0101:29770 / Ports 31 & 32 – SMF with SC connectors |  |  |  | bpdd (standard 3/23/2015) | 2015-05-01 | 2015-05-01 |  | Site contact is Luke Martin, Phone: (763) 744-1692 Luke_Martin@optum.com | activation requested. | 2/10- sent to ShaRita 2/12- ShaRita working to submit order 2/19- order submitted, pending provisioning approval. Sent follow up email to provisioning 2/26- provisioning encountered a few issues preventing approval but should be resovled today 3/5- provisioning is awaiting port assignment for the ckt then the logical task will proceed and she will be able to write the mux message and provide LOA 3/11- provisioning is awaiting port capacity at Lax 15 3/19-pending logical port assignment, VDDS ticket T1386912 3/26- New Ticket T1421549 for the port assignment to be cleared for use on this order 4/2- provisioning is awaiting port issue to be resolved by IT 4/16- port issue resolved, CKT: C1018051 GW: PIO/GW4LAX15.0.1B.0.1 we should have LOA by COB 4/23- pending dispatch for this Internet mux message for a physical path/wire 4/30- MUX message has been updated and re-stepped for dispatch 5/1- ready for activation, customer notified
2015-04-04 | ShaRita | PA007-01-IJ | 15 Campus Boulevard, Newtown Square, PA 19073 | 1G, John will throttle down to 500M Optical SMF LC MD5 UHGVERbgpbqZyofa | O-1253844 Quote ID: 191022062 Order Request 191022333 Service Order(s) [ 191034824 ] has been created for Order Request 191022333 20997148 access 20997147 port | 191034824 |  | 5590934 | 30000 | E5001284 C0050641 | 11.KFGS.303449..PA VZB DMARC: 1ST FL DATA RM WALL MNT TAGGED | 2015-04-17 | 2015-06-05 | 2015-05-12 | BPDD (standard 05/15/15) | 2015-06-12 | 2015-05-13 | unitedhealthgroup-64887 | 763-553-4801 sonja_d_mroczynski@optum.com | 7/9 at 8pm CST Bridge: 866-878-8630 Pass code: 6653710 | 4/9- site survey scheduled for Tuesday, April 14th at 10am EST 4/16- pending site requirements, forwarded to John 4/23- pending site requirements 4/30-pending site requirements, FOC date 6/5 but subject to change if requirments are delayed (CRD 5/8) 5/7- pending site readiness 5/13- ready for activation, custoner notified
2015-05-22 | ShaRita | C1559-05-IJ | Catamaran 2425 Busse Rd., Elk Grove Village, IL 60007 | 100M, John will throttle down to 50M Gig UNI - Optical MMF LC | O-1312016 Quote ID: 191219121 Order Request 191219861 Service Order 191234424 created for Order Request 191219861 21142754 access 21142753 port | 191234424 |  | 5607980 | 20M | E4005066 C1021654 | ea5i9 5i9 0041 The demark is at 1st floor, Verizon area on 2.02 shelf 6 positon 9 and 10. Labeled with ckt id |  |  |  | BPDD (Standard 7/13) | 2015-06-11 | 2015-06-10 | UHG-ECC-65521 | 763-744-1587, Leon_L_Betterman@optum.com | 7/10 at 11am CST Bridge: 868-878-8630 Passcode: 6653710 | 5/28- ShaRita working on order 6/4- order submitted to provisioning, pending ASR submission to LEC 6/11- ready for activation, customer notified
2015-04-20 | ShaRita | NJ722-02-IJ | 95 Christopher Columbus Drive 16th Floor, Jersey City, NJ 07302- hub order | 100M, John will throttle down to 50M Optical SMF LC Md5 UHGVERbgpbqZyofa terminate to 16th Fl MDF | O-1284373 Quote ID: 191085553 Order Request 191086018 Service Order(s) [ 191096069 ] has been created for Order Request 191086018 21008263 access 21008262 port njy I145449 | 191096069 |  | 5592621 | 1.5M | C1020306 E4004392 | ea-95c-95c-0054 Demarc 19th fl qts telco room fiber panel wall mount lgx1 pos#60, 61tx, rx |  |  |  | bpdd 6/1 Standard | 2015-04-30 | 2015-05-20 | unitedhealthgroup-65062 | 763-744-1957 ranjit_adhikari@optum.com | per john active on 7/21 | 4/20-submitted to ShaRita 4/23- order submitted to provisioning 4/30- circuit designed, pending site survey 5/7- site survey completed. Building 95c Floor(FL) mez Room pop. ISG5K 1.2.5:2.3 -- cross connects are to be completed from the mezz to the 19th floor ,in house tech will extended dmarc from the 19th to the 16th - ea-95c-95c-0054 5/14- pending dispatch to connect circuit and complete RFC testing 5/19- rescheduled for 5/20. 5/21- ready for activation, customer notified
2015-06-12 | ShaRita | none | 10770 E. Briarwood Ave Centennial, CO 80112 | disconnect | NSPE0009370275 OQBK6M1Q | [5 empty] | BCBKS4MF0001 |  |  |  | 6/11/2015 (standard 30 business days) | 2015-07-13 | 2015-07-15 |  |  |  | 6/15- submitted to Sadisconnects, pending order information and due date 6/25- sent follow up email to Sadisconnect requesting order be processed before COB today and order information/due date be provided 7/2- pending disconnecte due date 7/13 7/9- pending disconnecte due date 7/13 7/17- disconnect complete
2015-06-12 | ShaRita | none | 822 Centennial Way LANSING MI USA 48917 | disconnect | NSPE0009370370 OQBK6M12 | [5 empty] | BCBKBCTT0001 |  |  |  | 6/11/2015 (standard 30 business days) | 2015-07-13 | 2015-07-15 |  |  |  | 6/15- submitted to Sadisconnects, pending order information and due date 6/25- sent follow up email to Sadisconnect requesting order be processed before COB today and order information/due date be provided 7/2- pending disconnecte due date 7/13 7/9- pending disconnecte due date 7/13 7/17- disconnect complete
2015-06-12 | ShaRita | none | 2300 Clayton Rd, Suite 1000 Concord CA 92108 | disconnect | NSPE0009370567 OQBK6M2B | [5 empty] | BCBKYTHH0001-0004 |  |  |  | 6/11/2015 (standard 30 business days) | 2015-07-13 | 2015-07-17 |  |  |  | 6/15- submitted to Sadisconnects, pending order information and due date 6/25- sent follow up email to Sadisconnect requesting order be processed before COB today and order information/due date be provided 7/2- pending disconnecte due date 7/13 7/9- pending disconnecte due date 7/13 7/17- disconnect complete
2015-06-12 | ShaRita | none | 160 North Dozier FLORENCE SC USA 29501 | disconnect | NSPE0009370697 OQBK6M3R | [5 empty] | BCBKV62H0001 |  |  |  | 6/11/2015 (standard 30 business days) | 2015-07-13 | 2015-07-15 |  |  |  | 6/15- submitted to Sadisconnects, pending order information and due date 6/25- sent follow up email to Sadisconnect requesting order be processed before COB today and order information/due date be provided 7/2- pending disconnecte due date 7/13 7/9- pending disconnecte due date 7/13 7/17- disconnect complete
2015-02-16 | ShaRita | C1570-01-IJ | 1831 Chestnut Street, St Louis , MO 63103- RNH Order | 100M, John will throttle down to 70M Optical MMF LC MD5 UHGVEReccgas4Usp9 | O-1207372 Quote ID: 190831402 Service Order(s) [ 190857790 ] has been created for Order Request 190831506 20857109 access 20857108 port | 190857790 |  |  |  | C1018093 E4003712 |  | 3/2/15 4/16/15 | 6/21/2015 6/26/2015 |  | bpdd (3/30 Standard) |  |  | UHG-ECC- 65409 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 4/1- FOC date 6/21 4/9-FOC date 6/21 4/16- pending new FOC date due to issue on the LEC VLAN 0002 is in use for another customer. Repath the NNI from EOHLHVJW0001 to EO3VJVJW0001 as they need this new circuit moved to eNNI chc00280173. VLAN 2 is available there and the eNNI is not oversubscribed. 4/23- pending FOC date. Escalated to provisionng 4th level for assistance with LEC to get the FOC date asap 4/30- Pending FOC date, Charter has an SLA of 15 bds upon receipt of a clean ASR for the FOC. Escalation POC has been assigned to order for assitance with obtaining the FOC date 5/7- Site walk completed on this order 3/22, construction is required-placing and splicing (ECD 6/14) / permits (ECD 5/15), Est install ECD/ FOC is 6/26 5/14- status per the Lec team - Charter advised that the 6/15 is the best due date they can provide at this time. Continuing to exp for better dd 5/26- Correct on FOC date, This requires a 60 day build which will put us near a standard interval of a 6/26 Foc date. 5/28- FOC date 6/26 6/4- FOC date 6/26 6/11- FOC date 6/26 6/17- Order on hold. Per Charter they have standard Right of Entry Agreement that must be executed by the propery owneror an authorized designee. Forwarded John ROE agreement 6/25- status per Lec team - Charter is pending the signed ROE (Right Of Entry) from LCON. FOC set at 7/15 but in Jeopardy, pending receipt of the signed ROE 7/2- per Johns request order has been supp'ed to cancel 7/9- Per email received from LEC: Yes, your ASR has been received and we are working to get the order canceled on our end 7/17- order cancellation complete
2015-04-01 | ShaRita | C1574-03-IJ | 11425 S 84th Street Midlands Data Center Papillion NE 68046 Need by june 1- | 100M John will throttle down to 20MOptical, LC SMF, MD5 UHGVEReccgas4Usp9 | O-1251324 Quote ID: 191009183 Order Request 191009924 Service Order 191024323 20965456 access 20965455 port | 191024323 |  | 5612757 | 1500 | E4004189 C1019538 | 21.KFGX.000419..COXC. Demarc location is d14 rmu 36 | 2015-04-07 | 2015-05-19 | 2015-05-05 | BPDD (standard 5/12/15) | 2015-05-27 | 2015-07-17 | UHGECC-65465 | 952-974-5838 hau.phan@optum.com | scheduled for 7/23/2015 1030am CST bridge: 866-692-3158 pass code 9236734 | 4/1- Order submitted to ShaRita 4/9- FOC date 5/19 4/16- FOC date 5/19 4/23- FOC date 5/19 4/29- FOC date 5/19 5/7- circuit delivered, pending beas installation, customer was out of office so couldn't be scheduled. 5/14- beas dispatch incomplete, circuit needs to be extended to customer cabinet 5/26- pending customer extension to cabinet 5/29- per john extention is done. 6/4- asked John to confirm exact location of demarc extension so that dispatch can move forward with scheduling of the beas installation 6/11- beas dispatch scheduled for 6/17 6/17- beas installation incomplete, unable to contact Scott/POC to confirm access. order on hold, please provide new lcon 6/24- BEAS is scheduled for install on 6/24 at 11am. 6/25- beas installation incomplete. Lcon unable to locate demarc extension. 7/2- John provided demarc extension details, pending rescheduling of beas dispatch 7/9- Our BEAS install was incomplete yesterday due to field tech unable to reach lcon. Also, field tech said that there is a router connected to LEC’s circuit (Circuit ID 21.VLxx.000780..COXC). Dispatch team wants those things confirmed before re-dispatching. The router is believed to be connected to LEC’s equipment. Can customer verify on whose router that is? Because there should not be any equipment connected to LEC’s equipment/box. 7/17- ready for activation, customer notified
2015-07-14 | Mel/ShaRita | UCA99-04-CJ, | San Diego CA | add multicast reciever | [5 empty] | P2080663 BCBK515X0001-5 |  |  |  |  | bpdd | [5 empty] | 7/16- Ivue requested. 7/18- multicasting added.
2014-03-24 | ShaRita | CA167-05-IJ | 160 West Santa Clara Street, San Jose, CA 95113 | 100mg ethernet with dport john will throttle down to 15mg rJ45 copper handoff md5 UHGVERbgpbqZyofa please add bfd extend to floor 1 mdf | SFDC Opportunity ID O-0976292 Quote ID: 190211520 Order Request [ 190216062 ] Service Order(s) [ 190216926 20247131 access 20247130 port New opp id O-1122310 Quote ID: 190545354 NEW Service Order(s) [ 190546649 ] has been created for Order Request 190546239 20561135 access NEW 20561134 port NEW | 190216926 190546649 |  | 5463703 5531404 | 5008 | E4000663 C1003838 C1010837 NEW E4002325 NEW | 86/KQGN/581991//PT VZB DMARC: 10th floor server room 63.KFGS.024893..CBCL | 4/1/2014 5/13/2014 10/20/2014 12/2/2014 12/4/2014 | 5/1/2014 5/30/2014 6/26/2014 12/4/2014 12/31/2014 | 6/25/2014 12/30/14 | bpdd | 5/8/2014 6/9/2014 7/31/2014 12/11/2014 1/8/2015 3/16/2015 3/25/2015 | 2015-03-19 | UnitedHealthGroup-65080 | 860-702-8284 keith_mangene@optum.com | per Tauoa cirucit was activated Friday evening. 7.31 | 10/15- old order has been supp'ed to cancel. new order approved by provisioning. Pending ASR tranmission due to system issue. 10/23- Pending FOC date 10/30- order on hold customer unresponsive in scheduling date for site survey/access. requested LEC engineer info to provide to customer 11/6- FOC date 12/4 11/13- FOC date 12/4 11/20- FOC date 12/4 11/26- FOC date 12/4 12/4- pending circuit delivery due to access issue, building management needs 24 hour prior notification 12/11- new FOC date 12/31 12/17- FOC date 12/31 1/8- circuit delivered, pending demarc extension 1/14- pending demarc extension 1/21- pending demarc extension 1/28- pending demarc extension 2/5- pending demarc extension, per Tauoa the network change freeze is extended until February 13. 2/12- pending demarc extension. 2/19- pending demarc extension. 2/25- pending demarc extension. 3/5- customer confirmed demarc extended. awaiting dispatch to schedule beas installation 3/11- awaiting dispatch to schedule beas installation. 3/19- beas installation scheduled for 3/19 between 9am-3pm pst. 3/20- ready for activation, customer notified
2015-01-06 | B end Varun | II539-02-IJ | 10th floor and part GF, Building Campus 5B, RMZ Ecoworld, Bangalore, Karnataka | 100mg ehternet on 150mg access SOO to Melbourne - circuit ID W0X83226 | OVI-1-1439415846, SO-5625756 |  |  |  | 20M | W1B63844 | [6 empty] | 2015-05-13 | UnitedHealthGroup-65170 | Mohammed Humayun Rafi 091 804 920-3530 humayun_rafi@optum.com | scheduled 5/14 at 1:30am central. | 2/26- pending MDF room ready date from UHG 3/5- MDF ROOM WILL BE READY ON 04/15/2015 FROM CONTACT SARVESH PRATAP SINGH, WILL CONTACT PTT FOR EARLY DELIVERY IF POSSIBLE. 3/12-pending MDF ready date of 4/15 3/26- pending MDF- asking about PTT progress While we are waiting for the MDF room readiness, we have asked the PTT to initiate the outside fiber work and keep the fiber ready till the building basement. Post MDF readiness, fiber would be pulled till server room and equipment installation can be planned accordingly. 4/1 pending MDF ready date 4/9- MDF will be ready 4/13 4/16-SERVER ROOM IS READY. UPS POWER SUPPLY WILL BE READY IN ANOTHER FEW DAYS TIME. OUTSIDE FIBER WORK HAS BEEN COMPLETED. INBUILDING FIBER WORK IS IN PROGRESS. EQUIPMENTS (RACK + MUX) WILL BE DELIVERED TO THE CUSTOMER SITE IN THIS WEEK. 4/24- As per the current status, fiber work has been completed till the customer server room. Equipments (Rack + MUX) have already been delivered to the customer site this week. Rack installation was scheduled yesterday. MUX installation + splicing + MUX integration + circuit provisioning has been scheduled for next week. I will share the circuit handover date by Monday. 4/30- asking about circuit handover date 5/4- The PTT has shared a FOC date of 13-14 May for the circuit. 5/7- Fiber work completed. Rack + MUX installation completed. SFP card insertion has been scheduled for tomorrow. Circuit will be provisioned in the next week. Testing will be initiated on 14 May.
2014-11-18 | B end | II538-02-IJ | 11th, 12th floor, Building 12B, Mind Space, Survey No. 64 (part), Hitech City, Madhapur, Hyderabad, Telangana 500081 | 150M will throttle down to 100M SOO to Melbourne - circuit ID W0X83226 | OVI order no-1-1422052275, SO-5614810 GL-7810941. |  |  |  | 21680 or closest in our contract | W1B59938 (port) |  |  | 2015-03-15 |  | bpdd | 2015-04-03 | 2015-05-14 | unitedhealthgroup-65191 | 91 91600 84400 harish_kandpal@optum.com | scheduled 5/14 at 5am central | 1/22- pending ptt response. 1/29- PTT FOC date = 15 March 2015 2/5- KINDLY NOTE THAT MDF ROOM (WHERE THE CIRCUIT HAS TO BE INSTALLED) IS EXPECTED TO BE READIED IN THE NEXT 10-15 DAYS. SITE SURVEY HAS BEEN SCHEDULED FOR THIS WEEK. 2/19 Asking UHG when site will be ready, PTT can't deliver until 4 weeks after site ready date. 2/26- pending date of MDF room readiness 3/4- pending date of MDF room readiness 3/12- pending MDF readiness, expected 4/15 3/26-THE OUTSIDE FIBER WORK HAS BEEN INITIATED. EQUIPMENTS HAVE ALSO BEEN DISPATCHED TO THE CUSTOMER SITE. POST OUTSIDE FIBER WORK, INBUILDING FIBER WORK WILL BE INITIATED BY 25-26 MARCH POST SERVER ROOM READINESS, RACK + MUX INSTRALLATION WILL BE SCHEDULED 4/1- . pending MDF ready date 4/9- MDF will be ready 4/22. 4/23- checking with UHG on MDF ready date 4/24- per UHG MDF now ready with permenant power, let service delivery know. 4/30 - NEW FOC DATE PROVIDED (05/08/2015) - AWAITING FOR NNI AND VLAN FOR PVC CREATIO - REMOVED FROM HCUS 5/7- – Fiber work completed. Rack + MUX installation completed. Circuit is under provisioning at the PTT end. Testing has been scheduled in the next week (Monday onwards).
9/25/2014 change to SMF 1/7/2015 | ShaRita | C1567-02-IJ | 910 15th Street, Suite 350 Denver, CO 80202 | 50M Ethernet UHGVEReccgas4Usp9 RJ45 handoff Type 1 Premium Ethernet Access MRC - $1000 (Provided by Verizon)- terminate 3rd Floor Meet Me Room | O-1109229 Quote ID: 190499346 Order Request 190501586 Service Order(s) [ 190504467 20533739 access 20533738 port dnv I32369 |  |  | 5526699 | 15000 | C1010084 E4002162 | ea-90d-90d-0032 Floor(FL) 3rd Suite(STE) 350 Room meet me MCS 303.3.10:3 |  |  |  | bpdd | 2014-11-06 | 2014-10-30 | UHG-ECC-65482 | 763-7442154 scott_moyer@optum.com | Scott will reschedule . It looks like we may have a bad SFP in the router. I’m working on getting another replacement. | 9/30- sent to ShaRita 10/2- order submitted, pending provisioning approval. 10/8- pending ccr 1230376 to order a card for existing media converter in meet me room 90d d5 303.3.10 port 3. rFT date 10/30 pending card shipment 10/16- pending CCR install, rFT date 10/30. VzB demarc will be Building Managments 3rd floor meet me room, it will be the customer^s responsibilitiy to order their x-connect thru building management once the CCR is completed. 10/23- pending CCR install, rFT date 10/30. Equipment set to install 10/24 10/30- circuit installed. pending end to end testing 10/31- ready for activation, customer notified 1/8- John requested to have handoff changed from MMF to SMF. Change order being submitted by ShaRita. 1/14- change complete, customer notified 5/5- need to reschedule due to SPF mismatch
2015-02-09 | ShaRita | NC002-08-IJ | 8333 Forest Point Blvd, Charlotte, NC 28273 to 4601 Corporate Drive NW, Concord, NC 28027 | Private Line pt to pt T1 | NSPE0009008075 IQBK4BK3 | 8235150 | P2103127 |  |  | MGBK7WJT0001 | 22/HCGS/499086//SB charlotte Data center mount 6 to 7 Rj48C. 22/HCGS/499103//SB concord DEMARK: 1ST FLR COMP RM MM 2 SLOT 26 RJ48C TAGGED NOT EXT | 2015-02-20 | Charlotte 3/5/2015 Concord 3/10/2015 | 3/5/2015 3/3/2015 | bpdd | 2015-03-12 | 2015-03-06 |  |  |  | 2/9- sent to ShaRita 2/12- ShaRita working to submit order 2/19- order submitted, pending provisioning approval. This request has been referred to the area planner for review. 2/26- Charlotte FOC date 3/5/2015 ¦¦ Concord FOC date 3/10/2015 3/5- circuit delivered for Concord, pending Charlotte FOC date 3/5 3/6- ready for activation customer notified
2015-02-09 | ShaRita | NC002-08-IJ | 8333 Forest Point Blvd, Charlotte, NC 28273 to 4601 Corporate Drive NW, Concord, NC 28027 | Private Line pt to pt T1 | NSPE0009008075 IQBK4BK6 | 8244364 | P2103128 |  |  | MGBK7WJW0001 | 22/HCGS/499088//SB mm6 slot 22 not ext rj48c tagged w/ both ckt ID 22/HCGS/499105//SB DEMARK: 1ST FLR COMP RM MM 2 SLOT 16 RJ48C TAGGED NOT EXT. |  | Charlotte 3/5/2015 Concord 3/10/2015 | 3/2/2015 3/3/2015 | bpdd | 2015-03-12 | 2015-03-11 |  |  |  | 2/12- ShaRita working to submit order 2/19- order submitted, pending provisioning approval. This request has been referred to the area planner for review. 2/26- Charlotte FOC date 3/5/2015 ¦¦ Concord FOC date 3/10/2015 3/5- Concord circuit delivered, pending Charlotte FOC date 3/5/2015 3/11- ready for activation customer notified
2014-05-16 | ShaRita | TX023-05-IJ | 1311 President George Bush Tollway, Richardson, TX 75080 | 100mg ethernet md5 UHGVERbgpbqZyofa RJ45 handoff | SFDC Opportunity ID O-1022175 Quote ID: 190286266 Order Request 190287039 Service order id 190296020 20322426 access 20322425 port special construction Quote 190411111 Order Request 190426762 | 190296020 |  |  | 22000 | C1005442 E4001093 | 12/KEGS/701756//GTEC 12/KEGS/702353//GTEC | 5/30/2014 10/8/2014 1/21/2014 | 10/21/2014 10/31/2014 4/15/2015 |  | bpdd | 10/28/2014 11/7/2014 4/22/2015 | 2015-03-05 | unitedhealthgroup-64517 | 214-647-4442 donald_r_osborn@optum.com |  | 10/8- order wasd jep'ed due to no access. John provided new contact information for Verizion to work with in order to secure a right of entry in order to bring in the fiber from the street. New FOC date 10/31 10/15- FOC date 10/31 10/23- FOC date 10/31 10/30- FOC date 10/31 11/6- pending loop delivery due to access issue. LEC requested that Ron and lcon, Raymond, call him at Jeff Zwolenik (972) 578-3224 jeff.s.zwolenik@verizon.com. Information provided to John. 11/13- pending loop delivery due to access issue. Advised John, that per Verizon Network team, customer needs to provide Telco License Agreement from the Property Manager of that building to gain access. 11/20- pending loop delivery due to access issue. 11/26- pending loop delivery due to access issue. 12/4- pending loop delivery due to access issue. 12/11- pending loop delivery due to access issue. 12/17-pending loop delivery due to access issue. 1/8- Documents received from legal and hand delivered to owner. They will need to sign and fax back to Verizon before we can move forward. 1/14- awaiting customer to return documents back to Verizon 1/21- documents returned to Verizon granting access, pending new FOC date 1/28- pending FOC date from LEC 2/5- FOC date 4/15- Work Order type is Fiber Placing and Splicing. This Work Order is to place and splice Fiber >2,500'. Build ECCD (Estimated Construction Completion Date) is 4/3/15. 2/12- FOC date 4/15 2/19- FOC date 4/15 2/23- FOC date 4/15 3/4- FOC date 4/15
2015-02-09 | ShaRita | NC002-08-IJ | 8333 Forest Point Blvd, Charlotte, NC 28273 to 4601 Corporate Drive NW, Concord, NC 28027 | Private Line pt to pt T1 | NSPE0009008075 IQBK4BK7 | 8244342 | P2103129 |  |  | MGBK7WJX0001 | NC/HCGS/959569/ /WINS/ concord demarc: 1st flr data center suite 115 westel sh 2 sl 15 rj48c tagged no ext 22/HCGS/499082//SB charolette 1st floor server room, mnt 6, slot 10, rj48c tagged not ext. | 2015-02-20 | Concord 3/9/15 Charlotte 3/4/15 | 3/5/15 3/3/15 | bpdd | 2015-03-16 | 2015-03-05 |  |  |  | 2/12- ShaRita working to submit order 2/19- order submitted, pending provisioning approval. This request has been referred to the area planner for review. 2/26- Concord FOC date 3/9/15 ¦¦ Charlotte FOC date 3/4/15 3/5- ready for activation, customer notified
2014-05-06 | B end | FR501-06-IJ | 41 Rue Des 3 Fontanot, Nanterre, FR 92000 | 6M Ethernet MD5 UHGVERbgpbqZyofa | 1-1342510313 s/o 5528751 |  |  | 5509703 | 3072 | W1B31940 | 0034WSF6 Orange |  | 2015-02-24 | 2015-02-25 | bpdd |  | 2015-03-02 | UnitedHealthGroup-64912 | 987-313-9388 anupam_datt@uhc.com |  | 8/21- FOC 29 SEPTEMBER 9/25- verifying remarks from PTT ORANGE'S STUDY DONE, THEY RELAUNCHED AGAIN THEIR TECHNICAL SERVICE TO GET THE DATE OF INSTALLATION. 10/2- ORANGE'S INSTALLATION FAILED, DUE TO CUSTOMER'S SECONDARY CABLING ISSUE. MAIL SENT TO ORANGE TO GET THE DATE OF DESATURATION OR IF THE CUSTOMER HAS BEEN ADVISED. 10/3- The ptt head is at the -1 floor, customer IT room is at 4th floor, the secondary cabling between these floors is saturated, and Orange is unable to do it.The customer have to advise his cabling subcontractor for that. I advised local contact this morning, the primary contact Mrs Lenfant is OOO today, and should be back next Monday. Her substitute take care of our request and advise us once Mrs Lenfant will come back. Currently we haven’t any demark to provide as the installation not done yet. 10/9- LCON AND HQ AWARE OF SECONDARY CABLING ISSUE, AND CONTACTED THEIR SUBCONTRACTOR. 10/16- pending secondary cabling. 10/30- pending secondary cabling 11/6- pending secondary cabling 11/13- pending secondary cabling 11/20- MRS LENFANT STILL WAIT THE APPROVAL FROM HER HQ TO LAUNCH THE WORKS. 11/26- pending secondary cabling. 12/4- pending internal cabling 12/11- Pending internal cabling. Service delivery has agreed to wait until end of year, then the order will be "parked" which means we need to sart over with OE and PTT ordering. 1/8- pending confirmation from uhg on secondary cabling 1/15 - order will be parked starting today and wil be re-initiated once secondary cabling is commpleted 2/19- ORANGE'S INSTALLATION PLANED THE 24TH FEBRUARY AFTERNOON. 2/25- orange delivered. pending line test for 2/27 3/2- COMPLETION LETTER SENT TOGETHER WITH THE CONFIGLET TO JOHN SERGOT ( 'SERGOT, JOHN' (JOHN_SERGOT@OPTUM.COM))
2014-11-05 | B end | IR507-03-IJ | No. 2 Harbourmaster Dublin, Ireland , IRL | E1 2048 SOO to Letterkenny W0Y12673 | 5594151 DISCONNECT S/O: 5594170 |  |  |  | 1536 | W1B13709 (disconnect) W1B54154 (New) |  |  |  |  | bpdd |  |  | unitedhealthgroup-64950 | Office +6(02)5884741/63 9297700576 aj_nalo@uhc.com |  | 11/6- pending SOF 11/20- asking Marc about SOF 11/26- SOF sent to marc and executed 12/4- checking on order numbers 12/11 followed up with Marc on order numbers 1/8- re-using Bell Taill, confirmed this is hotcut and pending update on dates. 1/15- escalating with Dany 1/16- ready for hotcut
2014-11-05 | B end | IR503-02-IJ | Old Naas Road, Dublin 12 / Waverley Office Park , Dublin IRL | E1 2048 SOO to Letterkenny W0Y12673 | 5594135 DIS ORDER: 5594130 |  |  |  | 1536 | W1A97105 (disconnect) W1B54150 (New) |  |  |  |  | bpdd |  |  | unitedhealthgroup-65086 | Office +6(02)5884741/63 9297700576 aj_nalo@uhc.com |  | 11/6- pending SOF 11/20- asking Marc about SOF 11/26- SOF sent to marc and executed 12/4- checking on order numbers 12/11 followed up with Marc on order numbers 1/8- re-using Bell Taill, confirmed this is hotcut and pending update on dates. 1/15- escalating with Dany 1/16- ready for hotcut
2014-11-18 | ShaRita | UFL88-10-IJ | 5908 HAMPTON OAKS PKWY, TAMPA, FL 33610 (AOBK6MKF0001 slot 10) to 4601 Corporate Drive NW, Concord NC 28027 AOBK6MKF0001 | pt to pt T1s | NSPE0008803449 IQBK2LXW IQBK2LY0 | CONNEXTIONS, INC - TIN 8133273 slot 10 | P2096380 |  |  | NP0C028W0001 (tampa) MGBK66R10001 (concord) | LEC CIRCUIT ID:NC/HCGS/586716/ /WINS DEMARC INFO:Demarc: 1st flr data center mux #1 slot 11, rj48C, tagged and not ext | 2014-12-09 | 2014-12-17 | 2014-12-15 | bpdd | 2014-12-17 | 2014-12-15 |  |  |  | 11/18- Sent to ShaRita 11/20- ShaRita is working on order submission 11/26- order submitted, pending provisioning approval 12/4- pending provisioning approval due to no available capacity. Request for capacity has been made by provisioning. 12/11- pending FOC date 12/16- ready for activation, customer notified
2014-11-18 | ShaRita | UFL88-10-IJ | 5908 HAMPTON OAKS PKWY, TAMPA, FL 33610 (AOBK6MKF0001 slot 11) to 4601 Corporate Drive NW, Concord NC 28027 | pt to pt T1s | NSPE0008803449 IQBK2L0K | TIN 8133573 slot 11 | P2096391 |  |  | NP0C028W0001 (tampa) MGBK66SG0001 (Concord) | NC/HCGS/543500/ /WINS/ DEMARC INFO: 1st flr data center mux #2 slot 19, rj48C, tagged and not ext | 2014-11-26 | 2014-12-17 | 2014-12-15 | bpdd | 2014-12-17 | 2014-12-15 |  |  |  | 11/18- Sent to ShaRita 11/20- ShaRita is working on order submission 11/26- pending FOC date for Concord. No need for ASR for Tampa since this was requested to terminate to BACS DS3 12/4- FOC is expected to be received today 12/11- FOC date 12/17 12/16- ready for activation, customer notified
2014-09-25 | ShaRita | UDC04-05-IJ | 701 PennsylvaniaAve, 2nd Floor Washington DC 20004 | 100M Optical MMF LC 100 Mb Type 2 Premium Ethernet Access MRC - $1,400 (provided by Verizon MD5 UHGVERbgpbqZyofa | O-1109819 Quote ID: 190503010 Order Request 190503630 Service Order(s) [ 190507183 ] has been created for Order Request 190503630 20535599 access 20535598 port |  |  | 5526993 | 20000 | C1009876 E4002178 | 36.KFGS.302819..CD VZB DMARC: 2nd floor Suite 200 / MDF 211, rack mounted tagged | 2014-10-01 | 2014-11-25 | 2014-11-24 | bpdd | 1/7/2015 | 2014-11-24 | unitedhealthgroup-65178 | 763-694-7409 terry_bjorke@optum.com |  | 10/2- ASR submitted, pending FOC date 10/8- site survey scheduled 10/9, pending survey results 10/15- pending completion of site requirements (sent to John and local contact) 10/23- pending completion of site requirements 10/29- pending completion of site requirements 11/6- pending completion of site requirements 11/13-pending completion of site requirements . Interduct is done, pending confirmation on power 11/20- pending completion of site requirements . Interduct is done, pending confirmation on power 11/26- pending completion of site requirements . Interduct is done, pending confirmation on power 12/4- pending completion of site requirements . Interduct is done, pending confirmation on power 12/11- ready for activation, customer notified
2014-09-10 | ShaRita | C1422-04-IJ | Unitech Cyber Park, Tower B, 10th Floor, Sector 39 Gurgaon, Haryana 122002 India | 20M ethernet MD5 UHGVEReccgas4Usp9 RJ 45 handoff dmarc 10th Floor, Telecom room, Rack #1 | O-1099474 Quote ID: 190467712 New Quote 190486254 Order Request 190479121 New Order Request 190499429 Service Order 190513684 20558259 access 20558258 port |  |  | 5530749 | 1536 | E3004951 Access C1010824 port | PTT CKT ID: 6799119 Demark: Device, port and interface detail : MUX BG202 // GRG_GIB_902_BG202_F L12:L1B_6F EoS port 4 // FE |  | 11/25/2014 12/3/2014 | 2014-12-03 | bpdd | 2014-12-12 | 2014-12-10 | UHG-ECC-65433 | 763-744-2265 travis_dent@optum.com |  | 9/11- pending access quote 9/18- access quote provided. 7-10 week delivery timeframe. Submitted to ShaRita 9/25- Pending pricing. Due to issue with NID, new order had to be reissued. 10/2- order reissued. New lcon information was provided. Pending lcon verification before order submission. 10/8- pending lcon verification 10/15- order submitted. pending provisioning approval 10/23- Local loop order placed to PTT, expected FOC date from PTT by end of next week. 10/29- FOC date 11/25 11/6- FOC date 11/25 11/13- FOC date 11/25 11/20- FOC date 11/25 11/26- Order re-provisioning work is going on & FOC date revised to 3rd of Dec. 12/4- pending confirmation that circuit was delivered 12/11- ready for activation, customer notified
2014-09-18 | ShaRita | UFL88-09-IJ | 5908 HAMPTON OAKS PKWY, TAMPA, FL 33610 | 1G, John will throttle to 400M, Optical handoff | Quote/Order # 190480420 Service Order(s) [ 190486580 ] has been created for Order Request 190480620 20533401 access 20533400 port |  |  | 5526653 | 30000 | C0009015 E5000494 | 69/KFGS/700811//GTES DEMARC IS 1ST FLOOR, VERIZON COLO AREA, RR 019308, MP-33, PORTS 87-88. | 10/1/2014 11/19/2014 | 11/18/2014 12/2/2014 | 2014-12-09 | BPDD | 11/12/2014 12/9/2014 12/19/2014 | 2014-12-10 | 65033- UnitedHealthGroup | 702-242-7654 tauoa.falo@optum.com |  | 9/22- ShaRita is working 9/25- site survey scheduled for Friday, Sept 26 10/2- site survey complete. Pending FOC date 10/8- confirmed that we're using an existing NID, there's no need for additional power or space ... it's already onsite. But order is on hold due to unresponsive lcon please have lcon call LEC engineer. Asked for clarafication on this The LEC rep assigned is waiting for clarification from the LEC engineer. Awaiting for LEC engineer to respond. Melissa also reached out to Rob on a data center name 10/15- Verizon needs to install equipment (Flashwave FW9500) in our cage at Centurylink's POP. CL requires us to do and official request and paperwork to request space and power in their POP. We are waiting for Centurylink's authorization to proceed with order. 10/23- > Pending LEC FOC Issuance > Currently waiting for Centurylink to return the paperwork but according to Tammy (VW Engr) there is no timeline and there's no way to push them. > Will check with the LEC next week if CTL has returned the paperwork. 10/29- Per LEC Engr, received the paperwork from Centurylink late on Friday. The work orders required have been sent for approval and they've brought in the ship dates letting everyone know we need the materials asap. The equipment probably wont arrive for at least 3 weeks. They won't know any etas until they receive all the equipment. Possibly looking at December. 11/6- The work orders have been processed for equipment. Pending FOC (NDMT TICKET C201411060053) .FOC issued for 11/18 11/13- FOC date 11/18 11/20- due access issue order was supp'ed for new due date. pending new FOC date of 12/2 11/26- FOC date 12/2 12/4- pending circuit delivery due to access issues, got correct order info and circuit from CL and re-dispatching. Asking for 12/12. 12/11- circuit ready for activation, customer notified
2014-11-04 | ShaRita | MN011-10-CJ | 1707 West Creek Lane, Chaska MN | Change - ADD UHGECC VPN to 10G | Order Number: 10434771 PVC ID: 5539402(Automated Pre-Build) Redirect PVC ID: No Redirect |  |  |  | 400mg | W0Z48442 / BOBKTD960001 |  |  |  |  | bpdd |  | 2014-11-13 | UHG-ECC- 65462 | 763-744-2265 travis_dent@optum.com |  | 11/6- Order Number: 10434771 PVC ID: 5539402(Automated Pre-Build) Redirect PVC ID: No Redirect 11/13- configlets sent to Travis and john.
2014-11-04 | ShaRita | MN011-11-CJ | 1707 West Creek Lane, Chaska MN | Change - ADD UHGECC VPN to 10G | Order Number: 10433082 PVC ID: 5538820(Automated Pre-Build) |  |  |  | 400mg | bobkwcw20001 |  |  |  |  | bpdd |  | 2014-11-13 | UHG-ECC- 65462 | 763-744-2265 travis_dent@optum.com |  | 11/5- Order Number: 10433082 PVC ID: 5538820(Automated Pre-Build) 11/6- configlet ready. 11/13- configlets sent to Travis and john.
2014-08-15 | B end | SG503-02-IJ | #07-02 55 Market Street, Singapore, 48941 | 2 x E1 SOO to Melbourne - circuit ID W0X83226 | OVI 1-1360648723 • Port : 5542952 • ether-access : 5542953 |  |  |  | 1024 | W1B36180 (E1) W1B36178 (port) | Starhub SERVICE ID: 1201201095/1201201096 |  |  |  | bpdd | 2014-11-11 | 2014-10-21 | unitedhealthgroup - 65223 | (+91)-80-49203530 humayun_rafi@optum.com | ACTIVATION IS SCHEDULED ON NOVEMBER 5, 11:00 AM SGT - NOVEMBER 4, 9PM US CST GLP ENGINEER ASSIGNED IS MARIA ORRO | 8/21- pending SOF from Varun 8/26- SOF returned from UHG. 9/4- following up with Varun on order information 9/11- TEV COMPLETED WITH THE LCON. CLIENT: OPTUM HEALTH & TECHNOLOGY SINGAPORE PTE LTD ADDRESS: #08-02 55 MARKET ST SINGAPORE 48941 SINGAPORE LOCAL CONTACT FOR SITE ACCESS: SARI ERLANDY (9641 7373) SARI.ERLANDY@AP.JLL.COM working on getting address changed 9/18- PTT starhub has order, pending FOC. 9/25- SITE SURVEY COMPLETED ON 24/9. PTT IS WORKING TO HANDOVER THE CIRCUIT ON 30/09. 10/2- Starhub advised THE NEXT VISIT FOR THE INSTALLATION AND TESTING WILL BE ON TUESDAY 14TH OCT 2014 AT 10AM. i am checking to see if this was due to site access issues. 10/9- pending installation and testing for the 14th 10/16- Starhub dleivered, pending line testing, pvc build and configlet
2014-01-21 | ShaRita | TX092-02-IJ | 1030 Bendsdale, Pleasanton, TX | 10752 7xT1 MD5 UHGVERbgpbqZyofa | smartform 190118086 NSPE0007748576 IQBKVTBL | 6218579 | P2061425 | 5437923 | 1536 | BCBK4LRM0001-7 | 31/HCGS/706108//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#1 31/HCGS/706109//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#2 31/HCGS/706110//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#3 31/HCGS/706111//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#1,SLOT#4 31/HCGS/706112//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#2,SLOT#1 31/HCGS/706113//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#2,SLOT#2 31/HCGS/706114//SW DEMARC LOC: 1ST FOOR,TELCO ROOM,CAB DEMARC LOC Continued: ROOM,CAB#2,SLOT#3 Jack Type: RJ48C | 1/23/2014 4/4/2014 5/16/2014 | 1/31/2014 3/31/2014 4/25/2014 5/30/2014 | 2014-06-09 | bpdd | 2/7/2014 4/2/2014 | 2014-06-13 | unitedhealthgroup-65277 | 763-744-0981 glenn_moore@uhc.com | activation scheduled for 7/10 at 2pm CST Bridge Number: 888-656-8232 pass code: 9158384 | 1/22- order approved by provisioning; pending ASR to be submitted to LEC 1/29- pending FOC date of 1/31 2/6- order on hold. LEC advised order should be cancelled and re-issued, customer will not be ready until MAY or JUNE. 2/20- pending new FOC date of 3/31 2/27- pending new FOC date of 3/31 3/6- pending FOC date of 3/31 3/12- pending FOC date of 3/31 3/20- pending FOC date of 3/31 3/27- FOC date 3/31 4/3- requested circuit be delivered to MPOE per John. Pending new FOC date. 4/10- FOC date 4/25 4/17- FOC date 4/25 4/23- FOC date 4/25 5/1- customer not ready; the building contractor is still placing conduit to the pole. It has to be completed first, so they can put the terminal. 5/8- customer not ready; the building contractor is still placing conduit to the pole. It has to be completed first, so they can put the terminal 5/14- requested new FOC date 5/22- FOC date 5/30 5/28- FOC date 5/30 6/5- circuit not delivered due to facilites issues on LEC side. There is a splicing job with an ECD of 6/9 6/11- circuit delivered; dispatch scheduled for 6/11 to verify wiring and optioning. unable to loop up SMJK for circuits BCBK4LRM0003 and BCBK4LRM0005 6/18- ready for activation; customer notified
2014-03-07 | B end | IR507-03-IJ | No. 2 Harbourmaster Dublin Ireland IRL (expedited) | E1 2048 r md5 UHGVERbgpbqZyofa SOO to Letterkenny - circuit ID W0Y12673 | Dublin OVI# 1-1293062194 new SO# 5481011 |  |  | 5484721 | 1536 | W1B13709 | : CIRCUIT COMES OFF VERIZON OVERTURE IECA01EC-0726 ON PORT 1. |  |  |  | bpdd |  | 2014-06-16 | UnitedHealthGroup-64950 | Office +6(02)5884741/63 9297700576 aj_nalo@uhc.com | 6am Central 6/19 Bridge is 866-819-9840 pcode 3365052 | 3/10- pending SOF 3/27- uHG provided signed SOF 4/10- checking on order information 4/17- new quote needed to be created because site is offnet 4/24- no additional charges to UHG, PCM waived, order can now progress. s/o assigned 5/15- TAIL ORDERED FROM EIRCOM, pending PTT delivery date 5/22- pending delivery date from EIRCOM 5/29COMMS ROOM WILL BE READY FOR EIRCOM TO RERETURN TO SITE ON MONDAY 9TH JUNE. SUBJECT TO CONFIRMATION BY THE CUSTOMERS PROJECT MANAGER BEFORE COB NEXT FRIDAY. ONCE THE EIRCOM TECH ATTENDS SITE TO INSTALL THEIR NTU, IT COULD TAKE A COUPLE OF DAYS TO TEST AND HAND OVER THE 6/12- tech expected to go to site friday to complete testing. pushing for friday handover 6/16- ready for activation, engineer informed.
2014-04-30 | ShaRita | NV750-02-IJ | 7135 S. Decatur Blvd., Las Vegas, NV 89118 | 100mg Ethernet with RJ45 handoff MD5 UHGVERbgpbqZyofa | SFDC Opportunity ID O-1009018 Quote ID: 190259429 Service Order(s) [ 190260625 ] has been created for Order Request 190260216 20287233 access 20287232 port CCR 1209709 lsv I2223 | 190260625 |  | 5476016 | 10000 | C1004727 E4000888 | ea-l4qk-l4qk-0039 overture re-boot worked and IPRT sees the new card in slot 2. We have left a hard loop in SLT:2 Port:1. Once this is tested, we will be using the following ETHERNET Tie-Cable LGX: 1.09 P:3B Port:12 |  | RFT 5/30/2014 | 2014-05-30 | bpdd | 2014-06-06 | 2014-06-03 | UnitedHealthGroup-65267 | 702-242-7654 tauoa.falo@optum.com |  | 4/3- pending credit 5/1- order submitted to provisioning 5/8- pending site survey. Pending CCR 1209709 for 100bt recard Overture 5100 @ l4qk,1,1.9.4, CCR due 5/30 5/14- Pending CCR 1209709, due 5/30, card received at terminal and pending install 5/22- Pending CCR 1209709, due 5/30, equipment set to install on 5/28 5/29- CCR completed; TI needs to complete the design on LSV I2223 and step to ops engineering to review 5/30- informed John Please ensure end-user is aware they are responsible for ordering all circuit extensions from Switch Communications. CCR complete. clr/dlr done. Order stepped for install. 6/3- order ready and engineer informed
2013-10-11 | ShaRita | UMD10-05-IJ | 6095 Marshalee Dr Elkridge MD,21075 | Type 2 50M ethernet, 50M access SAR 1-1S9K5UD, conf 026L74-001, exp 2/16/14 iNet CP37035.00, PER 10141302 md5 UHGVERbgpbqZyofa | Smartform 190015843 NSPE0007434343 IQBKSKNT (EACS) IQBKSK6R (PORT) | 6117922 | P2047539 P2047343 (access) | 5415769 | 10800 | EDBK3HWN0001 BCBK3H6J0001 | 38/KEGS/303057//CM BLDG MAIN 2ND FLOOR SUITE 200...RACK MOUNTED | 2013-10-24 | 12/9/2013 3/6/2014 | 2014-03-12 | bpdd | 12/31/2013 3/21/2014 | 2014-03-14 | unitedhealthgroup- 64617 | 987-313-9388 anupam_datt@uhc.com |  | 11/6- pending site visit scheduling; CNR states that LCON and tech is in contact and waiting for site visit scheduling. 11/14- facilites not available; minor build. pending FOC date of 12/9 11/20- facilites not available; minor build. pending FOC date of 12/9 11/25- ASR has been jeop’d back by the LEC with comments: “CUSTOMER HAS NOT PLACED CONDUIT. EUCR form sent to John. 11/26- order on hold; awaiting customer to provide date conduit will be in place 12/5- Estimated completion of our construction with LEC was moved to 12/20 with the conduit, pending customer conduit 12/12- pending customer conduit 12/19- pending site readiness; Per customer contact Bill Smith 410-379-3443, customer has not placed conduit and has no idea when it will be placed. 12/31- pending site readiness 1/9- pending site readiness 1/16- pending site readiness 1/22- pending site readiness 1/29- order on customer hold; pending conduit 2/6- order on customer hold; pending conduit. should be ready in the next 2 weeks. 2/18- pending new FOC date of 3/6 2/27- customer confirmed conduit work complete; pending FOC date of 3/6 3/6- pending confirmation from LEC that circuit was delivered 3/12- This is already escalated to group manager she is working with the right group on this pending completion order. They will provide us update not sooner than tomorrow.
2013-06-17 | ShaRita | OH069-02-IJ | 7755 Paragon Road Suite 106, Dayton, OH 45459 | 3072, 2xT1 md5 encryption UHGVERbgpbqZyofa | smartform 189899281 NSPE0006918264 IQBKNBJG | 5938030 | P2017494 | 5367158 | 1536 | BCBK1J0X0001 BCBK1J0X0002 | 98/HCGS/228149//OB 1ST FLR TELCO RM SHELF 3 SLOT 1 Jack Type: RJ48C 98/HCGS/228150//OB 1ST FLR TELCO RM SHELF 3 SLOT 2 Jack Type: RJ48C | 2013-06-19 | 2013-07-02 | 2013-06-26 | bpdd | 2013-07-10 | 2013-06-27 | unitedhealthgroup-65279 | 763-744-2077 robert_a_benson@uhc.com |  | 6/20- pending FOC date of 7/2 6/27- pending FOC date of 7/2 7/11- ready for activation; customer notified
2015-04-02 | ShaRita | NY165-01-IJ | 7 VERMONT DR, NEW HYDE PARK, NY 11042-1128- hub order | 500M, John will throttle down to 200M MD5 UHGVERbgpbqZyofa SMF LC connector | O-1252572 Quote ID: 191014985 Order Request 191019061 Service Order(s) [ 191034992 ] has been created for Order Request 191019061 20977898 access 20977897 port | 191034992 |  | 5588896 | 1.5M | E5001256 C5000928 | 32.KFGS.204341..NY DEMARC LOC: 1ST FL SERVER RM WALL MOUNT TAGGED IDS MAINT NBR | 2015-04-13 | 6/10/2015 7/30/15 | 2015-07-29 | BPDD (standard 5/13/2015) | 2015-06-17 | 2015-07-30 | unitedhealthgroup- 65108 | 763-744-1971 mohan_basnet@optum.com | activation scheduled for 8/11 at 9am CST Bridge 866-878-8630 Passcode 6653710 | 4/2- pending pricing validation 4/9- pending lcon verification before proceeding with order submission 4/16- order submitted and approved by provisioning. ASR sent, pending FOC date. 4/23- Pending site readiness, requirements forwarded to John. FOC date 6/10 but subject to change if requirments are delayed. FOC is far out because facilities are not available. 4/24- ShaRita checking with engineer on EUCR address (it reflected 7 Deleware) 4/30- LEC engineer confirmed Site survey was done at 7 Vermont Dr with the Lcon. Pending site readiness. FOC date 6/10 but subject to change if requirments are delayed (CRD 5/1) 5/7- pending site readiness, scheduled to be done 5/22 5/14-pending site readiness, scheduled to be done 5/22 5/26-pending site readiness 6/4- pending site readiness 6/11- pending site readiness 6/17- pending site readiness 6/18- site now ready. need to get signed EUCR form 6/22- Site readiness form received, asked provisioning to proceed with the order, pending new FOC. 6/25- customer site is still not ready, lcon advised site will be ready 7/17. new FOC date 7/30 7/2- Confirmed with engineer site is ready, FOC date 7/30 7/9- FOC date 7/30 7/17-FOC date 7/30 7/23- FOC date 7/30 7/30- ready for activation, customer notified
2015-05-05 | ShaRita | CA013-02-IJ | 7 Technology Drive, irvine, CA 92618- hub order | 100M, John will throttle down to 50M Optical SMF LC deliver to building DMARC FD enabled Md5 UHGVERbgpbqZyofa | O-1296128 Quote ID: 191142199 Order Request 191142788 COX Service Order(s) [ 191169163 ] has been created for Order Request 191142788 21063799 acccess 21063798 port | 191169163 |  | 5600493 | 1500 | E4004700 C1020906 | 12.KFGX.000327..COXC. overture back to the data room rack two u-18, reconnected the fiber from the Cox NID to the patch panel #2 | 2015-05-12 | 2015-06-09 | 2015-06-09 | BPDD, may be expedited (standard 6/18) | 2015-06-16 | 2015-07-17 | unitedhealthcare- 64874 | 763-744-1957 ranjit_adhikari@optum.com | Didn't go on 7/31, RNH order | 5/5- sent to ShaRita 5/7- ShaRita working on order 5/12- per LEC We will update our records to reflect the 7 Technology location, pending FOC date 5/26- FOC date 6/9 6/4- FOC date 6/9 6/11- circuit delivered, pending line testing with LEC 6/17- Customer has not responded to the dispatcher call for Access. Kindly follow up with customer to respond back to the VM for Access 6/24- John indicated Tim is the correct contact. Supping for re-dispatch.; 6/25- CONFIRMED WITH LCON TIM 6/26 10AM PDT access for beas installation 7/2- Beas-box is online howeverthese two things were determined. • The Fiber extension is faulty from MPOE to customer demark. • The Beas box has been moved back to MPOE. • Field tech notified local contact James to get the fiber extension fixed. 7/9- pending BEAS install 7/17- ready for activation, customer notified
2015-06-17 | ShaRita | none | 48 MONROE TPKE # 1 TRUMBULL CT 06611 | disconnect | OQBK6WWC |  |  |  |  | mci10151 mci28531 u263530 | [6 empty] | 2015-07-30 |  |  |  | 7/9- pending disconnect due date 7/9 7/30- Orders soft disconnected. ShaRita will confirm the biling stop date is 7/9 8/5- disconnect complete 7/30
2015-05-13 | ShaRita | CA168-02-IJ | 13930 Seal Beach Blvd Seal Beach, CA 90740- VZT | 100M, John will throttle down to 10M Optical SMF LC | O-1302877 Quote ID: 191186607 Order Request 191186829 | 191201405 |  |  | 1.5M | [5 empty] | BPDD (Standard 6/30) |  |  | unitedhealthcare- 64853 | 210-877-7919 chris_spoor@optum.com |  | 5/14- submitted to ShaRita 5/26- site survey scheduled for May 28th 6/4- Customer has not provided a CRD for their end user contingencies(EUCR) 6/11-Customer has not provided a CRD for their end user contingencies(EUCR) 6/18- still waiting on the EURC form to be returned with CRD. Order on standstill. 6/25-still waiting on the EURC form to be returned with CRD. Order on standstill. 7/2- still waiting on the EURC form to be returned with CRD. Order on standstill. 7/9- still waiting on the EURC form to be returned with CRD. Order on standstill. 7/17- still waiting on the EURC form to be returned with CRD. Order on standstill. 7/23- still waiting on the EURC form to be returned with CRD. Order on standstill. 7/30- advised John, order will be cancelled if CRD not provided before COB Friday, July 31st 8/3- order now cancelled, customer advised to re-issue once site requirements are complete.
2015-04-17 | ShaRita | PA014-01-IJ | 52 East Swedesford Road, Malvern PA 19355- Hub order | 500M, John will throttle down to 50M Md5UHGVERbgpbqZyofa SMF LC | O-1278928 Quote ID: 191079202 Order Request 191079441 Service order 191088404 21023147 access 21023146 port | 191088404 |  | 5594874 | 30000 | C5000960 E5001345 | 11.KFGS.303504..PA 1ST FLR DATA ROOM WALL MOUNTED TAGGED | 2015-04-29 | 2015-06-05 | 2015-06-04 | 5/29/15 Standard Interval. | 2015-06-12 | 2015-06-05 | unitedhealthgroup-64886 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@optum.com | activation scheduled for 8/10 at 7pm CST Bridge 866-878-8630 Passcode 6653710 | 4/17- sent to ShaRita 4/23- site survey scheduled for 4/24 4/30- pending FOC date 5/7- FOC date 6/5 5/14- FOC date 6/5 5/26- FOC date 6/5 6/4- FOC date 6/5 6/11- READY FOR ACTIVATION CUSTOMER NOTIFIED
2015-04-28 | ShaRita | NY040-05-IJ | 77 Water Street, New York, NY 10004- Hub site | 100M, John will throttle down to 40M Optical MMF LC | SFDC# O-1291722 Service Order(s) [ 191120544 ] has been created for Order Request 191119755 21115037 access 21115036 port | 191120544 |  | 5605423 | 3.5M | C1021429 E4004950 | 32.KFGS.204758..NY 14 th flr data room..RACK #1, POSITION #35 | 2015-05-27 | 8/11/2015 7/27/2015 | 2015-08-03 | BPDD | 2015-08-20 | 2015-08-03 | UnitedHealthGroup-65159 | 763/694-7370, masroor_khan@optum.com | activation scheduled for 8/18 3pm CST Bridge: 866-692-3158 Passcode: 9236734 | 4/30- pending lcon verification 5/7- pending site survey, scheduled for 5/11, rescheduled for the 20th due to LCON not being available. FOC dependant on site survey. 5/14- site survey rescheduled for next week, Wednesday, May 20th at 1130am 5/26- pending site readiness, requirements forwarded to customer. 5/28- pending site readiness, FOC date 8/11/2015. 252PLACE AND SPLICE FIBER >2,500';PLACE AND SPLICE FIBE 6/4- per John site should be ready by June 6th. 6/11- customer confirmed site is now ready. awaiting confirmation from LEC if FOC date will remain 8/11 6/17- FOC date 8/11 6/25- FOC date 8/11 7/2- FOC date 8/11 7/9- FOC date 8/11, work to start on the 14th. Originally 6/26 and 7/1, construction is set to complete 7/24 7/17- supp'ed order to relect expedite with due date of 7/30, pending new FOC date. 7/21- New FOC of 7/27 7/30- tech scheduled to install circuit today, 7/30 8/5- ready for activation, customer notifed
2015-05-12 | ShaRita | CA006-02-IJ | 10601 Walker St Cypress, CA 90630- AT&T | 100M, John will throttle down to 20M Optical SMF LC 2nd fl MDF | O-1301267 Quote ID: 191174434 Order Request 191175171 21091712 access 21091711 port | 191190660 |  |  | 1.5M | E4004872 C1021272 | 13/KRGN/584063//PT | 2015-05-21 | 2015-06-10 | 2015-06-09 | BPDD (standard 7/1) | 2015-06-17 |  | unitedhealthcare- 64868 | 443-853-3646 edward.mclaughlin@optum.com |  | 6/4- FOC date 6/10 6/11- circuit delivered, pending demarc extension 6/18- still pending dmarc extension 6/25- Per Brendan- still working with our cable vendor to place the fiber cable required. As soon as we have a completion date, I’ll get that to you. 7/2- pending demarc extension 7/9- pending demarc extension 7/17- pending dmarc extenstion 7/23- pending demarc extension 7/30- pending demarc extension 8/5- pending demarc extension ***Date needed to avoid cancellation*** 8/13- sent email to John informing him that order will be cancelled Monday, 8/17 if extension due date not provided by COB Friday, 8/15 8/19- pending order cancellation completion 8/27- order cancelled
2015-05-12 | ShaRita | CA020-02-IJ | 15785 Laguna Canyon Rd, Ste 310 Irvine, CA 92618- Cox | 100M, I will throttle down to 10M Optical SMF LC 3rd fl MDF | O-1301317 Quote 191175299 Order Request 191175610 21092482 access 21092481 port | 191190662 |  |  | 1.5M | E4004894 C1021313 | 12.KFGX.000332..COXC. | 2015-05-21 | 2015-06-26 |  | BPDD (standard 7/1) | 2015-07-06 |  | unitedhealthcare- 64856 | 210-877-7919 chris_spoor@optum.com |  | 6/18- pending building access agreement to be signed. Need by tueesday or FOC will no longer be valid 6/24- since building access agreement wasn't signed, FOC was lost. When BAA comes back signed they will mark it first available. That means if another installation cancels or gets finished faster than anticipated, we will have the ability to bring in this install. The only downside is a date and time cannot be guaranteed ahead of the official PTD and FOC. 7/2- order on hold, still pending loop delivery and need a new date coming from LEC. LEC is pending signed Building Access Agreement coming from the customer 7/9- order on hold, still pending loop delivery and need a new date coming from LEC. LEC is pending signed Building Access Agreement coming from the customer 7/23- order on hold, LEC is still pending signed Building Access Agreement coming from the customer 7/30- order still on hold, LEC is still pending signed Building Access Agreement coming from the customer 8/5- order still on hold, LEC is still pending signed Building Access Agreement coming from the customer ***need date agreement will be signed/retured to avoid cancellation*** 8/13- sent email to John informing him that a date is needed when document will be signed/returned before COB tomorrow, if not order will be cancelled Monday 8/17- pending order cancellation completion 8/27- order cancelled
2015-05-12 | ShaRita | CA067-02-IJ | 500 S. Anaheim Hills Road, Suite 206 Anaheim, CA 92807 | 100M, I will throttle down to 10M Optical SMF LC | O-1301317 Quote 191175299 Order Request 191175610 21092516 access 21092515 port | 191190702 |  |  | 1.5M | E4004878 C1021279 | 13/KRGN/584064//PT | 2015-05-21 | 2015-06-08 | 2015-06-10 | BPDD (standard 7/1) | 2015-06-15 |  | unitedhealthcare- 64873 | 763744-0981 glenn_moore@optum.com |  | 6/10- circuit delivered. Sent follow up email to John on demarc extension 6/18- Pending demarc extension. Per Brendan, This site is problematic in that there is no room at the MPOE where the circuit is currently demarc’d and we have no equipment room (MDF). We have been working with the business to overcome the situation on space, and is taking longer than initially anticipated. At this time, it will be a minimum 2 weeks (26-Jun) before a location for the BEAS maybe ready. We will need to re-visit this task at that time. 7/2- pending demarc extension 7/9- pending demarc extension 7/17- pending demarc extension 7/23- pending demarc extension 7/30- pending demarc extension 8/5- pending demarc extension ***need date to avoid cancellation*** 8/13- sent email to John informing him that order will be cancelled Monday, 8/17 if extension due date not provided by COB Friday, 8/15 8.17- pending order cancellation completion and will need to be re-issued once site is ready. 8/27- order cancelled
2015-05-06 | ShaRita | C1580-02-IJ | Xerox- 3315 Central Ave., Hot Springs AR 71913 | 50M, John will throttle down to 10M Optical MMF, LC , GIG UNI Building demarc MD5 UHGVEReccgas4Usp9 | O-1297578 Quote ID: 191150985 Order Request 191151219 Service Order(s) [ 191169984 ] has been created for Order Request 191151219 21070113 access 21070112 port | 191169984 |  | 5601164 | 1.5 | E4004754 C4001374 | 63/KRGN/096283//SW BEAS DMARC: 2nd floor telco rm, east wall port 5 , beas box 4 inches away from telco demarc | 2015-05-14 | 2015-06-03 | 2015-06-03 | BPDD (standard 6/17) | 2015-06-10 | 2015-06-09 | UHG-ECC 65479 | 763-744-2082 eric_taylor@optum.com | activation scheduled for 8/20 at 3pm CST Bridge 866-878-8630 Passcode 6653710 | 5/6- Sent ShaRIta order 5/14- ASR submitted, pending FOC date 5/26- FOC date 6/3 6/3- circuit delivered, pending demarc confirmation from John 6/11- ready for activation customer notifed
2015-04-10 | ShaRita | CO751-05-IJ | Qwest Denver Cyber Center, 8534 Concord Center Drive, Englewood, CO 80112 terminating to Connextions cage. | 200M, John will throttle down to 150M Optical MMF LC MD5 UHGVERbgpbqZyofa Building: QWEST DCC; Floor: 1; Suite:122 | O-1258050 Quote ID: 191050404 Service Order(s) [191099358 ] has been created for Order Request Order Request 191090056 21010468 access 21010467 port | 191099358 |  | 5593065 | 1.5M | E5001325 C5000949 | 40/KFFN/111246/TWCS LEC Demarc: 1st floor data center cage 11, RR 11.2, w2001 gig 016, taaged with ckt id BEAS should be placed in 11.5. ****Verizon/BEAS DMARC**** = beas installed and located 1st floor data center cage 11.5 RU39 all is labeled | 2015-04-23 | 6/1/2015 6/11/15 | 2015-06-11 | BPDD | 6/8/2015 8/7/15 | 2015-08-10 | unitedhealthgroup-64934 | 214-647-4442 donald_r_osborn@optum.com | activation rescheduled for 8/20 2/30pm CST Bridge: 866-819-9840 Passcode: 3365052 | 4/16- pending answer from John if they want to use Quest access or Time Warner 4/21- John said to proceed with Time Warner 4/23- order submitted to provisioning 5/14- FOC date 6/1 5/26- FOC date 6/1 6/4- FOC has been Push from 6/1 to 6/11. LEC Status : Per Adam, the order was canceled and re-added to a different order LEC order #: 8118007 and the due date was pushed-out to 6/11. 6/11- circuit delivered, pending line testing with LEC and scheduling of beas installation 6/17- pending confirmation from John if circuit will be extended 6/25- awaiting confirmation on circuit extension 7/2- John confirmed demarc extending, pending scheduling of bea dispatch, circuit extended to cage 16 7/9-pending scheduling of beas installation 7/17- beas dispatch incomplete due to extension not in our cabinet 11.5. Sent email to TW seeking help with the order, advised customer is asking if they will go out and connect in 11.2 on top of rack. 7/23- Awaiting response from TW in regards to dispatch. Order is on Manager’s escalation with Time Warner. 7/30- pending scheduling of beas installation. TW did cross connect today 8/5- received notification that beas failed during software updated. Data center wont' touch equpment because of liability. Disptach to reboot BEAS for Friday 8/7 8/12- ready for activation, customer notified
2015-07-22 | ShaRita | NV039-02-IJ | 2239 Crestline Loop, Las Vegas NV 89030- Cox | 100M Copper, RJ45 Building demarc MD5 UHGVERbgpbqZyofa BFD gig uni | O-1356527 Quote ID: 191513706 Order Request 191514639 Service Order(s) [ 191535182 ] has been created for Order Request 21348364 access 21348363 port | 191535182 |  | 5628542 | 20M | C1024065 E4005868 | 33.KFGX.000947..COXC DEMARC LOC: south data center, 1st floor, telco rack | 2015-07-31 | 2015-08-21 | 2015-08-12 | bpdd (standard 9/16) | 2015-08-28 | 2015-08-18 | unitedhealthgroup-64826 | 702-242-7654 tauoa.falo@optum.com | activation scheduled for 8/26 at 10pm CST Bridge 866-878-8630 Passcode 6653710 | 7/30- order submitted to provisioning, pending ASR submission 8/5- FOC date 8/21 8/13- circuit delivered, asked John if circuit will be extended pending feedback 8/19- ready for activation, customer notified
2015-05-06 | ShaRita | CA768-02-IJ | UHG - Monarch, 2301 W. 120th St, Hawthorne, CA 90250- hub | 150M, I will throttle down to 100M Optical SMF LC md5 UHGVERbgpbqZyofa BFD enabled | O-1297397 Quote ID: 191150812 Order Request 191152439 Service Order(s) [ 191170143 ] has been created for Order Request 191152439 21072407 access 21072406 port | 191170143 |  |  |  | E4004766 C4001383 | 13/KRGN/583953//PT Demarc: demarc: cus cage, 1st flr data room, rack 2, top. Data center extended smf to fiber panel in cus cage rack 1 | 2015-05-15 | 2015-06-01 | 2015-06-02 | BPDD (standard 6/17) | 2015-06-08 | 2015-08-19 | unitedhealthcare- 65011 | 210-877-7919 chris_spoor@optum.com | activation scheduled for 8/28 at 11pm CST Bridge 866-878-8630 Passcode 6653710 | 5/6- Sent ShaRIta order 5/14- order submitted to provisioning 5/18- ASR submitted, pending foc 5/19- FOC 6/1 5/26- FOC 6/1 6/4- circuit delivered, pending demarc extension 6/11- demarc not extended, beas installation scheduled for 6/12 6/17- beas installation incomplete, awaiting customer to reschedule. order on hold No access. Security stated that these arrangements are the responsibility of the customer. Arrangements will also need to be made to have the circuit extended by data center staff to the customers rack/cage. Once we have confirmation of these requirements, we may return. Proceed to site and spoke with security. This is a secure data center and a temporary access ticket must be opened with building security with the techs name and date/time of arrival. Security had no record expecting my arrival and access was denied. 6/25- Dispatch scheduled for Friday, 6/26 @ 1pm PT. Access arranged with security for Matt Webb : Ticket: 202647488 with AT&T 6/26- I will need to re-group on the approach to the BEAS installation for this location. The site is currently working towards a new cage, and respective circuit extension. Please anticipate ~2 weeks before a date can be provided. 7/2-pending demarc extension 7/9- pending demarc extension 7/17- pending demarc extension 7/23- pending demarc extension 7/30- awaiting confirmation of beas installation 8/5- pending demarc extension ***Date needed to avoid cancellation*** 8/10- extenstion completed Monarch is; Cage#46 (Site#023705) in reference for your tech. 8/12- beas installation scheduled for 8/13. 8/19- ready for activation, customer notified
6/11//15 | ShaRita | GA010-02-IJ | 1850 Parkway Place, Suite 1025, Marietta - Parkway GA 30067- LEC comcast- RNH Phase 2 | 1G, I will throttle down to 400M Optical MMF LC | Order Request 191299459 has been generated for the Quote 191298679 Service Order 191326779 created for Order Request 191299459. 21206066 access 21206065 port | 191326779 |  | 5613296 | 1.5M | E5001575 C0055697 | 30.KFGS.025741..CBCL.. DMARC: 10th fl. Data Rm., Telco Cabinet, R.R.101.2, Bay F2 56, Equipment Rack, Chest High, On verizon Overture 400 Beas Box, Lavel for Unithed HealthCare Services, On Fiber port 0.1, Multimode 850nm, LC Connector Hinterface, Tagged Not Extended, | 2015-06-18 | 7/24/2015 8/28/15 | 2015-08-17 | BPDD | 2015-08-28 | 2015-08-21 | unitedhealthgroup-64829 | 763-744-1971 mohan_basnet@optum.com | activation scheduled for 9/1 at 830pm CST Bridge 866-878-8630 Passcode 6653710 | 6/11- ShaRita working on order 6/17- order submitted to provisioning 6/25- FOC date 7/24 7/2- FOC date 7/24 7/9- FOC date 7/24 7/17- FOC date 7/24 7/23- FOC date 7/24 7/30- As per LEC there is an Shortage of equipment due to which the loop could not be delivered and they would send us an revised FOC. The FOC is revised to 8/28. Have escalated to get the dates improved., awaiting response . 8/5- FOC date 8/28 8/13- FOC 8/28 8/19- informed John that The tech has tried to get in touch with the LCON for two days but LCON is not returning their calls. We are placing this order on Jeopardy for customer issue. Kindly provide us a valid LCON. 8/27- ready for activation, customer notified
2015-06-05 | B end- Varun | AU548-02-IJ | Level 3, 173 Strickland Crescent, Deakin Canberra, Australia 2600 | 10mg Ethernet with Dport SOO to elbourne - circuit ID W0X83226 | S/o 5725041 - 5725042 Port & Access. |  |  |  | 1536 | W1B94584 (port) W1B94585 (access) | Access provider is Telstra |  |  |  | BPDD |  |  | unitedhealthgroup-64835 | (63)2 5885331 kevin_cantor@optum.com |  | 6/5- pending SOF 6/16- SOF with UHG. 7/10- SOF with UHG 7/13- SOF received. 7/16- pending SOF info 7/23 pushing Varun for s/o info 7/24- SO received and order in TEV. 7/30- pending LCON verification/TEV 8/5- RESPONSE FROM NICK FOROSTENKO: PLEASE CONTACT VERIZON REGARDS THIS SERVICE. THE PROJECT HAS BEEN DELAYED UNTIL NEXT YEAR. Asking John if we should cancel 8/20- order will be cancelled. Asking John what we should do. John sent cancellation charges past the project team. 9/4- per John order is cancelled
2015-05-28 | ShaRita | n/a | Connextions- Richmond VPN add | VPN Add | CW Order ID 191233885 NSPE0009327764 CQBK6JJ7 CQBK6JJ8 NSPE0009456384 CW Order ID [ 191432384 CQBK6XQ5 | 8380680 8423251 | P1837463 P1838876 | 2048025 |  | Ckt - BCBKK1FD0001-2048025 |  |  |  |  | BPDD |  |  | UHGECC-65408 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 5/29- submitted to ShaRita 6/4- order submitted to provisioning 6/16- checking the install order IQBJTKSK, we don’t have enough space for the new additional request since current speed of install order is 70m and its port speed is full to 70 M also. Order was cancelled and order to downgrade port first to 35mg issued. Order submitted. 6/17- ready for hotcut for downgrade, customer notified 7/2- downgrade complete, ShaRita working on submitting order to add VRFLPORT 7/9- Melissa submitted order to add VRLPORT 7/17- order submitted to provisioning 7/23- ready for hotcut, customer notified 9/10- Order complete cancelled. per John, Please cancel request to add the UHGECC VPN. We still need the Richmond circuit active with Connextions.
2015-05-05 | ShaRita | CA767-01-IJ | 17400 Von Karman Ave, Irvine, CA 92614- Hub order- Time warner | 500M, John will throttle down to 200M Optical SMF LC, deliver to building DMARC FD enabled Md5 UHGVERbgpbqZyofa | O-1296089 Quote ID: 191141645 Order Request 191141881 Time Warner Service Order(s) [ 191169020 ] has been created for Order Request 191141881 21067605 access 21067604 port | 191169020 |  | 5601014 | 1.5M | E5001431 C5001007 | 1L/KFFN/000006/TWCS VZB DMARC: Installed overture in the customer's data cage 1st RR top Rear. THE Time Warner circuit has not been extended. The Data center will extend Single Mode Fiber crossconnects to patch panel in the customer's cage. | 2015-05-15 | 2015-06-11 | 2015-06-11 | BPDD, may be expedited (standard 6/18) | 2015-06-18 | 2015-09-10 | unitedhealthcare- 64874 | 763-744-1957 ranjit_adhikari@optum.com | Per Ranji activated on 0/14 | 5/26- Pending FOC date, FOC SLA for LEC Timewarner 10BDs. 6/4- FOC date 6/11 6/11- FOC date 6/11 6/17- circuit delivered, pending demarc confirmation from John 6/25- Beas installation was Cancelled, see tech remarks. “ The Time Warner circuit has not been extended. The Data center will extend Single Mode Fiber crossconnects to patch panel in the customer's cage.” 7/2- pending demarc extension 7/9- pending demarc extension. Per customer, We are still working on ordering the cross connect., x-con should be complete 7/.16 7/17- pending dmarc extension...Per customer, The entity is working with the Co-Lo to complete the cabling. I do not have a date as to when this will happen, but at least we now have the go ahead to move forward. 7/23- pending demarc extension 7/30- pending demarc extension 8/5- pending demarc extension ***Date needed to avoid cancellation***, data center asked for LOA. Melissa Provided 8/13- John confirmed demarc extending. pending location of extension to proceed with beas installation 8/19- demarc extended and location received, requested beas installation to be scheduled 8/27-Dispatch called Mark but was provided another person for dispatch to contact. The number Mark gave was to call Harry Kwok at 9096058088. He seemed very confused and said that the circuit dispatch gave him is not the same one and that an extension still needs to be done. Dispatch spent quite a bit of time with him on the phone and got nowhere. 9/3- Tech has already installed overture in the customer's data cage 1st RR top Rear but BEAS box is still not pingable upon checking.. it appears we still need to send out a tech on site to configure this one. Pending scheduling of dispatch 9/13- ready for activation, customer notified
2015-07-22 | ShaRita | none | 24 Albion Road,Bui lding 400, Lincoln,R I, 02865 | disconnect | NSPE0009489673 |  |  |  |  | u318468 | [5 empty] | 2015-08-31 | 2015-09-11 |  |  |  | 8/13- order assigned, awaiting response from Kevin 1-We require all the site ids to be listed to avoid a disconnect in error. I show the following 8xT1 site ids u318468,u318469,u318470,u318471,u318472,u318473,u318474,u318475,u318476. Please advise if I have your approval to proceed with the said site ids. 2-You selected Yes for managed service. If there is associated managed service requiring disconnection, we need the DNS shortname or "G" account number (ie:G123456). 8/19- pending disconnect due date 8/31 8/27- pending disconnect due date 8/31 9/3- sent a follow up email to the disconnect team requesting status of the disconnect, pending feedback 9/11- disconnect complete
2015-05-22 | ShaRita | UFL71-05-IJ | 495 N. Keller Road Maitland, FL 32791- Level 3 | Optical MMF LC 50M, John will throttle down to 20M | O-1312016 Quote ID: 191219121 Order Request 191219861 Service Order 191234425 created for Order Request 191219861 21142778 access 21142777 port | 191234425 |  |  | 4M | E4005067 C4001494 | 5S/KFFN/001009/TWCS DMARC Info: ste 200, LAN eq. room, cabinet 2, upper cabinet, BEAS box SFP in slot 1, Multi Mode LC interface, labeled. -ST-/321-229-1308 | 2015-06-03 | 2015-06-30 |  | BPDD (Standard 7/13) | 2015-07-08 | 2015-07-27 | unitedhealthgroup-64611 | 91 91600 84400 harish_kandpal@optum.com | activation scheduled for 9/15 at 5pm CST bridge 866-878-8630 pass code 6653710 | 5/28- ShaRita working on order 6/4- order submitted to provisioning, ASR submitted, pending FOC date 6/11- pending FOC date 6/17- pending FOC date 6/25- FOC date 6/30 7/2- Created late loop ticket, sent email to TW PM for status/reason on late loop delivery 7/9- LEC Status : Per Carlos/TW/LVL3 comm PM - "This order was a bit delayed due to the Internal Wiring getting cut by the local contractors. Apparently, they are downsizing and they cut our cabling. We had to force our FOC date to July 17th. This will allow us to correct the issue and delivery the circuit. Please address this with the end user and the expectations. This was not a carrier delay." Emailed Carlos/PM for an update on the progress of the order, and if there's any chance that July 17 due date could be pulled in. Pending response at this moment. Will continue escalating for resolution and completion of circuit install and turn-up. 7/17- FOC date today, 7/17. Pending LEC confirmation circuit was delivered 7/22- LEC has delivered their loop. Please advise customer of dmarc: 2nd flr customer server room wall mounted level 3 patch panel port 1 & 2 multi mode fiber sc connector. 7/24- per John circuit is installed in MDF, we may proceed with BEAS install. 7/30- ready for activation, customer notified
2015-05-12 | ShaRita | CA076-02-IJ | 31852 Coast Highway, Suite 400 Laguna Beach, CA 92651- Verizon Telecom | 100M, I will throttle down to 10M Optical SMF LC 4th fl MDF | O-1301317 Quote 191175299 Order Request 191175610 | 191190701 |  |  | 1.5M | [5 empty] | BPDD (standard 7/1) |  |  | unitedhealthcare- 64858 | 443-853-3646 edward.mclaughlin@optum.com |  | 5/26- Per LEC engineer, site survey not required, order submitted to provisioning 5/28- there was a system glitch, site survey was scheduled May 26th at 1130am. Site requirements forwarded to customer. Informed John that order is on hold until we receive a signed copy of the EUCR form with the committed a CRD. We cannot provide a service date until we receive this signed document. 6/4- pending customer ready date and returned EUCR form. Per Brendan, waiting to hear back from our local Facilities Manager on this. 6/11- pending customer ready date and returned EUCR form. Per Brendan, waiting to hear back from our local Facilities Manager on this. 6/18- still waiting on the EURC form to be returned with CRD. Order on standstill. 6/25- still waiting on the EURC form to be returned with CRD. Order on standstill. 7/2- still waiting on the EURC form to be returned with CRD. Order on standstill. 7/9- still waiting on the EUCR form to be returned with CRD. Order on standstill. 7/17- Pending customer requirements: Obtain building management approval for new VZ equipment in MPOE. 7/23- sent follow up email to engineer asking what is needed from enduser to move forward with order. pending feedback 7/30- order cancelled. Verizon does not have the IOF network in the Laguna Beach serving area to support SES services at this time.
2015-05-11 | ShaRita | TX738-01-IJ | UHG / MedSynergies 2501 S. State Hwy 121 BU#500 Lewisville, TX 75067- hub- Verizon Telecom LEC | 1G, John will throttle down to 200M, Optical MMF LC Gig UNI, Meet Me Room / Building 5 MedSynergies Cage in Data Hall 4 | O-1300301 Quote ID: 191174234 Order Request 191174412 21108113 access 21108112 port | 191190600 |  | 5605096 | 1.5M | E5001473 C0052871 | 12/KFGS/700718//GTEC first floor, building 7, section mdf3 rack mdf3-04 NID 9 PW | 2015-05-26 | 9/8/2015 8/17 | 2015-08-13 | BPDD (standard 6/25) | 2015-08-24 | 2015-08-14 | unitedhealthcare- 65012 | anthony_flesher@optum.com 763.744.1949 | activation scheduled for 9/15 at 8pm CST Bridge 866-692-3158 Passcode 9236734 | 5/12- submitted to ShaRita 5/21- Per LEC engineer, no site survey required. There will be a build required. Order submitted to provisioning, pending FOC date and build detail. 5/28- pending FOC date 6/4- pending FOC date, 65 day build required. Pending details on build 6/11- FOC date 9/8 6/17- FOC date 9/8 6/25- FOC date 9/8 7/2- FOC date 9/8 7/9- FOC date 9/8 7/17- supp'ed order to relect expedite with due date of 7/30, pending new FOC date. 7/23- new FOC date 8/17 7/30- FOC date 8/17 8/5- FOC date 8/17 8/12- FOC 8/17 8/19- ready for activation, customer notified
2015-05-26 | ShaRita | VA016-06-IJ | UHG / Lewin 3130 Frairview Park Drive Suite 500 Falls Church,VA 22042- RNH order | Gig UNI - Optical SMF LC 500M, john will throttle down to 200M | O-1312026 Quote ID: 191220128 Order Request 191220241 Service Order(s) [ 191234066 ] has been created for Order Request 191220241 new Quote ID: 191338403 for vpn change Order Request 191354781 service order id 191383459 21249709 access 21249708 port | 191234066 191383459 |  | 5618045 | 1.5M | E5001640 C5001110 | 36.KFGS.303836..CD lec dmarc DEMARC LOC: basement main phone room, wall mount pos 1, Isg400 installed 6th fl, server rm 6001, top of customer rack, port 1, BEAS DMARC: 6th fl, server rm 6001, top of customer rack, port 1 | 2015-07-01 | 7/30/2015 7/23/2015 | 2015-07-23 | BPDD (Standard 7/13) with vpn add 8/7 | 2015-08-06 | 2015-08-06 | unitedhealthgroup-64840 | 763-744-1957 ranjit_adhikari@optum.com | activation scheduled for 9/21 at 730pm CST Bridge 866-692-3158 pass code 9236734 activation scheduled for 8/20 at 730pm CST Bridge 866-878-8630 Passcode 6653710 | 5/28- ShaRita working on order 6/4- early site survey scheduled for 6/11 6/11- pending cancel/reissue, customer would like to additional VPN 6/18- Order has been at a standstill due to no response to complete the early site survey. John will re-issue with dual vpn 6/22- new order issued with dual VPN. Per site contact The site survey was completed on 6/12, by Charles Herold, (703) 212-5278, charles.l.herold@one.verizon.com 6/25- site survey completed, ShaRita is working on submitting reissued order and will cancel old 7/2- order submitted to provisioning 7/9- FOC date 7/30 7/17- : ******RE-FOC RECEIVED******* 07/23 7/23- FOC date today, 7/23 7/24- delivered, pending dmarc extension. DEMARC LOC: basement main phone room, wall mount pos 1, 7/30- pending dmarc extension 8/3- Circuit extended. MDF, 6th floor – Room 6001 8/5- beas installation complete. RFC test failing, awaiting TT to be resolved 8/6- ready for activation
2015-07-10 | ShaRita | MS010-07-CJ | 795 Woodlands Parkway, Suite 301, Ridgeland, MS 39157 AT&T access | Upgrade from 4xT1 to 8xT1 BCBKV60X0001-4 | O-1347049 CW Order (ID : 191443214 NSPE0009463402 IQBK62F8 in OQBK620N out | 8425301 |  | P2117496 in P1992050 out | 4608 | BCBK8T5X0001-0008 in BCBKYXLP0001-0004 out | BCBK8T5X00050005 --- DEMARC LOC: 3RD FLOOR TELCO ROOM WALL MOUNT DEMARC LOC Continued: SLOT 1 --- BCBK8T5X00060006 --- DEMARC LOC: 3RD FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 2 --- BCBK8T5X00070007 --- DEMARC LOC: 3RD FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 3 --- BCBK8T5X00080008 ---- DEMARC LOC: 3RD FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 4 EW Reason/Location:NOT ORDERED Jack Type: RJ48C | 2015-08-03 | 8/14/2015 9/14/15 |  | bpdd | 2015-09-21 |  | unitedhealthgroup-64713 | 763/694-7370, masroor_khan@optum.com | activation scheduled for 9/24 at 7pm CST bridge 866-692-3158 passcode 9236734 | 7/17- ShaRita working on order 7/23- internal ticket open unable to query Service ID for related in/out. Once ticket is resolved will submit request to order entry 7/30- ticket resolved, order submitted to provisioning. 8/5- pending construction for facility. No ECD as of yet. Estimated FOC 8/14 8/12- New FOC 9/14 Per email received from telco, “There is a construction build necessary in order to complete your order. Escalations on builds are only being done in emergency situations. The ESD 9/14/15 has been provided so we ask that you kindly wait until after that date for status. AT&T will contact you if additional information is required. This will allow our network staff time to focus on that job and give them time to meet that date. It will also allow our service reps time to continue typing your new orders that come in daily. Once construction is complete and the order gets designed, my team is notified and you will be provided a less than standard (7days) interval of a 5 day due date for installation to be completed. If you want less than that less than standard interval you need to SUP your PON with EXP=Y and the DDD you are now requesting. At that time we can see if your requested date can be obtained.” 8/19 - FOC 9/14 8/27- FOC 9/14 9/3- READY FOR HOTCUT, customer notified
2015-05-19 | ShaRita | FL751-05-CJ | Address: 11300 NW 25th Street MIAMI FL USA 33172 need by the end of august. Telefonica- level 3 | Please place an order for an inside move for the below. The circuit is currently in Server Room 4 on the first floor and needs to be moved to Server room 2 on the first floor. | Quote 191248301 service group 34987009/34987010 Order Request 191248980 service order id 191318580 Order request 191318623 service order id 191318680 21227752 access IN 21227751 port IN 21197029 access OUT 21197028 port OUT | 191318580 (in) 191318680 (out) |  | 5615663 | 50M | C4001645 /E4005390 (in) C1003370 /E4000576 | 60/OBGS/750794//SB lEC dmarc DMARC Information: 1st flr TC-3-7 rack mount unit 2 panel 13 port 16 1007FLYW-BBPF48850 11300 NW 25TH ST - MIAMI, FL Customer Dmarc: Alcatel labeled mes101.mia18 port 15 DMARC Info: customer data cage. Rack AD3 above routers. Labeled with Vz circuit id. | 2015-06-25 | 2015-08-10 | 2015-07-31 | BPDD (standard 7/14) | 2015-08-17 | 2015-09-16 |  | 763.744.0981 glenn_moore@Optum.com | activation scheduled for 9/18 at 9am CST Bridge 866-692-3158 Passcode 9236734 | 6/2- submitted order to ShaRita 6/4- ShaRita workinng on order 6/11- ShaRita will submit order today 6/17- order submitted to provisioning,but stuck in progress. TT opened Ticket: T1906620. Pending resoultion. Also, informed John new circuit will be installed bacause VRD does not support move orders 6/25- ticket resolved, ASR submitted to LEC. Pending FOC date. 7/2- pending FOC 7/9- pending FOC 7/17- FOC date 8/10 7/23- FOC date 8/10 7/30- FOC date 8/10 8/5- BEAS installation scheduled 08/07 @ 11:00 AM, loop delivered 7/31 8/13- requested tag and locate for customer 8/19- Tag and locate ticket# 9604773 with Level 3 has been opened; pending Tech assignment. 8/27- escalated request for a vendor meet with LEC (Level 3), they have yet to reply for their techs availability. 9/3- customer was able to find dmarc and now working on extension 9/9- Per John extension complete. extended to Server Room 2 Rack AD6 Dmark Patch Panel port Port 9. Order supp'ed pending scheduling of bea install 9/14- BEAS installation scheduled tomorrow 09/15 at 2:00 PM local. 9/15 issues with access. Need John to send an e-mail to the data center to add our techs name to the access list before we can step order for re-dispatch. 9/16- ready for activation, customer notified 9/24- activation completed, pending disconnect completion of the out order 9/30- No access. This is a data center. Customer must plave VZ tech on access list before redispatching
2015-05-13 | ShaRita | CA192-02-IJ | 800 Corporate Way, Suite 100 Ladera Ranch, CA 92694 Cox | 100M, John will throttle down to 10M Optical SMF LC | O-1302877 Quote ID: 191186607 Order Request 191186829 21092613 access 21092612 port | 191201374 |  |  | 1.5M | E4004882 C1021284 | 12.KFGX.000335..COXC. LEC DEMARC : MPOE is located inside the building on 1st Floor, in Telco/Electrical room. Accedian mounted in D/C Rack Fiber handoff SFP-B 1310nm SMF to fiber termination panel above Accedian NID. | 2015-05-21 | 7/29/2015 8/6/15 | 2015-08-10 | BPDD (standard 7/1) |  |  | unitedhealthcare- 64861 | 763744-0981 glenn_moore@optum.com |  | 7/2- FOC date 7/29 7/9- FOC date 7/29 7/17- FOC date 7/29 7/23- FOC date 7/29 7/30- There were internal delays within Cox in regards to the scheduling of contractors to finalize fiber splicing, FOC date of 08/06/2015 8/5- FOC to 08/06 due to construction completion delay 8/12- circuit delivered, awaiting demarc confirmation from John 8/19- awaiting demarc confirmation from John 8/27- pending demarc extension 9/3- order on hold, pending dmarc extension ***to avoid cancellaton demarc has to be extended by 9/21*** 9/10- order on hold, pending dmarc extension ***to avoid cancellaton demarc has to be extended by 9/21*** 9/17- order on hold, pending dmarc extension ***to avoid cancellaton demarc has to be extended by 9/21*** 9/24- order supp'ed to cancel, pending cancellation completion. informed John, This is due to the lengthy hold on this order, 30 business days, without providing confirmation of demarc extension as well as provide extended dmarc location. Please reissue once this site has been confirmed ready. 10/1- pending cancellation completion 18/8- order complete cancelled
2015-05-13 | ShaRita | CA062-02-IJ | 5977 East Spring Street Long Beach, CA 90808- VZT | 100M, John will throttle down to 10M Optical SMF LC | O-1302877 Quote ID: 191186607 Order Request 191186829 21172571 access 21172570 port | 191201406 |  |  | 1.5M | E4005160 C1021889 | 81/KFGS/501756//GTEW | 2015-06-09 | 2015-08-14 |  | BPDD (Standard 6/30) |  |  | unitedhealthcare- 64854 | 210-877-7919 chris_spoor@optum.com |  | 7/17- FOC date 8/14 7/23- FOC date 8/14 7/30- FOC date 8/14 8/5- FOC date 8/14 8/12- revised FOC 10/15 8/19- informed by the LEC that CUSTOMER NEEDS TO PROVIDE 75 FT OF CONDUIT.” 8/27- order on hold, awaiting customer to provide conduit 9/3- order on hold, awaiting customer to provide conduit ***to avoid cancellaton site readiness confirmation is needed by 10/1*** 9/10- order on hold, awaiting customer to provide conduit ***to avoid cancellaton site readiness confirmation is needed by 10/1*** 9/17- order on hold, awaiting customer to provide conduit ***to avoid cancellaton site readiness confirmation is needed by 10/1*** 9/24- order on hold, awaiting customer to provide conduit ***to avoid cancellaton site readiness confirmation is needed by 10/1*** 10/1- order will be cancelled due to the lengthy hold on this order, 30 business days, awaiting conduit to be provided. 10/8- order complete cancelled
2015-05-13 | ShaRita | CA022-02-IJ | 29873 Santa Margarita Pkwy, Suite 100 Rancho Santa Margarita, CA 92688- cox | 100M, John will throttle down to 10M Optical SMF LC | O-1301832 Quote ID: 191181221 Order Request 191182081 21092569 access 21092568 port | 191201338 |  |  | 1.5M | E4004880 C1021282 | 12.KFGX.000333..COXC. DMARC INFO:1st flr.,suite 100 cox rack acedian metronid hand off port sfp b VZ Demarc: Installed overture in the IMPOE cross from the customer's equipment and above COXC equipment. | 2015-05-21 | 7/30/2015 8/13/15 | 2015-08-14 | BPDD (standard 7/1) |  |  | unitedhealthcare- 64849 | 210-877-7919 chris_spoor@optum.com |  | 7/23- FOC date 7/30 7/30- pending confirmation for LEC that circuit has been delivered. 8/5- LEC Status: Per email received from Brandon/Cox PM,we had to re-FOC this install on 7/8 to push it out to 8/13 due to construction not completed yet. As of now we are still working with our contractor to bring proper power in to the room to support our equipment. Once the power is brought in and finished, we will be on track to deliver by our FOC date of 8/13 with a PTD/Plant Test Date of 8/12. 8/12- FOC 8/13 8/19- circuit delivered and beas installation complete 8/27- order on hold, pending demarc extension 9/3- order on hold, pending demarc extension. ***to avoid cancellation need confirmation that demarc is extended by 9/23*** 9/10- order on hold, pending demarc extension. ***to avoid cancellation need confirmation that demarc is extended by 9/23*** 9/17- order on hold, pending demarc extension. ***to avoid cancellation need confirmation that demarc is extended by 9/23*** 9/24- order supp'ed to cancel, pending cancellation completion. informed John, This is due to the lengthy hold on this order, 30 business days, without providing confirmation of demarc extension as well as provide extended dmarc location. Please reissue once this site has been confirmed ready. 10/1- pending cancellation completion 10/8- Order complete cancelled
2015-06-12 | ShaRita | VA726-02-IJ | 22451 Shaw Road Sterling VA 20166- RNH order- VZB | 1G, I will throttle down to 400M Optical SMF LC | Service Order(s) [ 191326860 ] has been created for Order Request 191312979 21200751 access 21200750 port WDC I126529 | 191326860 |  |  | 1.5M | C0056130 E5001563 | easaw saw 0006 left loop up on card 3 port 1 labeled with the circuit id |  |  |  | BPDD 8/4/15 (standard 30 business days) | 2015-09-10 | 2015-09-01 | unitedhealthgroup-64827 | 763-744-1957 ranjit_adhikari@optum.com | activation scheduled for 10/8 at 9pm CST Bridge 866-692-3158 Passcode 9236734 | 6/16- order submitted to provisioning 6/25- sent follow up email to provisioning requesting that he review/approve order ASAP 7/2- order accepted, awaiting provisioning to provide valid assignment to design team 7/9- order stepped for site survey 7/17- pending ccr 1266688 CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01. ) RFT 8/19 7/23- pending ccr 1266688 (CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01.) RFT 8/19 7/30- pending ccr 1266688 (CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01.) RFT 8/19 8/5- Op’s is trying to complete this early but they are pending a call back from the LCON for access. LCON listed is Dan Sughrue, 703-773-6360 8/13- pending ccr 1266688 (CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01.) RFT 8/19 8/13- OC48 equipment in stalled and topology complete, pending closure of install, then we can proceed with ethernet provisioning 8/19- node work complete at zb0, scoped, cleaned fibers, attenuated at roadm rx -15db, labeled, ETE testing scheduled for 8/21 8/27- escalated to dispatch. Auto or Manual test did not detect hard loop.. Verify path no alarms...MX960 142.6.L2:4.0.6 LINK IS UP...Referred back to dispatch to work with testing group 9/3- order ready for activation, customer notified
2015-09-03 | ShaRita | none | 77 Water Street NEW YORK NY USA 10004 | disconnect | NSPE0009616830 OQBK7LX1 |  |  |  |  | BCBKWCVM0001-6 |  |  |  |  | 2015-09-03 | 2015-10-01 | 2015-10-06 |  |  |  | 9/3- submitted to VZB FULL DISCO OPTION 1 AND 2 9/10- pending disconnect due date 10/1 9/17- pending disconnect due date 10/1 9/24- pending disconnect due date 10/1 10/1- pending soft disconnect to take place 10/8- disconnect complete
5/12/2015 started over 5/21 change of address | ShaRita | CA189-02-IJ | Street Address1: 32312 CAMINO CAPISTRANO SAN JUAN CAPISTRANO CA | 100M, I will throttle down to 10M Optical SMF LC | O-1301832 Quote ID: 191181221 Order Request 191182081 Order Request 191209697 has been generated for the Quote 191207827 21097318 access 21097317 port | 191211112 |  |  | 1.5M | E4004901 C1021328 | 12.KFGX.000337..COXC | 2015-05-27 | 7/28/15 11/20/15 |  | BPDD (Standard 7/2) | 2015-08-04 |  | unitedhealthcare- 64864 | 763744-0981 glenn_moore@optum.com |  | 7/23- FOC date 7/28 7/30- per LEC PM The original FOC was issued before the city denied our permits to do construction. Cox had to come up with a new design that the city would allow. We then re-FOCd the order to 11/20/15. Unfortunately we are at the mercy of the City of San Juan Capistrano to complete our construction and fiber pull. As of now, the FOC will remain 11/20/15 until construction completes. If it completes ahead of schedule, Cox will pull in the installation. 8/5- FOC date 11/20 8/12- FOC 11/20 8/19- FOC 11/20 8/27- FOC 11/20 9/3- FOC 11/20 9/10- FOC 11/20 9/17- FOC 11/20 9/24- FOC 11/20 10/1- FOC 11/20 10/8- FOC 11/20 10/9- per John cancel order, order has been supp'ed to cancel 10/13- Order complete cancelled
2015-05-13 | ShaRita | CA024-02-IJ | 30110 Crown Valley Pkwy, Suite 101 Laguna Niguel, CA 92677- Cox | 100M, John will throttle down to 10M Optical SMF LC | O-1301832 Quote ID: 191181221 Order Request 191182081 21092590 access 21092589 port | 191201337 |  |  | 1.5M | E4004881 C1021283 | 12.KFGX.000331..COXC. | 2015-05-21 | 7/31/2015 9/4/15 10/16/15 |  | BPDD (standard 7/1) |  |  | unitedhealthcare- 64864 | 210-877-7919 chris_spoor@optum.com |  | of 9/4/15. 8/12- FOC 9/4 8/19- FOC 9/4 8/27- FOC 9/4 9/3- LEC Status: Received permits on 8/21. Construction is starting up and hoping to be completed mid to late September. 9/10- As per LEC PM, They're targeting for a September 18th completion date for construction. This date is subject to change due to Cox still coordinating the build and traffic control with the city. 9/17- LEC status expected complete date late September 9/24- Construction Build Fiber Build 09/25/2015 Splice Review 09/28/2015 Fiber Splice 10/01/2015 QC Build 10/08/2015 Circuit Installation Circuit Design 10/08/2015 Network Provisioning 10/12/2015 Circuit Provisioning 10/12/2015 CPE Staging 10/13/2015 Fiber Turn Up & Test 10/15/2015 10/1- FOC 10/16 10/8- FOC 10/16 10/9- per John cancel order, order has been supp'ed to cancel 10/13- Order complete cancelled
5/19/2015 started over 5/21 change of address | ShaRita | CA018-02-IJ | 30131 Town Center Dr Laguna Niguel, CA 92677- Cox | Copper RJ45 100M, John will throttle down to 10M 1st fl mdf | O-1308294 Quote ID: 191203635 Order Request 191204125 Order Request 191209697 has been generated for the Quote 191207827 access 21097417 port 21097416 | 191211114 |  |  | 1.5M | E4004903 C1021331 | 12.KFGX.000338..COXC. | 2015-05-28 | 8/7/2015 9/15/15 11/5/15 |  | BPDD (standard July 7th) | 2015-08-04 |  | unitedhealthcare- 64842 | 443-853-3646 edward.mclaughlin@optum.com |  | 7/30- FOC date 8/7 8/5- Received response from PM : The install was pushed to 09/15 due to needing excavation permits from the city. The permit has not been received yet but we are hopeful that it should be received soon and we will stay on track for our new FOC date 8/13- FOC 9/15 8/19- FOC 9/15 8/27- FOC 9/15 9/3- FOC 9/15 9/10- re-FOC'd to 11/05 due to ACCESS PROBLEMS AT IDF CLOSETS IN MID PULL LOCATION. asked provisioning if this is a LEC issue or customer issue, pending feedback. 9/17- FOC date 11/5. LEC confirmed that access issue is not in the actual site. 9/24- FOC date 11/5 9/30- FOC date 11/5 10/8- FOC 11/5 10/9- per John cancel order, order has been supp'ed to cancel 10/13- order complete cancelled
2015-05-12 | ShaRita | CA097-02-IJ | 724 S. El Camino Real San Clemente, CA 92672- COX | 100M, I will throttle down to 10M Optical SMF LC 1st fl MDF | O-1301267 Quote ID: 191174434 Order Request 191175171 21091847 access 21091846 port quote for new addres Quote ID: 191361856 Order Request 191362579 Service Order(s) [ 191379340 ] has been created for Order Request 191362579 21232562 access 21232561 port | 191190641 191379340 |  | 5617213 | 1.5M | E4005440 C1022818 | 12.VLXX.001928..COXC. | 2015-06-30 | 9/15/2015 10/28/15 |  | BPDD (standard 7/1) new standard 8/4 with address change |  |  | unitedhealthcare- 64872 | 443-853-3646 edward.mclaughlin@optum.com |  | 7/2- ASR submitted, pending FOC 7/9- Order is currently pending FOC Issuance with COX-SYN Sent email with LEC rep (Anthony) asked on when the FOC will be received on this order, pending response at the moment. Will escalate higher if needed. 7/14- FOC 9/15 due to construction 7/23- FOC 9/15 7/30- FOC 9/15 8/5- FOC date 9/15 8/12- FOC 9/15 8/19- FOC 9/15 8/27- FOC 9/15 9/3- FOC to 10/28 due to construction completion ETA 9/10- FOC to 10/28 due to construction completion ETA 9/17- FOC 10/28 9/24- FOC 10/28 10/1- construction has been pushed out due to workload to 11/6/15. This has caused our FOC to be pushed to 11/20/15 10/8- FOC 11/20 10/9- per John cancel order, order has been supp'ed to cancel 10/12-order complete cancelled
2015-08-11 | Varun | PH550-03-CJ | Upgrade W1B26074(access) W1B26059 (port) | an order to upgrade the port from 100M to 400M on the below circuit. Please schedule for 11:00pm local time(Philippines). | OVI#1-1541552720 s/o 5748531 | [9 empty] | BPDD |  |  |  |  | hotcut completed 10/6 | 8/12- sent to varun, port isn't dport. SOF is needed. 8/14- John confirmed he has the SOF 9/4- SOF returned 9/14- order ready for upgrade, asking John when he wishes to have it done.
2015-09-17 | ShaRita | n/a | Site Address: 1707 West Creek Lane Chaska MN USA 55318 | Please upgrade the commit rates on the following ISP circuit. - CTC Verizon u327321 change to 2G commit | Opp ID O-1401518 smartform 191787130 NSPE0009682981 U327321 | 8521197 |  |  |  | Circuit ID: u327321 | [5 empty] | BPDD |  |  |  |  | 9/22- pending ticket. 10/8- order submitted to provisioning 10/12- Order has been marked up and billable.
2015-04-04 | ShaRita | CA205-02-IJ | 145 Thunder Drive, 2nd Floor, Vista, CA 92083 | 100M, John will throttle down to 10M Optical SMF LC MD5 UHGVERbgpbqZyofa | O-1254296 Quote ID: 191023167 Order Request 191023303 Service Order(s) [ 191035005 ] has been created for Order Request 191023303 20982191 access 20982190 port | 191035005 |  | 5588943 | 2000 | C1019872 E4004259 | 11.KFGX.000434..COXC. | 2015-04-13 | 7/8/2015 8/14/15 |  | BPDD (standard 05/15/15) | 2015-07-15 |  | unitedhealthgroup-65126 | 210-877-7919 chris_spoor@optum.com |  | 7/23- FOC date 8/14 7/30- FOC date 8/14 8/5- FOC date 8/14 8/12- FOC 8/14 8/19- FOC 8/28. Pushed FOC out due to construction delays. 8/27- FOC 8/28 9/3- Per LEC, the construction to bring the fiber into the building had slipped a few days. Created missed loop ticket #C201509020129 9/10- order on customer hold, due to finance approval needed. ***If confirmation that finance approval has not been received by close of business on 10/15, the order will be cancelled the next business day, 10/16.*** Brandon turned them away because of the financial approval 9/17- order on customer hold, due to finance approval needed. 9/24- order on customer hold, due to finance approval needed. 10/1- order on customer hold, due to finance approval needed. 10/8- order on customer hold, due to finance approval needed. 10/9- per John cancel order, order has been supp'ed to cancel 10/12- pending cancellation completion 10/22-order complete cancelled
6/11//15 | ShaRita | NY723-02-IJ | 777 Old Sawmill Road Tarrytown, NY 10591 - VZ business- RNH phase 2 | 500M, I will throttle down to 200M Optical MMF LC | Order Request 191299459 has been generated for the Quote 191298679 Service Order 191326760 created for Order Request 191299459. 21200731 access 21200730 port whp I12492 whp C12492 | 191326760 |  |  | 1.5M | E5001562 C5001077 | ea-bsq-bsq-0013 Dmarc C level data center (ACS) , LGX panel, fibers 21-22,xconnected to MC shelf 1.2.8, position 4, sm/mm, loop left on mm handoff for testing Dmarc C level data ctr, lgx panel B, fibers 21-22, to MC shelf 1.2.8, MC card #4, MM fiber loop left for testing |  |  |  | BPDD | 8/4/2015 9/14/2015 | 2015-09-04 | unitedhealthgroup-64830 | 763-744-1971 mohan_basnet@optum.com | activation rescheduled for 10/13 at 8pm CST Bridge 866-878-8630 Passcode 6653710 | 1264898 07/28/15 pending (EBAP Standard) OV1400 @bsq,14 w/ SM GigE client in 0.1 and 0.2 and SM GigE trunk in 0.5 (RFT 7/28, material recieved) ...tech was not able to complete job Called away on pri1 trouble ticket at Sterling Forest 8/5- provisioning is reviewing order, seems to be some discrepancy on where tech delivered the circuit. there are two different access orders going to the same location. provisioning is working on assignment to match up to related order 8/13- Stiil working with provisioning to clear the discrepancy with the 2 access orders placed between Xerox and UHG 8/19- Dmarc C level server room, (another 9), vzb MC#3, slot 2. SM/MM card. MM loop left up on handoff for testing. Pushing to autotest 8/27- end to end testing complete, pending closing of order 9/3- sent email to provisioning asking them to close order ASAP 9/10- ready for activation, customer notified 9/17- change order is needed Engineer did physically install at A9/Cohere, but was told to move it because it wasn’t per the design. We need to redesign this and send him back out. 9/24- order stepped for site survey 10/1- RFC testing complete, ready for activation
2015-02-26 | ShaRita | AZ012-05-IJ | 2222 West Dunlap Ave, Phoenix, AZ 85021 | 100M Optical, MMF LC MD% UHGVEReccstr82tcW | O-1220197 Quote ID: 190865041 Order Request 190865248 Service Order(s) [ 190867484 ] has been created for Order Request 190865248 20867602 access 20867601 port | 190867484 |  | 5574047 | 30M | C1018210 E4003756 | 56/KFFN/112758/TWCS DEMARC: 1st floor MDF room. RR 4, RMU 28, port 1 | 2015-03-04 | 4/2/2015 4/10/15 | 2015-04-13 | bpdd (standard 4/13) | 2015-04-09 | 2015-04-23 | UnitedHealth Group-TCW 65426 | 952-906-1396 eric_sandberg@optum.com | activation scheduled for 10/15 at 12pm Bridge 866-769-7504 Pass code 4372840 | 3/5-pending FOC date 3/11-pending FOC date 3/19- FOC date 4/2 3/26- FOC dare 4/2 4/1- FOC date 4/2, awaiting completion notification from LEC 4/9- after confirming demarc with customer, LEC provided new FOC date of 4/10 4/16- circuit delivered, beas installation scheduled on 4/21. sent email to John/Eric to confirm demarc provided, pending response. 4/23- pending completion of beas installation, testing and closing of order 5/6- activation has to be rescheudled due to SFP mismatch
5/19/2015 started over 5/21 change of address | ShaRita | CA061-02-IJ | 1198 Pacific Coast Highway, Suite 1 Seal Beach, CA 90740- VZT | Copper RJ45 100M, John will throttle down to 10M 1st fl mdf | O-1308294 Quote ID: 191203635 Order Request 191204125 Order Request 191209697 has been generated for the Quote 191207827 21148324 access 21148323 port | 191211113 |  |  | 1.5M | E4005091 | 81/KFGS/501752//GTEW | 2015-06-04 | 2015-07-17 | 2015-07-30 | BPDD (standard July 7th) | 2015-07-24 |  | unitedhealthcare- 64843 | 443-853-3646 edward.mclaughlin@optum.com |  | 7/2- FOC date 7/17 7/9- FOC date 7/17 7/17- FOC date today, 7/17. Pending LEC confirmation circuit was delivered 7/23- LEC Loop - Escalated. Missed FOC date of 7/17. Per VZT, in service date is 07/21. 7/30- circuit delivered, pending dmarc confirmation from John 8/5- waiting on John to confirm if demarc will be extended 8/13- waiting on John to confirm if demarc will be extended 8/19- waiting on John to confirm if demarc will be extended 8/27- pending demarc extension 9/3- order on hold, pending demarc extension. ***to avoid cancellaton demarc has to be extended by 9/10*** 9/11- advised John that order is cancelled and will need to be reissued once end user is ready to proceed. 9/17- pending cancellation completion 9/24- pending cancellation completion 10/1- pending cancellation completion 10/8- pending cancellation completion 10/12- pending cancellation completion 10/22- order complete cancelled
2015-05-12 | ShaRita | CA201-02-IJ | 26131 Marguerite Parkway Ste A Mission Viejo, CA 92691 | 100M, I will throttle down to 10M Optical SMF LC 1st fl MDF | O-1301317 Quote 191175299 Order Request 191175610 21095539 access 21095538 port | 191190681 |  |  | 1.5M | E4004893 C1021312 | 12.KFGX.000334..COXC. | 2015-05-21 | 2015-07-30 |  | BPDD (standard 7/2) |  |  | unitedhealthcare- 64865 | 443-853-3646 edward.mclaughlin@optum.com |  | 7/9- FOC date 7/30 7/17- FOC date 7/30 7/23- FOC date 7/30 7/30- pending confirmation from LEC if circuit was installed 8/5- FOC date pushed out to 9/9/15 due to new construction 8/12- FOC 9/9 8/13- asked John for a valid lcon. Cox is trying to coordinate installation and fiber pull for this new order but not able to get in touch with the POCs that were provided. 8/19- order on hold pending valid lcon information from Brendan 8/27- order on hold, still need valid lcon 9/3- order on hold. valid lcon needed by 9/23 to avoid cancellation 9/10- order on hold. end user did not provide access and informed LEC they will be moving soon ***to avoid cancellation valid lcon needed by 9/23*** 9/17- order on hold. end user did not provide access and informed LEC they will be moving soon ***to avoid cancellation valid lcon needed by 9/23*** 9/24- pending cancellation completion. advised John that order is cancelled and will need to be reissued once end user is ready to proceed. 10/1- pending cancellation completion 10/8- pending cancellation completion 10/12- pending cancellation completion 10/22- pending cancellation completion 10/29- order complete cancelled
6/9/2015 change handoff 7/29 | ShaRita | C1576-01-IJ | EXL Service (Century Link Co-Lo ZZSN1) 1400 Kifer Rd. Sunnyvale, CA 94086 | 100M, I will throttle down to 50M Gig UNI Optical MMF LC changed 7/29 to change this from MMF to SMF LC. | Quote: 191268939 Service Order(s) [ 191326688 ] has been created for Order Request 191288145 21200700 access 21200699 port snj i49956 Opp id O-1288507 change opp id O-1364041 change Quote 191589676 Change Order Request 191589841 Service Order(s) [ 191600707 ] has been created for Order Request 191598699 21411736 access SNJ I50220 | 191326688 191600707 |  | 5612757 | 10M | E4005262 REMOVE E4006127 ADD C1022274 | ea-4r3-4r3-0005 Demarc Overture ISG5100 Aisle 93.Bay 6.Shelf 11.Card2.Port 1 ea-4r3-4r3-0008 Fiber extended and labelled. RR 93.6.10: jk 13/14, 6000 series panel. |  |  |  | BPDD | 2015-07-20 | 7/10/2015 10/8/2015 | UHGECC -65511 | 763-744-1587, Leon_L_Betterman@optum.com |  | 7/2- CCR 1264751 RFT 7/13 minor build. Please install a MM GigE SFP (GE card in place already)-in the Overture ISG5100 at 4r3,02 1400 Kifer Rd, Sunnyvale, CA. Equip in 4r3,02 93.6.11 Slot 2. This replaces the existing SM GigE SFP. 7/9- CCR 1264751 RFT 7/13 minor build. Please install a MM GigE SFP (GE card in place already)-in the Overture ISG5100 at 4r3,02 1400 Kifer Rd, Sunnyvale, CA. Equip in 4r3,02 93.6.11 Slot 2. This replaces the existing SM GigE SFP. Customer keeps delaying access - now tentative for 7/10 for card install 7/17- ready for activation, customer notified 8/5- ShaRita working on order 8/13- order submitted to provisioning. IN/OUT not required request submitted as a CHANGE 8/19- pending CCR# 1272050 (Overture @ 4r3,02). Temp Trunk order is SNJ A50151. RFT 09/11/2015 8/28- pending CCR# 1272050 (Overture @ 4r3,02). Temp Trunk order is SNJ A50151. RFT 09/11/2015 9/3- SNJ I50220 this order is replacing snj i50140. Pending CCR-1272050 Overture 1400 @ 4r3,02 RFT=09/11/2015 9/10- Pending CCR-1272050 Overture 1400 @ 4r3,02 RFT=09/11/2015 9/14- RFT pushed to 9/18, Access denied for install - site requires 72hrs advance notice for work visits. 9/18- CCR complete, BEAS certified. 9/24- This is a Data Center and they require an access ticket for our tech’s visit. 9/30- pending RFC testing, dispatch completed and fiber extended on 9/28 10/1- RFC testing complete, pending closure of order ber extended on 9/28 10/8- ready for activation, customer notified
2015-07-22 | B end-Varun | PH511-02-IJ | Filinvest Cyberzone Tower 1 Salinas Drives Apos, Cebu Philippines- October 5th move in date. | 100M access and port Bill to Account SGP2001096 MMF LC on this one. And site of origin should be pasig-city-phl_w1b26059-5505541. globe requested. | OVI- 1-1535302695 • 5737018 - Port • 5737019 - W1B98697 Access |  |  | 5638300 | 72 m | W1B98696 Port W1B98697 Access | need to keep ptt same as W1B53388/W1B53389 PTT CIRCUIT ID : SID: MW01-092015-20360 PTT ORDER ID : PID: 101603059 FLOOR NO. : 9/F ROOM : SERVER ROOM DEVICE, PORT AND INTERFACE DETAIL: [NE: 217-10169] RNCB_UHLTHG8601 SLOT 4 PORT 1 DEVICE MAKE, MODEL AND SERIAL NO. : HUAWEI OSN500 CABLE TYPE : OPTICAL_MULTIMODE 1000M FULL DUPLEX / AUTO NEG OFF / FLOW |  |  |  | bpdd | 2015-11-23 | 2015-10-12 | unitedhealthgroup-64844 | Dianne Mariz Concepcion Reyes drreyes@optum.com 639985765586 | per john activate on 11/4 | 9/14- site is ready, sent over to PTT, pending FOC date. 9/17- PTT special build is Usually is 3-4 weeks. But based from the PTT’s advise last week, if there will be no other roadblock, they should be completing the build within the week and hopefully they finish the other tasks soon as well. 9/24- PTT still working on special build 9/28 TARGET RFS FOR THIS WILL BE BY FIRST WEEK OF OCT. (WEEK OF OCT, 5-9). TO UPDATE YOU, FOC AND MSAP NODE ARE ALREADY INSTALLED AT THE CUSTOMER. WE ARE JUST RE-ROUTING THE UPLINK FROM MACTAN TO CEBU JONES EXCHANGE NODE AS THE FORMER HAS BEEN VERIFIED WITH INSUFFICIENT CAPACITY TO SUPPORT UHG-S 2X100MB CIRCUIT REQUIREMENTS. WE-LL KEEP YOU POSTED ON THIS. 9/30- pending 10/9 delivery 10/6 . PTT are actually waiting for the LCON to grant their access to the site but until now the LCON has not responded Can you follow up as well? 10/8- PING TEST BETWEEN PTT AND GLP COMPLETED SUCCESSFULLY. PLEASE REFER TO CIRCUIT NOTEPAD. 10/12- order is now ready for activaiton
2015-08-18 | ShaRita | FL040-05-IJ | 701 NW 57 Ave Suite 150, Miami, fL 33126- Bell South | Gig UNI Optical MMF LC 10Mb Ethernet | O-1375742 Quote ID: 191616444 Order Request 191617104 Service Order 191618913 created for Order Request 191617104. 21456508 access 21456507 port | 191618913 |  | 5637393 | 4M | E3013141 C0060826 | 60/KRGN/756111//SB VZB DMARC: OPTICAL MM PORT6 EXTENDED TO SUIT 150 IT RM WALL PNL JK 1/2 TAGGED | 2015-08-24 | 9/29/2015 10/9/15 | 2015-10-09 | bpdd (standard 10/5) | 2015-10-06 | 2015-10-14 | unitedhealthgroup-64812 | robert_a_benson@optum.com 763-744-2077 | scheduled for 10/29 at 4 pm CST Bridge 866-878-8630 Passcode 6653710 | 8/18- sent to sharita 8/21- order submitted to provisioning 8/27- FOC 9/29 9/3- FOC 9/29. pending site requirements, sent to John 9/10- pending site requirements 9/17- pending site requirements, still pending FOC no longer valid 9/24- pending site requirements 10/1- informed by John site requirements completed, pending new FOC 10/9- FOC 10/9 10/12- circuit delivered. John confirmed demarc, beas installation scheduled 10/14 10/21- ready for activation, customer notified
2015-05-12 | ShaRita | CA188-02-IJ | 26922 Oso Parkway Mission Viejo, CA 92691- cox | 100M, I will throttle down to 10M Optical SMF LC 1st fl MDF | O-1301267 Quote ID: 191174434 Order Request 191175171 21092219 access 21092218 port | 191190621 |  |  | 1.5M | E4004875 C1021275 | 12.KFGX.000330..COXC. Demarc info: Suite 380 MPOE (Room with Biohazard Sign) on Cox Rack Accedian Eq. Port SFP-B (Labelled) | 2015-05-20 | 2015-09-25 | 2015-09-16 | BPDD (standard 7/1) |  |  | unitedhealthcare- 64867 | 443-853-3646 edward.mclaughlin@optum.com |  | 7/30- FOC 9/25 8/5- FOC date 9/25 8/12- FOC 9/25 8/19- FOC 9/25 8/27- FOC 9/25 9/3- FOC 9/25 9/10- FOC 9/25 9/17- circuit delivered, pending demarc confirmation from John 9/24- circuit delivered, pending demarc confirmation from John ***If demarc confirmation/extension information is not received by close of business, 10/28, the order will be cancelled the next business day, 10/29. *** 10/1- circuit delivered, pending demarc confirmation from John 10/8- pending demarc confirmation from John 10/9- per John cancel order, order has been supp'ed to cancel 10/12- pending cancellation completion 10/22- pending cancellation completion 10/29- awaiting CPE retrievel 11/5 -emai sent to PM Brandon following up with the cancelation of the PON. pending response. 11/10- order complete cancelled
2015-08-18 | ShaRita | FL046-05-IJ | 7800 SW 24th Street Miami FL 33155- Bell South | Gig UNI Optical MMF LC 10Mb Ethernet | O-1375742 Quote ID: 191616444 Order Request 191617104 Service Order 191619020 created for Order Request 191617104. 21456686 access 21456685 port | 191619020 |  | 5637406 | 4M | E3013143 C0060830 | 60/KRGN/756115//SB DMARC Info: main data room, rack mounted, position 20. Labeled with VZ id. | 2015-08-24 | 2015-10-15 | 2015-10-15 | bpdd (standard 10/5) | 2015-10-22 | 2015-10-20 | unitedhealthgroup-64810 | robert_a_benson@optum.com 763-744-2077 | scheduled for 11/5 at 4 pm CST Bridge 866-878-8630 Passcode 6653710 | 8/18- sent to sharita 8/21- order submitted to provisioning 8/27- pending FOC 9/3- FOC 10/15 9/10- FOC 10/15 9/17- FOC 10/15 9/24- FOC 10/15 10/8- FOC 10/15 10/12- FOC 10/15 10/15- circuit delivered, pending dmarc confimration 10/22- ready for activation customer notified
2015-08-12 | ShaRita | NJ023-09-CJ | 333 Thornall Street, Edison, NJ 08837 | Upgrade to 4xT1, 6144 | O-1375518 Quote ID: 191614839 Order Request 191616119 Service Order(s) [ 191689752 ] has been created for Order Request 191688974 IN Order Request: 191651627 Service Order(s) [ 191697999 ] has been created for Order Request 191651627 OUT 21517645 access OUT 21517644 port OUT 21517776 IN 21517775 IN | 191689752 IN 191697999 OUT |  | 5650688 | 3.5 | N1003819,N1003818,N1003817 OUT C0003658 OUT C1026308 IN N1023371 / IN N1023372 / IN N1023373 / IN N1023374 / IN | .HCGS.843065..NJ DEMARC LOC: GND,RM phone,TEL RM,RJ48C,LP Y,CAB N,SHELF,9,POS,3,, .HCGS.843066..NJ DEMARC LOC: GND,RM phone,TEL RM,RJ48C,LP Y,CAB N,JCK,8,POS,5 .HCGS.843067..NJ DEMARC LOC: main telco room jack 9 pos 1 .HCGS.843068..NJ DEMARC LOC: main telco room 1st floor behind cafeteria smjk sh-9 pos-2, DEMARC LOC Continued: ext to wall rj21x labeled sj9 on pos 2 Extended Wire (Yes or No): Yes Jack Type: RJ21X | 2015-09-18 | 9/29/2015 10/9/15 10/16/15 | 2015-10-07 | bpdd | 2015-10-02 | 2015-10-20 | Unitedhealthgroup-65298 | 763/694-7370, masroor_khan@optum.com | cutover scheduled for 11/6 at 5pm CST Bridge 866-878-8630 Passcode 6653710 | 8/14- Melissa is working on 8/18- sent to ShaRita 8/27- sent email to Melissa informing that change issue with need to be reissued 9/3- Melissa sent install order for 4xT1. ShaRita working on order. 9/10- internal TT open, system issue preventing order from being submitted to provisioning 9/17- TT resolved. order submitted to provisioning, pending ASR submission 9/24- FOC 9/29 10/1- access was denied, requested new FOC date. FOC date 10/9 10/8- TESTING ON CKT 1 AND 2 PENDING ACCEPTANCE ON CKT 3 AND 4 10/12- CKT 1&2 WERE TESTED; PENDING CIRCUIT DELIVERY ON CKT 3&4. FOC DATE 10/16 10/21- ready for hotcut customer notified 11/10- Remarks: Customer accepted the Multilink with just 2 out of 4 T1s up and agreed to get a ticket opened for the 2 down ckts and work with him thru email. ETMS: 2015111042290 LEC ID: .HCGS.843066..NJ LEC ID: .HCGS.843067..NJ LEC ticket: VNJNJ073843 LECticket: VNJNJ073844 LEC Contact #: 8007344276 Telco detected a hardloop on the network and they were able to drop it.
2015-07-06 | ShaRita | NY029-01-IJ | RNH Order phase 2 1311 Mamaroneck Ave. Suite 240 White Plains, NY 10605 - Verizon Telecom | Gig UNI MMF LC 100M, I will throttle down to 20M UHGVERbgpbqZyofa MMF LC Building demarc | O-1343362 Quote ID: 191420159 Order Request 191420319 Service Order(s) [ 191461202 ] has been created for Order Request 191420319 21348224 access 21348223 port | 191461202 |  | 5628532 | 1.5m | E4005864 C1024061 | 32.KFGS.205643..NY flr 1 lan room wallmntd mounting 3 pos 1 | 2015-07-31 | 2015-09-17 | 2015-09-17 | bpdd Standard 8/21 | 2015-09-24 | 2015-09-18 | unitedhealthgroup-64819 | 763-744-1971 mohan_basnet@optum.com | scheduled for 11/10 at 7pm CST Bridge 866-878-8630 Passcode 6653710 | 7/7- submitted to ShaRita 7/16- informed lcon early site survey Tuesday, July 21st between the hours of 9am to 12pm local. 7/24- site survey rescheduled for 7/24 7/30- site survey complete, no site requirements. Order submitted to provisioning, pending ASR submission 8/5- FOC 9/17 8/13- FOC 9/17 8/19- FOC 9/17 8/27- FOC 9/17 9/3- FOC 9/17 9/10- FOC 9/17 9/17- circuit delivered, pending testing and closing of order 9/24- ready for activation customer notified
2015-10-02 | Varun | AU548-04-IJ | Level 3, 173 Strickland Crescent, Deakin Canberra, Australia 2600 | 10mg Ethernet Level 3 Server Room SOO melbourne-aus_w0x83226-2017032 |  |  |  |  | 1536 | [6 empty] | BPDD |  |  | (63)2 5885331 kevin_cantor@optum.com |  | 10/2- sent to Varun for SOF 10/14- pending SOF 10/22- SOF with uhg 10/30- SOF still with UHG 11/5- per John this is cancelled.
2015-10-01 | ShaRita | WA022-05-CJ | 1111 3rd Ave, Suite 1100, 11th Floor Seattle, WA 98101 | 10.752 Mb Upgrade 5xT1 to 7xT1 | O-1408872 smartform 191821544 NSPE0009698373 IQBK72MW IN OQBK72QV OUT | 8534996 | P2124549 IN P2094529 OUT | 5539353 | 4M | BCBK621X0001-0005 | 74/HCGS/521748//PN 74/HCGS/521749//PN DEMARC LOC: 19th flr mn ph rm /multi mt # 10 slt 58 Jack Type: rj48c DEMARC LOC: 19th flr mn ph rm /multi mt # 10 slt 4-8 | 2015-10-14 | 2015-10-27 | 2015-10-27 | BPDD | BPDD 11/3/15 | 2015-10-28 | unitedhealthgroup-65202 | 763/694-7370, masroor_khan@optum.com |  | 10/2- submitted to ShaRita 10/8- working on submitting order 10/12- order submitted to provisioning, pending ASR submission to LEC 10/15 - FOC for 10/27 10/22- FOC 10/27 10/29- ready for hotcut, customer notified
2015-11-06 | ShaRita | none | 1831 Chestnut Street ST LOUIS MO USA 63103 | please place an order to have the Connextions VPN removed from the below circuit. | CW Order (ID : 192094980) NSPE0009804515 CQBK8HPW | 8563601 | P1840324 |  |  | BCBKK3WW0001 | [10 empty] | 11/11- order submitted to provisioning 11/19- order complete
2015-11-05 | ShaRita | none | 777 Bay Street TORONT O / ONTARI O CN CANADA M5G 2C8 | disconnect | NSPE0009763768 5780459 5780465 | 8559637 |  |  |  | W1A26870 (port) W1A26866, W1A26867, W1A26868, W1A26869 | [6 empty] | 2015-11-17 |  |  |  | 11/5- disconnect submitted 11/10- pending disconnect completion 11/18- disconnect complete
2015-09-28 | ShaRita | UTX43-07-CJ | 2301 W Plano Pkwy. Suite 300 Plano, TX 75075 | Please place an order to upgrade to the existing 2xT1 internet bundle to a 4xT1. | O-1405618 Smartform 191792607 NSPE0009685606 IQBK764V U293605 U293606 U293607 U332314 U332315 | 8521698 |  |  |  | Master u293605 Circuit ID: u293606 and u293607 U332314 U332315 MGBK85NG0001-0002 | LEC CIRCUIT ID: 12/HCGS/628793//GTEC 12/HCGS/628794//GTEC CKT 1: DEMARC LOC: 1st floor telco east wall patch panel jk7 CKT 2: DEMARC LOC: 1st floor telco east wall patch panel jk 8 Jack Type: RJ48X | 2015-10-22 | 2015-10-28 | 2015-10-28 | BPDD | BPDD | 2015-10-29 |  | John Curtiss, 469-229-6712, jcurtiss@uhcsr.com |  | 9/29- sent to ShaRita 10/1- ShaRita working on order 10/8- pending install date, 11/11 10/12- pending install date, 11/11 10/22- ASR sent. FOC is expected in 1BD. 10/29- order ready for hotcut, customer notified
2015-07-06 | ShaRita | CA109-02-IJ | RNH Order phase 2 18 Centerpointe Drive La Palma, CA 90623 AT&T | Gig UNI MMF LC 100M, I will throttle down to 20M UHGVERbgpbqZyofa MMF LC Building demarc | Quote: 191358093 Order Request 191420472 Service Order(s) [ 191461362 ] has been created for Order Request 191420472 21299756 access 21299754 port | 191461362 |  | 5623731 | 1.5m | C1023705 E4005666 | 13/KRGN/584560//PT | 2015-07-21 | 9/3/2015 9/15/15 | 2015-09-05 | bpdd Standard 8/21 | 9/11/2015 9/22/15 |  | unitedhealthgroup-64821 | 763-744-1971 mohan_basnet@optum.com |  | 10/8- still pending confirmation from John if this is a data center for the BEAS to be installed at the MPOE or not. If not, we will need a date from the customer on when this will be completed. ***to avoid cancellation extension must be completed by October 20th*** 10/12-John confirmed building is owned by UHG/AppleCare and that beas can be installed at the MPOE. Order supp'ed pending scheduling of beas install. 10/15- BEAS will be installed at : 1st flr fiber terminal room relay rack 100 optical #6 virtual edge jack 4 and 5 tagged 10/22- spoke with local contact, Sean, and he informed me that they are demolishing both mpoes and he does not believe it would be a good idea to install our beas equipment at this moment. mpoes are expected to be completed November 23rd. 10/29- asked John if we will be cancelling the order and reissue once mpoes are reconstructed, awaiting response 10/5- sent John an email asking if order will be cancelled, pending feedback. 11/6- per John cancel, he will re-issue in a couple of weeks. 11/10- pending cancellation completion 11/18- pending cancellation completion. Equipment retrieval schedule 11/20 12/1- order cancel complete
2015-09-15 | ShaRita | TN017-05-IJ | 7105 Moores Lane Brentwood TN 37027 | 200M, I will throttle down to 100M Gig UNI Optical MMF LC | O-1396156 Quote ID: 191728965 Service Order(s) [ 191734504 ] has been created for Order Request 191729845 21559982 access 21559981 port | 191734504 |  | 5650570 | 22M | E0000295 C0063734 | T4/KRGN/822211//SC DMARC Info: 1st Floor Server Room, rack mounted under LEC Demarc device. | 2015-09-17 | 2015-10-05 | 2015-10-02 | bpdd | bpdd 10/12/15 11/20/2015 | 2015-11-16 | unitedhealthgroup-64911 | 214-647-4442 donald_r_osborn@optum.com | scheduled for 12/1 at 10 pm CST Bridge 866-692-3158 Passcode 9236734 | 9/16- ASR sent, pending FOC 9/24- FOC 10/5 10/1- FOC 10/5 10/8- circuit delivered, pending demarc extension 10/12- order on hold, pending demarc extension 10/22- order on hold, pending demarc extension 10/29- order on hold, pending demarc extension 11/5- per Donald, Circuit will be extended on Monday, 11/9. 11/11- beas install scheduled for today, 11/12 11/18- ready for activation, customer notified
2015-09-29 | ShaRita | UCA97-07-IJ | 5757 Plaza Dr. Cypress, CA 90630 aT&T | Gig UNI Optical SMF LC 150M I will throttle down to 100M | SFDC# O-1407057 Quote ID: 191803062 Order Request 191804696 21640573 access 21640572 port | 191805825 |  | 5662051 | 22Mb (not avail had to do 25) | E4007126 C4002300 | 13/KRGN/585376//PT Dmarc 5757 plaza dr. Cypress. ..mope on site/Telcom room west wall next to AT&T equipc | 2015-10-08 | 2015-11-02 | 2015-11-03 |  | BPDD (stnadard 11/16) 11/9/15 | 2015-11-05 | unitedhealthgroup-64605 | 763-553-4801 sonja_d_mroczynski@optum.com | scheduled for 11/24 at 7 pm CST Bridge 866-878-8630 Passcode 6653710 | 9/30- sent to ShaRita 10/8- pending FOC date 10/12- pending FOC date 10/15- CNR received, asked provisoning to address 10/22- FOC date 11/2 10/29- FOC date 11/2 11/5- circuit delivered, awaiting John to confirm demarc 11/10- pending demarc extension ***to avoid cancellation demarc confirmation must be provided by close of business, 12/2*** 11/12- ready for activation, customer notified
2015-10-06 | ShaRita | UTX49-02-IJ | 5859 Farinon Drive San Antonio, TX 78249 AT&T access | Gig UNI Optical, MMF LC 100M, I will throttle down to 50M | O-1411955 Quote ID: 191881403 Order Request 191882079 Service Order(s) [ 191884960 ] has been created for Order Request 191882079 21656820 access 21656819 port | 191884960 |  | 5664069 | 4M | C1027141 E4007185 | 31/KRGN/651668//SW | 2015-10-14 | 2015-10-29 |  | BPDD | BPDD (standard 11/27) 11/05/2015 |  | unitedhealthgroup-65044 | 763-744-1589 david_casanova@optum.com | completed on the 3rd | 10/13- order submitted to provisioning, pending approval and ASR submission 10/22- FOC date 10/29 10/29- circuit installed, Demarc info: 1ST FLR STE 100 INSIDE ELECTRICAL RM S129. Beas installation already scheduled for 11/2. Need John to confirm the demarc prior in case beas dispatch needs to be cancelled. 11/5- order on hold No power available in the demarc room. Customer is going to request power outlets be installed and then call tech back to install the equipment 11/10- pending demarc room readiness ***to avoid cancellation demarc confirmation must be provided by close of business, 12/14*** 11/19- John informed that power was now available . BEAS install was successful today. Pending closing of order 12/1- ready for activation, customer notified
2015-11-03 | ShaRita | C1585-02-IJ | 6160 Lusk Blvd Suite 203 San Diego, CA 92121 | 6.144, 4xT1 | O-1433689 Quote ID: 192059450 Order Request 192059746 Service Order(s) [ 192065860 ] has been created for Order Request 192059746 21744987 access 21744986 port | 192065860 |  | 5675577 | 4M | C1028697 N1024884 N1024885 N1024886 N1024887 | 19/HCGS/627737//PT WESTEL SHELF 1 SLOT 2 AT THE 1.1 19/HCGS/627738//PT WESTEL SHELF 1 SLOT 3 AT THE 1.1 19/HCGS/627739//PT WESTEL SHELF 1 SLOT 4 AT THE 1.1 19/HCGS/627740//PT WESTEL SHELF 1 SLOT 6 AT THE 1.1 2ND FLOOR STE 203 SERVER ROOM Jack Type: RJ48C | 2015-11-06 | 2015-11-17 | 2015-11-17 | bpdd | BPDD (standard 11/30) | 2015-11-17 | UHGECC - 65525 | 763-7442154 scott_moyer@optum.com | Per John activated | 11/4- sent to ShaRita 11/5- ASR rejected from the LEC, asked lcon to confirm the suite letter associated with the suite number 11/10- FOC date 11/17 11/29- ready for activation, customer notified
2015-08-12 | ShaRita | NM020-07-IJ | 8220 San Pedro NE, Suite 300 Albuquerque, NM 87113- Qwest access | Gig UNI, optical MMF LC 50Mb, I will throttle down to 30M Gig UNI, Optical SMF LC | O-1371642 Quote ID: 191608771 Order Request 191610549 Service Order 191651622 created for Order Request 191610549. 21483971 access 21483970 port NDMT C201509180049 | 191651622 |  | 5640161 | 10 Mb | E4006406 C4002014 | 59/KXGS/119611//MS order R23980033 DMARC Info: Vz Demarc 3rd floor MDF rack one | 2015-08-28 | 2015-10-19 | 2015-11-02 | bpdd (standard 10/5) | 2015-12-04 | 2015-12-02 | Unitedhealthgroup-65232 | 981-005-9326 pradeep_yadav@optum.com | activated | 9/30- CTL replied.“This project is held up for another one to complete and then this order will go through as a flow thru. The fiber has just completed on the other project and we are on track to complete it on 10/9 or sooner. Unfortunately I am not able to get this project FOC’ed until the other one completes. Once that is done this order will go quickly. “ 10/8- pending FOC, escalated 10/13-FOC date 10/19 10/20- Called and spoke with CL/kevin and was advised that order is not out with design. Sent email to CL PM/Rick to assist in getting the design completed. Once design is done, order will be ready for dispatch. 10/29- Pending response from CL if desgin is completed. Provisioning reached out to CL Director/Terri for further assistance. Once design completes, order will be sent out for dispatch to do the isntallation. 11/3 local loop delivered, need dmarc confirmation of Lec demark: 1ST FL TELCO RM, E-WALL, PORT-4 11/4- it would seem that there are still issues with LEC even with the completion notice reopened the missedloop ticket C201510201935 as it was advised that this is still not ready for testing 11/11- pending demarc extension. Per John They have to run fiber in the building. They are hoping to have that done early next week. 11/18- pending dmarc extension. Per John, They are working on the extension, no eta yet. 11/19- Per John dmarc is complete 12/1- beas install scheduled for tomorrow, 12/2
2015-08-18 | ShaRita | FL045-05-IJ | 5355 West 20th Ave Hialeah, FL 33012 | Gig UNI Optical MMF LC 10Mb Ethernet | O-1375742 Quote ID: 191616444 Order Request 191617104 Service Order 191618914 created for Order Request 191617104. 21456820 access 21456819 port | 191618914 |  | 5637424 | 4M | E3013146 C0060833 | 60/KRGN/756107//SB Demarc is main server room, rack mounted in position 9. Tagged and labeled | 2015-08-21 | 10/15/2015 12/8/2015 11/16/2015 | 2015-11-17 | bpdd (standard 10/5) | 10/22/2015 12/15/2015 |  | unitedhealthgroup-65167 | 91 91600 84400 harish_kandpal@optum.com | activated | 9/3- FOC 10/15 9/10- pending site requirements, fowarded to John 9/17- pending site requirements 9/24- pending site requirements 10/1- pending site requirements ***to avoid cancellation confirme site readiness by close of business, 10/13*** 10/2- Per John site requirements are complete. 10/8- per AT&T we are not on track for FOC date of 10/15. They have not been granted access yet by the building manager to complete the fiber build. The manager has said he may schedule access for them some time mid- to late next week. Once that’s completed, the ASR will have to be sup’d for a new DDD.” 10/12- order on hold. due to LEC needs access from the building manager to complete fiber build 10/21- order still on hold due to access issue ***to avoid cancellation access issue must be resolved by 11/19*** 10/29- Per LEC, CNR was removed. New FOC date 12/8. 11/5- FOC 12/8 11/10- Improved FOC date 11/16 11/18- circuit delivered, per John extension not needed. Pending scheduling of beas install. 12/1- ready for activation, customer notified
2015-08-20 | B end Varun | II538-04-IJ | 11th, 12th floor, Building 12B, Mind Space, Survey No. 64 (part), Hitech City, Madhapur, Hyderabad | 300M will throttle down to 200M soo hyderabad-ind_w0z96959, gurgaon-ind_w1a31791 letterkenny-irl_w1a68428 | OVI# 1-1543726195 Parallel Upgrade has been raised in F&E • 5755161 - W1C03340 IN • 5755162 - W1C03341 IN • 5755164 - W1B59938 OUT • 5755165 - W1B59939 OUT |  |  |  | 90Mb or closest in our contract |  | need to use PROVIDER : TTSL |  | 2015-10-07 |  | bpdd | 2015-11-19 | 2015-11-30 | unitedhealthgroup-65191 | 91 91600 84400 harish_kandpal@optum.com | activated with Harish on 12/28 HARISH CONFIGURED THE INTERFACE, ARP ENTRY SEEN. BGP ESTABLISHED. TEST IS CLEAN THE OLD CKT (W1B59938) WILL BE DISCONNECTED ONCE THEY HAVE TRANSFERRED THE TRAFFIC TO THIS NEW CKT. | 8/20- pending SOF 9/.4- SOF generated and sent to UHG. 9/9- SOF returned. Reminder we need to use the same PTT as W1B59938 9/14 - order veified, pending order info 9/18- PARTIAL TEV HAS BEEN DONE WITH THE CUSTOMER. . INTERFACE CONFIRMATION IS AWAITED FR0M THE LCON. 9/24- TEV completed 10/2- FOC DATE = 27 OCTOBER 2015 10/7-OSP NEW RING EXTENSION WORK IS IN PROGRESS WITHIN THE BUILDING PREMISES. 10/14- PTT access arranged for the weekend of the 16th 10/30- IN-CAMPUS WORK HAS BEEN COMPLETED. INBUILDING WORK HAS BEEN COMPLETED. FOC DATE = 15 NOVEMBER 2015 11/9- Circuit testing would be initiated on Thursday, 12 Nov onwards. 11/12- PTT IS GETTING FIBER LOSS DURING INTERNAL CIRCUIT TESTING AT THEIR END. PTT IS RE-PLANNING TO DO THE MUX INTEGRATION TO RECTIFY THE FIBER LOSS. MUX INTEGRATION HAS BEEN SCHEDULED FOR TOMORROW. 11/19- MUX integration has been completed. Circuit testing will be initiated on 20 Nov. 11/23- CIRCUIT TESTING HAS BEEN INITIATED. HOWEVER, GETTING ERRORS ON THE CIRCUIT. WORKING WITH THE PTT TO GET THIS RESOLVED 11/30- circuit is now ready for activation.
2015-10-20 | ShaRita | none | 7067 N Mariposa Street FRESNO CA USA 93702 | disconnect | NSPE0009744971 order request 192129262 21778270 access 21778269 port | 192129842 |  |  |  | C0057672 |  |  |  |  | BPDD | 2015-12-30 |  |  |  |  | 11/12- order submitted to disconnect team 11/18- pending disconnect completion due date 12/30 12/1- pending disconnect completion due date 12/30 completed.
2015-10-22 | ShaRita | IL016-05-IJ | 4205 Westbrook Drive Aurora, IL 60504- AT&T provider | Copper RJ45 100M, I will throttle down to 50M | O-1425602 Quote ID: 192009861 Order Request 192010981 Service Order 192053879 21745039 access 21745038 port | 192053879 |  | 5675603 | 5M | E4007618 C1028709 | /KQGN/122482//LB | 2015-11-05 | 2015-11-23 | 2015-11-18 | BPDD | BPDD (standard 12/18) 12/2/2015 | 2015-11-29 | unitedhealthgroup-65253 | 763-744-1589 david_casanova@optum.com |  | 10/28- sent to ShaRita 11/5- order submitted to provisioning, pending ASR submission 11/10- FOC 11/23 11/19- circuit delivered, awaiting John to confirm demarc 11/29- circuit ready for activation
2015-10-01 | ShaRita | NJ013-05-IJ | 1 Quakerbridge Plaza Hamilton, NJ 08619- VZT access | 3.072, 2xT1 | O-1408870 Quote id 191823081 Order Request 191823659 21657036 access 21657035 port | 191885000 |  | 5664078 | 1.5M | C1027153 N1024000 / ADD N1024001 / ADD | .HCGS.843734..NJ DEMARC LOC: GND,RM TELCO,TEL RM,RJ48C,LP N,CAB N,RCK,2,SLOT,7,RJ48C CUST DEMARC LOC Continued: SERVER RM .HCGS.843735..NJ DEMARC LOC: GND,RM tel,TEL RM,RJ48C,LP N,CAB N,RCK,2,SLOT,10,Rj48c 1st DEMARC LOC Continued: flr customers s Jack Type: RJ48C | 2015-10-14 | 10/22/2015 11/17/2015 | 2015-11-17 | bpdd | BPDD (standard 10/30) 10/27/2015 11/20/2015 | 2015-11-17 | Unitedhealthgroup-65240 | 763/694-7370, masroor_khan@optum.com |  | 10.2- Sent to ShaRita 10/8- working on submitting order 10/13- order submitted to provisioning, pending approval and ASR submission 10/22- awaiting confirmation from LEC that circuit was installed today 10/29- order on hold, lcon refused service 11/5- order supp'ed for new due date, pending FOC 11/10- FOC date 11/17 11/18- ready for activation, customer notified
2015-09-03 | ShaRita | CA049-05-IJ | 3115 Melrose Dr #100 Carlsbad, CA 92010 AT&T access | Gig UNI Optical MMF LC 50M, I will thorttle down to 20M | SFDC# O-1389052 Quote ID: 191697355 Order Request 191698452 Service Order 191710122 created for Order Request 191698452. 21555484 access 21555483 port | 191710122 |  | 5649983 | 5.5M | E4006727 C4002162 | 11.KFGX.000553..COXC. Demarc rack closest to west wall,pos 26 | 2015-09-16 | 10/14/2015 10/30/2015 | 2015-11-03 | bpdd | bpdd (standard 10/23) 11/25/2015 | 2015-11-17 | unitedhealthgroup-65068 | 763-744-1589 david_casanova@optum.com |  | 9/14- ShaRita working on order 9/16- ASR sent, pending FOC 9/24- pending FOC 10/1- FOC 10/14 10/8- FOC 10/14 10/12- new FOC 10/30 10/22- We received an email from COX that this order will be getting rescheduled per end user going on vacation. Per their attached email from their project manager; “Nikki can we reschedule this for 10-28-15 at 9am. We were able to do site survey to see how to run cable but did not have time to complete install. Customer is going on vacation till then and we won't have anyone to give us access” 10/29- LEC tech was able to contact lcon to gain access, awaiting confirmation that circuit was installed 11/5- circuit delivered, john confirmed demarc. order stepped for beas install 11/11- beas installation scheduled for 11/17 11/18- ready for activation, customer notified.
2015-09-15 | ShaRita | IL722-02-IJ | CatamaranRx/Optum c/o CenturyLink 2425 Busse Road | 1G, I will throttle to 500M Gig UNI Optical SMF LC | Opp id : O-1396152 Quote ID: 191723272 Order Request 191723521 Service Order(s) [ 191729360 ] has been created for Order Request 191723521 21555708 access 21555707 port CFO I173997 | 191729360 |  | 5650006 | 20Mb | E5002051 C0064222 | ea-5i9-5i9-0043 Demark is at data center , 2.4.8. | 2015-09-16 |  |  |  | bpdd | 2015-11-09 | unitedhealthgroup-64721 | 763-694-7333 skbrown1@optum.com |  | 10/8- Overture CCR is not installed yet. This is a closed building with an exclusive inside wiring contract with IMG. A fiber cable pull will need to be arranged with IMG btwn our POP on the 26th floor and the customer suite on the 13th floor. 10/9-Card ccr 127928 issued to install giGE sfp's in oc192.roz at 3eg,01and 5i9,02. EBAP ccr 1279231 issued to install overture 1400 at 5i9,02. 10/13- CCR 1279231 RFT 11/13. Dependant on 1279228 install GigE sfp's in shared roadm at 3eg,01 and 5i9,02 10/15- Overture inventoried in tcoms and SNM. Stepping to prov for VDDS/SNM assignment to 2#F.0.1.1 / ENIKE2#F0001. 10/22- engineering working on running the fiber to get it to the panel 10/29- CCR 1279231 RFT 11/13. - Overture, pending equipment ship 11/5- :Preconfigured the Overture before installing. Arrived at the data center, 2425 Busse. Accessed to our cage. Mounted the Overture at Aisle, bay shelf 2.4.8. run power from the fuse panel at 2.4 top position 1A/1B. (REDLINED), that's the only position that's open. Run single mode fiber from the Tellabs Nano equipment at 2.2.4:2.2.4 to Overture 2.4.8:0.6, labeled with ckt id Gp-111p-5i9-0001. Powered up the Overture, saw 0.6, of the Overture sync up to the Tellabs, port shelf 2 card 2 port 4 (both green LED). Placed a SM fiber hardloop at 0.1 of the Overture, saw that port turned gree. No visible alarm on the Overture. Labeled the Overture equipment with TID and IP address 166.56.12.155. Run a ping test and I was able to ping. This box is pingable. Demark is at data center , 2.4.8. Phil 11/10- ready for activation, customer notified
2015-06-09 | ShaRita | NY385-02-IJ | 1 Dakota Drive Lake Success, NY 11042- VZT | Optical MMF LC 100M, I will throttle down to 10M 3rd Floor MDF | O-1323253 Quote 191282964 Order Request 191283190 Service Order(s) [ 191326641 ] has been created for Order Request 191283190 21232615 access 21232614 port | 191326641 |  | 5616138 | 3 Mb | E4005403 C1022692 | 32.KFGS.205374..NY demark: 3 rd floor suite 315 server room wall mounted | 2015-06-26 | 8/18/2015 10/9/15 10/27/15 11/10/15 | 2015-11-09 | BPDD Standard 7/27 | 8/25/2015 10/16/15 | 2015-11-10 | unitedhealthgroup-64866 | Deven Patterson (210) 877-7969 Deven_Patterson@optum.com | Request cancelled scheduled for 11/16 at 5 pm CST Bridge 866-878-8630 Passcode 6653710 | 7/17- pending site requirements. requested a copy of the EUCR form. FOC date 8/18 7/23- pending site requirements. FOC date 8/18 7/30- pending site requirements. FOC date 8/18 8/5- pending site requirements 8/13- site requirements complete. pending FOC, per John, Phillip Arnold provided EUCR to engineer 8/19- Our engineer spoke with landlord Phillip Arnold and confirmed they are not ready, conduit has not been installed. 8/27- FOC 10/9 9/3- FOC 10/9 9/10- FOC 10/9 9/17- FOC 10/9 9/24- FOC 10/9 9/28-The customer changed the demarc location from the 2nd flr to the 3rd flr in the building. New conduit is now needed from the 2ndflr to the 3rd flr. We also require power in the 3rd fl tel room. Both of these requirements have not been completed. 10/1- received confirmation that site is certified ready. new FOC date 10/27 10/8- FOC 10/27 10/12- date moved to 11/10 since customer site wasn't confirmed ready until last week. 10/22- FOC date 11/10 10/29- FOC date 11/10 11/5- FOC date 11/10 11/10- ready for activation, customer notifed
2015-07-28 | B end-Varun | PH510-03-IJ | Building O UP North Science and Techno Park, Commonwealth Quezon City Manila Philippines | 300M, I will throttle down to 250M soo to host w1b26059 3rd Floor MDF MMF LC BFD | OVI-1 1535683213 • 5737510 - Port • 5737511 - Access |  |  |  | 90M | W1B98841 Port W1B98842 Access | ON W1A80465 VLAN 580 (300MB) |  | 2015-10-28 |  | bpdd |  | 2015-10-30 | unitedhealthgroup- 65260 | Dianne Mariz Concepcion Reyes drreyes@optum.com 639985765586 |  | 7/28- pending carrier question from uhg 7/30- pending SOF 8/12- SOF sent to Verizon, pending order numbers 8/20- pending TEV with 5737511 8/27- TEV completed. Order sent to PTT, pending FOC 9/14- pending PTT FOC 9/25- PTT IS HAVING A CAPACITY ISSUE WITHIN THE AREA. THEY ARE STILL TRYING TO LOOK FOR RESOURCES OR OTHER ROUTES THAT CAN ACCOMMODATE THIS BANDWIDTH. 10/9- Asking PTT about if they can accomadate this bandwidth. 10/15- RFS date for local loop is 10/28 10/29- PING TEST COMPLETED, SENDING INFORMATION FOR PLUG AND PLAY TO CUSTOMER AWAITING CONFIRMATION AND ADVISE AS WELL.
2015-08-11 | ShaRita | GA008-09-IJ | 5775 Peachtree Dunwoody Rd NE Suite C600, Atlanta, GA 30342- Time Warner access | 1G, I will throttle down to 500M Gig UNI, optical MMF LC | Quote ID: 191592069 Order Request 191594465 Service Order(s) [ 191625702 ] has been created for Order Request 191594465 21447614 access 21447613 port | 191625702 |  | 5636678 | 20M | E5001935 C0060731 | 3X/KFFN/002012/TWCS demarc, 6th floor, bldg C, MDF room, rack1, tagged. | 2015-08-20 | 2015-09-22 | 2015-10-01 | BPDD (standard 9/28/2015) | 2015-09-29 | 2015-10-22 | Unitedhealthgroup-65043 | 702-242-7654 tauoa.falo@optum.com |  | 8/27- pending FOC 9/3- FOC 9/22 9/10- FOC 9/22 9/17- FOC 9/22 9/24- FOC missed, pending loop delivery. An email has been sent to (TW/Level 3 PM) to get details on where we are on the order as of today. Will keep pressing TW/Level 3 for updates and better resolution for the order. 10/1- circuit delivered. Awaiting John to confirm demarc. Demarc information: 6th floor (customer occupies entire floor), MDF room, customer RR #1 (in front of door), RMU11, XF003 (12count SM fiber), Ports 1&2, tagged 10/2- per John BEAS can be installed,no dmarc extension needed. 10/8- current LEC handoff is SM, but in beas box kit was 2 mm sfp.order need lec to change sfp to MMF . Called LEC and they see that they provisoned it to SMF they are now working on setting dispatch no eta or ticket opened as its a new install 10/12- called time warner today was advise by Tom that there inside wiring contact is on site advised by customer that they can do that on firday. But they all agreed to finish splicing tomorrow no eta 10/15- Dispatch incomplete. Due to handoff issue. Follow up with ACD Pachy if TW already has status of this pending dispatch for inside wiring, per ACD as of now no status yet. -Working with PDM Lead Glenda in getting the handoff issue back with TW. 10/22- ready for activation customer notified
2015-07-28 | B end-Varun | PH504-03-IJ | Science Hub Tower 3 McKinley Hill Cyberpark Taguig City Philippines | 400M, I will throttle down to 350M 2nd Floor MDF Room MMF LC BFD SOO to w1b26059 | OVI 1--1535296810 • 5737548 Port • 5737549 access |  |  | 5656545 | 90M | W1B98872 (port) W1B98873 (accessP | Bayan Tel DEMARCATION DETAILS FLOOR: GF 8F RACK: - - PORT: VITRO_2015 NPT1600C: I2 PORT 6 (GE OPTICAL) R13A09-B4.01 (WORKING) TX VERIZON PORT R13A09-B4.02 (WORKING) RX VERIOZN PORT ECI BG20 IOM PORT 1 (GE OPTICAL) CONNECTOR TYPE: LC SM LC MM DEVICE, PORT AND INTERFACE DETAIL: FIBER MUX/LC DEVICE MAKE, MODEL AND SERIAL NO. : ECI BG20 PTT CIRCUIT ID : 591354 BAYAN SERVICE ORDER #: 393961 |  |  | 2015-10-07 | bpdd |  | 2015-10-12 | unitedhealthgroup- 64925 | Dianne Mariz Concepcion Reyes drreyes@optum.com 639985765586 |  | 7/28- pending carrier question from uhg 7/30- SOF with UHG for signature 8/12- SOF sent to Verizon, pending order numbers 8/20- pending lcon validation 8/27- TEV completed. Order sent to PTT, pending FOC 9/14- pending PTT FOC 9/24- CHAISNG PTT FOR FIRM RFS DATE, PENDING REPLY 10/2- working on PVC for ping testing..need to redesign directly to PE 10/9- LEC delivered, working on layer 3 build. 10/12- order is now ready for activation
2015-08-11 | ShaRita | TX175-07-IJ | 14141 Southwest Freeway, Sugarland, TX 77478 | Gig UNI, Optical MMF LC 200M, I will throttle down to 150M Building demarc | O-1369966 Quote ID: 191594071 Order Request 191594274 Service Order(s) [ 191625644 ] has been created for Order Request 191594274 21445701 access 21445700 port | 191625644 |  | 5636502 | 50M | C5001249 E5001933 | 3I/KFFN/002016/TWCS DMARC Info: 5th floor customer server room, rack mount Overture 1400, tagged, customer handoff SFP port 1 Multi Mode LC fiber connection | 2015-09-03 | 2015-09-25 | 2015-09-30 | BPDD (standard 9/28/2015) | 2015-10-02 | 2015-10-08 | Unitedhealthgroup-65114 | (91)-9900022170 humayun_rafi@optum.com |  | 8/11- sent to ShaRita 8/19- order submitted to provisioning 8/27- pending FOC 9/3- John confirmed correct floor, ASR re-transmitted, pending FOC 9/10- FOC 9/25 9/17- FOC 9/25 9/24- FOC 9/25 10/1- circuit delivered, awaiting John to confirm if circuit needs to be extended 10/2- per John DMARc doesn't need to be extended. 10/8- ready for activation, customer notified
2015-05-04 | ShaRita | C1578-02-IJ | 11632 Harrisburg Road, Fort Mill SC provider is Palmetto | 100M, John will throttle down to 50M Optical MMF LC MD5 UHGVEReccgas4Usp9 BFD enabled | O-1295637 Quote ID: 191143764 Order Request 191143979 Service Order(s) [ 191169543 ] has been created for Order Request 191143979 21064984 access 21064983 port | 191169543 |  |  | 1.5M | E4004716 C1020919 | PNET-ENET-960719 VZB DMARC: 2nd floor rack 1 mounted in back under lec adva . Circuit is tagged | 2015-05-18 | 2015-08-04 | 2015-08-10 | BPDD (standard 6/18) | 2015-09-29 | 2015-09-29 | UHG-ECC- 65533 | 763-744-2082 eric_taylor@optum.com |  | 8/5- Pending advise from Spirit Communications. Per LEC PM, experienced a technical issue with new ckt., and havent, as yet, been able to test it as good. We will dispatch our install and test tech to customers premise tomorrow, 08/05/2015, to see if we can get his resolved. 8/6- - Lec loop has been delivered as per PADM - Demarc: 2ND FLR SERVER ROOM FIRST RACK ON THE LEFT HAND SIDE ADVA PORT 1 8/12- Circuit delivered, awaiting John to confirm if demarc has to be extended 8/19- pending demarc extension confirmation ***requested LEC handoff confirmation for John*** 8/27- pending demarc extension 9/3-pending demarc extension. ***to avoid cancellation demarc extension has to be done by close of business, 9/21*** 9/10- per John demarc extended. awaiting extension location to request beas installation ***to avoid cancellation demarc extension has to be done by close of business, 9/21*** 9/14- ShaRita asked John where the extnesion was extended to. john confirme it was extended to second floor server room. 9/17- beas scheduled for 9/25 9/24- beas scheduled for 9/25 9/28- BEAS installed, Dmarc 2nd floor rack 1 mounted in back under lec adva . Circuit is tagged, BEAS not pingable 9/30 - ready for activation, ShaRita please send out completion.
2015-07-28 | B end-Varun | PH503-03-IJ | 8th - 9th Floor Calyx Cetre, Cebu I.T. Park, Apas, Cebu | 200M, I will throttle down to 150M MMF LC 8th Floor MDF Room soo to w1b26059 BFD | OVI 1-1535675649 5737522 port 5737523 |  |  |  | 72M | W1B98845 W1B98846 | BAYAN CIRCUIT ID (CID) 522108 FIBERMAX OPTICAL PORT #2ECI BG20SPEED 1000 FULL DUPLEX AUTO NEG OFF |  | 2015-09-24 | 2015-09-24 | bpdd | 2015-10-14 | 2015-09-30 | unitedhealthgroup- 64937 | Dianne Mariz Concepcion Reyes drreyes@optum.com 639985765586 |  | 7/28- pending carrier question from uhg 7/30- SOF with UHG for signature 8/12- SOF sent to Verizon, pending order numbers 8/20- pending lcon validation, looks like MORIEL B. MAPULA sent it to HENRY S HENRY_LAUREQUEZ@OPTUM.COM 8/27- RECEIVED INFORMATION FROM SALES TO CHANGE LAST MILE PROVIDER FROM PLDT TO BAYANTEL WITH ECOST 8053254. UPON CHECKING, THIS CEBU CITY ORDER HAS ALREADY BEEN PLACED TO PLDT. EMAIL SENT TO SD&A/TJ TORNO FOR POSSIBLE CANCELLATION FEE FROM PLDT BEFORE WE PROCEED WITH THE CHANGES. AWAITING RESPONSE. 9/4- **ORDER MOVED TO CFOC ¦ TARGET RFS DATE: 09/24/2015** **CCD SET TO: 10/14/2015 BASED ON BCD: 10/08/2015 AND RELATED DELIVERABLES** 9/14- Bayantedl sourcing for LC patch cord, Bayantel can produce, however, it will take a minimum of 30 days for the item to arrive. Henry asked if we can change loop provider to PLDT. Asking John if that is what UHG wants. 9/17- UHG decided to stay with PLDT. 9/25- PTT delivered, we are now working on our install activites 9/30- ready for activation. need to change QOS, add BFD and multicasting, asekd Mark to add
2015-06-12 | ShaRita | VA726-02-IJ | 22451 Shaw Road Sterling VA 20166- RNH order- VZB | 1G, I will throttle down to 400M Optical SMF LC | Service Order(s) [ 191326860 ] has been created for Order Request 191312979 21200751 access 21200750 port WDC I126529 | 191326860 |  |  | 1.5M | C0056130 E5001563 | easaw saw 0006 left loop up on card 3 port 1 labeled with the circuit id |  |  |  | BPDD 8/4/15 (standard 30 business days) | 2015-09-10 | 2015-09-01 | unitedhealthgroup-64827 | 763-744-1957 ranjit_adhikari@optum.com |  | 6/16- order submitted to provisioning 6/25- sent follow up email to provisioning requesting that he review/approve order ASAP 7/2- order accepted, awaiting provisioning to provide valid assignment to design team 7/9- order stepped for site survey 7/17- pending ccr 1266688 CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01. ) RFT 8/19 7/23- pending ccr 1266688 (CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01.) RFT 8/19 7/30- pending ccr 1266688 (CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01.) RFT 8/19 8/5- Op’s is trying to complete this early but they are pending a call back from the LCON for access. LCON listed is Dan Sughrue, 703-773-6360 8/13- pending ccr 1266688 (CCR to install an oc48 from fw9500 at mlb,01 to bcrw,01.) RFT 8/19 8/13- OC48 equipment in stalled and topology complete, pending closure of install, then we can proceed with ethernet provisioning 8/19- node work complete at zb0, scoped, cleaned fibers, attenuated at roadm rx -15db, labeled, ETE testing scheduled for 8/21 8/27- escalated to dispatch. Auto or Manual test did not detect hard loop.. Verify path no alarms...MX960 142.6.L2:4.0.6 LINK IS UP...Referred back to dispatch to work with testing group 9/3- order ready for activation, customer notified
2015-06-09 | ShaRita | C1576-01-IJ | EXL Service (Century Link Co-Lo ZZSN1) 1400 Kifer Rd. Sunnyvale, CA 94086 | 100M, I will throttle down to 50M Gig UNI Optical MMF LC | Quote: 191268939 Service Order(s) [ 191326688 ] has been created for Order Request 191288145 21200700 access 21200699 port snj i49956 | 191326688 |  | 5612757 | 10M | E4005262 C1022274 | ea-4r3-4r3-0005 Demarc Overture ISG5100 Aisle 93.Bay 6.Shelf 11.Card2.Port 1 |  |  |  | BPDD | 2015-07-20 | 2015-07-10 | UHGECC -65511 | 763-744-1587, Leon_L_Betterman@optum.com | need to change handoff | 6/11- ShaRita working on order 6/16- order submitted to provisioning 6/25- CCR 1264751 RFT 7/13 minor build. Please install a MM GigE SFP (GE card in place already)-in the Overture ISG5100 at 4r3,02 1400 Kifer Rd, Sunnyvale, CA. Equip in 4r3,02 93.6.11 Slot 2. This replaces the existing SM GigE SFP. 7/2- CCR 1264751 RFT 7/13 minor build. Please install a MM GigE SFP (GE card in place already)-in the Overture ISG5100 at 4r3,02 1400 Kifer Rd, Sunnyvale, CA. Equip in 4r3,02 93.6.11 Slot 2. This replaces the existing SM GigE SFP. 7/9- CCR 1264751 RFT 7/13 minor build. Please install a MM GigE SFP (GE card in place already)-in the Overture ISG5100 at 4r3,02 1400 Kifer Rd, Sunnyvale, CA. Equip in 4r3,02 93.6.11 Slot 2. This replaces the existing SM GigE SFP. Customer keeps delaying access - now tentative for 7/10 for card install 7/17- ready for activation, customer notified
2014-07-22 | B End- Marc | UK513-02-IJ | 10TH FLOOR - 5 MERCHANT SQUARE, London, W2 1AS handoff on this one is an RJ45 electrical connection to us. | 30M PIP ethernet SOO to Letterkenny - circuit ID W0Y12673 MD5 UHGVERbgpbqZyofa and BFD | 5534618 (closed and delivered on vodaphone) 5609819 |  |  |  | 4000 | 5534618 vodaphone W1B33843 5609819 BT order W1B58493 | ETHC12383878/ETHA12145081/ONEA922669 ETHA12145081 FLOOR - 10TH ROOM - MDF LOCATION - TBC STREET NAME - MERCHANT SQUARE WEST CITY - LONDON COUNTRY - UNITED KINGDOM POSTAL CODE - W2 1AS ETHERFLOW - CONNECTED TRAFFIC CLASS : PREMIUM ETHERFLOW - CONNECTED A-END VLAN ID : 126 |  | 2015-08-14 |  |  |  |  | unitedhealthgroup-65248 | Sonja Mroczynski 715-841-7731 sonja_d_mroczynski@uhc.com | hotcut completed. Disconnect needed for 5534618 W1B33843 | 10/15- received today an update that BT is waiting for UHG to accept some time related charges for the internal cabling? emailed site contact Karen for more info 10/23- karen said work didn't happen on the 9th, she wasn't in the office, James will be taking over. work needs to be re-scheduled. 10/30- RAMs accepted by the customer. Re-sent request to BT to schedule work. 11/5- We sent the information to BT wholesale on the 30/10/15 Bt wholesale then need to send to BT Openreach which was done on the 1st Openreach confirmed this has been received and they are now progressing the order Next update due on the 13/11/15 11/9- OPENREACH'S CDD TO BT WHOLESALE HAS BEEN MOVED TO 11/13 WHICH MEANS OURS WILL MOVE OUT TO 11/19 THIS ALLOWS FOR THE ETHERWAY AND ETHERFLOW CONFIGURATION BUT THIS HAS NOT BEEN CONFIRMED AS YET 11/12- BT wholesale have received the handover from BT Openreach so all work was completed We are pushing then for the final congiruation to be completed 11/19- BT delivered, we are working on our PVC/layer 3 for handover 11/20- Unfortunately during yesterday tests was detected a small issue in configuration that is being sorted out to ensure a perfect connection. Hardware loop was left in site to allows us to keep testing and upon confirmation that everything is fine, I will re-dispatch an engineer to remove it and Verizon will be ready for migration. I had a call yesterday with Leslie and he advised me that will be on vacations this following days. So we are trying to schedule the earliest possible date.
2015-07-15 | ShaRita | GA019-02-IJ | 2100 Riveredge Parkway, Atlanta, GA 30328- VZB access | Gig UNI Optical MMF LC 150M, I will throttle down to 100M UHGVERbgpbqZyofa 5th Fl MDF | O-1350136 Quote ID: 191451549 Order Request 191453242 Service Order(s) [ 191490902 ] has been created for Order Request 191453242 21341300 access 21341299 port atl I0084729 | 191490902 |  | 5627905 | 25Mb | E4005837 C4001829 | ea-aay-aay-0005 DMARC IS 5th fl. IDF NOT MDF rm. Telco backboard on Verizon MCS 1.1.1:1.1 with multi mode fiber loopback, taged to extended. |  |  |  | bpdd (standard 8/31) | 2015-09-03 | 2015-12-03 | unitedhealthgroup-64818 | (91)-9900022170 humayun_rafi@optum.com | ready for activation | 10/22- order on hold. call the lcon Michael Johnson @336-655-6900 and per him. The customers site on the 5th fl. Is still not ready, no plywood backboard or power just yet for Verizon to extend our circuit to. He estimates 10/30/15 date . 10/29- order still on hold, awaiting customer to confirm site is ready 11/5- Customer site is still not ready for Verizon to extend service line to the 5th fl. Still no power or telco backboard. Spoke to Lcon Michael Johnson and he will call me back after todays conference call. *** to avoid cancellation site must be confirmed ready by close of business, 11/30*** per john they are working to have this in place by 11/9 11/10- order still on hold, awaiting customer to confirm site is ready *** to avoid cancellation site must be confirmed ready by close of business, 11/30*** per john they are working to have this in place by he 19th, however they are now trying to have completed by the end of this week, or early next week. 11/18- order still on hold, awaiting customer to confirm site is ready *** to avoid cancellation site must be confirmed ready by close of business, 11/30*** per john they are working to have this in place by he 19th, however they are now trying to have completed by the end of this week, or early next week. 11/19- per John, site is now ready. Order supp'ed requesting new due date. 11/19- per John they are ready for delivery 12/3- Verizon install ete test is complete with Bryan of MOE, DMARC IS 5th fl. IDF NOT MDF rm. Telco backboard on Verizon MCS 1.1.1:1.1 with multi mode fiber loopback, tagged to extended
2015-10-21 | ShaRita | TX777-05-IJ | Equinix DA3 Facility 1950 N Stemmons Frwy Dallas, Texas 75207 | internet T1 mirror u202907 | O-1425938 Quote ID: 191998841 Order Request 191999096 Service Order(s) [ 192066444 ] has been created for Order Request 191999096 21745248 ACCESS 21745247 PORT dal I100339 | 192066444 |  | 5675569 |  | D1053737 C0068183 | LEC CIRCUIT ID:13-nrc-ste-0034 DEMARC INFO:1st floor NIU Aisle 1 Bay 3 Shelf 3 Jack 26 left hard loop for testing |  |  |  | BPDD | BPDD (standard 11/26) | 2015-12-01 |  | is John Curtiss 469-229-6712 jcurtiss@uhcsr.com |  | 10/27- sent to ShaRita 10/29- ShaRita working on order 11/5- order submitted to provisioning, pending ASR submission 11/11- design completed, waiting for site survey 11/18- The design is completed. The next step on that is to test the circuit since the design is already completed. Once testing is done then this circuit will be ready for activation. 12/1- circuit is ready for activation
2015-08-14 | ShaRita | C1122-05-IJ | UHG - redden Anders 2170 Satellite Blvd, Suite 150 Duluth, GA 30097- Time Warner access | Gig UNI Optical MMF LC 50M, I will throttle down to 20M | O-1371642 Quote ID: 191608771 Order Request 191610549 Service Order 191651621 created for Order Request 191610549. 21485699 access 21485698 port | 191651621 |  | 5640467 | 10 Mb | E4006425 C4002021 | 4Y/KFFN/002289/TWCS Installed Overture in Optum/United Healthcare ste 150 server RR 1 in same rack as Lvl 3 Adva. Ran mm fiber to port 6, and went green. | 2015-08-28 | 10/2/2015 10/21/2015 | 2015-10-30 | bpdd (standard 10/5) | 10/9/2015 11/23/2015 | 2015-11-16 | unitedhealthgroup-64846 | 981-005-9326 pradeep_yadav@optum.com | scheduled for 10pm on 2/1 | 8/14- Melissa is working on 8/17- submitted to ShaRita 8/27- order submitted to provisioning. Pending ASR submission to LEC 9/3- pending FOC 9/10- pending FOC 9/17- FOC 10/2 9/24- FOC 10/2 10/1- FOC 10/2 10/8- FOC date missed FT was not able to reach LCON. Awaiting new FOC date. 10/12- pending new FOC date 10/22- We received an email from LEC PM assigned. Sent email to lcon requesting they call Beth Thorogood to scheduling inside wiriing 10/29- Per LEC PM, circuit should be installed today 11/5- circuit delivered. awaiting customer to confirm demarc. ***To avoid cancellation demarc confirmation need by close of business, 12/1**** 11/10- John confirmed demarc. beas install scheduled 11/16 11/18- ready for activation, customer notified.
2015-08-12 | ShaRita | M0111-09-IJ | 505 Boices Ln. Kingston, NY 12401- Verizon Telecom access | Gig UNI, optical MMF LC 200Mb, I will throttle down to 100M | O-1371642 Quote ID: 191608771 Order Request 191610549 Service Order 191651639 created for Order Request 191610549. 21504527 access 21504526 port | 191651639 |  | 5643172 | 20Mb | E5002003 C5001271 | 33.KFGS.206181..NY Demarc: 1st floor, server room, rear wall mounted ISG1400, optical port 0.1, MM/LC, tagged, not extended. | 2015-09-04 | 1/11/2016 11/20/15 10/15/15 | 2015-10-15 | bpdd (standard 10/5) | 2015-12-01 | 2015-10-21 | Unitedhealthgroup-64662 | 981-005-9326 pradeep_yadav@optum.com |  | 8/14- Melissa is working on 8/17- submitted to ShaRita 8/27- site survey schedule for 9/1 9/3- site survey complete, no site requirements. Order submitted to provisioning, pending ASR submissiong to LEC 9/10- Facilities are not available.Our best estimate to deliver FOC is 01/11/2016 9/24- Called status desk received update that there is no switch availability til DEC 31 st and order cannot be FOC'd 10/1- received FOC date of 11/20. sent email to provisioning to confirm this is correct, pending confirmation. 10/8- FOC 11/20 10/12- FOC date improved to 10/15/15 10/20- circuit delivered, pending DMARC confirmation 10/21- ready for activation, customer notified
2015-03-27 | B end Varun | UIX50-09-IJ | Unitech World (Cyber Park) - Sector 39, Building B - 14th, Gurgaon Haryana 122001 | port 200M Ethernet access 300M Ethernet SOO to Letterkenny - circuit ID W0Y12673 MD5 UHGVERbgpbqZyofa | 5696681 - port 5696682 – access |  |  | 5608685 | 72mg | W1B85587 (access) W1B85586 (port) | Tata |  | 2015-07-30 |  | BPDD | 2015-08-20 | 2015-08-05 | unitedhealthgroup-64896 | 981-005-9326 pradeep_yadav@uhc.com | 8/17- per Pradeep The circuit is turned up but no BGP route is advertised on this new link. We will burn this circuit for couple of days and test it before turning routing on. | 4/2- SoF with John at UHG. 4/17- Siva sent new SOF with new pricing 4/24- Pending goverenance approval for SOF signature 5/15- SOF returned to Verizon for signature 5.26- following up with B end team for ordering info 6/4-TEV IS OVER WITH LCON(PRADEEP). LOCAL LOOP ORDER WILL BE SUBMITTED TO PTT BY EOD TODAY 6/18- PTT IS STILL WORKING FEASIBILITY RE-VALIDATION 6/22- ORDER ACCEPTED BY PTT AND PTT IS CURRENTLY HAVING BW CRUNCH REQUIRE NETWORK UPGRADE. RFS AWAITED 6/26- still pending upgrade date from PTT 6/29- PTT HAS TO UPGRADE THE CUSTOMER END MUX AND REQUIRE DOWN TIME FROM CU CUSTOMER(UNITED HEALTH. TENTATIVE RFS DATE FOR LINE IS 3 WEEKS AFTER DONW TIME APPROVAL BY CUSTOMER 6/30 - We are coordinating with customer for down time approval. Customer will be confirming schedule in next 2 days. Accordingly we will arrange ptt. 7/9- CE END PTT MUX UPGRADE COMPLETED LAST WEEKEND AS PLANNED. CE END PTT MUX UPGRADE COMPLETED LAST WEEKEND AS PLANNED 7/14 LOCAL LOOP DELIVERY DATE: JULY 30 , our RFS is 8/20 7/23- pending delivery date of July 30th 7/30= local loop not yet delivered. 8/6- order ready for activation, engineer notivfied
2015-02-03 | B end | UK730-02-IJ | Sungard Hounslow Heathrow Corporation Park, Green Lane, Hounslow UK | 100M, John will throttle down to 50M MD5 UHGVERbgpbqZyofa, LC connector | Oppty - 1-NZCZPW, Proposal ID 537630, OECZ25 1-1491592377 s/o 5676522 |  |  | 5603880, | 15M | W1B78034 | FLOOR : 1ST ROOM : TELCO 7 CABINET : LG-2 ( CU12 ) ODF PANEL : PANEL 9, PORT 8 |  | 2015-05-15 |  | bpdd | 2015-06-26 | 2015-06-24 | UnitedHealthGroup-65160 | 763/694-7370, masroor_khan@optum.com |  | 2/3- sent over for SOF. 2/10- SOF sent to John 2/13- SOF modified to add dport and dcar. Sent to john. 3/12- billing entity changed, new SOF sent to UHG 3/17- John changed the signatory name 4/2-pending signed SOF 4/17- SOF signed and returned to Verizon 4/27- We need to know the floor and area (or cage information) on this in order to proceed. 4/30- floor and cage provided, order proceeding 5/4- TECHNICAL VALIDATION WAS REJECTED DUE TO NO REPLY FROM CUSTOMER, IS I POSSIBLE TO REMIND CUSTOMER THAT WE CANT PROCEED THIS ORDER WITHOUT TECHNICAL VALIDATION. LOCAL TEAM NEEDS GET BACK TEV MAIL. THANKS 5/5- TEV re-sent 5/19- Circuit designed, all on-net. Circuit expected to be cross connected by 5/25 5/25- physical path done. Working on logical provisioning 6/4- configlet created. Checking to see if order is ready for activation 6/17- pending ETE testing. Escalating. 6/24- ETE testing completed. order ready for activation.
2015-08-03 | ShaRita | C1581-01-IJ | Concentrix Tower B, 6th floor DLF Building No-14 DLF Ciber City DLF Phase 2 Gurgoan Haryana, India 122002 | 20M ethernet md5 UHGVEReccgas4Usp9 Electrical RJ45 Building DMARC 6th floor | OVI # 1-1560765511, F&E with s/o 5784156 - 5784157 Port & Access. |  |  |  | 1.5 | W1C11947 port |  |  |  |  | BPDD | 2015-01-04 | 2015-12-20 | UHG-ECC -65421 | 763-744-2265 travis_dent@optum.com | per John activated | 8.6-need to be processed in country because of tax regulations. Varun is working SOF and seeing if they can bill to the US Account. 8/14- pending SOF 8/20- SOF assigned to John 9/14- Per John UHG still has SOF 10/9- UHG still has the SOF 10/19- UHG decided to move forward with Domestic billing but we can't because of tax regulations, pending SOF signature 11/3- SOF signed, pending order information. 11/10-technical validation is pending so for so creation. 11/19- esclalating for TEV 11/30- TEV completed 11/20, request sent to PTT. Bharti has given the FOC of 29th Dec 15 however with our relationship with PTT I was able manage the delivery of this circuit within this week and the current status is that PTT has provisioned the link and we are planning to do the last mile cable and testing started in next 2-3 days max and if the testing is clean I will try to close the delivery by this weekend and link would be ready for activation by early next week. 12/8 We have got some hits during testing and team is checking with PTT regarding the same and will update you with next plan of action. 12/15- local loop delivered, L3 build complete, pending order closure 12/20- order is now ready for activation
2016-03-01 | B end Ezequiel | BZ508-01-IJ | Avenida das Americas, 8445 Barra da Tijuca Rio de Janeiro, Brazil 22793-081 | 100M, I will throttle down to 20M Optical SMF LC MDF 12th Floor |  |  |  |  | 2M |  | Level 3 |  |  |  | BPDD |  |  | UnitedHealthGroup- 64701 | 715-841-7731 sonja_d_mroczynski@uhc.com |  | 3/1- pending SOF 3/10- SOF issued but had wrong port pricing, asked that it be re-issued. 3/11- SOF corrected and sent to John 3/16-per John order is cancelled.
2015-10-02 | II702-09-IJ | II519-04-IJ | Pheonix Infocity Private Limited SEZ, Building No. H06, First, Second and Third Floor, Hitech City 2, Gachibowli (V), Hyderabad - need fo Jan 1 | 300M port, 400M access.OO New SOO Primary hyderabad-ind_w0z96959 New SOO secondary haryana-ind_w1b85586 | OVI# 1-1560473974 5780552 - W1C10980 IN 5780553 - W1C10981 IN (access) 5780567 - W1A44771 OUT 5780568 - W1A44772 OUT |  |  |  | 90m |  | TTSL |  |  |  | BPDD | 2015-02-01 | 2015-02-11 | unitedhealthgroup-65035 | 91 91600 84400 harish_kandpal@optum.com | Scheduled Saturday, March 5, 2016 at 1:00:00 AM | 1/21- circuit under PTT provisioning prcoess 1/22- As per the latest, PTT got some bandwidth issues in their backbone will provisioning the circuit. The bandwidth is getting upgraded during the weekends. We expect the circuit to be provisioned in the next week 1/29 THE BANDWIDTH CONSTRAINT ISSUE IS STILL NOT RESOLVED AT THE PTT END. PTT TEAM TRIED TO AUGMENT THE BANDWIDTH LAST WEEKEND, HOWEVER WERE UNSUCCESSFUL. ANOTHER ATTEMPT IS BEING DONE TOMORROW, 29 JAN TO ENHANCE THE BANDWIDTH IN THE NETWORK RING. POST BANDWIDTH AVAILABILITY, WE CAN GET THE CIRCUIT PROVISIONED. 2/1- The bandwidth upgrade has been done in the network ring structure at the PTT end during the weekend activity.The circuit provisioning is in progress at PTT end. We expect to initiate the circuit testing on 03 – 04 February 2017. 2/4- As per the latest, circuit provisioning has been completed. We have schedule the optical patching today at the Verizon node site. Post patching, we will initiate the circuit testing tomorrow. 2/11- ready for hotcut, customer notified 3/11- Harish agreed to proceed with dis 3/24- ORDER MOVED TO ABIL LBD SET TO 3/11/2016
2015-12-03 | b-end | none | Unitech World / Cyber Park / Sector 39 / HARYAN A GURGA ON INDIA INDIA 122001 |  | NSPE0009873235 |  |  |  |  | W1A31791 /W1A31792 |  |  |  |  | BPDD | [5 empty] | 12/17 followed up with Varun 1/7- Account Number: INP6000304 Product Description: Private IP Order Processing #: 1-1581769704 Termination Request Reference : 5801767 / 5801763 Circuit ID: W1A31791 / W1A31792 Last Bill Date : February 01 2016 2/11-LOOP TERMINATION ORDER PLACED TO PTT 2/18- pending disconnect 2/25- PTT LAST BILL DATE 6 MAR 2016 3/24- order confirmed as disconnected
2016-02-02 | B End- | UK513-02-IJ | 10TH FLOOR - 5 MERCHANT SQUARE, London, W2 1AS handoff on this one is an RJ45 electrical connection to us. | disconnect of old serivce w1b33843 | 5814258 |  |  |  |  | w1b33843 |  |  |  |  | BPDD | [5 empty] | CONFIRMATION REFERENCE - A-286098 CUSTOMER NAME - VERIZON BUSINESS BILLING ACCOUNT NUMBER - 13075091 CIRCUIT REFERENCE - 2C01869445,EAFE01869413 CONFIRMED CEASE DATE - 25/03/2016 CUSTOMER REFERENCE - OUR REF 5814258 confirmed disconnected
2016-01-20 | B end | PH503-04-IJ | UHG 8th - 9th Floor Calyx Cetre, Cebu I.T. Park, Apas Cebu Philippines SOO to Melbourne - circuit ID W0X83226 NEED THE CIRCUIT TO BE ACTIVATED BY WK3 OF APRIL 2016 | 600mg port and access | OVI#1-1598958408 s/o 5824881 / 5824882 |  |  |  | 182500?? | W1C24000 | BAYAN TEL |  |  |  | BPDD |  |  | unitedhealthgroup-64937 | Dianne Mariz Concepcion Reyes drreyes@optum.com 639985765586 | turned up with Dianne | 1/20- Siva sent for SOF and Melissa asked about SOO 1/27- SOF provided to John 182M Gold CAR isn’t in the contract so we priced it out 139M Gold CAR 2/4- John returned signed SOF. 2/24- We are still waiting for the INET AP56953.00 to be in “Project Completed” status. But Local Loop is already submitted to PTT. 3/8- Inet approval completed. 3/24- PTT BEST EFFORT DATE : 08 APR 2016 PTT FIRM RFS DATE : 15 APR 2016 4/14- LOCAL LOOP DELIVERY COMPLETE JOINT L3 TEST BETWEEN VZ GLP & PTT FE YIELDS ERROR FREE pending order closure
2015-09-24 | B end - Varun | II702-09-IJ | 5th, 6th and 7th Office Level, Building No. 14, Sundew Properties SEZ (Mindspace), APIIC Layout, Survey No. 64 (Part). Hitech City, Madhapur, Hyderabad- need Jan 1- check on the PTT | 500M, I will throttle down to 400M Multi Mode Fiber LC | OVI# 1-1560473675 5808259 - W1C19354 Port 5808261 - W1C19355 Access OUT order 5813704 - W0Z96959 Port 5813705 - W0Z96958 Access |  |  |  | 240 mg |  | PROVIDER : TATA COMM(FORMERLY VSNL) TSL |  |  |  |  | 2016-04-04 | 2016-02-16 |  |  | harish activated on 3/5, but now wishes to downgrade to 400mg. SOF will be needed and pricing is minimal. | 12/9- SOF sent to John for 300mg since 400mg isn't in the contract. 12/17- we may be able to support 500mg UNI with existing SOF. B end team is checking 1/7- Varun working on 500mg UNI with TCL, is there a SOF needed? 1/14- following up with Varun 1/15- new order enter and TEV completed. PTT FOC : PENDING FOC WILL BE AVAILABLE WITHIN 15 BUSINESS DAYS 1/21- pending FOC 1/25- reverted back and there is Bandwidth Congestion in Access Ring thus estimated RFS will be March End/April Starting. 2/1- PTT will be able to close bandwidth congestion issue in this week and we are trying to complete new 500 Mb link installation by mid-feb. 2/4- asking if Bandwidth issue was resolved. 2/11- WE ARE PRETTY MUCH ALMOST COMPLETE WITH THIS ORDER. CAPACITY ISSUE RESOLVED, STABILITY TEST COMPLETED. ONCE FOPS SIGN'S OFF THE TASKS IN ASRS, I'LL TRIGGER GLP TO VERIFY THE CIRCUITS FOR VLAN MAPPING THEN AFTER THAT, ORDER WILL BE READY TO BE SCHEDULED FOR UPGRADE/ACTIVATION. If everything goes well, we will be ready to activate the customer next week. Please help to plan the activation date with customer as once the order is ready. 3/24- was pending last bill date from customer....melissa told them to disco asap
2015-08-25 | ShaRita | UAL10-05-IJ | 33 Inverness Center Parkway, Hoover, AL 35242 - Bell South, AT&T | Gig UNI Optical Multi-Mode LC, 100M, I will throttle down to 10M | O-1381856 Quote ID: 191646029 Order Request 191646242 Service Order(s) [ 191651620 ] has been created for Order Request 191646242 21483117 access 21483116 port | 191651620 |  | 5640062 | 4mg | E4006396 C1025295 | A3/KRGN/601079//SC DMARC Info: 3rd floor Telcom room Wall mounted ISG400 port 1 | 2015-08-28 | 2015-10-01 | 2015-09-24 | bpdd (standard 10/12) | 2015-10-08 | 2015-10-19 | unitedhealthgroup-64733 | 987-313-9388 anupam_datt@optum.com |  | 8/25- sent to ShaRita 8/27- order submitted to provisioning. Pending ASR submission to LEC 9/3- pending FOC 9/10- pending FOC 9/17- pending FOC 9/24- Loop has been delivered to DEMARC: 3RD FL TELCO RMPANEL 1 PORT 2TAGGED. Kindly verify with the customer if demark still needs to be extended or if we are good to proceed with BEAS Install. 10/1- order on hold, awaiting for demarc extension 10/9- awaiting demarc extension, per john should be done next week 10/12- demarc extended, pending scheduling of beas install 10/22- ready for activation, customer notified
2015-09-03 | ShaRita | IL004-05-IJ | 200 East Randolph St Chicago, IL 60601- Verizon Business access. | Gig UNI Optical MMF LC 100M, I will throttle down to 20M | SFDC# O-1389052 Quote ID: 191697355 Order Request 191698452 Service Order 191710097 created for Order Request 191698452. 21559723 access 21559722 port cfo I173836 | 191710097 |  | 5650541 | 5.5 | C1026298 E4006745 | eastd std 0009 Building std Location: 01 Designator: Floor(FL) 52 ISG400 2.2.11:0.2 Customer responsible for extension |  |  |  |  | bpdd (standard 10/23) 10/27/15 | 2015-10-20 | unitedhealthgroup-65073 | 763744-0981 glenn_moore@optum.com |  | 9/14- ShaRita working on order 9/17- submitted to provisioning 9/24- went to site and found that cust is not on 1st flr cust is eitheron 53/54 flr lcon is not in office.... this is a closed building and will need cust to have building electrician run MMF to their suite.... will have to find out where CCR is SFP card has not been installl yet.... will also need 2 media converter... tie cable is SC-SC connectors per order rmks will need LC handoff 10/1- Need to know where the customer is located. Once the floor is provided, we can request a quote from the building vendor. 10/8- Received the following quote from building vendor IMG to install a MM fiber to the 53rd floor from VZ^s 52nd floor pop. Order needs to be stepped to sales to have charges accpeted.----Provide and install (1) 6-strand multi-mode 50 micron fiber cable from the 52nd floor Verizon Netpop to the 53rd floor server room.-- Terminate on SC connectors at both ends.-- Provide and install (1) rack mount LIU on the 53rd floor and use existing LIU in Verizons room.-- Secure cable in risers and fire stop.-- All work will be tested and clearly labeled upon completion.-- All work to be completed during regular business hours.----Price: $2,756.00 10/13- per Melissa, will talk to John to have them go to the cabling vendor directly. We are supping the order to terminate our circuit to the 52nd floor Verizon pop, so we can avoid the charges. 10/22- ready for activation, customer notified
2015-08-14 | ShaRita | FL086-02-IJ | 507 West Alexander St. Plant City, FL 33563 | 10752, 7xT1 | O-1375518 CW Order (ID : 191622825 ) NSPE0009576213 IQBK7H4W | 8463675 | P2120686 | 5640494 | 1.5M | BC BK8Y6Y 0001 BC BK8Y6Y 0002 BC BK8Y6Y 0003 BC BK8Y6Y 0004 BC BK8Y6Y 0005 BC BK8Y6Y 0006 BC BK8Y6Y 0007 | 69/HCGS/439187//GTES 1STFL-SERVERRM-SH 3-POS 1/4-TAGGED 69/HCGS/439188//GTES 1STFL-SERVERRM-SH 3-POS 2/4-TAGGED 69/HCGS/439189//GTES 1STFL-SERVER RM-SH 3-POS 3/4-TAGGED 69/HCGS/439190//GTES STFL-SERVER RM-SH 3-POS 4/4-TAGGED 69/HCGS/439191//GTES 1STFL--SERVER RM-SH 4-POS 1/4-TAGGED 69/HCGS/439192//GTES 1STFL-SERVER RM-SH 4-POS 3/4-TAGGED 69/HCGS/439193//GTES 1STFL-SERVER RM-SH 4-POS 3/4-TAGGED Jack Type: RJ48X | 2015-09-08 | 2015-09-18 | 2015-09-24 | bpdd (standard 10/5) | 2015-09-23 | 2015-09-25 | unitedhealthgroup-64814 | 763744-0981 glenn_moore@optum.com |  | 8/18- auth code requested 8/20- submitted to ShaRita 8/27- order submitted to provisioning. Pending ASR submission to LEC 9/3- there was some internal confusion with the address so provisioning is still working with submitting the ASR 9/10- FOC 9/18 9/17- FOC 9/18 9/24- Field tech has installed circuits, however there are still 4 CO jobs still open. Provisioning called and spoke with the CO tech and he will check to make sure everything is wired before closing out the jobs, however field tech states all is done. We will follow up in the morning and escalate with out test group for test, turn up and completion. 10/1- ready for activation, customer notified
2015-07-24 | ShaRita | CO710-02-IJ | 9945 Federal Drive Colorado Springs, CO 80921- Qwest access | 9216, 6xT1 md5 UHGVERbgpbqZyofa BFD Building demarc | O-1359547 Quote ID: 191518867 Order Request 191519482 Service order id 191535320 21348414 access 21348413 port CW Order (ID : 191630102) re-issue NSPE0009580405 IQBK7H41 | 191535320 8463678 | P2120689 | 5628540 | 2M | BCBK8Y660001-0006 C1024064 N1022253 N1022255 N1022254 N1022256 | 26/HCGS/638206 /MS DEMARC LOC: first flr electrical room cab b slot 7/8 26/HCGS/638207 /MS DEMARC LOC: first flr electrical room cab b slot 8/8 26/HCGS/638208 /MS DEMARC LOC: first flr electrical room cab c slot 1/4 26/HCGS/638209 /MS DEMARC LOC: first flr electrical room cab c slot 2/4 26/HCGS/638210 /MS DEMARC LOC: first flr electrical room cab c slot 3/4 26/HCGS/638211 /MS DEMARC LOC: first flr electrical room cab c slot 4/4 Jack Type: rj48c 26/HCGS/638116//MS 1st flr main telco/fire control rm cab#a slot#2/8 26/HCGS/638117//MS 1st flr main telco/fire control rm cab#a slot#3/8 26/HCGS/638118//MS 1st flr main telco/fire control rm cab#a slot#4/8 26/HCGS/638119//MS 1st flr main telco/fire control rm cab#a slot#5/8 Jack Type: rj48c | 8/4/2015 8/28/15 | 8/17/2015 9/16/15 | 8/14/2015 9/9/2015 | bpdd (standard 8/27) | 8/20/2015 9/23/15 | 8/17/2015 9/14/15 | unitedhealthgroup-65263 | 763/694-7370, masroor_khan@optum.com |  | 7/19- sent to ShaRita 7/30- order submitted to provisioning, pending ASR submission 8/5- FOC 8/17 8/13- FOC 8/17 8/19- ready for activation, customer notified, ordered as wrong speed, re-installing 8/27- order submitted, pending ASR submission to LEC 9/3- FOC 9/16 9/10- circuits delivered, pending end to end testing and closing of order
2015-08-20 | ShaRita | IA021-08-CJ | 1089 Jordan Creek Parkway, Des Moines, IA 52066 | Upgrade from 4xT1 to new 7xT1 | O-1379482 CW Order (ID : 191631320) IQBK7HXQ | 8463669 | P2120639 |  | 4M | BCBK8Y4X0001-0007 | 32/HCGS/091391//NW DEMARC LOC: 3rd flr main tele rm mt# 2 slot# 1 of 4 32/HCGS/091392//NW DEMARC LOC: 3rd flr main tele rm mt# 2 slot# 2 of 4 32/HCGS/091393//NW DEMARC LOC: 3rd flr main tele rm mt# 2 slot# 3 of 4 32/HCGS/091394//NW DEMARC LOC: 3rd flr main tele rm mt# 2 slot# 4 of 4 32/HCGS/091395//NW DEMARC LOC: 3rd flr main tele rm mt# 3 slot# 1 of 4 32/HCGS/091396//NW DEMARC LOC: 3rd flr main tele rm mt# 3 slot# 2 of 4 32/HCGS/091397//NW DEMARC LOC: 3rd flr main tele rm mt# 3 slot# 3 of 4 Jack Type: rj48c | 2015-08-28 | 2015-09-11 | 2015-09-10 | bpdd | 2015-09-18 | 2015-09-11 | unitedhealthgroup-65134 | 91 91600 84400 harish_kandpal@optum.com |  | 8/20- pending migration circuit id 8/27- order submitted to provisioning. Pending ASR submission to LEC 9/3- FOC 9/11 9/10- ready for activation, customer notified
2015-07-08 | ShaRita | UNJ08-05-IJ | 131 Morristown Road Basking Ridge, NJ 07920- VZT access | Gig UNI Optical MMF LC 200M, I will throttle down to 150M UHGVERbgpbqZyofa Building demarc with vlan tag | O-1345248 Quote ID: 191431591 Order Request 191433321 Service Order ID: 191462080 21308885 access 21308884 port | 191462080 |  | 5627894 | 30M | E5001742 C5001176 | .KFGS.304593..NJ DMARC Info: FL,1 MAIN TELCO RM. RR#2, POS #8 | 2015-07-25 | 2015-08-13 | 2015-08-06 | BPDD standard 8/25 | 2015-08-20 | 2015-08-06 | unitedhealthgroup-64541 | 763-744-1556 john_l_rothstein@optum.com | activation scheduled for 8/21 at 8pm CST Bridge 866-878-8630 Passcode 6653710 | 7/17- Tuesday, July 21st between the hours of 9am to 12pm local. 7/23- site survey complete, no site requirements. FOC date 8/13 7/30- FOC date 8/13 8/5- FOC 8/13 8/13- ready for activation, customer notified
2015-07-16 | ShaRita | MA005-02-IJ | Commonwealth of MA 19 Staniford St, Boston, MA 02114- VZT telecom | 6.144, 4 x T1 5th Floor Closet 581T | O-1351678 Quote ID: 191460024 Order Request 191477476 Service Order(s) [ 19153506 0 ] has been created for Order Request 21348279 access 21348278 port | 191535060 |  | 5626545 | 4Mb | C1024062 N1022251 N1022252 N1022250 N1022249 | 95.HCGS.490800..NE UPR,RM 5th,TEL CLOSET,RJ48X,LP N,CAB N,JCK,1,POS,4,, 95.HCGS.490799..NE UPR,RM 5th,TEL CLOSET,RJ48X,LP N,CAB N,JCK,1,POS,3,, 95.HCGS.490798..NE UPR,RM telco,TEL CLOSET,RJ48X,LP N,CAB N,JCK,1,POS,2,, 95.HCGS.490796..NE ,RM 3rd,DATA CTR,RJ48X,LP N,CAB N,OTHER,fico,POS,6,Fico Jack Type: RJ48C | 2015-07-31 | 8/7/2015 8/13/15 | 2015-08-17 | bpdd (Standared 8/17) | 2015-08-18 | 2015-08-20 | unitedhealthgroup-64816 | 443-872-3099 robert.winston@optum.com |  | 7/16- pending auth code 7/21- submitted to ShaRita 7/30- order submitted to provisioning, pending ASR submission 8/5- FOC date 8/7 8/7- Jamie asked to supp to change lcon to to Kelvin Oluwole 617-699-5568 8/12- FOC 8/13 8/19- circuits delivered, pending end to end testing and closing of order 8/27- ready for activation customer notified
2015-07-28 | ShaRita | FL141-02-IJ | 13751 Metropolis Avenue Fort Myers, FL 33912 | 10.752, 7xT1 MD5 | O-1360270 CW Order (ID : 191520680) NSPE0009509365 IQBK637T | 8441924 |  |  | 2M | BCBK8VWW0001-0007 | 25.HCGS.273349..UFLG FIRST FLR TELCO ROOM - NOT EXT - SLOT 2 OF 8 25.HCGS.273350..UFLG FIRST FLR TELCO ROOM - NOT EXT - SLOT 3 OF 8 25.HCGS.273351..UFLG FIRST FLR TELCO/SLOT 1 of 8 25.HCGS.273352..UFLG FIRST FLR TELCO SLOT 5 of 8 25.HCGS.273353..UFLG FIRST FLR TELCO ROOM - NOT EXT - SLOT 6 OF 8 25.HCGS.273354..UFLG FIRST FLR TELCO ROOM - NOT EXT - SLOT 7 OF 8 25.HCGS.273355..UFLG FIRST FLR TELCO ROOM - NOT EXT - SLOT 8 OF 8 Jack Type: RJ48X WITH OPEN PLUG | 2015-08-12 | 2015-08-18 | 2015-08-21 | bpdd | 2015-08-25 | 2015-08-25 | unitedhealthgroup- 65075 | 443-872-3099 robert.winston@optum.com |  | 7/30- order sent to ShaRita 8/5- orders submitted, pending provisioing approval. Available capacity is just for one ckt. Awaiting capacity for 7 ckts 8/13- FOC 8/18 8/19- order on hold , customer not ready, no backboard, no access, building under construction 8/27- ready for activation, customer notified
2015-07-20 | ShaRita | C1345-05-IJ | 11330 IH-10 West San Antonio, TX 78249- TW access- Peak Season- Time Warner | 100M, I will throttle down to 50M Gig UNI Optical MMF LC MD5 UHGVEReccgas4Usp9 Building demarc | O-1354418 Quote ID: 191478148 Order Request 191481946 Service Order(s) [ 191535071 ] has been created for Order Request 191481946 21348337 access 21348336 port | 191535071 |  | 5629969 | 1.5M | C1024169 E4005866 | 21.L1XX.004941..TWCC | 2015-08-05 | 2015-11-03 | 2015-11-18 | bpdd | 2015-11-10 | 2015-12-04 | UHG-ECC 65483 | 763-744-2081 tim_gunderson@optum.com |  | 8/26 Pending construction design and the property owner to sign the ROE 8/18Pending construction design. 8/10 FOC sent. Pending Walkout. 9/24- Copy of ROE agreement sent to John, awaiting ROE to be returned 9/28- pending ROE. Real estate management had some changes, gave them a nam of someome to work with at TW on making changes 10/1- pending ROE. 10/8- pending revised ROE 10/12- pending ROE. informed John to have property manager work directly with Anthony. Anthony D Singletary Commercial Property Access Specialist Desk: 469-464-4572 E- FAX: 704-945-1056 anthony.singletary@twcable.com 10/.15- ROE received from John, sent to provisioning 10/22- order supp'ed, pending new FOC date 10/29- FOC 11/3 11/5- Loop delivery missed to pending construction completion (ECD of 11/13). 11/10- FOC pushed out, ECD on track for 11-13 overall delay due to ROE. 11/18- Install complete and circuit tested. Demark is 1st floor suite 150 server room, rack RU 30 work with Mark Hettler. Pending demarc confirmation from John. 12/3- beas install complete, pending testing and closing of order
2015-05-22 | ShaRita | C1560-04-IJ | Catamaran 8534 Concord Center Drive Englewood, CO 80112- Quest access | 100M, John will throttle down to 50M Gig UNI - Optical MMF LC | O-1312016 Quote ID: 191219121 Order Request 191219861 Service Order 191234423 created for Order Request 191219861. 21142726 access 21142725 port | 191234423 |  | 5607921 | 20M | C1021653 E4005065 | 24/KXGS/130127//ACSO LEC Demarc info: DATA CENTER CAGE #11 RR 3 SH #4 Customer OPTICAL PORT 3 Demarc extension info : customer cage rack 301 RU 42 fiber patch panel port 2 | 2015-06-03 | 2015-07-27 | 2015-07-28 | BPDD (Standard 7/13) | 2015-08-03 | 2015-10-19 | UHC-ECC-65523 | 763-744-1587, Leon_L_Betterman@optum.com |  | 8/5- waiting on John to confirm if demarc extension needed 8/13- asked John to confirm if demarc extension is needed, awaiting feedback. 8/19- pending demarc confirmation from John 8/27- the circuit has been extended to cage 11 into the Century Link LEC cabinet (sitting on top of cabinet) labeled with LEC id: 24/KXGS/130127//ACSO. Since the cabinet is locked we need to ask CL to go back out to connect the extension to the demarc. Coordinating with LEC (Centurylink) for resolution. 9/3- awaiting CTL tech dispatch to go back out to connect the extension to the demarc 9/9- Customer has to call CTL on this one. They have to refer to ticket 5086829 - Catamaran Request for access to CTL data center 9/17- Received from John, the Cross connect is now completed from our Cage to the Carrier NODE Cage and into the Demarc port provide by VZN/CTL LEC. Pending scheduling of beas dispatch. 9/24- dispatch is asking for confirmation on if an access ticket is needed for tech to gain access to the data center 10/1- order on hold, pending access ticket from John 10/8- attempted to install overture, but our equipment and sfp's are mmf and the data center has delivered smf....took package back to orchard site until sfp replacement or delivery of correct fiber mode. Customer’s DATA center uses SMF yet they requested MMF. Per John data center will change extension to MMF 10/12- Informed by John that issue has been resolved. Order supp'ed to have tech redispatched to complete beas install. 10/15- BEAS install scheduled fo 10/16, assigned to Richard Esparaza 10/21- ready for activation, customer notified
2015-08-13 | ShaRita | C1583-01-IJ | UHG EGS- neeed for AEP 21111 Ridgetop Circle Sterling, VA 20166- Verizon Business access | Gig UNI, Optical SMF LC 400Mb, I will throttle down to 300Mb | O-1371642 Quote ID: 191608771 Order Request 191610549 Service Order 191651592 created for Order Request 191610549. 21483909 access 21483908 port wdc i127004 a0127104 | 191651592 |  | 5640476 | 10 Mb | C5001260 E5001975 | ea-pd9m-pd9m-0007 Demark floor 1 room ccb rr 0ccb.12.33 port 5 |  |  |  | bpdd (standard 10/5) | 2015-10-21 | 2015-10-15 | UHG-ECC | 763-744-2265 travis_dent@optum.com |  | 8/27- order submitted to provisioning. Pending ASR submission to LEC 9/3- order sent to engineering for design and scheduling of site survey 9/10- MINOR CCR 1274688 to add oc12 cards to oc48.ckg at pd9m,01 MAJOR CCR 1274689 CCR to install an Overture 1400 at pd9m,01 equipped for an oc12 from the local network and a single mode gig-e handoff to the customer RFT 10/14 9/17- EQDL- CCR- 1274689.. Overture 1400 @ pd9m,01.... RFT=10/14/2015 9/24- VP expedite approved CCR 1274688 (WDC) Card Add is now closed. CCR 1274689 (WDC) EBAP - Pending the A-order (network orders) that need to be stepped to field for Ops to complete patching. Once the patching is complete MOE will review and provided the path tests good the A order will be closed and the CCR will auto step to Ops for BEAS install. 9/28- dispatching to verify Oc12 trunking and equipment (scheduled for today), once OC12 path is verified, we can step to install BEAS. 9/30- dispatch moved to today to test OC12...BEAS can be dispatched once this is complete 10/5- BEAS Scheduled to install today. 10/8- ENABLED AND BUILT OVERTURE 166.50.120.41 PORT 0.1 READY FOR RFC TEST -- THIS IS 400 MG CKT GIGE INTERFACE Demark floor 1 room ccb rr 0ccb.12.33 port 5 Pending visloss ticket for L2 switch 166.42.70.210 (V6HF902), per GTNOC tkt is scheduled for dsp... 10/13- Testing was done successfully this morning. Almost ready for activation provisioning still has a task to close they were emailed on it this morning. 10/15- order ready for activation.
2015-08-31 | ShaRita | FL143-02-IJ | 12926 GRAN BAY PKWY WEST, JACKSONVILLE, FL 32258 | 12.288, 8xT1 | O-1385720 Quote ID: 191682568 CW Order (ID : 191682617) IQBK7LQ4 | 8482391 | P2121429 | 5643219 | 4608 | BCBK805S0001-0008 | 52/HCGS/775852//SB DEMARC LOC: 5TH FL TEOCO M SLOT9 RJ48C NON 52/HCGS/775853//SB DEMARC LOC: 5TH FL TELCO MM SLOT 10 RJ48C 52/HCGS/775854//SB DEMARC LOC: 5TH FL TELCO MM SLOT1 RU48C NON EXT 52/HCGS/775855//SB DEMARC LOC: 5TH FL TELCO MM SLOT12 RJ48C NON EXT 52/HCGS/775856//SB DEMARC LOC: 5TH FL TELCO MM SLOT13 RJ48C NON EXT 52/HCGS/775857//SB DEMARC LOC: 5TH FLOOR TELCO RM MM SLT14 RJ48C NON EXT 52/HCGS/775858//SB DEMARC LOC: 5TH FL TELCO MMSLOT15RJ48C NON EXT 52/HCGS/775859//SB DEMARC LOC: 5TH FL TELCO MM SLOT16 RJ48C NON EXT | 2015-09-10 | 2015-09-23 | 2015-09-23 | bpdd | 2015-09-30 | 2015-09-25 |  | 981-005-9326 pradeep_yadav@optum.com |  | 9/3- order submitted to provisioning, pending ASR submission to LEC 9/10- ASR sent, pending FOC 9/17- FOC 9/23 9/24 - pending testing and closing of order 9/25- ready for activation
2015-06-09 | ShaRita | C1563-03-IJ | C3 Connect 5215 West Wiley Post Way, Suite 200 Salt Lake City, UT 84116 peak season | Gig UNI Optical MMF LC 200M, John will throttle down to 100M terminate to 2nd floor data center | O-1318552 Quote ID: 191282103 Order Request 191282441 Service Order(s) [ 191326620 ] has been created for Order Request 191282441 21200648 access 21200647 port slc i11279 | 191326620 |  | 5612750 | 50M | E5001561 C5001076 | eavro vro 0005 Building vro Location: 04 Designator: Floor(FLR) 2 Suite(STE) 200 ISG400 100.3.2:0.2 |  |  |  | BPDD Standard 7/27 | 2015-08-03 | 2015-09-04 | UHG-ECC-65409 65416 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 6/2- John asked to put the order on hold 6/9- John said to go with the order as is. 6/16- order submitted to provisioning 6/25- sfp is installed, customer is responsible for extension. They willbe connecting to our port, and it is labeled and ready. Worked with Joe Bon^s C3 IT manager. Demarc is per TCOMS CLR. Test it and turn it over to customer. Dispatch complete, port is ready. 7/2- E-help ticket : T1982127 due to unable to NOC move circuit E5001561 from port:GW ZTF/ZTF.0.3.1 to the correct port ZTF.0.2.1 due to disco PVC is still on that port 7/9- sent email to provisioning requesting an update on the Trouble ticket that was created for the NOC move 7/17- escalated to provisioning management for an update, pending feedback 7/23- provisioning needs to engage Tier 2 support to have the device rebooted, then run the disconnection actions for the PVC and Access circuit mentioned 7/30- NOC moved circuit:E5001561 to the correct port assignment ZTF.0.2.1.., order sent to design 8/5- ETMS ticket 2015072404853 opened to reboot the overture set for 8/14 OKTUL.GTTS: This is due to the kernel 148 issue. Device needs to be rebooted and upgraded. ed to send a tech out to the site and reboot the Overture device under L1 Mastars and schedule with Tier2 to Upgrade the kernel and software on the device to keep this from reoccurring. 8/13- Per ETMS ticket a re-boot is set for tomorrow 8/14 8/19- still unable to access overture, dispatched is scheduled for tech to reboot on 8/27- escalated to have tech dispatched to reboot overture 9/3- dispatch was scheduled for Wednesday to reboot overture. sent email to confirm if it had been done, pending feedback 9/4- BEAS re-booted and order is now ready for activation
2015-05-28 | ShaRita | MS002-02-IJ | 755 Woodlands Parkway Ridgeland, MS 39157 AT&T Bell South | 9216, 6xT1 | O-1314905 Quote ID: 191241945 CW Order (ID : 191248986 ) NSPE0009337651 IQBK6GWR | 8380048 | P2112881 | 5611690 | 4000 | BCBK8MRJ0001 BCBK8MRJ0002 BCBK8MRJ0003 BCBK8MRJ0004 BCBK8MRJ0005 BCBK8MRJ0006 | M1/HCGS/447393//SC DEMARC LOC: 1ST FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 1 M1/HCGS/447394//SC DEMARC LOC: 1ST FLOOR COMMON TELCO ROOM WALL MOU DEMARC LOC Continued: WALL MOUNT SLOT 1 M1/HCGS/447395//SC DEMARC LOC: 1ST FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 3 M1/HCGS/447396//SC DEMARC LOC: 1ST FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 4 M1/HCGS/447397//SC DEMARC LOC: 1ST FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 1 M1/HCGS/447398//SC DEMARC LOC: 1ST FLOOR TELCO ROOM WALL MOUNT SL DEMARC LOC Continued: MOUNT SLOT 2 Jack Type: RJ48C | 2015-06-12 | 7/24/2015 9/21/15 | 2015-08-21 | BPDD | 2015-07-31 | 2015-08-21 | unitedhealthgroup-64839 | 763/694-7370, masroor_khan@optum.com |  | 5/28- Melissa working on order 6/4- submitted to ShaRita 6/11- lcon verification complete. CORRECTED ADDRESS ON SUBJECT LINE PROVIDED BY LOCAL CONTACT, RUSSELL to 775 not 755. Order submitted to provisioning 6/17- FOC date 7/24 due to construction job 6/25- FOC date 7/24 7/2- lec has a build on their side and the delivery of the service will be delayed. 7/9- FOC date 7/24 due to build 7/17- FOC date 7/24 7/23- FOC date 7/24 7/30- Pending Loop Delivery. Per LEC, this one has apending work order, they will place new repeater with an ECD of 8/27 8/5- awaiting LEC to place new repeater with an ECD of 8/27 8/13- new FOC 9/21 there is a construction build necessary to turn up a MULDEM in order to complete the order. Escalations on builds are only being done in emergency situations. The ESD 9/21/15 has been provided. A better due date cannot be provided as of now. 8/19- FOC 9/21 8/27- FOC 9/21 9/3- ready for activation, customer notified
2015-07-31 | ShaRita | CA005-05-IJ | 7067 N. Mariposa Street, Fresno, CA 93702- AT&T access | 3072, 2 x T1 md5 UHGVERbgpbqZyofa Building demarc | O-1363935 Quote ID: 191550371 Order Request 191550684 Service Order 191578422 Service Order(s) [ 191578422 ] has been created for Order Request 191550684 21379830 access 21379829 port | 191578422 |  | 5631439 | 1.5 | N1022420 / ADD N1022419 / ADD C1024343 | 88/HCGS/533273//PT DEMARC LOC: NIU/RJ AT 1.1 MPOE. DUAL MNT#4, S DEMARC LOC Continued: MNT#4, SLOT 2, TAGGED. 88/HCGS/533272//PT DEMARC LOC: NIU/RJ AT 1.1 MPOE. DUAL MNT#4, S DEMARC LOC Continued: MNT#4, SLOT 1, TAGGED. Jack Type: RJ48C | 2015-08-07 | 2015-08-19 | 2015-08-17 | BPDD (standard 8/31) | 2015-08-26 | 2015-08-19 | UnitedHealthGroup-65289 | 91 91600 84400 harish_kandpal@optum.com |  | 8/3- Sent to ShaRita 8/5- ShaRIta working on order 8/13- FOC 8/19 8/19- ready for activation, customer notified
2015-06-25 | ShaRita | FL113-02-IJ | Wellmed 141 Webb Dr, STE 200 Davenport, FL 33837 | 7xT1, 10752 | CW Order (ID : 191382124) NSPE0009421426 SUPP TO CANCEL ORDER: IQBK6QH2A P2114859 RE-ISSUE ORDER: IQBK6XN7 P2116331 | 8404985 | P2116331 |  | 1.5m | BCBK8SVR0001-0007 | 69/HCGS/438729//GTES DEMARC LOC: MAIN 1ST TELCO SHELF 3 POS 1 OF 4 SSUMM 69/HCGS/438730//GTES DEMARC LOC: MAIN 1ST TELCO SHLF 3 POS 2-4 69/HCGS/438731//GTES DEMARC LOC: MAIN 1ST TELCO SHLF 3 POS 3-4 69/HCGS/438732//GTES DEMARC LOC: MAIN TELCO 1ST 69/HCGS/438733//GTES DEMARC LOC: MAIN 1ST TELCO SHELF 4 POS 1 OFV4 69/HCGS/438734//GTES DEMARC LOC: MAIN 1ST TELCO SHELF 4 PO S2 OFV4 69/HCGS/438735//GTES DEMARC LOC: MAIN 1ST TELCO SHELF 4 POS 4 OF 4 Jack Type: RJ48X | 2015-07-21 | 2015-07-30 | 2015-07-27 | bpdd | 2015-08-06 | 2015-07-28 | unitedhealthgroup-64823 | 763744-0981 glenn_moore@optum.com |  | 6/26- submitted to ShaRita 7/2- order submitted to provisioning 7/9- sent an email to provisioning requesting ASR be sent asap 7/17- pending capacity before ASR can be sent 7/23- FOC date 7/30 7/30- ready for activation, customer notified
2015-07-08 | ShaRita | C1352-04-IJ | 701 Grant Ave Suite 709, Lake Katrine, NY 12449- VZT | 3072, 2xT1 UHGVEReccgas4Usp9 Building DMARC - 1st Floor Telco room | O-1344968 Quote ID: 191428201 Order Request 191428359 Service Order(s) [ 191467422 ] has been created for Order Request 191428359 21299881 access 21299880 port | 191467422 | N1021949 N1021948 | 5623739 | 1.5m | C1023708 N1021949 N1021948 | 33.HCGS.853424..NY 1st flr telco rm slot 16 of 28 rj48c tagged not ext 33.HCGS.853423..NY 1st flr telco rm slot 20 of 28 rj48c tagged not ext | 2015-07-20 | 2015-07-28 | 2015-07-27 | BPDD Stadard 7/30 | 2015-07-31 | 2015-07-27 | UHG_ECC-65418 | 763-744-2265 travis_dent@optum.com |  | 7/9- submitted to ShaRita 7/17- order submitted to provisioning 7/23- FOC date 7/28 7/30- ready for activation, customer notifed
2015-05-22 | ShaRita | C1093-05-IJ | ATT Secaucus Data Center c/o Wipro LTD 15 Enterprise Ave, Secaucus NJ 07094 | Copper, RJ45 100mg Ethernet circuit | O-1312023 Quote ID: 191219968 Order Request 191220053 Service Order 191234491 created for Order Request 191220053 21142805 access 21142804 port NJY I145721 | 191234491 |  | 5608002 | 50M | E4005068 C1021655 | ea-fyvs-fyvs-0105 Demarc fl 1 cabinet 1.78.8.0 left hard mm loop,tagged |  |  |  | BPDD (Standard 7/13) | 2015-07-15 | 2015-07-15 | uhg-ecc-65423 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 5/28- ShaRita working on order 6/4- order submitted to provisioning, pending ASR submission to LEC 6/11- customer request to change to Optical MMF LC. Provisioning working on order 6/17- pending CCR 1263849 RFT 7/8 minor build for OVERTURE ISG 1400 please add a MM GigE 850nm client card in slot 0.2., card shipped 6/25- pending CCR 1263849 RFT 7/8 minor build for OVERTURE ISG 1400. Installed, pending testing, certification 7/2- CCR 1263849 is complete. pending RFC test completion 7/9- The CCR’s are completed. Tcoms was stepped for dispatch out to complete the install and testing. email sent to the NJ dispatch group to advise 7/17- ready for activation, customer notified
2015-05-12 | ShaRita | CA004-02-IJ | 3460 Katella Avenue Los Alamitos, CA 90720 | 100M, I will throttle down to 10M Optical SMF LC | O-1301694 Quote ID: 191175707 Order Request: 191175897 21131181 access 21131180 port | 191201393 |  | 5606892 | 1.5M | E4005048 C1021623 | 81/KEGS/506998//GTEW 1st Flr MPOE, Wallmounted on North Wall, Tagged, Not Ext | 2015-06-02 | 2015-07-16 | 2015-07-10 | BPDD (standard 7/1) | 2015-07-23 | 2015-07-10 | unitedhealthcare- 64859 | 763744-0981 glenn_moore@optum.com |  | 5/12- submitted to ShaRita 5/21- early site survey scheduled for May 22 5/26- pending site survey results 5/28- site survey completed, order being submitted to provisioning 6/4- FOC date 7/16 6/11- FOC date 7/16 6/25- FOC date 7/16 7/2- FOC date 7/16 7/9- Please ensure access is secured on Plant testing date, 7/13 as well as FOC date 7/16 7/17- ready for activation, customer notified
2015-02-12 | ShaRita | C1333-05-IJ | 9910 Maple Street , Omaha, NE 68114 | 200M, John will throttle down to 150M, Optical, SMF LC MD5 UHGVEReccgas4Usp9 | O-1205260 Quote ID: 190831313 Order Request 190831500 Service Order(s) [ 190852688 ] has been created for Order Request 190831500 20844116 access 20844115 port | 190852688 |  | 5570991 | 90M | C5000806 E5001024 | 21.KFGX.000412..COXC. 1ST FLOOR CUSTOMER DATA ROOM RACK #21 | 2015-02-25 | 2015-04-09 | 2015-04-06 | bpdd (3/30 Standard) | 2015-04-16 | 2015-07-15 | UHG-ECC- 65478 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 4/6- circuit delivered, awaiting John to provide demarc extension info 4/15-awaiting John to provide demarc extension info before order can be stepped to dispatch to request beas installation 4/23- John confirmed demarc. Supp'ed order to request beas installation be scheduled. 4/30- per field tech, tech could not find the circuit to rack J21, nor could he find it in the cox rack either. asked John to help confirm where the demarc was extended 5/7- per onsite contact Verizon tech installed beas. Waiting customer to confirm that circuit has been extended to beas 5/14- per customer, we are still working on cabling for the extension within the data center. waiting on information from them to determine when we will have cabling installed. 5/26- customer still working on cabling for the extension 5/28- customer still working on cabling for the extension 6/4- extension complete, pending beas installation 6/11- order on hold, Extended demarc was ran with single mode fiber. The extension needs to be multimode. Will return when customer has ran mmf. 6/17- order on hold, Extended demarc was ran with single mode fiber. The extension needs to be multimode. Will return when customer has ran mmf. 6/25- order on hold, Extended demarc was ran with single mode fiber. The extension needs to be multimode. Will return when customer has ran mmf. 7/2- order in jeporady of being cancelled. please advise when demarc extension will be complete. 7/9- John confirmed that end user fixed the demarc extension for MMF. awaiting scheduling of beas installation 7/17- ready for activation, customer notified
2015-05-22 | ShaRita | C1246-05-IJ | 200 North Nash Street El Segundo, CA 90245 | Copper, RJ45 100mg Ethernet circuit | O-1312023 Quote ID: 191219968 Order Request 191220053 Service Order 191234448 created for Order Request 191220053 21142817 access 21142816 port | 191234448 |  | 5608004 | 50M | E4005069 C1021656 | ea6hr 6hr 0028 demarc per CLR 1st floor colo R 2.2.5c:0.4. Labeled ckt ID on the Overture and on the hard loop with a red Vz tag. |  |  |  | BPDD (Standard 7/13) | 2015-06-12 | 2015-06-12 | uhg-ecc-65458 | Scott Moyer 763-7442154 scott_moyer@optum.com |  | 5/28- ShaRita working on order 6/4- order submitted to provisioning, pending ASR submission to LEC 6/11- pending RFC testing 6/18- ready for activation, customer notified
2015-03-31 | ShaRita | CA204-02-IJ | 2562 State Street, Suite D, Carlsbad, CA 92008 | 3072, 2xT1 MD5 UHGVERbgpbqZyofa | Opp ID O-1250252 Quote ID: 191002757 Order Request 191003424 Service Order 191004874 20954593 access 20954592 port | 191004874 |  | 5584846 | 1.5Mb | C1019400 N1018188, N1018189 | 19/HCGS/625635//PT (N1018188) DEMARC LOC: SHELF 1 SLOT 1 DEMARC 19/HCGS/625636//PT (N1018189) DEMARC LOC: SHELF 1 SLOT 3 DEMARC Extended Wire (Yes or No): No EW Reason/Location:LCON REFUSED Jack Type: RJ48C | 2015-04-02 | 2015-04-15 | 2015-04-14 | BPDD (standard 4/22/14) | 2015-04-20 | 2015-04-16 | unitedhealthgroup-65125 | 210-877-7919 chris_spoor@optum.com |  | 4/2- awaiting provisioning to submit ASR to LEC 4/9- FOC date 4/15 4/16- ready for activation, customer notified
2015-03-31 | ShaRita | CA203-02-IJ | 2067 W. Vista Way, Suite 280, Vista CA 92083 | 3072, 2xT1 MD5 UHGVERbgpbqZyofa | Opp ID O-1250252 Quote ID: 191002757 Order Request 191003424 Service Order 191004873 20954966 access 20954965 port | 191004873 |  | 5584864 | 1.5Mb | C1019405 N1018192, N1018193 | 19/HCGS/625626//PT (N1018192) DEMARC LOC: NIU 0.1 QUAD 1 SLOT 3 Extended Wire (Yes or No): YES EW Reason/Location:SUITE 280 SERVER ROOM 19/HCGS/625627//PT (N1018193) DEMARC LOC: NIU 0.1 QUAD 1 SLOT 4 Extended Wire (Yes or No): Yes EW Reason/Location:NIU 0.1 QUAD 1 SLOT 4 Jack Type: RJ48C | 2015-04-02 | 2015-04-14 | 2015-04-15 | BPDD (standard 4/22/14) | 2015-04-17 | 2015-04-15 | unitedhealthgroup-65128 | 443-853-3646 edward.mclaughlin@optum.com |  | 4/2- awaiting provisioning to submit ASR to LEC 4/9- FOC date 4/14 4/15- ready for activation, customer notified
2015-03-31 | ShaRita | CA202-02-IJ | 2067 W. Vista Way, Suite 280, Vista CA 92083 | 3072, 2xT1 MD5 UHGVERbgpbqZyofa | Opp ID O-1250252 Quote ID: 191002757 Order Request 191003424 Service Order 191004872 20954907 access 20954906 port | 191004872 |  | 5584856 | 1.5Mb | C1019403 N1018191, N1018190 | 19/HCGS/625620//PT (N1018190) DEMARC LOC: -1.1 TERM, SHELF 1, SLOT 1, SNAPJACK DEMARC LOC Continued: SNAPJACK PORT 2 19/HCGS/625621//PT (N1018191) DEMARC LOC: -1.1 TERM, SHELF 1, SLOT 2, SNAPJACK DEMARC LOC Continued: SNAPJACK PORT 3 Extended Wire (Yes or No): NO EW Reason/Location:LCON REFUSED Jack Type: RJ48C | 2015-04-01 | 2015-04-13 | 2015-04-10 | BPDD (standard 4/22/14) | 2015-04-16 | 2015-04-13 | unitedhealthgroup-65133 | 443-853-3646 edward.mclaughlin@optum.com |  | 4/1- pending FOC date 4/9- FOC date 4/13 4/15- ready for activation, customer notified
2015-10-30 | Varun- B end | UE505-01-IJ | IBN Sina Bldg,Bldg No 27,Block B, Unit 201, 2nd Floor, Dubai Healthcare City, 20th Street, Oud Metha Road, Dubai, United Arab Emirates | 4M ethernet | 1-1577844878 SO 5819114 – Port SO 5819115 – Access |  |  |  | 2.048Mbps | W1C12889 port W1C22357 access |  |  |  |  | BPDD | appearance | 2016-03-23 | Unitedhealthgroup-64875 | 987-313-9388 anupam_datt@optum.com | John thinks it's active | 10/30- Varun generating SOF 11/19- pending SOF 12/4 - SOF returned by john, but some pages that needed to be signed wee missing 12.15- SOF with Verizon and being processed 1/6- Sent to Anupam and john for TEV 1/12- LCON confirmed below that the site will only be ready on mid-March order will be Parked for the meantime and will be Entered in F&E by February. 2/3- orders entered. 2/4- CUSTOMER IS NOT READY. SERVER ROOM AND CABLING WORK IS STILL ONGOING. We can not progress to the PTT until the site is ready. 2/18- CUSTOMER IS NOT READY. SERVER ROOM AND CABLING WORK IS STILL ONGOING. We can not progress to the PTT until the site is ready. 2/26- per John site readiness may be mid march PTT will take 30 days after site readiness to deliver circuit 3/21- HI DANIELA, ALL, PLEASE BE INFORMED THAT WE ARE NOT ABLE TO DELIVER THE SERVICE SINCE THE BUILDING MANAGEMENT IS NOT ALLOWING ACCESS FOR DU FE. APPRECIATE YOUR PROMPT SUPPORT TO DO THE NEEDFUL AND GRANT ACCESS APPROVAL WITH YOUR BUILDING MANAGEMENT TO RESUME THE INSTALLATION AND SERVICE DELIVERY. 3/23- order now ready for activtion
2015-11-06 | B end Varun | II523-06-IJ | Oxygen Blvd - Tower D Floors Ground through 3 Plot No 7 Sec 145, Noida | 500M, I will throttle down to 300M | OVI# 1-1571357753 s/o 5798003 - 5798004 Port & Access |  |  | 5724411 | 90M | W1C16373 (port) W1C16374 (access) | Bharti |  | 2016-03-11 |  | BPDD |  | 2016-04-07 | unitedhealthgroup-65078 | 981-005-9326 pradeep_yadav@optum.com | activated with Pradeep 5/17 | 12/10- varun verified PTT, order progressing 12/17- asked Sarvesh to confirm handoff again 12/21- Pradeep confirmed handoff 1/6- Order was placed to PTT last December 22, 2015. 1/13- We have a FOC date of March 11, 2016 for this link. 2/18- FOC date March 11th but working to improve due date. Physical work has been completed, working to complete logical work. /25- THERE IS ISSUE WITH CABLING PERMISSION ON CUSTOMER SITE WHERE IN CUSTOMER IS REQUESTING FOR DELIVERY CHALAN FOR CABLE AND AS PER PTT THEY DONT HAVE THIS DOCUMENT FOR PATCH CORDS, CABLES ETC... BUT CAN SHARE THE DETAILS ON PTT LETTER HEAD AND CUSTOMER IS CHECKING THIS INTERNALLY. 3/24- asking Sarvesh if he has approvals 3/28- PTT Team has already delivered and install the fiber Patch cables at Noida site and they are currently testing the link. 3/29- test could not start last week as the SFP got fault which we are getting replaced today post which we will start the stability test 4/1- Yesterday team was there on site to start the stability test but this could not start as PTT had some issue for which they have involved their NOC team to resolve and should be fixed shortly 4/7 - ready for activation notice sent
2015-08-12 | B end- varun | II747-02-IJ | RNH order BSNL IDC 8th and 9th Floors, MTNL Telephone Exchange Fountain, Building II, Mumbai, India Target date Nov 15th, deliver to 8th floor MMR.. | 1G, I will throttle down to 500M Single Mode Fiber LC | OVI# 1-153813564 • 5746103 - • 5746104 access New OVI 1-1613200243 new s/o 5847976 5847977 |  |  |  | 20 Mb | Verizon circuit: W1C31564 ; Tata Communication Service ID: 091MUMB515015005405 |  |  |  |  | bpdd |  |  | Unitedhealthgroup-64949 | 763-744-1727 marcus_boog@optum.com | ` | 4/11- per BSNL The output from the equipment will be LC Optical. Then thereafter any interface can be given by using relevant patch cord. 4/14- AT A-END, CUSTOMER WILL PROVISION CIRCUIT WITH HANDOFF AS "SINGLE MODE FIBER WITH LC CONNECTOR" THIS WILL GO TO BSL FMS/ODF AT LVSB, PRABHADEVI AND FROM THEIR_TCL WILL EXTEND CIRCUIT TILL VERIZON MMR ODF. UHG WILL SHARE BSNL LINE READINESS DATE IN NEXT WEEK 4/28- pending BSNL infor from UHG. We are working in provisioning in parrallel 5/5 pat Moran is looking to get delivery info from BNSL 5/19- pending mux infor from BNSL 5/23- Verizon loop i.e. optical cross connect at LVSB location has been built and we have kept fiber pair ready for patching at BSNL device. Please revert back with exact rack details, so we can extend fiber patch cable up to that point. Please note, physical patching will be done by BSNL engineer at LVSB end, circuit handoff is SMF-LC type. 6/9- Shridhar to Please arrange a loopback at BSNL FORT towards prabhadevi. 6/15- order ready for activation, BNSL still needs to extend to UHG rack. 6/17- activation letter sent
2016-04-28 | B- end Ezequiel | BZ508-02-IJ | Mind Solutions Avenida das Americas, 8445 Barra da Tijuca Rio de Janeiro, Brazil 22793-081 | 100mg acess 20mg port |  |  |  |  | 2mg |  | LEVEL 3 PTT |  |  |  | BPDD |  |  | unitedhealthgroup-64701 | 715-841-7731 sonja_d_mroczynski@uhc.com |  | 4/28- SOF sent to John 6/20 - per John order is cancelled
2016-01-11 | Varun- B end | n/a | Hyderabad port change | W1C03340 / W1C03341 | 5884842 |  |  |  |  | W1C03340 / W1C03341 | [9 empty] | completed Friday July 15th with Harish. | Attached is the revised SOF Only the port pricing has changed , rest all remains same. the difference between 200 and 300 MB Port is 2777 MRR. Fx 63 It’s a minor difference, let share this with UHG to see if they agree to continue on 300 mb 3/24 engineer wants to move forward with port chnages, John will sign 6/10- Check with Varun to see if this is in process. 6.14- downgrade is in process. TEV completed 6/23- order is now ready for downgrade
2016-07-12 | ShaRita/Alex | n/a billing change | W0Y51076 | circuits needs to have one appearance only – they are currently billing for 2. | CW Order (ID : 193259758) NSPE0010466839 | 8833487 | [14 empty] | 7/13- submitted to OM
2016-07-12 | ShaRita/Alex | n/a billing change | W0Y51078 | circuits needs to have one appearance only – they are currently billing for 2. | CW Order (ID : 193261472) NSPE0010466913 | 8833417 | [14 empty] | 7/13- submitted to OM
2016-07-12 | ShaRita/Alex | n/a billing change | W0Z66371 | circuits needs to have one appearance only – they are currently billing for 2. | CW Order (ID : 193261546) NSPE0010467184 | 8833395 | [14 empty] | 7/13- submitted to OM
2016-07-12 | ShaRita/Alex | n/a billing change | W1B05870 | needs to be changed to the 10GLANPHYPT from the current LAN PHY MPL ENDLINK | CW Order (ID : 193261718) NSPE0010467306 | 8833297 | [14 empty] | 7/13- submitted to OM
2016-08-09 | B end | n/a | UNITEDHEALTH GROUP , TOWER B 10TH FLOOR,UNITECH CYBER PARK Sector 39, Gurgaon , 122002 Ph: 09811273848 | disconnect | NSPE0010254404 22530182 access 22530181 port |  |  |  |  | T_ C1010824 A_E3004951 | [10 empty] | 8/12- disconnect being worked 8/25- order being worked. 9/7 disconnect completed
2016-09-01 | Sharita | n/a | Node to Node 10G Single - 10 Gig Unprotected Ethernet appearance Single mode fiber, LC connector A End: Chaska Data Center 1707 West Creek Lane, Chaska, MN 55317 MDF 700 TCOMS ID: M6L7/01 Z end: Elk River Data Center 14100 Business Center Dr, Elk River, MN 55330 Server Room 1 TCOMS ID: LLM8/06 |  | opportunity O-1751598 | 8897980 | [14 empty] | 9/6- Alex submitted tin
2015-11-24 | B End- Jonathan | UK508-03-IJ | Floor 3, Building 8, Vantage Point Business Village Mitcheldean Gloucestershire UK GL17 0DD | Please use Talk Talk as last mile provider 100M, I will throttle down to 10M Base TX | O-1452730 1-1607758437 S/O 5835836 |  |  | 5731840 | 3072 | [5 empty] | BPDD |  |  | unitedhealthgroup-65064 | leslie.isaac@optum.com |  | 3/29- pendign TEV from Leslie I’m not based at the UK508 site I’m afraid so I don’t have the answers you are looking for; these would ideally need to come from Will Ruck or Adam Taylor. Will responded to TEV. 3/31- Will responded to TEV, order progressing 4/7- FIRM TAIL DELIVERY DATE: TBP 6-MAY 4/14- BT didnt' have accesss BT ORDER REFERRED BACK 11/04. BT HAVE CALLED ALL 3 CONTACTS, ADAM TAYLOR 01594545100, WILL RUCK 01594545130, AND THE HELP DESK 0800 072 7748 WITH NO ANSWER. 4/21- BT reaching out to lcon again for access 4/27- Asking if BT was able to get a hold of lCONS 4/28- BT can't deliver. VF can on-net 5/5- Seeing if this can be on a seperate mux 5/19- asking what came out of the pTT review. 6/2- pending news from GL team 6/17- in order to provide diversity, both circuits would need to be provided by Verizon 9/29- per John cancelling
2016-07-20 | B end Varun | PH503-07-CJ | 8th - 9th Floor Calyx Cetre, Cebu I.T. Park, Apas, Cebu, Central Visayas, Philippines, 6000 | downgrade the port from 600M to 400M on circuit w1c24000 | [5 empty] | w1c24000 | [10 empty] | 8/4- SOF provided to John 10/4- John asked to cancel this order to have both the port and access downgraded.
2016-03-31 | B end | IR508-02-IJ | Optum Block CSpencer DockDublin 1Ireland Dublin Leinster- need June 1 | 200 mg access 100mg port RJ45 SOO Letterkenny - circuit ID W0Y12673 no dport available | OVI: 1-1627201775 s/o 5865560 |  |  |  | 21680, if in contract | W1C36069 |  |  |  |  | BPDD |  | 2016-07-19 | UnitedHealthGroup- 64671 | 214-647-4442 Leslie.Isaac@optum.com | 5:53 AM 9/20/2016 PING TEST PASSED on CE int speed: auto duplex auto. 5:53 AM 9/20/2016 advised to hard coded to speed 1000 duplex full. 5:54 AM 9/20/2016 he will call us back on or before Sept 30, 2016 for BGP turn up. | . 5/16 The site survey has been arranged for 15:00pm on Monday afternoon 16th May. 5/19- ISSUES: VM DO NOT OFFER AN EXPEDITE, BUT DELIVER ORDER ASAP FIRM TAIL DELIVERY DATE: TO BE PROVIDED ON 15TH OF JULY 5/26- Site survey went well. This is splicing exercise only connecting back to Guild Street and reliant on ISM who manage internal Cross Connects in the building. Reliant on ISM to provision the Cross Connect from the street to the Customers Comms Room. We will progress asap from our side but ISM can be quite slow in delivering Cross Connects. We can provisionally set the planned handover date as July 29th. This is to allow for project sign-off and ISM lead-times. If ISM confirm a shorter lead-time once order is placed, we can review the planned delivery date. 6/2- AWAITING PTT INSTALLATION - FOC DATE 29TH OF JULY 6/27- I received ISM handover details yesterday and I’ve scheduled our splicing works for next week. The CPE install is then scheduled for the following week (w/c 4th July). All going to plan, we should be able to handover to Verizon by Monday July 11th. 7/15- PTT delivered, pending site access for field engineer to do end to end testing. 7/19- ready for activation
2016-01-16 | B end | CN518-02-IJ | Catamaran 555 Industrial Drive, 3rd Floor Milton ON L9T 5E1 | 100M, I will throttle down to 10M | 5871225 and 5871226 (access) | TIN 8719470 |  |  | 1.5M | W1C38337 (port) W1C38336 (access) |  |  |  |  | BPDD |  | 2016-06-13 | unitedhealthgroup-64727 | 763-744-1847, donald_r_osborn@optum.com |  | 1/15- Siva sent for SOF 1/28- checkign SOF 2/25- pending SOF 4/15- pending SOFS back from UHG 4/29 SOF back from UHG and is being processed 5/5- order with oe 5/16- FIRM TAIL DELIVERY DATE: TO BE PROVIDED AROUND 15-JUNE-2016 5/20/2016: Circuit install: 6/10/2016; FOC: 6/15/2016. Site access required on 6/10. 5/30/2016: Rogers advised they might be able to install on 6/2 and hand off circuit on 6/7 if test went well. 5/31/2016:5/31/2016: Rogers on site to install. Site contact Laurie Faulknor directed him to Cabinet 3. Install completed. Rogers to test and then hand over circuit to VZ. 6/9- 5871226 6/6/2016: Rogers advised site not ready for install; customer re-scheduled install to 6/10; circuit delivery date 6/15 6/7/2016: Customer pushed install date again to 6/8 ready for activation on 6/13
2015-10-06 | B end Ian | UUK04-09-IJ | 20 Grenfell Road, Maindenhead, England SL6 1EH | 100mg access 20 mg port SOO Letterkenny - circuit ID W0Y12673 Base-TX, RJ45 Floor 01 (MDF Room) | O-1413340 s/o 5787961 |  |  |  | 1536 | W1C12889 | Vodaphone |  |  |  | BPDD | 2016-03-16 | 2016-04-11 | unitedhealthgroup-65150 | leslie.isaac@optum.com |  | WE ALWAYS PLANNED TO RETIRE THE DS3 CIRCUIT ONCE OUR NEW ETHERNET CIRCUIT WAS UP AND RUNNING, SO HAVING THE NEW CIRCUIT DEPENDING ON THE OLDER DS3 KIT IS NOT A SOLUTION WE ARE HAPPY WITH AS WE WANT TO REMOVE ALL THAT EQUIPMENT FROM OUR RACKS. this info sent to VF 3/24- CURRENTLY THE SDH EQUIP IS THE ONLY METHOD AVAILABLE TO SUPPLY ETHERNET SERVICES TO THIS LOCATION. DUE TO THE BUILD IN THE AREA. MAYBE IN THE FUTURE, WE CAN LOOK TO REMOVE THE SDH EQUIP AND JUST PROVIDE FIBRES DIRECT TO THE VODAFONE ADVA BOX AS FOR THE AGE OF THE EQUIP 2012, THAT IS NOT AN ISSUE FOR VODAFONE AS WE HAVE SPARE STOCKS OF THE EQUIP. SO THE EQUIP HAS GONE END OF SALE, BUT NOT END OF LIFE. Melissa to send to leslie and copy john 3/29- Leslie oked equipment and to proceed with circuit install. 3/31- access approved for 4/1 4/7- ETE test completed, confirming if circuit is ready for activation 4/11- order is now ready for activation
2016-09-02 | B- end Varun | II757-02-IJ | Tata Communications, No.226, Red Hills Road, Kallikuppam, Ambattur Chennai, Tamil Nadu 600053- new SOO host. | 500mg port 1 gig access. | 1-1679806929. • port SO : 5940233 • access SO : 5940234 |  |  |  | 1.5m | [5 empty] | BPDD |  |  | UnitedHealthGroup- 64568 | 0091-9900022164 emad@optum.com |  | PTT FOC 12/15. RFS 12/15- circuit in ETE testing 12/29- We are waiting for GLP status to confirm the circuit readiness for activation. Once provided, I will send the completion letter for a plug and play option to customer for circuit activation on their end.
2016-01-16 | B end | CN521-02-IJ | Catamaran 3960 Quadra Street, Ste 505 Victoria, BC V8X 4A3 | 100M, I will throttle down to 10M | s/o 5868656 (port) and 5868657 (access) | TIN 8720315 |  |  | 1.5M | W1C37395 (port) W1C37394 (access) |  |  |  |  | BPDD |  |  | unitedhealthgroup-64728 | 763-744-0981 glenn_moore@optum.com |  | 1/15- Siva sent for SOF 1/28- checkign SOF 2/25- pending SOF 4/15- pending SOFS back from UHG 4/29 SOF back from UHG and is being processed 5/5- ASR sent to PTT, pending response 5/17/2016: Shaw completing inside cabling this week. Targeting to complete by 5/30. This is only tentative and FOC Firm Order Commit date will be provided after cablling work is done. 5/25/2016: Pending Shaw completion, then FOC will be provided. 5/27/2016: Circuit delivered; PVC built. Ready for activation.
2017-06-30 |  | CA165-07-IJ | 8880 Cal Center Drive Sacramento, CA 95826 South Side of Building | Gig UNI, 1000BaseSX MMF LC 50mg port 10mg access | 194265129 | [15 empty] | The circuits were delivered to the MPOE on the 1st floor north side of the building, extended through the risers, and terminated in the riser closet of the second floor. They should have been delivered to the 1st floor electrical room on the south side of the building.
2019-01-15 |  | TX079 |  | We need to place a move order to the carrier to move the existing telco circuit to Suite A (as the order indicated). BEAS was already moved via a trouble ticket. E4036994/ADD (27697730) C4014355/ADD (27697729) Time Warner Telecom TX/KXFN/056424/LVLC | 197939699 | Access (28380506)
2019-02-12 |  | PH510 | Building O UP North Science and Techno Park, Commonwealth Quezon City National Capital | Please add SOO to the following W1D43292 access W1D43291 SOO host PH550 pasig-city-phl_w1b26059-5505541 Please coordinate hotcut if needed. |  |  | (SO: 6280472 - W1D43292) | [13 empty] | 4/23 - SOO completed 4/22 - Prebuild has been completed 4/18 - service order created, waiting to get completion date 4/10 - Asked for update 4/4 - VZ internal change form created and submitted 3/28 - Asked for update 3/22 - Asked Varun for update 3/14 - Asked Varun if he can prioritize request 3/1 - APAC said sales must process so they OM team gets order package 2/27 - asked apac escalations team for update on change order 2/22 - sent to management asking to address 2/21 - asked APAC OM for an update on order 2/14 - sent request to APAC team for processing 2/21 - asked APAC OM for an update on order 2/14 - sent request to APAC team for processing
2018-08-30 |  | IR516-02-IM | Ground Floor & 4th Floor Suites / 2 Dublin Landings North Wall Quay North Dock Dublin D D1 Dublin D1 | Network Protocol / Encapsulation Ethernet PortCircuitSpeed 100Mbps Termination Type LC Ethernet Port Access Speed 200Mbps Handoff information Base-SX Ethernet Shaping 85% Gold CAR (1536k has no cost) 70000 Dmarc Location (floor/room) Ground Floor MDF room |  | OVI# 1-2032030573 | s/o 6236329 |  |  | W1D49308 |  | 6132947 | [8 empty] | 4/18 - Updating Gold CAR to 72000 as per order: 6280797 4/11 - LET/E3E TESTING COMPLETED, turn-up 4/19 4/9 - PTT has delivered access circuit 4/4 - FOC delivery 4-10 of April 3/28 - e-net confirmed that open eir have installed RAD box and handed their circuit to e-net, waiting to confirm schedule date for CIENA Box installation. should be within two weeks 3/22 - Asked Phil for update on agreement 3/14 - fiber splicing done, EIR is testing and needs to install RAD Box, hoping to be done by 3/22 2/21 - had call with customer IR team along with VZ IR team to discuss on 2/19 2/14 - best option is Enet using EIR, they are progressing order and they will provide Verizon on or around 2/21 with full scope of work 2/7 - Colt still not responding.....EIR open air has urgent order and we are pending response based on 2/21 SLA date or sooner 1/31 - asked for update, as of 1/25 EIR open air has not advised, colt contact from meeting was out on sick leave 1/18 - another site survey was taking place next Wednesday with enet. Also placing inquired to EIR for access 1/17 - still have not heard back from enet on site survey, followed up yesterday with enet for an update 1/9 - Colt has no conduit into building, they have a meeting for another site survey on 1/16. They are looking for different options on how to deliver 1/3 - asked OM team and local Ireland team for update 12/20 - FOC date will be sent Jan 3rd 12/13 - should get FOC from PTT on around January 3rd 12/6 - Pending FOC 11/29 - ASR sent 11/21 11/23 - TEV completed 11/21 11/8 - Asked Phil for update 11/1 - on 11/3 SOF sent back to Verizon 10/25 - Pending SOF signature from UHG 10/18 - SOF sent on 10/17 10/4 - Phil still working on SOF 9/27 - Asked Phil for update 9/20 - UHG asked what PTT, Phil chasing down and updating SOFs 9/13 - SOF sent to UHG 9/6 - pricing sent to Mel on 9/3 8/30 - order sent to Phil
2019-01-14 |  | II542-04-CM | Optum Global Solutions (India) Pvt. Ltd. (Unit-II)6th & 7th Floor, Tower-A,Oxygen Business Park Pvt. Ltd., - SEZ,Plot No. 07, Sector-144 | upgrade to 200 meg |  |  | 6257559 - W1C83926 for site II547 |  |  | 6268869 - W1C18272 | [10 empty] | 5/15 - upgrade completed 4/24 - Verizon outage. Port upgrade scheduled for 5/11 4/10 - Port upgrade schedule for 4/19 4/10 - Determined wrong location being tracked 3/28 - completed 3/22 - hot cut was 3/10, circuit upgraded 2/27 - got signed 3/1, sent to varun 2/21 - still waiting on approval 2/14 - still waiting for approvals, but said it was just approved 2/7 - Still waiting for approvals 1/31 - UHG sent for approvals 1/24 - UHG sent for approvals 1/17 - Shefali sent SOF to account team
2019-12-21 | Melbourne | AU507-06-IM | Level 25, 303 Collins Street Melbourne Victoria VIC 3000 Charlie Evangelio 6325883409 charlie_evangelio@optum.com | Network Protocol / Encapsulation Ethernet PortCircuitSpeed 20Mbps Termination Type LC Ethernet Port Access Speed 50Mbps Handoff information Base-SX Ethernet Shaping 85% Gold CAR (1536k has no cost) 11000 Dmarc Location (floor/room) 1st Floor MDF Room |  | 1-2062297455 | 6268867 / W1D59605 Port 6268868 / W1D59606 Access | [13 empty] | 5/15 - completed 5/9 - Testing scheduled for 5/13 (monday) 5/6 - Loop has been installed waiting on testing 4/11 - FOC DATE ACCORDING TO TELSTRA IS 3RD MAY 2019 4/3 - Pending FOC Date (will be available within 15 business days) 3/28 - Site survey booked for 3/26 asking for further update 3/22 - Still pending TEV from LCON Robert / UHG 3/14 - Pending TEV from LCON Robert / UHG 3/11 - orders generated 2/27 - Shelfai working with back end teams to create order 2/21 - asked Varun and Shelfai for order number, only have OVI. Also sent request to APAC escalations to see if they can get a copy 2/14 - asked Varun and Shelfai for order number, only have OVI. Also sent request to APAC escalations to see if they can get a copy 2/7 - asked Varun and Shelfai for order number, only have OVI 1/31 - asked for update from Varun 1/24 - sent UHG updated SOF 1/17 - Shefali sent updated SOF with modifications per request 1/11 - Shefali said PTT is Telstra and sent SOF 1/10 - Asked Shefali for update, she was working on ecost and to avoid AAPT 1/3 - Shefali was working on SOF 12/27 - provided bill copy on W0X83226 to mirror 12/26 - Asked for specific details to process order
2019-02-12 |  | PR517-05-CM | MONTEHIEDRA OFFICE CENTRE, 9615 LOS ROMEROS AVE SAN JUAN, PR. 926 | Please process the attached port and gold CAR upgrade in Puerto Rico. Circuit ID C5005749/E5013251 Circuit type Ethernet Port Speed 200Mbps Ethernet Port Access Speed Gold CAR (1536k has no cost) 100000 ( 100 Mbps) | UHT Site Engineer Sahil Tuteja UHT Site Engineer Phone 8285670647 UHT Site Engineer Email sahil_tuteja@optum.com | 198682583 | Order Request 198682125 |  |  | NSPE0012855066 | [10 empty] | 5/21 - Upgrade complete 5/16 - upgrade ready. 5/20 10:15PM 5/9 - upgrade submitted 5/2 - port upgrade has been created 4/26 - signed amendment/new order being created 4/4 - Amendment sent out: 3/28 - John asked Jill for better pricing. 3/22 - 3/14 - amendment sent to Becky and Jamie on 2/26, pending customer signature 2/27 - amendment sent to Becky and Jamie on 2/26, pending customer signature 2/21 - pending amendment and pricing with PCM 2/14 - New SOF must be generated since speeds not in existing one.
2019-06-03 |  | PR517-02-IM | 9615 AVE LOS ROMEROS, SAN JUAN, PR 00926-7036, Puerto Rico | Please process gold CAR upgrade in Puerto Rico. 90 meg Circuit ID C5005749/E5013251 Circuit type Ethernet Port Speed 200Mbps Ethernet Port Access Speed Gold CAR (1536k has no cost) 100000 ( 100 Mbps) |  | Quote 198980213 | [14 empty] | 6/4 - Gold CAR upgraded to 90 meg 6/3 - Order submitted
2019-03-01 |  | C1581-05-DM | TOWER B, DLF CIBER GURGAON, 122002 IND. | Please process the disconnect for the following circuits in Pune, India. W1C11947 W1C11948 | S/O 6275121 - W1C11947 and S/O 6275125 - W1C11948 | NSPE0012780924 | [14 empty] | 5/30 - Order remarks were not updated. Ask order owner for confirmation. Confirmed billing stopped on 5/24 4/18 - Disconnect and billing stop 5/25 4/4 - preferred disconnect date 5/24 3/28 - Keyed into portal for disconnect by Melissa 3/22 - APAC said this is keyed in portal now, sent John and Mel BAN and auth code to key 3/11 - sent to APAC terminations team for processing
2019-04-01 |  | PP508-01-IM | 14th and 15th Floor Vector 2 Northgate Cyberzone, Filinvest City, Alabang Muntinlupa City | Access Line Speed: 1 Gbps Port Type: Ethernet Port Speed: 600 Mbps Port Category: Non-Standard CAR Category: Fixed EF Real Time CAR: 248.8 Mbps | W1D66876 W1D66877 | OVI # 1-2095518704 | Port SO: 6290059 - W1D66876 Access SO: 6290060 - W1D66877 |  |  |  | LCON CHARLIE EVANGELIO |  |  |  | Globe |  |  |  |  | PLDT and Radius are available | 8/8 - activation complete 8/6 - confirmed time 8/4 - Scheduled for 8/8 10-1pm Manila time: pending confirmation 8/2 - Having trouble activating 8/1 - Order Completed 7/25 - Circuit activation and testing started yesterday. Radius encountering errors 7/15 - FOC date 8/16 7/11 - multiple dates for FOC date given. Asking for confirmation: 8/16 or 7/31 7/3 - Approved Globe using Radius 7/1- Radius and PLDT pricing given 6/24 - Pending new LEC/agreement with Globe 6/12 - FOC date of 6/28 5/30 - Order placed to PTT. FOC DATE WILL BE AVAILABLE WITHIN 15BUSINESS DAYS 5/23 - order assigned ask for update 5/15 - Order submitted 5/9 - SOF signed 5/6 - New SOF sent to Melissa 5/2 - new SOF being generated based on new address by Melissa 4/18 - pending signed SOF 4/5 - pending signed SOF from UHG
2019-05-07 |  | PH510-05-CM | Building O UP North Science and Techno Park, Commonwealth Quezon City, National Capital 1101 | Please place an upgrade order to upgrade W1D43291 to 800mg no change to gold CAR | W1D43291 | OVI 1-2110385749 | 6302935 - port 6302936 – access | [11 empty] | LCON : RAJESH JOHN CATALONIA TEL # : 6327906177 EMAIL : RAJESH_CATALONIA@OPTUM.COM (invalid email address as per ISD) |  | 8/12 - 8/14 6am Manlia Time 8/9 - 8/14 pending time 8/8 - pending new upgrade time and date 8/1 - Upgrade scheduled for 8/4 at 9pm Manila Time: changed 7/29 - Globe finished access circuit: Pending scheduling for port upgrade 7/25 - Globe provisioning access circuit for update: Pending FOC date 7/16 - pending HOTCUT scheduling 7/10 - OM assigned 7/3 - Waiting for creation of SO. Will push to completion once created. 6/27 - Asked for update: Pushing for July 1 6/18 - Melissa sent signed SOF to Jill and Varun 6/13 - SOF updated and resent to Melissa 5/29 - SOF sent to Melissa: Pending Signature 5/22 - Pending SOF 5/15 - order originally cancelled due to miscommunication: pending SOF from Varun
2018-08-15 |  | IR508-08-IM | Block C, Spencer Dock, Dublin 1, Ireland Dublin Leinster | PortCircuitSpeed 300Mbps Termination Type LC Ethernet Port Access Speed 500Mbps Handoff information Base-SX MMF LC Ethernet Shaping 85% Gold CAR (1536k has no cost) 1500 | 2/22 - company name does not exist that Chris wants to use, so we have to create a new ban | OVI# 1-2093793584 | SO 6286626 |  |  | W1D65899 | SO 6286626 / Circuit ID W1D65899 OVI# 1-2093793584 | 6131466 | [8 empty] | 8/14 - scheduled for 8/20 8/8 - need new contact to deliver circuit 7/5 - Cross Connect complete: Confirmed FOC of 8/9 6/27 - Planned handover date of 8/2: Pending landlord providing cross connect in a timely manner 6/12 - FOC date 8/16 6/5 - PTT has 10-15 Bdays to provide FOC date after ASR sent 5/29 - Asked for Update: ASR Sent 5/23 - TEV completed 5/16 - Asked for update 5/9 - Order submitted- Mirror from original order 5/2 - Jill Reviewed with Chris S. 4/24 - Sent SOF for signature 4/18 - Creating new SOF: New name still not available 4/11 - Asked for update 4/4 - Customer has sign agreement needs to be countersigned by VZ 3/27- Agreement still with legal. 3/22 - Asked Phil for update on agreement 3/14 - Ovation agreement needed for name change on legal entity, VZ legal has it, asked for update from Phil 2/27 - Chris asked VZ to do a name change on SOF, asked Phil for update 2/21 - Still wiating on SOF to be sent back 2/14 - Still wiating on SOF to be sent back 2/7 - SOF sent for updated pricing, waiting on UHG Signature 1/31 - Phil updating the ecost with carrier and then new SOF....Phil sent new SOF 2/1 1/24 - asked customer which carrier, BT or Enet to proceed with order, advised to use Enet, new SOF being developed 1/17 - asked for update on Enet pricing from Ireland team, also ask customer if cooridnates were available for BT to quote 1/10- asked for update from Verizon Ireland telco team, got cost from Virgin, waiting on Enet and BT is asking for coordinates, ATT is using Colt 1/7 - Ireland telco team is working with carrier to get costs with new pricing 1/3 - landlord has cross connects charges and passing thru to PTT and is increasing cost to Verizon. We are updating the GL and will advise of increased cost 12/20 - circuit optimized, ASR generated and pending being sent 12/13 - Henry just sent back TEV 12/6 sent to henry laurequez and kevin cantor 11/29 - still pending TEV 11/15 - asked if orders were placed, could not find any pending. 11/8 - Customer signed on 11/2 11/1 - Mel said it was with approver in Ireland 10/25 - Mel was submitting SOF for approval on 10/18 10/18 - Pending SOF signature from UHG 10/11 - SOF sent to UHG 10/4 - issue with dport and dcar, new SOF needs generated 9/27 - asked for order numbers 9/20 - TEV sent back on 9/19 9/13 - TEV sent 9/6 - SOF sent to UHG, pending signature 8/30 - SOF sent to UHG, sent back with docu sign
2019-04-18 |  | PH507-01-IM | 16th to 20th Floor Axis Tower 2 Northgate Cyberzone, Filinvest City Alabang Muntinlupa, City, Philippines | 500meg Gold CAR 250000 |  | OVI: 1-2104078348 | PORT SO: 6298795 Circuit: W1D69644 ACCESS SO: 6298796 Circuit: W1D69645 | [7 empty] | Globe |  |  |  | Primary Contact Name: Ma Corazon C Hernandez Email: marion_hernandez@optum.com Phone Number: +6325883203 |  | 8/30 - Fiber work done. Per PTT Globe activation, installation and testing done. Joint testing with Verizon is also done 8/29 - Radius was unable to finish fiber laying. Did not have permit for 18 floor MDF 8/22 - Planned handover to Verizon 8/30 8/20 - pushing for 8/27 completion date 8/15 - Fiber Plan has been approved by Radius 8/8 - Ask for update (hold under construction) 8/1 - On track: Pending Fiber work to be done in next 3-4 days depending on approval 7/23 - Site readiness 7/28 7/22 - Hold: Installation site under construction: Target site readiness 8/23 7/16 - FOC date 9/2 as worst case scenario 7/10 - Site survey complete: FOC date within 15 business days 7/3 - Approved Globe using Radius 6/27 - OM assigned: Order placed with PTT; pending FOC 6/20 - Asked Varun for update: Call scheduled for Monday at 8am 6/13 - Asked Varun for update 6/4 - SOF signed 5/22 - pending signature 5/14 - SOF sent to Melissa: pending signature 5/9 - Waiting on SOF-Friday 5/2 - Varun providing access pricing 4/18 - pending signed SOF
2019-04-08 |  | II553 | Old Data Center - Dodda Banaswadi Main Rd - Harischandra layout - Jeevanhalli - Maruthi Sevanagar Bengaluru, Karnataka 560005 | 1 gig access 400 meg port gold CAR 250000 | 6295492 / W1D68588 -port 6295495 / W1D68589 – access | OVI # 1-2099286186 | [8 empty] | Airtel |  |  |  | Primary Contact Name: Deepaka Tulupule Email: deepaka.tulupule@optum.com Phone Number: +918049203611 Mobile Number: +918049203611 |  | 10/30 - Circuit Ready for activation 10/24 - PTT with access bandwidth capacity issue: Tentative ETR 10/29 10/17 - Oct 16th missed. Target Oct. 18th 10/3 - the target handover date is Oct 16, 2019 9/26 - Pending FOC date 9/18 - Order released from hold 9/17 - Site Ready 9/12 - MDF room is ready: Power in progress 9/11 - asked for update on site readiness 9/6 - Update will be provided monday regarding MDF readiness. 7/23 - Server room ready date 9/8 7/19 - Order on hold (customer site is under construction) 7/11 - FOC date 8/23 6/27 - TEV completed: Pending FOC within next 15 business days 6/20 - Pending TEV 6/13 - Order assigned to Order managment 6/6 - Asked Varun for update 5/30 - Asked Varun for update 5/23 - Order submitted 5/17 - Varun submitting order 5/16 - pending signature 5/9 - Sent for signature 5/6 - SOF created pending signature 5/2 - access has been provided: Varun creating SOF
2019-10-07 |  | II518 | 2nd Floor Eapens Timber 570 571 Sarjapur Road Bangalore, Karnataka |  |  | OVI # 1-2153482803 | 6333109 / W1C45306 | [13 empty] | 11/4 - upgrade complete 11/1 - 11/4 8am India confirmed 10/30 - Pending approval of 11/4 8am date/time 10/23 - OVI Number created: Pending Service Order creation 10/17 - SOF signed and returned 10/15 - SOF sent to Melissa for signature 10/7 - upgrade to 10mg and gold car to 5.5
2019-06-28 |  | II554-02-IM | 6th Floor of Block 2 of Phase 1 Building and a part of ground floor in Block 1 of Phase 1 Building in IT/ITES SEZ of M/s ITPG Developers Private Limited at Behrampur, Near Sector 59 | 1 gig access 500 meg port with gold car 350meg |  | OVI # 1-2124717812 | Port SO: 6317557 - W1D76903 Access SO: 6317558 - W1D76904 | [13 empty] | 11/14 - “The circuit is not giving up good results, PTT has been told to investigate matter.” 11/7 - PTT has completed ring however could not complete bandwidth reservation and circuit mapping. PTT to hand over early next week 10/31 - Pending new ring completion 10/24 - Power available onsite: Dispatch to be scheduled to install equipment: New ring still being created 10/17 - Major fiber damage on access ring due to road expansion. 10-12 day delay to create new ring 10/9 - Verizon hand off 48 hours after PTT delivers. Barring no issues 10/3 - PTT can deliver link by Oct-22/23,2019 9/24 - Link will be ready by first week of November 11/6. Will this work? 9/19 - Pending FOC date 9/6 - Pending FOC date: will be available in next 15 business days 9/5 - TEV completed 8/29 - Internal system error stopped order from progressing. Ticket created. ETR Friday/Monday 8/27 - setting up internal call 8/22 - asked for update 8/15 - asked for update 8/8 - asked Varun for update 7/31 - SOF signed and sent to Varun 7/12 - SOF provided to Melissa: Pending signature 7/11 - Pricing given: Order with 248.8 Gold CAR: Pending SOF 6/28 - requesting access pricing
2019-01-07 |  | Uk544-04-IM | Address 46 Aldwych3rd floor, Melbourne House City London State Zip UHT Data Engineer Larry Walsh UHT Data Engineer Phone # (317) 715-7773 UHT Data Engineer Email Larry_L_Walsh@optum.com UHT Project Manager Kevin Joslyn UHT Project Manager Email kevin_joslyn@optum.com UHT Project Manager Phone 952-833-6548 Site Contact Name Karin MomBourquette Site Contact_Phone + 2022666901 Site Contact Email MombourK@advisory.com | Network Protocol / Encapsulation Ethernet PortCircuitSpeed 10Mbps Termination Type LC Ethernet Port Access Speed 50Mbps Handoff information (International or High bandwidth only) Base-SX Ethernet Shaping 85% Gold CAR (1536k has no cost) 5500 Dmarc Location (floor/room) 3rd Floor/Server Room MDF ePVC Information VPN Name UnitedHealth Group DLCI 150 Routing Protocol (EBGP, RIPV2 Static): EBGP/AS 65117 Configuration Option - BGP MD5 encryption UHGVERbgpbqZyofa Dport (Y/N) Yes Dcar (Y/N) Yes Muticasting (Y/N) Yes - Receive Auto RP Access - MCI (Y/N) Yes Class of Service (Standard or Enhanced Traffic Mgmt) R12 Voice/Video Centric (90,60,5,10,5,20) |  |  | 6258062 |  |  | W1D56427 | needs to be configured to host w1c99764 | [8 empty] | Colt is available | 11/26 - Order cancelled 11/11 - Melissa asked to cancel order 10/30 - Waiting on signature from landlord 10/9 - Verizon continues to chase: no change in status 10/3 - no change in status 9/26 - Landlord solicitors are awaiting signature from the tenant before this can progress 9/18 - Waiting to hear back form landlord 9/11 - no change in status 9/5 - Waiting to hear back from Landlord 8/29 - VZ Legal have not received engrossments to be issued by the landlord. 8/29 - UK contact on vacation. Emailed backups for update 8/20 - Documentation being reviewed by Verizon 8/14 - Checking with Verizon solicitors to confirm all documentation is in order 8/1 - Could cancel this order and start new order with Colt 6/12 - Colt is available at this location 6/5 - waiting on Phillipe what other carriers are available 5/30 - With Lawyers: Checking with Phillippe for other carriers 5/22 - checking on other access carriers for this site 5/16 - With Verizon lawyers 5/9 - Back with Verizon lawyers 5/2 - Verizon lawyers made edits, waiting to hear back from landlord on new draft 4/18 - Landlord happy, currently with Verizon lawyers for approval 4/8 - waiting to hear back from landlord, will then pass back to Verizon contact 4/5 - wayleave back on. Getting VZ contact 4/4 - Waiting on wayleave form 3/28 - Followed on Tom's request for permission and wayleave form 3/22 - asked UHG on update for permission and wayleave form 3/14 - order on hold, install pack was provided to customer, waiting on permission to proceed or instructions that a legal wayleave is required 2/27 - order sent down to provsioning for circuit design, asked for update and if made it to site survey 2/21 - Asked UK local team for update on site survey 2/14 - TEV submited back to VZ on 2/12, order sent downstream and next steps is site survey 2/7 - TEV sent on 2/5, pending response 1/31 - pending order submission, then TEV 1/25 - UHG sent signed SOF 1/17 - Pending SOF signature 1/11 - Phil sent SOF to customer
2019-12-02 |  | PH503-09-CM | 8th - 9th Floor Calyx Cetre, Cebu I.T. Park, Apas Cebu, Central Visayas 6000 | upgrade circuit c5002793 to 500 mg | 200769629 | [15 empty] | 12/17 - Scheduled for 12/18 at 22:30 CT 12/12 - Melissa returned signed SOF: resent for signature: Order submitted 12/4 - sent to Melissa for signatures
2019-10-30 |  | PH001-02-CM | 18th Floor, The Link Bldg, Cebu I.T. Park, Lahug Cebu, Central Visayas 6000 | upgrade circuit W1D38268 to 100mg | 6341225 | [15 empty] | 12/16 - DECEMBER 14,2019 SCHEDULE OF UPGRADE HAS BEEN CANCELLED AND IT WAS RESCEDULE ON JANUARY 12,2020 AT 1:30AM EST 12/9 - Asking to be rescheduled to 2:30pm local time 12/3 - Hot cut set for 12/14 at 12:30pm local time 12/2 - asking for date for hot cut 11/21 - pending order creation 11/14 - returned with signature: sent to Varun 11/8 - SOF sent for signature 11/4 - 100 meg port with 50 meg Gold CAR 10/30 - Upgrade to 100meg Gold CAR?
2019-12-13 |  | PH510-06-CM | Building O UP North Science and Techno Park, Commonwealth Quezon City, National Capital 1121 | upgrade W1D43291 to 1 gig port. No change in Gold CAR |  | 1-2191590946 | SO 6353511 | [13 empty] | 2/6 - Upgrade scheduled for 2/22 10am local time 1/31 - service order created 1/29 - pending order validation and SO creation 1/23 - signed SOF returned. Order being submitted 1/10 - Updated SOF sent to Melissa 12/26 - Pending Signature 12/17 - SOF sent to Melissa. Melissa asking for gold CAR pricing
2020-01-08 |  |  | C0167608 Cologix Verizon Circuit | [17 empty] | 3/2 - completed 2/27 - IVUE scheduled for 3/2: working on site tech dispatch 2/20 - Syra is confirming status 2/13 - Tickets are open and being escalated: pending update on status of ticket 2/5 - Syra and Gayle working on further research 1/30 - Investigation is completed and issue found. Change Order being created. More updates next week 1/23 - Syra working with Gayle to get issue escalated and resolved 1/13 - Syra working on investigating the issue and how to solve 1/8 - move order?
2019-12-17 |  | II747-04-CM | 8th Floor, BSNL IDC, Fountain Building II, Fort Mumbai, Maharashtra 400001 | upgrade to 1 gig port W1C31564 | SO: 6357958 - W1C31564 | 1-2199359915 | [14 empty] | 3/23 - completed 3/13 - 3/21 at 11:30pm CT 3/12 - 3/21 after 22:15 CT if not this time then 3/27 or 3/28 3/9 - asking for 3/20 after 22:15 CT: Verizon Outage Time will not work 3/6 - waiting on ATT upgrade to complete: that is scheduled for 3/13 3/5 - no reponse yet from Sarvesh. Another email sent 3/3 - asked Sarvesh for date and time 2/25 - asking Sarvesh for date and time of hotcut 2/20 - Order numbers created: Pending hotcut schedule with Sarvesh 2/17 - order validated 2/12 - submitted for validation 2/11 - SOF received: Pending order creation 12/26 - Pending Signature 12/19 - SOF created: Pending Signature. 12/18 - pending SOF creation
2019-07-11 |  | II555 | D-13, Sector-59,Noida Noida, U.P India 201301 |  | 6324685 / W1D79153 - port 6324687 / W1D79154 – access INP6001629 | OVI# 1-2136219704 | Port SO: 6342728 - W1D85095 ¦ IN Access SO: 6342729 - W1D85096 ¦ IN Port SO: 6342730 - W1D79153 ¦ OUT Access SO: 6342731 - W1D79154 ¦ OUT |  |  |  | INQ2020033198983 | [9 empty] | 5/1 - credits posted on account 4/30 - INQ2020021751132 for old circuit 2/3-2/29: 4/17 - Credit with Ramesh management for approval. Checking credit calculations. 4/9 - asked for update on ticket 3/31 - INQ2020033198983 created for credit of Dec, Jan and Feb Invoices 3/19 - confirmed billing has stopped: Ramesh and team to place credit 3/18 - asked if billing has stopped 3/5 - manual trigger to stop billing: credit to be placed 2/26 - Ramesh to work with Team to get credit placed for wrong PTT circuit 2/20 - IN order to begin billing. OUT order to stop billing and to be disconnected 2/13 - Old SOF will work. Can continue with OUT order. 2/5 - Determinded that a new SOF is needed for billing 1/31 - IN order is complete: Ready to begin OUT order? 12/19 - Site survey complete: FOC date, 2/10/2020 12/13 - order placed 12/9 Pending FOC date 12/12 - Waiting to hear back from Varun on new SO 11/20 - order complete: wrong PTT more to follow 11/14 - PTT HANDED OVER LINK FOR STABILITY TEST 10/17 - FOC date 11/25 10/3 - TEV completed: Pending FOC date 9/26 - OVI created Pending validation 9/19 - Asked for update: Call being scheduled with Varun and team 9/12 - Asked for update 9/5 - Pending Order creation 8/30 - Signed SOF returned 8/27 - Revised SOF provided: Pending signature 8/21 - SOF needs to be updated with correct information 8/9 - SOF received to be sent to Melissa: Pending signature 8/8 - asked Varun for update 7/23 - order sent to Varun to be placed: 50 meg gold car: Pending SOF 7/17 - Budgetary access pricing given 7/11 - Pending access pricing
2020-01-21 |  | PH516-01-IM | 4th-6th Floors, Fintech 2, Iloilo Business Park, corner of Megaworld Boulevard & Digital Road Mandurriao IloIlo 5000 | new 500mg port and access | 6361540 / W1D92005 - port 6361544 / W1D92006 - access | 1-2200948493 |  |  |  | PTT: Globe | IF cancelled: Globe Charges : One Time charge of USD $1,500. Verizon Charges : No charges. ETF WAIVER as a special COVID Situation | [9 empty] | 5/19 - order cancelled 5/14 - asked for update 5/5 - Melissa asking to cancel this order 5/1 - Hold: site not ready 3/31 - order may be canceled 3/26 - site still not ready 3/11 - customer advised Globe that their site is not ready 3/4 - service order created 2/25 - OVI created: pending order creation/order verification 2/20 - asked for update 2/14 - Signed SOF received 2/5 - SOF created: Pending Signature 1/31 - SOF draft provided 1/21 - Order sent to Jill: sent off for SOF creation
2020-03-17 |  | II542-01-IM | Optum Global Solutions (India) Pvt. Ltd. (Unit-II)6th & 7th Floor, Tower-A,Oxygen Business Park Pvt. Ltd., - SEZ,Plot No. 07, Sector-144 | upgrade order for II542 -(circuits W1C18272 and W1C17891) 500M port 1G access 248.8 CAR | [15 empty] | on hold | 5/21 - No signed SOF. No order created to cancel 5/20 - Melissa asking to cancel order 3/23 - SOF sent to Melissa: pending signature 3/17 - submitted to Ramesh and team
2020-03-06 |  |  | Disconnect of W1C45306 NSPE0013575112 - DR2020030323984 | Account Number: INP6000886 Product Description: Private IP Order Processing #: 1-2215805902 S/O: 6365759 / 6365760 Circuit ID: W1C45306 / W1C45307 Bill Stop Date: 3-May-2020 | [16 empty] | 5/21 - new disco date 6/12 5/14 - confirmed billing stopped on 5/3 5/7 - asked for update 3/20 - bill stop date of 5/3. Disco 5/2 3/17 - asked for update 3/11 - Disconnect request sent to APAC Terminations 3/10 - Ana owner of ticket. Emailed for update
2019-12-30 |  | II553 | Old Data Center - Dodda Banaswadi Main Rd - Harischandra layout - Jeevanhalli - Maruthi Sevanagar Bengaluru, Karnataka 560005 | Cables need to be re-routed | 6384395 - port 6384396 - acces | 1-2243034909 | W1D68588 -port W1D68589 – access | [11 empty] | 2020-08-12 |  | 8/24 - cables moved and circuit confirmed up 8/17 - PTT has completed cable routing. Downtime on 8/23 to complete activity 7/30 - customer has not given work permission to PTT yet 7/21 - will not have access until 7/23: Covid 7/13 - ground work to begin in the next few days 6/29 - FOC 8/20? Confirming this date 6/11 - pending FOC 6/4 - SO numbers shared 6/2 - waiting for SO numbers to be shared 5/21 - asked for update: OVI created. Have not seen validation emails 5/19 - order submitted 5/13 - signed SOF sent to Ramesh: pending new order 4/30 - pending decision to proceed from UHG 4/17 - Ramesh responded. With reduction in monthly charges. It will take 20 months to offset one time charges 4/16 - asked Ramesh for update 4/9 - Ramesh being asked if one time charges can be decreased 3/31 - Pending signed SOF from UHG India team 3/13 - SOF sent to Melissa: pending signature from UHG India team 3/12 - Ramesh presenting access re-route SOF for customer signature tomorrow 3/5 - site survey complete: Ramesh to raise relocation request 3/4 - asked for update 2/26 - Looking to schedule site visit for 2/28 10-11am local 2/21 - unable to reach Raja to schedule site survey. Providing Parveen's contact information 2/20 - asked for update 2/13 - Reached out to LCON Raja to schedule site survey 2/6 - change order to be created 1/30 - Ramesh now running point. 1/23 - pending response from Varun. Call to be scheduled for next week 1/13 - Varun placing investigation into issue. 1/9 - Meeting scheduled for next week to discuss cable re-route 12/30 - inquiring on process/steps to accomplish task
2020-03-19 |  | II523-09-CM | 5 Community Centre, New Delhi | upgrade India circuit w1c16373 to 500mg | SO: 6385125 - W1C16373 | 1-2247741132 | [12 empty] | need 5 b day notice | NO | 6/26 - July 11 at 11pm CT 6/25 - trying to find a date and time that works for both parties 6/24 - asking for 7/3 23:30 CST 6/22 - outage for Verizon at this time. Need a different time. Advising for 6/26. Need to hear back if this time works 6/19 - asking for 6/27 at 23:30 CST 6/9 - asking for date and time for upgrade 6/8 - order number shared 6/4 - Pending validation email 5/29 - SOF signed and returned to Verizon 5/15 - new SOF sent to Melissa: Pending signature 5/6 - Melissa asking to downgrade gold Car to 35mg: New SOF is needed 3/24 - SOF sent to Melissa: Pending signature 3/19 - submitted to Ramesh and team: pending SOF creation
2020-04-16 |  | PH504-05-IM | Science Hub Tower 3 McKinley Hill Cyberpark Taguig City, National Capital 1634 | Port: 800 meg Access: 1 gig CAR: 150 meg | IN 6381354 - PORT 6381355 - ACCESS OUT 6381362 - PORT 6381363 - ACCESS | 1-2238194990 | [12 empty] | 2020-08-11 | NO | 9/10 - out order completed 7/27 - Melissa okays the disconnect of old circuit 7/15 - activating circuit 7/22 scheduled 7/13 - Ready for activation 7/10 - Loop installed and tested by PTT Globe.VZ on going testing. Possible order will complete today or Monday. 6/16 - FOC date 7/24/2020 6/11 - pending FOC 6/8 - PTT stating the did not receive order until 6/1. Pushing PTT for FOC date 6/4 - pending FOC date 5/28 - pending FOC date 5/21 - Order information shared: Pending FOC date 5/14 - pending validation completion 5/12 - 5/12 - should be ready by Friday 5/4 - signed SOF received: pending order creation 4/27 - sending SOF to UHG: pending signature 4/23 - pending SOF 4/16 - Order Submitted by Melissa
2020-02-14 |  | II757 | OPTUM-OGS NO. 226 - Red Hills Road CHENNAI, INDIA 600053 | Access: 3G Port: 2G Car: 50M | IN PORT SO: 6380783 - CIRCUIT: W1E00476 IN ACCESS SO: 6380784 - CIRCUIT: W1E00477 OUT PORT SO: 6380785 - CIRCUIT: W1C56594 OUT ACCESS SO: 6380786 - CIRCUIT: W1C56595 | 1-2236322751 | Access: W1C56595 Port: W1C56594 disco order NSPE0014052529 | [11 empty] | 2020-07-27 | NO | 9/18 - disconnect completed 9/10 - out order started. Billing stop date 9/4 8/18 - activated today 8/6 - activation 8/13 7/30 - ready for activation 7/24 - stability test completed: Ping test scheduled for July 25th 7/21 - Circuit under testing: results by tomorrow 7/15 - PTT handed link over for testing 6/9 - FOC date 7/16/2020 6/4 - pending FOC date: asked for update 5/29 - pending FOC date 5/21 - Pending FOC date 5/19 - order information shared 5/14 - pending validation completion 5/6 - pending order creation 4/29 - signed SOF received 4/23 - SOF needs to be updated per India team 4/17 - SOF sent to Melissa: pending signature 4/16 - Order submitted by Melissa 4/9 - SOF created. 4/8 - order being placed 3/12 - Ramesh getting pricing: pricing to be sent to Melissa 3/5 - Port Pricing received. Waiting on Access pricing. 2/20 - don't have pricing for higher bandwidth yet
2020-04-08 |  | II747-04-CM | 8th Floor, BSNL IDC, Fountain Building II, Fort Mumbai, Maharashtra 400001 | Access: 3G Port: 2G Car: 50M | PORT SO: 6387988 - W1E03480 ACCESS SO: 6387989 - W1E03481 | 1-2250762190 | W1C31564 Disco order NSPE0014052526 | [11 empty] | 2020-08-27 | YES | 12/2 - billed 11/1-11/6. Billing stopped 11/12 - disco order complete: removed from Billing? Check December invoice 10/15 - disco date: 11/7 9/10 - disconnect order placed. Order: 6406241 8/19 - activation completed 8/18 - to be activated in next 2-3 days 8/12 - 8/18 8:30 am local 8/5 - scheduled for activation 8/7 at 8:30am India Time 8/4 - ready for activation 7/31 - Not all testing completed: Should be completed Monday 7/30 - Ongoing Testing- possible to complete tomorrow 07/31/2020 unless issue 7/29 - Testing failed with errors. Troubleshooting with PTT 7/27 - physical work completed: pending testing 7/24 - pending cross connect completion 7/20 - Per Ramesh: Our partner is extending the cross connects 7/17 - link is ready. LCON thinks cross connect will be done by Veizon? 7/9 - SITE FEASIBILITY SURVEY HAS BEEN DONE. PTT WILL NOW PROGRESS THE ORDER AND EXPECTING A FOC DATE TO BE AVAILABLE BY EARLY NEXT WEEK 7/3 - PTT has informed that there is discrepancy with the Feasibility and they are doing a revised site survey accordingly. PTT will confirm whether they will be able to deliver the link or not. 6/23 - Pending FOC 6/18 - order created 6/16 - pending validation 6/9 - signed SOF returned: Pending validation email to be sent 6/4 - pending signed SOF from UHG 5/27 - updated SOF shared with Melissa 5/22 - New SOF for circuit to be at DC (see email from Ramesh) 5/21 - Customer evaluating another option/cancel this order 5/12 - order information shared 5/6 - pending order creation 4/29 - signed SOF received 4/24 - SOF needs to be updated per India team 4/20 - SOF sent to Melissa: Pending signature 4/16 - order submitted by Melissa 4/9 - pending SOF creation 4/8 - order being placed
2020-04-16 |  | PH503-09-IM | 8th - 9th Floor Calyx Cetre, Cebu I.T. Park, Apas Cebu, Central Visayas 6000 | Port: 600 meg Access: 1 gig CAR: 139 meg | 6386023 / W1E02649 - PORT 6386025 / W1E02650 - ACCESS | 1-2239054305 | NSPE0014071494 C5002793 203996489 | [11 empty] | 2020-09-02 | YES | 12/9 - billed through 11/3 12/3 - waiting for December invoice to post 12/2 - need to check next invoice. last posted 11/2 11/12 - disco order complete: removed from Billing? Check December invoice 10/15 - disco date 11/4 9/18 - disconnect placed 8/31 - activated 8/28 - Trying to activate 8/29 8/18 - ready for activation 8/14 - circuit installed 8/13 - On Track for loop delivery tomorrow 7/27 - FOC date 8/28 7/21 - site survey complete: pending FOC 7/17 - PTT has gained certificates. Target survey schedule is July 20,21 7/2 - Order is in COVID 19 HOLD - Cebu City is in Total lockdown until July 15,2020 due to increasing COVID positive - Local government will not provide a certificate to PTT team allowing them to conduct the site survey. 6/18 - pending FOC 6/16 - MM Fiber vs Copper. Escalated to Ramesh 6/11 - order created 6/8 - asked for update on order creation 6/4 - pending order number creation 6/2 - received response from Ray-Ann 5/29 - No response from UHG (Jose/Ray-Ann) that I could see 5/21 - Pending response from Jose/Ray-Ann 5/14 - pending validation completion 5/12 - should be ready by Friday 5/7 - signed SOF received: Pending order creation 4/28 - SOF sent to UHG: Pending signature 4/27 - should have SOF by 4/29 4/24 - will have SOF: will need disconnect of the original circuit 4/20 - No SOF needed. Order can be submitted VRD with approval 4/16 - Order Submitted by Melissa
2020-05-19 |  | II519-08-IM | Pheonix Infocity Private Limited SEZ, Building No. H06, First, Second and Third Floor, Hitech City 2,Gachibowli (V), Hyderabad, Andhra Pradesh 500081 | Port: 600 Access: 1000 CAR: 90 | Port SO: 6393486 - Circuit: W1C10980 Access SO: 6393487 - Circuit: W1C10981 | 1-2252068390 | [12 empty] | 2020-09-21 | NO | 11/9 - order completed 11/5 - bridge information sent 10/28 - requesting 11/7 at 7am IST. 10/21 - ready for hot cut/activation 10/16 - MUX installed 10/15 - attempting to gain access to install new MUX 10/12 - fiber work completed: need to install new MUX 9/23 - NEW FOC: 10/30 inbuilding fiber + splicing needs to be done to upgrade backbone bandwidth. Having issues with site access 8/13 - FOC Date 9/30 8/11 - escalating for FOC date 8/6 - Escalating within PTT for FOC date 7/21 - pending FOC 7/13 - order number created 6/25 - order validated: pending order creation/entry 6/23 - pending order validation and order creation 6/16 - validation email should be out tomorrow 6/12 - signed SOF received: Pending validation 6/2 - SOF sent to Melissa: pending signature 5/27 - Pending SOF creation 5/19 - order submitted by melissa: pending SOF creation
|  | II500 |  | Disconnect for W1b85586 | NSPE0014110520 |  | 6411174 | [13 empty] | 12/2 - billing stopped as of 11/22 10/21 - target date of 11/22/20
2020-05-14 |  | II538-07-IM | Optum Global Solutions (India) Private Limited9th, 10th, 11th and 12th Floor, Building No. 12BSundew Properties SEZ (Mindspace)TSIIC Layout, Survey No. 64 (Part)Hitech City, Hyderabad, Telangana | Port: 400 Access: 500 CAR: 45 | In Port SO: 6393946 - Circuit: W1E05609 In Access SO: 6393947 - Circuit: W1E05610 Out Port SO: 6393948 - Circuit: W1C03340 Out Access SO: 6393949 - Circuit: W1C03341 | 1-2258364588 | circuit moved to Untagged | [12 empty] | NO | 1/21 - credit on separate invoice 1/14 - opened ticket INQ2021011473692 12/9 - pending next month invoice 11/13 - Bill stop date 12/5 11/5 - pending green light to begin disco order 10/28 - packet loss cleared 10/26 - activated over the weekend: Packet drops. Ticket open with PTT 10/19 - asking to activate 10/24 10:30pm CT: This date/time does not work due to Verizon outage 10/2 - waiting 2 weeks to follow up on disco with customer: activation is plug and play: Call HOTLINE 9/23 - circuit delivered and tested good: pending activation 9/9 - THE MUX INSTALLATION WORK HAS BEEN COMPLETED. 8/27 - - INBUILDING FIBER WORK HAS BEEN COMPLETED. - NEW MUX NEEDS TO BE INSTALLED IN THE CUSTOMER SERVER ROOM. - ACCCESS REQUEST HAS BEEN APPLIED WITH THE CUSTOMER FOR THE REQUIRED ACCESS CONFIRMATION IS AWAITED FROM THE LCON ON THE DATES 8/11 - FOC Date 9/30 8/6 - Escalating within PTT for FOC date 7/21 - pending FOC 7/15 - order numbers created 6/29 - SOF received: Pending validation 6/15 - SOF created: Pending signature 6/4 - new amendment signed. Pending new SOF creation 6/2 - wanting 400M port. Renewal amendment needs to be signed before SOF can be created for pricing 5/27 - Looking for PIP pricing in contract 5/22 - per Ramesh: should have SOF by Tuesday/Wednesday 5/19 - pending SOF creation. 5/14 - order submitted By Melissa
2020-02-28 |  | PH550 | IDC BLDG CENTER - DANNY FLORO ST. BAGONG ILOG - 4TH FLOOR PASIG CITY, Philippines | Upgrade to 2 gig port, 3 gig access, 8mg CAR | Port SO: 6385075 - W1E02142 ¦ IN Access SO: 6385076 - W1E02143 ¦ IN Port SO: 6385078 - W1B26059 ¦ OUT Access SO: 6385077 - W1B26074 ¦ OUT | 1-2240561291 | [12 empty] | 2020-08-31 | NO | 3/25 - credit note posted: $14,605.16 Dec 10-31. Completed 3/4 - credit being calculated. Pending 2/18 - worked as ticket INQ2020123062400 1/14 - opened ticket INQ2021011473689 12/9 - pending next month invoice 11/12 - bill stop date 12/10 11/10 - proceeding with OUT orders for disconnect 11/5 - pending green light to begin disco order 10/28 - Coordinated turn up 10/31: Bridge information sent out 10/26 - activation successful 10/21 - calendar invite sent 10/8 - rescheduled activation: 10/24 11:15 PHT 9/28 - tentative date 10/10 11:15PHT 9/2 - activation cancelled: pending next scheduled activation 9/1 - 9/1 at 10pm CT 7/14 - Ready for activation 7/10 - Loop installed and tested. Send email to LCON if we will re-use the IP address. Order is BCOM but pending Billing trigger waiting for LCON confirmation. 7/3 - FOC date 7/10 6/18 - pending FOC 6/16 - ticket created for circuit design 6/8 - Order numbers created: Pending TEV response from Ray-Ann: pending FOC 6/2 - OVI validated: pending order numbers 5/29 - asked for update 5/24 - validation email sent 5/21 - asked for update on validation email being sent 5/14 - pending validation completion 5/11 - SOF received: Pending order creation 5/8 - Need changes on SOF (company name) 4/26 - SOF sent to UHG: Pending Signature 4/23 - pending SOF 4/16 - order submitted by Melissa 4/9 - keep on spreadsheet or move off? 3/12 - Ramesh getting pricing: Have pricing to be sent to Melissa 3/3 - confirming circuit ID: provided
Note on Z4: melissa.chapman: