## MOW Orders
Type | Service | UHG Order# | Business | PM | End User | Street Address | City, State | AT&T Project# | AT&T Order# | Date Ordered | CRDD | AT&T Overall Due Date | Completion Date | Ready for Activation? | AT&T Circuit ID's | LEC (CLEC) | LEC Circuit ID(s) | Scheduled Access Install Date | Access Demarc(s) | Handoff | Technical Info | ICORE Site ID | VLAN ID | CER | PER | ASN COS | VPN ID | VPN Name | Status | Status Date | Current Status
New | HOT ORDER 2G Port / 10G Access Ethernet AVPN 1000Base-SX | II747-06-IM | UHG | Melissa Chapman | EXPEDITE COVID WAR ROOM | 8th Floor, BSNL IDC, Fountain Building II, Fort | Mumbai Maharashtra India | VS20070812 | ISR20052134441 3094-BWDQ | 2020-04-09 | ASAP | 2020-08-30 | 2020-08-14 | No | IZYF.102427 | TCL (PTT) BSNL (Govt owned ) is the colo provider where the customer is located | 091MUMB1258035283154 | 2020-08-07 |  | 10GBase LR - LC |  |  |  | 10.1.85.5 | 10.1.85.6 | 64949 | 202610 | UHG GLOBAL 150 | 3/22: The customer is having their Project team in India reaching out. 3/12: Per AT&T AIM, TCL is still working with BSNL to schedule their tasks. TCL provided the contacts they have been in touch with and can reference the TCL fiber laying activity: Asst. Dir - Sales Mr P. Mathew Kochuvarkey @ +919427860400 AGM Mr.Desai @ +919420130130 PGM EB Mr.PK Singh @ +919423012525 Next update: March 19 3/9: Nothing new from the carrier yet - contacts provided to end user. 2/26: TCL provided the contacts they have been in touch with and can reference the TCL fiber laying activity Asst. Dir - Sales Mr P. Mathew Kochuvarkey @ +919427860400 AGM Mr.Desai @ +919420130130 PGM EB Mr.PK Singh @ +919423012525 2/22: TCL continues to chase BSNL for a response ,TCL did share a snapshot of the emails they have been sending BSNL which indicates they are following up constantly ..Will share once we hear more. 2/10: Per AT&T AIM, TCL is still working with BSNL to schedule their tasks. Next update: Feb. 17 2/3: Per AT&T AIM, TCL (Telco) made the payments and they are currently arranging the schedule with BSNL (customer's datacenter). Next update: Feb. 9 1/25: TCL advised the payment approval has been cleared by their commercial team and payment should be made by end of this week. Once payment is completed, TCL will be able to plan the fiber work (approx. 200 meters) to complete the provisioning of the permanent diverse solution. Next update: Feb. 2 1/13: TCL advised that BSNL revised the payment terms and they are working to arrange payment. AT&T AIM is escalating again with Global Carrier Management to ensure this is escalated appropriately with TCL. Next update will be shared next week. Next update: Jan. 20 1/6: Unchanged; awaiting BSNL to complete their fiber work. An update is expected early next week. Next update: Jan. 12 12/28: (customer turned up on Aug. 14th - this record is to correct the provisioning to a fully diverse solution). Per the AT&T AIM manager - The telco - TCL - continues to chase BSNL for a timeline for the fiber work and a final completion date but TCL are still awaiting feedback from BSNL. As explained earlier, BSNL is a legacy Government owned carrier and difficult to get any commitment from. We (AT&T) will continue to chase the telco - TCL on a weekly basis. Please note that the order is closed in our tooling and there is no impact to the customer's service. Next update will be January 5 close of business. 12/10: Telco TCL and customer's datacenter owner (BSNL - government owned) are discussing the fiber work that will need to be undertaken by BSNL. There is no estimated time of completion, but it is expected to take at least 2-3 weeks (late December circuit delivery). Next update: Dec. 17 12/4: TCL confirms the purchase order has been sent and they are coordinating the on site work with BSNL. Next update: Dec. 10 11/20: TCL confirms they have reached the agreement with BSNL and they expect the purchase order to be ready within 10 days. Next update: Dec. 1 11/13: TCL & BSNL are still negotiating the delivery agreement. TCL expects to have an update by middle of next week. Next update: Nov. 19 11/4: TCL & BSNL are still negotiating the delivery agreement. Per AT&T AIM, the highest escalation level in TCL has asked time till early next week and AIM has escalated this to GCM Director as well for additional support. Once the agreement has been finalized, TCL advised it will take approx. two weeks to deliver the permanent solution. Next update: Nov. 11 10/20-11/3: ESCALATED - Being tracked by TCL level 3 - We will share once we hear more and continue to check with them on a weekly basis. 10/13: TCL continues with their legal discussions with BSNL. Next update early next week. (10/20) 10/5: Still ongoing ,the BSNL legal team had health issues and was delayed ,we should know more by next week ---- October 5 status: Unchanged; TCL & BSNL are still working through drafts of the delivery agreement. BSNL's legal team is experiencing health issues. Once the agreement has been finalized, TCL advised it will take approx. two weeks to deliver the permanent solution. Next update 10/13. 9/21: Based on the discussions we had today this will continue to take time. The draft version has still not been agreed by BSNL and with no clear timeliness currently on agreement correctly . Next check by 10/2. 9/14: Unchanged; pending update from BSNL regarding the agreement. TCL advised it will take approx. two weeks to deliver the permanent solution, once the agreement is reached. Next update: 9/21/2020 9/4: Pending update from BSNL regarding the agreement. TCL advised it will take approx. two weeks to deliver the permanent solution, once the agreement is reached. Next update: 9/11/2020 8/28: TCL & BSNL are still working through drafts of the delivery agreement. Once the agreement has been finalized, TCL advised it will take approx. two weeks to deliver the permanent solution. Next update: 9/4. 8/25: AT&T AIM is following up with TCL for a firm delivery date for the permanent diverse solution. Any update will be shared immediately. Next update: 8/28 8/17: Circuit handover received; SPIRENT test successful. Ready for T&TU. AT&T SIM will send the TID letter to the customer. 8/11: TCL confirms the circuit is delivered and tests are successful. Awaiting customer to complete their inside wiring, then we will complete SPIRENT testing. Please advise when the customer expects to complete their inside wiring. Next update: August 14 8/7: TCL confirms final provisioning & tests will be completed next week. Handover expected by August 14. Next update: August 14 7/29: All ,we have had inputs from TCL that as a interim solution to help provide connectivity to the customer they are willing to provide the circuit on linear connectivity on a recently identified fiber pair (small 200 mt segment near the customer DC in Fort,Mumbai ) with a slightly reduced SLA .The alternative option is to wait for 8-10 week for all the legal and paperworks to be completed ..TCL has promised to provide the customer will fully redundant path once the legal/contractual works are completed ..The information is being shared so that customer/accounts team can help provide a go ahead and we can proceed with execution to get the services to the customer in the next 10 days . 7/24: TCL again advised they are still in negotiations to move forward with the bandwidth augmentation. It is difficult to estimate when this could be resolved, as TCL and BSNL legal teams are involved in the negotiations. AT&T AIM team continues to escalate with TCL for soonest completion, and GCM team is engaged for additional support as well. TCL is the telco and BNSL is the datacenter owner. As seen in earlier updates, TCL highlighted the fact that BSNL is difficult to work with and they were hoping the customer could intervene. That request was apparently denied and we are down to a legal negotiation between the two parties. BSNL (Govt owned ) is the colo provider where the customer is located .TCL needs fiber pairs from BSNL for installing their equipments for providing service .BSNL owns the IBD fibers and will provide it to TCL after a contractual agreement only ..This agreement needs to be vetted by the legal teams of both companies .Timelines for this agreement are awaited . Next update: July 29 7/17: TCL advised they are still in negotiations to move forward with the bandwidth augmentation. AT&T AIM team continues to escalate with TCL for soonest completion, and GCM team is now engaged for additional support as well. Next update: July 24. Firm delivery date remains August 7 7/10: TCL confirms their work is still underway at customer's datacenter. Fiber work and equipment installation are expected to complete by end of next week, then they will begin bandwidth augmentation. Firm delivery date remains August 7 and TCL continues best efforts to accelerate. Next update: July 17 7/7: TCL confirms they have arranged access with the datacenter and fiber work is underway. Once completed, they will schedule equipment installation. Firm delivery date remains August 7 and TCL continues best efforts to accelerate. Next update: July 10 6/30: Telco (TCL) confirms the POP work is completed, and they are now working with the datacenter management to obtain permission to run fiber from the nearest manhole. TCL advised they are close to reaching an agreement, therefore the August 7 delivery date should be on track. TCL will advise if any support is needed. Next update: July 7 6/24: Back-haul bandwidth readiness is in progress. In parallel, Telco is working with customer site building maangement for permission to start In-building fiber work. Pending further updates this week. 6/12: Scope of work: About 150 meters of In-building fiber work, new MUX installation & integration, circuit provisioning & testing. Last mile cable extension will be customer responsibilty (Risk: Timely permission from building management to perform In-building fiber work) 6/9: Expedite token# AVAP0609205994 received today. Access Drop Dead Date requested is 6/18. 6/1-6/8: Received Firm date of 8/7/2020 from PTT 4/9: Order rec'd | 2021-03-22 | The customer is having their Project team in India reaching out.
New | 400M Port / 500M Access Ethernet AVPN 1000Base-SX | CB502-02-IM | UHG | Melissa Chapman |  | Connecta Ave. Calle 26 No,92-32 Floors 1 - 3 | Bogota, Columbia |  |  | 2021-02-08 |  |  |  | No | [9 empty] | 10.45.10.53 | 10.45.10.54 | 65242 | 202610 | UHG GLOBAL 150 | 2/23: Per Christine, contract was requested and shooting for receipt of info by end of week. 2/16: Custom quote process - should have quote back this week. 2/8: Order rec'd | 2021-02-23 | Per Christine, contract was requested and shooting for receipt of info by end of week.
New | 10G |  | UHG | Melissa Chapman |  |  | Philippines | [6 empty] | No | [12 empty] | 202610 | UHG GLOBAL 150 | 2/23: This is a custom contract request - doing capacity checks, etc right now. Beginning stages of the contract process. 2/16: Replacement order for PH550 - Christine working on pricing. | 2021-02-23 | This is a custom contract request - doing capacity checks, etc right now. Beginning stages of the contract process.

## HOT Orders
Type | Service | UHG Order# | Business | PM | End User | Street Address | City, State | AT&T Project# | AT&T Order# | Date Ordered | CRDD | AT&T Overall Due Date | Completion Date | Ready for Activation? | MD5 | AT&T Circuit ID's | LEC (CLEC) | LEC Circuit ID(s) | Scheduled Access Install Date | Access Demarc(s) | Handoff | Technical Info | ICORE Site ID | VLAN ID | CER | PER | ASN COS | VPN ID | VPN Name | Status | Current Status Date | Current Status | Excel Function =CONCATENATE(TEXT(AF14,"m-dd"),": ",AG14," ",CHAR(10),AE14)
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | AZ174-02-IM | UHG | Melissa Chapman | United Healthcare | 4790 E. Grant Rd. | Tucson, AZ | VS20107028 | 3102-0293 PON HWS03905476 3102-BCCJ | 2020-08-10 | 2020-08-11 | 10/27/2020 (DELAYED) | 2021-03-22 | No | Y | BBEC.641334 | Qwest | 19KXGS577542MS | 2021-03-22 | UNI FIRST FLOOR ,CUSTOMERS SERVER ROOM ,WALL MOUNTED CIENA |  |  |  | 52 | 10.1.87.165 | 10.1.87.166 | 65384 | 202610 | UHG GLOBAL 150 | 3/22: Escalated to Tech AM ERIC MCBEE for completion. 3/16: UPDATE: LEC install complete (R80) - pending testing completion. 3/15: LEC came back and adjusted the install date to 3/22. 3/8: Issued LEVEL1 Escalation on AERO ticket. 3/2: Issued AERO Design ticket 1842163 to get scope of work/milestones for this Qwest access circuit which is showing due 5/5. Customer advised fiber is in building and they have a 4/4 move in date. 3/1: Access install scheduled for 5/5 2/24: Melissa advised site was ready - per end user, "We finished our meeting this afternoon and permanent power is scheduled for 2/26/21 so please start your install 3/1/21 so we can get our office open on time." 2/22: Had to resend the PON on this order. Qwest came back again and said CNR so I updated the order notes again with confirmation site has been ready since 1/29 (ATT notified on 2/2) and that we need an install date. Will monitor for access install date. 2/16: FOC due back from the LEC Qwest by 3/9. 2/2: Melissa/Dean confirmed site is good - reissued PON to the LEC today. FOC showing due back by 3/9. 2/1: Email to Dean Moen & Melissa to confirm site readiness - LEC advised BUILDING NOT READY, CUSTOMER WILL ADVISE. 1/13-2/1: PON resent to the LEC - pending new install date. FOC due back by 2/17. 1/12: Added to HOT list 1/12 AM: Confirmed PON was resent to the LEC - pushing to get a new date. Only news so far from LEC indicated site access issues but no clear reason outside of that. Because the original PON was sent back in August it was decided that resending was the best option to get a new set of eyes on this from Qwest. Will follow up by tomorrow 1/13 for status. 1/8-1/11: Escalating on missed install date - IOS Escalation on missed EAD. 1/5: Date is showing missed as of this morning - will need to escalate miss +2 (Thur) 11/9-1/4: LEC still showing on track for 1/4/2021 11/3: CNR? PER LEC: CUSTOMER NOT READY, PEND CUSTOMER, SITE ACCESS ISSUES, SITE CONTACT ISSUES. 11/2: SC team Susan Newsome received the following information from Lumen/CenturyLink for this order: "Special Construction Charges are no longer required at this time for this order. We were able to pair with another order to pay for construction and are proceeding with this order." This means there are no charges being passed along for this order so this is not special construction and this order can be managed through normal procedures. SC has changed the jep code on the order so we can manage the order normally. WORKING TO SEE IF 1/4/2021 DATE FOR INSTALL IS FIRM 10/12-11/2: LEC provided an install date of 1/4/2021. SIGNED/COUNTERSIGNED PRICING SCHEDULE SEBT TO THE SPECIAL CONSTRUCTION TEAM PER AVM - Pending update on date. 9/15-10/5: LEC R15 on order - SPECIAL CONSTRUCTION NOTICE from Qwest - SPC OF $1,902.69. Deidre engaged. 8/18-9/14: Pending an install date from the LEC Qwest - FOC due back by 9/18. 8/10: Order rec'd | 2021-03-23 | ORDER COMPLETE
| EXPEDITE 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX587-02-IM | UHG | Melissa Chapman | Wellmed | 2413 Memorial Parkway | Portland, TX | VS21007204 | 3102-0901 PON 7MS02442947 3102-BCJC 3102-BCJB | 2021-01-14 | 2021-01-21 | 6/9/2021 EXDD 4/1/2021 |  | No | Y | BBEC.673010 | Time Warner Cable | 36L1XX005105TWCC | 2021-06-01 | [5 empty] | 10.45.10.177 | 10.45.10.178 | 65243 | 202610 | UHG GLOBAL 150 | 3/15: Carrier Mgmt Tier2 Remains engaged....per Tara Locke, SPECTRUM, NO IMPROVEMENT AT THIS TIME. CONSTRUCTION ECD IS STILL 4/23. Next follow up scheduled for 3/26. 3/3: REQUESTED DROP DEAD DATE 3/02 NOT MET DUE TO PENDING SPECTRUM CONSTRUCTION. ECD 4/23. MONITORING CONSTRUCTION FOR IMPROVEMENTS (Per Tara Locke - CM Tier2) - Install date still showing 6/1 3/1: Per Spectrum......CONSTRUCTION IS WORKING ON THEIR INFRASTRUCTURE AND CLEANUP AFTER THE WINTER STORM. ECD STILL PENDING AND THEY ARE WORKING TO DETERMINE THE DATE. SOW FROM TIE POINT: OVERLASH 840', 48 CT FIBER/RISER DOWN 25'/DIG UP CAPTURE EXISTING 4" CONDUIT/PTE 85'/PULL 50' SLACK INTO BLDG/PLACE ON RACK. JOINT USE PERMIT IS APPROVED. 2/22: Expedite applied - TIER II CARRIER MGMT being engaged to request completion by 3/2. 2/16: Install date still showing 6/1. Sent email to Rachelle this morning to issue customer paid expedite per Melissa's request. 2/9: Melissa requested installation into BUILDING B.Wellmed is located in an existing facility - there is another building and we do not want this installed there 2/8: Access install scheduled for 6/1. Emailed Melissa with status. 1/25-2/1: Pending a date from the LEC Time Warner. Early stages of order. FOC due back by 3/3. 1/21: Tracking Reference Number: 1-EWGKJZQ - Pending USOs 1/19: Pending USO's | 2021-03-22 | Carrier Mgmt Tier2 Remains engaged....per Tara Locke, SPECTRUM, NO IMPROVEMENT AT THIS TIME. CONSTRUCTION ECD IS STILL 4/23. Next follow up scheduled for 3/26.

## AT&T Open Orders
Type | Service | UHG Order# | Business | PM | End User | Street Address | City, State | AT&T Project# | AT&T Order# | Date Ordered | CRDD | AT&T Overall Due Date | Completion Date | Ready for Activation? | MD5 | AT&T Circuit ID's | LEC (CLEC) | LEC Circuit ID(s) | Scheduled Access Install Date | Access Demarc(s) | Handoff | Technical Info | ICORE Site ID | VLAN ID | CER | PER | ASN COS | VPN ID | VPN Name | Historical Status | Current Status Date | Current Status | Excel Function =CONCATENATE(TEXT(AF14,"m-dd"),": ",AG14," ",CHAR(10),AE14)
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX255-09-IM | UHG | Melissa Chapman | Wellmed | 4500 Williams DriveSuite 285 | Georgetown, TX | VS20060016 | 3102-1482 PON RMSC2432987 3102-BBVY 3102-BBVX | 2020-04-22 | 2020-04-28 | 2021-04-07 |  | No |  | BBEC.674820 | Frontier-CTF | 13KRGN509564FTNC | 2021-03-24 | [5 empty] | 10.45.11.137 | 10.45.11.138 | 64542 | 202610 | UHG GLOBAL 150 | 2/26-3/15: LEC Frontier provided a 3/24 install date. 2/22: Reached out to Melissa for update on EUCR, etc. - UPDATE: Per Melissa they have the EUCR in hand and are following up to see if it was signed. 2/12: Melissa rec'd the EUCR from Frontier and confirmed they are working on getting it signed. PON delayed due to this issue so will need to supp for new date. 1/11-2/8: Access install scheduled for 2/9 12/30: Harish Kandpal (Optum) reached out to Brenda (Wellmed) to ask that she arrange site access for the AT&T team to schedule the circuit install work at this location and asked that she respond to his email when that is feasible. No response as of 1/4. The PON RMSC2432987 is past due from 12/22 so will need to supp. 12/24: HIT ticket issued for missed EAD. 11/16-12/21: LEC (Frontier) provided a 12/22 access install date. 11/11: CNR Removed - AERO DESIGN# 1489973 has been raised to supp a new due date. 11/9: Melissa advised the site was going with the aerial option and that a ROE is required. Per the CNR group, The ROE form should be provided by the Property Manager or the owner to Frontier directly. Frontier will sign and return the same to the Property Manager/Owner. Issued AERO Design ticket 1476441 to have R15 design issue cared for. 10/27: Rec'd email from Melissa with additional info between Wellmed and Frontier that wasn't provided by Frontier to AT&T. Per Wellmed, their Landlord has asked if Frontier can trench and re-pour concrete for the new drop. Frontier pushed back to see if Wellmed is open to the proposed anchor, weather head, and conduit pathway attachment to the exterior of the building instead (aerial option.) The issues appear to be unresolved from looking at the emails. 10/26: PER LEC - NO ACCESS. CUST DID NOT KNOW ABOUT THIS ORDER, LEFT MSG FOR LCON. (/LCON KESHANA ODOM, 512 869-4800, KODOM@WELLMED.NET) 9/8-10/19: Access install scheduled for 10/20. 8/31: Pending install date on PON RMSC2410576. FOC due back by 10/2. 8/28: JM9467 Joseph Matthew is working to clear R15 and respond back to the LEC for installation. 8/17-8/24: New PON RMSC2410576 issued on 8/11 - FOC due back by 9/15. (issued AERO ticket 1198495 to have PON R15 issued fixed) 8/11: Issued request to CNR AGENT RAHA, SAYANTAN to have S19C coding removed and PON resent. No longer Covid delayed per Melissa on WIP call today. All Wellmed orders are no longer affected by Covid19. 8/10: Order is S19C on hold. 6/29: PON was released on 6/22 - pending FOC 6/1: Need to S19C per Melissa email 5/5-5/26: Pending an install date from the LEC Frontier. AERO Design 991864 for R15 4/22: Order rec'd | 2021-03-22 | LEC Frontier provided a 3/24 install date.
New | SPECIAL CONSTRUCTION 50M Port/ 100M Access EaAVPN 1000 Base-SX | AZ182-02-IM | UHG | Melissa Chapman | UHG | 7534 E. 2nd St. Suite 102 | Scottsdale, AZ | VS20129990 | 3102-1346 PON 7WS03886742 3102-BCFN | 2020-09-30 | 2020-10-02 | 2021-05-20 |  | No |  | IUEC.970105 | Qwest | 19KXGS555060MS | 2021-05-12 | [5 empty] | 10.1.95.81 | 10.1.95.82 | 65130 | 202610 | UHG GLOBAL 150 | 1/5-3/15: CTL provided a 5/12 construction completion/access install date. 1/4: Update from 12/24....the Special Construction contracts have been signed and submitted for processing. ATT will send payment to Centurylink (CTL) and CTL will release the order to be worked. ECD is typically available in 4-6 weeks PON was resent on 12/29 and FOC is due back by 2/2. Pending ECD. 12/22: Escalated to 2nd Level SAIKRISHNA, D MURALI for assistance on Construction status.-- UPDATE: The Signed document has been sent to the AVM team and it'll be updated soon. Early stages. 12/21: Reached out to Mohammed Thariq Khan Ordering Associate for status of Construction. 12/14: Deidre reached out to team to confirm everything is moving forward since the executed SC agreement was returned November 23rd 11/17: Per Deidre, still waiting on the UHG signed contract back to me to send to SC group to proceed. 11/12: Deidre sent AT&T pre-signed agreement to Melissa today. Please sign and send back to me with the fax coversheet included. 11/10: Scope Rec'd - Pending OK from end user on scope/cost. 11/9: Pending dates and scope of work. 10/26: Pending approval from UHG - and details of build. 10/19: Advised Deidre of note from LEC regarding special construction - SPC OF $23,215.93 10/6-10/12: Pending an install date from the LEC Qwest 9/30: Order rec'd | 2021-03-22 | CTL provided a 5/12 construction completion/access install date.
New | 50M Port/ 100M Access EaAVPN 1000 Base-LX | C1661-04-IM | UHG | Melissa Chapman | Rose International | 4580 West Post Road | Las Vegas, NV | VS20153308 | 3102-0481 PON 7WS03896684 3102-BCGY 3102-BCGX | 2020-10-21 | 2020-12-01 | 2021-03-22 | 2021-03-18 | Yes | y | IUEC.799938 | Embarq | 53KXGS570153CTRL | 2021-02-12 | EXTENDED FROM BT TO MAIN PHONE ROOM. WALL MOUNT |  |  |  | 2 | 10.191.22.225 | 10.191.22.226 | 65402 |  | UHG ECC | 3/15: PON resent to the LEC on 3/12 and requested an install date of 3/26. Pending confirmation from the LEC on the date.Advised Ron Manning (Lumen) that site is ready to go and asked him to look into rescheduling. 3/11: MICK BRIDGINS (ROSE INTERNATIONAL) ADVISED THAT THE FIBER EXTENSION HAS BEEN COMPLETED AND THEY ARE READY FOR THE LEC TO INSTALL THE CIRCUIT. Removing CNR coding and resending PON to the LEC. Will also reach out to Ron Manning (Lumen) to advise of completion. 3/8: Reached out to Melissa and Vaishna for update on fiber run. Once completed, I'll need to resend PON to LUMEN and re-engage Ron Manning (Lumen) for a date. 2/22-3/1: Customer working with their building mgmt group to get the fiber extended - I will need to advise Ron B Manning, at Lumen once ready. 2/16: REMARKS: CUSTOMER WILL NEED TO HAVE A FIBER RAN BEFORE WE CAN FINISH THIS INSTALL. SUP NEW DD WHEN CUST READY. Customer will be running the fiber for this........pending status. 2/11: Reached out to Carrier Mgmt (AERO CM 1777890) for details on fiber needed at site.PER THE CUSTOMER, VERIZON STATED THAT CENTURYLINK/EMBARQ WOULD NOT BE ABLE TO USE THEIR FIBER LINE (THE ONLY FIBER IN THE BLDG) AND EMBARQ WOULD HAVE TO RUN THEIR OWN. WHEN THE TECH FROM EMBARQ LEFT THAT DAY, HE STATED HE WOULD SPEAK TO HIS HIGHER UPS ABOUT THE NEXT STEP BUT THEY HAVE NOT HEARD ANYTHING SINCE. CUSTOMER NEEDS DETAILS OF WHAT IS NEEDED AND CONFIRMATION ON WHO (CUSTOMER OR EMBARQ) WILL BE DOING WORK. 2/3-2/8: Updated to 2/12 access install. 12/21-2/1: Access install scheduled for 3/12/2021. 1A OUTSIDE PLANT (OSP) - MINOR BUILD 11/30-12/14: Pending an install date from the LEC EMBARQ. FOC due by 1/11/2021 11/17-11/30: Reached out to Clyde (email) for an update. 10/21: Order rec'd | 2021-03-19 | ORDER COMPLETE
New | 20M Port/ 20M Access EaAVPN 1000 Base-SX | Namm Project Rain CA472 | UHG | Melissa Chapman | NAMM | 299 West Foothill Blvd., Suite 209 | Upland, CA | VS21014012 | 308102870 3102-0962 HWSC3911011 3102-BCJP 3102-BCJQ | 2020-10-23 | 2021-02-04 | 2021-04-09 |  | No |  | MMEC.593594 | Frontier-CTF | 45KRGN553594FTNC | 2021-04-30 | [5 empty] | 10.0.1.21 | 10.0.1.22 | 65516 |  | New VPN UHG NAMM | 3/15: LEC Frontier came back with a 4/30 access install date. 3/8: Pending FOC from the LEC Frontier. Requested 3/23 install. 3/2: PON resent to the LEC to prompt them for a date.SUPPED DUE DATE ON PON HWSC3911011 FOR 03/23/21 2/16-3/1: Pending completion of the site survey and access install date. From Frontier's update......PER LCON JOHN M. SALAZAR <JSALAZAR@NAMMCAL.COM> "I HAVE NOT GOT CONFORMATION FROM THE SITE OR THE PROJECT LEAD, SO LET S PUSH IT BACK UNTIL I CAN GET IT CONFIRMED" 2/8: Pending an install date from the LEC Frontier - PON released on 2/5 - FOC due back by 3/12. 2/2: Email to Deidre for update. 1/19: Order to be reissued with Frontier as LEC to avoid SCON. Requires custom quote (per Deidre.) Frontier advised they were on-net but will not find out if there's construction on their end until the order flows down to them. Going with 20M access instead of 50M. UPDATE: Per Deidre, This has been sent to AT&T Contracts team for Access Addendum. Once I get back, I will send for AT&T presign and then send your way for UHG signature. 1/12: Per Deidre, the SC is looking a bit lower, at around $22,917, and is made up of loop cable and structure (code 845c) that will need to be installed to deliver the circuit. Deidre has submitted a custom quote requesting an alternative access provider to ATT OF CA and hopefully avoid the SC. Pending a response. 1/6: Per Deidre, Approx $40K in SC costs. The Upland CA site was AT&T OF CA (SPORT) access, those always require a sold notice and from that sold notice we discovered the SC 12/22: DW update: SC costs, pending response from ICB 12/15: Special Construction - From sales.....per pricing team, "We are receiving an outside financial parameters message from the tools provided to us by Pricing and are unable to obtain a rate letter. For this reason I cannot complete the sold notice." Sales requested details of Special Construction cost and scope of work. 11/17: Per Deidre (email), waiting for sold notice 10/23: Order rec'd | 2021-03-22 | LEC Frontier came back with a 4/30 access install date.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX611-02-IM | UHG | Melissa Chapman | Wellmed | 416 Village Dr., Suite A | Murphy (Plano), TX | VS20150189 | 3102-0169 PON 7MS02433722 3102-BCGT 3102-BCGV | 2020-11-11 | 2020-11-18 | 2021-04-20 |  | No |  | BBEC.666159 | Time Warner Cable | 97L1XX815722TWCC | 2021-04-12 | [5 empty] | 10.1.91.145 | 10.1.91.146 | 65204 | 202610 | UHG GLOBAL 150 | 2/1-3/15: LEC Time Warner still showing on track for 4/12 access install date 12/1-1/25: LEC Time Warner provided a 4/12 access install date. Need to get more details (none provided by LEC Time Warner) but long interval appears to be due to build. UPDATE FROM LEC: FOC REMARKS: ORD#19750426. NEW 50M CIRCUIT W/FIBER H/O, NNI 21.KGFD.000332..TWCC, VLAN 0049.UNI CLLI PLARTX90. CONSTRUCTION REQUIRED 11/11: Order rec'd - Please avoid Frontier as an access carrier if possible. | 2021-03-22 | PER THE LEC, CNR - CXN ONHOLD, PROPERTY MANAGER IS UNRESPONSIVE TO SCHEDULE PRECON MEETING.
| SPECIAL CONSTRUCTION 50M Port/ 100M Access EaAVPN 1000 Base-SX | AZ178-02-IM | UHG | Melissa Chapman | 4C Medical/Mountain West/Optum Care Delivery | 15021 W. Bell Road | Surprise, AZ | VS20155091 | 3102-1300 PON 7WS03897879 3102-BCHD | 2020-11-18 | 2020-12-09 | 2/18/2021 (DELAYED) |  | No |  | IUEC.672027 | Qwest | 19KXGS569554MS | 2021-07-28 | [5 empty] | 10.1.90.129 | 10.1.90.130 | 64702 | 202610 | UHG GLOBAL 150 | 3/15: Pending a date for construction and access install completion from Lumen. 3/5: SPECIAL CONSTRUCTION CONTRACTS ALL APPROVED AND PROCESSED FOR PAYMENT APPROVAL TO LUMEN, THIS ORDER HAS COMPLETED THE SC PROCESS STEPS AND CAN BE MANAGED THROUGH NORMAL PROCESS 3/1: Per Rachelle, Just received customer signed contract and sent to eSign for processing this morning. 2/16: Rachelle sent presigned agreement to Melissa 2/12: UHG gave approval to move forward with Special Construction Quote: $16,962.13. Rachelle sent for AT&T presignature 2/1: SPC: $16,962.13 W/ENTRYWAY OR SPC: $7,222.84 W/O ENTRYWAY. Email to Melissa and Rachelle to notify of SCON issue. Rachelle working to obtain details on the ENTRYWAY. 1/11-1/25: Pending FOC back from LEC Qwest - due back by 2/8. 1/5: PON resent - cnr coding removed. 1/4: Order showing CNR - CUSTOMER NOT READY, PEND CUSTOMER, SITE ACCESS ISSUES, SITE CONTACT ISSUES. ---- CNR coding will need to be removed and PON resent. 12/14-12/21: Address issue resolved. PON showing FOC due back by 1/14/21. 12/8: Per Clyde Laman.....ADDRESS ISSUE - Regarding the order, order was submitted with 15021 W BELL RD SURPRISE AZ 85374 but USO shows 15226 W BELL RD, SURPRISE, AZ, 85374 -- As checked the requested address is not validating in LEC database. Please confirm us the correct address as per E911 with the sub locations such as BLDG/FLR/Room to progress the order. 12/7: FOC due back by 1/7/2021 (Qwest). 11/18: Order rec'd | 2021-03-22 | The LEC Qwest has provided a 7/28 construction and access install target completion date.
| SPECIAL CONSTRUCTION 50M Port/ 100M Access EaAVPN 1000 Base-SX | AZ176-02-IM | UHG | Melissa Chapman | 4C Medical/Mountain West/Optum Care Delivery | 10249 W. Thunderbird Blvd. | Sun City, AZ | VS20155093 | 3102-1423 PON 7WS03901497 3102-BCHF | 2020-11-20 | 2020-12-01 | 2/17/2021 (DELAYED) |  | No |  | IUEC.685864 | Qwest | 19KXGS573755MS | 2021-07-15 | [5 empty] | 10.1.93.241 10.1.88.157 | 10.1.93.242 10.1.88.158 | 64722 | 202610 | UHG GLOBAL 150 | 3/1-3/15: The LEC Qwest has provided a 7/15 construction and access install target completion date. 2/19: Per SC, "I have processed the approved contracts and approved the payment to Lumen for this project. This order has completed the SC process steps and can now be managed through normal procedures" Pending dates 2/16: Per Rachelle email to Melissa......Contract management is following up regarding this agreement. Apparently presignature is pending expiration if not signed and implemented soon. 2/9: Pending sig on UHG side 2/2: Per Rachelle, sent for presig on AT&T side on 2/1. 1/28: Per Rachelle, Special Construction Quote: $12,052.49 Expiration Date: 3/31/21 Scope of Work: LUMEN TO BORE (1) 1.25 ID E/W (1) UO24NS FROM EXISTING HH 9156 TO NEW 3048 HH.-467 LUMEN TO PLACE (1) 3048 HH ADJACENT TO SAI X 10247. LUMEN TO LOCATE EXISTING CBO WITH 25 PR COPPER CABLE AND SWEEP INTO NEW 3048 HH.-5 LUMEN TO PULL (1) 1.25 ID E/W (1) UO24NS THRU CBO TO THE SOUTH SIDE OF CUSTOMRS BUILDING.-83 LUMEN TO PLACE A NEW NEMA CABINET ON THE SOUTH SIDE OF THE BUILDING NEXT TO THE EXISTING NEMA CABINET. LUMEN TO PULL UP (1) UO24NS INTO EXISTING NEMA CABINET, THEN THRU TO NEW NEMA CABINET.-4 LUMEN TO PLACE A FDP AND CIENA 5142 IN NEW NEMA CABINET. LUMEN TO LEAVE A 50 SLACK LOOP IN EXISTING HH 9156 AND IN NEW 3048 HH. LUMEN TO LEAVE A 20 SLACK LOOP IN NEW NEMA CABINET. 1/26: R15 Notice from LEC - SPECIAL CONSTRUCTION required. Need sales engaged to obtain SCON info. Sent to Rachelle. 12/21-1/25: Pending an install date from the LEC Qwest - FOC due back by 1/26. 12/15: HITS ticket to upload order being pushed - engaged William Keith for assistance although this is a HALO order not under his jurisdiction. Provided him the HITS ticket#. 12/14: Requested sales reissue as the USO's are still not loaded. 12/7: Ticket issued (IOS) to have USO's loaded in SOTS. 11/30: New IP's rec'd 11/20: Order rec'd - IP issues per Deidre - already in use | 2021-03-22 | The LEC Qwest has provided a 7/15 construction and access install target completion date.
| SPECIAL CONSTRUCTION 50M Port/ 100M Access EaAVPN 1000 Base-SX | AZ175-02-IM | UHG | Melissa Chapman | 4C Medical/Mountain West/Optum Care Delivery | 3090 N. Litchfield Rd | Goodyear, AZ | VS20155544 | 3102-1431 PON 7WS03897859 3102-BCHG | 2020-11-23 | 2020-12-02 | 2021-07-21 |  | No |  | IUEC.871420 | Qwest | 19KXGS569075MS | 2021-07-13 | [5 empty] | 10.1.95.33 10.1.89.13 | 10.1.95.34 10.1.89.14 | 65116 | 202610 | UHG GLOBAL 150 | 2/8-3/15: Access install and special construction scheduled to complete on 7/13. 1/15: SOTS UPDATE: SPECIAL CONSTRUCTION QUOTE PROVIDED, NEED TO KNOW IF THE CUSTOMER ACCEPTS CHARGE. SN2891 1/12: Special Construction Quote: $6598.89 Expiration Date: 3/15/21 Scope of Work: Item Summary PLACEMENT POF MH_5983: - PLACE (2) 1.25" ID AND (1) FUTUREPATH (+/- 850') THROUGH EXISITING DUCT TO MH_6783. - JET (+/- 1050') 144CT MICRO FIBER THROUGH THE NEW FP TO MH_6783 WITH (100') LOOPS IN EACH MANHOLE. MH_6783: - BORE (1) 1.25" ID (115') TO THE NORTH THEN PLACE NEW 3048 HH TO SERVE AS MMP. NEW 3048 HH(MMP): - CUSTOMER IS TO BORE (55') FROM NEW HH WEST TO THE CTL PED AND ITERCEPT THE EXISTING 4" DUCT. - PULL (410') UO24PL-I/O THROUGH THE NEW ID TO THE MPOP WITH (50') LOOP IN MH AND MMP, (120') ENTRY AND (20') LOOP AT FDP FOR FUTURE SPLICING. MPOP: - PLACE NEW 24 PORT FDP AND CIENA 3916 NO PWR OR SPACE IN THE NEMA BOX. WILL PASS THROUGH THE NEMA BOX WITH 1.25" ID AND 24CT 1/5-1/11: Sent email to Susan Newsome (SC) to obtain quote 1/4: Reached out to Deidre for update on notification for SC. 12/22: DW update – Please fwd me the notification on SC. I have searched my inbox on a number of different words and can’t find anything received on this order. 12/21: SPECIAL CONSTRUCTION - $6,598.89. Sales notified by provisioning on 12/18. 12/7-12/14: FOC due back by 1/7/2021 (Qwest). 11/30: New IP's rec'd 11/23: Order rec'd - IP issues per Deidre - already in use | 2021-03-22 | Access install and special construction scheduled to complete on 7/13.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX619-02-IM | UHG | Melissa Chapman | Wellmed | 13420 State Hwy 249, Ste I 13420 TOMBALL PKWY | Houston, TX | VS20165847 | 3102-0708 PON 7MS02440015 3102-BCHN | 2020-12-07 | 2020-12-31 | 2021-04-30 |  | No |  | BBEC.659945 | ATT SW | 28KRGN750942SW | 2021-04-15 | [5 empty] | 10.1.94.253 | 10.1.94.254 | 65284 | 202610 | UHG GLOBAL 150 | 3/15: The fiber date of 4/12 remains unchanged however the access install date was moved from 4/15 to 4/28. If fiber remains on track, we'll push for access install shortly after that piece completes. 1/19-3/8: No change in dates at this time - Fiber work due to complete on 4/12. Access install scheduled for 4/15. 1/14: Confirmed address of 13420 Tomball Pkwy and 13420 State Hwy 249 are one in the same. Address confirmed by construction and LEC - dates provided and on track. 1/11: Fiber work due to complete on 4/12. Access install scheduled for 4/15. Construction letter sent to Melissa….ASE offer accepted. 1/4: Site visit schedueld for 1/6. FOC due back by 1/11. 12/7: Order rec'd | 2021-03-22 | Per the LEC, ACCESS DENIED TO THE BUILDING - Currently CNR - The fiber date of 4/12 remains unchanged however the access install date was moved from 4/15 to 4/28. If fiber remains on track, we'll push for access install shortly after that piece completes.
| 10M Port/ 100M Access EaAVPN 1000 Base-SX | PA183-02-IM | UHG | Melissa Chapman | OptumRX | 4000 Chemical Road Suite 100 | Plymouth Meeting, PA | VS21003484 | 3102-0492 PON 7ESC2955084 3102-BCHV 3102-BCHW | 2020-12-17 | 2021-01-13 | 2021-03-18 | 2021-03-17 | No | y | IUEC.758507 | Comcast | 11KGGS026812CBCL | 2021-03-12 | 1GIG OPTICAL, 1000 FULL DUPLEX, AUTO NEG DISABLED, 100M PREMIUM COS, MMF (850), MTU 9100, 1ST FLR, SUITE 100, MDF ROOM, RACK UNIT 10, RACK MTD, LABELED WITH COMCAST CKT ID .. CKT IS RDY FOR TTU |  |  |  | 652 | 10.1.87.189 | 10.1.87.190 | 64623 | 202610 | UHG GLOBAL 150 | 3/15: Access install showing R84 completed - pending demarc info and testing completion. 2/22-3/8: Access install scheduled for 3/12. 2/8-2/16: Pending an install date from Comcast - FOC due back by 3/10. 2/1: Pending an install date from Comcast - issued AERO Design ticket 1735505 to clear R15 address issue - PLEASE SUP TO CORRECT DEMARC: 4000 CHEMICAL RD,MAIN BLDG, 1ST FL, TELCOM RM PLYMOUTH MEETING, PENNSYLVANIA, 19462 (order had 1st Floor Suite/Rm 100 - no telco room) 1/19-1/25: Pending an access install date from the LEC Comcast - FOC due back by 2/19. 1/11: UPDATE: Per Melissa, go with 100m access / 1000BaseSX Optical MMF / Comcast @ $1000.30 1/11: Per Deidre, just heard back from the ethernet access team. If we want to go with 50m access with optical interface and a provider other than Verizon, we will have to submit for a custom bid to see if any available. Our immediate choices from available quotes are: 50m access / 1000BaseSX Optical MMF / Verizon @ $1,128.72 50m access / 100BaseTX Electrical / Comcast @ $793.10 100m access / 1000BaseSX Optical MMF / Comcast @ $1000.30 12/17: Order rec'd | 2021-03-18 | ORDER COMPLETE
| 300M Port/ 500M Access EaAVPN 1000 Base-SX | CT008-04-IM | UHG | Melissa Chapman | Prohealth CT RNH | 3 Farm Glen Boulevard | Farmington, CT | VS21001564 | 3102-0776 PON HNSC1992342 3102-BCHQ 3102-BCHP | 2020-12-17 | 2021-01-07 | 2021-04-14 |  | No |  | BMEC.550762 | Comcast | 20KGGS037475CBCL | 2021-04-06 | [5 empty] | 10.45.10.137 | 10.45.10.138 | 64683 | 202610 | UHG GLOBAL 150 | 3/15: Access install remains on track for 4/6 3/5: I spoke with Glenn Gill at Comcast and he basically said they’ve had a ROE for this site for 7-years now so not sure why they issue popped up. As expected, I think the Customer Site Readiness Manager is going by some old notes in the system. That being said, I’m going to remove all CNR coding on the order and allow things to progress as they should at the site. Glenn said that the Comcast vendor working this site is called UtiliCon so you may or may not have been contacted by them already. If you have any issues or more questions going forward, let me know and I’ll loop in Glenn from Comcast and whoever is doing the work from UtiliCon. -- Access install still currently showing scheduled for 4/6 3/1: Pending updates from the field team on the Comcast side. Working directly with Glenn Gill (Comcast) although Mark (LCON) is also working with Comcast field team. 2/25: Per Mark (LCON) (email from Melissa) - We just completed the walk thru with Comcast. They had no documentation of the site and nothing was labelled. They did identify their cable and junction box. They will return next week to review the work with the install team." They were able to identify the fiber facilities and they believe they have a path to the building. 2/23: Reached out to Glenn Gill (Comcast PM) about this to see if he had news on the ROE and if he could tell us why Comcast is indicating aerial work over neighboring property. - FOLLOW UP TO GLENN TO RESEND THE EXISTING COMCAST CIRCUIT ID'S AND TO ADVISE WE'RE WORING ON GETTING PICS. 2/22: CNR ROE has delayed this order. Pending update from Comcast on ROE and aerial work. 2/16: Brian to follow up with Glenn Gill, Project Manager, Comcast Carrier Ethernet Services for status of the ROE, aerial work and to find out who the ROE was provided to on UHG/customer side. 2/8: Access install scheduled for 4/6. Per the LEC FOC REMARKS: CLASS D, RIGHT OF ENTRY PENDING, OSP WITH AERIAL PLUS ISP REQUIRED. RIGHT OF ENTRY PENDING TO BEGIN WORK ON PRIVATE PROPERTY OSP WITH AERIAL IS ALSO REQUIRED WILL DELIVER ASAP. 2/1: CNR POSTED - AS PER COMCAST WEEKLY REPORT SPREADSHEET, "CLASS D FIBER CONSTRUCTION. SITE SURVEY COMPLETED. RESULTS AND RIGHT OF ENTRY PENDING. FOC SLA IS 15 BUSINESS DAYS FROM LAST CLEAN ORDER RECEIPT". 1/11-2/1: Pending an access install date from the LEC Comcast - FOC due back by 2/12. 12/17: Order rec'd | 2021-03-22 | Access install remains on track for 4/6
| 100M Port/ 100M Access EaAVPN 100 Base-TX | CA424-03-IM | UHG | Melissa Chapman | NAMM | 1700 N Waterman Ave | San Bernadino, CA | VS21004363 | 3102-0740 PON 7WS03905660 3102-BCHY 3102-BCHZ | 2021-01-11 | 2021-01-14 | 2021-05-24 |  | No |  | IUEC.810406 | Time Warner Cable | 90L1XX802872TWCC | 2021-05-14 |  |  |  |  | 2 | 100.69.0.9 | 100.69.0.10 | 64603 | 202610 | UHG NAMM | 1/25-3/15: Time Warner access install scheduled for 5/14 - TW build. 1/19: Pending an install date from the LEC Time Warner. FOC due back by 2/19. 1/11: Order rec'd | 2021-03-22 | Time Warner access install scheduled for 5/14 - TW build.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX625-02-IM | UHG | Melissa Chapman | Wellmed | 6710 Capitol St | Houston, TX | VS21010434 | 3102-0854 PON 7MS02444400 3102-BCJF | 2021-01-25 | 2021-01-28 | 2021-04-24 |  | No |  | BBEC.665770 | AT&T SOUTHWEST | 28KRGN751059SW | 2021-04-22 | [5 empty] | 10.1.95.125 | 10.1.95.126 | 65093 | 202610 | UHG GLOBAL 150 | 2/22-3/15: Construction fiber work scheduled to complete on 4/19. Access install scheduled for 4/22 2/1-2/16: Construction fiber work scheduled to complete on 4/19. Access install scheduled for 4/22 by the LEC ATT SW. Should see update from Construction shortly on work needed onsite. 1/25: Order rec'd | 2021-03-22 | Construction fiber work scheduled to complete on 4/19. Access install scheduled for 4/22
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX623-02-IM | UHG | Melissa Chapman | MediCorp Wellmed | 720 E. Tidwell Rd | Houston, TX | VS21012564 | 3102-0935 PON 7MS02445253 3102-BCJK | 2021-01-29 | 2021-02-02 | 2021-03-30 |  | No |  | BBEC.685850 | ATT SW | 28KRGN751094SW | 2021-04-22 | [5 empty] | 10.1.91.157 | 10.1.91.158 | 64654 | 202610 | UHG GLOBAL 150 | 2/8-3/15: Fiber work due to complete on 4/19. Access install scheduled for 4/22. 1/29: Order rec'd | 2021-03-22 | Fiber work due to complete on 4/19. Access install scheduled for 4/22.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX628-02-IM | UHG | Melissa Chapman | MediCorp Wellmed | 4000 Fulton St | Houston, TX | VS21013572 | 3102-0954 PON 7MS02445656 3102-BCJN | 2021-01-29 | 2021-02-03 | 2021-05-11 |  | No |  | BBEC.632217 | ATT SW | 28KRGN751128SW | 2021-04-26 | [5 empty] | 10.1.89.45 | 10.1.89.46 | 64546 | 202610 | UHG GLOBAL 150 | 3/15: Fiber date still showing 4/21. Monitoring construction notes to ensure work gets completed on time. 3/1-3/8: Customer Prem ready date completed 2/23 - Fiber work still showing due to complete on 4/21. 2/8-2/22: Fiber work due to complete on 4/21. Access install scheduled for 4/26. 1/29: Order rec'd | 2021-03-22 | Fiber rework showing complete last week. Working to get a new install date.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX636-05-IM | UHG | Melissa Chapman | Wellmed | 2111 Fort Worth Hwy | Weatherford, TX | VS21015941 | 3102-1022 PON 7MS02446609 3102-BCJS | 2021-02-02 | 2021-02-09 | 2021-04-05 |  | No |  | BBEC.685817 | ATT SW | 14KRGN890215SW | 2021-04-28 | [5 empty] | 10.1.87.33 | 10.1.87.34 | 64778 | 202610 | UHG GLOBAL 150 | 2/22-3/15: Fiber work due to complete on 4/23. Access install scheduled for 4/28. 2/16: Site visit completed on Friday 2/12. Pending fiber and access install dates. 2/9: Pending an install date from the LEC ATT SW. 2/2: Order rec'd | 2021-03-22 | Fiber work due to complete on 4/23. Access install scheduled for 4/28.
| 10M Port/ 10M Access EaAVPN 100 Base-TX | C1406-01-IM | UHG | Melissa Chapman | Philadelphia Dept of Public Welfare | 1 Technology Park Drive / Harrisburg State Hospital | Harrisburg, PA | VS21020234 | 3102-0116 PON RESC2957817 3102-BCJX 3102-BCJW | 2021-02-11 | 2021-02-16 | 2021-05-27 |  | No |  | MLEC.601509 | Comcast | 16KGGS025622CBCL | 2021-05-19 | [5 empty] | 10.191.22.245 | 10.191.22.246 | 65471 | 202610 | UHG GLOBAL 150 | 3/8-3/15: Comcast has provided a 5/19 access install date. 3/2: Per Bob Gordon (LCON): Everything went well with the Comcast site survey this morning. We determined where Comcast’s POP is in the Commonwealth Technology Center’s data center at 1 Tech Park, Harrisburg. We also located the UHC/Optum router in the CTC CoLocation for business partners. The new Comcast modem and ethernet converter box will go in the same rack/cabinet as the UHC router. The UHC router’s G0/1 ethernet port will need to be configured to connect to the ethernet converter box/network interface device when the NID and modem are installed. I can be on site to do this connection unless UHC wants their own technician to do this, or Comcast. Comcast said the circuit turnup date is 3/29. I gave Comcast my contact info for subsequent activities in the circuit upgrade process. The next item to be done is to run coax cable from the Comcast POP to the CTC CoLo rack where the UHC router resides. Comcast will notify me when this work is to be done. 3/1: Pending a date from the LEC Comcast - design issues fixed. 2/22: PON released to Comcast - rec'd R15. Aero Design ticket 1813198 2/11: Order rec'd | 2021-03-22 | Comcast has provided a 5/19 access install date.
| 50M Port/ 100M Access EaAVPN 1000 Base-SX | TX584-04-IM | UHG | Melissa Chapman | Wellmed | 125 E. Grubb Drive Suite 105 | Mesquite, TX | VS21022155 | 3102-0134 PON 7MS02448891 3102-BCJY | 2021-02-15 | 2021-02-19 | 2021-04-15 |  | No |  | IUEC.874370 | ATT SW | 14KRGN890311SW | 2021-04-28 | [5 empty] | 10.45.11.21 | 10.45.11.22 | 64798 | 202610 | UHG GLOBAL 150 | 3/1-3/15: Access install scheduled for 4/28. 2/22: Pending an install date from the LEC ATT SW. Construction site visit showing scheduled for 2/24. 2/15: Order rec'd | 2021-03-22 | Access install scheduled for 4/28.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL463-02-IM | UHG | Melissa Chapman | Wellmed | 1259 S.Pinellas Ave | Tarpon Springs, FL | VS21027287 | 3102-0928 PON HSS03729654 3102-BCKF 3102-BCKD | 2021-02-19 | 2021-03-01 | 2021-05-06 |  | No |  | BBEC.685685 | Brighthouse Networks | [7 empty] | 10.1.95.125 | 10.1.95.126 | 65093 | 202610 | UHG GLOBAL 150 | 3/15: Issued another AERO ID 1889671 to clear latest R15 issue from Brighthouse (coding issue on order.) Pending an access install date. 3/9: Pending an install date from the LEC Brighthouse Networks. Issued AERO ticket 1867040 to have R15 cleared (LEC needed VLAN PON issued.) 2/19: Order rec'd | 2021-03-22 | Pending an access install date. Brighthouse showing FOC due 4/20.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL464-02-IM | UHG | Melissa Chapman | Wellmed | 4111 Little Road | Trinity, FL (NEW PORT RICHEY) | VS21028254 | 3102-0990 PON 7SSC3729652 3102-BCKG 3102-BCKH | 2021-02-26 | 2021-03-05 | 2021-05-10 |  | No |  | BBEC.665529 | Frontier-CTF | 65KRGN571165FTNC | 2021-05-07 | [5 empty] | 10.1.93.169 | 10.1.93.170 | 64928 | 202610 | UHG GLOBAL 150 | 3/16: Access install scheduled for 5/7 per Frontier. 1B OUTSIDE PLANT (OSP) - MAJOR BUILD. FOC REMARKS: ENDUSER SITE MUST BE READY BY 04/05/2021; FIBER PLACING/FIBER SPLICING LESS THAN 2,500 TO IMPRV DD, SUPW/ EXP=Y L 3/9-3/15: Pending an install date from the LEC Frontier - FOC due back by 4/12. 2/26: Order rec'd | 2021-03-22 | Access install scheduled for 5/7 per Frontier. 1B OUTSIDE PLANT (OSP) - MAJOR BUILD. FOC REMARKS: ENDUSER SITE MUST BE READY BY 04/05/2021; FIBER PLACING/FIBER SPLICING LESS THAN 2,500 TO IMPRV DD, SUPW/ EXP=Y L
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | LA050-01-IM | UHG | Melissa Chapman | UHG | 3017 Veterans Memorial Blvd. | Metairie, LA | VS21029169 | 3102-1195 PON 7SS03730157 3102-BCKJ | 2021-03-01 | 2021-03-08 | 2021-04-30 |  | No |  | BBEC.665512 | ATT SE | [7 empty] | 10.1.93.145 | 10.1.93.146 | 65294 | 202610 | UHG GLOBAL 150 | 3/15: CNR per Construction -- Dawn Gwin the LCON contacted Construction Engineer to advise that a site visit isn't possible just yet. Their lease doesn't begin until April 1st. The renovations begin on that date and the telco room may not be ready for another couple of weeks. 3/9: Site visit showing scheduled for 3/11. 3/1: Order rec'd | 2021-03-22 | CNR per Construction -- Dawn Gwin the LCON contacted Construction Engineer to advise that a site visit isn't possible just yet. Their lease doesn't begin until April 1st. The renovations begin on that date and the telco room may not be ready for another couple of weeks.
| 10M Port/ 20M Access EaADI Internet 1000 Base-SX MMF | NY385-04-IJ | UHG | John Sergot |  | 1 Dakota Drive | New Hyde Park, NY | IP21016853 | 3102-0900 3102-BCKC | 2021-02-18 | 2021-03-15 | 2021-05-14 |  | No |  | MMEC.657414 | CABLEVISION LIGHTPATH | 01LUXS254216CLVI | 2021-04-21 | [10 empty] | 3/16: Pending an install date from the LEC Cablevision Lightpath. FOC due back by 3/23. 2/18: Order rec'd | 2021-03-22 | Access install scheduled for 4/21.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX627-02-IM | UHG | Melissa Chapman | Wellmed | 6430 Hillcroft St | Houston, TX | VS21032180 | 3102-0338 PON 7MS02452897 3102-BCKL | 2021-03-09 | 2021-03-15 | 2021-08-05 |  | No |  | BBEC.665471 | ATT SW | 28KRGN751378SW | 2021-07-21 | [5 empty] | 10.1.92.21 | 10.1.92.22 | 64752 | 202610 | UHG GLOBAL 150 | 3/8: Order rec'd | 2021-03-22 | Construction scheduled to complete fiber work on 7/16. Access install scheduled for 7/21.
| 100M Port/ 100M Access EaAVPN 1000 Base-SX | NV190-05-IM | UHG | Melissa Chapman | 4c Medical | 8410 W. Warm Springs Rd. Ste 10 | Las Vegas, NV |  |  | 2021-03-10 |  |  |  | No | [10 empty] | 10.1.95.125 | 10.1.95.126 | 65295 | 202610 | UHG GLOBAL 150 | 3/15: Per Rachelle, order submitted. 3/10: Order rec'd | 2021-03-22 | Per Rachelle, order submitted. Pending USO's
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX622-02-IM | UHG | Melissa Chapman | Wellmed MediCorp | 6969 Gulf Fwy., Ste. 200B | Houston, TX | VS21032181 | 3102-0275 PON 7MS02452896 3102-BCKK | 2021-03-11 | 2021-03-15 | 2021-05-07 |  | No |  | BBEC.685586 | ATT SW | [7 empty] | 10.1.94.209 | 10.1.94.210 | 65293 | 202610 | UHG GLOBAL 150 | 3/11: Order rec'd | 2021-03-22 | CNR - Access denied to the building - Per Construction, Primary and Secondary LCON's were contacted and they do not have access to the centralized comm room for the building. Will follow up with the Property Management team on Monday, March 22nd.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX644-02-IM | UHG | Melissa Chapman | Wellmed | 951 York Dr. | Desoto, TX | VS21033938 | 3102-0344 PON 7MS02453644 3102-BCKM | 2021-03-12 | 2021-03-18 | 2021-05-12 |  | No |  | BBEC.659472 | ATT SW | [7 empty] | 10.1.93.137 | 10.1.93.138 | 64896 | 202610 | UHG GLOBAL 150 | 3/15: Per Rachelle, order submitted. 3/12: Order rec'd | 2021-03-22 | Site Visit scheduled for 3/23

## MACD
Type | Service | UHG Order# | Business | PM | End User | Street Address | City, State | AT&T Project# | AT&T Order# | Date Ordered | CRDD | AT&T Overall Due Date | Completion Date | Ready for Activation? | MD5 | AT&T Circuit ID's | LEC (CLEC) | LEC Circuit ID(s) | Scheduled Access Install Date | Access Demarc(s) | Handoff | Technical Info | ICORE Site ID | VLAN ID | CER | PER | ASN COS | VPN ID | VPN Name | Status | Status Date | Current Status
MACD | Port/VLAN Upgrade 20M to 50M | LA040-01-IM | UHG | Melissa Chapman |  | 1215 N Broad St | New Orleans, LA | ISR21031024034 | 3094-BWSN 3094-BWSP HSSV4648607 |  |  | 2021-04-08 |  |  |  | BBEC.664760 | [13 empty] | 3/15: Currently showing a 4/8 target completion date. The PON to the LEC (HSSV4648607) is also showing 4/8 due date. 3/10: Per Melissa, Please add this and track on the spreadsheet. We also need to push this to complete ASAP. | 2021-03-22 | Currently showing a 4/8 target completion date. The PON to the LEC (HSSV4648607) is also showing 4/8 due date.

## ISSUES
DATE: | ACCT: | LOCATION: | USO: | ISSUE: | NOTES:

## Completed
Type | Service | UHG Order# | Business | PM | End User | Street Address | City, State | ATT Project# | AT&T Order# | Date Ordered | CRDD | AT&T Overall Due Date | Completion Date | Ready for Activation | MD5 | AT&T Circuit ID's | LEC (CLEC) | LEC Circuit ID(s) | Scheduled Access Install Date | Access Demarc(s) | Handoff | Technical Info | ICORE Site ID | VLAN ID | CER | PER | ASN COS | VPN ID | VPN Name | Status | Status Date | Current Status
| 20M Port/ 50M Access 1000 Base-SX | PR516-05-IM | UHG | Melissa Chapman |  | 100 State Road 165, Tower 1 Suite 802 | Guaynabo, Puerto Rico |  | VS18082935 3094-3730 3094-BTMT 3094-BTMV | 2018-05-08 |  | 2018-08-03 | 2018-07-03 |  |  | BBEC.511424 | CENTENNIAL OF PUERTO RICO | BBEC511424CEN | [11 empty] | 7/3: ORDER COMPLETED - READY FOR TURN UP PLUG AND PLAY 7/3: BERT Escalation issued yesterday requesting vendor mgmt to engage and request status update from Centennial - LEC advised access is complete but they have not yet completed the feed back to AT&T notifying us of completion. 6/26 Update: Fiber extension is targeted for this week, tentatively for 6/27. Centennial will test circuit as soon as extension is complete. 6/22: Jose Nieves Morales – AT&T Digital Technician informed us that he needs to change the hand-off to fiber with multi-mode which he stated should be completed by no later than Tuesday morning, June 26th. AT&T requested completion by Monday, June 25th. 6/12-6/18: Pending confirmation that access is complete. The LEC Centennial of PR advised that the VLAN PON HSSV3987197 is targeting completion on 6/18. UHG requires this completed no later than 7/9. 5/29-6/4: Access install scheduled for 6/11. UHG needs circuit turned up by 7/9. 5/21: FOC completed on 5/21, access install scheduled for 6/11. 5/14: Foc scheduled for 5/16. 5/7: Received new set of IPs for site, pending USOs. 4/30: Pending order submitted and Cproject number. 4/23: Received order on 4/20.
| 20M Port/ 50M Access 1000 Base-SX | URI10-04-IM | UHG | Melissa Chapman |  | 475 Kilvert Street MDF Room3rd Flr | Warwick, RI |  | VS18066457 3094-3970 3094-BTLG 3094-BTLH | 2018-04-10 | ASAP | 2018-07-06 | 2018-07-05 |  |  | BBEC.563384 | Cox Communications | 20KFGX160177COXC | 2018-07-05 | DEMARC: 1ST FLR CUSTOMER DATA ROOM ACCENDIAN PORT 3; MMF HANDOFF; TGD |  |  | 3095725 | 500 | 10.1.93.65 | 10.1.93.66 | 65069 COS 6039 | 202610 | UHG GLOBAL 150 | 7/5: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 7/3: Tracking for 7/6 completion. 6/18-6/25: Access install completed - pending demarc info - added order to district escalation list for completion earlier than 7/6 posted due date. 6/8-6/12: Access install was pushed out to 6/15 - notes indicate customer pushed out date. 6/4: Access install date has been updated to 6/8 per LEC (Cox Communications). 6/1: Created CM ticket to assist with access install completion. 5/29; Pending access install completion, will follow up on 5/30. 5/21-5/14: Access install scheduled for 5/28. 5/7: FOC completed on 5/4, access install scheduled for 5/28. 4/30: FOC has been rescheduled for 5/22. 4/23-4/16: FOC scheduled for 5/16. 4/9-4/3: Order placed, pending USO.
| 20M Port/ 50M Access | VA012-01-IM | UHG | Melissa Chapman |  | 8270 Greensboro Drive | Mclean, VA |  | VS18009725 3094-3591 3094-BTDX Site ID: 573767 | 2018-01-24 |  | ASAP |  |  |  | BBEC.570857 | LNS | [12 empty] | 7/9: REQUESTED ORDER CANCELLATION PER MELISSA. 6/25-7/3: NSS PM advised Outlook for ROE completion: 7/19/18. 5/21-6/18: Per Acquisition manager: Revised documents have been with building owner since 3/23. AT&T is pending a response from the building owner to move forward with the order. Outlook for ROE Completion: 06/19/18 5/14: Pending call back from acquisition manager on firm dates. 5/8: Pending update from acquisition manager. 5/7-4/30: Per ATT legal team ROE completion has been rescheduled for 5/19. 4/23-3/26: ECD for site acquisition team & building owner for ROE is 4/30. 3/19-2/26: SOW/ drawings being put together. Site acquisition team have been informed a ROE is needed. The agreement will be between AT&T and building owner. 2/19: Site visit scheduled for 2/21. 2/12-1/29: USO received in 1/24, FOC scheduled for 2/15. 1/22: OM is needing to confirm IP addresses are correct. 1/15-1/8: Pending order number/USO 1/2: Order sent to for processing on 12/27, pending order being submitted by sales.
New | Port Upgrade to 150M | IR508-04-CM | UHG | Melissa Chapman |  | Block C, Spencer Block, N/A Ground Mdf, Dublin, IE | Dublin, Ireland |  | ISR18022017297 3094-BTGZ |  |  |  | 2018-07-14 | [16 empty] | 7/16: Order completed successfully. 6/26-7/9: Customer provided TTU date of 7/14 at 14:00 Dublin time (15:00 CET). DTAC booked. Invitation sent to customer/DTAC. 5/14-6/18: Per UHG: With regret, we need to postpone this booking once again. The other circuit order is still being adjudicated by our legal team, and it's taking a while. I just confirmed that both circuits will be upgraded simultaneously, so I can't schedule this one yet. Let's set a reminder for Q2. I'll contact you prior to that if we're ready to go." 5/14-3/12: Per UHG: "I'm still waiting for another circuit order to be fulfilled. Once we have that, I will be able to determine the date & time. It is possible that this will extend into April." 3/5: Order is ready to be turned up OM has reached out to UHG to schedule.
New | 200M Port / 500M Access Ethernet AVPN | II550-01-IM | UHG | Melissa Chapman |  | Level 7(8th floor) and Level 8( 9th floor), H-04, aVance Business Hub SEZ, HITEC CITY 2, Gachibowli (V) | Hyderabad, India |  | ISR18042081051 | [20 empty] | 7/10: ORDER COMPLETE 7/9: MACD created ISR18070960829-0001 , 3094BTQW / VS18120510 - Change MD5 - Pending TTU 7/3: Circuit delivered - TID sent, pending scheduling of TTU 6/26: Smart ticket created (CTT-TOM) and ticket number is CTS18-062690 for Spirent testing (Remote Ethernet Testing.) Also customer confirmation last mile cabling pending. Circuit id tagging confirmed by customer. 6/25: MUX integration completed. Circuit provisioning is in progress. 6/19: Access permission received from customer / SEZ authorities for fiber tapping/Provisioning activity on 19Jun. 6/18: Mux installation completed. MUX integration in progress. 6/12: Outside the building fiber work completed. MUX installation planned and expected to be completed in a day or two. 6/8-6/12: In building fiber work completed. Outside the building fiber work is in progress. 6/4: Per our PM, In building fiber work is in progress. 6/1: In building access permission received from UHG / SEZ authorities to start the fiber work on 6/2. 5/29-5/21: Firm date scheduled for 6/28. Scope of work: 75 mtrs of outside the building fiber work required with New hand whole creation (PROW - provisional Right of Way involved) and 820 Meters of in-building fiber work involved along with new Rack/MUX installation & Integration, circuit provisioning, last mile cabling and testing. 4/30: Pending correct ISR number. 4/23: Received ISR, pending firm dates. 4/16-4/10: Order submitted., pending ISR 4/9-4/3: Pending countersignature. 3/26-3/20: Pending contract by end of week. 3/19-3/6: Contract with UHG for signing. 3/5-2/27: New contract with new provider, pending 2/26-2/20: Sent contracts to UHG 2/19-2/5: Access has been requested for this location.
New | Upgrade to 50MB | CN522-03-IM | UHG | Melissa Chapman |  | 555 Industrial Drive, 3rd Floor, Milton Ontario L9T 5E1 | Ontario, Canada |  | ISR18010591421 3094-BTCJ | [20 empty] | 6/29: Administratively closed in tools. DTAC confirmation received that change was completed. ORDER COMPLETE 6/18-6/26: TTU scheduled for 6/28 at 21:00 EST 6/11: PM escalating for DTAC for 6/19 at 10pm EST. 5/14-6/4: Per UHG: We are targeting the upgrade to be scheduled in June Wk1.Still working on the new router to be shipped on-site with the configuration."8 May 2018 5/7-4/3: - No change-Aside from port upgrade/hot cut, this requires router replacement to a higher model that can handle a new BW of 50M. April 3rd schedule is unlikely to happen. This may be rescheduled to May 2nd, the earliest. I will keep you posted. 3/26-3/5: Cutover scheduled for 4/3 @ 12:30 CT 2/26-1/22: Pending UHG to provide schedule for upgrade. 1/15-1/8: Per OM: Reached out to customer for schedule. 1/2-12/26: Pending ISR for upgrade to 50M order.
New | 500M Port /1G Access Ethernet AVPN | II529-04-IM | UHG | Melissa Chapman |  | 4 Hosur Road, Audugodi, Opposite MICO BOSCH, Next to NDDB, Salapur 1 Comm | Bangalore, Karnataka, India | [22 empty] | 6/18: UHG has contracts - possibly on hold, engineers checking this site- on hold pending UHG 6/1-6/12: UHG requested order on 5/30. Pending ISR#. No access quote yet - pending.
| 20MB Port/ 50M Access EaAVPN 1000 Base-SX | M0331-09-IM | UHG | Melissa Chapman |  | 1250 Capital of Texas Highway | Austin, TX |  | VS18115635 3094-0800 3094-BTQD | 2018-06-22 | ASAP | 2018-09-14 | 2018-07-10 |  |  | BBEC.556524 | ATT SW | 32KRGN652979SW | 2018-07-10 | 1ST FLR TELCO ROOM RACK MOUNTED SWITCH CUST HANDOFF PORT 5 | 1000 BASE SX/LH |  | 3131444 | 50 | 10.1.92.1 | 10.1.92.2 | 65102 COS 6039 | 202610 | UHG GLOBAL 150 | 7/10: ORDER COMPLETE - READY FOR TURN UP 7/9: Access due to install on 7/10 6/22: Order rec'd
| 50M Port/ 100M Access 1000Base-SX | UIL55-01-IM | UHG | Melissa Chapman |  | 1001 Jefferson Street | Lawrenceville, IL |  | VS18074168 3094-3450 3094-BTMD | 2018-04-25 |  | 7/23/2018 Will be pushed out | 2018-08-10 |  |  | BCEC.571214 | FRONTIER TELEPHONE | 30KRGS866748FTNC | 2018-08-10 | SLOR 1 PORT 2 LOCATION 1ST FLOOR TELCO ROOM JACK SFP NOT EXT |  |  | 3102061 | 2 | 10.1.95.161 | 10.1.95.162 | 64939 COS 6039 | 202610 | UHG GLOBAL 150 | 8/13: ORDER COMPLETE - Ready for turn up plug and play. 6/12-8/06: LEC Frontier due to install access on 8/10 due to minor build. 6/4-6/11: Access install still scheduled for 8/10 per Frontier. Pending details of long interval (most likely minor build.) 6/1-5/29: FOC completed, access install scheduled for 8/10. 5/21-5/7: PON sent, FOC scheduled for 6/12. 5/1: Escalation ticket with design team for PON release. PON was scheduled for 4/30. 4/30: Pending USO. 4/23: Order confirmed by UHG with OM to proceed, pending USO. 4/16: Sold notice provided for processing. 4/9: Pending USO & order numbers. 4/3: Order sent by UHG on 3/22, pending USO.
| 10M Port/ 50M Access 1000 Base-SX | TX428-01-IM | UHG | Melissa Chapman |  | 5627 University Heights Blvd Building B Rm 108 | San Antonio, TX |  | VS18093830 3094-2556 3094-BTNW | 2018-05-24 |  | 2018-08-10 | 2018-07-31 |  |  | BBEC.515696 | ATT SW | 31KRGN653074SW | 2018-08-07 | 1ST FLOOR MAIN TELCO ROOM ATT FIBER HAND OFF BOX PORTS 3 AND 4 |  |  | 3115946 | 50 | 10.1.92.137 | 10.1.92.138 | 64831 |  | UHG GLOBAL 150 | 8/01: Complete 7/31 7/31: LEC showing access installed - demarc 1ST FLOOR MAIN TELCO ROOM ATT FIBER HAND OFF BOX PORTS 3 AND 4. VLAN PON HMSV3995496 showing due to complete on 8/7. 7/30: LEC showing dispatch request to site for possibly today by close of business. 7/23: Access install is not compelte due to AT&T SW issue. Working to get more information and dispatch. 7/16: LEC advising install was improved to 7/17. Monitoring order for access completion notice. 7/10: GRETA (LEC) systems showing access install was pushed to 8/7. 6/4-7/3: FOC completed, access install scheduled for 8/3. 5/29: FOC scheduled for 6/18. 5/21: Order placed, pending cproject number.
| 10M Port/ 50M Access LC - Multi Mode Fiber 1000BSX | NJ139-01-IM | UHG | Melissa Chapman |  | 19 Chapin Rd Bldg. D MDF Room | Pine Brook, NJ |  | VS18048791 3094-2704 3094-BTJX | 2018-03-16 |  | 2018-07-09 | 2018-08-13 |  |  | BBEC.540656 | Verizon- South | KRGS503326NJ | 2018-07-23 | FL 1 MAIN ELECTRIC ROOM SIP PANEL 1 POS 4 AND 5 |  |  | 3084909 | 50 | 10.1.93.153 | 10.1.93.154 | 64850 COS 6039 | 202610 | UHG GLOBAL 150 | 8/14: ORDER COMPLETE - Ready for turn up plug and play. 08/06: Access shows installed. Escalation on end to end testing. 7/20-7/30: Access install pushed out to 8/3. 7/16: Access install scheduled for Monday 7/23. 7/12: Melissa Chapman (UHG) has notified AT&T that power is now in place at the MPOE and it's OK for Verizon to proceed with access install. I've requested that Ordering team sup the order and request earliest re-dispatch for access completion. (IOS INQUIRY) 7/10: CNR Customer Not Ready - status of power issues required so order can be supp'd for redispatch by LEC Verizon. Site not ready yet - no dates yet 7/3: CNR Customer Not Ready - Per Verizon, order is currently roadblocked due to no power at the customer site. Once power is supplied, please advise and we'll supp the order for LEC redispatch. 6/26: Escalating on missed access install by LEC Verizon. 5/29-6/18: Access install scheduled for 6/22. 5/21: Order is being supped by the OM, pending firm dates. 5/15: Demarc should be ready today. Existing order in with Verizon 5/14-5/7: Pending new FOC date from Verizon. Please verify address BLDG D FLR 1 & RM MDF IS INCORRECT. PLEASE PROVIDE CORRECT DIRECTIONALS. 5/1: UHG provided new LCON. 4/30: UHG requested to change port speed to 50M. FOC not completed due to invalid LCON info. Ryan Cameron- 404-308-5876. 4/23-3/26: FOC rescheduled for 4/27. 3/19: FOC scheduled for 4/20. 3/5: Order placed and sent to ordering pending Cproject number.
| 10M Port/ 50M Access | AZ034-01-IM | UHG | Melissa Chapman |  | 6365 E Tanque Verde Rd | Tucson, AZ |  | VS18014398 3094-3619 3094-BTFL | 2018-01-29 | ASAP | ASAP |  |  |  | BBEC.593781 | Qwest | 19KXGS294945MS | 2018-07-05 | 1ST FLOOR SERVER ROOM INSIDE OF SUITE 120, RACK MOUNTED BELO | [9 empty] | 7/23: Order complete 7/19 7/10-7/16: Access install completed - demarc provided - requested District Escalation Manager place order on HOT list for completion since order is past due. 7/3: Access install scheduled for 7/5. 6/26: Per UHG, site requirements are now done for VS18014398 AZ034. CL sill has some splicing to do. - MAKE CL AWARE 6/18: Reached out to Kevin (Optum) for status of work - targeting mid-June. Still on track - pending update from Kevin later this week on the vendor's progress. 6/5-6/11: Per Kevin McCormick (Optum), the Vendor has hired Team Fishel to connect the AT&T fiber to the MDF room. This is the same firm that AT&T used to bring fiber to the property line. There is still some paperwork to be completed but this work should be complete by the middle of this month and Kevin will update when completed. 5/29-6/4: Pending firm date for site readiness from UHG. 5/22: Send OM update on site work. push out date. 5/21-5/8: Pending date this week. 5/7: Per UHG should know site readiness completion date by next week. 4/30-4/3: Access install scheduled for 5/22. Confirm with UHG that site is ready ( pending) 3/26-3/19: Access install scheduled for 5/22. Pending site requirements ECD from UHG. 3/12-2/28: Confirmed by CL that there are site requirements. Pending ECD for site requirements. :Customer to place 1.25" inner duct and pull rope 150' in existing 4" conduit to meet point from MPOP. 2/27: Check with AIM/LEC for site require work. Showing no work needed by UHG 2/26: Order requires interoffice facility build. 2/19-2/12: FOC completed 2/7, access install scheduled for 5/22. Sent out site requirements to UHG pending confirmation ECD. 2/5-1/29: FOC scheduled for 3/5. 1/23: OM sent out order form to be approved. Pending approval from UHG to move forward with order. 1/15: Order submitted for processing on 1/12.
| 150M Port/ 300M Access 1000 Base-SX | UNH01-13-IM | UHG | Melissa Chapman | Oxford Health Plans | 14 Central Park Dr. Mpoe Flr 1 | Hooksett, NH |  | VS18093789 3094-2173 3094-BTNT 3094-BTNV | 2018-05-25 |  | 2018-08-21 | 2018-08-21 |  |  | BDEC.991501 | Fairpoint | 84KRGN77266600MJD | 2018-07-27 | 1ST FLOOR MAIN TELCO ROOM WALL MOUNTED METRO NID GT PORT NUMBER 2 NOT EXTENDED. | [9 empty] | 8/21: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 8/20: Pending respond on AERO ticket 298354 and BERT/IOS escalation for missed install on 7/27. 8/14: Escalating on AERO ticket 298354 for missed install (EAD) 8/06: AERO 296707 closed/resolved on 08.01. AT&T Escalation ticket 298354 with TIER to follow up on missed install. 7/30: Access missed on 7/27. AERO ticket 296707 opened for miss (R15.) 7/16 - 07/23: Access install scheduled for 7/27. 7/10: LEC advised order was missing information. Provisioning Design supp'd the order with the requested info. LEC provided an updated install date of 7/27. VLAN PON HNSV4014493 due to complete 7/27 as well. 7/3: Access ckt 84KRGN77266600MJD was due to install yesterday 7/2. Pending status update from the LEC - no completion showing yet in our systems. VLAN PON# HNSV4014493 was issued and is pending FOC (due 7/6.) 5/29-6/25: FOC scheduled for 6/29. 5/21: Order placed, pending cproject number.
| 10MB Port/ 50M Access EaAVPN 1000 Base-SX | VA074-01-IM | UHG | Melissa Chapman |  | 3160 Fairview Park Drive | Falls Church, VA |  | VS18110874 3094-0791 3094-BTPY 3094-BTPZ | 2018-06-11 |  | 2018-09-18 | 2018-08-21 |  |  | BBEC.564759 | Cox Communications | 49KFGX000880COXC | 2018-08-02 | 1ST FLR MPOE TELEPHONE ROOM #115 PORT 3; TGD |  |  |  | 500 | 10.1.92.37 | 10.1.92.38 | 64800 COS 6039 | 202610 | UHG GLOBAL 150 | 8/21: Access install is complete (demarc provided) however testing is showing issues at the site. Cox created trouble ticket on their side to investigate. UPDATE: ORDER COMPLETE 8/14: Escalating on missed install - Cox installation delays due to equipment issues. AERO TICKET 311336 opened. Tier 1 contacted Cox yesterday 8/13 and Cox confirmed they have a design issue and they are requesting ETA internally. Next update by close of business 8/15. 8/03: Access install pushed out to 08/10 7/11-7/30: Access install scheduled for 8/2. 7/3-7/10: Pending install date from LEC Cox Communications - FOC due 7/27 6/26: Pending USO's 6/11: Order rec'd
| 10M Port 11 Base-TX- Electric Handoff | TX340 Build Pricing Order | UHG | Melissa Chapman |  | 1302 E GENERAL CAVAZOS BLVD Building , Floor 1, Room | Kingsville, TX |  | VS17175715 3094-2938 3094-BSWM | 2017-09-28 | [5 empty] | MLEC.524988 | ATT SW | 34KQGN614683SW | [11 empty] | 6/1-7/3: OSP engineer is needing name and number of POC at the site. Possible Cancellation 4/23: Per UHG: Fiber has been trenched on the ground of site location, but we are trying to verify the exact location the fiber was extended to and POE. Will provide more details as information is obtained. 4/16: UHG shared updates on pending site work. 4/16-1/29: Sent UHG site requirements form. OSP team work will continue. Pending site requirements completion ECD. 1/22: Needing to replace order. Per OSP team work/build will still continue since it has already been received. 1/15-1/8: Pending update from CWO and provisioning team. 1/2: Check for document that needs to be signed. 1/2: C&E requesting signed copy of CWO payment form to proceed with order. 12/26-12/18: Fiber PLC/SPLC scheduled for 1/3/2018. 12/11: Build cost confirmed by UHG, pending firm dates. 12/4: Pending completion of site requirements. Pending ECD from UHG for site ready date. 11/27-10/30: Access delivery date scheduled for 11/29. 10/24: Received build cost on 10/23. 10/23-10/9: FOC completed 10/5, estimated access install date scheduled for 11/29. Checking for build cost. 10/2: USO received on 9/29, FOC scheduled for 10/24. | Move to cancelled
New | 10M Port / 50M Access Ethernet AVPN | UK544 | UHG | Melissa Chapman |  | 46 Aldwych, 3rd Floor, Melbourne House | London UK |  | ISR18071395937 VS18124543 3094-BTRP 3094-BTRQ | 2018-07-16 | ASAP |  | 2018-09-05 |  |  | MLYF.113036..ATI | SAREA // British Telecom | SR/VLXP/045178/ATI | 2018-09-11 |  |  | 1000BaseSX SC Connector |  |  | 10.1.94.9 | 10.1.94.10 | 65117 COS 6039 |  | GRI | 9/5: Circuit Delivered - TID sent out - Ready for turn up 8/27: Woosh test (diagnostic tests) failed, the job has been referred to SFU team. 8/20: Amelia Langeberg added as new contact on order. Delivery date of 8/28 is on target. 8/14: Customer Agreed on a NEW delivery Date: 8/28/2018. Fiber Build Work appointment at the B-end has been completed by Openreach. 8/13: Site survey completed on 7/30. Pending PTT date from SAREA / British Telecom 6/1-6/18: Order assigned to OM, pending ISR#. Waiting on technical verification
New | 100M Port / 200M Access Ethernet AVPN | II549-01-IM | UHG | Melissa Chapman |  | TAMARAI TECH PARK SOUTH BLOCK, 5TH FLOOR, INNER RING ROAD, | Nagar Chennai India |  | ISR18052395895 VS18094655 3094-BTNY 3094-BTNZ |  | ASAP | 2018-08-23 | 2018-08-30 |  |  | IUYF.103540..ATI | Bharti | 12057256 | 2018-08-03 | Demarc: cable tagged with 12057256 confirmed as identified by Sathish |  | 1000 Base-SX MMF LC connector |  |  | 10.1.93.161 | 10.1.93.162 | 65123 COS 6039 |  | UHG GLOBAL 150 | 8/30: Circuit delivered, tested, closed in tools, TID, TP3 sent - Ready for turn up 8/28: Still waiting for testing with Telco 8/20-8/27: Circuit provisioned and testing is being planned 8/13: Confirmed bearer changed. Pending update from PTT on access completion. 7/31: Telco(Bharti) confirms there is no free Bearer for Chennai POP. New bearer is under implementation. 7/30: On track for Firm date of 8/3. 7/16- 7/23: Outside Fiber work in progress. expecting to complete by end of this week. On track for Firm date of 8/3. 7/9: No further news, request sent to IPC team to check whether we are on track for 8/3 PTT date. 7/3: Pending completion of fiber work - PTT on track for 8/3. 6/26: Outside Fiber work has been initiated. PTT still on track for 8/3. 6/18: PTT still on track for 8/3. Scope of work for this order will be: 450meters in-building Fiber work, 200meters outside Fiber work, Mux/Rack installation, Node integration, circuit provisioning, Testing, Circuit hand-over. 6/12: Access ordered with Telco. PTT install date showing 8/3. 5/22-6/4: Order has been placed, pending ISR - have ISR 5/21-5/15: Pending Countersign 5/14-4/17: Contract with UHG 4/16: Pending access, once access is received contract will be sent over. 4/9-3/19: Received order on 3/15, pending order number/USO/ISR. Waiting on access.
New | 30M Port / 100M Access Ethernet AVPN | C1581-03-IM | UHG | Melissa Chapman |  | Tower B, 6th floor DLF Building No-14 DLF Ciber City DLF Phase 2 | Gurgaon, HR India |  | ISR18062921135 VS18117340 3094-BTQF 3094-BTQG |  | ASAP | 2018-08-31 | 2018-09-03 |  |  | MNYF.102394..ATI | TCL (VSNL) | 091NOID1143031828410 |  |  |  | 1000BaseLX - LC Connector |  |  | 10.191.21.253 | 10.191.21.254 | 65421 |  | UHGECC GLOBAL | 9/3: ICORE,EFMS,USO closed, TID & TP3 sent- Ready for turn up 9/3: Spirent Test successful customer confirmed that, they are aware of the demarc and they will label the circuit ID on cable. 8/30: Customer has requested to proceed with Electrical handoff (RJ 45 interface) at customer end. Communicated the same to Telco. Telco will review further and confirm the revised firm date awaited by this week end or early next week. 8/27: Per customer they need the interface as 100 Base T, notified IPC to check whether Telco can change and if there is any pricing change 8/20: Bandwidth augmentation and circuit provisioning completed. Telco Test successful and results uploaded in NGGNI document center. CTT Ticket #:CTS18-082015 created to perform the Spirent Test and also last mile cabling and circuit ID tagging confirmation awaited from customer. 8/13: Bandwidth augmentation is in progress and expected to be completed by early this week. The 8/31 firm date is unchanged. - 8/14 UPDATE: Bandwidth augmentation expected to be completed by this weekend. 7/31: Bandwidth augmentation is in progress. Showing on track for 8/31 firm date. 7/24: Customer site is connected and bandwidth check is in progress. 7/19: Telco site survey scheduled, Expected to be completed by Mid of next week. 7/17: Firm date 8/31/2018. 7/5: Access order accepted by Telco Firm Date will be available by 7/18 6/18 Contracts signed with new address. Order resent in 6/12: Per Christine Isaacs, Address changed on order. Requested new access and will then need new contract. 5/22-6/4: Order has been placed, pending ISR 5/21-4/24: Sent for countersign, pending. 4/23-4/3: Contract with UHG, pending update on contract status. 4/3-3/19: Pending order number/ USO 3/12: Received order on 3/6.
| 600M Port/ 1GB Access 1000 Base-LX | C1632-01-IM | UHG | Melissa Chapman |  | 2091 Commerce Drive | McKinney, TX |  | VS18070703 3094-3055 3094-BTLR |  |  | 2018-07-30 | 2018-09-06 |  |  | IZEC.597448 | ATT SW | 14KFGS872979SW | 2018-07-09 | 1ST FLR,ATT RM,RR B3,E-PANEL 1, BRITEJK #1 CLIENT #2 PORTS |  | ESP Ethernet Dedicated Access | 3098473 | [6 empty] | 9/6: ORDER COMPLETE - READY FOR TURN UP 9/4: LEC encountered issues during testing last week. A ticket was issued to have the OSWF at the Dallas CO check the wiring....possible flipped fibers. Ticket# 873113802. Scheduled to have vendor meet on TUESDAY 9/4/2018 AT 9:00 AM. VENDOR MEET TCKT# BE121610 8/27: Working with Provisioning Tech Area Manager Marcia Drane to push for completion. UPDATE: MARCIA ADVISED SHE IS GETTING A TECH ON THIS TODAY 8/21: Requested updated from 2nd Level Cedrick Scott in Provisioning (TECH.) TIcket was opened to schedule vendor meet however that is showing CUSTOMER ATX/UNITED-HEALTHCAR AGREED CIRCUIT RESTORED AT 1245 ON 08/09/18. Order is not yet completed and I'm escalating for this to be made ready plug and play. 8/06: Ckt wiried. Vendor meet requested. Working on end to end testing. 7/30: Engineering (RID) completed. Issued ticket for completion of access testing and overall turn up. 7/26: Escalation sent for AERO tkt # 285853 7/10-7/23: Access install completed - demarc provided. Pending testing completion and the OK to turn up. AERO Design ticket 285853 to complete engineering. 6/5-7/3: LEC ATT SW provided 7/9 access install date. 6/1-5/29: Per BUPM: Working with LEC to provide firm timeline. 5/23: Created escalation AIM ticket for assistance with missed FOC. 5/21-4/30: FOC scheduled for 5/21. 4/23: Received USO, pending PON delivery and firm dates. 4/16: Received Cproject number, OM requested confirmation of order details. 4/9: Received order from UHG, pending order placement.
| 100MB Port/ 200M Access EaAVPN 1000 Base-SX | CA377-01-IM | UHG | Melissa Chapman | EPIC Hearling Healthcare | 3191 West Temple Avenue Main Building, Floor 3, Room 2 | Pamona, CA |  | VS18105926 3094-0038 3094-BTPJ 3094-BTPK | 2018-06-06 |  | 2018-09-11 | 2018-09-12 |  |  | BKEC.999902 | Frontier | 45KFGS901487FTNC | 2018-07-31 | NID IS AT DEMARCATION IN TELCO ROOM 2ND FL SUITE 200 USER PORT 5 TAGGED NT XTNDED RJ45 |  |  | 3125001 | 500 | 10.1.92.45 | 10.1.92.46 | 64807 COS 6039 | 202610 | UHG GLOBAL 150 | 8/21-9/10: Escalation (BERT/IOS) for due date completion. Overall due date targeting 9/11 but pushing for sooner. 8/14: Access and VLAN showing R80 completed. Overall due date is 9/11. 8/06: LEC/FTR working with site on install due to fiber drop. Targeting work to be completed today (08/06). 7/3-7/30: Frontier access install scheduled for 7/31. 6/26: Pending USO's 6/6: Order rec'd - customer needs by end of August
| 1GB Port 1GB Access 1000 Base-SX | UT011-01-IM | UHG | Melissa Chapman |  | 280 W 10200 S STE 200 | Sandy, UT |  | VS18085723 3094-3792 3094-BTMY | 2018-05-10 |  | 2018-08-13 | 2018-09-19 |  |  | IZEC.567186 | Qwest | 69KXGS346957MS | 2018-09-10 | MAIN FLOOR TELCO/IT ROOM ROACK MOUNT TYPE: OPTICAL PORT: 2 | 1000 Base-SX |  | 3109928 | 1944 | 10.1.92.217 | 10.1.92.218 | 64862 | 202610 | UHG GLOBAL 150 | 9/19: ORDER COMPLETE - READY FOR TURN UP 9/17: Access install is complete - pending testing completion and ok to turn up. Issued BERT/IOS ticket for assistance in completing order. 9/10: Access due to install by COB today on existing USO - no need for new order as new PON was issued on existing order. No issues and access is pending completion today. 9/4: Pending new USO's from ordering - being worked this morning. 8/27: Order is being cancelled and reissued as shared over dedicated due to design issues. The assembler Raul is going to cancel the order in the system which will free up the CER/PER and that is supposed to happen by Tuesday. 8/20: ESCALATION TO CEDRICK SCOTT - DESIGN ISSUE 8/14: Escalation sent to OM (IOS Inquiry) for missed completion. 6/25-7/30: Access install completed - pending testing completion and OK to turn up. Order is future due (Aug 13.) 6/18: Access Vendor Mgmt (AVM) engaged on LEC missed install. Per Centurylink, PENDING POWER EQUIPMENT FOR UPLINK DEVICE AT CO. Next follow up scheduled for 6/19 by LEC. 6/12: Access install showing missed on Friday 6/8. BERT ticket issued. VLAN still showing on schedule for 8/7. 6/4: FOC completed, VLAN scheduled for 8/7. Access install due 6/8. 5/29-5/14: FOC scheduled for 6/20. 5/7: Order processed by sales, pending cproject number.
| 10MB Port/ 50M Access EaAVPN 1000 Base-LX | UCAA1-01-IM | UHG | Melissa Chapman |  | 505 N. Brand Blvd. | Glendale, CA |  | C11379358 VS18122501 3094-0040 3094-BTRS | 2018-07-06 |  | 2018-10-01 | 2018-09-12 |  |  | BBEC.543664 | ATT West | 13KRGN594217PT | 2018-07-25 | CKT/OPTICAL PORT 6 TAGGED ON PANEL 1 ITIONS 5 6 IN 7TH FLOOR |  |  | 3138011 |  | 10.1.92.25 | 10.1.92.26 | 64744 No COS | 202610 | UHG GLOBAL 150 | 9/12: ORDER COMPLETE - READY FOR TURN UP - RESEND COMPLETION NOTICE 7/26 - 9/10: Access installed. Future due order (10/1) - note, critical dates are future due (CTA 9/24 and DD 10/1.) 7/16 - 07/23: Access install scheduled for 7/25 7/16: USO's rec'd - pending access install date. 7/9: C-project# received - pending USO's 7/6: Order rec'd
New | 1GB Port/ 1GB Access EaAVPN 1000 Base-SX | KS015-11-IM | UHG | Melissa Chapman |  | 6860 West 115th Street | Overland Park, KS |  | C11384350 VS18153079 3094-0500 3094-BTTT | 2018-08-07 |  | 2018-11-14 | 2018-09-13 |  |  | IZEC.501202 | ATT SW | 74KRGN905321SW | 2018-09-14 | 1ST FLR DATA CTR/G-902, CUST CAB SHLF PNL 1, POS 11&12, TAGGED |  |  |  |  | 10.1.88.117 | 10.1.88.118 | 64905 | 202610 | UHG GLOBAL 150 | 9/13: ORDER COMPLETE - READY FOR TURN UP 9/4-9/10: Access due to install on 9/13. 8/7: Order rec'd - Pending USO's
Change | Upgrade to 50MB | CN521-02-IM | UHG | Melissa Chapman |  | 3960 Quadra Street - Suite 505 | Victoria, BC Canada |  | ISR18011988668 3094-BTDJ |  | ASAP |  | 2018-09-30 | [16 empty] | 10/1: Change completed 9/24: Cutover booked for 9/30/2018. Invitation sent by PM 9/17: Pending status on customer equipment - targeting 9/26 9/4-9/11: Waiting for response from customer on equipment status - Equip by end of next week 8/28: Equipment still not at site, next check will be next week. 8/13-8/27: Waiting for date and time from customer. Additional equipment is missing on site that needs to be delivered before the change can be scheduled. Current outlook is end of August completion. - Mid Sept per Melissa. 8/1: Waiting for date/time from customer - reminders sent by MOW team. 6/26-7/30: Routers still not at site, waiting for customer. Routers have been shipped - End of August for turn up - missing parts. 6/12-6/18: PM Ivana Lajciakova still waiting for date from UHG 5/21-6/4: Per UHG: "The circuit is ready for activation anytime. However, the new routers are not ready yet. Our project manager and vendor are working with the shipment of items to the site but it seems there's a bit of roadblocks which causes delays on the delivery. We are doing our best to expedite it" - dlvd to site 5/14: OM is asking for update from UHG. Please provide update. Pending router shipping possible end of May. 5/7-2/5: No change: Per UHG: Site requires router upgrade to handle new bandwidth speed. Will provide update once everything is ready at the site. 1/29-1/23: Order ready for upgrade 1/22-1/8: Upgrade placed, pending ISR #.
| 150 Port/ 200M Access 1000 Base-LX - Optical Handoff | DC006-01-IM | UHG | Melissa Chapman |  | 2445 M ST NW Building , Floor 6, Room MDF | Washington, DC |  | VS18036555 3094-3681 3094-BTHL 3094-BTHM | 2018-02-23 |  | 6/5/2018 DD will be pushed out | 2018-09-26 |  |  | BKEC.998137 | VERIZON - SOUTH | 36KFGS308440CD | 2018-09-28 | 1C LVL, MTR RACK MTD NID, TAGGED |  |  | 3075499 | 16 | 10.45.11.53 | 10.45.11.54 | 65105 | 202610 | UHG GLOBAL 150 | 9/26: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 9/25: Engineering, Design and Wiring all completed yesterday. Email to tech manager Cedrick Scott to complete testing and turn up circuit. 9/24: AERO Design Ticket 353521 (RID) - Pending testing completion. 9/17: Received notification from the LEC that access install has completed. Pending additional details (demarc), VLAN completion and testing. 9/10: Verizon has sent FOC back with an updated install date of 9/28. 9/4: From Verizon: Verizon has always had a fiber build but the build was continuiously roadblocked because of customer power. Please advise when customer became ready and when customer notified Verizon Engineer of their readiness. AVM Tier II will then push back and see what can be done. 8/31: AERO 332021 to AVM for status from VZ. 8/20-8/27: Access install scheduled for 8/28. Fiber build 9/15 per Verizon (make sure no CNR) 8/13: Order showing CNR CUSTOMER NOT READY. 7/30: Access install still showing 8/9. Pending status on ticket for update on why date was pushed out. - UPDATE: PER TICKET 3012, "LEC was not able to access the premise" 7/23: Access install pushed out on the 19th. Access now targeted for 8/09, escalation ticket sent to get more information. Ticket # 3012 6/25-7/16: Access showing due 7/19. No change in status. 6/19: Added to HOT list - UHG needs by 7/23. 6/4-6/18: Verizon has scheduled access install for 7/19. 6/1: Per CM: Escalated to director of engineering for update. Next update scheduled for 6/1. 5/29: Per CM ( Carrier Management): Order is being escalated with construction manager. 5/21: Per AIM : Verizon engineer manager has been engaged to assist with FOC. Next update scheduled for 5/23. 5/14: Opened AIM escalation ticket for FOC completion. 5/7-4/9: FOC rescheduled for 5/9. Order supped with Verizon due to invalid acct number. 4/3: Pending FOC completion. 3/26-2/26: FOC scheduled for 4/2.
| 10M Port/ 50M Access LC - Multi Mode Fiber 1000BSX | FL273-01-IM | UHG | Melissa Chapman |  | 15953 North Florida Ave MDF Room | Lutz, FL |  | VS18054467 3094-3192 3094-BTKF 3094-BTKG | 2018-03-22 | ASAP | 2018-07-11 | 2018-09-25 |  |  | BBEC.538033 | BRIGHTHOUSE NETWORKS | 81L1XX005925TWCC | 2018-07-05 | FIRST FLOOR DATA ROOM WALL |  |  | 3087280 | 500 | 10.1.93.145 | 10.1.93.146 | 65082 | 202610 | UHG GLOBAL 150 | 9/26: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 9/24: Access install has completed - pending testing completion and OK to turn up. BERT/IOS escalation to complete CTA and Due Date and post order complete. 9/17: Per Spectrum, construction is now complete and they are pending HUB work before scheduling CPE installation. Next update by 9/21 COB. AVM continues to be engaged and pushing Spectrum to completion. 9/10: Access Vendor Management advised that Spectrum's fiber splicing is now complete, however they are currently troubleshooting an ongoing light level issue that arose during testing. Spectrum's next update is expected by 9/13 or as information becomes available. 9/4: Per Spectrum, construction rescheduled estimated completion date to 9/14. Spectrum is checking the status of the splicing and to see if 9/14 is in jeopardy or on track. Next update by COB 9/7 per AVM. 8/27: Per Spectrum, pending completion of the fiber splicing. Pending update from Access Vendor Mgmt (by 8/31.) 8/14-8/20: CONSTRUCTION ECD OF 8/24 IS CURRENTLY ON TRACK. NEXT UPDATE BY 8/23. 7/26: Per AT&T AVM TIER II. SPECTRUM PENDING PERMITS BEFORE CONSTRUCTION CAN COMPLETE. 2 PERMITS NEEDED FOR THIS JOB WITH 1 PENDING (HILLSBOROUGH COUNTY PERMIT) AND 1 APPROVED (FLORIDA DOT PERMIT). CONSTRUCTION IS FOLLOWING UP CONSISTENTLY. SOW 158' OF TRENCHING, 308' BOARING, 226' PULL FIBER PULL THEN 100' INTERNAL FIBER PULL AND SPLICING. 7/23: AT&T AVM TIER II escalating with LEC. Delay due to "County Permits" , requesting scope and timeline of work needed. 7/17: Requested AVM Tier II follow up with Spectrum ASAP. No updates. 7/16: Access Vendor Mgmt escalation with Spectrum update by COB today. 7/10: Access install missed on 7/5 - Access Vendor Mgmt (AVM) engaged and escalating within Brighthouse for status - Brighthouse (Nick) advised this morning that there is no install information on the circuit yet and a ticket has been opened for status and ETA for completion. AVM remains engaged and will continue escalating. 5/29-7/3: Access install scheduled for 7/5. 5/21: FOC completed 5/18, access install scheduled for 7/5. 5/14: Per AIM: Escalation in progress with LEC for new firm dates. 5/7-4/30: Per AIM: FOC is scheduled for completion 5/8. 4/23: Pending FOC completion. 4/16-4/3: FOC scheduled for 4/20. 3/26: Received USO, PON scheduled for 3/27. 3/19: Pending order number/ USO. 3/12-3/5: Order placed and sent to ordering pending Cproject number.
New | Plymouth to Minneapolis 4G Port/ 10G Access EaAVPN 1000 Base-LX | UMN98-10-IM | UHG | Melissa Chapman |  | Plymouth to the Minneapolis POP | Minneapolis, MN |  | VS18144304 3094-0402 3094-BTTF 3094-BTTG | 2018-08-27 |  | 2018-09-20 | 2018-09-21 |  |  | L4YS.989369 |  |  |  | DEMARC FIC::F7 PANEL::2A JACK::27/28 HANDOFF::SC/SM |  |  | 3155506 | 2 3 | 10.1.63.173 10.191.22.205 | 10.1.63.174 10.191.22.206 | 65023 - COS 6039 65023 - COS 9249 | 202610 202609 | UHG GLOBAL 150 UHGECC GLOBAL | 9/21: READY FOR ACTIVATION. 9/17: BERT/IOS ticket issued for escalation - FFLOW ticket 6218741 9/4-9/10: Engineering and Design completed on 8/30. Order due 9/20
New | Plymouth to Omaha 4G Port/ 10G Access EaAVPN 1000 Base-LX | UMN99-10-IM | UHG | Melissa Chapman |  | Plymouth to the St. Paul UVN node (w/ backhaul 10G IOC to Madison or Milwaukee) | Minneapolis, MN |  | VS18146605 3094-0408 3094-BTTH 3094-BTTJ | 2018-08-27 |  | 2018-09-20 | 2018-09-21 |  |  | L4YS.989444 | [6 empty] | 3155514 | 2 3 | 10.1.63.177 10.191.22.209 | 10.1.63.178 10.191.22.210 | 65023 - COS 6039 65023 - COS 9249 | 202610 202609 | UHG GLOBAL 150 UHGECC GLOBAL | 9/21: READY FOR ACTIVATION. 9/18: BERT/IOS ticket issued for escalation - FFLOW ticket 6218823 9/10: Engineering completed on 9/4. Pending completion of Design and other critical dates. Overall due date 9/20. 9/4: Due 9/20
| 50MB Port/ 50M Access EaAVPN 1000 Base-SX | TX078-01-IM | UHG | Melissa Chapman |  | 3434 Saratoga Boulevard | Corpus Christi, TX |  | VS18135357 3094-0177 3094-BTSH | 2018-07-26 |  | 2018-10-18 | 2018-10-03 |  |  | BBEC.549849 | ATT SW | 34KRGN613862SW | 2018-10-12 | 1ST FL IT ROOM SINGLE DATA JACK CN3930 PORT 5, TAGGED |  |  | 3146749 | 10M | 10.1.95.173 | 10.1.95.174 | 64793 | 202610 | UHG GLOBAL 150 | 10/3: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 10/2: Access install completed - pending testing completion and the OK to turn up. 9/24: Construction & Engineering completed fiber placement and splicing ahead of schedule on 9/20. Access install has been bumped up from 10/12 to 10/1. 8/14-9/17: Construction and Engineering target date for fiber work to complete is 10/05. Access install is scheduled for 10/12 and overall due date is 10/18. 8/6: USO's rec'd 7/25: Order rec'd - Pending USO's
New | 2gig Access Port | PH550-05-IM | UHG | Melissa Chapman |  | IDC Bldg. Danny Floro St. Corner C.P. Garcia Ave. Bagong Ilog - 4th Floor | Pasig, Philippines |  | ISR18081578166 VS18144329 3094-BTSV 3094-BTSW | 2018-08-15 | ASAP | 2018-11-07 | 2018-10-08 |  |  | IZYF.101575 | Innove | IC-AOZ-9779 |  | Demarc: 4FVTC8 - GF MDF New ODF pair 13/14 ( port #7) SO#09172018-VDC-29070-N | 10GBase LR | LC - Single Mode Fiber 1000BLX Customer Interface: 10GBase LR | 3153098 | 2 | 10.1.94.101 | 10.1.94.102 | 65272 COS 6039 | 202610 | UHG GLOBAL 150 | 10/9: Possible handoff change 10/8: ICORE,EFMS & USO closed, TID sent-order completed 10/2: Telco testing successful. Circuit has been extended to AT&T Manila 2 POP. Spirient testing is pending. 9/24: Telco confirmed that their core network upgrade is in progress and expected to be completed by end of Sep. 9/3-9/17: No change in status at this point - Telco confirmed that their core network upgrade is in progress and expected to be completed by end of Sep. Scope of work: Telco core network needs to be upgraded to deliver the circuit and also cross connect required to extend the circuit to customer router rack at PLDT Vitro IDC. 8/27: Firm date 10/12/2018 - CNDD 11/7 8/17: Access order placed and acceptance awaited Pending ISR - order placed by Christine 7/3: AT&T rec'd signed contract today 7/3 5/7-6/18: Waiting for contracts, with UHG. 5/7-3/20: Pending signing will follow up. Contract with UHG. 3/19-2/27: Pending signing of contract, with management. 2/26-2/20: Sent contracts to UHG, 2/19-2/13: Have access pricing. 2/12-2/6: Pending access pricing for order. 2/1: Order requested for processing.
New | Dublin MACD PORT / CIR upgrade from 150M to 200M | IR508-05-CM | UHG | Melissa Chapman |  | Block C, Spencer Block, Dublin 1 | Dublin, Ireland |  | ISR18082328800 VS18149258 3094-BTTK 3094-BTTL | 2018-08-15 | ASAP | 2018-09-27 | 2018-10-05 |  |  | IUYF.101673 | SAREA / Enet | SR/VLXP/001278/ATI |  |  | 1000BaseSX | SC Connector |  |  | 10.1.84.237 | 10.1.84.238 | 64671 COS 6039 |  |  | 10/9: ORDER COMPLETE 10/8: Pending confirmation of testing completion 10/1: Scheduled for 10/05 11:00 PM 9/11-9/24: Waiting on the customer to schedule. 8/31-9/10: Customer to provide date and time for TTU 8/15: Order rec'd
| 400M Port/ 1GB Access 1000 Base-SX - Optical Handoff | WI012-10-IM | UHG | Melissa Chapman |  | 115 W Wausau Ave | Wausau, WI |  | VS17191168 3094-3103 3094-BSYK | 2017-10-25 |  | ASAP | 2018-10-09 |  |  | IZEC.571100 | FRONTIER TELEPHONE | 30VLXP893509FTNC | 2018-09-21 | RAD 103 1ST FLR MDF RM TAGGED LABELLED NOT EXTENDED MM PORT 5 | [9 empty] | 10/9: ORDER COMPLETE 10/9: Testing ongoing this morning - testing with Frontier failed but we ran good to loop. Ticket out to OSWF to remove loop. 10/8: REQUESTED UPDATE FROM DEREK HUNTER 10/1: Escalation sent to District Escalation Mgr Derek Hunter to add to provisioning escalation list - pending testing completion. 9/25: BERT/IOS ticket opened to escalate for completion of testing and remaining critical dates. 9/17-9/24: We received R80 on the access PON which is an indicator access install is complete on the LEC side. Pending additional details, VLAN completion, testing, etc. 7/30- 9/10: Access still showing on track for 9/21 due to construction. 7/24: Project mgr for FTR - LORI.LEYA@FTR.COM 919 224-116 7/23: Follow up sent to provisioning to request details on construction. Access currently targeted to install 9.21. 7/16: Provisioning advised construction details were provided to LCON by Frontier. I've requested Ordering OM reach out to LEC for those details. 7/9: Frontier provided a 9/21 access install date due to construction. - NEED CONSTRUCTION DETAILS. Check for expedite. 6/18-7/3: Pending an install date on new access PON HCSC3999588. Date of 7/3 for POP Collector is unchanged. Working to firm up dates with LEC Frontier 6/12: CORRECTION ON TIMEFRAME - We received a CONFIRMED completion date on POP Collector PON# HCS03985945 for 7/3. The new Access PON# HCSC3999588 was released on 6/7. 6/6: Escalation sent to District Escalation Manager - new PON# HCS03985945 issued on 6/5. 6/5: Provisioning indicated there is a design issue on this order. The customer is located in LATA 350 but the order is requesting the serving office of DKLBILRS which is in LATA 354. OM Ferdinand Cabiso confirmed yesterday that he's working with his SME's on how to proceed. Pending status update. - 2-mo issue - escalation 6/1-5/29: FOC scheduled for 6/22. 5/21: SME ticket closed order has been supped, pending supped firm dates. 5/14- 5/7: SME ticket has been opened to assist with design completion. 4/30-4/9: FOC scheduled for 5/3. 4/3: Order has been reFoc'd with the LEC, pending firm dates. 3/26: Issue with RUID with order. Provisioning working to resolve the issue. 3/19-2/20: PON created, FOC scheduled for 3/23. 2/12: Escalation team assisting with pushing to correct LSO and provide firm dates. 2/5: Order is being supped due to LSO mismatch. Pending new firm dates. 1/29-1/8: Pending access install date from provisioning team. 1/2-12/26: Provisioning manager engaged to gain new FOC date. 12/18-12/11: Pending new FOC date. 11/27: Received new token and sent to OM, pending new PON. 11/20: Order needs new token issued to move forward with PON. 11/13: Working with OM and provisioning leadership to provide PON. 11/6: Escalated with provisioning manager for PON. 10/30: Received USO 10/26, pending PON on 10/31. 10/23: Received C-project # pending USO's. 10/16-10/9: Pending order processing.
| 10M Port/ 50M Access 1000 Base-SX | TX422-01-IM | UHG | Melissa Chapman | Wellmed | 3199 W. Camp Wisdom Rd Mpoe Flr 1 | Dallas, TX |  | VS18094011 3094-2792 3094-BTNX | 2018-05-24 |  | 2018-08-10 |  |  |  | BBEC.565289 | ATT SW | 14KRGN884223SW | 2018-10-18 | [10 empty] | ACCESS DUE 10/18 - VLAN PON HMSV4089664 10/22. 10/15: For access, the date was improved from 10/29 to 10/18 which is better news. We’re still pushing on the escalation side as well to get these done ASAP and hope to have good news as we move forward this week. 10/8: PON acknowledged - LEC provided a new circuit ID (14KRGN884223SW) and completion date of 10/29. 10/1: New access PON issued - HMS02305094 - to update suite#. Pending completion by LEC 9/27: Access PON HMS02282397 showing EAD of 9/28. 9/21 Escalation to Kauyaii Moore for status of DDF escalation ticket. Need status of supp and eta for completion. - RECEIVED FFLOW TICKET 6220786 TO UPDATE SUITE TO 170, OPENED DDF TICKET TO REQUEST PON CANCELLED & REISSUED. ORDERING & SOA IS UNABLE TO SUP DUE TO C03 BILL TRIGGERED...EXCEPTION HANDLING-KMOORE 9/17: REACHED OUT TO OS CHRISTIAN CHILDS TO MAKE SURE SUPP IS COMPLETE FOR SUITE 170. Pending access install completion notice from the LEC 9/11: Order is being supp'd with SUITE 170 per Melissa. Pending supp and access completion notice from the LEC. Access has installed in suite 170 (demarc provided), we just need supp issued, testing completed and critical dates posted complete. 9/10: Reached out to Melissa regarding address issue - LEC advised suite# should be 170, not 500. 9/4: Construction & Engineering completed the fiber work on 8/30. Pending an updated access install date. 8/27: Customer prem work is showing completed as of 8/24. Construction & Engineering is scheduled to complete fiber placement and splicing by 8/31. 8/21: The Construction Contractor has now found a problem with the SOC going from a pole to the Cust. Bldg. AT&T may have to fix the issue with the existing SOC, in order to place the new fiber to the Bldg. 8/20: Construction & Engineering determined there are issues with the conduit going from the pole to the building and the date is now showing 10/24. Emailed UHG with details. Pending further status. 8/14: Our construction site is showing the customer prem was due to be ready on 8/2 however it's now showing this item completed. Escalation sent to NSS PM Brian Mayfield for status and to find out if 8/20 date provided for fiber work is in jeopardy. 6/25-08/06: Access install scheduled for 8/27. Delay due to Construction & Engineering fiber placement and splicing which is not due to complete until 8/20. 6/18: New PON HMS02282397 issued on 6/6. FOC due 6/29. 6/6: PER LCON CORRECT ADDRESS WAS 3107 WEST CAMP WISDOM RD. DALLAS,TX 75237, SUITE 500. SUPP ORDER TO UPDATE THE ADDRESS. 5/21: Order placed, pending cproject number.
New | 100MB Port/ 250M Access EaAVPN 1000 Base-SX | M0289-07-IM | UHG | Melissa Chapman |  | 170 Parkway West | Duncan, SC |  | VS18166656 3094-0869 3102-BBBG | 2018-09-04 | 2018-11-30 | 2018-11-30 | 2018-10-11 |  |  | BREC.711048 | ATT SE | 30KRGN402043SB | 2018-10-17 | 1ST FLOOR TELCO RM WALL MOUNT PORT 2, TAGGED |  |  | 3166071 | 50 | 10.1.91.5 | 10.1.91.6 | 65259 | 202610 | UHG GLOBAL 150 | 10/11: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 9/25-10/8: Access install scheduled for 10/17. Construction & Engineering fiber work is scheduled to complete on 10/10. 9/18: Site visit completed yesterday - pending news from Construction & Engineering on any fiber work needed as well as an update from the LEC on when access install will take place. FOC due back by 10/9. Overall due date is 11/30. 9/4: Order rec'd - Pending USO's
| HOT ORDER 3M 2xT1 AVPN | TN050-01-IM | UHG | Melissa Chapman |  | 1893 General George Patton Drive | Franklin, TN |  | VS18157237 3094-2944-FR 3094-2945 3094-2946 3102-BBBD | 2018-07-26 |  | 2018-10-04 | 2018-10-23 |  |  | DHEC.173780.811 DHEC.173780.812 | ATT SE | T4HCGS866970SC T4HCGS866969SC | 2018-10-11 | 1ST FLR TELCO RM MM1 POS1 1ST FLR TELCO RM MM1 POS2 |  |  | 3161879 |  | 10.45.11.5 | 10.45.11.6 | 64790 | 202610 | UHG GLOBAL 150 | 10/23: ORDER COMPLETED THIS MORNING - Ready for turn up plug and play. 10/22: Escalating for missed DD - order completion. - UPDATE: Testing issues - could not loop smart jack - TICKET# HT025665 10/15: Access install completed - pending testing completion and OK to turn up. DD 10/19 10/8: Access install rescheduled for 10/11. 10/2: Pending status of HITS ticket on PON supp with new LCON info - Escalating no date provided yet. 9/24: Supp issued last week with new LCON info. Requested HITS ticket escalation in IOS for update on supp and ETA for install. 9/18: Customer Site Not Ready CNR - Per the LEC, TECH VISITED PREMISE, NA TO SITE. NO ONE ONSITE, SITE UNDER CONSTRUCTION, CALLED AHEAD, UNABLE TO LEAVE VM DUE TO IT BEING FULL. Order will require a supp and new date once site is ready to accept LEC. 9/17: Access install scheduled for today 9/11: Rec'd USO's 9/11: Reprocessed per Chris - pending USO's - VTNS 7/27: Order rec'd - Pending USO's
| 50MB Port/ 100M Access EaAVPN 1000 Base-SX | UNY14-07-CM | UHG | Melissa Chapman |  | 2950 Express Drive South | Islandia, NY |  | C11384719 VS18152119 3094-0574 3094-BTTZ 3094-BTVB |  |  | 2018-11-19 | 2018-10-29 |  |  | IUEC.822442 | Verizon North | 32KFGS217208NY | 2018-10-17 | 2ND FLR SUITE 240 SERVER ROOM. WALL MOUNTED CANOGA . UNIT #2.TAGGED WITH CKT ID. | 1000BASESX |  | 3161141 | 500 | 10.45.10.233 | 10.45.10.234 | 64553 | 202610 | UHG GLOBAL 150 | 10/29: VLAN PON HNSV4077590 completed. ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 10/18: Access install completed - demarc provided - VLAN PON HNSV4077590 due to complete on 10/30. 10/15: Access install rescheduled for 10/17. 10/2-10/8: Access install scheduled for 10/26. 9/10-9/24: Pending an install date from the LEC Verizon North. FOC due 10/15. 8/14: Order rec'd - Pending USO's
New | 200MB Port/ 400M Access EaAVPN 1000Base-SX | CA858-03-IM | UHG | Melissa Chapman | UHG- Optum 360 | 3215 Prospect Park Drive | Rancho Cordova, CA |  | VS18184928 3094-1333 3102-BBCK | 2018-10-01 |  | 2018-12-24 | 2018-10-25 |  |  | BLEC.975300 | ATT West | 18KRGN520048PT | 2018-10-25 | 1ST FLR, 1.1 MPOE, WALLMOUNTED. PORT 5 HANDOFF TO PNL 2 POS 5&6 | 1000 Base-SX |  | 3177026 | 50 | 10.1.89.205 | 10.1.89.206 | 64787 | 202610 | UHG GLOBAL 150 | 10/25: ORDER COMPLETE - READY FOR TURN UP 10/22: ATT West access install scheduled for 10/25 10/15: Pending an install date from ATT West 10/1: Order rec'd - Pending USO's
New | 1G Port/ 1G Access EaAVPN 1000Base-SX | UTX34-09-IM | UHG | Melissa Chapman | UHG- Pacificare | 6200 Northwest Parkway | San Antonio, TX |  | 303730963 VS18187163 3094-1082 3102-BBBQ | 2018-09-24 |  | 2018-12-28 |  |  |  | IZEC.500412 | ATT SW | 31KRGN653349SW | 2018-11-28 |  |  |  | 3178983 |  | 10.1.90.1 | 10.1.90.2 | 64608 | 202610 | UHG GLOBAL 150 | 11/2: Melissa requested cancellation of this order - HITS ticket issued. 10/22-10/29: Access install scheduled for 11/28. 10/15: Pending an install date from ATT SW. 9/24: Order rec'd - Pending USO's
New | 200MB Port/ 400M Access EaAVPN 1000Base-SX | GA026-06-IM | UHG | Melissa Chapman | UHG- Alere | 3200 Windy Hill Road The Towers at Wildwood Plaza | Atlanta, GA |  |  | 2018-10-02 | [14 empty] | 10.1.89.189 | 10.1.89.190 | 64698 | 202610 | UHG GLOBAL 150 | ORDER CANCELLED PER UHG 10/22: Ordered as 300M. Chris advised ATT SE doesn't offer 300M or 350M so processed with 400M 10/2: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX456-01-IM | UHG | Melissa Chapman |  | 901 South Mopac Expressway | Austin, TX |  | VS18194351 C11390934 3094-1576 3094-BVBP | 2018-10-11 |  | 2019-01-03 | 2018-11-02 |  |  | BBEC.587968 | ATT SW | 32KRGN653171SW | 2018-11-02 | I BUILDING 2 BASEMENT TELCO ROOM 1 POS 12 MM/LC HANDOFF | 1000 BASE SX |  | 3184157 | 50 | 10.45.10.205 | 10.45.10.206 | 65232 | 202610 | UHG GLOBAL 150 | 11/2: ORDER COMPLETED EARLIER THAN ANTICIPATED - READY FOR TURN UP PLUG AND PLAY 10/11-10/22: Order rec'd - Pending USO's
| HOT ORDER 1G Port/ 1G Access EaAVPN 1000 Base-SX | C1626-07-IM | UHG | Melissa Chapman | UHG- Nexidia | 12655 Edison Dr | Alpharetta, GA |  | VS18184929 3094-1235 3102-BBCG | 2018-10-02 |  | 2018-12-24 | 2018-10-29 |  |  | IZEC.521492 | ATT SE | 38KRGN614242SB | 2018-10-29 | 1ST FL TLCO RM RR AL28 3930 UNIT 11 TO E PNL 4 JCK 5 | 1000 Base-SX |  | 3177025 | 50 | 10.191.22.61 | 10.191.22.62 | 65413 | 202609 | UHGECC GLOBAL | 10/30: ORDER COMPLETE - READY FOR TURN UP 10/15-10/22: Access install scheduled for 10/29. 10/2: Rec'd order from UHG - pending USO's
| 20MB Port/ 50M Access EaAVPN 1000 Base-SX | TX427-01-IM | UHG | Melissa Chapman |  | 3300 N McColl Rd. | McAllen, TX |  | C11384727 VS18154165 3094-0523 3094-BTTV | 2018-08-15 |  | 2018-12-10 | 2018-11-12 |  |  | BBEC.551711 | ATT SW | 38KRGN613699SW | 2018-11-21 | 1ST FLR SUITE H I J K L IT ROOM R/R TCH PNL 1 POS 1 AND 2 |  |  | 3160022 | 50 | 10.1.91.161 | 10.1.91.162 | 64771 | 202610 | UHG GLOBAL 150 | 11/12: ORDER COMPLETE 10/30-11/5: Access install completed. VLAN completed in SOTS - Pending testing completion and OK to turn up. 10/22-10/29: Access install moved up to 10/29. 10/15: Access install scheduled for 11/21. Due date pushed to 12/10. 10/8: Order was supp'd on 10/3 - pending FOC (due 10/26) 10/2: Email to Stephanie Batie (Ordering) for update on supp to change LCON. 9/26: Melissa provided new contact info: 956-455-5057 Luis E. Casas, CHC <luis@casasgroup.net> 9/25: Pending FOC - Construction update says "waiting on Jason Ozer to provide LOCAL LCON name & number." Requested update to see what the LCON issue is. Order is CNR'd (Customer Not Ready) because of the LCON issue. Working to get details. 9/4-9/17: Pending FOC from ATT SW. FOC due back by 9/24. 8/15: Order rec'd - Pending USO's
| 10MB Port/ 50M Access EaAVPN 1000 Base-SX | KY010-07-IM | UHG | Melissa Chapman |  | 9100 Shelbyville Rd | Louisville, KY |  | C11384805 VS18159441 3094-0781 3094-BTVP | 2018-08-20 |  | 2018-11-23 | 2018-11-20 |  |  | BBEC.570961 | ATT SE | K1KRGN402042SC | 2018-11-20 | 2ND FLR CUST MDF ROOM UNIT#1 SC PORTS 9/10 LABELED W/ CRKT ID |  |  |  |  | 10.45.10.249 | 10.45.10.250 | 65021 | 202610 | UHG GLOBAL 150 | 11/20: ORDER COMPLETE 11/12: Access install scheduled for 11/20. 10/29-11/5: FOC due back by 11/13. Pending install date. 10/15: Supp'd order with new LCON: Eddie Gibson / 502-318-1820 / todd.gibson@optum.com 10/2-10/8: CNR - Per LEC: FOC WILL BE DELAYED DUE TO CURRENT CNR ON THIS ORDER FOR SITE VISIT. WE ARE WAITING ON LCON TO PROVIDE ACCESS TO SUITE TO CONDUCT THIS SV. 9/25: CNR (Customer Not Ready) for site visit - delayed. Site Visit Scheduled, pushed to 9/26/18 9/10-9/17: Pending an install date from the LEC ATT SE. FOC due back by 10/1. 8/20: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL354-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 13301 N Dale Mabry | Tampa, FL |  | VS18186417 3102-0153 3094-BTZH 3094-BTZJ | 2018-09-21 | 2019-01-08 | 2019-01-08 | 2018-11-30 |  |  | BBEC.521363 | Frontier-CTF | 65KEGS685140FTNC | 2018-11-26 | SL01#SH 1#PRT03#PHYSTE A 1ST FLOOR TELCO BOARD PDEMARC L2: ORT 3 # 45 #EXTN#TAGY |  |  | 3178154 |  | 10.1.90.129 | 10.1.90.130 | 64679 | 202610 | UHG GLOBAL 150 | 12/3: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 11/27: Pending order completion - access install is complete. DD is 12/26. 11/12: Access due 11/26 - UPDATE ORDER SHOWING R80 ACCESS INSTALL COMPLETE - Pending Demarc. 10/12-11/5: Rec'd new USO's 3102-0153 - pending install date from LEC - FOC due 11/14. 10/9: USO's are in REJECTED state - pending update from Clyde CSS 9/21: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL366-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 20615 Amberfield Dr | Land O Lakes, FL |  | 303691290 VS18180645 3102-0116 3094-BTYS 3094-BTYT | 2018-09-27 | 2018-12-28 | 2018-12-28 | 2018-11-30 |  |  | BBEC.508795 | Frontier | 65KEGS998953FTNC | 2018-11-26 | SLOT 01, SHELF 01, PORT 03, PHYSICAL LOC: 1ST FLR TELCO BOARD JK: RJ45, EXTENDED: NO, TAGGED: YES |  |  |  |  | 10.1.90.17 | 10.1.90.18 | 64593 | 202610 | UHG GLOBAL 150 | 12/3: ORDER COMPLETE - NO DEMARC PROVIDED - OPENED AERO CM 422705 11/27: No update from the LEC Frontier that access install completed - pending status - will send escalation at miss +2 which is Wednesday 11/28 10/22-11/12: Frontier Access install scheduled for 11/26. 10/9-10/15: Pending access install date from LEC Frontier 9/27: Order rec'd - Pending USO's
New | 300MB Port/ 500M Access EaAVPN 1000Base-SX | TX023-12-IM | UHG | Melissa Chapman |  | 1311 President George Bush Tollway | Richardson, TX |  | 303820144 VS18199464 3102-0183 3094-BVCG 3094-BVCH | 2018-10-19 | 2019-01-29 | 2019-01-29 |  |  |  | BMEC.914841 | GTSW | [7 empty] | 10.1.92.245 | 10.1.92.246 | 64517 | 202610 | UHG GLOBAL 150 | 11/12: ORDER CANCELLED BY UHG MELISSA 11/5: Pending install date from the LEC 11/1: USO's rec'd 10/19: Order rec'd
New | HOT ORDER 10MB Port/ 50MB Access EaAVPN 1000 Base-SX | FL349-01-IM | UHG | Melissa Chapman | Wellmed | 1685 Gulf to Bay Boulevard | Clearwater, FL |  | VS18172304 3094-0995 3094-BTXH 3094-BTXJ VS18184930 3094-1332 3102-BBCJ 3102-BBCH | 2018-08-23 |  | 2018-12-21 | 2018-12-06 |  |  | BBEC.557519 | Frontier | 65KFGS001273FTNC | 2018-11-05 | BACK OF SUITE/MN ELEC RM/WL MNTD/TGGD/RAD 203/PORT #5 |  |  |  |  | 10.1.91.25 | 10.1.91.26 | 64757 | 202610 | UHG GLOBAL 150 | 12/7: ORDER COMPLETE 11/13-12/3: We have R80 completion of access - pending testing completion. DD 12/21 11/5: Access due to install today. 10/22-10/29: Access install scheduled for 11/5. 10/15: Pending an access install date from the LEC Frontier. FOC due back by 11/13. 10/5: New order submitted by Clyde Laman CSS. Pending USO's 10/2: Pending status on change to Frontier - process new order 9/25: Pending an access install date from the LEC Brighthouse. FOC due back by 10/29. - Per UHG change to Frontier 8/23: Order rec'd - Pending USO's
| 20MB Port/ 50M Access EaAVPN 1000 Base-SX | UT016-01-IM | UHG | Melissa Chapman | SavvySherpa | 13961 Minuteman Dr. | Draper, UT |  | C11382019 VS18135398 3094-0208 3094-BTSJ 303730965 VS18187169 3094-1077 3102-BBBN 3102-BBBP | 2018-07-30 |  | 2019-01-09 |  |  |  | BBEC.568885 | Zayo | ETYX231298ZYO | 2018-12-13 |  |  | 08/28/2018 19:16: C&E update: Additional information for installation. Customer is in bldg. 3 of three building office complex. Outside communication cables all come in to property through bldg. 1. Common area for all three bldgs. in 1st floor Bldg. 1.Will need new fiber from Network splice to customer suite: approx. 1,500. Will also need new UG in ROW approx. 400’ As per LCON Gerome – no available fiber on site – will need to place new fiber for entire on-site route.Customer wants no active equipment in 3rd floor suite – Placing 3930 in Bldg. 3 - 1st floor common room and VEP handoff in 3rd floor customer suite. Will need to place duct from 1st floor to 3rd floor in riser and also to traverse 3rd floor to suite 330. 120v AC Power available via wall outlet in Bldg 3 – 1st floor common room. Property Management Contact – MIKE DEJONG - 801-706-9733 - mdejong@dawcg.com | 3146944 |  | 10.1.93.49 | 10.1.93.50 | 65058 | 202610 | UHG GLOBAL 150 | 12/10: Requested order be cancelled per Melissa's email. 11/5-12/10: Zayo confirmed a 12/13 install date for access. 10/15-10/29: New USO's rec'd - LEC is Zayo. PON released on 10/16. FOC due back by 11/19. 10/9: Pending USO's on reissued order. 9/28: Confirmed VS18135398 has been cancelled per UHG's request. Pending new USO's. 9/25: Melissa advised this needs to be changed to ZAYO. 9/10-9/24: Access install scheduled for 11/29. Fiber work due to complete 11/16. The client has informed Chris that they would like to cancel this ASE (EaAVPN) order due to a potential impasse between AT&T install and the Property manager. This will be a cancelation and new order with a different ESP 9/4: Construction & Engineering provided an 11/16 completion date for fiber placement and splicing. The only site requirement is to have the customer "place a 120V AC dedicated outlet on a dedicated 15Amp circuit breaker. Single standard 3 prong 120V AC, 15Amp dedicated receptacle." Please c COLUMN T for more details on work C&E will be doing at site. 8/31: LEC advised site visit delayed bu scheduled. 8/28: Escalating on missed FOC. Pending install date from the LEC. 8/14-8/21: FOC due back by 8/24. 7/30: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL353-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 508 S Habana Ave | Tampa, FL |  | 303683815 VS18179779 3094-1115 3102-BBBR 3102-BBBS | 2018-09-21 | 2018-12-27 | 2018-12-27 | 2018-12-05 |  |  | BBEC.598991 | Frontier | 65KEGS995561FTNC | 2018-11-15 | SL01#SHL F01#PRT01#PHYSTE 280 UTILITY #JKRAD#EXTN#TAGY .WALL MOUNTED NID IN 2ND FL STE280 UTILITY ROOM...NID LABELED. |  |  | 3173853 |  | 10.1.90.141 | 10.1.90.142 | 64687 | 202610 | UHG GLOBAL 150 | 12/5: ORDER COMPLETE 12/3: Access install is complete - pending testing completion and turn up (targeting 12/14) 11/27: Install date was missed - Tier has engaged and is currently escalating for LEC tech dispatch to the customer site. 11/12: Access install scheduled for 11/15. 10/9-11/5: Pending access install date from LEC Frontier. FOC due 11/7 9/21: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL355-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 4278 W Linebaugh Ave | Tampa, FL |  | 303683837 VS18179773 3094-1114 3102-BBBT 3102-BBBV | 2018-09-21 |  | 2018-12-27 | 2018-12-14 |  |  | BBEC.533809 | Frontier | 65KEGS996334FTNC | 2018-11-15 | SL01#SHLF01#PRT03#PHYFIRST FLOOR TELCO LOST#JKRJ45 C#EXTN#TAG I STALLED RAD NID ON PHONE BOARD IN THE |  |  | 3173849 | 4 | 10.1.90.125 | 10.1.90.126 | 64676 | 202610 | UHG GLOBAL 150 | 12/14: ORDER COMPLETE 12/10: AERO Design ticket 430740 to issue VLAN PON. PON was not submitted so escalation issued. 11/27-12/3: Pending completion - DD is 12/14. 11/5-11/12: Access install completed (R80) ahead of schedule. Demarc provided. Pending testing completion, 10/15-10/29: Access install scheduled for 11/15. 10/9: Pending access install date from LEC Frontier 9/21: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL360-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 2706 W St Isabel St | Tampa, FL |  | 303685249 VS18180447 3094-1167 3094-BTYG 3094-BTYH | 2018-09-25 | 2018-12-28 | 2018-12-28 | 2018-12-06 |  |  | BBEC.500538 | Frontier | 65KEGS997689FTNC | 2018-12-14 |  |  |  | 3174179 |  | 10.1.90.181 | 10.1.90.182 | 64646 | 202610 | UHG GLOBAL 150 | 12/6: ORDER COMPLETE 12/3: Received access install notification from Frontier - pending testing completion and OK to turn up. Due Date 12/28. 10/29-11/27: Access install scheduled for 12/14. 10/9-10/22: Pending access install date from LEC Frontier 9/25: Order rec'd - Pending USO's
New | London UK MACD | UK508 | UHG | Melissa Chapman |  | VANTAGE POINT BUSINESS VILLAGE | (MITCHELDEAN) London UK |  | ISR18071933257 VS18127584 3094-BTRV | 2018-07-19 | 2018-08-20 | 2018-11-16 | 2018-12-12 |  |  | EAET00955232 | SAREA | SR/VLXP/037002/ATI |  |  | 10BaseT |  |  |  | 10.1.88.177 | 10.1.88.178 |  |  |  | 12/12: Completed and Closed 12/10: Per Yaro (NCON), the testing was completed OK, but there is a circuit id mismatch - once cleared Yaro will close the order (should be by tomorrow) 12/3: Migration to take place for both the circuits at the same time on 12/4 from 10:00- 14:00 hrs 11/27: Feedback from Vodafone: “I have urgently passed the below request to cabling team to complete the works as per customer request. I will get back to you upon response whether they will able to fetch resource for 11/27.” Red Freeze are 11/27 & 11/14 dates when Vodafone cannot perform any kind of works. 11/12-11/16: Pending cut confirmation for DECEMBER 14TH at 6:00pm UK LOCAL TIME 11/5: Telco on site today to complete fiber work. Requested cut for DECEMBER 14TH at 6:00pm UK LOCAL TIME 10/29: Shooting for 11/16 move of circuit around 6pm Ireland time. Request submitted to NCON. 10/16: Still targeting Vodafone firm date of 11/16/2018. Reached out to NCON Jaroslav Bosansky - Jaro requested downtime window on the 16th so we can align resources. 10/8: Vodafone gave us following: Please be informed Access engineer requested to use the existing fibre at the site hence order has been awaiting to request the cabling works. As we have found the below to involved in the circuit to be completed. Please find the scope of works: o CEA was located in Ground Floor (Customer floor 1), Cage SR3 of Building 7. OMS 1674 in this CEA is having fibre connectivity to GCR o OMS 1674 in CEA of Building 7 is daisy chained to OMS 846 (Customer Location) of Building 8 at 2nd Floor, Server Room, Server Rack. Also OMS 846 is not located at CEA o Now customer requested for the NTP shift from 2nd Floor to Ground floor in Building 8 o There is a fibre Patching from 7th Building to 8th Building connecting to OMS 846. o Now the requirement would be to shift the Fibre & Mux OMS 846 located at Building 8 to Ground Floor. 9/28: No further updates, IPC has requested the latest from PTT 9/26: The scope of work is to shut down the Telco equipment, unmount it from the current rack, mount it in the new rack and power it up once connected to the new infrastructure build. There are no changes to existing configs and only reason the circuit would not come up immediately after NTU being reconnected in the new rack is faulty cabling, but Vodafone will have that tested prior & will also be able to support any troubleshooting while on site. 9/1-9/24: Vodafone firm date is 11/16/2018 - Requested confirmation from NCON Jaro on scheduling guidelines and whether a hot cut will be required. 9/11: Order has been placed with fiber services team as they will need to pull back the fiber or run in a new internal fiber to the new comms room. Once team completes the fiber work, we will able to begin the migration from, **EXISTING NTP:2nd floor, MDF(SERVER Room),routes to the MDF on Floor 2,Other Mount. **NEW NTP: Ground floor, Comms Room, Customer's Rack, Rack Mounting. Estimated ready for service (ARFS) date for this circuit is 11/16. 9/10: Pending update from PTT on dates. 9/5: The design & planning have been completed as of yesterday and the order moved to the PTT provisioning team. We have reached out to the PTT asking for additional details. Status pending. 8/30: Vodafone access engineer completed the work and sent an email to planning team with the details. This is now with PTT planning team. However in a call b/t the PTT engineer and customer indicated the customer would send a rack layout and floor plan to VF engineer (Tanya Vincent , tanya.vincent@vodafone.com) which she has not received. Can you please check and ask customer to send this to Tanya? 8/30: Per last week's update from Vodafone, they were planning a call with the customer to have all the details clarified. In-country PM has reached out to Vodafone asking for the outcome, more to come shortly.
New | 300M Port Upgrade MACD Ethernet AVPN | II529-05-CM | UHG | Melissa Chapman |  | 4 HOSUR ROAD, AUDUGODI, OPPOSITE MICO BOS | Bangalore India |  | ISR18101216782 3094-BTZPC 3094-BTZQ | 2018-08-22 | ASAP | 2018-12-18 | 2018-12-18 |  |  | BKYF.101276 | Tata TTSL | 8001806096 |  |  |  | 1000base SX- LC | [7 empty] | 12/18: Upgrade completed successfully. Order complete 11/13-12/10: Upgrade scheduled for December 15th after 22:15 CST 10/16-11/5: ISR rec'd. Per NCON Arun Mohan, "Awaiting window from customer." 10/9: Countersigned rec'd - pending ISR#.
| HOT ORDER 60MB Port/ 250M Access EaAVPN 1000 Base-SX | PR517-01-IM | UHG | Melissa Chapman | United Healthcare Optum | MONTEHIEDRA OFFICE CENTRE, 9615 LOS ROMEROS AVE | San Juan, PR |  | VS18105943 3094-0138 3094-BTPL 3094-BTPM | 2018-06-08 |  | 2018-09-11 | 2018-12-19 |  |  | BREC.609941 | Centennial of PR | Centennial CKT: A9180531 Centennial Order#: 765318 | 2018-09-21 | DEMARC: 1ST FLOOR CHAMBER ROOM, RIGHT SIDE, RACK MOUNTED CISCO 3400 PORT 0/2 TAGGED WITH CKT D: A9180531 |  |  | 3125165 | 310 | 10.1.94.165 | 10.1.94.166 | 64805 | 202610 | UHG GLOBAL 150 | 12/19: Order Complete 12/10: PON was supp'd requesting 12/18. Reached out to JOSE NIEVES MORALES requesting his support to confirm the date/status. 11/28-12/10: Order due date to LEC Centennial has been supp'd requesting install by 12/18. Pending confirmation from LEC. 11/27: PER THE LCON,THEY ARE STILL UNDER CONSTRUCTION AT THIS SITE, AND ARE STILL WAITING TO IDENTIFY THE IT ROOM TO HAVE THE SERVICE DEMARKED 11/16: Carrier Management engaged - they have ESCALATED TO THE CARRIER FOR STATUS ON CKT COMPLETION 11/12: No word back from LEC Centennial. I have issued an AERO CM ticket 401670 to have Carrier Management engage if possible to find out why the delays. 11/5: Access install missed - BERT/IOS ticket to be opened to escalate. 10/29: Access install showing due to complete today. - UPDATE: INSTALL MISSED - ESCALATE ON EAD+2 (10/31) 10/22: Confirmed in TIRKS - Access PON was reissued on 10/18 requesting a 10/29/18 install. Pending confirmation. 10/16: Assembler team advised they need 9-biz days lead time on request so I asked for 10/29 install date from Centennial. 10/15: No EAD provided by LEC Centennial. BERT/IOS Escalation issued for missed install. Pending update from field. 10/8: PER TELCO (CENTENNIAL PR), THE LOCAL CUSTOMER (BRENDA DAVILA 787 806 5748) DID NOT HAVE A LEASING AGREEMENT. Pushing back to team as we have been advised that lease IS signed. Requested PON supp and new install date from LEC. 10/2: The 9/21 access install date was missed - reached out to Jose Nieves Morales who helped us on previous orders into Puerto Rico. Pending status. LEASE IS SIGNED 8/27-9/17: Access install scheduled for 9/21. 8/21: CARRIER NEEDS SUP WITH VALID LCON AND THE LOCATION WHERE THE CKT NEEDS TO BE INSTALLED. Need update on lease issues. Pending signatures for the lease - access after 9/1. 8/14: Order showing CNR - Possible lease issues. Pending customer update and OK to request LEC redispatch. 7/25: AT&T TIER II engaged. Ckt is currently a CNR. LEC request valid LCON and location for install. Possible lease issues 07/23: Ckt designed. 7/16: Pending install date from Centennial - reached out to tech to find out who in Centennial is assigned. Centennial CKT: BREC609941CEN == Centennial Order#: 765318 7/3-7/10: Pending install date from LEC Centennial of PR 6/26: Pending USO's 6/12: Chris Cowan changed the Ethernet from 200 to 250 as Centennial did not offer 200M - order released 6/11. 6/6: Order rec'd
| HOT ORDER 10MB Port/ 50M Access EaAVPN 1000 Base-SX | TX437-01-IJ | UHG | Melissa Chapman |  | 9380 W. Sam Houston Parkway S Suite 200 | Houston, TX |  | C11384734 VS18154170 3094-0573 3094-BTTY | 2018-08-17 |  | 2018-09-28 | 2018-12-20 |  |  | BBEC.550613 | ATT SW | 28KRGN747153SW | 2018-11-12 | BACK OF BUILDING CIENA 3931 PORT 1 TAG |  |  | 3160041 | 50 | 10.1.91.77 | 10.1.91.78 | 64769 | 202610 | UHG GLOBAL 150 | 12/20: ORDER COMPLETE 12/10: Reached out to Niara Shipmon (Network Services) who was working this order a few weeks back when she followed up with ENOC regarding access order. Requested update and details on issues. 11/27-12/3: Escalating for update on missed install. BERT/IOS 11/5: New install date: 11/12/2018 10/29: Fiber work completed on 10/25. Pending new install date. DDF ticket issued for new dispatch date. 10/2-10/22: Customer prem work ready date 10/26. Construction still set for 11/13 on fiber placement and splicing completion. 9/25: I reached out to the Planner Michael Valentine to find out why they didn't catch this earlier on. He advised that the Engineering Contractor linked this request to the existing NTE which was on the opposite side of the strip center. Due to limitations of an electrical handoff, they had to change this to installing new equipment on the other side where the customer will be located. The job to place a new outside unit (3931) and fibers was approved on 9/20. Fiber work not scheduled to complete until 11/13/18 but they are working to improve this timeframe considering the delays. 9/17: Per Construction & Engineering, site visit completed 9/13. Fiber work not scheduled to complete until 11/13/18. SITE VISIT NOTES: WALKED WITH: LCON WAS NOT AVAILABLE BUT LEFT ME INSTRUCTION FOR BLD ACCESS. ALT LCON: CURTIS: 903-261-5359 GENERAL TELCO NOTES: LOCATION IS SUIT 200 BUT AT THE MOMENT IS CURRENTLY NOT LABLED. I HAD TO GAIN ACCESS VIA A KEY BOX IN THE BACK ATTACHED TO POWER EQUIPMENT WITH THE 4 DIGIT CODE, (0326) BUILDING DOES NOT HAVE POWER AT THE MOMENT. BLD IS LIKELY TO UNDERGO CONSTRUCTION PRIOR TO THE TENANT MOVING IN, BUT THIS IS NOT CERTAIN. I PROPOSE WE DROP A CIENA 3931 OUTSIDE TO SERVE ALL CURRENT AND FUTURE TENANTS OF THIS STRIP CENTER. EXISTING: CIENA 3930 HKTNTXCU-0BW 840 BANDWIDTH AV AND PORTS AV. LOCATED OPPOSITE END OF STRIP CENTER WITH NO SHARED MPOE. USING THIS NTE WOULD BE COMPLICATED. SOC FROM ROW TO FDF. OUTSIDE GROUND ROD FDF REQUIRED: A NEW A/C OUTLET CIENA 3931 TO BE PLACED OUTSIDE. INNERDUCT TO PROVIDE PATHWAY FROM FDF TO SUIT 9/4: Access due to install on 9/13. Overall due date 9/28. 8/17: Order rec'd - Pending USO's
New | HOT ORDER 10MB Port/ 100M Access EaAVPN 1000 Base-SX | TX430-01-IM | UHG | Melissa Chapman | Wellmed | 5340 Walzem Road | San Antonio, TX |  | VS18159471 3094-0815 3094-BTVS | 2018-09-04 | 2018-11-27 | 2018-12-19 | 2018-12-18 |  |  | IUEC.802207 | ATT SW | 31KRGN653269SW | 2018-12-04 | 1ST FLR, IT ROOM, CIENA 3903X, PORT TAGGED | 1000BASESX |  | 3164136 | 50 | 10.1.91.5 | 10.1.91.6 | 65259 | 202610 | UHG GLOBAL 150 | 12/18: ORDER COMPLETE 12/11: Ray McVay (Pre CTA CNR SME) confirmed that he has removed the CNR status form this order, requested a new due date, and updated the logs. 12/10: DUE DATE MISSED DUE TO CUSTOMER SITE NOT READY...CUSTOMER NEEDS TO PROVIDE CONDUIT WITH PULL STRING. POSTING A C01B DUE TO SITE NOT READY. UPDATE: PER MELISSA: We did get a notice from our Verizon order (who is also using ATT for access) that the conduit and pull string was needed. This was completed on 11/27. Why was 12/10 missed? - UPDATE 12/11 1:51pm - Issued request in IOS to have order supp'd for new dispatch now that conduit is complete 12/4: Escalating for missed install 11/27-12/3: Fiber work completed 11/14. Pending install completion on 12/4. 9/18-11/12: Access install scheduled for 12/4. Construction & Engineering's fiber placement and splicing scheduled to complete on 11/16 8/23: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL356-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 18956 N Dale Mabry | Lutz, FL |  | 303683841 VS18179743 3094-1106 3094-BTYB 3094-BTYC | 2018-09-24 | 2018-12-27 | 2018-12-27 | 2018-12-14 |  |  | BBEC.529585 | Frontier | 65KEGS995102FTNC | 2018-11-15 | SL01#SHLF01#PRT03#PHYSUITE 102 INSIDE OF TELCO CL OSET ON PHOE GYINSTALLED 1 RAD NID ON PHONE BAIRD I |  |  | 3173822 | 4061 | 10.1.90.121 | 10.1.90.122 | 64666 | 202610 | UHG GLOBAL 150 | 12/14: ORDER COMPLETE 11/27-12/10: Access install and VLAN PON did complete - pending testing completion and OK to turn up. DD is 12/14 10/15-11/12: Frontier scheduled to install on 11/15. 10/9: Pending access install date from LEC Frontier 9/24: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL357-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 6502 Gunn Hwy | Tampa, FL |  | 303685221 VS18180438 3094-1176 3102-BBBW 3102-BBBX | 2018-09-24 | 2018-12-28 | 2018-12-28 | 2018-12-17 |  |  | BBEC.594146 | Frontier | 65KEGS996455FTNC | 2018-11-15 | 1ST FLR TELCO ROOM MOUNTED ON RAD203 AND T AGGED ON ELECTRICAL PORT 1 WITH CKT ID |  |  | 3174173 | 500 | 10.1.90.117 | 10.1.90.118 | 64661 | 202610 | UHG GLOBAL 150 | 12/17: ORDER COMPLETE 11/27-12/3: Access install and VLAN PON did complete - pending testing completion and OK to turn up. DD is 12/17 10/15-11/12: Frontier scheduled to install on 11/15. 10/9: Pending access install date from LEC Frontier 9/24: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL361-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 415 Apollo Beach Blvd | Apollo Beach, FL |  | 303685232 VS18180452 3094-1216 3102-BBBZ 3102-BBBY | 2018-09-25 | 2018-12-28 | 2018-12-28 | 2018-12-17 |  |  | BBEC.501603 | Frontier | 65KEGS996966FTNC | 2018-11-19 | SLNA#SHLFNA#PRTNA#PHYREAR SERVER ROOM, EAST WALL#JKRJ45 #EXTN#TAGY |  |  | 3174182 | 8 | 10.1.90.85 | 10.1.90.86 | 64627 | 202610 | UHG GLOBAL 150 | 12/17: ORDER COMPLETE 12/3-12/11: Demarc provided. Pending testing completion and OK to turn up. Due Date 12/17. 11/5-11/27: Access install is showing R80 completion, although we do not have demarc info back from the LEC yet. Pending testing completion and OK to turn up. 10/22-10/29: Access install scheduled for 11/19. 10/9-10/15: Pending access install date from LEC Frontier 9/25: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL362-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 500 Vonderburg Dr | Brandon, FL |  | 303685210 VS18180454 3102-0094 3102-BBCC 3102-BBCB | 2018-09-25 | 2018-12-28 | 2018-12-28 | 2018-12-17 |  |  | BBEC.573040 | Frontier | 65KEGS996833FTNC | 2018-11-30 | Pending - issued AERO CM 445893 for demarc info on 12/26 |  |  | 3174183 | 123 | 10.1.90.81 | 10.1.90.82 | 64627 | 202610 | UHG GLOBAL 150 | 12/17: ORDER COMPLETE - Pending demarc. 11/12-12/11: We have R80 completion notice on access install from LEC. Pending testing completion. DD 12/17 11/5: Access install scheduled for 11/30. 10/22-10/29: Order supp'd 10/17 - pending install date from LEC Frontier 10/15: Pending install date - LEC advised to PLEASE CORRECT SUITE FROM RM 303 TO 303E. Supp will delay receipt of install date. 10/9: Pending access install date from LEC Frontier 9/25: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL363-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 1901 Haverford Ave | Sun City, FL |  | 303691285 VS18180647 3102-0137 3102-BBCF 3102-BBCD | 2018-09-25 | 2018-12-28 | 2018-12-28 | 2018-12-17 |  |  | BBEC.549832 | Frontier | 65KEGS997810FTNC | 2018-11-19 | SIDE CLOSER, SERVER ROOM, SHELF MOUNTED, RJ45C, TAGGED NOT EXTENDED |  |  | 3174301 | 800 | 10.1.90.53 | 10.1.90.54 | 64614 | 202610 | UHG GLOBAL 150 | 12/17: ORDER COMPLETE 11/27-12/11: Access install is showing R80 completion - pending testing completion. DD is 12/17 10/22-11/12: Access install scheduled for 11/19. 10/9-10/15: Pending access install date from LEC Frontier 9/25: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL364-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 6350 Central Ave | St Petersburg, FL |  | 303691291 VS18180646 3102-0095 3094-BTYQ 3094-BTYR | 2018-09-27 | 2018-12-28 | 2018-12-28 | 2018-12-12 |  |  | BBEC.509022 | Frontier | 65KEGS996579FTNC | 2019-01-14 | SL01#SHLF01#PRT01#PHYTELCO CLOSET/ WALL MOUNTED RA D-NID. |  |  | 3174300 | 907 | 10.1.90.45 | 10.1.90.46 | 64603 | 202610 | UHG GLOBAL 150 | 12/12: ORDER COMPLETE 12/11: We received R80 notification that access install has completed ahead of the 1/14 scheduled install. Demarc provided. Pending testing completion and OK to turn up. 10/16-12/3: Frontier access install scheduled for 1/14/2019 - 1B OUTSIDE PLANT (OSP) - MAJOR BUILD 10/9-10/15: Pending access install date from LEC Frontier 9/27: Order rec'd - Pending USO's
New | 600M Port / 1G Access Ethernet AVPN | II519-07-IM | UHG | Melissa Chapman | UnitedHealth Group Information Services Private Limited | Pheonix Infocity Private Limited SEZ, Building No. H06, First, Second and Third Floor, Hitech City 2,Gachibowli (V) | Hyderabad India |  | ISR18102694541 VS18196051 3094-BVCB 3094-BVCC | 2018-08-22 | ASAP | 2019-01-29 |  |  |  | BEYF.100148..ATI | Bharti | 12635883 |  | MUX: HYD_HCH_912_T1401_F ETH-1-1-5 | 1000 Base-SX | Multimode Electrical Interface: 1000 - Base SX Physical Connector: LC AT&T Network Edge Router IP Address: 10.1.91.34 Customer Premise Equipment IP Address: 10.1.91.33 AT&T Network Edge Router IPV6 Address: 2001:DF0:54:488::EEA6:F73E Customer Premise Equipment IPV6 Address: 2001:DF0:54:488::11A6:F73E WAN IPv6 / pre-fix length: 64 VPN name: UHG GLOBAL 150 AT&T ASN: 21326 Customer ASN: 65035 COS profile: 6039 - 60% RT, 60/5/10/20/5 Data Encapsulation dot1q VLAN ID # 2 Duplex full Speed 1000 Auto-negotiation Off Flow-control Off | 3185753 | 2 | 10.1.91.33 | 10.1.91.34 | 65035 COS 6039 | 202610 | UHG GLOBAL 150 | 1/7: NCON has coordinated turn up with Sahil Tuteja (Optum.) TTU scheduled for Jan-13 at 9:30 am IST 1/2: Circuit delivered. TID, TP3 and Demarc touch points sent. Requested TID from NCON 12/10-12/26: No change in dates - PTT targeting 1/18/19 - Bandwidth augmentation is in progress. 12/3: PTT firm date targeting 1/18/2019 11/5-11/27: SR released to PTT Bharti on 10/26. Pending survey and firm date. 10/2-10/29: Pending UHG Signatures - order just placed 9/11: Contracts sent to UHG last week 8/22: Order rec'd
| 1G Port/ 1G Access 1000 Base-LX | PA007-08-IM | UHG | Melissa Chapman | Executive Health Resources | 15 Campus Blvd | Newtown, PA |  | VS18098552 3094-3454 3094-BTPF |  |  | 2018-08-28 | 2019-01-03 |  |  | IZEC.591480 | LNS | PAKRGN100426TPM | 2018-11-02 | 1ST FLOOR DATA/TELCO ROOM, WALL 01WWAL.021 PORT 2 TAGGED | 1000 BASE LX |  | 3119566 | 50 | 10.1.92.69 | 10.1.92.70 | 64914 COS 6039 | 202610 | UHG GLOBAL 150 | 1/3: ORDER COMPLETE 12/11-12/26: ESCALATION TO ENOC TECH TEAM REGARDING COMPLETION. 12/4: Order reassigned to Melondy Spain (Pre-CTA CNR Agent) - sent follow up with cc to Lottie Lee (2nd Lvl.) Requested status of access install which was missed over a month ago with no status. Construction shows fiber work completed 10/29 so should be no infrastructure issues. 11/12-12/3: Request to Raymond McVay (PRE-CTA CNR AGENT) for status of missed install date. Pending status. 11/5: Access install missed - BERT/IOS ticket to be opened to escalate. 10/2-10/29: Access install scheduled for 11/2. 9/24: LEC is pending completion of access this week. Awaiting confirmation of install completion. - UPDATE LEC EAD 11/2 9/17: Order is back on track - LNS has fiber to the site and advised not to cancel order as they CAN provide service. C&E has been informed. Pending a new date for install. 9/11: Advised team that "per C&E we were not given permission to proceed due to costs associated with the build." Checking for alternate LEC's that service this site. NOTE: ALT LEC IS VZ 9/4-9/10: Per Construction & Engineering, they were able to complete the site visit and they are currently putting together the scope of work and drawings. Order is not ready for FOC and next follow up is 9/11. 8/27: AERO Ticket 326175 opened for missed FOC by LEC. Pending response from Access Vendor Mgmt. 8/20: Pending install date from the LEC - Site Visit Delayed but Scheduled 8/14: IOS/BERT ticket issued for missed FOC (08/14/18 08:16 am) - pending install date from LEC. 7/30 - 8/06: Construction advised they were able to complete the site visit for this order. They are currently putting together the SOW/Drawings. Pending response. 7/10-7/23: Address issue required supp - SUPPED WITH NEW ADDRESS INFORMATION CITY TO NEWTOWN SQUARE SHOWS AS 15 CAMPUS BLVD. FOC due back by 7/27. 6/25-7/3: Pending install date. (FOC due 7/10) 6/4-6/18: FOC due back to AT&T by 7/10. Pending install date. 6/1: Order requested by UHG on 5/29.
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL365-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 2191 9th Ave N | St Petersburg, FL |  | 303691304 VS18180639 3102-0134 3094-BTYW 3094-BTYV | 2018-09-27 | 2018-12-28 | 2018-12-28 | 2019-01-02 |  |  | BBEC.514106 | Frontier | 65KEGS004756FTNC | 2018-12-21 | SUITE 235 ...TELCO CLOSET ... WALL MOUNTED RAD203 NID ... PORT 3 | 100 Base-TX |  | 3174291 | 340 | 10.1.90.41 | 10.1.90.42 | 64601 | 202610 | UHG GLOBAL 150 | 1/3: ORDER COMPLETE 12/26: Due Date 1/2/2019 11/27-12/11: Access install is complete - pending testing completion. Due Date 1/2/2019 10/29-11/12: Access install scheduled for 12/21. 10/9-10/22: Pending access install date from LEC Frontier 9/27: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX436-01-IM | UHG | Melissa Chapman | Wellmed | 2200 Park Bend Dr Bldg 2 Suite 300 | Austin, TX |  | VS18184968 3094-1308 3094-BTYX | 2018-10-02 | ASAP | 2018-12-17 | 2019-01-11 |  |  | BBEC.557447 | ATT SW | 32KRGN653142SW | 2018-10-18 | HANDOFF OUTSIDE MOUNT PORT 1 |  |  | 3177084 | 50 | 10.45.10.217 | 10.45.10.218 | 64579 | 202610 | UHG GLOBAL 150 | 1/14: ORDER COMPLETE 1/7: Still not showing updated dates. Reached out to Christian requesting escalation for jep removal (still showing CNR) and new date from the LEC. UPDATE: CHRISTIAN CONFIRMED HE HAS CLEARED THE CNR AND SUPP'D THE PON 12/11-12/26: Pending an update from Construction on completion of the fiber work. Still showing customer prem is not ready and infrastructure is not completed yet. Pending update from CNR agent Christian Childs. Bill G pushed again to Christian Childs on 12/20. 11/27-12/3: Fiber work delayed due to 'customer not reachable.' The install date for fiber was pushed to 12/5. 11/5-11/12: Pending completion of fiber work - scheduled for 11/14. 10/25: SITE VISIT WAS COMPLETE AND SVCL UPLOADED, C&E FIBER PLACING AND SPLICING ECD 11/14/18. ORDER NEEDS TO BE INFRASTRUCTURE COMPLETE SO ORDER CAN RELEASE TO ENOC/TESTING CENTER TO SCHEDULE TEST AND TURN UP 10/22: Issued BERT/IOS escalation for missed install - DESIGN ISSUE per SOTS notes. 10/15: Access install scheduled for 10/18. 10/2: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX444-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 11901 W PARMER LANE, SUITE 300 | Cedar Park, TX |  | VS18206643 3094-0011 3094-BVCZ | 2018-10-30 | ASAP | 2019-01-30 |  |  |  | BBEC.521348 | ATT SW | 32KRGN653215SW | 2019-05-29 |  |  |  | 3193539 |  | 10.45.10.221 | 10.45.10.222 | 64583 | 202610 | UHG GLOBAL 150 | 12/21: Ticket # 36706 issued to cancel order per Melissa's request 12/11: Construction & Engineering provided a 5/20/19 fiber completion date. Access install scheduled for 5/29 due to fiber build. Probably cancelling this one. 11/13-12/3: Pending an install date from ATT SW. Overall DD 1/30/2019 11/12: Pending USO's - late due to duplicate IP issue per OM. 10/30: Order rec'd - pending USO's - LATE order needs to be pushed
| HOT ORDER 10MB Port/ 50M Access EaAVPN 1000 Base-SX | TX442-01-IM | UHG | Melissa Chapman |  | 1251 A E Red Bird Lane | Dallas, TX |  | C11384813 VS18158504 3094-0685 3094-BTVL | 2018-08-16 | ASAP | 2018-11-21 | 2019-01-11 |  |  | BBEC.560125 | ATT SW | 14KRGN884046SW | 2019-01-09 | 1ST FLOOR SERVER RM MM OPTICAL HANDOFF AGGED W/CIRCUIT ID | 1000 Base-SX |  | 3162395 | 50 | 10.1.91.117 | 10.1.91.118 | 65094 | 202610 | UHG GLOBAL 150 | 1/11: ORDER COMPLETE 12/26-1/7: Received a 1/9 access install date from the LEC. 12/10: Reached out to CNR agent Steven Whatley for update on PON. Order still showing CNR so need Provisioning to work that issue and get with LEC about redispatching for install. Has BIC been notified by customer about completion? 12/3: Reached out to Melissa to confirm site conduit is complete.UPDATE: PER MELISSA, According to the PM the work is done at the site but I suspect the BIC eingeer may not have been notified. 11/27: AERO TKT: 409486 - Escalation sent to ENOC for tech assignment and dispatch. Pending access completion. 11/16: Access install delay - Per the LEC Tech, EMUX HAS NOT BEEN INSTALLED YET. Pending EMUX completion. Working on ETA. 11/13: Escalating for completion of fiber work - 10/23 site completed 10/8-11/05: Construction & Engineering scheduled to complete fiber work on 11/9 and access install has been scheduled for 11/16. 9/25-10/2: Construction & Engineering is showing fiber placement and splicing is due to complete on 11/09. 9/10-9/17: Pending an install date from the LEC ATT SW. FOC due back by 9/28 8/16: Order rec'd - Pending USO's
New | HOT ORDER 400MB Port/ 1G Access EaAVPN 1000 Base-SX | VA731-01-IM | UHG | Melissa Chapman |  | 21721 Filligree CT | Ashburn, VA |  | VS18153851 3094-0789 3094-BTVQ VS18195769 3094-1673 3094-BVBX 3094-BVBY | 2018-08-23 | Drop Dead 12/7/2018 | 2018-01-23 | 2018-11-28 |  |  | IZEC.549429 IZEC.543095 | ADE LNS | DCKFGS100157TPM DCKFGS100178TPM | 2018-11-13 | 020001.02/FF2/02/07/25-26 PER ENOC TECHNICIAN DMARC: IBX#DC11;CGE#21131;CBNT#020001.02;PNL#7;CP:0102: 1128753;PRTS#25-26;SC |  |  | 3185462 | 2 | 10.1.91.49 | 10.1.91.50 | 64767 | 202610 | UHG GLOBAL 150 | 1/14: Reached out to Ranjit for status update. - UPDATE - EQUINIX WIRING ISSUE WAS THE PROBLEM - RANJIT CONFIRMED THEY ARE NOW UP AND RUNNING. 1/7: Pending cutover reschedule - customer Ranjit to meet with AT&T SME Richard Wilson to troubleshoot before going forward. 12/26: Cutover scheduled for Friday 12/28: HSSD SCHEDULING TEAM NOTE: ASSIGNED CUT TECH: KEN VICK 404-926-6953 USO'S:30941673 / 3094BVBX SCHEDULED FOR: 12/28/18 @ 11:00AM EST ELECTRONIC COPY SENT TO ASSIGNED TECH & TECH'S COACH: CEDRICK SCOTT 12/10: Sent request for TTU document - order complete. 12/7: Created AERO CM ticket 428733 for location of LEC equipment. Reached out to ENOC David Rios who tested the circuit and he advised he only had the demarc provided. 020001.02/FF2/02/07/ pairs 25 & 26 11/28: ORDER COMPLETE 11/27: Pending completion - 11/28 11/16: Engineering and Design completed yesterday - ORDER HAS BEEN ADDED ON L4/L5 TECH LIST to complete CTA/DD. 11/13: We have R80 completion on the access - demarc provided - pending testing completion and OK to turn up. LEV5 11/7: Client just gave us Drop dead date of 12/7 11/5: PON released on 10/31 and FOC due back by 11/26. Pushing LEC for status. 10/25: Rec'd new USO's - pending install date REISSUED - Pending USO's - Clyde 10/2-10/8: Access install scheduled for 10/24. 9/11-9/25: LNS Access - pending install date. FOC due back by 10/3. 8/23: Order rec'd - Pending USO's
New | HOT ORDER 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX449-01-IM | UHG | Melissa Chapman |  | 2858 N Belt Line Rd #600 | Sunnyvale, TX |  | VS18195873 3094-1629 3094-BVBZ | 2018-10-22 | 2019-01-14 | 2019-01-14 | 2019-01-09 |  |  | BBEC.534389 | ATT SW | 14KRGN884419SW | 2018-12-19 | OUTSIDE REAR WALL CIENA 3931. OPTICAL HANDOFF ON PORT 1, LABELED |  |  | 3185555 | 50 | 10.1.89.73 | 10.1.89.74 | 64556 | 202610 | UHG GLOBAL 150 | 1/9: ORDER COMPLETE 1/8: Added to HOT list per Melissa. UHG needs this completed by 2/1. 1/7: Pending updated access install date - Construction advising NTE install date is 1/10. 12/26: Access install missed - Per the LEC Tech, THE CIENA THAT THIS ORDER IS ASSIGNED TO IS NOT TURNED UP. Pending updated install date. 11/12-12/11: Access install scheduled for 12/19. 10/30-11/5: FOC due back by 11/16. Pending install date. 10/22: Order rec'd
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL358-01-IM FL358-04-CM | UHG | Melissa Chapman | UHG- Wellmed | 11924 Sheldon Rd | Tampa, FL |  | 303685272 VS18180463 3102-0080 3094-BTYJ 3094-BTYK VS18192653 C11390934 3094-1531 3094-BVBG 3094-BVBH | 2018-09-24 | 2018-12-28 | 2019-01-17 | 2019-01-11 |  |  | BBEC.542236 | GTFL - Frontier | 65KEGS009686FTNC | 2018-12-24 | 1ST FLR TELCO RM/TAGY/RJ45 JK | 100 Base-TX |  | 3174189 | 399 | 10.1.90.113 | 10.1.90.114 | 64652 | 202610 | UHG GLOBAL 150 | 1/15: CHANGE ORDER NEEDED - change IP addressing to 10.1.89.75/30 10.1.89.76/30 on BBEC.542236 1/11: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 12/24-1/7: Access install completed (R80.) Pending testing completion and OK to turn up. Due Date 1/7/2019 -- UPDATE - TESTING ISSUES: RECEIVED CALL FROM BRIAN/FRONTIER-- THEY ARE NOT ABLE TO REACH NID AND WILL HAVE TO DISPATCH OUT.. CALLED CUSTOMER MIKE NELSON AND HE SAID THEY WOULD HAVE NO PROBLEM GETTING INTO THE TELCO RM. PENDING. 11/27-12/3: Access is scheduled to be installed on 12/24. 11/5-11/12: Pending install date from LEC GTFL - FOC due back by 12/18. Aero Design 394402 / 401777 for R15 10/22: Order had to be reissued per Chris Cowan - There was an internal issue where token from FL358 was placed on FL359 10/9-10/16: Pending access install date from LEC Brighthouse Networks 9/24: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL359-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 10933 Countryway Blvd | Tampa, FL |  | VS18192691 C11390934 3094-1561 3094-BVBK 3094-BVBL | 2018-09-24 | 2018-12-28 | 2019-01-17 | 2019-01-17 |  |  | BBEC.544556 | GTFL - Frontier | 65KEGS009971FTNC | 2018-11-20 | SLOT 1, SHELF 1, PORT 01, ELECTRICAL ROOM, R AD, NOT EXTENDED, TAGGED. CM DISENGAGED. | 100 Base-TX |  | 3174181 | 4061 | 10.1.90.105 | 10.1.90.106 | 64648 | 202610 | UHG GLOBAL 150 | 1/20: ORDER COMPLETE 12/26-1/15: Access install complete - pending testing completion - overall due date is 1/17. 12/10: Access and VLAN PON R80 complete - pending testing completion and OK to turn up. 11/27-12/3: Access install completed - Pending demarc - overall DD is 1/17/2019 11/5-11/12: Access install scheduled for 11/20. 10/22: Order had to be reissued per Chris Cowan - There was an internal issue where token from FL358 was placed on FL359 10/16: USO cancelled 10/9: Pending access install date from LEC Frontier 9/24: Order rec'd - Pending USO's
New | HOT ORDER 10MB Port/ 50M Access EaAVPN 1000 Base-SX | TX415-01-IM | UHG | Melissa Chapman | Wellmed | 448 Castroville Road | San Antonio, TX |  | VS18172307 3094-0987 3094-BTXK | 2018-08-24 |  | 2018-12-06 | 2019-01-18 |  |  | BBEC571017 | ATT SW | 31KRGN653300SW | 2019-01-16 | 1ST FLR MAIN I.T. RM WL MT CIENA 3903 2 TAGGED |  |  | 3168838 | 50 | 10.1.91.17 | 10.1.91.18 | 64754 | 202610 | UHG GLOBAL 150 | 1/18: ORDER COMPLETE 1/7-1/14: Access install scheduled for 1/16 12/27: Added order to HOT list per Melissa. 12/26: Site work was completed and pictures sent confirming at the end of November. Escalation sent to team to provide status of the fiber work completion and update on the access install date. 12/3-12/10: Access install scheduled for 12/13. 11/27: Escalated to Jeremy Brown (CNR agent) for status of install. 11/14: Rec'd email from Melissa with pictures confirming site readiness - providing to CNR agent assigned. 11/12: Access install missed - CNR – customer not ready - sent details to Melissa. 10/2-11/5: Access install scheduled for 11/9. 9/25: ATT SW Access - pending install date. FOC due back by 10/15. 8/24: Order rec'd - Pending USO's
New | 60MB Port/ 100M Access EaAVPN 100Base-TX | UT007-04-IM | UHG | Melissa Chapman | UHG- Helios | 680 W. Price River Drive | Price, UT |  |  | 2018-09-26 | [14 empty] | 10.1.90.81 | 10.1.90.82 | 64627 | 202610 | UHG GLOBAL 150 | 10/30-1/28: Pending special bid/pricing quote FOR 100M ACCESS - REMOVE THIS ONE 10/1: ORDER ON HOLD - Cancelled for now - keep for now on sheet 9/25: Order rec'd - Pending USO's
| 400MB Port/ 1GB Access 1000 Base-SX | UNJ08-11-IM | UHG | Melissa Chapman |  | 131 Morristown Road | Basking Ridge, NJ |  | VS17142784 3094-0533 3094-BSRF Site ID: 515817 | 2017-08-16 |  | 2017-11-10 | 2019-01-31 |  |  | IZEC.578025 | ASE LNS | NJKRGN100461TPM | 2019-01-31 | 3930 2ND FLR MDF RM WALL MNTD VE PANEL H.3 PORTS 1 & 2. |  |  | 2998724 | 50 | 10.1.95.245 | 10.1.95.246 | 64541 COS 6039 | 202609 | UHGECC GLOBAL | 2/4: ORDER COMPLETE - READY FOR TURN UP 1/29: Checked CLO NJS001319001 (GRETA) and it's showing LEC install is due to complete on 2/28. 1/28: Requested status from Becky Duncan (NSS PM.) 1/22: Construction and Engineering ECD 1/25 1/21: LEC equipment delivered Friday 1/18/2019 at 10:05 am. Pending update that work is complete. 1/14: LEC required equipment (OPTICAL TRANSCEIVER) for install. Fedex delivering equipment by COB tomorrow 1/15. Next follow up 1/16. 1/7: Construction Fiber placement is scheduled to complete today 1/07 - UPDATE: CONSTRUCTION HAS COMPLETED THE FIBER WORK. PUSHING FOR ACCESS INSTALL DATE. 12/26: Construction was scheduled to complete fiber work on 12/21 but that has been missed. This has been escalated and next follow up is set for today 12/26. 12/10: Construction fiber work pushed out to 12/21 due to delays in accessing manholes. Reached out to Rebecca Duncan (C&E) for further updates. 12/3: Engineering completed 11/28. Construction fiber work pushed out to 12/05. Per C&E – they still have splicing to do for this order and are having issues getting access to the manholes. 11/27: Construction's fiber work delayed until 11/30. Pending delay reason. 10/29-11/12: Access install scheduled for 11/26. Fiber work scheduled for 11/14 10/23: UPDATE: The customer did approve the 2nd floor location. C&E indicated customer site is ready as of 10/23 and fiber work scheduled for 11/14. Pending confirmation of access install date. 10/22: EMAIL TO KRISTEN BOREHAM for status on 2nd floor delivery. 10/15: Per the LEC, There isn't enough space on the 1st floor, so they have proposed the 2nd floor space. AT&T will proceed with the original plan for cable and equipment placement up to the 2nd floor MDF Room. Fiber work scheduled for Wednesday 10/24/18 10/8: Pending status of survey that was scheduled for 10/03. C&E will receive and upload survey docs by COB 10/08. 10/2: C&E working to reschedule survey for Wednesday 10/03/18 at 9:00am. Mutiple issues at site (floor#, order info, etc) per C&E. 9/10-9/24: PON was supp'd on 9/5 to LEC requesting new install date. FOC due back by 9/27 or earlier. 9/4: Requested update from C&E PM on dates now that ROE is executed. 8/27: ROE is fully complete and executed. Advised C&E PM to move forward w/the work and update estimated completion dates accordingly. 7/17-8/21: Received ROE w/AT&T revisions from CM. Outlook for ROE Completion: 8/31/2018 7/3: Construction & Engineering advised Outlook for ROE Completion: 07/31/2018 - Revised ROE doc by 7/9. - ROE returned on Friday 6/25: OUTLOOK FOR ROE COMPLETION: 06/30/2018. 6/1-6/18: Pending review from Carol Reed at CBRE. AT&T sent over documents 4/23. Left VM msg with Carol Reed. (Carol back from vacation) 5/7: Left msg with CBRE contact, will follow up with CBRE for update. 4/30: Acquisition team has completed review of revisions and submitted to BLDG owner for review. 4/24: Expected completed by 5/1. then will send back to CBRE 4/23-4/9: Documents are going through risk management review. Once risk management portion is completed the order will move to AT&T legal for final review. 4/3: Documents pending OSP approval & ATT legal review. 3/26: Estimated ECD for ROE is 3/30. 3/19-3/5: ROE is still being processed with various AT&T departments. 2/26: Pending status of from acquisition team. 2/19-2/5: AT&T acquisition team is moving forward with the forms as is. It will take 3-4 weeks to gain all the necessary approvals for the forms. Then the forms will be sent back to CBRE for approval. 1/29: Pending completion of form/open items between AT&T and CBRE building owner. 1/15: Pending form/open items being completed by CBRE to move forward with order. 1/8: Talked with contact @ CBRE and they are looking into item and form to return to AT&T. 1/2: ATT acquisition team is trying to reach LCON@ CBRE to properly complete the ROE. 12/26: UHG confirmed open items completed, sent to OM team. Pending ATT acquisition team to now review ROE. 12/18: Pending ROE completion from ATT acquisition team so C&E team can move forward. 12/4-10/16: Infrastructure build required, ECD 12/05. 10/9: Received approval for SOW and order has been sent over to site acquisition team for ROE agreement. 10/2: Pending update from LCON. Lcon must contact engineer for FOC. 9/27: LCON is out of office until 10/2. Engineer is pending call back. 9/25-9/18: Estimated FOC date scheduled for 9/27. 9/11: PON was supped to change LCON info. New FOC date scheduled for 9/27. 9/5-8/28: Target FOC date scheduled for 9/11. 8/21: Received USO 8/16. Target FOC date scheduled for 9/11. 8/14: Pending order number/ USO. 8/7: Order assigned on 8/4, pending order number/ USO.
New | 10MB Port/ 50M Access EaAVPN 1000 Base-SX | AZ029-04-IM | UHG | Melissa Chapman |  | 985 W Chandler Heights Road | Chandler, AZ |  | HALO Ord 303655102 VS18175424 3094-1067 3102-BBBL | 2018-09-19 | 2018-12-11 | 2018-12-11 | 2019-01-24 |  |  | BBEC.519806 | Qwest | 19KXGS352233MS | 2019-01-14 | GROUND FLOOR, MAIN I.T.(SOUTH SIDE OF BLDG.)(ACCES S BY PROP. | 1000 BaseSX |  | 3170749 | 52 | 10.45.10.253 | 10.45.10.254 | 64610 | 202610 | UHG GLOBAL 150 | 1/28: ORDER COMPLETE 1/14-1/21: Access install is complete - pending testing completion and OK to turn up. DD 1/24 10/29-1/7: Access install scheduled for 1/14/2019 - 1B OUTSIDE PLANT (OSP) - MAJOR BUILD PER LEC, ON THIS PROJECT THERE IS ONLY ONE END USER REQUIREMENT LEC WILL BE PLACING THEIR SWITCH IN THE MPOP. END USER WILL NEED A CLEAR PATH AND CAT5 FROM MPOP TO THEIR SUITE FOR THEIR CONNECTIVITY TO IT. 10/22: CNR Customer Not Ready - CODE: 1S=BUILDING NOT READY - email to Melissa 10/2-10/15: Pending access install date from LEC Qwest 9/19: Order rec'd - Pending USO's
New | 10MB Port/ 10M Access EaAVPN 1000Base-SX | TX454-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 1202 FM 3036 | Rockport, TX |  | VS18206661 3094-1158 3094-BVDB | 2018-10-26 | ASAP | 2019-01-30 | 2019-01-30 |  |  | MLEC.881667 | ATT SW | 34KRGN613933SW | 2019-02-01 | 1ST FLR SERVER RM, WALL MT BISCUIT |  |  | 3193541 | 50 | 10.1.89.65 | 10.1.89.66 | 64554 | 202610 | UHG GLOBAL 150 | 1/30: ORDER COMPLETE 1/22-1/28: Access install date adjusted to 1/29. 1/7-1/15: Construction completed their fiber work on 1/4. Access install on track for 2/1 completion. 12/3-12/26: Construction fiber work scheduled to complete on 1/24. Access install scheduled for 2/1. 11/27: Per Construction - contractor unable to access site. LCON is un-responsive. Site visit delayed. 11/13-11/27: Pending an install date from ATT SW. Overall DD 1/30/2019 10/26: Order rec'd
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX446-01-IM | UHG | Melissa Chapman | Wellmed | 1921 Lohman’s Crossing Road,Suite 150 | Lakeway, TX |  | VS19002188 3094-2206 3102-BBCS | 2019-01-02 | 2019-03-22 | 2019-03-22 | 2019-01-30 |  |  | BBEC.556159 | ATT SW | 32KRGN653324SW | 2019-01-29 | PARKING GARAGE TELCO ROOM BISCUIT JK AND LABELED |  |  | 3214937 | 50 | 10.1.94.197 | 10.1.94.198 | 64689 | 202610 | UHG GLOBAL 150 | 1/30: ORDER COMPLETE 1/22-1/28: Access due to install on 1/29. 1/15: Pending install date from ATT SW
New | HOT ORDER 150MB Port/ 300M Access EaAVPN 1000Base-SX | FL351-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 15320 Amberly Dr Ste B | Tampa, FL |  | 303887234 VS18207319 3102-0238 3094-BVCY 3094-BVCX | 2018-11-02 | ASAP | 2018-02-11 | 2019-01-28 |  |  | BDEC.993451 | Frontier | 65KFGS050078FTNC | 2019-02-04 | SL01#SHLF01#P RT05#PHYWALL MOUNT IT CLOSET BACK BOARD #JKRJ45X#EXTN#TAGY |  |  |  | 847 | 10.1.90.165 | 10.1.90.166 | 64688 | 202610 | UHG GLOBAL 150 | 1/29: ORDER COMPLETE 1/28: Received R80 notification that access install has been completed by the LEC. Pending further status from provisioning, completion of remaining critical dates, and OK to turn up. Tech did contact Frontier today and is working on testing completion. 1/21: Access install scheduled for 2/4 1/14: Pending install date from the LEC on new PON HSSC3554707. 1/8: Added to HOT list per Melissa. UHG needs this installed by 1/28. 1/4: Pending update on new PON - sent request (DDF Ticket) to request new PON be issued 12/26: LEC FRONTIER CANCELLED THE PON DUE TO CNR CUSTOMER NOT READY. Please advise when site is ready to proceed with the install and AT&T will supp the request and request new date from Frontier. 12/11: FOC due back by 12/20 however order is showing a CNR Customer Not Ready - Issues on site? 12/3: LEC indicating CNR issue - please verify LCON details for this request. Pending order supp and install date. MIKE NELSON IS CORRECT 11/13-11/27: Rec'd USO's - Pending install date from Frontier 11/2: Order rec'd
| 1GB Port/ 1GB Access EaAVPN 1000 Base-SX | C1641-01-IM | UHG | Melissa Chapman | UHG- Teletech | 21635 Red Rum Dr | Ashburn, VA |  | C11384382 VS18147612 3094-0419 3094-BTTM 3094-BTTN | 2018-08-03 |  | 2018-11-20 | 2019-02-05 |  |  | IZEC.579184 | Zayo | ETYX178111ZYO | 2018-10-01 | RM BC-01CAGE A 39B14 MDF-2 CAB A34-B10(F6) MOUNTIONG POS 142 ACEDIAN FMP 1 PORT 1 |  |  |  | 2 | 10.191.223.137 | 10.191.223.138 | 65477 | 202609 | UHGECC GLOBAL | 2/5: ORDER COMPLETE 2/4: Access install complete - pending testing completion and OK to turn up. NEED COMPLETED ASAP FOR IP CHANGE 1/21: Pending status of new order/internal change request w/ Zayo --- INTERFACE SINGLE MODE FIBER - MAKE SURE SYSTEMS ARE IN SYNC - ATT SYSTEMS NEED TO SHOW SAME 1/14: Zayo is asking that we change handoff to SMF - Melissa sent request to supp - PER CHRIS - NEED TO ISSUE NEW ORDER 12/10-12/26: PENDING CUSTOMER TO PROVIDE CFA FOR ZCOLO CROSS CONNECT PENDING CUSTOMER TO COMPLETE AND RETURN SPACE AND POWER DOCUMENT 12/3: Pending install date and confirmation forms were provided back to Zayo. Check with Provisioning on the CFA forms - held for UHG side? 11/27: Original emails for CFA and power/space provided to Melissa on 11/21. Pending new install date and confirmation forms were provided back to Zayo 10/8-11/12: Zayo advised that circuit is still in provisioning and not ready for testing. Install date of 11/15 remains unchanged. No additional details provided yet. 10/2: ZAYO sent new install date of 11/15. Escalating for details. 9/17-9/24: Zayo access install scheduled for 10/1. 9/4-9/10: PON released on 8/28. FOC due back no later than 10/9. 8/28: Received USO's this morning - overall due date 11/20. Pending release of the PON to Zayo. 8/3: Order rec'd - Pending USO's
New | 20MB Port/ 50MB Access EaAVPN 1000 Base-SX | NY004-06-IM | UHG | Melissa Chapman |  | 168 Centre Street | New York, NY |  | C11384997 VS18153186 3094-0544 3094-BTTW 3094-BTTX | 2018-08-21 |  | 2018-11-27 | 2019-02-07 |  |  | BBEC.551985 | Time Warner | 21L1XX022537TWCC | 2019-03-01 | MPOE ROOM WALL MOUNTED LBLE WITH CKT ID PORT3 |  |  |  | 106 | 10.1.91.41 | 10.1.91.42 | 64761 | 202610 | UHG GLOBAL 150 | 2/7: ORDER COMPLETE 1/7-2/4: Access install scheduled for 3/1. 12/10-12/26: FOC due back by 1/7/2019 12/4: Received confirmation from CNR agent that he supp'd order to remove the jeops and request for another tech dispatch. He also advised he tried reaching out to Jenelle Fleary (LCON) via phone and no answer. Please reconfirm LCON info and advise Jenelle that the order could be delayed further if the LEC is unable to reach her. 11/30: Pre CTA Agent CC226U supp'd order to clear CNR and request new install date. Pending FOC. 11/27: PER LEC: NEED NEW LCON THE LCON LISTED JENELLE FLEARY IS NOT RESPONDING 10/29-11/12: Confirmed order was sup'd a week ago - Pending access install date from Time Warner. FOC due back by 11/27. 10/22: Escalation to Joe Scrudato for status of order - PON was supp'd on 9/26 with new LCON info but not seeing an update from LEC. Pending an install date. - UPDATE ORDER WAS SUPP'D - PENDING INSTALL DATE 10/15: Escalation sent for Time Warner update on fiber work and/or access install. Pending status. 10/2-10/8: Email to Stephanie Batie (Ordering) for update on supp to change LCON. 9/25: Issued AERO Design ticket 354966 to change LCON to JENELLE FLEARY, (929) 226-4755, JENELLE_FLEARY@UHG.COM 9/25: Per the LEC Time Warner - NEED LCON TO RESPOND TO CONSTRUCTION. They have requested a new LCON to contact. Current LCON is ROBERT K CHO, 212 271-0784, RCHO@OPTUM.COM 9/17: PER MY CONSTRUCTION TEAM THE POC'S LISTED ON THE ORDER ARE NOT RESPONDING. THIS ORDER IS ON HOLD UNTIL THE POC'S RESPOND OR AT&T PROVIDES NEW ONES 9/10: Pending access install date from LEC Time Warner - FOC due back by 10/9 9/4: USO's rec'd - pending release of the PON to the LEC Time Warner (9/5.) 8/21: Order rec'd - Pending USO's
New | 300M Port / 500M Access Ethernet AVPN 1000Base-SX | IR508-07-IM | UHG | Melissa Chapman |  | Block C, Spencer Block, Dublin 1 | Dublin, Ireland |  | ISR18100883518 VS18184463 3094-BTZC 3094-BTZD 3094-BTZF | 2018-08-15 | ASAP | 2019-01-10 | 2019-02-05 |  |  | BDYF.100580 | Sarea/ Colt | SAREA: SR/VLXP/048815/ATI ACCESS PROVIDER ID: DUB/DUB/LE-245917 | 2019-03-29 | Floor: ground Room: server Demarcation point: Customer Rack A2,_DUB_CA_01580 @'U' position 37_P4 Customer connector / handoff: SC |  | 1000base SX- LC |  | 2 | 10.1.91.133 | 10.1.91.134 | 64671 COS 6039 | 202610 | UHG GLOBAL 150 | 2/5: TID sent - order complete ready for turn up 2/4: Pending circuit testing completion and handover from PTT. UPDATE 2/5: NCON Veronika working now to send TID document and demarc info. 1/21-1/28: 3/29 install is unchanged. 1/14: NCON Veronika Matuscinova has contacted the provisioning team that is in communication with the local telco about the latest status. Pending update. At this point the 3/29 install is unchanged. 1/7: Colt still showing 3/29 install date. Escalated order to NCON Veronika as well has her 2nd level to find out details of the CNR that Colt posted on the order. As far as AVPN MOW is telling me, the order has been coded CNR-B as the issue with LCON has been ongoing since November 7th -- 1/8 UPDATE: CNR has been resolved for now, the customer confirmed the local contact information to the telco. The provisioning team has reached out to the telco and is chasing the latest status update. 12/26: Colt is providing a 3/29/19 firm date and we still are seeing a CNR condition. We have asked Colt for details since we already provided an updated LCON a few weeks back. 12/10: “According to COLT, Enet contacted all contacts provided to try arrange access for a site survey today, but have not had a response from any of the contacts. They advised they will need to reschedule a survey and contact again next week.” Melissa has followed up internally. 12/4: Request to NCON Veronika Matuscinova for interval details and whether this can be expedited. 11/27-12/3: PTT firm date still targeting 3/29/2019 11/12: Order is progressing. PTT was having contact issues - provided David Guinan - David.Guinan@structuretone.ie (m) 00.353.86.8364670 Derek Slattery - Derek.Slattery@structuretone.ie (m) +353 86 6012670 Fran Fahy - Fran.Fahy@structuretone.ie (m) +353 86 0280369. PTT firm date still targeting 3/29/2019. 11/5: PTT Firm Date 3/29/2019 10/15-10/29: Access order placed 10/9. Pending a date from the PTT. 10/9: Rec'd ISR18100883518 this morning. System due date 1/10/2019 10/2: Waiting on capacity check 8/15: Order rec'd
New | HOT ORDER 50MB Port/ 50M Access EaAVPN 1000 Base-SX | TX410-01-IM | UHG | Melissa Chapman |  | 830 Kohlers Crossing | Kyle, TX |  | 303730959 VS18187170 3102-0169 3094-BTZK 3094-BTZL | 2018-07-17 |  | 2019-01-09 | 2019-02-05 |  |  | BBEC.530264 | Time Warner | 51L1XX019433TWCC | 2019-02-27 |  |  |  |  | 505 | 10.1.91.245 | 10.1.91.246 | 64794 | 202610 | UHG GLOBAL 150 | 2/5: ORDER COMPLETE - READY FOR TURN UP 2/4: Time Warner has completed access install ahead of schedule. Pending testing completion and demarc. 1/28: LEC Time Warner has provided a firm 2/27 access install date - confirmed. 1/14-1/21: LEC still indicating due date target is 2/27/19. Working to firm up and see if possible improvement. 1/7: Sent direct email to LEC contacts (PM Miranda Coates) to find out what is left on their side to install access. -- UPDATE: PER MIRANDA COATES/SPECTRUM: "We are still pending the VLAN before FOC can be sent. Right now, I can estimate the due date at 2/27/19" 12/26: IOS ticket issued (Escalation Support/AVPN) to ordering team for assistance in escalating to LEC Time Warner for status of install date. 12/10: ROE has been passed on already and we are just pending Construction to set firm ECD and Design to sign off on the design so that we can release FOC to AT&T. 12/3: Followed up with our team this morning on the ROE as I have not seen any updates. I know they mentioned that FOC would be sent out as soon as the ROE is forwarded but to this point, I have not seen a date. I’ll keep pressing them for info and hope to have news for you shortly. 11/27: Pending ROE - Please push end user to work with Property Mgmt to get that signed. Once signed, FOC will be provided. 11/16: FOC missed - escalation to be issued for missed FOC 10/15-11/13: Pending access install from LEC Time Warner. FOC due 11/15. 10/2: PENDING USO's 9/25: Order processed last night 7/17: Order rec'd - pending USO's - Special Construction (Time Warner Cable) - ATT working with special bid team - facilities available - per Chris - will require addendum
| HOT ORDER 7xT1 AVPN | 7xT1 order (TX410-05-IM) | UHG | Melissa Chapman |  | 830 Kohlers Crossing | Kyle, TX |  | 303597471 VS18164065 3094-4881 3094-4882 3094-4879 3094-4878 3094-4880 3094-4883 3094-4877 3102-BBBF | 2018-09-11 |  | 2018-10-30 |  |  |  | DHEC.385933.811 DHEC.385933.812 DHEC.385933.813 DHEC.385933.814 DHEC.385933.815 DHEC.385933.816 DHEC.385933.817 | Frontier | 13HCGS688006FTNC 13HCGS687985FTNC 13HCGS682856FTNC 13HCGS682990FTNC 13HCGS682813FTNC 13HCGS682970FTNC 13HCGS682844FTNC | 11/30/2018 11/30/2018 10/23/2018 10/23/2018 10/23/2018 10/24/2018 10/24/2018 | TBD TBD 1ST FLR TEL RM HOUSING#1 SLOT#2 of 8 COMPLETE COMPLETE COMPLETE COMPLETE | [9 empty] | 1/7: Customer is up and running on (5) T-1's. Monitoring Ethernet for completion. 12/26: .813 thru .817 circuits are up and running - pending direction on remaining (2) T-1's that require special construction. 12/10: Customer is up and working on (4) T1's - working with provisioning to complete out the 5th. 12/3: Working to update last two T-1's. Multiple messages from LEC (construction, CNR, CO equipment requirements) so working to pin down issues and timeframe for completion of access. === PER JEROME( FRONTIER) THERE IS A SPECIAL CONSTRUCTION. THE ORDER IS IN PHASE 2 OF 4, PENDING QUOTE FROM SALES. 11/27: Last two T-1's scheduled to install on 11/30. 11/5-11/13: Escalated this back to provisioning to clear all issues regarding conduit and junction box with the LEC Frontier. Advised that we need a clear update from Frontier on whether they still consider this CNR and what the roadblocks are. At this point we do not show any issues at the customer site that are yet unresolved so access should be clear to install. UPDATE: CONTINUING TO ESCALATE FOR ACCESS INSTALLATION COMPLETION -REC'D COMPLETION ON 5 of 7. 10/29: LEC Frontier still indicating issues onsite - CONDUIT IS NOT DAMAGED. THE ISSUE IS THE JUNCTION BOX WHICH WILL INVOLVE A TWO PHASE PULL. Working to obtain new due date. Need update from site on junction box issues. 10/22: Issued LEVEL1 Escalation on AERO D ticket 377807 for update on supp. 10/18: Ticket has been issued to request order supp back to Frontier with this info. AERO D ticket 377807. 10/16: Rec'd update from UHG that Per Wellmed: The conduit was not damaged upon their review. There is a junction box that they need to inform carriers about. It will be a 2 phase pull: 1) Will be from street to junction box and 2) Will be from junction box to IT room. When Frontier was onsite they were not aware of the junction box which lead them to believe that the conduit was damaged. Requested ordering sup the order with this info and request that Frontier recheck with the LCON about the junction box issues. 10/15: PER ENGINEERING CUSTOMER CONDUIT BLOCKED. Advised UHG 9/24-10/8: Frontier Access install scheduled for 10/23 and 10/24. 9/18: Pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000 Base-SX | FL367-01-IM | UHG | Melissa Chapman | Wellmed New Construction | 9302 N. Blvd. West 2380 N. Blvd. West | Tampa, FL Davenport, FL |  | VS18193411 C11390934 3094-1606 3094-BVBQ 3094-BVBR | 2018-09-17 | 2018-11-23 | 2019-01-22 | 2019-02-15 |  |  | BBEC.521260 | Frontier | 65KFGS058980FTNC | 2019-02-26 | 1st FLR TELCO RM MDF SHELF 1 PORT 3 WALL MOUNTED RAD PORT 5 |  |  | 3184369 | 150 | 10.1.90.237 | 10.1.90.238 | 64740 | 202610 | UHG GLOBAL 150 | 2/15: ORDER COMPLETE - READY FOR TURN UP 2/4-2/11: Access install scheduled for 2/26. 1/28: Engineering, Design and Wiring completed last week. Frontier provided a 2/26 access install date (LEC ID 65KFGS058980FTNC) 1/21: Escalation to Lottie Lee (Mgr - CNR Agents) for status of LEC order - no dates have been provided - requested date. CUSTOMER HAS FOC FROM VERIZON 2/26 1/14: Requested CNR Agent Tinicha Freeman work to remove any barriers on order and have LEC redispatch ASAP as MDF is ready. 1/8: No date provided by Frontier yet - Opened BERT/IOS ticket to request LEC Frontier provided new target install date now that site work is complete. 12/26: Requested LEC dispatch on/after 1/4 once as that is the MDF ready date per UHG. 12/3: Per UHG, Supposed to get construction schedule this week - MDF ready 1/4/2019 - 2/28/2019 CRDD 11/12-12/3: Per LEC: PER LCON - BUILDING IS UNDER CONSTRUCTION - PLEASE RESUBMIT ORDER WHEN PHONE ROOM IS READY - REFERRING TO ORDERING; LEC WANTS PON CANCELED 11/5: Pending access install date from the LEC Frontier. 10/22-10/29: Pending USOs 10/12: Confirmed no longer special bid - address has been updated - pending USO's. 10/9: SPECIAL BID - Pending USO's 9/17: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX448-01-IM | UHG | Melissa Chapman | Wellmed | 874 Ed Hall Drive, Suite 106 | Kaufman, TX |  | 303760225 VS18190691 3102-0177 3094-BTZZ 3094-BVBB | 2018-10-12 | 2019-01-04 | 2019-01-04 | 2019-02-15 |  |  | BBEC.589487 | Embarq | 86KXGS358134UDTX | 2018-12-11 | FIRST FLOOR, COMM ROOM, BEHIND THE RECEPTIONIST DESK, WALL M |  |  |  | 2 | 10.1.89.89 | 10.1.89.90 | 64562 | 202610 | UHG GLOBAL 150 | 2/15: ORDER COMPLETED 2/11: Confirmed access install completed - issued AERO DES 493080 to complete engineering. UPDATE: ENGINEERING, DESIGN and WIRING COMPLETED - WORKING TO HAVE TECH TEAM CLOSE OUT ORDER PLUG AND PLAY 2/4: Reached out to David Rhodes (Centurylink) directly since he was working the install/status with Melissa. I advised him that Centurylink updated their order on Friday with a 2/28 access completion date. Trying to find out what changed on their side to push out the date. Pending an update. - UPDATE: A Technician was dispatched this morning to install and turn up the RAD / NID device. David spoke with him.....barring anything unforeseen, it will be ready by EOB today. 1/28: Centurylink targeting fiber in place by end of this week. Pending status from LEC. 1/21: Per David Rhodes/Centurylink: "There was initially a need for conduit and entrance facilities, but upon realizing that this is a MTU location, and our subsequent receipt of more orders, we went ahead and placed the conduit on our dime. We will have interconnecting fiber in place by the end of next week. Then we can get the circuit turned up." 1/15: Working with CNR agent Ken Schaefer to obtain details from Embarq on site requirements. Also pending update from the LEC on new rescheduled access install date. 1/7: Per LEC Embarq - access delayed - "THE CUSTOMER MUST PLACE CABLE AND CONDUIT AND ENTRANCE FACILITIES" 12/26: Embarq date missed - order still showing CNR customer not ready. Pushing for status and new due date. 11/5-12/11: Embarq has provided a 12/11 access install date. 10/22-10/29: Pending an install date from the LEC EMBARQ - FOC due by 11/21 10/24: Per Melissa, "The Century Link person I spoke to yesterday and today, Rick, was given the clinic admin’s contact info. They spoke and arranged for the person with access (Freddie) to the closets/room that Rick needs to get into, to meet with Rick in the lobby this afternoon. I just got off the phone with Rick and he was with Freddie and said that he was getting what he needed. Rick said he would call me after to let me know how things went and what is needed." 10/12: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | FL368-01-IM | UHG | Melissa Chapman | Wellmed | 13142 Elk Mountain Drive Suite 106 | Riverview, FL |  | VS18224900 3094-0274 3094-BVDW 3094-BVDX | 2018-12-03 | ASAP | 2019-02-26 | 2019-02-11 |  |  | BBEC.505835 | Frontier | 65KFGS040904FTNC | 2019-02-19 | FLR 1 SUITE 106 RAD 203 AX |  |  | 3206478 | 115 | 10.1.89.21 | 10.1.89.22 | 64543 | 202610 | UHG GLOBAL 150 | 2/11: ORDER COMPLETE 1/28-2/4: Access install date has been updated to 2/19. 1/22: PON WILL CANCEL ON 2/4 IF DATE IS NOT SUPP'D. LEASE OK - LCON HAS BEEN OUT - CHECK WITH LEC 1/15: Melissa indicating possible lease issues and she will address on her side. Need to find out if there are customer site requirements. 1/15: LEC still indicating major build - once site is ready for access, please advise AT&T - SUPP IS REQUIRED FOR NEW DD 1/8: Per LEC, 1B OUTSIDE PLANT (OSP) - MAJOR BUILD. They did just come back with a CNR condition as well - need to make sure site is ready and request new due date (currently showing 1/25 for install but that may change.) 1/3: LEC install showing 1/25. 11/16-12/11: Order rec'd - pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX450-01-IM | UHG | Melissa Chapman | Wellmed | 2301 S Hampton Ste 900 | Dallas, TX |  | VS19006293 3102-0270 3094-BVFV | 2019-01-08 | 2019-03-29 | 2019-03-29 | 2019-02-15 |  |  | BBEC.508792 | ATT SW | 14KRGN884853SW | 2019-02-14 | 1ST FLOOR TELCO CLOSET BEHIND SUITE 900, 6-POSITION |  |  | 3217670 | 50 | 10.1.89.8 10.1.88.253 | 10.1.89.9 10.1.88.254 | 64512 | 202610 | UHG GLOBAL 150 | NOTE: IP's were changed by UHG - Email sent to Melissa/Chris on 6/18/2019 to confirm those changes were made in January when the order was submitted. 2/15: ORDER COMPLETE - READY FOR TURN UP 2/4-2/11: Access install scheduled to complete on 2/14 1/28: Construction completed fiber work on 1/25. Infrastructure is complete - pending access install date (FOC due back by 2/5.) 1/22: Site Survey pending - scheduled for 1/24 1/15: Pending install date from ATT SW
New | 100M Port / 200M Access Ethernet AVPN | IR516-01-IM | UHG | Melissa Chapman | We work | Ground Floor & 4th Floor Suites / 2 Dublin Landings North Wall Quay North Dock | Dublin, Ireland |  | ISR18111286213 VS18207222 3094-BVDG 3094-BVDH | 2018-11-13 | 2018-12-12 | 2019-02-13 | 2019-02-25 |  |  | IUYF.104050 | SAREA / COLT | SR/VLXP/051190/ATI DUB/DUB/LE-247775 | 2019-02-22 | Ground Floor Comms Room, Customer Cabinet, DUB_CA_01635 at "U" position 41, Port 1. | 1000BaseSX LC Connector |  | 3193659 | 2 | 10.1.91.133 10.1.91.13 | 10.1.91.134 10.1.91.14 | 64671 COS 6039 | 202610 | UHG GLOBAL 150 | 2/25: ORDER COMPLETE - TID SENT 2/19: Colt has advised below, can you please confirm the access and the query regarding the parking? From Colt: Kit install & test on track for this Friday, 2/22. Can you please confirm access can be approved by Optum as follows? – Date & Time: Fri, 2/22, @ 10:00 Technician: Tommy Callaghan Desc: Install LT-S & test circuit DUB/DUB/LE-247775 Site: Ground Floor, MDF Room, 2 Dublin Landings, Dublin 1 Parking: Can you confirm if a parking space can be made available for Tommy please? 2/15: Cabling is underway. External cabling completed last 2/13. Fiber work due to be completed by the end of this week. Colt scheduled a Tech to install the kit & test the circuit Friday, 2/22. Tentative Colt completion date showing 2/25. 2/11: Mark Gahan has approved Colt's drawings, as of the last hour. Colt is planning on going to pull the cable Wednesday or Thursday or next week. Mark is the best contact, he can be reached at Mark.Gahan@CBRE.com or at +353 161 85763. AIM checking remaining questions w Colt including where is Colt planning on terminating inside the building, in the basement, or in Optum's MDF and what is the timeline for the remaining milestones and activities. 1/31-2/5: Building Manager identified an alternative internal route which does not require cable tray to be installed. The Fibre Supervisor is looking to schedule the internal cabling & BFP install for week commencing 2/11. The Contractors schedule is full this week (2/4-2/8.) They will put together the RAMS etc & submit to the Building Manager for approval. The internal cabling & BFP install will take 3 days. Once the civils is complete, external cabling & splicing can be scheduled. There is approx.. 150m of external cabling which will require 2 day's work. Access permits will be required & some of the work may need to take place out-of-hours (OOH). 1/28: Escalation manager is checking with Colt for the site survey result. NCON working to find out from Colt about the remaining milestones 1/25: Per David Guinan (StructureTone), Power is available and MDF room is complete as per scope. As per the feedback from the Colt External Ops Team is that they are working to complete civils work on 2/02. They reiterated that there are some time restrictions on Colt due to the construction sites in the area. Trial holes have been completed & some chambers completed. 1/22: Per email just now from Kristina (EMEA Site Implementation Manager (SIM)), Colt will contact Laura Nugent to arrange site visit. For the dates, it’s not known yet. 1/21: UPDATE: WeWork POC provided - Laura Nugent (copied in). Her number is 0879299160. 1/17: Colt provided further details about the current status and also explained that the multiple site visits will be needed. From Colt: "The Civils Inspector clarified that the 3 chambers Colt mentioned, this is the ‘entry point’ in to the building. The Site Foreman needs to confirm which chamber Colt is to use as it is not clear whether the 3 chambers go to 3 different comms rooms. If AT&T could let Colt know the best customer contact for the site, the Fibre Supervisor will arrange a site visit to assess the internals. As the site is under construction, he may need to carry out a number of site visits." 1/14: According to Colt Manager they are not going to get the building connected until the end of January 2019, but they will have further updates once they receive the City permits. We have requested further updates on the delivery dates. 1/8: Per David McVeigh (Optum), no change in PTT required. As per the latest update Colt is awaiting City Council to end the digging embargo. Once Colt receives the permission to dig they will advise AT&T. 1/7: Per David McVeigh (Optum): The delays are creating significant issues for the business. Requested AT&T provide an alternative last mile provider that would have a more favorable timeline. 1/7: Colt advised as follows: “As this is a new building for Colt to connect, delivery is currently with the External Ops Team who have received the licences to commence the digging work. There are a lot of services in the road, one is a gas transmission pipe. As it’s gas transmission, Bord Gáis supervision MUST be on site during the excavation works. we also have a 5 lane road crossing to do. There is also a dig embargo by Dublin City Council around Dublin City from 26/11/2018 to 03/01/2019 (no street digging can take place during this time) . we are not going to get the building connected until the end of January 2019 is my guess at this stage.” 12/26: Customer wants Colt to prepare cross connects...IPC notified. Still tracking for possible end of January timeframe for completion of build/digging. 12/14: “As this is a new building for Colt to connect, delivery is currently with the External Ops Team who have provided the following update – “We have received the licences to commence the digging work. There are a lot of services in the road, one is a gas transmission pipe. As it’s gas transmission, Bord Gáis supervision MUST be on site during the excavation works. We also have a 5 lane road crossing to do. There is also a dig embargo by Dublin City Council around Dublin City from 26/11/2018 to 03/01/2019 (no street digging can take place during this time) . We are not going to get the building connected until the end of January 2019 is my guess at this stage.” 12/10: Still pending a firm PTT date - MPOE details requested from Colt order manager 11/27-12/3: Pending PTT date - asking Colt for the Intake point / MPOE location. Order accepted on 11/23 and in planning stage 11/13: Rec'd ISR - SR was released to PTT today. Pending surveys and estimated date for completion of access. 10/16-10/29: Waiting on technical validation 9/11: Pending order info
New | Connector Change | PH550 | UHG | Melissa Chapman |  |  | Philippines | [22 empty] | 2/26: Order complete 2/12: PTT completing their work possibly this week per Christine 1/29: Targeting Feb 4th Install - will be TTU (week of Feb 11th) 1/22: Order went through - with PTT to coordinate the change - targeting this week
New | 7xT1 AVPN | TX444-04-IM | UHG | Melissa Chapman | UHG- Wellmed | 11901 W PARMER LANE, SUITE 300 | Cedar Park, TX |  | 303896221 VS18209812 3102-1141-FR 3102-1142 3102-1147 3102-1144 3102-1140 3102-1146 3102-1145 3102-1143 3094-BVDK | 2018-11-02 | ASAP | 2018-12-10 | 2019-02-26 |  |  | DHEC.358263.811 DHEC.358263.812 DHEC.358263.813 DHEC.358263.814 DHEC.358263.815 DHEC.358263.816 DHEC.358263.817 | ATT SW | 32HCGS697779SW 32HCGS697783SW 32HCGS697787SW 32HCGS697780SW 32HCGS697781SW 32HCGS697782SW 32HCGS697778SW | 12/14/2018 12/20/2018 12/14/2018 11/28/2018 12/20/2018 12/14/2018 11/28/2018 | 1ST FLR TELCO ROOM T1 CAB 3 SLOT 2 1ST FLR TELCO ROOM T1 CAB 4 SLOT 2 1ST FLR TELCO ROOM T1 CAB 4 SLOT 3 STE 300 1ST FLR TELCO RM CAB 3 SLOT 3 1ST FLR TELCO ROOM T1 CAB 3 SLOT 4 1ST FLR TELCO RM, T1 CAB 4 SLOT 4 1ST FLR TELCO ROOM T1 CAB 3 SLOT 1 |  |  | 3195467 |  | 10.1.90.113 | 10.1.90.114 | 64583 | 202610 | UHG GLOBAL 150 | 2/26: ORDER COMPLETE 2/18-2/25: Final T-1 completed - pending testing completion and OK to turn up. ADDED TO REEVES SDM SHEET FOR WWR TURNUP - UPDATE: REACHED OUT TO TECH MARY BANKS-TAYLOR VIA Q TO COMPLETE THIS ORDER 2/11: Issued IOS Escalation ticket on remaining T1 - 3102-1140 2/4: One of the T1's is showing complete on the LEC side - pending on 2nd. 1/21-1/28: Issued BERT/IOS tickets to follow up on last (2) T-1's........UPDATE: LEC advised firm install date on final (2) T-1's will be 1/30. 1/15: PON's on last two T1's show they're targeting 1/25 for install. Pending confirmation. 1/7: Requested ordering supp the request to obtain an install date on the last (2) T-1's. HALO ticket opened. 12/26: Pending completion of last two T-1's. LEC indicated equipment issues. 12/11: Access install bumped out to 12/14 and 12/20 - PRE-CTA CNR AGENT CH8854 IS ASSIGNED. Need to confirm that customer's contractor completed the wiring on prem. 12/3: Access install on final T-1 scheduled for 12/6. PER LEC THE CUSTOMER NEEDS TO PROVIDE 25 PAIR INSIDE WIRING TO EXTEND SERVICE FROM THE TELCO SERVING TERMINAL TO SUITE. CSR IS AWARE OF THIS ISSUE AND ARRANGED FOR A CONTRACTOR TO COMPLETE THIS WORK BY 4PM CST DEC 4TH. 11/27: Pushed DDF ticket to provisioning as still not seeing install date on 3102-1144. Requested PON be submitted to LEC. 11/16: Six of the T1's are scheduled to install on 11/28. The final T-1 3102-1144 has FOD due today 11/16 which means the PON is being sent out today. My guess is that circuit will install after the others due to timing, but no ETA yet. Probably within a few days. Overall due date 12/10. 11/2: Order rec'd
New | 20MB Port/ 50M Access EaAVPN 1000Base-SX | ID011-01-IM | UHG | Melissa Chapman | Optum | Idaho Water Center 322 East Front Street | Boise, ID |  | VS19011942 3094-2283 3094-BVGB | 2019-01-15 | 2019-01-30 | 2019-04-09 | 2019-02-12 |  |  | BBEC.546691 | Qwest | 39KXGS381396MS | 2019-02-14 | 1ST FLOOR DMARC, WEST WALL TYPE: OPTICAL PORT: 2 |  |  | 3221826 | 800 | 10.1.89.113 | 10.1.89.114 | 65106 | 202610 | UHG GLOBAL 150 | 2/12: ORDER COMPLETE 2/11: Access completed ahead of schedule. Pending testing completion and OK to turn up. 1/29-2/4: Access install scheduled for 2/14. 1/15: Order Rec'd
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | NY078-08-IM | UHG | Melissa Chapman |  | 136-02 Roosevelt Ave | Flushing, NY |  | VS19020176 3094-2293 3094-BVGS 3094-BVGT | 2019-01-28 | ASAP | 2019-04-22 | 2019-02-19 |  |  | BBEC.567977 | Verizon North | 32KFGS218398NY | 2019-02-13 | FLR 1 DATA RM, MOUNTED ON REAR WALL...TAGGED |  |  | 3228009 | 219 | 10.1.94.69 | 10.1.94.70 | 65131 | 202610 | UHG GLOBAL 150 | 2/19: ORDER COMPLETE 2/18: Access install completed - demarc provided. Pending testing completion and OK to turn up. 2/11: Access install scheduled for 2/13. 1/28: Order rec'd
New | 300MB Port/ 500M Access EaAVPN 1000Base-SX | DC006-04-IM | UHG | Melissa Chapman | Advisory Board | 2445 M Street | Washington, D.C. |  | VS19005635 3102-0243 3094-BVFP 3094-BVFQ | 2019-01-09 | 2019-03-28 | 2019-03-28 |  |  |  | BMEC.974356 | Verizon South | 36KFGS309690CD | 2019-02-07 | C1 LEVEL MTR RR 1 SH 13 |  |  | 3217256 |  | 10.1.92.145 | 10.1.92.146 | 65105 | 202610 | UHG GLOBAL 150 | RECEIVED CANCELLATION REQUEST - Submitted request via IOS 2/11: Access install completed - pending testing completion. 2/4: Access install scheduled for 2/7 1/15-1/29: Pending install date from Verizon South
New | 400M Port / 500M Access Ethernet AVPN | IR512 | UHG | Melissa Chapman | UHCSLETIE10 | Letterkenny Office Park WindyHall Cmps | Letterkenny, Ireland |  | ISR19010439810 VS19001405 3094-BVFF 3094-BVFG | 2019-01-04 | 2019-03-06 | 2019-04-04 | 2019-03-04 |  |  | BLYF.100277 | SAREA/Enet |  |  | Demarc: Building 2 Letterkenny Office Park, Windy Hall Campus, Comms room is located on ground floor Node/Patch Panel lky_CN3916_tn45 A-Port 1 | 1000BaseLX / LC Connector |  | 3214410 | 2 | 10.1.89.37 | 10.1.89.38 | 65047 COS 6039 | 202610 | UHG GLOBAL 150 | 3/4: ORDER COMPLETE 2/18-2/25: ON TRACK - Per NCON Matej Karovic, Splicing is now completed. The enet NTU installation is scheduled for 2/26 with handover to AT&T following network acceptance testing - forecasted handover 2/28. NCON tried to improve the date of NTU install, however 2/26 is the earliest slot available in ENET 2/12: UPDATE: NCON advised he cannot confirm splicing completed as he did not receive results yet. He's currently waiting for his Enet contact to respond 2/4: Dates remain unchanged - Splicing scheduled for 2/11. NTU install targeting 2/18 with handover to AT&T. 1/28: Splicing scheduled for 2/11. NTU install targeting 2/18 with handover to AT&T. NCON is checking if there is room for improvement in the current schedule 1/22: The order was placed with ENET on 1/9, accepted on 1/11. Pending scheduling and completion of site survey. 1/21: Pending date from PTT - reached out to NCON Matej Karovic for status. 1/9: Pending order to be placed with SAREA/Enet 1/8: Rec'd order info and ISR from Christine.
| 5TH LEVEL VP ESC HOT ORDER 1GB Port 1GB Access 1000 Base-SX | NY464-01-IM | UHG | Melissa Chapman |  | 992 S 2ND ST Ronkonkoma, NY 11779 | Ronkonkoma, NY |  | VS18085635 3094-3762 3094-BTMW 3094-BTMX | 2018-05-10 | ASAP | 2019-02-27 | 2019-02-27 |  |  | IZEC.566142 | ALTICE (aka Cablevision Lightpath) | 01LUXS253588CLVI | 2018-11-01 | 1ST FLOOR DATA ROOM, VE JACK #8 RCATION IS THE FIRST FLOOR MDF ROOM VIRTUAL EDGE PATCH PANEL PORT 1. THE HANDOFF IS MULTI MODE, SPEED IS 1000MB FULL DUPLE X, NO AUTONEG. THE VLAN IS 340, TAGGED, AND THE CIR IS 1000MB | 1000 Base-SX |  | 3109880 | 340 | 10.1.92.209 | 10.1.92.210 | 64848 | 202610 | UHG GLOBAL 150 | 2/27: ORDER COMPLETE 2/26: Access install date moved out to 2/27. 2/25: LEC working to resolve issue - advised Carrier Management that they would have this installed/fixed by COB 2/25. UPDATE: Install is still scheduled for 2/25. Carrier Mgt has follow up for 2/26. Next update will be 2/27 unless status is available prior to then. 2/18: The LEC Cablevision installed a 10G access instead of 1G. We are escalating for resolution and quick turnaround to fix this. 2/11: Per provisioning, we have the wiring date completed as we have good light from the LEC, however the interface is not up. Testing oingoing. Carrier Management escalated order back to LEC yesterday morning - Diane Carter (Exec Esc Manager) remains engaged. 2/5: Spoke with Jane Tansor (AM) about this one this morning - ball is in AT&T's court - Jane is engaging Diane Carter (Exec Esc Manager) to get this closed out complete/plug and play. 2/4: Escalation to Mary Bruce (Esc Mgr) for assistance on status and completing order. 1/29: Received demarc location - Escalation Mgr Mary Bruce working order - JACKIE COCHRAN ,EOSD PROV TECH assigned to work order. Pending status of testing. --- UPDATE: TECH ADVISED TESTING ISSUES (SEE NO INCOMING LIGHT FROM ACCESS DIRECTION - OPENED WMS TKT 912810677 FOR TESTING - CALLED OFFICE LEFT VM 1/21: Pending update from LEC regarding completion of access. Per Carrier Management, they advised that access was set to be installed last week on 1/17. Provisioning working on other critical dates to complete engineering/wiring/design. 1/14: Pending update from Carrier Management - Reached out to LEC's Kathy O'Brien for status UPDATE: LEC scheduled this morning with Simon for 1/16/19 1/7: Escalation to Chris Lane (Carrier Management) for status from the LEC. UPDATE: PROVIDED PICTURES OF SITE TO CARRIER MANAGEMENT AND REQUESTED DISPATCH OUT ASAP BY LEC 12/26: Targeting 1/8 for access completion - pending status from Escalation Manager and her efforts to escalate for confirmation. 12/10: Order accepted into the VP portal without the expedite and one of our best VP escalation managers is working it. She will need 1-2 days to work with carrier managment and the carrier, but will then begin sending E-notes to the SDM team and working to bring in the install dates. 12/3: Escalation to Derek Hunter for status - pending install completion date. 11/27: Order was escalated to Derek Hunter (District Escalation Manager) - confirmed added to VP portal escalation list. 11/5-11/13: Access install missed - BERT/IOS ticket to be opened to escalate.- 3 CONTACTS - NO RESPONSE FROM LEC 9/24-10/29: LEC has provided an 11/1 access install date. 9/17: PER LEC MANAGER, CUSTOMER NAME ISSUE HAS BEEN RESOLVED ORDER IS IN DESIGN. 9/10: Follow up to AIM requesting status of install date for this site - no issue on company name. 9/5: Advised AIM that companies are the same - requesting new date from LEC 9/4: AIM (Access Intervention Mgmt) confirmed LEC now has PON's - RECEIVED A CALL FROM THE LEC AND THEY NEED TO KNOW IF THE CUSTOMER NAME UHR IS THE SAME AS NATIONAL MEDTRANS NETWORK. 8/27: Per LEC Manager, PON's were not received. PON was reissued on 8/24 - FOC due no later than 9/17 - Back to AVM - 2nd time around - need dates ASAP. 8/20: No install date provided - escalating on missed FOC (BERT/IOS Escalation) 8/14: FOC due 8/15. PON HNS01936431 7/30 - 8/06: Pending access install date - FOC due back by 8/15. 7/25: PON released. ESA PON: HNS01936433; Access PON: HNS01936431 7/24: PON's canceled by the LEC. New PONs need to be issued. 7/23: Follow up on escalation/provisioning tickets. 7/16: Escalated issue to Provisiong Design Coach Pat Tate-Jackson. LEC advised missing PON's. Provisioning tickets were issued by Design team. 7/10: Provisioning has escalated this back to the LEC Cablevision/Lightpath via AERO ticket 245961 for status of access install - next follow up is 7/11. 7/3: LEC Cablevision/Lightpath advised they did not receive PON's - requested Provisioning Design Coach engage and have Assembler group reissue PON's. 6/26: Escalating on missed FOC by LEC Cablevision/Lightpath. 6/18: LEC Cablevision/Lightpath missed FOC. AERO Ticket 255969 issued to escalate on the miss and to push for access install date. 5/21-6/12: FOC scheduled for 6/12. 5/14: PON scheduled to be issued on 5/15. 5/7: Order placed, received cproject number.
New | Noida port upgrade | II542 | UHG | Melissa Chapman |  |  |  |  | ISR19010962818 | [20 empty] | 3/11: DTAC confirmed Port and CIR speed upgrade from 100 Mb to 200 Mb successfully completed. 2/26: Scheduled with customer for 3/10 1/28-2/25: Note sent to customer on 1/10 requesting a downtime. NCON is pending receipt of this info. 1/22: Rec'd ISR# 1/21; Follow up with Christine - have iSR# - Process of being scheduled 12/4: contracts with UHG
New | MOW ORDER | AU507 | UHG | Melissa Chapman | Morneau Shepell | 303 Collins Street | Melbourne AUS |  | ISR19012555079 VS19014366 3094-BVGD 3094-BVGF | 2019-01-25 | ASAP | 2019-04-25 | 2019-03-18 |  |  | MMYF.108150 | SAREA / AAPT |  | 2019-04-03 |  | 100Base-T |  |  |  | 10.45.10.193 | 10.45.10.194 | 65264 COS 6039 | 202610 | UHG GLOBAL 150 | 3/18: ORDER COMPLETE AND READY FOR TURN UP. TID DOC SENT OUT 2/25-3/11: Revised planned delivery date is 4/3/2019 2/18: Per NCON Ahmad Badri, reached out to LCON for building info but no response 2/4-2/11: Order placed to PTT on 1/29. Pending survey results. 1/29: ISR rec'd 1/15: Order has been placed. 1/8: Per Christine, waiting on countersignature and will then place order
| HOT ORDER 100M Port/ 200M Access 1000 Base-SX | DC007-01-IM | UHG | Melissa Chapman | Optum Insight | 655 New York Ave | Washington, DC |  | VS18100653 3094-3493 3094-BTPG 3094-BTPH |  | ASAP | 2018-08-21 | 2019-03-15 |  |  | BKEC.999809 | Verizon South | 36KFGS308903CD |  | BSNT,P2,RM MTR,TEL RM,,SFP,LP N,CAB N,,RCK,1,OTHER ,SFP, |  |  |  | 125 | 10.1.92.49 | 10.1.92.50 | 64813 | 202610 | UHG GLOBAL 150 | 3/18: ORDER COMPLETE - READY FOR TURN UP 3/12: VLAN PON HESV4189379 scheduled to complete 3/15. 3/11: Access install is complete - (R80) - Pending completion date for VLAN PON# HESV4189379. 3/4: PON supp'd to have Verizon re-contact site for survey etc. FOC due back by 3/26. 2/25: LCON NOT RESPONSIVE, ENGINEER REACHED OUT TO LCON AT CKL1 ON ASR, PENDING CALL BACK. NO SUP REQUIRED. FOC delayed. 2/4-2/18: New PON# HES02893870 issued. Pending install date. FOC due 3/4. ROE has been signed - PON to be submit 1/21-1/28: Pending completion or ROE - PON has been cancelled and will need to be reissued once the ROE issues are resolved. 1/14: PROPERTY MANAGER WANTS VERIZON TO SIGN ROE DOCUMENTS. THIS IS A LEGAL ISSUE WHICH HAS BEEN REFERRED TO VERIZON LEGAL 1/7: Reached out to CNR Agent Melondy Spain for status of ROE.- Close to getting ROE signed per Melissa. No ETA yet. 12/26: ROE Delay 12/3-12/10: PRE-CTA CNR AGENT MELONDY SPAIN assigned. ROE delay 11/5-11/27: ROE issues - CNR 10/15-10/29: Access install showing 10/29. FOC updated on 10/8. ROE issues 9/10-10/8: CNR/ROE Delay - Pending update on Landlord issues at site. 8/28-9/4: CNR - Still pending ROE w/ LL 8/14-8/20: Order showing CNR CUSTOMER NOT READY. Landlord issues - they want Verizon to sign ROE/Insurance. No supp required. PER MELISSA - STILL WORKING ON THE LANDLORD ISSUES - 7/23-8/06 FOC reached, access targeted to install 8/21. 6/25-7/16: Pending an access install date. (FOC due 7/24) 6/6-6/18: USO's rec'd - Pending FOC 6/1-6/4: Order placed by sales on 5/31, pending cproject number.
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | WY002-04-IM | UHG | Melissa Chapman |  | 2515 Warren Ave Suite 205 | Cheyenne, WY |  | 304200209 VS19015594 3102-0275 3102-BBCW | 2019-01-18 | 2019-04-15 | 2019-04-15 | 2019-03-11 |  |  | BBEC.581735 | Qwest | 79KXGS382890MS | 2019-02-12 | 2ND FLOOR TELEPHONE ROOM. TYPE: OPTICAL PORT: 5 |  |  | 3224736 | 69 | 10.1.88.205 | 10.1.88.206 | 64563 | 202610 | UHG GLOBAL 150 | 3/12: ORDER COMPLETE (Letter sent late PM yesterday) 3/11: Access and VLAN PON's are complete - I've reached out to the assigned tech (Greg Boyer) to get this closed out plug and play. 3/4: LEC DELAY - CENTRAL OFFICE EQUIPMENT NOT AVAILABLE - Pending new date for access completion. 2/25: Qwest has provided an estimated 3/1 completion date for install - LEC DELAY. 2/18: DELAY REASON: "QWEST/CL IS NOT READY FOR ACCESS TESTING" - BERT/OS ticket issued to escalate the missed install with provisioning to find out why the delay and when the LEC expects to have completion. 2/11: Access install scheduled for 2/12. 2/4: Pending an install date from the LEC Qwest. 1/18: Order Rec'd
New | 7xT1 AVPN | NV124-04-IM | UHG | Melissa Chapman | Optum Care | 4090 West Craig Road | Las Vegas, NV |  | VS19028320 3102-1620-FR 3102-1626 3102-1619 3102-1625 3102-1624 3102-1622 3102-1623 3102-1621 3102-BBDD | 2019-02-13 | ASAP | 2019-03-11 | 2019-03-11 |  |  | DHEC.182587.811 DHEC.182587.812 DHEC.182587.813 DHEC.182587.814 DHEC.182587.815 DHEC.182587.816 DHEC.182587.817 | Centurylink | 53HCGS335461CTRL 53HCGS335420CTRL 53HCGS335413CTRL 53HCGS335460CTRL 53HCGS335414CTRL 53HCGS335458CTRL 53HCGS335412CTRL | 2019-02-28 | 1ST FLR MAIN TELCO RM, SLOT 14/14 1ST FLR MAIN TELCO RM, SLOT 4/14 1ST FLR MAIN TELCO RM, SLOT 2/14 1ST FLR MAIN TELCO RM, SLOT 13/14 1ST FLR MAIN TELCO RM, SLOT 3/14 1ST FLR MAIN TELCO RM, SLOT 12/14 1ST FLR MAIN TELCO RM, SLOT 1/14 |  |  |  | Local DLCI 125 | 10.1.88.193 | 10.1.88.194 | 64760 | 202610 | UHG GLOBAL 150 | 3/11 UPDATE: ORDER COMPLETE - READY FOR TURN UP 3/11: Reached out to tech Evonye Gibson to close out order - all T-1's are complete, pending just the PORT USO as it's future due. UPDATE: EVONYE checking now (3:02pm) 3/5: UPDATE: All but one T1 are complete - pending completion of the last T-1 and the port USO. 3/4: Access install completed - pending testing completion and OK to turn up 2/26: Pending USO's 2/13: Order rec'd
New | 10MB Port/ 20M Access EaAVPN 1000Base-SX | NY025-06-IM | UHG | Melissa Chapman |  | 30 Flatbush Ave. | Brooklyn, NY |  | 303981929 VS18221449 3094-2134 3102-BBCR | 2018-11-29 | ASAP | 2019-03-04 |  |  |  | MMEC.778822 | ASE LNS | [7 empty] | 10.1.90.113 | 10.1.90.114 | 65268 | 202610 | UHG GLOBAL 150 | 2/28: RECEIVED CANCELLATION NOTICE FROM MELISSA 2/26: Followed up with Becky Duncan (Construction) to confirm the LCON info and see about getting this back on track. 2/25: Reconfirmed with construction that the correct LCON is Fleary, Jenelle. If they continue to have issues contacting the LCON they are to let me know as we continue to see this order delayed. 2/15: PER LEC: "LEFT VMAIL/EMAIL FOR LCON, NO RESPONSE" - PENDING UPDATE ON LEC INSTALL DATE 2/12: Confirmed with CNR Agent that CNR was removed and PON supp'd for new install date. We requested 2/15 but that is just a request. 2/11: Followed up with Bill Buhrman (LNS) regarding redispatch to install access. Requested CNR Agent Melonie Williams supp order to remove CNR coding and request redispatch ASAP. 2/4: Switching gears on order back to LNS. Working with LNS team to expedite access delivery. LNS looking to schedule site visit - have 2-fibers avail. 1/22: Going with Verizon for access 1/17: Per Chris Cowan, LNS does not have a ROE agreement with this site. The lack of an ROE could add unwanted delays to this order so Chris recommended UHG issue an order cancelation and submit a new order with an alternate LEC. Hudson Valley shows approved but only for 100M access. Pending UHG response. 1/15: Escalated to NSS PM Rebecca Duncan for update on site survey and fiber date. CHRIS ALSO CHECKING HIS RESOURCES - Reached out Melissa to advise this is CNR from Construction as they cannot get in touch with LCON for SV. 1/7: Escalating for missed site survey by Construction & Engineering. Pending date, fiber details and access install info. (sent to DEQUENTEZ ALLEN) 12/11-12/26: FOC due back by 12/28. 11/29: Order rec'd
New | 10MB Port/ 10M Access EaAVPN 1000Base-SX | NC057-01-IM | UHG | Melissa Chapman |  | 4129 Raeford Road | Fayetteville, NC |  |  | 2019-03-06 | [14 empty] | 10.1.95.121 | 10.1.95.122 | 65223 | 202610 | UHG GLOBAL 150 | 3/18: JOHN S. CANCELLED ORDER - INCORRECT ADDRESS 3/6: Order rec'd
New | 10MB Port/ 50M Access EaAVPN 100Base-TX | FL055-04-IM | UHG | Melissa Chapman |  | 1425 N.W. 82 Avenue | Doral, FL |  | VS19046790 3102-0317 3102-BBDL | 2019-03-05 | ASAP | 2019-05-31 | 2019-03-28 |  |  | BBEC.528381 | ATT SE | 60KQGN787466SB | 2019-03-26 | 1ST FL, WAREHOUSE, NORTH WALL, CIENA 0, PORT 2 |  |  | 3246945 | 50 | 10.1.87.161 | 10.1.87.162 | 64863 | 202610 | UHG GLOBAL 150 | 3/28: ORDER COMPLETE 3/18-3/25: Access install scheduled for 3/26. 3/5: Order rec'd
New | 10M Port / 50M Access Ethernet AVPN 1000 Base-SX MMF LC connector | UK544-03-IM | UHG | Melissa Chapman | Advisory Board | 46 Aldwych 3rd Floor, Melbourne House | London, UK |  | ISR19013082579 ISR19031447928 |  |  | 2019-05-06 |  |  |  |  | SAREA/Vodafone (C&W) | [7 empty] | 10.1.94.9 | 10.1.94.10 | 65117 |  | UHG GLOBAL 150 | 4/8: Circuit delivered - TID sent -- Demarc: Floor - 3, Room - Telco 4/1: PTT SAREA/British Telecom targeting 5/7 for completion of access. 3/20: Order released to the PTT SAREA/British Telecom - pending install date. Overall due date showing 6/17. 3/18: New ISR# rec'd - pending order info. 3/12: Working to correct order. 3/4: Need to use BT on this order 2/25: Per the NCON, they have reviewed this order and can confirm that Vodafone has acknowledged it and are awaiting the survey schedule date from Openreach. Once we received this information the NCON will update the team. 2/18: SR released on 2/5. Pending PTT date. 1/29: Pending ISR 1/8: Per Christine, requested access, will then place order
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | FL371-02-IM | UHG | Melissa Chapman | Wellmed | 819 Cypress Village Blvd | Ruskin, FL |  | 303972339 VS18219904 3094-2085 HSSC3562325 3102-BBCQ 3102-BBCP | 2018-11-29 | ASAP | 2019-02-28 | 2019-04-02 |  |  | BBEC.586202 | FRONTIER-CTF | 65KFGS068403FTNC | 2019-03-07 | BUILDING 1 FLOOR MDF RAD 203 PORT 5 |  |  | 3203177 | 104 | 10.1.89.29 | 10.1.89.30 | 64935 | 202610 | UHG GLOBAL 150 | 4/2: ORDER COMPLETE 4/1: Escalated to Provisioning Design Davitta Thurmond to have PON checked - not showing supp request for redispatch in TIRKS. 3/29: AERO ticket completed - reissued DDF ticket to get supp for redispatch. 3/25: Issued 2nd level escalation on AERO DES 527300 and issued DDF ticket to assist on LEC redispatch. 3/18: Issued Escalation on AERO ticket 527300 for missed install - pending status on redispatch and access completion. 3/11: Opened AERO Design 527300 for missed install. 2/18-3/4: Access install scheduled for 3/7 2/11; PON HSSC3562325 was sent to LEC on 2/8. Pending install date. (due back by 3/15) 2/4: Q to Lasherl Thomas regarding ticket #479436 - still no updates from Frontier - Sent escalation also to Lottie Lee (CNR team) to find out why this was missed - no CNR coding on order so not sure why Frontier missed their 1/25 install date. Pushing for an update. 1/28: AERO CM ticket 479436 opened - Carrier Management engaged due to missed install by Frontier. 1/7-1/21: Frontier access install scheduled for 1/25. 12/11-12/26: FOC due back by 1/10/2019 - issued AERO DES 445901 for R15. 11/29: Order rec'd
New | 1G Port/ 1G Access EaAVPN 1000Base-LX | VA732-01-IM | UHG | Melissa Chapman |  | 44245 GIGABIT PLZ | Ashburn, VA |  | 304435281 VS19045483 3102-0022 3102-BBDF 3102-BBDG VS19017183 3094-2287 3094-BVGL 3094-BVGM VS19002197 3102-0257 3094-BVFK 3094-BVFL | 2019-01-02 | 2019-03-22 | 2019-04-17 | 2019-04-05 |  |  | IZEC.568603 | Verizon South | 46KFGS305482CV | 2019-03-26 | GND,,RM MTR,DATA CTR,,LGX,LP N,CAB N,,SHELF,1,JCK, 8, |  |  | 3246103 | 24 | 10.1.63.217 | 10.1.63.218 | 64566 | 202610 | UHG GLOBAL 150 | 4/5: ORDER COMPLETE 4/1: Access install completed - pending testing completion and OK to turn up. 3/25: Access install scheduled for 3/26. 3/18: Pending release of the access PON to the LEC. Will be sent out by COB today. 3/14: Received NEW USO's - 3102-0022 3/11: Per Chris, this is being reissued - pending status on the reissued order. Pending new set of IP's - Chris working 3/5: UPDATE: PROVISIONING DESIGN ADVISED THIS NEEDS TO BE CANCELLED/REISSUED - TO BE DISCUSSED ON WEEKLY CALL TODAY. THIS ORDER WAS REISSUED AS SWITCHED/DED PER TOKEN, WINKY AND ICORE, WILL NEED TO BE CANCELLED AND REISSUED WITH CORRECT PRODUCT 3/4: AERO Design 520356 for design work completion (engineering) 2/25: Access install complete - pending VLAN completion (DDF Ticket issued). Demarc provided. Engineering due 2/28, Design/Wiring due 3/1 and 3/6. Working to complete ahead of schedule if possible. 2/18: Access install scheduled for 2/20 2/11: PON released on 2/6 - FOC due back by 3/13. 2/5: New USO's rec'd 3094-2287 - Pending release of PON to Verizon (2/5). 1/30: Per Chris Cowan: VA732 is the Ashburn order that AT&T, my ordering team, created an ordering error when they submitted this original order to Verizon. The order should have been placed as you and I requested it, as standard Switched access. AT&T’s ordering error, they processed it as Switched over Dedicated. This is a different product from Verizon than standard Switched Ethernet that would require a SOLD notice from AT&T. Our only option to correct this was to issue a cancel and reissue of this order for VA732 and that was accomplished yesterday. Original order was cancelled and a new order was processed, with new MDS ID: 1-9XXQRRW. We are now pushing for the new order numbers associated with the second order (Correction) for VA732, Ashburn (44245 GIGABIT PLZ). 1/29: Chris working to correct order - pending new install date (as standard switched access) - Follow up with Clyde 1/22: Access due to install on 1/25. 1/15: Pending install date from Verizon South
New | 20MB Port/ 50M Access EaAVPN 1000Base-SX | KY003-01-IM | UHG | Melissa Chapman |  | 401 S Fourth Street | Louisville, KY |  | VS19035445 3094-2356 3094-BVJN | 2019-02-19 | 2019-05-13 | 2019-05-13 | 2019-04-03 |  |  | BBEC.537533 | ATT SE | K1KRGN402197SC | 2019-03-19 | 17TH FLR IDF ROOM WALL MOUNT |  |  | 3238377 | 51 | 10.1.88.181 | 10.1.88.182 | 65224 | 202610 | UHG GLOBAL 150 | 4/24: Per Chanze Cowan...MGR OSP PLNG & ENGRG DESIGN (Louisville)....From my understanding this is located inside of a data warehouse. And they are normally in control of the common spaces. I reached out to the LCON on the order and really didn’t get a reply, so we were forced to link this to an existing NTE. If this circuit needs to be moved to a different location I suggest a new order be made and a better LCON listed to set up a site visit. It’s in a shared location and others will be able to work from this NTE as well. 4/8: ORDER COMPLETE 4/1: Per Construction Notes: There is no multimode riser fiber in this building so need this ckt to work out of NTE on the 16th floor. lsvnkypo0iw. Requested roll back uni, unlinked and add new NTE, new CLO KYS028434001. Pending rework completion. 3/25: Network (Construction) req'd rework on the fiber side. That was completed as of 3/21. Pending redispatch date from LEC. 3/11-3/18: Access install scheduled for 3/19. 3/4: Pending access install date from the LEC ATT SE 2/19: Order rec'd
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX474-01-IM | UHG | Melissa Chapman | Wellmed | 466 Mid Cities Boulevard | Hurst, TX |  | VS19028347 3102-0282 7MS02328804 3102-BBDC | 2019-02-11 | 2019-05-02 | 2019-05-02 | 2019-04-17 |  |  | BBEC.524092 | ATT SW | 14KRGN885094SW | 2019-04-25 | 1ST FLR TELCO CLOSET (3903) -3 CUSTOMER= PORT-2 |  |  | 3233609 | 50 | 10.1.88.197 | 10.1.88.198 | 65174 | 202610 | UHG GLOBAL 150 | 4/18: ORDER COMPLETE 4/15: Access install has been improved to 4/17. 4/8: Construction completed their fiber work ahead of schedule. Pending access install completion on 4/25. 2/26-4/1: Dates are unchanged. Construction site visit completed on 2/21. The EF offer was accepted. Construction fiber placement and splicing scheuled to complete on 4/16. Access install scheduled for 4/25. 2/19: PON released on 2/15. Pending install date from LEC ATT SW 2/11: Order rec'd
New | 10MB Port/ 10M Access EaAVPN 1000Base-SX | TX452-01-IM | UHG | Melissa Chapman | UHG- Wellmed | 8030 Camp Bowie Road | Fort Worth, TX |  | VS18214660 3094-2017 3102-BBCN | 2018-11-16 | ASAP | 2019-02-04 | 2019-04-26 |  |  | MLEC.728248 | ATT SW | 14KRGN884594SW | 2019-04-24 | 1ST FLOOR IT RM BACK BOARD CEINA PORTS & 2 |  |  | 3198551 | 50 | 10.1.89.33 | 10.1.89.34 | 64540 | 202610 | UHG GLOBAL 150 | 4/29: ORDER COMPLETE 4/22: Access due to install on 4/24. 4/15: Verified that PON was supp'd on 4/8. Pending new dates for fiber and access work. 4/8: Rec'd notification that site is ready - I've issued a request to have the PON supp'd for new dispatch date. 4/1: Per LEC/Construction, customer is tearing out existing phone room, Construction is waiting on customer to finish before the EF work can be completed. CNR agent PR3151 advised he sent email to customer today to verify date when site will be ready. 3/25: Access install scheduled for 3/28. Per Melissa, End user requirements have been met at Camp Bowie. The tech validated today. 3/18: Pending new install date. HITS ticket opened requesting redispatch ASAP now that phone room is completed. 3/11: Follow up set for 3/12 for stauts of existing phone room tear out that was scheduled to complete 3/8. PHONE ROOM READY AS OF 3/11 3/4: AERO TKT 512239: PER ASEDB CUSTOMER IS TEARING OUT EXISTING PHONE ROOM, CONSTRUCTION IS WAITING ON CUSTOMER TO FINISHING BEFORE THE EF WORK CAN BE COMPLETED: ECD IS SET FOR 3/8- WILL FOLLOW UP 3/12 WITH NSS 2/25: Access install missed - BERT/IOS ticket to be issued on 2/27. 2/18: NEW INSTALL DATE: 2/22/2019 2/12: UPDATE: Confirmed PON 7MS02315335 (Version AC) was supp'd requesting new install date from LEC 2/11: Requested ordering supp the PON - Pending new install date from LEC 2/5: Saundra Watson (customer) confirmed OK to redispatch. IOS inquiry submitted to supp order. _ HITS issued 2/4: REMOVED CPR ACD. AT&T WAS TOLD THAT WE CANNOT DO ANYTHING UNTIL THE ACQUISITION IS COMPLETED. SHE IS BUYING THE BUILDING. COPY & PASTE OF THE EMAIL FROM WELL MED - SAUNDRA WATSON: "PLEASE DO NOT GO OUT TO THE SITE ON THIS DATE. I HAVE ASKED PREVIOUSLY THAT A SITE VISIT NOT OCCUR ON THIS SITE UNTIL I GIVE THE GO AHEAD. THE CLINIC WILL REFUSE ENTRY UNTIL THEY ARE SCHEDULED AND READY." POSTING C01B FOR SITE NOT READY - F/U 2/4/2019 - Melissa to follow up - check into supp'ing order date out with ordering 1/28: Per Construction, the estimated completion for fiber placement and splicing is 1/30. 12/26-1/22: Access install scheduled for 1/22 12/11: FOC due back by 12/31 11/16: Order rec'd
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | NV124-01-IM | UHG | Melissa Chapman | Optum Care | 4090 West Craig Road | Las Vegas, NV |  | VS19018010 3094-2294 3094-BVGN 3094-BVGP | 2019-01-25 | 2019-03-01 | 2019-04-29 |  |  |  | BBEC.500507 | Cox Communications | 33KFGX001846COXC | 2019-06-27 | [5 empty] | 10.1.88.237 | 10.1.88.238 | 64760 | 202610 | UHG GLOBAL 150 | 4/23: Received CANCELLATION request from Melissa. Issued cancel request via IOS. 3/11-4/22: Dates unchanged - targeting 6/27 for access - UPDATE ROM COX: BELOW IS A MILESTONE TRACKER FOR THE PROJECT WITH ANTICIPATED DATES. THE DATES ARE PRELIMINARY AND IF ANY ADJUSTMENTS ARE REQUIRED NOTIFICATION WILL BE PROVIDED THIS PROJECT HAS A FOC DATE OF 6/27/19 MILESTONES: SITE WALK: COMPLETE ENGINEERING AND DESIGN: 2/28/19 PROOFING: 3/29/19 PERMITS: 5/17/19 CONSTRUCTION: 6/12/19 SPLICING: 6/21/19 EQUIPMENT INSTALL: 6/25/19 TEST AND TURN SENT OUT: 6/27/19 - RC9254 2/19-3/11: LEC COX came back with a 6/27 Access Install Date - 1A OUTSIDE PLANT (OSP) - MINOR BUILD - FIBER BUILD. Issued AERO CM ticket 505501 to have Carrier Management obtain details of build. 2/5: PON released on 2/2 to Cox - access install date due back to AT&T by 3/8. 1/25: Order rec'd - Melissa confirmed that we're to use COX Communications as LEC
New | PORT UPGRADE to 500M | II547-03-CM | UHG | Melissa Chapman |  |  |  |  | ISR19032839134 VS19056217 |  |  | 2019-04-23 |  |  |  | BKYF.101303 | [13 empty] | 4/23: ORDER COMPLETED Issues on the router side - ticket opened - pending READY TO SCHEDULE - APRIL 21st - Check 3/12: Contract issues being fixed 2/14: Per Christine, Deepak had to go back and get resigned because of an error on the access 2/2: Contracts were signed 2/1
| HOT ORDER 300MB Port/ 500M Access EaAVPN 1000 Base-SX | UVA23-01-IM | UHG | Melissa Chapman |  | 3160 Fairview Park Drive | Falls Church, VA |  | VS18135290 3094-0139 3094-BTSD 3094-BTSF 3094-BTSG | 2018-07-25 |  | 2018-10-26 | 2019-05-01 |  |  | BMEC.968702 | Cox Communications | 49KFGX000995COXC | 2019-04-30 | GRD FLR--TELCO RM--ACCEDIAN PORT #3--TAGGED AND LABEL |  | http://p1npe1c1.vci.att.com:8080/apex/f?p=161:1:4015958160911695 | 3146148 |  | 10.1.91.241 10.1.91.229 | 10.1.91.242 10.1.91.230 | 64800 | 202610 | UHG GLOBAL 150 ECCMA | 5/1: ORDER COMPLETE 4/29: Access completed on Friday. Pending confirmation that VLAN's are complete as well and will push for testing completion and OK to turn up. 4/8-4/22: Access install scheduled for 4/30. 4/1: FOC due back by 5/01 on new access PON. 3/25: POP Collector build has completed - Provisioning has issued access PON 7ES02883853 AND VLAN PON HESV4197802. AERO DES 541619 issued. Pending install date. 3/18: Provisioning Assembler advised that the Collector Build has not yet completed. Reached out to POP Collector team for status. 3/11: Working to verify the POP Collector is complete and next steps. PON below 5ES02888750 showing completed in SOTS. 3/4: Contacted POP Collector group for status of build - they advised that once we get the TDI they will then proceed to get everything wired up in an escalated manner. They expect the colllector circuit to be turned up by 3/31 but are escalating for sooner.Related PON# 5ES02888750 - USO 6803-2751. 2/18-2/25: POP Collector build still showing pending completion - Pending TDI status. 2/11: POP Collector team has gone back to the NACOE group to find out if Cox Communications came back with the TDI and waiting on a reply. Per the Sr. Specialist Network Design Engineer working this collector build, "We are currently at the mercy of the ESP." 1/28-2/4: Pending POP Collector Build - reached out to build team for status - last update indicated targeting end of February for build completion. UPDATE: Cox Communications is scheduled to provide TDI on 2/8/19 1/15-1/21: Pending POP collector build completion (targeting end of Feb.) Once POP Collector build is confirmed complete, the order will bascially start from that point. The PON will be released to the LEC and the clock starts up again. The standard interval for the LEC Cox Communications to provide FOC (provide an install date) is showing 8-business days from the point that we send them the PON. The intervals past that are dependent on the LEC install date, testing completion, etc. 12/26-1/14: We're being provided a status from the POP Collector team that is indicating that the previous update that the collector build was completed was not accurate. I am pushing for status from the team to confirm this 100%, but latest update indicates the current projection is having capacity by the end of February. As soon as this is confirmed, I will advise but we still appears we have more work to be completed on the collector side. 12/10: Engaged AM Jane Tansor for assistance in getting order rolling. Network team did confirm POP Collector completion, however I need to find out if there's anything left to do in order to get the access PON rolling. - UPDATE: DDF Ticket 201812110096 issued 1:12PM for PON release. 12/3: Opened BERT/IOS ticket for missed FOC. POP Collector build is complete, need PON issued and access install date posted ASAP. 11/27: Reached out for status of POP Collector build. 11/5-11/12: RFS for the end of November - reached out to ECollector Link for status. 10/8-11/5: Per POP Collector Team: “We are currently waiting for the LEC to provide TDI, hand off information, so we can move forward. They are past due in providing that to us. We are stuck until that happens. The current projected date of 10/26 will probably not be met. This has been escalated to NACOE, the group responsible for interacting with the LEC, and we will escalate all actions on our side once we get TDI. For now I would estimate RFS for the end of November but that’s just a guess until we get that TDI.” 10/2: RFS planned for end of Oct 10/26. Reached out to ECollector Link for status of build and when we might expect completion. 9/10-9/24: POP Collector build ongoing - RFS Planned date is 10/26. No further work can be done at this time. Once POP collector is complete, we'll request PON be issued for access install. No PON can be issued until POP collector is complete. 8/28-9/4: POP Collector build start date was 6/14 and is still pending TDI and additional work. The RFS PLANNED date is 10/26/18. Ethernet order on hold until POP Collector is complete. 8/14-8/21: There is a POP Collector build that has an avg 120-150 day process. Pending ETA for completion. Order is currently on hold pending POP Collector build completion. - Building Manager - they already have fiber from 8/6: USO's rec'd 7/25: Order rec'd - Pending USO's
New | HOT ORDER 7xT1 AVPN | TX423-04-IM | UHG | Melissa Chapman | UHG- Wellmed | 100 Wilson Drive | Floresville, TX |  | VS18214649 3102-1295-FR 3102-1294 3102-1301 3102-1297 3102-1298 3102-1296 3102-1299 3102-1300 3094-BVDL | 2018-11-16 | ASAP | - | 2019-05-02 |  |  | DHEC.426808.811 DHEC.426808.812 DHEC.426808.813 DHEC.426808.814 DHEC.426808.815 DHEC.426808.816 DHEC.426808.817 | ATT SW w/ Frontier CTF | 13HCGS688243FTNC 13HCGS688240FTNC 13HCGS688256FTNC 13HCGS688271FTNC 13HCGS688246FTNC 13HCGS688244FTNC 13HCGS688412FTNC | 2019-02-08 | IN IT RM ON WEST WALL HOUSING 1 SLOT 1 WEST WALL, HOUSING #2, SLOT 1 IT ROOM ON WEST WALL HOUSING 1 SLOT 4 IT ROOM WEST WALL, HOUSING #1, SLOT 3 IN IT RM ON WEST WALL HOUSING 1 SLOT 2 IT ROOM ON WEST WALL HOUSING 2 SLOT 1 IT ROOM ON WEST ALL HOUSING 2 SLOT 2 |  |  | 3198541 |  | 10.45.10.197 | 10.45.10.198 | 64724 | 202610 | UHG GLOBAL 150 | 5/2: ORDER COMPLETE 4/29: Last T-1 completed on the LEC side - pushing for overall completion of testing on AT&T provisioning side. 4/22: PON GMS02333796 for USO 3102-1300 is targeting completion for 4/29. ESCALATING FOR IMPROVEMENT 4/16: USO 3102-1299 is complete - sent update to Melissa to have end user add 6th T-1. 4/15: For the remaining Floresville T-1’s, the Provisioning Area Manager advised that 3102-1299 will be completed today and 3102-1300 has a LEC date of 4-17 Wednesday. I’ll let you know when I have news to share. 4/9: UPDATE: AREA MGR confirmed they identified CFA mismatches on these yesterday and will push for the redesigns with the design team. 4/8: Reached out to Escalation team for status. Advised we need this done ASAP. 4/1: Per Derek Hunter Esc Mgr - looks like the design team closed their ticket for redesign and tech team can now move forward with testing. Derek pushing for overall completion. 3/26: Escalation to District Escalation Manager DEREK HUNTER to push these to VP level. LEC saying these didn't recieve correct ASR and there were design issues on these last two because of that. 3/18-3/25: Reached out to Lisa Myers for status on final two T-1's. 3/12: Escalated to next level within provisioning (Rick Woodard) for status of final (2) T-1's. 3/11: Reached out to Lisa Myers (Provisioning) for update - two orders still open due to CFA mismatch errors being worked. 3/4: Advised 3102-1301 - DHEC.426808.812 is now complete. Pending completion of last three T-1's. UPDATE: .113 CIRCUIT COMPLETED 3/5 - PENDING FINAL TWO CIRCUITS 2/26: CONFIRMED COMPLETION OF (3) T-1's - PER TECH, just activated the port and noted three of these orders are now UP UP They are: 3102-1294 (DHEC.426808.811) 3102-1296 (DHEC.426808.815) 3102-1298 (DHEC.426808.814) The remaining order (3102-1301) shows an AIS condition and we cannot loop the NIU Looks like in all four cases, Southwestern Bell worked with Frontier, however, we have a Down Down condition on DHEC.426808.812. All four uso’s were found to be completed already; thus this may have just went down. Still checking 2/25: Issued AERI Design 512822 to clear R15 Design Issue on the last T-1 3102-1300. 2/18: Carrier Mgmt engaged on final T-1 3102-1300. Pending completion - Per LEC UNABLE TO LOOP THE S/J. Following up 2/19. - UPDATE: DETERMINED IT'S A BAD CFA SLOT CAUSING ISSUES - PROVISIONING IS WORKING TO RESOLVE. 2/12: UPDATE: CARRIER MANAGEMENT ADVISING LAST TWO T-1'S ARE TARGETING COMPLETION BY COB TOMORROW 2/13. 2/11: At this point Frontier (who is also working with a secondary LEC at this location) has completed (2) T-1’s………..confirmed install on (3) more T-1’s but testing is incomplete……..and no confirmation on the final (2) T-1’s outside of advising AT&T that they’re having either technical issues or unresolved issues with the secondary LEC. We’re escalating to have these all completed as Frontier is past due. I’ll continue to press and hopefully get all of the issues resolved and completed ASAP. 1/7-2/4: Access install on track for 2/8. 12/10-12/26: ICO (Independent Co.) Frontier facilities issues - ICO NOT READY TILL 020819 11/27-12/3: Pending USO's 11/16: Order rec'd
New | 1G Port/ 1G Access EaAVPN 1000Base-SX | NY232-04-IM | UHG | Melissa Chapman |  | 3 Delaware | Lake Success, NY |  | VS19016745 3102-0278 3102-BBCY 3102-BBCX | 2019-01-24 | ASAP | 2019-04-16 |  |  |  | IZEC.563085 | Cablevision Lightpath | 01LUXS253720CLVI | 2019-03-27 | 2ND FLOOR TELCO/DATA ROOM VE PORT #3 |  |  |  | 2 | 10.1.88.221 | 10.1.88.222 | 65124 | 202610 | UHG GLOBAL 150 | 4/30: ORDER COMPLETE - READY FOR TURN UP 4/29: As of this morning, provisioning techs are still working to get this tested and closed out ready for turn up. A ticket was opened internally to have the On Site Work Force (OSWF) complete out the redesign work that was approved and we’re pending completion on their end. Once this is Wired and Office Tested, it should be a quick turnaround to get it complete and over to UHG for use. Follow up is scheduled for early this week so I’ll push to make sure that happens sooner than later. 4/22: Original design had a bad riser. Redesign has been completed. New design is waiting to flow to techs to be rewired and expecting further updates this week. 4/16: Added to the HOT list per Melissa's request. 4/15: Testing issues/delays - Provisioning worked with tech at the NY54 POP and he proved that he has a bad riser cable. He placed barrel loop at 5th floor and they were not able to see the card go green. Referred to their design team to make changes. Awaiting ETA for fix. 4/8: Targeting 4/11 completion date. 4/1: Access install has completed - pending testing completion and the OK to turn up. 3/18-3/25: Cablevision/Lightpath has provided a 3/27 access install date. 3/11: Reached out directly to Kathy O'Brien (Altice USA) for status of access install. Issued AERO Design 527369 on VLAN PON HNSV4168473 (R15) 3/5: Update - FOC missed - escalation to be sent tomorrow 3/6 (miss +2) 2/11-3/4: FOC due back by 3/4 from Cablevision Lightpath. 1/22: Order rec'd - Chris confirmed going with Cablevision. PROCESSED ON 24th
New | SPECIAL BID HOT ORDER 10MB Port/ 50M Access EaAVPN 1000 Base-SX | TX423-02-IM | UHG | Melissa Chapman | UHG- Wellmed | 100 Wilson Drive | Floresville, TX |  | VS18229202 C11397578 3094-0547 3094-BVDY VS19007255 3094-1969 HMS02324111 3094-BVFY 3094-BVFZ | 2018-09-18 |  | 2019-03-18 |  |  |  | BBEC.552680 BBEC.504345 | CLTX GVCS CLEC | [7 empty] | 10.45.10.225 | 10.45.10.226 | 64724 | 202610 | UHG GLOBAL 150 | 2/18-4/1: Working to complete NxT1 because of Ethernet provider issues. ORDER CANCELLED 2/5: Per Chris Cowan: "I was able to have a lengthy conversation with Guadalupe Valley Comm. Unfortunately their Ethernet coverage for Floresville was GREATLY overstated. Please see their build requirements and Monthly charges….The current access addendum has you contracted for a 3 year term at $1965 MRC and a $375 OTC. I turn out that I can now generate a Standard access rate for 50M access with Guadalupe for $861 MRC but the OTC goes up to $4575. After the order is placed you would get hit with the Special construction that would run in the $70,000.00 range. Over three years you would pay $39,744 less than if you had stayed with the original bid of $1965 MRC but that very large Special Construction charge is a killer. Please let Brian and I know if you would like to cancel the order. There would be no cancelation charges because of the Special Construction. UPDATE: GVCS IS REJECTING THIS ORDER. "WE DO NOT HAVE FACILITIES IN THIS LOCATION. WAS BID ON IN ERROR." 1/28: Pending FOC on new order to Guadalupe Valley Comm. New PON HMS02324111 issued on 1/21. VENDOR DOES NOT SERVICE THE POP - Chris working to re-route order to GUADALUPE VALLEY COMM 1/7-1/14: Pending LEC install date - overall due date 3/18 - AERO DES 462784 12/26: Pending USO's 11/13: Per Chris, recd addendum - sending over to UHG 10/30: Pending addendum - 3 yr term agreed to by UHG 9/18-10/22: Order rec'd - Pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX477-01-IM | UHG | Melissa Chapman | Wellmed | 6430 Bandera Rd Suite 98 | San Antonio, TX |  | VS19029467 3094-2306 7MS02329130 3094-BVHQ | 2019-02-04 | 2019-03-18 | 2019-05-03 |  |  |  | BBEC.549038 | ATT SW | 31KRGN653618SW | 2019-05-09 |  |  |  | 3234220 | 50 | 10.45.10.185 | 10.45.10.186 | 64758 | 202610 | UHG GLOBAL 150 | 4/25: CANCELLATION ISSUED IN IOS ON 4/17. 4/22: Construction fiber work set to complete on 4/30. Access install scheduled for 5/9. 3/18-4/15: The Construction & Engineering team advised that fiber work is scheduled to complete on 4/30. Pending an access completion date, which is normally approx a week after fiber work (barring any other site requirement delays, builds, etc.) 3/12: CNR Agenet Roger Baxter confirmed he removed the CNR coding and requested for a Desired due date of 03/15/19 (this is not a firm date) 3/11: Reached out to CNR Agent Roger Baxter (rb130v) for status of access piece and to confirm fiber work dates. Construction dates are showing unchanged. 2/26-3/4: Construction site visit completed on 2/19. The EF offer was accepted. Construction fiber placement and splicing scheuled to complete on 4/30. No access install date yet - LEC advised "PENDING ENTRANCE FACILITY FORM CUSTOMER SIGNATURE REQ'D" 2/19: PON released on 2/18. Pending install date from LEC ATT SW. Overall due date 5/3. 2/11: Per Melissa, access needs to change from 10M to 50M 2/4: Order rec'd
New | 7xT1 AVPN | TX481-01-IM | UHG | Melissa Chapman | Wellmed | 4323 N. Josey Lane | Carrollton, TX |  | 304576170 VS19062664 3102-1564-FR 3102-1559 3102-1562 3102-1566 3102-1561 3102-1560 3102-1563 3102-1565 3102-BBDS | 2019-03-27 | 2019-05-09 | 2019-05-09 | 2019-05-02 |  |  | DHEC.625914.811 DHEC.625914.812 DHEC.625914.813 DHEC.625914.814 DHEC.625914.815 DHEC.625914.816 DHEC.625914.817 | FRONTIER-CTF | 13HCGS105068FTNC 13HCGS105067FTNC 13HCGS105337FTNC 13HCGS105082FTNC 13HCGS105338FTNC 13HCGS105080FTNC 13HCGS105081FTNC | 2019-04-18 | SHELF 5, SLOT 1 SHELF 2, SLOT 4 SHELF 1, SLOT 2 SHELF 2, SLOT 3 SHELF 1, SLOT 3 SHELF 1, SLOT 4 SHELF 2, SLOT 2 |  |  | 3258193 |  | 10.1.92.89 | 10.1.92.90 | 64695 | 202610 | UHG GLOBAL 150 | 5/2: ORDER COMPLETE 4/22-4/29: Access install completed - pending testing completion. Overall DD 5/9 4/9-4/15: Frontier access install scheduled for 4/18 3/27: Order rec'd
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | AZ086-01-IM | UHG | Melissa Chapman | UHG- UHC Medicaid Clinic | 1805 N Scottsdale Rd | Tempe, AZ |  | VS19002229 3094-2230 3094-BVFJ | 2019-12-27 | ASAP | 2019-03-22 | 2019-05-21 |  |  | BBEC.557436 | Qwest | 19KXGS377320MS | 2019-04-09 | 1ST FLOOR TELCO SPACE CLOSE TO NORTH ENTRANCE OF BLDG.BY THE |  |  | 3214952 | 98 | 10.45.10.189 | 10.45.10.190 | 64802 | 202610 | UHG GLOBAL 150 | 5/21: ORDER COMPLETE 5/21: Access install completed yesterday - pending testing completion. 5/20: Per the LEC Centurylink, "NO ACCESS TO THE PREMISE PER THE TECH" - Reached out to Melissa to verify LCON info 5/13: UPDATE FROM THE CENTURYLINK ESCALATION ON MISSED EAD. CO WORK COMPLETED. RESCHEDULED DD IS 5/14. TECH LOADED FOR 5/14. NEXT FOLLOW UP 5/14 5/9: Update from the Centurylink Escalation Team on missed install: They have a design issue. Central Office steps are being loaded for cross connect work. Plant Test Date is 5/9 (today) and rescheduled install date completion is 5/14. Next follow up by end of week. 4/29: PER LEC CENTURYLINK - NEEDS FIBER AND EQPT BUILD. ECD FOR CONSTRUCTION IS 5/3. NEXT FOLLOW UP IS 4/30. 4/22: Carrier Management Tier II engaged - ESCALATED TO CENTURYLINK SERVICE MANAGEMENT. LEC DUE DATE SLIPPED TO 5/14 and Carrier Mgmt has requested WHY and whether date can be improved. Next follow up by 4/23 end of day. 4/1-4/15: Per Scott Fyffe (LEC), the site requirements are scheduled to be finished on 4/22 and Centurylink has scheduled to return to complete their part on 4/23-4/24. 3/18-3/25: Reached out to CNR agent to confirm 4/9 date still on track. NEED TO CONFIRM FROM UHG ALL SITE REQUIREMENTS ARE COMPLETE 1/15-3/18: LEC Qwest has a build - 1A OUTSIDE PLANT (OSP) - MINOR BUILD - access install scheduled for 4/9. 1/8: Pending an install date from Qwest. 12/27: Order rec'd - pending USO's
New | 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX501-01-IM | UHG | Melissa Chapman |  | 1701 S Cage, Suite 16-21 | Pharr, TX |  | VS19046793 3102-0288 3102-BBDH | 2019-03-12 | 2019-05-31 | 2019-05-22 | 2019-05-20 |  |  | BBEC.528167 | ATT SW | 38KRGN613828SW | 2019-05-20 | 1ST SOUTH SIDE SOUTH END OF BLDG. |  |  | 3246947 | 50 | 10.1.94.221 | 10.1.94.222 | 64923 | 202610 | UHG GLOBAL 150 | 5/21: ORDER COMPLETE 5/20: Access install showing due to complete by COB today. 5/9-5/13: Access install was moved to 5/20. LEC advised SITE REQUIRES PATH/PWR/GRD/SPACE - need to verify 100% this work is done as LEC appears to still have issues with the power OR do not have confirmation it has completed from the end user. 4/29: Construction advised that fiber work completed on 4/24. Reached out to CNR Agent Sharita Bonds to see if she can have CNR coding removed and request LEC redispatch sooner than the 5/7 posted date. Also, LEC order not showing in Greta....requested Sharita's help in reviewing that for issues. 4/22: SITE REQUIRES PATH/PWR/GRD/SPACE - Advised Melissa that LEC jep'd the order CNR Customer Not Ready. EUCR 4/1-4/15: Access install scheduled for 5/7. 3/12: Order rec'd
New | 200MB Port/ 300M Access EaAVPN 1000 Base-SX | AZ007-05-IM | UHG | Melissa Chapman |  | 9040 South Rita Road | Tucson, AZ |  | VS18172312 3094-0988 3094-BTXL | 2018-08-27 | ASAP | 2019-03-12 | 2019-05-29 |  |  | BDEC.992952 | Qwest | 19KXGS356107MS | 2019-01-24 | 2ND FLOOR IT RR 1 BOTTOM SHELF OPTICAL PORT 1 |  |  |  | 51 | 10.45.10.241 | 10.45.10.242 | 64882 | 202610 | UHG GLOBAL 150 | 6/3: ORDER COMPLETE 5/28: PER LEC: ORDER DEPENDENT ON COMPLETION OF NEW SWITCH ORDER. ESCALATED TO BRING IN THE ECD FROM WHAT IS NOW SHOWING AS 6/20. 5/20: Carrier Mgmt Tier 2 is engaged - they reached out last Thur/Fri to Centurylink and they were advised that Centurylink needs to complete a new switch order before they can complete access. Tier 2 advised this is ridiculous and that they had 2-months to get this work done. Tier 2 requested VP Level Escalation with follow up by close of business 5/21. 5/13: Expecting follow up today by COB for status of install that was to have taken place on Friday 5/10. UPDATE: TIER 2 CARRIER MANAGEMENT ENGAGED - ESCALATED TO VALERIE/CTL FOR STATUS, DID THIS ONE INSTALL 5/10 AS EXPECTED. PLEASE PROVIDE DEMARC. PENDING RESPONSE. IF NO RESPONSE TODAY, F/U 5/14. 5/9: UPDATE FROM VALERIE ESTROGA/CTL SERVICE MANAGER - TECH ADVISED YESTERDAY AFTERNOON THAT THE LOCAL CONTACT, ANTHONY, HAS SET UP AN ACCESS TIME OF 05/10 AT 1:00PM. WORKING TO COMPLETE THE INSTALL FRIDAY. NEXT FOLLOW UP 5/13 4/22-4/29: PENDING UPDATE FROM CL - Gene (Centurylink Tech) advised that the customer needs additional 200ft of cabling between 2nd Floor and Suite. Customer agreed to Centurylink completing requirements. Customer advised work needs to be done after hours so as not to affect production. Customer would like a Friday evening after 7pm to begin work. Pending confirmation from LEC. 4/15: Reached out to CNR AGENT Roger Baxter to provide update on new date from the LEC. 4/8: Follow up with Centurylink to request FOC date. 4/4: Received notification that site is ready. 4/1: Per Betty (Qwest), they are awaiting completion of clear path for the NID, completion of site requirements. Hoping to be onsite today. 3/25: Need confirmation that site requirements are complete - LEC Qwest ready to move forward. 3/11-3/18: LEC Qwest advised they're awaiting a clear path from the customer to complete the install of the NID. Reached out to Melissa for an update. SITE REQ NOT COMPLETED YET - 3/4: Added order to SDM WWR Reeves Sheet for order completion. Pending TTU. CTA SCHEDULED FOR 2/27 - SEE WHAT THIS BRINGS US AND ESCALATE IF NOT COMPLETED BY COB 2/25: LEC access is showing R84 completed - pending test completion and the OK to turn up. - PLEASE CHECK CIRCUIT - ICORE/AISE SHOWING COMPLETE - SOTS ORDERS SHOWING PENDING. ATT TECH CALLED CTL AND THEY ADVISED NOT YET COMPLETE EVEN THOUGH ORDER SHOWS R84 COMPLETION ON ACCESS. 2/18: Chris provided site requirements doc to UHG. There is a reference to Inner duct requirement that would be customer responsibility. The Inner Duct will require pull string as well. Jake at Century Link looked the order up and confirmed that the safety review was just recently completed. Completion of the inner duct would clear the way for CL to get back out to the site to complete and close the job out. 2/11: C/NR DATED 1/14 IS FOR NO ACCESS TO THE PREMISE. PER CTL, THIS CUSTOMER REQUIRES A SAFETY COURSE BEFORE ANY WORK CAN BE DONE ON SITE. MEETING WITH LCON WAS SCHEDULED WITH CENTURYLINK'S CONTRACTORS FOR 1/14, LCON NEVER SHOWED. CENTURYLINK SENT NO ACCESS C/NR ACCORDINGLY. DD SUP NEEDED AND LCON MUST ADMINISTER THE SAFETY CLASS FOR THE LEC TO OBTAIN ACCESS. 2/4: Requested ordering supp with new contacts provided by Melissa - DARRIN Klopp, 520-918-9876, darrin.klopp@optum.com or ANTHONY Cook, 520-918-8930, Anthony.Cook@optum.com 2/4: “CNR FOR NO ACCESS TO THE PREMISE. PER LEC CTL, THIS CUSTOMER REQUIRES A SAFETY COURSE BEFORE ANY WORK CAN BE DONE ON SITE. MEETING WITH LCON WAS SCHEDULED WITH CENTURYLINK'S CONTRACTORS BACK ON 1/14, LCON NEVER SHOWED. CENTURYLINK SENT NO ACCESS CNR ACCORDINGLY. DUE DATE SUP NEEDED AND LCON MUST ADMINISTER THE SAFETY CLASS FOR THE LEC TO OBTAIN ACCESS.” Are you able to check with the end user to see if they can arrange this safety class? 1/28: Sent BERT/IOS ticket for escalation of missed Qwest access install date (1/24.) 1/21: PER LEC: SITE ACCESS ISSUES SITE CONTACT ISSUES. Pending update to see if dates will be changed. 10/29-1/14: Qwest access install scheduled for 1/24/2019. 1B OUTSIDE PLANT (OSP) - MAJOR BUILD 9/25-10/22: Qwest Access - pending install date. 8/27: Order rec'd - Pending USO's
New | 30MB Port/ 50M Access EaAVPN 1000Base-SX | PA138-01-IM | UHG | Melissa Chapman | Optum | 1818 Market Street | Philadelphia, PA |  | VS19041799 3094-2513 3094-BVKK 3094-BVKL VS19016718 3102-0281 3102-BBCZ 3102-BBDB | 2019-01-23 | ASAP | 2019-05-23 | 2019-05-24 |  |  | BBEC.531772 | Level 3 Communications | BBWW34338LVLC | 2019-04-26 | CISCO 920 PORT 14. CAB #2 RU #27. |  |  | 3244091 | 100 | 10.1.89.13 10.1.95.9 | 10.1.89.14 10.1.95.10 | 64529 | 202610 | UHG GLOBAL 150 | 5/28: ORDER COMPLETE 5/20: Per LEC Level3, PROJECTED ECD RANGING FROM 6/6 - 6/7 COB. More updates are expected by close of business 5/22. 5/9-5/13: LEC PROVIDED THE FOLLOWING STEPS STILL NEEDED FOR ORDER COMPLETION: (1) IP BUILD TEAM TO FINALIZE CKT DESIGN & FWD TO FIELD OPS (F-OPS) TEAM; (2) F-OPS TEAM TO DISPATCH & INSTALL CIRCUIT AT CUSTOMER PREM, & RELAY ORDER BACK TO ACTIVATIONS TEAM; & (3) ACTIVATIONS TEAM TO COMPLETE END-TO-END TESTING & REFER ORDER BACK TO AT&T FOR TESTING. LEC EXPRESSED THEY'LL WORK HARD TO COMPRESS DATES ONCE ISSUES RESOLVED. MORE DETAIL ARE ANTICIPATED ON 5/13 COB, BUT URGENTLY DRIVING FOR MORE INFO TO BE PROVIDED SOONER (NO GUARANTEES). 4/29: Carrier Management has escalated this back to LEC Centurylink/Level3 Executive Mgmt Team. LEC indicating their IP Build Team notified of internal error issue. LEC provided steps to completion: (1) IP BUILD TEAM TO FINALIZE CKT DESIGN & FWD TO FIELD OPS (F-OPS) TEAM; (2) F-OPS TEAM TO DISPATCH & INSTALL CKT AT CSTR PREM, & RELAY ORD BCK TO ACTIVATIONS TEAM; & (3) ACTIVATIONS TEAM TO COMP END-TO-END TST'NG & REFER ORD BCK TO ATT FOR TST'NG. ONCE IP BUILD ISSUE CLR'D, FOC RELEASE WITHIN 2-3 BUS. DAYS (I.E. 5/7 - 5/8 COB), BUT THEY'LL WRK TO COMPRESS ONCE ISSUE RESOLVED. LEC also noted that due to the internal issue, they're unable to provided an overall estimated completion date. More details are anticipated on 5/6 by COB, but driving for more info to be provided sooner. 4/22: LEC install scheduled for 4/26. 3/18-4/15: FOC is showing due back from Level3 by no later than 4/16. Pending install date at this time. 3/11: New USO's rec'd - pending install date from Level 3. 3/4: ORDER BEING REISSUED WITH LEVEL3 AS LEC. HITS ticket issued to cancel existing order 3102-0281. 2/19-2/25: Time Warner (LEC) issue - TW indicates they cannot serve the POP on our order. PHLAPASL. Working to find resolution, POP change, etc. 2/11: Pending install date - DDF ticket issued for missed FOD. 1/23: Order rec'd - Melissa requested Time Warner for access - PROCESSED on 28th
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | AZ047-04-IM | UHG | Melissa Chapman | Optum | 1669 West Ina Road | Tucson, AZ |  | 304580184 VS19063127 3102-0363 3102-BBDV | 2019-03-28 | 2019-07-05 | 2019-07-05 | 2019-06-03 |  |  | BBEC.511579 | Qwest | 19KXGS408088MS | 2019-05-06 | FIRST FLOOR MAIN IT WALL MOUNTED 3916.. PORT 4 MULTI MODE OP |  |  |  |  | 10.1.89.121 | 10.1.89.122 | 64525 | 202610 | UHG GLOBAL 150 | 5/20-6/3: Pending testing completion and OK to turn up. 5/13: Engineering, Design and Wiring completed this morning. Pending overall testing completion and OK to turn up. FUTURE DUE ORDER 7/4/2019 5/9: Access install completed - DEMARC FIRST FLOOR MAIN IT WALL MOUNTED 3916.. PORT 4 MULTI MODE OP. Pending testing completion and the OK to turn up. 4/30: Qwest access install scheduled for 5/6. 4/29: Order loaded into SOTS on 4/23. Pending FOC from Qwest - due back by 5/28. 4/22: ADVISED CLYDE TO REISSUE - NOT LOADED IN SOTS - 4/23 UPDATE: Ordering has checked the order and found that it is still not loaded in SOTS. They have raised a SOA ticket # 568069 to load order in SOTS. Follow up on: 04/26/2019. 4/9: USO still pending loading into systems. No dates yet. 4/5: Pending USO's - 1-AD7ZLRC 3/28: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | FL413-01-IM | UHG | Melissa Chapman |  | 3000 Bayport Drive | Tampa, FL |  | VS19079766 C11410978 3094-2667 3094-BVNR | 2019-04-25 | 2019-07-18 | 2019-07-18 | 2019-05-31 |  |  | BBEC.552126 | Level 3 Communications | BBXK18342LVLC | 2019-05-31 | 9th FLOOR, ELECTRICAL ROOM, WALL MOUNTED UNIT #2, EQUIP: CISCO 3600 |  |  |  | 100 | 10.1.89.61 | 10.1.89.62 | 64708 | 202610 | UHG GLOBAL 150 | 6/3: ORDER COMPLETE 5/9-5/28: Pending install date from LEC Level3 Communications.FOC due back by 6/6 4/25: Order rec'd
New | 50M Port/ 50M Access EaAVPN 1000Base-SX | WA112-01-IM | UHG | Melissa Chapman | BriovaRx | 8107 W Bostian Rd 8025 A West Bostian Rd | Woodinville, WA |  | VS19073876 3094-0402 3094-BVMW 3094-BVMX | 2019-04-01 | 2019-04-29 | 2019-07-18 |  |  |  | BBEC.575829 | Frontier | [7 empty] | 10.1.88.173 | 10.1.88.174 | 64674 | 202610 | UHG GLOBAL 150 | 5/29: City changed address - portfolio build will delay - will cancel and reissue in next few weeks. CANCEL THIS ONE. 5/13-5/28: PON showing FOC due back by 6/13. Pending install date. 5/9: Issued AERO Des Ticket 584228. Pending update on PON and possible construction charges. 4/29: BUILD IDENTIFIED - A FACILITY ISSUE HAS BEEN IDENTIFIED ON YOUR PON AND SPECIAL CONSTRUCTION CHARGES MAY APPLY. YOUR ACCOUNT MANAGER WILL BE IN TOUCH WITH ADDITIONAL DETAILS. 4/23: USO's rec'd - LEC is Frontier - pending an install date. POSSIBLE BUILD PER MELISSA 4/16-4/22: Pending USO's - need to check with Chris/Clyde that this was submitted with new address. 4/10: Melissa provided address change to 8025 A West Bostian Rd 4/1: Order rec'd - Per Melissa, this is a new build so it likely will need to go to special bid.
New | 30M Port/ 50M Access EaAVPN 1000Base-LX | KY003-04-IM | UHG | Melissa Chapman | Optum | 401 S Fourth Street 17th Floor MDF Room | Louisville, KY |  | VS19091526 3102-0490 3102-BBFZ | 2019-05-10 | 2019-08-09 | 2019-08-09 |  |  |  | BBEC.598571 | ATT SE | K1KRGN402287SC | 2019-06-04 | Demarc Lc: 17 UTILTY WALL UNIT 1 PORT 8 |  |  |  | 50 | 10.1.88.93 | 10.1.88.94 | 65224 | 202610 | UHG GLOBAL 150 | 6/10: CNR - PER LEC, ORDER DELAYED DUE TO NO ACCESS. LCON ON VACATION UNTIL 6/10/19 PER OUTSIDE TECH LOG NOTES 6/3: Access install due tomorrow 6/4. 5/28: Pending install date - FOC due back by 6/17 5/10: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | UPA02-05-IM | UHG | Melissa Chapman | Optum | 401 N Broad Street / Suite 600 | Philadelphia, PA |  | VS19090302 3102-0448 3102-BBFR | 2019-05-14 | 2019-07-26 | 2019-07-26 | 2019-06-06 |  |  | BBEC.558013 | ASE LNS | PAKRGN100632TPM | 2019-06-03 | 6TH FLOOR, PORT#8 CUSTOMER PLUGS INTO 11.08.0B PROVIDER EDGE PNL10 |  |  |  | 50 | 10.1.88.85 | 10.1.88.86 | 64732 | 202610 | UHG GLOBAL 150 | 6/7: ORDER COMPLETE 5/28-6/3: LNS access install scheduled for 6/3 5/15: Order rec'd
New | HOT ORDER 1G Port/ 1G Access EaAVPN 1000Base-LX | AZ731-01-IJ | UHG | John Sergot | UHG- Avella | 615 N 48th StIron Mountain Data Center | Phoenix, AZ |  | VS19056715 3102-0338 3102-BBDP CLO AZS000876001 | 2019-03-21 | 2019-07-05 | 2019-07-05 | 2019-06-12 |  |  | IZEC.591245 | ADE LNS | AZKFGS100062TPM | 2019-05-22 | CAGE 218 RR 010002.02 PNL 3 JACKS 39 40 TO MMR MDF RR 400.02 U30-33 JACKS 39/40 SM SC. | 1000 Base-LX |  | 3253912 | 2 | 10.1.94.97 | 10.1.94.98 | 64915 | 202610 | UHG GLOBAL 150 | 6/12: ORDER COMPLETE 6/10: ACCESS INSTALL IS COMPLETE - PENDING TESTING COMPLETION AND OK TO TURN UP 6/3: Requested escalation on AERO 596096 - still no update from LNS on access install miss - UPDATE: CONFIRMED ACCESS INSTALL IS COMPLETE - PENDING TESTING COMPLETION - DEMARC PROVIDED. 5/28: Did not receive completion from LNS. Carrier Management engaged (AERO CM TICKET 596096) 5/9-5/20: Received a 5/22 access install date from LNS. 4/30: Added to HOT list - customer needs this by mid-June 4/29: Pending access install date from the LEC - FOC due back 5/15. 4/23: PON released 4/22: Pending release of the PON to the LEC ADE LNS - due to release tomorrow 4/23. 4/15: USO still pending loading into systems. No dates yet. 4/4: Awaiting for resolution on Fflow ticket# 8177139. Please expect follow up on: 04/09/2019. Thank you.(1st Level Escalation contact:g31791) 4/1: AISE shows the following error: ICORE Error: INVALID USO, already used on another order [ projectName - FR00156845 , USO Number - N3102-0338]. Reached out to ordering to correct. 3/21: Order rec'd
New | 50MB Port/ 100M Access EaAVPN 1000 Base-SX | FL350-01-IM | UHG | Melissa Chapman | UHG- Briova | 5700 Dot Com Court STE 1000 | Orlando (Oviedo), FL |  | HALO Ord 303655100 VS18175449 3094-1050 HSS03592425 3102-BBBK | 2018-09-18 | 2018-12-11 | 2018-12-11 | 2019-06-12 |  |  | IUEC.745837 | ATT SE | 58KRGN703086SB | 2019-06-12 | 1ST FLR SERVER RM, WALL MT D CIENA , PORT-2, TAGGED | 1000 BASE SX |  | 3170765 | 50 | 10.1.90.225 | 10.1.90.226 | 64738 | 202610 | UHG GLOBAL 150 | 6/12: ORDER COMPLETE 6/10: Access install scheduled for 6/12 6/3: New PON HSS03592425 issued 5/31. Pending install date now that power is ready. 5/29: Per Melissa, Power will be ready on 6/3. 4/29-5/28: Pending completion of permanant power at the site - targeting mid-May. STILL PENDING POWER 5/28 4/22: Still showing power issues - need to verify the the gnd and Power outlet are placed - following up regarding TEMPORARY POWER that we were advised was in place. Reached out to Construction team to see what the issue is with using Temp Power. - PERM POWER MID MAY - 4/8-4/15: Access install scheduled for 4/19. 4/1: Per HITS ticket DDF ticket raised as to sup the PON since the site is ready. Expected follow up on: 04/03/2019. 3/28: Temporary power installed - issued HITS ticket to supp PON and request redispatch. 3/18-3/25: Per UHG, POWER NOT UNTIL APRIL 15 3/12: Construction & Engineering is showing fiber work completed as of 3/8. We have a 4/3 install date for access and I will issue a ticket (DDF) request to see if this can be improved. 1/25-3/11: Per site, ATT was on site late last week and did a site survey, permanent power is scheduled for 3/11/19. 12/3-1/21: Pending confirmation permanent power is available. Once confirmed order will be supp'd to request install - and confirmation LCON is updated to Jim Irby. UPDATE: PER MELISSA, They are saying power wont’ be in place until Jan 15th 2019 - 1/15: Date pushed out per Melissa - possible mid-Feb. 11/27: Advised CNR agent BEDGOOD, WANETHIA that site telco demarc is ready. Pending update from UHG on whether permanant power is available. 11/12: Escalated to 2nd Level for update on access install date. 10/31: Per Melissa, construction has started on the site. It’s renovations. Please make sure the LCON is the following: Jim Irby 321-288-0922 10/29-11/5: Escalated to CNR Agent Tinicha Freeman (via Q) for status - last update was construction would begin around 10/15 but no additional notes. 10/22: Pending update from the field on new construction - no fiber or access install dates have been set yet as order is on hold pending update on construction. 10/15: Per the BIC: "This is new construction which wont begin until 10/15.". 10/2-10/9: Pending access install date from LEC ATT SE (NOTE: SITE VISIT - BLDG NOT READY PER LEC) 9/18: Order rec'd - Pending USO's
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | TX435-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 3016 Guadalupe St | Austin, TX |  | VS19098342 3102-0709 3102-BBGP | 2019-05-22 | 2019-08-21 | 2019-08-21 | 2019-06-17 |  |  | IUEC.941156 | ATT SW | 32KRGN653659SW | 2019-06-17 | 1ST FLOOR MPOE CAGE MOPE CAGE IN GARAGE PORT 3 | 1000 BASE SX |  |  | 50 | 10.1.88.133 | 10.1.88.134 | 64577 | 202610 | UHG GLOBAL 150 | 6/17: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 6/11: Access install scheduled for 6/17 5/22: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000Base-SX | CA382-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 2288 Auburn Blvd., Ste 102 | Sacramento, CA |  | 304816218 VS19089953 3102-0445 7WS03779087 3102-BBFQ | 2019-05-15 | 2019-08-07 | 2019-08-07 | 2019-06-20 |  |  | BKEC.925822 | ATT West | 18KRGN520536PT | 2019-06-20 | 1ST FLR SERVER RM HANDOFF TRAY 1 N/JACKS 2-3 |  |  |  |  | 10.1.89.249 | 10.1.89.250 | 64516 | 202610 | UHG GLOBAL 150 | 6/20: ORDER COMPLETE 6/17: LEC ATT West provided a 6/20 install date. 6/10: Site visit delayed but scheduled and completed - was CNR - LEFT VMAIL/EMAIL FOR LCON, NO RESPONSE. Pending date for fiber work. 5/21-6/3: FOC due back by 6/13 5/15: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000Base-SX | FL369-02-IM | UHG | Melissa Chapman | United Healthcare- Avella | 100 Technology Park | Lake Mary, FL |  | VS19091525 3102-0489 3102-BBGB | 2019-05-20 | 2019-08-09 | 2019-08-09 | 2019-06-24 |  |  | BREC.705823 | ATT SE | 58KRGN703103SB | 2019-06-24 | 1 SERVER RM TELCO BKBRD SLIMBOX MM FIBER |  |  |  | 50 | 10.1.89.229 | 10.1.89.230 | 65130 | 202610 | UHG GLOBAL 150 | ORDER COMPLETE 6/24: Access install completed - pending testing completion and the OK to turn up. 6/17: ATT SE access install scheduled for 6/24. 6/3: HITS ticket issued. 5/28: USO's rec'd - pending loading in all systems. 5/20: Order rec'd
New | 100M Port/ 100M Access EaAVPN 1000Base-LX | MI073-01-IM | UHG | Melissa Chapman |  | 3000 Town Center | Southfield, MI |  | VS19101096 3102-0708 3102-BBGN | 2019-05-28 | 2019-08-26 | 2019-08-26 |  |  |  | IUEC.862918 | ATT MW | KRGN214694MB | 2019-06-20 | 14TH FLR,TELCO CLOS,WALL MOUNT SLIM BOX 1,2 |  |  |  |  | 10.1.88.69 | 10.1.88.70 | 65263 | 202610 | UHG GLOBAL 150 | 6/24: ORDER COMPLETE 6/17: Access install scheduled for 6/20. 6/11: Pending an install date from ATT MW 5/20: Order rec'd
New | HOT ORDER 2xT1 AVPN | NC057-03-IJ | UHG | John Sergot |  | 2485 Hemby Lane | Greenville, NC |  | VS19059265 3102-0493-FR 3102-0494 3102-0492 3102-BBDR | 2019-03-21 | 2019-05-10 | 2019-05-10 | 2019-06-25 |  |  | DHEC.335688.811 DHEC.335688.812 | Centurylink | 58HCGS340131CRLN 58HCGS340130CRLN | 2019-06-25 | FIRST FLOOR TELCO/DATA ROOM LEFT SIDE OF THE ROOM LOT 2 OF |  |  | 3256078 |  | 10.1.95.121 | 10.1.95.122 | 65223 | 202610 | UHG GLOBAL 150 | 6/25: ORDER COMPLETE 6/24: Access install completed ahead of schedule. Pending testing completion. 6/17: Access install scheduled for 6/25. 6/11: CNR Agent Kirsten Bass advised new PON#'s TSS03594443 and TSS03594445 were issued. This will prompt LEC to provide redispatch date. 6/7: Added to Hot Order tab. Reached out to CNR AGENT Kirsten Bass for supp. 6/3: No update - reached out to Rose Crawford (LSSD Area Mgr) to see if we can get a resource on this as we need a redispatch date. UPDATE: PER ROSE, ISSUED AERO DESIGN 604499 and 604501 REQUESTING NEW PON's AS ORIGINAL PON'S TIMED OUT AND WERE CANCELLED DUE TO CNR. 5/28: HITS TICKET ISSUED FOR DISPATCH. Followed up with HALO team for status of redispatch request. 5/13-5/20: Reached out to Melissa to confirm LCON info and request OK to redispatch. - UPDATE: LEC can visit the site on 5/27 or after. Two contacts for you for Greenville: • First: David Bray, superintendent: 336-520-4717 • Second: Nathan Mazzuca, landlord representative: 252-214-2974 They can always call Lisa if they can’t reach either and shewill help track someone down. Lisa McNamara T 952.202.0242 C 773.263.5992 5/9: ORDER HELD DUE TO NO ACCESS TO CUSTOMER PREMISE - NEED TO CONFIRM IF SITE WILL ALLOW ACCESS AND THEN WILL NEED TO SUPP AND REQUEST NEW DATE. 4/22-4/29: LEC rescheduled install for 5/6. 4/15: May have to request new date - LEC tried to go out early and rejected the order back. PER LEC: NO ACCESS TO END USER PREMISE -- NO ACCESS TO PREMISES - SUP DUE DATE 4/8: Access install scheduled for 4/16. 3/21: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000Base-SX | FL411-01-IM | UHG | Melissa Chapman | Wellmed | 306 E Oak St. | Kissimmee, FL |  | 304713198 VS19079855 3102-0436 3102-BBFL 3102-BBFK | 2019-04-29 | 2019-07-18 | 2019-07-18 | 2019-07-15 |  |  | BBEC.552558 | Embarq | 25KXGS411141UFLG | 2019-06-26 | 1ST FLOOR, TELCO ROOM, WALL MOUNTED, NOT EXTENDE T/L, RAD2 | OPT. - 50 MM |  |  | 100 | 10.1.93.217 | 10.1.93.218 | 64870 | 202610 | UHG GLOBAL 150 | 7/17: ORDER COMPLETE 7/8: VLAN PON HSSV4253553 incomplete - issued Aero Design ticket 645560 to push that PON. UPDATE: PON RESUBMITTED TO LEC ON MONDAY 7/8 - THERE WAS A VLAN DISCREPANCY NEEDING UPDATE. 7/1: Access install completed - pending testing completion and the OK to turn up. 6/10-6/24: Access install scheduled for 6/26. 6/5: Moved to HOT list. 6/3: UPDATE FROM CENTURYLINK. WE HAVE BEEN HAVING LCON ISSUES, HENCE THE CNR SENT. I HAVE ESCALATED THIS OVER TO THE SPOC(SITE SURVEY SCHEDULER) TO VERIFY LCON ISSUES THEY ARE RUNNING INTO FOR THE SITE SURVEY. NEXT FU 6/4. 5/28: Per Carrier Management (5/24), Per the LEC Embarq PM, they were finally able to arrange a site visit with the LCON for last week (5/24.) Once they gather the info they will be able to FOC the order. Next follow up by COB 5/29. Carrier Management remains engaged. 5/20: Per LEC: SUPI: N RCODE: 1S=BUILDING NOT READY, CUSTOMER WILL ADVISE RDET: CUSTOMER NOT READY - ADDL INFORMATION TO FOLLOW 5/9-5/13 Pending install date from LEC EMBARQ. 4/29: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | AZ046-04-IM | UHG | Melissa Chapman | Optum | 695 Pecan Tree Lane | Green Valley, AZ |  | 304580123 VS19063122 3102-0408 3102-BBFB 3102-BBFC | 2019-03-28 | 2019-07-03 | 2019-07-03 |  |  |  | BBEC.511738 | Cox Communications | [7 empty] | 10.1.92.153 | 10.1.92.154 | 64799 | 202610 | UHG GLOBAL 150 | CANCELLED AND REISSUED - CUSTOMER DOES NOT ACCEPT CHARGES SO ORDER WAS REISSUED 6/24-7/17: NOTE ONE TIME SPECIAL CONSTRUCTION CHARGE OF $51,900 NRC WOULD APPLY. SUP ORDER AND NOTE CHARGES ARE APPROVED IF YOU WANT TO PROCEED. MRC WOULD BE $500 6/10-6/17: SUPPED THE PON WITH INFORMATION CSR WOULD LIKE TO KNOW THE CHARGES - Pending Special Construction quote. 5/28-6/3: Carrier Management Tier 1 engaged. Ticket# 594802. Past due FOC for PON HWS03768771. They have reached out to Cox Communications end of last week but no answer. Reps busy. Follow up by COB 5/28. Pending Special Construction quote. 5/20: Pending Special Construction quote. 5/9-5/13: Per Chris Cowan: Confirmed that this order is getting processed to possibly or likely flow through the Special Construction team. We’ve been told to expect SC charges to be applied. NOTE: UHG saw something similar with their Verizon order as well. 4/29: ORDER ISSUES PER COX COMMUNICATIONS - SENT TO CHRIS COWAN FOR REVIEW. "THE ORDER FALLS OUTSIDE CNN (CARRIER NEAR NET) PARAMETERS AND WILL NEED TO BE EITHER CANCELED OR TO REACH OUT THROUGH PROPER CHANNELS TO OBTAIN AN ICB QUOTE FOR COSTS TO INSTALL THE SERVICE" LOOKS LIKE THIS MAY NEED TO GO BACK TO ORDERING UNLESS CUSTOMER IS WILLING TO PAY FOR COST OF INSTALL. 4/9-4/23: Pending an access install date. Due back by 5/15. 3/28: Order rec'd - AVOID QUEST
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | OH067-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 4830 Knightsbridge Blvd. | Columbus, OH |  | VS19101099 3102-0579 3102-BBGK | 2019-05-21 | 2019-08-26 | 2019-08-26 | 2019-07-16 |  |  | BBEC.527325 | ATT MW | 94KRGN202528OB | 2019-07-16 | PATCH PANEL POSITION 12 IN 1F MAIN ROOM INSIDE SUITE A |  |  |  | 50 | 10.1.88.145 | 10.1.88.146 | 64647 | 202610 | UHG GLOBAL 150 | 7/17: Access install completed ahead of schedule - order is now complete plug and play. 7/8: New install date: 7/18. 7/1: Pending updated access install date - Per LEC --> SPOKE WITH EDDIE MARTIN ABOUT THIS ORDER. WE WILL HAVE TO CANCEL THIS ORDER AND REISSUE IF THE CUSTOMER WANTS IT FROM THEIR SUITE. ALSO CAN'T PUT IT ON THE EXISTING CIRCUIT BECAUSE IT BELONGS TO ANOTHER BUSINESS. CUSTOMER HAD A WALK THROUGH AND AGREED TO HAVE DEMARC AT MPOE WITH THE EXTENTION BEING THEIR RESPONSIBILITY. --> issued DDF ticket 201907020027 on 7/2 for new install date. 6/24: Access install delayed - ORDER DESIGNED OUT OF WRONG NTE PER LOG NOTES FROM OUTSIDE TECH. ORDER WILL GO BACK AND GET CORRECTED AND THEN DESIGN WILL BE ISSUED TO CORRECT. NO ETA 6/11-6/17: Access install scheduled for 6/20 5/21: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | FL417-01-IM | UHG | Melissa Chapman |  | 12854 Kenan Drive | Jacksonville, FL |  | VS19099817 3102-0713 3102-BBGQ | 2019-05-23 | 2019-08-23 | 2019-08-23 | 2019-07-15 |  |  | IUEC.705442 | ATT SE | 52KRGN703022SB | 2019-07-15 | 1ST MAUIN TELC CIENA 3930 PPORT8 MM |  |  |  | 51 | 10.1.89.249 | 10.1.89.250 | 64883 | 202610 | UHG GLOBAL 150 | 7/17: Order complete - ready for turn up plug and play 7/8: New install date: 7/15. 7/2: Reached out to Victoria (CNR Agent - VD526B) to supp order and have LEC install to MDF. 6/24-7/1: Install delayed - CUSTOMER SITE NOT READY PER LOG NOTES FROM OUTSIDE TECH CUSTOMER HAS NOT MOVED IN YET 6/11-6/17: Access install scheduled for 6/19 5/23: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | CA015-05-IM | UHG | Melissa Chapman | UHG | 3131 Camino Del Rio N | San Diego, CA |  | VS19113885 3102-0776 3102-BBHH | 2019-06-17 | 2019-09-17 | 2019-09-17 | 2019-07-13 |  |  | IUEC.813335 | ATT West | 19KRGN533035PT | 2019-07-12 | 1ST N/A TO ATT DEMARK PANEL 1 X PORTS AND 2 |  |  |  | 50 | 10.1.89.57 | 10.1.89.58 | 65087 | 202610 | UHG GLOBAL 150 | 7/13: ORDER COMPLETE 7/8: Access install scheduled for 7/12. 7/1: Pending install date from ATT West. 6/17: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX451-01-IM | UHG | Melissa Chapman | Optum | 3250 West Pheasant Run Rd 2424 West Pleasant Run Rd | Lancaster, TX |  | 304580125 VS19063130 3102-0392 7MS02339139 3102-BBDX | 2019-03-28 | 2019-06-24 | 2019-06-24 | 2019-07-18 |  |  | BBEC.511665 | ATT SW | 14KRGN885567SW | 2019-06-19 | FIRST FLOO REAR WALL CKT IS INSTALLED REAR WALL OF PREM |  |  |  | 50 | 10.1.93.125 | 10.1.93.126 | 64739 | 202610 | UHG GLOBAL 150 | 7/18: ORDER COMPLETE 7/17: Fiber work completed on 7/12 ahead of schedule. Requested that PON be supp'd (DDF ticket) for improved install date. 7/8: Construction targeting 8/23 for completion of fiber infrastructure work. 7/2: Sent Melissa the Construction letter with site requirements details and contact info for the Engineer Michael Martin. 7/1: Per AERO CM ticket: CUSTOMER PREM READY ECD 8/23. DELAY-CUSTOMER. WILL FOLLOW UP 8/27 - Power issues unresolved. 6/24: Access install date of 6/19 was missed as expected. The notes from the LEC indicate power issues are unresolved. 6/17: Access install is showing scheduled for 6/19, however there are notes indicating power issues continue to be an issue at the site. Please verify whether power/ground/backboard, etc have been completed. 6/10: Possible delays in Lancaster - 6/4/19 Per Eric Jungman add CNR, building has no power & we have been pending since 5/21 5/13-6/3: Construction fiber work scheduled to complete by 6/10. Access install scheduled for 6/19. 4/15-5/9: Construction & Engineering provided a 6/10 fiber placement and splicing completion date. Pending access install date (normally about a week after fiber dates.) -- 4/15 UPDATE: sent Construction letter to Melissa. 4/9: Pending access install date from ATT SW 4/5: Address change - pending USO's. 3/28: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX483-01-IM | UHG | Melissa Chapman | Wellmed | 1717 N Garrett Ave | Dallas, TX |  | 304580131 VS19063125 3102-0369 7MS02339137 3102-BBDW | 2019-04-05 | 2019-06-24 | 2019-06-24 | 2019-07-18 |  |  | BBEC.511663 | ATT SW | 14KRGN885566SW | 2019-07-17 | 1ST FLR,LOBBY,FRONT OFFICE TAGGED |  |  |  | 50 | 10.1.88.121 | 10.1.88.122 | 64548 | 202610 | UHG GLOBAL 150 | 7/18: ORDER COMPLETE 7/8-7/17: Access install unchanged - targeting 7/17. 7/1: Construction completed their fiber work on 6/28. Issued DDF ticket to have PON supp'd for new date. -- 7/17 install 6/24: Construction fiber placement and splicing is scheduled for 7/5. 6/18: Per NSS PM, Construction advised this is still pending engineering completion. The engineer should have the design issued to construction by 6/18. Once it has been issued he will be able to get a better date as to when construction will complete. 6/11-6/17: Escalation to NSS PM for status - no updates on 6/10 fiber date in sytems. 5/9-6/10: Construction Fiber work scheduled to complete on 6/10. LEC has provided a 6/19 access install date. 4/29: Per IOS ticket - address updated and a DDF- 201904290135 ticket raised to sup the PON 4/26: Issued IOS supp request per Melissa's request - Customer requested that we sup the ROOM and FLOOR for this Dallas Ethernet order. Please change FLOOR to "Second Floor" and ROOM to "Laundry Closet." 4/16-4/22: Construction provided a 6/10 fiber placement and splicing completion date. Access install scheduled for 6/19. -- UPDATE: Sent Melissa the Construction letter. 4/9: Pending access install date from ATT SW 4/5: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX512-01-IM | UHG | Melissa Chapman | Wellmed | 605 N Main St., Suite-C | Donna, TX |  | 304671953 VS19075869 3102-0431 7WS03772695 3102-BBFH | 2019-04-15 | 2019-07-11 | 2019-07-11 | 2019-07-19 |  |  | BBEC.567982 | ATT SW | 38KRGN613853SW | 2019-07-22 | 1ST FLR TELCO RM DEMARC 1ST FLR RM FROM CIENA |  |  |  | 50 | 10.1.89.232 | 10.1.89.233 | 65201 | 202610 | UHG GLOBAL 150 | 7/22: ORDER COMPLETE 7/17: Access install improved to 7/22. 7/8: Access install unchanged - targeting 8/5 6/10-7/1: Access install still showing due 8/5. Pending date improvement. 6/3: Fiber work completed on 5/31. Pending improvement in access install date. 5/9-5/28: Construction fiber work scheduled to complete on 7/25. Access install scheduled for 8/5. 4/29: PON sent 4/24 - FOC due back by 5/16. 4/15: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000Base-SX | AZ076-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 1101 N Central Ave. Ste 102 | Phoenix, AZ |  | VS19089536 3102-0439 3102-BBFP VS19091523 3102-0488 3102-BBFY VS19112055 3094-2925 3094-BVQK | 2019-05-16 | 2019-08-09 | 2019-09-13 |  |  |  | BKEC.933048 | Qwest | 19KXGS430614MS | 2019-07-24 | 1ST FLOOR MPOP IN TELEPHONE/ELECTRICAL ROOM NEAR PHARMACY |  |  |  |  | 10.1.93.233 | 10.1.93.234 | 64749 | 202610 | UHG GLOBAL 150 | COMPLETE 08/02: Tested end to end. Ready for plug and play. 08/01: Ckt designed and wired. AT&T to work on end to end testing. 07/29: Access shows installed. EVC/VLAN PON FOC'd and ready. Requested AT&T design be worked. 7/22: Access install scheduled for 7/24. 7/1-7/17: Pending an access install date from Qwest. 6/28: CHECK TO MAKE SURE USO'S LOADED BY CLYDE ON FRIDAY 6/28 ARE IN ALL SYSTEMS THERE IS A SUPP TO CANCEL THIS ORDER PER CLYDE - VERIFIED HE IS CORRECT - RESUBMITTED AS MDS ID: 1-AT10KV9 6/10-6/24: Access install has completed - demarc provided - pending testing completion and the OK to turn up. 6/4: USO's changed (due to duplicate orders issued in our systems which was corrected) - but access on schedule for 6/6. 6/3: Access install scheduled for 6/6 5/21-5/28: FOC due back by 6/24 5/16: Order rec'd
New | 200M Port/ 400M Access EaAVPN 1000Base-SX | AZ074-02-IM | UHG | Melissa Chapman | United Healthcare- Avella | 23620 N 20th Dr, Ste 12, | Phoenix, AZ |  | VS19091527 3102-0475 3102-BBFV | 2019-05-17 | 2019-08-09 | 2019-08-09 | 2019-07-11 |  |  | BLEC.983203 | Qwest | 19KXGS417200MS | 2019-06-12 | 1ST FLOOR SERVER ROOM SUITE 10 RACK MOUNTED TYPE OPTICAL PO |  |  |  | 191 | 10.1.94.5 | 10.1.94.6 | 64901 | 202610 | UHG GLOBAL 150 | 7/11: ORDER COMPLETE 7/8: LEC delay - LEC states fiber splicing has an ECD of mid-July - follow up by 7/17. 7/1: Escalating on missed EVC PON. 6/24: EVC PON HWSV4254824 due to complete on 6/28. 6/17: PER LEC QWEST- DELAYED - PART OF A PROJECT BUILD - WITH ENGINEERING TEAM - PENDING ESTIMATED COMPLETION DATE. 6/10: Access install scheduled for 6/12. 5/21-6/3: FOC due back by 6/27 5/17: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | MO021-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 450 N New Ballas Rd | St Louis (Ladue), MO |  | VS19095151 3094-2714 7MS02356380 3094-BVPS | 2019-05-20 | 2019-08-19 | 2019-08-19 | 2019-07-18 |  |  | IUEC.963630 | ATT SW | 41KRGN707261SW | 2019-07-18 | 2ND FLR STE 256 SERVER RM ON WALL BK PUCK JACK850NM 50M SC HAND |  |  |  | 50 | 10.1.88.157 | 10.1.88.158 | 65139 | 202610 | UHG GLOBAL 150 | 7/18: ORDER COMPLETE 7/17: Access install scheduled for 7/18. 7/8: Reached out to CNR Agent WB778T to confirm they can fix this city name issue - order came across as "Ladue" but it's showing ST LOUIS online and needs to be corrected. 7/1: ORDERING EMAILED CUSTOMER REQUESTING ADDRESS CONFIRMATION. CITY IS SHOWING ST.LOUIS MO IN GOOGLE. KT2791 6/24: PRE-CTA CNR WB778T - CREATED EXH TICKET TO HAVE THE ADDRESS CORRECTED AND UPDATED. TICKET# 9104799. 6/18: Escalated to 2nd Level for address issue clarification. 6/17: Follow up with Jessica (jt392t) (CNR Agent) to determine what the address issues are. 6/10: Notes indicate address issue - issued DDF ticket to assist in clearing R15 jep and provide details on what exactly the address issue is. 6/4: Pending fiber/access install dates. 5/20: Order rec'd
New | 50M Port/ 50M Access EaAVPN 100Base-TX | ULA02-01-IJ | UHG | John Sergot | Peoples Health | 655 Clinic Dr | Mobile, AL |  | VS19118456 3102-0785 3102-BBHL | 2019-06-26 | ASAP | 2019-09-25 |  |  |  | BBEC.559918 | ATT SE | A2KQGN468280SC | 2019-07-29 | EQUP RCK MMR208...2ND FLR TELCO CAGE ED PATCH PANEL RACK...PO 4 |  |  |  |  | 10.128.1.14 | 10.128.1.13 | 65534 |  | PeoplesHealthSIP | ORDER COMPLETE 07/30: Access installed. Ckt tested end to end. Order is complete. 07/29: Address does show 650 Clinic Drive. Access shows targeted to install today (7.29) 7/17: PLEASE CONFIRM ADDRESS SHOULD BE 650 CLINIC DRIVE……..NOT 655 CLINIC DRIVE 6/26: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | TX201-05-IM | UHG | Melissa Chapman | Wellmed | 2922 Morgan Ave. | Corpus Christi, TX |  | VS19119415 3102-0824 3102-BBHN | 2019-06-27 | ASAP | 2019-09-26 | 2019-07-22 |  |  | BBEC.510139 | ATT SW | 34KRGN614057SW | 2019-07-25 | 1,TELCO RM,OPTICAL MULTIMODE SC HANDOFF |  |  |  | 50 | 10.1.87.253 | 10.1.87.254 | 64730 | 202610 | UHG GLOBAL 150 | 7/22: ORDER COMPLETE 7/17: Access install scheduled for 7/25. 6/27: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | SC023-02-IM | UHG | Melissa Chapman | Wellmed | 5895 Core Road Suite 417 | North Charleston, SC |  | VS19123594 3102-0927 3102-BBJN | 2019-07-16 | 2019-10-04 | 2019-10-04 | 2019-07-30 |  |  | BBEC.525262 | ATT SE | 36KRGN401279SB | 2019-07-30 | 1ST FLR TELCO RM, WALL MT D CIENA PORT-5 |  |  |  |  | 10.1.87.209 | 10.1.87.210 | 64851 | 202610 | UHG GLOBAL 150 | 07/31: Ckt installed and tested end to end. Ready for T&TU. 07/29: Access shows targeted for 7.30. Ckt is designed and wired. AT&T will monitor. 7/22: Pending an install date from ATT SE 7/16: Order rec'd
New | CANCELLED 10M Port/ 50M Access EaAVPN 1000Base-SX | TX431-01-IM | UHG | Melissa Chapman | Wellmed | 410 West Sunset | San Antonio, TX |  | VS19110338 3102-0752 7MS02353526 3102-BBGZ | 2019-06-17 | 2019-09-11 | 2019-09-11 |  |  |  | BBEC.561299 | ATT Southwest | [7 empty] | 10.1.91.93 | 10.1.91.94 | 65088 | 202610 | UHG GLOBAL 150 | CANCELED 08/05: Order and PON canceled. C91. 08/01: Melissa asking to cancel order. HALO request sent to cancel request. 7/17-7/22: Pending FOC (due 7/18) - CNR Customer Not Ready coding on order indicates delay in receiving dates. Checked the construction side and I'm not seeing a site survey was completed or scheduled (possibly b/c of the CNR.) 7/8: Pending site survey completion - CNR - awaiting fiber and install dates. 7/2: Pending install date from ATT SW - C01B 6/17: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX510-01-IM | UHG | Melissa Chapman | Wellmed | 4101 S Staples Street | Corpus Christi, TX |  | 304643757 VS19072363 3102-0428 7MS02341451 3102BBFG | 2019-04-15 | 2019-07-05 | 2019-07-05 |  |  |  | BBEC.532853 | ATT SW | 34KRGN614010SW | 2019-08-09 | 1ST FL MAIN LAN RM WALL MOUNTED ON TELCO BOARD |  |  |  |  | 10.1.93.49 | 10.1.93.50 | 65058 | 202610 | UHG GLOBAL 150 | 8/12: ORDER COMPLETE 08/07: Site confirmed work was completed. CNR removed from order and LEC/AT&T SW order. 08/06: Sent email to Melissa with site visit letter. Need to confirm when site work will be compelted, so CNR can be removed and new access install can be provided. 08/02: Order shows a "Customer Not Ready" due to Path/Pwr/Grd/Space 07/29: No change, access still shows targeted to install 08/09 7/8-7/22: Access install unchanged - targeting 8/9. 7/1: Construction's fiber work completed ahead of schedule on 6/28. Pending improved access install date. DDF Ticket 201907010064 issued. 4/30-6/24: Construction fiber work scheduled to complete 7/31. ATT SW access install scheduled for 8/9. Sent letter to Melissa with site work details. EF offer accepted. 4/22-4/29: Pending an install date from ATT SW - FOC due 5/13 4/15: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | NV110-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 701 Shadow Ln | Las Vegas, NV |  | VS19101100 3102-0674 3102-BBGL 3102-BBGM | 2019-05-21 | 2019-08-27 | 2019-08-27 | 2019-08-05 |  |  | IUEC.522788 | Embarq | 53KXGS422358CTRL | 08/07/19 7/30/2019 | MPOE, MAIN ELECTRICAL ROOM, WALL MOUNT, MULTI MODE |  |  |  |  | 10.1.94.45 | 10.1.94.46 | 64668 | 202610 | UHG GLOBAL 150 | 8/6: Ckt installed on the 5th. Tested end to end. Ready for plug and play. 07/31: Access install pushed out to 08/07. 07/30: Access targeted to install today. AT&T team will monitor. 7/22: Access install improved to 7/30. 7/17: Possible delay per LEC "SITE ACCESS ISSUES SITE CONTACT ISSUES" - Please make sure site is aware of install and OK to allow LEC Tech access. 6/24-7/8: Access install scheduled for 8/6. 2A INTEROFFICE FACILITY (IOF) - MINOR BUILD 6/17: USO loaded - pending access install date from Embarq. 6/11: HITS ticket issued to load order in SOTS. Just rec'd USO yesterday. LEC is EMBARQ. Overall due date 8/27 - UPDATE ORDER HAS BEEN LOADED IN ALL SYSTEMS - FOD is 6/14 5/21: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | FL372-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 1072 East Brandon Blvd | Brandon, FL |  | VS19103443 3102-0183 3102-BBGS 3102-BBGT | 2019-05-30 | 2019-09-10 | 2019-09-10 | 2019-08-09 |  |  | BBEC.594337 | FRONTIER-CTF | 65KFGS161446FTNC | 2019-08-20 | 1ST FLOOR SERVER ROOM,WALL MOUNTED,RAD203,PORT 5,MULTI MODE |  |  |  | 79 | 10.1.89.225 | 10.1.89.226 | 65083 | 202610 | UHG GLOBAL 150 | 8/12: ORDER COMPLETE 7/22 - 08/09: Frontier access install scheduled for 8/20 6/17-7/17: Pending an access install date from Frontier. 5/30: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | TN050-05-IM | UHG | Melissa Chapman | Briova | 1893 General George Patton Drive | Franklin, TN |  | VS19119416 3102-0890 3102-BBHP | 2019-07-03 | ASAP | 2019-09-26 | 2019-08-08 |  |  | BBEC.517468 | ATT SE | T4KRGN824679SC | 2019-07-25 | 1ST FLOOR, MAIN TELCO ROOM, WALL MOUNT PORT 5 |  |  |  | 50 | 10.1.88.9 | 10.1.88.10 | 64790 | 202610 | UHG GLOBAL 150 | 08/09: Access installed. Ckt tested end to end, ready for plug and play. 08/05: Access still shows targeted to install 08/08. 07/30: PON supp'd. Access now shows targeted to install 08/08. 07/30: CNR removed. Request to supp PON for the soonest possible install. DDF Tkt # 201907300007 07/29: Access not installed due to site issues. Person who could provide access on the 25th was OOO. Working to remove "Customer Not Ready" and will send order back requesting a new install. 7/17-7/22: Access install scheduled for 7/25. 7/3: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000Base-SX | CA178-02-IM | UHG | Melissa Chapman | March Vision | 21300 Victory Blvd. 8th Floor | Woodland Hills, CA |  | VS19120109 3102-0863 3102-BBHT | 2019-07-08 | ASAP | 2019-09-27 | 2019-08-10 |  |  | BREC.964204 | ATT West | 13KRGN599060PT | 2019-07-24 | 8TH FLOOR SERVERROOM TERM CIR ON PANEL #1 POS #2 |  |  |  | 50 | 10.1.88.49 | 10.1.88.50 | 64636 | 202610 | UHG GLOBAL 150 | 8/12: ORDER COMPLETE 8/01: PON supp'd waiting for order to be re-foc'd. 07/31: Removed CNR and requested PON be supp'd. DDF 201907310127 07/29: Requesting the email address for Charles be updated. AT&T was working the CNR last week and site requesting advance notice for dispatch. 07/29: Access not installed LCON (Charles Price) and site not aware of order, refused access. Currently a "Customer Not Ready". 7/17-7/22: Access install scheduled for 7/24. 7/8: Order rec'd
New | HOT ORDER Channelized DS3 Service type M28 |  | UHG | Melissa Chapman |  | 14100 Business Center Dr 1st Floor, Rm MDF700 | Elk River, MN |  | PL19020610 3094-2567 HCS04257051 | 2019-04-01 | 2019-04-12 | 2019-05-13 | 2019-07-19 |  |  | DNEC.951170 | Qwest | 03HFGS006467NW | 2019-07-31 | MAIN LEVEL MDF ROOM 7 RELAY RACK M700 AF707 SHELF1 SLOT 9/2 |  | Client to order T-1s to the channels on this DS3 to handle their voice traffic POP CLLI: PLMOMNTO |  |  | 10.1.89.25 | 10.1.89.26 | 65183 | 202610 | UHG GLOBAL 150 | 8/6: Tech says change was completed and tested clean. John is not seeing the DS3 up.. Escaltion sent back to AT&T tech team to have someone check again and work with John. 08/05: AT&T Tech team working on re-testing the ckt. 08/02: AT&T Assembler needed to have the POP Cilli (MPLSMNDT) corrected on the order. 7/22: ORDER COMPLETE 7/17: DAN FROM CENTURYLINK CALLED IN WITH FIELD TECH READY TO CUTOV ER TO NEW CFA. HE MOVED OVER TO THE NEW CFA AND I SAW THE CIR CUIT OPEN. HE GAVE ME A SOFTWARE LOOP AT THE CENTRAL OFFICE T HAT I COULD SEE. HE THEN GAVE ME A LOOP AT THE CUSTOMER PREMI SES THAT I COULD SEE. CANNOT DETECT ANY CUSTOMER EQUIPMENT. W ILL F/U TO CLOSE ORDER. 7/8: PON was supp'd and targeting 7/31 completion. 7/1: The 6/28 date was missed - Per the LEC, 1C=CUSTOMER NOT READY - CUSTOMER CHANGE IN REQUIREMENTS, ADD'L INFORMATION TO FOLLOW -- AERO DESIGN TICKET 639966 issued for status. 6/17-6/24: New PON HCS04257051 showing due date of 6/28. 6/10: PER PROVISIONING, ISSUED PON HCS04257051 TO CHANGE CFA FROM SLOT 10 TO SLOT 2 902/OC48/02/MPLSMNDTKBC/MPLSMNDTWDX PER TECH THE CFA WAS EFECTIVE. 6/3: Provisioning working through Design issues. 5/28: Provisioning is working through Design issues - PER TECH THE CURRENT CFA 3311 OC48 10 MPLSMNDT MPLSMNDTA00 IS DEFECTIVE......ISSUED OPOI TFAS 91410385 FOR A NEW CFA. 5/20: CFA issues being resolved by provisioning - RID has posted. 5/13: SUPP REQUIRED TO CHANGE LCON PHONE NUMBER. USO is correct, but the PON showing in TIRKS engineering has an incorrect phone number for the LCON. Reached out to Ray McVay (CNR Agent) to assist. 5/9: DESIGN ISSUE - PER PROVISIONING WAITING ON RESPONSE FROM IOS TICKET THAT WAS ISSUED.....THIS ORDER HAS AN DISCREPANCY ON CKLP THE CILLI IS PLMOMNTO BUT THE LSO PROVIDED (763-241) IS IN MPLSMNDT. PLEASE PROVIDE WHICH ONE IS CORRECT FOR THIS ORDER 4/30: Level 1 Escalation Submitted on AERO DES ticket 574422. 4/29: LEC Centurylink is saying they have no access to the site. SUPI: Y RCODE: IG=NO ACCESS TO END USER PREMISE RDET: NO ACCESS TO PREMISES - SUP DUE DATE ---- Issued AERO DESIGN Ticket# 574422 to see if we can get RID (Engineering) completed. 4/22: Issued ESCALATION via IOS for missed install completion (Missed EAD) - pending response. - UPDATE: CARRIER MGMT ADVISED THAT THEY REACHED OUT TO CENTURYLINK FOR AN UPDATE AND WERE TOLD ORDER WAS DELAYED DUE TO A FACILITY CHECK AND HAS A NEW DATE OF 4/24. 4/16: Centurylink/Qwest advised DD IS 4/17. FOLLOW UP 4/16. PENDING confirmation of FOC. 4/9: FOC due back by approx 4/10 4/1: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | MA088-01-IJ | UHG | John Sergot | UHG- Optum | 75 State Street Brookfield Properties | Boston, MA |  | VS19056725 3102-0344 3102-BBDQ | 2019-03-21 | 2019-06-24 | 2019-06-24 | 2019-08-09 |  |  | BBEC.565965 | ASE LNS | MAKRGN100942TPM | 2019-07-30 | 29 FLOOR DATA ROOM WALL MOUNT 3903 MM OPTICAL PORT 2 |  |  | 3253938 | 50 | 10.1.89.173 | 10.1.89.174 | 64697 | 202610 | UHG GLOBAL 150 | 8/9: ORDER COMPLETE 8/05: Melissa confirmed pwr issue was resolved. Removing the CNR and will request a supp on the PON to send back to the LEC/AT&T LNS. DDF # 201908050133 / Assigned to if4592 07/31: Power issue will be resolved 08/02. 07/30: Per Melissa, site is aware but there is no power outlet. 07/30: Email to John to confirm LCON is aware and will return LEC/AT&T LNS calls. If LCON needs to be changed, will need name, number and email. Once we hear back we can remove the customer not ready and request a new access install date. 7/22: ACCESS MISSED -- Per LEC, "C03: STILL PENDING CALL BACK FROM LCON JANICE B TO SCHEDULE ACCESS." LCON: /LCON JANICE BUSS, 781 247-4962, JBUSS@CORETELLIGENT.COM 7/17: Access install has been improved to TODAY 7/17. Monitoring the order for access completion. 7/8: Still tracking a 7/30 access install date. 6/24-7/1: LEC LNS has provided a 7/30 access install date. Pending update from Siena Engineering on fiber work. 6/18: Per Dennis Matthews (Siena Engineering)< The cable installation was completed at 75 State Street and they are setting up splicing and testing. 6/13-6/17: Per Dennis Matthews (Siena Engineering), Sonet Electrical will be going out on Monday morning, 6/17 to install a fiber optic cable to Optum’s 29th floor data room 6/3: Sent request for update on MDF completion to Melissa. 5/20-5/28: Reached out to Melissa for any updates on MDF install or from Siena Engineering and their work. PON will need to be supp'd on AT&T side as it's not progressing due to site work. - UPDATE: Per Melissa, MDF completion is set for 5/31. 5/9: Per Dennis Matthews (Siena Engineering Group); "Once the MDF is nearing completion and I can identify the backboard space, electrical outlets, etc., I can return and complete the site survey. Usually within a couple of weeks after that we can have the fiber optic cable installed and spliced. At that point we will turn the order over to AT&T to turn up the circuit. We do not control their schedule, but we can note that this order is urgent if necessary." MELISSA UPDATE: "Thanks, If you can note this order is urgent that would be great. We have people moving into the space the end of June, but we will need the circuit up mid June. Doug- Please work with real estate the best you can to pull in the MDF ready date." 4/23: Per Dennis Matthews (Sienna Engineering), "The MPOE at 75 State is in the Parking Level of the basement. You would need to get from there to the 29th floor with a multimode cable (providing that it did not exceed the distance limitation). I do not think that you want to do that." FOLLOW UP FROM MELISSA: "Please advise if you wish to extend the distance from the parking level basement up to the floor (also let us know if MMF would suffice or if we need to change to SMF), or wait until the data room is complete on 5/31. Keep in mind if we have to wait for the data room to complete, we may not have a circuit by FDOB of 7/1." 4/22: PER ASEDB, ENGINEER WENT TO COMPLETE SITE SURVEY BUT CUSTOMER IS NOT READY AS THE SPACE HAS NOT COMPLETED CONSTRUCTION. TIER 2 CARRIER MANAGEMENT DISENGAGED. CNR POSTED ON ORDER. Please advise when site is ready to proceed and we'll supp for a new date. 4/16: Construction advised site visit tentatively scheduled for 4/17 4/1-4/8: LEC is ASE LNS - ASR released on 3/28 and FOC due back by 4/22. 3/21: Order rec'd - what LEC are we using?
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | FL394-01-IM | UHG | Melissa Chapman | Wellmed | 2940 S. US Highway 1 | Fort Pierce, FL |  | VS19101097 3102-0175 3102-BBGR | 2019-05-29 | 2019-08-26 | 2019-08-26 | 2019-08-19 |  |  | BBEC.590716 | ATT SE | 60KRGN763114SB | 2019-08-19 | 1ST SERVER BACKBOARD |  |  |  |  | 10.1.88.61 | 10.1.88.62 | 64758 | 202610 | UHG GLOBAL 150 | 8/19: ORDER COMPLETE 8/12: Fiber work completed on 8/8. Access on track for 8/19. 7/17-08/05: Access install scheduled for 8/19. Fiber on track for 8/8 completion. 7/8: Construction fiber work scheduled to complete on 8/8. Pending access install date. 6/11-7/1: Pending an install date from ATT SE 5/29: Order rec'd
New | HOT ORDER #2 1G Port / 1G Access EaAVPN | CA764-01-IM | UHG | Melissa Chapman | Monarch | 1661 Golden Rain Rd | Seal Beach, CA |  | VS19054746 3102-0319 3102-BBDN 3102-BBDM | 2019-03-26 | ASAP | 2019-06-20 | 2019-08-21 |  |  | IZEC.549430 | Frontier-CTF | 45KFGS139444FTNC | 2019-06-24 | A-END SL0#SHLF1#PRT4#PHYCOLOCATE RM INSIDE THE ATMP T POP RR -011008 MS 50 JK 67/68#JKSC#EXTN#TAGY Z-END RAD ETX203 E/5. 3RD FLR SUITE 330. TAGGED. | 1000 Base-SX |  |  | 51 | 172.27.27.249 | 172.27.27.250 | 64628 COS 6039 | 488101 | Monarch | 8/21: ORDER COMPLETE 8/19: TESTING WITH LEC FAILED this past Friday 8/16. Carrier Mgmt Tier 2 still engaged and pushing for status. UPDATE: LEC reported NOC tested OK to NID. LEC TECH SAYS WILL RE-DISPATCH INTO CO FOR TEST ASSIST. 8/12: Carrier Mgmt followed up Friday - EMAILED LEC FOR AN UPDATE ON CONSTRUCTION. Next follow up 8/13 08/05: AT&T Carrier mgmt following up on construction. Once construction work is completed, the request will flow to design and provisioning. 7/17-7/29: Carrier Mgmt Tier II Update - Per LEC, they have a conduit issue which is being repaired. No estimated completion date. Repair involves city permits, facility markup crews, traffic control, dig up repair and restoration along a busy road. Should have an estimated completion date from construction by 7/26. Next follow up from Carrier Mgmt is 7/31. 7/8: Reached out to Derek Hunter (Exec Escalation Mgr) for assistance. Last meaningful update from Frontier is that they ran into a facility issue while working the fiber build and it was referred to their engineering team for revision. 7/2: AERO CM issued 641558 - 7/1: Escalation sent to Derek Hunter (District Escalation Mgr) for assistance in pushing this HOT order. Advised Frontier access is showing missed and we need escalation assistance. 6/25: Reached out to Frontier contact for update - systems not showing access or VLAN completed. 6/17: Although a build was mentioned last week, Frontier just responded to Provisioning with a 6/24 access install date. The LEC ID provided was 45KFGS139444FTNC. 6/10: Pending install date on new PON, however initial indication is there will be a build. Notes from LEC show 1B OUTSIDE PLANT (OSP) - MAJOR BUILD. Working to firm up details. 6/3: Pending install date on new PON GWSC3781037 5/29: New PON GWSC3781037 released 5/28: Issued AERO DESIGN 598664 to request new PON to LEC. Showing LCON was updated but original PON showing cancelled so I asked for a new one to be sent to the LEC. 5/20: No install date - LEC has jep'd the PON. Issued AERO ticket 592205 for clarification on issues (R15.) Reached out to Melissa to verify LCON info - LEC Frontier saying LCON unresponsive. - UPDATE: MELISSA ADVISED TO USE QUOC HUYNH AS THE LCON. I HAVE REQUESTED ORDER BE SUPP'D TO CHANGE LCON/ALCON. WILL WORK TO GET THAT COMPLETED AND PON SENT BACK TO LEC. 5/9-5/13: Pending install date on new PON HWSC3768765. FOC showing due back by 5/15. 4/15-4/29: POP Collector PON is complete - new access PON HWSC3768765 was released and is pending an install date which is due back to AT&T by 5/15. 4/9: Showing an ESA2 PON only - (which is the PON for the POP Collector circuit connecting the LEC and AT&T Networks)- Opened AERO DES 554676 to see what issues are and if we have a POP Collector issue. 4/1: Issued AERO DES 547581 for missed order release to the LEC. 3/26: New USO's rec'd
New | HOT ORDER 10MB Port/ 50M Access EaAVPN 1000Base-SX | TX500-01-IM | UHG | Melissa Chapman |  | 126 N. International Suite B | Garland, TX |  | VS19043393 3094-0007 HMSC2348823 3094-BVKM 3094-BVKN | 2019-02-21 | ASAP | 2019-06-05 |  |  |  | BBEC.505872 | FRONTIER-CTF | 13KFGS139067FTNC | 2019-08-06 | SERVER CLOSET WALL MOUNTED NID USER PORT 5 |  |  | 3244357 |  | 10.1.95.181 | 10.1.95.182 | 64939 | 202610 | UHG GLOBAL 150 | MD5 issue due 9/3 8/2: Access installed. Ckt tested end to end. Ready for plug and play. 07/29: No change, access still shows targeted to install 08/06. 7/17-7/22: Access install scheduled for 8/6 7/8: Confirmed PON HMSC2348823 was supp'd requesting new install date - advised LEC CNR should not be an issue. Pending install date. 7/1: Continuing to see LCON UNRESPONSIVE from the LEC. PER GT10 IDA COUCH--LCON INFO:OSP ENGNR STATED LCON UNRESP ONSIVE, UNABLE TO SCHEDULE SITE SURVEY-UPDATE JEP CODE 6/24: Follow up to Melonie Williams (CNR Agent) regarding PON supp and redispatch. Still not seeing dates in our systems. 6/17: LCON unresponsive - Frontier unable to schedule site survey - advised Melissa via email - UPDATE: Issued IOS ticket to redispatch and request LCON change to Rick Williamson 6/3-6/10: New PON HMSC2348823 was issued on 5/29 and is pending an access completion date. 5/28: Issued AERO DESIGN 598678 to check on PON and obtain due date for install. 5/20: Followed up again on EUCR (Ray McVay) - Reached out to Irving (CNR Agent) to redispatch LEC ASAP as Verizon's Frontier circuit has installed. 5/13: Escalated to Lottie Lee (CNR Mgr) for assistance in obtaining EUCR. Being advised form was provided by Frontier to the end user however I have requested a copy. 5/9: Reached out to KEVIN FORD (Carrier Management) asking for EUCR that is required by Frontier. To date, we have not been provided this form so we need Kevin/CM to engage and escalate for a copy ASAP 4/29: Pending receipt of EUCR form. I've also opened a ticket with the ordering team to have order supp'd for redispatch ASAP. Pending status. 4/15: Per Melissa,"no date on the backboard. As soon as I know I’ll pass that on." 4/26 READY DATE 4/15: Advised Melissa that the LEC Frontier has advised that “CUSTOMER NEEDS BACKBOARD - AWAITING SIGNED EUCR FROM LCON.” DATE:: 4/26 FOR WORK COMPLETE 4/1-4/8: PON issues corrected - released to LEC on 3/28 - FOC due back by 5/2. 3/25: Escalated AERO 534576 for install date - issue is with (2) ASR's issued per LEC. Working to fix design 3/18: Issued AERO Design ticket 534576 to push for access install date and clear any design issues (R15.) Pending FOC which is not due until mid-April. 3/12: Pending an install date from FRONTIER-CTF (LEC.) Overall due date 6/5 2/21: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX511-01-IM | UHG | Melissa Chapman | Wellmed | 6181 Bonnie View Drive | Dallas, TX |  | Halo 304690309 VS19077562 3102-0471 7MS02343162 3102-BBFJ | 2019-04-25 | 2019-07-15 | 2019-07-15 | 2019-08-23 |  |  | BBEC.557231 | ATT SW | 14KRGN885720SW | 2019-08-26 | I OUTSIDE SW CORNER OF BUILDING PORT 1 |  |  |  | 50 | 10.1.88.105 | 10.1.88.106 | 65252 | 202610 | UHG GLOBAL 150 | 8/26: ORDER COMPLETE 8/19: Received a confirmed 8/26 access install date from ATT SW 8/13: UPDATE: PER OSPE THIS IS A NEW BUILING NEW CONSTRUCTION CUST IS RESPONSIBLE FOR CONDUIT AND PULL STRING FROM THEIR SERVER RM TO OUR CIENA 3931 WHICH IS LOCATED SW CORNER OF BUILDING, I HAD ADVISED CONTRACTOR OF WHAT WE NEEDED TO BE DONE BY CUST, WHEN I CAME FOR ANOTHER ORDER AT SAME LOCATION. NEED CUST TO PLACE CONDUIT AND PULL STRING FROM THEIR SERVER RM TO OUR CIENA 3931 SW CORNER OF BUILDING. 8/12: Pending new date from supp'd PON. PON was supp'd on 8/1. 7/30: AT&T working to supp and send PON back to the LEC. DDF ticket opened (tkt # 201907300004 ) 7/22: Order was jep'd on Friday 7/19........CUSTOMER - NO ACCESS - PER LEC TECH: I CALLED THE LCON TWICE AT THE ASSIGN D NUMBER NO ANSWER LFT VM NO CALL BACK . I WENT TO THE SITE WHICH IS A MULTI SUITE SITE AND NONE ARE NAMED UNITED HEALTHCARE . I NEED A GOOD LCON CONTACT TO WORK WITH TO GAIN ACCESS TO THE DEMARK TO COMPLETE 07/09/2019 02:18: 234713 Fiber-C&E Build Jeop Issued 7/8: Fiber on track for 7/8 and access install on 7/17. 6/3-7/1: Site ready as of 5/29. Fiber on track for 7/8 and access install on 7/17. 5/20-5/28: Construction fiber work scheduled to complete on 7/8 (EF accepted.) Access install scheduled for 7/17. 5/9-5/13: Pending install date from LEC ATT SW. 4/25: Order rec'd
New | 200M Port/ 400M Access EaAVPN 1000Base-SX | AZ078-02-IM | UHG | Melissa Chapman | United Healthcare- Avella | 24416 N 19th Ave | Phoenix, AZ |  | 304960913 VS19104284 3102-0731 3102-BBGW 3102-BBGV | 2019-05-17 | 2019-06-28 | 2019-09-11 | 2019-08-23 |  |  | BLEC.984303 | Cox Communications | 23KFGX991622COXC | 2019-10-09 | 1ST FLR MDF ROOM RISER ROOM PANEL 16 METRONID PORT 3 SFP 3 |  |  |  | 40 | 10.1.92.129 | 10.1.92.130 | 64533 | 202610 | UHG GLOBAL 150 | 8/26: ORDER COMPLETE 8/12-8/19: Cox access install scheduled for 10/9 due to build. 6/25-08/06: Cox Communications access install scheduled for 10/9 - 1B OUTSIDE PLANT (OSP) - MAJOR BUILD - OFFNETWORK SITE, PENDING SCOPE OF WORK 6/17: Pending USO's 5/17: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000Base-SX | CA236-02-IM | UHG | Melissa Chapman | March Vision | 560 E. Hospitality Lane | San Bernadino, CA |  | VS19122889 3102-0116 3102-BBJC 3102-BBJD | 2019-07-08 | ASAP | 2019-10-03 | 2019-08-26 |  |  | BKEC.935910 | Level 3 Communications | BBYD92789LVLC | 2019-08-20 | 3RD FLR ELECT/PHONE ROOM MPOE WALL MOUNTED BOTTOM RIGHT HAND SIDE PORT 11 |  |  |  | 40 | 10.45.10.185 | 10.45.10.186 | 65085 | 202610 | UHG GLOBAL 150 | 8/26: ORDER COMPLETE 8/13-8/19: Access install scheduled for 8/20. 8/12: Pending install date from the LEC Level3 07/29 - 08/05: Pending FOC (Firm Order Commitment). Once reached, we will know our access install from the LEC/Level3. 7/22: Pending an install date from Level3 7/8: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | AZ077-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 9777 N 91 St., Ste 102 | Scottsdale, AZ |  | VS19089537 3102-0150 3102-BBFM 3102-BBFN | 2019-05-15 | 2019-08-15 | 2019-08-15 | 2019-08-28 |  | Y | IUEC.998932 | Cox Communications | 23KFGX991597COXC | 2019-09-18 | COMMON AREA, TELCO ROOM, ELECTRICAL ROOM, ALCATEL-LUCENT (ALU) , PORT# 16 ON DMARC PANEL EXTENDED WIRE: DEMARC LABELED AT&T |  |  |  | 50 | 10.1.92.149 | 10.1.92.150 | 64667 | 202610 | UHG GLOBAL 150 | 8/28: ORDER COMPLETE 8/26: Access completed per Cox. Pending engineering completion to make tech ready. No Demarc provided yet. 8/27: AERO DES 701648 6/17-8/19: LEC Cox provided a 9/18 install date - MAJOR build. 6/10: Per Cox, 1B OUTSIDE PLANT (OSP) - MAJOR BUILD - PENDING ACCESS FOR SITE SURVEY TO CONFIRM SCOPE OF WORK 5/21-6/3: FOC due back by 6/24 5/15: Order rec'd - use Cox Communications
New | 50M Port/ 100M Access Managed AVPN w/ SIP | PA007-10-IM | UHG | Melissa Chapman | Executive Health Resource | 15 Campus Blvd | Newtown Square, PA |  | VR19122969 3094-1077 3094-BVRB 3094-BVRC | 2019-07-18 | 2019-08-01 | 2019-10-03 | 2019-08-27 |  | N | IUEC.543484 | Verizon South | 11KFGS311373PA | 2019-08-23 | 1ST FL DATA RM, WALL MOUNT #2 |  |  |  |  | 32.246.161.230 | 32.246.161.229 | 65000 | 1244159 | OPAS SIP | 8/27: ORDER COMPLETE - MD5 is a NO (because this is Managed it won't have MD5) 8/26: Rec'd R80 access completion from Verizon - pending testing completion and OK to turn up. Sent AERO DES 701110 for Engineering completion. 8/19: Access on track for 8/23. 8/12: Previous update showed 9/23 install.........however I'm showing FOC came back with 8/23 install. 8/05: FOC reached, access shows targeted to install 9/23. AT&T will work to release EVC/VLAN PON. 07/29: PON released to the LEC on 7.25. PON # HES02913427 7/19-7/22: USO's rec'd - pending install date from LEC 7/9: Order rec'd
| 10M Port/50M Access EAVPN 1000Base-SX | LA042-01-IM | UHG | Melissa Chapman | BriovaRx | 3200 Ridgelake Dr. Suite 202 | Metairie, LA |  | VS19136417 3102-0134 3102-BBKD | 2019-08-08 | 2019-10-29 | 2019-10-29 | 2019-08-31 |  |  | BBEC.593114 | ATT SE | L2KRGN822349SC | 2019-08-26 | 3RD FLR,TELCO RM,UNI OPTICAL PORT 5 |  |  |  | 50 | 10.45.11.53 | 10.45.11.54 | 64550 | 202610 | UHG GLOBAL 150 | 9/3: ORDER COMPLETE 8/27: ORDER WILL BE DELAYED DUE TO ATT SE WORK STOPPAGE 8/20: Access install scheduled for 8/26. 8/8: Pending USO's
| 30M Port/50M Access EAVPN 1000Base-LX | KY003-04-IM | UHG | Melissa Chapman | Optum | 401 S. 4th Street | Louisville, KY |  | 305324622 VS19137882 3102-0169 3102-BBKG | 2019-08-15 | 2019-10-31 | 2019-10-31 | 2019-08-28 |  |  | BBEC.590118 | ATT SE | K1KRGN402348SC | 2019-08-27 | 17 MPOE WALL MOUNT PORT 7 |  |  |  | 50 | 10.1.92.5 | 10.1.92.6 | 65224 | 202610 | UHG GLOBAL 150 | 8/28: ORDER COMPLETE 8/22: Install completed - pending testing completion. - Get with Tech team to close out testing and turn up - also make sure previous orders are closed out / disco'd. 8/19: Pending USO's
| HOT ORDER 4.5G Port/10G UVN Access EAVPN 1000Base-SX | MN011-50-IM | UHG | Melissa Chapman |  | 1707 West Creek Lane | Chaska, MN |  | VS19140611 3094-2135 3094-BVSD 3094-BVSF | 2019-08-01 | 2019-09-15 | 2019-09-23 | 2019-09-05 |  |  | L4YS.949446 | UVN ACCESS |  |  | Bay: AJ 804 Panel: 2A Jacks: TX – 05, RX – 06, handoff: SC/SM |  | F7 2A TX-27, RX-28 UHBPMH1SS01-04021401 UVN Ultra-Available Network Dedicated LNS (ALS) MPLSMNDTW84 WW .ACDC.101121..ATI TDI 080064.12.05.63 |  |  | 10.1.88.25 | 10.1.88.26 | 65023 | 202610 | UHG GLOBAL 150 | 9/5: ORDER COMPLETE 9/3: Overall due date 9/23. Added to HOT list 8/26: USO's rec'd - not loaded in SOTS - tickets opened in IOS. Minneapolis POP 8/5: Chris spoke with John on the need to upgrade these original port orders to 4.5G to accommodate the larger VLAN for ECC. Chris advised he will delete the order email and wait for UHG's updated RDS forms. 8/1: Order rec'd - pending USO's
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX528-02-IM | UHG | Melissa Chapman | Wellmed | 1948 E. Hebron Parkway Suite # 110 | Carrollton, TX |  | VS19122888 3102-0900 3102-BBHX 3102-BBHW | 2019-07-12 | 2019-10-14 | 2019-10-14 | 2019-09-04 |  | Y | BBEC.585293 | Frontier-CTF | 13KFGS174442FTNC | 2019-09-11 |  |  |  |  | 100 | 10.45.11.1 | 10.45.11.2 | 64620 | 202610 | UHG GLOBAL 150 | 9/4: ORDER COMPLETE - ESCALATING FOR DEMARC 8/5-9/3: FOC reached and shows Frontier access targeted to install 9/11. Design completed. 08/02: Order looks to have been FOC'd and shows a major LEC/FTR build. Working to resolve errors, so target date will be populated. AERO # 674812 7/22 - 07/29: Pending an install date from Frontier-CTF 7/12: Which order is correct? TX482 or TX528??
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | TX506-02-IM | UHG | Melissa Chapman | Wellmed | 11820 Miriam Drive | El Paso, TX |  | VS19123595 3102-0920 7MS02358291 3102-BBJL | 2019-07-16 | 2019-10-04 | 2019-10-04 | 2019-09-04 |  | Y | BBEC.574143 | ATT SW | 30KRGN615319SW | 2019-10-18 | 1ST,FIRE RISER,PANEL 1 PORT 5 TAGGED |  |  |  | 51 | 10.1.87.205 | 10.1.87.206 | 64889 | 202610 | UHG GLOBAL 150 | 9/4: ORDER COMPLETE 9/3: Fiber work completed 8/28. Access install bumped up to TODAY 9/3. 8/13-8/26: Fiber work targeting completion on 10/9. Access install scheduled for 10/18. 7/22 -8/12: Pending an install date from ATT SW 7/16: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000Base-SX | IL134-01-IM | UHG | Melissa Chapman | UHG | 1 Kone Court DMARC is Center of floor – Room 304 101 17th Street | Moline, IL |  | VS19116191 3102-0816 3102-BBHJ 3102-BBHK | 2019-04-26 | 2019-10-01 | 2019-10-01 | 2019-09-13 |  |  | BBEC.503576 | STRATUS NETWORKS | NFSN101044GGO | 2019-11-07 | 3rd FLOOR, NETWORK ROOM, RACK MOUNTED, TELCO 280, PORT# 1/1 OPTICAL HANDOFF |  |  |  | 847 | 10.1.94.33 | 10.1.94.34 | 64619 | 202610 | UHG GLOBAL 150 | 9/16: ORDER COMPLETE 9/9: LEC sent R84 notice that access install has completed. Pending receipt of completion notice and demarc. VLAN PON HCSV4311282 also showing R84 complete. 7/17-9/3: Access install scheduled for 11/7/2019. 7/8: USO's rec'd - pending install date from LEC "STRATUS NETWORKS" 6/11: Added to HOT list 5/30: ADDRESS CHANGE REC'D FROM MELISSA 4/26-5/13: Order rec'd - pending USO's - ORDER NOT PLACED YET - SPECIAL BID PROCESS
New | 50M Port/ 50M Access EaAVPN 1000Base-SX | WA112-01-IM | UHG | Melissa Chapman | BriovaRx | 8131 A West Bostian Road | Woodinville, WA |  | VS19110342 3102-0733 3102-BBHB 3102-BBHC | 2019-06-12 | 2019-09-20 | 2019-09-20 | 2019-09-12 |  | Y | BBEC.572355 | Frontier | 86KRGN704644FTNC | 2019-09-16 | SLOT 1 SHELF 1 PORT 1 ELECTRICAL ROOM RJ45 |  |  |  | 40 | 10.1.88.173 | 10.1.88.174 | 64674 | 202610 | UHG GLOBAL 150 | 9/13: ORDER COMPLETE 9/9: Access on track for 9/16 completion. No issues showing. 8/27-9/3: Order still showing 9/16 install date - reached out to ordering team regarding the request to confirm Special Construction which we believe was sent in error. I’m showing access PON# HWSC3788235 was resent on 8/13 to FV03/Frontier to refresh this order. 8/19-8/26: Facility issues pushed install date out to 9/16. 8/12: Access install scheduled for 8/27. 86KRGN704644FTNC 8/08: Address change per Melissa. " 8131 A W Bostian Rd; Floor: 1; Room: MDF; Woodinville, WA 98072" 08/05: Order was sent back, waiting for FTR to provide FOC (Firm Order Commitment). Once FOC is reached, we will know our targeted access install. 07/30/19: Being asked to send back order to FTR. Per FTR, order should not have been flagged for SC Charges. WE HAVE RECEIVED THE SPECIAL CONSTRUCTION QUOTE FROM FRONTIER QUOTE IS $116,800.00 QUOTE EXPIRES ON 9/16/19 SCOPE OF WORK - 3,800 FEET OF FIBER. ENGINEERING, BORING/ TRENCHING CONDUIT, PLACING AND SPLICING LABOR. PLEASE LET ME KNOW IF THE CUSTOMER WILL ACCEPT THE CHARGES. 7/9: PON was supp'd yesterday and LEC responded: A FACILITY ISSUE HAS BEEN IDENTIFIED ON YOUR PON AND SPECIAL CONSTRUCTION CHARGES MAY APPLY. YOUR ACCOUNT MANAGER WILL BE IN TOUCH WITH ADDITIONAL DETAILS. 7/8: Issued AERO DES ticket 645887 to clear R15 - still construction on customer side?? 7/2: Pending install date from Frontier. -- PER UHG POSSIBLE CONSTRUCTION 6/25: Cancelled old order VS19073876 (8025 Bostian Rd) 6/12: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | SC022-02-IM | UHG | Melissa Chapman | Optum RX | 1901 Main Street Suite 1400 | Columbia, SC |  | VS19119418 3102-0808 3102-BBHR | 2019-06-28 | ASAP | 2019-09-26 | 2019-09-19 |  | Y | BBEC.562744 | ATT SE | 34KRGN401620SB | 2019-09-19 | 14TH FLOOR,MAIN TELCO RM,3930 WALL PORT#5 |  |  |  | 50 | 10.1.87.245 | 10.1.87.246 | 64916 | 202610 | UHG GLOBAL 150 | 9/20: ORDER COMPLETE 9/16: Access install scheduled for 9/19. 9/9: Escalated to CNR agent BEDGOOD, WANETHIA for status - advised we need this redispatched ASAP. -- UPDATE: Per CNR Agent, created DDF ticket# 201909090274 to have PON supped for new due date 8/27: HITS ticket issued - "CUSTOMER ADVISED BUILDING SAYS THAT THEIR ROOM HAS BACKBOARD INSTALLED AND AT&T SHOULD INSTALL AT MPOE. PLEASE SUP FOR REDISPATCH AND UPDATE LEC WITH THIS INFO." Pending install date. 8/27: ORDER WILL BE DELAYED DUE TO ATT SE WORK STOPPAGE 8/26: CUSTOMER SITE NOT READY PER LOG NOTES FROM OUTSIDE TECH THERE IS NO BACKBOARD AT CUSTOMER LOCATION. 8/21: AT&T called Kim Zerkle (LCON) Wednesday 8/21 and they are scheduled to install the circuit tomorrow, 8/22 at 9 AM in the DMARC room. Kim let the building know so hopefully everything will go as planned. 8/12-8/19: ORDER DELAYED - PER LCON KIM ZIRKLE THEY HAVE JUST STARTED RENOVATION OF THIS SUITE AND WILL NOT BE READY UNTIL 9/9. CUSTOMER SITE NOT READY. 7/30 - 08/05: No change, access targeted to install 8.19 7/22: Access install scheduled for 8/19 7/17: Pending an install date from ATT SE 6/28: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000Base-SX | AZ046-04-IM | UHG | Melissa Chapman | Optum | 695 Pecan Tree Lane | Green Valley, AZ |  | VS19126159 3102-0935 3102-BBJR | 2019-03-28 | ASAP | 2019-10-09 | 2019-09-04 |  | Y | BBEC.511065 | Qwest | 19KXGS441431MS | 2019-08-23 | FIRST FLOOR MAIN IT WALL MOUNTED CIENA 3916.. OPTICAL PORT 2 |  |  |  | 70 | 10.1.87.197 | 10.1.87.198 | 64799 | 202610 | UHG GLOBAL 150 | 9/4: ORDER COMPLETE 9/3: Original AERO ticket was pushed back because VLAN wasn't completed. Checked VLAN and that is now complete (R84.) Issued AERO DES 709670 for engineering completion. 8/26: Access install completed - pending testing completion and the OK to turn up. AERO DES 701666 to complete Engineering. 8/19: Access install scheduled for 8/23. 8/12: HALO ticket issued - pending USO's loading in SOTS 7/18: Reissued order - pending USO's
New | 100M Port/ 250M Access EaAVPN 1000Base-LX | VA094-02-IM | UHG | Melissa Chapman |  | 12355 Sunrise Valley Drive, Suite 400 | Reston, VA |  | VS19125743 3102-0928 3102-BBJP | 2019-07-22 | 2019-10-18 | 2019-10-18 | 2019-09-13 |  | Y | BREC.976641 | ASE LNS | DCKRGN100574TPM | 2019-09-11 | 1ST FLOOR ROOM CR4 BAY E0833-H PANEL 6 PORT 1 AND 2 |  |  |  | 50 | 10.45.10.177 | 10.45.10.178 | 64702 | 202610 | UHG GLOBAL 150 | 9/13: ORDER COMPLETE 9/9: ACCESS INSTALL DATE IMPROVED TO 9/11. 8/19-9/3: Access install scheduled for 10/10 7/22: Order rec'd - per Chris, We processed with LNS, ASE access for this site. We did upgrade access to 250M as ASE does not offer 200M Eth.
New | CANCELLED PER UHG HOT ORDER #1 1G Port / 1G Access EaAVPN | CA764-01-IM | UHG | Melissa Chapman | Monarch | 1661 Golden Rain Rd | Seal Beach, CA |  | C11383162 VS18144167 3094-0376 3094-BTTC 3094-BTTD | 2018-08-02 | 2018-10-01 | 2018-11-13 |  |  |  | IZEC.524667 | Time Warner Cable | 56L1XX345685TWCC | 2019-02-22 |  | 1000 Base-SX |  |  |  | 172.27.27.111 | 172.27.27.112 | 64628 | 488101 | Monarch | 9/17: =============CM TIER II CLOSED --- PON 7WS03709927 CANCELED. 9/12: Issued cancellation request per Melissa. IOS request 81809. 9/9: Carrier Mgmt Tier II engaged - advised that Spectrum confirmed permits are still pending. Next follow up by 9/13 or before. Permits are required in order for work to proceed. 8/1-9/3: Still pending permits, ETA for Permits is 09/04. Construction cannot begin until permits are received. All engineering work has been completed. AT&T Carrier Mgmt continuing to follow up. Next update 9/6 7/22-07/29: Per Spectrum via Carrier Mgmt.....STILL PENDING PERMITS. UPDATES TO FOLLOW BY COB 8/2 7/17: Per Spectrum, construction following up for access and a preconstruction walk. Estimated completion of fiber work is 9/4. Next update from Carrier Mgmt is 7/19. 6/24-7/8: Per Spectrum, permits and underground work are both pending. Currently Construction has an estimated completion of 9/4 and a detailed scope of work is pending. Next update from the LEC is by close of business on 7/12 per Carrier Mgmt Tier II (Tara Locke.) 6/17: Email to John S / Melissa with details - TW/Spectrum is still dealing with the permitting required for this site. We’re working to confirm if any work has started and to see if they have an ETA on when they’ll have this permit back from SCE. NEXT UPDATE TO FOLLOW BY COB 6/20 OR BEFORE 6/10: REDESIGN NEW SOW: UG (UNDERGROUND)FIBER, BORING AND PERMIT SUBMITTED. CONSTRUCTION JOB ECD 9/4. NEXT UPDATE BY COB 6/28. 6/3: From Carrier Mgmt Tier II -- Per Spectrum, due to pole issues, they need to redesign the scope of work because of underground bore requirements that will now be required. This is with their fiber design team to redesign and updates to follow by close of business on 6/7. 5/13-5/28: Tier 2 Carrier Mgmt engaged - pending update from LEC on permits. Expecting further updates within next 2-weeks with follow up no later than 5/31. 5/9: Carrier Mgmt Update: Per LEC, what has to happen now since the permits were denied is they will resurvey and submit new cost. Underground cost a lot more so they will need approvals. More to come. This has been referred to Carrier Mgmt Tier 2 for further escalation assistance. Tier 1 has disengaged. 4/1-4/29: Per Time Warner: PERMIT ECD IS 5/24. CONSTRUCTION ECD = 6/7. SOW 130' NE UG FIBER. CONSTRUCTION SHOULD ONLY TAKE ABOUT 2 WEEKS ONCE PERMITS ARE RECEIVED. NEXT UPDATE TO FOLLOW 4/29. 3/18-3/25: PER SPECTRUM, PENDING POLE PERMITS FOR RISER. ECD FOR APPROVED POLE PERMIT IS SET FOR 5/24/2019. ESCALATING FOR SOW AND TO DETERMINE IF POLE APPROVAL DATE CAN IMPROVE. NEXT UPDATE BY COB 3/29. 3/12: Update from Carrier Management Tier II: PER SPECTRUM, STILL PENDING PERMITS. PENDING ECD FOR RECEIPT. NEXT UPDATE TO FOLLOW BY COB 3/18 3/11: Dates are unchanged - pending scope of work outside of what was provided. 3/4: TIER II CM === RECEIVED UPDATE FROM AERO CM TICKET, "PER SPECTRUM CONSTRUCTION REQUIRED. ECD 6/7. PENDING SCE POLE PERMIT FOR RISER. ECD FOR APPROVED POLE PERMIT IS SET FOR 5/24/2019. PENDING SOW DETAILS.” ESCALATING FOR ASSISTANCE ON ORDER - Requested Derek Hunter (Esc Mgr) engage. Chris exploring alternate LEC's. If we stick with Spectrum, Derek Hunter is requesting an EXPEDITE be applied to allow this order to go on the VP Portal list for management assistance. 2/25: PER SOTS LOG, EAD WAS MISSED DUE TO AN ISSUE WITH SPECIAL CONSTRUCTION. ADVISED CUSTOMER TO ALLOW 2 BUSINESS DAYS FOR AERO TICKET TO BE WORKED. BERT/IOS Escalation to be issued 2/27 10/29-2/18: Rec'd best/final 2/22/19 install date from Spectrum.Charter due date on the construction build is 1/24/2019 and the DLR is not due until 2/15/2019. 10/22: Per Spectrum, order is still pending circuit design / construction completion. No FOC yet until both are completed - next follow up by COB 10/26. AVM is engaged 10/15: Per LEC TW: THIS ONE IS STILL PENDING CONSTRUCTION. ECD DATE STILL 1/24/19 10/8: Carrier Management engaged. Time Warner advised they are still pending construction design on this order. Once that is done, it will go to their circuit design team. Once their work is done, Time Warner advised they would be able to provide FOC.Also working with Derek Hunter (Esc Mgr) to see what else can be done. Can we expedite? 10/2: Escalated this order to District Esc Mgr Derek Hunter last week - advised Carrier Management is engaging for the missed FOC. Pending status of POP collector and access PON's. 9/28: BERT/IOS Escalation issued for missed POP Collector and Access PON's. 8/27-9/24: Pending FOC for POP Collector PON 7WS03709928 and Access - due back by 9/24. Order DD in November. 8/20: Pending release of ASR to the LEC and access install date. UPDATE: ASR released for access and POP Collector. Pending FOC (9/24) 8/17: Rec'd USO's 8/10: Received C-project# C11383162 8/2: Order rec'd - pending USO's
New | 20MB Port/ 50M Access EaAVPN 100Base-TX | TX079-04-IM | UHG | Melissa Chapman | UHG- Wellmed | 9999 Kenworthy, Ste A | El Paso, TX |  | 303659106 VS18177665 3094-1068 HMS02345311 3102-BBBM | 2018-09-20 | 2018-12-13 | 2018-12-14 | 2019-09-18 |  | Y | BBEC.502292 | ATT SW | 30KQGN617154SW | 2019-09-18 | 1ST FLR ELECTRICAL RM WALL MOUNT A 3903X PORT-1 |  | Interface Type: ELECTRICAL Interface Mode: VLAN TAGGED ONLY (TRUNK) Talked to Circuit1: 30/VLXP/103538/SW Talked to Circuit2: Interface Speed: 10/100 VLAN: 50 Network Interface Port Type: 10/100 BASE T | 3172476 | 50 | 10.1.90.5 | 10.1.90.6 | 64572 | 202610 | UHG GLOBAL 150 | 9/18: ORDER COMPLETE 9/9-9/16: Received 9/18 access install date. 9/3: Fiber work was completed last Wednesday 8/28. DDF ticket issued to supp PON for new install date. LEC does show they were working on this last week as it was Wired on 8/29 in the CO. 8/26: Customer prem was completed on 8/19. Fiber work is showing due to complete on 8/27. 8/19: Customer prem and fiber work both showing target 8/20 completion. PM to track to this date & F/U 48 hours after ECD on 8/22 8/13: Q-message to Julie Reeder (Construction) to see if power work completed. UPDATE: CUSTOMER PREM READY DATE SHOWING 8/20 - that would include the work for the power that was needed as this is EF Offer YES. 8/12: Construction advised that per FMC (JG), turns out that the CC did not build pwr for the EF work. They were working on that this past Friday and will provide an ECD shortly. 8/09: Escalation to get update on C&E 08/06: Following up to confirm if C&E/Fiber work completed on the 5th. Access still shows targeted to install 8.14. 07/30: Fiber work still targeted for 08/05, w/ access targeted to install 8/14. AT&T team following up to see if on target. 5/28-7/22: Construction provided an 8/5 date for fiber work completion. Access install scheduled for 8/14. 5/20: Site visit completed on 5/16. Indications are the EF offer was accepted. Pending a letter from the Engineer with site requirements, fiber dates, etc. 5/9-5/13: New PON HMS02345311 pending install date and update on the Construction side. UPDATE: PON LOADED IN ASEdb (CONSTRUCTION SIDE.) SHOWING SITE VISIT TENTATIVELY SCHEDULED FOR 5/16. 4/30: Follow up with Janice Rivera (CNR Agent) to check into next steps for fiber work to be completed. 4/25: ROE has been signed per UHG. 4/22: ROE still pending (Landlord) 4/15: Melissa confirmed on last call that COI that was provided will work for the client. Pending status on site being ready. 4/8: Requested assistance from sales team on COI. Peter Mousa advised that the change requested by the end user makes the COI no longer a blanket COI at this point. It would need to be generated specifically for them. This is a much more detailed form than what we normally deal with and will probably need to go to our legal team. 4/1: Per Mousa confirmed on Friday that he generated the request for a general COI. Should have shortly. UPDATE: SENT MELISSA THE COI THAT WAS GENERATED FOR EL PASO. 3/25: Pending update from UHG on site readiness. STILL NEED BLANKET COI 3/15: Email sent 3/15 5:30pm - Email from Brady Hickman (CNR Agent) regarding CNR - pending status from UHG 3/11-3/18: Reached out again to Peter Mousa's backup in Design Engineering for blanket COI. 3/4: Pending response from MOUSA, PETER (Design Engineering) for blanket COI agreement per UHG request. Pending status on agreement with LL to enter property. 2/11-2/25: Pending status on the agreement - LL doesn't want to sign AT&T agreement - has his own and needs to go through AT&T legal. It's in que and being worked. 2/5: Per ROBERTO CORTEZ (ATT SW), "Its been a while since I heard anything on this order but if I recall correctly we were pending the signing of the permission form allowing at&t to bore under their parking lot to access the cust conduit which served their demark. Apparently their soc didn't make it completely out to the parkway as shown on records and the construction contractors second option was to bore up to the closest point outside their building to access it there. There were several parties involved in getting it approved, I believe their legal got involved and offered up their own document that they wanted signed. -- LL doesn't want to sign our agreement - has his own and needs to go through AT&T legal. It's in que and being worked. 2/4: Reached out to Roberto Cortez (ATT SW) for the latest on the conduit issues 1/28: Pending update from Construction and customer on conduit issues at site. ---> there is no SOC into the customer's building. 1/21: Follow up to Darrell Steele (NSS PM) for update on construction dates. LL didn't want to sign agreement - LL wanted to make changes - called Robert - sent her to Legal. 1/15: UHG working with Roberto Cortez (ATT SW) -- Roberto provided the end user with a pdf which shows the proposed work as well as an explanation of where AT&T intends to terminate equipment. Pending status. 1/4-1/7: Per the Construction Manager, there is no SOC (Subscriber Owned Conduit) into the customer's building. The site is EF qualified however we will need permission from the customer to provide the path. Pending permission.As it stands, the order has been CNR’d because of the issue. I’ll keep my eyes on it and let you know when I see updates.Please work with end user to ensure they're providing permissions to Construction to perform work. BIC Engineer to contact is ALEXIS HAM - 432-684-1021 - AH5763@att.com 12/26: Escalating on missed construction fiber date of 12/11. sent 2nd status request to FMC regarding past due C&E ECD; awaiting response/update 12/10: Construction reset their fiber placement/splicing date to 12/11. 12/3: Construction is past due - C&E WILL FOLLOW UP 12/04 11/27: Fiber work is past due and is being escalated. There will be a delay on the install. 10/9-11/12: Construction & Engineering fiber placement/splicing scheduled for 11/16. ATT SW Access install 11/27 9/20: Order rec'd - Pending USO's
New | 50M Port/ 100M Access EaAVPN 100Base-TX | NY463-02-IM | UHG | Melissa Chapman | National MedTrans | 3050 Whitestone Expressway | Flushing, NY |  | VS19126184 3102-0954 3102-BBJV 3102-BBJW | 2019-07-19 | ASAP | 2019-10-18 | 2019-09-19 |  | Y | IUEC.949710 | Time Warner | 34L1XX000482TWCC | 2019-10-25 | EQUIPMENT WALL MOUNTED IN SERVER ROOM |  |  |  | 5 | 10.1.87.193 | 10.1.87.194 | 64824 | 202610 | UHG GLOBAL 150 | 9/19: ORDER COMPLETE 8/12-9/16: Time Warner access install scheduled for 10/25. 7/19: Order rec'd
New | HOT ORDER 20MB Port/ 50M Access EaAVPN 1000Base-SX | AZ066-01-IM | UHG | Melissa Chapman | Steingard Medical | 5830 N. 19th Avenue | Phoenix, AZ |  | VS19014413 3102-0276 3102-BBCT 3102-BBCV | 2019-01-22 | 2019-04-23 | 2019-04-23 | 2019-09-30 |  | Y | BBEC.572382 | Cox Communications | 23KFGX991506COXC | 2019-07-22 | BASEMENT OF BUILDING A, SERVER ROOM, EQUIP- ALCATEL#7210 PORT 1 |  |  | 3223674 | 50 | 10.1.89.1 | 10.1.89.2 | 64828 | 202610 | UHG GLOBAL 150 | 9/30: ORDER COMPLETE 9/23: LEC Cox pushed out install to 9/26 citing the major build which appears to be holding things up. Escalation to be sent to Carrier Mgmt since LEC continues to delay order. 9/9-9/16: Tracking VLAN and Access for 9/19 completion. 9/3: Build is still delaying this order a bit. Checked VLAN PON and that was sent out to the LEC last Wednesday 8/28 and FOC'd same day for 9/19. Access install tracking for 9/19 as well. 8/27: Follow up on HITS ticket to find out more re: 9/19 install date - Per Escalation team, email sent to assembler to know the delayed reason for tech dispatch.Please expect my follow up on: 08/28/2019. 8/23-8/26: Cox advising 9/19 access install date pushed out due to FULL OFF NET BUILD WITH CONSTRUCTION AND EQUIPMENT 8/20: HALO ticket opened to engage Carrier Mgmt to find out why due date for access was pushed out - due date was adjusted again, this time from 9/22 to 9/19. 8/19: NEED TO OPEN HALO TICKET - DUE DATE FOR ACCESS WAS PUSHED OUT TO 9/22 PER LEC DUE TO FURTHER BUILD DELAYS. 8/05-8/12: No change, access still shows targeted to install 8/22. 7/22 - 07/29: Access install remains at 8/22. 7/8-7/17: PERMITS WERE NOT RECEIVED UNTIL 6/8. CONSTRUCTION TAKES APPROXIMATELY 21 BUSINESS DAYS TO COMPLETE – ETA 7/11. SPLICING TAKES APPROXIMATELY 5 BUSINESS DAYS – ETA 7/18. TRANSPORT/ACTIVATION TAKES APPROXIMATELY 5 BUSINESS DAYS – ETA 7/25. FOC IS CURRENTLY 8/22 – THIS DATE WILL BE BROUGHT IN IF POSSIBLE 7/1: Cox updated the PON with an 8/22/19 target completion date due to build and permits. Issued AERO Design ticket 639196 for additional details on dates being pushed out. 6/10-6/24: FULL OFF NET BUILD WITH CONSTRUCTION - 1B OUTSIDE PLANT (OSP) - MAJOR BUILD. Install date still showing 7/22. Pending status of permits. 5/13-6/3: Status unchanged - Still showing full off net build with construction and equipment with and UPDATED install completion date of 7/22 due to permitting isssues. PENDING STATUS ON AERO CM TICKET 603569 FOR UPDATE ON PERMITS 5/9: Pending status on Permit rejection - showing an "ETA 5/28" but working to firm up if that's for permit resolution or some other milestone. From the way the notes are written, it appears they're expecting resolution on the permit issue by 5/28. Still showing full off net build with construction and equipment with and UPDATED install completion date of 7/22 due to permitting isssues. 5/3: Added to hot list per Melissa's request. 4/15-4/29: Access install has been pushed out to 6/21. Permits were rejected ('by SRP') which requires new draft and resubmission. 2/11-4/8: No change in dates. Access install scheduled for 5/10 --- 1B OUTSIDE PLANT (OSP) - FULL OFF NET BUILD WITH CONSTRUCTION AND EQUIPMENT - Per Melissa only carriers are Centurylink and Cox. Verizon is using Centurylink and they have a SCON of about 30k. 2/4: PON released to LEC Cox on Friday 2/1 - access install date due back to AT&T by 3/8. 1/29: Pending release of the PON to the LEC Cox - awaiting install date. 1/22: Order rec'd
New | HOT ORDER 20M Port/ 50M Access EaAVPN 1000Base-SX | TX518-02-IM | UHG | Melissa Chapman | Wellmed | 4700 W Sam Houston Parkway N Suite-220 | Houston, TX |  | VS19126910 3102-0962 7MS02359337 3102-BBJZ | 2019-07-09 | 2019-10-10 | 2019-10-10 | 2019-09-30 |  | Y | BBEC.554222 | ATT SW | 28KRGN748748SW | 2019-09-30 | 1ST FLR EXT TO 220 WALL JACK #3 TAGGED |  |  |  | 50 | 10.1.87.233 | 10.1.87.234 | 65071 | 202610 | UHG GLOBAL 150 | 10/1: ORDER COMPLETE 9/23-9/30: Access install has been scheduled for 9/30. 9/18: DDF ticket issued - PER SMART CHAT FROM JP210H INSIDE WIRING COMPLETED BY VENDOR. Please sup PON and request LEC install access ASAP now that inside wiring is completed. Thx! 9/17: Confirmed the CCLCON group is handling this work at the site. This is AT&T hiring an outside vendor to do the fiber runs. My contact Jessica King (Carrier Intervention Team Lead) reached out late yesterday to the CCLCON group for status of the order C574157HO. Expecting feedback today. 9/9: LCON VENDOR QUOTE APPROVED - WAITING FOR ECD . PROVISIONING WILL FOLLOW UP 9/24 9/3: Requested follow up on fiber pull order which was due yesterday (but it was Labor Day.) Added to HOT list. 8/19-8/26: SENDING REQUEST TO HAVE CONTRACTOR PULL 300FT MM FIBER TO SERVER ROOM STE 220 ON 2ND FLR FROM DATA RM 1ST FLR OPPOSITE SIDE OF BUILDING. THE ORDER WILL BE DELAYED 10- 14 BUSINESS DAYS. NEXT FOLLOW UP 9/2. 8/12: Access install scheduled for 8/9 but was missed. Per LEC, NO PATH. SENDING REQUEST TO HAVE CONTRACTOR PULL 300FT MM FIBER TO SERVER ROOM STE 220 ON 2ND FLR FROM DATA RM 1ST FLR OPPOSITE SIDE OF BUILDING. Pending ETA. 7/22: Pending USO's from sales 7/11: Added to HOT list per Melissa 7/9: Order rec'd
| HOT ORDER 4.5G Port/10G UVN Access EAVPN 1000Base-SX | MN053-75-IM | UHG | Melissa Chapman |  | 14100 Business Center Drive | Elk River, MN |  | VS19141430 3094-2096 3094-BVSB 3094-BVSC | 2019-08-01 | 2019-09-15 | 2019-09-23 | 2019-09-24 |  |  | L4YS.947342 | UVN ACCESS | Elk River A, 14100 Business Center Drive Bay: AM156 Panel: 2A Jacks: TX-03, RX-04, SC/SM |  | Bay: AM156 Panel: 2A Jacks: TX-03, RX-04, SC/SM |  | F7 2A TX-27, RX-28 UHBPMH1SS01-04021401 UVN Ultra-Available Network Dedicated LNS (ALS) MPLSMNDTW84 |  |  | 10.1.88.13 | 10.1.88.14 | 65023 | 202610 | UHG GLOBAL 150 | 9/24: ORDER COMPLETE 9/24: Notes show techs were testing this yesterday with the OSWF to check light levels. Appears they are scheduled to continue working this today. I'll monitor and advise when testing is successful and ready for TTU. 9/23: Engineering posted complete last week. Pending update from Provisioning. 9/3-9/16: Overall due date 9/23. Added to HOT list 8/26: USO's rec'd - not loaded in SOTS - tickets opened in IOS. Minneapolis POP 8/5: Chris spoke with John on the need to upgrade these original port orders to 4.5G to accommodate the larger VLAN for ECC. Chris advised he will delete the order email and wait for UHG's updated RDS forms. 8/1: Order rec'd - pending USO's
New | 50M Port/ 50M Access EaAVPN 1000Base-SX | AZ045-04-IM | UHG | Melissa Chapman | Optum | 1460 West Valencia Road | Tucson, AZ |  | 304580148 VS19063124 3102-0416 3102-BBFF 3102-BBFD | 2019-03-28 | 2019-07-03 | 2019-07-03 | 2019-09-26 |  | Y | BBEC.511763 | Cox Communications | 47KFGX990222COXC | 2019-05-23 | 1ST FLR TELCOM RM, NORTH WALL, PORT 6 |  |  |  |  | 10.1.92.165 | 10.1.92.166 | 64522 | 202610 | UHG GLOBAL 150 | 9/26: ORDER COMPLETE 9/9-9/23: Tracking access/VLAN completion for 10/4. 9/3: LEC Cox is still indicating delays on their end due to 1B OUTSIDE PLANT (OSP) - MAJOR BUILD. Checking the VLAN and Access PONs this morning, those both show a due date of 10/4. Apparently the R84 completion notice was sent in error by the LEC. They are saying they still need to complete the ACCESS CABINET install to complete their work. 8/26: AERO Design ticket escalation (Level1) issued. Pending Engineering completion.....once complete, order will be tech ready to complete testing. -- 8/27 UPDATE: ENGINEERING, DESIGN AND WIRING COMPLETED - PUSHING TO TECH TEAM FOR TESTING AND TTU. 8/23: R84 completion rec'd from Cox indicating access install has completed - working to get Engineering completed and then will get Tech team engaged to complete testing. AERO Design Ticket 698320 8/19: Per COX, ORDER IS CURRENTLY HOLDING FOR COMPLETION OF ROW ACCESS CABINET BEING PLACED UNDER SEPARATE ORDER WO 316152. 8/13: Per Cox, they are now able to schedule the equipment installation. They have moved this site back into August and they are "targeting" 8/21 for their infrastructure to be completed. Next follow up by end of day 8/14. 8/12: Pending Carrier Mgmt update - Cox was targeting late August for build out completion and we're pushing for status of build and completion of access. 8/06: AT&T Carrier Mgmt following up to confirm if work was completed and when updated access install date will be provided. 07/29: LEC construction still in progress. AT&T TIER monitoring. 7/8-7/22: Per the LEC, Construction is currently estimating to complete row cabinet and customer prem by the end of July. This location is currently on track for completion by the 8/9 FOC. 6/10-7/1: PER MARTIN AT COX COMMUNICATION ORDER ON HOLD AS SITE IS STILL DEPENDENT ON BUILD....PLACEMENT OF ROAD CABINET AS UNDER CONSTRUCTION AS OF 5/28. FOLLOW UP 7/2 6/3: Carrier Mgmt Tier 1 Escalation - Per Cox Communications, they are still building the circuit path and it's still processing in their systems with no estimated install date just yet. Pending follow up this week by Carrier Mgmt. 5/28: LEC ISSUES (COX): FOC REMARKS: OFFNET LOCATION, CURRENTLY PENDING SITE SURVEY TO CONFIRM SCOPE OF WORK. INITIAL FOC IS 8/23/19 5/20: Access due to install on 5/23. 5/9-5/13: PON released on 5/2 - access install due back by 6/6. 4/29: Order loaded in systems today - overall due date 7/3. Pending install date from Cox. 4/26: Still no response on SOA ticket # 568069 . Escalated to first level. Awaiting for resolution. Please expect my follow up on: 05/01/2019. Thank you.(1st Level Escalation contact:g31791@att.com) 4/22: ISSUED HITS TICKETS - ADVISED CLYDE POSSIBLE ORDER REISSUE - 4/23 UPDATE: Ordering has checked the order and found that it is still not loaded in SOTS. They have raised a SOA ticket # 568069 to load order in SOTS. Follow up on: 04/26/2019. 4/9: USO still pending loading into systems. No dates yet. 4/5: Pending USO's - 1-AD6D9RH 3/28: Order rec'd
New | 50M Port/ 50M Access EaAVPN 100Base-TX | ULA07-01-IJ | UHG | John Sergot | Peoples Health | 3838 North Causeway Blvd | Metairie, LA |  | VS19118457 3102-0800 HSS03609890 3102-BBHM | 2019-06-26 | ASAP | 2019-09-25 | 2019-09-26 |  | Y | BBEC.515679 | ATT SE | L2KQGN827799SC | 2019-09-26 | 23RD SERVER RM ALL FLD WK COMPLETE. ALL CENIA 390 ALL FLD WK COMPLETE. INSTALL CENIA 3903X RX-5.9 TX-6.9 MAC ADDRESS 144E22AB0A00 EXTEND FIBER FROM LGX ON 24TH FLR RISER RM TO STE 2300 SERVER RM WALL MOUNT. |  |  |  | 50 | 10.128.1.10 | 10.128.1.19 | 65535 |  | PeoplesHealthSIP | 9/27: ORDER COMPLETE 9/23: Access install has been rescheduled for 9/26. 9/17: Sent follow up email this morning to Lottie Lee - CNR coding is still on order and I'm not seeing the PON supp'd yet. Asked for resolution ASAP. Will take this up a level (Joe Scrudato) if I don't hear back by tomorrow morning. UPDATE: PON CLEARED OF CNR CODING AND SUPP'D FOR REDISPATCH PER KENRITIA MEADOWS (CNR AGENT) 9/16: Escalated to CNR AM Lottie Lee for movement on supp. 9/9: Follow up sent to CNR agent to find out if PON was supp'd and when we'll have updates on install. 9/3: Work stoppage is over - need update as to whether LCON's know of order and will allow access. PON will need to be supp'd - UPDATE FROM JOHN S: I did receive confirmation that the site will allow access. We have multiple offices in this building and the tech contacted the UHG office and not Peoples Health, that is why they were denied access. Please contact Eric (original LCON) or Rick Tittle 8/27: ORDER WILL BE DELAYED DUE TO ATT SE WORK STOPPAGE 8/26: Access install missed. LCON ERICK ORGERON 504 681-8921. NO ANSWER LEFT MESSAGE NO RETURN CALL. ALSO SPOKE TO MOD JUDY CANNATELLA 504 849-1538 AT UNITED HEALTHCARE. SHE ADVISE ME SHE HAS NO INFO ON AT T DOING ANY WORK FOR HER.ORDER NEEDS TO BE JEP TO CUST. POSTING C01L AGAINST EAD-0C02 IN EFMS- LCON UNAVAILABLE 8/19: Access install scheduled for 8/20. 8/12: New PON HSS03609890 issued Friday. Pending install date. 8/07: Per email from John, requesting to change the floor and suite on the order (23rd floor suite 2300). Request to change order, once changed PON will be supp'd. 08/05: AT&T team following up on new PON. 08/02: Follow up sent to AT&T Assembler team reqesting new PON. 07/30: AT&T HALO working the address issue and opened a DDF tkt (DDF # 201907290056) requesting updated PON. 7/23: Update...working with Ravindra Madokar, Tier 1 Support, AT&T HALO to fix address issue. 7/22: This order had an address issue - R15. UHG confirmed that the address is correct and that we should be dropping this in the AT&T MDF Room, 1ST FLOOR. When I Google the address, I also show “Three Lakeway Center” on the address so that might be what the LEC is looking for. Working with CNR Agent Victoria Dean to correct. 7/17: Pending an install date from ATT SE 6/26: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX521-02-IM | UHG | Melissa Chapman | Wellmed | 4230W Green Oaks Blvd | Arlington, TX |  | VS19120111 3102-0901 7MS02357287 3102-BBHY | 2019-07-01 | ASAP | 2019-09-27 | 2019-09-25 |  | Y | BBEC.524367 | ATT SW | 14KRGN886353SW | 2019-09-25 | 1 BREAK RM WALL MOUNTED CIENA PORT-9 |  |  |  | 50 | 10.1.94.65 | 10.1.94.66 | 64943 | 202610 | UHG GLOBAL 150 | 9/26: ORDER COMPLETE 9/23: Access install scheduled for 9/25. 9/17: UPDATE: FIBER completed yesterday - access due 9/25 7/22 -9/16: Fiber placement/splicing scheduled to complete 9/16. Access install scheduled for 9/25. 7/17: Pending an install date from ATT SW 7/1: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX524-02-IM | UHG | Melissa Chapman | Wellmed | 434 SW Wilshire Blvd | Burleson, TX |  | VS19120110 3102-0854 7MS02357286 3102-BBHS | 2019-07-01 | ASAP | 2019-09-27 | 2019-09-24 |  | Y | BBEC.563260 | ATT SW | 14KRGN886354SW | 2019-09-24 | 1ST FLR,SERVER RM,ATT.PNL 1, SC PORTS AND 2 |  |  |  | 50 | 10.1.94.73 | 10.1.94.74 | 65253 | 202610 | UHG GLOBAL 150 | 9/24: ORDER COMPLETE 9/23: Access install on track for 9/24. 9/16: Fiber work completed 9/16 - access install on track for 9/24. 7/29 -9/9: FOC reached, access targeted to install 9/24. Fiber work scheduled for 9/13. 7/22: Site visit completed 7/19. Pending fiber and install dates. 7/17: Pending an install date from ATT SW 7/1: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX520-02-IM | UHG | Melissa Chapman | Wellmed | 2225 Vatican Ln | Dallas, TX |  | VS19122890 3102-0891 7MS02358119 3102-BBHV | 2019-07-09 | 2019-10-03 | 2019-10-03 | 2019-10-05 |  | Y | BBEC.583817 | ATT SW | 14KRGN886382SW | 2019-09-18 | 1 TELCO BK BRD CIENA 3903 PORT 2 |  |  |  | 50 | 10.1.87.241 | 10.1.87.242 | 64544 | 202610 | UHG GLOBAL 150 | 10/5: ORDER COMPLETE 9/27: Carrier Mgmt engaged - AERO TKT 731010 - THE C&E ECD IS 9/27. WILL FOLLOW UP 10/1 UNLESS RESPONSE COMES PRIOR - F/U 10/1/2019 9/23: Infrastructure completion date is showing 9/24. 9/16: Per Construction, Engineer has to issue EAC (Engineering Authorized Change) request to repair blocked SOC (Subscriber Owned Conduit.) Pending ETA for completion of work. EF Offer was accepted so this is part of that work. 9/10: Site work is not completed yet - EF offer accepted - From Construction, "EF WORK WILL NOW INCLUDE SOC PLACEMENT TO THE BUILDING. THE EXISTING SOC WAS BLOCKED. -- this site will now require permission to place a new soc into the building via the ef offer. the existing soc was found to be damaged 8/12-9/9: Access install on track for 9/18. Fiber work scheduled to complete 9/9. 7/31/19 - 08/06: FOC reached, access targeted to install 9/18. 7/22 - 07/29: Pending an install date from ATT SW. 7/9: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | GA073-01-IM | UHG | Melissa Chapman | BriovaRx | 1800 Phoenix Boulevard Suite 310 | Atlanta, GA |  | VS19125742 3102-0929 3102-BBJQ | 2019-07-19 | ASAP | 2019-10-09 | 2019-09-25 |  | Y | BBEC.507303 | ATT SE | 38KRGN615886SB | 2019-09-25 | 1ST FLR RM 310, WALL MNT 3930, PNL 1, RT 5, TAGGED |  |  |  | 50 | 10.1.87.221 | 10.1.87.222 | 64624 | 202610 | UHG GLOBAL 150 | 9/25: ORDER COMPLETE 9/16-9/23: LEC set to redispatch on 9/25 to complete access install. 9/9: Follow up to Jessica Turney (CNR Agent) - confirmed that Customer is saying the DEMARC area does have power and is ready so that’s why they want the LEC to redispatch and just install at demarc. Pending install date. 9/4: Request to CNR agent to supp order for redispatch and request delivery to the demarc. 9/3: UPDATE THIS MORNING - CUST NOT READY PER TELCO - SUITE NOT READY....STILL UNDER CONSTRUCTION 8/27: ORDER WILL BE DELAYED DUE TO ATT SE WORK STOPPAGE 8/19-8/26: Access install scheduled for 8/27. 7/19: Order rec'd
| 100M Port/100M Access EAVPN 1000Base-SX | AZ154-01-IM | UHG | Melissa Chapman | 4c Medical | 10238 E Hampton Ave # 406 | Mesa, AZ |  | VS19155182 3102-0270 3102-BBLP | 2019-09-12 | 2019-12-05 | 2019-12-05 | 2019-10-02 |  | Y | IUEC.589629 | Qwest | 19KXGS453230MS | 2019-10-02 | 4TH FLOOR APOP WALL MOUNT CISCO3750 GIG PORT 1 TYPE: OPTICAL |  |  |  | 54 | 10.1.93.249 | 10.1.93.250 | 64616 | 202610 | UHG GLOBAL 150 | 10/2: ORDER COMPLETE 10/1: Access was scheduled to install tomorrow however LEC provided an update yesterday that they have completed install. Demarc provided. Pending completion of VLAN PON HWSV4332169 which is scheduled to complete 10/4. 9/23: Pending an install date from the LEC Qwest 9/12: Order rec'd
| 20M Port/50M Access EAVPN 1000Base-LX | UPA02-05-IM | UHG | Melissa Chapman |  | 401 N. Broad St Floor 2, Meet Me Room | Philadelphia, PA |  | VS19152599 3102-1108 3102-BBLH | 2019-09-13 | 2019-12-10 | 2019-12-10 | 2019-09-25 |  | Y | BBEC.530539 | ASE LNS | PAKRGN100681TPM | 2019-09-26 |  |  |  |  | 50 | 10.1.87.117 | 10.1.87.118 | 64732 | 202610 | UHG GLOBAL 150 | 9/25: ORDER COMPLETE 9/18-9/23: Access install scheduled for 9/26
New | 7xT1 10Meg AVPN | NM047-02-IM | UHG | Melissa Chapman | Wellmed | 530 N Telshor Blvd, Suite C | Las Cruces, NM |  | VS19152557 3102-1768FR 3102-1767 3102-1763 3102-1764 3102-1769 3102-1766 3102-1765 3102-1770 3102-BBKY | 2019-09-09 | 2019-10-23 | 2019-10-23 | 2019-10-14 |  | Y | DHEC.228918.811 DHEC.228918.812 DHEC.228918.813 DHEC.228918.814 DHEC.228918.815 DHEC.228918.816 DHEC.228918.817 | Qwest | 59HCGS343617MS 59HCGS343629MS 59HCGS343631MS 59HCGS343614MS 59HCGS343630MS 59HCGS343618MS 59HCGS343615MS | 2019-09-30 | 1ST FLR STE C REAR ENTRY ELEC RM NORTH WALL MOUNT SLOT 1/4 SLOT 4/4 SLOT 2/4 SLOT 1/4 SLOT 3/4 SLOT 3/4 SLOT 2/4 |  |  |  |  | 10.1.87.133 | 10.1.87.134 | 65433 | 202610 | UHG GLOBAL 150 | 10/15: ORDER COMPLETE 10/7: Carrier Management advised NO RESPONSE yet from the LEC Centurylink. Follow up is scheduled for 10/8. 10/1: Access install missed - Per LEC update: SUPI: N RCODE: 1D=NO LOOP AVAILABLE - RDET: ORDER DELAYED DUE TO LACK OF FACILITIES 9/17-9/23: Access install scheduled for 9/30 9/9: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX526-02-IM | UHG | Melissa Chapman | Wellmed | 1350 N. Buckner Blvd. Suite 101 | Dallas, TX |  | VS19122342 3102-0137 7MS02357955 3102-BBJF | 2019-07-12 | 2019-10-02 | 2019-10-02 | 2019-10-15 |  | Y | BBEC.590503 | ATT SW | 14KRGN886377SW | 2019-10-14 | TELCO BK BRD CIENA 3930 PORT 5 |  |  |  | 51 | 10.1.95.1 | 10.1.95.2 | 65105 | 202610 | UHG GLOBAL 150 | 10/15: ORDER COMPLETE 10/15: Access install completed - pending testing completion. 10/7: Access install scheduled for 10/14. 9/23-9/30: PON was supp'd on 9/16. Pending install date. FOC due back by 10/18 9/16: Fiber work completed ahead of schedule. Requested PON supp for install date for access. DDF Ticket 201909160183 9/3-9/16: Fiber work due to complete on 10/3. Pending install date for access 8/12-8/26: Site Visit showing scheduled with LCON for 8/27 07/30: CNR removed and PON sent back to the LEC/AT&T SW. LEC needs to contact the LCON. 07/29: Order is a "Customer Not Ready". LCON (Thomas Sympson) contacted but will not commit to a site survey date. Need to confirm corect LCON, remove CNR and send order back to LEC/AT&T SW 7/22: Pending an install date from ATT SW 7/12: Order rec'd
New | CANCEL ORDER 7xT1 AVPN | TX493-05-IM | UHG | Melissa Chapman | Wellmed | 615 Zaragoza | El Paso, TX |  | VS19152556 3102-1835-FR 3102-1834 3102-1831 3102-1837 3102-1838 3102-1833 3102-1836 3102-1832 3102-BBKX | 2019-09-13 | 2019-10-07 | 2019-10-07 |  |  | Y | DHEC.229089.811 DHEC.229089.812 DHEC.229089.813 DHEC.229089.814 DHEC.229089.815 DHEC.229089.816 DHEC.229089.817 | ATT SW | 30HCGS631362SW 30HCGS631365SW 30HCGS631367SW 30HCGS631364SW 30HCGS631376SW 30HCGS631363SW 30HCGS631366SW | 9/24/2019 9/24/2019 9/26/2019 9/24/2019 9/30/2019 10/1/2019 9/24/2019 | 1ST FLR, STE 86, REAR WALL, TELCO BK TELCO BK BD CAB1,SLOT4 CAB1, SLOT3 CAB2,SLOT1 CAB1, SLOT2 ?? CAB2,SLOT3 ?? |  |  |  |  | 10.1.94.117 | 10.1.94.118 | 65030 | 202610 | UHG GLOBAL 150 | 10/21: Orders completed out - reached out to ordering to confirm they'll be working disco orders. - Melissa to issue disco's 10/10: DDF 201910100250 opened to cancel PON. Once PON cancelled request can be send to dummy USO completion and then circuit disconnection can be placed. Next follow up expected on 10/15/2019, 1st Lv Escalation contact 10/7: UPDATE: PER MELISSA, PLEASE CANCEL ORDER - HITS TICKET ISSUED 10/7: Pending completion of the .815 and .817 T-1's. We have demarcs on the rest. 9/30: Pending completion of T-1's. Only one showing installed - Trouble showing: "PENDING TO CLEAR CABLES" 9/23: So far, 9/24 and 9/26 are being sent back as install dates. Pending a date on last two T-1's. 9/16: Pending install date from the LEC ATT SW
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TN073-01-IM | UHG | Melissa Chapman |  | 8 SHERIDAN SQ 2033 MEADOWVILLE LANE - KINGSPORT LANE | Kingsport, TN |  | VS19126185 3102-0956 3102-BBJX 3102-BBJY | 2019-07-19 | 2019-10-09 | 2019-10-09 | 2019-10-17 |  | Y | BBEC.514803 | EMBARQ | 87KXGS435564UIMN | 2019-10-10 | SUITE 150, 1ST FLOOR, 1ST CLOSET ON LEFT, NEAR BOT TOM OF RACK |  |  |  | 2 | 10.45.10.229 | 10.45.10.230 | 64801 | 202610 | UHG GLOBAL 150 | 10/17: ORDER COMPLETE 10/15: Access install showing completed - pending testing completion and OK to turn up. 10/7: Access install date improved to 10/10 from 10/17. 8/19-9/30: Access install scheduled for 10/17. 2A INTEROFFICE FACILITY - MINOR BUILD 8/12: Pending install date from the LEC - FOC due back by 8/28. 8/07: Order was written end of July. PON released to the LEC (7SS03605959) 08/07: Address being questioned, need order #'s to see what is being requested 7/19: Order rec'd
New | CANCEL ORDER 7xT1 AVPN | IL134-04-IM | UHG | Melissa Chapman | UHG | 101 17th Street | Moline, IL |  | VS19109973 3102-1825-FR 3102-1823 3102-1829 3102-1827 3102-1830 3102-1826 3102-1824 3102-1828 |  |  | 2019-07-23 | 2019-07-23 |  |  | DHEC.171411.811 DHEC.171411.812 DHEC.171411.813 DHEC.171411.814 DHEC.171411.815 DHEC.171411.816 DHEC.171411.817 | ATT MW | HCGS725653LB HCGS725656LB HCGS725657LB HCGS725658LB HCGS725659LB HCGS725655LB HCGS725654LB | 2019-07-08 | FLR 2 DATA RM, ADTRAN JCK PNL 01, JACK 01 JK 12 OF 28 JK 10 OF 28 JK 13 OF 28 JK 08 OF 28 JK 09 OF 28 JK 11 OF 28 JK 14 OF 28 |  |  |  |  | 10.1.94.37 | 10.1.94.38 | 64619 | 202610 | UHG GLOBAL 150 | 10/28: I have requested cancellation of this order per Melissa's request. I will keep it on the sheet until it has been removed from our systems. 10/22: Received COMPLETION notification from the LEC this morning on the final T-1. Pending testing completion and turn up. 10/21: Escalated to 2nd and 3rd levels (Jessica King, Juan Cordova) for assistance on this past due order. 10/8: ESCALATED TO DOROTHY SAPP (CARRIER MGMT) 10/7: Escalated Carrier Mgmt AERO CM ticket 738205 for status. 9/30: Carrier Mgmt engaged on missed install - AERO CM TICKET 738205 9/16-9/23: PON RCS04319938 was released with new CFA - due date 9/24 on the final T-1. 9/10: Requested status update from Theron Frazier, Manager Network Services – End-to-End Delivery 9/9: Requested update from Tech team on last T-1. 9/3: Correction to the CFA was processed last week on final T-1. Pending ETA for completion. Provided IP info to Melissa/LCON to make sure they're using the correct technical info for turnup of the other 6-T-1's which are ready. 8/27: Requested escalation to complete final T-1. Also requested Theron turn up the already completed (6) T-1's. so we can at least get a majority of the port bandwidth available for the end user. 8/19: Escalated to Theron Frazier (Tech Coach) for assistance in getting this final T-1 3102-1830 completed. Apparently it's designed out of a defective piece of equipment so they need to change the design and get this fixed ASAP. UPDATE: THERON FRAZIER ENGAGED - DEFECTIVE CFA IDENTIFIED AND THEY HAVE RELEASED NEW CFA AND REQUEST TO MOVE CKT INTERNALLY TO THAT NEW CFA. PENDING ETA. 8/12: Last T1 is not running clean. Seeing errors from the smartjack which will require a redesign. Design change will cause CFA to change to correct defective piece of equipment. Pending status of change. 8/02: AT&T working on last remaining ckt (3102-1830) which is not testing clean. TKT# WJ070792 07/29: AT&T testing and working the two remaining T1's. Escalation sent. 7/23: There are two remaining T-1's that need to be completed - working with provisioning to close those out and make this order plug and play ready. 7/17-7/22: Pending testing completion on 5 of 7 T-1's - due 7/23. 7/8: Access install complete - pending testing completion and OK to turn up. 6/14: Order rec'd
| HOT ORDER 50M Port/100M Access EAVPN 1000Base-SX | C1647-02-IM | UHG | Melissa Chapman | RDI Corporation | 4500 Lake Forest Drive | Cincinnati (Blue Ash), OH |  | VS19153276 3102-0238 3102-BBLM 3102-BBLL | 2019-08-28 | 2019-12-02 | 2019-12-02 | 2019-10-22 |  | Y | IUEC.922996 | Level3 Communications | BBYX98988LVLC | 2019-10-23 | FIRST FLOOR SERVER ROOM WALL MOUNTED IN 6RU BRACKET ZG002 PORT0/0/15 OPTICAL MULTI MODE/LC |  |  |  | 1021 | 10.191.22.53 | 10.191.22.54 | 65473 |  | ECC VPN | 10/22: ORDER COMPLETE 10/22: Engineering, Design and Wiring completed THIS MORNING. Will work to get this in front of a tech to complete out the order. 10/21: Level3 advised access install complete. Pending testing completion as well as demarc info. Engineering due 11/13. 10/7-10/15: Pending install date from the LEC - PON released on 10/4. FOC due back by 11/8. 9/25: USO's loaded - issued AERO Design ticket 743158 to load PON to LEC. 9/23: Issued HITS ticket to have USO's loaded in the systems. 8/28: Order rec'd - needed for peak season
| 10M Port/50M Access EAVPN 1000Base-SX | NM045-02-IM | UHG | Melissa Chapman | Wellmed | 271 Paseo De Dia, Suite 1A | Las Cruces, NM |  | VS19152510 3102-1087 3102-BBKW | 2019-08-21 | 2019-11-29 | 2019-11-29 | 2019-10-21 |  | Y | BBEC.599418 | Qwest | 59KXGS450714MS | 2019-10-16 | 1ST FLOOR IT ROOM EAST WALL SHELF01 POSITION04 MULTIMODS TYP |  |  |  | 365 | 10.1.89.177 | 10.1.89.178 | 65039 | 202610 | UHG GLOBAL 150 | 10/21: ORDER COMPLETE 10/15-10/21: Access install has completed - demarc provided. Pending testing completion. 10/7: Access install improved to 10/16. 9/23-9/30: Access install scheduled for 11/21. 9/17: PON released to Qwest yesterday. Pending install date. 8/21: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX482-02-IM | UHG | Melissa Chapman | Wellmed | 1779 E. Whitestone Blvd | Cedar Park, TX |  | 304580129 VS19063123 3102-0359 7MS02339138 3102-BBDT | 2019-04-01 | 2019-06-24 | 2019-06-24 | 2019-10-31 |  | Y | BBEC.511491 | ATT SW | 32KRGN653502SW | 2019-10-24 | 1ST FLR BLDG 2 LAN RM RACK PANEL1 POS 2 |  |  |  | 50 | 10.1.89.25 | 10.1.89.26 | 65183 | 202610 | UHG GLOBAL 150 | 11/1: ORDER COMPLETE 10/28: Infrastructure completed this past Friday 10/25. Access install date was readjusted to 11/8. 10/21: New install date of 10/24 posted. 10/15: Reached out to Melissa to confirm site work is complete - Construction is showing past due, site work not complete, etc. 10/8: Checked Construction today and still not showing complete - will escalate for status. 10/7: Fiber work due to complete today 10/7. 6/24-9/30: Fiber work still showing on schedule for 10/7. Access install has been confirmed for 10/16. 4/22-6/17: No change in dates - Construction and Engineering have scheduled fiber placement and splicing for 10/7/2019. See notes below and letter is also below that went to the client. Looks like this will take a few months. Some NOTES: - CONSTRUCTION & ENGINEERING BUILD INTERVAL = 122 DAYS - TOTAL LOOP FIBER FOOTAGE: 1,215 - BUILD COMPLEXITY: COMPLEX - ADDITIONAL TIME FOR CITY OF AUSTIN PLACING PERMITS - NEW CONSTRUCTION / VOIDS EF - NEW FDF LOC = 1ST FLR TELEPHONE RM / - NEW NTE LOC = 1ST FLR TELEPHONE RM / - 3903X TO BE WALL MOUNTED / 4/15: Construction Site Visit scheduled for 4/18. 4/9: Pending access install date from ATT SW 4/1: Order rec'd
| 10M Port/50M Access EAVPN 1000Base-SX | TX527-02-IM | UHG | Melissa Chapman | Wellmed | 4903 N McColl Road | McAllen, TX |  | VS19137008 3102-0990 7WS03799030 3102-BBKF | 2019-08-09 | 2019-10-30 | 2019-10-30 | 2019-10-30 |  | Y | BBEC.597744 | ATT SW | 38KRGN613922SW | 2019-11-12 | 1ST FLOOR TELCO ROOM TELCO CLOSET MNT |  |  |  | 50 | 10.1.89.141 | 10.1.89.142 | 64638 | 202610 | UHG GLOBAL 150 | 10/31: ORDER COMPLETE 10/28: Need to consider CANCELLING and REISSUING this order. Per the LEC< CUSTOMER PREM NOT READY- PER LOCAL CONTACT GABE RODIGUEZ, HE IS HAVING THE IT ROOM REMODELED AND CANNOT HAVE ANY EQUIPMENT INSTALLED AT THIS TIME - F/U 1/1/2020 DROPPING AT MPOE 10/21: Infrastructure completed 10/17. Access install bumped up to 10/22. 8/26-10/15: Construction & Engineering fiber work scheduled to complete 11/1. Access install on track for 11/12. 8/20: Access install scheduled for 11/12. CHECK FIBER 8/7: New order sent to AT&T.
| 10M Port/50M Access EaAVPN 1000Base-SX | OK021-02-IM | UHG | Melissa Chapman | Health Markets | 4500 S Garnett Rd | Tulsa, OK |  | VS19172516 3102-1169 3102-BBMR | 2019-10-21 | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | Y | BBEC.554109 | ATT SW | 98KRGN885526SW | 2019-11-01 | 1,TELCO RM,UPPER CABINET. PORT 4 |  |  |  | 50 | 10.45.10.129 | 10.45.10.130 | 65423 | 202610 | UHG GLOBAL 150 | 11/1: ORDER COMPLETE 10/28: Pending an install date from the LEC ATT SW. 10/21: Order rec'd
| 20M Port/50M Access EaAVPN 1000Base-SX | FL401-02-IM | UHG | Melissa Chapman | Health Markets | 4901 NW 17th Way | Ft Lauderdale, FL |  | VS19172518 3102-1179 3102-BBMS | 2019-10-22 | 2019-11-01 | 2019-11-01 | 2019-11-04 |  | Y | BBEC.572345 | ATT SE | 60KRGN764055SB | 2019-11-04 | 3RD FLR TELCO RM SUITE 301 SLIM BOX PORTS 1&2 TAGGED |  |  |  | 50 | 10.45.10.125 | 10.45.10.126 | 65422 | 202610 | UHG GLOBAL 150 | 11/4: ORDER COMPLETE 11/4: Access install scheduled for today 10/28: Pending an install date from the LEC ATT SE 10/22: Order rec'd
| 50M Port/100M Access EaAVPN 1000Base-SX | OK023-02-IM | UHG | Melissa Chapman | Equian | 2448 East 81st St | Tulsa, OK |  | VS19172510 3102-1195 3102-BBMX | 2019-10-22 | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | Y | IUEC.595630 | ATT SW | 98KRGN885525SW | 2019-11-01 | 4 MEET ME EXT TO SUIT 750 SERVER |  |  |  | 50 | 10.1.131.249 | 10.1.131.250 | 65428 | 202610 | UHG GLOBAL 150 | 11/1: ORDER COMPLETE 10/28: Access install scheduled for 11/1 10/22: Order rec'd
| HOT ORDER 4.5G Port/10G UVN Access EAVPN 1000Base-SX | MN011-51-IM | UHG | Melissa Chapman |  | 1707 West Creek Lane | Chaska, MN |  | VS19162659 3094-2251 3094-BVVH 3094-BVVJ | 2019-08-01 | 2019-09-15 | 2019-11-01 | 2019-11-05 |  |  | L4YS.889650 | LNS |  |  |  |  | F7 2A TX-27, RX-28 UHBPMH1SS01-04021401 UVN Ultra-Available Network Dedicated LNS (ALS) MPLSMNDTW84 |  |  | 10.1.88.21 | 10.1.88.22 | 65023 | 202610 | UHG GLOBAL 150 | 11/5: ORDER COMPLETE 11/4: Design completed - OSWF HAS WIRED IN BOTH OFFICES - IN-EFFECTING THE FACILITY. Pending testing completion. 10/28: Issued AERO DES 773454 for PON - pending LEC PON completion. IOC WILL ALWAYS COME OUT OF ST PAUL 10/15-10/21: Overall due date 11/1 on track. 10/9: USO's loaded in SOTS 10/7: USO's rec'd - overall due date showing 11/1. Pending loading in SOTS. 8/5: Chris spoke with John on the need to upgrade these original port orders to 4.5G to accommodate the larger VLAN for ECC. Chris advised he will delete the order email and wait for UHG's updated RDS forms. 8/1: Order rec'd - pending USO's
| HOT ORDER 4.5G Port/10G UVN Access EAVPN 1000Base-SX | MN053-76-IM | UHG | Melissa Chapman |  | 14100 Business Center Drive | Elk River, MN |  | VS19165346 3094-3057 3094-BVVN 3094-BVVP | 2019-08-01 | 2019-09-15 | 2019-11-07 | 2019-11-07 |  |  | L4YS.923484 | LNS |  |  |  |  | F7 2A TX-27, RX-28 UHBPMH1SS01-04021401 UVN Ultra-Available Network Dedicated LNS (ALS) MPLSMNDTW84 |  |  | 10.1.88.17 | 10.1.88.18 | 65023 | 202610 | UHG GLOBAL 150 | 11/7: ORDER COMPLETE 11/4: Pending test completion - overall due date still showing on track for 11/7. 10/28: Issued AERO DES 773456 for PON - pending LEC PON completion. ST PAUL 10/15-10/21: Overall due date 11/7 on track. 8/5: Chris spoke with John on the need to upgrade these original port orders to 4.5G to accommodate the larger VLAN for ECC. Chris advised he will delete the order email and wait for UHG's updated RDS forms. 8/1: Order rec'd - pending USO's
New | 300MB Port/ 400M Access EaAVPN 1000 Base-SX | MA008-05-IM | UHG | Melissa Chapman |  | 1325 Boylston Street | Boston, MA |  | HALO 303641809 VS18178523 3094-0971 3102-BBBH 3102-BBBJ | 2018-09-13 | 2018-12-26 | 2018-12-26 |  |  | Y | IZEC.511506 | ASE LNS | [7 empty] | 10.1.90.249 | 10.1.90.250 | 64705 | 202610 | UHG GLOBAL 150 | 10/29: Received Cancellation Request from Melissa - issued HITS ticket to have order cancel the order. 8/02-10/15: Revised ROE estimated completion date targeted for 10/01/19 - ORDER CANCELLED 5/13-07/31: Pending ROE resolution. No ETA 3/25-5/9: Pending ROE resolution - 4/23: site suvey possible for today 1/28-3/18: Pending ROE signing - Per Melissa. Pending update. 2/5 UPDATE: MELISSA TO FOLLOW UP - POSSIBLE USING VZ FOR ACCESS. 1/7-1/21 ESCALATION SENT TO NSS PM TO HAVE ASE UPDATED , ROE RESOLUTION ECD 1/4 IS PAST DUE - Melissa thinks not signed yet. Following up. 12/26: Pending status of ROE which has a 1/4/2019 ECD. 11/12: Pending ROE- ECD 01/04/19 - FOLLOW UP SCHEDULED FOR 12/21 11/5: Internal escalations continue to obtain FOC. Issues are internal with ATT and construction team. Being worked for resolution. 10/25-10/29: Access install date still pending - Escalation issued (BERT IOS TICKET) for missed FOC. 10/2-10/22: Pending access install date from LEC LNS. FOC due 10/23 9/13: Order rec'd - Pending USO's
| 50M Port/100M Access EAVPN 1000Base-SX | FL211-02-IM | UHG | Melissa Chapman | OptumServe | 10210 Windhorst Rd | Tampa, FL |  | VS19142963 3102-1009 HSSC3621581 3102-BBKL 3102-BBKM | 2019-08-12 | 2019-11-20 | 2019-11-20 | 2019-11-07 |  | Y | IUEC.855040 | Frontier-CTF | 65KFGS231764FTNC | 2019-11-27 | 1st FLR--DATA RM--WEST WALL-- RAD 203-- PORT #5--TAGGED AND LABEL |  |  |  | 75 | 10.1.94.173 | 10.1.94.174 | 64763 | 202610 | UHG GLOBAL 150 | 11/11: ORDER COMPLETE 10/21-11/4: Access install scheduled for 11/27. 10/8-10/15: Access PON HSSC3621581 and VLAN PON HSSC3621581 released to the LEC. Indications are possible POP Collector issue as both PON's mentioned it. Working with Provisioning to get clarity around the issue and have them finalize dates with Frontier. 9/30: Escalated the AERO ticket 726899 to 2nd Level - Pending install date 9/23: Level 1 Escalation Submitted - AERO DES TICKET - Pending Install Date. 9/9-9/16: Pending access install date from Frontier. AERO Des 726899 for R15 9/3: USO's loaded - R15 design issue on access PON - issued AERO DES 709685 to get that PON moving so we can obtain access install date. 8/27: Pending USO's - USO's not loaded - HITS ticket issued. 8/12: Pending USO's
| 100M Port/100M Access ADI 100 Base-TX | UTN19-01-IM | UHG | Melissa Chapman | Prospero Health | 40 S MAIN ST | Memphis, TN |  | IP19102335 3102-1124 3102-BBMC | 2019-09-24 | 2019-12-20 | 2019-12-20 | 2019-11-11 |  | NA | IUEC.996110 | ATT SE | T3KQGN828204SC | 2019-11-08 | BASEMENT - 5140 - PORT 8 - TO 13TH FLOOR DATA RM | [9 empty] | 11/11: ORDER COMPLETE 11/8 - READY TO SCHEDULE TTU. 10/28-11/4: Access install scheduled for 11/8. 10/21: Pending an install date for access. Per Construction: LCON IS NOT RESPONDING AND ASSIGNED TO TIER 2 10/18: Customer requested we sup the order to change the LCON to KEITH MANGENE, T 860-702-8284 ¦ M 860-302-5734 Keith_mangene@uhc.com. Change request sent via IOS HALO ticket 10/17: Per Bradley Chow (LCON), "Karen spoke with them earlier today. I have an appt with them on my calendar for 2pm Monday." 10/15: Pending dates - CNR Customer Not Ready situation - LEFT VMAIL/EMAIL FOR LCON, NO RESPONSE 10/4-10/8: USO's rec'd - pending install date from ATT SE 10/7: Pending USO's 9/24: Is this AVPN or ADI (Internet)? (THIS IS ADI)
| 8xT1 AVPN | NV097-02-IM | UHG | Melissa Chapman | Sierra Health | 4895 Boulder Highway | Las Vegas, NV |  | VS19171818 3102-1576 3102-1580 3102-1578 3102-1581 3102-1575 3102-1582 3102-1577 3102-1574 3102-1579-FR 3102-BBMV | 2019-10-21 | 2019-12-04 | 2019-12-04 | 2019-11-06 |  | Y | DHEC.329909.811 DHEC.329909.812 DHEC.329909.813 DHEC.329909.814 DHEC.329909.815 DHEC.329909.816 DHEC.329909.817 DHEC.329909.818 | Centurylink | 53HCGS345017CTRL 53HCGS345027CTRL 53HCGS345028CTRL 53HCGS345029CTRL 53HCGS345016CTRL 53HCGS345015CTRL 53HCGS345026CTRL 53HCGS345018CTRL | 2019-11-07 | BT ROOM AT WALGREENS. NIU # 2 SLOT 3 OF 8 BT ROOM AT WALGREENS. NIU # 2 SLOT 6 OF 8 BT ROOM AT WALGREENS. NIU # 2 SLOT 7 OF 8 BT ROOM AT WALGREENS. NIU # 2 SLOT 8 OF 8 BT ROOM AT WALGREENS. NIU # 2 SLOR 2 OF 8 BT ROOM AT WALGREENS. NIU # 2 SLOR 1 OF 8 BT ROOM AT WALGREENS. NIU # 2 SLOT 5 OF 8 BT ROOM AT WALGREENS. NIU # 2 SLOT 4 OF 8 |  |  |  |  | 10.1.94.241 | 10.1.94.242 | 65167 | 202610 | UHG GLOBAL 150 | 11/6: ORDER COMPLETE 11/4: Access install scheduled for 11/7. 10/28: Pending an install date from the LEC Centurylink. 10/21: Order rec'd
| 200M Port/400M Access EaAVPN 1000Base-SX | AL042-02-IM | UHG | Melissa Chapman | Equian | 7480 Halcyon Pointe Drive | Montgomery, AL |  | VS19174416 3102-1214 3102-BBNJ | 2019-10-25 | 2019-11-06 | 2019-11-16 | 2019-11-06 |  |  | BLEC.989665 | ATT SE | A1KRGN401750SC | 2019-11-06 | 2ND FLR TELECO RM WALL MTN |  |  |  | 50 | 10.45.10.145 | 10.45.10.146 | 65427 | 202610 | UHG GLOBAL 150 | 11/5: ORDER COMPLETE 11/4: Access install scheduled for 11/6. 10/25: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | UMD51-01-IM | UHG | Melissa Chapman | Wellmed | 800 King Farm Blvd SUITE 300 | Rockville, MD |  | VS19110416 3102-0740 3102-BBHF 3102-BBHG | 2019-06-18 | 2019-09-11 | 2019-09-11 | 2019-11-13 |  | Y | IUEC.840649 | Verizon | 36KFGS310520CD | 2019-11-08 | UPR,310,RM SERVER RM ,TEL CLOSET,,SFP,LP N,CAB N,, MNTG,WALL ,OTHER,VE13 #2 ,TGGD BTH IDS |  |  |  | 100 | 10.1.92.1 | 10.1.92.2 | 65102 | 202610 | UHG GLOBAL 150 | 11/13: ORDER COMPLETE 11/11: Sent AERO Design ticket 788516 for Engineering completion. Access and VLAN are both complete. 11/4: Received Verizon access completion notice this morning - pending testing completion. Demarc provided. 10/7-10/28: Verizon has provided an 11/8 access install date - LEC ID 36KFGS310520CD 9/30: Reached out again to HARRIS, JACINTA (CNR Agent) to clear CNR coding and have PON supp'd for redispatch. C01 popped up on the PON again. - UPDATE: SITE CONTACT NEEDS DATE FOR DISPATCH 9/24: Melissa confimed site is ready - UPDATE: reached out to HARRIS, JACINTA (CNR Agent) to clear CNR coding and have PON supp'd for redispatch. 9/23: Pending update from UHG on site requirements. 9/17: Melissa advised via email yesterday, no word yet on site requirements being completed. Pending update from customer side. 9/9: LEC still indicating site requirements needing completion - reached out to Melissa to confirm. PER LEC, ERR MSG: CUSTOMER BLDG/TELCO ROOM NOT READY CKL 1 - UPDATE: Per Melissa, Verizon amended site requirements. New Site requirements will be in place 9/13. 8/26-9/3: There are site requirements - per LCON. Pending customer status - PON will need to be supp'd. 8/26 UPDATE: ENGINEER HAS CONTACTED LCON, PENDING LCON RESPONSE AVAILABILITY, ON HOLD FOR SITE SURVEY NO SUP REQUIRED AT THIS TIME 8/19: Pending an install date from Verizon - please confirm LCON has contacted VZ. 8/12: PER VERIZON, PON IS HELD PREFOC CNR TO THE LCON. PLEASE HAVE LCON CONTACT VERIZON ENGINEER JAMES WALDEN, (240) 970-6289, JAMES.W.WALDEN@ONE.VERIZON.COM -- SITE SURVEY IS DONE - SITE REQ 8/05: Verizon engineer waiting on LCON to respond back to schedule site vist. Verizon Engineer: JAMES.W.WALDEN@VERIZON.COM @ 240.970.6289 07/30: Waiting on FOC (Firm order commitment) to be reached, targeted for 8.16. Once reached, we will be provided our targeted access install date. 7/17-7/22: PON HES02911717 supp'd on 7/15 requesting new install date - order was CNR, advised LEC LCON is ready. 7/8: No dates provided yet - CNR - Per Verizon, LCON NOT RESPONSIVE, ENGINEER REACHED OUT TO LCON AT CKL1 ON ASR, PENDING CALL BACK. 7/1: DDF issued for missing PON - pending install date from Verizon. 6/18: Order rec'd
New | 50M Port/ 50M Access EaAVPN 1000Base-LX | PA138-07-IM | UHG | Melissa Chapman | Optum | 1818 Market Street | Philadelphia, PA |  | VS19120711 3102-0094 7ES02913045 3102-BBHZ | 2019-07-10 | 2019-10-09 | 2019-10-09 | 2019-11-15 |  | Y | BBEC.538471 | ASE LNS | PAKRGN100662TPM | 2019-12-19 | 19TH FLOOR. MIDFIELD ROOM 190002.08. VIRTUAL EDGA PORT 1 & 2 |  |  |  | 50 | 10.1.95.117 | 10.1.95.118 | 64529 | 202610 | UHG GLOBAL 150 | 11/15: ORDER COMPLETE 11/11: Access install is scheduled for 12/19. 11/4: NTE placement still showing scheduled for 12/9. Issued BERT/IOS escalation on missed FOC. 10/28: Per Construction, EMUX- LOOP BUILD EXPECTED RESOLUTION DATE 12/9/19 10/15-10/21: WAITING ON EQUIPMENT TO BE INVENTORIED IN ORDER TO FINALIZE BUILD DETAILS. NEXT FOLLOW UP 10/22. 10/7: Escalation to Carrier Mgmt: "INTERVALS HAVE NOT BEEN POPULATED - WAITING ON EQUIPMENT TO BE INVENTORIED IN ORDER TO FINALIZE BUILD DETAILS FOR FOC." 9/9-9/30: PENDING CIENA 5150 COMPLETION IN BASEMENT COMMON SPACE. EXPECTED RESOLUTION DATE IS 10/4 9/3: Escalation this morning - T2 ETH FOC TICKET (678527) EMAILED NSS PM FOR PAST DUE 8/13-8/26: Per Construction, SURVEY COMPLETED. PENDING CIENA 5150 COMPLETION IN BASEMENT COMMON SPACE. NO ETA PROVIDED YET. 8/12: Site visit was scheduled for Friday 8/9 but not showing complete. Pending update from Construction. 7/22 - 08/05: Pending install date from ASE LNS. 7/17: USO not loaded in SOTS 7/10: Order rec'd
New | 7xT1 10Meg AVPN | TX482-05-IM | UHG | Melissa Chapman | Wellmed | 1779 E. Whitestone Blvd Building 2 | Cedar Park, TX |  | VS19123102 3102-1609-FR 3102-1615 3102-1613 3102-1611 3102-1612 3102-1614 3102-1616 3102-1610 3102-BBJM | 2019-07-18 | 2019-08-09 | 2019-11-05 |  |  | Y | DHEC.414463.811 DHEC.414463.812 DHEC.414463.813 DHEC.414463.814 DHEC.414463.815 DHEC.414463.816 DHEC.414463.817 | ATT SW | 32HCGS697985SW 32HCGS698062SW 32HCGS697987SW 32HCGS698063SW 32HCGS698057SW 32HCGS698056SW 32HCGS697991SW | 2019-11-01 | [5 empty] | 10.1.87.225 | 10.1.87.226 | 65183 | 202610 | UHG GLOBAL 150 | 11/1: ORDER CANCELLED BY MELISSA. ISSUED HALO CANCELLATION TICKET. 10/28: Access install on schedule for 11/1. 10/22: UPDATE: LEC PROVIDED AN 11/1 INSTALL DATE THIS MORNING 10/21: Reached out to Andrew Birdwell (Mgr) to make sure order is supp'd for new dispatch date. Requested redispatch last week after UHG notified site was ready, power complete. 9/30-10/15: LEC pushed back - BUILDING NOT READY SERVICE NOT NEEDED UNTIL MID OCTOBER -- UPDATE: 10/14-ish Perm Power Estimate. 9/23: Access install is 9/25 and 9/26. All PON's have been fixed and we should be good for delivery this week. 9/16: Sent request directly to Provisioning Assembler Mgr BIRDWELL, ANDREW D for assistance in getting PONs back on track. Some were showing cancelled, others R15 jeps (site not ready.) I've asked Andrew to correct all PON's and get dates. 9/13: Followed up again with Jonathan CNR agent. 9/9: Reached out to CNR agent for status - no update on LEC redispatch yet. 8/26-9/3: Working with CNR Agent Jonathan Hickman to have LEC redispatch ASAP. Conduit issues - VZ using ATT as well - should be able to redispatch - 8/6-8/19: Per Melissa Wiring Rough In targeted for 8/21 – 8/27 w/ a MDF Room Ready – 9/6 08/05: AT&T Carrier mgmt updated order and was jep'd a "Customer Not Ready". Building is not ready (only a shell) and service is not needed until mid-October. Email to Melissa to confirm 08/02: Follow up sent to AT&T Carrier mgmt for status. Following up with LEC/AT&T SW also, 07/31: Access install missed. AT&T Carrier mgmt engaged. AERO # 670585 07/30: No change, access shows targeted for today (7.30). 7/22: Access install scheduled for 7/30. 7/18: Order rec'd
| 10M Port/50M Access EAVPN 1000Base-SX | TX525-02-IM | UHG | Melissa Chapman | Wellmed | 2413 Memorial Parkway | Portland, TX |  | VS19148318 3102-1022 3102-BBKR 3102-BBKS VS19161030 3094-2237 3094-BVVF 3094-BVVG | 2019-08-14 | 2019-12-02 | 2019-12-30 | 2019-11-14 |  | Y | BBEC.593293 BBEC.591821 | Time Warner | 36L1XX004832TWCC | 2020-01-22 | FIRST FLOOR IT ROOM. CPE RACK MOUNTED AS CUSTOMER REQUESTED |  |  |  | 2 | 10.1.94.169 | 10.1.94.170 | 64841 | 202610 | UHG GLOBAL 150 | 11/14: ORDER COMPLETE 11/4-11/11: Received customer access install completion notice - completed well ahead of schedule - demarc provided - pending testing completion and the OK to turn up. Engineering due 11/14. 10/21-10/28: Access install scheduled for 1/22/2020. Fiber build to support access. 10/7-10/15: New USO's rec'd - pending install date from Time Warner. 9/23: Notified Chris this order was cancelled - pending response. 9/16: Escalating on missed PON release to LEC. Issued DDF ticket to have FOD cared for. 9/10: Pending release of PON to Time Warner (scheduled today.) 8/29: Per Chris Time Warner Cable was our only standard option. Pending USO's 8/15: Pending USO's
| 500M Port/1G Access EaAVPN 1000Base-SX | TX491-02-IM | UHG | Melissa Chapman | Health Markets | 9151 Boulevard 26 | North Richland Hills, TX |  | VS19172521 3102-1194 3102-BBMW | 2019-10-22 | 2019-11-01 | 2019-11-01 | 2019-11-12 |  | Y | IZEC.590125 | ATT SW | 14KRGN887157SW | 2019-11-11 | 2ND FLR,SERVER ROM,RR2 TELCO BLDG. B, SE CORNER OF RM,UNI MM PORT 5 |  |  |  | 50 | 10.45.10.133 | 10.45.10.134 | 65424 | 202610 | UHG GLOBAL 150 | 11/12: ORDER COMPLETE 11/11: Access due to install today 11/11 10/28-11/4: Pending an install date from the LEC ATT SW (PON 7MS02374927) 10/22: Order rec'd
| HOT ORDER 50M Port/100M Access EAVPN 1000Base-SX | C1646-02-IM | UHG | Melissa Chapman | RDI Corporation | 1111 Mary Crest Rd, Suite H | Henderson, NV |  | 3102-1032 3102-BBKT 3102-BBKV VS19157219 3102-1109 3102-BBLR 3102-BBLS | 2019-08-28 | 2019-12-06 | 2019-12-10 | 2019-11-21 |  | Y | IUEC.556490 IUEC.530617 | Embarq/Centurylink | 53KXGS454603CTRL | 2019-11-25 | DEMARKED IN ELEC.ROOM EAST WALL CIENA 5142 PORT 1 850 MULTI |  |  |  | 2 | 10.191.22.57 | 10.191.22.58 | 65475 |  | ECC VPN | 11/21: ORDER COMPLETE 10/7-11/18: Access install scheduled for 11/25. 10/1: New USO's populated on 9/24. MD5 showing YES. Pending install date from Embarq. 9/25: Per Chris, Clyde did a cancel and reissue on the below order that was originally ordered without MD5. The order had yet to generate PON so this would ne the quickest path to getting client the accurately completed circuit WITH MD5. 9/24: This order WILL require MD5 - Chris looking into whether this can be changed now or will require a MACD after the order completes. 9/23: Pending install date from Embarq - rec'd email to update address with SUITE H and LCON to Hossein Naderi -- NOTE: MD5 NO 8/28: Order rec'd - needed for peak season
| HOT ORDER 1G Port/1G Access EAVPN 1000Base-SX | WI014-04-IM | UHG | Melissa Chapman | LHI | 3237 Airport Road | La Crosse, WI |  | VS19146018 ESA2 HCS04332933 3102-1011 HCS04317373 3102-BBKQ EVC HCSV4341487 3102-BBKP | 2019-08-14 | 2019-11-26 | 2019-11-26 |  |  | Y | IZEC.550289 | Centurytel | 78KXGS448116CYWI | 2019-09-18 | CIENA 3960 PORT 1 |  |  |  | 2 | 10.1.89.53 | 10.1.89.54 | 65169 | 202610 | UHG GLOBAL 150 | 11/18: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 11/11: Engineering and Design completed - per the Tech Coach, the tech started to review the order and found an issue that will be worked with design. Once it is resolved, this should be ready by Tuesday. 11/4: Escalated AERO DES 775615 to 1st level for completion of engineering. 10/29: Issued AERO DES 775615 to have RID completed. 10/28: VLAN PON HCSV4341487 completed (R84) - pending overall testing and turn up. 10/21: VLAN PON past due. Issued AERO DES 766077 for escalation in getting PON completed. 10/15: POP Collector PON HCS04332933 completed 10/10. That same day the VLAN PON HCSV4341487 was issued to the LEC. Pending completion. Once that VLAN PON is complete, we'll push for critical date and testing completion. 10/7: Provisioning advised that in order to release the VLAN PON, the ESA2 PON (which is the POP Collector PON) needs to be FOC'd. Right now the POP Collector PON HCS04332933 is showing FOC due back by 11/1. 9/30: Escalated the VLAN PON 735208 for assistance as all EVC PON's are showing cancelled. Needs to be reissued. 9/24: Added to HOT list 9/23: Access showing complete - issued AERO DES TICKET 735208 for missed FOC on the VLAN PON HCSV4322730 9/16: Access install complete - pending testing completion.VLAN PON HCSV4322730 released on 9/13, pending FOC (due tomorrow) 9/9: Access install scheduled for 9/18. - KEEP EYES ON THIS ONE - ATT POP MADISON to LA CROSSE ISSUE 9/3: Pending release of PON to the LEC Centurytel (9/5 release date) 8/15: Pending USO's
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | FL418-02-IM | UHG | Melissa Chapman | Briova RX | 4220 Executive Circle | Ft. Myers, FL |  | VS19128221 3102-0968 3102-BBKC 3102-BBKB | 2019-07-16 | ASAP | 2019-10-14 | 2019-11-12 |  | Y | BBEC.503723 | EMBARQ | 25KXGS445228UFLG | 2019-10-14 | 1sT FL FACP RM 850 TELCO BACKBOARD WLLMNT RAD 203 OPTICAL PORT 4 |  |  |  | 144 | 10.1.91.93 | 10.1.91.94 | 64639 | 202610 | UHG GLOBAL 150 | 11/18: ORDER COMPLETE 11/12: UPDATE: ACCESS INSTALLED (R84) - VLAN PON HSSV4333454 COMPLETE (R84) - Pending testing completion. Reached out to assigned tech to complete out the order ASAP. 11/11: Reached out to Assembler Coach - TRICE, DEVONJA for assistance in getting the LEC back to the site and contacting LCON Jesse Moreno if they need assistance in installing at the MPOE. LEC recently rejected the order again so I've asked Devonja for some hand holding on this one. 11/4: LEC planned on 10/31 redispatch but advised that this is CUSTOMER NOT READY - CUSTOMER TO PROVIDE ENTRANCE CABLE OR CONDUIT. This continues to be an issue at this site and we need to get with the local contacts to see where things stand. 10/28: Confirmed Access PON HSS03613293 was resent to the LEC on 10/21. Pending redispatch date. 10/18-10/21: Per CNR team, The CNR holds have been removed and AERO Design ticket 765226 has been opened to request a redispatch and for them to update the LCON and ALCON. 10/15: CNR CUSTOMER NOT READY --> CUSTOMER NEEDS TO PROVIDED GROUND POWER BACKBOARD OR CONDUIT. NEED A UNITED HEALTH CARE LOCAL CONTACT. PLEASE SUP WITH NEW DD. REFERRING TO CNR TEAM. 10/7: Access install improved from 10/14 to 10/10 (this Thursday) 9/9-9/30: Access install scheduled for 10/14. 25KXGS445228UFLG 8/26-9/3: Pending install date from Embarq (LEC) 8/12-8/19: HALO ticket issued - pending USO's loading in SOTS 7/16: Order rec'd
| 10M Port/50M Access EAVPN 1000Base-SX | TX514-02-IM | UHG | Melissa Chapman | Wellmed | 1601 S Hwy 77, Suite E | Kingsville, TX |  | VS19138166 3102-0984 7MS02362752 3102-BBKH | 2019-08-09 | 2019-11-01 | 2019-11-01 | 2019-11-19 |  | Y | BBEC.535624 | ATT SW | 34KRGN614094SW | 2019-11-20 | 1ST FLR ELECTR RM 1ST FLR MPOE ELE RM 2 PORT PANEL POS2 |  |  |  | 50 | 10.45.10.169 | 10.45.10.170 | 64838 | 202610 | UHG GLOBAL 150 | 11/19: ORDER COMPLETE 11/11-11/18: Access install on track for 11/20. 10/15-11/4: Construction completed fiber work on 10/14. Pending improvement in access install date, still showing 11/20. 9/23-9/30: Fiber date showing 11/6 - Access install scheduled for 11/20. 9/16: Fiber date showing 11/6. Per Construction, During a site visit conducted on 09/04/19 with Mr./Ms. GABE RODRIGUEZ, I explained that certain site preparation requirements must be completed before we can install network terminating equipment (NTE) needed to provide your service. The site preparation requirements mentioned above are currently being completed in connection with another order and are the responsibility of another customer at your location. That customer is currently responsible for the completion of the following site preparation requirements: Place a 120V AC dedicated outlet on a dedicated 15Amp circuit breaker. Single standard 3 prong 120V AC, 15Amp dedicated receptacle. Per your acceptance of the Entrance Facility (EF) Offer, AT&T will complete the specified site readiness requirements listed above. In order to avoid a delay in the delivery of your ASE Ethernet order, the site readiness requirements must be completed by 10/16/19. 9/9: THIS PON NEEDS TO BE SUPP'D FOR REDISPATCH. SITE REQUIREMENTS CHECK CONSTRUCTION 9/3: ACCESS DENIED TO THE BUILDING per LEC. No site survey completed, although fiber date is showing 11/06. Need to check with LCON on this one to make sure they will allow access. 8/20-8/26: Pending an install date from ATT SW 8/9: Pending USO's
| 200M Port/300M Access EaAVPN 1000Base-SX | CO144-02-IM | UHG | Melissa Chapman | Equian | 600 12th St, Suite 300 | Golden, CO |  | VS19174412 3102-1207 3102-BBNF | 2019-10-24 | 2020-01-17 | 2020-01-17 | 2019-11-21 |  | Y | BDEC.995924 | Qwest | 29KXGS467735MS | 2019-11-18 | 1ST FLR TELCO ROOM CISCO 3750 TYPE: OPTICAL PORT: GIG 101 |  |  |  | 130 | 10.45.10.141 | 10.45.10.142 | 65426 | 202610 | UHG GLOBAL 150 | 11/22: ORDER COMPLETE 11/18: VLAN PON completed - pending testing completion and the OK to turn up. 11/11: Access installed - pending testing completion - VLAN PON HWSV4359448 sent to the LEC today - pending a completion date. 11/4: Pending an install date from Qwest - AERO Design Ticket 781601 10/24: Order rec'd
| 50M Port/100M Access EaAVPN 1000Base-SX | OH148-02-IM | UHG | Melissa Chapman | HealthScope | 5150 E. Dublin-Granville Rd. | Columbus, OH |  | VS19178332 3102-1248 3102-BBNR | 2019-11-07 | 2020-01-28 | 2020-01-28 | 2019-11-20 |  |  | IUEC.987166 | ATT MW | 94KRGN202754OB | 2019-11-20 | 3FL ITSERVEROOM REAR PATCHPANEL 5 |  |  |  | 50 | 10.1.87.145 | 10.1.87.146 | 65443 | 202610 | UHG GLOBAL 150 | 11/20: ORDER COMPLETE 11/12-11/18: Access install scheduled for 11/20. 11/7: Order rec'd
| 10M Port/50M Access EaAVPN 1000Base-SX | MO042-02-IM | UHG | Melissa Chapman | HealthScope | 2350 7th Street | St. Louis, MO |  | VS19178333 3102-1221 3102-BBNS | 2019-11-07 | 2020-01-28 | 2020-01-28 | 2019-11-21 |  |  | BBEC.558450 | ATT SW | 41KRGN707573SW | 2019-11-21 | 1ST DATA WALL MOUNT PORT 1 AND 2 |  |  |  | 50 | 10.1.87.165 | 10.1.87.166 | 65449 | 202610 | UHG GLOBAL 150 | 11/21: ORDER COMPLETE 11/12-11/18: Access install scheduled for 11/21. 11/7: Order rec'd
| 20M Port/50M Access EaAVPN 1000Base-SX | TN071-02-IM | UHG | Melissa Chapman | HealthScope | 2875 Elm Hill Pike | Nashville, TN |  | VS19178939 3102-0282 3102-BBNW | 2019-11-08 | 2019-11-18 | 2019-11-18 | 2019-11-18 |  |  | BBEC.582576 | ATT SE | T4KRGN824938SC | 2019-11-18 | 1 TELCO RM PORT 5 ON CIENA IN MAIN RM |  |  |  | 50 | 10.1.87.141 | 10.1.87.142 | 65441 | 202610 | UHG GLOBAL 150 | 11/18: ORDER COMPLETE 11/18: Access installed this morning - pending testing completion and OK to turn up. 11/11: APRN ONNET-5 - Access install scheduled for 11/18 11/8: Order rec'd
| 20M Port/50M Access EaAVPN 1000Base-SX | TX507-02-IM | UHG | Melissa Chapman | HealthScope | 221 N. Kansas St. Suite 400 | El Paso, TX |  | VS19178938 3102-0022 3102-BBNV | 2019-11-08 | 2020-01-29 | 2020-01-29 | 2019-11-21 |  |  | BBEC.581562 | ATT SW | 30KRGN615382SW | 2019-11-21 | BSMNT TELCO RM WALL MOUNT DEMARK PNL POS 11 & 12 |  |  |  | 50 | 10.1.87.137 | 10.1.87.138 | 65434 | 202610 | UHG GLOBAL 150 | 11/21: ORDER COMPLETE 11/11-11/18: Access install scheduled for 11/21 11/8: Order rec'd
New | 20MB Port/ 50M Access EaAVPN 1000 Base-SX | FL040-07-IM | UHG | Melissa Chapman | Wellmed | 701 NW 57 Ave Suite 150 | Miami, FL |  | VS19180396 3102-1242 3102-BBPD | 2019-11-13 | 2019-11-21 | 2019-11-21 | 2019-11-19 |  | Y | BBEC.561886 | ATT SE ONNET-5 | 60KRGN764182SB | 2019-11-21 | 1ST FLR, SUITE 150, SERVER ROOM, AT&T BER SILM BOX, JACKS 1 & 2, |  |  |  | 51 | 10.1.86.173 | 10.1.86.174 | 65412 | 202610 | UHG GLOBAL 150 | 11/19: ORDER COMPLETE 11/15-11/18: Access install scheduled for 11/21. ON-NET 11/13: Order rec'd
| CANCELLED (ADDRESS ISSUE - REISSUED UNDER 3102 1297) 500M Port/1G Access EaAVPN 1000Base-SX | IN710-02-IM | UHG | Melissa Chapman | Equian | 731 W Henry St #200 | Lightbound, IN INDIANAPOLIS |  | VS19164798 3102-1150 3102-BBMH | 2019-10-07 | 2019-10-16 | 2019-12-31 |  |  | Y | IZEC.534890 | ATT MW | KRGN106481NB | 2019-11-11 | 2ND FL TELCO RM TT 01.01.10 OPT PORT 6 |  |  |  | 50 | 10.45.10.161 | 10.45.10.162 | 64584 | 202610 | UHG GLOBAL 150 | CHECK THE BILLING ON THE ORDER BEING CANCELLED 11/26-12/3: Issued cancellation request per Melissa due to address issue - being reissued as 650 W Henry St INDIANAPOLIS IN 46225 11/25: Access install completed - pending testing completion. 11/18: REQUESTED DISPATCH VIA AERO FOR 11/20. AWAITING CONFIRMATION. 11/11: LEC design issued - missed install on 11/4. Escalations issued to push back to ATT MW for update on when they'll fix the issue and when access will be installed. IOS/BERT ESCALATION on missed install. 11/4: Access install is showing targeted for completion today 11/4. 10/21-10/28: Access install scheduled for 11/11. 10/15: Pending an install date from ATT MW 10/7: Order rec'd
| HOT ORDER 2XT1 AVPN | AZ143-01-IM | UHG | Melissa Chapman | Optum | 1125 East Glendale Ave | Phoenix, AZ |  | VS19155915 3102-1144-FR 3102-1142 3102-1143 3102-BBLQ | 2019-09-12 | 2019-10-30 | 2019-10-30 | 2019-12-12 |  | Y | DHEC.451481.811 DHEC.451481.812 | Qwest | 19HCGS343901MS 19HCGS343889MS | 10/7/2019 12/12/2019 | OUTSIDE SOUTH WALL SHELF 1 SLOT 2 OF 4 OUTDOOR WALL TERM SHELF 1 SLOT 1 OF 4 - SOUTH SIDE BLDG |  |  |  |  | 10.45.11.1 | 10.45.11.2 | 65430 | 202610 | UHG GLOBAL 150 | 12/12: Final T-1 installed - Order is now complete and ready for turn up plug and play 11/11-12/3: INSTALL DELAY - Access install pushed out to 12/12 due to facilties issues. 10/28-11/4: Access install pending for second T-1 - access install scheduled for 11/29. 10/21: Pushing final T-1 install - still showing ORDER DELAYED DUE TO LACK OF FACILITIES. Issued AERO DES 766076 for dispatch. 10/15: Access install showing 10/22 on only one of the T-1's. Issued AERO DES Ticket 760278 to push for same date for 2nd T-1. 9/30-10/7: Access install scheduled for 10/7. - SHOWING 10/22 - LACK OF FACILITIES PER LEC 9/18: Added to HOT list 9/12: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000Base-SX | UTX01-02-IM | UHG | Melissa Chapman | Wellmed | 6430 Bandera Rd Suite 74 | San Antonio, TX |  | VS19122341 3102-0153 7MS02357954 3102-BBJG | 2019-07-15 | 2019-10-02 | 2019-10-02 | 2019-12-06 |  | Y | BBEC.518097 | ATT SW | 31KRGN654095SW | 2019-10-25 | 1 74 TELCO BACKBOARD SLIM BOX PORT 1 2 |  |  |  | 50 | 10.1.92.145 | 10.1.92.146 | 64910 | 202610 | UHG GLOBAL 150 | 12/6: ORDER COMPLETE 12/3: ACCESS AERO TKT 773368 - FOLLOW UP EMAIL SENT REQUESTING AN UPDATE ON DISPATCH OR TO ADVISE ON WHAT NEEDS TO HAPPEN NEXT, SO THAT THIS ORDER CAN BE COMPLETED. - F/U 12/3/2019 11/18-11/25: Per Construction - AERO TKT 773368 - REQUESTED DISPATCH FOR 11/25 VIA DISPATCH TOOL, WILL FOLLOW UP 11/26 FOR ANY FURTHER UPDATES. 11/12: Carrier Mgmt pushing this morning for updates from Tech - FOLLOW UP EMAIL SENT REQUESTING A MORE CURRENT UPDATE AND IF THERE IS NOT THEN TO ADVISE ON WHAT NEEDS TO HAPPEN NEXT, SO THAT THIS ORDER CAN BE COMPLETED. - F/U 11/13/2019 11/11: AERO TKT 773368 - NO RESPONSE FROM ENOC, EMAIL SENT TO MANAGER REQUESTING AN UPDATE OR TO ADVISE ON THE STEPS THAT NEED TO BE TAKEN TO KEEP THIS ORDER PROGRESSING TOWARDS COMPLETION. 11/4: Engaged Carrier Management for assistance in pushing for update from construction - AERO CM ticket 773368 10/28: Per the LEC Tech who was dispatched to install access. FIBER TERM IS ON NORTH END OF BLDNG AND CUSTOMER TOLD BY ATT TO RUN CONDUIT TO OPPOSITE SIDE. OSPE WILL CHECK. Reached out to Doug Graham (Mgr OSP Engineering) to see if his team can re-engage. 10/15-10/21: Access install has been scheduled for 10/25. 10/7: Fiber work still showing due to complete on 10/31. - ISSUE: PER LOG, LCON IS UNRESPONSIVE. C&E has followed up with the LCON for status - F/U 7 DAYS PENDING NO RESPONSE. -- UPDATE PER MELISSA EMAIL: "Please sup the order to dispatch on or after 10/23." Working to supp PON. 9/30: Construction showing delayed - new fiber date 10/31. Working to find out why dates were pushed out. ADDED TO HOT LIST 9/23: Fiber work on track for 9/27 9/16: Fiber work scheduled for 9/27. Systems permission form sent to Janee Griffin (per ASEdb) 9/11: SYSTEM PERMISSION FORM sent to Engineer Douglas Graham 8/5-9/9: FOC reached, access shows targeted to install 9/26. Fiber work scheduled for 9/12 - NTE install 9/17. 7/22: Pending an install date from ATT SW --- UPDATE: PER LEC, "SITE VISIT - BLDG NOT READY" -- PER CONSTRUCTION - suite not ready ,being remodeled. no tenant yet. 7/15: Order rec'd
| 200M Port/300M Access EaAVPN 1000Base-SX | MI074-02-IM | UHG | Melissa Chapman | Equian | 26555 Evergreen Rd | Southfield, MI |  | VS19174413 3102-1208 3102-BBNG | 2019-10-24 | 2019-11-20 | 2019-11-20 | 2019-12-10 |  | Y | BLEC.989628 | ATT MW | KRGN215421MB | 2019-11-20 | 2ND FLR SERVER RM MM HANDOFF ON SLIM IN SERVER RM |  |  |  | 50 | 10.1.87.33 | 10.1.87.34 | 65429 | 202610 | UHG GLOBAL 150 | 12/12: ORDER COMPLETE 12/3: Provisioning is escalating on the missed install - requested next level escalation today. Per LEC field team (access installer), "INCORRECT DESIGN ON A 5140 MM PORT 9. I CONTACTED JARED JONES AND HE IS GOING TO SEND IT TO THE NSS PM TEAM." 11/25: Access install missed - IOS/BERT Escalation issued. 11/4-11/18: Access install scheduled for 11/20. (APRN NEARNET-15) 10/25: Order rec'd
| 500M Port/1G Access EaAVPN 1000Base-SX | KY025-02-IM | UHG | Melissa Chapman | Equian | 9390 Bunsen Way | Louisville, KY |  | VS19176068 3102-1219 3102-BBNM | 2019-10-30 | 2020-01-22 | 2020-01-22 | 2019-12-03 |  |  | IZEC.501346 | ATT SE | K1KRGN402444SC | 2019-12-12 | 1 SERVER TAGGED W/ ID |  |  |  | 50 | 10.1.87.109 | 10.1.87.110 | 65418 | 202610 | UHG GLOBAL 150 | 12/4: ORDER COMPLETE 11/18-12/3: Access install scheduled for 12/12. 11/11: Pending an install date from ATT SE 10/30: Order rec'd
| 10M Port/50M Access EaAVPN 1000Base-SX | TX546-02-IM | UHG | Melissa Chapman | Wellmed | 1901 W William Cannon Dr., Suite 123 | Austin, TX |  | VS19176655 3102-1224 3102-BBNP | 2019-10-31 | 2020-01-23 | 2020-01-23 | 2019-12-05 |  |  | BBEC.532989 | ATT SW | 32KRGN654046SW | 2019-12-04 | 1ST FLR STE 131 EXT TO CUST SRVR BKBRD N STE 123 |  |  |  | 50 | 10.45.10.113 | 10.45.10.114 | 65416 | 202610 | UHG GLOBAL 150 | 12/5: ORDER COMPLETE 11/22-12/3: Access install scheduled for 12/4. 11/11: Issued HITS ticket to have USO loaded in SOTS. 10/31: Order rec'd
| 100M Port/200M Access EaAVPN 1000Base-SX | AR035-02-IM | UHG | Melissa Chapman | HealthScope | 27 Corporate Hill Drive | Little Rock, AR |  | VS19180960 3102-1249 3102-BBPF | 2019-11-05 | 2020-02-04 | 2020-02-04 | 2019-11-25 |  | Y | BREC.552653 | ATT SW | 63KRGN602449SW | 2019-11-26 | 1ST FLOOR TELCO WALL MOUNT POS 7/8 OF POS DMARC PANL |  |  |  | 50 | 10.1.93.41 | 10.1.93.42 | 650015 | 202610 | UHG GLOBAL 150 | 11/25: ORDER COMPLETE 11/18-11/25: Access install scheduled for 11/26. 11/15: USO's loaded - pending install date from LEC. 11/5: Order rec'd
New | 500M Port/ 1G Access EaAVPN 1000Base-SX | CA177-02-IM | UHG | Melissa Chapman | Wellmed | 6601 Center Drive West, Ste 200 | Los Angeles, CA |  | VS19122891 3102-0095 7WS03793194 3102-BBJB | 2019-07-09 | 2019-10-03 | 2019-10-03 | 2019-12-13 |  | Y | IZEC.565023 | ATT West | 13KRGN599120PT | 2019-11-20 | CIENA INSTALLED INSIDE MPOE ON P2 |  |  |  |  | 10.45.10.181 | 10.45.10.182 | 65019 | 202610 | UHG GLOBAL 150 | 12/16: ORDER COMPLETE 12/12: Pending update from the field on the wiring vendor work - last update advised PER ASE CC-LCON - "INSIDE WIRING HAS BEEN SCHEDULED TO BE COMPLETED 12/10." 12/3: Per Construction, "QUOTE APPROVED. APPROVAL SENT TO AT&T'S WIRING VENDOR. REVIEW LATER FOR ESTIMATED COMPLETION DATE." 11/25: CNR CUSTOMER NOT READY - Per Carrier Mgmt....THIS ORDER IS BEING DELAYED DUE TO AN INSIDE WIRING JOB THAT REQUIRES A VENDOR/CONTRACTOR TO COMPLETE THE WORK. 11/18: Access install date improved from 12/19 to 11/20 now that construction is completed. 11/4-11/11: LEC still showing they're pushing towards the 12/19 install date. Construction work is showing complete, access install 12/19. 10/28: LEC tech was at the customer site on 10/23 - Per LEC, CUSTOMER NOT READY, NO ACCESS TO MPOE. 10/21: FIber work completed ahead of schedule on 10/18. Pending install date improvement. 10/15: Construction & Engineering has scheduled fiber work for 12/9. Access install scheduled for 12/19. 10/7: ACCESS INSTALL DELAY - Per LEC, LCON CONTACTED BUT WILL NOT COMMIT TO SITE VISIT DATE 9/23-9/30: Construction & Engineering has scheduled fiber work for 12/9. Access install scheduled for 12/19. Sent ppt diagram to Melissa. 9/16: PON resent on 9/11. Pending update on access install date from LEC. 9/9: Follow up with AM Lottie Lee (CNR team) regarding update on PON supp with info supplied by Melissa to access site by contacting Summit Riser. 9/3: Appears to be delayed due to issue below. Need UHG to confirm with LCON and property management what the process is to allow the techs to access the MPOE. 8/26: Delays in getting onsite to complete site survey - FIELDER WAS IN THE AREA ON 8/13/19 AND ATTEMPTED PROACTIVE VISIT. ROADBLOCK, NO ACCESS PROACTIVE. PROP. MGMT. INFORMED FIELDER THEY WILL NOT LET SUBCONTRACTORS ACCESS MPOE. BUILDING ENGINEER MUST ALSO BE PRESENT FOR MPOE ACCESS. 8/19: PON# 7WS03793194 supp'd on 8/14. Pending new install date. 8/12: Pending new install date - PON supp 8/06: Per Melissa, changing primary LCON to Eddie Gonzalez @ (M) 310-686-4793; (O) 310-216-2300 ext 2714 ; EGonzalez@marchvisioncare.com. 08/05: Note sent to Melissa to confirm LCON and Alt LCON will be available. Once confirmed, CNR can be removed and PON sent back out to the LEC/AT&T 07/29: Jep'd "Customer Not ready". LEC/AT&T W reached out to LCON (ELANGO MURUGAN) and no response. Elango is OOO until 08.01. Access needs to be coordinated w/ building engineer to provide access to MPOE. CNR will be removed end of week, PON will also be sent back out. 7/22: Pending an install date from ATT West. 7/9: Order rec'd
| 50M Port/100M Access EAVPN 1000Base-SX | AZ146-01-IM | UHG | Melissa Chapman | 4c Medical | 600 N Dobson Rd Ste D27 | Chandler, AZ |  | VS19163368 3102-1148 3102-BBMF 3102-BBMD ORIG ORDER: VS19152598 3102-1125 3102-BBLG | 2019-09-11 | 2019-11-29 | ASAP | 2019-12-19 |  | Y | IUEC.543452 | Qwest | 19KXGS451042MS | 2019-12-04 | 1ST FLOOR DMARC SE CORNER OF BUILDING CIENA 3916 OPTICAL POR |  |  |  | 51 | 10.1.90.113 | 10.1.90.114 | 65268 | 202610 | UHG GLOBAL 150 | 12/19: ORDER COMPLETE 12/12-12/17: Pending testing completion. 12/3: Access install completed yesterday ahead of schedule. Pending testing completion. 11/25: Access install has been updated and improved to 12/4/2019. 11/4-11/18: Switching gears on this order and going back to the original USO 3102-1125 which was not cancelled - Qwest is the access provider and is showing a 2/7 access install date. 10/29: Per Melissa, Since Cox has the POP collector, can we order this on Qwest again? Can we use the IP addressing we used on the original Qwest order? 10/28: PER PROVISIONING - YOUR ORDER HAS TO WAIT FOR THE COLLECTOR CIRCUIT BUILD. 120-150 DAY PROCESS 10/15-10/21: Issued AERO Design 760711 to submit PON to LEC. 10/7: New USO's rec'd - pending install date from Cox. 10/1: Switching providers - Pending new order info - UPDATE: LOOK TO REISSUE USING COX 9/24: Qwest provided a 2/10/2020 install date.1B OUTSIDE PLANT (OSP) - MAJOR BUILD 9/17-9/23: Pending an install date from Qwest 9/11: Order rec'd
| Cancelled 7xT1 AVPN | NY498-04-IM | UHG | Melissa Chapman |  | 161 Canal St. | New York, NY |  | VS19171817 3102-1623-FR 3102-1622 3102-1626 3102-1627 3102-1621 3102-1628 3102-1625 3102-1624 3102-BBMT | 2019-10-24 | 2019-11-27 | 2019-11-27 |  |  | Y | DHEC.330916.811 DHEC.330916.812 DHEC.330916.813 DHEC.330916.814 DHEC.330916.815 DHEC.330916.816 DHEC.330916.817 | Verizon - North | 32HCGS917602NY 32HCGS917598NY 32HCGS917416NY 32HCGS917468NY 32HCGS917601NY 32HCGS917599NY 32HCGS917600NY | 12/6/2019 11/27/2019 11/18/2019 12/3/2019 3/2/2020 11/27/2019 11/14/2019 | [7 empty] | 64607 | 202610 | UHG GLOBAL 150 | 12/3: All dates are missed or pushed out as far as March 2020 due to facility issues at site. UPDATE: REC'd CANCELLATION REQUEST FROM MELISSA CHAPMAN - ISSUED HITS TICKET TO CANCEL ORDER. 11/25: Looks like Verizon is trying to reschedule for 11/27 (for at least 2 of the 3 T-1s left to install) - Verizon still indicating customer not allowing access to the site. 11/18: PER VERIZON NO ACCESS TO SITE ON 11/14. Pending redispatch (which are scheduled for 11/18 and 11/20.) 11/11: The LEC Verizon has provided (4) different install dates for access (why, I don't know)........11/7 (missed), 11/14, 11/15 and 11/18. No Copper, going with FIOS Fiber. 11/4: Provisioning design issues are being corrected to release PON to the LEC Verizon - "THE PON's ARE IN AF STATUS AND HAS BEEN REFERRED TO DESIGN VIA AN R15 FOR REVIEW AND CLEARANCE" - working with Provisioning Assembler team to push for status. 10/28: PON released to Verizon on 10/25. Pending install date. 10/25: USO's rec'd
| HOT ORDER 20M Port/50M Access EAVPN 1000Base-SX | UVA06-02-IM | UHG | Melissa Chapman |  | 12018 Sunrise Valley Drive, Suite 400 | Reston, VA |  | VS19166685 3102-1146 3102-BBLW 3102-BBLV | 2019-09-19 | 2019-10-14 | 2019-12-31 | 2019-12-19 |  | Y | BBEC.537877 | Verizon - South | 36KFGS311107CD | 2019-12-09 | DEMARK 1ST FLOOR MTR WALL MOUNT UNIT 5 TAGGED WITH IDS |  |  |  | 50 | 10.1.90.77 | 10.1.90.78 | 65176 | 202610 | UHG GLOBAL 150 | 12/20: ORDER COMPLETE 12/16: Added to HOT list per Melissa's request - need this ASAP this month (Dec.) Pending testing completion and the OK to turn up. Overall due date is 12/31 but pushing for sooner. 12/12: Access install has completed - VLAN PON HESV4372130 was due 12/17 but is showing completed as well. Pending testing completion and the OK to turn up. 11/25-12/3: PON was supp'd on 11/19 changing LCON name. Pending install date. 7ES02920452 11/18: Updated AERO Des ticket 795204 - advised that USO HAS BEEN CHANGED - NEED TO HAVE THE R15 REMOVED AND PON SUPP'D BACK ADVISING THE LEC THAT LCON WAS CHANGED TO /LCON JEFF DOBIES, 703 929-4623, JEFF.DOBIES@BROOKFIELDPROPERTIES.COM 11/11: Pending status on new install date from Verizon - HITS ticket was issued to change LCON/ALCON to Jeff Dobies and Bryan Hagadorn per Melissa's direction. Once USO is confirmed changed, the PON will be supp'd to the LEC. 11/4: Please verify LCON info and I'll have the PON supp'd back to Verizon to request a new install date. 10/15-10/28: Pending an install date from the LEC Verizon South. AERO DES 773887 (R15) - UPDATE: PER LEC/PROVISIONING, REJECTED DUE TO UNRESPONSIVE LOCAL CONTACTS. Please verify LCON info. 9/19: Order rec'd
New | 10MB Port/ 50M Access EaAVPN 1000 Base-SX | TX537-02-IM | UHG | Melissa Chapman | Wellmed | 800 N. Bishop Ave., Suite 2 | Dallas, TX |  | VS19192222 3094-2356 3094-BVXF | 2019-11-25 | 2020-03-02 | 2020-03-02 |  |  | Y | BMEC.781114 | ATT SW | [7 empty] | 10.1.86.149 | 10.1.86.150 | 65410 | 202610 | UHG GLOBAL 150 | 12/16: Confirmed cancellation ticket issued in IOS. 12/2: Melissa cancelled order 11/25: Order rec'd
| 100M Port/100M Access EAVPN 100Base-TX | CA438-01-IM | UHG | Melissa Chapman | Monarch | 5500 E. Atherton St. Ste. 416 | Long Beach, CA |  | VS19152588 3102-1105 3102-BBLD 3102-BBLC | 2019-09-03 | 2019-12-10 | 2019-12-10 | 2020-01-02 |  | Y | IUEC.846856 | Frontier-CTF | 45KEGS216113FTNC | 2019-12-11 | 1ST FL; TELCO RM IN GARAGE; SHELF 1; SLOT 3 |  |  |  | 86 | 172.27.27.241 | 172.27.27.242 | 64740 | 202610 | UHG GLOBAL 150 | 1/3: ORDER COMPLETE 12/30: Received R80 access completion notice on Friday 12/27. Pending receipt of access demarc and completion of testing. 12/16: Carrier Mgmt engaged - AERO TICKET #818100. Per the LEC - PENDING WORK ORDER - FOR CONSTRUCTION TO PLACE 100 FT OF FIBER - EXPECTED DD IS 12/24 DUE TO THIS FLUP 12/26. 12/12: At this point, access is not showing completed - this will need to be escalated by COB tomorrow 12/13 to meet the 48hrs escalation requirement post-install date. 9/30-12/3: Access install scheduled for 12/11. 9/17-9/23: Pending an install date from the LEC Frontier. 9/16: USO's rec'd 9/3: Order rec'd
| 10M Port/50M Access EaAVPN 1000Base-SX | IN123-02-IM | UHG | Melissa Chapman | HealthScope | 8901 Otis Avenue, Suite 200 | Indianapolis, IN (FORT BEN , IN) |  | VS19178330 3102-1225 3102-BBNQ | 2019-11-07 | 2020-01-28 | 2020-01-28 | 2019-12-31 |  | Y | BBEC.556087 | ATT MW | KRGN106588NB | 2019-11-20 | 2ND FLOOR 200,CX FIBER PANEL JACKS 1 & 2 |  |  |  | 50 | 10.1.87.169 | 10.1.87.170 | 65016 | 202610 | UHG GLOBAL 150 | 12/31: ORDER COMPLETE 12/31: UPDATE: INSIDE WIRING COMPLETED. TECHNICIAN DISPATCHED ON 12/30/2019. REACHED OUT TO ENOC FOR ORDER COMPLETION - Next follow up 1/2/2020. 12/12-12/30: Confirmed this is an INSIDE WIRING JEP due to LEC facilities, not customer. Working to firm up the completion date. 11/25: Access install delay - Message Type: CUSTOMER SITE NOT READY - PER FIELD TECH: ,NEED MULTI MODE FIBER RAN IN BSMNT FROM ROOM WITH CIENA TO ANOTHER ROOM IN BSMNT WITH FIBER PANEL THAT RUNS TO CUSTOMER SUITE 200. Per Construction, THIS ORDER IS BEING DELAYED DUE TO AN INSIDE WIRING JOB THAT REQUIRES A VENDOR/CONTRACTOR TO COMPLETE THE WORK. Pending target date for completion. Added note requesting clarification on who owns responsibility (customer or AT&T/Contruction.) 11/12-11/18: Access install scheduled for 11/20. 11/7: Order rec'd
New | 200MB Port/ 400M Access EaAVPN 1000 Base-SX | AL013-07-IM | UHG | Melissa Chapman | OptumRX | 4525 Executive Park Drive | Montgomery, AL |  | VS19189596 3102-1299 3102-BBPP | 2019-11-18 | 2019-12-13 | 2019-12-13 | 2019-12-18 |  |  | BLEC.990424 | ATT SE ONNET-5 | A1KRGN401781SC | 2019-12-13 | 1ST FLR SEVER RM RELAY RACK MOUNTED CK 2 |  |  |  | 50 | 10.1.87.181 | 10.1.87.182 | 64806 | 202610 | UHG GLOBAL 150 | 12/30: ORDER COMPLETE 12/16: CNR Customer Not Ready - PON needs to be supp'd for redispatch - LCON NOT AVAILABLE / NO ACCESS 12/12: Access install scheduled for 12/13. 11/19-12/3: USO's rec'd - pending install date. FOC due back by 12/20. 11/18: Order rec'd
New | CANCELLED 10MB Port/ 50M Access EaAVPN 1000 Base-SX | TX537-02-IM | UHG | Melissa Chapman | Wellmed | 800 N. Bishop Ave., Suite 2 | Dallas, TX |  | VS19195324 3094-0139 3094-BVXH |  | 2020-03-09 | 2020-03-09 |  |  |  | BBEC.575546 | ATT SW | [9 empty] | 65410 | 202610 | UHG GLOBAL 150 | 1/7: Issued CANCELLATION per Melissa. 12/30-1/6: CNR LCON CONTACTED BUT WILL NOT COMMIT TO SITE VISIT DATE.
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX493-02-IM | UHG | Melissa Chapman | Wellmed | 615 Zaragoza | El Paso, TX |  | VS19126158 3102-0943 7MS02359096 3102-BBJT | 2019-07-15 | 2019-10-09 | 2019-10-09 |  |  | Y | BBEC.520477 | ATT SW | 30KRGN615322SW | 2020-01-08 | 1ST MECH/LAN FIRST FLOOR MECH/LAN ROOM PATCH PANEL |  |  |  | 50 | 10.1.94.117 | 10.1.94.118 | 65030 | 202610 | UHG GLOBAL 150 | 1/10: ORDER COMPLETE 1/6: Access install showing on track for 1/8/20 12/30: NTE placement completed 12/23. Access install showing on track for 1/8/20. 9/16-12/16: C&E Fiber work due 12/24. Access install moved up to 1/8/2020. 9/3-9/9: C&E Fiber work due 12/24. Access install scheduled for 1/13/2020. 8/26: C&E FIBER PL & SPL FUTURE COMPLEX BUILD 12/24/19 - F/U 9/6/2019 === SITE VISIT CONDUCTED BY ALBERTO ROBLES OF UNDC 7404326521. SITE CONTACT JASON OZER NOT PRESENT FOR SITE VISIT 2102501454. UNITED HEALTH CARE SERVICES ARE LOCATED IN SUITE 86 GPS 31.705040, -106.320954. ROOM READY. EXISTING FIBER TERMINAL APPROX. 600' FROM SUITE. NEW FIBER TERMINAL WILL BE PLACED ON NORTH WALL ON THE OUTSIDE OF THE BUILDING TO SERVE FUTURE SUITES. CIENA 3930 WILL BE PLACED IN SUITE 86 ON NORTH WALL. CUSTOMER PLANS TO INSTALL DROP CEILING IN SUITE AND ATT WILL HAVE TO DROP THROUGH TO CIENA. 8/12-8/19: Pending access install date. Per Construction team, waiting on equipment to be inventoried in order to finalize build details for FOC. Currently tracking for completing the build on 8/24 but working to firm this up. 7/15: Order rec'd
| 10M Port/50M Access EaAVPN 1000Base-SX | TX536-02-IM | UHG | Melissa Chapman | Wellmed | 1108 Dallas Dr. Suite # 337 | Denton, TX |  | VS19176071 3102-1215 3102-BBNL 3102-BBNK | 2019-10-31 | 2020-01-31 | 2020-01-31 | 2020-01-08 |  |  | BBEC.554682 | Frontier-CTF | 13KFGS256388FTNC | 2019-12-19 |  |  |  |  | 2 | 10.1.87.13 | 10.1.87.14 | 65110 | 202610 | UHG GLOBAL 150 | 1/8: ORDER COMPLETE 1/6: Pending access completion - per LEC Frontier, CUSTOMER SITE IS NOT READY. THEY NEED TO PLACE A BACKBOARD 12/30: AERO CM 826297 - Carrier Mgmt engaged - Frontier advised access install should be completed by end of this week. 11/25-12/16: Access install scheduled for 12/19. 11/11-11/18: Pending an install date from Frontier-CTF - FOC due back by 12/13. 10/31: Order rec'd
| HOT ORDER 10M Port/50M Access EAVPN 1000Base-SX | TX440-02-IM | UHG | Melissa Chapman | Wellmed | 524 Singing Oaks,Suite 200 | Bulverde-Spring Branch, TX |  | VS19182351 3102-1263 3102-BBPH 3102-BBPG | 2019-08-19 | 2020-02-17 | 2020-02-17 | 2020-01-20 |  | Y | BBEC.559374 | GVCS CLEC | 31KQA5438224GVC | 2020-01-14 | LABELLED, OPTICAL, INTERFACE MODE, UNTAGGED TUNNEL, JACK TYPE OPTICAL 2ND FLOOR, COMM ROOM, FIBRE MEET MEBOX, PORT 1. |  |  |  | 75 | 10.1.91.221 | 10.1.91.222 | 64682 | 202610 | UHG GLOBAL 150 | 1/20: Confirmed access has completed - pending testing completion and OK to turn up. - UPDATE: ORDER COMPLETE 1/6-1/13: Access install date was revised to 1/14. - Carrier Mgmt is engaged - AERO ticket 839017 IN REF TO PON GMS02378838, CALLED GUADALUPE VALLEY COMM. FOR AN UPDATE. AS PER LEC, ECD= 01/14/2020. FOLLOW UP DATE : 01/15/2020 12/12-12/30: Access install scheduled for 1/6/2020. 12/3: Followed up with the Assembler for update on PON. 11/25: Issued AERO ticket 801793 to release PON to the LEC. 11/11: Pending USO's 10/22: Order released yesterday - addendum countersigned 9/10: This is special bid per Chris 8/28: Added to hot list - I reached out to Chris Cowan to check on the USO’s for this order and he advised it was just processed yesterday through Business Center so nothing back yet. 8/19: Pending USO's
| HOT ORDER 10M Port/50M Access EAVPN 1000Base-SX | TX516-02-IM | UHG | Melissa Chapman | Wellmed | 509 S. Expressway 83 | Harlingen, TX |  | VS19166683 3102-0275 3102-BBMK | 2019-09-18 | 2019-10-14 | 2019-12-31 |  |  | Y | BBEC.588879 | ATT SW | 38KRGN613960SW | 2020-01-13 | 1ST FLR,IT RM,CIENA 3903 WALL MT, PORT 2 CKT ID TAG |  |  |  | 50 | 10.1.87.105 | 10.1.87.106 | 64660 | 202610 | UHG GLOBAL 150 | 1/13: ORDER COMPLETE 1/6: Pending CTA testing and order turn up - delayed as electricians onsite advised they were working on the electrical panel. Once confirmed they're up on perm power, we'll have tech test. 12/30: UNABLE TO CONTACT TESTER FOR MANUAL TURNUP, NO POWER UPON ARRIVAL, SPOKE TO ELECTRICIANS ON SITE AND THEY ADVISE THEY WERE STILL WORKING ON THE ELECTRICAL PANEL;DEMARC:1ST FLR,IT RM,CIENA 3903 WALL MT, PORT 2 CKT ID TAG 12/16: Pending release PON supp. 12/12: Received email from Bill Gipson regarding power at the site including pics. I checked the Construction website and they're showing fiber work completed as of 12/3. I've requested the PRE-CTA CNR team remove the customer not ready coding from the order and that the PON be supp'd to request LEC redispatch based on this news from the customer. 12/12 10AM UPDATE: CNR CODING IS REMOVED - ISSUED DDF TICKET TO HAVE THE PON SUPP'D FOR REDISPATCH ASAP. 12/4: Added to HOT list per Melissa's request - UHG needs an active circuit by 1/25. 10/21-12/3: Access install scheduled for 1/13/2020…...Fiber install showing scheduled for 12/30/2019. 10/15: Pending an install date from the LEC ATT SW. 9/18: Order rec'd
| 300M Port/600M Access EAVPN 1000Base-SX | PR518-02-IM | UHG | Melissa Chapman | Optum Puerto Rico | 997 San Roberto St. | San Juan, PR |  | VS19142137 3102-1008 7SS03614292 3102-BBKK 3102-BBKJ HSSV4329989 | 2019-08-13 | 2019-11-19 | 2019-11-19 | 2020-01-17 |  | Y | BEEC.552652 | Centennial of PR | BEEC552652CEN |  | DEMARC: COMM ROOM OF THE BLDG., RACK MTD ON LEFT SIDE OF COMM RM, FLR P1, CISCO 3400, MM SFP, GI0/3. CUSTOMER WILL HAVE TO EXTD WIRING FROM COMM RM TO CUST OFFICE ON 10TH FLR PER OMAR.. EXTENDED WIRE: DEMARC LABELED AT&T |  |  |  | 128 | 10.1.95.85 | 10.1.95.86 | 65256 | 202610 | UHG GLOBAL 150 | 1/20: ORDER COMPLETE 1/13: Per Preetesh, "I’ve been back and forth with our team regarding this order as there were major issues at the time of testing. Our engineering team was taking a look at this as the circuit would never reach the requested 600Mbps bandwidth. Ultimately it was decided to have the circuit moved to another equipment, and provisioned. Currently the DLR is being worked, and we are expecting to have the circuit installed tomorrow in the afternoon." 1/7: Added to HOT list. Escalated to next level above Preetesh in Puerto Rico for status. 1/6: Follow up - Reached out to Preetesh Mirchandani, PMP in Puerto Rico for status. HOT LIST 12/30: Reached out to Preetesh Mirchandani, PMP in Puerto Rico for status. 12/17: I reached out to my contact down on the LEC side to see if they had status and here’s what he provided: “We were looking to work with the LCON on having the service extended from the MPOE to the customer’s suite, but the LCON listed in the order isn’t from United Health, rather the property manager. If the service can be demark’d at the MPOE, we will proceed. Sorry about the confusion. We expect to have this order completed out this afternoon.” 12/16: Follow up escalation to find out status from the LEC Centennial. 12/12: Escalated to Lawrence Manning (Carrier Mgmt AM) to go back to Centennial for status of install. Jane Tansor (AM - Service Delivery) engaged. 12/3: Escalated to Lawrence Manning (Carrier Mgmt AM) for his engagement. Centennial was closed last week when an attempt was made to push for status - next follow up was scheduled for yesterday but not seeing news yet. 11/25: Escalated to Carrier Management - (Quentin Thomas - I/C for Lawrence Manning) - Requested escalation to Centennial for update on access. 11/18: AERO CM ticket 745036 - Requested update from the Carrier Mgmt team and that they escalate to Centennial for status of install. 11/4-11/11: ATT Escalation team reached out to Centennial to provide clarification on buildings at the site - per escalation team, PROVIDED INFO TO PR10 MGR - NEXT F/UP 11/5 10/28: Per Centennial of PR - WE NEED CLARIFICATION ON THIS ORDER. THEE ASR STATES THE ADDRESS AS PFIZER BUILDING 10TH FLOOR. THERE IS NO 10TH FLOOR AT THIS BUILDING. ALSO, THE LCON IS UNAWARE OF THIS ORDER PLEASE SUP WITH CLARIFICATION. Sent info to Melissa for follow up. - UPDATE: PROVIDED UPDATE FROM CUSTOMER TO CARRIER MGMT ON AERO ID 745036. Per the customer: "THE ADDRESS YOU HAVE IS CORRECT, HOWEVER, THE BUILDING IS NOT THE PFIZER BUILDING. THE PFIZER BUILDING IS NEXT DOOR AND IT IS ONLY 5 FLOORS. THIS BUILDING USED TO BE ANCHORED BY ORIENTAL BANK AND THUS PEOPLE MIGHT REFER TO IT AS THE ORIENTAL BUILDING. MAYBE THAT HELPS. PS – THE PEOPLE FROM AT&T/CENTENNIAL ARE LITERALY LOCATED ON THE BUILDING RIGHT NEXT TO THE ONE YOU LEASED. THEY BOTH EVEN SHARE A PARKING GARAGE. IF YOU MENTION THE OLD ORIENTAL BUILDING RIGHT BEHIND THE CENTENNIAL BUILDING, THEY WILL IMMEDIATELY KNOW WHERE YOU ARE AT." 10/21: Pending update from Centennial and Carrier Mgmt - expecting delivery this week. 10/15: PER CENTENNIAL - "THE ORDER HAS BEEN PROCESSED, AND IS CURRENTLY HAVING THE DLR WORKED BY OUR TEAM. WE EXPECT TO HAVE THIS SERVICE INSTALLED BY EARLY NEXT WEEK" 10/8: AERO CM 745036 opened with Carrier Mgmt on 10/1 -- I have requested they "escalate back to Centennial of PR for status of the access and VLAN PON's. We need to hold them accountable for these missed dates. Please engage Tier II." 9/30: ZENOBIA/CARRIER MANAGEMENT/ TIER I/ TICKET 738094 - Reached out twice to Centennial so far - follow up 10/1. LEC ID was provided by Centennial with a 9/23 install date but not yet confirmed it completed. 9/23: DENISE CARRIER MANAGEMENT TIER 1 engaged - reached out directly to Centennial - pending response. Follow up 9/24 9/16: HALO ticket issued for missed FOC. Still pending an install date from Centennial. Requested Carrier Mgmt be engaged to push for an install date. 9/3-9/9: Pending install date date from LEC. 8/29: Order loaded in SOTS 8/15-8/27: Pending USO's - USO's not loaded - HITS ticket issued 8/26.
| 20M Port/50M Access EaAVPN 1000Base-SX | FL406-02-IM | UHG | Melissa Chapman | Health Markets | 1060 Maitland Center Commons Blvd | Maitland, FL |  | VS19172517 3102-1165 7SS03630171 3102-BBMQ 3102-BBMP | 2019-10-18 | 2020-01-14 | 2020-01-14 |  |  | Y | BBEC.571329 | Embarq | 25KXGS469197SMPN | 2020-01-14 | 1ST FL MAIN TELCO WALL MOUNT |  |  |  | 2 | 10.45.10.117 | 10.45.10.118 | 65420 | 202610 | UHG GLOBAL 150 | 1/10: ORDER COMPLETE 1/6: Access install moved up to 1/10. 12/3-12/30: Access install scheduled by Embarq for 1/14/2020. 11/18-11/25: Pending FOC from new access PON 7SS03630171 - BERT/IOS Escalation Ticket issued for missed FOC. 11/11: New PON released on 11/7. Pending install date from the LEC CL/Embarq 11/6: PLEASE ISSUE NEW PON, ADDRESS HAS BEEN CORRECTED ON USO I.E. 1060 MAITLAND CENTER COMMONS STE 350 MAITLAND FL 32751, PLEASE ISSUE NEW PON ACCORDINGLY AND CLEAR ALL ADDRESS JEOP. ( FULL STREET NAME CANNOT UPDATE IN OCX SO PLEASE ISSUE THE PON WITH FULL STREET NAME I.E. MAITLAND CENTER COMMONS ) -- I believe this info was obtained by provisioning from the LCON. 11/4: HALO ticket issued to have Carrier Mgmt engaged to escalate on missed FOC by the LEC Embarq. 10/28: Pending install date from LEC Embarq 10/18: Order rec'd
| 200M Port/400M Access EaAVPN 1000Base-SX | KY027-02-IM | UHG | Melissa Chapman | Equian | 9420 Bunsen Way | Louisville, KY |  | VS19174417 3102-1209 3102-BBNH | 2019-10-22 | 2019-11-06 | 2020-01-14 | 2020-01-14 |  | Y | BLEC.989646 | ATT SE | K1KRGN402487SC | 2020-01-14 | 1 DATA RM WALL UNIT 1 PORT 5 |  |  |  | 50 | 10.1.87.45 | 10.1.87.46 | 64561 | 202610 | UHG GLOBAL 150 | 1/17: ORDER COMPLETE 1/6-1/13: Access install scheduled for 1/14. 12/30: PON HSS03640637 issued on 12/27. Pending install date. 12/12-12/16: Emailed Steph Ealy (AM) to find out why this order is not progressing. The SOTS notes indicate "Complex Address Issues" for this site and I'm trying to find out why. 12/3: This needs to be escalated to Assembler 903x 11/25: HITS ticket issued on 11/18 - Address for the order#305726406, address is validated and successfully supped and reflected in Winky. DDf ticket #201911180212 is raised to issue new PON on this order. Pending new date. 11/12-11/18: Added SUITE 250 to address - HITS ticket issued - Pending update from LEC. 11/12: For this site in Louisville, the address was rejected back with issues. I reached out to provisioning and was told “This address doesn't validate with 9420 BUNSEN PKWY…..it errors out as THIS ADDRESS ALSO HAS LIVING UNITS WITH SUPPLEMENTAL ADDRESSES.” 11/4-11/11: Pending access install date from ATT SE 10/22: Order rec'd
| 10M Port/50M Access EaAVPN 1000Base-SX | TX538-02-IM | UHG | Melissa Chapman | Wellmed | 912 Wright Street, Suite A | Arlington, TX |  | VS19180569 3102-1223 7MS02377947 3102-BBNZ | 2019-11-11 | 2020-02-03 | 2020-02-03 | 2020-01-15 |  | Y | BBEC.556366 | ATT SW | 14KRGN887300SW | 2020-01-22 | 1 SUITE A TELCO CLOSET BB |  |  |  | 50 | 10.1.86.177 | 10.1.86.178 | 65413 | 202610 | UHG GLOBAL 150 | 1/20: Access install complete - ORDER COMPLETE 1/13: Fiber work completed last week. Pending access completion (pending for today.) NOTE FROM LEC: PENDING DISPATCH "FIELD TECH HAS BEEN ASSIGNED NO ETA YET" 12/3-1/6: Fiber work scheduled for 1/9 - Access install scheduled for 1/22. 11/25: Target completion date from Construction for Fiber Work - 1/9/20. Pending access install date. 11/15-11/18: Pending install date from the LEC ATT SW. Construction site visit scheduled for 11/19. 11/11: Order rec'd
| 400M Port/500M Access EaAVPN 1000Base-SX | DC007-06-IM | UHG | Melissa Chapman | Optum Insight | 655 New York Ave | Washington, D.C. |  | VS19180556 3102-0293 3102-BBNY 3102-BBNX | 2019-11-05 | 2020-02-03 | 2020-02-03 | 2020-01-23 |  | Y | BMEC.968416 | Verizon South | 36KFGS311282CD | 2020-01-15 | P1 LEVEL MTR VZ RR 1 SHELF 13 |  |  |  | 842 | 10.1.87.109 | 10.1.87.110 | 64813 | 202610 | UHG GLOBAL 150 | 1/24: ORDER COMPLETE 1/21: VLAN (EVC) PON HESV4397255 was sent today and completed this morning by Verizon. Pending testing completion and the OK to turn up. I'll push this back to Design for Engineering completion and than work to have this tested. 1/20: Issued AERO DESIGN 851518 to have EVC PON issued to Verizon. 1/13: Verizon installed access ahead of schedule. Demarc provided. Pending release of the VLAN PON to Verizon and target completion date. 12/12-1/6: Access install scheduled for 1/15/20. 11/15-12/3: USO's loaded - pending install date from LEC Verizon South. FOC due 12/20. 11/5: Order rec'd
New | HOT ORDER 10MB Port/ 50M Access EaAVPN 1000 Base-SX | C1648-02-IM | UHG | Melissa Chapman | Nice_Data_Center | 900 N Alameda St | Los Angeles, CA |  | VS20011887 3094-2440 3094-BVYD | 2020-01-02 | ASAP | 2020-04-13 | 2020-02-07 |  |  | BBEC.576514 | ATT West | 13KRGN601495PT | 2020-02-06 | 2A2 PORT 9 &10 TAGGED |  |  |  | 50 | 10.191.22.69 | 10.191.22.70 | 65420 | 202609 | UHGECC GLOBAL | 2/11: ORDER COMPLETE 2/3: Access install scheduled for 2/6. 1/28: Added to HOT order list - USO's rec'd this morning. PON released to ATT West. Pending construction/access install dates. 1/2: Order rec'd
| 100M Port/100M Access EAVPN 1000Base-SX | AZ150-02-IM | UHG | Melissa Chapman | 4c Medical | 9590 E Ironwood Square Dr #125 | Scottsdale, AZ |  | VS19157766 3102-0257 3102-BBLN | 2019-09-10 | 2019-12-11 | 2019-12-11 | 2020-02-04 |  | Y | IUEC.938298 | Qwest | 19KXGS454090MS | 2020-02-19 | 1ST FLR MAIN IT, KEY WITH CUSTOMER STE 125 NORTH WALL MOUNTE |  |  |  | 50 | 10.1.93.109 | 10.1.93.110 | 65179 | 202610 | UHG GLOBAL 150 | 2/4: ORDER COMPLETE 2/3: Access install completed ahead of schedule. Pending testing completion and the OK to turn up. ADDED TO THE WWR INTERNAL SHEET TO BE WORKED ASAP 1/27: LEC Centurylink provided an updated target date for install of 2/4. 1/20: LEC Centurylink targeting 2/19 for install - 3A BOTH OSP AND IOF - MINOR BUILD 1/6-1/20: PENDING ROE - Access install date is showing updated on 12/31 by the LEC Centurylink targeting 2/19/20. 12/12: Reached out to Melissa to see if we had any news back from Kathy (Centurlink) regarding the backboard, work, etc. UPDATE FROM MELISSA: "Nothing yet. I just followed up to see if she has anything new." 12/4: Per Melissa's email from Kathy Zales (Centurylink Wholesale) - "Centurylink will be placing the backboard. We are working with property mgmt. / owner on the approvals to do the work." 12/3: Per Qwest, 2/19 is the install date - PEND EASEMENT BEA ROW PLACED TO MEET POINT ON 11/15/2019. PENDING BEA TO PLACE PREM WORK BACKBOARD. 11/18-11/25: CNR CUSTOMER NOT READY per the LEC - SUPI: N RCODE: 1S=BUILDING NOT READY, CUSTOMER WILL ADVISE RDET: CUSTOMER NOT READY - ADDL INFORMATION TO FOLLOW 11/4-11/11: Access install still showing on track for 2/19. Working to improve. 10/29: Per Melissa, Grounding BAR is in place. 10/15-10/28: Access install showing 2/19/2020 - PER LEC, 3A BOTH OSP AND IOF - MINOR BUILD 10/1-10/7: Pending an install date from the LEC Qwest 9/25: USO's rec'd 9/10: Order rec'd
| 50M Port/100M Access EAVPN 1000Base-SX | AZ145-01-IM | UHG | Melissa Chapman | 4c Medical | 36889 N Tom Darlington Dr #A-4 | Carefree, AZ |  | VS19152600 3102-1107 3102-BBLF | 2019-09-12 | 2019-11-29 | 2019-11-29 | 2020-02-05 |  | Y | IUEC.534132 | Qwest | 19KXGS451476MS | 2020-02-11 | 1ST FLOOR MAIN IT- CTL LOCK BOX, NORTHSIDE OF BLDG . WALL MOU |  |  |  | 55 | 10.1.87.185 | 10.1.87.186 | 65100 | 202610 | UHG GLOBAL 150 | 2/5: ORDER COMPLETE 10/7-2/3: The Qwest 2/11/20 access install date remains unchanged. 10/1: UPDATE per Chris - DO NOT CANCEL THE CAREFREE, AZ order. The site does not qualify for any other ESP than Qwest, who we have the order with today. 10/1: LEC Qwest provided a 2/11/2020 access install date. 2A INTEROFFICE FACILITY (IOF) - MINOR BUILD - UPDATE: LOOK TO REISSUE USING COX 9/17-9/23: Pending an install date from Qwest 9/12: Order rec'd
| 50M Port/100M Access EAVPN 1000Base-SX | AZ151-01-IM | UHG | Melissa Chapman |  | 14811 W Bell Rd | Surprise, AZ |  | VS19166681 3102-1140 3102-BBLT | 2019-09-13 | 2019-12-31 | 2019-12-31 | 2020-02-07 |  | Y | IUEC.823018 | Qwest | 19KXGS462826MS | 2019-02-27 | 1ST FLOOR RISER ROOM/IT WALL MOUNTED, NW CORNER OF BUILDING. |  |  |  | 63 | 10.1.88.173 | 10.1.88.174 | 64596 | 202610 | UHG GLOBAL 150 | 2/11: ORDER COMPLETE 2/3: ORDER DELAY - PER LEC, CUSTOMER NOT READY - ADDL INFORMATION TO FOLLOW. PEND EASEMENT BEA ROE 11/4-1/27: Access install scheduled for 2/27/20 10/15-10/28: Pending an install date from the LEC Qwest. 9/13: Order rec'd
| 5M Port/50M Access EaAVPN 1000Base-SX | TX366-01-IM | UHG | Melissa Chapman | OPTUM-M&R | 6242 Rufe Snow Drive, Suite 218 | North Richland Hills, TX |  | VS19178331 3102-1222 3102-BBNT | 2019-11-06 | 2020-01-28 | 2020-01-28 | 2020-02-10 |  | Y | BBEC.558892 | ATT SW | 14KRGN887263SW | 2020-01-29 | 1ST TELCO CIENA 3903X PORT-2 |  |  |  | 50 | 10.1.86.213 | 10.1.86.214 | 65415 | 202610 | UHG GLOBAL 150 | 2/11: ORDER COMPLETE 2/3: Access install rescheduled for 2/10. 1/20-1/27: Confirmed fiber work is now complete - access install was moved up from 1/29 to 1/17 but was missed due to CNR - PER LEC: CUSTOMER NOT READY MESSAGE NOTES CUSTOMER IS NOT READY;NEED COMMERCIAL POWER AND BACKBOARD INSTALLED. PON NEEDS TO BE SUPP'D WHEN SITE IS READY 12/3-1/13: Per Construction, EF offer accepted - prem ready date is 1/16/20 with fiber work targeted to complete that same day. Access install scheduled for 1/29/20. These requirements were thoroughly covered during the site visit conducted on 11/19/19 with CHRIS COPELAND. The following requirements need to be completed in full by 12/30/19 to avoid a delay of your ASE order. Per your acceptance of the ASE Entrance Facility Offer, AT&T will complete the specified site readiness requirements listed below: - Minimum 1½" hard plastic innerduct or 2" EMT type conduit (per electrical code) with pull tape is required from the Main Equipment Room (Common Area) to another interior location within the building as identified by the AT&T Representative. Paths longer than 300' or with two or more 90 degree turns will require a pull box no higher than 10 feet from floor level and have the minimum dimensions (12"x12"x4" Deep) 11/12-11/25: Pending an install date from the LEC - FOC due back by 12/4. 11/6: Order rec'd
New | 200MB Port/ 500M Access EaAVPN 1000 Base-SX | UCA56-09-IM | UHG | Melissa Chapman | Pacificare | 3515 Harbor Blvd | Costa Mesa, CA |  | VS20003255 3102-1319 3102-BBQB | 2019-12-18 | 2020-01-16 | 2020-01-16 | 2020-02-10 |  |  | BMEC.936469 | ATT West Onnet | 13KRGN601317PT | 2020-02-10 | FIRST SERVER FIRST FLOOR SERVER ROOM |  |  |  | 50 | 10.1.86.113 | 10.1.86.114 | 64906 | 202610 | UHG GLOBAL 150 | 2/11: ORDER COMPLETE 2/3: Access install rescheduled for 2/10. 1/27: Please advise if customer is ready - PON will need to be supp'd with site is ready to request a new date MLK DAY ISSUE 1/21: Pending new install date - customer wasn't available yesterday (CNR) 1/13-1/20: Access install scheduled for 1/20. 12/18: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000Base-SX | TX431-02-IM | UHG | Melissa Chapman | Wellmed | 430 West Sunset, Suite 200 | San Antonio, TX |  | VS19119205 3102-0865 HMS02386240 3102-BBHQ | 2019-07-02 | ASAP | 2019-09-26 | 2020-02-13 |  | Y | BBEC.562489 | ATT SW | 31KRGN654524SW | 2020-02-05 | 2ND FL TLCO RM HAND OFF TRAY PORT 3 | 1000 BASE SX |  |  | 50 | 10.1.87.201 | 10.1.87.202 | 65088 COS 6039 | 202610 | UHG GLOBAL 150 | 2/14: ORDER COMPLETE 2/11: Escalating on missed install which I'm told will require redispatch. Pending update from Construction/Field Tech. 1/21-2/3: Access install has been scheduled for 2/5. 1/10-1/20: Melissa advised site is ready - issued new PON HMS02386240 to LEC. FOC due back by 2/3. 11/25-1/6: Awaiting update on power install from UHG - PON will need to be supp'd (pending update from customer on 12/2) 11/18: Pending update on power install at site - NO POWER ONSITE UNTIL 11/18 11/11: Construction is advising that the site is NOT ready - although fiber work was showing completed on the construction side, the dates are all now showing INCOMPLETE and it has been rejected with CNR REASON: CNR-PATH/PWR/GRD/SPACE. Need to confirm the status of the site before we can push back to Construction. NO POWER ONSITE 11/18 11/4: BERT/IOS escalation ticket issued for missed install - no updates on the LEC side. 10/21-10/28: Access install scheduled for 10/29. 10/7-10/15: Fiber work completed ahead of schedule on 10/01. Access install still showing on track for 10/29. 8/19-9/30: Access install on track for 10/29 install date. Fiber work scheduled to complete 10/15 7/22-8/12: Construction update: This is a NEW Construction 4 story building. Baptist Medical will occupy the first floor, Wellmed will occupy the 2nd Floor. 3rd is vacant and then there will be a food court type places on the 4th floor. Conduit is in place in the Main Mechanical room in the underground parking facility. Conduit also exist from the mechanical room to each IDF closet on all floors. 3rd Floor layout has not been approved as of yet so move in date is unknown. Interior framing for Baptist Medical is under way. FLOORS - 4 TENANTS - 2 OWNED – Tenant FDF COUNT - NA NEED BACKBOARD, POWER AND GROUND ON WAL - NWAL WALL MOUNT NTE ON WAL - NWAL ON SITE CONTACT – Gabriel Rodriguez, 2109746678 EMT - Y MMP LOCATION - TELCO ROOM IW SUGGESTED PATH - NEXT TO FDF ENGINEER - Mike Petit, TrueNet, 2147097602 7/17: Pending access install date. 7/2: Order rec'd
New | 50M Port/100M Access EAVPN 1000Base-SX |  | UHG | Melissa Chapman | 4c Medical | 4110 N 108th Ave | Phoenix, AZ |  | VS19196731 3102-0281 3102-BBPV 3102-BBPT |  | 2020-03-20 | 2020-03-20 | 2020-02-24 |  | Y | IUEC.607163 | Cox Communications | 23KFGX991774COXC | 2020-02-07 | GROUND FLOOR INSIDE FIRE RISER. ROOM ON THE LEFT SIDE OF THE BLDG ON THE EAST WALL, INSIDE AN 19 INCH RACK, FTP PANEL PORT 1. |  |  |  | 235 | 10.1.86.249 | 10.1.86.250 | 64919 | 202610 | UHG GLOBAL 150 | 2/24: Reached out to Sheila Randolph for WWR - UPDATE: ORDER COMPLETE 2/11-2/17: Access and VLAN have been completed by the LEC - pending demarc info and completion of testing. Future due 3/10. 1/20-2/3: Cox access install scheduled for 2/7. 1/13: PON released on 1/7. Pending FOC - due back by 2/10. 1/7: Issued HITS ticket to have the OM change the AAV code to drive this to COX. 12/30-1/6: Pending release of the PON to the LEC Cox. AERO Design 837214 12/24: USO's rec'd 11/18-12/12: New order issued using COX as the access provider. Pending USO's
| 500M Port/1G Access EaAVPN 1000Base-SX | IN710-02-IM | UHG | Melissa Chapman | Equian | 650 W Henry St | Indianapolis, IN |  | VS19189106 3102-1297 7CS04372990 3102-BBPK | 2019-12-04 | 2020-02-21 | 2020-02-21 | 2020-02-21 |  |  | IZEC.506419 | ATT MW | KRGN106635NB | 2020-02-12 | FLOOR 3,TELCO ROOM,RR.0300.02 PLNG 1 PORT 7 AND 8 |  |  |  | 50 | 10.45.10.105 | 10.45.10.106 | 64584 | 202610 | UHG GLOBAL 150 | 2/21: ORDER COMPLETE 2/17: Access install complete - pending testing completion and OK to turn up. 2/11: Possible delay on access install - LEC showing LATE DROP ON DESIGN which appears to be delaying install. Pending new completion date. 2/3: Access install scheduled for 2/12. 1/27-1/28: Carrier Management was escalating on this order this morning - ticket 829405 - pushing to get Ethernet FOC from ATT MW 1/20: Carrier Mgmt pushed back to Construction for target completion date. Once rec'd we'll push for access install date. 1/13: Carrier Mgmt engaged on AERO ticket 829405 - pending update 1/6: AERO CM 829405 ticket opened for missed FOC. Pending install date from ATT MW - engaging Carrier Mgmt. 12/12-12/30: Pending install date from ATT MW
New | 500M Port/ 1G Access EaAVPN 1000 Base-LX | KY706-02-IM | UHG | Melissa Chapman | Genoa | 401 S 4th St | Louisville, KY |  | VS20004026 3102-1346 3102-BBQF | 2020-01-07 | 2020-03-26 | 2020-03-26 | 2020-02-20 |  |  | IZEC.567327 | ATT SE | K1KRGN402492SC | 2020-02-20 | 3RD FLR TELCO RM, SERV UNIT #1, PORT #1, TAGGED W/ ID S | 1000 BASE LX/LH |  |  | 50 | 10.1.87.121 | 10.1.87.122 | 65432 | 202610 | UHG GLOBAL 150 | 2/21: ORDER COMPLETE 2/17: LEC requested VLAN PON. Checked and the original PON was cancelled. Issued DDF Ticket 202002170065 to release VLAN PON to LEC. Unsure if this will affect install date of 2/20. (NOTE: COMPLETION NOTICE SENT IN ERROR) 2/11: Access install is scheduled for 2/20. 2/3: Access install rescheduled for 2/7. 1/27: We're being advised this is CUSTOMER NOT READY - CNR ---> JUSTIN ROSSI 5026185535 W/ WEST IP IS DENYING ACCE SS AT THIS TIME PENDING CONTRACT FINALIZATION WITH HEALTHCARE SYSTEMS 1/20: Access install scheduled for 1/22. 1/14: Pending an install date from ATT SE. Construction site visit scheduled for 1/15. 1/7: Order rec'd
| HOT ORDER 10M Port/50M Access EAVPN 1000Base-SX | TX473-02-IM | UHG | Melissa Chapman | Wellmed | 601 Crystal Falls Parkway, Suite 100 | Leander, TX |  | VS19164079 3102-1149 7MS02372106 3102-BBMG | 2019-08-21 | 2019-12-24 | 2019-12-24 | 2020-03-02 |  | Y | BBEC.585286 | ATT SW | 32KRGN653949SW | 2020-03-17 | 1ST FL IT ROOM PATCH PANEL 1 PORT 3/4 |  |  |  | 50 | 10.1.87.233 | 10.1.87.234 | 65222 | 202610 | UHG GLOBAL 150 | 3/3: ORDER COMPLETE 3/2: Access installed - demarc provided - the UNI Port SFP was missing so tech is redispatching to customer location to install the SFP. Pending ETA. 2/24: Confirmed new install date is 2/28. 2/17: No access install date improvement yet. I supp'd the PON to try and jump start this. Requested EAD is showing 2/27 but that is not confirmed. 2/11: Fiber Infrastructure completed ahead of schedule on Friday 2/7. Working to have the 3/17 install date moved in. 11/18-2/3: Construction scheduled fiber completion for 2/28/2020. NTE Placement on 3/4/2020. Access install scheduled for 3/17/2020. --- NOTES: Placing up to 2,000ft Fiber, Splicing, OBC Order Type of New EMT selected, Conduit required, Long Term Permits Required, Capital Cost exceeded regional threshold and the job will be bid and NTE required. 11/13: Added to hot list. 10/21-11/11: Construction scheduled fiber completion for 2/28/2020. Access install scheduled for 3/17/2020. --- NOTES: Placing up to 2,000ft Fiber, Splicing, OBC Order Type of New EMT selected, Conduit required, Long Term Permits Required, Capital Cost exceeded regional threshold and the job will be bid and NTE required. 10/15: Pending an install date from ATT SW 10/7: Pending USO's 10/4: Per Clyde, IP’s you provided for this order has been already 8/27: Per Chris, Please note that this order was processed through Business Center tool today with SBC as ESP.
New | HOT ORDER 500MB Port/ 1G Access EaADI 1000 Base-LX | UCA10-10-IJ | UHG | John Sergot |  | 5701 Katella Avenue | Cypress, CA |  | 3102-0488 7WS03835837 | 2020-01-17 | 2020-04-15 | 2020-04-15 | 2020-02-27 |  |  | IZEC.501343 | ATT West | 13KRGN601521PT | 2020-03-06 | RACK MOUNTED VIRTUAL EDGE PORTS 5 6 |  | Order Information AT&T Order Number: 1014877266 Order Type: New Start Interface Type: 1000 Base-LX AT&T Circuit ID: /IZEC/501343//ATI/ VLAN Tag Control: ARPA WAN Information IPv4 WAN IP Address: 32.140.143.196 IPv4 CR IP Address: 32.140.143.198 IPv4 AR IP Address: 32.140.143.197 IPv4 WAN Subnet Mask: 255.255.255.252 IPv6 WAN IP Address: 2001:1890:0C05:311A:0000:0000:FF2C:3F68 Compressed IPv6 CR IP Address: 2001:1890:0C05:311A:0000:0000:112C:3F68 Compressed IPv6 AR IP Address: 2001:1890:C05:311A::EE2C:3F68 Routing Routing Protocol: Static IPv4 Default Gateway: 32.140.143.197 IPv6 Default Gateway: 2001:1890:C05:311A::EE2C:3F68 LAN Information IPv4 LAN IP Address: IPv4 Subnet Mask: 255.255.255.240 IPv6 LAN IP Address: Additional Configuration Notes for WAN Interface Auto Negotiation: Off/Diabled Duplex Full | [7 empty] | 2/27: Order complete 2/17-2/24: No change - access install still showing due to complete on 3/6. 2/10: Fiber infrastructure completed. Pending date improvement for access install which is currently scheduled for 3/6. 2/7: The site visit was completed this past Tuesday and we’re currently pending an update from Construction on fiber dates as well as an install date for access from the local techs. I would expect we’ll have more news on dates next week as they gather requirements and start to update our systems. 1/29: Added to HOT list 1/17: Order rec'd
| 100M Port/200M Access EaAVPN 1000Base-SX | CO147-02-IM | UHG | Melissa Chapman |  | 169 Inverness Dr. West | Englewood, CO |  | VS19172513 3102-1196 3102-BBMY | 2019-10-22 | 2020-01-14 | 2020-02-19 | 2020-02-19 |  | Y | BKEC.950793 | Qwest | 29KXGS464934MS | 2020-02-04 | GARAGE LEVEL MAIN TELEPHONE ROOM WALL MOUNT TYPE: OPTICAL PO |  |  |  | 119 | 10.1.87.17 | 10.1.87.18 | 65419 | 202610 | UHG GLOBAL 150 | 2/20: ORDER COMPLETE 1/29-2/17: Confirmed access install completed - Rec'd R80/R84 on access and VLAN PON's. Pending tech assignment and testing completion.Future due 2/19. VLAN ID 119. 1/27: Install is currently scheduled for 2/5 - UPDATE: Rec'd request today to change LCON's - This may jep order and push dates out - is that OK? 1/23: The installation is currently scheduled for 2/5, however the LEC reached out to us that they are ready to deliver the circuit earlier, but both LCON and Alt LCON are unresponsive. 1/13-1/20: Access install date has been adjusted out 1-day to 2/5/2020. No reason provided by Qwest. 11/18-1/6: Access install scheduled for 2/4/2020. 10/28-11/11: Pending an install date from the LEC Qwest 10/22: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | TX541-02-IM | UHG | Melissa Chapman | Vivify Health | 7201 Bishop Rd Suite E-200 | Plano, TX |  | VS19192923 3102-1318 3102-BBPQ | 2019-11-19 | 2020-03-02 | 2020-03-02 | 2020-02-28 |  | Y | IUEC.999277 | AT&T Sport of Texas | 50KRGN887462SWDL | 2020-03-02 | PARKING GARAGE ELEC RM EMUX PRT 5 SC JK 1 EXT |  | 1000 BASE SX |  | 50 | 10.1.86.253 | 10.1.86.254 | 65171 | 202610 | UHG GLOBAL 150 | 3/2: ORDER COMPLETE 1/27-2/24: Access install has been scheduled for 3/2 1/21: Pending update from ordering team - submitted HITS ticket to advise the token should now be loaded correctly with the sold notice. 1/13-1/20: Reached out to Chris re: sold notice issue with ATT Texas. 1/6: Pending an install date from AT&T of Texas. FOC due 1/8 12/16-12/30: Pending an install date from AT&T of Texas. DDF ticket issued 12/30 for R15 to clear PON issues. 11/25: Per Chris, AT&T of Texas is the only ESP that was confirmed as available for Standard Ethernet access to this location. 11/19: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX548-02-IM | UHG | Melissa Chapman | Wellmed | 3310 Live Oak Street | Dallas, TX |  | 3102-1323 3102-BBPW | 2019-12-16 | 2020-01-15 | 2020-01-15 | 2020-02-19 |  |  | BBEC.552145 | ATT SW | 14KRGN887589SW | 2020-02-19 | 3RD MAIN TELCO 3RD FLR MAIN TELCO ROOM WALL MOUNT TAGGED |  |  |  | 50 | 10.1.86.121 | 10.1.86.122 | 65407 | 202610 | UHG GLOBAL 150 | 2/20: ORDER COMPLETE 2/11-2/17: Access install scheduled for 2/19. 2/6: Melissa advised site is ready - I’ve issued a PON supp and that went out this morning. FOC is due back 2/12 and I’ve requested install 2/19 or sooner. 1/20-2/3: Access install missed. Per LEC this is CNR - CUSTOMER PREM STILL UNDER CONSTRUCTION WONT BE READY UNTIL 2 MONTHS CALLED LCON LEFT VOICEMAIL - PON NEEDS TO BE SUPP'D WHEN SITE IS READY 1/13: Access install scheduled for 1/15. 12/16: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | UNY33-02-IM | UHG | Melissa Chapman | Optum Health | 1311 Mamaroneck Ave | White Plains, NY |  | VS20011689 3102-0363 3102-BBQH 3102-BBQJ | 2019-12-19 | 2020-04-09 | 2020-04-09 | 2020-03-02 |  |  | BBEC.518047 | Cablevision Lightpath | 08LUXS256108CLVI | 2020-03-18 | 1ST FLOOR TELCO ROOM VRTUAL EDGE POS 1 |  |  |  | 2 | 10.1.86.105 | 10.1.86.106 | 64796 | 202610 | UHG GLOBAL 150 | 3/2: ORDER COMPLETE 2/11-2/24: Access install scheduled for 3/18. 2/3: PON released - install date pending. FOC due back by 2/19. Cablevision 1/24: New USO 3102-0363 received from Clyde - pending install date - PON set to release to LEC on 1/29 1/20: Asked Clyde/Chris to reissue - PON is still not loaded and I don't anticipate they'll be able to fix in timely manner - requested order be reissued. 1/13: USO's are not loaded in SOTS. Issued HITS ticket to have order team address the issue. 12/19: Order rec'd
New | 100M Port/ 250M Access EaAVPN 1000 Base-SX | UCA28-09-IM | UHG | Melissa Chapman |  | 2858 Loker Ave East | Carlsbad, CA |  | VS20024494 3102-0732 3102-BBQT | 2020-02-11 | 2020-02-26 | 2020-02-26 | 2020-02-26 |  | Y | BREC.646051 | ATT West ONNET-5 | 19KRGN533680PT | 2020-02-26 | HANDOFF IN MDF ROOM :CIRCUIT IS TURNED UP, DEMARC, LOCATION IN MDF ROOM, HANDOFF IS LABELED WITH CIRCUIT. I SHOWED THE IT TECH ONSITE THE LOCATION, CLOSED OUT WITH ENOC TECH, LEFT CARD WITH CUSTOMER, ACCESS TO MDF ROOM TOOK A BIT, STRICT SECURITY PROTOCOL;DEMARC:1ST FLOOR,MDF,IN BACK OF WAREHOUSE IN SAME ROOM AS 1.1 | 1000 BASE SX |  |  | 50 | 10.1.86.29 | 10.1.86.30 | 64902 | 202610 | UHG GLOBAL 150 | 2/26: ORDER COMPLETE 2/25: Access install scheduled for tomorrow 2/26. 2/11: Order rec'd
| 50M Port/100M Access EAVPN 1000Base-SX | AZ147-02-IM | CANCELLED | Melissa Chapman | 4c Medical | 16838 E Palisades Blvd #C-153 | Fountain Hills, AZ |  | VS19152583 3102-1097 3102-BBKZ 3102-BBLB | 2019-09-11 | 2019-12-10 | 2019-12-10 |  |  | Y | IUEC.817077 | Cox Communications | 23KFGX991707COXC | 2020-01-17 | [5 empty] | 10.1.87.177 | 10.1.87.178 | 64750 | 202610 | UHG GLOBAL 150 | 2/13: Rec'd cancellation request from Melissa. Issued the request via HITS ticket. 2/3-2/11: Access install date showing on track for 3/13/2020. 1/13-1/27: Order is delayed - per LEC, 1B OUTSIDE PLANT (OSP) - MAJOR BUILD. DURING CONSTRUCTION CONTRACTOR FOUND THAT OPEN CUT WOULD BE REQUIRED IN PROPERTY PARKING LOT. CURRENTLY PENDING FOUNTAIN HILLS CITY PERMIT. Access install date has been pushed out to 3/13/2020. 12/3-1/6: Access install pushed to 2/12. FOC REUT WOULD BE REMARKS: CU: SITE HAS RECEIVED BAA APPROVAL, CURRENTLY PENDING FOUNTAIN HILLS CITY PERMIT, ETA ON APPROVAL IS 12/11. 10/7-11/25: Access install scheduled for 1/17/2020. Cox Communications long interval build req'd. 9/23-9/30: Issued AERO DES 735218 for missed FOD. Pending release of the PON to the LEC. UPDATE: PON RELEASED 9/23 - FOC due back by 10/28. 9/17: Pending an install date from the LEC Cox 9/11: Order rec'd
| 50M Port/100M Access EAVPN 1000Base-SX | AZ149-02-IM | CANCELLED | Melissa Chapman | 4c Medical | 16620 N. 40th St, Suite C1 | Phoenix, AZ |  | VS19165948 3102-1151 3102-BBMJ | 2019-09-11 | 2019-12-30 | 2019-12-30 |  |  | Y | IUEC.637550 | Qwest | 19KXGS461385MS | 2020-04-14 | [5 empty] | 10.1.87.173 | 10.1.87.174 | 64646 | 202610 | UHG GLOBAL 150 | 2/17: Order in process of cancellation. 2/4: Received cancellation notice from Melissa. 1/6: Access install scheduled for 4/14/20. 12/30: PON 7WS03811556 was resent to the LEC on 12/16. Pending a response. No additional info related to a previous update that construction was required. Working to obtain an update to see if construction is still required OR if new date for install will be provided. 12/6-12/16: UPDATE: SPEC CONSTRUCTION REQUIRED -CTL WILL CONTACT WITHIN 11 DAYS WITH QUOTE. Pending quote from the LEC for construction. 11/25-12/3: PER LEC: CUSTOMER NOT READY - CNR - BUILDING NOT READY, CUSTOMER WILL ADVISE - CUSTOMER NOT READY - ADDL INFORMATION TO FOLLOW 11/4-11/18: Access install rescheduled for 11/22. 10/28: Access install missed - per LEC "NO ACCESS TO PREMISES - SUP DUE DATE" - Reached out to Melissa to contact LCON - UPDATE: ISSUED AERO DES 773968 to change LCON to Linda Vaccaro (NOTE: REC'D UPDATE ON AERO TICKET - PON HAS BEEN SUPP'D.) -- SECOND UPDATE: Received another contact (Melvin Ramirez) for this site from Melissa. Another supp request has been sent - AERO DES 774790. 10/21: Access install scheduled for 10/24. 10/15: Pending an install date from the LEC Qwest 9/11: Order rec'd - processed 9/13 - get with Clyde
| 50M Port/100M Access EAVPN 1000Base-SX | AZ148-01-IM | CANCELLED | Melissa Chapman | 4c Medical | 17218 N 72nd Dr, Suite 101 | Glendale, AZ |  | VS19166680 3102-1145 3102-BBLX | 2019-09-13 | 2019-10-14 | 2019-12-31 |  |  | Y | IUEC.823097 | Qwest | 19KXGS461072MS | 2020-02-27 | 1ST FLOOR MAIN IT/RISER ROOM, WALL MOUNTED. OPTICAL PORT 1 T |  |  |  | 58 | 10.1.89.17 | 10.1.89.18 | 61914 | 202610 | UHG GLOBAL 150 | 2/17: Order in process of cancellation. 2/13: Rec'd order cancellation from Melissa. 2/11: Access install showing R80 completed - VLAN PON completed as well. Pending testing completion. Demarc and VLAN ID provided in columns S and W. Future due 3/13. 10/28-2/3: Per LEC Qwest - Access install scheduled for 2/27/2020 - 1B OUTSIDE PLANT (OSP) - MAJOR BUILD 10/15-10/21: Pending an install date from the LEC Qwest. 9/13: Order rec'd
| 50M Port/100M Access EAVPN 1000Base-SX | AZ144-01-IM | CANCELLED | Melissa Chapman | 4c Medical | 4110 N 108th Ave | Phoenix, AZ |  | VS19166684 3102-1147 3102-BBLY | 2019-09-13 | 2019-10-14 | 2019-12-31 |  |  | Y | IUEC.823461 | Qwest | 19KXGS461071MS | 2020-03-11 | [5 empty] | 10.1.94.21 | 10.1.94.22 | 64919 | 202610 | UHG GLOBAL 150 | 2/18: Melissa requested order cancellation - HITS ticket issued. 1/20-2/17: Qwest access install scheduled for 3/11/2020 - 1B OUTSIDE PLANT (OSP) - MAJOR BUILD 11/11-12/12: Pending USO's for backup order (LEC = Cox Communications) 10/30: Per Chris Cowan: "I sent a request to Qwest asking for them to offer any clarification on how long they estimate they would take to complete the work needed to support the Ethernet order for your AZ144 Ethernet access to AVPN order. I hope to get a response in a few days and will report that to you. From that point we can revisit next steps." 10/29: Per Melissa, "Can we order this on Cox also since Qwest has an access date of March? I want to keep both orders in play in case Cox has a pop collector." 10/28: Per LEC Qwest - Access install scheduled for 3/11/2020 - 1B OUTSIDE PLANT (OSP) - MAJOR BUILD 10/15-10/21: Pending an install date from the LEC Qwest. 9/13: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | GA074-02-IM | UHG | Melissa Chapman | BriovaRx | 425 Franklin Drive Ste 530 | Marietta, GA |  | VS20011996 3102-0445 3102-BBQM | 2020-01-17 | 2020-04-10 | 2020-04-10 | 2020-03-06 |  |  | BBEC.521773 | ATT SE | 38KRGN616870SB | 2020-03-06 | 1ST FL MAIN TELCO RM,BLDG MPOE,TELCO L ON SLIMBOX,PORT 5 | 1000 Base-SX LC |  |  | 50 | 10.1.86.45 | 10.1.86.46 | 64770 | 202610 | UHG GLOBAL 150 | 3/6: ORDER COMPLETE 3/2: Access install scheduled for 3/6 2/25: Follow up to ordering team to check on PON supp to change suite to "Suite 535." 2/19: Please sup the order to ATT to change the LCON to Charles Phillips: Cell – 678-641-3510 Email cphillips@asacarlton.com 2/17: Access install missed per LEC. CUSTOMER SITE NOT READY FIELD TECH WAS UNABLE TO COMPLETE UNI GAS066769001 /38/KRGN/616870/SB - THE BUSINESS SUITE IS UNDER CONSTRUCTION AT THIS TIME AND THE FIELD TECH WAS UNABLE TO REACH THE LISTED LCON BY PHONE 2/11: Access install showing rescheduled for 2/12. 2/3: Access install scheduled for 3/4. 1/27: Pending an install date from ATT SE 1/21: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000Base-SX | CO103-01-IM | UHG | Melissa Chapman | United Healthcare- Avella | 1245 East Colfax Ave, Ste 102 | Denver, CO |  | VS19091524 3102-0481 3102-BBFX 3102-BBFW | 2019-05-15 | 2019-08-20 | 2019-08-20 |  |  | Y | IUEC.741726 | Comcast | 60KGGS011663CBCL | 2020-01-13 | [5 empty] | 10.1.89.245 | 10.1.89.246 | 65233 | 202610 | UHG GLOBAL 150 | 3/18: Confirmed - Order cancelled in OCX IM, status cancelled in EFMS, WINKY and ICORE. 3/9: Issued Order Cancellation in IOS. :Leaving on sheet until confirmed removed from systems. 3/2-3/9: Advised Melissa of the LCON/ALCON issue. LEC contacted both and they are not familiar with the order. Per Melissa: "Nothing yet Brian…we may need to cancel this, but I am trying to verify." 12/30-2/24: Access install has been updated with a 3/17/20 install date due to permitting issues in Denver. 11/18-12/16: Access install scheduled for 1/13/20. Per latest from LEC side, LENGTHY PERMITS REQUIRED BY DENVER - ETA FOR CONSTRUCTION COMPLETION NOW 1/5. 10/28-11/11: All dates are up in the air right now - Per latest from LEC side, LENGTHY PERMITS REQUIRED BY DENVER - ETA FOR CONSTRUCTION COMPLETION NOW 1/5. WILL ISSUE FOC ONCE PERMITS ARE REC'D. 10/15-10/21: Access install has been rescheduled for 11/13. (issued AERO DES 766126 for R15) 10/7: Per Provisioning, THIS IS PENDING LEC CONSTRUCTION. WE MAY POSSIBLY GET RE-FOC THIS WEEK WITH AN EARLY NOVEMER DUE DATE 9/30: Access install still scheduled for 10/7 - issued 2nd AERO DES ticket 743331 due to R15. 7/17-9/23: Access install scheduled for 10/7. Minor build. R15 - AERO DES 734934 7/1-7/8: No dates back from the LEC Comcast. Carrier Mgmt Tier 1 engaged. Per Comcast, the site survey is complete and they are awaiting wavelengths and design in order to issue FOC. Carrier Mgmt remains engaged and continuing to press for status. 6/10-6/24: USO's loaded on 6/4 - PON sent to LEC COMCAST on 6/5. Pending FOC which is showing due back by 7/10. 6/3: HITS ticket issued. 5/28: USO's rec'd - pending loading in all systems. 5/15: Order rec'd
New | 500M Port / 1G Access Ethernet AVPN 1000Base-SX | II553-XX-CM | UHG | Melissa Chapman | Xl Health | Old Data Center - Dodda Banaswadi Main Rd - Harischandra layout - Jeevanhalli - Maruthi Sevanagar | Bangalore Karnataka India |  | ISR19062877548 VS19113671 3094-BVQL 3094-BVQM |  |  |  | 2019-11-03 |  | BMYF.100516 | TCL (VSNL) | 091BANG1143033866027 | 2019-09-06 | [5 empty] | 10.1.88.109 | 10.1.88.110 | 64823 QoS profile 6039 | 202610 | UHG GLOBAL 150 | 11/18: ORDER COMPLETE - AT&T testing completed , TID, TP3 sent to customer and order closed. 11/4-11/11: Telco testing completed and AT&T testing is in progress. 10/29: Circuit provisioning completed, Telco testing being planed. 10/28: MUX integration completed and circuit under provisioning. 10/21: MUX installation completed and integration being planed. Firm date revised to 11/8 as there is a delay on customer side for power readiness. 10/15: Fiber termination is in progress by Telco. 10/7: Per PM, Rack space confirmed by customer. However, tile cutting is required. Communicated the same to customer and further updates awaited. 9/30: Customer confirmed the access permission and in building fiber work are complete. Pending rack space confirmation from customer 9/24: Telco is pushing to get install completed and Workman compensation policy is a possible issue. PM Mahesh working to get status of site requirements that are to be completed by the customer. Sent status email to Melissa. 9/20: Site requirements readiness confirmation awaited from customer. Per Mahesh (PM), Telco needs permanent UPS power for the equipment. PM also checking with Telco on the cable laying work. 9/18: Per Parveen Kumar Sharma ¦ Optum, MDF room is ready with temp power. Reached out to Mahesh to advise and push for telco work to be completed. 9/12: "Customer confirmed that cable tray is ready till the server room. Site readiness requirements awaited from customer." MDF ROOM READY 9/9: Sharma, Parveen K (customer) reached out internally to Cholanj, Raja for status of server room this past Thursday. Pending update from customer. 9/3: No change. per customer's Project Team, server ready room is 9/8/2019 7/29-8/26: Customer confirmed site is expected to be ready by end of Aug-2019. Telco would require 4 to 5 weeks to deliver the circuit once server room is ready with site requirements. CNR Billing letter sent to customer by PM Mahesh Vn 7/22: PTT waiting for timelines on server room readiness. Please check with LCON and advise when they expect the server room to be ready. PTT will then be redispatched. 7/17: Firm date 9/6, subject to customer site readiness. 7/9: Reached out to Mahesh Vn (PM) this morning to find out when we expect to hear back from telco.UPDATE: PER Mahesh, he spoke with Pradeep Kumar (LCON) and he confirmed server/MDF room is not yet ready 7/8: Pending firm date from Telco 6/3: The order has been assigned to an Order Manager. Pending ISR#. 5/9-5/13: Pending ISR#
New | 500M Port / 1G Access Ethernet AVPN 1000Base-SX | II554-01-IM | UHG | Melissa Chapman | Optum Global Solutions (India) Private Limited | 6th Floor of Block 2 of Phase 1 Building and a part of ground floor in Block 1 of Phase 1 Building in IT/ITES SEZ of M/s ITPG Developers Private Limited at Behrampur, Near Sector 59 | Gurgaon Haryana India |  | ISR19081330555 VS19136131 3094-BVRR 3094-BVRS | 2019-08-02 | 2019-10-13 | Target 10/14/2019 | 2019-10-29 |  | BMYF.100532 | Bharti | 13246095 | [6 empty] | 10.1.88.29 | 10.1.88.30 | 64938 QoS profile 6039 | 202610 | UHG GLOBAL 150 | 11/18: ORDER COMPLETE - Issue resolved. TID , TP3 sent to customer and order closed. 10/28-11/11: Pending results of the Telco tests. Awaiting OK for turn up. 10/21: Telco facing issue to complete the circuit testing. Telco confirmed that optical multimode handoff is not working on FTTH solution and they are working with internal team to resolve. Telco L2 confirmed that they are working with product team to address the issue and further updates expected in 2 to 3 days. 10/15: Customer confirmed site is ready with UPS power. Telco has been advised. Telco has completed the fiber work however fiber is damaged and Telco is working to re-store. Pending ETA. 10/7: Customer site readiness timelines awaited. 9/25: Customer confirmed that, site expected to be ready by 10/5. 9/16-9/23: Targeting 10/11 for delivery. Per Mahesh. Fiber work completed for FTTH. Customer site readiness timelines awaited. 9/11: Access confirmed by customer and communicated the same to Telco. 9/9: Telco site survey scheduled and access confirmation awaited from customer. Still targeting 10/11 delivery. 9/3: Telco provided a 10/11 firm date for delivery. 8/26: Pending firm date from Telco. Per the PM Mahesh, Telco will deliver the interface as ordered (1000-BaseSX) and same has been communicated to customer. 8/23: Follow up to PM Mahesh Vn regarding handoff issue - customer wants SX, Telco advised they can deliver on LX only. Need to find out what was decided on customer and telco sides. 8/19: Telco explored the option to deliver the interface as required 1000BaseSX. Communicated the same to customer. 8/16: Telco highlighted share the feasibility on Fiber FTTH Media for this circuit delivery and they can deliver only 1000BaseLX interface on FTTH Media. However, interface required is 1000BaseSX. Hence, requested customer to check and confirm if we can deliver 1000BaseLX-LC. Further updates awaited from customer. 8/14: Rec'd ISR# from sales 7/2: Contracts sent out this morning to UHG per Christine 6/28: Pending ISR#
New | 100M Port / 200M Access Ethernet AVPN 1000Base-LX | II555-01-IM | UHG | Melissa Chapman | Optum Global Solutions (India) Private Limited | D-13 / Sector 59 Noida | Uttar Pradesh India |  | ISR19093091879 VS19159503 3094-BVTZ |  | 2019-10-30 | 2019-11-25 | 2020-02-04 |  | IUYF.104988 | TCL (VSNL) | 091NOID1143034482393 |  | Mux Name: NOID_BSOFTD13S59_03// Mux IP:172.23.55.138 / Slot.8-Port.P10 |  |  |  | 2 | 10.45.10.173 | 10.45.10.174 | 64701 QoS profile 6039 | 202610 | UHG GLOBAL 150 | 2/4: ORDER COMPLETE 2/3: Telco testing completed. AT&T SPIRENT Testing in progress, circuit will be ready for activation on or before 2/5/2020. 1/27: Reached out to Devaraj's backup for status of move to new bearer. - FOLLOWED UP W/ DEVARAJ 1/28 9:01am ET 1/20: Per NCON, during circuit provisioning Telco highlighted there is no sufficient capacity on assigned Bearer. Requested OC to check and re-assign to New bearer, feedback awaited. 1/6-1/13: There was delay on customer side to arrange access for SFP installation. Revised Firm date is 1/27/2020. 12/30: Reached out to backup PM GOPAL, PRAVEEN for status and ETA for completion. Showing as of 12/18, Fiber ring upgrade was scheduled & completed and that the Telco will review and share revised Firm date. UPDATE: Per Praveen, Telco is waiting for customer access permission to install a SFP module & this is delayed by customer due to Holiday season.Devaraj will provide status in next couple of days. 11/26-12/16: Still awaiting downtime from customer - pending response from Kapil Mendiratta (kapil.mendiratta@hcentive.com) - working to arrange 5-hour window for Fiber ring upgrade with 5 to 6 days prior notice. Weekdays from 11PM to 6pm(from Monday till Saturday) or Sunday from 10am to 6pm. Below circuits will be impact during activity. 1. 091NOID1258009060185 NPL Intracity TATA TELESERVICES LIMITED --E1 2. 091NOID1258009060203 NPL Intracity TATA TELESERVICES LIMITED --E1 3. 091NOID030008175984_382624_HCENTIVETECHN --FE 11/18: There is capacity constraint in Telco network. Telco need 5hours downtime window to upgrade Fiber ring. Awaiting downtime from customer 11/11: Firm date from PTT is 01/02/2020. 10/22-11/4: Access ordered with Telco. Expecting Firm date by 11/6/2019 10/21: NCON Devaraj Puttannanavar - pending additional order details and release of order to PTT 9/9: Per Christine, countersigned, placed order 9/3. 8/27-9/3: Pending ISR#
New | Upgrade to 1G | II747-05-CM | UHG | Melissa Chapman |  | 8th Floor, BSNL IDC, Fountain Building II, Fort | Mumbai Maharashtra India |  | ISR20021860478 | 2019-12-17 |  |  | 2020-03-14 |  | BMYF.100065 | [13 empty] | 3/14: Activity completed. 3/2-3/9: Activity scheduled on 14-Mar-2020 at 8AM IST. 2/18: Per NCON, Downtime confirmation awaited from customer for port & CIR upgrade. MACD - change (upgrade) Port & VLAN (CIR) speed from 500M to 1G ICORE Site ID: 2681623 Port Circuit ID: BMYF.100065..ATI Connection ID: 12340964 NO Rehome 12/17: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | TX550-02-IM | UHG | Melissa Chapman | Wellmed | 1200 Binz Street Suite – 1200 | Houston, TX |  | 3102-0392 3102-BBQW | 2020-02-11 | 2020-03-11 | 2020-03-11 | 2020-03-11 |  | Y | BBEC.561767 | ATT SW | 28KRGN749687SW | 2020-03-11 | 12TH MECH RM FIBER HANDOFF JACK IN MECH RM |  |  |  | 50 | 10.1.86.21 | 10.1.86.22 | 64902 | 202610 | UHG GLOBAL 150 | 3/11: ORDER COMPLETE 2/25-3/9: Access install scheduled for 3/11. 2/12: Order rec'd
New | HOT ORDER 10MB Port/ 50M Access EaAVPN 1000 Base-SX | C1649-02-IM | UHG | Melissa Chapman | Nice_Data_Center | 3180 Irving Blvd. | Dallas, TX |  | VS20004025 3102-1325 7MS02386342 3102-BBQD | 2020-01-02 | 2020-03-26 | 2020-03-26 | 2020-03-18 |  | Y | BBEC.582537 | ATT SW | 14KRGN887614SW | 2020-03-18 | 1ST FLOOR,DATA CENTER,CABINET C08-55 DEMARK PNL#1,POS 23/24 |  |  |  | 50 | 10.191.22.65 | 10.191.22.66 | 65412 | 202609 | UHGECC GLOBAL | 3/18: ORDER COMPLETE 3/9-3/16: Access install scheduled for 3/18. 3/3: SITE VISIT SCHEDULED FOR 3/6. 3/2: Q to Debojit Das (CNR Agent) for status and ETA on Construction work. 2/24: Requested update from Construction on timelines for fiber work. 2/17: Pending site visit completion - ASEdb does not show this was scheduled with the end user yet (although today is a holiday.) 2/11: PON was supp'd to request redispatch. Also advised Construction that per NICE, the circuit should be dropped at the MMR. Pending response with target date for both Construction work (if any) and access install. 2/3: Per Melissa, "Yes, we’re working on a site contact and have escalated the issue. Initially, NICE stated that circuits to MMRs shouldn’t require a site contact. Does ATT have a MMR on site or are they building into this DC?" - FROM NICE The circuits will only need to be dropped to the MMR in the facility. Our order = Main Bldg, 1st Floor, Telco Rm 1/28: Added to HOT order list 1/20-1/27: CNR - LCON CONTACTED BUT WILL NOT COMMIT TO SITE VISIT DATE. Pending update from LEC/Construction. (Customer unable to schedule SV until this week after Tuesday.) - Might want to reach out to site contacts to see if they can reschedule this. I also put a note in the Construction team's site to see if they can contact KERI CHRISTENSEN. The initially contacted Carlos Martinez Carlos.Martinez@cyient.com so not sure how they got his info. 1/14: Pending an install date from ATT SW 1/2: Order rec'd - Please verify city name - ordered as Houston - being provisioned to Dallas.
| HOT ORDER 40G Port/100G UVN Access ADI 1000Base-SX | MN011-52-IM | UHG | Melissa Chapman |  | 1707 West Creek Lane | Chaska, MN |  | 306329958 3102-0579 | [6 empty] | /L8YX/997977//ATI/ |  | UVN CIRCUIT ACDC.101121.ATI |  |  |  | TDI: 010203.04.05.17-18 IOC UFC 198 PLID 57432 PAID 13397875 PORT cgcil412me9 5/3/0 | [5 empty] | 202610 | UHG GLOBAL 150 | 3/13: Office wiring expected to complete today followed by CTA testing. Chaska A (MDF 700) channel will be built between Chaska and STPLMNRO
| HOT ORDER 40G Port/100G UVN Access ADI 1000Base-SX | MN053-74-IM | UHG | Melissa Chapman |  | 14100 Business Center Drive | Elk River, MN |  | 306346826 3102-0713 | [6 empty] | /L8YX/997116//ATI/ |  | UVN CIRCUIT ACDC.101121.ATI |  |  |  | TDI 080064.12.05-65-66 IOC N/A PLID 58018 PAID 13390826 PORT mpsmn403me9 5/2/0 | [5 empty] | 202610 | UHG GLOBAL 150 | 3/13: Activation Complete . Elk River B (MDF700) channel will be built between ER and MPLSMNDT AT&T node
| HOT ORDER 40G Port/100G UVN Access ADI 1000Base-SX | UMN99-66-IM | UHG | Melissa Chapman |  | 6150 Trenton Ln | Plymouth, MN |  | 306329876 3102-0494 | [6 empty] | /L8YX/996715//ATI/ |  | UVN CIRCUIT ACDC.101121.ATI |  |  |  | TDI 080064.12.05-67-68 IOC UFC 197 PLID 57433 PAID 13394163 PORT kc9mo405me9 1/3/0 | [5 empty] | 202610 | UHG GLOBAL 150 | 3/13: Ready for activation, customer deferred to a later time and will contact Ike for turn up when they are ready. Plymouth (Single Node) channel will be built between Plymouth and MPLSMNDT
| HOT ORDER 10M Port/50M Access EAVPN 1000Base-SX | NY498-02-IM | UHG | Melissa Chapman |  | 161 Canal St. | New York, NY |  | VS19166682 3102-1120 3102-BBMB 3102-BBLZ | 2019-09-19 | 2019-10-14 | 2020-01-10 | 2020-04-03 |  | Y | BBEC.538489 | Time Warner | 21L1XX815370TWCC | 2020-02-14 | CUSTOMER SERVER ROOM, RACK MOUNTED, PORT 5 |  |  |  | 200 | 10.1.87.229 | 10.1.87.230 | 64607 | 202610 | UHG GLOBAL 150 | 4/6: ORDER COMPLETE 3/30: Reached out to AM Jane Tansor for next level escalation. 3/23: Requested assistance from AM Jane Tansor for order completion. UPDATE: JANE REACHED ACROSS TO PROVISIONING FOR ESCALATION ASSISTANCE. 3/14: Reached out to Sheila Randolph (Provisioning Tech Coach) for completion assistance. 3/9: Access install completed - demarc provided - pending testing completion and the OK to turn up. 3/2: Per Larry Shearholdt, If the Carrier misses that 3/6 commitment, his team will refer the order to the OOR Tier 2 team and ask them to step in and manage to access delivery completion. 2/25: Added to hot list 2/24: LEC is saying target date was moved out to 3/6. I've escalated to 2nd Level Carrier Management to find out why. 2/17: Pending escalation on missed access install - Spectrum still advising Construction is delay reason. 2/11: Access install scheduled for 2/14/2020 1/13-2/3: === PER SPECTRUM, PREVIOUS CNR CONDITION FOR ROE IS NO LONGER AN ISSUE. HOWEVER WILL REQUIRE A SUP TO CLEAR THE JEOPARDY. CURRENTLY THE ORDER IS PENDING DOT PERMITS BEFORE CONSTRUCTION CAN RESUME PROGRESS. SOW (GROUND) FOOTAGE, 465' PULL THRU FIBER. PLEASE ENSURE SUP GETS RELEASED. CM TIER II IS NO LONGER MONITORING OR ENGAGED. Confirmed PON was resent on 1/10 to move order forward. 12/12-1/6: LEC advised order delayed - PENDING ROE 10/21-12/3: Access install scheduled for 2/14/2020. Pending details. 10/15: Pending an install date from the LEC Time Warner. 9/19: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL435-02-IM | UHG | Melissa Chapman | Wellmed | 734 Elkcam Blvd | Deltona, FL |  | VS20025527 3102-0436 3102-BBRB 3102-BBQZ | 2020-02-18 | 2020-05-06 | 2020-05-06 | 2020-04-08 |  | Y | BBEC.542308 | Embarq | 25KXGS495627UFLG | 2020-04-08 | RAD 203 WALL MOUNTED IN TELCO CLOSET CUST HAND OFF IS 850 MU |  |  |  | 2 | 10.1.85.241 | 10.1.85.242 | 65403 | 202610 | UHG GLOBAL 150 | 4/8: ORDER COMPLETE 4/6: R80/R84 completion received on Access and VLAN PON's. Working to complete. UPDATE: ISSUED AERO DESIGN TICKET 951793 TO COMPLETE ENGINEERING. 3/30: VLAN PON RSSV4437795 due 3/31. 3/23: Issued AERO Design 931427 for VLAN PON R15. Still working to confirm the 4/15 date from Embarq 3/16: New Embarq estimated date is 4/15.This is still ahead of overall May due date. 3/3: Embarq provided a 3/9 install date. MISSED 2/25-3/2: PON released to Embarq on 2/21. Pending FOC. 2/18: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | NC061-02-IM | UHG | Melissa Chapman | Briova | 4015 Shopton Road | Charlotte, NC |  | VS20003254 3102-1300 HSS03659370 3102-BBPZ | 2019-12-18 | 2020-03-25 | 2020-03-25 | 2020-04-07 |  | Y | IUEC.903906 | ATT SE | 22KRGN404387SB | 2020-02-13 | 1ST FI,STE 600,SERVER RM WALL MOUNT |  |  |  | 50 | 10.1.86.165 | 10.1.86.166 | 65411 | 202610 | UHG GLOBAL 150 | 4/8: ORDER COMPLETE 4/6: New PON HSS03659370 showing due to install on 4/8. 3/30: Follow up on DDF ticket 202003300040 for new PON to be issued as existing PON was cancelled due to CNR 3/24: UHG confirmed site is ready for delivery - DDF ticket issued to check PON 3/23: Once site is confirmed ready, we'll need to issue a NEW PON as existing PON has been cancelled pending site readiness. 2/25-3/16: UHG ADVISED SITE DEMARC AREA IS UNDER CONSTRUCTION/REHAB AND IS SCHEDULED TO BE READY 3/23 OR POSSIBLY SOONER. PON SUPP REQ'D 2/24: CNR - THE CPR ECD IS POPULATED AS 02/04/20. BUT CPR ACD HAS NOT BEEN POPULATED YET. ALSO, THERE IS A JEP FOR "PATH/PWR/GRND/SPACE", WHICH INDICATES THAT THERE IS A SITE REQUIREMENT ISSUE. HENCE, SITE REQ INITIAL TPL IS BEING SENT. PLEASE F/U ON 03/05/2020. 2/18: ORDER IS ON HOLD DUE TO CUSTOMER SITE IS NOT READY. ENGAGING CUSTOMER NOT READY TEAM. - F/U 3/17/2020 2/17: Access install MISSED - Pending update - Issuing Escalation on Tuesday 2/18. 1/20-2/11: Access install scheduled for 2/13. 1/13: Construction site visit scheduled for 1/14. Pending fiber and access install date. 12/18: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX552-02-IM | UHG | Melissa Chapman | Wellmed | 4510 Medical Center Drive, Suite 311 | McKinney, TX |  | VS20004027 3102-1324 3102-BBQC | 2020-01-06 | 2020-03-26 | 2020-03-26 |  |  |  | BBEC.502783 | ATT SW | [7 empty] | 10.45.10.101 | 10.45.10.102 | 65406 | 202610 | UHG GLOBAL 150 | CANCEL Per Melissa. POSSIBLE CANCEL - Chris looking into alternate LECs - Alt carrier in there (Spectrum) 1/27: Reached out to Russ Gilbreath and his next level to find out more about this site 1/20: THIS CNR IS NOT RESOLVED. AT THIS TIME WE CANNOT PLACE ATT FACILITIES AT THIS ADDRESS. SHOWING NO ACCESS FOR SITE VISIT. 1/14: Pending an install date from ATT SW - NOTE: CNR ACCESS DENIED TO THE BUILDING - Per Construction, "at this time there is no signed agreement with Lincoln Harris Properties which covers this specific address. It is listed as an affected property on a pending agreement that is with Lincoln Harris for signatures. Russ Gilbreath (rg8747 - CLIENT SOLUTIONS EXECUTIVE 2 - Fort Worth) has been coordinating the agreement for AT&T and Lincoln Harris." 1/6: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | UTX04-02-IM | UHG | Melissa Chapman |  | 2000 West Loop 9th Floor, Main Bldg, MDF Room | Houston, TX |  | VS20042345 3102-0150 3102-BBRZ | 2020-03-16 | 2020-04-14 | 2020-04-14 | 2020-04-14 |  |  | IUEC.726726 | ATT SW NEARNET-15 | 28KRGN749840SW | 2020-04-14 | 10 MECH MM FIBER HANDOFF PORT 4 |  |  |  | 50 | 10.1.85.197 | 10.1.85.198 | 65396 | 202610 | UHG GLOBAL 150 | 4/14: ORDER COMPLETE 4/6-4/13: Access install scheduled for 4/14. 3/31: Advised Clyde this shows a different address on the USO - 2000 WESTCREEK LN 3/12: Order rec'd
New | 300M Port/ 500M Access EaAVPN 1000 Base-SX | IN156-02-IM | UHG | Melissa Chapman | Equian | 5975 Castle Creek Pkwy Suite 100 | Indianapolis, IN |  | VS20042343 3102-0169 3102-BBSB | 2020-03-17 | 2020-06-09 | 2020-06-09 |  |  |  | BMEC.983451 | ATT MW | KRGN106917NB | 2020-04-13 | 2ND FLOOR TELCO INSIDE SUITE #250. WALL MOUNT CIENA 3930. OPTICAL HANDOFF PORT #5 |  |  |  | 50 | 10.45.10.153 | 10.45.10.154 | 65042 | 202610 | UHG GLOBAL 150 | 4/13: ORDER COMPLETE 4/6: Access install scheduled for 4/13. 3/31: Pending an access install date - SITE VISIT DELAYED BUT SCHEDULED - showing Construction scheduled visit for 4/3. 3/17: Order rec'd
| HOT ORDER 7xT1 AVPN | TX473-05-IM | UHG | Melissa Chapman | Wellmed | 601 Crystal Falls Parkway, Suite 100 | Leander, TX |  | VS19189113 3102-1760-FR 3102-1756 3102-1758 3102-1759 3102-1754 3102-1761 3102-1755 3102-1757 3102-BBPJ | 2019-12-02 | Mid January | 2019-12-30 |  |  | Y | DHEC.215522 .811 DHEC.215522 .812 DHEC.215522 .813 DHEC.215522 .814 DHEC.215522 .815 DHEC.215522 .816 DHEC.215522 .817 | ATT SW | 32HCGS698098SW 32HCGS698094SW 32HCGS698096SW 32HCGS698099SW 32HCGS698097SW 32HCGS698093SW 32HCGS698095SW | 2020-01-28 | FST FLR REAR ROOM DEMARC FST FLR REAR DATA ROOM DEMARC FST FLR DATA ROOM DEMARC BACK ROOM DATE ROOM DEMARC FST FLR FST FLR REAR ROOM MPOE TELCO ROOM CAB3 SLOT 3 |  |  |  |  | 10.1.86.137 | 10.1.86.138 | 65222 | 202610 | UHG GLOBAL 150 | DISCO USO's D3094-4881 D3094-4882 D3094-4884 D3094-4885 D3094-4886 D3094-4887 D3094-4888 4/21: Escalated to Area Manager this morning on disco order 030620XCW54140 4/13-4/20: Requested update from overseas team on disco RDS 030620XCW54140 3/30: Requested update from team on Disco RDS#030620XCW54140. 3/16: Per SME Remma Dayanand, Divyasree, submitted RDS#030620XCW54140. Going further the Disconnection team will be working on the order and will proceed with the full site disconnection. 3/4: Order cancelled by Melissa - IOS request issued 3/2: Escalating within the LEC to complete out this order. Notes indicate they are working it. 2/24: Per the LEC: WE ARE WORKING A MATTER WITH THE ELECTRONIC CONTEST. AT THIS TIME THERE IS NOT AN ECD. -- ESCALATED TO THERON FRAZIER (Tech Group - Provisioning) 2/17: No change - access install for last (2) T-1's scheduled to complete on 2/18 and 2/19 2/11: LEC had issues with final (2) T-1 installs. Both are now showing targeted to complete on 2/18 and 2/19. Working to improve. 2/3: Requested completion of final (2) orders by Tech AM Theron Frazier. 1/21-1/27: Access install has been confirmed for 1/28 for all (7) T-1's. 1/13: Reached out to Melissa to confirm the name of the person confirming site is ready. - UPDATE: Melissa confirmed site is ready - CNR CHAT removed all CNR coding - Issued DDF ticket to have PON's supp'd for redispatch ASAP. 1/6: Advised Melissa that the LEC indicated there were still conduit issues - asked for name/number of person confirming the conduit is complete 12/30: Reached out to Melissa for status of conduit work and site readiness. PON will need to be supp'd when ready. UPDATE: Melissa advised OK to proceed. 12/17: Update to Melissa via email: For this NxT1 AVPN for the Leander TX location, I mentioned on the call this morning that the access orders were set to install today. I checked the LEC’s site and they updated the order as follows:"CUST BUILDING NOT READY, CONTRACTOR STILL NEEDS TO EXTEND CONDUIT FROM OUTSIDE TO INSIDE CUST BLDG. PLS SUP WITH NEW DD WHEN BLDG. READY."As with any CNR (Customer Not Ready) order, once we confirm the site is ready we’ll need to supp the PON and request a new date (which starts the clock over.) As soon as you have news on building readiness, please let me know and I’ll get the PON sent back out. 12/12-12/16: Access install scheduled to take place on 12/16 and 12/17. 12/2: Order rec'd - added to HOT list immediately - need by mid-January
| 10M Port/50M Access EaAVPN 1000Base-SX | TX534-02-IM | UHG | Melissa Chapman | Wellmed | 2200 W Spring Creek Pkwy | Plano, TX |  | VS19196697 3102-0278 HMS02386077 3102-BBPS 3102-BBPR | 2019-11-05 | 2020-03-20 | 2020-03-20 | 2020-04-17 |  | Y | BBEC.589896 | Time Warner | 46L1XX002682TWCC | 2020-04-23 | 1ST FLR TELCO ROOM, WALL MOUNTED TAGGED AND LABELED |  |  |  | 22 | 10.1.86.189 | 10.1.86.190 | 65414 | 202610 | UHG GLOBAL 150 | 4/20: ORDER COMPLETE 4/14: Added to WWR sheet to have provisioning close out order plug and play. 4/13: Access install completed - pending testing completion and the OK to turn up. 2/11-4/6: Access install scheduled for 4/23. 12/30-2/3: Pending an install date from Time Warner on PON HMS02386077. FOC due 2/12 (updated from 1/31) 11/5: Order rec'd - pending USO's
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX554-02-IM | UHG | Melissa Chapman | Wellmed | 209 East 2nd Street | Elgin, TX |  | VS20042342 3102-0408 7MS02397832 3102-BBRX | 2020-03-18 | 2020-03-31 | 2020-03-31 | 2020-04-20 |  |  | BBEC.516960 | AT&T SW ONNET-5 | 32KRGN654248SW | 2020-04-20 | 1ST FLR TELCO CLOSET WALL MOUNT PORT 2 |  |  |  | 50 | 10.1.85.185 | 10.1.85.186 | 64761 | 202610 | UHG GLOBAL 150 | 4/21: ORDER COMPLETE 4/20: Fiber work completed ahead of schedule. Access install rescheduled for 4/20. 4/6-4/13: Construction fiber infrastructure due to complete on 6/3. Access install scheduled for 6/12. 3/31: Pending an install date from ATT SW. Site visit completed on 3/25. Pending update from Construction team. 3/18: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-LX | C1653-02-IM | UHG | Melissa Chapman | Centris | 119 West Tyler St | Longview, TX |  | VS20046665 3102-1423 3102-BBSN | 2020-03-30 | 2020-04-09 | 2020-04-09 | 2020-04-16 |  | Y | IUEC.945030 | ATT SW ONNET-5 | 18KRGN611908SW | 2020-04-16 | 1ST 248 MAIN IT ROOM RLY RCK FOT HO PT 37-38 |  |  |  | 50 | 10.191.22.73 | 10.191.22.74 | 65446 | 202610 | UHG GLOBAL 150 | 4/17: ORDER COMPLETE 4/13: Access install scheduled for 4/16. 4/6: Pending an install date from ATT SW. Confirmed requested 1000Base-LX (winky) 3/30: Order rec'd
New | 500M Port / 1G Access Ethernet AVPN 1000Base-SX | II542-02-IM | UHG | Melissa Chapman |  | Optum Global Solutions (India) Pvt. Ltd. (Unit-II)6th & 7th Floor, Tower-A,Oxygen Business Park Pvt. Ltd., - SEZ,Plot No. 07, Sector-144 | Noida, Uttar Pradesh, India |  |  | 2020-03-17 | [13 empty] | 10.1.89.213 | 10.1.89.214 |  |  |  | 4/28: Removing order - Biz hasn't accepted so not idea when project will move forward. This will have to be reissued by UHG when ready. Moving to completed tab. 3/17: Order rec'd - held by business
New | 100M Port/ 100M Access EaAVPN 100 Base-TX | CA383-01-IM | UHG | Melissa Chapman | Monarch | 2910 Jefferson St #100 | Carlsbad, CA |  | VS20009452 3102-0338 3102-BBQG VS20011791 3102-0439 3102-BBQK | 2020-01-13 | 2020-04-06 | 2020-04-09 | 2020-04-22 |  | Y | IUEC.856655 | ATT West | 19KQGN541820PT | 2020-04-07 | 1ST FL,1ST,VIRTUAL EDGE POSITION 1 |  |  |  | 50 | 172.27.27.237 | 172.27.27.238 | 64736 | 488101 | Monarch | 4/23: ORDER COMPLETE 4/20: Per Construction: THIS IS EF ACCEPTED OFFER. INFRASTRUCTURE IS NOT COMPLETED YET. NEXT STEP IS PLACING CIENA(NTE) WITH ESTIMATED COMPLETION DATE 4/20. 4/13: Requested status from Construction on dig work due last week. 4/6: Per Construction, Order delayed, work is not complete. Dig work won't complete until 4/8 and remaining workgroup will be 1-2 weeks past that date. 3/30-4/6: Fiber work completed - NTE placement scheduled for 3/31 - access install still targeting 4/7. 2/3-3/23: Fiber infrastructure targeted to complete on 3/25. Access install scheduled for 4/7. 1/27: Original USO cancelled due to 'order entry error." Clyde provided new USOs - 3102-0439. Site visit was completed on Friday 1/24. EF offer accepted. Pending dates for fiber and access....but details of some of the work were provided: AT&T WILL PLACE THE FOLLOWING IN THE MPOE - A 20” X 43” X ¾” FIRE – RETARDANT PLYWOOD BACKBOARD FOR EQUIPMENT PLACEMENT, A 12” X 22” X ¾” FIRE – RETARDANT PLYWOOD BACKBOARD FOR THE PLACEMENT OF A FIBER COIL, A STANDARD 3 PRONG 120V 15 AMP DEDICATED SINGLE ELECTRICAL OUTLET AND A 2’ COIL OF #6 AWG ON BACKBOARD, AN FTE, CIENA 3930 EMT AND A DEMARC 1/21: Construction site visit scheduled for 1/24. Pending install date from ATT West 1/7: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | AZ032-07-IM | UHG | Melissa Chapman | Optum | 1981 N Pebble Creek Pkwy | Goodyear, AZ |  | VS20011998 3102-0448 3102-BBQL | 2020-01-16 | 2020-04-10 | 2020-05-25 | 2020-04-20 |  | Y | BBEC.507867 | Qwest | 19KXGS487747MS | 2020-05-12 | 1ST FLOOR MPOP IN FIRE RISER ROOM SOUTHEAST CORNER OF BLDG. |  |  |  | 51 | 10.1.86.61 | 10.1.86.62 | 64902 | 202610 | UHG GLOBAL 150 | 4/20: ORDER COMPLETE 4/13-4/20: Access install complete - VLAN ID 51 - pending testing completion and OK to turn up. Added to WWR sheet for completion. 4/6: Qwest advising access install date has changed from 5/12 to 4/15. 2/4-3/30: Access install scheduled for 5/12. 1B OUTSIDE PLANT (OSP) - MAJOR BUILD (per Qwest) 1/27-2/3: Pending an install date from Qwest. 1/16: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | UT019-03-IM | UHG | Melissa Chapman | United HealthGroup | 1403 East Sego Lily Drive | Sandy, UT |  | VS20048220 3102-1431 3102-BBSS | 2020-04-01 | 2020-06-22 | 2020-06-22 | 2020-04-22 |  | Y | BBEC.634251 | Qwest | 69KXGS507651MS | 2020-04-17 | WALL MOUNT CIENA. OPTICAL PORT4. LOCATION ELECTRICAL ROOM IN |  |  |  | 184 | 10.1.92.181 | 10.1.92.182 | 64833 | 202610 | UHG GLOBAL 150 | 4/23: ORDER COMPLETE 4/21: Added to WWR sheet. 4/20: Access install complete - pending testing completion and the OK to turn up. 4/13: Access install scheduled for 4/17 4/7: USO's received this morning. PON released to Qwest. FOC due back by 5/11. 4/1: Order rec'd
New | 100M Port/ 100M Access EaAVPN 100Base-TX | CA430-01-IM | UHG | Melissa Chapman | Monarch | 3998 Vista Way. Suite C. | Oceanside, CA |  | VS19126157 3102-0936 7WS03800300 New SITE ID 944532 3102-BBJS | 2019-07-18 | 2019-10-09 | 2019-10-09 |  |  | Y | IUEC.944167 | ATT West | 19KQGN541120PT | 2019-08-30 | WALL MOUNT, ELECT HANDOFF PORT 1 JACK PANEL 1 POS 1, TAG |  |  |  | 50 | 172.27.27.245 | 172.27.27.246 | 64744 | 488101 | Monarch | NTE PLACEMENT ORDER 5/4: Order has been reissued by UHG to change the handoff to MMF (1000base SX MMF), LC connector. Added replacement order to HOT list. 4/28: Per Q: Thank you for the update. This is unfortunate as we were navigating through this order based on customer instructions from the ATT Engineering direction on their initial site survey. With the unsupported design option of the converter, I do not want to take the risk if there are potential risk of performance of a non-support design. If we are going to do this right, we will need to re-order the circuit. 4/28: Per Chris C: I did confirm that the Lec was able to establish the correct drop location to run the needed fiber to drop you requested, suite C. The lec also confirmed that the needed fiber run to drop this access is still beyond the allowed run length of 300’ and the circuit can’t be delivered as requested. If a circuit is order with an electrical interface as this order was (100Based TX), the fiber can’t be longer than 300’ and unfortunately, this run is longer than 300’. Options: • Lec can install a Media Converter that would allow them to complete this access order (this has not been a supported design option in past) • Option 2 is for us to cancel and reissue this order and this time request the access interface is optical (1000 based SX or LX) that will support this fiber run that is greater than 300’ If we cancel and reissue we will need a new set of IP’s as the current order will not release the IP’s until later on in the cancelation process. Please confirm you approved path and we will work to proceed. 4/27: The roadblock we are facing now, would have appeared, was the order designed correctly the fist time. (instead of autolinked via automation to wrong NTE.) The recovery order has been designed as ordered, however it seems to be not feasible due to the distance limitations for electrical handoff. C&E is advising of possible customer options below. Its up to customer to decide what they want to do next. EMT was built to the 0.1 MPOE which is the correct location. This MPOE was set to feed all 7 BU’s in this 3 story building. If end user is past the 328’ they would then need to use media converters or change circuit to optical (which is a new order.) 4/20: A tech was dispatched on 4/17 for order completion, however looks like there is a problem with the distance for electrical handoff. Per Tech: ASSIGNED EMT AT 0.1 DW. IS TOO FAR. WHEEL MEASURED AT 300 FT TO SECONDARY MPOE. CUSTOMER HAS EXPLAINED THIS TO SALES AND HAS YET TO BE CORRECTED. NEW DESIGN NEEDS TO HAVE 3930 AT SECONDARY MPOE.;ADT:04/17/2020 10:36:19 PM GMT;REDESIGN 4/20: Reached out to Construction for status of the 4/17 dispatch we were advised was scheduled. 4/13: Construction advised - removing CNR jep in ASE and asked ENOC team to clear CNR jep from the order and request redispatch. 4/6: Reached out to LCON Q for status of building -- UPDATE FROM Q: "The last update I’m aware of is ATT came out on March 2nd and advised they would need to return. We have been waiting on ATT since then and have not received any notification. I have a tech in the region who has been providing ATT initial access. If you can schedule and provide me the date/time when ATT will need to be back on premise, I can coordinate my tech to meet with the ATT tech and provide access." UPDATED Stefan Varga, Tier 1 Teamlead - Carrier Management WITH THIS STATUS. 3/30: Requested update from LEC regarding who they contacted onsite that wouldn't allow access at the suite. Advised them we may have issues accessing site due to state wide lockdown in place due to Covid19. 3/24: Stefan Varga Tier 1 Teamlead - Carrier Management Requesting Update 3/23: ORDER ON HOLD DUE TO NO ACCESS WAS PROVIDED TO CUSTOMER'S PREMISE. NO ACCESS TO 0.1, PERSON IN SITE C106 DIDN T HAVE THE KEY OR KNOW ABOUT PHONE ROOM. CANNOT ACTIVATE TO MINIMUM POINT OF ENTRY. ENGAGING CUSTOMER NOT READY TEAM. 3/17: Pending update from field. 3/16: Per Construction, order on track to meet DD 3/17 2/24-3/9: Construction acknowledged 3/16 fiber infrastructure date is on track. Only addition was NTE PLACED ECD TO 3/19. (CANOPI EXCEPTION- USH TICKET NUMBER 000000275335396 - F/U 3/11/2020) 1/13-2/17: NTE Recovering order to install this correctly in the Suite on Floor 2 is under new SITE ID 944532 in ASEdb. Construction is showing a 3/16 target date for completion. Construction advised they will be doing the inside work to install a minimum 4' x 4' x ¾" fire-rated plywood backboard required in the suite. ADDITIONAL CUSTOMER WIRING REQUIREMENTS: As discussed at the Site Visit, UHG is also responsible for a path, if required, from the NTE location which the engineer pointed out in the Common Area/MPOE, on floor 00, to the customer demarcation panel and then to UHG's router (usually located in your suite or equipment room). This path may include available space in existing floor sleeves, a minimum 2" conduit, and pull tape if the demarcation panel is located in a separate room than the NTE. 1/6: Pending update from team on NTE Recovery order to install service using existing NTE on 2nd Floor. 12/30: Site visit completed on 12/23. Per Engineer Tat Kan Lee (who met with LCON Q)........"We plan to provide your service using the existing Network Terminating Equipment (NTE) in the Suite on floor 02, as discussed during the Site Visit. Although we are providing your service using existing NTE, you may have requirements beyond the NTE as stated below. ADDITIONAL CUSTOMER WIRING REQUIREMENTS: As discussed at the Site Visit, you are also responsible for a path, if required, from the NTE location which I pointed out, to the customer demarcation panel and then to your router (usually located in your suite or equipment room).This path may include available space in existing floor sleeves, a minimum 2" conduit, and pull tape if the demarcation panel is located in a separate room than the NTE." 12/19: NTE REC - NTE RECOVERY order was issued. The original site id is 892551 and the new (recovery) site id is 944532. This order is now considered a company miss and past due C&E SPOC and NSS PM SPOC were notifed 12/12-12/16: Working with Provisioning to redesign circuit to SUITE C (currently dropped in a separate suite due to Ciena equipment issues on the AT&T Construction side.) 12/3: Reached out to Tech team for update this morning as the order is not yet closed out. 11/25: Escalation to Cashmin Banhan (Tech Area Mgr) to get this closed out. 11/18: Pending Order testing completion and the OK to turn up. 11/4-11/11: Received R80 access completion notice from the LEC. Escalating for critical date completion and test and turn up. 10/28: Showing work was done onsite on Friday 10/25. Demarc was posted, but access order not complete. LEC WOT (Wiring) is showing complete, but still a few critical dates remaining to be completed. Pending status update from LEC. 10/17-10/21: AERO CM 762188 - Escalating to have NSS PM issue new design on the ASR per Steph Ealy. AERO TICKET UPDATE: REFERRED TO NSS FOR ASSISTANCE IN GETTING NEW UNI/CNL CLO POPULATED IN ASEDB - F/U 10/22 10/15: Escalating to find out what's going on with this order. Date missed - CNR - still looks like LEC has issues contacting people at site. Working the issues. 10/8: Order updated late yesterday with a 10/15 access install/redispatch date. 10/7: Issued DDF TIcket 201910070099 to fix this issue with the PON and get it supp'd with Q's info. 10/1: Followed up in IOS with a HITS ticket to have the PON supp'd - provided all of the LCON Q's contact info, advised them the lease was signed on 9/13 and to have the LEC contact Q on his cell. 9/30: Followed up with Construction on contacting the LEC Q.....Construction Contact Sherrell Myhand 9/24: Per Melissa, the lease issues might have been the hold up but we should be good now. 9/24: Melissa confirmed she was reaching out to LCON (Q) to see about the LEC NO ACCESS issue. 9/23: Per GRETA log, there are 2 issues with this order. VLAN has not been issued. Asked the AsseMler to issue an EVC. (UPDATE: FIXED - HWSV4325661 ISSUED AND DUE TO COMPLETE 9/25.) Second issue is that Tech called LCON for access and no answer. No access and site was vacant. Asked Tech if secondary LCON has been contacted as well. Pending response. 9/17: Followed up with Scott Gray Sr Specialist-Technical Consulting Engineer who is working this order on the Construction side. Pending an update on next steps. LEC side indicates Design issues being worked (damaged fibers) and I've asked for an ETA for fixing this. 9/9: This has not yet been installed. There’s mention of damaged fibers that need to be corrected before proceeding and I’m awaiting word back on the escalation that was sent Friday. Hope to have more news this week. 9/3: Appears to be a fiber design issue holding up install - LINK THIS CIRCUIT WITH CIENA 3930 OCSDCAJM0BW. PORTS AND BANDWIDTH AVAILABLE. Once C&E fixes this (no ETA yet), access install will proceed. 8/26: Access install scheduled for 8/30. 8/19: USO rec'd - not loaded in SOTS - HALO ticket issued 7/18: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX553-02-IM | UHG | Melissa Chapman | Wellmed | 219 S. O'Connor Rd | Irving, TX |  | VS20025927 3102-0475 3102-BBRD 3102-BBRC | 2020-02-03 | 2020-05-18 | 2020-05-18 | 2020-04-30 |  | Y | BBEC.597449 | Frontier-CTF | 13KFGS318992FTNC | 2020-05-01 | 1ST FLR SERVER ROOM NID 2 WALL MOUNTED | 1000 Base-SX MMF |  |  | 100 | 10.1.86.41 | 10.1.86.42 | 65265 | 202610 | UHG GLOBAL 150 | 5/1: ORDER COMPLETE 4/20-4/27: Access install still showing due 5/1. No updates from LEC or change in dates. 4/14: Sent request via Q to CNR Team to remove C01B (DONE) - working to find out why date was pushed out. 4/6-4/13: Frontier pushed out install date to 5/1. Appears to be a site readiness issue. 3/25-3/30: AERO Design Ticket 938680 - advised site is ready, requested redispatch. 3/24: Received CNR notification - CUST NOT READY, SUPP REQD FOR NEW DD 3/9-3/16: Access install scheduled for 4/22 per Frontier (LEC.) --- SITE VISIT 2/7/20 ¢ENTR CDT W/PULLSTRING, WEATHER CAP, BB, POWER! CRD TBD 2/25-3/2: PON sent to Frontier on 2/24 - FOC due back by 3/27. 2/3: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL439-02-IM | UHG | Melissa Chapman | Wellmed | 5575 S. Semoran Blvd. | Orlando, FL |  | VS20056436 3102-0854 3102-BBTJ | 2020-04-15 | 2020-04-21 | 2020-07-08 | 2020-05-01 |  |  | BBEC.661723 | ATT SE | 58KRGN703604SB | 2020-05-01 | 1ST FLOOR SUITE#26 SUITE 26 MY FAMILY DOCTOR | 1000Base-SX MMF |  |  | 50 | 10.1.84.173 | 10.1.84.174 | 65146 | 202610 | UHG GLOBAL 150 | 5/4: ORDER COMPLETE 4/27: Access install scheduled for 5/1. 4/15: Order rec'd
New | HOT ORDER 20M Port/ 50M Access EaAVPN 1000 Base-SX | MA095-02-IM | UHG | Melissa Chapman | UHG- Commonwealth of MA | 100 Hancock Street | Quincy, MA |  | VS20047254 3102-1424 3102-BBSP 3102-BBSQ | 2020-03-30 | 2020-06-01 | 2020-06-30 | 2020-05-12 |  | Y | IUEC.967976 | Comcast Business Comm | 20KGGS033665CBCL | 2020-07-01 | 2ND FLOOR MDF ROOM RACK MOUNTED RU39, LABELED, CIENNA 3903 PORT 1 |  |  |  | 390 | 10.1.95.225 | 10.1.95.226 | 65394 | 202610 | UHG GLOBAL 150 | 5/13: ORDER COMPLETE 5/11: LEC Comcast has provided a completion notice on the VLAN and Access PON's, but no demarc provided yet. Working with provisioning to obtain Demarc and close out order. 4/20-5/4: LEC Comcast provided a 7/1/2020 install date. I've reached out directly to Comcast for details. UPDATE: PER COMCAST: This is a Class D order which carries a standard interval of 60 BD, which brings us to an estimated FOC of 7/1/20 from when they received the order (4/6/20). More than likely the FOC date can be improved if the market is able to improve their timeline, which they haven’t as of yet. 4/13: PON released to Comcast on 4/6 and FOC due back by 5/11. 4/6: USO's rec'd - PON to be released to Comcast by 4/8. 3/31: Per Melissa, "Please proceed with Comcast." 3/30: Order rec'd - This is an urgent order (not Covid related), the state wants in by June 1. Added immediately to the HOT list. Per Chris, at 50M the only option came back Verizon. Chris upped it to 100M Eth and HVD and Comcast became available. Per Melissa, using Verizon.
| 10M Port/50M Access EaAVPN 1000Base-SX | UMNEA-06-IM | UHG | Melissa Chapman |  | 513 Eaton St. (Hangar) | St. Paul, MN |  | VS19174418 3102-1200 3102-BBNB | 2019-10-17 | 2020-01-17 | 2020-01-17 | 2020-05-05 |  | Y | BBEC.546848 | Qwest | 03KXGS465552NW | 2020-05-07 | MAIN LEVEL CUSTOMER DATA ROOM. RACK MOUNT CIENA 3916. MM OPT |  |  |  | 96 | 10.1.95.41 | 10.1.95.42 | 64564 | 202610 | UHG GLOBAL 150 | 5/8: ORDER COMPLETE 5/4: Access install improved to 5/7. 3/23-4/27: Access install scheduled for 6/8 DUE TO PERMITTING DELAYS AND WINTER FROST 3/16: Carrier Management advised DELAY IS DUE TO PERMITTING DELAYS AND WINTER FROST, AND A NEW ECD HAD TO BE PROVIDED. 3/9: LEC Qwest changed the install date from 4/7 to 6/8 with no reason provided. AERO CM ticket 911055 opened to engage Carrier Management to find out what's going on. 11/18-3/2: QWEST PROVIDED A 4/7/2020 INSTALL DATE - MAJOR BUILD 11/4-11/11: USO's rec'd - pending install date from LEC Qwest - FOC due back by 12/6. 10/17: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000 Base-SX | NY500-02-IM | UHG | Melissa Chapman | Uniland | 600 Airborne Pkwy | Cheektowaga, NY (Buffalo) |  | VS19189701 3102-1298 3102-BBPM 3102-BBPN | 2019-11-25 | 2020-02-24 | 2020-02-24 | 2020-05-08 |  | Y | BKEC.958630 | Verizon North | 40KFGS221523NY | 2020-03-05 | 1ST FLOOR...ELEC ROOM...WALL MOUNTED... NID # 1... MMF |  |  | 1000 Base-SX | 117 | 10.1.86.161 | 10.1.86.162 | 64775 | 202610 | UHG GLOBAL 150 | 5/8: ORDER COMPLETE 4/27-5/4: VLAN PON incomplete - issued Aero Design ticket 981078 to complete engineering so we can push on rest of order. LEVEL1 ESCALATION ISSUED 4/20: Access install completed per Verizon. Pending demarc info and completion of remaining critical dates. NOTE: VLAN PON HNSV4409365 is not yet showing complete on the Verizon side. 3/9-4/13: Our order with Verizon shows an install date of 4/15. Per Melissa last week, "Verizon circuit is 40.KFGS.222047..NY and has a FOC of 4/15" 3/2: LEC CAME BACK WITH "1C=CUSTOMER NOT READY" AGAIN. - NOTE FROM LEC: UNABLE TO CONTACT ROB DARATA JR AND PHILIP JOSEPH DAMASCO II OVER THE PHONE. SENT VOICE MAIL. 2/17-2/24: Access install has been improved from 4/15 to 3/5 2/11: Access install rescheduled for 4/15. 2/4: Per Design, LCON has been updated and an Aero Design ticket #864966 has been raised to supp the PON. UPDATE THIS MORNING: LEV VERIZON SENT R15 NOTICE - "CUSTOMER BLDG/TELCO ROOM NOT READY CKL 2" 1/30-2/3: Reached out to ordering to ensure USO has been updated appropriately with LCON change. Design is advising they're not seeing the change. Once confirmed I will escalate on the PON. 1/27: Issued 2nd Level escalation on AERO Design ticket 847651 to remove R15 - confirm LCON change 1/20: Issued 1st Level escalation on AERO Design ticket 847651 to remove R15 - confirm LCON change 1/15: Aero Design ticket 847651 - remove R15 - confirm LCON change 12/18-1/13: Some not-so-good news from Verizon for your Uniland order in Cheektowaga, NY: Per Verizon: “FACILITIES ARE NOT AVAILABLE. OUR BEST ESTIMATE DATE IS 03/16/2020. A FOC WILL BE SENT WHEN AN ACTUAL DUE DATE HAS BEEN DETERMINED.” CUSTOMER BLDG/TELCO ROOM NOT READY 12/17: Email from Vaishnavi Sabunkar (Ordering team) looking to confirm address and "Sodexo" building. 12/12-12/16: Pending release of the PON to the LEC Verizon North. UPDATE: PON released 12/12. Pending install date. 11/26: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-LX | C1654-02-IM | UHG | Melissa Chapman | Sitel | 11830 Webb Chapel Rd | Dallas, TX |  | VS20058805 3102-1476 7MS02402790 3102-BBVS | 2020-04-10 | 2020-04-24 | 2020-07-13 | 2020-05-06 |  | Y | IUEC.944682 | ATT SW | 14KRGN888257SW | 2020-05-06 | LOC STE#200, MEET ME CAGE, RELAY RACK 102.14, SHELF 2, PORT 10 |  |  |  | 50 | 10.191.22.89 | 10.191.22.90 | 65509 |  | UHG ECC | 5/7: ORDER COMPLETE 4/28-5/4: Access install scheduled for 5/6. 4/27: Pending an install date from ATT SW 4/10: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | CO026-04-IM | UHG | Melissa Chapman | Optum | 12503 E Euclid Drive, Ste. 80 | Centennial, CO |  | VS20056266 3102-0808 3102-BBTG | 2020-04-16 | 2020-04-21 | 2020-07-08 | 2020-05-06 |  | Y | BBEC.661729 | Qwest | 29KXGS512663MS | 2020-05-22 | TELEPHONE ROOM TYPE: OPTICAL PORT: 2 |  |  |  | 61 | 10.1.84.53 | 10.1.84.54 | 64654 | 202610 | UHG GLOBAL 150 | 5/7: ORDER COMPLETE 5/4: Access install completed last week well ahead of schedule. VLAN PON HWSV4460446 was just released yesterday 5/3 and pending a target date for completion. 4/27: Qwest Access install scheduled for 5/22. 4/21: Pending an install date from the LEC Qwest. 4/16: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL015-05-IM | UHG | Melissa Chapman | Wellmed | 1627 US Hwy 1, Suite 101 | Sebastian, FL |  | VS20057308 3102-0954 3102-BBTV | 2020-04-16 | 2020-04-29 | 2020-04-29 | 2020-04-29 |  |  | BBEC.661705 | ATT SE ONNET-5 | 60KRGN765224SB | 2020-04-29 | SBSTFLEG0AW 01EWAL.000 01-05 TAGGED |  |  |  | 50 | 10.1.84.17 | 10.1.84.18 | 65028 | 202610 | UHG GLOBAL 150 | 4/29: ORDER COMPLETE 4/27: Access install scheduled for 4/29. 4/16: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL158-05-IM | UHG | Melissa Chapman | Wellmed | 10151 Deerwood Park Blvd Bldg 300 Suite 310 | Jacksonville, FL |  | VS20060035 3102-1484 3102-BBWC | 2020-04-20 | 2020-04-28 | 2020-05-22 | 2020-05-06 |  | Y | BBEC.671624 | ATT SE | 52KRGN703361SB | 5/7 | 3RD FL, SUITE 310, SERVER RM, WALL |  |  |  | 50 | 10.1.83.73 | 10.1.83.74 | 65180 | 202610 | UHG GLOBAL 150 | 5/7: ORDER COMPLETE 5/5: ATT SE Access install scheduled for 5/7. 4/20: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX371-05-IJ | UHG | John Sergot | Wellmed | 850 W Business Hwy 77 | San Benito, TX |  | VS20058712 3102-1475 HWS03854814 3102-BBVR | 2020-04-21 | 2020-04-24 | 2020-07-22 | 2020-05-07 |  | Y | BBEC.665036 | ATT SW | 38KRGN614046SW | 2020-05-06 | 1ST FLR,IT ROOM,CIENA 3903 WALL MT, RT 1 |  |  |  | 50 | 10.1.82.109 | 10.1.82.110 | 65279 | 202610 | UHG GLOBAL 150 | 5/7: ORDER COMPLETE 4/27-5/4: Access install scheduled for 5/6. 4/21: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | MS007-04-IM | UHG | Melissa Chapman | Catamaran | 3539 Bluecutt Road | Columbus, MS |  | VS20061530 3102-1511 3102-BBWJ | 2020-04-23 | 2020-04-29 | 2020-07-17 | 2020-05-07 |  | Y | BBEC.642076 | ATT SE | M1KRGN825784SC | 2020-05-11 | 1,SERVER RM,WALL MT |  |  |  | 50 | 10.1.84.149 | 10.1.84.150 | 64552 | 202610 | UHG GLOBAL 150 | 5/8: ORDER COMPLETE 5/4: Access install scheduled for 5/11. 4/23: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-LX | C1622-05-IM | UHG | Melissa Chapman | Sitel | 5601 No. 103rd St | Omaha, NE |  | VS20053542 3102-0416 7CS04454097 CLO NES000176001 3102-BBSZ | 2020-04-13 | 2020-07-13 | 2020-07-13 | 2020-05-12 |  | Y | IUEC.872875 | ASE LNS | NEKRGN100097TPM | 2020-05-11 | PLACED SFP ON JACK2 IN 5150 AND RAN JUMPER TO DMARC ON JACKS 3 AND 4. TAGGED ON BOTH ENDS. RAN UTG. DEMARC INFO: 1000A.06LGX PANEL JACKS 3 & 4 SC CONNECTOR. SINGLE MODE | 1000 BASE LX |  |  | 50 | 10.191.19.5 | 10.191.19.6 | 65504 COS 9249 |  | UHG ECC | 5/13: ORDER COMPLETE 5/11: Fiber infrastructure showing completed as of 5/6. Work being done onsite as of Friday. Access demarc provided, pending testing completion and the OK to turn up. 4/27-5/4: SITE VISIT CNR ISSUE. SITE VISIT IS PENDING DUE TO LCON UNRESPONSIVE. 4/21: Pending an install date and construction update on fiber work. 4/13: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL212-08-IM | UHG | Melissa Chapman | Wellmed | 809 S ORLANDO AVE Building , Floor 1, Room J | Winter Park, FL |  | VS20056515 3102-0901 3102-BBTN 3102-BBTM | 2020-04-16 | 2020-04-21 | 2020-07-08 | 2020-05-13 |  | Y | BBEC.634168 | Embarq | 25KXGS513720UFLG | 2020-06-24 | FIRST FLOOR MAIN TELCO REAR OF PALAZA WALL MOUNTED RAD203A PORT 4 |  |  |  | 2 | 10.1.84.85 | 10.1.84.86 | 65271 | 202610 | UHG GLOBAL 150 | 5/14: ORDER COMPLETE 5/11: Access install scheduled for 6/24. 4/27-5/4: Pending an install date from the LEC Embarq 4/16: Order rec'd - requested to use Embarq
New | 100M Port/ 250M Access EaAVPN 1000 Base-SX | WI053-02-IM | UHG | Melissa Chapman | United Healthcare | 125 South 84th Street Floor 4 | Milwaukee (West Allis), WI |  | VS20064166 3102-1559 3102-BBXG | 2020-05-04 | 2020-05-13 | 2020-05-13 | 2020-05-13 |  | Y | BREC.802551 | ATT MW ONNET-5 | 44KRGN103123WT | 2020-05-13 | BASEMENT ATT PHONE POPRT 5 SLOT 5/6 |  |  |  | 50 | 10.1.87.109 | 10.1.87.110 | 64944 | 202610 | UHG GLOBAL 150 | 5/13: ORDER COMPLETE 5/12: Access install scheduled for 5/13. 5/4: Order rec'd
New | HOT ORDER 50M Port/ 50M Access EaAVPN 1000 Base-SX | NJ735-02-IM | UHG | Melissa Chapman | Optum | One Harmon Plaza | Secaucus, NJ |  | VS20029770 3102-0776 HNS01978907 3102-BBRQ 3102-BBRP | 2020-02-20 | 2020-05-14 | 2020-05-14 | 2020-05-19 |  | Y | BBEC.568525 | Level3 Communications | BCCG93725LVLC | 2020-05-26 | 2ND FLOOR, ELECTRICAL ROOM. RACK 02.01, RMU 29 SWITCH SCCS3407W2001 PORT 11. |  |  |  | 50 | 10.1.93.113 | 10.1.93.114 | 65397 | 202610 | UHG GLOBAL 150 | 5/23: ORDER COMPLETE 5/19: Engineering, Design and Wiring completed yesterday - working to get this to a tech to complete it out. 5/15: We have R84 completion notice from the LEC on the access PON. Pending demarc info and completion of remaining milestones so we can make this ready for turn up plug and play. 5/15: LEC provided 5/26 target install date. 5/4-5/11: Order issues fixed. New PON HNS01978907 was released on 5/1 and we're currently pending an install date from Time Warner. FOC due back by 6/5. 4/28: Provisioning advised there is currently a ticket to get the PON reissued to the LEC. Expecting to hear back on that ticket today. 4/27: Per the LEC, REJECTED STATUS because the collector ID is invalid and needs to be fixed by ATT Provisioning. AERO Design ticket 981172 issued to reissue the access PON per Lev3/Centurylink. ADDED TO HOT LIST. 4/20: LCON changes are complete on the USO - pending an install date from the LEC. 4/13: Pending confirmation of LCON change and an install date from the LEC. 4/9: Issued IOS change order to change LCON/ALCON per Melissa. 4/8: Issued AERO DESIGN 954025 for R15 issue from LEC Time Warner. Melissa sent email at 3:35pm today to adjust contacts. 3/23-4/6: Pending FOC on PON# 7NS01975292 3/9-3/16: PON released on 3/6 and FOC due back by 4/9. 3/2: Pending PON release to Level3 (scheduled to go out tomorrow 3/4) 2/20: Order rec'd
New | 20M Port/ 20M Access Ethernet ADI 1000 Base-SX | TX092 | UHG | John Sergot |  | 1030 Bensdale Rd | Pleasanton, TX |  | IP20030394 3102-1406 7MS02398751 3102-BBSG |  |  | 2020-06-15 | 2020-05-20 |  |  | MMEC.876342 | SBC | 31KRGN654677SW | 2020-06-11 | 1ST FLR TELCO RM ON WALL MOUNT UNIT 1 |  | WAN IP Information CR Serial IP Address: 32.140.165.178/30 IPv6 CR Serial IP Address: 2001:1890:0C05:1FD6:0000:0000:116A:921A/64 Compressed IPv6 CR Serial IP Address: 2001:1890:C05:1FD6::116A:921A AR Serial IP Address: 32.140.165.177/30 IPv6 AR Serial IP Address: 2001:1890:0C05:1FD6:0000:0000:EE6A:921A/64 Compressed IPv6 AR Serial IP Address: 2001:1890:C05:1FD6::EE6A:921A Wan IP Address: 32.140.165.176/30 ------------------------- LAN Information IPV4 Block: 12.222.64.0/28 LAN IP Gateway: 12.222.64.1 First Network Assignable: 12.222.64.2 Usable IP Range: 12.222.64.2 - 12.222.64.14 Broadcast IP Address: 12.222.64.15 Subnet Mask: 255.255.255.240 IPv6 Block: 2001:1890:1827:D400::/56 IPv6 LAN IP Gateway: 2001:1890:1827:D400::1 IPv6 Prefix: 0,56 Internet Services: | [7 empty] | 5/26: ORDER COMPLETE - READY FOR TURN UP - IP Details in column U 5/18: Construction completed their fiber work on Thursday 5/14. Access install was moved up from 6/11 to 5/19. 4/6-5/11: Construction fiber work scheduled for 6/2. Access install scheduled for 6/11. 3/30: USO's loaded - PON released to the LEC. Pending install date. 3/24: Per Clyde: This order has been prioritized by Dev Team and trying to resolve the issue. Will let you know once I received another updates. 3/3: Reached out to Clyde - UPDATE PER CLYDE: "Order is still not loaded in the system. I have already escalated this to HALO Team. Will let you know the new update by eod." 2/24: Order rec'd
New | 20M Port/ 20M Access Ethernet ADI 1000 Base-SX | TX259-04-IJ | UHG | John Sergot |  | 113 Star Grass Suite 110 | Spring Branch, TX |  | IP20018666 3102-0708 7MS02393387 3102-BBRK | 2020-02-24 | 2020-05-12 | 2020-05-12 | 2020-05-19 |  |  | MMEC.541826 | GVCS CLEC | 31KRBD935066GVC | 2020-05-12 | COM ROOM PORT 1 OF FIBER ONT EXTENDED TO A PATCH THRU BOX ON |  | WAN IP Information CR Serial IP Address: 32.140.187.34/30 IPv6 CR Serial IP Address: 2001:1890:0C05:1F7E:0000:0000:11DA:2B61/64 Compressed IPv6 CR Serial IP Address: 2001:1890:C05:1F7E::11DA:2B61 AR Serial IP Address: 32.140.187.33/30 IPv6 AR Serial IP Address: 2001:1890:0C05:1F7E:0000:0000:EEDA:2B61/64 Compressed IPv6 AR Serial IP Address: 2001:1890:C05:1F7E::EEDA:2B61 Wan IP Address: 32.140.187.32/30 --------------------------- LAN Information IPV4 Block: 12.44.156.208/28 LAN IP Gateway: 12.44.156.209 First Network Assignable: 12.44.156.210 Usable IP Range: 12.44.156.210 - 12.44.156.222 Broadcast IP Address: 12.44.156.223 Subnet Mask: 255.255.255.240 IPv6 Block: 2001:1890:1827:7100::/56 IPv6 LAN IP Gateway: 2001:1890:1827:7100::1 IPv6 Prefix: 0,56 Internet Services: | [7 empty] | 5/26: ORDER COMPLETE - READY FOR TURN UP - IP Details in column U 5/18: Access installed - pending completion of remaining provisioning milestones and the OK to turn up. Also working to get clarification of demarc. 4/27-5/11: Access install remains on track for 5/12. 4/13-4/20: Access install rescheduled for 5/12. No reason provided yet - falls right on overall 5/12 due date. 3/30-4/6: Access install scheduled for 4/30. 3/23: LEC GVCS pushed out the install to 4/30 on Friday. No reason provided yet. 3/16: Access install scheduled for 3/31. 3/9: PON sent on 2/27 - FOC due back by 3/10 2/25: Address change per Chris 2/24: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | AR003-04-IM | UHG | Melissa Chapman | Optum | 1 Allied Drive, Ste. 2210 | Little Rock, AR |  | VS20064417 3102-1560 3102-BBXH | 2020-04-16 | 2020-05-13 | 2020-05-20 | 2020-05-19 |  | Y | BBEC.661606 | SBC ONNET-5 | 63KRGN602657SW | 2020-05-19 | 2ND FL TELCO RM CIENA PORT 2 EXT TO 2210 MDF ROOM |  |  |  | 50 | 10.1.84.201 | 10.1.84.202 | 64947 | 202610 | UHG GLOBAL 150 | 5/20: ORDER COMPLETE 5/12: Access install scheduled for 5/19. 4/16: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX092-05-IM | UHG | Melissa Chapman | Wellmed | 1030 Bendsdale | Pleasanton, TX |  | VS20057248 3102-0920 7MS02402300 3102-BBTP | 2020-04-17 |  | ASAP | 2020-05-20 |  | Y | BBEC.667655 | SBC | 31KRGN654753SW | 2020-06-11 | 1ST FLR TELCO RM ON WALL MOUNT UNIT 1, PORT 7 |  |  |  | 50 | 10.1.84.137 | 10.1.84.138 | 65277 | 202610 | UHG GLOBAL 150 | 5/26: ORDER COMPLETE 5/18: Access install scheduled for 6/11 5/11: Confirmed LCON has been changed on USO to Cynthia Zuniga, 830-569-6615, cyzuniga@wellmed.net 4/27-5/11: Access install scheduled for 6/11. 4/23: HITS ticket issued to change the LCON to Cynthia Zuniga 830-569-6615 cyzuniga@wellmed.net. 4/17: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL077-05-IM | UHG | Melissa Chapman | Wellmed | 2191 9th Ave. N. Ste. 110 | St Petersburg, FL |  | VS20057401 3102-1435 3102-BBTX 3102-BBTW | 2020-04-20 | 2020-04-22 | 2020-07-20 | 2020-05-16 |  | Y | BBEC.674848 | Frontier-CTF | 65KFGS372533FTNC | 2020-05-29 | RAD-ETX 203 PORT 5. SUITE 235 TELCO CLOSET WALL MOUNTED |  |  |  | 55 | 10.1.83.149 | 10.1.83.150 | 65187 | 202610 | UHG GLOBAL 150 | 5/18: ORDER COMPLETE 5/11: Access install scheduled for 5/29. 5/4: PON released last week. Pending access install date. 4/27: Pending release of the PON to the LEC Frontier (FOD 4/27) - AERO Design 982056 for PON issuance 4/20: Order rec'd
New | CANCELLED 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX423-06-IM | UHG | Melissa Chapman | Wellmed | 100 Wilson Drive | Floresville, TX |  | VS20057400 3102-1022 3102-BBTZ 3102-BBTY | 2020-04-20 | 2020-04-22 | 2020-07-20 |  |  |  | BBEC.661701 | Frontier-CTF | [7 empty] | 10.1.83.77 | 10.1.83.78 | 64724 | 202610 | UHG GLOBAL 150 | SPECIAL CONSTRUCTION - COST: $49,710.00 SOW: 6000 FT OF FIBER PLUS LABOR SPLICING & EQUIPMENT. EXPIRES: 7/3/20 ORDER CANCELLED BY MELISSA - IOS TICKET ISSUED 4/27-5/18: Pending an install date from Frontier - AERO Design ticket 981730 (cleared 4/30) 4/20: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | TX354-05-IM | UHG | Melissa Chapman | Wellmed | 809 W. Nash St. #100 | Terrell, TX |  | VS20059550 3102-1479 7MS02402996 3102-BBVW | 2020-04-22 | 2020-04-27 | 2020-07-23 | 2020-05-18 |  | Y | BBEC.671633 | SBC | 14KRGN888263SW | 2020-06-02 | 2ND FLR...TELCO RM. WALL MOUNT. PORT 1 |  |  |  | 50 | 10.1.83.9 | 10.1.83.10 | 64594 | 202610 | UHG GLOBAL 150 | 5/18: ORDER COMPLETE 5/4-5/11: Construction fiber work scheduled to complete on 5/21. Access install scheduled for 6/2. 4/28: Pending install date from the LEC 4/22: Order rec'd
New | 150M Port/ 200M Access EaAVPN 1000 Base-LX | C1657-01-IM | UHG | Melissa Chapman | Broadpath c/o Equnix | 910 15th St. | Denver, CO |  | 3102-0137 3102-BBXW | 2020-05-06 | 2020-05-14 | 2020-08-11 | 2020-05-19 |  | Y | BREC.811511 | ASE LNS | COKRGN100792TPM | 2020-05-28 | 3RD FLOOR MMR 030003.05 SH 7 JK 25/26 | 1000 BASE LX |  |  | 50 | 10.191.22.217 | 10.191.22.218 | 65439 |  | UHG-ECC | 5/26: ORDER COMPLETE 5/19: Access install scheduled for 5/28. 5/6: Order rec'd
New | HOT ORDER 200M Port/ 500M Access EaAVPN 1000 Base-SX | MI078-02-IM | UHG | Melissa Chapman | DIPLOMAT FLINT DATACENTER | 4100 S Saginaw Street | Flint, MI |  | VS20064927 3102-1568 3102-BBXR | 2020-04-29 | 2020-05-29 | 2020-05-29 | 2020-05-29 |  | Y | BMEC.528650 | AT&T MIDWEST NEARNET-15 | KRGN216178MB | 2020-05-29 | 2ND FLR DATA CENTER RACK MNT,PORT#5 |  |  |  | 50 | 10.1.95.157 | 10.1.95.158 | 65045 | 202610 | UHG GLOBAL 150 | 6/1: ORDER COMPLETE 5/18-5/26: Access install scheduled for 5/29. 5/13: Added to HOT order list 5/11: Pending an install date from ATT MW 4/29: Order rec'd
New | CANCELLED 10M Port/ 50M Access EaAVPN 1000 Base-SX | NV064-07-IM | UHG | Melissa Chapman | Optum | 2210 E. Calvada | Pahrump, NV |  |  | 2020-03-23 | [14 empty] | 10.1.85.137 | 10.1.85.138 | 65144 | 202610 | UHG GLOBAL 150 | 6/3: ORDER CANCELLED 3/23: Order rec'd - special access pricing
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | CA459-02-IM | UHG | Melissa Chapman | United Healthcare | 9055 Las Tunas Drive Suite 120 | Temple City, CA |  | VS20053543 3102-0177 3102-BBSY | 2020-04-10 | 2020-07-13 | 2020-07-13 | 2020-05-29 |  | Y | BBEC.671712 | SBC | 13KRGN602452PT | 2020-05-28 | BASEMENT MPOE N/A - CIRCUIT 13KRGN602452PT TAGGED ON HANDOFF 1 IN MOPE ON SE CORNER |  |  |  | 50 | 10.1.84.209 | 10.1.84.210 | 65056 | 202610 | UHG GLOBAL 150 | 6/1: ORDER COMPLETE 5/19-5/26: Access install scheduled for 5/28. 4/21: Pending an install date from the LEC. PER CONSTRUCTION: Fielder spoke to contact, Neelanshu Singh and an additional contact, David Hsu. They want to wait for a later date for the site survey when more places start opening back up due to COVID-19. 4/10: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | UCA99-08-IM | UHG | Melissa Chapman | Optum | 4365 Executive Drive #500 | San Diego, CA |  | VS20057304 3102-0935 7WS03854165 3102-BBTT | 2020-04-16 | 2020-04-22 | 2020-07-09 | 2020-05-29 |  | Y | BBEC.674851 | ATT West | 19KRGN533879PT | 2020-06-03 | 5 MPOE PATCH PANEL 1 POS 4 TAGGED |  |  |  | 50 | 10.1.84.73 | 10.1.84.74 | 64942 | 202610 | UHG GLOBAL 150 | 6/1: ORDER COMPLETE 5/26: Access install complete - pending testing completion and the OK to turn up. 5/19: Pending update from the field tech....showng they were working the access, had an equipment issue. Overall due date 6/18 not in jep at this point. 5/18: Confirmed infrastructure completed last week. Access install has been bumped up to TODAY 5/18 5/11: Fiber work due to complete on 5/22. Access install scheduled for 6/3. 5/4: Site visit completed on Friday 5/1. Pending details and target date for fiber work. 4/27: Pending an install date from the LEC ATT West 4/16: Order rec'd
New | 150M Port/ 200M Access EaAVPN 1000 Base-LX | C1656-01-IM | UHG | Melissa Chapman | Broadpath c/o Equnix | 180 Peachtree Street NW, 2nd Floor | Atlanta, GA |  | VS20067917 3102-0238 3102-BBXX | 2020-05-06 | 2020-05-14 | 2020-07-31 | 2020-05-27 |  | Y | BREC.811698 | ATT SE | 38KRGN617452SB | 2020-05-26 | 2FLR CAGE 021710 CP:0103:1031028 |  |  |  | 50 | 10.191.22.213 | 10.191.22.214 | 65435 |  | UHG-ECC | 6/1: ORDER COMPLETE 5/19-5/26: Access install scheduled for 5/26. 5/6: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL039-09-IM | UHG | Melissa Chapman | Wellmed/preferred care partners | 415 West 49 Street | Hialeah, FL |  | VS20057969 3102-1448 7SS03664269 3102-BBVH | 2020-04-20 | 2020-04-23 | 2020-07-10 | 2020-06-05 |  | Y | BBEC.671651 | ATT SE | 60KRGN765227SB | 2020-06-05 | 415 SERVER ROOM WALL | 1000Base-SX |  |  | 50 | 10.1.83.193 | 10.1.83.194 | 65274 | 202610 | UHG GLOBAL 150 | 6/6: ORDER COMPLETE 6/1: Fiber work completed last week, well ahead of schedule. Access install moved up from 8/10 to 6/5. 5/26: Pending fiber work completion - access install showing 8/10. 5/4-5/18: Fiber work due to complete on 8/4. Access install scheduled for 8/13. Per your acceptance of the ASE Entrance Facility Offer, AT&T will complete the specified site readiness requirements listed below: - Pull Tape in conduit capable of supporting a minimum of 200 lb. pulling weight. Depending on the specific site requirements a System Permission form may be required to be signed by the building owner. If required, the AT&T site visit engineer will provide a copy of the System Permission form by hand or via email to the building owner or appropriate Building Management group identified during the site visit. It is crucial for AT&T to receive a prompt signature and returned copy of the System Permission form, when required, to meet the due date specified above. If the site requirements are interior to the building, the System Permission form is not required. However, per the language in your ASE service agreement, the Customer is obligated, in a timely manner, to allow AT&T access to the property and equipment the Customer controls, and/or obtain permission to access and install the site requirements identified above in areas controlled by third parties such as the Customer's landlord. ADDITIONAL CUSTOMER WIRING REQUIREMENTS: As discussed at the Site Visit, you are also responsible for a path, if required, from the NTE location which I pointed out in the Common Area/MPOE, on floor 01, to the customer demarcation panel and then to your router (usually located in your suite or equipment room). This path may include available space in existing floor sleeves, a minimum 2" conduit, and pull tape if the demarcation panel is located in a separate room than the NTE. 4/27: Pending an install date from ATT SE 4/20: Order rec'd
New | CANCELLED 20M Port/ 50M Access EaAVPN 1000 Base-SX | TX341-07-IM | UHG | Melissa Chapman | Wellmed | 1313 E Alton Gloor Blvd. | Brownsville, TX |  | VS20066821 3102-1562 3102-BBXK | 2020-04-23 | 2020-05-07 | 2020-08-07 |  |  |  | BBEC.674754 | SBC | [7 empty] | 10.1.82.233 | 10.1.82.234 | 65242 | 202610 | UHG GLOBAL 150 | 6/4: ORDER CANCELLED PER MELISSA. 6/1: Need to S19C per Melissa email 5/19-5/26: Pending site visit on the Construction side - C01 5/12: USO's rec'd 4/23: Order rec'd
New | CANCELLED 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX346-06-IM | UHG | Melissa Chapman | Wellmed | 7198 Merchant Ave | El Paso, TX |  | VS20066820 3102-1565 7MS02405330 3102-BBXM | 2020-04-23 | 2020-05-07 | 2020-10-14 |  |  |  | BBEC.664952 | SBC | 30KRGN615474SW | 2020-09-28 | [5 empty] | 10.1.82.229 | 10.1.82.230 | 64832 | 202610 | UHG GLOBAL 150 | 5/20: Rec'd cancellation request from Melissa. HITS ticket issued. 5/19: Fiber work due to complete 9/17. Access install scheduled for 9/28. 4/23: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | NJ139-05-IM | UHG | Melissa Chapman | Optum RX | 19 Chapin Rd Building D | Pine Brook, NJ |  | VS20065607 3102-1570 3102-BBXV 3102-BBXT | 2020-05-06 | 2020-05-08 | 2020-07-27 | 2020-06-04 |  | Y | BBEC.664938 | CABLEVISION LIGHTPATH | 06LUXS605737CLVI | 2020-07-06 | BEHIND BUILDING D UTILITY ROOM/ SPRINKLER CONTOL VALVE WALL BOARD 1JW SFP A |  |  |  | 202 | 10.1.84.193 | 10.1.84.194 | 64850 | 202610 | UHG GLOBAL 150 | 6/5: ORDER COMPLETE 5/26-6/1: Access install scheduled for 7/6. 5/12-5/18: Pending an install date from the LEC CABLEVISION LIGHTPATH 5/6: Order rec'd
New | 500M Port/ 1G Access EaAVPN 1000 Base-LX | LA013-02-IM | UHG | Melissa Chapman | People's Health | 3838 N. Causeway Blvd | Metairie, LA |  | VS20071043 3102-0962 3102-BBYC | 2020-05-19 | 2020-05-21 | 2020-06-23 | 2020-06-04 |  | Y | IZEC.645799 | ATT SE | L2KRGN822595SC | 2020-06-05 | 23 2300 DATA ROOM WALL MOUNT |  |  |  | 50 | 10.1.83.85 | 10.1.83.86 | 65393 | 202610 | UHG GLOBAL 150 | 6/5: ORDER COMPLETE 6/2: LEC access install scheduled for this Friday, 6/5. 5/19: Pending USO's
New | CANCELLED 30M Port/ 50M Access EaAVPN 1000 Base-SX | LA015 -01-IM | UHG | Melissa Chapman | People's Health | 100 Warrington Dr | New Orleans, LA |  |  | 2020-05-20 | [14 empty] | 10.1.82.181 | 10.1.82.182 | 65384 | 202610 | UHG GLOBAL 150 | 5/27: ORDER CANCELLED by Melissa via email. 5/20: Pending USO's
New | HOT ORDER 50M Port/ 100M Access Managed AVPN w/ SIP | PA007-11-IM | UHG | Melissa Chapman | Executive Health Resource | 15 Campus Blvd | Newtown Square, PA |  | VR19122845 3094-0987 3094-BVQY 3094-BVQZ | 2019-07-18 | 2019-08-01 | 2020-02-03 | 2020-06-16 |  | N | IUEC.527103 | Comcast Business Comm | 11KFGS046096CBCL 11KGGS024346CBCL | 5/29/2020 6/24/2020 | 1ST FLOOR SERVER ROOM ON THE PILLA PORT 1 TAGGED AND LABELED. |  |  |  | 200 | 32.246.148.106 | 32.246.148.105 | 65000 | 1244159 | OPAS SIP | 6/17: ORDER COMPLETE 6/16: We have R84 completion notice back from the LEC Comcast on the new PON# HESC2939430. Working to close this out. 6/15: Target completion date of new PON - 6/24. Working to improve if possible. 6/8: Tech SME make the correction to the Pop Collector. New PON HESC2939430 issued end of last week. Pending completion date. 6/1: Escalation to Jay Hodges to get order worked. 5/19: RECEIVED R84 FROM LEC - pending access completion details. 5/18: Comcast provided an improved 5/20 install date. 4/27-5/11: Currently the LEC Comcast is targeting a 5/29 access install date. Access circuit ID was changed to 11KFGS046096CBCL. 4/21: All the various entrances to this site are owned by Verizon. The end-user isn't 100% certain they want to allow Comcast into this building. The likelihood of VZ allowing Comcast to use one of their conduits has a very low probability. So at this time, UHG needs to decide to allow Comcast to build their own entrance (another delay in delivery) or cancel the order with Comcast and reissue using VZ as the LEC. 4/17: Per Christian Buyser (Optum), "I went onsite again today and met with Verizon (Brian), while there ran into a surveyor (Tommy from Master Locators) working for Buckley who will be pulling the new fiber. It appears from what I discussed with Tommy that Buckley is preparing to run new conduit to 15 Campus. I discussed other alternatives with both Tommy and Brian, asking Tommy to include the possible alternatives in his notes for Buckley." 4/14: Comcast provided powerpoint with build details. Comcast advised target date for completion of build is 5/11. 4/13: Jane Tansor, Libby Cohen (Director) and Leigh Canada (Escalation Mgr) engaged last week for additional assistance - Leigh and Jane are pursuing this order with Comcast to understand their request for additional conduit. 4/6: Per Carrier Management, Comcast advised they are pending results of the site survey and expect that info this week. FOC will be issued after that. Carrier Mgmt set to follow up by COB 4/8. 3/31: TICKET # 917496 - COMCAST SAYS THE SITE SURVEY SHOULD TAKE PLACE TODAY (31 MARCH), FOLLOWED BY ISSUANCE OF THEIR CIRCUIT DESIGN AND FOC TO AT&T. - F/U 4/3/2020 3/31: Escalated back to Carrier Management this morning on AERO CM TICKET 917496. Included 2nd/3rd Levels (Shearholdt) 3/30: Requested PON update from Carrier Management SOURAV DALAL. 3/23: Pending update on PON sent 3/11. 3/11: Confirmed PON supp sent today - pending update from LEC. 3/10: Both the LCON and ALCON confirmed we have the correct info and that they have NOT been contacted by the LEC. I have reached out to the CNR AGENT assigned (DEBNATH, SUDIP) and advised him we need to supp the PON and escalate to the LEC Comcast as it doesn't appear we're getting truthful updates from them. 3/9: Reached out to LCON's Darryl and Paul to confirm if LEC Comcast has reached out to them. We continue to receive CNR emails from Comcast and I want to make sure the LCON's are being contacted by Comcast. 3/3: Added to HOT list 3/2: Level2 Escalation issued on AERO Design Ticket 887170 - need R15 removed and dispatch ASAP. 2/24: AERO ticket 887170 (clear R15) - CNR agent not engaged - working to get update from LEC. Advised team we need immediate dispatch - competition has already installed. Pending update on escalation. 2/11-2/17: Please reconfirm LCON details. Latest update from my AERO ticket: PER LEC R15, LCON IS NOT RESPONDING TO CALLS TO SCHEDULE THE INSIDE WORK. 2/3: Issued 1st Level escalation on AERO ticket 856199 - R15. Access still showing due to complete on 2/14, working to confirm 12/30-1/27: Access install scheduled for 2/14/20. - AERO 856199 12/3-12/16: Pending install date from the LEC Comcast - FOC due back by 12/24. 11/25: PON was supp'd on 11/18....apparently the word "Square" wasn't in the PON to the LEC - corrected and now pending an install date. 11/18: Pending clearing of R15 address issue - AERO DESIGN ticket 795554 issued and provided them example circuit which is using same address. 9/23-11/4: Still pending completion of POP Collector build. Engineering is showing tentatively scheduled for 11/29. 8/26-9/16: POP Collector build - THIS ORDER INVOLVES COLLECTOR CKT BUILD.(120-150 DAY PROCESS) 7/29-8/26: POP Collector Build Needed (D15I). Build targeted for the end of NoveMer. Once build is completed, PON will be released to the LEC. 7/19-7/22: USO's rec'd - pending install date from LEC 7/9: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX561-02-IM | UHG | Melissa Chapman | Wellmed | 9209 Elam Road, Suite 102 | Dallas, TX |  | VS20024496 3102-0369 7MS02392054 3102-BBQV | 2020-02-13 | 2020-05-05 | 2020-05-05 | 2020-06-15 |  | Y | BBEC.561746 | ATT SW | 14KRGN887818SW | 2020-06-15 | 1 102 SUITE 102 |  |  |  | 50 | 10.1.86.17 | 10.1.86.18 | 64902 | 202610 | UHG GLOBAL 150 | 6/16: ORDER COMPLETE 6/8: Access install rescheduled for 6/15. 6/3: PON SUPP SENT via ServiceNow. Added to HOT list. 5/26-6/1: LEC rejected the order back and advised: Message Type: CUSTOMER - NO ACCESS NO ACCESS DUE TO COVID19. This has been CNR'd again. 5/11-5/18: Pending access install on 5/19....fiber work showing complete. 3/23-5/4: Fiber work scheduled for 5/8. Access install scheduled for 5/19. 3/16: Fiber infrastructure work targeting 5/8 completion. Pending access install date. 2/25-3/9: Pending an install date from ATT SW. Site visit schedule for 3/9 2/13: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | AZ006-07-IM | UHG | Melissa Chapman | Life Print Health | 20414 North 27th Avenue | Phoenix, AZ |  | VS20066201 3102-1485 3102-BBWD | 2020-03-23 | 2020-05-31 | 2020-07-28 | 2020-06-08 |  | Y | IUEC.738852 | Qwest | 19KXGS519734MS | 2020-06-05 | UNI 1ST FLOOR TELCO ROOM WALL MOUNTED TYPE: OPTICAL PORT |  |  |  | 57 | 10.1.85.181 | 10.1.85.182 | 65269 | 202610 | UHG GLOBAL 150 | 6/9: ORDER COMPLETE 6/8: Access install and VLAN completed. Pending testing completion and the OK to turn up. 6/1: Access install scheduled for 6/5. 5/26: PON released on 5/21 - FOC due back by 6/25. 5/18: USO's loaded - need to clarify LEC.....provisioning reached back to ordering to confirm if this is QWEST or COX (confirmed it should be Qwest) 5/12: New USO's 3102-1485 showing in AISE. Those are not loaded in SOTS yet. 5/11: Ordering team is showing order cancelled - working to find out what's going on with this order. 5/4: Issued AERO Design 989818 to have PON issued. 4/30: ORDER SHOWING LOADED IN SOTS 4/20: Clyde confirmed he was cancelling and reissuing. 4/6-4/13: Advised Clyde that the USO 3102-0927 is still not loaded in SOTS. 3/31: Advised Clyde USO is still not loaded in SOTS - recommended he reissue. 3/30: USO's rec'd - pending loading in all systems. Once loaded, check LCON's. Per Melissa, Can you please change the local contacts to the following: Phone Number +1(623) 707-0837 Business Email danny_h_stewart@optum.com Phone Number +1(623) 707-0897 Business Email john_m_candelaria@optum.com 3/23: Order rec'd
New | 40M Port/ 100M Access EaAVPN 1000 Base-SX | LA014-01-IM | UHG | Melissa Chapman | People's Health | 2633 Napoleon Ave | New Orleans, LA |  | VS20076335 3102-0968 3102-BBYD | 2020-05-20 |  | 2020-06-19 | 2020-06-11 |  | Y | IUEC.682185 | ATT SE | L2KRGN822601SC | 2020-06-12 | 5 RISER CLOS 5TH FLOOR RISER CLOSET |  |  |  | 50 | 10.1.82.81 | 10.1.82.82 | 65374 | 202610 | UHG GLOBAL 150 | 6/12: ORDER COMPLETE 6/8: Access install scheduled for 6/12. 5/20: Pending USO's
New | 10M Port/ 20M Access Ethernet ADI 1000 Base-SX | TX371-05-IJ | UHG | John Sergot |  | 850 W Business Hwy 77, Suite C | San Benito, TX |  | IP20011759 3102-0492 3102-BBQS | 2020-02-04 | 2020-03-06 | 2020-05-07 |  |  |  | MMEC.582862 | ATT SW | 38KRGN614013SW | 2020-04-24 | 01 TELCO RM WALL-MOUNTED CIENA 3903 2 LABELE | [9 empty] | 6/29: ORDER IS COMPLETE AND READY FOR TTU 4/6: Fiber infrastructure completed ahead of schedule. LEC advised order delayed - SPOKE TO LCON, MELISSA LOPEZ, ON PRE-CALL @ 956-361-4558, AND EXPLAINED TO HER OUR INSTALLATION ORDER FOR ADDRESS 850 W BUS 77, SAN BENITO TX, SHE SAID UNFORTUNATELY DUE TO COVID19 VIRUS, BUILDING IS CURRENTLY CLOSED TO THE PUBLIC UNTIL FURTHER NOTICE. ORDER JEP'd S19C 3/2-3/30: Fiber infrastructure scheduled to complete on 4/15. Access install scheduled for 4/24. 2/4: Order rec'd
New | ORDER CANCELLED 50M Port/ 100M Access EaAVPN 1000 Base-SX | UWI05-06-IM | UHG | Melissa Chapman | UHG | 2700 Midwest Drive | Onalaska, WI |  | VS20054090 3102-0733 3102-BBTC 3102-BBTB | 2020-03-25 | [5 empty] | IUEC.672118 | [8 empty] | 10.1.85.173 | 10.1.85.174 | 64680 | 202610 | UHG GLOBAL 150 | 6/29: Confirmed order has been cancelled. 6/17: Received cancellation request from Melissa. HITS ticket issued. 5/26-6/15: USO's loaded - PON released to the LEC on 5/20. Pending an install date. FOC due back by 6/24. 5/19: Reached out to PRADHAN, PHALGUNI per Clyde's direction to find out latest on USO's and the POP Collector issue. 5/11: Reached out to Clyde about USO's still not being loaded in SOTS - ordering advised there is a POP COLLECTOR BUILD delaying order. No ETA yet. 4/21: Second set of USO's not showing in SOTS yet. Reached out to Clyde. 4/20: Clyde confirmed he was cancelling and reissuing. 4/6: Advised Clyde that this USO isn't loaded in SOTS. VS20045451 3102-1422 3102-BBSM 3102-BBSL 3/25: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000 Base-SX | AZ163-01-IM | UHG | Melissa Chapman | 4c Medical- UHG | 6501 E Greenway Pkwy Bldg 6, Unit 160 | Scottsdale, AZ |  | VS20054203 3102-0740 3102-BBTD | 2020-04-09 | 2020-07-02 | 2020-06-23 | 2020-06-23 |  | Y | BKEC.968197 | Qwest | 19KXGS510628MS | 2020-06-02 | UNI 1ST FL MPOP SOUTH SIDE WALL MNT TYPE: OPTICAL PORT 3 |  |  |  | 50 | 10.1.87.21 | 10.1.87.22 | 65142 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 6/1-6/15: Access install is showing completed ahead of schedule. VLAN PON HWSV4455028 showing completed R84 as well. Pending testing completion and OK to turn up. Demarc provided. 5/26: New install date showing 6/2. 5/20: PON has been supp'd - pending install date. 5/19: Per Melissa, site requirements complete 5/4: CNR: UPDATE FROM PROVISIONING: CUSTOMER SITE REQUIREMENTS ARE NOT FULFILLED..THEY DO HAVE A FIBER JOB ASSOCIATED WITH THIS ORDER AND NEW EQUIPMENT. THEY EXPECT THE FIBER DESIGN DUE BACK BY END OF WEEK AND THEN IT CAN BE ISSUED TO THE FIELD. THE NEW EQUIPMENT HAS ALREADY BEEN DESIGNED AND ORDERED.THE CUSTOMER DOES HAVE THE MENTIONED SITE REQUIREMENT TO COMPLETE AS WELL.IT NEEDED ONE (1) 15-AMP NEMA 5-15R (STANDARD 3-PRONG 15AMP 120V AC OUTLET) AT THE BACKBOARD LOCATION..HENCE REFERRING THE CASE TO CNR TEAM. 4/21-4/27: Access install scheduled for 4/28. 4/13: Per Melissa, Please go with Qwest 4/9: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL016-06-IM | UHG | Melissa Chapman | Wellmed | 513 NW Lake Whitney Place, Bldg G, Suite 102 | Port St Lucie, FL |  | VS20064418 3102-1561 3102-BBXJ | 2020-04-16 | 2020-05-28 | 2020-05-28 | 2020-06-09 |  | Y | BBEC.671562 | ATT SE | 60KRGN765301SB | 2020-06-03 | 1ST FLR SERVER RM UNIT 1 PORT 5 |  |  |  | 50 | 10.1.84.9 | 10.1.84.10 | 65091 | 202610 | UHG GLOBAL 150 | 6/9: ORDER COMPLETE 6/8: Site was Covid19 delayed per UG but Access and VLAN install completed - pending testing completion and the OK to turn up. 6/1: Access install date improvement from 6/15 to 6/3. 5/18-5/26: Access install scheduled for 6/15. 5/12: Pending an install date from ATT SE 4/16: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL024-06-IM | UHG | Melissa Chapman | Wellmed | 4740 Exploration Ave | Lakeland, FL |  | VS20057250 3102-0929 3102-BBTS 3102-BBTR | 2020-04-17 | 2020-04-22 | 2020-07-20 | 2020-06-16 |  | Y | BBEC.661707 | Frontier-CTF | 65KRGN395464FTNC | 2020-06-16 | BUILDING 1 PHYSICAL EQUIPMENT ROOM RAD 203 PORT 6 MULTIMODE SFP |  |  |  | 340 | 10.1.83.217 | 10.1.83.218 | 65277 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 6/2: USO's loaded in SOTS. Issued AERO Design ticket 1029245 to have PON released to the LEC Frontier. Should this be put on Covid-19 hold?? 6/1: Escalation to Leslie Talochino (AM Ordering) to resolve USO issue 5/26: Requested escalation on USO loading issue - sent to Rajkumar Orsu (OM) 4/27: Pending USO's loading in SOTS - emailed Clyde 4/17: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX164-05-IM | UHG | Melissa Chapman | Wellmed | 1143 E. Sinton St. | Sinton, TX |  | VS20057968 3102-1440 7MS02402528 3102-BBVF | 2020-04-20 | 2020-04-23 | 2020-07-21 | 2020-06-11 |  | Y | BBEC.674844 | SBC | 34KRGN614195SW | 2020-06-23 | 1,LAN, |  |  |  | 50 | 10.1.84.81 | 10.1.84.82 | 65275 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 5/18-6/8: Fiber work still showing due to complete on 6/12. Access install scheduled for 6/23. 5/11: LCON change PON supp request 5/4-5/11: Fiber work due to complete on 6/12. Access install scheduled for 6/23. 4/27: Pending an access install date. 4/20: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL086-05-IM | UHG | Melissa Chapman | Wellmed | 507 West Alexander St. | Plant City, FL |  | VS20057402 3102-1108 HSSC3664246 3102-BBVC 3102-BBVB | 2020-04-20 | 2020-04-22 | 2020-07-20 | 2020-06-11 |  | Y | BBEC.687765 | Frontier-CTF | 65KRGN365622FTNC | 2020-07-16 | FLOOR 1 MDF RM RAD203 PORT 5 |  |  |  | 907 | 10.1.83.125 | 10.1.83.126 | 64814 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 6/1: Need to S19C per Melissa email 5/11-5/26: Access install scheduled for 7/16. 4/27-5/4: Pending an access install date from the LEC Frontier. 4/20: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX414-05-IJ | UHG | John Sergot | Wellmed | 304 E. San Patricio Ave | Mathis, TX |  | VS20058713 3102-1450 7MS02402739 3102-BBVQ | 2020-04-21 | 2020-04-24 | 2020-07-22 | 2020-06-24 |  | Y | BBEC.661689 | ATT SW | 34KRGN614196SW | 2020-07-15 | 1ST FLR ,LAN RM,1ST FLR LAN RM, 3903X, PORT 2 |  |  |  | 50 | 10.1.82.105 | 10.1.82.106 | 65090 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 6/1: Need to S19C per Melissa email 5/4-5/26: Fiber work set to complete on 7/3. Access install scheduled for 7/15. 4/27: Pending an install date from the LEC SBC 4/21: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX349-06-IM | UHG | Melissa Chapman | Wellmed | 6513-C Smithfield Rd | North Richland Hills, TX |  | VS20060847 3102-1539 7MS02403440 3102-BBWL | 2020-04-27 | 2020-04-29 | 2020-07-27 | 2020-06-23 |  | Y | BBEC.664997 | SBC | 14KRGN888282SW | 2020-08-03 | 1ST FLR SUITE C TELCO RM WALL MOUNT ON BK-BRD TAGGED |  |  |  | 50 | 10.1.82.141 | 10.1.82.142 | 65193 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 6/1: Need to S19C per Melissa email 5/11-5/26: Fiber work scheduled to complete on 7/23. Access install scheduled for 8/3. 5/5: Pending an install date from the LEC 4/27: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | LA021-01-IM | UHG | Melissa Chapman | People's Health | 105 Medical Center Dr | Slidell, LA |  | VS20078239 3102-1619 7SS03672951 3102-BBYL | 2020-05-26 | ASAP | 2020-08-21 | 2020-06-18 |  | Y | BBEC.687479 | ATT SE | L2KRGN822611SC | 2020-06-19 | 1 TELCO WALL MT ATT DEMARC PORT 1 TAGD |  |  |  | 50 | 10.1.82.161 | 10.1.82.162 | 65381 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 6/15: Access install scheduled for 6/19. 6/8: Site visit scheduled for 6/10. 5/26: Pending USO's
New | 30M Port/ 50M Access EaAVPN 1000 Base-SX | LA024-01-IM | UHG | Melissa Chapman | People's Health | 2645 O'Neal Lane | Baton Rouge, LA |  | VS20077784 3102-1572 7SS03672737 3102-BBYJ | 2020-05-26 |  | 2020-06-25 | 2020-06-25 |  | Y | BBEC.661409 | ATT SE | L0KRGN401144SC | 2020-06-25 | 1, 1, SERVER RM, WALL MT D CN3930, 5 |  |  |  | 50 | 10.1.82.205 | 10.1.82.206 | 65391 | 202610 | UHG GLOBAL 150 | 6/15: Access install scheduled for 6/25. 6/8: Site visit scheduled for 6/9. 5/26: Pending USO's
New | 30M Port/ 50M Access EaAVPN 1000 Base-SX | LA028-01-IM | UHG | Melissa Chapman | People's Health | 120 Ochsner Blvd 120 MEADOWCREST ST | Gretna, LA |  | VS20077777 3102-1571 7SS03672723 3102-BBYH | 2020-05-27 |  | 2020-08-20 | 2020-06-17 |  | Y | BBEC.664764 | ATT SE | L2KRGN822615SC | 2020-06-17 | 1ST FL TELCO 1ST FL ELECT/TELCO RM H PNL POS 1 |  |  |  | 50 | 10.1.82.201 | 10.1.82.202 | 65389 | 202610 | UHG GLOBAL 150 | 6/29: ORDER COMPLETE 6/9-6/16: Access install scheduled for 6/17. 6/8: Pending an access install date from ATT SE 5/28: Note street address change - IGLOO says 120 MEADOWCREST ST 5/27: Pending USO's
New | 300M Port/ 500M Access EaAVPN 1000 Base-LX | TX479-02-IM | UHG | Melissa Chapman | US HealthGroup | 300 Burnett Street | Fort Worth, TX |  | VS20082790 3102-0022 3102-BBYX | 2020-06-05 |  | 2020-09-11 | 2020-06-26 |  | Y | BMEC.971862 | SBC | 14KRGN888518SW | 2020-06-26 | 3RD SERVER RM CN3930 O-PORT 5 TAGGED |  |  |  | 50 | 10.1.82.57 | 10.1.82.58 | 65085 | 202610 | UHG GLOBAL 150 | 6/30: ORDER COMPLETED - ASN change can be submitted 6/23: ASN change sent by Melissa - new ASN 65085. We will need to wait for the current order to complete before any changes can be made 6/5: Order rec'd
New | Dublin Ireland Upgrade | IR777-05-IM | UHG | John Sergot | EXPEDITE COVID WAR ROOM |  |  |  | CSM200519130850 |  |  |  | 2020-07-06 |  |  | DUBDUBLE549572 | [12 empty] | 7/6: Circuit ready for test and turn up. Technical info document, LOA (letter of authorization) have been sent to the customer. IP details, router config file also have been sent to the customer. Once the customer completes their cross-connect, the customer can configure their router and turn up the circuit. The port is up and operational. 7/3: AT&T SIM is escalating with the AT&T FSE (field service engineer) regarding the node wiring issue. Pending further update from the AT&T FSE. Next update is July 6 by close of business. 6/29: Reached out to the PM Matej Karovic for status - latest update from Friday indicated port was up and LOA sent but need to find out what more is left to make this ready for TTU. 6/15: Pending target completion date. 6/8: Validation in progress - early stages of order 4/27: Last update: Contract signed by AT&T - Need UHG Signatures
New | ORDER CANCELLED 200M Port/ 300M Access EaAVPN 1000 Base-SX | IL137-02-IM | UHG | Melissa Chapman | Equian | 1000 Warrenville Rd, Suite 200 | Naperville, IL |  | VS20038748 3102-0116 3102-BBRW | 2020-03-12 | 2020-03-24 | 2020-04-10 |  |  |  | BLEC.992040 | ATT MW | KRGN126339LB | 2020-03-26 | [5 empty] | 10.45.10.137 | 10.45.10.138 | 65425 | 202610 | UHG GLOBAL 150 | COVID-19 SITE DELAY - S19C 6/30: Rec'd cancellation request from Melissa. HITS ticket 1192369070 4/14: Confirmed order has been jep'd S19C (Covid19 Delay) 4/13: CNR - Customer Not Ready - Per Construction ORDER HOLD DUE TO COVID-19 CRISIS 3/30-4/6: CUSTOMER SITE NOT READY - CNR - PER CONSTRUCTION, FOREMAN REACHED OUT TO CUSTOMER BUT CUSTOMER WILL NEED TO GET APPROVAL FOR 4/7 AS INSTALL DATE 3/24: Access install scheduled for 3/26. 3/12: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | CO162-02-IM | UHG | Melissa Chapman | BriovaRX | 6547 South Racine Circle Suite 300 | Centennial, CO |  | VS20048999 3102-1433 7WS03850894 3102-BBST | 2020-04-06 | 2020-06-23 | 2020-06-23 | 2020-07-06 |  | Y | BBEC.665148 | Qwest | 29KXGS508187MS | 8/11/2020 7/2/2020 | 1ST FLOOR TELCO ROOM, REAR OF BUILDING NEAR LOADING DOCK |  |  |  | 601 | 10.1.85.17 | 10.1.85.18 | 64655 | 202610 | UHG GLOBAL 150 | 7/7: ORDER COMPLETE 7/6: Reached out to the LEC Russell Brumfield to complete testing. Access install is now complete 6/29: Order was updated last week with a 7/1 target date for access install. 4/27-6/15: LEC Qwest provided an 8/11 access install date due to "Minor Build." Melissa advised via email. 4/20: LEC Jep'd the order…..."SITE IS NOT READY HAS NOT PASSED INSPECTION IS RAW LAND" - should order be cancelled and reissued later or do we have a date Telco Room/Power will be available? 4/14: Pending an install date from the LEC Qwest. FOC due back by 5/12. 4/6: Order rec'd
New | CANCELLED 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX348-06-IM | UHG | Melissa Chapman | Wellmed | 6344 Davis Blvd | North Richland Hills, TX |  | VS20066819 3102-1563 3102-BBXL | 2020-04-23 | 2020-05-07 | 2020-08-07 |  |  |  | BBEC.667551 | SBC | 14KRGN888347SW | 2020-08-13 | [5 empty] | 10.1.82.145 | 10.1.82.146 | 65163 | 202610 | UHG GLOBAL 150 | 6/5: Submitted cancellation request per Melissa. 6/1: Need to S19C per Melissa email 5/19-5/26: Fiber work due to complete on 8/4. Access install scheduled for 8/13. 4/23: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL194-06-IM | UHG | Melissa Chapman | Wellmed | 2701 West Saint Isabel Street | Tampa, FL |  | VS20061627 3102-1541 RSSC3666406 3102-BBWR 3102-BBWS | 2020-04-27 | 2020-04-30 | 2020-07-28 | 2020-07-02 |  | Y | BBEC.634088 | Frontier-CTF | 65KRGN374315FTNC | 2020-06-30 | 1ST FLOOR, IT ROOM, RAD203, PORT# 5, FIBER MM |  |  |  | 842 | 10.1.82.137 | 10.1.82.138 | 64555 | 202610 | UHG GLOBAL 150 | 7/2: ORDER COMPLETE 6/29: R80 completion notice on access and VLAN received last week from LEC Frontier. Pending testing completion. 6/1: Need to S19C per Melissa email 5/26: Access install scheduled for 6/30 5/5-5/18: Pending an install date from the LEC Frontier 4/27: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL149-04-IM | UHG | Melissa Chapman | AxelaCare | 201 N Tarragona St | Pensacola, FL |  | VS20063081 3102-1553 7SS03666468 3102-BBWZ | 2020-04-27 | 2020-05-04 | 2020-07-21 | 2020-07-02 |  | Y | BBEC.667573 | ATT SE | 48KRGN700469SB | 2020-08-04 | 1ST FLR TELCO/SERVER RM WALL MOUNT |  |  |  | 50 | 10.1.82.129 | 10.1.82.130 | 64640 | 202610 | UHG GLOBAL 150 | 7/2: ORDER COMPLETE 6/29: Fiber work completed ahead of schedule. Pending improvement on 8/4 access install date. 5/11-6/15: Fiber work scheduled to complete on 7/24. Access install scheduled for 8/4. 5/5: Pending an install date from the LEC ATT SE 4/27: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX570-02-IM | UHG | Melissa Chapman | Wellmed | 105 S. Main Street | Cedar Hill, TX |  | VS20064167 3102-1557 7MS02404462 3102-BBXF | 2020-05-04 | 2020-05-06 | 2020-08-03 | 2020-07-01 |  | Y | BBEC.667560 | SBC | 14KRGN888321SW | 2020-07-30 | 1ST CLOSET CLOSET BY FRONT DOOR PORT 5 |  |  |  | 50 | 10.1.82.85 | 10.1.82.86 | 65375 | 202610 | UHG GLOBAL 150 | 7/2: ORDER COMPLETE 6/29: Fiber work completed last week ahead of schedule. Access install date improved to 7/8. 6/8-6/15: Fiber work on track for completion on 7/21. Access install scheduled for 7/30. 6/1: Fiber work due to complete on 7/21. Pending access install date (usually about 7-10 days after fiber completes.) 5/18-5/26: Site visit completed last week. Pending fiber and access install dates. 5/12: Pending an install date from the LEC. 5/4: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL083-02-IM | UHG | Melissa Chapman | Wellmed | 260 Wekiva Springs Road, Suite 1000 | Longwood, FL |  | VS20056473 3102-0900 3102-BBTK 3102-BBTL | 2020-04-15 | 2020-04-21 | 2020-07-08 | 2020-07-07 |  | Y | BBEC.671675 | Embarq | 25KXGS512718UFLG | 2020-06-11 | 1ST FLOOR, MAIN TELCO ROOM, WALL MOUNT |  |  |  | 2 | 10.1.84.181 | 10.1.84.182 | 65182 | 202610 | UHG GLOBAL 150 | 7/8: ORDER COMPLETE 6/29-7/6: VLAN completed - pending testing completion and OK to turn up. Due 7/8. 6/8-6/15: Access install completed ahead of schedule. VLAN PON HSSV4466648 due to complete on 6/16. 5/11-6/1: Access install scheduled for 6/11. 4/27-5/4: Pending an install date from the LEC Embarq 4/15: Order rec'd - Please use CL/Embarq
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX 1000 Base-LX | TX259-06-IM | UHG | Melissa Chapman | Wellmed | 113 Star Grass | Spring Branch, TX |  | VS20070972 3102-1569 3102-BBXS | 2020-04-22 | 2020-05-07 | 2020-07-29 | 2020-07-09 |  | Y | BBEC.687666 | GVCS | 31KRBJ935067GVC | 2020-06-18 | 1ST FLR IT ROOM, BCK WALL FIBER MEET BOX, LABLED, ACEDIAN PORT 4 |  |  |  | 150 | 10.45.11.125 | 10.45.11.126 | 65095 | 202610 | UHG GLOBAL 150 | 7/13: ORDER COMPLETE 6/29: LEC sent access completion notice on Friday 6/26. Pending testing completion and the Ok to turn up. 6/2: Access install scheduled for 6/18. Does this need to be put on Covid19 hold?? 5/7: Per Chris email to Phalguni (OM): Per our Q session, please cancel this order for Spring Branch, TX. This is the order with Ethernet access through GVCS requesting 1000 Based SX/MMF that GVCS can’t support. 4/22: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX263-08-IM | UHG | Melissa Chapman | Wellmed | 8107 Springdale Road # 110 | Austin, TX |  | VS20059551 3102-1478 7MS02402994 3102-BBVV | 2020-04-22 | 2020-04-27 | 2020-07-23 | 2020-06-29 |  | Y | BBEC.687742 | SBC | 32KRGN654312SW | 2020-07-07 | 1ST OUTSIDE BA BACK OF NORTH SIDE |  |  |  | 50 | 10.45.10.97 | 10.45.10.98 | 65218 | 202610 | UHG GLOBAL 150 | 7/13: ORDER COMPLETE 6/29: Access install is showing scheduled for 6/30. 6/1: Need to S19C per Melissa email 5/18-5/26: Fiber work scheduled to complete on 6/25. Access install scheduled for 7/7. 4/28-5/11: Pending install date from the LEC 4/22: Order rec'd
New | Cancelled 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX481-05-IM | UHG | Melissa Chapman | Wellmed | 4323 N. Josey Lane Suite 204 | Carolton, TX |  | VS20060025 3102-1483 HMSC2403362 3102-BBVZ 3102-BBWB | 2020-04-21 | 2020-04-28 | 2020-07-24 |  |  |  | BBEC.665016 | Frontier-CTF | 13KFGS370645FTNC | 2020-07-24 | [5 empty] | 10.1.83.57 | 10.1.83.58 | 64695 | 202610 | UHG GLOBAL 150 | 7/21: Per TOMAS PALENCAR: I am assigned to cancel the order mentioned in the subject per UTH/CTH/HITS ticket 1208152306. Per notes: *Customer is moving to a new location* Can you please confirm? I need a written approval attached in OMX in order to process the cancellation. 7/13: Access install has been rescheduled for 7/24. 6/1: Need to S19C per Melissa email 5/11-5/26: Access install scheduled for 6/22. This is NOT COVID19 Delayed 5/5: Pending an install date from the LEC Frontier 4/21: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX347-06-IM | UHG | Melissa Chapman | Wellmed | 1317 E Jasmine Ave | McAllen, TX |  | VS20060717 3102-1512 7WS03855636 3102-BBWK | 2020-04-23 | 2020-04-29 | 2020-07-27 | 2020-07-17 |  |  | BBEC.665005 | SBC | 38KRGN614049SW | 2020-08-12 | 1ST FLR SERVR CLST TELCO BB CIENA PORT 2 TAGGED. |  |  |  | 50 | 10.1.82.149 | 10.1.82.150 | 65219 | 202610 | UHG GLOBAL 150 | 7/20: ORDER COMPLETE 7/13: UPDATE FROM LEC: WAITING ON CONSTRUCTION TO PLACE CONDUIT FROM OUTDOOR FOT TO CUSTOMER IT ROOM TO SATISFY ACCEPTED EF OFFER. 6/29: Access is scheduled for 8/12. 6/1: Need to S19C per Melissa email 5/18-5/26: Fiber work scheduled to complete on 8/3. Access install scheduled for 8/12. 5/11: Site visit completed on 5/4. Pending info from field on fiber work target completion date. - HALO TICKET: Please change the LCON to Cassandra Pinon, 956-240-0469, cpinon@homecaredimensions.com. Once the USO has been changed, please sup the PON to the LEC for a new date. 5/4: Site visit scheduled for today 4/23: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL141-05-IM | UHG | Melissa Chapman | Wellmed | 13751 Metropolis Ave | Fort Myers, FL |  | VS20061626 3102-1543 7SS03665877 3102-BBWP 3102-BBWQ | 2020-04-27 | 2020-04-30 | 2020-07-17 | 2020-07-17 |  |  | BBEC.667588 | Embarq | 25KXGS520056UFLG | 2020-07-13 | FIRST FLOOR SERVER ROOM CPE RACK MOUNT |  |  |  | 100 | 10.1.82.133 | 10.1.82.134 | 65075 | 202610 | UHG GLOBAL 150 | 7/20: ORDER COMPLETE 7/13: CNR 7/6: Access install updated to 7/9. 6/29: Access install scheduled for 7/13. 6/1: Need to S19C per Melissa email 5/5-5/26: Pending an install date from the LEC Embarq 4/27: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | LA043-01-IM | UHG | Melissa Chapman | People's Health | 1520 Gause Boulevard | Slidell, LA |  | VS20078872 3102-1752 7SS03673214 3102-BBYR | 2020-05-27 |  | 2020-08-24 | 2020-07-20 |  | Y | BBEC.667344 | ATT SE | L2KRGN822614SC | 2020-08-17 | 1,TELCO ROOM,1ST FLOOR WALL MNTED, |  |  |  | 50 | 10.1.82.165 | 10.1.82.166 | 65382 | 202610 | UHG GLOBAL 150 | 7/20: Fiber work completed last week ahead of schedule. Access install complete - READY FOR TURN UP 7/6-7/13: Customer prem showing ready as of 6/30. Fiber work still on schedule for 8/6. 6/15-6/29: Construction fiber work scheduled to complete 8/6. Access install scheduled for 8/17. 6/8: Site visit scheduled for 6/11. Pending an install date from AT&T SE. 5/27: Pending USO's
New | 500M Port/ 1G Access EaAVPN 1000 Base-SX | UAL11-02-IM | UHG | Melissa Chapman | People's Health | 650 Clinic Drive | Mobile, AL |  | VS20085291 3102-0990 3102-BBZF | 2020-06-16 | 2020-07-14 | 2020-07-14 | 2020-07-17 |  | Y | IZEC.699588 | AT&T SOUTHEAST NEARNET-15 | A2KRGN466877SC | 2020-07-14 | 2ND FLR TELCO RM, RACK MT D CN3960, 1 |  |  |  | 50 | 10.1.95.69 | 10.1.95.70 | 65362 | 202610 | UHG GLOBAL 150 | 7/20: ORDER COMPLETE 6/30-7/13: Access install scheduled for 7/14. 6/16: Order rec'd
| HOT ORDER - MACD Please change handoff on BBEC.576514 1000base LX, SMF LC | C1648 | UHG | Melissa Chapman | NICE DATA CENTER | 900 N Alameda | Los Angeles, CA |  | VS20087252 3094-2017 GWS03867570 |  |  |  | 2020-07-28 |  |  | BBEC.576514 | ATT West | 13KRGN601495PT | 2020-07-24 | [10 empty] | 7/28: Pending OK to schedule -- SERVICE IMPACTING HOTCUT/CHANGE HANDOFF FROM SX TO LX - ORDER COMPLETE 7/27: LEC working to correct a design issue - PER LEC: **STS** PORT 20 SHOWS AN SX SFP. CANOPI SHOWS THAT IT SHOULD BE AN LX TYPE SFP. WORDDOC IS CURRENTLY SHOWING THE SX TYPE. CHANGE FROM SX TYPE TO LX TYPE SFP. 7/20: LEC expected onsite this week (7/24.) 7/14: Issued DDF ticket Order Number: 202007140026 to remove R15 on PON and address any design issues holding up order. Also requested they check on engineering which is still future due. Overall due date remains at 8/17. 7/7: Added to sheet
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX566-02-IM | UHG | Melissa Chapman | Wellmed | 4682 McDermott Rd STE 100 | Plano, TX |  | VS20042344 3102-0344 7MS02397834 3102-BBRY | 2020-03-19 | 2020-06-18 | 2020-06-18 | 2020-07-28 |  | Y | BBEC.516761 | SBC | 14KRGN888039SW | 2020-07-27 | 1ST FLR SPRINKLER RM ,POS 5 TGGD |  |  |  | 50 | 10.1.85.133 | 10.1.85.134 | 65395 | 202610 | UHG GLOBAL 150 | 7/27: Fiber work completed last week ahead of schedule - access install rescheduled for TODAY 7/27. 6/8-7/20: Fiber work set to complete on 8/10. Access install scheduled for 8/19. 6/1: PON sent 5/26. FOC due back by 6/17. 5/26: Melissa emailed - Marco Wong advised site is ready - PON supp'd via ServiceNow for new date. PON resent to LEC today. Covid19 delay removed on sheet. 4/14: Confirmed order has been jep'd S19C (Covid19 Delay) 3/31: Access PON showing COVID 19 DELAY CONTACT CARRIER MANAGEMENT FOR ADDITIONAL INFORMATION. Per the Construction Engineer, "Marco Wong notified me that they cannot go onsite until April 27th due to COVID-19. I will contact him on that date to get service set up." 3/19: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | UOK07-07-IM | UHG | Melissa Chapman | UHG-RX solutions | 755 Research Parkway | Oklahoma City, OK |  | VS20045449 3102-1410 3102-BBSH | 2020-03-25 | 2020-04-07 | 2020-04-21 | 2020-07-21 |  | Y | IUEC.905398 | ATT SW ONNET-5 | 97KRGN895959SW | 2020-07-21 | BASEMENT TELCO RM WALLMOUNT POS 1&2 OF TT PANEL |  |  |  | 50 | 10.1.85.165 | 10.1.85.166 | 64892 | 202610 | UHG GLOBAL 150 | 7/21: ORDER COMPLETE 7/20: Access install scheduled for 7/21. 7/14: This was removed from Covid hold - advised Joe Scrudato (AT&T) to push for PON release COVID-19 SITE DELAY - S19C. 4/7: Per Lynn McClure (Optum) - We will need to delay the installation until after May 2020 due to COVID-19 building restrictions. Please feel free to reach out to us by May 15th and hopefully we will be able to give you a date closer to the end of May to schedule installation. 4/6: Access install scheduled for 4/8. 3/25: Order rec'd
New | 400M Port/ 1G Access EaAVPN 1000 Base-LX | CT039-13-IM | UHG | Melissa Chapman | United HealthGroup | 185 Asylum St | Hartford, CT |  | VS20049471 3102-1434 3102-BBSV | 2020-04-01 | 2020-07-06 | 2020-07-06 | 2020-07-23 |  | Y | IZEC.672101 | ASE LNS | CTKRGN100246TPM | 2020-07-27 | T1 TELCO ROOM AT&T CAB 000001.02, VE EL PORTS 1&2 |  |  |  | 50 | 10.1.87.21 | 10.1.87.22 | 65153 | 202610 | UHG GLOBAL 150 | 7/23: ORDER COMPLETE 7/20: Access install has been scheduled for 7/27. Working to firm up as I'm still showing NTE install is 8/4. 7/14: On the call today I mentioned the ROE issue had been resolved and that I was going to check with Construction on next steps. As it stands, Construction is advising that the fiber work is complete as of yesterday 7/13. They have scheduled NTE (Ciena 3930) installation for 8/4 and, from what I’m reading, it will be placed in the T1 closet in the parking garage. From there, because Building Management will not allow AT&T LNS to build riser cables, it will be the customer responsibly to build to this location. From previous updates, I believe this will work out fine for the end user as it’s my understanding that they already have privately owned fiber running from our cabinet in the T1 Closet “Common Space” directly to their space. 7/13: Reached out to Amanda Stewart ATT for status of ROE, etc. 7/6: UPDATE: LCON Keith advised "This is solved." 7/1: Per Amanda Stewart AT&T, "Executables are being prepared by AT&T Contract Management. This has been in the works so long that questions regarding policies we agreed to set aside a year ago came up as the final was being circulated for approval, i.e. termination rights. We should have a final to you in the next day or two." 6/29: Construction showing a ROE due date of 7/10. Reached out to Keith Mangene (LCON) to see if he's aware of the ROE. 6/8-6/15: Construction advised this is a ROE issue - LOA is still being reviewed by the tenant. ECD 6/19. 6/2: Reached out to Becky Duncan (PM) to find out latest. 5/26-6/1: Pending update from the field on next steps - working to get update 5/18: Engineer was able to work something out with LCON Keith. Engineer advised that the final testing in the field was set for this past Friday (pending an update) with additional updates due today. 5/11: Requested Becky Duncan (NSS PM) provide update - need to know if Engineer reached out to the site contact Keith to go over the riser issues. 5/4: Notified NSS PM of following: I just spoke with the end user Keith Mangene at the site and it sounds like this is WAY more simple than getting a ROE and negotiating with the building owner. Whoever is assigned as the OSP Engineer needs to call Keith directly as it sounds like Keith has his own private riser in the building with enough fiber to light up his half of the state. After talking with Keith I honestly don’t think Construction will need to do any work and this will just end up being shifted off to the Access Techs to complete their portion as it sounds like fiber work is a non-issue per Keith. 5/4: OSP spoke with the LCON on this order and he stated that they already have privately owned fiber run from our cabinet in the T1 Closet “Common Space” directly to their space. OSP to confirm w/SA if we give him the LOA to sign so we can put a 3930 in AT&T’s existing cabinet and get them service instead of waiting for ROE. This has now bounced back to SA trying to work out an agreement with the building in terms of an LOA vs ROE which will alter where/what equipment is placed. 4/14-4/27: PON released on 4/9 to LNS. Pending dates. FOC due back by 5/4. 4/1: Order rec'd - Per Melissa….Can we change the handoff on this to SMF- 1000base SX/LC ????????
New | 200M Port/ 500M Access EaAVPN 1000 Base-SX | AZ008-19-IM | UHG | Melissa Chapman | United Healthcare | 4425 East Cotton Center Blvd | Phoenix, AZ |  | VS20052563 3102-0134 7WS03852286 3102-BBSX 3102-BBSW | 2020-04-08 | 2020-07-10 | 2020-07-10 | 2020-07-23 |  | Y | BMEC.927838 | Cox Communications | 23KFGX991846COXC | 8/14/2020 7/24/2020 | 1ST FLR, RM MDF, PORT 3, MMF |  |  |  | 106 | 10.1.85.13 | 10.1.85.14 | 65132 | 202610 | UHG GLOBAL 150 | 7/24: ORDER COMPLETE 7/20: Access install is showing R84 complete - pending demarc info and testing completion. 6/29-7/13: Access install date has been updated to 7/24. 5/26-6/15: Access install scheduled for 8/14. LEC ID 23KFGX991846COXC 5/4-5/18: Pending an install date from the LEC Cox, FOC due back by 6/1 4/21: Pending an install date from the LEC Cox. R15 needs to be addressed. (AERO ID 981389) - UPDATE: Jeps cleared and PON supp'd today. Pending install date. (UPDATE: R15 removed) 4/8: Order rec'd
New | CANCELLED 20M Port/ 50M Access EaAVPN 1000 Base-SX | TX356-07-IM | UHG | Melissa Chapman | Wellmed | 200 West Kearney Street | Mesquite, TX |  | VS20059549 3102-1477 3102-BBVT | 2020-04-22 | 2020-04-27 | 2020-07-23 | 2020-07-23 |  |  | BBEC.674827 | SBC | 14KRGN888264SW | 2020-07-10 | [5 empty] | 10.1.82.253 | 10.1.82.254 | 64617 | 202610 | UHG GLOBAL 150 | 7/23: Cancellation confirmed complete. 6/29: Disco order 3094-0971 in process. Due 7/21 THIS WILL REQUIRE A DISCONNECT 6/2: Received cancellation notice from Melissa via email. HITS ticket issued to cancel. 5/11-6/1: Fiber work scheduled to complete on 6/30. Access install scheduled for 7/10. 4/28-5/4: Pending install date from the LEC 4/22: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-LX | TX529-02-IM | UHG | Melissa Chapman | US HealthGroup | 2563 SW Grapevine Pkwy | Grapevine, TX |  | VS20081405 3102-1764 3102-BBYV 3102-BBYT | 2020-06-08 |  | 2020-09-09 | 2020-07-24 |  | Y | IUEC.961426 | Frontier-CTF | 13KRGN403250FTNC | 2020-07-24 | FL 1 RM MDF RAD203 PORT 5 |  |  |  | 905 | 10.1.82.65 | 10.1.82.66 | 65371 | 202610 | UHG GLOBAL 150 | 7/27: ORDER COMPLETE 6/29-7/20: Access install scheduled for 7/24. 6/19: Received LCON phone number from customer. Issued HITS ticket to change LCON to change the LCON to Tony Turner, tony_turner@optum.com, 205-276-3588. Once LCON change is completed on the USO a supp will be sent on the PON. 6/15: Pending release of the PON to Frontier. Received LCON change which will require a USO supp and resending of the PON. Order will be delayed. 6/8: Order rec'd
New | CANCELLED 30M Port/ 50M Access EaAVPN 1000 Base-SX | NC068-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 10 Herman Ave | Asheville, NC |  | VS20089403 3102-1109 3102-BBZN | 2020-06-26 | 2020-06-30 | 2020-09-16 |  |  |  | BBEC.671177 | ATT SE | 20KRGN400806SB | 2020-08-04 | [5 empty] | 10.45.10.69 | 10.45.10.70 | 65427 | 202610 | UHG GLOBAL 150 | 7/20: Sent OM email from Melissa cancelling order. Pending update from OM. 7/13: Melissa issued cancellation request. Issued HITS Request ID: 1201662486 7/7-7/13: ATT SE access install scheduled for 8/4. 6/26: Order rec'd
New | CANCELLED 10M Port/ 50M Access EaAVPN 1000 Base-SX | MO048-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 601 W Nifong Blvd Bldg 6C, Suite 11 | Columbia, MO |  | VS20090012 3102-1195 3102-BBZR 3102-BBZS | 2020-06-29 | [5 empty] | BBEC.687284 | [8 empty] | 10.1.82.9 | 10.1.82.10 | 65358 | 202610 | UHG GLOBAL 150 | 7/20: ISSUED AS DISCONNECT ORDER, W3774010 7/13: Melissa issued cancellation request. Issued HITS Request ID: 1201714750 7/13: HITS Request ID: 1195503445 - As the USO got rejected. Hence, the FFLOW # 13654960 has been raised to resolve this issue. Please expect my next follow-up by ''07-14-2020''. Thank you. 7/7: USO not loaded in SOTS - issued HITS ticket to have this fixed. 6/29: Order rec'd
New | 200M Port/ 250M Access EaAVPN 1000 Base-SX | CA447-01-IM | UHG | Melissa Chapman | Monarch | 5581 Alton Parkway MDF Room: Inside the suite | Irvine, CA |  | VS20092073 3102-1242 3102-BBZZ | 2020-06-30 | 2020-07-02 | 2020-10-01 | 2020-07-21 |  | Y | BREC.927754 | ATT West | 13KRGN603271PT | 2020-07-21 | W MPOE HANDOFF TO VIRTUAL EDGE 3 4 |  |  |  | 50 | 172.27.27.233 | 172.27.27.234 | 64732 | 488101 | MONARCH | 7/22: ORDER COMPLETE 7/14-7/20: Access install scheduled for 7/21. 6/30: Order rec'd
New | 30M Port/ 100M Access EaAVPN 1000 Base-SX | CA453-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 1819 Aston Avenue Suite 104 | Carlsbad, CA |  | VS20091844 3102-1574 3102-BCBF | 2020-07-01 | 2020-07-27 | 2020-07-27 | 2020-07-27 |  | Y | IUEC.924355 | SBC NEARNET-15 | 19KRGN534013PT | 2020-07-27 | 1ST FLR TELCO DMARC PNL 1 SC JKS PRT CKTID TGGD |  |  |  | 50 | 10.1.81.233 | 10.1.81.234 | 65350 | 202610 | UHG GLOBAL 150 | 7/28: ORDER COMPLETE 7/13-7/27: Access install scheduled for 7/27. 7/7: Pending an install date from the LEC 7/1: Order rec'd
New | HOT ORDER 5M Port/ 10M Access EaAVPN 1000 Base-SX | TX563-01-IM | UHG | Melissa Chapman | UHG | 10613 Bellaire Blvd, Bldg A, Suite 250 | Houston, TX |  | VS20057403 3102-1437 7MS02402377 3102-BBVD | 2020-04-21 | 2020-04-29 | 2020-04-29 | 2020-07-30 |  | Y | MLEC.948059 | ATT SW | 28KRGN749918SW | 2020-07-30 | 1ST MPOE OPTICAL JACK |  |  |  | 50 | 10.1.82.117 | 10.1.82.118 | 64648 | 202610 | UHG GLOBAL 150 | 8/10: ORDER COMPLETED (7/30) 7/24-7/27: Access install scheduled for 7/30. Customer confirmed as well. 7/21: Tim Patton (Optum) advised he has no concerns, Kidist was in the electrical room. The key is in a lock box near the elevator. Dean Moen (Optum) advised that they access for the AT&T tech to complete the order, Kidist has met with the local site contact who has access to the areas needed to complete the circuit. I had the CNR/COVID related jeps on the order removed this morning and DDF ticket 202007210044 was created for dispatch. 7/20: Previous LCON Kidist not aware of issues but reached out to Dean Moen (Optum) and Tim Patton (Optum) for status. I sent a follow up this morning to Dean and Tim for an update. 7/14: Reached out to the LCON Kidist to see if he had any news about a possible Covid19 delay at the prem. 7/13: CARRIER MGMT TIER II ENGAGED -- ACCESS AERO 1043776: SERVICE CANNOT BE DELIVERED AT THIS TIME BECAUSE THE AREA IS IMPACTED BY COVID19 VIRUS AND THE CUSTOMER COULD NOT PROVIDE ACCESS. MY NEXT - F/U 8/13/2020 ---- UPDATE: PER MELISSA, requested we change LCON to LOAN SWEET, 713-232-3205, lsweet4@uhc.com. HITS ticket issued. 7/2: Email to Melissa: Regarding your order TX563 in Houston where we advised the tech to use the lockbox to enter the facility to install this circuit, I received an update just now from the tech who visited the site. Please let me know your thoughts on what he provided: “The Ciena where the circuit drops from is an outdoor 3911 placed at the back wall of the building. We need to run fiber IW from there into the MPOE room in the first floor. To do that , we would have to cross an adjacent tenant space A120 ( Vu Chiropractic ). However, the business owner , Dr. Vu will not allow us do any work in their space. They want to limit activities in their space to business only due to covid-19. The end user needs to get property management involved. They may have to provide conduit and pull-string for us from the MPOE room to the back wall if we are not allowed to do work in adjacent space, ste A120.” Let me know your thoughts on getting property management involved on this. I’m sure they’ll want to have input as to whether we traverse the other tenant’s space or run separate conduit to avoid it. 6/26: Showing access order is still open. Reached out to Jerome Adams (Mgr) and Anthony Baca (Tech) for status. 6/19: Reached out again today to Jerome Adams (Mgr) and Anthony Baca (Tech) about accessing the MPOE using the lock box info provided by UHG. Requested status. 6/18: I reached out to JEROME ADAMS who is the MANAGER BUSINESS FIELD SERVICES down in the Houston area and he is working with his team to load the order to Tech Anthony Baca (or available tech) as soon as possible. As soon as I see a redispatch date, I’ll let you know. 6/15: Per the LEC technician ANTHONY J BACA, "JUST SPOKE WITH LISTED LCON KIDIST ATNAFU 832-500-6638 AND CONFIRMED BUSINESS IS STILL CLOSED DUE TO COVID-19" 6/8: Access install rescheduled for 6/11. 6/1: The 5/26 date was missed - per the LEC update, CALLED LCON KIDIST ATNAFU 8325006638, SAYS NO ONE ON SITE - STILL WORKING OUT A PLAN TO RETURN TO WORK DUE TO COVID-19. 5/19: New install date, 5/26. Emailed Melissa this morning to confirm. Added to HOT list. 5/4: PER CONSTRUCTION: THE ORDER IS ON HOLD DUE TO COVID 19 ISSUE. I have advise them the site is ready and to move forward. 5/1: Per Melissa, "I am not sure why ATT thinks they can’t access this site because of covid, but per the below the site is open." Patton, Timothy <timothy_patton@uhg.com advised the site is open. 4/27: Access install scheduled for 4/29. 4/21: Order rec'd
| 200M Port/300M Access EaAVPN 1000Base-SX | MA093-02-IM | UHG | Melissa Chapman | Equian | 500 Unicorn Park, 2nd Floor | Woburn, MA |  | VS19174415 3102-1201 GNSC1972097 3102-BBNC 3102-BBND | 2019-10-22 | 2020-01-28 | 2020-01-28 | 2020-08-10 |  | Y | BDEC.995921 | Comcast | 20KGGS031817CBCL | 2020-04-07 | 2ND IDF ROOM, RACK MOUNTED , UR 42, PORT 1 |  |  |  | 222 | 10.45.10.149 | 10.45.10.150 | 65446 | 202610 | UHG GLOBAL 150 | 8/11: ORDER COMPLETE 8/10: We received R84 completion notification from the LEC Comcast. Working to complete next milestones and push for TTU. Reached out to Cedrick Scott. 7/28: UPDATE: Per Kevin Joslyn, PMP ¦ Optum, "Just received a meeting invite that Comcast will be on-site on 8/4 10AM ET for the install. I’ll coordinate Comnet at the same time." 7/27: AERO CM ticket 1133984 - requested Carrier Management engage. CM UPDATE: ESC'D BCK TO COMCAST EXEC MGMT TEAM REQ'NG STATUS OF ORD. LEC INVESTIGATING W/INTERNAL TEAMS FOR DELAY ISSUE & POSS. ETR. MORE DETAILS ARE ANTICIPATED ON 8/4 COB, BUT URGENTLY DRIVING FOR MORE INFO TO BE PROVIDED SOONER (NO GUARANTEES). 7/6-7/20: PON resent requesting 7/23 install date. Pending confirmation from LEC Comcast. 6/29: Reached out to Rhonda Miles (Assembler) and Rose Crawford (AM) for support in cleairing R15 and getting PON resent to Comcast. UPDATE: PON RESENT 6/15: CNR chat group removed all CNR coding. Issued DDF ticket to have R15 cleared. Will then issue PON supp. 6/8: Pending completion of LCON change on USO and PON supp. 5/29: Issued IOS ticket to change LCON per Melissa. Once changed, PON will be resent to the LEC 5/26: CNR - will require a PON supp when ready. 5/18: Issued AERO ticket 1010374 to clear R15 issues on PON. Need confirmation site is ready. 4/27-5/4: Need to find out if this site is delaying access due to Covid19. If so we'll need to jep the order S19C 4/6-4/20: Access install will be delayed - Per LEC "LCON STATES NO ACCESS WILL BE GRANTED UNTIL AFTER 4/3. WILL RE FOC ONCE SITE IS READY TO PROCEED." Please advise when site will be ready. 3/3-4/6: Access install scheduled for 4/7 3/2: Pending FOC. Due back by 3/17. 2/19: Sent completed COI back to Melissa. Pending FOC 2/18: Received completed COI back from Melissa. Sent to team for processing. 2/17: Pending date on supp'd PON. COI FORM? 2/11: Issued PON supp request - COI form back yet? 2/3: CNR CUSTOMER NOT READY: PER COMCAST REP GWEN CPM DVISED UNABLE TO REACH LCON TO SCHEDULE SITE SURVEY...NOTIFIED NCON... COI FORM 1/27: Escalating for FOC from LEC - Ticket is open to have Design fix R15. 1/6-1/20: PON resent on 1/3. FOC due back by 2/6. 12/30: LEVEL1 Escalation on AERO Design 818200 to get PON sent back out. 12/12-12/16: Issued AERO DESIGN ticket 818200 to have the PON sent back out as LEC Comcast advised we/they are OK to move forward with the 300M service per the original request. 12/3: This PON will need to be supp'd and resent once Chris confirms the bandwidth issue is resolved. 11/25: Sent email to Chris Cowan - LEC COMCAST rejected the order due to access bandwidth issue. - UPDATE PER CHRIS: "I covered this with Comcast last week. They are getting their rates added in support of the requested 300M for this location. They told me that they should have this resolved just after Thanksgiving. I have the OM holding off on rejecting the current order." 11/18: Level 1 escalation ticket issued on AERO 789017 for missed release of PON to the LEC. 11/11: AERO 789017 for missed FOD - pending release of PON to the LEC. 11/4: Pending release of the PON to the LEC Comcast 10/22: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | LA017-01-IM | UHG | Melissa Chapman | People's Health | 501 Rue de Sante | LaPlace, LA |  | VS20077058 3102-1142 7SS03672433 3102-BBYG | 2020-05-20 |  | 2020-08-19 | 2020-08-04 |  | Y | BBEC.667363 | ATT SE | L2KRGN822629SC | 2020-07-22 | 1ST FLR TLCO CLST WALL MNT 3903 SLOT 2 |  |  |  | 50 | 10.1.82.177 | 10.1.82.178 | 65383 | 202610 | UHG GLOBAL 150 | 8/10: ORDER COMPLETE 7/27: UPDATE: Melissa provided new LCON info - Rick Tittle, Rick.Tittle@peopleshealth.com, Work: 504-681-8928 or Cell: 504-339-4000. USO will need to be changed.......PON will need to be resent once USO change is complete. 7/27: Order showing CNR Customer Not Ready - Per LEC Tech: ANSWER LEFT MESSAGE. NO RETURN CALL. NO STE NUMBER ON TKT. JEP ORDER TO CUST NO ACCESS - reached out to Melissa. 7/20: Fiber work complete. Access install moved up to 7/22. 7/6-7/13: Site visit completed on 6/30 - fiber work due to complete on 7/20. Access install scheduled for 7/29. 6/29: Per BIC Engineer (ED) Messages left for LCONs. no response. Still pending site survey 6/8-6/15: Pending a site survey and install date from ATT SE. 5/20: Pending USO's
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | LA044-01-IM | UHG | Melissa Chapman | People's Health | 42078 Veterans Ave | Hammond, LA |  | VS20084556 3102-0359 3102-BBZB | 2020-06-12 | 2020-06-19 | 2020-09-04 | 2020-07-28 |  | Y | BBEC.687377 | ATT SE | L2KRGN822626SC | 2020-07-06 | 1ST FLR,TELCO CLST,WALL MNT 3903 PORT |  |  |  | 50 | 10.1.82.197 | 10.1.82.198 | 65388 | 202610 | UHG GLOBAL 150 | 8/10: ORDER COMPLETE 7/20-7/27: Fiber work completed ahead of schedule - pending new date for access install. 7/13: Order delayed - fiber work showing due to complete on 7/22. 7/7: Access showing missed: Message Type: AT&T NOT READY - JS7027 TECH EC-C57 CIRCUIT ASSIGNED OUT OF CIENA IN SUITE E1, NEED ASSIGNED OUT OF SUITE E2. NEED A CONDUIT PLACED IN SUITE E2 BETWEEN SERVER CLOSET 7/6 4:19pm Notes from LEC Tech: "NO CIENA LOCATED IN SUITE E2. LOST ACCESS TO SUITE. NO CIENA IN SUITE E2 AND UNABLE TO PLACE SERVICE OUT OF 3903 CIENA IN SUITE E1. LOST ACCESS TO SUITE, CUSTOMER IS NO LONGER ON SITE." The LEC did also mention last Thursday 7/2 that they were onsite and had no access to the People's Health server room so it was rescheduled for yesterday Monday 7/6. 6/30-7/6: Access install scheduled for 7/6. 6/12: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-LX | TX569-02-IM | UHG | Melissa Chapman | Wellmed | 7461 Airport Freeway | Richland Hills, TX |  | VS20081475 3102-1765 7MS02410719 3102-BBYW | 2020-06-10 |  | 2020-09-09 | 2020-07-29 |  | Y | BBEC.633801 | SBC | 14KRGN888505SW | 2020-07-29 | 1 DATA RM TELCO WALL |  |  |  | 50 | 10.1.82.41 | 10.1.82.42 | 65368 | 202610 | UHG GLOBAL 150 | 8/10: ORDER COMPLETE 7/27: Access install scheduled for 7/29. 7/13-7/20: CNR DELAY - CM T2 ACCESS AERO 1102835- ORDER ON HOLD DUE TO CUSTOMER'S SITE IS NOT READY. TELCO ROOM IS NOT READY. DUE DATE NEED S TO BE SUPPLEMENTED. ENGAGING CUSTOMER NOT READY TEAM. 7/6: Fiber work completed on 7/1. Access install date improved to 7/7. 6/29: Fiber work due to complete on 8/10. Access install scheduled for 8/19. 6/15: Site visit scheduled for 6/17. 6/10: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | NY510-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 2805 Veterans Memorial Highway | New York (Ronkonkoma), NY |  | VS20090020 3102-1207 3102-BBZV 3102-BBZT | 2020-06-26 | 2020-07-01 | 2020-09-17 | 2020-08-03 |  | Y | IUEC.641236 | Cablevision Lightpath | 01LUXS254100CLVI | 2020-08-28 | 1ST FLOOR TELCO, GAS METER ROOM VIRTUAL EDGE JACK#1 |  |  |  | 2 | 10.45.10.69 | 10.45.10.70 | 65016 | 202610 | UHG GLOBAL 150 | 8/10: ORDER COMPLETE 7/20-7/27: Access install scheduled for 8/28. 7/7-7/13: Pending access install date from the LEC Cablevision Lightpath. 6/26: Order rec'd
New | 30M Port/ 100M Access EaAVPN 1000 Base-SX | CT187-01-IM | UHG | Melissa Chapman | Optum/Diplomat | 100 Corporate Dr Suite 111 | Windsor, CT |  | VS20090706 3102-1248 3102-BCBB | 2020-07-01 | 2020-07-02 | 2020-09-29 | 2020-08-03 |  | Y | IUEC.512783 | ASE LNS | CTKRGN100357TPM | 2020-08-04 | WNDSCT040CW 010001.012 01-05 TAGGED |  |  |  | 50 | 10.1.81.241 | 10.1.81.242 | 65352 | 202610 | UHG GLOBAL 150 | 8/10: ORDER COMPLETE 7/27: Access install scheduled for 8/4. 7/20: PM Becky Duncan engaged - Sent inquiry to OSP to confirm if site visit completed as scheduled on 7/15 7/7-7/13: Pending an install date from the LEC ASE LNS. 7/1: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX551-02-IM | UHG | Melissa Chapman | Wellmed | 1387 George Dieter, Bldg B | El Paso, TX |  | VS20063687 3102-1556 7MS02404294 3102-BBXD | 2020-04-30 | 2020-05-05 | 2020-07-22 | 2020-08-13 |  | Y | BBEC.671573 | ATT SW | 30KRGN615471SW | 2020-08-13 | 1ST FLR,DATA RM, BCKBRD, WALL MOUNT PATCH PANEL, POS 1 |  |  |  | 50 | 10.45.10.93 | 10.45.10.94 | 65376 | 202610 | UHG GLOBAL 150 | 8/17: ORDER COMPLETE 8/10: Access install re-scheduled for 8/13. 7/27: LEC UPDATE: Message Type: CUSTOMER SITE NOT READY - 7/27/2020 NO POWER, NEW CONSTRUCTION 7/20-7/27: Fiber work completed ahead of schedule end of last week. Access install has been bumped up to 7/27. 6/15-7/13: No change in status - fiber still showing on track for 9/30. 6/1-6/8: Still showing 9/30 fiber date. Reached out to BIC Engineer Tim Dunham directly for details. 5/26: Sent another request for fiber details. Consruction still targeting 9/30. 5/12-5/18: Site visit completed 5/7. Construction is targeting 9/30 for completion of the fiber work. Access install scheduled for 10/9/2020. Pending fiber work details. 4/29: Order rec'd
New | 200M Port/ 300M Access EaAVPN 1000 Base-SX | NY725-04-IM | UHG | Melissa Chapman | OptumHealthcare- CyrusOne Data Center | 155 Myers Corners Road | Wappingers Falls, NY |  | VS20078351 3102-1629 3102-BBYM 3102-BBYN | 2020-05-29 | ASAP | 2020-08-21 | 2020-08-18 |  | Y | BDEC.997292 | CABLEVISION LIGHTPATH | 08LUXS256183CLVI | 2020-08-07 | F1 MDF RM RR 103.00 VIRTUAL EDGE PP#4 P8 |  |  |  | 2 | 10.1.82.69 | 10.1.82.70 | 64573 | 202610 | UHG GLOBAL 150 | 8/18: ORDER COMPLETED this morning. 8/17: LEC confirmed completion - demarc F1 MDF RM RR 103.00 VIRTUAL EDGE PP#4 P8. Pending R80 completion on the PON and completion of the testing to make ready for turn up plug and play. 8/10: Pending update - no completion back from LEC. Will need to escalate COB Tues 8/11. 7/20-7/27:Cablevision/Lightpath access install scheduled for 8/7. 7/13: Carrier Management Tier I engaged and pushing on the missed FOC - AERO CM ticket 1102789. 6/29-7/6: PON released on 6/16 - FOC due back by 7/8. 6/15: AERO design ticket 1046613 to have Pon released. 6/8: Pending release of the PON to the LEC CABLEVISION LIGHTPATH 5/29: Pending USO's
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | PA120-02-IM | UHG | Melissa Chapman | Optum | 1001 Adams Avenue | Norristown, PA |  | VS20081342 3102-1763 3102-BBYS | 2020-06-11 | 2020-06-12 | 2020-10-09 | 2020-08-17 |  | Y | BBEC.687438 | ASE LNS | PAKRGN100791TPM | 2020-09-24 | 1ST FL ELECT RM,01NWAL.04.01 PORTS MULTIMODE SC |  |  |  | 50 | 10.1.82.49 | 10.1.82.50 | 65370 | 202610 | UHG GLOBAL 150 | 8/17: ORDER COMPLETE 6/30-8/10: Construction fiber work scheduled to complete 9/15. Access install scheduled for 9/23. Per Dion Dixon DD429S (Engineer), "Install location still pending construction. No completion eta as of yet. Will follow up with customer for timeline" 6/11: Order rec'd
New | 5M Port/ 10M Access EaAVPN 1000 Base-SX | CA461-01-IM | UHG | Melissa Chapman | Optum | 5832 Beach Blvd, Suite 112 | Buena Park, CA |  | VS20084630 3102-0984 3102-BBZD | 2020-06-12 | 2020-09-16 | 2020-09-16 | 2020-08-20 |  | Y | MLEC.534005 | SBC | 13KRGN603108PT | 2020-08-11 | BASEMENT 0.1 VIRTUAL EDGE 1 PORT 12 |  |  |  | 50 | 10.1.82.53 | 10.1.82.54 | 65449 | 202610 | UHG GLOBAL 150 | 8/20: Order complete - I checked the LEC’s system this morning and there were no additional notes regarding the change to MMF. Can you check with the site and see if they can locate the circuit based on the demarc info above? The only other thing we were told by the engineer was that it was “completed yesterday with an MMF extended to the customer suite.” 8/17: Per Philip Walton (LEC Tech AM): "This bldg. is a newer construction and every suite was prewired with 5 strands of SMF placed to it in a micro duct which makes it more difficult to pull new fiber. I’ll go by tomorrow and see if there is something else that can be done." 8/12: Access install missed - handoff issue - requested Deidre check to see what would need to happen to switch this to SMF. I checked the LEC notes and the technician did advise as follows: CANCEL/REDESIGN ORD FOR SGL-MODE FIBER HANDOFF; NEW BLDG IS PRE-WIRED FOR SGL-MODE APC HANDOFF FIBER. It’s my understanding this would need to be cancelled and reissued. 8/10: Access install is scheduled for 8/11. (still showing due today) 7/27: Per the LEC Tech: NO CALL BACK FROM LCON SHERI OR ALT. LCON DEAN / SUITE STILL UNDER CONSTRUCTION / PLACED SFP IN PORT 5 OF BNPKCATY0BW WIRED MM JUMPER TO JK 12 OF V.E.;ADT:07/21/2020 03:53:01 PM GMT;NO CALL BACK FROM LCON / SUITE STILL UNDER CONSTRUCTION 7/20: Access install rescheduled for 7/21. 7/13: Requested install date was 7/15. Monitoring for up LEC updates. Last LEC update was "SITE STILL UNDER CONSTRUCTION" 7/6: LCON change complete - ServiceNow ticket issued for redispatch. PON resent. 7/1: Issued HITS ticket 1191708616 to have LCON changed to TIMOTHY PATTON per Melissa's request. 6/30: Access install scheduled for 7/1. 6/12: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | LA047-02-IM | UHG | Melissa Chapman | People's Health | 3625 Houma Blvd | Metairie, LA |  | VS20084599 3102-0865 7SS03676003 3102-BBZC | 2020-06-12 | 2020-06-19 | 2020-09-04 | 2020-08-11 |  | Y | IUEC.920958 | ATT SE | L2KRGN822628SC | 2020-08-11 | 1ST FLR TLCO/SRVR WALL MOUNT 3903X ED |  |  |  | 50 | 10.1.82.29 | 10.1.82.30 | 65369 | 202610 | UHG GLOBAL 150 | 8/11: ORDER COMPLETE 8/10: Fiber work completed last week on 8/6. Access install scheduled for 8/11. (still showing due today) 7/28: Fiber work scheduled for 8/07 6/30-7/27: Per BIC (ED), "please CNR SV delayed but scheduled. I spoke with LCON. The building is not under lease yet by the customer. She is reaching out to the property manager to try and schedule for tomorrow or Friday." 6/15: Order rec'd
New | 200M Port/ 400M Access EaAVPN 1000 Base-LX | C1622-10-IM | UHG | Melissa Chapman | Sitel | 5601 No. 103rd St. | Omaha, NE |  | VS20105858 3102-1612 7CS04524054 3102-BCCG | 2020-08-03 | 2020-08-07 | 2020-11-03 | 2020-08-17 |  | Y | BLEC.995073 | ASE LNS | NEKRGN100118TPM | 2020-08-19 | 1000A.06 LGX PNL JACKS 5&6.SC SINGLEMODE |  |  |  | 50 | 10.191.19.5 | 10.191.19.6 | 65504 | 202609 | UHGECC GLOBAL | 8/17: ORDER COMPLETE - LOA sent 8/18 8/10: Site visit scheduled for 8/12. 8/3: Order rec'd
New | 100M Port/ 100M Access EaAVPN 1000 Base-SX | AZ162-01-IM | UHG | Melissa Chapman | Mountain West | 4845 E Thunderbird Rd | Phoenix, AZ |  | VS20070488 3102-0891 HWS03866657 3102-BBXZ | 2020-05-19 | 2020-05-20 | 2020-08-19 | 2020-08-20 |  | Y | IUEC.657299 | Qwest | 19KXGS528144MS | 2020-08-25 | UNI 1ST FL MPOP WALL MNT TYPE: OPTICAL PORT: 3 |  |  |  | 151 | 10.1.87.193 | 10.1.87.194 | 65372 | 202610 | UHG GLOBAL 150 | 8/24: ORDER COMPLETE 8/17: Access install rescheduled for 8/25. 7/13-8/10: Access install scheduled for 9/9. 7/6: Pending install date on PON HWS03866657 6/29: Per LEC, CUSTOMER NOT READY - THE CUSTOMER MUST PLACE CABLE CONDUIT ENTRANCE FACILITIES CONSTRUCTION ON PROPERTY 6/2-6/15: Qwest access install scheduled for 8/11. --- 1B OUTSIDE PLANT (OSP) - MAJOR BUILD 5/19: Pending USO's
New | 30M Port/ 50M Access EaAVPN 1000 Base-SX | LA025-01-IM | UHG | Melissa Chapman | People's Health | 7049 Perkins Road | Baton Rouge, LA |  | VS20078355 3102-1630 7SS03673006 3102-BBYP | 2020-05-28 |  | 2020-08-21 | 2020-08-21 |  | Y | BBEC.641826 | ATT SE | L0KRGN401145SC | 2020-09-14 | 1ST SERVER 1ST SERVER RM BB 3930 RT 5 TAG |  |  |  | 50 | 10.1.82.225 | 10.1.82.226 | 65392 | 202610 | UHG GLOBAL 150 | 8/24: ORDER COMPLETE 8/17: Infrastructure completed 8/13. Access rescheduled for 8/25. 6/15-8/10: Construction fiber work scheduled to complete 9/2. Access install scheduled for 9/14. 6/12: Issued HITS ticket to change LCON to Pat Davidson / Pdavidson@primarycareplus.com / 225-706-2166 6/8: Site visit scheduled for 6/10. 5/28: Pending USO's
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | TX588-02-IM | UHG | Melissa Chapman | Wellmed | 4203 E. Southcross | San Antonio, TX |  | VS20099548 3102-1225 3102-BCBR | 2020-07-22 | 2020-07-30 | 2020-07-30 | 2020-08-20 |  | Y | IUEC.600355 | SBC ONNET-5 | 31KRGN654918SW | 2020-07-30 | 1ST FLR TELCO RM WALL MNT,PORT#2 |  |  |  | 50 | 10.1.88.49 | 10.1.88.50 | 65042 | 202610 | UHG GLOBAL 150 | 8/24: ORDER COMPLETE 8/17: Going by the dates and notes in GRETA (LEC) and the Construction website. The fiber work was completed on 8/11 and access is showing due to complete on 8/20. No other issues at the site at present. 8/10: ORDER DELAYED - FIELD TECH DISPATCHED TO FIND THAT THERE IS NO LONGER A CIENA 3930 AT THIS SITE AS THE PREVIOUS OCCUPANT REMOVED IT. Site visit was conducted end of last week and we're pending a date from Construction for any fiber work needed AND Ciena install. 7/28: ON-NET - Access install due to compete 7/30. 7/22: Order rec'd
New | 200M Port/ 400M Access EaAVPN 1000 Base-LX | C1654-07-IM | UHG | Melissa Chapman | Sitel | 11830 Webb Chapel Rd | Dallas, TX |  | VS20105206 3102-1582 7MS02418826 3102-BCCC | 2020-08-04 | 2020-08-06 | 2020-11-02 | 2020-08-18 |  | Y | BLEC.995062 | SBC | 14KRGN888802SW | 2020-08-18 | 1ST FLR,,STE 200,MMR, TELCO CAGE, RR 12, PNL 2, POS 9 |  |  |  | 50 | 10.191.22.89 | 10.191.22.90 | 65509 | 202609 | UHGECC GLOBAL | 8/20: ORDER COMPLETE 8/10-8/17: Access install scheduled for 8/18. 8/4: Order rec'd
New | 300M Port/ 500M Access EaAVPN 1000 Base-LX | TX595-02-IM | UHG | Melissa Chapman | USHealth Group | 700 Austin Ave | Waco, TX |  | VS20107027 3102-0338 3102-BCCK | 2020-08-07 | 2020-08-18 | 2020-08-21 | 2020-08-19 |  | Y | BMEC.800618 | SBC ONNET-5 | 39KRGN610439SW | 2020-08-19 | 1ST FL SERVER RM CKT IS TAGGED N SLOT 9 ON W/TELL PAN |  |  |  | 50 | 10.1.87.141 | 10.1.87.142 | 64592 | 202609 | UHGECC GLOBAL | 8/20: ORDER COMPLETE 8/18: Access install scheduled for 8/19. 8/7: Order rec'd
New | 200M Port/ 500M Access EaAVPN 1000 Base-SX | C1658-02-IM | UHG | Melissa Chapman | Insight Distribution Center | 1600 Hunter Road | Hanover Park, IL |  | VS20107029 3102-0275 3102-BCCH | 2020-08-07 | 2020-08-11 | 2020-11-05 | 2020-08-21 |  | Y | BMEC.799961 | SBC | KRGN127470LB | 2020-08-21 | 2ND SERVER RACK MOUNT HANDOFF TRAY 2, PORT 5 |  |  |  | 50 | 10.191.22.101 | 10.191.22.102 | 65470 | 202609 | UHGECC GLOBAL | 8/24: ORDER COMPLETE 8/18: Access install scheduled for 8/21. 8/7: Order rec'd
New | 300M Port/ 400M Access EaAVPN 1000 Base-SX | MA008-05-IM | UHG | Melissa Chapman |  | 1325 Boylston Street | Boston, MA |  | VS19180563 3102-1241 3102-BBPC 3102-BBPB | 2019-11-11 | 2020-02-03 | 2020-02-03 | 2020-08-31 |  | Y | BLEC.989994 | Verizon | 95KFGS010888NE | 2020-02-19 | 9TH FL SERVER ROOM WALL MOUNT EXT FROM BASEMENT. |  |  |  | 399 | 10.1.93.205 | 10.1.93.206 | 64705 | 202610 | UHG GLOBAL 150 | 8/31: Escalated to Sheila Randolph (TECH COACH) to complete order plug and play. UPDATE: ORDER COMPLETE 8/24: Continued delays to get remaining critical dates completed - I've reached out to Phil Cunningham (Assembler Coach) to have his team complete the work. 8/14: DDF ticket 202008170004 issued to complete engineering and other critical dates to make ready for turn up. 8/11: UPDATE: Access completed ahead of schedule - pending testing completion and OK to turn up. 8/10: Access install scheduled for 8/12. 7/21-7/27: PON resent - pending update from LEC - targeting 8/7 for LEC due date 7/15-7/20: Reached out to Phil Cunningham (Design AM) for assistance in clearing out order CNR/Covid coding and resending PON. COVID-19 SITE DELAY - S19C ALLOWING ACCESS - Call LCON AHEAD 3/30: Reached out to ATT Provisioning team.......Requested that we NOT cancel the Boston order. Melissa confirmed the Landlord was allowing our LEC Verizon access until Covid19 hit and we expect that in due time they will allow work to continue at the site. We may want to consider jepp’ing the order with the Covid19 code “S19C” to ensure the provisioning team understands this is a Special Use Order Impacted by COVID-19. 3/23: Per Melissa, "All work at site has been halted for the next couple of weeks due to Covid-19." 3/10: Per Jennifer Dupuis (AT&T): Verizon was on site yesterday (3/9), arrived around 9AM and worked in the demark area until 2PM. At 2PM I had to run to meetings and other sites. I informed the techs to contact their office to reschedule the remainder of the work; advance notice is required as well as an estimated time of arrival and for completion as access to the MDF is restricted. 3/6: Per Jennifer Dupuis (AT&T): I just heard from Vz and the tech got pulled off for an emergency. Can we reschedule this for next week? Let me know what days may be best. 3/3: Per Jennifer Dupuis (AT&T): I have heard from Verizon and for the next visit they need, they just need access to P1 Demark NT (either a first floor or basement). They only need one day for this visit and proposing 03/06 – Ashley, they have your contact, can they work with you for access. The visit after that, may be more involved as they will be installing their equipment for our project and may need more than a day and more scope involving the Landlord and other tenant areas. For now, we just need that initial access. 3/3: Reached out again to CNR agent - requested update within the hour. UPDATE: Advised CNR Agent to check and see if Verizon provided the COI to the end user AND to find out when they will redispatch as we're being told site is ready. 3/2: Reached out to the CNR Agent to see what can be done to dispatch this week. 2/24: Access install missed - is site allowing Verizon access? - FIRST WEEK OF MARCH DISPATCH POSSIBLE 2/11-2/17: Access install scheduled for 2/19. 1/29-2/3: Confirmed PON was resent to the LEC. Pending install date. 1/27: Pending PON supp and new date 1/23: Received OK from Melissa to move forward - "We have approval from the landlord. We need a COI from Verizon and an due date for dispatch. Can you sup the order and get that please" 1/6-1/20: There is a CUSTOMER NOT READY CNR on this order from the LEC Verizon. Once site is ready I'll have the CNR removed and PON supp'd. Need status from UHG - PENDING LANDLORD APPROVALS FOR ACCESS. PON NEEDS TO BE SUPP'D WHEN SITE IS READY 12/30: Per Melissa, need a contact name for the OSPE for Verizon. The onsite was saying that the tech was saying they needed to pull some fiber. This site is rather picky and they want a Statement of work of what Verizon wants to do at the site. UPDATE: SENT OSPE INFO TO MELISSA. 12/12-12/30: CARRIER MANAGEMENT ENGAGED due to CNR Customer Not Ready - Per Carrier Mgmt, SPOKE WITH KATHLEEN @VERIZON WHO VERIFIED THIS ORDER TECH WENT OUT, NO ANSWER WITH THE CUSTOMER, NO ACCESS TO THE BUILDING, WAITING ON LCON DUE TO THIS POSTING A C01L CARRIER MGMT TIER 1 DISENGAGED 11/25-12/3: Access install scheduled for 12/10. 11/15-11/18: Pending install date from the LEC Verizon North 11/11: Order rec'd - reissue using Verizon for access
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | TX013-03-IM | UHG | Melissa Chapman | OptumHealth | 1301 W. President George Bush Parkway | Richardson, TX |  | VS20064892 3102-1566 3102-BBXN | 2020-04-20 | 2020-05-07 | 2020-07-24 | 2020-08-28 |  | Y | BBEC.634047 | AT&T OF TEXAS (SPORT) | 50KRGN888418SWDL | 2020-07-14 | 2 TELCO CLST POS 5 ON BB. EXT TO CUZST DF ROOM |  |  |  | 50 | 10.1.85.177 | 10.1.85.178 | 65070 | 202610 | UHG GLOBAL 150 | 8/28: ORDER COMPLETE 8/24: Access install showing scheduled for 8/28. Reached out to LEC Tech AM Brian Mauer to see if we can get tech name since site will not allow tech to arrive Friday unannounced. 8/19: PON resent today 8/18: COI info rec'd 8/14: For the COI for TX013, I need to confirm the following information that you need to see on the form. Can you advise? Certificate Holder/Third Party Customer Name: Attn: Street Address: City, State Zip: Phone: Email: 8/10: Melissa sent email on 7/30 (Thur) that they need a COI for TX013 7/27: Reached out to Harish Kandpal (Optum) to see if her heard from the LCON's on allowing access. PON will need to be supp'd when we find out site is ready. 7/20: ORDER IS DELAYED AS PROPERTY MANAGER REFUSED ACCESS TO THE FIELD TECHNICIAN.PLEASE SUPPLEMENT THE PURCHASE ORDER NUMBER FOR A NEW DUE DATE WHEN CUSTOMER IS READY TO PROVIDE ACCESS.ENGAGING CUSTOMER NOT READY TEAM. 7/6-7/13: Fiber work is complete - pending access install completion on 7/14. 6/1-6/29: Construction fiber work set to complete on 7/2. Access install scheduled for 7/14. 5/12-5/26: Pending an install date from the LEC ATT OF TEXAS - DDF TICKET 202005120006 FOR R15. 4/20: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | FL118-06-IM | UHG | Melissa Chapman | XL Health | 1049 Lake Sumter Landing | The Villages, FL |  | VS20061558 3102-1540 7SS03665818 3102-BBWM 3102-BBWN | 2020-04-27 | 2020-04-29 | 2020-07-17 | 2020-08-31 |  | Y | BBEC.674802 | Embarq | 25KXGS517908UFLG | 2020-07-03 | FIRST FLOOR TELCO ROOM WALL MOUNT TAGGED AND LABEL |  |  |  | 2 | 10.1.82.113 | 10.1.82.114 | 64900 | 202610 | UHG GLOBAL 150 | 9/1: ORDER COMPLETE 8/31: Requested assistance from Cedrick Scott (Tech AM) in completing order plug and play. 8/24: Received completion (R84) on VLAN PON HSSV4527644. Pending testing completion and the OK to turn up. 8/17: VLAN PON HSSV4527644 due to complete 8/18. 8/10: VLAN PON issued - sent AERO Design ticket 1158501 for clearing of Design issue related to VLAN ID. 7/27: Issued AERO Design ticket 1134021 to look into the VLAN PON as it's not showing up on the USO and may need to be issued to the LEC. 7/20: Access install is complete - pending testing completion and the OK to turn up. VLAN ID 2 7/14: JOE SCRUDATO (AT&T) looking for status on this CNR - Need customer status. UPDATE: This was removed from Covid hold - advised Joe Scrudato (AT&T) to push for PON release S19C COVID19 Jep'd - Need to remove jep codes once we confirm with UHG that the site is ready - then PON will need to be resent via ServiceNow ticket. 7/6: LEC advised this is CNR - "UNABLE TO COMPLETE ORDER DUE TO NATIONAL EMERGENCY" 6/29: Access install rescheduled for 7/3. 6/1: Per LEC Embarq - SUPI: Y RCODE: 1S=BUILDING NOT READY, CUSTOMER WILL ADVISE. CUSTOMER NOT READY - ADDL INFORMATION TO FOLLOW. PEND COVID19 CUST CONTACT 5/5-5/26: Pending an install date from the LEC Embarq 4/27: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | NC063-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 220 Horizon Drive | Raleigh, NC |  | VS20089909 3102-1169 3102-BBZP | 2020-06-26 | 2020-07-23 | 2020-07-23 | 2020-08-26 |  | Y | IUEC.673924 | ATT SE NEARNET-15 | 26KRGN402253SB | 2020-08-26 | 1 100 SERVER ROOM TELCO BB |  |  |  | 50 | 10.1.82.17 | 10.1.82.18 | 65360 | 202610 | UHG GLOBAL 150 | 8/27: ORDER COMPLETE 8/18-8/24: Access install scheduled for 8/26. 8/17: Sent request to have CNR/S19C removed from this order. UPDATED - REDISPATCH SENT VIA SERVICE NOW. 8/11: NO NEW DATES ON THIS ORDER YET - FOLLOWING UP TODAY TO SEE WHAT CAN BE DONE TO GET THIS BACK ON TRACK. 7/28: Per Melissa, issued HITS ticket to change LCON - Can you supp to change the local contact to Tony Cattaruzza at 919-649-8649 (cell phone). TCattaruzza@diplomat.is 7/27: CNR per LEC Tech -- NO ACCESS - NO ONE ON SITE AT CUST SUITE - CLOSED DUE TO COVID-19 PANDEMIC - NO RETURN CALL FROM LCON BRIAN STOCKFISCH, 8107689920 - SLOTTED SFP IN CN5140 EMUX PORT 5 - REUSE FIBER FROM EMUX TO CUST STE 105 BUT NO ACCESS TO INSIDE CUST STE 105. 7/7-7/20: ATT SE access install scheduled for 7/23. 6/29: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | MD140-01-IM | UHG | Melissa Chapman | United Healthcare | 5275 Westview Drive | Frederick, MD |  | VS20098145 3102-0095 3102-BCBH 3102-BCBJ | 2020-07-13 | 2020-07-19 | 2020-10-06 | 2020-08-24 |  | Y | BBEC.633545 | Time Warner | MDKXFN428739LVLC | 2020-08-14 | FLOOR 1 - ROOM MDF |  |  |  | 213 | 10.1.82.61 | 10.1.82.62 | 64599 | 202610 | UHG GLOBAL 150 | 8/25: ORDER COMPLETE 8/24: Access install completed - pending testing completion and the OK to turn up. 8/18: Access install missed - no update from the LEC TW. Escalation to be sent tomorrow. 8/10: TW access install scheduled for 8/14. 7/28: FOC due back from Time Warner by 8/27. 7/13: Order rec'd
New | 100M Port/ 250M Access EaAVPN 1000 Base-SX | TX593-02-IM | UHG | Melissa Chapman | Wellmed | 9215 Westover Hills Blvd | San Antonio, TX |  | VS20103950 3102-1581 3102-BCBY | 2020-07-28 | 2020-08-11 | 2020-08-11 | 2020-08-27 |  | Y | BREC.972760 | SBC ONNET-5 | 31KRGN654931SW | 2020-08-11 | 2NDFLOOR, IT ROOM, 3903X, PORT 2 |  |  |  | 50 | 10.1.87.161 | 10.1.87.162 | 64779 | 202610 | UHG GLOBAL 150 | 8/28: ORDER COMPLETE 8/24: Fiber work scheduled to complete on 9/15. 8/17: Install date missed - Ciena/NTE issues showing in GRETA as well on this order. -PER DISPATCH TO 9215 WESTOVER HILLS BLVD ON TRBL TKT XH100373. CKT DISCONNECTED TWO YEARS AGO AND CIENA SENT BACK TO AT&T PER LCON CHRISTIAN ROMERO, 210.727.7333 8/10: Access install scheduled for 8/11. (still showing due today) 7/28: Order rec'd
New | HOT ORDER 400M Port / 500M Access Ethernet AVPN 1000Base-SX | II538-08-IM | UHG | Melissa Chapman |  | Optum Global Solutions (India) Private Limited9th, 10th, 11th and 12th Floor, Building No. 12BSundew Properties SEZ (Mindspace)TSIIC Layout, Survey No. 64 (Part)Hitech City | Hyderabad, Telangana India |  | ISR20063096637 VS20096557 ISR20080624878 VS20105466 3094-BWHM 3094-BWHN | 2020-06-25 | ASAP | 2020-10-20 | 2020-09-03 |  | BLYF.100359 | SAREA // Bharti |  | 2020-10-20 |  | 1000BaseSX - LC |  |  |  | 10.1.92.49 | 10.1.92.50 | 65191 | 202610 | UHG GLOBAL 150 | 9/3: Access is delivered. Completion document sent (reached out to PM for doc) 8/28: Circuit provisioning completed. Telco confirms they getting errors during Testing. Team working to resolve issue. 8/24: Circuit provisioning in progress - Firm date still showing 10/12. 8/17: Firm date provided by PTT is 10/12/2020. 8/10: Order was reworked and new ISR# was provided -- Order is accepted by Telco. Expecting Firm date by 8/20. 7/14: Per Christine (AT&T), Special Construction charges may apply on this order. Christine is working on getting clarification - possibly a few thousand $$ but working to confirm. 7/13: Veronika Matuscinova - reminder sent to sales if not approved by July, 14 order will be canceled 7/7: ISR# rec'd - pending PTT details, dates, etc. 6/9: Order placed this morning per Christine 5/14: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL445-02-IM | UHG | Melissa Chapman | Wellmed | 7775 SW 87th Avenue | Kendall (Miami), FL |  | VS20084483 3102-0094 7SS03675978 3102-BBYY | 2020-06-16 | 2020-06-19 | 2020-09-04 | 2020-09-04 |  | Y | BBEC.661303 | ATT SE | 60KRGN765498SB | 2020-09-02 | 1ST FLOOR, SUITE 100, SERVER ROOM |  |  |  | 50 | 10.1.95.41 | 10.1.95.42 | 65364 | 202610 | UHG GLOBAL 150 | 9/4: ORDER COMPLETE 8/25-8/31: UPDATE THIS MORNING...Access install scheduled for 9/2. 8/24: Request to CNR CHATROOM to remove S19C - DONE.....ASE request sent by chatroom to push PON out to the LEC. 8/21: ALCON changed per request 8/18: Need to supp ALCON 8/17: Customer prem is showing ready as of 8/12. The fiber date has been pushed to 9/2. C&E Delay Reason = Customer Not Ready On Time. Per OSP Engineer: "During a site visit conducted on 07/30/20 with TODD VANDERSCHA, I explained that certain site preparation requirements must be completed before we can install the Network Terminating Equipment (NTE) in the Common Area/MPOE on floor 01, needed to provide your service. Such site preparation requirements are currently being completed in connection with another order and are the responsibility of another customer at your location. That customer is currently responsible for completion of the following site preparation requirements: - Pull Tape in conduit capable of supporting a minimum of 200 lb. pulling weight. - Minimum 1½" hard plastic innerduct or 2" EMT type conduit (per electrical code) with pull tape is required from the Main Equipment Room (Common Area) to another interior location within the building as identified by the AT&T Representative. · Paths longer than 300' or with two or more 90° turns will require a pull box no higher than 10 feet from floor level and have the minimum dimensions (12"x 12" x4" Deep) 8/10: Construction set to complete fiber work on 8/14. Pending access install date (most likely 7-10 days after fiber completes.) 7/29: Per OSP Engineer Tomas Morejon - "There are no requirements on behalf of the customer. The location does not have fiber and our contractors and field technicians are still working on the assignment to tie in the conduits and bring in the fiber to the location." 7/28: Our Construction notes show a site visit is scheduled for 7/30. 7/24: Added to HOT list. 7/27: Per Construction: THERE IS NO FIBER AT THE SUITE. CONTACTED PROVISIONING TEAM IN ORDER TO OPEN REWORK FOR THIS ORDER. MY NEXT - F/U 7/27/2020. Melissa provided update from their other VZ order - "Site visit has been completed on 07/22/20. CPR ECD and C&E ECD is on 08/07/20 respectively. " Unsure if the two orders are related yet. 7/21: Per installing LEC tech: This order is for 7775 SW 87th Avenue. The EMUX is in building 7765 which is a 2-story building, plus the handoff is MMF. The customer is in 7775 which is a 1-story building with (3) suites and that building has no fiber or fiber path. Tech is Robert Suter and AM is Miguel Lopez (ml879w.) LEC ADVISED COULD NOT CONTACT CUSTOMER JEOPARDY NO SERVING FIBER. I reached out to OSP Design Engineer TOMAS MOREJON this morning to advise him of the issues and see what next steps are. 7/20: Access install is due to complete today. 7/13: Site visit completed 7/8. Pending completion of fiber infrastructure by Construction team. Letter did not indicate any work needed by customer site. 7/6: Site visit scheduled for 7/8. 6/30: Per Construction, this is CNR. No site visit can be scheduled yet. Per BIC (TM), "spoke with the LCON, Todd, and he is working on getting access to the telephone rooms for this site. They are leasing the location and have not received the keys yet." 6/16: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX116-06-IM | UHG | Melissa Chapman | Wellmed | 1900 N. Main | San Antonio, TX |  | VS20057249 3102-0928 3102-BBTQ | 2020-04-17 | 2020-04-22 | 2020-07-09 | 2020-09-04 |  | Y | BBEC.642125 | ATT SW | 31KRGN654752SW | 2020-09-02 | 1ST FLR TELCO RM N MAIN SENIOR CLINIC SUITE PORT 2 |  |  |  | 50 | 10.1.84.125 | 10.1.84.126 | 64538 | 202610 | UHG GLOBAL 150 | 9/4: ORDER COMPLETE 8/31: Access install scheduled for 9/2. 8/25: HITS ticket issued to change LCON to Rick Williamson - once completed, PON will need to be resent. CNR AGENT SD5731. 8/24: No mention of ROE (per email from Melissa)......CNR - The LEC went out to install and came back with the following update: Message Type: CUSTOMER - NO ACCESS ARRIVED ON SITE. ONLY ONE STAFF MEMBER. NO COMBO TO STORAGE ROOM. POSSIBLE OTHER TENANT BUT NO ONE FOR THAT SITE AVAILABLE. Please let me know when we have confirmation from the site that they will allow tech access and we’ll have the PON supp’d to request a new date. 8/17: Access install has been rescheduled for 8/18. CNR issue lifted. 8/10: Access install scheduled for 9/24 due to CNR. 6/2: CNR Agent Sudip confirmed that the Customer Not Ready hold on this order has been removed. The new site visit date as per our system information is scheduled for 6/5/20. 6/1: Reached out to the CNR agent Sudip to get an update on the Construction end. So far no dates posted yet. 5/18: LCON was changed on USO. PON resent on 5/13. Pending an install date. 5/11: Please change the LCON to Reina Trevino, 210-508-5819, RTrevino@wellmed.net. Once the USO has been changed, please sup the PON to the LEC for a new date. 5/4-5/11: CNR: LEFT VMAIL/EMAIL FOR LCON, NO RESPONSE 4/27: Pending an install date from the LEC ATT SW 4/17: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX575-02-IM | UHG | Melissa Chapman | Wellmed | 1521 S. Staples Street, 3rd Floor | Corpus Christi, TX |  | VS20114688 3102-1165 3102-BCCY | 2020-08-21 | 2020-09-04 | 2020-09-04 | 2020-09-04 |  | Y | BBEC.666717 | SBC | 34KRGN614241SW | 2020-09-04 | 3 LAN MDF WALL MNT BISK JK |  |  |  | 50 | 10.1.92.153 | 10.1.92.154 | 64894 | 202610 | UHG GLOBAL 150 | 9/8: ORDER COMPLETE 8/31: Access install scheduled for 9/4. 8/21: Order rec'd
New | 1G Port/ 1G Access EaAVPN 1000 Base-SX | PA178-02-IM | UHG | Melissa Chapman | Flexential | 1000 Black Rock Road | Collegeville, PA |  | VS20087917 3102-1008 3102-BBZK 3102-BBZJ | 2020-06-23 | 2020-06-26 | 2020-09-23 | 2020-09-15 |  | Y | IZEC.699553 | Comcast | 11KGGS024689CBCL | 2020-09-14 | SE 406, RACK MOUNTED, RU27, LABELED WITH CIRCUIT INFORMATION, CIENNA 3930 |  |  |  | 2 | 10.1.85.33 | 10.1.85.34 | 65234 | 202610 | UHG GLOBAL 150 | 9/16: ORDER COMPLETE 9/15: Access showing missed this morning - pending update - need to give 2-biz days before escalating. 9/14: LEC updated the access install date this past Thursday - now showing 9/14 9/8: LEC updated the access install date to 9/21. 7/27-8/31: Comcast provided a 10/13 access install date. - AERO DESIGN 1199954 for removal of R15. 6/30-7/20: Pending an install date from the LEC Comcast. FOC due back by 8/3. 6/23: Order rec'd
New | 100M Port/ 200M Access EaAVPN 1000 Base-SX | OH160-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 7167 E Kemper Road | Cincinnati, OH |  | VS20088798 3102-1011 3102-BBZM 3102-BBZL | 2020-06-25 | 2020-06-29 | 2020-09-24 | 2020-09-08 |  | Y | BKEC.975271 | Time Warner Cable | 51L1XX816827TWCC | 2020-09-28 | 1STFL, SERVER RM , RACK LOCATION RU70 |  |  |  | 117 | 10.1.90.173 | 10.1.90.174 | 64636 | 202610 | UHG GLOBAL 150 | 9/9: ORDER COMPLETE 9/8: Time Warner completed access on 9/7 ahead of schedule (R84.) Pending testing completion and the OK to turn up. 7/13-8/31: Time Warner access install scheduled for 9/28. Minor build. 6/30-7/6: Pending an install date from Time Warner Cable. 6/25: Order rec'd
New | 30M Port/ 50M Access EaAVPN 1000 Base-SX | NC062-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 311 Pomona Dr | Greensboro, NC |  | VS20089945 3102-1179 3102-BBZQ | 2020-06-29 | 2020-07-01 | 2020-09-17 | 2020-09-11 |  | Y | BBEC.667168 | ATT SE | 24KRGN401598SB | 2020-09-22 | 1ST TELCO WALL MNT TGD |  |  |  | 50 | 10.1.82.13 | 10.1.82.14 | 65359 | 202610 | UHG GLOBAL 150 | 9/14: ORDER COMPLETE 7/13-9/8: Construction provided a 9/11 fiber completion date. Access install scheduled for 9/22. 7/7: Pending an install date from the LEC ATT SE 6/29: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | MO045-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 103 Corporate Lake Drive Suite B & 101C | Columbia, MO |  | VS20090578 3102-1221 HMS02419014 3102-BBZY 3102-BBZX | 2020-06-30 | 2020-07-02 | 2020-09-29 | 2020-09-08 |  | Y | IUEC.756445 | Centurytel | 48KXGS544439CTMO | 2020-09-03 | IN SERVER CLOSET ON 1ST FLR |  |  |  | 624 | 10.1.82.5 | 10.1.82.6 | 65357 | 202610 | UHG GLOBAL 150 | 9/9: ORDER COMPLETE 9/8: Access install completed - pending testing completion. Demarc provided. 8/31: Access install scheduled for 9/3. 8/24: PON Issue - CANCELLED, RECREATED AS PORT BASED - resent on 8/20 and FOC due back by/before 9/24 8/10-8/17: PON released to Centurytel on 8/7 and FOC due back by 9/11. 7/27: Order progressing as of late last week - pending an access install date. 7/20: Advised Clyde he should push for reissuing this order ASAP as Ordering team having no luck with multiple tickets getting this USO loaded. Pending response. 7/13: HITS Request ID: 1195505597 - Hi Team, regarding this HITS query an AERO SOA # 1101712 has been raised to load USO in SOTS. Please expect my next follow up by 07-09-2020. Thank you 7/7: USO not loaded in SOTS - issued HITS ticket to have this fixed. 6/30: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-LX | NV058-02-IM | UHG | Melissa Chapman | Optum RX | 1650 Spring Gate LN | Las Vegas, NV |  | VS20098270 3102-0257 3102-BCBN 3102-BCBM | 2020-07-01 | 2020-07-21 | 2020-10-06 | 2020-09-14 |  | Y | IUEC.797273 | Embarq | 53KXGS542439CTRL | 2020-09-15 | 1ST FLOOR ELECTRIAL ROOM WALL MOUNTED RAD #4 CUSTOMER PORT #3 |  |  |  | 2 | 10.1.91.173 | 10.1.91.174 | 64643 | 202610 | UHG GLOBAL 150 | 9/15: ORDER COMPLETE 9/14: Access install completed - pending testing completion and the OK to turn up. Carrier Mgmt ticket 1279652 opened to confirm demarc. 9/8: Access install now showing 9/14. 8/31: Access install scheduled for 9/15. 8/17-8/24: LEC Embarq advised FOC will be delayed. FOC due back by 9/15. 7/28-8/10: FOC due back from Embarq by 8/24. 7/1: Order rec'd
New | CANCELLED 200M Port/ 300M Access EaAVPN 1000 Base-SX | M0014-02-IM | UHG | Melissa Chapman | United Healthcare | 425 Market Street | San Francisco, CA |  | VS20044188 3102-1401 7WS03849220 3102-BBSF | 2020-03-23 | 2020-06-15 | 2020-06-15 |  |  |  | BLEC.992555 | ATT West | 86KRGN594797PT | 2020-04-10 | [5 empty] | 10.1.85.169 | 10.1.85.170 | 64642 | 202610 | UHG GLOBAL 150 | This is being reordered - keep on sheet for now until Melissa OK's reorder 8/18: This site will need to be re-ordered since the USO was cancelled as it was on hold for too long. UHG advised. COVID-19 SITE DELAY - S19C 8/10: Email to Melissa/John: I checked this order again this morning and I can’t even find it active in our systems anymore. I know we had some back and forth below about it below……did you find out if this is billing you monthly charges or was it maybe cancellation fees of some sort? Just trying to figure this one out and get it corrected. At this point I can tell you the order is cancelled so if we want service in San Fran, we’ll need to get this order reissued. (not to mention correct any billing issues you might have.) 7/14: Still on hold per Melissa. 5/4: AS PER THE RESPONSE FROM THE INSIDE WIRING TEAM, THE VENDOR IS STILL TRYING TO SCHEDULE FOR THE INSTALL THEY ARE TRYING EVERY OTHER DAY BUT HAVE NOT HAD A CALL BACK. THEY ARE CLOSED DUE TO THE COVID-19 AND ARE NOT RECEIVING THE MESSAGES. DUE DATE NEEDS TO BE SUPPLEMENTED. ENGAGING CUSTOMER NOT READY TEAM. - F/U 5/28/2020 4/27: CONTACTED INSIDE WIRING TEAM AND AS PER THEIR RESPONSE, IT APPEARS THAT THE VENDOR HAS NOT BEEN ABLE TO SCHEDULE THE SITE SURVEY WITH THE CLIENT YET THEY ARE EXPECTING TO OBTAIN A FIRM DATE BY 04/28/20. NEXT - F/U 4/28/2020 4/20: CARRIER MGMT ENGAGED - PER THE LEC, "ORDER IS BEING DELAYED DUE TO AN INSIDE WIRING JOB THAT REQUIRES A VENDOR TO COMPLETE THE WORK. THIS JOB SHOULD COMPLETE WITHIN 10 BUSINESS DAY S. Next follow up is 4/24. 4/13: Access install date missed - LEC showing jep'd H40 - Wiring Problems. Pending new date. Still within dates (overall due date is June) 4/6: Access install scheduled for 4/10. 3/31: Pending an install date from ATT West. Site Visit completed yesterday, pending update on Fiber work. 3/23: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX213-05-IM | UHG | Melissa Chapman | Wellmed | 2821 Lackland Road, Suite 101 | Fort Worth, TX |  | VS20057970 3102-1447 7MS02402529 3102-BBVG | 2020-04-20 | 2020-04-30 | TBD |  |  |  | BBEC.687760 | SBC ONNET-5 | [7 empty] | 10.1.84.77 | 10.1.84.78 | 65250 | 202610 | UHG GLOBAL 150 | DUMMY COMPLETED 9/8: Pending USO's on resubmitted order - Deidre issued IP change on this circuit so the IP's can be reused for the new order. 8/24: Need to have this order reissued - advised Deidre and Melissa via email. 8/17: Issued DDF ticket 202008170014 to have new PON issued. REACHED OUT TO TESIA KING (ATT ATLANTA) TO CHECK ON PON ISSUANCE. 8/11: Issued HITS ticket to request update as to whether a new PON can be sent out or whether a new USO is required. 8/10: CNR - New PON will need to be sent when ready. 6/1: Access install date pending - Need to S19C per Melissa email 5/18-5/26: PON supp sent via ServiceNow. Pending new date for install. 5/11: LCON change PON supp request 5/4-5/11: CNR per Construction: "SENT MULTIPLE EMAILS TO LCON. NO RESPONSE. PHONE NUMBERS GO TO OFFICE WITH NO ANSWER", WHICH INDICATES THAT THE SITE VISIT IS PENDING DUE TO UNRESPONSIVE LCON." 4/28: LCON change per Melissa: Jonathan Benson 469-776-6207 jbenson2@wellmed.net 4/27: Pending an install date from ATT SW 4/20: Order rec'd
New | HOT ORDER 100M Port/ 100M Access EaAVPN 100Base-TX | CA430-01-IM | UHG | Melissa Chapman | Monarch | 3998 Vista Way. Suite C. | Oceanside, CA |  | VS20063080 3102-1554 7WS03856842 CLO SMS598925001 3102-BBXB | 2020-05-01 | 2020-05-26 | 2020-05-26 | 2020-09-17 |  | Y | IUEC.779129 | SBC NEARNET-15 | 19KRGN533896PT | 2020-07-01 | 1ST FLR, INSIDE CO, CN3930, PORT-5 |  |  |  | 50 | 172.27.27.145 | 172.27.27.146 | 64744 | 488101 | Monarch | 9/18: ORDER COMPLETE 9/14: Requested update from internal team regarding quoted 10/23 access install date. Requested this be firmed up. 8/28-9/8: Seeing notes on the LEC side looking to update the ACCESS install date to 10/23. This hasn't been confirmed yet but working to find out what more has to be done to pull the date in. Right now still seeing a 9/11 due date for Fiber completion. 8/17-8/24: Received confirmation that the target date of 9/11 for completion of the fiber rework is accurate. There is a private property dig that was identified on 7/30 that has an ECD of 8/26. Permits were required and received. Construction has an overall ECD target of 9/11. 8/10: Advised by UHG (Q) that cabling is completed. The PON was resent on 8/7 and the LEC provided us an 8/18 install date...........HOWEVER.........I'm seeing notes on the construction side that their rework is not supposed to complete until 9/11. So I have reached out internally to escalate for clarification on the rework issue and to confirm what is needing to be done and whether the 9/11 date is accurate. Escalation issued via the NSS Tracker Bot tool. 7/27: Reached out to Q for status of the cabling. UPDATE: PER Q: still waiting on the ext work from our cable vendor. 7/20: Per Q: We have engaged our local cable vendor to add the fiber ext. We are still waiting for a scheduled site walk. 7/13: Per Dale (BIC): AT&T TO PLACE #6 GROUND COIL ON BB. ROD AND ROPE FROM 0.1 TO 1.1 FOR SUITES A,B & C. PLACE FAP IN 0.1. PLACE FTE, CIENA 3930 EMT AND DEMARC IN 1.1 FOR SUITES A, B & C. NOTE: CUSTOMER HAS CHANGED HANDOFF FROM OPTICAL TO ELECTRICAL. 3 BU'S IN THIS BLDG -- UPDATE FROM Q: He is opting out of the media converter option and sticking with Fiber. Q will engage their cable vendor to get this extension in place. Pending update. 6/30: Q Response to Dale (BIC): "Confirmed. We will work on adding the conduit pathway with Fiber MM / LC from (MPOE 3398) into our (Suite C MDF Room) where our Network Router equipment resides. Give me few weeks as we have various projects with our cable vendor and will need to determine availability to complete the work. I will update when this is done." 6/30: Per Dale (BIC): "Attached is the revised drawing for this order. We will be placing fiber into the MPOE in your building (suite C). This fiber and associated equipment will be located in the phone utility room shown below and in drawing. The only requirement will be to place the fiber extension from this phone utility room to your router in suite. We normally use SC to LC for the jumpers. Let me know if there are further questions." 6/29: Bill Gipson engaged on this order last week. Bill spoke with Lee and responded to the emails with Melissa. He sent a note to Dale (BIC) to see if he can assist, since it seems there is a major question or issue with the path. We need to push local engineers to go back out to the site. Path is an issue but also confirming what the customer expects seems to be in question. Q advised he was reaching out to Dale (BIC) regarding site visit from Friday. Per notes I'm seeing from Dale, they intend to: PLACE BACKBOARD AND GROUND, ROD AND ROPE FROM 0.1 TO MPOE FOR SUITES A, B AND C. PLACE INC FIBER FROM 0.1 MPOE TO MPOE FOR SUITES A, B AND C. PLACE FTE, CIENA 3930 EMT AND A DEMARC. ACCESS INSTALL SHOWING 7/1/2020 IN SOTS 6/16: CNR agent advised this morning that the Customer Not Ready hold on this order has been removed. We have raised a request to schedule the installation. The installation date will get scheduled in 24-48 hours. 6/15: Requested additional assistance from CNR Agent Muzassam to get the right people involved to have this installed in the garage MPOE. 6/9: Keith Denhart (OSP Engineer) referred this to an internal resource who is involved in locating the equipment inside the prem. I've asked for status and what can be done to install the equipment in the garage MPOE. 6/8: I've reached out to Keith Denhart (OSP Engineer) to confirm if they need to re-engineer this to the Garage MPOE. Checked the local access notes in Greta and they said it would need to go back to engineering if we plan to get this into garage MPOE. 6/2: Per Melissa, " I talked to Q and he said the tech went out to deliver and he said that fiber extension needs to be run. Previously ATT told ! to run a CAT5 cable, which obviously isn’t enough length...... Is it possible to just have ATT deliver at the MPOE in the garage as below. Give us DMARC and then Q will run the extension. Is that the issue or is there no fiber to building C? According to Q, the tech said he needed to go back to engineering so there is some confusion here." -I'm going to run this by BIC ENGINEER DENHART,KEITH C 6/1: Update on the Oceanside CA order CA430. Access install was scheduled for last week and here’s the update from the LEC: - NO PATH. PER TECHNICIAN DISPATCHED ON 5/26/2020 - "3 SEPARATE BUILDINGS AT ONE ADDRESS. 3998 EMUX IN MAIN BUILDING. NO PATH BETWEEN THE BUILDINGS. CUSTOMER QUOC WORKING WITH ATT TO GET THIS RESOLVED. NO FIBER TO CUSTOMER'S BUILDING." ONCE THE SITE IS READY AND ACCESS CAN BE PROVIDED, A NEW DUE DATE FOR DISPATCH NEEDS TO BE NEGOTIATED WITH THE CUSTOMER AND ORDER SUPPED WITH THE NEW DUE DATE. ISSUE OWNER - CNR TEAM (MU318K) 5/11-5/18: Access install scheduled for 5/26. 5/5: Pending an install date from ATT West 5/1: Order being reissued. Order has been reissued by UHG to change the handoff to MMF (1000base SX MMF), LC connector.
New | HOT ORDER 200M Port/ 400M Access Ethernet ADI 1000 Base-SX | DC007-08-IJ | UHG | John Sergot |  | 655 New York Ave | Washington D.C. |  | IP20023635 3102-0709 7ES02931947 3102-BBRL IP20061052 3102-1214 3102-BBZW | 2020-02-24 | 2020-07-16 | 2020-09-21 | 2020-09-16 |  |  | BLEC.994372 | Zayo | ETYX284575ZYO | 2020-08-07 | 655 NEW YORK AVE NW/FL-B1/RM-TELCO, WASHINGTON, DC, PORT HANDOFF: GIGE BANDWIDTH: 400MB VLAN ID: 110 CONNECTOR TYPE: LC HANDOFF: MULTIMODE 850NM SX/SR - 500M , DEMARC: 3RD FLOOR / MDF ROOM / RACK 2 / RU-37 ACCEDIAN NID PORT: 1 |  | LAN Information IPV4 Block: 12.32.45.192/28 LAN IP Gateway: 12.32.45.193 First Network Assignable: 12.32.45.194 Usable IP Range: 12.32.45.194 - 12.32.45.206 Broadcast IP Address: 12.32.45.207 Subnet Mask: 255.255.255.240 IPv6 Block: 2001:1890:14A9:2100::/56 IPv6 LAN IP Gateway: 2001:1890:14A9:2100::1 IPv6 Prefix: 0,56 WAN IP Information CR Serial IP Address: 12.127.253.170/30 IPv6 CR Serial IP Address: 2001:1890:0C02:0A29:0000:0000:11CB:9E31/64 Compressed IPv6 CR Serial IP Address: 2001:1890:C02:A29::11CB:9E31 AR Serial IP Address: 12.127.253.169/30 IPv6 AR Serial IP Address: 2001:1890:0C02:0A29:0000:0000:EECB:9E31/64 Compressed IPv6 AR Serial IP Address: 2001:1890:C02:A29::EECB:9E31 Wan IP Address: 12.127.253.168/30 | [7 empty] | 9/18: ORDER COMPLETE 9/14: Advised the LEC (Dani) to use VLAN ID 50 (or whatever is available.) Had CNR team remove the CNR coding and resend PON to the LEC. - UPDATE: LEC (DANI) ADVISED THEY WERE OK'D BY AT&T PROVISIONING TO USE VLAN ID 110. LEC SENT COMPLETION NOTICE (R84) - PENDING TESTING COMPLETION AND OK TO TURN UP. 8/31: Reached out to John Sergot to find out if customer reached out to Zayo to provide them forms being requested. UPDATE: Per JohnS he has reached out to his pm to see where they are at with this extension 8/24: Carrier Management advised ZAYO EMAILED CUSTOMER LCON = MILLERV@ADVISORY.COM WITH THE NEEDED FORMS. Please advise if customer has been in contact with Zayo to proceed . On AT&T side, Joe Scrudato is engaged if we need to involve provisioning on this order. 8/18: AERO CM Ticket 1172598 opened for have Carrier Management reach out to Zayo to advise them the customer cannot extend something not installed yet. Pending CM response. 8/17: PER ZAYO, PENDING SPACE AND POWER FORM FILLED OUT PENDING EXTENSION / CROSS CONNECT TO DISPATCH FOR INSTALL. JEP AS CUSTOMER NOT READY. 8/11: Added to HOT list. 8/10: Reached out to CNR AGENT BHATTACHARYYA, SAGAR for status on Zayo access. Advised Sagar that we received word on 6/30 that it was OK to deliver to the MPOE on 1st floor so should be no issues. 7/27: Received an access install date of 8/7 from Zayo. 7/13-7/20: Pending install date from the LEC Zayo. FOC due back by 8/12. 7/7: Pending USO's.- UPDATE, received USO's from Clyde. 6/30: John S confirmed back to Chris C that it's OK to deliver access to the MPOE on the 1st floor 6/19: Per John S: Please process an order to install a new 400M port/access ADI circuit using Zayo as last mile provider If possible please use MMF LC connector. DC007 655 New York Avenue NW, Washington, District of Columbia 20001 Venita Miller +1 202-266-5955 MillerV@advisory.com 3rd Floor Let me know if you need any other information. 6/15: Reached out to Chris to see if we have other carriers. 6/8: Zayo is requesting single mode fiber extension because Zayo installs single mode fiber circuits and the customer extension needs to match what they install. In this case, when a customer requests multimode fiber handoff (or even a copper handoff), the way they provide the MMF handoff is through the Accedian NID device which they say is yet to be installed. I went back and explained UHG's situation that they only have MMF in the building and running new SMF would cost approx $6K and they advised that unfortunately there is no other option and that “this is the way Zayo installs circuits.” 6/8: Reached out to Daniela Knauf (Zayo) for info regarding Single Mode fiber request in her email. UHG and AT&T order both show multi mode fiber was requested. 6/1: 5/29 install date showing missed. Investigating CNR response from the LEC. 4/6-5/26: Zayo provided a 5/29 access install date. 3/16-3/30: PON released on 3/11 - FOC due back by 4/15. 3/10: USO's rec'd today - pending PON release to Zayo. 2/26: Opportunity ID: 1-CMASJAD - Order Tracking ID: 1-CMJR8V5 2/24: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX586-02-IM | UHG | Melissa Chapman | Wellmed | 316 W Beltline Rd. Suit 100 | Cedar Hill, TX |  | VS20070394 3102-0276 3102-BBXY | 2020-05-19 | 2020-05-20 | 2020-09-03 | 2020-09-18 |  | Y | BBEC.661513 | SBC | 14KRGN888384SW | 2020-09-17 | 1RST ,SERVER,1RST FLR MAIN SERVER |  |  |  | 50 | 10.1.87.45 | 10.1.87.46 | 64824 | 202610 | UHG GLOBAL 150 | 9/21: ORDER COMPLETE 9/14: Access install has been rescheduled for 9/17. 9/8: Received word from Kelly Sjelin ¦ Optum that conduit work is complete. CNR coding was removed via the chatroom and PON was resent to the LEC notifying them the site is ready. 8/28: Email to Melissa.....I’m seeing notes in the system that the conduit issue at this Cedar Hill location is a customer responsibility to fix. From what the notes say, “THE CUSTOMERS CONDUIT IS BLOCKED AND NEEDS TO BE CLEARED AND A PULL STRING PLACED FROM THE POLE TO THE CUSTOMERS DEMARC.” When you get a chance, can you reach out to the local contacts and see if they understand what needs to be done? 8/24: Reached out to LEC AM Alan Sullivan to find out more about the blocked conduit and who is doing what. 8/10-8/24: Access install DUE TODAY - UPDATE FROM LEC TECH: CUSTOMER CONDUIT IS BLOCKED NEEDS TO BE CLEARED AND PULL STRING PLACED PER OUTSIDE TECH LOG NOTES. Pending date for redispatch to correct issue. 7/27: Sent follow up to Melissa to see if conduit work completed on Friday. UPDATE - CONDUIT WORK COMPLETED ON FRIDAY PER MELISSA.......working on next steps for delivery. 7/22: Per Melissa, The MPOE will be moved to the “IT Room” below on this drawing and 2” conduit is being completed on Friday the the 25th. Power and Backboard are already in place. 7/1-7/13: Per LEC: CUSTOMER SITE NOT READY - PER LEC: RECEIVED CALL BACK FROM OSPE KT6874, HE SAID WE WILL HAVE TO PULL FIBER FROM POLE TERM INTO CUSTOMER SUITE. CUSTOMER WANTS TO MOVE LOCATION OF INSTALL AND HAS NOT DETERMINED WHERE THEY WANT TO PLACE SERVER ROOM. KT6874 WILL WORK WITH CUSTOMER TO PLACE TERMINAL WHEN CUSTOMER HAS DETERMINED NEW LOCATION. 6/29: Access install showing rescheduled for 6/30. 6/2-6/15: LEC access install scheduled for 8/19. 5/19: Pending USO's
New | 40M Port/ 100M Access EaAVPN 1000 Base-SX | LA026-01-IM | UHG | Melissa Chapman | People's Health | 632 Corporate Dr., Suite C | Houma, LA |  | VS20078367 3102-1631 7SS03673005 3102-BBYQ | 2020-05-28 |  | 2020-08-21 | 2020-09-16 |  | Y | IUEC.872667 | ATT SE | L2KRGN822612SC | 2020-09-16 | 1 1 OPTICAL PORT 2 SUITE C WALL MNT |  |  |  | 50 | 10.1.82.193 | 10.1.82.194 | 65387 | 202610 | UHG GLOBAL 150 | 9/18: ORDER COMPLETE 8/11-9/14: LEC provided a 9/16 install date. 7/29: PER MELISSA - The decision was made to keep Suite D. Can we have the new circuit installed there? The current circuit is terminated in Suite C, which is probably going to be vacated. 7/20-7/27: CNR - CUSTOMER NOT READY - Per LEC, PER I.T DEPT SUPV RICK. CUST MAY BE MOVING TO UNIT D INSTEAD OF ASSIGNED UNIT C. REQUIRING NEW CONDUIT IF MOVING TO UNIT D. CUST WILL CALL US TO ADV ADDRESS CHANGE AND NEW DUE DATE WHEN IS READY FOR NEW SERVICE. 7/13: Fiber complete - access install date improved to 7/14. 6/15-7/6: Construction fiber work scheduled to complete 8/6. Access install scheduled for 8/17. 6/8: Site visit scheduled for 6/10. 5/28: Pending USO's
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | MA065-02-IM | UHG | Melissa Chapman | Diplomat M&A | 20 Commerce Way Suite 2 | Woburn, MA |  | VS20098976 3102-0153 3102-BCBK 3102-BCBL | 2020-07-13 | 2020-07-21 | 2020-10-07 | 2020-09-15 |  | Y | BBEC.633527 | Verizon North | 95KFGS011904NE | 2020-08-13 | GROUND FLOOR DATA ROOM EXT FROM MAIN TELCO ROOM WA LL MOUNTEDTAGGED WITH ID S |  |  |  | 75 | 10.1.82.1 | 10.1.82.2 | 65356 | 202610 | UHG GLOBAL 150 | 9/18: ORDER COMPLETE 9/15: VLAN PON due to complete on 9/17. 9/14: Pending completion date on VLAN PON. Issued AERO ticket 1279978 to push it. 9/8: Access install completed - demarc provided - pending testing completion on access. Also pending FOC on the VLAN PON HNSV4520204. 8/31: PON released today - pending install date - FOC due back by 10/5. 8/25: CNR agent MAJUMDER, ANANYA advised to have order submitted for redispatch. Site requirements are complete. 8/24: CNR - AS PER THE EWPTS TOOL OF VERIZON THIS ORDER IS JEP'D TO THE CUSTOMER...THE LEC IS WAITING FOR THE CUSTOMER TO RUN THE HOUSE FIBRE...IT IS ALSO PENDING ENGINEERING WORK ORDER. 8/17: Per Provisioning: REACHED OUT TO LEC ( REP AMY ) AND GOT THE INFORMATION THAT THE BUILD WASN'T COMPLETED AND THUS THE CASE HAS BEEN MARKED AS CNR'ED . HENCE I AM ROUTING THE CASE TO PRE-CTA CNR TEAM FOR FOLLOW UP 8/10: VZ access install scheduled for 8/13. 7/28: FOC due back from Verizon by 8/25. 7/13: Order rec'd
New | 200M Port/ 400M Access EaAVPN 1000 Base-LX | WA133-02-IM | UHG | Melissa Chapman | UHG | 17930 International Blvd. | Seatac, WA |  | VS20099031 3102-1224 3102-BCBQ | 2020-07-21 | 2020-07-22 | 2020-10-07 | 2020-09-22 |  | Y | BMEC.965197 | Qwest | 04KXGS535922PN | 2020-11-11 | 1ST FLR TELCO ROOM RACK MOUNT TAG. |  |  |  | 82 | 10.1.88.121 | 10.1.88.122 | 65353 | 202610 | UHG GLOBAL 150 | 9/21: Access install completed. VLAN PON HWSV4519987 R84 completed. Pending testing completion and the OK to turn up. 9/14: Per Qwest, 1A OUTSIDE PLANT (OSP) MINOR BUILD still delaying order. Pending updated install date. 8/31-9/8: Qwest has updated their anticipated install date to 9/10. 8/10-8/17: Qwest provided an 11/11 access install date. -- 1A OUTSIDE PLANT (OSP) - MINOR BUILD 7/28: FOC due back from Qwest by 8/25. 7/21: Order rec'd
New | 100M Port/ 100M Access EaAVPN 1000 Base-SX | UNY14-12-IM | UHG | Melissa Chapman | United Healthcare | 2950 Expressway Drive South | Islandia, NY |  | VS20110059 3102-1105 3102-BCCN 3102-BCCM | 2020-08-11 | 2020-08-18 | 2020-11-03 | 2020-09-18 |  | Y | IUEC.576405 | Cablevision Lightpath | 01LUXS254124CLV | 2020-10-12 | BASEMENT COMMON SPACE MAIN TELCO RM UNI 254124 JACK 5 |  |  |  | 4 | 10.45.10.233 | 10.45.10.234 | 64553 | 202610 | UHG GLOBAL 150 | 9/21: ORDER COMPLETE 9/8-9/14: Access install scheduled for 10/12. 8/25-8/31: Pending an install date from the LEC Cablevision Lightpath 8/11: Order rec'd - This needs to be delivered to the new MDF RM 228 (new MDF), which is expected to be ready in December
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX346-06-IM | UHG | Melissa Chapman | Wellmed | 7198 Merchant Ave | El Paso, TX |  | VS20108762 3102-0943 7MS02420067 3102-BCCL | 2020-08-11 | 2020-08-14 | 2020-11-10 | 2020-09-21 |  | Y | BBEC.660871 | SBC | 30KRGN615531SW | 2020-09-22 | EXTENDED CIRCUIT FROM OUTSIDE CIENA TO NSIDE WHSE DATA SERVER RM |  |  |  | 50 | 10.1.82.229 | 10.1.82.230 | 64832 | 202610 | UHG GLOBAL 150 | 9/21: ORDER COMPLETE 9/14: Fiber work completed ahead of schedule on 9/10. Access install has been rescheduled for 9/22. 8/24-9/8: Fiber work scheduled to complete 12/14. Access install scheduled for 12/23. 8/18: Pending an install date from the LEC. Site visit scheduled for 8/19. 8/11: Order rec'd - Please re-process the attached. This was accidently cancelled.
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX601-02-IM | UHG | Melissa Chapman | Wellmed | 3228 Interstate 30, STE 200 | Mesquite, TX |  | VS20111490 3102-1124 7MS02421010 3102-BCCQ | 2020-08-19 | 2020-08-28 | 2020-08-28 | 2020-09-23 |  | Y | BBEC.686909 | SBC ONNET-5 | 14KRGN889024SW | 2020-09-22 | 1ST FLR SERVER RM WALL MOUNT ON BB TAGGED (14KRGN889024SW) |  |  |  | 50 | 10.1.95.217 | 10.1.95.218 | 65150 | 202610 | UHG GLOBAL 150 | 9/24: ORDER COMPLETE 9/21: Access install scheduled for 9/22. 9/14: PON reissued on 9/11 - FOC due back by 9/16. 9/8: Issued IOS Escalation for missed FOC - pending install date from ATT SW (SBC) 8/25-8/31: Pending an install date from the LEC SBC (on-net) 8/19: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX555-02-IM | UHG | Melissa Chapman | Wellmed | 1901 W William Cannon Dr., Suite 112 | Austin, TX |  | VS20028481 3102-1373 7MS02393294 3102-BBRN | 2020-02-26 | 2020-03-26 | 2020-05-12 | 2020-09-22 |  | Y | BBEC.592592 | ATT SW | 32KRGN654209SW | 2020-03-09 | OUTSIDE BOX NEXT TO 3931 |  |  |  | 50 | 10.1.93.197 | 10.1.93.198 | 64934 | 202610 | UHG GLOBAL 150 | 9/22: ORDER COMPLETE 9/22: Reached out for update on NTE placement due yesterday. 9/21: Fiber work completed as scheduled. NTE placement due today 9/21. 8/31-9/14: No change in dates - 9/17 for fiber, 9/22 for NTE. PON resent for access install date. 5/18-8/24: Construction still showing a 9/17/2020 Fiber Infrastructure completion date and 9/22 NTE placement date. 4/6-5/11: Construction showing a 9/17/2020 Fiber Infrastructure completion date. Customer requirements letter sent to Melissa. - UPDATE EF OFFER accepted per Melissa. 3/30: Pending Construction timeframes. Delay appears to be with the address........"site visit says address is 1901 W William Cannon, new cllicode has address of 1901 E William Cannon/ which is the correct address for this order" 3/24: Site visit completed yesterday - pending construction timeframes. 3/23: Site visit is scheduled for TODAY per Construction 3/16: AT&T NOT READY - CUSTOMER SUITE IS IN ADJACENT BUILDING FROM WHERE 3930 EQUIPMENT IS LOCATED IN. THERE IS NO PATHWAY FROM STATE FARMS SUITE TO SUITE 112. THEY ARE 2 SEPARATE BUILDINGS. PENDING UPDATE ON DATES. SITE VISIT SCHEDULED FOR 3/17. 2/26: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | TX589-02-IM | UHG | Melissa Chapman | Wellmed | 600 Division Ave | San Antonio, TX |  | VS20102102 3102-1576 7MS02417534 3102-BCBT | 2020-07-28 | 2020-07-29 | 2020-10-23 | 2020-09-23 |  | Y | IUEC.848484 | SBC | 31KRGN654930SW | 2020-10-07 | IN COMMON CLOSET |  |  |  | 50 | 10.1.89.85 | 10.1.89.86 | 64863 | 202610 | UHG GLOBAL 150 | 9/24: ORDER COMPLETE 9/21: FIber work completed 09/17 ahead of schedule. Access install rescheduled for 9/22. 8/24-9/14: No change - Fiber work scheduled to complete 9/28. Access install scheduled for 10/7. 8/10-8/17: Site visit completed on Friday - Fiber work scheduled to complete 9/28. Access install scheduled for 10/7. These requirements were thoroughly covered during the site visit conducted on 08/07/20 with CHRISTIAN ROMER. The following requirements need to be completed in full by 09/14/20 to avoid a delay of your ASE order. Per your acceptance of the ASE Entrance Facility Offer, AT&T will complete the specified site readiness requirements listed below: - Place new #6 ground wire bonded to an MGN (except in CA) or UFER Ground terminated to a grounding bus bar - ATT TO PROVIDE #6 GROUND 7/28: Order rec'd
New | CANCELLED 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX603-02-IM | UHG | Melissa Chapman | Wellmed | 2728 Loop 337 | New Braunfels, TX |  | VS20116510 3102-1615 7MS02422732 3102-BCDV | 2020-08-18 | 2020-09-02 | 2020-11-30 |  |  |  | BBEC.664087 | SBC | [7 empty] | 10.1.95.141 | 10.1.95.142 | 65441 | 202610 | UHG GLOBAL 150 | 9/29: Rec'd email from Melissa to cancel order - HITS ticket issued. 9/15-9/21: PON 7MS02422732 CNR Customer Not Ready - SITE VISIT - BLDG NOT READY - THE SITE VISIT IS PENDING AS THE BUILDING IS NOT YET READY. 8/18: Order rec'd - ground up construction
New | 50M Port/ 50M Access EaAVPN 1000 Base-LX | NAMM CA767 | UHG | Melissa Chapman | NAMM | 17400 Von Karman Ave. | Irvine, CA |  | VS20115926 3102-1194 3102-BCCZ | 2020-08-25 | 2020-09-23 | 2020-09-23 | 2020-09-24 |  | Y | BBEC.673902 | SBC NEARNET-15 | 13KRGN603959PT | 2020-09-23 | 1 MDF-01 INSIDE BLDG, RACK MT CN3930, PORT-5 |  |  |  | 50 | 10.1.2.9 | 10.1.2.10 | 64513 | 202610 | UHG GLOBAL 150 | 9/28: ORDER COMPLETE 9/15-9/21: Access install scheduled for 9/23 - SBC NEAR NET 8/25: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX606-02-IM | UHG | Melissa Chapman | Wellmed | 17045 Saint Edwards Drive, Suite 302 | Houston, TX |  | VS20121374 3102-0281 3102-BCDW | 2020-09-10 | 2020-09-21 | 2020-09-21 | 2020-09-21 |  | Y | BBEC.664003 | SBC ONNET-5 | 28KRGN750424SW | 2020-09-21 | 3RD FLR STE 302 SERVER CLOSET SLIMBOX |  |  |  | 50 | 10.1.89.189 | 10.1.89.190 | 65185 | 202610 | UHG GLOBAL 150 | 9/22: ORDER COMPLETE 9/15: Access install scheduled for 9/21. 9/10: Order rec'd
New | CANCEL/REISSUE 5M Port/ 10M Access EaAVPN 1000 Base-SX | NJ194-01-IM | UHG | Melissa Chapman | Optum | 7 Broad Ave | Palisades Park, NJ |  | VS20087860 3102-1009 3102-BBZG 3102-BBZH | 2020-06-15 | 2020-06-26 | 2020-09-14 |  |  |  | MLEC.646280 | Verizon South | [7 empty] | 10.45.10.73 | 10.45.10.74 | 65363 | 202610 | UHG GLOBAL 150 | 9/29: Order will need to be resent - USO was cancelled so unable to reissue the PON. Notified Deidre and Melissa. Added to HOT list. 9/16: Per Melissa, New Jersey electrical is in so we can proceed. 9/2: Per Melissa.......The requested electric will be in place no later than 9/14 (Danielle Maiorana - UHG) 8/31: Per Melissa on status, "No word back yet on our side. I’ll follow up again." 8/24: PON will need to be resent. 8/17: CNR AGENT SX8702: AS WE HAVE NOT RECEIVED ANY RESPONSE FROM CUSTOMER, SENDING F/U TPL AND F/U WILL BE ON 08/26/2020. 8/10: Order shows CNR on customer side per LEC (Verizon). 7/24: Sent EUCR to Melissa - end user will need to fill this out and get back with the VZ Engineer (also provided engineer info to UHG). 7/20: Verizon advised CNR - CUSTOMER BLDG/TELCO ROOM NOT READY CKL 2 - VZ: PLEASE CORRECT ERRORS AND RESPOND WITH A SUP TO AVOID CANCELLATION OF YOUR ASR. E/U: CKL2: DANIELLE MAIORA,347 909 1344 ,.PLACE 4 FT X 4 FT PLYWOOD BACKBOARD IN FLOOR 3 TELCO CLOSET. SEE COMPLETE EUCR IN EWPTS 7/14: Melissa forwarded emails indicating site survey was scheduled with Alicia from Verizon for Thursday, 7/16 @ 11:30am. 7/13: Verizon has rejected this order back as "REJECT FOR NON RESPONSIVE CONTACTS." LCON NOT RESPONDING TO OSPE ALICIA.GASTON@ONE.VERIZON.COM. PLEASE CORRECT ERRORS AND RESPOND WITH SUPP. 6/30-7/6: Pending an install date from Verizon South. 6/15: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | UNY24-07-IM | UHG | Melissa Chapman | UnitedHealth Group | One Penn Plaza FL 8 | New York, NY |  | VS20045450 3102-1411 3102-BBSJ | 2020-03-24 | 2020-06-25 | 2020-06-25 | 2020-10-05 |  | Y | IUEC.905505 | ASE LNS | NYKRGN101721TPM | 2020-09-21 | 1 PENN PLAZA 080001.02. POS. 1,2 |  |  |  | 50 | 10.1.85.149 | 10.1.85.150 | 64782 | 202610 | UHG GLOBAL 150 | 10/6: ORDER COMPLETE 10/5: Reached out to Bill Cronin (AM - LEC Field Techs) to see if he could pin down status - showing demarc but order not complete on LEC side. UPDATE FROM ANTHONY REGISTER OPS MGR "We’ll work this in for provisioning today." 9/28: Possible CNR - LEC STATES THAT IT IS AN ACCESS ISSUE. - checked the LEC notes and I am seeing work appears to have been done and a demarc is present, but LEC has not yet completed the PON. 9/21: Access completion not received yet from the LEC. AERO CM#1297170 engaging Carrier Mgmt. 9/14: Fiber work completed as scheduled on 9/10. Access install pulled in from 9/21 to 9/17. 9/8: Construction target completion 9/10 - access install scheduled for 9/21 8/31: Construction target completion 9/10 - PON resent for access install date. 8/28: Construction came back this afternoon and provided us with a 9/10 target completion date for the fiber infrastructure. I would expect access install will be about a week or so after that date. 8/24: Escalating for status of fiber work. Reached out to Becky again for status from OSP team. The 8/17 fiber date is past due and the 8/26 install date is in jeopardy of being missed. 8/18: Becky Duncan (ATT) engaged for update on missed fiber date from yesterday - Advised OSP C&E Fiber PL & SPL, INC Riser Fiber and IC ECDs are all past due and need to get updated accordingly. 8/10-8/17: Fiber work set to complete on 8/17 - Access install scheduled for 8/26. 7/27: Fiber work set to complete on 8/17. Pending access install date (most likely about a week after fiber completes.) 7/21: Reached out to PM Becky Duncan - site visit was showing scheduled for 7/17 but no updates in ASEdb. 7/20: Pending construction site visit details. 7/13: Not seeing any movement on construction side. I've closed out the site ready date in ASEdb to see if that kickstarts things. Pending status. - REACHED OUT TO BECKY DUNCAN (PM) FOR STATUS AS SHE STILL THINKS THIS IS CNR. ADVISED HER PON WAS RESENT ON 6/30 AND WE'RE BEING ADVISED THIS IS NOT CNR. UPDATE: Becky is requesting OSP reach out to the LCON to schedule the SV. 6/30-7/6: PON resent - Covid19 removed per Melissa's request - FOC due back by 7/23. COVID-19 SITE DELAY - S19C 4/20: Per LEC LNS "COVID 19 DELAY" - issued HITS ticket to have S19C applied. 4/14: Order has not yet been jep'd S19C. FOC is still pending and due 4/23. 4/13: Reached out to Construction for update on site visit info - no dates populated yet - possible Covid19 delay. FOC due 4/23. 4/6-4/13: FOC due back by 4/23. 3/24: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | TX057-06-IM | UHG | Melissa Chapman | UHC | 12668 Silicon Drive | San Antonio, TX |  | VS20045448 3102-1421 3102-BBSK | 2020-03-24 | 2020-06-16 | 2020-06-16 | 2020-09-30 |  | Y | IUEC.905885 | ATT SW | 31KRGN654682SW | 2020-10-20 | 1ST FLR; SERVER RM; CIENA 3903X WLMT ATT NTE 1 PORT 2 |  |  |  | 50 | 10.1.85.153 | 10.1.85.154 | 64520 | 202610 | UHG GLOBAL 150 | 9/30: Access install showing completed - pending completion on the LEC side so AT&T can test. ORDER COMPLETE 9/29: CNR - Per LEC: CALLED LCON ANTONIO ARELLAN 210-270-4808 ON ORDER NO ANSWER. DROVE TO SITE,WAS TOLD TO CONTACT 210637553 DAVID GAMEZ, FOR ACCESS. CONTACTED MANAGER ADVISED OF RETURNING JOB UNTIL ACCESS IS ARRANGED WITH NEW LCON. 9/28: Fiber work completed ahead of schedule - Access install showing due today 9/28. 8/17-9/21: Fiber work targeted to complete on 10/9. Access install scheduled for 10/20. 8/10: New CM AERO ticket 1157941 - AS PER LCON DAVID GAMEZ'S CONFIRMATION THE CUSTOMER IS READY FOR THE SITE VISIT. CUSTOMER REQUESTED FOR SV ON 8/12 9:30AM. Confirmed ASEdb (Construction) is showing 8/12 for site visit. 7/27: AERO CM TICKET 1134949 - FOC missed and Carrier Mgmt engaged to find out why. 6/30-7/20: PON resent - Covid19 removed per Melissa's request - FOC due back by 7/23. COVID-19 SITE DELAY - S19C4/27: Per Construction - ACCESS DENIED DUE TO COVID-19 - THEREFORE IWLL WAIT FOR THE END OF THE LOCKDOWN. 4/20: There is mention of permits being required and due in late May - I've reached out to Construction for updates. 4/14: Per Construction notes: RECEIVED AN EMAIL FROM SUSHIL GAUTAM (SUSHIL_GAUTAM@UHC.COM) STATING "THANKS FOR THE CONFIRMATION, PLEASE PROCESS" THIS INDICATES THAT THEY ARE READY FOR SITE VISIT. REMOVED THE JEOPRDY FROM ASEDB AND POSTING CNR RESOLVED, CNR TEAM DIS-ENGAGED. 4/9: "PER AMDOCS ENGINEER: Sent an email to both LCONS LCON: ANTONIO ARELLAN, 2102704808, TONY.ARELLANO@UHC.COM, SECONDARY LCON: MELISSA CHAPMAN 7637442114, MELISSA_R_CHAPMAN@OPTUM.COM , Antonio sent an email to a Brad Neimeyer and Brad has yet to respond". Sending a site visit initial TPL with a f/u as on 04/16/20. 4/6: FOC due back by 4/23. 3/24: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | LA019-01-IM | UHG | Melissa Chapman | People's Health | 712 Westbank Expressway | Westwego, LA |  | VS20077021 3102-1087 7SS03672427 3102-BBYF | 2020-05-26 | ASAP | 2020-08-19 | 2020-09-30 |  | Y | BBEC.687494 | ATT SE | L2KRGN822608SC | 2020-10-01 | 1ST FL TELCO ROOM 1ST FL CUST TELCO WALL MNT |  |  |  | 50 | 10.1.82.157 | 10.1.82.158 | 65380 | 202610 | UHG GLOBAL 150 | 9/30: ORDER COMPLETE 9/28: Access install was rescheduled for Friday 9/25 but no completion notice rec'd yet. Pending escalation. 9/21: Fiber work completed on Friday - access install still showing due 10/1. 6/15-9/14: Construction due to complete fiber work on 9/22. Access install scheduled for 10/1. 6/8: Site visit completed today. Pending a fiber and install date. 5/26: Pending USO's
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX571-02-IM | UHG | Melissa Chapman | Wellmed | 5449 Bear Lane, Suite-308 | Corpus Christi, TX |  | VS20084548 3102-0282 7MS02411871 3102-BBYZ | 2020-06-15 | 2020-07-10 | 2020-09-16 | 2020-10-02 |  | Y | BBEC.664663 | SBC | 34KRGN614218SW | 2020-10-14 | 1 308 IN IT ROOM |  |  |  | 50 | 10.1.82.25 | 10.1.82.26 | 65366 | 202610 | UHG GLOBAL 150 | 10/5: ORDER COMPLETE 6/30-9/28: Construction is showing a 10/8 fiber completion date. Sent Construction/Fiber requirements letter to Melissa. EF offer accepted. Access install scheduled for 10/14. 6/15: Order rec'd
New | HOT ORDER 20M Port/ 50M Access EaAVPN 1000 Base-SX | UVA30-02-IM | UHG | Melissa Chapman |  | 9020 Stony Point Parkway | Richmond, VA |  | VS20024702 3102-0431 3102-BBQY 3102-BBQX | 2020-02-14 | 2020-05-14 | 2020-05-14 | 2020-10-08 |  | Y | BBEC.598689 | NTELOS NETWORK | 10ETTA661769000CFW | 2020-09-18 | BLDG MAIN/FLR 3/ RM MDF. |  |  |  | 1072 | 10.1.86.9 | 10.1.86.10 | 64902 | 202610 | UHG GLOBAL 150 | 10/12: ORDER COMPLETE 10/6: Multiple requests for turn up and the order is still incomplete. Escalated to AM Jane Tansor for assistance. 9/28: Rec'd completion notice from the LEC. Reached out to Marcia Drane (Prov Tech Coach) to have tech complete this plug and play. 9/21: Reached out internally and advised we'll see R80 completion on the PON TODAY. Once that's done I'll push for completion plug and play. 9/21: The LEC advised they sent a completion notice on 9/18. Pending testing completion, demarc info and the OK to turn up. 9/14: John Mackenzie (LEC) advised this is being handled by Carol Lane-Edgar (@ Segra.) I reached out to Carol this morning for an update. - UPDATE FROM CAROL: "I am checking with our internal teams on this and have added David Ready as he is now handling this order. We will provide an update ASAP." 9/9: Updated Melissa via email - pending install date - reached out to John Mackenzie at the LEC for status. 8/28-9/8: PON was resent yesterday 8/27 as site is ready - pending date from LEC. 8/24: Need to update the provisioning team with status of fiber run. 8/17: Per the LEC, access install is delayed. CUSTOMER NEEDS TO RUN FIBER CABLE FROM THE 3RD FLOOR DOWN TO THE BASEMENT TO THE COMMON DEMARK ROOM. 7/7-8/10: LEC provided a 8/13 access install date. 7/1: Missed FOC escalation in IOS - NTELOS NETWORK has not provided FOC. 6/29: FOC was missed on 6/26. Escalation to be sent on Wed 7/1 5/18-6/15: Pending instal date from the LEC Ntelos. FOC due by 6/26. 5/13: Added to HOT order list - This is not VA037 which is how it was labeled on the emails from Melissa. 5/11: Per Martin Hromek (Carrier Mgmt)...confirmed the foc should be released to us tomorrow 5/12. 5/4: Carrier Mgmt Tier 2 engaged and escalating to LEC TO CONFIM IF THE SITEWALK WAS SCHEDULED 4/27: Per Ntelos, they are checking on the availability of equipment within their warehouse which will determine their target date for completion of the work. Carrier Mgmt remains engaged and continuing to push for more frequent updates. 4/28 UPDATE: NTELOS ADVISED THEY ARE CURRENTLY PENDING SCHEDULING OF THE SITEWALK. - I went back to Carrier Mgmt and advised them that Ntelos already indicated completion of a site survey back around 4/15. Carrier Mgmt is pushing back this morning to find out why the sitewalk. 4/20: Carrier Mgmt update: Per the LEC Ntelos Network, "SITE VISIT WAS COMPLETED AND PENDING THE ENGINEERING PACKAGE." 4/14: CARRIER MANAGEMENET TIER II engaged and pushing for FOC. 4/6-4/13: No response from LEC Ntelos. Are there any other LEC's we can use at this site? - 4/7: PER CHRIS, THIS NEEDS A SOLD NOTICE and he's working on that now. No other CLEC's. 3/30: Access Vendor Mgmt engaged (Larry Shearholdt) - 3rd contact to Ntelos, no response yet. 2/25-3/23: Pending access install date from the LEC NTELOS NETWORK. - AERO DESIGN 900254 (R15) - FOC due 4/6 2/14: Order rec'd
New | HOT ORDER 2G Port / 10G Access Ethernet AVPN 1000Base-SX | II757-04-IM | UHG | Melissa Chapman | EXPEDITE COVID WAR ROOM | STTelemedia Data Center (Tata Communications Data Center)Tiruvalluvar Satellite Earth StationNo.226, Red Hills Road, Kallikuppam, Ambattur | Chennai, Tamil Nadu India |  | ISR20060195414 VS20076037 3094-BWDV 3094-BWDW | 2020-04-09 | 2020-08-01 | 2020-09-21 | 2020-09-21 |  | IZYF.102438 | Bharti | 13587769 | 2020-08-10 |  | 10GBaseLR - LC |  |  | 2 | 10.1.85.1 | 10.1.85.2 | 64568 | 202610 | UHG GLOBAL 150 | 10/5: Per Mahesh Vn (PM), port issues are resolved. Complete 9/29: Per Mahesh VN (PM), order completed, but issues turning up port. Ticket is opened 9/21: Bharti access handover received and will proceed with AT&T Spirent Test. 9/14: Bharti confirms the FMS installation is completed and the cross-connect is in progress. Next update: 9/16/2020 9/11: Bharti confirms the internal work commenced yesterday, Sept. 10. AT&T AIM will follow up on Monday for remaining tasks and expected final handover date. Next update: 9/14 9/8: Rack space confirmed by customer; now pending final delivery date from Bharti. Next update: 9/11/2020. 9/4: Rack space confirmed by customer. Pending confirmation of Telco MUX install in customer rack 8/28: TCL advised they have requested space in the customer rack to install a new FMS panel. Customer will then need to work with the datacenter management to complete the cross-connect. Next update: 9/3. 8/25: Per TCL, the datacenter owner advised the existing fiber on the first floor is out of capacity and new cabling will be needed. Pending a date for new cabling installation. Next update: 8/28 8/19: Mahesh Vn (TOM) wrote on 19 Aug 2020 10:37:33: Telco placed the cross connect with DC team and DC team confirmed customer rack not at ground floor. Written to customer and waiting for the floor re-confirmation. 8/17: Bharti confirms their activities are progressing and circuit handover is on track for August 20. Next update: August 20 8/11: Bharti confirms all installation tasks are completed. Fiber stability tests in progress, then final provisioning tasks and tests will be scheduled. Circuit remains on track for handover by next week. Next update: August 14 8/7: Bharti confirms their tasks remain on track for circuit handover during the week of August 17. Next update: August 14 7/28: ***CNR*** Customer has now allocated space at the site, but power is not expected to be ready until end of this week, July 31. Bharti has installed their rack at the site already, and they will schedule remaining tasks after customer's power is ready. Next update: August 4 7/21: ***CNR*** Unchanged; space & power are still not ready. Customer now expects the site to be ready on July 27. Bharti will schedule the equipment installation and advise when a date has been agreed. Next update: July 28 7/14: ***CNR*** Unchanged; space & power are still not ready. Bharti advised they were informed by TCL that site readiness is expected on July 20. Bharti will then arrange another site survey to confirm site is ready, and provide an estimated delivery date. Next update: July 21 7/8: ***CNR*** Unchanged; space & power are still not ready. Bharti continues to follow up with the datacenter, but readiness date has not been provided. Estimated delivery date remains August 10 at this time; subject to change if space & power are not provided in a timely manner. Next update: July 14 7/6: Unchanged; Bharti is working with the datacenter management to ensure space & power are available for this installation. Further feedback is expected from the datacenter later this week. Estimated delivery date remains August 10 at this time; subject to change if space & power are not provided in a timely manner. Next update: July 8 7/2: Unchanged; Bharti is working with the datacenter management to ensure space & power are available for this installation. Estimated delivery date remains August 10 at this time; subject to change if space & power are not provided in a timely manner. Next update: July 7 6/26: Telco got space and power for rack at 7th floor in TCL DC and floor is not completely ready with all required infra to install new MUX. TCL DC team confirmed that all DC readiness works stopped due to lockdown now. Further feedback awaited from Telco by 7/6/2020. Still working with Firm date of 8/10/202 6/9-6/15: Received Firm date of 8/10/2020 from PTT. Working to improve. 6/8: Awaiting Firm Date 6/2: Per PM, Access, port and CIR corrected in ICORE, waiting for CMO to unlock port. Custom 10G access with 2G port 6/1: ISR# received - pending release of order to PTT 4/9: Order rec'd
New | HOT ORDER 50M Port/ 100M Access EaAVPN 1000 Base-LX | C1659-01-IM | UHG | Melissa Chapman | Genesys Colo, Equinix DC12 | 44790 Performance Circle | Ashburn, VA |  | VS20127976 3102-1319 3102-BCFH | 2020-09-25 | ASAP | 2020-10-14 | 2020-10-06 |  | Y | IUEC.621477 | ASE LNS | VAKRGN100175TPM | 2020-10-14 | IBX DC2 FLR 1 CAGE 2140 BAY 0202 ATT L 6 JKS 57/58 |  |  |  | 50 | 10.1.84.93 | 10.1.84.94 | 64602 | 1493527 | FRONMEXSIP | 10/7: ORDER COMPLETE 10/6: Access install scheduled for 10/14. 9/25: Order rec'd - This is a hot order for a new SIP platform for Frontier Medex
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX213-05-IM | UHG | Melissa Chapman | Wellmed | 2821 Lackland Road, Suite 101 | Fort Worth, TX |  | VS20115433 3102-1215 7MS02422329 3102-BCDD | 2020-08-25 | 2020-09-08 | 2020-09-24 | 2020-10-12 |  | Y | BBEC.641169 | SBC ONNET-5 | 14KRGN888949SW | 2020-10-02 | 2CND FLR ELECTRIC ROOM ACROSS FROM NG MACHINES. EXT TO SUITE |  |  |  | 50 | 10.1.84.77 | 10.1.84.78 | 65250 | 202610 | UHG GLOBAL 150 | 10/12: ORDER COMPLETE 10/5: Install was missed - LEC having issues getting in touch with LCON/ALCON - Reached out to Kenneth Feaster (LEC AM) to find out issues, verify LCON/ALCON info. 9/28: Access install scheduled for 10/2. 9/21: Pending confirmation PON was released with new LCON info. 9/16: HITS ticket issued to change LCON to Bonnie Stephenson, 210-986-5282, bstephenson@wellmed.net 9/15: Access install missed - Message Type: CUSTOMER - NO ACCESS PER FIELD TECH NO ACCESS TO SUITE 214 SWITCH SHOULD BE. WENT TO SUITE 300 AND CHECKED IN BUT THEY CAN'T ACCESS 214. NEED A GOOD LCON AND NUMBER. NAME ON ORDER NOT KNOWN BY ANYONE ONSITE AND PERSON WHO ANSWERED 4697766207 SAID WE HAD WRONG NUMBER..NEED CORRECT LCON, NUMBER AND SUITE INFO. LCON on our order is JONATHAN BENSON at 469# above. 8/26: Reissued order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | IA028-02-IM | UHG | Melissa Chapman | Optum/Diplomat | 10607 Aurora Avenue | Urbandale, IA |  | VS20090724 3102-1249 3102-BCBC 3102-BCBD | 2020-07-01 | 2020-07-02 | 2020-09-29 | 2020-10-08 |  | Y | BBEC.674350 | UPN | BBEC674350UPW | 2020-10-07 | 1ST FLOOR, UTN RACK,WALL MOUNTED,SUITE 10627, CISCO ASR 920, PORT 4 |  |  |  | 2 | 10.1.81.249 | 10.1.81.250 | 65354 | 202610 | UHG GLOBAL 150 | 10/12: ORDER COMPLETE 7/7-10/5: The LEC UPN has provided a 10/7/2020 access install date. 7/1: Order rec'd
New | HOT ORDER 50M Port/ 100M Access EaAVPN 1000 Base-LX | C1660-01-IM | UHG | Melissa Chapman | Genesys Colo, Equinix SV5 | 9 Great Oaks Boulevard | San Jose, CA |  | VS20128340 3102-1222 3102-BCFG | 2020-09-25 | ASAP | 2020-10-20 | 2020-10-19 |  | Y | IUEC.617277 | SBC NEARNET-15 | 86KRGN596508PT | 2020-10-20 | IBX SV1 CAGE 1230 CP.0102.1103166 TS 225/226 TAGGD |  |  |  | 50 | 10.1.84.69 | 10.1.84.70 | 64647 | 1493527 | FRONMEXSIP | 10/20: ORDER COMPLETE 10/12-10/19: Access install scheduled for 10/20. 10/6: Pending an install date from SBC/ATT W. 9/25: Order rec'd - urgent with executive visibility.
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX572-02-IM | UHG | Melissa Chapman | Wellmed | 11255 Garland Road Suite 19 | Dallas, TX |  | VS20077272 3102-0956 7SS03605959 3102-BBYB | 2020-05-15 |  | 2020-08-31 | 2020-10-15 |  | Y | BBEC.667449 | SBC | 87KXGS435564UIMN | 2020-10-10 | 1 SUITE PORT 1 TAGGED |  |  |  | 50 | 10.45.10.81 | 10.45.10.82 | 65373 | 202610 | UHG GLOBAL 150 | 10/19: ORDER COMPLETE 10/13: Customer sent pics of demarc room - reached out to Anubhav Dasgupta (WIPRO) to escalate back to the LEC for a date. Updated notes in GRETA on PON# 7MS02409038 (SHERRY GREEN (WELLMED) ADVISED SUITE AND IT ROOM ARE ACCESSIBLE AND READY FOR INSTALL. ANDREW ROSALES <AROSALES@WELLMED.NET) ADVISED THERE IS NO COVID RELATED DELAYS ON THEIR END AT ALL AND THEY HAVE NO IDEA WHY THE DELAY. PLEASE DISPATCH ON EARLIEST DATE POSSIBLE. 10/12: LEC came back again with CUSTOMER NOT READY. CUSTOMER SUITE IS NOT READY DUE TO COVID DELAY. SUITE 1130 IS UNDER CONSTRUCTION, UNSAFE. 10/6: Install scheduled for 10/10. 10/5: CNR CHAT ROOM - requested C01B removal so PON can be resent. UPDATE: CODING REMOVED - PON RESENT 9/28: Access denied to building per LEC. - The 9/24 install date was missed so I've issued an IOS ticket on the miss and also looking into the possible CNR access issue. 9/21: Access install confirmed for 9/24. 9/14: LEC updated us on Friday that access install has been rescheduled for 9/24. 9/3: Sent revised COI to Melissa. Need more info on the ACCESS AND INDEMNITY AGREEMENT needing to be signed. I'm showing PON 7MS02409038 on track for 9/28. 8/31: Sent COI to Melissa. Access install set for 9/28. 8/28: Issued COI request per Melissa's request. 8/17-8/24: Same dates as below - on track. Issued DDF ticket 202008170019 to remove old 2019 PON from order (design issue that won't affect dates.) 7/27-8/10: Fiber work (including NTE install) is set for 9/17 - access install date came back as 9/28. 7/13-7/20: So for this Dallas order, I can confirm that the Suite has been changed on the USO to Suite 1130 as requested. The PON 7MS02409038 is correct and is currently in the hands of SBC/ATT SW. The customer prem ready date is showing 8/21 and the fiber completion date is 9/17. Right now we’re awaiting an install date on the access but will probably come back as late September based on the dates we have from Construction. Please note that they accepted the EF offer so AT&T Construction will be completing the site requirements. 6/29: Suite 1130 is correct per Melissa........new PON HWS03866657 issued 6/23 with the GETO field corrected. PER THE LEC/CTL PM (BILL WINTERS @ 602-325-0563) " THIS LOCATION WOULD QUALIFY FOR “SITE READY” PROCESS. WE WOULD NEED A SUP TO THE GETO FIELD (F).". IF WE CAN SUPP THE PON/ASR, THIS WILL THEN HAVE THE LEC/CTL 6/15: Construction notes: Added CNR Reason Bldg Mgmt. Will need authorization from property manager to core drill into building, and for common power use for proposed Ciena 3931 EMT placement. UPDATE: SITE NEEDS TO BE CNR'D FOR INCORRECT ADDRESS ONLY. SUB ADDRESS SHOULD BE: BUILDING 11 SUITE 1130. EACH BUILDING AT ADDRESS HAS SEPARATE MPOE/DMARC. NEW CUSTOMER CLLI NEEDS TO BE ASSIGNED FOR BUILDING 11. SO I HAVE RAISED A TICKET IN HITS WITH TICKET NO CTH/1174960062. HENCE MARKING THIS TICKET AS NOT CNR G15A. 6/8: Site survey scheduled for 6/9. 5/19: Pending USO's
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX576-02-IM | UHG | Melissa Chapman | Wellmed | 1517 S McColl Rd | Edinburg, TX |  | VS20093736 3102-1575 7WS03869646 3102-BCBG | 2020-06-23 | 2020-07-09 | 2020-10-05 | 2020-10-19 |  | Y | BBEC.633610 | SBC | 38KRGN614081SW | 2020-10-19 | 1ST FLOOR MDF TELCO BB FIBER JACK. MM/SC TAGGED |  |  |  | 50 | 10.1.92.82 | 10.1.92.81 | 65443 | 202610 | UHG GLOBAL 150 | 10/20: ORDER COMPLETE 10/13: Access install has been rescheduled for 10/19. 10/5-10/12: Fiber work is showing complete however delay per LEC ---- LEC UPDATE: CUSTOMER SITE NOT READY - BUILDING IS NOT READY STILL UNDER CONSTRUCTION. 8/17-9/28: Fiber work scheduled for 9/30. Access install scheduled for 10/9. 8/11: Rec'd emails with pics of MDF room construction work that has been completed so far. I've sent this off to the OSP Design Engineer Joel Rodriquez. 7/20-8/10: CNR - Building Not Ready - Per Construction, NEW BUILDING, OUTER SHELL OF BUILDING COMPLETE, INSIDE OF BUILDING IS INCOMPLETE, HAS NO WALLS, NO FLOORS ,NO ELECTRICAL WIRING, NO CEILING, NO PLUMBING CONSTRUCTION NEEDS TO BE COMPLETED, ALSO, CUSTOMER WILL HAVE A COMMUNICATION ROOM (MDF ROOM) AND WILL BE PLACING BACKBOARD, GROUND, POWER AND CONDUIT DURING COMPLETION OF CONSTRUCTION. THEREFORE THIS IS NOT AN EF OFFER. 7/14: Pending install date from ATT SW. 7/7: Reached out to Clyde to verify if he processed this order. 6/23: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | IL141-02-IM | UHG | Melissa Chapman | Diplomat | 1370 E Busch Parkway | Buffalo Grove, IL |  | VS20105788 3102-1610 7CS04523925 3102-BCCD | 2020-08-04 | 2020-08-14 | 2020-08-14 | 2020-10-13 |  | Y | BBEC.641358 | SBC ONNET-5 | KRGN127442LB | 2020-08-14 | 1ST FLR,NTWK RM,WALLMOUNT HANDOFF |  |  |  | 50 | 10.1.86.145 | 10.1.86.146 | 65427 | 202610 | UHG GLOBAL 150 | 10/14: ORDER COMPLETE 10/12: Issue appears to be a wiring problem on customer end - PER THE LEC, THE LCON WAS SUPPOSE TO INSTALL A 6 STRAND MULTI MODE FIBER BUT ACTUALLY ONLY INSTALLED A 2 STRAND MULTI MODE FIBER. THE CUSTOMER HAS ORDERED TWO UNI ASE CKTS. ONLY ONE CAN BE INSTALLED WITH THE AMOUNT OF FIBER THE LCON HAD INSTALLED. 10/6: Construction update: YOUR ORDER IS BEING DELAYED DUE TO AN INSIDE WIRING JOB THAT REQUIRES A VENDOR TO COMPLETE THE WORK. THIS JOB SHOULD COMPLETE WITHIN 10 BUSINESS DAYS. 10/5: Fiber job still needed at the site - Construction is being re-engaged for Fiber Rework request - AS PER THE LATEST UPDATE RECEIVED FROM PROVISIONING TEAM, REWORK IS REQUIRED FOR THIS ORDER. ESCALATED PROVISIONING TEAM TO OPEN A REWORK IN ASEDB 9/28: Carrier Mgmt Tier II engaged on missed install. Pending status. 9/21: FOLLOWED UP WITH LCON IN ORDER TO GET AN UPDATED STATUS REGARDING INSIDE WIRING COMPLETION,AS PER LCON,WAITING FOR TECHNICIAN TO CONFIRM THAT THIS NEEDS WIRING AND SEND US THE FORM.MY NEXT - F/U 9/23/2020 9/11: Per Customer LCON: "OUR TECH IS MEETING WITH THE MAINTENANCE SUPERVISOR, GARY, AT 10AM TOMORROW TO DETERMINE AN APPROVED PATH." Next follow up 9/15. 9/8: Latest status from Provisioning: "CONTACTED LCON IN ORDER TO GET AN UPDATED STATUS REGARDING INSIDE WIRING COMPLETION.MY NEXT - F/U 9/9/2020" 8/31: Latest status from Provisioning: "CONTACTED LCON IN ORDER TO GET AN UPDATED STATUS REGARDING INSIDE WIRING COMPLETION.MY NEXT - F/U 9/2/2020" 8/24: Pending completion of inside wiring job. 8/17: Access install delayed - AERO 1168965:YOUR ORDER IS BEING DELAYED DUE TO AN INSIDE WIRING JOB THAT REQUIRES A VENDOR TO COMPLETE THE WORK. THIS JOB SHOULD COMPLETE WITHIN 10 BUSINESS DAYS. 8/10: Access install scheduled for 8/14. 8/4: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL443-02-IM | UHG | Melissa Chapman | Wellmed | 621 W. Brandon Blvd. | Brandon, FL |  | VS20115826 3102-1223 3102-BCDG 3102-BCDF | 2020-08-28 | 2020-09-01 | 2020-11-27 | 2020-10-15 |  | Y | BBEC.670695 | Frontier-CTF | 65KRGN461657FTNC | 2020-10-23 | SECOND FLR SERVER AREA RAD 203 PORT 6 TGGD WITH CKT ID ON ELECTRICAL HANDOFF |  |  |  | 2 | 10.1.88.181 | 10.1.88.182 | 64718 | 202610 | UHG GLOBAL 150 | 10/19: ORDER COMPLETE - Please check demarc and handoff. 9/15-10/12: LEC Frontier provided a 10/23 install date. 8/28: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX607-02-IM | UHG | Melissa Chapman | Wellmed | 11920 Astoria Blvd, Ste 280 | Houston, TX |  | VS20126007 3102-1097 3102-BCDZ | 2020-09-21 |  | 2020-12-21 | 2020-10-19 |  | Y | BBEC.633033 | SBC | 28KRGN750501SW | 2020-10-05 | 2ND ,280,INSIDE SERVER CLOSET IN SLIMBOX |  |  |  | 50 | 10.1.94.29 | 10.1.94.30 | 64911 | 202610 | UHG GLOBAL 150 | 10/20: ORDER COMPLETE 10/19: Construction completed ahead of schedule. PON was resent to the LEC to request new install date for access. 10/12: CONSTRUCTION AND ENGINEERING FIBER PLACING AND SPLICING SCHEDULED FOR 10/30/2020 10/6: Access install was missed - per LEC: NO AVAILABLE FIBER FACILITIES BETWEEN TWO BUILDINGS..AN ASE DATABASE ESCALATION HAS BEEN SUBMITTED.. 9/29: Access install scheduled for 10/5. 9/17: Order rec'd
New | CANCELLED/REISSUED 20M Port/ 50M Access EaAVPN 1000 Base-LX | C1661-02-IM | UHG | Melissa Chapman | Rose International | 4580 West Post Road | Las Vegas, NV |  |  | 2020-10-12 | [14 empty] | 10.191.22.225 | 10.191.22.226 | 65402 | 202610 | UHG GLOBAL 150 | 10/21: Replaced with C1661-04-IM - 50M/100M Port 10/15: Per John Sergot: We will need to cancel this request. We have received a change in requirements and will be submitting a new order. 10/12: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX597-02-IM | UHG | Melissa Chapman | Wellmed | 1303 Mccullough Ave Ste 135 | San Antonio, TX |  | VS20122636 3102-0732 3102-BCDY | 2020-09-14 | 2020-09-23 | 2020-09-23 | 2020-10-22 |  | Y | BBEC.660617 | AT&T SOUTHWEST ONNET-5 | 31KRGN655034SW | 2020-10-22 | 2ND,COMM ROOM,2ND FLOOR COMM ROOM NEAR 3930 |  |  |  | 50 | 10.1.89.81 | 10.1.89.82 | 65367 | 202610 | UHG GLOBAL 150 | 10/26: ORDER COMPLETE 10/19: Access install scheduled for 10/22. 10/13: Customer advised All conduit has been placed and extended. CNR agent confirmed The Customer Not Ready hold on this order has been removed. We have raised a request to schedule the installation. 10/12: PON will need to be resent once site is ready - Need UHG/Wellmed to confirm site readiness. 9/28: PER LEC TECH, CUSTOMER PREM NOT READY FOR INSTALL. MDF RM IN SUITE IN PROCESS OF BEING BUILT AND MULTI MODE FIBER BEING PLACED BY VENDOR. MDF IN SUITE NOT READY. CUSTOMER IS GETTING CABLE VENDOR TO RUN FIBER TO MDF AND MECHANICAL CLOSET. 9/22: Access install scheduled for tomorrow 9/23. 9/14: Order rec'd - Melissa advised UHG missed sending this to AT&T in July and it needs to be added to hot list.
New | HOT LIST 10M Port/ 50M Access EaAVPN 1000 Base-SX | LA040-01-IM | UHG | Melissa Chapman | People's Health | 1215 North Broad St. | New Orleans, LA |  | VS20078138 3102-1607 7SS03672916 3102-BBYK | 2020-05-27 |  | 2020-08-21 | 2020-10-27 |  | Y | BBEC.664760 | ATT SE | L2KRGN822610SC | 2020-10-01 | 1,IT,FIRST FLOOR IT ROOM ON BACKBOARD |  |  |  | 50 | 10.1.82.185 | 10.1.82.186 | 65385 | 202610 | UHG GLOBAL 150 | 10/27: ADDED TO HOT LIST - ORDER COMPLETED 10/26: Construction working fiber issues - 10/23 PER CONSTRUCTION & ENGINEERING - "BIC ADVISED THE SCOPE OF THE JOB CALLED FOR OF13, 58-60 TO BE ACTIVATED TO THE PFP AND FOR OF13, 59-60 TO BE USED FOR THE PASS-THRU FIBERS. THE PROBLEM IS WITH THE F1. SENT 2ND REQUEST TO CONSTR MGR (JP), PLEASE ADVISE WHEN ISSUE WILL BE RESOLVED." PENDING RESPONSE FROM CONSTRUCTION MANAGER 10/19: Fiber issues requiring Construction to reengage. Working through the issues. 10/5-10/12: Per LEC, FIBER ISSUE CAUSING DELAY IN TURNING CIRCUIT UP. Pending updates from the field on ETA for completion. FIBER ISSUE CAUSING DELAY IN TURNING CIRCUIT UP. 9/28: Access install scheduled for 10/1. 9/22: Per Heather Taylor email, conduit work is complete. CNR coding was removed from the order - PON sent back out today requesting redispatch date. 9/21: Per UHG, the conduit work will be completed on Tuesday, September 22nd 9/14: Reached out to Heather/Melissa for update on conduit work. -- Per Heather, "Dawn (Optum FM for Peoples Health) has been working to find a willing GC. She should have a commitment from one of the vendors today." 9/8: Need update from Heather on the conduit work status. 8/28: Email to Melissa/Heather - "On the Construction side for the fiber work, the EF offer was previously accepted on this order and that work completed back in July. The conduit work needed by the customer is a separate issue that was brought to us by the LEC ACCESS Technician so that is not fiber/infrastructure related. That being said, it’s not something covered under an ASE Entrance Facility offer." 8/18: Provided scope of work to Melissa and Heather Taylor. Pending update. 8/18: Notes indicate access install is on hold pending completion of the conduit work by the customer. Conduit needs to be extended to outside of building with weather head and pull string. LEC advised customer was made aware. LCON CHARLENE DUKE, 504 620-2733 ---- REACHED OUT TO LEC TECH ERIC CAPDEVILLE AND HIS BACKUP AM FOR SPECS ON CONDUIT. 8/14-8/17: The LEC just advised yesterday 8/13 that there are additional issues needing to be addressed by the end user: CUSTOMER PREM NOT READY/CONDUIT NEEDS TO BE EXTENDED TO OUTSIDE OF BUILDING WITH WEATHER HEAD AND PULL STRING. 8/11: Pending update from LEC - GRETA showing incomplete but no notes from tech. 8/10: Access install DUE TODAY 7/28: Reached out for update from Construction/TFS regarding fiber install from terminal to building. 7/24: I have taken this issue back to the BIC ENGINEER and he advised that Construction’s fiber work is complete up to the terminal OUTSIDE the building. He said that TFS is responsible for getting fiber from the terminal to the customer’s building. That’s why the LEC Access install tech rejected this back………because TFS has not yet installed the fiber to the building nor have they installed the Ciena device. Escalating this to someone in TFS and see if they can engage and get their piece of the fiber work completed. 7/20: PER LEC: CUSTOMER SITE NOT READY - NO FIBER IN BUILDING --- ORDER IS ON HOLD DUE TO CUSTOMER'S PREMISE NOT READY. NO FIBER IN BUILDING YET/NO CIENNA TO INSTALL SFP/CIRCUIT CUSTOMER SITE NO READY/NO FIBER IN BUILDING. ENGAGING CUSTOMER NOT READY TEAM. 7/13: Access install improved to 7/14. 7/6: Fiber work completed well ahead of schedule. Pending date improvement on accesss. Still showing 8/28. 6/15-6/29: Construction fiber work scheduled to complete 8/19. Access install scheduled for 8/28. 6/8: Site visit scheduled for 6/10. 5/27: Pending USO's
| 100M Port/200M Access EaAVPN 1000Base-SX | MN108-02-IM | UHG | Melissa Chapman | Health Markets | 23505 Smithtown Road | Excelsior, MN |  | VS19172515 3102-0317 3102-BBMN 3102-BBMM | 2019-10-18 | 2020-01-23 | TBD | 2020-10-26 |  | Y | BKEC.950112 | Zayo | ETYX263332ZYO | 2020-02-28 | FL: 2/RM: Telco/RR: 1/MP: 38 Accedian NID Port: 1 | LC Connector Multimode |  |  | 100 | 10.45.10.121 | 10.45.10.122 | 65421 | 202610 | UHG GLOBAL 150 | 10/27: ORDER COMPLETE 10/26: SPOKE TO ANDY/ ZAYO. CONFIRMS CORRECT MM SFP WAS INSTALLED 10/26: Working to escalate completion of Zayo's handoff correction. Requested assistance from Cedrick Scott (Provisioning AM-Tech) 10/20: Emailed Melissa the completion notice from Zayo indicating they were supposed to install MMF. Advised that once the LEC fixes the handoff this should be a quick turnaround for completion. Waiting on Melissa to verify her side did the extensions correctly as MMF. 10/19: Delay is due to handoff issue on the LEC Zayo side. The LEC installed a Singlemode fiber handoff instead of the MMF handoff we requested. LEC arranging redispatch with the LCON to gain access to the cage in the data center. Good news is the circuit tested good outside of the handoff issue. 10/12: Escalated to Marcia Drane (Cedrick Scott's backup) for status on closing this out complete 10/5: Escalated to Cedrick Scott (AM - Provisioning) to have this order completed out. 9/28: Dani (Zayo) advised access install is complete and notification of completion sent to AT&T. Advised Dani we're still not seeing Zayo's completion and I asked her to resend it to me OR to AT&T Provisioning. _ UPDATE: Demarc provided. Pending testing completion and the OK to turn up. 9/22: Reached out to Dani (Zayo) this morning for status on PON 7CS04351580 9/14-9/21: PON was resent to the LEC on 9/9. Pending confirmation of install date. FOC is due back by 10/13. 9/8: Sent HITS ticket for assistance in releasing PON back to the LEC. Request ID: 1249838917 9/1: Per Melissa's email, Zayo extension is completed. 7/28: Melissa reached out to Tony Turner and Brandon Little for status of fiber extensions. Pending update. 7/7-7/27: Melissa confirmed they have the LOA and site is running fiber extensions according to that LOA. 6/29-7/6: PON was resent to the LEC Zayo on 6/19 and "target" date for install is 7/20. Working to confirm this with Zayo. 6/15: Issued IOS ticket to have PON resent and redispatched. Melissa advised site completed their extension work. 5/26-6/8: Pending confirmation that extension work is completed so PON can be supp'd. 5/18: Per Tony Turner (Optum) extension work is scheduled to be completed Thursday 5/21. CNR agent Joe Scrudato will supp PON when ready. 5/11: LEC Zayo advised the delays are due to CNR - "THEY DON'T KNOW WHERE TO INSTALL CIRCUIT" (the "THEY" part was directed to the customer not being aware of where to install the circuit.) 5/4: Multiple attempts to contact ZAYO have gone unanswered. Issued AERO ticket 989663 to Carrier Management to assistance in escalating. 4/20-4/27: Pending update from LEC from PON supp on 4/14. Targeting possible date of 5/5. 4/14: PON supp'd today for redispatch 4/13: Follow up - AERO ticket 958165 (Design) to have Zayo install access - should not need customer to run extensions BEFORE access is installed. 4/6: Need status of customer inside wiring extensions. LEC Zayo indicated this is CNR and they are pending an update from the customer that they've completed their extensions. 4/1: Carrier Mgmt engaged - DROPPED A MAIL TO ACCESS PROVIDER REGARDING THE ECD DATE OF THE PON # 7CS04351580. THUS NEED TO DO ANOTHER FOLLOW UP ON THIS CASE .SD993W CM OOF TIER 1 . TICKET # 941775 3/31: ESCALATED TO JAHANARA KHAN (Re: AERO ticket #928962) - showing PON past due from 3/29 - no updates from LEC. 3/30: The LEC Zayo confirmed last week that install was moved to 3/29, however that was a weekend (Sunday) and I don't show install was completed. Pushing back to provisioning. Can UHG confirm if any site access issues? 3/23: Pushing for update from LEC Zayo. AERO TICKET #928962 3/2-3/16: CNR resolved per Zayo. Pending update on LEC date. PON resent on 2/28 and pending a date. 2/25: LEC sent CNR notice - PENDING CUSTOMER ACCESS FOR US TO INSTALL THE FIBER/CIRCUIT PENDING CUSTOMER EXTENSION FROM ZAYO DEMARK TO CUSTOMER RACK 2/24: LEC access install pending earlier completion 12/3-2/17: Access install scheduled for 2/28/20. 10/28-11/25: Pending install date from LEC Zayo - FOC due 12/4. 10/18: Order rec'd
New | 10M Port/ 100M Access EaAVPN 1000 Base-SX | NV064-07-IM | UHG | Melissa Chapman | Optum | 2210 E. Calvada | Pahrump, NV |  | VS20102849 3102-1578 7WSC3877380 3102-BCBV 3102-BCBW | 2020-07-31 | 2020-07-31 | 2020-12-16 | 2020-10-22 |  | Y | IUEC.940725 | Cox Communications Valley Electric | 33KFGX002157COXC | 2020-10-22 | 1ST FLR / DATA RM / ACCEDIAN NID / OPTICAL PORT 3 / TAGGED TESTED WITH COX TECH, HE WAS ABLE TO VERIFY MY MAC OUT AT THE CUST'S NID. DEMARC: 2ND FLR VZ ROOM DATACENTER RR203.03 CANOGA USER PORT. |  |  |  | 2 | 10.1.85.137 | 10.1.85.138 | 65144 | 202610 | UHG GLOBAL 150 | 10/22: Showing multiple demarc locations - see column S. Order complete. 10/19: New LCON changed on the order.......LEC Cox has rescheduled access install for 11/12. 10/12: LCON changed on order - pending FOC on access PON. 10/6: HITS ticket was processed to change LCON to Hernand Dela Cuesta but it has not resolved in ALL systems (mainly, SOTS) yet. Scheduled to hear back today on getting it loaded into SOTS. From there PON will be resent once resolved. HITS TICKET 1265233404 10/5: PON was resent on 10/2 and the LEC immediatedly CNR'd it again.........said POC IS UNRESPONSIVE. Need to verify that LCON KIMBERLY STRICKLER (702-243-8545, KIMBERLY.STRICKLER@OPTUM.COM is correct LCON. We have Melissa as the ALCON. 10/2: Issued AERO Design ticket 1347103 for R15 on PON - AERO TOOL HAS BEEN USED TO SUP THE ORDER FOR SITE SURVEY. CNR ISSUE HAS BEEN RESOLVED. CNR TEAM DISENGAGED 9/29: Rec'd request from Melissa - Please change the LCON to Hernand Dela Cuesta, 702-335-5978, hernand.delacuesta@optum.com. Please have PON supp'd to the LEC once LCON is changed. - HITS TICKET ISSUED TO CHANGE LCON 9/28: Carrier Mgmt reached out to LEC and advised PON IS PENDING CUSTOMER ALLOWING ACCESS. Need to resolve CNR - Carrier Mgmt disengaged. 8/24-9/21: Pending install date on PON 7WSC3877380 - FOC due back by 9/23. 8/17: DESIGN ISSUE - Because this is Cox, a different LSO required to drive it to them. Per Provisioning FOR COX THE ORDER WILL NEED A DIFFERENT LSO. I CREATED HITS TICKET 1225897979 TO CORRECT THE LSO. 8/10: Pending an install date from LEC Cox. Check PON that was showing cancelled due to LSO issue. 7/21: Added to sheet - pending USO's
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX599-02-IM | UHG | Melissa Chapman | Wellmed | 2138 N. Josey Lane, Suite 102 | Carrollton, TX |  | VS20116417 3102-1301 HMS02424370 3102-BCDP 3102-BCDN | 2020-08-26 | 2020-09-02 | 2020-11-30 | 2020-10-28 |  | Y | BBEC.673883 | Time Warner Cable | 97L1XX815590TWCC | 2021-01-12 | 1ST FLOOR, BACK ROOM, WALL MOUNTED |  |  |  | 70 | 10.1.92.5 | 10.1.92.6 | 64721 | 202610 | UHG GLOBAL 150 | 10/28: Added to SDM WWR sheet - UPDATE: ORDER COMPLETE 10/26-10/27: Received R84 access completion notice from the LEC. Pending testing completion and the OK to turn up. Due date is pushed out to January so I'll add this to our WWR (WORKS WHEN READY) sheet and see if we can get this done sooner. 9/28-10/19: Access install scheduled for 1/12/2021. 9/2-9/21: Pending access install date from LEC Time Warner. FOC due back by 10/19. 8/26: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX600-02-IM | UHG | Melissa Chapman | Wellmed | 2822 North Belt Line Rd Suite 200 | Sunnyvale, TX |  | VS20113917 3102-1151 3102-BCCX | 2020-08-20 | 2020-08-27 | 2020-11-23 | 2020-10-28 |  | Y | BBEC.666732 | SBC | 14KRGN888925SW | 2020-10-22 | 1ST 200 1ST FLR SERVER RM. BB WALL MOUNTED |  |  |  | 50 | 10.1.92.89 | 10.1.92.90 | 64899 | 202610 | UHG GLOBAL 150 | 10/29: ORDER COMPLETE 10/27: Issued IOS escalation for missed install on 10/22. Carrier Mgmt also remains engaged (ticket 1432513) - pushing for status and ETA for access delivery. 10/26: Carrier Mgmt engaged on missed install - AERO_CM#1426501. 10/13-10/19: Access install scheduled for 10/22. 10/12: No dispatch has taken place so I had the CNR team remove any CNR coding on the CKL (OCO2) and had them resend the PON today to the LEC in an attempt to secure a firm install date. 10/5: LEC system is showing a dispatch request with a 10/8 target completion. 9/26: Emmanuel Udoji responded - "The site is ready for installation. The ATT tech must contact me to schedule site access before the installation. This is a medical facility and not just a regular business place. Contact #: 214-707-6875" 9/23: Added to HOT list - LEC CNR'd this again today - asked Melissa to verify the LCON/ALCON info so I can have CNR removed and PON resent. 9/21: Escalated to 2nd Level CNR group (Prama Deb) for status of PON. 9/15: Received email from Melissa that site is ready - rec'd forwarded email from LCON Emmanuel Udoji that he will allow access. Sent email to the CNR Agent Manasi Parida to have CNR coding removed from order and supp for redispatch. 9/14: AERO 1266814: WE MISSED DUE DATE AS CUSTOMER IS NOT READY FOR INSTALL AT THIS TIME. AS PER LOCAL CONTACT -THEY JUST TOOK OVER THIS LOCATION AND DO NOT WANT ANYTHING AT THIS TIME.PLEASE SUPPLEMENT THE ORDER FOR NEW DUE DATE.ENGAGING CUSTOMER NOT READY TEAM - F/U 1/1/2021 8/31-9/8: Access install scheduled for 9/8. 8/20: Order rec'd
New | 1G Port/ 1G Access EaAVPN 1000 Base-LX | NV184-01-IM | UHG | Melissa Chapman | Optum Tech | 3330 E Loan Mountain Road North | Las Vegas, NV |  | VS20116511 3102-1613 3102-BCDQ 3102-BCDR | 2020-08-19 | 2020-09-02 | 2020-11-30 | 2020-10-28 |  | Y | IZEC.663322 | Cox Communications | 33KFGX002164COXC | 2020-10-08 | 1ST FLR ROOM MMR-A THE NID IS AN ASYDIAN THEN FIBER TO A PATCH PANEL PORT #3 |  |  |  | 50 | 10.1.89.117 | 10.1.89.118 | 65355 | 202610 | UHG GLOBAL 150 | 11/2: ORDER COMPLETE 10/28: Added to SDM WWR Sheet 10/26-10/27: Received R84 access completion notice from the LEC COX. Pending testing completion and the OK to turn up. 10/5-10/19: Cox pushed out the install date to 10/20. No reason provided. Order dates still fall within overall timeframe (Overall due date remains at 11/30.) 9/15-9/28: LEC Cox Communications provided a 10/8 access install date. 8/19: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | FL432-02-IM | UHG | Melissa Chapman | UHG / Diplomat | 15471 SW 12th St Bay 207 of Bldg B | Sunrise, FL |  | VS20135715 3102-0363 3102-BCFS | 2020-10-07 | 2020-10-23 | 2020-10-23 | 2020-10-31 |  | Y | BBEC.666358 | ATT SE | 60KRGN766124SB | 2020-10-23 | 1 SERVER RM SLIM BOX MM FIBER HANDOFF GGED |  |  |  | 50 | 10.1.94.213 | 10.1.94.214 | 65220 | 202610 | UHG GLOBAL 150 | 11/2; ORDER COMPLETE 10/27: Carrier Mgmt engaged - CM T2 ACCESS AERO 1429512- YOUR ORDER IS BEING DELAYED DUE TO AN INSIDE WIRING JOB THAT REQUIRES A VENDOR TO COMPLETE THE WORK. THIS JOB SHOULD COMPLETE WITHIN 10 BUSINESS DAYS. - Checked LEC notes and they indicated "CCLCON ASE HOF RECEIVED AND SENT TO VENDOR. REVIEW LATER FOR SITE SURVEY DATE." "CCLCON" is the AT&T group handling the inside wiring issues....they've sent the hand off form to our vendor to get the conduit issue fixed. 10/26: LEC advised there are conduit issues - CONDUIT WON'T FISH - TRIED 3 TIMES - BOTH WAYS GETTING STUCK OVER 250FT - NO STRING - BLUESTREAM PULLED OUR STRING OUT. 10/20: Access install scheduled for 10/23. 10/7: Order rec'd
New | 200M Port/ 400M Access EaAVPN 1000 Base-SX | TX591-02-IM | UHG | Melissa Chapman | Wellmed | 7355 Barlite Blvd. Ste 301 | San Antonio, TX |  | VS20100019 3102-1299 HMS02418595 3102-BCBS | 2020-07-21 | 2020-07-31 | 2020-07-31 | 2020-11-06 |  | Y | BLEC.994725 | SBC ONNET-5 | 31KRGN654936SW | 2020-10-29 | 1ST FLR,BLDG 3,1ST FLR SVR RM/WALL |  |  |  | 50 | 10.1.87.21 | 10.1.87.22 | 64548 | 202610 | UHG GLOBAL 150 | 11/9: ORDER COMPLETE 11/2: Pending access install completion - per LEC JOB ID 114285014 SHOWS ASSIGNED TO I/M TECH JG3613 FOR DISPATCH but no eta. 10/26: Access install scheduled for 10/29. 10/20: Shawna Malone (Wellmed) confirmed via email this morning that the conduit is in place. Pending CNR removal on USO by CNR AGENT ANANYA MAJUMDER and resending of the PON to the LEC. 10/13: Per customer (Christian Romero), "ATT is onsite splicing the cable and getting ready to install CPE. I will send confirmation once complete, but all conduit is completed and the new fiber has already been run from mdf back to the pole" 9/29-10/12: CNR NTE CUSTOM WORK ORDER REQUESTED came back from Construction - looked into this further and Construction advised IT IS A REQUIREMENT ISSUE - CUSTOMER NEEDS TO PROVIDE CONDUIT ON THE SITE. We need to find out from the site when they expect the conduit work to be completed so we can re-engage Construction to complete fiber work. SITE REQUIRES PATH/PWR/GRD/SPACE 9/21: ORDER IS ON HOLD AS CUSTOMER WANTS CUSTOMER WORK ORDER (CWO) PROJECT PRIOR TO THIS ORDER AND (CWO) CUSTOMER WORK ORDER CHARGES ARE PENDING FROM CUSTOMER SIDE WHICH THEY HAVE TO PAY.PLEASE SUPPLEMENT THE ORDER FOR A NEW DUE DATE.ENGAGING CUSTOMER NOT READY TEAM. 8/31-9/14: Fiber work due to complete on 9/17. 8/24: Site visit for PON HMS02418595 scheduled for 8/25. 8/18: LEC sent update - access install missed - NO CIENA IN PLACE. Pending resolution date. 8/17: Pending confirmation from Construction on dates and whether Ciena equipment is still an issue as same issue popped up on line 44. 8/10: Access install is rescheduled for 8/14. The old PON HMS02417004 was cancelled after LEC spoke with the LCON -- customer (LCON Christian) advised requirements changed because the ATT equipment in the building was removed. LCON wanted ATT to install the fiber terminal into the MDF of the building. New PON HMS02418595 is now showing the 8/14 install date. 7/28: ON-NET - Access install due to compete 7/31. 7/21: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | ULA06-08-IM | UHG | Melissa Chapman | UHC | 8550 United Plaza Blvd | Baton Rouge, LA |  | VS20139079 3102-0824 3102-BCFY | 2020-10-14 | 2020-11-12 | 2020-11-19 | 2020-11-03 |  | Y | BBEC.673515 | ATT SE NEARNET-15 | L0KRGN401202SC | 2020-11-03 | 4TH SERVER RM |  |  |  | 50 | 10.45.10.157 | 10.45.10.158 | 65190 | 202610 | UHG GLOBAL 150 | 11/4: ORDER COMPLETE 10/27-11/2: Access install scheduled for 11/3 (ATT SE - NEARNET) 10/14: Order rec'd
New | REWORK 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX601-02-IM | UHG | Melissa Chapman | Wellmed | 3228 Interstate 30, STE 200 | Mesquite, TX |  | VS20111490 3102-1124 7MS02421010 3102-BCCQ | 2020-08-19 | 2020-08-28 | ASAP | 2020-09-23 |  | Y | BBEC.686909 | SBC ONNET-5 | 14KRGN889024SW | 2020-09-22 | 1ST FLR SERVER RM WALL MOUNT ON BB TAGGED (14KRGN889024SW) |  |  |  | 50 | 10.1.95.217 | 10.1.95.218 | 65150 | 202610 | UHG GLOBAL 150 | 11/4: I just confirmed with Codie Bueckner (AT&T) that his tech went out to the site yesterday evening and completed the extension. He confirmed that the demarc is now located in the IT Room the customer requested. Sent confirmation to Melissa and Emmanuel. 11/3: Requested update from Codie Bueckner (AT&T) on rework.UPDATE SENT TO EMMANUEL/MELISSA: I’ve received word from Codie Bueckner (AT&T) that he has a technician that is working on completing another job right now, but once he has finished that job he is going to send him over to your Mesquite location. Codie will let me know when he has more info on arrival time, but he confirmed it should be this afternoon. 10/20: Customer (Emmanuel Udoji) just sent an email confirming the conduit between the two IT rooms is complete. Per Codie Bueckner (AT&T), "I will work on getting a technician back over there, but I’m not sure when just yet. My techs are loaded out at the moment, but I will let you know when I an available tech to send that way."
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX598-02-IM | UHG | Melissa Chapman | Wellmed | 1601 Alton Gloor Blvd. Suite 105 | Brownsville, TX |  | VS20111494 3102-1120 7WS03878262 3102-BCCP | 2020-08-18 | 2020-08-20 | 2020-11-17 | 2020-11-12 |  | Y | BBEC.660828 | SBC | 38KRGN614101SW | 2020-11-16 | 01,MDF ROOM,RR 01, CIENA 3930 POS 25 |  |  |  | 50 | 10.45.11.17 | 10.45.11.18 | 65381 | 202610 | UHG GLOBAL 150 | 11/16: ORDER COMPLETE 11/9: Access install re-scheduled for 11/16. (pushed out due to CNR) 11/2: Construction completed the fiber work ahead of schedule. LEC went to install on Friday and no one available - Message Type: CUSTOMER - NO ACCESS - NO ONE ONSITE, OFFICE CLOSED. 8/31-10/26: Fiber work scheduled to complete 10/30 (11/4 for NTE completion.) Access install scheduled for 11/9. 8/25: Site visit scheduled for 8/26. 8/18: Order rec'd
New | 100M Port/ 250M Access EaAVPN 1000 Base-SX | FL054-07-IM | UHG | Melissa Chapman | United Healthcare | 3100 SW 145th Avenue | Miramar, FL |  | VS20145308 3102-1767 3102-BCGR | 2020-10-26 | 2020-11-13 | 2020-11-13 | 2020-11-12 |  | Y | BREC.929906 | AT&T SOUTHEAST ONNET-5 | 60KRGN766295SB | 2020-11-13 | 2 201 MM FIBER FROM 4TH FLR CIENA TO 2ND FLR |  |  |  | 50 | 10.1.91.61 | 10.1.91.62 | 65215 | 202610 | UHG GLOBAL 150 | 11/16: ORDER COMPLETE 11/10: Access install scheduled for 11/13. 11/6: USO's loaded 10/26: Order rec'd
New | HOT ORDER 5M Port/ 10M Access EaAVPN 1000 Base-SX | NJ194-01-IM | UHG | Melissa Chapman | Optum | 7 Broad Ave | Palisades Park, NJ |  | VS20129935 3102-1323 3102-BCFM 3102-BCFL | 2020-10-02 | ASAP | 2020-12-18 | 2020-11-19 |  | Y | MLEC.752860 | Verizon South | KFGS314708NJ | 2020-10-30 | 1ST FLOOR TELCO ROOM WALL MOUNTED NID TAGGED |  |  |  | 50 | 10.45.10.73 | 10.45.10.74 | 65363 | 202610 | UHG GLOBAL 150 | 11/30: ORDER COMPLETE 11/16: Escalation AERO Design Ticket 1501235 issued - pushing for VLAN PON completion as it's past due and holding up this order. 11/9: Advised that Engineering is pending completion of the VLAN PON HNSV4561162. Verizon needs to complete out that PON and than engineering and the rest of the critical dates will be completed out. 11/2: Access install completed - pending testing completion and the OK to turn up. Issued AERO Design 1457190 to complete engineering. 10/12-10/24: Access install scheduled for 10/30. 10/6: Pending install date from Verizon South. 9/29: This is the new order - old order 3102-1009 had to be cancelled due to lengthy CNR which ended up cancelling the order.
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX475-02-IM | UHG | Melissa Chapman | Wellmed | 165 Hargraves D Ste-100 | Austin, TX |  | VS20036968 3102-1392 7MS02396085 3102-BBRV | 2020-02-27 |  | 2020-12-22 | 2020-11-25 |  | Y | BBEC.564012 | ATT SW | 32KRGN654232SW | 2020-10-08 | 1ST,SRVR,WALL MNT, PNL 1 ,POS 1 |  |  |  | 50 | 10.1.85.217 | 10.1.85.218 | 64904 | 202610 | UHG GLOBAL 150 | 11/30: ORDER COMPLETE 11/16: Sent follow up email to Rick Williamson and rest of UHG team......LEC tech visited the site on 11/13 (Friday) and confirmed the site is still under "heavy construction." Provided Rick and team all of the LEC notes and asked that they update me when the site is ready for redispatch. 11/10: LEC still on track for 11/13 - GRETA shows a dispatch request is set up for 11/13 but not tech assignment yet. 11/6: Reached out to Douglass Morgan (AM - LEC) - the customer sent the email below and the attached picture regarding the electrical requirements at the site. We received an 11/13 install date for access and I wanted to see if you could verify if electrical requirements are still needed at the site. If they are, I would recommend contacting Ray Silva-Reyes below as it appears he is on top of things at the site for Wellmed. 11/3: Reissued PON - customer advising they're ready per Melissa emails. Pending new date. 10/12-10/26: CNR - CUSTOMER SITE NOT READY - PER THE LEC, THERE IS NO AC POWER FOR CIENA. LCONS ---KELLY SJELIN 952 833 7371, IAN HAMILTON 512 676 7205 NOR RICK 2103769633 ---------- ARE EITHER UNAWARE OF ORDER OR UNREACHABLE. No EF offer accepted so inside work remains responsibility of the end user. Recommend the customer contact PAUL WHITE (pw1809@att.com) OSP engineer for any questions on what needs to be done. 10/6: Install rescheduled for 10/8. 10/5: Escalated to Paul White (OSP) for status of construction. Overall install date remains at 12/7. - UPDATE: PER PAUL, The placing and splicing of the new fiber is complete. All of the work on the construction and engineering side of things are completed." I've closed out the Customer Ready date in ASEdb and it has completed the infrastructure date as well. Will work to get the access date pulled in. 9/29: Per Paul White (OSP Engineer) - The job to place and splice the new fiber cable for this location has been completed. For some reason, the order was showing that we were awaiting conduit repair which has obviously been corrected. I have removed that restriction so that the order will flow through the remaining departments. It should now be moving to installation. Fiber infrastructure still shows due 11/24 and access install is scheduled for 12/7 8/25-9/28: Melissa advised on WIP call that site work was slated to complete end of August and she was going to follow up. - fiber infrastructure still shows due 11/24 and access install is scheduled for 12/7 8/24: Dates are back to where they were previously.......fiber infrastructure shows due 11/24 and access install is scheduled for 12/7. The site in ASEdb (Construction) still shows CNR though - SITE REQUIRES PATH/PWR/GRD/SPACE. Need to verify this. 8/17: Fiber infrastructure work update - target completion is 9/22 (was 11/24) 8/10: One addtional note for this order....ASEdb showing CNR so might want to touch base with the site and make sure there are no roadblocks to completing the inside work (no EF offer so site is responsible.) 6/29-8/10: Construction has provided an 11/24 fiber completion date and access install is scheduled for 12/7. These requirements were thoroughly covered during the site visit conducted on 06/19/20 with IAN HAMILTON. The following requirements need to be completed in full by 09/29/20 to avoid a delay of your ASE order. Per your acceptance of the ASE Entrance Facility Offer, AT&T will complete the specified site readiness requirements listed below: - Place new #6 ground wire bonded to an MGN (except in CA) or UFER Ground terminated to a grounding bus bar - Place 110v 5-15R, 15 Amp 3-prong GFI electrical outlet in weatherproof junction box Depending on the specific site requirements a System Permission form may be required to be signed by the building owner. If required, the AT&T site visit engineer will provide a copy of the System Permission form by hand or via email to the building owner or appropriate Building Management group identified during the site visit. It is crucial for AT&T to receive a prompt signature and returned copy of the System Permission form, when required, to meet the due date specified above. If the site requirements are interior to the building, the System Permission form is not required. However, per the language in your ASE service agreement, the Customer is obligated, in a timely manner, to allow AT&T access to the property and equipment the Customer controls, and/or obtain permission to access and install the site requirements identified above in areas controlled by third parties such as the Customer's landlord. ADDITIONAL CUSTOMER WIRING REQUIREMENTS: As discussed at the Site Visit, you are also responsible for a path, if required, from the NTE location which I pointed out in the Common Area/MPOE, on floor 01, to the customer demarcation panel and then to your router (usually located in your suite or equipment room). This path may include available space in existing floor sleeves, a minimum 2" conduit, and pull tape if the demarcation panel is located in a separate room than the NTE. 6/8-6/15: FOC due back by 6/26. 6/2: Melissa advised OK to proceed - issued ServiceNow ticket to supp PON for new install date. 4/14: HITS ticket issued to request S19C jep code. - UPDATE S19C CODE APPLIED 3/24-4/13: Per LCON Ray J Silva-Reyes "This project still in the early phases of digging for utilities, retaining walls and the like. They may be going vertical in end April/May time." the site visit has not yet been conducted. Hence, sending a site visit initial TPL with a f/u as on 03/25/2020. 3/17-3/23: PER LEC: CNR - SITE VISIT - BLDG NOT READY 3/12: USO's rec'd - pending an install date. 2/27: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL160-04-IM | UHG | Melissa Chapman | Wellmed | 3160 Southgate Commerce Blvd | Orlando, FL |  | VS20064450 3102-1555 7SS03667132 3102-BBXC | 2020-04-29 | 2020-05-05 | 2020-11-25 | 2020-11-26 |  | Y | BBEC.634062 | ATT SE | 58KRGN703623SB | 2020-11-25 | 1ST FL STE 34 IT ROOM WALL MOUNTED PORT2 |  |  |  | 50 | 10.1.83.17 | 10.1.83.18 | 65276 | 202610 | UHG GLOBAL 150 | 11/30: ORDER COMPLETE 11/17: LEC provided an 11/25 access install date. 11/16: ORDER IS ON HOLD BECAUSE PER VENDOR: THE PROPERTY MANAGER IS NOT ALLOWING ACCESS. HE ADVISED THAT ANOTHER COMPANY ALREADY DID THE WORK THERE IS A LOT OF CONFUSION BETWEEN THE PROPERTY MANAGER AND THE TENANT. PENDING SALES DUE TO NO ACCESS FROM PROPERTY MANAGER. INSIDE WIRING TEAM IS NOTIFYING TECH/FSM/AND SALES CONTACT. A NEW DUE DATE NEEDS TO BE SUPPLEMENTED FOR THIS ORDER. HENCE, ENGAGING CUSTOMER NOT READY TEAM. - UPDATE: Reached out to Melissa and Gabino Ledezma (Powerlogic - AT&T contractor) to find out the latest from the site. 2ND UPDATE: I had the CNR coding removed and the PON resent to the LEC today. I’ve also added notes to the LEC’s system indicating the property mgr advised it was OK to redispatch and gave them Glenda Escalante's (Wellmed) info. 11/10: UPDATE per Melissa....FL160 is now ready with pullstring.. Please supp the order to let the carrier know to proceed. - PER GRETA: 11/9/2020: CCLCON- PROPERTY MANAGEMENT BELIEVES ANOTHER VENDOR RAN FIBER. CURRENT VENDOR WILL TRY TO SURVEY. 11/10: CCLCON PRPRTY MGMT WON'T ALLOW ACCESS. UNABLE TO PROVIDE INSIDE WIRING. 11/9: CCLCON PROPERTY MANAGEMENT BELEIVES ANOTHER VENDOR RAN FIBER. CURRENT VENDOR WILL TRY TO SURVEY. 11/6: CCLCON VENDOR QUOTE APPROVED. EXPECTING COMPLETION WITHIN 5 BUSINESS DAYS. PULL HEIGHT FEET: 12' - PULL TAGGED WITH BAN# CYCN3CD9 - VENDOR NAME 1 POWERLOGIC IT LLC. PULL BOXES: 2 - PULL LENGTH FEET: 350' FIBER - CONNECTORIZED: NO. MPOE REAR OF BLDG - PATH TYPE CONDUIT AND PULL STRING - CUSTOMER SUITE 210. 11/5: Per CCLCON CURRENT PATH NOT POSSIBLE. VENDOR WILL SUBMIT ALT PATH TO PRP MGMT FOR APPROVAL. 11/3: CCLCON TARGET SITE SURVEY DATE IS 11/4 11/2: Melissa advised she would look into this one. 11/2: SITE DELAY - Message Type: CUSTOMER SITE NOT READY - CONDUIT RUN IS ABOUT 370' AND HAS EXISTING 25 PAIR WIRE IN IT WITH AT LEAST 5 TURNS. UNABLE TO BLOW IT IN. NEED FISH TAPE TO PUT IN. 10/26: Access install rescheduled for 10/29. 10/20: CNR coding removed - PON resent to LEC. Notes added to LEC order: This bldg. doesn’t utilize a COM room but an exterior NEMA demark with padlock. If someone lets Paul know which day the appt is they can have the padlock already opened unless they start before 7am. --- Contact: Paul Caruso, Vice President, Pineloch Management Corp. Paul@pineloch.com or call 407-257-6005. 10/13-10/19: Email to Melissa.......Regarding your question about the Orlando order and the LEC losing access, here’s what their notes indicate: SECURED SITE, LOCATED PATH OF CONDUIT -- PULL BOX ABOVE REAR DOOR INSIDE SUITE 34 -- CONNECTING CONDUIT GOES INTO SUITE 38 BEFORE GOING INTO GROUND, COMES UP IN PAD LOCK SECURED NEMA CLOSURE. I believe the field tech needs access to this padlocked closure where the conduit terminates. 10/5-10/12: Per the LEC, CUSTOMER - NO ACCESS - LOST ACCESS TO DEMARC. PON will need to be supp'd. 9/28: Fiber work completed ahead of schedule - access install bumped up to 9/29. 8/24-9/21: Fiber work set to complete on 11/2. Access install scheduled for 11/5. Construction Complexity: Splicing, Long Term Permits Required and NTE required. Permits are scheduled to be aquired by 10/23. 8/17: CNR CHATROOM WORKING TO CLEAR C01/S19C - UPDATE: Sudip Debnath: @Brian Cooper -- 3102-1555-- CNR has been removed. ASEDB jeop cleared. SV is scheduled for 08/20/20 8/11: Advised Joe Scrudato that this is not Covid19 delayed and PON needs to be resent. 7/14: JOE SCRUDATO (AT&T) looking for status on this CNR - Need customer status. 6/1: Need to S19C per Melissa email. 5/12-5/26: Pending an install date from ATT SE 4/29: Order rec'd
New | 50M Port/ 50M Access EaAVPN 1000 Base-LX | NAMM UCA01 | UHG | Melissa Chapman | NAMM | 1950 W. Florida Avenue | Hemet, CA |  | VS20115911 3102-1209 3102-BCDB 3102-BCDC | 2020-08-25 | 2020-09-11 | 2020-11-27 | 2020-11-20 |  | Y | BBEC.666707 | Frontier-CTF | 45KRGN462121FTNC | 2020-11-16 | DEMARC:BLDG 1 FLR MDF RELAY 1 UNIT 1 H/O PORT 6 RAD203 FULL DUPLEX AUTO NEG OFF |  |  |  | 50 | 10.1.2.13 | 10.1.2.14 | 64514 | 202610 | UHG GLOBAL 150 | 11/30: ORDER COMPLETE 11/17: Date showing missed as of this morning - will submit escalation on miss+2. 10/26-11/9: Access install scheduled for 11/16. 10/20: PON resent 10/19. 10/12-10/19: Frontier install date missed. Carrier Management engaged and provided the following update: NO ACCESS TO PREM. ENTRANCE ROPED OFF. VM LEFT FOR LCON TO ARRANGE TIME FOR ACCESS. CUSTOMER IS NOT READY, SUPP REQUIRED FOR NEW DUE DATE , THUS OVERLAYING THE JEOP WITH C01F TO ENGAGE THE CNR TEAM , AND MARKING IT AS HOLD CNR. 9/15-10/5: LEC Frontier provided a 10/6 install date. 8/25: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | IA021-10-IM | UHG | Melissa Chapman | United Healthcare | 1089 Jordan Creek Parkway | Des Moines, IA |  | VS20129331 3102-1297 RCS04557903 3102-BCFK 3102-BCFJ | 2020-09-17 | 2020-10-01 | 2020-12-16 | 2020-11-24 |  | Y | IUEC.827564 | ENVENTIS TELECOM INC | KRGN90934MPT | 2020-11-11 | BUILDING FL 2 MPOP, NORTH WALL MOUNT BTI704, PORT 6 |  |  |  | 2 | 10.1.87.21 | 10.1.87.22 | 65134 | 202610 | UHG GLOBAL 150 | 11/30: ORDER COMPLETE 11/16: Access install complete - pending testing completion and the OK to turn up. 11/2-11/9: Access install delayed to 11/11. This was due to an issue with the VLAN PON RCSV4571163 that was corrected. Back on track, albeit a bit delayed until 11/11. Date looks to be firm now but keeping an eye on the order. 10/26: Access install scheduled for 11/3. 10/6-10/19: FOC due back by 11/5 from LEC ENVENTIS. 9/17: Order rec'd
New | 50M Port/ 100M Access EaAVPN 1000 Base-SX | AZ184-02-IM | UHG | Melissa Chapman | 4C Medical | 21300 N. John Wayne Parkway Suite #123 | Maricopa, AZ |  | VS20144110 3102-1761 3102-BCGL | 2020-10-22 | 2020-11-04 | 2021-01-22 | 2020-11-20 |  | Y | IUEC.890999 | Qwest | 19KXGS563671MS | 2020-11-20 | UNI MAIN LEVEL BILLING ROOM WALL MOUNTED, TAGGED ELE. PORT |  |  |  | 52 | 10.1.94.29 | 10.1.94.30 | 65076 | 202610 | UHG GLOBAL 150 | 11/30: ORDER COMPLETE 11/16: Access install scheduled for 11/20. 11/10: Pending an install date from Qwest - FOC due back by 12/10. 11/4: USO's loaded. 10/22: Order rec'd
| 30M Port/ 50M Access EaAVPN 1000 Base-SX | NC068-04-IM | UHG | Melissa Chapman | Optum/Diplomat | 10 Herman Ave | Asheville, NC |  | VS20146785 3102-1769 3102-BCGS | 2020-11-06 | 2020-11-10 | 2020-12-09 | 2020-11-23 |  | Y | BBEC.640664 | ATT SE | 20KRGN400873SB | 2020-11-20 | 1ST FLR DATA RM APC CAB RACK MOUNTED |  |  |  | 50 | 10.45.10.201 | 10.45.10.202 | 65207 | 202610 | UHG GLOBAL 150 | 11/30: ORDER COMPLETE 11/16: Access install scheduled for 11/20. 11/6: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL213-08-IM | UHG | Melissa Chapman | Wellmed | 8380 Baymeadows Way | Jacksonville, FL |  | VS20055903 3102-0800 HSS03691963 3102-BBTF | 2020-04-17 | 2020-04-20 | 2020-10-01 |  |  |  | BBEC.667683 | ATT SE | 52KRGN703360SB | 2020-12-08 | 1ST,SERVER,HANDOFF ON BISCUIT JACK |  |  |  | 50 | 10.1.84.153 | 10.1.84.154 | 65196 | 202610 | UHG GLOBAL 150 | 12/8: ORDER COMPLETE 12/7: NTE Placement is showing completed as of 12/05. LEC systems are showing access has been installed and demarc provided. Pending completion on the PON so AT&T can begin testing and turn up. Should be a quick turnaround as Engineering, Design and Wiring are all complete and only thing pending is tech testing and closing it out plug and play. 12/1: AS PER THE UPDATE RECEIVED FROM PROVISIONING TEAM, CENTRAL OFFICE IS READY. AWAITING UPDATES ON NTE INSTALL 11/30: Networking team engaged - pending updates on network terminating equipment installation. Also contacted the provisioning team to get an update. Next follow up from team is expected by COB 12/1. 11/16: Per OSP team........This (placement of NTE equipment onsite) is scheduled with TFS, it should be installed very soon. 11/9: NTE placement scheduled for 11/11. 9/28-11/2: SITE ID 1042201 - Fiber infrastructure showing due to complete on 11/11. EF Offer accepted. 9/21: Access install showing due to install today. PON HSS03691963 9/14: The OSP engineer Tony Pellegrini is advising there are some paperwork delays due to Property Management requirements - "The property management is asking for us to sign a Right of Entry agreement instead. I had our legal review it and they made minor changes. I sent this back to the property manager last week and have not received a response." 8/24-9/8: EF OFFER NOW ACCEPTED. The customer prem ready date has been changed to 9/4 and fiber completion to 9/11. NTE placement is now scheduled for 9/17 which is now the Infrastructure Completion date. Request to clear R15 (DDF 202008310027) 8/21: I was able to reach OSP Planner Diane Keuning and she sent the info about the customer wanting to accept the EF offer to Taylor Stowell (OSP) who then forwarded to Frank Williams and Michael Walters at Truenet Communications. Frank's email is fwilliams@truenetcommunications.com as an FYI. They are working to have the SPF resent to customer for this location. This is a SYSTEM PERMISSION FORM that is completed by the end user to accept the offer. 8/11-8/17.: If the customer would like ATT Construction to do this work, they would have to reach out to the OSP Engineer (Frank Williams) to see if it’s offered for this site. Frank will be able to confirm the options for any inside work needed. Frank’s email is fw8854@us.att.com in case you want to email instead of call him. 8/11: Site req letter from Construction sent to Melissa. 8/10: THE ORDER IS ON HOLD AS THE SITE IS NOT READY. ENTRANCE FACILITY OFFER NOT ACCEPTED. CUSTOMER NOT READY TEAM IS ENGAGED - CNR AGENT MP9640. 7/7-7/27: Construction is showing an 8/11 completion date for fiber infrastucture. Room Ready ECD is 07/16/2020 5/18-6/8: Construction is showing a fiber completion date of 8/6. ORDER IS YES-EF/ENTRANCE FACILITIES OFFER ACCEPTED SO ATT IS RESPONSIBLE FOR THE CUSTOMER REQUIREMENTS. Letter sent to Melissa showing construction details. 5/11: Access install delayed due to design issue - FOC ACCEPTED BUT USO NEEDS TO BE UPDATED TO SHOW FOC LSO: 904-256 AND FOC (S)SWC: JCVLFLSJ TO REPLACE ASR LSO: 904-363 AND ASR CLLI: MNDRFLAV. Issued ticket to ordering team to fix this issue. -- HITS TICKET Please change the LCON to Julie Frady, 904-831-3543, jfrady@homecardimensions.com. Once the USO has been changed, please sup the PON to the LEC for a new date. 5/4: Access install scheduled for 5/7. 4/27: sa305u issued HITS ticket to change to 8380 Baymeadows Rd, Suite 12. -- 4/28 UPDATE: USO SHOWING SUITE 12 -- FOLLOWING UP ON PON BEING RESENT WITH THIS UPDATE 4/21: Pending an install date from the LEC ATT SE. Reached out to Tony (engineer) regarding the address. Construction notes indictate " The address should be 8380 Baymeadows Rd, Suite 12" 4/17: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX579-02-IM | UHG | Melissa Chapman | Wellmed | 1417 N. Ware Rd Suite 300 | McAllen, TX |  | VS20103011 3102-1577 7WS03874152 3102-BCBX | 2020-07-28 | 2020-07-31 | 2020-11-13 | 2020-12-03 |  | Y | BBEC.633437 | SBC | 38KRGN614088SW | 2020-12-03 | 1ST FLR MDF RM,SOUTH WALL,CIENA OFF,PORT 2 |  |  |  | 50 | 10.1.93.61 | 10.1.93.62 | 65361 | 202610 | UHG GLOBAL 150 | 12/7: ORDER COMPLETE 11/30: Access install rescheduled for 12/3. 11/16: Order CNR'd as of late last week - pending update from Melissa on email sent today. UPDATE: Per Gabriel Rodriguez, MSA (San Antonio)(Wellmed)......."We met with supervisor and area manager. More requirements were requested and have been submitted to the general contractor. They should be done by Friday (11/20.)" 11/9: Access install rescheduled for 11/17. 11/5: CNR team confirmed with end user (Gabriel Rodriguez - Wellmed) that they removed the CNR hold from this order and raised a request to get a new installation date 11/2: Email to Melissa.........CNR CUSTOMER NOT READY - NEW BUILDING UNDER CONSTRUCTION NO COMMERCIAL POWER AND NO BACKBOARD AVAILABLE WITH CONDUIT TO OUTSIDE FOT NEXT TO POWER METER NO EF TRAIL;NEW BUILDING NOT READY NEEDS COMMERCIAL POWER AND BACKBOARD WITH CONDUIT 10/26: Access install scheduled for 10/28. 10/19: Per Christian Romero....All work has been completed and we are ready to move forward with installation and site readiness. CNR coding removed - PON resent for new date. 10/12: CNR - once resolved we'll have to complete the date in ASEdb and push for fiber completion and new install date from LEC. 10/5: Construction showing this as CNR CUSTOMER NOT READY - "CNR-Path/Pwr/Grd/Space." There was no EF offer accepted so customer is responsible for work at the site. Site requrements (Per Letter from Construction): - Place 2" Rigid Conduit with pull tape from the property line to the minimum point of entry as identified by the AT&T Representative. · Note: Conduit should have a minimum 3' sweeping radius - no right angles - no more than three 90° turns without a pull box. Paths longer than 300' or with two or more 90° turns will require a pull box. Minimum Dimensions for an in-ground pull box is 17"x30"x24" deep or 12"x12"x6" deep for other applications. - Minimum 1½" hard plastic innerduct or 2" EMT type conduit (per electrical code) with pull tape is required from the Main Equipment Room (Common Area) to another interior location within the building as identified by the AT&T Representative. · Paths longer than 300' or with two or more 90° turns will require a pull box no higher than 10 feet from floor level and have the minimum dimensions (12"x 12" x4" Deep) 8/18-9/28: Fiber work set to complete on 10/7. Construction letter sent to Melissa. Access install scheduled for 10/12. 8/17: Site visit completed on 8/13 - pending update on Fiber work and dates for completion of infrastructure and access. 8/10: Site visit scheduled for 8/13. 7/28: Order rec'd
New | 500M Port / 500M Access Ethernet ADI 1000 Base-SX | CA177-06-IJ | UHG | John Sergot |  | 6601 Center Drive West, Suite 200 | Los Angeles, CA |  | IP20099656 3102-1147 3102-BCGC | 2020-10-27 | 2020-12-02 | 2020-12-02 | 2020-12-03 |  |  | BMEC.870145 | SBC ONNET-20 | 13KRGN604681PT | 2020-12-02 | P2 MPOE VIRTUAL EDGE PORT 4 |  | WAN IP Information CR Serial IP Address: 32.141.33.158/30 IPv6 CR Serial IP Address: 2001:1890:0C05:F7C6:0000:0000:1117:5EB1/64 Compressed IPv6 CR Serial IP Address: 2001:1890:C05:F7C6::1117:5EB1 AR Serial IP Address: 32.141.33.157/30 IPv6 AR Serial IP Address: 2001:1890:0C05:F7C6:0000:0000:EE17:5EB1/64 Compressed IPv6 AR Serial IP Address: 2001:1890:C05:F7C6::EE17:5EB1 Wan IP Address: 32.141.33.156/30 LAN Information IPV4 Block: 12.21.112.64/28 LAN IP Gateway: 12.21.112.65 First Network Assignable: 12.21.112.66 Usable IP Range: 12.21.112.66 - 12.21.112.78 Broadcast IP Address: 12.21.112.79 Subnet Mask: 255.255.255.240 IPv6 Block: 2001:1890:1918:5D00::/56 IPv6 LAN IP Gateway: 2001:1890:1918:5D00::1 IPv6 Prefix: 0,56 Internet Services: | [7 empty] | 12/7: ORDER COMPLETE ready for turn up. 11/10-11/30: Access install scheduled for 12/2. 10/27: Order rec'd
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | TX608-02-IM | UHG | Melissa Chapman | Wellmed/OptumCare | 341 Wheatfield Drive, Suite 100 | Sunnyvale, TX |  | VS20143968 3102-1149 7MS02431795 3102-BCGD | 2020-10-29 | 2020-11-04 | 2021-02-02 | 2020-12-10 |  | Y | BBEC.673429 | ATT SW | 14KRGN889365SW | 2020-12-18 | 1ST FLR COM/TELCO RM WALL MOUNT ON TO PATCH PNL 1 POS 2 TAGGED |  |  |  | 50 | 10.1.89.245 | 10.1.89.246 | 65425 | 202610 | UHG GLOBAL 150 | 12/11: ORDER COMPLETE 12/8: Melissa advised site is ready - CNR coding removed and PON resent - UPDATE: LEC provided a 12/18 install date. 12/7: CNR code from LEC - SITE REQUIRES PATH/PWR/GRD/SPACE - REQUIREMENT ISSUE BECAUSE CPR ECD IS PASSED DUE. Requirements: - Place a minimum 4' x 4' x ¾" fire-rated plywood backboard - Place 110v 5-15R, 15 Amp 3-prong electrical outlet (Interior) Dedicated outlet is recommended to ensure the draw of electrical current not overload your system, blow a fuse, or trip a circuit breaker. At a minimum, the circuit must accommodate for a maximum of 95 Watts. Use of extension cords are not permitted. - Place 220v L6-20R, 20 Amp Twist-Lock AC electrical outlet (dedicated circuit) - Minimum 1½" hard plastic innerduct or 2" EMT type conduit (per electrical code) with pull tape is required from the Main Equipment Room (Common Area) to another interior location within the building as identified by the AT&T Representative. · Paths longer than 300' or with two or more 90° turns will require a pull box no higher than 10 feet from floor level and have the minimum dimensions (12"x 12" x4" Deep) 11/16: Access install scheduled for 12/10. 11/10: Site visit completed 11/6 - Pending fiber dates and an access install date from ATT SW. 10/29: Order rec'd
New | 1G Port/ 1G Access EaAVPN 1000 Base-LX | TX567-01-IM | UHG | Melissa Chapman | Flexential - Texas - Plano Data Center | 3500 East Plano Parkway | Plano, TX |  | VS20144807 3102-1766 3102-BCGP 3102-BCGQ | 2020-08-19 | 2020-11-05 | 2021-01-22 | 2020-12-08 |  | Y | IZEC.693541 | UPN | IZEC693541UPW | 2020-12-07 | 1ST FLR MMRA RR 2.1 RMU 42 Port 11 SMF LC Handoff |  |  |  | 2 | 10.1.91.113 | 10.1.91.114 | 65358 | 202610 | UHG GLOBAL 150 | 12/9: ORDER COMPLETE 12/8: Access install showing missed - reached out to Lisa Jameson Provisioning Tier I Escalation contact for UPN for status. UPDATE: Lisa advised access was installed - pending technical docs from UPN so provisioning can manually update systems and test. 11/10-12/7: LEC UPN - access install scheduled for 12/7. 11/5: USO's loaded 10/6: OAPI Quote - UPN - pushed back for clarification (?construction) - Melissa advised 9/9: Per Deidre - FYI – this one needed a Sold Notice (AT&T OF TEXAS – SPORT). The Sold Notice came back with significant cost associated with it. I have sent this to Pricing last night to see if we can absorb that cost. I will let you know once I hear back from Pricing. 8/19: Order rec'd
New | HOT ORDER UHG CTO ESCALATION Port/VLAN Upgrade 100M > 200M | C1619-04-CM | UHG | Melissa Chapman |  | 900 Venture Dr | Allen, TX |  | ISR20121453585 3094-BWPH-FR 3094-BWPJ-FR | 2020-12-14 | ASAP | 2021-01-06 | 2020-12-18 |  |  | IZEC.580395 | [13 empty] | 12/21: ORDER COMPLETE 12/15: USO's rec'd - currently showing 1/6 Due Date - UHG needs by 1/1. CTO LEVEL ESCALATION (James Franke.) Request to MACD AM Aaron Rickles and Service Delivery AM Jane Tansor for assistance. 12/14: Upgrade order processed via Business Center by Melissa - requested addition to HOT sheet as UHG needs by 1/1/2021.
New | HOT ORDER Port/VLAN Upgrade Upgrade to 20M | LA040-02-CM | UHG | Melissa Chapman |  | 1215 N Broad St | New Orleans, LA |  | 3094-2874-FR 3094-BWPQ-FR | 2020-12-03 | ASAP | 2020-12-24 | 2020-12-19 |  |  | BBEC.664760 | [13 empty] | 12/21: ORDER COMPLETE 12/14: Overall due date 12/24. Pushing for earlier completion. 12/4: Biz Case: It’s affecting call quality issues and file transfer. Business is slowing down during our busiest time of year. - Escalating for completion ASAP 12/3: Added to sheet per Melissa
New | 100M Port/ 200M Access EaAVPN 1000 Base-SX | IN156-05-IM | UHG | Melissa Chapman | Equian | 5975 Castle Creek Pkwy, Suite 100 | Indianapolis, IN |  | VS20121373 3102-0488 3102-BCDX | 2020-09-09 | 2020-09-14 | 2020-12-09 | 2020-12-17 |  | Y | BREC.965182 | SBC | KRGN107334NB | 2020-12-17 | 1ST,DATA,EXT. FROM 2ND FL. TO 1ST FL |  |  |  | 50 | 10.45.10.153 | 10.45.10.154 | 64698 | 202610 | UHG GLOBAL 150 | 12/21: ORDER COMPLETE 12/14: Access install scheduled for 12/17. 12/8: Confirmed LCON on the order is Stephen Klein - resent PON to the LEC. FOC showing due back by 12/31. 12/4: LCON change from Melissa. 12/4: FIELD TECH HAS BEEN DISPATCHED, ETA 12:30 PM 12/1: Reached out to RONALD MILLER (rx1949) - AM LEC - to find out who the tech David Mattingly is working with on the Property Mgmt side. 11/30: ORDER IS ON HOLD DUE TO NO ACCESS TO CUSTOMER PREMISES. FIELD TECHNICIAN WAS UNABLE TO REACH PROPERTY MANAGEMENT GROUP FOR ACCESS TO TELCO ROOM PER UPDATES. DUE DATE NEED TO BE SUPPLEMENTED. ENGAGING CUSTOMER NOT READY TEAM. This update is directly from DM9726 - David Mattingly (317-966-2575) LEC TECH. 11/16: Access install rescheduled for 11/19. Can we have someone reach out to the Property Mgmt group to reconfirm the LEC will be onsite on the 19th? Right now I'm showing the following tech is assigned on the 19th - DM9726 - David Mattingly (317-966-2575) 11/9: CNR coding has been removed and PON resent for new date. Notes updated in the LEC system with request to contact Property Mgmt group 2-days ahead of schedule. 11/3: Still showing CNR - Escalating for status and ETA for install. 10/26: Access install rescheduled for TODAY 10/26. UPDATE: Install missed - possible delay in site allowing access. LEC is aware of the process............IN ORDER TO INSTALL THIS CIRCUIT, PRECALL MUST BE MADE TO PROPERTY MANAGEMENT GROUP 48 HOURS IN ADVANCE FOR ACCESS TO TELCO ROOMS - PROP MGMT. NUMBER IS 3178199644 - ACCESS TO PHONE ROOMS WILL NOT BE GRANTED IF PRECALL NOT MADE 2 DAYS PRIOR TO APPT 10/19: Access missed - Carrier Mgmt engaged - AERO CM#1402210 - LEC working to gain access by giving Property Mgr 48hrs notice. 10/6-10/12: Access install re-scheduled for 10/15. 10/5: CNR team has removed CNR coding - confirmed the LCON STEPHEN KLEIN's info on this order IS correct. PON was resent, pending new date back for install. 9/28: Per LEC, CUSTOMER - NO ACCESS - CNR. LCON AVAILABLE, BUT PROP MGMT GROUP UNWILLING TO PROVIDE ACCESS TO TELCO ROOMS W/O SETTING UP APPOINTMENT AHEAD OF TIME FOR ACCESS - LCON WILL HAVE TO ARRANGE FOR ACCESS TO TELCO ROOMS AT LATER DATE - PROVIDED NUMBER FOR PROP MGMT GROUP IN OSSLOG. ORDER WILL NEED RESCHEDULED AND PROP MGMT GROUP CALLED AHEAD OF TIME FOR ACCESS - PROP MGMT GROUP DID NOT SAY HOW FAR IN ADVANCE THEY WANTED NOTIFIED. PROP MGMT UNWILLING TO OPEN DOORS TO TELCO ROOMS W/O SCHEDULED ACCESS - NUMBER FOR PROPERTY MGMT GROUP IS 317-819-9644. 9/15-9/21: Access install scheduled for 9/23. 9/9: Order rec'd
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX610-02-IM | UHG | Melissa Chapman | Wellmed | 6907 N. Capital of Texas Hwy Suite 230 | Austin, TX |  | VS20158180 3102-1771 3102-BCHH | 2020-12-03 | 2020-12-15 | 2020-12-15 | 2020-12-15 |  | Y | BBEC.663424 | SBC ONNET-5 | 32KRGN654743SW | 2020-12-15 | 2ND FLR TELCO RM, CN3930, CKT TAG ON M BOX |  |  |  | 50 | 10.1.88.145 | 10.1.88.146 | 64679 | 202610 | UHG GLOBAL 150 | 12/21: ORDER COMPLETE 12/14: ATT SW install scheduled for Tuesday 12/15 - ON-NET 12/3: Order rec'd
| 200M Port/ 500M Access EaAVPN 1000 Base-LX | C1662-02-IM | UHG | Melissa Chapman | Equinix Data Center | 41 Alexander Rd | Billerica, MA |  | VS20155090 3102-0408 3102-BCGZ | 2020-11-17 | 2020-12-10 | 2021-03-01 | 2021-01-04 |  | Y | BMEC.984277 | ASE LNS | MAKRGN101214TPM | 2020-12-21 | 1ST FLOOR ATT CABINET - VIRTUAL EDGE DEMARC PANEL PORT 7 & 8 |  |  |  | 50 | 10.191.22.229 | 10.191.22.230 | 65407 | 202610 | UHG GLOBAL 150 | 1/4: ORDER COMPLETE 12/24: Per Greta, AT&T NOT READY - DESIGN ERROR being worked. Access install will be rescheduled. 12/22: LNS showing access install not yet completed - monitoring GRETA on LEC order C477194 / IMSC65 for updates. CLO MAS002307001 12/8-12/14: Access install scheduled for 12/21. 12/7: FOC due back by 12/10. 11/17: Order rec'd
| 100M Port/ 100M Access EaAVPN 1000 Base-SX | CA476-01-IM | UHG | Melissa Chapman | Monarch | 23521 Paseo De Valencia # 311 | Laguna Hills, CA |  | VS20160979 3102-0137 3102-BCHJ | 2020-12-10 | 2020-12-22 | 2020-12-28 | 2021-12-28 |  | Y | IUEC.548254 | SBC ONNET-5 | 13KRGN605101PT | 2020-12-28 | BASEMENT MPOE IN VIRT-EDG UNDER EMUX TOP RIGHT SLOTS 1&2 TAGGED |  |  |  | 50 | 172.27.27.229 | 172.27.27.230 | 64747 | 202610 | UHG GLOBAL 150 | 1/4: ORDER COMPLETE 12/21: Access install scheduled for 12/28 - SBC ON-NET 12/10: Order rec'd
New | HOT ORDER 10M Port/ 50M Access EaAVPN 1000 Base-SX | VT001-05-IM | UHG | Melissa Chapman | Optum | 46 Main Street | Winooski, VT |  | VS20064915 3102-1567 3102-BBXP 3102-BBXQ | 2020-05-04 | 2020-05-07 | 2021-01-21 | 2021-01-11 |  | Y | BBEC.687668 | FAIRPOINT | 88KRGN26177200MJD | 2021-01-07 | 1ST FLR DATA RM RACK MOUNTED METYRO NID GT SFP #2 TAGGED W/ CVKT ID/ EXTENDED FROM VZLGX MMF |  | PICS 96227 |  | 100 | 10.1.83.33 | 10.1.83.34 | 65186 | 202610 | UHG GLOBAL 150 | 1/11: ORDER COMPLETE 1/8-1/11: Escalation to Cedrick Scott (Prov AM) for assistance in completing CTA testing and closing this out complete plug and play. 12/21-1/4: Access showing due to install on 1/7 12/14: Access showing due to install on 1/7 - pending LCON change in systems and update from LEC as to whether date will change (most likely) 12/7: Access install scheduled for 1/7/2021. - UPDATE: NEW SITE CONTACT PROVIDED MURALIDHAR MULPURI. PON will need to be supp'd and 1/7 date most likely pushed. 12/3: Opened AERO Ticket 1555238 to engage Carrier Management. 12/2: Escalated to Marilyn Planinsek at Consolidated. 12/1: Second request to Meg Spalding for an update. 11/30: Reached out to Meg Spalding for status 11/17: Per JEFF RICHER ¦ OSP Engineer II - (LEC) - "I checked with the field supervisor who said that they completed the install. I haven’t heard back from the business office with any info about this." There are currently no updates in our system indicating access was completed. 11/9: Reached out to Meg Spalding (LEC) this morning for status on their work now that the path is complete. UPDATE: Per Meg, "Our engineering group was able to confirm that the needed conduit was placed on the 5th and have moved the order forward. We still have splice work to be completed, which was on hold for the end user requirements, followed by provisioning. At this time I do not have an updated ECCD for the completion of the work, however; I’m assured we are working on this presently." 10/29: Per Meg Spalding (LEC), her engineer advised as follows: “I have spoken with Gerry Hanifin and emailed back and forth with him, he was going to check with the building owner on installing a path to the Optum space (there several different tenants in this building) and get back to me. As of now we do not have a path for the space and are waiting to hear what is going to happen.” 10/27: Reached out to Meg Spalding this morning to see if she had news from her engineer. 10/21: Per Meg Spalding who is the INSTALLATION PROJECT MANAGER assigned to this request. Here’s what Meg told me: The most updated note per our Engineer is as follows: "I am waiting to hear back from Gerry Hanifin as to whether or not they are willing to provide a path from the VZW room to the demark room for the customer. I spoke with Coty on 10/05/20 who said he was delivering the message of the needed work to Gerry and that he would get back to me. The property company (Gerry Hanifin) will need to provide a path in order for us to move along with this project.” I have reached out to our engineer to see if there are updated notes that have not yet made it onto the order; I recommend you do the same for the end user as well. I’ll be in touch when I am able to gather more information. If you could reach across to Gerry and Coty regarding the path and get some details on where that stands, I would appreciate it. 10/20: Reached out to Marilyn Planinsek (Consolidated - Fairpoint) to confirm all of the access info and to verify that they have everything they need for the 11/6 date. Need to follow up by Wednesday afternoon if I do not hear back. 10/12-10/19: Access install was rescheduled by the LEC for 11/6. There is a Carrier Mgmt ticket opened and AT&T is reaching out to the LEC to get update/status. 10/5: Access install rescheduled for 10/8. 9/28: Received an email response from one of the Senior Account Managers with the LEC on this order. She advised she’ll get this info below on accessing the building and doors to the proper place so they don’t miss the appointment. 9/23: Reached out to Design AM Phil Cunningham to ensure LEC has all of the info they need to access the building/doors. 9/21: Access install rescheduled for 10/8. 9/14: PON was re-released on 9/9 - FOC is due back by 10/13. Working to reach out directly to LEC to push this. 9/8: Tackling this one across a few fronts. Issued request to have old CNR coding removed from order and will refresh the PON to the LEC once that is done. Also working on a LEC contact to reach out directly for status and to advise PON refresh is coming. Pending a date for dispatch. 8/31: The install date is showing missed - escalation to be sent to Carrier Management on Wednesday if we do not hear back in 2-biz days. 8/10-8/24: Access install scheduled for 8/28. This one concerns me because of the access issues back in July surrounding Neville Properties. I would recommend contacting the LCON to make sure they'll allow access. 7/21: Melissa sent name/info of person that can provide access (Gerry Hanifin) - issued request to adjust LCON on order (using Melissa's email address) - pending notification that the change went through. 7/13-7/20: RECEIVED A MAIL FROM THE LEC SAYING THAT ACCESS IS NEEDED TO THE TERMINAL ROOM, NEVILLE PROPERTIES IS UNWILLING TO ALLOW THEM ACCESS, THEY SAY IT IS UP TO OPTUM TO GET THE TENANTS TO LET THEM IN. PLEASE HAVE ACCESS TO ALL 4 FLOOR EQUIPMENT ROOMS LINED UP FOR A DAY WHERE WE CAN PLACE THE FIBER DROP FROM THE BASEMENT TO WHERE THE DEMARC WILL BE LOCATED. 7/6: Missed install by LEC - issued IOS escalation to find out why date was missed. UPDATE: CM Tier I engaged. 6/1-6/29: Access install scheduled for 6/29. 5/26: PON released on Friday 5/22. FOC due back by 6/26. 5/18: Issued AERO Design 1011557 to have pon issued to LEC Fairpoint. 5/12: Pending an install date from the LEC FAIRPOINT 5/4: Order rec'd
New | cancelled 10M Port / 20M Access Ethernet ADI Electrical Handoff - RJ45 | PA007-09-IJ | UHG | John Sergot | ASE/LNS ORDER | 15 Campus Blvd. 1st Floor MPOE | Newtown Square, PA |  | ROME SR 1-EPAAI53 (Opp 1-EPAE4NW) IP20115350 3102-0416 | 2020-11-24 | 2020-12-07 | 2021-02-16 |  |  |  | MMEC.741202 | Comcast | 11KGGS026334CBCL | 2021-02-10 | [10 empty] | NOTES: Confirmed that in certain cases (this one applies), in order to provide access ASE/LNS access we use and resell 3rd party facilities…..In this case we resell Comcast so the ASE/LNS order is hitting the same build issues that the original order hit, Comcast installed a 1G feeder and they already have one client on that so they would need to upgrade to 10G feeder to accommodate. Comcast is likely declining to upgrade for 20M Ethernet for AT&T due to the financials. Working to validate the final AT&T stance and if answer is LNS is not an option we'll work to make sure the IGLOO database is updated to allow alternate vendors. 1/5: CANCEL REQUEST : Cancel Order ATT Reason/No Facilities or cannot deliver as promised Site 1083079 - Per OSP - This order requires 3rd party leased fiber. We have discussed this location previously. It is not cost effective to proceed with additional fibers. Order will need to get cancelled. 12/23: Pending USO's.
New | 20M Port/ 50M Access EaAVPN 1000 Base-SX | NV200-02-IM | UHG | Melissa Chapman | Optum RX | 6425 Santa Margarita St | Las Vegas, NV |  | VS20130868 3102-1616 3102-BCFP 3102-BCFQ | 2020-09-29 | 2020-10-06 | 2021-01-11 | 2021-01-05 |  | Y | BBEC.663827 | Embarq | 53KXGS555899CTRL | 2020-12-17 | RAD 203 IS IN THE BT ON THE NORTH SIDE OF THE BUILDING WALL |  | PICS 96229 |  | 499 | 10.1.95.213 | 10.1.95.214 | 65233 | 202610 | UHG GLOBAL 150 | 1/6: ORDER COMPLETE 1/5: Embarq provided a completion notice on the access. Demarc was provided. Pending testing completion and the OK to turn up. 1/4: Order is still showing CNR due to no access to the end user prem. PON will need to be resent as soon as we confirm site is ready to allow access. 12/21: CNR - Per LEC< CUSTOMER NOT READY-NO ACCESS TO END USER PREMISE. Reached out to Melissa to check with site. UPDATE: Melissa advised she needs more info on the CNR, site readiness issue and conduit requirements if any. Because this info would have been relayed to the site and not AT&T directly, I opened a HITS ticket to have ordering/provisioning reach across to the LEC to provide further details. Also reached out to CNR AGENT SHARMA, SNEHAL today 12/22 for assistance in reaching out to the LEC. 12/14: Access install is now showing updated to 12/17. 10/20-12/7: Embarq provided a 12/31 access install date. REASON: 1A OUTSIDE PLANT (OSP) - MINOR BUILD 10/6-10/19: Pending an install date from the LEC Embarq 9/29: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL453-02-IM | UHG | Melissa Chapman | Wellmed | 28959 Wesley Chapel Blvd 28959 STATE ROAD 54 | Wesley Chapel, FL |  | VS20139432 3102-1201 3102-BCGB 3102-BCFZ | 2020-10-19 | 2020-10-23 | 2021-01-21 | 2021-01-05 |  | Y | BBEC.660354 | Frontier-CTF | 65KRGN500006FTNC | 2021-01-19 | MAIN BLDG FL 1 TELCO RM RAD203 PORT 5 |  | PICS 96228 |  | 944 | 10.1.93.113 | 10.1.93.114 | 65139 | 202610 | UHG GLOBAL 150 | 1/11: ORDER COMPLETE 11/30-1/4: Access install scheduled for 1/19/2021. 11/20: New PON RSSC3701916 sent today - pending FOC (due back by 12/29.) 11/18: Issued AERO 1513568 - Clear R15 - resend PON for new date since LCON is now back in the office (or should be since it's past 11/16.) 11/16: LEC advised NEED NEW DUE DATE. LCON IS OUT OF TOWN UNTIL 11/16/20. PLEASE PROVIDE A NEW DD. 11/2-11/9: Pending install date from Frontier - FOC due back by 12/2 10/27: USO's rec'd - pending release of the PON to the LEC Frontier. 10/19: Order rec'd
New | SPECIAL CONSTRUCTION CANCELLED 50M Port/ 50M Access EaAVPN 1000 Base-SX | NAMM Project Tiger CA082 | UHG | Melissa Chapman | NAMM | 40690 California Oaks Rd, Suite A | Murrieta, CA |  | VS20144102 3102-1759 3102-BCGJ 3102-BCGK | 2020-10-22 | 2020-11-04 | 2021-02-02 |  |  |  | BBEC.666237 | Time Warner Cable | [7 empty] | 10.0.1.17 | 10.0.1.18 | 65515 |  | New VPN UHG NAMM | 1/12: Cancel order# 307624511 1/11: UPDATE: CANCELLATION REQUEST REC'D FROM MELISSA. SENT HITS TICKET TO CANCEL. 1/11: Per Mark Powley, preference is to move ahead with Frontier and avoid $21K charges. The new order using Frontier (below) has been handed off to ordering. Before Brian can request the cancel on the inflight order he will need written notice from UHG requesting the cancelation. Can you send us an email when you are ready to cancel the order in flight, USO 3102-1759. 12/22: DW update: SC costs shared with UGH. Pending direction from UGH 12/14: Melissa confirmed with Deidre......still pending feedback from the business unit on the SC cost, and the alternative using Frontier was not a good options as that eliminates the access diversity. Melissa following up with business. 12/8: Reached out to Melissa....."I reached out to our team today for status of this Murrieta special construction and they advised me that they have sent the special construction quote to sales and they’re awaiting a response as to whether UHG accepts the charges or not. If accepted, they will request the PS document internally that needs to be signed by both sales and customer. I know below you were investigating other providers with Deidre and I’m not sure how far you both got on that exercise." UPDATE: Per Melissa, "waiting for sign off from the business" 11/25: Per Deidre: I was able to secure a quote from Frontier. Do you want to cancel order in flight and place new order using Frontier? 11/19: We have received the Special Construction quote from TIME WARNER CABLE(Vendor). Please let me know whether or not UNITED HEALTHCARE SERVICES, INC is willing to accept the charges. SOW(Scope Of Work) : Bore 192’, Pull Thru 236’, Traffic Control Permit. Cost: $21,394.00 - Quote expires - 1/18/21 11/10-11/16: Pending an install date from Time Warner - FOC due back by 12/15 11/4: USO's loaded 10/22: Order rec'd
New | 300M Port/ 500M Access EaAVPN 1000 Base-SX | UT027-02-IM | UHG | Melissa Chapman | Optum Tech | 12921 South Vista Station Blvd | Riverton (Draper), UT |  | VS20116512 3102-1614 3102-BCDS 3102-BCDT |  | 2020-09-02 | 2020-11-06 | 2021-01-12 |  | Y | BMEC.502540 | Zayo/Electric Lightwave | ETYX290196ZYO | 2020-11-06 | Floor 1 / Suite 155 / MPOE Room / Rack 1 / MP-144 Accedian NID Port: 1 | Multimode 850nm SX/SR - 500meters LC Connector |  |  | 50 | 10.1.95.101 | 10.1.95.102 | 65351 | 202610 | UHG GLOBAL 150 | 1/12: ORDER COMPLETE 1/11: Escalation to Tech AM Mary Ellen Bruce for completion. Engineering, Design and Wiring are all complete. 1/5: Per Dani Knauf (Zayo): "It looks like the NID was installed but it’s not coming up. I requested a re-dispatch for ASAP date, I will inform you once the date is confirmed." 12/24-1/4: Reached out to Dani Knauf for status. 12/21: Per DANI KNAUF (Zayo): Field Technician Assigned: Matthew Brady, Date: 12/22/2020, Estimated Start Time: 10am local time *Techs can arrive an hour before or after “Estimated Start Time” Approximate Duration of Work: 2 hours 12/15: Afternoon Update: Reached out to Dani Knauf (Zayo) and reconfirmed that extensions are complete. Requested she advise if anything else is needed from AT&T or the customer to complete out the Zayo portion of the order. 12/15: Reached out to Joe Scrudato to find out what next steps are. 12/14: Provided all of the info we have to Joe Scrudato (ATT) and Dani Knauf (Zayo.) Advised that customer said extensions are in place per Parallel's update that circuit already extended to MDF on 4th Floor. 12/10: Customer advised “We were wondering about that circuit because we hadn’t extended it. Parallel went to extend it but it had already been extended to the MDF on the 4th floor Rm 4065. In addition, it has been connected to a small Cisco device which has a yellow/orange light glowing. So that circuit looks to be complete except for configuring.” 12/7: Email from Melissa...Jessica Stoneburg (Parallel Technologies = Vendor onsite) advised that there is a distribution switch in the MDF that is connected to a fiber back to the DMARC so the extension appears to be in place. Still need confirmation of power and space per the bulleted list we need to provide back to Frontier. Sent this back to Melissa to verify the info and then we'll send it back to Frontier to confirm power/space/extensions are all in place. 12/7: Pending confirmation that the cross connections from the ZAYO NID to the rack/cabinet have been completed 11/30: Sent LOA info to Melissa (from Joe Scrudato.) Pending response. 11/18: Reached out to Michael Nicholson (Zayo) to see if he can assist with power/space requirements details. Michael is a Service Delivery Manager (Switched Service) and the Zayo Provisioning Escalation Primary Contact (Tier I.) 11/9-11/16: Carrier Mgmt engaged on missed install - Per Zayo…..."CALLED ZAYO, SW KELLY, SHE ADVISED THE NEW/FUP DATE ON ORDER HAS BEEN PUSHED OUT TO 11/23, PENDING SPACE AND POWER AT CUSTOMER LOCATION PENDING-NID INSTALL." 9/28-11/2: Rec'd 11/6 install date from Zayo/Electric Lightwave. 9/15-9/22: FOC due back from LEC Electric Lightwave by 10/12. 8/19: Order rec'd
New | SPECIAL CONSTRUCTION CANCELLED 20M Port/ 50M Access EaAVPN 1000 Base-SX | AZ167-02-IM | UHG | Melissa Chapman | UHG / Diplomat | 9045 E Pima Center Pkwy | Scottsdale, AZ |  | VS20135717 3102-0392 3102-BCFV 3102-BCFT | 2020-10-07 | 2020-10-15 | 2021-01-04 |  |  |  | IUEC.968950 | Cox Communications | [7 empty] | 10.1.94.29 | 10.1.94.30 | 64633 | 202610 | UHG GLOBAL 150 | 1/14: Cancellation in process. 1/12: Per Deidre, the SC is made up of underground cables and conduit (code 85-c) that will need to be laid in order to deliver the circuit. UPDATE: PER MELISSA, AZ167 is a no go….let’s cancel that. We will review other options for that site. 1/9: Per Deidre: "For Scottsdale AZ167 , we received no bid when we submitted for a 3rd party access custom quote. We currently do not have any certified external 3rd party type 2 vendors to deliver to this location which is why we attempted the LNS route. I’m working on getting specifics on both SC costs. I will ask them to confirm they “can” deliver to the address on Scottsdale." o As you had suspected, getting access into AZ167 is going to be a challenge. The following was provided by our OSP Engineers. Let me know how you want to proceed on this one…  No we are not really, really sure we can get this built. We have never actually successfully deployed service on the reservation, but when we last pursued it we determined that all communications facilities on the reservation are managed by Saddleback communications and the customer would need to lease facilities from Saddleback to a hand-off point at the reservation border/property line. Since we have no experience going through this process we don’t have a lot of experience. I think sales would need to make sure the customer is aware that they may need to negotiate this with Saddleback or we would need to make them aware of potential for additional monthly reoccurring costs… 12/22 DW update: new process for quotes with costly SC…need ICB engagement to get estimates. My request is still with ICB pending SC costs. 12/21: Pending update from Deidre 11/17: NO BID - Possible LNS with Build is an option 11/9: Deidre confirmed an OAPI (custom quote) was submitted for this site on 11/2 to try and avoid Cox. Working to obtain response on OAPI. 11/2: LEC issues sent to sales and provisioning - LEC ERR MSG: ADDRESS IS IN SADDLEBACK TERRITORY AND IS NOT SERVICEABLE. WE ARE NOT CURRENTLY SELLING TYPE 2 SERVICES TO ATT IN AZ. 10/20-10/26: Pending an install date from the LEC Cox. 10/7: Order rec'd
| ORDER CANCELLED SPECIAL CONSTRUCTION 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX587-02-IM | UHG | Melissa Chapman | Wellmed | 2414 Memorial Parkway | Portland, TX |  |  | 2020-11-18 | [14 empty] | 10.45.10.177 | 10.45.10.178 | 65243 | 202610 | UHG GLOBAL 150 | 1/19: ORDER CANCELLED - address had to be changed to 2413 Memorial Pkwy 1/12: Melissa advised paperwork was submitted for signature and sent back to AT&T on 1/8. 12/29: Presigned agreement sent by Deidre to Melissa. 12/22 DW update – SC agreement submitted for AT&T pre-sign. Will send signed agreement to UHG once received. 11/18: Order rec'd - Custom Access Quote req'd - possible lengthy interval
New | 250M Port/ 500M Access EaAVPN 1000 Base-SX | WI054-04-IM | UHG | Melissa Chapman | UHG | 2020 Innovation Court | De Pere, WI |  | VS20132647 3102-1754 7CS04561206 3102-BCFR | 2020-09-30 | 2020-10-08 | 2021-01-11 | 2021-01-25 |  | Y | BMEC.958211 | SBC | 41KRGN101301WT | 2021-01-22 | 1,ELECTRICAL,TAGGED ON 3930 WALL MOUNT; |  |  |  | 50 | 10.1.82.73 | 10.1.82.74 | 65428 | 202610 | UHG GLOBAL 150 | 1/26: ORDER COMPLETE 1/25: Access installed but still pending a completion notice from the LEC. Demarc has been provided. Pending completion on LEC side so remaining milestones and testing can be completed by AT&T. Good news is Engineering, Design and Wiring are all completed. 1/14-1/19: Access install rescheduled for 1/22. 1/12: PON was resent to the LEC requesting a new install date - reconfirmed site is ready. 1/11: Escalating to 2nd Level WIPRO to push on the missed install date. The latest delay on this order from the LEC is showing CNR - CNR-PATH/PWR/GRD/SPACE, although we did advise the LEC a few weeks ago in December that the site was ready. This CNR is delaying NTE placement and access install which are both past due. 1/4: Reached out to WIPRO RAHA, SAYANTAN to have them address the PON issue. We advised back on 12/22 that site was ready but PON still not showing it was sent back to the LEC. Requested all CNR coding be removed and PON resent ASAP for a new date. 12/22: Email to Melissa/John regarding NTE delay and possibly related to customer site work being incomplete. Sent end user requirements from original site visit letter from Oct to confirm if work has been completed or status. UPDATE FROM JOHN: "Here is the response from our pm. The General Contractor has assured me this has been completed and we communicated this back to AT&T several weeks ago." 12/21: NTE placement delayed - there is a CNR condition showing and working to get details. Once NTE is installed, access can be rescheduled. 12/14: Construction completed their fiber work last week. NTE install is scheduled for 12/17 and access still on track for 12/18. 10/19-12/7: Construction fiber work scheduled to complete on 12/14. Access install scheduled for 12/18. 10/13: Site visit scheduled for today. 9/30: Order rec'd
New | 30M Port/ 50M Access EaAVPN 1000 Base-SX | TX574-02-IM | UHG | Melissa Chapman | Wellmed | South Coast Plaza 1620 S. Padre Island Dr. | Corpus Christi, TX |  | VS20144015 3102-1325 7MS02431805 3102-BCGH | 2020-10-22 | 2020-11-11 | 2020-11-11 | 2021-01-20 |  | Y | BBEC.640707 | SBC ONNET-5 | 34KRGN614288SW | 2020-01-05 | COMM ROOM WALL, 1ST FLOOR |  |  |  | 50 | 10.1.92.157 | 10.1.92.158 | 65094 | 202610 | UHG GLOBAL 150 | 1/25: ORDER COMPLETE 1/19: Requested an estimated completion date for the inside wiring. 1/11: AT&T LEC DELAY- AT&T NOT READY REFERRED TO CCLCON FOR WIRING ISSUES. Pending rescheduling of install date. Notes indicate inside wiring to complete WITHIN 10 BUS. DAYS - NOTE: CCLCON (inside wiring team) SITE SURVEY SCHEDULED FOR 1/11 1/4: Access install still showing on track for 1/5. 12/24: Escalation to ordering/provisioning as well as LEC Field Tech Area Mgr for missed date. UPDATE: Rec'd 1/5/2021 access install date - email to Melissa to advise her of the rescheduled date. 12/21: Melissa confirmed to Please proceed with Suite 550 in response to email from Abdul khadeer.ATT Ordering Associate -- Access install still showing due 12/23. 12/14: Access install was missed - resent PON to the LEC to see why the miss. UPDATE: LEC DELAY - CONFIRMED INSTALL RESCHEDULED FOR 12/23. 12/7: Access install rescheduled for 12/10. 12/1: Access install date was missed yesterday - LEC systems show no update and due date past due. I've resent the PON to them this morning to prompt them for status. Pending a new date and status. 11/30: Access install is showing scheduled for today. 11/17: LCON Jason Ozer confirmed the Suite# is 550 for this location. I have suppd the order to add an additional contact phone number for Jason and to add the suite number. Resent PON to the LEC. 11/16: CNR - Per the LEC, we need to narrow down the suite number at the site. Here’s what the LEC is saying: "NEED SUITE AND BETTER LCON NUMBER AND CONTACT. THIS IS A MULTI TENANT BLDG- NO SUITE IS GIVEN FOR ORDER, CALLED # REACHED A CUSTOMER THAT HUNG UP ON TECH, CIENA IS PLACED IN “TIDE DENTAL” AND THEY STATED THEY KNOW NOTHING OF THIS ORDER OR THE LCON ON THE ORDER." Can you check on this and let me know? 11/10: ATT SW ONNET - Access install scheduled for tomorrow 11/11. 11/4: USO's loaded 10/22: Order rec'd
| CANCELLED 30M Port/ 50M Access EaAVPN 1000 Base-SX | WI019-02-IM | UHG | Melissa Chapman | Logistics Health (OPH) | 102 Jay St | La Crosse, WI |  | VS20143969 3102-1318 3102-BCGF 3102-BCGG | 2020-10-29 | 2020-11-04 | 2021-02-02 |  |  |  | BBEC.666240 | CC FIBERLINK LLC | [7 empty] | 10.45.11.65 | 10.45.11.66 | 65046 | 202610 | UHG GLOBAL 150 | 1/26: Showing cancelled in SOTS - moving to completed tab 1/25: HITS ticket issued Friday to cancel order - Request ID: 1334741949. Will leave on active tab until cancellation shows in SOTS. 1/22: Rec'd cancellation notification from Melissa. 1/19: Reached out to Assembler on this ticket to get an update on the scope of work details. 1/13: AERO Design Information ticket 1679312. Pending scope of work details. 1/11: There is a LEC build associated with this order. As per the Charter Weekly Report to AT&T, the build is on hold due to WINTER CONSTRUCTION MORATORIUM enforced by the city. Unable to complete the build until Spring 2021. 12/1-1/4: PON resent to LEC CC FIBERLINK today. Pending an install date. FOC due back by 1/6. AERO Design 1585514 for R15. 11/30: 1st Level Escalation issued on AERO Design ticket 1503047 11/10-11/16: Pending an access install date from CC FIBERLINK LLC - FOC due back by 12/10 - 11/16: PON design issue R15 - AERO ticket 1503047 11/4: USO's loaded 10/29: Order rec'd
New | 10M Port/ 50M Access EaAVPN 1000 Base-SX | FL454-02-IM | UHG | Melissa Chapman | Wellmed | 18900 N Tamiami Trail Suite 9 | North Fort Myers, FL |  | VS20127922 3102-1196 3102-BCFD 3102-BCFF | 2020-09-25 | 2020-09-29 | 2020-12-15 | 2021-02-01 |  | Y | BBEC.640948 | Embarq | 25KXGS554076UFLG | 2021-02-02 | 1ST FLR CABINET WALL MOUNTED |  |  |  | 2 | 10.45.10.61 | 10.45.10.62 | 64695 | 202610 | UHG GLOBAL 150 | 2/2: ORDER COMPLETE 2/1: Access is showing complete - demarc provided. Pending testing completion. 1/25: Access install updated - now showing due to install on 1/28. 12/14-1/19: No change in status - LEC provided a 2/2 access install date - delayed due to Special Construction 12/8: Per Deidre, We finally heard back from Lumen/CenturyLink on the North Fort Meyers FL454-02-IM special construction. There are no charges being passed along for this build so we can proceed BAU with this order. 11/30-12/7: LEC provided a 2/2/2021 access install date - delayed due to Special Construction 11/19: The access provider is reassessing our SC quote. Being that UHG paid for SC through the Vz order, the access provider is uncertain if add’l SC charges will apply. As soon as we receive feedback from them we will advise. 11/9: Pending dates and scope of work. Per Melissa last week, VZ also provided SC charges and we need to find out if there are in fact two separate SC charges for our order and VZ's order. 10/21: Melissa advised this was sent to the business for approval 10/19: Advised Deidre of note from LEC regarding special construction - SPC OF $2,866.68. 10/6-10/12: Pending an install date from the LEC Embarq 9/25: Order rec'd
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX617-02-IM | UHG | Melissa Chapman | Wellmed | 8235 S. New Braunfels Ave., Ste 101 | San Antonio, TX |  | VS20152229 3102-0278 PON 7MS02434427 3102-BCGW | 2020-11-11 | 2020-11-23 | 2021-03-16 | 2021-02-01 |  | Y | BBEC.670115 | SBC | 31KRGN655164SW | 2021-03-01 | 1ST,BUILDING MAIN COMM ROOM,PER CONTACT DEMARC IN MAIN COMM ROOM; |  |  |  | 50 | 10.1.92.21 | 10.1.92.22 | 64729 | 202610 | UHG GLOBAL 150 | 2/2: ORDER COMPLETE 2/1: LEC showing a demarc from this past Friday - they have not yet sent a completion notice to AT&T. Pending confirmation so remaining milestones can be completed. 1/25: Fiber work completed last week ahead of schedule. Access install date adjusted to 1/27. Melissa advised (email) 1/19: Access instal date has been adjusted to 2/25. Fiber work is still on track for completion on 2/23. 1/4-1/11: Construction provided a 2/23 fiber completion date. Access install is scheduled for 3/1. Customer is currently CNR....site won't be ready until after 1/11. 12/21: Per Shawna Malone (Wellmed): This site is part of an acquisition that we will not be effective until 1/11/20. Can we schedule the site survey for some time after 1/11/20 and then access will not be an issue? 12/1-12/14: Construction provided a 2/23/21 fiber completion date. Access install is scheduled for 3/1/2021. Long interval per OSP team --- Placing 2,000-5,000ft Fiber, Splicing, Long Term Permits Required, Capital Cost exceeded regional threshold and the job will be bid and NTE required. 11/11: Order rec'd
| 2G Port/ 10G Access EaAVPN 10G Base-LR (SMF) | C1663-02-IM | UHG | Melissa Chapman | Teletech DC | 6900 S Peoia | Centennial, CO |  | VS20163700 3094-0815 7WS03901937 3094-BWPT | 2020-12-08 | 2021-01-21 | 2021-02-26 | 2021-01-27 |  | Y | L4YS.862924 | ADE LNS | COKGGS100149TPM | 2021-01-18 | 040414.13/FF2/13/04/117 & 118 01.0A08.35.07 JK21&22 (ZAYO KNOWS IT AS IDF-01R CK A63-B47 RU6&7 |  |  |  | 2 | 10.191.22.241 | 10.191.22.242 | 65436 | 202610 | UHG GLOBAL 150 | 2/1: ORDER COMPLETE 1/26: Escalation to be sent today for missed WOT (Wiring) date - was due yesterday. 1/21: Pending completion - Wiring due 1/25 - DD is 1/29. 1/20: Sent LOA to Melissa. 1/19: We've received R80 completion notice from the LEC on the access. Demarc provided. Pending wiring and testing completion. NOTE: The LEC provided a lot of demarc details - please check on these and advise if they're in the proper format for the end user. If not I'll escalate back to the LEC. 1/11: Access install scheduled for 1/18. 1/4: Site visit scheduled for 1/13. 12/8: Order rec'd
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX634-02-IM | UHG | Melissa Chapman | Wellmed | 207 S FM 548, Suite A | Forney, TX |  | VS20161399 3102-0238 7MS02437723 3102-BCHK | 2020-12-09 | 2020-12-16 | 2021-02-22 | 2021-02-01 |  | Y | BBEC.686083 | SBC | 14KRGN889648SW | 2021-02-01 | 1ST FLR,TELCO RM |  |  |  | 50 | 10.1.87.233 | 10.1.87.234 | 64626 | 202610 | UHG GLOBAL 150 | 2/2: ORDER COMPLETE 2/1: Fiber work completed on schedule on 1/27. Pending completion of access (today 2/1) 1/4-1/25: Fiber work scheduled to complete on 1/27. Access install scheduled for 2/1. 12/24: Site visit delayed (CNR) but rescheduled for 12/28. 12/21: Pending an access install date - FOC due back by 12/28. Site visit scheduled for 12/22. 12/9: Order rec'd
New | CANCELLED 20M Port / 50M Access Ethernet AVPN 1000Base-SX | II553-04-IM | UHG | Melissa Chapman |  | ITC Green Centre -No. 18, Banaswadi Main Road , Maruthi Sevanagar | Bengaluru (Bangalore) Urban, Karnataka India |  |  | 2020-11-06 | [13 empty] | 10.1.95.165 | 10.1.95.166 | 65193 | 202610 | UHG GLOBAL 150 |  | 2/9: Moved to completed per Melissa - not moving forward with the order.
New | EXPEDITE - CANCELLED 10M Port / 20M Access Ethernet ADI Electrical Handoff - RJ45 MACD Req'd After Completion | PA007-09-IJ | UHG | John Sergot | COMCAST ORDER | 15 Campus Blvd. 1st Floor MPOE | Newtown Square, PA |  | 1-EHYRR3Z 3102-0439 PON 7ESC2952491 3102-BCHC | 2020-11-24 | 2020-12-07 | 2021-02-16 |  |  |  | MMEC.741202 | Comcast | 11KGGS026334CBCL | 2021-02-10 | [10 empty] | 2/8: Issued cancellation on Friday 2/5 per John's request. 2/1: Per an update from Carrier Management: COMCAST EXECUTIVE MGMT TEAM CONFIRMED RECEIPT OF SUPP (PON 7ESC2952491 - VERSION AE - SUPPED 1/26 W/REQ'D DD - 2/10) - LEC PROVIDED AN ETA FOR MORE DEFINITES WITHIN 4-5 BUS. DAYS. MORE DETAIL ARE ANTICIPATED ON 2/5 COB, BUT URGENTLY DRIVING FOR MORE INFO TO BE PROVIDED SOONER 1/26: Carrier Management engaged (Quentin Thomas) - working on pushing Comcast for date. Combo PON 7ESC2952491 has been supped to change hand-off to 1000-base-SX and update SPEC to CWEFPM. 1/22: John S confirmed OK to go with fiber and MMF handoff / LC Connector. The AT&T order supp has been completed to change from 100Base-TX to 1000Base-SX. I have resent the PON# PON 7ESC2952491 to Comcast - follow up with Heather sent (she was OOO on Friday 1/22) so pending response. 1/19: Ticket assigned internally - working with ordering to see what can be done to supp the order with the proper coding that Comcast requires to change to Fiber inside wiring (w/ keeping 100Base-TX handoff) 1/15: Heather Smith (Comcast) advised that on her internal call they confirmed that delivering via coax as transport will require construction, but that they do have fiber in this building they can use. She suggested that we supp to change transport type to fiber and she’ll do her best to expedite. From talking with my internal team, I’m told they believe there is a way to change coding on the order to change it to Fiber with a 100Base-TX handoff without having to cancel and reissue the order. I requested the ordering team engage their SME group to find out what coding is required and the process to get the order supp’d. 1/11: Comcast’s Executive Mgmt team reports that they're working to compress the 2/10 estimated date. They informed us that the order is slightly delayed because the LCON was unavailable for a 1/7 dispatch and that the visit will need to be rescheduled when the LCON is available. At this time the LEC is pending their field ops team coordinating with the customer for that visit. The LEC has not flagged the order CNR (Customer Not Ready) but they are escalating for an updated dispatch timeslot with more news to come within 4-5 business days. If the LEC is able to dispatch, there is a pretty good chance the 2/10 ECD will be compressed. More details are anticipated by 1/15 COB but our team is driving for status to be provided sooner. AT&T Carrier Management remains engaged and they spearheading the push for an improved date. 1/4: No improvement yet...Next update from LEC is this week 12/24: Update from Comcast regarding the COAX issue.....“The transport for this will be COAX this is what the building is lit with and what their current service is provided on. The handoff is RJ45. I did send a CNR yesterday but we have cleared the line for coax transport and a new FOC should be issued today.” 12/21: UPDATE: DEIDRE....."was able to pull an AT&T LNS quote, and it allowed me to quote optical! Do you want me to submit a new order using AT&T access? If so, let me know SMF or MMF." ---- JOHN: "Is Verizon not an option? I don’t believe that LNS has fiber into this building." 12/21: LEC Comcast provided a 2/10/2021 install date on the 16th. The PON was resent to them on the 17th once the expedite was applied and we're awaiting Comcast's best/final for install. ----------CM TIER ESC TEAM************************ COMCAST EXEC MGMT TEAM ADVISED THIS CKT ORD IS CLASSIFIED AS A "CLASS D" BLDG, WHICH THEY CATEGORIZE AS NEW CONSTRUCTION REQ'D WITH A 60-75 BUSINESS DAY ECD (CONSTR ONLY) WHERE LEC HAS "NO EQUIP" AT CSTRS SITE & PERMITTING REQ'D. LEC INFORMED OF POTENTIAL DELAYS AS S/S RESULTS ARE TO INCLUDE ASSOCIATED BUILD COST, POTENTIAL PERMITS NEEDED, & ALL PARTICULARS RELATED TO SOW W/MILESTONE DATES, WHICH THEIR CONSTR & INTERNAL TEAMS WILL DETERMINE NEEDED WRK. LEC UNABLE TO SPECULATE W/REGARDS TO THEIR B&F &/OR "POTENTIAL", OVERALL ECD. LEC MENTIONED OF POSS. DELAY W/INFO W/APPROACHING HOLIDAY WHERE RESOURCES ARE LTD. LEC REFERENCED THEIR OFC'S CLSD 12/24 -12/25. THUS, MORE DETAILS ARE ANTICIPATED ON 12/29 COB, BUT URGENTLY DRIVING FOR MORE INFO TO BE PROVIDED SOONER (NO GUARANTEES). CARRIER MGMT TIER. NEXT F/U 12/29/2020 12/15: John OK'd the $4K expedite fee. The expedite request has been submitted. Request #: 15562057 12/7-12/14: PON was released to the LEC Comcast on 12/1. FOC is showing due back to AT&T by 1/6. The overall target due date for handover to UHG is currently 2/16/21. 11/25: Per Deidre, Handed off to ordering 11/24: Order rec'd - PLEASE BE SURE THAT THIS ORDER IS NOT PLACED ON THE CURRENT UVN RING AS UHG IS WORKING TO DISCONNECT IT. UHG cannot wait for the optical handoff - note this is an electrical handoff request. -- Once circuit is turned up we will need to move the below ip addresses from the old circuit to the new circuit (scheduled cut). ip route 12.53.160.96 255.255.255.224 12.53.160.126 ip route 12.152.59.224 255.255.255.224 12.53.160.126
New | 50M Port/ 50M Access EaAVPN 1000 Base-SX | NAMM Project Tiger CA082 | UHG | Melissa Chapman | NAMM | 40690 California Oaks Rd, Suite A | Murrieta, CA |  | Tracking Reference Number: 1-ET9ONZV VS21003294 3102-0022 PON 7WSC3905294 3102-BCHR 3102-BCHS | 2021-01-11 | 2021-01-12 | 2021-03-17 | 2021-02-05 |  | Y | BBEC.685968 | Frontier-CTF | 45KRGN539999FTNC | 2021-02-16 | SL###SHLF###PRT05#PHY1ST FLOOR ELECTRICAL ROOM WALL MOUNTED ID ON WEST WALL #JKSFP-5D#EXTN#TAGY |  |  |  | 2 | 100.69.0.14 | 100.69.0.13 | 64604 |  | UHG NAMM | 2/8: ORDER COMPLETE 2/1: Access install completed ahead of schedule. Pending completion of milestones (Engineering, wriring, design) and final testing. AERO Design ticket 1741119 to complete Engineering 1/26: Frontier access due to install on 2/16. 1/25: Pending FOC from Frontier-CTF - FOC due back by 2/18. 1/11: Pending USO's - Deidre
| 20M Port/ 50M Access Managed EaADI 1000 Base-SX - MMF LC BVOIP | CA109-08-IJ | UHG | John Sergot |  | 18 Centerpointe Drive | La Palma, CA | IP21002728 | 1018311208 3102-0733 PON 7WS03905457 3102-BCHX | 2020-12-09 | 2021-01-20 | 2021-02-09 | 2021-02-09 | Yes |  | BBEC.632347 | SBC ONNET-5 | 13KRGN605330PT | 2021-02-09 |  |  | WAN IP Address: 32.132.27.64 AR IP Address: 32.132.27.65 CR IP Address: 32.132.27.66 | [7 empty] | 2/10: ORDER COMPLETE 2/1-2/8: Access install scheduled for 2/9. - Reached out to ABS Staging team for status of the managed router. UPDATE: Equipment team confirmed that the router was shipped by UPS via tracking# 1ZX1093Y0159538079 and it was delivered on 1/15/21 as mentioned below. 1/25: CNR - agent Subham Bose reached out to John for site readiness. John S reached out to Jon Seung for status. 1/19: Access install scheduled for tomorrow 1/20. Router was delivered by UPS on Friday 1/15 at 10:19 AM -- Rec'd by ROSEMARY (FRONT DESK) 1/14: Router shipped to Jon Seung, 18 CENTERPOINTE DR, LA PALMA CA 906231028. UPS TRACKING INFO 1ZX1093Y0159538079. 1/12: ADI order - need uso's 12/21: Pending decision from John S (UHG) on whether we are going ADI with AT&T provided router or AVPN with customer provided router 12/9: Order rec'd - Please place an order for a new internet circuit to be used for SIP
| 300M Port/ 300M Access EaADI 1000Base-SX LC | CT008-05-IJ | UHG | John Sergot | Prohealth CT RNH | 3 Farm Glen Boulevard | Farmington, CT |  |  | 2021-01-20 |  |  |  | No | [15 empty] | 2/18: Per John, order cancelled. 2/16: Per Rachelle, she sent the presigned contract addendum to John last week (we needed access contract when selling at the OAPI rate) 1/20: Pending USO's - Assigned as of 2/9
New | CANCELLED 50M Port/ 100M Access EaAVPN 1000 Base-SX | TX584-02-IM | UHG | Melissa Chapman | Wellmed | 125 E. Grubb Drive Suite 105 | Mesquite, TX | VS20127923 | 3102-1140 7MS02426288 3102-BCFC | 2020-09-23 | 2020-09-29 | 2020-12-24 |  | Cancelled |  | IUEC.601866 | SBC | [7 empty] | 10.45.11.21 | 10.45.11.22 | 64798 | 202610 | UHG GLOBAL 150 | 10/15: ORDER CANCELLED PER MELISSA. Keep on sheet as this will need to be reordered. Requested cancellation of this order since building won’t be ready until early 2021. 10/12: CNR - site visit not scheduled. PON will need to be resent once we confirm LCON is correct and will allow site visit. LCON KHANH NGUYEN, 817 368-6081 and ALCON KELLY SJELIN 952 833-7371 10/6: Pending an install date from the LEC SBC. 9/23: Order rec'd
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX626-02-IM | UHG | Melissa Chapman | Wellmed | 325 W 20th Street | Houston, TX | VS21010581 | 3102-0927 PON 7MS02444445 3102-BCJH | 2021-01-25 | 2021-01-28 | 2021-04-05 | 2021-02-19 | Yes | Y | BBEC.672955 | AT&T SOUTHWEST | 28KRGN751062SW | 2021-02-19 | 1ST FLR, NETWORK RN, RELAY RACK, 3903,PORT#1, TAGGED |  |  |  | 50 | 10.1.93.165 | 10.1.93.166 | 65370 | 202610 | UHG GLOBAL 150 | 2/22: ORDER COMPLETE 2/16: Fiber work completed - pending access install completion (due 2/19) 2/1-2/8: Construction fiber work scheduled to complete on 2/16. Access install scheduled for 2/19. 1/25: Order rec'd
New | CANCELLED 500M Port/ 1G Access EaAVPN 1000 Base-SX | TX547-02-IM | UHG | Melissa Chapman | Wellmed | 19500 IH-10 West | San Antonio, TX | VS20105787 | 3102-1611 PON 7MS02418983 3102-BCCF | 2020-08-03 | 2020-08-07 | 2021-03-01 |  | No |  | IZEC.645436 | ATT SW | 31KRGN654947SW | 2020-02-11 | [5 empty] | 10.1.85.29 | 10.1.85.30 | 64710 | 202610 | UHG GLOBAL 150 | 3/1: Per email from Melissa (and per Greg Kieschnick, PE ¦ PMP ¦ LEED® AP - T 713.822.4066 ): room will not be ready until 11/21. Order CANCELLED. 2/22: POSSIBLE CANCELLATION 2/8-2/16: Site Delays - CNR - CNR Reason changed from "CNR-Path/Pwr/Grd/Space" to "CNR-Bldg Not Ready". Per construction...building is not under construction and at 179 cycle time days. Please inquire about canceling and re-issue once building is closer to being ready. 8/24-2/1: Fiber infrastructure scheduled to complete 2/4. Access install scheduled for 2/11. Melissa confirmed this is totally new construction so no issue with dates at this time. 8/17: Site visit completed on 8/12 - pending update on Fiber work and dates for completion of infrastructure and access. 8/10: Site visit scheduled for 8/12. 8/3: Order rec'd - This is a ground up build.
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX632-02-IM | UHG | Melissa Chapman | Wellmed | 1315 St. Joseph Pkwy Suite 1310 | Houston, TX | VS21011402 | 3102-0929 PON 7MS02444768 3102-BCJJ | 2021-01-22 | 2021-02-19 | 2021-02-19 | 2021-02-26 | Yes | Y | BBEC.665754 | AT&T SOUTHWEST NEARNET-15 | 28KRGN751071SW | 2021-02-19 | 10TH FLR,ELECTRICAL RM, WALL MNT PNL PORTS 5/6 | 1000Base-SX MMF |  |  | 50 | 10.1.90.81 | 10.1.90.82 | 64675 | 202610 | UHG GLOBAL 150 | 3/1: ORDER COMPLETE 2/22: Access install rescheduled for 2/26. 2/8-2/16: Access install scheduled for 2/19. 2/1: Pending an install date from the LEC ATT SW (Nearnet) - Site visit scheduled for Wed 2/3. 1/22: Order rec'd
| 500M Port/ 1G Access EaAVPN 1000 Base-SX | MA710-02-IM | UHG | Melissa Chapman | Optum Analytics | 70 Innerbelt Rd. | Somerville, MA | VS21014061 | 3102-0968 PON 7NS01993623 3102-BCJR | 2021-01-27 | 2021-02-04 | 2021-04-09 | 2021-03-05 | Yes | Y | IZEC.683006 | ADE LNS | MAKFGS100143TPM | 2021-02-22 | 020002.02 PANEL 6 PORTS 7&8 |  |  |  | 2 | 10.1.89.153 | 10.1.89.154 | 65053 | 202610 | UHG GLOBAL 150 | 3/8: ORDER COMPLETE 3/2: Tier 2 Carrier Mgmt Update on ACCESS AERO TKT: 1816614 - PER OPERATIONS SPECIALIST - TRANSCEIVER (SFP) WAS ALREADY REPLACED, CONTACTED PROVISIONING TECH WITH MANAGER TO ADVISE IF ORDER CAN BE COMPLETED OR TO PROVIDE ACTIVE ROADBLOCK. 3/1: Access install date was missed although it appears install did take place but issues arose during testing. TIER2 CM engaged. (AERO TKT 1816614.) - issue showing as "WRONG TRANSCEIVER AND REPLACEMENT NEEDED" at the CO level. 2/9-2/16: Access install moved out to 2/22 due to LCON change. 2/8: Access install scheduled for 2/19. UPDATE: Per Melissa, LCON had to be supp'd to change to Name: Raffaele Mortillaro Phone: 9785599481, Email: raffaele.mortillaro@optum.com. Possible delay on 2/19 install date due to change. 2/3: Added to the HOT list per Melissa's request 1/27: Order rec'd
| SPECIAL CONSTRUCTION 10M Port/ 50M Access EaAVPN 1000 Base-SX | UT028-01-IM | UHG | Melissa Chapman | OptumCare | 6321 S. Redwood Road #201 | Taylorsville, UT | VS20155089 | 3102-0436 PON 7WS03900139 3102-BCHB | 2020-11-18 | 2020-12-01 | 2021-05-07 | 2021-03-09 | No | Y | BBEC.663494 | Qwest | 69KXGS572532MS | 2021-04-30 | UNI WALL MOUNT CIENA 3916M OPTICAL PORT3 MULTIMODE. | 1000 Base-SX |  |  | 192 | 10.1.91.61 | 10.1.91.62 | 65104 | 202610 | UHG GLOBAL 150 | 3/11: ORDER COMPLETE 3/8: Adding to WWR sheet.Engineering, Wiring and Design all completed last week. 3/1: Rec'd R80 notification that access has been installed ahead of schedule. Pending remaining milestones being completed (Engineering, Design, Wiring.) Issued AERO Design ticket 1835939 to have VLAN PON issued. 2/9-2/22: Qwest provided a 4/30 install date. 2/8: PON resent on 2/5. 2/2: Per Rachelle, paperwork submitted back to AT&T on 2/1, in AT&T 's hands, paperwork sent back to SCON team same week. 1/21: Rachelle sent Melissa the pre-signed Special Construction agreement 1/11: SOTS notes from LEC indicating Special Construction - $1,000.00. Sent note to sales to look out for this one. 1/5: Melissa provided email advising site is ready - CNR coding removed - PON resent 1/4: Order showing CNR - FOC delayed. Per LEC Qwest....."SUPI: N RCODE: 1S=BUILDING NOT READY, CUSTOMER WILL ADVISE RDET: CUSTOMER NOT READY - ADDL INFORMATION TO FOLLOW." ---- CNR coding will need to be removed and PON resent. 12/21: PON sent on 12/17 - FOC due back by 1/22/21. 12/15: USO's are LOADED. Issued request to ROSE CRAWFORD (ATT Provisioning) to have PON sent to the LEC (FOD missed.) 12/14: Requested sales reissue as the USO's are still not loaded. 12/7: Ticket issued (IOS) to have USO's loaded in SOTS. 11/18: Order rec'd
| 250M Port/ 1G Access EaAVPN 1000 Base-SX | TX491-06-IJ | UHG | Melissa Chapman | HealthMarkets | 9151 Boulevard 26 Bldg B | North Richland Hills, TX | VS21009006 | 3102-0808 PON 7MS02443827 3102-BCJD | 2021-01-21 | 2021-02-02 | 2021-04-08 | 2021-03-05 | Yes | Y | IZEC.644261 | AT&T SOUTHWEST ONNET-5 | 14KRGN889974SW | 2021-04-08 | 2ND FLOOR DATA RM RELAY RACK CIENA PORT 5 | 1000Base-SX MMF |  |  | 50 | 10.1.2.2 | 10.1.2.1 | 64514 | 202610 | UHG GLOBAL 150 | 3/8: Fiber work completed ahead of schedule last week. Access installed - COMPLETE - READY FOR TURN UP P&P 2/8-3/1: Fiber work scheduled to complete on 4/7. Access install scheduled for 4/8. No Construction letter provided yet. 2/2: Site visit delayed but scheduled - showing scheduled for today 2/2. 2/1: Pending an install date from the LEC ATT SW (Onnet) 1/21: Order rec'd
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX642-01-IM | UHG | Melissa Chapman | Wellmed | 2327 N. Riverside Drive | Fort Worth, TX | VS21018709 | 3102-1148 PON 7MS02447693 3102-BCJV | 2021-02-09 | 2021-02-12 | 2021-04-08 |  | No |  | BBEC.640109 | ATT SW | [7 empty] | 10.1.95.1 | 10.1.95.2 | 65082 | 202610 | UHG GLOBAL 150 | 3/9: Issued HITS ticket to cancel this order per Melissa's request. 3/1-3/8: AS OF 2/24, THE LCON STILL CANNOT COMMIT TO A SITE VISIT DATE AND TIME - THEY ARE CURRENTLY IN THE PROCESS OF PURCHASING THIS LOCATION, AND CAN'T MOVE FOWARD UNTILL THE LEASE HAS BEEN SIGNED 2/22: Site visit delay (CNR) LEFT VM AND SENT EMAILS TO LCONS ROGER SEDBERRY 817-782-7400 ROGER.SEDBERRY@US.AF.MIL AND RONALD MARCHAND 817-782-7400 RONALD.MARCHAND1@NAVY.MIL Lcon EMMANUEL UDOJI, 2147076875 NO RESPONSE 2/16: Site visit scheduled for 2/18. 2/9: Order rec'd
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | CA477-01-IM | UHG | Melissa Chapman | Optum RX | 26243 Research Road | Hayward, CA | VS21024089 | 3102-0431 3102-BCKB | 2021-02-19 | 2021-03-03 | 2021-03-03 | 2021-03-04 | Yes | Y | BBEC.673500 | PAC BELL ONNET-5 | 86KRGN598179PT | 2021-03-03 | 1,MPOE,TAGGED M. MODE OPTICAL PORTS 7 AND 8 |  |  |  | 50 | 10.1.95.61 | 10.1.95.62 | 64549 | 202610 | UHG GLOBAL 150 | 3/8: ORDER COMPLETE 3/2: Access install scheduled for tomorrow 3/3. 2/22: Order rec'd
New | 10M Port / 20M Access Ethernet ADI 1000Base-SX (MMF) | PA007-09-IJ | UHG | John Sergot | VERIZON NORTH ORDER | 15 Campus Blvd. 1st Floor MPOE | Newtown Square, PA | IP21002782 | 3102-0177 PON 7ES02955135 3102-BCHT | 2021-01-20 | 2021-01-27 | 2/15 (DELAYED) | 2021-02-23 | No |  | MMEC.582155 | Verizon North | 11KFGS314138PA |  | 1ST FLOOR DATA ROOM WALL MOUNTED - NID #3 - TAGGED |  | WAN IP Address 12.124.23.16 ATT PE Address 12.124.23.17 Broadcast IP 12.124.23.19 Subnet Mask 255.255.255.252 1st USABLE 12.124.23.18 | [7 empty] | 3/15: John confirmed up and working on new circuit - disco issued for old circuit. Order complete. 3/3: John forwarded email to their engineer to confirm details and date and time for test and turn up. 3/2: Rachelle issued MACD to MOVE IP's from existing circuit. Has to be hot cut. 2/23: READY FOR TTU. 2/23: Escalation to AM Jane Tansor and District Escalation Mgr Leigh Canada. They are working to get status and completion of the POP hardware issue. ORDER COMPLETE 2/16: Order still not yet complete as of this morning. Will follow up with team that is working this ticket and escalate for status and ETA. The download issue is due to Router Hardware issue. It has been already reported by NOC to Metro Data. They will scheduled the RE replacement in a few days. No ETA yet. There has been a AOTS ticket 000000296887914 created for this issue. Biz Case: UHG is waiting on this circuit to complete so they can submit a disco order to disconnect a $42,000/mo UVN ring. 2/8 PM: RID (Engineering) is complete - working on completing out rest of the order. 2/8: Issued LEVEL1 Escalation on AERO ticket - Per Design Assembler: JUST SPOKE TO THE LEC AND WAS TOLD THE ORDER WAS STUCK IN THE SYSTEM. THEY ARE GOING TO REFLOW THE FOC FOR THE EVC PON. IT COULD TAKE AS LONG AS 24 HOURS. THIS SHOULD BE RID COMPLETED BY MONDAY 2/4: Issued AERO DESIGN TICKET# 1753557 to have VLAN PON 7ESV4624533 worked - missed FOC yesterday 2/3. 1/20: Pending USO's
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | NV190-02-IM | UHG | Melissa Chapman | 4C Medical | 8410 W. Warm Springs Rd. Ste 10 | Las Vegas, NV |  |  | 2021-02-26 |  |  |  | No | [10 empty] | 10.1.94.177 | 10.1.94.178 | 65295 | 202610 | UHG GLOBAL 150 | 3/9: Per Rachelle was put on hold by customer as speed may change - replaced with NV190-05-IM 2/26: Order rec'd
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX633-02-IM | UHG | Melissa Chapman | Wellmed | 1611 N. Beltline Road Suite A | Mesquite, TX | VS20161438 | 3102-0317 PON 7MS02437743 3102-BCHL | 2020-12-07 | 2020-12-16 | 2021-03-17 | 2021-03-10 | Yes | Y | BBEC.660003 | SBC | 14KRGN889636SW | 2021-03-02 | 1,OUTSIDE REAR,WALL, PORT 1, TAGGED |  |  |  | 51 | 10.1.93.25 | 10.1.93.26 | 64677 | 202610 | UHG GLOBAL 150 | 3/12: ORDER COMPLETE 3/9: Resent PON to the LEC this morning to prompt them for an install date now that fiber work is complete. 3/8: Infrastructure Complete as of 3/5. Pending access installation. 3/1: Fiber work delayed - moved out to 3/8. Access install will be moved out as well (pending new date) 12/24-2/22: Fiber infrastructure due to complete on 2/24. Access install scheduled for 3/2/21. Sent fiber letter to Melissa - EF offer accepted so AT&T will be completing this work. 12/21: FOC due back by 12/24. Site visit scheduled for 12/23. 12/7: Order rec'd | 2021-03-12 | ORDER COMPLETE
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX620-02-IM | UHG | Melissa Chapman | Wellmed | 7737 Southwest Fwy #640 | Houston, TX | VS21010433 | 3102-0920 PON 7MS02444402 3102-BCJG | 2021-01-25 | 2021-02-18 | 2021-03-12 | 2021-03-09 | Yes | Y | BBEC.632269 | AT&T SOUTHWEST NEARNET-15 | 28KRGN751060SW | 2021-03-09 | 6TH FLR, STE 640 IT RM, CN5140, PORT-2 |  |  |  | 50 | 10.1.86.137 | 10.1.86.138 | 64627 | 202610 | UHG GLOBAL 150 | 3/12: ORDER COMPLETE 3/2-3/8: Received a 3/9 access install date 2/26-3/1: Rec'd email from Melissa that the site is ready - issued PON back to the LEC this afternoon. Pending new date. 2/25: Email from Melissa - Customer requirements will be completed by 3/4/2021 2/22: PON supp'd for new install date - target EAD is 3/3 but noted order saying IT room will be ready 3/5. NEED TO SUPP THIS FOR A 3/5 TARGET INSTALL DATE OR AFTER - IT ROOM WILL BE COMPLETED THEN 2/1-2/16: Access install scheduled for 2/18. ATT SW (Nearnet) 1/25: Order rec'd | 2021-03-12 | ORDER COMPLETE
| 10M Port/ 50M Access EaAVPN 1000 Base-SX | TX621-02-IM | UHG | Melissa Chapman | MediCorp Wellmed | 1315 St. Joseph Parkway Suite 1309 | Houston, TX | VS21015942 | 3102-1108 PON 7MS02446608 3102-BCJT | 2021-01-29 | 2021-02-16 | 2021-03-12 | 2021-03-11 | Yes | Y | BBEC.640150 | AT&T SOUTHWEST ONNET-5 | 28KRGN751181SW | 2021-03-10 | FLR 10 MECH RM, PNL 1, PORTS 7/8, |  |  |  | 50 | 10.1.92.149 | 10.1.92.150 | 64578 | 202610 | UHG GLOBAL 150 | 3/12: ORDER COMPLETE 3/2-3/8: Received a 3/10 access install date. (CHANGED TO 3/11.) 3/1: Resent PON to the LEC to get a new install date. 2/19: JEP'D CO1W - DELAYED DUE TO INCLEMENT WEATHER - NO ETA JUST YET 2/16: Install due to complete today. 2/9: Pending an install date from the LEC ATT SW (Onnet) - UPDATE ACCESS INSTALL SCHEDULED FOR 2/16 1/29: Order rec'd | 2021-03-12 | ORDER COMPLETE

## MACD Completed
UHG PON | Address | City, ST | Order Type Service | CPDD | Sales to Ordering | Order/USO | RAW USO | ATT Ckt ID's | LEC / PON | LEC Ckt ID | Estimated Due Date | Complete Date | Demarc | STATUS | Order Mgr. / Current Responsible Party
UTN18-08-CM | Brentwood | Tennessee | please upgrade to 50mg port |  |  | 3094BTWH & 3094BTWG |  | IUEC.840811..ATI |  |  | 2018-10-15 |  |  | Received request on 08/28/18 Order has been submitted and a USO generated, expected DD is 10/15/18 On target to be completed 10/15/18 Completed 10/18/18 | Ana Chavez
TX406-03-CM | Austin | Texas | upgrade to 100mg |  |  | 3094BTWJ & 3094BTWK |  | IUEC867796 |  |  | 2018-10-15 |  |  | Received request on 09/10/18 Expected DD is 10/15/18 On target to be completed on 10/15/18 Completed on 10/17/18 | Allan Musni
C1626-05-CM | Alpharetta | Georgia | Please upgrade port BMEC881816 to 500M |  |  | 3094BTXR, 3094BTXQ |  | BMEC.881816..ATI |  |  | 10/24/18 |  |  | Received request on 09/13/18 Estimated Due Date is 10/24/18 Completed on 10/8/18 | Melanie Ontay
GA777-13-CM | Atlanta | Georgia | Existing 1G port and access with one VLAN (UHG Global 15). Need two MACDs, one to reduce current VLAN for UHG Global 150 from 1G to 900M and then add a second VLAN of 100M in support of VPN, ASN 65138, CE IP 10.1.90.185, PE IP 10.1.90.186 |  |  | 3094BTZX 3094BTXS |  | IZEC.574366 | [5 empty] | Received request on 9/18/18 Original order was cancelled due to IP issues, new order has a ticket opened on it to clear an issue with the new VLANs New orders issued and completed on 10/15/18
MI041-06-CM | Lansing | Michigan | Upgrade to 50M |  |  | 3094BTXV, 3094BTXW |  | BBEC569998 | [5 empty] | Received request on 9/20 Due Date is 10/26/18 Completed on 10/09/18 | Marcelina Arizo
VA074-05-CM | Falls Church | Virginia | Upgrade to 20M |  |  | 3094BTXZ, 30941089 |  | BBEC564759 | [5 empty] | Received request on 9/21 Completed on 10/4 | Marcelina Arizo
PA062-06-CM | Horsham | Pennsylvania | Upgrade to 200M |  |  | 3094 BTXY, 30941083 |  | BKEC984685 | [5 empty] | Received request on 9/20 Completed on 10/4/18 | Marcelina Arizo
PR516-07-CM | Guaynabo | Puerto Rico | Upgrade BBEC511424 to 50M |  |  | 30941435 3094BVBJ |  | BBEC511424 | [5 empty] | Received Request 10/11, order placed 10/12 USO's received on 10/22/18, with an estimated DD of 10/26 Order cmpleted on 10/26 | Angel Lou B Cadiao
C1584-05-CM |  | CARROLLTON, TX | Upgrade port to 1 gig |  |  | 3094-0805 |  | IZEC520861ATI |  |  | 2018-08-03 |  |  | Ready to schedule 08/14 - Per Cliff Remigio to Melissa: I have emailed the Site Contact to schedule the cutover date with ATT. We are currently waiting for their feedback. OM wokring with the end user to schedule, there will be downtime per OM Scheduling for 10/26 at 22:15 Central Cancelled the activation Order cancelled per Melissa Cancelled Unable to put on hold per OM | NOEL HORMILLOSA
C1567-07-CM | 910 15TH ST, | Denver, CO | Upgrade from 600 mb to 1G |  |  | 3094-BTRD |  | IZEC.575632..ATI |  |  | 2018-08-10 |  |  | Ready to schedule 08/14 - Per Cliff Remigio to Melissa: I have emailed the Site Contact to schedule the cutover date with ATT. We are currently waiting for their feedback. OM wokring with the end user to schedule, there will be downtime per OM Scheduling for 11/16 at 22:15 Central Project cancelled per Erickson Santos on 11/15/18 Cancelled Unable to put on hold per OM | Noel Hormillosa
UVA01-05-CM | Richmond | Virginia | Upgrade to 50M |  |  | 3094BVCN, 3094BVCP |  | BBEC506409 | [5 empty] | Order Received 10/23/18 Order is due to complete on 11/27 Provided name to OM to schedule with Clifford, looks like it is ready Order has been cancelled per the OM | Benjamin Chinchilla
IL722-13-CM | Elk Grove Village |  | Reduce speed down to 100M |  |  |  |  | IZEC.557077 | [5 empty] | ATT Account 8310005570653, from Russell Hawkins, Sent to ATT on 10/23. AVPN port Billing change from HiCap to Fixed. New fixed bandwidth will be 100M. Completed on 11/19/2018 | Susan Ines
PA134-04-CM | Plymouth Meeting | Pennsylvania | Please upgrade to 20M port on circuit BBEC588445 |  |  | 3094BVBD 3094BVBF |  | BBEC588445 | [5 empty] | Received Request on 10/8/18 Order has overall Due Date of 12/5. Have sent an email to the OM to understand why the date is out to December. Per the OM this will auto complete out on 11/15 Sent not to OM to see if this is ready to cut Sent another note to the OM to see if this is ready to cut | Benjamin Chinchilla
CA858-05-CM | Rancho Cordova | California | Upgrade IUEC560646 to 100M |  |  | 3094BVBM 3094BVBN |  | IUEC560646 | [5 empty] | Order has been cancelled per Susana Order will be cancelled per John Raymondo CUT DATE: 2019-01-11 TIME: 11:30PM EST (10:30PM CST) Order submitted on 10/17/18 Scheduled to be completd on 11/20/18 Ready to schedule, provided name to OM Susana Ines Scheduled for 12/14 1030pm ct to activate | Susan Ines
FL358-04-CM | Tampa | Florida | We need to change the IP addressing on 0.1.89.75/30 10.1.89.76/30 on BBEC.542236 |  |  | 3094BVFX |  | BBEC.542236 | [5 empty] | Completed on 1/16/19 Submitted January 10, Order placed January 10th
IL046-04-CM | Chicago | Illinois | Upgrade to 100M PORT |  |  | 3094BTZV 3094BTZW |  | IUEC.982691 | [5 empty] | Hotcut Completed 2/14/19 OM working to re-schedule with Clifford. Sent emails to Clifford to re-schedule. Have not heard back from Clifford. Need to schedule a time to activate. Received Request on 10/2/18 Order placed, waitig on USO's Circuit has a Due Date of 11/12, but also has a CNR attached. Sent an email to the OM to understand why and how we remove. Per the OM Manager this is ready to schedule a cut. Melissa has engaged Cliff to get a scheduled time to cut. Per Cliff schedule this one for 11/9 @ 22:15 Central Rescheduled due to att maintenance. It does not appear to have been settled Re-sent to OM to work with Clifford to schedule Sent a note to Clifford for an update | Gilbert Francis D Amor
FL361-04-CM | Apollo Beach | Florida | Change ASN to 64644 on BBEC.501603 |  |  |  |  | BBEC501603 | [5 empty] | Order has autocompleted since not in use. . Submitted January 4th/2019
GA777-13-CM | Atlanta | Georgia | Existing 1G port and access with one VLAN (UHG Global 15). Need two MACDs, one to reduce current VLAN for UHG Global 150 from 1G to 900M and then add a second VLAN of 100M in support of VPN, ASN 65138, CE IP 10.1.90.185, PE IP 10.1.90.186 |  |  | 3094BTZX 3094BTXS |  | IZEC.574366 | [5 empty] | Cut scheduled for 12/16 10pm CST Need to re-schedule Scheduled Date: 2019-01-25 Time:11:30 PM EST (10:30PM CST) Received request on 9/18/18 Original order was cancelled due to IP issues, new order has a ticket opened on it to clear an issue with the new VLANs New orders issued and completed on 10/15/18 | Susan Ines
C1584-05-CM | Carrollton | Texas | Upgrade from 500M to 1G |  | VS19030017 | 30942311 3094BVHR |  | IZEC520861 |  |  | 2019-02-19 |  |  | Order auto completed on 2/19/19 Order submitted 2/12/2019 2/11/19, original order cancelled, need to re-submit upgrade order Ticket opened on 2/1 to clear out old order that was cancelled. Received 1/28/19
CA269-06-CM | Irwindale | California | Please upgrade from 10M to 50M |  | VS19021275 | 30942300 3094BVHJ |  | BBEC583425 |  |  | 2019-02-13 |  |  | Order completed 2/13/19 Order created 2/8/19 Order submitted 2/1/19 Received 1/30/19 | Susana Ines
C1641-01-IM | Ashburn | Virginia | Need to correct IP Adress |  | VS19026627 | 3094BVHL |  | IZEC.579184 | [5 empty] | Per Ann, work to be done Tuesday evening. VPN Name changed to UHGECC Global VPN Order submitted & Comp 2/13/19 Order Created 2/6/19
AL013-04-CM | Montgomery | Alabama | Please upgrade from 50 to 100M |  | VS19019407 | 3094BVGQ 3094BVGR |  | IUEC939588 |  |  | 2019-03-05 |  |  | Order auto completed on 3/7, Melissa to verify router. Sent email to Gilbert that this needs to be a hot cut. On track for 3/5, order will auto complete. Order created 2/5/19 Order placed 1/25/19 Received 1/24/19 | AMOR, GILBERT FRANCIS D <ga168k@abs.att-mail.com>
FL070-07-CM | Jacksonville | Florida | Upgrade from 100M to 200M |  | VS19021251 | 3094BVHG 3094BVHH |  | BREC870644 |  |  | 2019-03-07 |  |  | Sent email to OM needs to be a hot cut, however I see comp on 2/27. On target for 3/7 completion Order created 2/8/19 Order submitted 2/1/19 Received 1/31/19 | Susana Ines
|  |  | Disconnect 3147380647 |  |  | D571336 | [7 empty] | Order due 3/1/19 Order submitted 2/19/19
TX720-05-CM | Dallas | Texas | ASN# Change to 64795 from 64714 |  | VS18037438 | 3094BVJS |  | BMEC979220 | [5 empty] | Order due to cut on the evening of 3/12 at 1030 pm. Order system completed 2/23/19 Order Submitted 2/14/19, waiting on USO's Received 2/11/19 | Marcelina Arizo
PA007-09-CM | Newtown | Pennsylvania | ASN Change to 65297 |  | VS19038292 | 3094BVKD |  | IZEC591480 | [5 empty] | Changed AVPN ASN to 65297, auto completed on 3/1/19
| Aloharetta | GA | Add MD5 |  |  | 3094BVKS |  | IZEC521492 | [5 empty] | Need to add MD5 by 3/15
AZ034-04-CM | Tucson | Arizona | Upgrade from 10M to 50M Port |  | VS19036484 | 30942404, 3094BVJT |  | BBEC593781 |  |  | 2019-03-28 |  |  | Order is completed, sent email to OM to see if auto completed or if hotcut is needed. Sent email to OM to ensure hot cut compete, overall DD is 3/28. Escalating for USO's Order submitted 2/14/19, waiting on USO's Received 2/11/19
PR517-04-CM | San Juan | Puerto Rico | Upgrade from 60M to 200M |  | VS19036518 | 30942408, 3094BVJV |  | BREC609941 | [5 empty] | Order Auto Completed Order completed on 3/6. Sent email to OM, this needs to hot cut complete, overall DD is 3/6. Escalating for USO's Order submitted 2/14/19, waiting on USO's Received 2/12/19
| Islandia | New York | Add MD5 |  | VS19031642 | 3094BVJK |  | IUEC822422 | [5 empty] | Did not complete on 3/14, new cut date is 3/25 Emailed to Jason to see if the MD5 addition was a success. Order due to cut on the evening of 3/14 Order is due to completed on 3/6, sent email to OM to schedule hotcut with UHG Sent not to OM to see why in reject status and to schedule a cut date/time
PA007-10-CM |  | Pennsylvania | ASN Change to 64887 |  | VS19064195 | 3094BVLZ |  | IZEC591480 |  |  | 2019-04-09 |  |  | Order completed on 4/9/19 Order received 4/8 and placed 4/8
| Flushing | NY | Add MD5 |  | VS19078326 | 3094BVNK |  | BBEC567977 |  |  | 2019-04-29 |  |  | Order may be completed, verifying with OM
| Irvine | CA | COS change to Profile to profile 3826, 80% RT, 10/50/25/15/0 |  | VS19078359 | 3094BVNL |  | IZEC560657 |  |  | 2019-04-29 |  |  | Order may be completed, verifying with OM
| Hawthorn | CA | COS change to Profile to profile 3826, 80% RT, 10/50/25/15/0 |  | VS19078382 | 3094BVNM |  | IZEC511225 |  |  | 2019-04-29 |  |  | Order may be completed, verifying with OM
C1567-07-CM | Denver | Colorado | Upgrade from 600M to 1G |  | VS19031319 | 30942347 |  | IZEC575632 |  |  | 2019-03-13 |  |  | Waiting on Cliff to schedule Ready to cut, sent email to Clifford. Escalated to Area Manager for a response from the OM Order notated to be a hotcut, DD is 3/13, waiting on OM to validate readiness Sent email to OM to request a hot cut, still on target for 3/13. Order received 2/26 USH ticket created 2/18/19 Received 1/28/19 | Byron Gaston
| BLK Canyon, Phoenix | Arizona | Upgrade to 50M |  | VS19064905 | 3094BVMB 3094BVMC |  | BBEC560340 |  |  | 2019-05-09 |  |  | Schedule for 5/28 Ana working to schedule for 5/28 Sent note to OM ANA, to check if ready Orders due to complete on 5/9/19
| Bell Rd, Phoenix | Arizona | Upgrade to 50M |  | VS19065127 | 30942590 3094BVMD |  | BBEC560523 |  |  | 2019-05-09 |  |  | Schedule for 5/28 Ana working to schedule for 5/28 Sent note to OM ANA, to check if ready Orders due to complete on 5/9/19
IR508 | Dublin | Ireland | Add MD5 | [10 empty] | Per Christine, hoping to completed next week
| 19thAve Phoenix | Arizona | Upgrade to 20M |  | VS19065434 | 30942598 3094BVMF |  | BBEC507696 |  |  | 2019-05-09 |  |  | Scheduled 6/10 at 1130pm ET Ready to schedule, working with OM to secure 6/10 at 1030pm cdt Order has an issue and OM Ana working to resolve, no ETTTR as of now. Sent note to OM ANA, to check if ready Orders due to complete on 5/9/19
PA138-06-CM |  | Pennsylvania | Upgrade to 50M |  | VS19107173 | 30942906 3094BVQD |  | BBEC531772 | [5 empty] | Order completed on 6 /19/19 Order received 6/12/19
| 2301 S HAMPTON RD | Dallas | Change IP's |  | VS19115291 | 3094BVQQ |  | BBEC508792 | [5 empty] | Completed on 7/3/19 Submitted on 6/27, waiting on order numbers
UVA01-08-CM | 9020 STONY POINT PKY | Richmoned, VA | Upgrade from 10M-50M |  | VS19128847 | 30941935 3094BVRL |  | BBEC506409 |  |  |  |  | ok to move | Order completed on 8/1/19 7/30/19, Order received as of 7/30, Due Date on the order is 8/6 7/23/19, Unable to submit as the old cancel order is still in the system, working to resolve this issue. Submitted on 7/9, waiting on orders | Joben Perez
NV039-10-CM |  | Las Vegas, NV | Upgrade from 200M to 300M |  | VS19120698 | 30940054 3094BVQT |  | BDEC989937 |  |  |  |  | ok to move | Order completed 7/31/19 7/30/19 Escalated to Ana Chavez, she has escalated to 2nd Level Tech Manager to see when this will be ready 7/23/19 DD is scheduled for 7/22/19, need to contact the OM on this one. Submitted on 7/10 waiting on orders | Ana Chavez
|  | Kyle, TX | VLAN speed from 50M to 10M |  |  |  |  | BBEC530264 |  |  |  |  | ok to move | 8/19/19 This VLAN speed change was completed and ICORE reflects a speed of 10M. Order number 195373830 for VLAN speed change is complete.
TX410-07-CM |  | Austin, TX | Port Downgrade from 50M to 10M |  |  |  |  | BBEC530264 |  |  |  |  | Take off | 8/19/19 This circuit is for Kyle, TX, sent email to OM to see if this can now be worked. 8/5/19 Not sure if Austin and Kyle are the same location. There was a business center order to downgrade Kyle. TX. Sent email to Chris to confirm. Order submitted 7/23/19
TN017-76-CM |  | Teneessee | Upgrade to 200M |  | VS19132647 | 30942946 3094BVRN |  | BREC984597 | [5 empty] | 9/9/19 Order completed on 9/5/19 8/19/19 Escalated to OM Area Manager to see if we are able to complete sooner. 8/12/19 Due date on the order is 9/5/19 8/5/19, I believe this one was submitted in Business Center, have inquired as to whether or not it completed. Order received on 7/30/19, need asap and needs to be a hotcut
UNY14-09-CM |  | Islandia, NY | Port Upgrade from 50M to 100M |  | VS19130360 | 30941979 3094BVRM |  | IUEC822442 |  |  |  |  | Leave on verify speed | 8/19/19 Order completed on 8/19/19 8/12/19 Order is not in the system, escalated to Order Creator Clyde Order submitted 7/23/19
|  | Overland Park, KS | Add MD5 | [9 empty] | Leave on verify speed | Per Chris order auto completed. VS19134900 Project:ISR19080918879 Order Number 195444619 successfully submitted.
TX500 | Garland | TX | Add MD5 |  | VS19139962 | 3094BVSH |  | BBEC.505872 | [5 empty] | 9/9/19 Escalated to Gilbert Amor and his Manager to get this auto completed, they have sent to a tech to complete. Let OM Gilbert Amor know it was ok to auto complete this one as UHG is not using. Due date is 9/3/19 USH ticket opened as the system will not allow the order to flow. Order SR: 1-B9J841M submitted 8/14/19
UPA02-06-CM |  | Philadelphia, PA | Change handoff to 1000Base LX |  | VS19120917 | 30940255 |  | BBEC558013 |  |  |  |  | Chris has been told that LNS will not do a move order and a new order is needed | 9/30/19 We will need to cancel/disconnect this circuit as a new one is being ordered to replace 9/9/19, Per Chris the new order will reuse facilities. We will leave this on until the new order is in and up and will then need to disc/cancel this order. Per Chris this will need to be a new order, will not be able to process as an inside move. Order has been changed to 1000BaseLX, completed 8/2/19 7/30/19 Email to OM to get the latest update, this is for a handoff change only scheduled for 8/19, will need a new order for an inside move if this needs to go to the 11th floor. Overall Due date is 9/4 on the order. 7/23/19 EAD is set for 7/31, overall DD is 9/4/19 Submitted on 7/10 waiting on orders | Joe Medalla
|  | Atlanta, GA | Disconnect DSL at 3200 Windy Hill Rd Atlanta, GA 30328 1. DSL #770-916-1310; User Name: aleretest@att.net 2. DSL #770-916-1762; User Name: jdahisgds_01@att.net 3. DSL #770-916-6077; User Name: keithley.huggins@att.net 4. DSL #770-916-6078; User Name: alere_ww@att.net 5. DSL #770-956-8628; User Name: alereww4thfloo9977@att.net 6. DSL #770-984-1305; User Name: 7709841305@att.net | [10 empty] | 9/30/19 The entire account was disconnected under 770-916-1310 9/23/19 Sent note to order manager to clarify what was disconnected. 9/9/19 New tracking number 090519OBI51860IO BTN: (770) 916-1310 Order #: DO84HQF6 Due Date: 9/12/2019 Product: 1FB 8/26/19 DSL Disc was cancelled on 8/26, sent a note to Order Manager and the Supervisor to understand why. 8/19/19 DDTS 2307970 is active, sent note to see when this would be completed. 080819OCW51370
| Baton Rouge | LA | Disconnect |  |  | 30942084 3094BVRZ |  | IUEC827030 | [5 empty] | 9/23/16 Order completed on 9/20/19 Due Date 9/20/19
MN011-56-CM | Chaska | MN | Port Upgrade from 7G to 7.5G and upgrade the VLAN UHGECC Global from 600M to 1.5G |  | VS19152536 | 3094BVTC 30943039 C11422905 |  | L4YS972991 | [5 empty] | 9/16/19 Auto completed on 9/13/19 Waiting on order number | CAASI,EMER E
MN011-58-CM | Chaska | MN | Port Upgrade from 7G to 7.5G and upgrade the VLAN UHGECC Global from 600M to 1.5G |  | VS19153101 | 30940274 3094BVTD C11422901 |  | L4YS973574 | [5 empty] | 9/16/19 Auto completed on 9/16/19 Waiting on order number | MEDALLA,ARGEL JOSEPH
MN011-57-CM | Elk River | MN | No Port upgrade so leave at 7G but Upgrade the UHGECC Global VLAN from 600M to 1.5G |  | VS19151009 | 30943030 C11423240 |  | L4YS973256 | [5 empty] | 9/16/19 Looks like order 30943030 completed on 9/11/19 and was a speed upgrade only to 7.5G, VLAN order 3094BVTB took VLAN to 2M | John Paulo Mercado
MN011-59-CM | Elk River | MN | No Port upgrade so leave at 7G but Upgrade the UHGECC Global VLAN from 600M to 1.5G |  | VS19153195 | 3094BVTF C11422863 |  | L4YS973612 | [5 empty] | 9/23/19 VLAN only upgrade auto-completed on 9/19/2019 9/16/19 No change Waiting on order number | BUSTILLO,JOSE MARIE
TX361-04-CM | Houston | TX | Upgrade to 200M |  | VS19153223 | 3094BVTG 3094BVTH |  | BBEC535872 | [5 empty] | 9/23/19 Both VLANS auto-completed on 9/18/19 9/16/19 Due Date is 10/15/19 Needs to be coordinated hotcut, submitted to ATT on 8/28/19
FL417-01-IM |  | Jacksonville, FL | Disconnect |  |  | 30941050 |  | IUEC705442 | [5 empty] | 10/7/19 Completed on 10/3/19 8/19/19 Due Date on disconnect order is 10/1/19 RDS 080519XE374798BE DDTS # 2304314
GA010-07-IM | Marietta | Georgia | Upgrade to 1G |  | VS19139558 | 30942082 3094BVRY |  | IZEC524117 | [5 empty] | 10/14/19 Hotcut completed on 10/6/19 10/7/19 Rescheduled for 10/6/19 9/30/19 Email to order manager Noel to see if this has been scheduled 9/9/19 Ready to schedule, need date,time and contact info Order Manager Noel Horemllosa is working to have this completed 1st week of Sept. Due Date is 9/19/19 Order submitted 8/16/19
| Manhattan | NY | Disconnect Service |  | VS19122535 | 30943063 3094BVQV |  | DHEC827636.811 | [5 empty] | 10/21/19 Completed on 10/15/19 10/14/19 Escalated to another level on disconnect that is past due 10/7/19 Escalated to the OM Manager for resolution 9/30/19 Escalated to OM, 3/5 orders are completed, remaining 2 I am pushing 9/23/19 Sent email to OM for assistance. Disconnect Date is 9/12/19
| Pharr | TX | Disconnect |  | VS19147768 | 30943007 3094 BVSS |  | BBEC538873 | [5 empty] | Order is due 10/24/19
GA026-03-DM | Atlanta | GA | Disconnect |  | VS19149075 | 30943024 3094BVSV |  | IUEC 817203 | [5 empty] | 11/4/19 Order complerted on 10/30/19 10/21/19 Due date is October 30th
| Fort Pierce | FL | Order to add Multicast |  | VS19173272 | 3094BVVX |  | BBEC590716 | [5 empty] | 11/4/19 Order completed 11/1/19 10/28/19 Order submitted, waitin on USO's
|  |  | Disconnect |  |  | 30942018 |  | IZEC501380 | [5 empty] | 11/25/19 Order completed on 11/14/19 9/30/19 Due date is 11/13/19 8/5/19 I do not see a disconnect in the system 7/23/19 Cleared out change order, now ok for DISC to be placed
| Anchorage | AK | Disconnect Service |  |  | 30942056 |  | MLEC554768 | [5 empty] | 11/25/19 Order completed on 11/13/19 9/30/19 DD is 11/13/19 Added to SS to assist in tracking
| Philadelphia | PA | Disconnect Service |  |  | 30942195 |  | BBEC558013 | [5 empty] | 11/25/19 Order completed on 11/20/19 Due Date is 11/20/19
| Kissimmee | FL | Disconnect |  | VS19147719 | 30944798 3094BVST |  | DHEC966888.811 | [5 empty] | 11/25/19 Order final completion on 11/12/19 11/11/19 Sent email to OM Martin Lazo for assistance. Order has not completely disconnected | ML687s
IL134-06-CM | Moline | IL | Upgrade to 20M |  | VS19180366 | 30940900 3094BVWH |  | BBEC503576 | [5 empty] | Auto-Completed 11/21/19
FL413-05-CM | Tampa | FL | Upgrade to 50M |  | VS19182375 | 30942281 3094BVWR |  | BBEC552126 | [5 empty] | Auto-Completed 11/25/19
C1380-09-CM | Cincinnati | OH | Upgrade to 500M |  | VS19180327 | 30940791 3094BVWG |  | BMEC917802 | [5 empty] | 12/9/19 Auto completed on 12/4/19 12/2/19 Sent email to OM for a scheduled hotcut, 2nd request 11/25/19 Sent email to OM to coordinate hotcut Due Date is 11/14/19 | Prathyusha Thalluri
|  | FL | Disconnect |  | VS19180021 | 30943946-3953, 3094BVWF |  | DHEC627572.811 | [5 empty] | 12/9/19 All aspects of order completed on 12/6/19 Due Date is 12/27/19
UTX4301DM |  |  | Disconnect |  |  | 30942134 |  | MMEC972270 |  |  |  | 2019-12-10 |  | 12/30/19 Disconnect has completed 12/9/19 Escalated to accept e-signature 11/4/19 Due date is 12/27/19 10/28/19 Disconnect submitted 102919XE372667 10/21/19 New order needed to disconnect the service 10/7/19 Melissa submitted 091919XE394615BE, with DDTS # 2325924, which was cancelled by Shyamali Naskar (sn9748), sent a note to Shymali and his manager to see why this was cancelled and what needs to be done to get disconnected. 8/5/19 I do not see a disconnect in the system Subscriber/Router ID 903039304
CA767-05-CM | Irvine | CA | Upgrade from 200M to 300M |  | VS19166770 | 3094BVVT 3094BVVV |  | BMEC990963 |  |  |  | 2019-12-17 |  | 12/30/19 Auto completed on 12/17/19 12/9/19 Sent an email to the OM for a status update 12/2/19 Escalated to a manager for no response to my email last week 11/25/19 Emailed OM to schedule Hotcut 10/21/19 Overall DD is Nov 12 10/14/19 Order submitted, waiting on USO's | Sinduja Erramsetti se535a
C1618-05-CM | Lake Mary | FL | Upgrade to 500M |  | VS19180395 | 30940936 3094BVWJ |  | BMEC992972 |  |  |  | 2019-12-17 |  | 12/30/19 Auto completed on 12/17/19 12/16/19 ATT not able to do on the 13th, maintenance weekend, looking to reschedule to another date 12/9/19 OM working to schedule 12/2/19 Melissa working to schedule 11/25/19 Sent email to OM to see if ready to schedule hotcut, but I see the DD is now 12/16/19 Due Date is 12/16/19 | Prathyusha Thalluri
M0289-10-CM | Duncan | SC | Upgrade to 200M |  | VS19186212 | 30942337 3094BVWV |  | BREC711048 |  |  |  | 2019-12-30 |  | 1/6/20 Order auto completed on 12/30/19 Due Date is 12/30/19 | Shenigarapu Sravya sx035a
MN053-82-IM | Elk River | MN | VLAN Change from 10M to 50M |  |  | 3094-BVXG |  | L4YS.973612.ATI |  |  |  | 2019-12-18 |  | 12/30/19 Waiting on order numbers Submitted to ATT 12/5/19
| Dallas | TX | Add Multicast |  | VS19197380 | 3094BVXM |  | BBEC590503 |  |  |  | 2019-12-26 |  | 12/30/19 Multicast completed on 12/26
NA | ADI |  | 4242 SIX FORKS RD | Raleigh, NC |  | IP20021946 |  | IUEC.930673..ATI |  |  | 2020-07-22 |  |  | 4/7: Reached out to the OM Radhika via Q for status. 3/11 - Order Assigned | Mamidishetti Radhika
NA | AVPN |  | 2775 Crossroads Blvd, 1 Main | Grand Junction, CO | 2020-03-25 | ISR20032374272/VS20041840 | 3094-BWBF | BMEC993526ATI |  |  |  | 2020-03-27 |  | 3/27: ORDER COMPLETE | Pamela Boyd
NA | AVPN |  | 7 TECHNOLOGY DR | Irving, CA |  | VS20045073 | 3094-BWBL 3094-BWBM | BMEC.997800 |  |  |  | 2020-04-01 |  | 4/1: ORDER COMPLETE 3/30 - Melissa requested: please upgrade port to 500mg on BMEC.997800 This is a Covid Upgrade
NA | AVPN | Downgrade Port 1G to 300 Mbps Downgrade VLAN Speed 1G to 300 Mbps | 44245 GIGABIT PLZ | Ashburn, VA |  | 206347211 |  | IZEC.568603 | [5 empty] | 4/7: Order number 206347211 for a port speed change and VLAN speed change is complete
UMNEA-06-IM | AVPN | Previous Port Speed 10 Mbps → New Port Speed 20 Mbps 14341431 Previous VLAN Speed 10 Mbps→ New VLAN Speed 20 Mbps | 513 EATON ST | ST PAUL, MN |  | ISR20052247155 3094-BWFT |  | BBEC.546848 |  |  |  | 2020-07-06 |  | 7/6: ORDER COMPLETE 6/30: Due date 7/27 - USO 3094-BWFT 6/2: ISR# rec'd - Pending USO's for the upgrades. 5/19: Order rec'd
UT019-03-IM | AVPN | Previous Port Speed 10 Mbps → New Port Speed 50 Mbps 14341431 Previous VLAN Speed 10 Mbps→ New VLAN Speed 50 Mbps | 1403 E SEGO LILY DR | SANDY, UT |  | ISR20060198825 3094-BWFW |  | BBEC.634251 |  |  |  | 2020-07-30 |  | 8/10: ORDER COMPLETED ON 7/30. 7/28: The USO is still showing incomplete and due yesterday. Can this be auto-completed? Let me know and I’ll get with ordering to see if they can get this closed out for us plug-and-play. 7/7-7/20: Pending completion - due 7/27. 6/30: Due date 7/27 - USO 3094-BWFW 6/2: Added to sheet per Melissa - ISR# rec'd
C1656-03-CM | AVPN | Please upgrade port from 150mg to 250mg on circuit BREC.811698 | 180 PEACHTREE ST N W | Atlanta, GA |  | ISR20081151909 3094-2151-FR |  | BREC.811698 |  |  |  | 2020-08-20 |  | 8/24: COMPLETE 8/18: MACD due date 9/1. 8/11: BREC.811698..ATI (ATL, GA) - ISR20081151909 - C000695055 (Charlie Penland on 8/11 at 8:18 AM CDT), GIOM # 206867519, USRP Order # VS20106819 - Tentative Due Date 9/1/20 - Assigned to Pamela Boyd (pb623t) 8/3: Order rec'd
C1654-07-CM | AVPN | Please upgrade port from 50mg to 100mg on circuit IUEC.944682 | 11830 WEBB CHAPEL RD | Dallas, TX |  | ISR20081151874 3094-0857-FR |  | IUEC.944682 |  |  | 2020-09-01 | 2020-09-14 |  | 9/15: ORDER COMPLETE 8/18-8/31: MACD due date 9/1. 8/11: IUEC944682..ATI (DALLAS, TX) - ISR20081151874 - C000695054 (Charlie Penland on 8/11 at 8:15 AM CDT), GIOM # 206867496, USRP Order # VS20106814 - Tentative Due Date 9/1/20 - Assigned to Stacey Farquharson (sf7662) 8/3: Order rec'd
C1657-03-CM | AVPN | Please upgrade port to 250mg on circuit BREC.811511 | 910 15TH ST | Denver, CO |  | 3094-BWHT-FR |  | BREC.811511 |  |  |  | 2020-08-20 |  | 8/24: ORDER COMPLETE 8/18: MACD due date 9/9. 8/11: BREC.811511..ATI (DENVER, CO) - ISR20081044625 - C000694933 (Melissa Chapman on 9:35 AM CDT), GIOM # 206862734, USRP Order # VS20106312 - Tentative Due Date 9/9/20 - Assigned to Pamela Boyd (pb623t) 8/3: Order rec'd
C1622-10-CM | AVPN | Port/VLAN Upgrade - 50M to 100M | 5601 N 103RD ST | Omaha, NE |  | ISR20081044297 3094-BWHR-FR |  | IUEC.872875 |  |  | 2020-09-09 |  |  | Cancelled per email from Melissa (email 8/18) 8/18: MACD due date 9/9. 8/11: IUEC872875..ATI (OMAHA, NE) - ISR20081044297 - C000694910 (Melissa Chapman on 8/10 at 9:09 AM CDT), GIOM # 206862532, USRP Order # VS20106284 - Tentative Due Date 9/9/20 – Assigned to Stacey Farquharson (sf7662) 8/10: Order processed by Melissa - not showing USO loaded yet.
UTX04-02-IM | AVPN | MACD order to move this circuit to the 9th Floor MDF | 2000 West Loop 9th Floor, Main Bldg, MDF Room | Houston, TX |  | 1-DH7NKHW 3094-2230 (Also issued NTE RECOVERY request) |  | IUEC.726726 |  | 28KRGN749840SW | 2020-09-10 | 2020-09-21 | 9TH FLOOR MDF ROOM (950) RELAY RACK-3 PANEL-1 POS 1 AND 2 | 9/21: ORDER COMPLETE 9/15: ATT SW DELAY - Provided update that they weren't able to meet the date - pending update on ETA for completion. - Escalation to be sent. 8/24-9/1: Order due to complete on 9/10. PON shows due 9/10 as well. 7/14: Clyde working with ordering team to generate USO's. 7/7: Added to sheet - Christine working to submit order in Chris' absence.
TX566-02-IM | AVPN | Port/VLAN Upgrade - 10M to 20M | 4682 MCDERMOTT RD | PLANO, TX |  | ISR20081047724 VS20109895 3094-2173 3094-BWJD |  | BBEC.516761 | [5 empty] | 9/30: ORDER COMPLETE 9/22: Reached out to Pamela Boyd (OM) for status on past due order. - UPDATE: PER PAMELA, 'The order has been escalated for PON. Once posted, I will then escalate for completion.' 8/28-9/15: Due date 9/17. 8/18: USO still not loaded - escalated to Pamela Boyd (MACD team) 8/10: Order processed by Melissa - not showing USO loaded yet.
TX575-02-IM | AVPN | Port/VLAN Upgrade - 10M to 20M | 1521 S STAPLES ST | CORPUS CHRISTI, TX |  | ISR20091777121 3094-BWKJ HMSV4547414 3094-BWKH |  | BBEC.666717 |  |  | 2020-10-16 | 2020-09-28 |  | 9/29: ORDER COMPLETE 9/21: PON HMSV4547414 released to the LEC - due date from LEC is 10/16. 9/17: Rec'd from Melissa to track
C1654-07-IM | MACD Upgrade | Upgrade Port/VLAN 200M to 400M | 11830 Webb Chapel Rd | Dallas, TX | 2020-11-10 | VS20164220 | ISR20111045957 ISR20120383338 3094-BWPV (Port) 3094-BWPW (VLAN) HMSV4606829 |  | BLEC.995062 |  |  | 2021-01-25 | 2021-01-23 |  | 1/25: COMPLETE 1/11-1/19: Manual USO's were loaded on 12/23. PON is scheduled to complete on 1/25. 12/22: MACD group advised both UHG and Deidre's Business Center orders failed and that we need to use the manual process. Reached out to Clyde in Deidre's absence to see if he can process. 12/21: Reached out to MACD OM in Deidre's absence. USO's still not generated for this order ISR20120383338. 12/14: Emailed Deide for assistance - ISR20120383338. There are no USO’s in the system and I checked inventory and there’s nothing there either. Not sure if it’s stuck or what, but no orders exist. 12/3: Provisioning advised the original UHG portal order failed because one of the applications was down when the order was submitted. Prov attempted to re-trigger the order, however that was unsuccessful. Deidre resubmitted it today and we have a new ISR#. Pending USO's. 12/1: There are no USO's for this ISR. Need sales to intervene and issue MACD in the system.
C1622-10-IM | MACD Upgrade | Upgrade Port/VLAN 200M to 400M | 5601 N 103rd St | Omaha, NE | 2020-11-10 | VS20146740 | ISR20111045811 3094-BWMV 3094-BWMW |  | BLEC.995073 |  |  | 2020-12-18 |  |  | 12/21: ORDER COMPLETE 12/14: Past due - Escalated to OM STACEY FARQUHARSON. PON HCSV4580805 was due 12/10. 12/1: On track for 12/10.
TX610 | MACD Upgrade | Upgrade Port/VLAN 200M to 400M | 6907 N CAPITAL OF TEXAS HWY | Austin, TX |  | VS21003870 | ISR21011305244 3094-BWQG-FR 3094-BWQH-FR HMSV4616001 |  | BBEC.663424 |  |  | 2021-02-11 | 2021-02-13 |  | 2/16: ORDER COMPLETED SATURDAY 2/13 1/20-2/8: PON HMSV4616001 showing due on 2/11.

## Melissa On Hold Orders
ATT | NY036 | Already Covid hold | Wellmed | New York, NY | sushil_gautam@uhc.com |  | 100mg access 50mg port DS3 migration for SDWAN | IUEC.905505 | VS20045450
3102-1411
3102-BBSJ
ATT | FL015 | Completed tab | Wellmed | Sebastian, FL | Vasudev.k@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.661705 | VS20057308
3102-0954
3102-BBTV
ATT | FL212 | Completed tab | Wellmed | Winter Park, FL | marion_olivete@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.634168 | VS20056515
3102-0901
3102-BBTN
3102-BBTM
ATT | FL016 | Access scheduled to install this week 6/3 | Wellmed | Port St Lucie, FL | Vasudev.k@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.671562 | VS20064418
3102-1561
3102-BBXJ
ATT | FL213 | Need to S19C this one | Wellmed | Jacksonville, FL | marion_olivete@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.667683 | VS20055903
3102-0800
7SS03663425
3102-BBTF
ATT | FL024 | Need to S19C this one | Wellmed | Lakeland, FL | Vasudev.k@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.661707 | 3102-0929
ATT | TX092 | Completed tab | Wellmed | Pleasanton, TX | marion_olivete@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.667655 | VS20057248
3102-0920
7MS02402300
3102-BBTP
ATT | TX116 | Need to S19C this one | Wellmed | San Antonio, TX | marion_olivete@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.642125 | VS20057249
3102-0928
3102-BBTQ
ATT | TX164 | Need to S19C this one | Wellmed | Sinton, TX | marion_olivete@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.674844 | VS20057968
3102-1440
3102-BBVF
ATT | FL039 | Due date moved up due to fiber work completing ahead of schedule. Should we on-hold this one (S19c)?? | Wellmed | Hialeah, FL | Vasudev.k@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.671651 | VS20057969
3102-1448
7SS03664269
3102-BBVH
ATT | FL077 | Completed tab | Wellmed | St. Petersburg, FL | Vasudev.k@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.674848 | VS20057401
3102-1435
3102-BBTX
3102-BBTW
ATT | TX213 | Need to S19C this one | Wellmed | Fort Worth, TX | marion_olivete@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.687760 | VS20057970
3102-1447
7MS02402529
3102-BBVG
ATT | FL086 | Need to S19C this one | Wellmed | Plant City, FL | jealine.teodoro@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.687765 | VS20057402
3102-1108
3102-BBVC
3102-BBVB
ATT | FL158 | Completed tab | Wellmed | Jacksonville, FL | aidyl_simbulan@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.671624 | VS20060035
3102-1484
3102-BBWC
ATT | TX481 | We were told last week this is not Covid19 delayed - now it is? Need to S19C this one if so. | Wellmed | Carrolton, TX | aidyl_simbulan@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.665016 | VS20060025
3102-1483
3102-BBVZ
3102-BBWB
ATT | TX255 | Need to S19C this one | Wellmed | Georgetown, TX |  |  | 50mg access 10mg port T1 migration for SDWAN | BBEC.674820 | VS20060016
3102-1482
3102-BBVY
3102-BBVX
ATT | TX259 | Need to S19C this one | Wellmed | Spring Branch, TX | sushil_gautam@uhc.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN- SMF only could be supported.
ATT | TX349 | Need to S19C this one | Wellmed | NORTH RICHLAND HILLS TX | kimuel_ramos@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.664997 | VS20060847
3102-1539
3102-BBWL
ATT | FL194 | Need to S19C this one | Wellmed | Tampa, FL | kimuel_ramos@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.634088 | VS20061627
3102-1541
3102-BBWR
3102-BBWS
306683340
ATT | FL141 | Need to S19C this one | Wellmed | Fort Myers FL | kimuel_ramos@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.667588 | VS20061626
3102-1543
7SS03665877
3102-BBWP
3102-BBWQ
ATT | TX414 | Need to S19C this one | Wellmed | Mathis, TX |  |  | 50mg access 10mg port T1 migration for SDWAN | BBEC.661689 | VS20058713
3102-1450
7MS02402739
3102-BBVQ
ATT | TX371 | Completed tab | Wellmed | San Benito, TX |  |  | 50mg access 10mg port T1 migration for SDWAN | BBEC.665036 | VS20058712
3102-1475
HWS03854814
3102-BBVR
ATT | TX263 | Need to S19C this one | Wellmed | Austin, TX |  |  | 50mg access 10mg port T1 migration for SDWAN | BBEC687742 | VS20059551
3102-1478
3102-BBVV
ATT | TX354 | Completed tab | Wellmed | Terrell, TX | katherine_acain@optum.com | harish_kandpal@optum.com | 50mg access 20mg port T1 migration for SDWAN | BBEC.671633 | VS20059550
3102-1479
3102-BBVW
ATT | TX341 | Need to S19C this one | Wellmed | Brownsville, TX | katherine_acain@optum.com | harish_kandpal@optum.com | 50mg access 20mg port T1 migration for SDWAN | BBEC.674754 | VS20066821
3102-1562
3102-BBXK
ATT | TX346 | TX346-06-IM - This is one that Melissa cancelled | Wellmed | El Paso, TX | kimuel_ramos@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.664952 | VS20066820
3102-1565
7MS02405330
3102-BBXM
ATT | TX348 | Need to S19C this one | Wellmed | North Richland Hills, TX | kimuel_ramos@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.667551 | VS20066819
3102-1563
3102-BBX
ATT | TX347 | Need to S19C this one | Wellmed | McAllen, TX | kimuel_ramos@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.665005 | VS20060717
3102-1512
3102-BBWK
ATT | FL160 | Need to S19C this one | Wellmed | Orlando, FL | aidyl_simbulan@optum.com | harish_kandpal@optum.com | 50mg access 10mg port T1 migration for SDWAN | BBEC.634062 | VS20064450
3102-1555
7SS03667132
3102-BBXC

## Lean Tail Migrations
AT&T Ckt ID | Existing LEC Ckt ID | New AT&T Access ID | Address | City | State | Port Sp | Lcon | Number | Email | Status
BKEC.985516.ATI | 19.KXGS.138448.MS | AZ.KRGN.100336.TPM | 4805 E Thistle Landing Dr | Phoenix | AZ | 100MB | Ignacio Sardinas |  | ignacio_sardinas@optum.com | Pending Fiber to the Floor Right Of Entry agreement. No ECD.
IZEC.501380.ATI | 19.KXGS.172456.MS | AZ.KRGN.100540.TPM | 801 S 16TH St | Phoenix | AZ | 1G | Johny Tran | 303-397-8306 | johnytran@teletech.com | LCON not responding.
IZEC.575632.ATI | 29.KXGS.146016.MS | TBD | 910 15TH St | Denver | CO | 1G | Melisa Chapman | 763-744-2114 | melissa_r_chapman@optum.com | On hold. Speed upgrade in progress.
BBEC.500949.ATI | 95.KRGS.323957.NE | MA.KFGS.100048.TPM | 200 Arlington St. | Chelsea | MA | 50MB | Frank Estabrook | 603-731-0508 | frank.estabrook@mass.gov | Order issued with multi-mode. Existing cabinet space too small. Will reissue as single-mode
IUEC.627105.ATI | 13.LCRM.108270.OED | TBD | 950 Winter St | Waltham | MA | 50MB | Karen McMullen | 781-472-8463 | karen.mcmullen@optum.com | Internal orders issued.
BMEC.990204.ATI | 38.KFGS.301318.CM | MD.KRGN.100028.TPM | 10480 Little Patuxent Pkwy | Columbia | MD | 100MB | Ignacio Sardinas |  | ignacio_sardinas@optum.com | Right Of Entry agreement needed. ECD is 3/28.
BKEC.990034.ATI | 07.KXGS.170834.NW | NE.KRGN.100053.TPM | 2717 N 118TH Cir | Omaha | NE | 100MB | Linda Beam | 402-445-5682 | linda_beam@uhc.com | Order issued on 3/4. Site visit upcoming.
IZEC.561544.ATI | 07.KXGS.171442.NW | NE.KRGN.100051.TPM | 9910 Maple St | Omaha | NE | 1G | Daniel Stang | 402-716-1277 | dnstang@west.com | Internal orders issued.
BKEC.981253.ATI | BKEC.981253.ATI | NJ.KRGN.100697.TPM | 131 Morristown Rd | Basking Ridge | NJ | 200MB |  |  |  | New AT&T access ckt installed and ready to cut.
IUEC.803278.ATI | KRGS.502454.NJ | NJ.KFGS.100124.TPM | 95 Christopher Columbus Dr | Jersey City | NJ | 50MB | Ignacio Sardinas |  | ignacio_sardinas@optum.com | Right Of Entry agreement needed. ECD is 3/15
IUEC.867370.ATI | 32.KFGS.204620.NY | NY.KRGN.101200.TPM | 77 Water St | New York | NY | 50MB | Ignacio Sardinas |  | ignacio_sardinas@optum.com | Need new LCON. LCON not responding.
BMEC.990918.ATI | 32.KFGS.205200.NY | NY.KRGN.101194.TPM | 777 Old Saw Mill River Rd | Tarrytown | NY | 200MB | Ignacio Sardinas |  | ignacio_sardinas@optum.com | On site space/power issue. No ECD.
BKEC.984685.ATI | 11.KFGS.304677.PA | PA.KRGN.100491.TPM | 680 Blair Mill Rd. | Horsham | PA | 200MB | Ignacio Sardinas |  | ignacio_sardinas@optum.com | ROE in place. AT&T needs UHC to contact building and let them know AT&T is ready to proceed.
IUEC.950555.ATI | 11.KEGS.314858.PA | PA.KRGN.100586.TPM | 1650 Arch St | Philadelphia | PA | 100MB | Summer Allen | 215-553-5150 | summer.allen@optum.com | LCON not responding.

## COVID-19 Orders
Type | Service | UHG Order# | Business | PM | End User | Street Address | City, State | AT&T Order# (USO/Project#) | Date Ordered | CRDD | AT&T Overall Due Date | Completion Date | MD5 | AT&T Circuit ID's | LEC (CLEC) | LEC Circuit ID(s) | Scheduled Access Install Date | Access Demarc(s) | Handoff | Technical Info | ICORE Site ID | VLAN ID | CER | PER | ASN COS | VPN ID | VPN Name | Status
New | COVID-19 5G Port/ 10G Access EaAVPN 10G Base-LR (SMF) | CA777-07-IM | UHG | Melissa Chapman | UHG- RNH Hub Equinix LA4 | 1920 E MAPLE AVE 445 North Douglas Street Equinix (LA4 - 01:041040) MMR Room | El Segundo, CA | C11437725 VS20042808 3094-1167 7WS03848594 CLO CAS001074001 3094-BWBJ | 2020-03-18 | ASAP | 2020-06-19 | 2020-04-09 | Y | L4YS.800261 | ADE LNS | CAKGGS100659TPM | 2020-04-13 | 030321.01/FF5/01/01/107 & 108 | 10GBaseLR |  |  | 2 | 10.1.85.45 | 10.1.85.46 | 65155 | 202610 | UHG GLOBAL 150 | 4/10: ORDER COMPLETE 4/9: LNS team confirms all equipment in hand and tech pursuing card installs; pending status and test results from the field. Access still showing due 4/13 but working to improve. 4/7-4/8: Pending confirmation equipment has arrived and tech is scheduling installation. 4/6: Reached out to Ops Specialist in CA for status of the equipment and ETA for delivery. Access install still showing target date of 4/13 and pending equipment delivery to proceed. -- UPDATE: The equipment should be delivered TODAY. Our local tech is aware of the urgent nature of this circuit and will work this order once he has the equipment in hand. 4/3: LEC logs indicate they are aware this is a VP escalation. LEC advised they have SFP's on order and pending arrival of equipment. Once received they will expedite access delivery. Access install still showing due to complete no later than 4/13. 4/1-4/2: Access install currently showing due 4/13 but being pushed for sooner by COVID19 team. 3/31: Site visit was completed yesterday 3/30 ahead of schedule. Construction advised fiber infrastructure is COMPLETE as of yesterday as well. Confirmed NETWORK complete. Pending an access install date on the PON 7WS03848594. 3/30: Currently showing a site visit has been scheduled with the customer for 4/10 by AT&T Construction team. Unsure if this date will be improved or whether this is first available date due to Covid19 situation. Working to clarify. 3/27: Pending release of the PON to the LEC. - UPDATE: PON RELEASED 3/20: Received C-Project#. Covid19 Command Center War Room engaged and awaiting USO's 3/18: Order rec'd - The El Segundo 10G order was processed yesterday after port capacity and reservation were confirmed. These three 10G orders are being managed by our CVD provisioning team. They will get an escalation amanger assigned to each order to push for earliest completion possible. We have passed on the UHG request date of 3/25-27. As discussed, the 10G access to Equinix campus will come into the following space and address below. UHG will need to order a campus cross connect from Equinix to get form 1920 . Maple to the 445 Douglas. You will want to pass this information off to Equinix when ordering your cross connect. • LNS cage #3310 Ring Id# WZ0402 • Service Floor: LA3
New | COVID-19 5G Port/ 10G Access EaAVPN 10G Base-LR (SMF) | GA777-14-IM | UHG | Melissa Chapman | UHG- RNH Hub Equinix Data Center (AT1 - 02:020984) | 56 MARIETTA ST NW MMR Room | Atlanta, GA | C11437726 VS20042838 3094-1501 7SS03659024 (Ded) 3094-BWBK | 2020-03-18 | ASAP | 2020-06-12 | 2020-04-08 | Y | L4YS.836043 | ATT SE | 38KGGS601299SB | 2020-04-10 | 2 FLR M39 002.06.08.84 JK#83-84 | 10GBaseLR |  |  | 2 | 10.1.85.49 | 10.1.85.50 | 65138 | 202610 | UHG GLOBAL 150 | CANCELLING - THIS WILL REQUIRE A DISCONNECT ORDER BY UHG IF ONE HASN'T BEEN SENT ALREADY. ORDER WAS COMPLETED ON 4/8. 4/8: ORDER COMPLETE - LOA SENT 4/6-4/8: Access install still showing targeted for 4/10 completion. Wiring completed on Friday per the LEC and they're working to see if date can be improved. 4/3: Fiber infrastructure completed yesterday 4/2. LEC has provided a 4/10 access install date. Working to see if that can be improved. As it stands, access targeted for completion next week. 4/2: Escalated to Network team and their Area Managers - INTERNAL CALL TODAY AT 10:30AM ET - pending info on fiber requirements and dates as well as access install. 4/1: Site Visit showing scheduled for 4/6. Monitoring order for changes/updates. 3/30-4/1: Pending an access install date. PON 7SS03659024 was released to the LEC on Friday 3/27 so we're expecting more information and dates as this week progresses. 3/27: USO's received - PON released to ATT SE. Pending an install date. 3/27: USO's delayed due to address validation issues. Address is fine, LEC selection is the issue. Sent the Atlanta order back to Order Manager to work. We had to change the LEC on order from ADE/LNS to Bell South. This should be resolved today and USO's should flow into all systems. 3/20: Received C-Project#. Covid19 Command Center War Room engaged and awaiting USO's 3/18: Order rec'd - The Atlanta 10G order was processed yesterday after port capacity and reservation were confirmed. These three 10G orders are being managed by our CVD provisioning team. They will get an escalation amanger assigned to each order to push for earliest completion possible. We have passed on the UHG request date of 3/25-27. As discussed, the 10G access to Equinix campus will come into the following space and address below. UHG will need to order a cross connect from Equinix 56 Marietta to your cage. You will want to pass this information off to Equinix when ordering your cross connect. • LNS Location (SW99) • Service Floor: Basement
New | COVID-19 5G Port/ 10G Access EaAVPN 10G Base-LR (SMF) | GA777-14-IM | UHG | Melissa Chapman | UHG- RNH Hub | 180 PEACHTREE ST NW FLR AT1 RM CAB 202 | Atlanta, GA | VS20052705 3094-0547 7SS03662325 3094-BWCB | 2020-04-14 | ASAP | 2020-07-10 | 2020-04-20 | Y | L4YS.894462 | ADE LNS | GAKGGS100382TPM | 2020-04-17 | TDI in Equinix Format: AT1:03:34235:0103:1143080 JKS 37/38 | 10GBaseLR |  |  | 2 | 10.1.90.9 | 10.1.90.10 | 65138 | 202610 | UHG GLOBAL 150 | 4/20: LOA provided to Melissa. Pending overall completion. - UPDATE ORDER COMPLETE 4/16: Access due to complete 4/17. 4/13: Chris advised that he spoke with Melissa and Jim Moskalik and confirmed he will have to order new circuit. The design given by the carrier hotel does not allow Equinix to cross connect to the Bell South Access Drop. Chris opened another COVID bridge on team WebEx . New order will be access into 180 Peachtree through LNS
New | COVID-19 5G Port/ 10G Access EaAVPN 10G Base-LR (SMF) | TX777-15-IM | UHG | Melissa Chapman | UHG- RNH Hub Equinix DA6 | 1950 North Stemmons Freeway Suite 3050 Equinix (DA6 - 03:030330 MMR Room | Dallas, TX | C11437723 VS20042486 3094-1106 7MS02398072 CLO TXDBBB52S001 3094-BWBH | 2020-03-18 | ASAP | 2020-06-19 | 2020-04-09 | Y | L4YS.781638 | ADE LNS | TXKGGS100568TPM | 2020-04-15 | 070121.20.PNL02 POS 23-24 | 10GBaseLR |  |  | 2 | 10.1.85.125 | 10.1.85.126 | 65246 | 202610 | UHG GLOBAL 150 | 4/10: ORDER COMPLETE 4/9: Access install complete. Order is now with Provisioning Design to complete engineering. Once complete, the order will move to the tech side to be assigned, tested and closed. VLAN ID 2. 4/8: Access install on track for 4/9. 4/7: Access install improved from 4/15 to 4/9. 4/3-4/6: Access install still targeting completion no later than 4/15. Working to improve and pending update from Command Center escalation team. 4/2: Access install scheduled for 4/15. Working to improve. Construction/Network confirmed PRE-BUILT CARRIER HOTEL. NO KO REQUIRED. NO SV REQUIRED. NO ROE REQUIRED. NO OSP FIBER REQUIRED. 4/1: PON released yesterday. Fiber infrastructure completed today. Pending an access install date. 3/31: Pending PON release to the LEC LNS. Reached out this morning for assistance. 3/30: The PON is scheduled to be released to the LEC today. Will monitor for dates. 3/27: Pending release of the PON to the LEC. 3/20: Received C-Project#. Covid19 Command Center War Room engaged and awaiting USO's 3/18: Order rec'd - The Dallas 10G order was processed yesterday after port capacity and reservation were confirmed. These three 10G orders are being managed by our CVD provisioning team. They will get an escalation amanger assigned to each order to push for earliest completion possible. We have passed on the UHG request date of 3/25-27. As discussed, the 10G access to Equinix campus will come into the following space and address below. UHG will need to order a cross connect from Equinix 1950 Stemmons Freeway to your cage. You will want to pass this information off to Equinix when ordering your cross connect. • ADE - Cage #30255 - Equinix / inside suite 1032 - Cologix Space
New | COVID-19 Upgrade 300M port to 500M BMEC.997800 | CA013-08-CM | UHG | Melissa Chapman | Monarch Healthcare | 7 Technology Dr | Irvine, CA | VS20045073 3094-BWBL 3094-BWBM EVC1 HWSV4444208 | 2020-03-30 | ASAP | 2020-04-29 | 2020-04-01 |  | BMEC.997800 | ATT West | 13VLXP154606PT | 2020-04-01 | [10 empty] | 4/2: ORDER COMPLETE - Confirmed ICORE is showing 500M speed. 3/31-4/1: EVC1 PON showing due 4/29 but we are escalating to improve dates across the board. Pending status from Command Center (Katie L Keyser-LEAD) 3/30: Order rec'd - added to Command Center by Heidi W. Fountain - ATT Region Director - Strategic Sales Programs
New | COVID-19 Upgrade 300M port to 1G IZEC.537138 | CA768-10-CM | UHG | Melissa Chapman | Monarch SIP/23705 | 2301 W 120th | Hawthorne, CA | VS20045461 3094-BWBN 3094-BWBP EVC1 HWSV4444693 | 2020-03-31 | ASAP | 2020-04-29 | 2020-04-08 |  | IZEC.537138 | ATT West | 13VLXP148905PT | [11 empty] | 4/9: ORDER COMPLETE 4/8: Reached out to the internal Command Center for game plan to improve 4/29 date on PON HWSV4444693 4/7: PON showing due to complete on 4/29 (system generated), but Command Center is working to improve that date. 4/3-4/6: Pending a completion date from the LEC on the PON. Command Center team advised they are escalating to engage the right teams to get the order completed. 4/1-4/2: Pending a completion date on the PON HWSV4444693 which was released to the LEC yesterday 3/31. 3/31: Order rec'd - Assigned to Katie Keyser (Lead)

## 2018 Archived Completed
UHG PON | Address | City, ST | Order Type Service | CPDD | Sales to Ordering | Order/USO | ATT Ckt ID's | LEC / PON | LEC Ckt ID | Estimated ATT Due Date | Complete Date | Demarc | STATUS | Order Mgr. / Current Responsible Party | SDM Managed | MD5 Password | ASN | IP Address CER/PER | APP DATE on ORDER | FOD | FOC Received | CTA complete | DD Complete
IL043-05-CM | 1600 MCCONNOR PKWY Schaumberg, IL 60173 | Schaumberg, IL | 150M Upgrade to 200M | TBD | 2017-11-29 | VS17214085 3094BTBH | BREC999286ATI | TBD | TBD | 2018-01-09 | TBD | TBD | SIMPLE REHOME 1/19: Order completed. 1/15: Escalated with OM manager for DD completion. 1/2-12/11: Received USO, DD scheduled 1/9/18. Order not managed by SDM. Order manager contact JEZREEL GAY DE GUZMAN dj608m@att.com 12/4: Received Cproject number on 11/29. Pending order number/USO. | JEZREEL GAY DE GUZMAN dj608m@abs.att-mail.com | Not SDM Managed
CT008-02-CM | 3 Farm Glen Blvd Farmington, CT 06032 | Farmington, CT | 100M Upgrade to 150M | TBD | 2017-11-27 | VS17213162 3094BTBD | BCEC553599ATI | TBD | TBD | TBD | TBD | TBD | SIMPLE REHOME 1/22: Order completed. 1/15: CUT request for 1/18 @ 10:30pm 1/8: 12th January 2018, 10:30PM CST, Bridge#: 8884313632 Host Code: 5203389 Participant Code: 4299667 1/8: Emailed OM for cut scheduling request. 1/2: Order is ready to schedule cutover. Please contact OM: Angel Cadiao ac744u@att.com tp schedule cut. 12/26: DD scheduled for 1/5/2018 12/4-11/27: Received order from UHG and order was processed. Pending order number /USO.
IL043-05-CM | 1600 MCCONNOR PKWY Schaumberg, IL 60173 | Schaumberg, IL | 150M Upgrade to 200M | TBD | 2017-11-29 | VS17214085 3094BTBH | BREC999286ATI | TBD | TBD | 2018-01-09 | TBD | TBD | SIMPLE REHOME 1/19: Order completed. 1/15: Escalated with OM manager for DD completion. 1/2-12/11: Received USO, DD scheduled 1/9/18. Order not managed by SDM. Order manager contact JEZREEL GAY DE GUZMAN dj608m@att.com 12/4: Received Cproject number on 11/29. Pending order number/USO. | JEZREEL GAY DE GUZMAN dj608m@abs.att-mail.com | Not SDM Managed
CT008-02-CM | 3 Farm Glen Blvd Farmington, CT 06032 | Farmington, CT | 100M Upgrade to 150M | TBD | 2017-11-27 | VS17213162 3094BTBD | BCEC553599ATI | TBD | TBD | TBD | TBD | TBD | SIMPLE REHOME 1/22: Order completed. 1/15: CUT request for 1/18 @ 10:30pm 1/8: 12th January 2018, 10:30PM CST, Bridge#: 8884313632 Host Code: 5203389 Participant Code: 4299667 1/8: Emailed OM for cut scheduling request. 1/2: Order is ready to schedule cutover. Please contact OM: Angel Cadiao ac744u@att.com tp schedule cut. 12/26: DD scheduled for 1/5/2018 12/4-11/27: Received order from UHG and order was processed. Pending order number /USO.
NC021-06-IM | 4242 Six Forks Rd, Main 1 Telco, Ral, NC, US, 27609 | Raleigh, NC | 50MB |  |  | 1005444731 30943014 3094BTCN | IUEC930673 ATI | ATT SE HSS03457259 | 26KQGN403564SB | 2018-03-26 | 2018-01-19 | 11TH FLR TELCO RM PORT 3/4 OF VIRTUAL | 1/24: Order completed
FL038-09-IM | 2960 SW 8th ST Miami, FL 33135 | Miami, FL | 10MB port/50MB Access | 2017-11-06 | 2017-10-30 | VS17197049 30943226 3094BSZD Site ID: 547212 | BBEC530714 ATI | ATT SE HSS03444514 | 60KRGN759415 SB | 2018-01-24 | 2018-01-25 | TELCO RM DUAL CN3930 PORT 6 SC PORTS | 1/29: Order completed on 1/25. 1/22: Order on hold due tech not having access to rear parking lot to pull fiber. Parking lot is being repaved. 1/15-1/2: Access install scheduled for 1/18. 12/26-12/4: FOC completed on 12/1, access install date scheduled for 1/18/18. 11/27-11/13: Order supped to correct address new FOC date scheduled for 12/6. 11/6: FOC scheduled for 11/30. 10/30: Order processed, pending order number/USO.
PR516-01-IM | 100 State Road 165, Tower 1 Suite 802 Guaynabo Puerto Rico, VA 00968 | Puerto Rico, VA | 7Xt1 | TBD | 2017-09-11 | VS17170065 30944181 30944182 30944183 30944184 30944185 30944186 30944187 | DHEC.354444.811.ATI DHEC.354444.812.ATI DHEC.354444.813.ATI DHEC.354444.814.ATI DHEC.354444.815.ATI DHEC.354444.817.ATI DHEC.354444.816.ATI | CENTENNIAL OF PUERTO RICO TSS03445998 TSS03445999 TSS03446001 TSS03445993 TSS03446002 TSS03446004 TSS03446006 |  | TBD | 2018-01-25 | DEMARC: RJ48X JK, TAGGED WITH BOTH IDS, EXTENDED FROM MPOE ON 1ST FLOOR TO COMPUTER ROOM IN CUSTOMER SUITE 804 | 1/25 Order completed. 1/22: SDM leadership pressing to have last T1 completed. Pending provisioning confirmation of CFA resolved. 1/15: New FOC date scheduled for 1/17. Order needed to be supped with LEC to correct CFA issue. 1/9: Check for ECD of CFA 1/8: Provisioning group is working on CFA mismatch. Next follow up is scheduled for 1/11. 1/3: Pending completion of last T1 by provisioning team. 12/26: Escalated with provisioning manager to complete and test last T1's. 12/18: 4T1's have end to end testing completed. Provisioning is working on last 3. 12/11: All circuits were delivered, Pending end to end testing. 12/4: Tech was dispatched out to the site but contractor work was done incorrectly. Contractors will correct work and tech will dispatch again this week. 11/27: Pending install dates from provisioning team. 11/20: Per AIM : Manual tickets have been sent to provisioning design manager. Once design is completed provisioning will provide install/ DD. 12/15 need by date 11/13: New FOC provided of 11/16. 11/6: Order supped with address and LCON info. Pending new FOC date. 10/30: Per AIM: From LEC- Address is incomplete and they were unable to contact LCON to verify. Request better address and landline phone number installed at desired location to track circuit facilities for that building. 10/23: Escalation ticket being worked by provisioning team. 10/16-10/2: Pending FOC date for order. 9/25: Pending PON being issued with FOC date. Checking with provisioning to confirm due to hurricane Maria. 9/18: Pending order number/USO. Follow up with Dawn 9/11: Sent over as 7xT1 9/11: Pending USO/ order number. 9/5-8/30: UHG replied with new address pending confirmation of Ethernet or accepting of Tx1.
NJ777-12-IM | 275 HARTZ WAY AT&T LNS SCCSNJ69N02 Rm: Meet Me, 1st Flr | SECAUCUS, NJ | 2Gbps/10Gbps 10G Base-LR (SMF) Carrier Hotel, Equinix, 1st Fl, R3139 B4oC2P3 "D" Facility 3139AOC768_ SDI# 4910900 | 2017-05-01 | TBD | C11331969 VS17118992 30943121 3094BXPC | L4YS896997 | LNS HNS01908776 | VLEC013221965ATI | 10/25/2017 | TBD | 1ST FLR. LNS CAGE #1000 01.01.09 PANEL 9 (EQUINIX 75765) PORTS 3 & 4 | 1/29: TTU successful. 1/22: TTU requested date 1/26 @ 2200 CST 1/8: Pending confirmation of cross connect completion from UHG. 12/18: Pending date and time to schedule hot cut. 11/27-10/30: New OM assigned for TTU scheduling. GWEN MCCOY GM7501@att.com 10/23-9/27: Order complete pending TTU scheduling. 9/25: Pending overall completion. 9/18-9/11: End to End wiring scheduled for 9/11, testing scheduled for 9/18. Overall DD scheduled for 9/25. 9/5-8/14: End to End design completed, End to End wiring- 9/11 & testing scheduled for - 9/18. 8/7: Demarc has been posted and circuit installed. Pending completion of End to End design, wiring & testing. Design scheduled to complete 8/8. 7/31: FOC completed 7/28, Target access install date scheduled for 8/7. 7/28: Target FOC date is scheduled for 8/4. 7/26-Designer can proceed with order 7/24-Pending FOC 8/4 7/17-Emld provisioning for update of when PON will be released 7/14-FOD missed, issue with CLLI, 7/10-Rcvd USO, pending PON to be released to LEC on 7/13 6/26-Pending USO 6/15-Rcvd C proj #, pending USO 6/12-Pending new order, need expedite 6/5-Order cancelled 5/31-Rcvd C proj #, pending USO 5/30-Sent to CSS 5/1-Rcvd order request
TX343-06-IM | 1711 S Staples Corpus Christi, TX 78404 | Corpus Christi, TX | 10M Port/ 50M Access |  | 2018-01-02 | VS18004534 30943136 3094BTCQ | BBEC557366 ATI | ATT SW HMS02252374 | 34KRGN613755SW | 2018-03-27 | 2018-01-31 | INSIDE BLDG., RACK MOUNTED CIENA 3930,SLIM-JIM HANDOFF, PORTS 3/4 | 2/5: Order completed on 1/31. 1/29: Fiber Plc & Splc completed on 1/22, access install scheduled for 2/1. 1/22: Customer prem ready on 1/11, Fiber Plc & Splc scheduled for 3/8. 1/15: FOC completed on 1/11, access install scheduled for 3/19. 1/8: Pending order number/USO. | JIELLE ALVAREZ ja746g@att.com
C1093-09-CM | 15 Enterprise Avenue - India OffShore SECAUCUS NJ | SECAUCUS NJ | Upgrade 300 to 500MB | TBD | 2017-07-27 | VS17140444 3094BSQM 3094BSQN | VLEC012714272ATI | TBD | TBD | TBD | 9/14/2017 | TBD | SIMPLE REHOME 2/5: Order completed on 2/2. 2/1: CUT was approved for 2/2 @ 11pm EST 1/22-10/9: Pending cut scheduling from UHG 10/3: Sent OM contact info for UHG contact. 10/2: Pending cut schedule from UHG. Please provide best contact to schedule cut. Contact: Steve Groebe 9/25-9/18: Order completed 9/14. Ready for scheduling with UHG 9/11: Escalated for access install completion with provisioning manager. 8/28-8/14: Pending order number/ USO. 8/7: Order sent to ordering team on 7/27. Pending order number/USO. | Pamela Boyd pb623t@att.com | SDM Managed
IL722-12-CM | 2425 Busse Rd Elk Grove Village, IL 60007 | Elk Grove Village, IL | Downgrade from 1GB to 100MB | TBD | TBD | VS17223194 3005CPNF 3005CPNG | IZEC557077 ATI | TBD | TBD | TBD | TBD | TBD | 2/5: Order completed on 2/2 1/29: Pending USO for order. Downgrade order for Vlan & Port.
FL047-05-IM | 9100 S DADELAND BLVD STE 1250 Miami, FL 33156 | Miami, FL | 80M Port / 250M Access | 2018-12-18 |  | VS17220754 30941050 3094BTBM | BREC922171 ATI | ATT SE HSS03453449 | 60KRGN759608SB | 2018-03-06 | 2018-02-08 | 14TH FLR IT ROOM EXTENDED PORT 5TO 14TH FLR IT ROOM | 2/12: Order completed on 2/8. 2/5:Access install scheduled for 2/8 1/29: Request has been sent to supp the order to change the floor to the 14th. 1/22: Emailed UHG to confirm correct demarc room. Order is for 1st floor tech showed room was on 14th floor. 1/15-1/8: FOC completed access install scheduled for 1/17. 1/2: No response from the LCON. UHG advised to contact LCON at beginning of new year due to vacation. 12/26: FOC completed on 12/20, access install scheduled for 12/28.
TX175-08-CM | 14141 SOUTHWEST FRWY Sugar Land, TX 77478 | Sugarland, TX | Upgrade 150Mb to 200MB | TBD | 2017-08-18 | VS17158678 3094BSTR 3094BSTS | BREC980171ATI | TBD | TBD | TBD | TBD | TBD | Simple Rehome 2/12: Order completed on 2/9. 2/5: Pending Cut details. 1/29-10/2: Pending new cut date from UHG. 9/27: Per UHG team, site is shutdown due to emergency. Postponed cut until further notice. 9/25: Pending scheduling of cutover. 9/18-9/11: Access install completed on 9/11, Order is now ready for hot cut. 9/5: Order DD scheduled for 9/29. Order manager Byron Gatson is the primary contact for order. 8/28-8/21: Pending order number /USO order has been submitted | Byron Gaston bg2322@att.com | SDM Managed
NY232 | New Hyde Park | NY | Please upgrade port on BMEC. 990230..ATT to 500mg | 2017-06-15 | TBD | VS17118593 30942463 3094BSNM | BMEC. 990230..ATT | TBD | TBD | TBD | TBD | TBD | SIMPLE REHOME 2/12: Order completed on 2/8. 1/29: UHG requested cut schedule of 2/7 @ 11:30 EST 1/22-10/2: Pending OM & UHG contact to schedule cut date/time. 9/25: OM is handling cutover pending scheduling. 9/20: Tech was not available for after hours cut on 9/21. Next available slot available 9/27. Pending UHG response to OM. 9/19: Request was sent to OM for 9/21 @ 10:30pm CST. 9/12: Per UHG request for cut; 9/19 @ 10 pm CST. Sent to OM to schedule cut, pending approval. 9/5: Pending follow up with new cut date and time from UHG 8/14; Order is ready to schedule cut. 7/27-Design verified, pending completion, DD 7/27 7/18-DD 7/27 7/6-DD 7/27 6/28-Rcvd USO, DD 7/27 6/15-Rcvd Order request | SUE MICHEL sm1090@att.com | Not SDM Managed
II538-06-CM | UHG | Upgrade to 300MB | ISR17110740663 | Mind Space, Survey No. 64 Part, Sundew Propertie, 12b 11 Mdf, Hyderabad, AP, IN | India | Hyderabad | TBD | 2/12: Pending confirmation order completed. 1/29: Cut booked for 2/7 @ 22:00 central. 1/22-12/4: Pending scheduling due to peak season UHG will provide scheduling date/time. 11/20: OM has reached out to UHG to schedule. 11/13-10/9: Pending order numbers. 10/2-9/11: Pending order number/USO. Contract signed. 9/5: Pending contract, pending order number/USO 8/28-8/7: Pending order numbers. Pending countersign
TX348-04-IM | WellMed 6344 Davis Blvd North Richland Hills, TX 76180 | North Richland Hills, TX | 7XT1 | 2017-10-13 | TBD | VS17183627 30944308 30944309 30944310 30944311 30944312 30944313 30944314 | DHEC433942811ATI DHEC433942812ATI DHEC433942813ATI DHEC433942814ATI DHEC433942815ATI DHEC433942816ATI DHEC433942817ATI | ATT SW GMS02239257 GMS02239260 GMS02239322 GMS02239258 GMS02239259 GMS02239323 GMS02239321 | 14HCGS161710SW 14HCGS161709SW 14HCGS161713SW 14HCGS161711SW 14HCGS161708SW 14HCGS161714SW 14HCGS161712SW | TBD | 2018-02-13 | IT/PHONE RM CAB 1 SLOT 10. IT,/PHONE ROOM, CAB 1 SLOT 9.9 IT/COMM ROOM CAB2 SLOT 1. IT/PHONE RM CAB 1 SLOT 11 IT/PHONE RM CAB 1 SLOT 8 IT/PHONE ROOM CAB 2 SLOT 2 IT/PHONE ROOM CAB1 SLOT 12 | 2/13: Order completed. 2/12: 5T1's completed, pending overall completion on last 2. 2/5:Per AIM: EWO is pending on the order. Splicing is pending completion before dispatch. 1/29: Dispatch date rescheduled for 2/1. 1/22: New dispatch date is scheduled for 1/30. 1/22: OM requested sup for re-dispatch. 1/16: Conduit complete. 1/15-1/8: Per UHG: The facilities team is waiting approval from the city for the path to the building. They estimate to have the approval by early next week and the work completed immediately after. 1/2: Pending update about site readiness. Looking to be ready by the week of 1/15. 12/26-12/18: Site not ready. UHG is working with customers facility team to resolve the issue. 12/11: Access install scheduled for 12/15. 12/4-11/27: Access install scheduled for 12/5 11/20: UHG confirmed site is ready, sup for redispatch has been requested. 111/3-11/6: Pending DD for site readiness from UHG. DD has been extended to 12/5. 10/30: Order marked as CNR, needing to provide conduit. 10/23: Estimated access install date scheduled for 10/24. 10/16: Foc completed on 10/14, estimated access install date scheduled for 10/24.
C1624-03-CM |  | Chandler, AZ | ASN Change |  | ASN Change | C11361246 | TBD | TBD | TBD | TBD | TBD | TBD | 2/27: Order completed. 2/26: Pending USO
C1614-01-IJ | 101 Yorkshire Blvd | Lexington, KY | 30MB/100MB LC - Multi Mode Fiber 1000BSX | 2017-05-25 | TBD | C11330052 VS17101612 30944016 3094BSMN 3094BSMP | IUEC905883 ATI | TIME WARNER HSS03407843 | 85L1XX001643TWCC | TBD | TBD | TBD | 2/26: Order completed. 2/26: UHG confirmed to keep circuit as SMF handoff. 2/20: Executive escalation team engaged to assist with having handoff changed. Provisioning team assigned and working with TW for change. 2/12: Pending confirmation that TW has received change order and ECD of change. 2/5: New PON has been sent to TW to change SFP type for MMF. Next update from provisioning scheduled for 2/7. 1/29: Access install completed on 1/25, escalated to SDM escalation manager for completion. 1/24: CPE install completed, LEC is in final testing and plans to handover circuit to AT&T within 72hrs. 1/22: CPE install scheduled for 1/23. Date pushed back by LEC due to inclement weather. 1/17: Per AIM: CPE install set for 1/17, after CPE install is completed LEC has 72 hrs to turn over to AT&T. Next update scheduled for 1/19. 1/15: AIM is escalating with TW leadership to provide ECD for fiber move. 1/8: Per AIM: Pending construction team to provide a ECD of fiber move. 1/2: Per AIM- Construction manager is reviewing with local t1/eam. 12/26: AIM escalating with construction team to provide timeline. 12/18-12/11: Per AIM: Construction team looking at options with LCON to move fiber to new data room. 12/4: AIM has requested a sup to have Fiber moved to correct telco room. 11/27: Emailed AIM for tag & Locate for fiber location. Pending status. 11/21: Was not moved need tag and locate. John 11/20-11/13: Fiber was run to a different part of the building originally and then a lateral run to the spot Randy requested. Pending confirmation that Lec is good for install. 11/6: Per AIM: Lec working with site contact Randy to confirm fiber. 10/30: Escalated with AIM for update with install firm dates. 10/23: Pending construction team confirmation to complete install. 10/16: Per AIM: LEC manager is checking with LCON Randy Abshare to confirm equipment is in correct location. 10/9: Per AIM: Pending confirmation that fiber has been moved to correct location. 10/2: Per AIM: Pending design completion. 9/27: Per AIM: Plan to receive design by next week. 9/25: Per AIM: Pending final construction design, equipment to be located in basement. 9/18: Per AIM: Order has been escalated with LEC manager for assistance with ECD. 9/11: Per AIM: Pending construction to provide firm dates. 9/5: Per AIM: Cust has requested that location of equipment be moved. reengaged construction to move equip where cuts wants and requested ECD. 8/28: Escalated for Access install completion. 8/21-8/17: Pending completion of install. 8/14-8/7: Per AIM: Per LEC manager install has been improved to 8/17. 7/31: CPE ( Customer premises equipment) installed scheduled for 8/21. AIM is pressing for date improvement. 7/26-CPE install set for 8/21, pending update on a better date 7/24-AIM has escalated order to TW manager for help with FOC update 7/19-Per TW manager, pending provisioning and hub work prior to scheduling cpe installation 7/18-Escalated for AIM engagement for FOC status 7/13-Eml sent to Time Warner regarding FOC status, escalation on 7/18 7/10-Pending FOC 7/12 6/27-Pending FOC 7/12 6/20-Pending FOC 7/12 6/8-Pending FOC 7/12 6/6-Rcvd USO, pending FOD 6/8 5/30-Rcvd C proj #, pending USO 5/30-Sent to CSS 5/25-Rcvd order request | Jiselle Alvarez ja746g@att.com
CA269-01-IJ | 1902 Marengo St. Suite 200 Los Angeles, CA 90033 | Los Angeles, CA | 10M Port/ 50M Access 1000 Base-SX |  | 2018-02-08 | VS18029494 30943024 3094BTGY | BBEC510571 ATI | Pac Bell HWS03664673 | 13KRGN592707PT | 2018-05-01 | TBD | TBD | 2/26: UHG requested order be cancelled. Sent request to OM for cancellation. 2/19: FOC completed on 2/14, access install scheduled for 2/28. 2/12: Order submitted by sales on 2/8, Cproject number generated.
VA060-04-IJ | 12018 Sunrise Valley Drive, Suite 400 | Reston , VA | 20MB/50MB SIP Upgrade Proj | 2018-12-27 |  | VS17225199 30943006 3094BTCD | BBEC561987 ATI | Verizon-South HES02848425 | TBD | TBD | TBD | GROUND FLOOR MAIN TELE RM, WALL MOUNTED CANOGA # 2BEHIND THE RACK | 2/26: Order completed on 2/22. 2/19-2/12: Access install completed with Demarc posted. Design scheduled for 2/26, end to end wiring 3/2, overall completion 3/14. 2/5: FOC completed on 2/2, access install scheduled for 2/12. 1/29-1/8: FOC reschedule for 2/6. 1/2: Received USO on 12/27, FOC scheduled for 1/31. | MARIA BRIONES
VA072-01-IM | 411 E FRANKLIN ST Building , Floor 2, Room MDF RICHMOND, VA, 23219 | Richmond, VA | 10MB port/20MB Access | 2017-12-01 | 2017-11-21 | VS17212186 30943522 3094BSZZ 3094BTBB | MMEC681081 ATI | VERIZON - SOUTH HES02845694 | 48KFGS304100CV | 2018-03-02 | 2018-03-05 | 1GIG OPTICAL, MMF, AUTO NEG DISABLED, 20M, 2ND FLR, STE 202 | 3/5: Order completed on 3/5 2/26-1/22: FOC completed on 1/17, access install scheduled for 3/2. 1/15: Pending EUCR form, Verizon order is set to cancel by 1/29 if form not received. 1/8: UHG must sign and return EUCR form Verizon for order to proceed. 1/8-1/2: Order supped with new LCON info & new FOC date of 2/1/18 provided. 12/26: FOC scheduled for 1/10/2018 12/20: UHG provided new lcon info. Sent info to OM to sup order. 12/18-12/8: Received USO, FOC date scheduled for 1/10/2018
C1583-04-IM | 21111 Ridgetop Circle Sterling, VA 20166 | Sterling, VA | 500MB Port/ 1GB Access 1000 Base-LX | TBD | 2017-12-08 | VS17219726 30942287 3094BTBN | IZEC596828 ATI | LNS HES02847625 | DCKRGN100215TPM | 2018-03-15 | 2018-03-07 | 1ST FLR CCA RM,CAGE 010.0CCA.031,PANELJACKS 3 & 4,TAGGED | 3/12: Order completed. 3/5-2/26: Access install scheduled for 3/12. 2/19: Resolution for fiber issue is scheduled for 2/23. 2/12-2/5: Per AIM: Site visit completed for order, currently trying to get additional fibers to existing equip. Once orders are inventoried TFS will need to turn it up before order can move forward. 1/29-1/15: Telco room ERD 1/31 FOC on hold. 1/8-12/26: FOC scheduled for 1/11/18. 12/18: Order validated on 12/15 by UHG to proceed, Pending USO 12/11: Order received and processed, pending USO/order number.
AL016-04-IM | 500 Paul Bryant E Tuscaloosa, AL 35401 | Tuscaloosa, AL | 20MB Port/ 100MB access | TBD | 2018-12-12 | VS18002928 30943057 3094BTCM Site ID: 569995 | IUEC958842 ATI | ATT SE HSS03458410 | A3KRGN602422SC | 2018-03-23 | 2018-03-09 | 1ST FLR TELCO ROOM WALL MOUNTPORT 2 | 3/12: Order completed on 3/9. 3/5: Fiber PLC/SPLC completed, access install scheduled for 3/9. 2/26-1/22: FOC completed on 1/18, Access install scheduled for 3/9. Build required: EF offer -Site Ready: 2/16: Complete -Fiber PLC/SPLC: 3/2 1/15: FOC scheduled for 2/5. 1/8-1/2: Pending USO for order. 12/26-12/18: Sales sent to ordering pending processing and Cproject number. | SHERRYL MENDEVIL
UMD14-07-IM | 2111 Van Demand St Baltimore, MD 21224 | Baltimore, MD | 20MB port/ 50MB access | 2017-12-18 | 2017-12-11 | VS17221382 30942459 3094BTBP | BBEC552147 ATI | Verizon- South HES02847643 | 38KFGS303055CM | 2018-03-06 | 2018-03-10 | MAIN DATA ROOM IST FLOOR WALL MOUNTED POSITION B..TAGGED | 3/12: Order completed 3/10. 3/5: End to end testing scheduled for 3/8 , overall DD scheduled for 3/12. 2/26: Access install completed. Pending end to end design and testing. 2/19-2/12: Per Verizon: Still have construction and broken conduit, pending ECD. 2/5: Per AIM: Construction delayed due to obstructed conduit. structure resolution is in progress and work order has been released to contractor, pending ECD. 1/29-1/15: FOC completed and access install scheduled for 1/31. 1/8: LCON info changed, order supped with new FOC date of 2/7. 1/2-12/26: FOC scheduled for 1/26/18. 12/18: Received USO on 12/18, FOC is scheduled for 1/23/18. 12/11: Received order, pending order number/USO. | MAILEN BACANG
TX261-01-IM | 13725 Northwest Blvd. - Suite A Corpus Christi, TX 78410 | Corpus Christi, TX | 10MB Port/50MB Access | 2017-08-30 | 2017-08-16 | VS17154271 30942976 3094BSTW C11339226 | BBEC598290 ATI | Time Warner HMS02232470 | 36L1XX000854 TWCC | TBD | 2018-03-13 | DMARC COM MON ROOM FLOOR- 1ST RACK LOCATION ? IT ROOM CPE RX LEVEL -6 HUB RX LEVEL-8 | 3/12: LEC delivered circuit with demarc posted. Pending firm date for end to end testing 3/5: Order has been supped for re-dispatch. 2/27: Room ready for delivery. 2/26: Pending confirmation of building being ready. 2/20: Site will be ready sometime next week. 2/19: Per AIM: Building under construction, sup has been requested for new DD. 2/12: AIM scheduled for follow up on 2/13 for construction updates. 2/5: Per AIM: Construction is complete, per field tech fiber was ran to incorrect building. Pending redesign to new wave build in correct building. 1/29-1/2: Per AIM: Lateral work is in progress, ECD scheduled for 1/29. 12/26-12/11: Per AIM: ROE singed on 12/7 , ECD scheduled for 1/29. 12/4: AIM is pending ROE. Following up with the LEC. 11/27: Emailed AIM to check with LEC about ROE form and scope of work to provide. 11/20: Pending ROE from landlord. 11/13: PM info was provided and sent to provisioning team. Order will be supped to move forward, pending new dates. 11/6: Lec is needing property managers contact info. Order is on hold due to no landlord info, needing to obtain ROE to move forward. 11/1: Per Lec manager : ECD on track for 11/6. 10/30: Escalating with AIM team for firm install dates. 10/23: Per AIM: Construction design complete, pending firm construction dates from construction team. 10/16: Escalation ticket being worked by AIM team to assist with FOC completion. 10/9: FOC escalated for completion. 10/2-9/11: Estimated FOC date scheduled for 10/5. 9/5: USO received 8/30, Target FOC date scheduled for 10/5. 8/28: Pending new IP's for order. 8/28-8/21: Ordering submitted order, pending order number/USO | Gabriel Rodriguez
CA250-01-IM | 4 Technology Drive Irvine, CA 92618 | Irvine, CA | 100MB Port/ 1GB Access | TBD | TBD | VS17206801 30943514 3094BSZY Site ID: 554930 | IZEC555583 ATI | Pac Bell HWS03645037 | 13KRGN592096PT | TBD | 2018-03-19 | 1.1, WALL MOUNTED VIRTUAL EDGE PANEL 1POS 1 & 2 | 3/21: Order completed. 3/19-2/19: Access install scheduled for 6/13. Fiber Plc & Splc scheduled for 6/5. Scope of work: 1) PL APPROX 663 FEET OF 1-1.25 INCH UNDERGROUND/BUILDING INNER-DUCT 2) PL APPROX 893 FEET OF 5B92MT-024 UNDERGROUND/BUILDING FIBER CABLE 3) ENERGIZE (2) FIBERS TO CUSTOMER LOCATION 4) PLACE (1) INDOOR WALL MOUNTED 24-FIBER TERMINATION PANEL (FBT) 5) PERFORM ALL ASSOCIATED FIBER SPLICING TO SUPPORT THE PROVISIONING OF (1) ASE CIRCUIT 2/12: Site visit completed 2/12, pending firm dates. 2/5: Pending site visit confirmation. 1/30: Site visit changed to 2/5 1/29-1/22-1/8: Per UHG: Requesting to schedule site visit for 2/2. 1/2: Site visit scheduled for 1/4, per LCON could not schedule site visit until beginning of year. 12/26: Pending foc completion, escalated for missed FOC. 12/18-12/4: Received USO on 11/28. FOC scheduled for 12/21.
NV018-07-IM | 2720 N Tenaya Way Las Vegas, NV 89128 | Las Vegas, NV | 200M Port/ 300M Access | TBD | TBD | VS18007643 30943537 | BDEC989909 ATI | Embarq HWS03654898 | 53KXGS291557CTRL | TBD | 2018-03-21 | 6TH FLOOR TELCO ROOM RACK MOUNTED, Jack Type: 850 NM, 50 MICRON MU | 3/23: Order completed on 3/21. 3/19: Access installed with demarc posted. End to end testing scheduled for 3/22, overall DD scheduled for 3/29. 3/12-2/19: Access install scheduled for 3/15. 2/12-1/22: FOC completed on 1/17, access install scheduled for 3/15 due to minor build. 1/15: FOC scheduled for 2/16. 1/8: Pending order number/USO 1/2: Order sent to for processing on 12/27, pending order being submitted by sales.
TX414-01-IJ | 304 E. San Patricio Ave Mathis, TX 78369 | Mathis, TX | 7xT1 |  | 2018-02-16 | VS18039481 30944790 30944791 30944792 30944793 30944794 30944795 30944796 | DHEC.338325.811.ATI DHEC.338325.812.ATI DHEC.338325.813.ATI DHEC.338325.814.ATI DHEC.338325.815.ATI DHEC.338325.816.ATI DHEC.338325.817.ATI | ATT SW | 34HCGS629719SW 34HCGS629716SW 34HCGS629715SW 34HCGS629717SW 34HCGS629720SW 34HCGS629718SW 34HCGS629721SW | 2018-03-23 | TBD | 1ST FLR TELCO CLOSET 8 POS MNT POS 5 1ST FLR TELCO CLOSET 8 POS MNT POS 2 1ST FLR TELCO CLOSET 8 POS MNT POS 1 1ST FLR TELCO CLOSET 8 POS MNT POS 3 1ST FLR TELCO CLOSET 8 POS MNT POS6 1ST FLR TELCO CLOSET 8 POS MNT POS 4 1ST FLR TELCO CLOSET 8 POS MNT POS7 | 3/23: Order completed on 3/22. 3/19: Access install complete on T1's with Demarc posted. Design completion pending on 1 T1 before wiring and testing. 3/12: Access install scheduled for 3/12. 3/1: FOC completed, access install scheduled for 3/12. 3/1: Order confirmed by UHG to proceed with OM. | Gemalyn Hufana gh031g@att.com
TX720-04-CM | 1950 N STEMMONS FWY DALLAS, TX USA 75207 Room: Floor: 2 | Dallas , TX | 150M Upgrade to 300M | TBD |  | VS18037438 3094BTHN 3094BTHP | BMEC979220ATI | ATT SW | TBD | 2018-03-26 | TBD | TBD | SIMPLE REHOME 3/26: Order completed on 3/24. 3/18-2/26: DD scheduled for 3/26.
TX413-02-IM | 1501 S. Closner Blvd Edinburg, TX 78539 | Edinburg, TX | 10M Port/ 50M Access | 2018-02-13 | TBD | VS18027190 30940844 3094BTGQ | BBEC599006 ATI | ATT SW HWS03664225 | 38KRGN613616SW | 2018-04-30 | 2018-03-29 | 1ST FL MPOE TELCO BB W/M POS 6,NEXT TO FIBER SLIM BOX BOX1 | 4/3: Order completed on 3/29. 3/26-3/23: Per C&E: UHG is missing their ground and will need to provide one. Please confirm that path/pwr/grnd/space are provided. 3/19-2/26: FOC completed, access install scheduled for 3/27. 2/19: FOC scheduled for 3/8. 2/13: Received valid IPs and OM will now proceed with the order. 2/2: Order requested for processing by UHG.
NV039-07-IM | 2239 Crestline North Las Vegas, NV 89030 | North Vegas, NV | 200M Port/ 300M Access | TBD | TBD | VS18008498 30942244 3094BTDC | BDEC989937 ATI | Zayo HWS03655773 | ETYX163158ZYO | 2018-04-16 | TBD | DATA CENTER AREA , RACK, LABELED NLVGNVFVAS2, PORT 1, MULTIMODE OPTIC | 4/3: Order completed on 4/2. 3/26-3/23: Access install completed, end to end testing scheduled for 4/10 & overall DD 4/16. 3/19-3/5: New access install date scheduled for 3/22 2/26-1/29: FOC completed 1/25, access install scheduled for 4/10. Build required. 1/22: FOC scheduled for 2/2. 1/15: Pending order confirmation from UHG then order can be processed by OM. 1/8: Pending order number/USO 1/2: Order sent to for processing on 12/27, pending order being submitted by sales. | JENNY CABOTAJE
TX777-08-CM | 1950 N STEMMONS FWY DALLAS, TX USA 75207 Room: Floor: 1 | Dallas, TX | 500MB Upgrade to 1GB | TBD | 2017-10-27 | VS17200052 3094BSZP 3094BSZQ | IZEC507823ATI | TDB | TDB | 2017-12-01 | 2018-03-29 | TDB | Simple REHOME 4/3: Order completed. 3/26: CUT scheduled for 3/29 @ 11pmEST 3/19: CUT scheduled for 3/21 @ 11PM EST Assigned Technician: Tonia Searcy 404-365-6148 ACCESS/PORT USO's: 3094-BSZP VLAN USO's: 3094-BSZQ Conference Bridge#: 888-675-2546 Host Code: 7255309 Participant Pin Code 1220352 LCON Name Donald R. Osborn LCON Phone 763-744-1847 LCON Email donald_r_osborn@optum.com 3/19-12/18: Port is ready for cut scheduling. 12/11-12/4: Pending DD completion, emailed OM for status. 11/27: DD scheduled for 12/1. 11/20-11/13: DD scheduled for 12/1. Order is managed by Order Manager Pavel Shames ps4324@att.com 11/6-10/30: Order processed 10/30, pending order number/ USO. | Pavel Shames ps4324@att.com | Not SDM Managed
CA269-03-IM | 1902 Marengo St. Suite 2004900 Rivergrade Road Irwindale, CA 91706 | Irwindale, CA | 10M Port/ 50M Access LC - Multi Mode Fiber 1000BSX | 2018-03-05 | 2018-02-27 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 4/3: Order cancelled to avoid SC charges. Order has been replaced with 1000BLX handoff. Pending confirmation & new IPs from UHG. 3/26-3/12: FOC scheduled for 4/13. 3/5: USO generated, PON/firm dates scheduled for 3/8.
II519-05-CM | UHG | Upgrade to 400MB | ISR18030639572 | Phoenix Infocity Private Limited SEZ, Building No. H06, First, Second and Third Floor, Hitech City 2,Gachibowli (V) Hyderabad India | India | Hitech City | Kevin Cantor 6325885331 kevin_cantor@optum.com | 4/3: Order completed. 4/3: Pending update for ISR/USO 3/26-3/6: Order placed. 3/5-2/27: Waiting on countersign 2/26-2/5: Pending contract to be signed by UHG.
UIX150 | UHG | Upgrade to 300MB | ISR18020944996 | Unitech World (Cyber Park) - Sector 39, Building B - 14th Gurgaon Haryana | India | Gurgaon |  | 4/3: Order completed on 3/26. 3/26: Pending completion confirmation of cutover. 3/19-3/5: Cutover schedule for 3/25 @ 6:30AM local. 2/27: Request for hot cut info email 2/26-2/19: OM has reached out to UHG asking for schedule. 2/19: Pending update from OM. 2/12: Received ISR pending update. 2/5: Pending ISR/order numbers 1/29-1/23: Order placed on 1/17, pending ISR | Bharti
IR777-02-IM | UHG | 1GIG MIS | CSM180105082850 | Unit 14 Northwest Business Park, Dublin Ireland | Ireland | Dublin | TBD | 4/3: Order completed. 3/26: Pending update from OM. 3/19: Per OM: Checking with CTS team if they have arranged access to site for Colt technician. 3/12: Ticket created UHG cannot see circuit up, NDI team involved assisting with resolution. 3/5: Circuit is now ready for testing, pending testing completion. 2/26: Circuit delivered handover received. TOM ( Transport order manager) team is working with IPC sarea support to resolve issue with activating circuit. 2/19: UHG confirmed that COLT can deliver on DB3, chasing IPC team to confirm if COLT can deliver through FEC1. 2/12: UHG is asking Colt to go through FEC1 instead of FEC2, checking response from IPC. 2/5: Pending firm dates. 1/29: OM is checking with IPC to see if PTT has provided firm dates. 1/22: Pending firm dates being provided. 1/16: Press for better DD and firm dates. 1/15: Order is being reworked to show customer un- managed router. 1/8: Pending update from OM. 1/2: Received new order numbers. 1/2-12/12: Order with account profile team. 12/11-11/13: Pending ISR/order number from Dublin internet. Order placed 11/14 11/7: Pending countersign 11/6: Waiting on signed contract | Colt
II529-03-IM | UHG | 300MB access 200MB port Ethernet | ISR18020191959 | 4 Hosur Road, Audugodi, Opposite MICO BOSCH, Next to NDDB, Bangalore, Karnataka, India 560034 | India | Bangalore | TBD | 4/3: Request TID letter. 4/3: Order completed. TID & TP3 letter sent. 3/26-3/5: Firm date scheduled for 4/18. 2/26-2/19: Order accepted by Telco, expecting firm dates to be provided by 2/28. 2/12: Received ISR, pending update from OM. 2/5-1/30: Received updated contract. 1/29-12/18: Pending ISR# 12/12: Have diagram, pending ISR. 12/11-12/5: Pending diagram. 11/27-11/20: Pending countersign for ISR # 11/20-11/7: Pending contract signing 11/6-10/9: Pending order numbers & revised contract. 10/2-9/25: Pending order number, pending revised contract. 9/18-9/11: Order pending order number, pending contract with new address. 9/11-8/30: Processing requested by UHG, pending confirmation. Pending legal address | TTSL
NJ722-05-CM |  | New Jersey | Port upgrade to 100M | TBD | TBD | VS18057835 3094BTKM 3094BTKN | IUEC803278ATI | TBD | TBD | TBD | 2018-04-03 | TBD | NO REHOME 4/9: Order completed on 4/3 4/3: DD scheduled for 4/3. 3/26-3/19: Received order on 3/15, pending cproject number. | Ana Chavez ac4200@abs.att-mail.com
UTX43-09-IM | UnitedHealth care Student Resources 2301 W. Plano Pkwy Suite 300 Plano, TX 75075 | Plano, TX | 10M port/ 20M Access | TBD | TBD | 30940054 3094BSZT | 30940054 | MMEC972270 ATI | AT&T of Texas RMS02245864 | 50KRGN881816SWDL | 2018-02-08 | TBD | TBD | 4/10: Order is ready for plugin. Pending confirmation of completion. 4/9-4/3: Order is being worked to change from managed to unmanaged. 3/26: MacD order release to be worked. 3/19-3/12: Pending solution for order being delivered as managed. 3/6: Order was completed as managed. 1/15: Per Halo team: demarc cannot be moved to 2nd floor since the order is already completed. Order will have to be replaced with request for 2nd floor. 1/8: Checking with backend team to see if demarc can be moved to 2nd floor. 1/8: Order completed on 1/4. 1/2-12/18: FOC completed 12/18, access install scheduled for 1/3/2018. 12/11: FOC scheduled for 12/29. 12/4: Halo/ MIS escalation ticket is opened to assist with providing FOC date. Order has been raised to next level Halo manager for assistance.
VA729-01-IM | 44480 Hastings Dr Ashburn, VA 20147 | Ashburn, VA | 500MB Port/ 1GB Access 1000 Base-LX |  | 2018-01-12 | VS18015469 30943607 3094BTDY | 30943607 | IZEC566215 ATI | Time Warner HES02851237 HES02851238 | 2SKFFN003738LVLC 7ZKFFN002518LVLC | 2018-04-10 | 2018-04-10 | FIRST FLOOR MMR 183 CABINET 2 FRONT ZG001 PORT 0/17 SMF LC | 4/11: Order completed on 4/10. 4/9: Demarc provided, overall DD scheduled for 4/10. 4/3: End to end testing scheduled for 4/3. 3/26: End to end wiring scheduled for 3/29, testing scheduled for 4/3. Overall DD scheduled for 4/10. 3/19-3/5: End to end design scheduled for 3/5, End to end wiring scheduled for 3/29, testing scheduled for 4/3. Overall DD scheduled for 4/10. 2/27: Created escalation ticket for access install. 2/26: Pending access install completion. 2/19: Access install scheduled for 2/23. 2/12: FOC completed on 2/7, access install scheduled for 2/23 2/5: FOC scheduled for 3/1. 1/29: OM assigned and order confirmed by UHG. Pending USO 1/22: Pending confirmation of OM assignment and USOs. 1/15: Order submitted for processing on 1/12.
TN048-01-IJ | 3102 West End Avenue Suite 800 Nashville, TN 37203 | Nashville, TN | 20M Port/ 50M Access | 2018-02-26 | 2018-02-21 | VS18037907 30943723 3094BTHS | 30943723 | BBEC530510 ATI | ATT SE HSS03473220 | T4KRGN823764SC | 2018-05-11 | 2018-04-11 | 7TH FLR, MAIN TELCO ROOM, PORT 8 | 4/11: Order completed on 4/11. 4/9-4/3: New access install date scheduled for 4/11. 3/26-3/23: Lec was not granted access due to site closing early. UHG provided next available time of 3/26 9-4pm local time. OM has notified the LEC 3/19-3/5: FOC completed, access install scheduled for 3/19. 2/26: Cproject number created, pending order number. Order confirmed with OM by UHG
CA109-07-CM | 18 CENTERPOINTE DR La Palma, CA 90623 | La Palma, CA | 40M Upgrade to 100M | TBD | 2018-01-05 | VS18023380 3094BTFX 3094BTFY | 3094BTFX Not SDM Managed | IUEC882705ATI | TBD | TBD | 2018-03-05 | TBD | TBD | SIMPLE REHOME Not Managed by SDM 4/16: Order completed on 4.16. 4/9: Requested cut date 4/16 @9:15pm CST confirmed 4/3: Order is ready for cut scheduling. 3/26-3/12: Pending DD completion. OM managed order. Lee Alday la269a@att.com 3/5-2/5: DD scheduled for 3/5. 1/29: OM assigned and working order. 1/15-1/8: Received order on 1/5 and processed. Pending order number/USO. | Lee Alday la269a@att.com
CO054-02-IM | 6251 Greenwood Plaza #300 Main Bldg. Telco RM 2nd flr Greenwood Village, CO 80111 | Greenwood Village, CO | 10M Port/ 50M Access 1000 Base-SX | 2018-02-14 | 2018-01-29 | VS18030631 30942735 3094BTGX Added | 30942735 | BBEC510304 ATI | Qwest HWS03664644 | 29KXGS299467MS | 2018-05-01 | TBD | 2ND FLOOR ELEC/TELCO ROOM WALL MOUNT CIENA MINI DIRECTLY ABO | 4/23: Order completed on 4/18. 4/16-4/3: Access install completed, end to end testing scheduled for 4/24. 3/26-2/26: FOC completed, access install scheduled for 4/2 due to interoffice facility build. 2/19: FOC scheduled for 3/21. 2/12: Order confirmed by UHG to proceed. Pending order number/USO. 2/5-1/29: Order submitted, received Cproject number. Pending USO/order numbers
| 21111 Van Deman Street, Baltimore, MD | Baltimore, MD | AVPN Change MACD Multicast Add |  |  | VS18071114 3094BTLS | 3094BTLS | VLEC013436331ATI | TBD | TBD | TBD | 2018-04-17 | TBD | 4/23: Order completed on 4/17 4/16: Received Cproject number pending USOs
MD021-04-IJ | 8501 Lasalle Rd, 1 Mdf, Towson, MD | Towson, MD | 50MB port/ 100MB Access 100 Base-TX | 2017-08-01 | 2017-07-26 | VS17138984 30943857 3094BSQH | 30943857 | IUEC617731 ATI | Comcast Business Comm HESC2831138 | 14KFGS049665 | 2017-11-06 | TBD | 2ND FLR SERVER RM, MOUNTED IN RACK U25/26 UNDER THE FIBER TRAY, LABELED COMCAST BUSINESS. | 4/23: LEC completed access install, pending firm dates for end to end testing. Escalated with provisioning team for ECD. 4/16: Per AIM: LEC will dispatch on 4/20 please provide access to the site. Please update LCON MELISSA COLLINS 410-371-6168 MELISSA_COLLINS@UHG.COM. 4/9: Escalated with AIM for dispatch new dispatch date. 4/2: Sup was submitted to change LCON info by provisioning team. 3/26-3/23: Requested that UHG provide a responsive LCON. Per LEC LCON was not responsive. 3/19: Per AIM: Comcast will dispatch to the site to perform final testing on 3/22. 3/12: Called Comcast contact for update & had no answer. SDM will follow up on 3/15. 3/5: Pending update from Lec manager on status of splicing work. 2/26-2/19: Splicing work with OSP continues. Comcast has provided tentative date of 3/2 for work completion. 2/14: Per AIM: Comcast is having issues with OSP and splicing work. 2/12: Escalated to AIM team for explanation on install schedule. 2/5: Access install has been rescheduled. Pending firm date from Comcast. 1/29-1/22: Access install scheduled for 2/2. 1/15-1/8: Per Comcast work is needed for order. 1/2: Access install scheduled for 1/31. 12/26: Escalated with provisioning manager and leadership to complete install. Ticket opened with AIM team. 12/18: Escalating with provisioning manager for install completion. 12/11: Escalated with provisioning for access install date. 12/4: Pending access install completion, escalation has been sent to provisioning team. 11/27-10/30: New access install date scheduled for 11/30. 10/23-9/11: Estimated access install date scheduled for 10/31 9/5: FOC completed 8/30, Target access install date scheduled for 10/31. 8/28: Escalated to provisioning manager for missed FOC, asked for AIM ticket. 8/21-8/14: Target FOC date scheduled for 8/23.
C1625-04-CM | 6900 S PEORIA ST CENTENNIAL, CO USA 80112 Room: MDF Floor: 1 | Centennial, CO | Change from 1000-SX optic to a 1000-LX SMF | TBD | TBD | VS18048332 30942514 3094BTJT | 30942514 | BMEC882033 ATI | Qwest HWS03677672 | TBD | TBD | 2018-05-03 | TBD | 5/3: Order completed on 5/3. 5/2: Physical switch has completed, CL will sned over completion letter. 4/30: Re-dispatch scheduled for 5/2. Will Check for tech info on 5/2 when techs are assigned. 4/16: Opened escalation ticket, AIM has engaged to assist with access install. Order shows CNR, requested details for CNR status. 4/9: FOC completed on 4/5, access install scheduled for 4/13. 4/4: PON received, FOC scheduled for 5/8. 4/3: Created escalation ticket with provisioning manager for PON release. 3/26-3/19: Escalated with provisioning team for PON and firm dates. 3/15: PON scheduled for 3/16, pending firm dates.
TX406-01-IM | 12357-C Riata Trace Parkway Austin, TX 78727 | Austin, TX | 70M Port/ 100M Access 1000 Base SX | 2018-03-12 | 2018-03-01 | VS18046076 30942021 3094BTJR | 30942021 | IUEC867796 ATI | AT SW HMS02265909 | 32KRGN652861SW | 2018-05-25 | 2018-04-30 | 1ST FLOOR MAIN TELCO ROOM WALL MOUNT | 5/1: Access install completed. 4/30: Access install scheduled for 4/30. 4/23: FOC completed, access install scheduled for 4/30. 4/16: Address was supped by LEC, new FOC date of 5/7 provided. 4/9: Opened escalation ticket for FOC completion. 4/3-3/15: FOC scheduled for 4/5 3/12: Pending USO/order number. UHG confirmed order on 3/7. 3/5: Cproject number received.
| 410 E FRANKLIN ST Richmond, VA 23219 | Richmond, VA | Remove Multicast |  |  | VS18075752 3094BTMB | [5 empty] | 2018-04-24 |  | 4/30: Order completed on 4/24.
| 411 E FRANKLIN ST Richmond, VA 23219 | Richmond, VA | VPN Reassignment |  |  | VS18078241 3094BTMJ | [5 empty] | 2018-04-27 |  | 4/30: Order complete on 4/27.
VA730-01-IM | 44664 Guilford Drive Telco Room Ashburn, VA 20147 | Ashburn, VA | 500MB Port/ 1GB Access 1000 Base-LX | TBD | 2018-01-30 | VS18029807 30940978 3094BTGR | 30940978 | IZEC550522 ATI | Time Warner HES02853881 HES02853882 | 2SKFFN003760LVLC | 2018-05-07 | 2018-05-07 | FIRST FLOOR V AULT 1 MMR RR J.6 RMU 30 PORT 73/74 SMF SC/SC LABELED WITH CID." R80 | 5/7: Order completed on 5/7. 4/30: End to end testing scheduled for 5/4, overall DD scheduled for 5/7. 4/23: Access install completed with demarc posted. Pending end to end design, wiring & testing. 4/16-4/9: FOC completed, access install schedule for 4/18. 4/3: Per TW: LEC FORECASTED THE FOLLOWING SOW W/MILESTONES: BENCH TEST - 3/29/2018; FIELD INSTALL (FCD) - 04/04/2018; TESTING -04/09/2018; TNOC - 04/10/2018; MAKE AVAILABLE (NCD) - 04/11/2018; NETBUILD DUE DATE (AKA - NDD) - 4/18. LEC NOTED, BARRING NO UNFORESEEN ISSUES, "TENTATIVELY", PROJECTED FOC ISSUANCE 4/11 W/AN ESTIMATED 5-7 BUS. DAYS FOR OVERALL CKT COMPLETION (I.E. 4/20 COB) 3/23-2/19: FOC scheduled for 3/23. 2/13: UHG confirmed order to proceed. 2/12: Pending UHG confirmation of order details to proceed. 2/5: Pending order numbers/ USO 1/29: Received order from UHG, order submitted.
UFL42-06-IM | 805 Executive Center Dr ST. Petersburg, FL 33702 | ST. Petersburg, FL | TBD | 2018-02-13 | TBD | VS18029284 30940274 3094BTGL | 30940274 | BBEC550830 ATI | Bright House HSS03469275 | 72L1XX000344TWCC | TBD | 2018-05-04 | 2ND FLOOR NETWORK ROOM WALL MOUNTED | 5/7: Order completed on 5/4 4/30-4/9: Access install scheduled for 6/11. 4/3: FOC completed, access install scheduled for 6/11. Order requires construction. 3/26-3/23: Per Brighthouse: Order has construction with ECD of 4/23, install scheduled for 5/7. FOC is pending engineering release next follow up scheduled for 3/30. 3/19: Raised escalation ticket to tier 2 with AIM for FOC completion. 3/12: AIM engaged for FOC completion. 3/5-2/19: FOC scheduled for 3/8. 2/12: UHG confirmed order with OM to proceed. 2/5: Pending order numbers/ USO 1/29: Pending technical details. 1/22: Order placed on 1/18, pending OM assignment and USOs 1/15: Pending UHG response with which ESP for order.
NY078-06-IM | 136-02 ROOSEVELT AV Building , Floor 1, Room TELCO FLUSHING, NY, 11354 | Flushing, NY | 10M Port/ 50M Access | 2018-01-12 | 2018-01-03 | VS18007613 30943536 3094BTCX | Canceled | BBEC578280 ATI | Verizon- North | TBD | TBD | TBD | TBD | 5/8: Remove 4/16-2/26: Order canceled until ROW completed. 2/19-2/5: Pending ROW status. 2/5-1/15: FOC scheduled for 2/15. | MARITES BALBEN
FL243-01-IM | 10650 Metro Parkway Suite 100 Fort Meyers, FL 33966 | Fort Meyers, FL | 10M Port/ 50M Access LC - Multi Mode Fiber 1000BSX | 2018-03-18 | 2018-03-09 | VS18051301 30942723 3094BTJZ 3094BTKB | 30942723 | BBEC507890 ATI | Embarq | 25KXGS307036UFLG | 2018-06-04 | TBD | TBD | 5/8: Order canceled 5/7: UHG requested to cancel order. Sent OM request to cancel order. 4/30-4/16: Access install scheduled for 5/14 due to minor build. 4/9: FOC completed on 4/4, access install scheduled for 5/14. Minor build required. 4/3: Escalated ticket to next level for AIM engagement for FOC completion. 3/26: Received PON, opened escalation ticket for FOC. 3/19: Received USO, pending PON and firm dates. 3/12: Received order on 3/6, placed on 3/9. Pending cproject order number.
II547-02-01 | UHG | New order with TCL | ISR18030855070 3094BTJM ROG: Added | 3094BTJM | BKYF.101303..ATI | TBD | TBD | Gurgaon, HR | Telco (TCL) has completed last mile cabling between MUX & Router rack (1000Base SX // LC // Multi-mode fiber interface) and also circuit ID tagged on fiber cable near router rack: 091NOID1143030888579 | 5/7: TID+TP3 letter sent: UHG confirmed that last mile cabling completed with circuit ID tagging. 4/30: Telco confirmed that they are getting errors while testing the circuit and NOC team is assisting to fix the issue. Order has been escalated for completion asap. 4/23: Circuit provisioning is still in progress and expected to be completed in a day or two. On track for 27April Apr 2018 4/16: IPC is pushing the TCL to complete the provisioning asap as they advised they are on track for 4/27 - I have requested the circuit to be handed over to us this week. 4/9: Per OM: The MUX has been upgraded, TCL will now move the order to provisioning - logical configuration and testing. Once done we're good to close the order but I expect the TID to be sent sometime next week. 4/3: Per OM: - TCL team confirmed that there is Bandwidth crunch issue on existing fiber ring so they need to upgrade the mux from STM 4 to new higher STM 16 fiber ring. Thus we required 5 hrs downtime for the below circuit to upgrade the mux. Kindly arrange downtime window and confirm to proceed further. Thanks. Down time Window Will be : Friday 6th Apr 2018 to Saturday 7th Apr 2018 from 7:00 PM to 5:00 AM OR Sunday 8th Apr 2018 from 11:00 AM to 6:00 PM. Please Note : basement Access also required without Basement Access we can't Perform the Activity 3/26-3/21: Firm date scheduled for 4/27. 3/19-2/13: Received access and order team is processing order. 2/12-1/23: Order new access for incorrect address changed zip code & building number. 1/22-1/8: Pending ISR# 1/2: Counter sign completed and order was placed. 1/2-12/11: Pending order information. Waiting for counter sign
II547-02-01 | UHG | 500mg access from TCL connecting to ND3 POP | ISR17073118344 3094BSPV ROG: Added | 3094BSPV |  | Unitech World Cyber Park 1ST-4TH Flr Tower C Sector 39, Gurgaon-122009 State-Haryana | India | Gurgaon, HR | JAROSLAV BOSANSKY | 5/8: Will install new circuit. 5/7-1/2: Order completed. Pending MD5. 1/2: Pending confirmation of overall completion. 12/26-12/5: Request auto complete for after hours. Pending confirmation for that request. 12/4: Pending MD5 password confirmation. 11/27: TID & TP3 letter sent. Pending MD5 password. 11/21: - Circuit provisioning- 2 to 3days Last-mile cabling-1day Telco Testing-1-day SPIRENT Testing-1day 11/20: Node integration, provisioning, cabling & Testing works are pending 11/13-10/30: Fiber ring creation in progress. On track for revised FOC date 11/22. 10/23-10/9: Telco shared revised FOC date as 11/22 since they need to re-do the Ring formation work(as highlighted earlier Bandwidth utilized for other circuit since order was on hold). 10/3: Updated OM with plan. 10/2: Bharti advised there is Bandwidth constraint to deliver on separate Fiber ring. Two options: - Bharti will deliver circuit via the same path as the Verizon circuit but will install separate MUX - Order will be reworked by Adam with TCL; Bharti cancellation fee towards customer will apply. 9/25-9/18: Revised delivery date is now set to 11/2. Telco will provide based on progress. Checking with different provider ( pending ) Scope of work: 400meters in-building Fiber work, Mux/Rack installation, Fiber termination, Node integration, circuit provisioning, Last-mile cabling, Testing & Circuit hand-over. 9/6-8/29: Order manager has confirmed with cust contact. Site is ready. Per email expected delivery from telco is 9/30/17. 8/29: Room is ready Per UHG. 8/28: Scope of work: 180meters outside Fiber work, 400meters in-building Fiber work, Mux/Rack installation, Fiber termination, Node integration, circuit provisioning, Last-mile cabling, Testing & Circuit hand-over. Confirm cust room ready. 8/21: PTT was informed rack were done. Pending response from PTT on scheduling. 8/14: Order accepted by Telco, Pending DD by 8/18. 7/26-Pending order numbers
MN066-01-IM | 2685 PATTON RD Building , Floor 1, Room MDF Roseville, MN, 55113 | Roseville, MN | 10M Port/50M Access 1000Base-SX | 2018-04-03 |  | VS18060659 30943787 3094BTKP ROG:4/3 | 30943787 | BBEC538092 ATI | Qwest HCS03953813 | 03KXGS310647NW | 2018-06-19 | 2018-05-08 | I2625 MPOP. LOCKBOX CODE 0 7. WALL MOUNT 3916. MM OPTICAL PO | 5/8: Order completed o 5/8/2018. 5/7: Order added to escalation list for early completion. 4/30-4/23: Order has be escalated for completion with escalation manager. 4/16-4/11: Access install completed, pending end to end testing. Write business case for WWR. 4/9: FOC completed on 4/6, access install scheduled for 4/13. 4/3: Received USO, FOC scheduled for 5/7. |  |  | Added on 4/3
MN060-01-IM | SavvySherpa 6200 Shingle Creek Pkwy 400 Suite 400 Brooklyn Center, MN 55430 | Brooklyn Center, MN | 100M Port/ 200M Access 1000 Base-SX | 2018-05-07 |  | VS18081507 30943715 3094BTMR | 30943715 | BKEC999256 ATI | Qwest HCS03977227 | 03KXGS318973NW | 2018-07-24 | 2018-05-18 | 1ST FLOOR MPOP. WALL MOUNT CIENA 3916. MM OPTICALPORT 3. TY | 5/21: Order completed on 5/18. 5/14: FOC completed on 5/14, access install scheduled for 5/17. 5/7: FOC scheduled for 6/11. 4/30: UHG placed order. Pending Cproject number.
IL043-07-IM | 1600 McConnor Parkway Schaumburg, IL 60173 | Schaumburg, IL | 250M Port/ 500M Access 1000 Base-SX | 2018-04-30 | 2018-04-17 | VS18075722 30943703 3094BTMK Site ID: 622491 | 30943703 | BMEC997998 ATI | ATT MW HCS03976104 | KRGN119429LB | 2018-07-17 | 2018-05-15 | FLOOR 1 TEL ROOM BAY 5 CUSTOMER DMARCSHELF 1 , PLUGS 3/4 & TAGGED | 5/21: Order completed on 5/15. 5/14-5/7: FOC completed on 5/4, access install scheduled for 5/15. 4/30: Received USO, PON schedule for 5/3. 4/23: Order placed on 4/17, pending OM assignment and USO
GA777-10-CM | 56 MARIETTA ST NW ATLANTA, GA USA 30303 Room: MMR Floor: 2 | ATLANTA, GA | Upgrade to 1Gig | TBD | TBD | VS18086312 3094BTNB 3094BTNC | 3094BTNB | IZEC574366ATI | LNS | TBD | TBD | 2018-05-18 | TBD | NO REHOME 5/21: Order completed on 5/18. 5/14: DD scheduled for 5/18. Order managed by 5/7: Order processed on 5/3, pending cproject number. 4/30: UHG submitted order for upgrade. | Al Franco Ocampo ao209j@att.com
WI014-02-IM | 3237 AIRPORT RD | LA CROSSE , WI | Upgrade Port to 1 gig | TBD | TBD | VS18056746 30943756 3094BTKJ | 30943756 Not SDM Managed | IZEC551053ATI | TDB | TDB | 2018-04-24 | TDB | TDB | NO REHOME 5/21: Order completed 5/15: Scheduled for 5/18 @ 8PM EST. 5/14: Orders are ready for cut scheduling. 4/23: Per OM: Circuits are ready for cut scheduling. 4/17: Received USO, DD scheduled for 4/23. 4/16: Orders have been assigned to OM, pending USOs. UHG requested that orders do not auto complete.
C1584-04-IM | 1649 W Frankford Rd Carrolton, TX 75007 | Carrollton, TX | 500MB Port/ 1GB Access 1000 Base-LX | 2018-01-19 | 2017-12-11 | VS18012207 30942530 | 30942530 | IZEC520861 ATI | Time Warner HMS02253876 | 1TKFFN007428LVLC | 2018-04-05 | 2018-05-25 | 1ST FLOOR AC RACK 02B RMU 39 W2008 GE0/0/23 SM L/C TAGGED WITH CID | 5/25: Order completed 5/25. 5/21: AT&T and LEC tech are reviewing order to complete switch on jacks. 5/14: Executive escalation manager working order with provisioning manager. Tech is verifying TDI with LEC. 5/7: Testing tech is not receiving light from Level 3, ticket has been created for testing assistance with Lvl3. 5/1: Order is being worked by executive escalation team for testing and overall completion. Escalation ticket has been opened to test loop with tech team. 4/23: From provisioning update: The EVC portion of the circuit has not yet been completed. AIM team has escalated with Exec TW team and request ECD for completion. AIM has a scheduled Exec meeting with TW on 4/25 for an update. 4/16: Design work completed, moved order to escalation manager for testing and overall completion. 4/9: Escalation ticket has been opened with design team. 4/3: TDI issue resolved, order has been sent to tech team to wire tail orders. 3/26-3/19: Requested that AIM engage level 3 with TDI issue. Pending LEC provide new TDI info. 3/12: ATT design team sent list of available TDI's to LEC waiting on new TDI from LEC. 3/6: AT&T design team has requested vendor meet with LEC. TDI that was provided is no assigned correctly. 3/5: End to end design scheduled for 3/20. 2/26: Access install completed, pending demarc and end to end design. 2/19-2/5: FOC completed, access install scheduled for 2/20. 1/29-1/22: FOC scheduled for 2/26. 1/16: Will use new carrier TW Sales issued on 1/9. 1/8-1/2: Pending new sold notice for order. 12/26-12/18: Received Cproject number pending USO. 12/11: Received order, pending order number/USO.
MD742-01-IM | Quality Metric 6900 Muirkirk Meadows Drive Beltsville, MD 20705 | Beltsville, MD | 200M Port/ 300M Access 1000 Base SX | 2018-03-14 |  | VS18048214 30942671 3094BTJV 3094BTJW | 30942671 | BDEC990623 ATI | Verizon HES02857976 | 36KFGS308363CD | 2018-05-30 |  | GND,,RM MAIN,TEL RM,,RJ48C,LP N,CAB | 6/1: Order completed on 5/30. 5/29-4/30: End to end testing schedule for 5/22, overall completion scheduled for 5/30. 4/23: Access installed with demarc posted, pending end to end testing ECD from provisioning. 4/9: Access delayed until 4/12 due to no access to customer site. 4/3: FOC completed, access install scheduled for 4/4. 3/26: FOC rescheduled for 4/23. 3/19: FOC scheduled for 4/20. 3/12: Order received from UHG on 3/9.
| Chennai | Circuit add to RG1 10 Meg Ethernet | [5 empty] | MLYF.108511..ATI | [5 empty] | 5/29-6/4: RG completed per UHG. 5/29-4/24: Schedule being worked out. 4/23-4/16: MACD has been processed to add this sit to RG1. 3 Step Process: 1. Remove multicast 2. Add site to route group 1 as a member site 3. Add multicast back on
WI011-06-IM | 11 Scott St Wausau, WI 54403 | Wausau, WI | 200M port/ 500M Access 1000 Base-SX |  | 2017-10-17 | VS17191210 3094-3142 3094-BSYM 3094-BSYN | 30943142 | BMEC859470 ATI | CC FIBERLINK LLC | 71L1XX005507TWCC |  | 2018-06-20 | SERVER ROOM -PORT 0/0/2 | 6/20: ORDER READY FOR TURN UP 6/18: Access install has completed and the order is pending testing completion and the OK to turn up. Order has been added to the district escalation list for completion. NEED DEMARC INFO 6/12: We received an update from Access Vendor Management (AVM) that they have been in touch with the LEC CC FIBERLINK (aka Spectrum) and Spectrum is estimating completion of access install by 6/15. AVM’s next follow up with the LEC is scheduled for 6/13. 6/6: Escalation sent to District Escalation Manager - submitted AERO CM Ticket 244637 to engage Access Vendor Mgmt (AVM) 6/5: Notes indicate an address issue - two addresses mentioned were 115 W WAUSAU AVE and 11 SCOTT ST. Order being jep'd CNR....can you confirm correct address? 6/1-5/29: Per LEC: Pending install completion, new estimated date of 6/1. Will follow up 6/4. 5/21: Per CC fiber link completion is pending. No firm ECD has been provided. 5/14: Per AIM: LEC has target completion date of 5/18. 5/7: Per AIM: Access has not been completed, LEC is working to deliver & pending ETA. 4/30: Escalation ticket created with AIM team for access install completion. 4/23-3/6: Access install scheduled for 4/27 3/5: Confirm address for site. Address stay the same. 2/26-12/11: FOC completed, access install scheduled for 4/27 due to build. Requesting build details from the LEC. 12/4-11/13: FOC scheduled for 12/18. 11/6: Escalated with provisioning manager for PON. 10/30: Pending PON being generated and sent to LEC. 10/23: Received C-project # pending USO's. 10/16: AltLCON provided pending confirmation of order processing. 10/9: Pending AltLCON info to place order.
TX401-03-IM | 1104 W Sam Houston Avenue Pharr, TX 78577 | Pharr, TX | 10M Port/ 50M Access 1000 Base-SX | 2018-04-25 | 2018-04-20 | VS18076200 3094-3451 3094-BTMF | 30943451 | BBEC538873 ATI | ATT SW HWS03682852 | 38KRGN613656SW | 7/12/2018 DD will be pushed out | 2018-06-14 | 1ST FLR MDF RM, WALL MOUNT, HANDOFF SLIM BOX POS#1 AND 2 | 6/18: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY. 6/12: Fiber placement/splicing work completed on 6/7 ahead of schedule. Access install has been improved from 7/24 to 6/18. 6/4-6/6: Construction & Engineering scheduled to complete fiber placement and splicing on 7/17. 5/29-6/4: Access install scheduled for 7/24. 5/21: FOC completed on 5/16, access install scheduled for 7/24. 5/14-4/30: FOC scheduled for 5/17. 4/23: Order placed on 4/20, pending OM assignment and USO | SHERRYL MENDEVIL
UAK01-01-IM | 301 K Street MDF RM Flr 7 Anchorage, AK 99501 | Anchorage, AK | 10M Port/ 10M Access 1000 Base-SX | 2018-04-03 |  | VS18061400 3094-3830 3094-BTKQ 3094-BTKR | 30943830 | MLEC554768 ATI | ALASKA COMMUNICATIONS SYS HWS03677442 | 47CUXP801978002ACSI | 2018-06-28 | 2018-06-25 | COMPLETION DEMARK INFORMATION: 47.CUXP.801978.002.ALS INSE RTED 850 MM SFP IN GI 4, LEFT PAPER TAG WITH ATT CIRCUIT I D AND LABELED 8044 WITH ACS CIRCUIT ID. CIRCUIT IS LOCATE D IN DEMARC IN SUITE 200. 8044 IS MOUNTED ON WALL HIGH ON THE LEFT. PON: HWS03677442/3094-3830-0002 ON 5/24 MESSAG | 6/26: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 6/18: Access install is complete. Demarc provided. Pending notification VLAN is complete. Once confirmed, I'll add this to the District escalation list for completion. 6/12: Tier 2 followed up with Alascom again yesterday 6/11. Pending update. 6/6: TIER 2 followed up with Alascom - pending status on access install. 6/4: TIER 2 engaged for support - they have sent a follow up to LEC Alascom for update on access install - next follow up is 6/6. 6/1-5/29: CM is pending a response from the LEC, will follow up on 5/30. 5/21: AIM ticket opened for access install completion. 5/14-5/7: Access install scheduled for 5/17. 4/30-4/16: FOC completed, access install scheduled for 5/17. 4/9: FOC scheduled for 4/18. 4/3: OM sent out confirmation letter, pending UHG response. 3/26: Pending Cproject number. 3/19: Received order 3/13, pending cproject number. | SHERRYL MENDEVIL
CA269-03-IM | 1901 Marengo St. Suite 4900 Rivergrade Road Irwindale, CA 91706 | Irwindale, CA | 10M Port/ 50M Access 1000 Base-LX | 2018-04-03 |  | VS18061623 3094-3802 3094-BTKS 3094-BTKT | 30943802 | BBEC583425 ATI | Frontier-CTF GWSC3677912 | 45KFGS843718FTNC | 2018-06-28 | 2018-06-26 | SLOT 00,SHELF 00, PORT 00, BASEMENT, NORTH WALL, JACK RJ45C, NOT EXTENDED, TAGGED | 6/26: ORDER COMPLETE - READY FOR TURN UP 6/18-6/25: Added order to district escalation list for completion - ready for turn up - overall target is 6/28 but pushing for earlier completion. 6/12: Pending testing completion on order and OK to turn up. VLAN PON GWSC3677912 is complete. Overall due date is 6/28. 6/4-6/11: R80 completion posted on access - demarc provided. Pending testing completion and the OK to turn up. Overall due date 6/28. 6/1: Per LEC: pending testing of circuit to post access install completion. 5/29: Access install scheduled for 5/31. 5/21: FOC completed on 5/15, access install scheduled for 5/31. 5/14: Created AIM escalation ticket for FOC completion. 5/7-4/9: FOC scheduled for 5/9
PA134-01-IJ | 620 W. Germantown PikeSuite 200 Plymouth Meeting, PA 19462 | Plymouth Meeting, PA | 10M Port/ 50M Access LC - Multi Mode Fiber 1000BSX | 2018-03-02 | 2018-02-22 | VS18039366 3094-3733 3094-BTJB Site ID: 591844 | 30943733 | BBEC588445 ATI | ASE LNS HES02856206 | PAKRGN100391TPM |  | 2018-06-18 | 2ND FLR DATA RM, RACK ATT VIRTUAL EDGE PANEL 020001.029 PORTS 1&2 | 6/18: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 6/12: Pending update from field on access install that was due yesterday 6/11. BERT ticket issued for missed EAD. 6/11: Customer didn't provide access to site - install rescheduled for today 6/11. 6/4: Order supped, access install scheduled for 6/8. 5/30: Received new Lcon info. Requested order be supped with new lcon and re-dispatch. 5/29: Please verify LCON, LEC tried to dispatch and had no access. Current LCON Carmen Phillips & Kevin Joslyn. 5/21-5/14: Access install scheduled for 6/5. 5/7: FOC completed on 5/2, access install scheduled for 6/5. 4/30-4/23: Order has been supped to correct the address to 2nd flr. New FOC date of 5/16 has been provided. 4/16-4/9: ECD for SOW has been changed to 4/18. 4/3: Per LEC: Site visit was completed. Currently trying to confirm that customer can be served from the EMUX in a different building on the campus. We will be putting together a SOW and sending it over to the building for approval. ECD 4/9 3/26-3/5: FOC scheduled for 3/26. 2/26: Cproject number created, pending order number. | JENNY CABOTAJE
C1631-02-IM | 683 South 4150 West Salt Lake City, UT 84104 | Salt Lake City, UT | 600MB Port/ 1Gbps |  |  | VS18029526 3094-0547 3094-BTGP Site ID: 586213 | 30940547 | IZEC543726 ATI | ASE LNS HWS03664157 | UTKRGN100000TPM |  | 2018-06-18 | ATT CAB DEMARK,A4 WESTEL 12 PORT SHELF R2 PORTS 3 AND 4 SC | 6/18: ORDER COMPLETE - READY FOR TURN UP PLUG AND PLAY 6/12: Access install showing on track for 6/14 completion. 5/14-6/11: Per Tech Engr: The location has been determined for the new 5150 box, showing a current ECD of 6/5. Access install date scheduled 6/14. 5/7: Technical engineer is pending an update by end of week. 4/30-4/23: OSP engineer will be working with site manager to negotiate space to accommodate larger ciena 5150 box. 4/16: OM provided Engineer contact to discuss details of site requirements with LCON for path/pwr/grnd/space. 4/9: OM sent email requesting UHG provide path/pwr/ground/space. 4/3: Fiber plc/splc scheduled for 6/5/18 3/26-3/19: Per C&E fiber inventory scheduled for 3/30 & plc/splc scheduled for 6/5/18. 3/12: Site survey completed on 3/7. Pending access install dates. -C&E Update: Escorted on survey by Ely Curtis (801-257-6054) No available open racks/bays in data room As per Darren Marshall ATT ISP there is room at the rear of the existing bay DMARC A-4 to place 5150 at bottom position and fiber management panel at position 4th from top 3/5-2/19: FOC scheduled for 3/8. 2/12: UHG confirmed order details and provided corrections. Pending order numbers/USOs 2/5: Pending order numbers/ USO 1/29: Pending technical details. 1/22: Order placed on 1/19, pending OM assignment and USOs.

## 2017 Archived Completed
UHG PON | Address | City, ST | Order Type Service | CPDD | Sales to Ordering | Order/USO | ATT Ckt ID's | LEC / PON | LEC Ckt ID | Estimated ATT Due Date | Complete Date | Demarc | STATUS | Order Mgr / Current Responsible Party | Customer Contacts | MD5 Password | ASN | IP Address CER/PER | APP DATE on ORDER | FOD | FOC Received | CTA complete
TN019-04-IJ | 1897 General George Patton Drive, Ste 112 | Franklin | 20MB/50MB | 2017-01-19 | Best | C11314610 30942863 3094BRYX | BBEC500774 ATI | BELL SOUTH HSS03373739 |  |  | 2017-02-02 | Demarc Lc: 1ST FLR TELCO RM, RACK MT, TAGGED PORT | BELL SOUTH 2/2 - READY FOR TTU 1/31 - FOC posted, EAD 2/10/17 1/31 - FOC not received due to multiple orders having same PON, I sent a request to have sup to issue a new PON 1/25 - pending FOC 1/30/17 1/23- C-Project received, pending USO 1/19 - John sent request | Ma. Cristine Quintas 16172492353 mq027t@att.com
UIN09-07-IJ | 2011 Willow Street | Vincennes | 50MB/100MB |  |  | C11312993 VS17009052 30942331 3094BRYL | IUEC880264 ATI | AT&T MW HCS03666446 | EC CKT ID KRGN104075NB |  | 2017-02-01 | Demarc Lc: 1ST FLR, SERVER RM, WALL MOUNT,PORT 1 Demarc L2: FURUKAWA HANDOFF ABOVE | AT&T MW 2/2 - READY FOR TTU 1/24 - RID, DVA, WOT POSTED, with EAD CTA pulled in to 2/8/17 1/18 - FOC rcvd 1/17, overall completion date of 3/27/17 1/17 - USO rcvd 1/6 - John sent Request | Roy Valesco rv213m@att.com 16172491324
GA024-04-IJ | 3025 Windward Plaza | Alpharetta | 20MB/50MB |  |  | C11312524 VS17007488 30942573 3094BRYK | BBEC525522 ATI | AT&T SE HSS03370934 |  |  | 2017-01-30 | Demarc Lc: 2ND FLSTE200 PH RM 3930 OPT HDOFF JK6 Demarc L2: PNL1 JK1 | AT&T 1/31 - COMPLETE READY FOR TTU 1/19 - FOC, RID, DVA, and WOT have posted with a DD of 1/31/17 1/17 - Bldg landlord needs LEC to bring certificate of insurance 1/13 - USO rcvd w/ pending FOC 1/18 1/4 - Pending Order | Roy Valesco rv213m@att.com 16172491324 |  | UHGATTbgpyI6HYRM
CA768-10-IJ | 2301 W 120TH | Hawthorne | 300MB/1GB |  |  | C11311085 VS16250638 30942056 3094BRXN | IZEC.537138..ATI | AT&T W HWS03563887 |  |  | 2017-01-30 | Demarc Lc: 2ND FLSTE200 PH RM 3930 OPT HDOFF JK6 Demarc L2: PNL1 JK1 | AT&T 1/30 - Ready for TTU 1/19 - FOC rcvd with new DD of 1/30/17, RID, DVA, and WOT have posted as well 1/17 - New LCON Amir Ali Semnanian M.Sc. ¦ Monarch HealthCare Part of OptumCare Manager, Infrastructure Technology Services 11 Technology Drive ¦ MS 07 ¦ Irvine, CA 92618 T: 949-923-3392 C: 949-573-3530 F: 949-923-3599 asemnanian@mhealth.com 1/9 - Eml about LCON changing to Pooyan Haghigh 949 923-3222 and santosh tendoemcar 949 923-3243, need new contact info 1/6 - Pending site visit date 1/5 - PON has been accepted by scope with no errors, pending FOC 1/3 - pending FOC 1/6/17
AL018-04-IJ | 1416 W I-65 Service Road South | Mobile | 5MB/10MB | 2016-11-15 | 2016-11-21 | C11306152 3094-BRVP-FR 3094-2882-LL | MLEC840311 ATI | AT&T SE HSS03357721 | EC CKT ID A2KRGN466385SC | 2017-02-13 | 2017-02-07 | Demarc Lc: 2ND FLR TELCO RM 3903 WALL MOUNT PORT | AT&T SE (CPR target 1/10/17 and C&E 1/31/17) EF qualified 2/8 READY FOR TTU 1/24 - All milestones have posted, pending EAD for 2/7/17 1/5 EAD 2/7/17 11/17 Received firm order delivery date targeted for 2/7/17. 11/16 Order sent and ASR submitted. 11/15 Request has been assigned, pending order issuance. 11/8 John approved details in confirmation letter. 11/3 CSS sent C project assignment C11306152 10/31 John sent in request. | Roy Valesco rv213m@att.com 16172491324 |  | UHGATTbgpyI6HYRM |  |  | 2016-11-15 | 2016-11-16 | 2016-11-17
| 1301 Atwood Avenue | Johnston | 100MB/200MB |  |  | C11310326 VS16244829 30941969 | BKEC992201 ATI | Verizon North HNS01892077 | EC CKT ID 85KFGS006711NE |  | Awaiting completion to order | DMARC 3RD FLOOR SERVER ROOM POSITION 1 OF 2 RACK MOUNTED TAGGED WITH LEC ID | Verizon North 2/15 - CKT complete, Ready for TTU 2/14 - On list for testing to begin today 2/13 - Will escalate for EAD/CTA on 2/14, giving 2 bus days for response 2/9 - All milestones received, pending EAD and CTA. Pushing to pull in before 3/1. 2/3 - Pending FOC on EVC PON 2/7, then RID will be posted, should pull in milestones, current DD still 3/1 2/3 - VZ completed PON, pending milestones RID, DVA, WOT, EAD, CTA. Overall DD of 3/1 is on track 1/23 - FOC rcvd with overall completion date of 3/1/17 1/3 - Pending FOC 1/26/17 | Roy Valesco rv213m@att.com 16172491324
TX720-01-IJ | 1950 N. Stemmons Freeway, Suite 1070, Rm Meet Me, 1st Flr | Dallas | 250MB/500MB | 2017-12-29 |  | C11315374 VS17020561 30943039 3094BRZY | BMEC979220 ATI | AT&T SW HMS02193870 |  |  | Awaiting completion to order | Demarc Lc: 2ND FLOOR MEET ME ROOM, RACK MNT, Demarc L2: RR 11.10, CIENA | AT&T SW 3/6 - CKT complete 2/21 - FOC rcvd, pending EAD 3/3/17 2/17 - Escalation on PON to correct demarc 2/13 - 2nd Level Escalation on PON 2/9 - Eml to assembler coach to provide status on new PON with demarc changes 2/7 - Demarc changes updated, having PON reissued 2/6 - Demarc info needs to be corrected. VIAWEST SUITE IS ON 2nd FLOOR Suite 2033. Please have the order corrected so that it may be assigned. ATT TELCO has no available fibers to floor 1 MMR for ViaWEST 2/2 - USO rcvd pending FOC 2/7/17 12/29 - John sent request | Roy Valesco rv213m@att.com 16172491324
UCO14-06-IJ | 6455 S. Yosemite | Englewood -GREENWOOD VLG | 20MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-14 |  | C11318514 VS17035821 30943228 3094BCSW | BBEC580928 ATI | QWEST HWS03576140 | 29KXGS215643MS |  |  | 8TH FLR ELECT RM WALL MT PORT 1 | QWEST 5/16-TTU 5/16 @ 10PM CST 3/10 - CKT ready for TTU 2/27- FOC rcvd LEC DD 3/14/17, overall completion 5/3 2/23 - USO rcvd 2/14 - John sent request | Ma. Cristine Quintas 16172492353 mq027t@att.com
CA238-01-IJ | 26740 Towne Centre Dr | Foothill Ranch | 50MB/50MB | 2017-01-26 |  | C11315248 VS17018832 30942918 3094BRZL | BBEC508970 ATI | AT&T PB HWS03570214 13KQGN612020PT |  |  | Awaiting completion to order | MPOE,WALLMNT,JACK ON WALL TAGGED | AT&T PB 3/16-CKT Complete 3/9 - EAD has been pulled in to 3/15 2/9 - All milestones have been met, scheduled for access to be delivered on 5/2 2/3 - FOC rcvd, pending EAD 5/2, DD 5/15 1/31 - USO rcvd, pending FOC 2/3 1/26 - John sent request | Roy Valesco rv213m@att.com 16172491324
UMN99-60IJ | 6150 Trenton Ln N. | Plymouth | 10GB UVN |  |  | CSM170130130350 IP17007389 30943103 | L4YS958941 ATI |  |  |  | Awaiting completion to order | UHBPMH1SS01-15011501 FIC::F7 PANEL 2A JACK 25/26 TE | 3/13 - Emld JS and provided demarc 3/10 - Pending customer testing and acceptance 2/28 - Overall DD changed to 3/8 2/17 - Overall DD 3/3 2/16 - PENDING COMPLETION OF DISCO 3134-9413 TO FREE UP SWITCH. D ISCO IS OUT TO OSWF FOR 2/16/17 2/10 - IOC project number received, assembler can now proceed with order, pending design on 2/15/17 2/9 - Emld OM requesting IOC project number so assembler can proceed with order 2/3 - USO rcvd, 11/17 - 11/8 Pending updates; IOC to be built first (tentative Dec 15) 8/23 - 7/18 Chris will be working this submission 6/15 John sent in request | Victer Basurco vb2486@att.com 7328445651
DE003-06-IJ | 4051 Ogletown Road | Newark | 10MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-14 |  | C11317797 VS17031120 30942422 3094BSBS 3094BSBT | BBEC588455 ATI | Verizon S HES02806609 | 11KFGS300851DS |  |  | 2ND FLR SUTE 200 SRVR RM, RCK-MNT, 2ND NID | VERIZON 3/16-CKT ccomplete 3/15-LEC DD/EAD/CTA complete 3/10 - Sent to tech coach for completion of EAD/CTA 3/2 - FOC rcvd w/LEC DD/EAD OF 3/9 2/17 - USO rcvd, pending FOC 3/23 2/14 - John sent request | Roy Valesco rv213m@att.com 16172491324
UCA17-06-IJ | 2300 Main Street | Irvine | 200MB/250MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-09 |  | C11317780 VS17032179 3094-2939 3094BSBY | BREC943241 ATI | AT&T W HWS03574670 | 13KRGN589806PT |  |  | RACK NEXT(LEFT OF)OPTERA METRO 3400 INSIDE TO CUST SERVER RM,H/O | AT&T W 3/16-CKT complete 3/13 - EAD 3/15 3/3 - EAD pushed to 3/15 2/22 - All milestones rcvd, pending EAD 3/2 2/20 - Rcvd FOC, pending EAD 3/2 2/17 - USO rcvd 2/13 - JS confirmed to go with 250Mb access 2/9 - John sent request | Ma. Cristine Quintas 16172492353 mq027t@att.com
MI025-08-IJ | 26957 Northwestern Hwy Suite 400/480 4th Flr | Southfield | 100MB/200MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-03-01 |  | C11319564 VS17042182 30943416 3094BSFF | BREC962925 ATI | AT&T MW HCS03694418 |  |  |  | MAIN PHONE RM FIRST FLOOR OF 26913 MOUNTED 3930,PANEL 1 ,PORT | AT&T MW 3/22-CKT complete 315-Rcvd FOC and all milestones and ckt wired and office tested, pending EAD 3/30 3/13 - 1st level escalation on missed FOC, request BUPM engagement 3/9 - FOC missed, follow up on 3/13 3/3 - Rcvd USO, pending FOC 3/8 3/2 - Rcvd C project #, pending USO 3/1 - Rcvd order request | Roy Valesco rv213m@att.com 16172491324
TN040-06-IJ | 2035 Lakeside Center Way | Knoxville | 20MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-14 |  | C11318625 VS17039193 30943296 3094BSDJ | BBEC546972 ATI | AT&T SE HSS03382175 | T2KRGN821855SC |  | 2017-03-24 | Same as original install | AT&T SE 3/27-CKT complete 3/15-CKT delivered, pending EAD/CTA overall completion 3/23 3/13 - EAD 3/14, CTA 3/21, overall comp 3/23 3/3 - FOC rcvd, pending EAD 3/14, ALL milestones have been met including wired and office tested 3/1 - Rcvd USO, pending FOC 3/3 2/22 - 2/22 - C Proj # rcvd, pending USO 2/14 - John sent request | Roy Valesco rv213m@att.com 16172491324
CA165-06-IJ | 8880 Cal Center Drive | Sacramento | 20MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-23 |  | C11319312 VS17041917 30943378 3094BSDT | BBEC591480 ATI | AT&T W HWS03578228 | 18KRGN518828PT |  | 2017-03-27 | Demarc Lc: 2ND FLR 2.1 ELEC ROOM, PORT 6 OF 6 Demarc L2: ON ENGINUITY SHELF DUAL LC | AT&T W 3/27-CKT complete 3/17-CKT wired and office tested, pending overall completion 5/18 3/13 - Rcvd FOC, LEC DD 3/22, Overall comp 5/18 3/4 - USO rcvd, pending PON to be released 2/28 - C proj # rcvd, pending USO 2/27- Order sent to SD, pending C proj # 2/23 - John sent request | Daisy Sambo 470 719-7904 ds8468@att.com
NJ013-06-IJ | 1 Quakerbridge Plaza | Hamilton | 5MB/10MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-14 |  | C11318527 VS17037328 30943235 3094BSCX 3094BSCY | MLEC642318 ATI | Verizon S HES02807705 | KFGS308564NJ |  | 2017-03-27 | FL.1 MAIN TELCO, WALL MOUNTED NID, TAGGED. | Verizon S 3/27-CKT complete 3/13 - LEC DD 3/21, overall completion 5/11 3/2 - FOC rcvd, LEC DD 3/21 w/overall completion 5/11 2/24- USO rcvd, pending FOC 3/30 2/22 - C Proj # rcvd, pending USO 2/14 - John sent request | Roy Valesco rv213m@att.com 16172491324
MI028-06-IJ | 950 Trade Centre Way, Ste 320 | Portage | 10MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-21 |  | C11319221 VS17042100 30943399 3094BSFD | BBEC513175 ATI | AT&T MW HCS03694412 | KRGN/210502/MB |  | 2017-03-27 | Demarc Lc: 1ST FLR MAINTAINENCE RM MAIN NETWRK Demarc L2: RM WALL MOUNTED PNL 1 POS | AT&T MW 3/27-CKT complete 3/17-LEC completed PON, ckt wired and office tested, pending EAD/CTA 3/23, Overall completion 3/27 3/13 - EVC issued ono 3/11, this will push out EAD 3/16, escalating for new DD 3/6 - Rcvd USO and FOC, EAD 3/16 02/27 - C proj # rcvd, pending USO 2/27 - Order sent to SD, pending C proj # 2/21 - John sent request | Roy Valesco rv213m@att.com 16172491324
OH046-01-IM | 5900 Parkwood Place | Dublin | 100MB/250MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-03-14 |  | C11321353 30942488 | BREC976078 ATI | AT&T HCS03706350 | 94KRGN201615OB |  |  | 2ND FLOOR DATA ROOM, COMMBOARD.FIRST DROPOFF IS TO HANDOFF | AT&T 4/7-Ready for TTU 4/3-LEC DD 4/6, overall completion 4/20 3/28-LEC DD 4/12 with overall completion 4/20 3/27-FOC rcvd, overall completion 6/7 3/22-Rcvd new IP addresses, still pending USO 3/16-C proj # received, pending USO 3/16-Order being processed 3/14-Rcvd Order request | Ma. Cristine Quintas 16172492353 mq027t@att.com
MD101-04-IJ | 10175 Little Patuxent Parkway | Columbia | 100 MB/200MB | …,…..,.,,., |  | C11307823 VS16227502 30943294 3094BRWF 3094BRWG | BKEC991972 ATI | Verizon South HES02796888 | EC CKT ID 38KFGS302254CM |  | Awaiting completion to order | Demarc Lc: 3RD ROOM 305 CLOSET WALL MOUNTED NID #1 | Verizon 4/10-CKT complete 4/4-Escalation for EAD 3/27-CKT has been wired and office tested, pending EAD/CTA 3/21-Verizon completed PON, pending ATT milestones 3/20-Order CNR'd, emld asking for status when bldg will be ready 3/9 - FOC rcvd on 3/8, pending LEC DD 3/17, then we will complete our milestones 2/27 - New PON sent, pending FOC 3/30 2/17 - JS emld stating site is ready for circuit install, emld OM to have CNR removed so order can progress, DD sup'd for redispatch 2/14 - OM confirmed processed request to push out DD to prevent billing trigger 2/13 - Emld OM again about changing pushing DD out to prevent billing 2/10 - Due to CNR and bldg not being ready until 2/22, emld OM requesting a sup to push DD out to prevent billing trigger 2/9 - Rcvd eml from JS stating bldg will be ready 2/22, currently CNR 1/30 - pending FOC 2/8 1/23 - Confirmed bldg ready end of Jan 1/5 - Bldg will be ready by end of Jan for install 1/5 - Request verification if bldg will not be ready until April 2017 1/3 - FOC rcvd, EAD 2/8/17 12/2 -Pending FOC changed to 1/3/17 11/28 - pending FOC 12/30 11/17 Order has been sent for processing on 11-17-2016. C-project # is C11307823. 11/16 John has sent in request | Jenny Cabotaje 16172491335 jc587j@att.com
MS010-04-IJ | 795 Woodlands Parkway, Suite 301 | Ridgeland | 50MB/100MB SIP Upgrade Proj | 2017-02-06 |  | C11316705 VS17026545 30943151 3094BSBH | IUEC833291 ATI | AT&T SE HSS03378731 | M1KRGN823592SC |  |  | 2ND ST FLOOR TELCO RM, WALLMOUNTED,CIENA 3930, PORT 5 HANDOFF | AT&T SE 4/6-CKT complete 3/28/2017 Updated LCON in aseDB and added to sots log in EFMS. Pending access delivery on 4/5 3/27-Emld MC and JS to advise 3/23-Access denied to building 3/20-SPF form sent to BUPM 3/17-Sent SPF form to OM 3/13 - Emld JS to check on entrance facility form 3/10 - PENDING ENTRANCE FACILITY FORM CUSTOMER SIGNATURE REQ'D, LEC DD/EAD 4/5 2/16 - FOC rcvd, pending EAD 4/5/17 2/9 - USO rcvd, pending PON 2/14 2/7 - Order processed, pending USO 2/6 - John sent request | Ma. Cristine Quintas 16172492353 mq027t@att.com
UWI30-06-IJ | 10701 W Research Dr | Wauwatosa | 100MB/150MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-23 |  | C11319324 VS17040565 30943376 3094BSDS | BCEC568497 ATI | AT&T MW HCS03693381 | 44/KRGN/101545/WT |  | 2017-04-07 | LOWER LEVEL, DATA ROOM, RR 00000.02, HANDOFF PANEL #2, PORT #1 | AT&T MW 4/10-CKT complete 4/4-LEC DD missed, pending C&E splicing, ECD 4/7 with overall completion 4/13 3/20-LEC DD 4/3, Overall completion 4/13 3/13 - LEC DD/EAD 4/3, overall completion 4/10 3/7 - ALL milestones met, pending LEC DD/EAD 4/3 3/6 - Rcvd FOC, pending EAD 4/3 3/2 - C proj # rcvd, pending USO 2/27 - Order sent to SD, pending C proj # 2/23 - John sent request | Ma. Cristine Quintas 16172492353 mq027t@att.com
CA016 -05-IM | 17900, Von Karman Avenue | Irvine | 100MB/150MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-03-17 |  | C11321689 VS17054131 30942305 3094BSGT | BCEC571010 ATI | AT&T HWS03583372 | 13KRGN590072PT |  |  | 1ST FLR TELCO CLOSET IN WOMENS PANEL 1,PORT 3 | AT&T 4/17-COMPLETE Ready for plug and play 4/10-Emld tech to provide more information and ECD 4/7-LEC DD missed, NO Ciena @ 17900 Von Karman, is at 17900 Jamboree, needs to be re-engineered 4/3-LEC DD/EAD 4/6, overall completion 4/20 3/27-Rcvd FOC, overall completion of ckt set for 6/7 3/22-Rcvd USOs 3/20-Order being processed 3/17-Rcvd Order request | Ma. Cristine Quintas 16172492353 mq027t@att.com
PA001-06-IJ | 1900 S Broad Street | Philadelphia | 10MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-14 |  | C11318503 VS17036618 30943286 3094BSDD 3094BSDF | BBEC526445 ATI | Verizon HES02807928 | 11KFGS306694PA |  |  | BASEMENT WALL MOUNT TAGGED NOT EXTENDED | Verizon 4/25-CKT Complete 4/17-Overall DD 5/12 4/12-LEC delivered circuit, overall completion 5/12 4/10-LEC DD 4/11 3/27-LEC DD 4/11 with overall completion 5/12 3/16-FOC rcvd, LEC DD 4/11 3/8 - PON corrected, FOC pushed to 4/11 2/27 - USO rcvd, pending FOC 3/31 2/21 - C Proj # rcvd, pending USO 2/14 - John sent request
AZ046-01-IJ | 695 Pecan Tree Lane | Green Valley | 10MB/10MB | 2017-01-20 | Best | C11314678 VS17013835 30942847 3094BRYW | MLEC507641 ATI | CenturyLink HWS03568482 | 19KXGS209533MS |  | 2017-05-03 | 1ST FLOOR UTILITY ROOM WALL MOUNT TYPE: OPTICAL PORT 1 | CenturyLink 5/3-CKT complete 4/17-LEC DD 5/2, OVERALL COMPLETION 5/10 4/11-LEC DD pushed to 5/2 4/10-LEC DD 4/13 4/3-LEC DD/EAD 4/13 3/20-Pending LEC DD/EAD 4/13 3/13 - All milestones rcvd including WOT, pending LEC DD/EAD 4/13 2/20 - FOC rcvd 2/17, pending EAD 4/13/17 2/17 - Per LCON site is ready 2/14 - Conduit- There is an existing 4” conduit with an inner duct equipped with 2500lb calibrated pull string from your equipment room (MPOP)of your building to the meet point at the property line that CTL will utilize to pull in the fiber cable. Space- There is sufficient backboard space on the south wall of your equipment room for our equipment, fiber panel and Ciena 3916 Ethernet switch. This where CTL will hand off the circuit. Power-We will require a new power outlet, 110/120VAC 15 Amp circuit equipped with NEMA 5-15R standard 3-prong receptacle within 4 feet of where the equipment will be placed on the south wall. Ground- There is an existing solid #6 AWG ground wire/bar (from isolated building ground) within six feet of the where the equipment will be mounted on the wall. 2/9 - FOC pushed to 3/16/17 1/25 - USO rcvd pending FOC 2/28/17 1/20 - John sent request | Sherryl Mendevil SM961Y@ATT.COM 7816026896
WA004-06-IJ | 1633 Westlake Ave North | Seattle | 5MB/10MB 1000 Base-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-21 |  | C11318713 VS17038790 30943322 3094BSDK | MLEC624214 ATI | QWEST HWS03577429 |  |  |  | P3 MAIN TELCO RACK MOUNT CIENA MINI OPTICAL PORT 3 MM HANDOFF | QWEST 4/28-CKT complete 4/24-LEC DD 5/8, OVERALL COMPLETIONI 5/19 4/17-LEC DD 5/8, OVERALL COMPLETIONI 5/19 4/10-LEC DD 5/8 4/3-LEC pending completion 5/8 3/27-Sent for status of build 3/22-CKT wired and office tested, overall completion shows 5/19 3/20-FOC rcvd, outside plant/major build, no dates provided for ECD 3/2 - PON released, pending FOC 4/5 2/22 - C Proj # rcvd, pending USO 2/21 - John sent request | Jenny Cabotaje 16172491335 jc587j@att.com
CA768-12-IM | 7 Technology Drive STE B | Irvine | 100MB/1GB SIP Upgrade Proj | 2017-04-26 |  | C11325872 VS17076797 30943585 3094BSKG | IZEC560657 ATI | AT&T W 7WS03593087 | 13KRGN590337PT |  |  | MPOE BKBD VE 1 POS 8,9 | AT&T W 5/16-CKT complete 5/9-LEC DD 5/15 overall DD 7/13 5/5-FOC rcved, LEC DD 5/15, overall DD 7/13 4/26-Rcvd USO, pending FOC 5/4 4/26-Rcvd order request
NJ005-06-IJ | 2 Market St 12TH FLR | Newark | 20MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-21 |  | C11319243 VS17042066 30943393 3094BSFB 3094BSFC | BBEC598303 ATI | Verizon S HNS01897653 | KFGS308599NJ |  |  | 9912 | Verizon S 5/11-CKT complete 5/9-CTA 5/11, overall DD 5/18 5/1-End-to-end testing pending 5/11, overall DD 5/18 4/25-TDI confirmed, design posted, wired and office tested, pending end-to-end testing to complete by 5/11, overall DD 5/18 4/20-LEC DD posted, pending TDI to be confirmed 4/17-LEC DD 4/19, ready for TTU 5/18 4/10-LEC DD 4/19, overall completion 5/18 4/3-LEC DD 4/19, overall completion 5/18 3/14-FOC rcvd, LEC DD 4/19 3/8 - PON released, pending FOC 4/10 3/4 - USO rcvd, pending PON 3/3 - C project # rcvd, pending USO 2/27 - Order sent to SD, pending C proj # 2/21 - John sent request | Jenny Cabotaje 16172491335 jc587j@att.com
OH044-01-IJ | 2182 Dividend Drive | Columbus | 10MB/50MB | 2017-01-27 |  | C11315657 VS17020653 30943075 3094BRZZ | BBEC538121 ATI | AT&T MW HCS03676314 | 94KRGN201569OB |  | Awaiting completion to order | OUTSIDE WEST SIDE OF BLDG, | AT&T MW 5/24-CKT complete 5/19-Escalation for end to end testing, DD 5/24 5/16-LEC DD posted 5/16, pending EAD and testing, overall DD 5/24 5/9-LEC DD 5/12, overall DD 5/24 4/24-LEC DD 5/12, Overall completion 5/24 4/17-LEC DD 5/12, Overall completin 5/24 4/10-LEC DD 5/12 3/27-LEC DD/EAD/CTA 5/12 3/13 - LEC DD/EAD/CTA 5/12 2/7 - ALL milestones rcvd including WOT, pending LEC DD/EAD 5/12 2/6 - FOC rcvd with LEC DD, EAD 5/12/17 2/2 - RCVD USO, pending FOC 2/7/17 1/17 - John sent request | Roy Valesco rv213m@att.com 16172491324
UOK03-06-IJ | 7666 E. 61st Street, Suite 500 | Tulsa | 5MB/10MB 1000 Base-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-14 |  | C11318634 VS17039229 30943353 3094BSDP 3094BSDQ | IUEC739222 ATI | WINDSTREAM HMS02198848 |  |  |  | 5TH FLOOR TELCO ROOM, WALL MOUNTED AND TAGGED WITH CKT ID | WINDSTREAM 5/24-CKT complete 5/22-LEC has sent completion on PON, need end to end testing to be completed 5/17-Pending end-to-end testing with windstream 5/15-Windstream is ready to test with ATT, CALLED ON 5/13 and their office was closed 5/5-Juniper is on backorder, estimated ship date is 5/17, tkt has been issued to expedite 4/24-FOC rcvd, pending LEC DD 5/3, overall completion 5/25 4/13-FOC rcvd, pending LEC DD 5/3, overall completion 5/25 4/10-Pending FOC 4/12 3/20-FOC 4/12 3/10 - Order sup'd to reflect, FLR, pushed FOC to 4/12 3/3 - PON rcvd, pending FOC 4/4 3/2 - USO rcvd, pendiing PON 3/6 2/22 - C Proj # rcvd, pending USO 2/14 - John sent request | Roy Valesco rv213m@att.com 16172491324
CA768-12-IM | 2301 W 120th Rm: Telco Flr 1 | Hawthorne | 100MB/1GB SIP Upgrade Proj | 2017-03-30 |  | C11325867 VS17077184 30943608 3094BSKK | IZEC511225 ATI | AT&T W HWS03594622 | 13KRGN590356PT |  |  | 1ST FLR DATA CENTER /CO-LO CAGE 93A RR101.02 VE#1 PORT#3&4 LABEL | AT&T W 5/19-CKT complete on 5/18, pending DD 5/30 5/15-Sent follow up when PON will be updated 5/11-Rcvd FOC, need PON updated to show FOC LSO: 714 239 overall completion 7/17 5/5-CNR 5/4-FOC 5/5 5/1-Rcvd USO, pending PON 5/3 4/24-Rcvd C proj # 4/20-Order being typed 4/3-Approval sent to EW 3/30-Rcvd order request | Jiselle Alvarez ja746g@att.com
M0352-08-IJ | 3838 N. Causeway Blvd. | Metairie | 30MB/100MB | 2016-04-25 | 2016-05-05 | VS17094000 30943731 3094BSLP C11280740 3094-BQVG-FR 30943173-LL | IUEC902716 ATI IUEC604969 ATI | AT&T SE 7SS03405077 HSS03304490 HSS03342753 | EC CKT ID L2KRGN821513SC L2KRGN821320SC | 2016-05-24 | Pending | Telco RM Wall Mnt Port 2 | AT&T SE 6/16-CKT complete 6/13-Design completed; ATT SE 6/16 6/8-Design scheduled for 6/12, LEC DD missed-pushed to 6/16 6/5-Rcvd FOC, LEC DD shows 6/7, will be missed, design not in 5/30-Pending FOC 6/19 5/25-Rcvd USOs and PON released 5/23-Pradeep provided new IPs: 10.1.90.241/30 - CER IP 10.1.90.242/30 - PER IP 5/22-MC requested new set of IPs from Pradeep 5/18-New order submitted and eml sent to rep assigned to the disconnect DDTS # 1852383 to reference new C proj # 5/11-Need disconnect and order re-issuance 5/9-Escalation for missed FOC 5/4-Pending FOC 5/5 5/1-OM submitting tkt for re-dispatch 4/25-Sent 3rd tier escalation 4/21-Escalation sent to AM backup to assist 4/17-Customer work completed, pushing for dates 3/27-Pending fund approval for fire caulking work 3/27-Emld JS and MC regarding interduct work completion 3/20-JS following up with PM 3/13 - Emld JS to check with PM if interduct work completed 2/14 - Interduct should be completed in a couple weeks 11/29 - Pending interduct bet/26th & 27th flrs 11/22 - Per JS interducts bet/ 26 & 27th flr being placed, update next week 11/17 - 11/8 Per discussion with OSPE Troy, there has been no change to the scope of the work. Dale Daniel advised that he will be speaking with Solange Cook (whom was with Troy during the site visit) to discuss 11/7 UHG installed innerduct from MPOE to MDF. AT&T will need to run fiber drop from demark to customer suite. Dale is asking OSPE for updated scope. 11/7 UHG installed innerduct from MPOE to MDF and will install fiber optic cable for this circuit in that innerduct. Inquiry sent to OSPE to respond to path of remaining requirements in order to make this site customer ready. 11/4 - 10/28 New PM taking over on UHG side; Monitoring for which path will be taken for this order. Site requirements must be complete before order can proceed. 10/26 Sent request to John to determine site readiness. 10/25 - 10/18 : Per construction database customer premise ready date (CPR) changed to 10/31. Construction and engineering (C&E) date posted complete. Awaiting confirmation of customer work completion. 10/14 - 9/30 The customer is discussing the work needed and cost now. Sounds as if it will move forward just waiting on final approvals. 9/29 - 9/28 Order has possibility to being canceled due to cost of EMT conduit for customer. Meanwhile, contingent on completion to conduit requirements, circuit install is targeted for 10/12/16. 9/27 - 9/19 Circuit install targeted for 10/12/16 contingent on CPR requirement below being resolved. 9/15 Site visit completed early on 9/15/16. Minimum 1" plenum rated innerduct or 1" EMT type conduit (per electrical code) with pull tape is required from the Main Equipment Room (Common Area) on 27th floor to the 26th floor suite as identified by the AT&T Representative. Paths longer than 300' or with two or more 90 degree turns will require a pull box no higher than 10 feet from floor level and have the minimum dimensions (12"Ã—12"Ã—4" Deep) 9/14 Site visit target is 9/19/16 9/13 - 9/12 Ordering is working to release new C&E order. Once assigned to OSPE, will work with Sue Paulsen (UHG PM) to obtain drawing/draft of final requirement that is customer related. 9/7 OSPE advised that there needs to be a new C&E order to be estabilished for this request and location in order to provide a drawing. Sent request to Ordering to submit ASE C&E order. 9/6 - 8/24 (CNR) PM has been assigned, he is in process of scheduling the electrician for site survey. 8/23 Pending PM assignment 8/24 - 8/19 Email sent to John for status on site requirement. 8/18 - 8/16 Site is running into issues with building management and this still needs to be assigned to a PM to complete the remaining EMT conduit work. 8/15 - 7/27 John is working with onsite to work the EMT conduit requirement. 7/26 - 7/25 Pending EMT conduit work requirement. 7/21 Provided John Sergot scope of work (EMT conduit) for the customer to complete. 7/19 Another follow-up was sent on 7/15/16 pending response from Pradeep on conduit readiness. 7/14 Awaiting response from Pradeep (customer) to assist to clear the duct issue. 7/12 Follow-up sent to Pradeep. 7/7 Conduit not complete - request sent to Pradeep to assist with issue. Duct needed to be ran by customer into main telco room on the 27th floor. 7/5 - 6/24 Circuit installation target is 7/6/16 6/21 Provisioning has notified TIER2 team that the site requirements are complete and have requested the DD sup and the dispatch to the site. 6/20 Working with provisioning for request of soonest dispatch for installation. 6/20 Per OSPE, conduit work is expected to be complete due to Comnet's intervention on work. 6/17 Comnet is stating innerduct work is done however cannot work EMT (electrical conduit) if it is required. Sent email to OSPE to confirm if EMT is a requirement that cusotmer still needs to fulfill. 6/14 - 6/10 Pradeep is coordinating vendor to complete remaining work. 6/9 Conduit issue causing roadblock at the site. Pending its completion. 6/8 NTE being installed in COMMON AREA and ready for install 6/7 Site requirements have been met and resolved in database. Pending new install dispatch date. 6/6 Pending confirmation of completion to customer site requirements from Vendor Comnet. 5/31 Comnet Vendor is stating 6/3 target to start customer work. Jane (comnet) will need to get confirmation from Lynn Wood (UHG) to confirm. 5/25 Sent follow-up email to Vendor to obtain update of customer requirements. 5/24 Sent an email to Jane Kessler (Vendor) on 5/23 for updated status on work requirements. 5/24 Follow-up sent to customer vendor regarding customer site requirements. Pending ECD. 5/20 Vendor will be working UHG's site requirements. Once resolved, new dispatch can occur for installation. 5/12 LEC advised that there are still customer site requirements and need to be resolved before completing access. Pradeep (Optum) is working to resolve. 5/10 - 5/3 Circuit installation target is 5/12/16 4/29 Confirming with customer site requirements are being met. 4/26 AT&T site visit happened on 4/25. LEC access installation target is 5/12/16. 4/25 Order submitted 4/13 John Sergot sent in request | Junne Lopez 16172491305 jl155j@att.com |  | UHGATTbgpyI6HYRM |  |  | 2016-04-25 | 2016-04-25 | 2016-04-25
WA022-04-IJ | 1111 3rd Ave, Suite 1100, 11th Floor | Seattle | 20MB/50MB SIP Upgrade Proj | 2017-02-06 |  | C11316718 VS17027356 30942244 3094BSBP | BBEC504306 ATI | LNS HWS03573594 | WAKRGN100123TPM |  |  | 1111 3rd Ave, Seattle, WA 11th Flr, MDF RM 11.0001.01 Port | ASE LNS 6/19-CKT complete 6/14 documents updated and will confirm next that correct Ciena 3903 is loaded. If so we will then work on dispatch 6/9-Incorrect equipment on CNL order, with NSS PM to assist with resolution 6/8-Emld NSS PM and BUPM to provide status on order and if can sup PON for re-dispatch 6/5-Sent request if design has been updated so order can move forward 6/1-NSS PM working on design 5/30-NSS PM engaged for design correction 5/26-Level 2 Tkt submitted to correct design 5/22-FLOW TKT #2870684 issued to correct design 5/18-Design issue being resolved with C&E PM 5/16-Escalated for status of design 5/11-Order being re-designed 5/9-Escalation for status 5/8-Advised again that this is MM hand-off 5/5-Pending confirmation if MM OR SM hand-off 5/1-BUPM checking if dispatch happened 4/26-Tech dispatched, pending update 4/25-Confirmed mulit-mode hand-off, advised dispatch to happen pending splicing to complete on 4/27 4/20-TKT sent and accepted for a tech re-dispatch 4/19-LEC DD missed, emld for status 4/17-LEC DD 4/17, OVERALL completion 5/10 4/7-FOC completed, new EAD 4/17 4/3-ECD pushed back to 4/7 3/27-ECD of C&E completion 3/30 3/22-Order held until C&E complete extending demarc and final flr 3/20-CNR placed on order 3/16-SV rescheduled for 3/18 3/8 - New FOC DD 3/15 3/1 - Rcvd confirmation LCON is good 2/28 - JS reached out to PM if better LCON 2/27 - LCON Mark Franks not in Seattle area, now knows of order, but will need additional details and who can be involved at the actual site prior to survey being scheduled, emld JS 2/23 - Emld JS to verify LCON, LCON is stating not aware of circuit install and will not allow site survey until has better information 2/21 - Escalation in for missed FOC 2/15 - USO rcvd, pending FOC 2/17 2/7 - Order processed, pending USO 2/6 - John sent request | Jenny Cabotaje 16172491335 jc587j@att.com
C1618-01-IM | Convergys FL Data Center 287 International Pkwy 1st Flr, Meet Me Rm | Lake Mary | 400MB/500MB LC-Multi Mode 1000 Base-SX | 2017-05-19 |  | C11329886 VS17102595 30943787 3094BSML | BMEC992972 ATI | AT&T SE 7SS03407469 | 58KRGN701949SB |  |  | CAB 1 HAND OFF B-3 TAGGED PORT 5 | AT&T SE 6/19-CKT completed on 6/16 6/13-LEC DD 6/15, overall completion 6/27 6/7-FOC rcvd, LEC DD 6/15, overall completion 6/27 6/5-USO Rcvd, pending FOC 6/26 5/26-Rcvd C proj #, pending USO 5-19-Rcvd Order Request & sent to CSS | Marites Balben 16172492393 mb874v@att.com
UMN20-05-IJ | 1902 Valley Pine Cir. | International Falls | 20MB/50MB |  |  | C11307506 VS16227043 30943129 3094BRWC 3094BRWD | BBEC571990 ATI | Enventis Telecom HCS03639710 | KRGN64034MPT |  |  | Customer Space, Accedian Metronid gt, Client Port 2 (MMF)/EEN/60213/MPT/VLAN0201 | Eventis Telecom 6/22-CKT complete 6/20-Tech engaged to complete circuit tested and accepted 6/19-Should be ready today 6/19, the offnet provider finished the install 6/16 6/14 AIM engaged and working with access provider making sure they will dispatch on 6/16. 6/12: LEC DD missed, pending update 6/9-LEC DD 6/9 6/8-LEC DD 6/9, overall DD 6/22 6/5-LEC DD 6/13, overall DD 6/22 5/30-LEC DD for PON completion 6/13, overall DD 6/22 5/9-LEC DD 6/9, overall DD 6/22 4/24-LEC DD 6/9, overall DD 6/22 4/17-LEC DD 6/9 overall DD 6/22 4/10-LEC DD 6/9 -overall completion 6/22 3/27-LEC DD 6/9 with overall completion 6/22 3/13 - ATT has milestones up to and including WOT completed, LEC DD 6/9 1/25 - Rcvd FOC, LEC DD 6/9 1/3 - Build held for frost freeze until spring 12/2 - Pending FOC 1/11/17 11/23 - Firm order delivery request (ASR) expected 11/28 11/16 Order has been submitted for processing on 11-14-2016. C-project # is C11307506. 11/15 Request is currently with the CSS to move request forward. 11/14 Request is being processed; contract has been sent for ecountersignature on 11-14-2016. 10/11 Chris sent to Jamie; 12 and 36 Mo term options for 50 and 100MB 10/5 Pending UHG approval and addendum signature 10/4 John sent in request | Jenny Cabotaje 16172491335 jc587j@att.com
FL117-06-IJ | 979 Del Mar | The Villages Lady Lake | 5MB/10MB 100 Base TX RJ45 LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-21 |  | C11319692 VS17042349 30943467 C11319211 | MLEC687662 ATI | CENTURYLINK HSS03406018 HSS03383749 | 25KXGS218805UFLG |  |  | 1st Flr, Telco Rm, Mounted on the Wall, RAD204 PORT 3 | CENTURYLINK 6/30-CKT complete 6/27-end-to-end testing scheduled to complete 6/28, will escalate 6/29 if not status change 6/20-CTL access installed, pending end-to-end testing, overall DD 6/28 6/13-CTL DD 6/28, overall completion 6/28 6/13-LEC DD 6/28, overall completion 6/28 6/8-MC emld and said LCON issues should be resolved 5/30-CTL stating they have requested the customer multiple times, sent email to team if need to use a different LCON 5/22-CKT has been wired and office tested, CTL validation of LCON E-mail ID :- dennis_prindle@uhc.com (#352 674 7161 ) 5/15-Working to get correct LCON 5/8-CenturyLink needs UHC to contact property manager to schedule with tech so they can install the circuit 4/24-LEC DD 5/3, overall completion 5/19 4/17-LEC DD 5/3, overall completion 5/19 4/10-LEC DD 5/3, overall completion 5/19 3/22-CKT has been wired and office tested, pending LEC DD/EAD 5/3, overall completion 5/19 3/17-FOC rcvd, Overall completion 5/19 3/13 - FOC delayed per CTL, order will be project managed, checking on build 3/7 - PON rlsd, FOC pending 3/10 3/6 - USO rcvd, PON to be released by 3/9 3/1 - JS requested to be changed to 100Base TX W/RJ45 Connector 2/28 - Order on hold, may want to change to 100 Base TX 2/27 - Rcvd C Proj #, pending USO 2/21 - John sent request | Sherryl Mendevil SM961Y@ATT.COM 7816026896
FL216-02-IM | Wellmed 585 NW Lake Whitney Pl Bldg F Ste 101 | Pt St Lucia |  | 2017-05-23 |  | C11328715 VS17093912 30943720 3094BSLL | MLEC911730 ATI | AT&T SE HSS03407296 |  |  |  | 1ST FL EQ RM BACKBOARD PORT 1 OPTICAL | AT&T SE 7/10-CKT completed 6/27-Access 7/13, overall DD 8/9 6/13-LEC DD 7/13, overall DD 8/9 6/5-Rcvd FOC, pending LEC DD 7/13, overall DD 8/9 5/30-FOD missed 5/24-Rcvd USOs, pending FOD 5/26 5/23-Rcvd order request | Jiselle Alvarez ja746g@att.com
MD021-04-IJ | 8501 LaSalle Road, Suite 200 | Towson, MD | 50MB/100MB SIP Upgrade Proj | 2017-02-06 |  | C11334564 VS17127994 30943517 3094BSPH 3094BSPJ C11324250 VS17071701 30943168 3094BSJP 3094BSJQ | IUEC740312 | COMCAST HESC2815977 |  |  |  |  | 7/26-Order cancelled 7/24-Emld OM requesting status of token being updated 7/21-Assembler correcting the token, was associated with previous order 7-17-Rcvd new USO, pending FOD 7/20 7/12-Rcvd new C proj # 7/6-Advised order has been cancelled, need resubmitted 7/5-Advised OM STE 200, Colleen is aware of the order 7/5-Colleen needs to be notified by corporate okay for Comcast to access. Need exact location of install. Comcast ECD for access is 7/18 6/27-No change--Colleen needs to be notified by corporate okay for Comcast to access. Need exact location of install. Comcast ECD for access is 7/18 6/15-Colleen needs to be notified by corporate okay for Comcast to access. Need exact location of install. Comcast has found a conduit into the bldg, we will not need a Baltimore City Permit to complete order 6/15-6/13 Building pending /permits contingent to the DD of 7/18 6/14-LEC DD 7/18, overall completion 7/24 6/13-LEC DD 7/18, overall completion 7/18 6/9-FOC rcvd, LEC DD 7/18, overall completion 7/18 6/7-FOC within the next 5 business days on this construction order: “STATUS UPDATE ON COMCAST SR 1896991: site survey completed & no special CX, pending CKT design before issuing FOC, pending ROE w/ bldg & county permits for OSP fiber work” 6/6-Assigned to assembler for status of FOC and to engage AIM 6/5-Sent to AM to escalate 6/2-FOC was incomplete/incorrect, has been corrected 6/1-Follow-up sent for AVM engagement 5/30-Escalation sent for AVM engagement 5/25-Follow-up sent to assembler regarding AVM engagement 5/23-Requested AVM engagement 5/19-Escalation missed FOC + 2 5/9-FOC 5/17 5/1-Pending FOC 5/17 4/25-JS advised that ALCON is in Phillipines, explained need a local number and asked for further direction 4/24-Comcast Needs Local number for ALCON 4/20-PON released 4/19-Rcvd USO 4/17-Pending new Ips 4/10-Rcvd C project # 4/7-Sent for order creation 4/4-Pending signature 3/16-On hold for bid 2/14 - Order held for special bid via Comcast 2/6 - John sent request | Sherryl Mendevil SM961Y@ATT.COM 7816026896
C1623-01-IM PEAK | 11830 Webb Chapel Road, suite 200 | Dallas, TX | 50MB/100MB 1000 Base-SX LC - Single Mode Fiber 1000BLX |  |  | C11334284 VS17128785 30943459 3094BSPG Site ID: 500643 | IUEC703866 | ATT SW | 14KRGN880911SW |  |  | 1ST FLR, STE 200, MEET ME RM, TELCORR 12, PANEL 1, POS 29 & 30 | 7/31: Access install completed with demarc posted. End to End testing completed. 7/21-Rcvd FOC, AT&T acess due 7/31, OVERALL DD 8/7 7/14-Rcvd USOs, pending FOD released to LEC 7/19 7/12-MC gave go ahead to proceed with order 7/6-Rcvd Order Request
CA165-06-IJ | 8880 Cal Center Drive 1st Flr Electrical Rm, South Side of the Bldg | Sacramento, CA | 20MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-23 |  | VS17041917 30943378 | BBEC591480 ATI | AT&T W | 18KRGN518828PT |  | 2017-03-27 | Demarc Lc: 2ND FLR 2.1 ELEC ROOM, PORT 6 OF 6 Demarc L2: ON ENGINUITY SHELF DUAL LC | 8/7: Order completed. 6/29-Move 1st Flr Electrical Rm, South side of Bldg 3/27-CKT complete 3/17-CKT wired and office tested, pending overall completion 5/18 3/13 - Rcvd FOC, LEC DD 3/22, Overall comp 5/18 3/4 - USO rcvd, pending PON to be released 2/28 - C proj # rcvd, pending USO 2/27- Order sent to SD, pending C proj # 2/23 - John sent request | Daisy Sambo 470 719-7904 ds8468@att.com
C1246-07-IJ | 200 North Nash Street | El Segundo, CA | 300MB | 2016-07-01 | 2016-07-06 | VS17120970 30942479 3094BSNW 30943466-LL 3094BRWR PL16033386 C11302165 3094-2723 LL | IZEC565704 IZEC.528433..ATI | LNS HWS03610328 HWS03559371 | CAKFGS100056TPM | 2017-03-08 | TBD | ATX 130001.00/FF5/00/01/077-078 ATX LGX | 8/8: Order completed. 8/8: Design completed 8/8. Next steps complete End to End wiring & End to End testing. Will follow up with Executive Escalation team for ECD. 7/31: Ticket is being worked to have tails wired. Once completed design milestone will be completed. 7/27-Tkt has been picked up by tech to wire tails, then RID will be posted 7/20-Access installed, overall DD 9/27, expedite applied with a DD of 8/28 7/13-Rcvd FOC, Access scheduled for 8/1, pending design 7/17, Expedite on order 7/10-Disco order has been placed, so that new order can be released 6/27-Pending dummy disco (so cn use same Ips) and re-issue 6/20-LNS DD will be missed, pending internal interface change 6/19-LNS DD 6/21, overall completion 6/30 6/14-LEC DD 6/21, overall completion 6/30 6/13-FOC rcvd, LEC DD 6/30, overall completion 6/30, CLLI being loaded into TIRKS 6/12-SECOND NCI CODE MISMATCH BETWEEN ASR AND PON, ADDRESSING IT NOW SO IT CAN BE REFLOWED. 6/9-System issue with ASRs should be resolved today and then should receive FOC sooner than 6/21 6/8-Pending FOC 6/21 6/6-Director engaged and escalating, another meeting today at 3 6/5-Requested status from BUPM 6/1-Order identified as plan of record remediation 5/30-PON has been supp'd correcting ASR information. 5-30-Rcvd confirmation assembler coach has assigned someone to update PON with correct ASR information, then order should be able to move forward 5/30-Follow up sent to assembler for status of PON being supp'd, 5/25-BUPM stated has submitted for the pon to be supp'd to correct ASR 5/23-Emld BUPM's manager regarding no response and need update 5/22-Emld BUPM requesting update on order 5/19-Emld BUPM backup asking for update 5/11-Soak test completed, order is network complete 5/8-Pending update when build will complete 5/3-Infrastructure build ECD change to 5/5 5/1-Pending BUPM response if requirements have been met 4/24- LEC WILL BE RESPONSIBLE FOR THE REQUIREMENT BELOW: SITE-READINESS: BEST SOLUTION THAT IS AVLBL WLD BE TO INCREASE POWER AND DEPLOY A 2-SLOT CIENA, REQUIRES A POWER UPG RADE AND ADD'L COST. SITE ACQUISITION WILL WORK WTIH BLDG TO NEGOTIATE CHARGES FOR POWER UPGRADE, ECD OF BUILD 4/28 4/18-Site-Readiness: Best solution that is avlbl wld be to increase power and deploy a 2-slot Ciena, requires a power upgrade and add'l cost. Site acquisition will work with bldg. to negotiate charges for power upgrade, ECD of build 4/28 4/17-Pending completion of build ECD 4/28 4/11-ECD of build 4/28 4/5-Infrastructure build ECD is 4/28/17 4/5-Emld BUPM to clarify status, order does not show what was sent in eml on 4/4 4/3-Emld BUPM requesting status of build 3/27-Infra build to be completed by 3/31 with overall completion mid-April 3/23-All signatures should be comp by the end of this wk for add 'l power requirements. OSP is working towards completing their new fiber splicing and they should be FC testing and complete by Mid-April. 3/17- Per BUPM, infra build expected to be completed on 3/31 3/2 - Project is on hold, site acquisition is working with building to negotiate MRC & NRC charges for power upgrade 2/28 - Emld BUPM if on track for infrastructure build of 3/31 1/3 - that infrastructure build is scheduled to be complete on 03/31/2017 1/3 - Request status from BUPM regarding missed FOC of 12/27 | JENNY CABOTAJE JC587J@ATT.COM 6172491335 | John Sergot | UHGATTbgpyI6HYRM
C1622-01-IM | 5601 N 103rd St, 1 Telco, Omaha, NE 68134 | Omaha, NE | 50MB/100MB 100 Base TX-Electrical RJ-11 1000 Base-SX RJ-10 |  |  | VS17137371 30943785 3094BSPZ | IUEC989589 ATI | Qwest/ Century Link | 07KXGS252128NW | 2017-10-16 | TBD | COMPUTER ROOM 1ST FLR, GRID LOCATION 4N, RACK #2, CISCO 3750 | 8/16: Order completed. 8/14: Access install completed with demarc posted, pending End to End testing scheduled for 10/9. 8/11: Target access install date scheduled for 8/10. 8/7: FOC completed on 8/1, Target access install date scheduled for 8/10. 7/13-Changing order over to 100 based TX, Electrical and RJ-11 for jack 7/7-Rcvd new order request with handoff change to copper 7/6-Rcvd Order Request
CA013-07-IM | 7 Technology Dr, Main Telco, Irvine, CA 92618 | Irvine, CA | 300MB port/ 500MB access | 2017-08-01 | TBD | VS17138523 30943866 3094BSQJ Site ID: 508289 | BMEC997800 ATI | Pac Bell HWS03617212 | 13KRGN591205PT | 2017-08-24 | 2017-08-18 | 1ST FLR ELECT RM,OUTSIDE ACCESS,PORT 6ON 3939 TO PORT 10 ON V/E | 8/21: Order completed 8/18. 8/14-8/7: FOC was completed on 8/4, Target access install date is scheduled for 8/18.
AZ056-01-IM | 20040 North 19th Ave Flr 1J Rm Telco | Phoenix, AZ | 10MB/50MB SIP Upgrade Proj 1gig UNI with a 1000base SX | 2017-03-27 | TBD | C11323518 30942952 VS17063009 | BBEC507696 ATI | QWEST HWS03587482 | 19KXGS226305MS | TBD | 8/24/2017 | 1ST FLOOR MAIN SERVER ROOM ON TELCO BACKBOARD TYPE Demarc L2: : OPTICAL | 8/24: Order is complete. 8/21: Escalating with Executive Escaltion team for completing testing. 8/14: Access install completed and demarc posted. Escalating with provisioning for End to End testing completion. 8/7: There is a facility issue and this is pending data assignment. Century and the AT&T provisiong team have an open ticket to resolve this issue. The ECD for install is scheduled for 8/11. 7/31: Escalated with service delivery leadership for assistance with completing EAD. 7/27-Emld Tech requesting status of EAD thru DD, emld wrong group on 7/25 7/25-Emld provisioning requesting AIM engagement for access DD missed + 3 7/17-Qwest DD 7/20, overall DD 8/2 7/10-Qwest DD 7/20, overall DD 8/2 6/27-Qwest DD 7/20, overall DD 8/2 6/20-Qwest DD 7/20, overall completion 8/2 6/13-LEC DD 7/20, overall completion 8/2 6/6-LEC DD 7/20, overall completion 8/2 5/31-LEC does own the conduit and now have permission from the landlord to proceed. LEC DD 7/20 5/30-LEC DD 7/20, eml MC to ask PM if they have any additional information from Qwest 5/15-PM stated CL is opening a tkt to send out a crew to determine who owns the conduit. 5/15-CNR, need to know when site will be ready, LEC DD 7/20 SITE REQUIREMENTS CUSTOMER PROVIDE FIBER PATH - TIE INTO THE EXISTING 2" CONDUIT AT THE MEET POINT AND EXTEND TO THE NORTH WALL OF DEMARC ROOM. PROVIDE SPACE FOR NEW EQUIPMENT ON NORTH WALL OF DMARC ROOM VERIFY 5-15R POWER OUTLET AT DMARC NORTH WALL BACKBOARD IS WORKING AND AVAILABE TO USE. 5/9-LEC DD 7/20, OVERALL dd 8/2 4/19-FOC rcvd, Major Build, LEC DD 7/20, overall DD 8/2 4/10-Pending FOC 5/11 4/6-USO rcvd, pending FOC 5/11 3/29- "HO CHANGE" 1gig UNI with a 1000 base SX 3/27-Rcvd order request | Jenny Cabotaje 16172491335 jc587j@att.com
CO039-01-IM | RNH ORDER 2775 Crossroads Blvd Flr 1st, Rm Main | Grand Junction, CO | 300MB/500MB 1000 BASE-SX |  |  | C11330488 VS17105263 30944026 3094BSMQ | BMEC993526 | QWEST HWS03603787 | 29KXGS239973MS | 2017-09-06 | 2017-08-24 | D-MARK 1 ST FLOOR CUSTOMER SERVER ROOM / CIENA 3916 MOUNTED | 8/28: Order completed 8/24 ready for turn up. 8/21-7/31: Target Access install date is scheduled for 8/30. 7/24-Access 8/30, overall completion 8/30 7/17-Access 8/30, overall completion 8/30 7/10-Access 8/30, overall completion 8/30 7/5-Access 8/30, overall completion 8/30 (major build) 6/27-Qwest DD 8/30, overall completion 8/30 (major build) 6/19-Qwest DD 8/30, overall completion 8/30 (major build) 6/13-FOC rcvd, LEC DD 8/30, overall completion 8/30 (MAJOR BUILD) 6/8-Rcvd USOs, pending FOC 7/12 6/2-Order submitted, pending USOs 6/1-Rcvd order request and email stating hot and needs circuit by 8/1 | Jiselle Alvarez ja746g@att.com
IL090-01-IM | 2655 Warrenville Road Downers Grove, IL 60515 | Downers Grove, IL | 250MB Ethernet | 2017-08-18 | 2017-08-14 | C11338626 VS17150433 30942028 | BREC919562 ATI | ATT MW HCS03805139 | KRGN117329LB | 2017-09-08 | 2017-08-29 | 1ST FL TELCO RACK 1 PORT 12 OF 12 | 8/30: Order completed on 8/29. 8/28: FOC completed 8/21, Target access install scheduled for 8/30. 8/21: Target FOC scheduled for 8/30. 8/15: Ordering submitted order, pending order number/USO. 8/14: Sent order to ordering team for processing, pending order number/ USO.
C1613-01-IJ | 510 West Parkland Dr | Sandy, UT | 30MB/100MB LC - Multi Mode Fiber 1000BSX | 2017-05-25 |  | C11330041 VS17101554 30944015 3094BSMM | IUEC842756 ATI | QWEST/Century Link HWS03602923 | 69KXGS239108MS | TBD | 2017-09-01 | 1st Flr Data center rack mount ciena 3e916 mini rr 7 rear she, jack type X | 9/5: Order completed 9/1. 8/28: Century Link pop collector down and ticket has been created. 8/21: Escalated with service delivery leadership to assist with completing testing. 8/17: Escalated with provisioning tech manager for End to End testing completion. 8/14: End to End wiring completed, End to End testing scheduled for 8/16 & overall DD-8/21. 8/7: Design completed on 8/3. End to End wiring ECD- 8/14 overall DD 8/21. 7/31: Facility design ECD- 8/3, End to End ECD- 8/14. Overall DD 8/21. 7/25-Design scheduled for 8/3, overall completion 8/21 7/17-Pending overall completion 8/21 7/10-Pending overall completion 8/21 6/26-Access delivered!!!! Overall completion 8/21 6/20-FOC rcvd 6/19, Qwest DD 6/22 (not gonna happen), overall completion 8/21, 6/13-pending FOC 7/10 6/6-Rcvd USO, pending FOC 7/10 5/30-Rcvd C proj #, pending USO 5/30-Request to change address and token 5/26-Sent to CSS 5/25-Rcvd order request | Jiselle Alvarez ja746g@att.com
UKS08-09-09 | 6860 West 115th Street Overland Park, KS 66211 | Overland Park, KS | 150MB port / 200MB Access | 2017-08-23 | 2017-07-19 | VS17152367 30942754 3094BSSH | BREC936350 ATI | ATT SW HMS02230823 | 74KRGN905078SW | 2017-09-19 | 2017-09-08 | 1ST FLOOR MAIN DATA RM | 9/11: Order completed 9/8. 9/5: FOC completed on 8/31, Target access install date scheduled for 9/8. 8/28: FOC scheduled for 9/15. Per UHG site visit is scheduled for 8/28. 8/21: Pending order number /USO. 8/14-8/7: Pending order number/ USO
TX064-05-IM | 2222 South 77 Sunshine Strip Harlingen, TX 78550 | Harlingen, TX | 100MB Port/ 250MB Access 1000 Base-SX | TBD | 2017-08-16 | VS17154280 30942819 3094BSTM C11339232 | BREC958969 ATI | ATT SW HWS03623659 | 38KRGN613551SW | 2017-11-10 | 2017-09-13 | 1ST FLR MDF RM CIENA 3930 RK MTD PRT 5 | 9/13: Order completed. 9/11: Estimated access install date is scheduled for 9/13. 9/5: FOC completed on 8/30, Target access install date scheduled for 9/13. 8/28: Received USO 8/26, Target FOC date scheduled for 9/19. 8/17: Ordering submitted order, pending order number/USO. 8/16: Sent to ordering for processing, pending order number/USO.
IR512-01-IM | Letterkenny Office Park, Windy Hall Campus Donegal County, Ireland | Donegal County, Ireland | 200mg access 100port Ethernet | TBD | TBD | VS17106125 ISR17060508596 | IUYF.102670..ATI | TBD | TBD | TBD | 2017-09-11 | DUB01.19.ODF4.U34.X04; node/patch panel: ixn_CN3940_an10; port 15 | 9/11: Order complete. 9/5: Splicing completed. NTU installation scheduled for 9/6 with handover to follow network acceptance testing. 8/28: Planning to do splicing early next week, pending NTU installation. Hot Order. 8/21: Order escalated for install dates. 8/14: Site contact advised that IT rack & clean power available from 8/17. Splicing & NTU(network termination unit) install to be scheduled. 8/7-7/26-CRD 8/17 7/17-Dates shared with PTT, waiting for site readiness 8/17 7/11-Our Enet contact visited this location yesterday with the landlord. The previous tenant was vacating there yesterday. Enet have a fibre presence in building 1. This will be a relatively straight forward fibre installation for Enet. Once Optum have their IT racks and clean power in place, Enet can schedule their works there. Enet will require minimum 2 weeks’ notice for scheduling their crews. 6/27-Optum do not have access here yet until 07/07 as the previous tenants still are operational,once Optum have keys,ENET can then see what is involved and get a timescale for the circuit delivery,based on new comms room fit out/IT rack & power availability etc.,ENET was instructed by the supplied contact to liaise directly with Henry on this as he is the overall PM re connectivity 6/19-Site not ready: PTT liaised with contact, advised that end customer not getting keys to new building until start of august - order on customer hold, requested clarification on circuit termination location 6/12-Order placed with PTT 2 May 2017-Rcvd Order info
AZ056-01-IM | 1107 East Bell Road- Suite 3 | PHOENIX , AZ | 10MB/50MB | 2017-04-26 | TBD | C11327203 VS17090487 30943715 3094BSLH | BBEC560523 ATI | QWEST HWS03599245 | 19KXGS235840 MS | TBD | 2017-09-20 | 1ST FLOOR MAIN SERVER ROOM SUITE 3. TELCO BACK BOARD NEXT TO EQUIP. RACK AND FDP TYPE: OPTICAL PORT:3 | 9/21: Order completed on 9/20. 9/18-9/15: End to End testing is scheduled for 10/3. Escalated for date improvement. 9/11: Demarc has been posted and access deliverd by Century Link. Pending end to end testing for completion. 9/5: PER AIM: Splicing job has been moved out to 9/12. Due to restoration work needed after placing hand hole. Sprinkler and sidewalk need to be repaired. Next follow 9/13. 8/28: Per AIM; per job source manager crews are stalled due to construction in the area. The new fiber splicing ECD is 8/30/17. 8/21: Escalated with provisioning manager to assist with completion of access delivery. 8/17: Pending completion of access install. 8/14- 7/31: Target Access install date is scheduled for 8/17. Received confirmation that conduit was completed by Comnet 7/20-Rcvd FOC, Qwest access DD 8/17, overall DD 8/17 7/17-Site requirements met and sent to LEC PM 7/13-MC double checking interduct 7/6-Need service installed by 9/1- PLACE A 4" ENTRANCE CONDUIT EQUIPPED WITH A CALIBRATED MULE TAPE FROM THE PROPERTY MEET POINT LOCATED NEAR BELL RD. TO YOUR BUILDING/SUITE - EQUIPMENT LOCATION (BACKBOARD). 6/27-Pending site requirements Place a 4" entrance conduit equipped with a calibrated mule tape form the property meet point located near bell rd to your building/suite-equipment location (backboard) 6/20-Qwest DD 7/17, overall DD 8/4 6/13-LEC DD 7/17, overall DD 8/4 6/1-Rcvd FOC, LEC DD 7/17, overall DD 8/4 5/18-USO rcvd, pending FOC 6/22 5/15-Pending USO 5/4-Rcvd C project #, pending USO 4/26-Rcvd order request | Jiselle Alvarez ja746g@att.com
LA010-01-IJ | 11211 Industriplex Blvd Baton Rouge, LA 70809 | Baton Rouge, LA | 10MB Ethernet 1000 Base-SX | 2017-08-18 | 2017-08-14 | VS17151228 30942251 3094BSRW C11338636 | BBEC577926 ATI | ATT SE HSS03427941 | L0KRGN400727SC | 2017-11-03 | TBD | 1ST FLR TELCO RM WALL MOUNT NETWORK PORT 9 UNI PORT 5 FIBER. | 9/18-9/14: Access delivered and testing completed. Overall DD scheduled for 9/20. Completion letter sent 9/11 order is ready for scheduling TTU. 9/11-9/5: Target access install date is scheduled for 9/13. 8/28: PON issues & FOC completed. Target access install date scheduled for 9/13. 8/21: Received USO, pending PON for FOC schedule. 8/15: Ordering submitted order, pending order number/USO. 8/14: Sent order to ordering team for processing, pending order number/ USO. | Jiselle Alvarez ja746g@att.com
UMD11-06-IJ | 800 King Farm Blvd, 500 and 600 Rockville, MD 20850 | Rockville, MD | 50MB/100MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-23 | TBD | C11319303 VS17041944 30943379 3094BSDV 3094BSDW | IUEC855430 ATI | VERIZON S HES02816799 HES02809566 | TBD | TBD | TBD | TBD | 9/11: Order was confirmed received on 9/6. Pending order number and USO 9/5: Sent order over to sale to be replaced. Pending order confirmation. 8/14- 8/7: Pending new order, pending site requirements. 7/26-Order cancelled, need new order 7/25-Need CRD or will need new order 7/17-CNR 7/3-Verizon cancelled order due to CNR 6/27-Pending site requirements 6/20-Pending pull string from 5th flr, sent to Comnet for site survey on 6/19 6/13-FOC pushed out to 6/19 for site requirements, nd CRD to avoid PON cancellation from VZ 6/5-FOC pushed out to 6/19 for site requirements, nd CRD to avoid PON cancellation from VZ 5/31-MC reached out to VZ engineer and stated that there are site requirements CUSTOMER NEEDS TO PROVIDE A 1 1/4 INCH INNERDUCT, WITH PULL STRING, FROM THE 5TH FLOOR SOUTH ELECTRICAL ROOM T18, TO EITHER YOUR MDF ROOM 712 OR YOUR IDF ROOM 511 5/30-Need LCON to contact VZ engineer to avoid PON cancellation, FOC 6/1 5/23-Per notes Need LCON to call VZ engineer Steven J. Lightcap 301 282-2289 5/18-Sent 2nd email to VZ engineer 5-16, Emld VZ engineer regarding CNR and LCON not being valid 5/15-Due to CNR, Verizon has pushed FOC out to 6/19 5/11-Verizon CNR, saying LCON listed is not a valid contact and to contact verizon's engineer Steven J. Lightcap 301 282-2289 steven.j.lightcap@one.verizon.com 5/9-Pending FOC 6/1 5/1-PON sent, pending FOC 6/1, asked to pull in 4/21-Engaged AM's backup to escalate for PON re-issuance, follow-up 4/26 4/17-Escalated to assembler coach to have PON reissued with Melissa's number as ALCON 4/11-Emld OM Melissa's number 763-744-2114, and having PON re-issued 4/10-Emld requesting verification of ALCON contact number 4/10-PON cancelled, emld assembler coach requesting replacement asap 3/20-pending FOC 4/11 3/9 - PON released, pending FOC 4/11 3/4 - USO rcvd, pending PON 3/8 2/28 - Rcvd C proj #,pending USO 2/27 - Order sent to SD, pending C proj # 2/23 - John sent request | Daisy Sambo 470 719-7904 ds8468@att.com
C1619-01-IJ | 900 Venture Dr Rm Meet Me 1st Flr | Allen, TX | 100MB/1GB Change to Single Mode LC-Multi Mode 1000 Base-SX Carrier Hotel Meet Me 1st Flr | 2017-05-25 | TBD | VS17117003 C11331913 30942880 | IZEC580395 | ADE LNS HMS02222991 | TXKFGS100051TPM | 2017-10-05 | 2017-09-19 | A-END DEMARC:DLLSTXTLW24 070123.03 PNLJKS 9/10 Z-END DEMARC:ALLNTXGMH12 010001.06 PNL 1 JKS 73/74 | 9/19: Order completed on 9/19. 9/18: Access delivered. End to end wiring- 1000 base LX.scheduled for 9/26, testing scheduled for 9/28. 9/11-8/21: Target Access install date scheduled for 9/14. 8/14: FOC completed 8/10, Target access install date scheduled for 9/14. 8/7: Escalated to Business Unit Project Manager (BUPM) for assistance with FOC completion. 7/31: Target FOC date scheduled for 8/4. 7/24-Pending FOC 8/4 7/11: PON released, pending FOC 8/2 7/7: Rcvd USOs, pending FOD 7/12 6/22: MC provided WTN 214-383-9569, AT&T IDC 6/22: Rcvd C proj # and needed WTN 6/12: Waiting for ADE capacity 6/5-Order Cancelled, replacing 5/26-Rcvd C proj #, pending USO 5/25-Rcvd order request & sent to CSS
C1619-01-IJ | 900 Venture Dr Rm Meet Me 1st Flr | Allen, TX | 100MB/1GB Change to Single Mode LC-Multi Mode 1000 Base-SX Carrier Hotel Meet Me 1st Flr | 2017-05-25 | TBD | VS17117003 C11331913 30942880 | IZEC580395 | ADE LNS HMS02222991 | TXKFGS100051TPM | 2017-10-05 | 2017-09-19 | A-END DEMARC:DLLSTXTLW24 070123.03 PNLJKS 9/10 Z-END DEMARC:ALLNTXGMH12 010001.06 PNL 1 JKS 73/74 | 9/19: Order completed on 9/19. 9/18: Access delivered. End to end wiring- 1000 base LX.scheduled for 9/26, testing scheduled for 9/28. 9/11-8/21: Target Access install date scheduled for 9/14. 8/14: FOC completed 8/10, Target access install date scheduled for 9/14. 8/7: Escalated to Business Unit Project Manager (BUPM) for assistance with FOC completion. 7/31: Target FOC date scheduled for 8/4. 7/24-Pending FOC 8/4 7/11: PON released, pending FOC 8/2 7/7: Rcvd USOs, pending FOD 7/12 6/22: MC provided WTN 214-383-9569, AT&T IDC 6/22: Rcvd C proj # and needed WTN 6/12: Waiting for ADE capacity 6/5-Order Cancelled, replacing 5/26-Rcvd C proj #, pending USO 5/25-Rcvd order request & sent to CSS
TX340-04 | 1311 E GENERAL CAVAZOS BLVD Building SUITE I, KINGSVILLE, TX 78363 | KINGSVILLE, TX | 7XT1 AVPN 10.8M | TBD |  | VS17156548 30944120 30944121 30944122 30944123 30944124 30944125 30944126 | DHEC713037811ATI DHEC713037812ATI DHEC713037813ATI DHEC713037814ATI DHEC713037815ATI DHEC713037816ATI DHEC713037817ATI | ATT SW | 34HCGS629619SW 34HCGS629614SW 34HCGS629616SW 34HCGS629617SW 34HCGS629615SW 34HCGS629618SW 34HCGS629620SW | 2017-10-18 | TBD | 1ST FLR TELCO RM CAB 2 QUAD MNT POSMNT POS 3 1ST FLR TELCO RM CAB 1 QUAD 1ST FLR TELCO RM CAB 1 QUAD MNT POS 4 RJ48C TAGGED 1ST FLR TELCO RM CAB 2 QUAD MNT POSMNT POS 1 1ST FLR TELCO RM CABV 1 QUAD MNTPOS 3 1ST FLR TELCO RM CAB 2 QUAD MNT POSMNT POS 2 1ST FLR TELCO RM CAB 2 QUAD MNT POSMNT POS 4 | 9/27: Order completed on 9/26. 9/25: 6 of T1's are delivered and tested. USO: 30944122- pending completion. 9/18: Redesign is back with OSPE this has been escalated by field team for ECD. Pending ECD on having pairs cleared. 9/14: Ticket has been assigned to work clearing fiber pairs. Pending ECD on clearing f2 cable pairs 9//11: Pending redisign completion and confirmation of degrated pairs being repaired. Once confirmed disatch will be rescheduled. Hot List 9/5: Target access install date scheduled for 9/12. 8/29: FOC completed 8/28,Target accesss install date scheduled for 9/12.
C1623-04-CM | 11830 WEBB CHAPEL RD Dallas TX, 75234 | Dallas, TX | Access change to 1000 base LX | 2017-08-22 | 2017-08-18 | VS17158798 30942932 | IUEC703866 ATI | TBD | TBD | TBD | 2017-09-19 | TBD | 9/19: Order completed on 9/19. 9/18: Order was adjusted to show as change order and not new. FOC was completed 9/18, Estimated access install date scheduled for 9/27. 9/11: FOC completed 9/6, Access install scheduled for 9/11. 9/5: Received USO 8/30, Target FOC date scheduled for 9/22. 8/28-8/21: Sent to ordering for processing, pending USO. |  | SDM Managed
TX272-01-IJ | 8400 Esters Blvd, Suite 185 | Irving, TX | 10MB/50MB | 2017-01-19 | TBD | C11313018 VS17009098 30942824 3094BRYP 3094BRYQ | BBEC584378 ATI | TIME WARNER HMS02230557 | 1TKFFN006630LVLC | TBD | 10/5/2017 | C1ST FLR SUITE 185 CISCO 3600 RK 3 PORTS 3,4. MM, AOTO NEG O FF EXTENDED WIRE | 10/5: Order completed. 10/3: Pending call back from Lec to test circuit. 10/2: Escalated with SDM leadership or overall completion. 9/25: Escalated with provisioning tech team for end to end testing and overall completion. 9/18: Acces install is scheduled for 9/20. 9/11: FOC completed 9/7, Estimated acces install date scheduled for 9/20. 9/5: Target FOC date scheduled for 9/26. 8/28: PON issued, FOC scheduled for 9/26. 8/21: Working with tech team to issue PON for order and gain firm dates. 8/7: Pending update from POP collector team. 7/25-Emld POP collector team requesting status 7/18-Request status of POP build 7/10-POP build, ECD July 6/13-POP build, ECD July 5/22-ECD of POP build is July 5/16-Pending update for ECD of pop build 5/9-Requested for ECD of pop build 3/13 - POP collector build, earliest date of completion is end of May 1/25 - POP collector build 120-190 days for completion and then PON will be released to LEC 1/23 - POP collector build, ECD 4/5/17, still pending FOC to be sent to LEC 1/24 1/19- USO rcvd, pending FOD request sent to LEC 1/24/17 1/6 - John sent Request | Jenny Cabotaje 16172491335 jc587j@att.com
TX356-05-IM | 200 W KEARNEY ST Mesquite, TX 75149 | Mesquite, TX | 7XT1 | 2017-08-09 |  | VS17167060 30944173 30944174 30944175 30944176 30944177 30944178 30944179 3094BSVM | DHEC977026811ATI DHEC977026812ATI DHEC977026813ATI DHEC977026814ATI DHEC977026815ATI DHEC977026816ATI DHEC977026817ATI | ATT SW | 14HCGS161394SW 14HCGS161393SW 14HCGS161397SW 14HCGS161392SW 14HCGS161395SW 14HCGS161398SW 14HCGS161396SW | 2017-10-05 | TBD | MAIN PHONE ROOM CAB 03 SLOT 0303 MAIN PHONE ROOM CAB 03 SLOT 02 MAIN PHONE ROOM CAB 04 SLOT 0202 MAIN PHONE ROOM CAB 03 SLOT 0101 MAIN PHONE ROOM CAB 03 SLOT 04 MAIN PHONE ROOM CAB 04 SLOT 0303 MAIN PHONE ROOM CAB 04 SLOT 0101 | 10/4: Order completed. 10/2-9/25: Access install & testing complete, overall DD scheduled for 10/5. 9/18: FOC completed on 9/13, estimated access install date 9/22.
C1623-04-CM | 11830 WEBB CHAPEL RD DALLAS, TX USA 75234 Room: STE 200 Floor: 2 | Dallas, TX | Change interface type to 1000 base-X |  | 2017-09-29 | VS17177095 | VLEC013230132ATI | TBD | TBD | 2017-10-02 | 2017-10-02 | TBD | 10/2: Order completed 10/2. Per OM completion notice has been sent out.
| 1707 WEST CREEK LN CHASKA, MN USA 55318 | CHASKA, MN | Upgrade to 6.5GB | TBD | TBD | VS17154651 VS17151217 3094BSRP | L4YS973574ATI | TBD | TBD | TBD | TBD | TBD | 9/25: Order completed 9/21. 9/11: Orders are scheduled for CUT 9/5: Order is ready for cut. 8/28: Order Manager Dana Lewis is primary contact for this order DD- 8/30 8/21: Order DD scheduled for 8/25. | DANA LEWIS dl0427@att.com | Not SDM Managed
| 1707 WEST CREEK LN CHASKA, MN USA 55318 | CHASKA, MN | Upgrade to 6.5GB | TBD | TBD | VS17154661 VS17151208 3094BSRM | L4YS972991ATI | TBD | TBD | TBD | TBD | TBD | 9/25: Order completed 9/20 9/11: Orders are scheduled for CUT 9/5: Order is ready for cut. 8/28: Order Manager Dana Lewis is primary contact for this order DD- 8/30 8/21: Order DD scheduled for 8/25. | DANA LEWIS dl0427@att.com | Not SDM Managed
| 14100 BUSINESS CENTER DR | Elk River, MN | Upgrade to 6.5GB | TBD | TBD | VS17154620 VS17151189 3094BSRH | L4YS973612ATI | TBD | TBD | TBD | TBD | TBD | 9/28: Cut was successful per OM. 9/25: Cut scheduled for 9/27 @ 11:30pm CT 9/11: Orders are scheduled for CUT 9/5: Order is ready for cut. 8/28: Order Manager Dana Lewis is primary contact for this order DD- 8/30 8/21: Order DD scheduled for 8/25. | DANA LEWIS dl0427@att.com | Not SDM Managed
| 14100 BUSINESS CENTER DR Elk River, MN 55330 | Elk River, MN | Upgrade to 6.5GB | TBD | TBD | VS17154645 VS17151203 3094BSRK | L4YS973256ATI | TBD | TBD | TBD | TBD | TBD | 9/29: Cus was successful per OM. 9/25: Cut scheduled for 9/28 @ 11:30pm CT 9/11: Orders are scheduled for CUT 9/5: Order is ready for cut. 8/28: Order Manager Dana Lewis is primary contact for this order DD- 8/30 8/21: Order DD scheduled for 8/25. | DANA LEWIS dl0427@att.com | Not SDM Managed
UWI29-10-CM | 3100 A*M*S BLVD Howard, WI | Howard, WI | Upgrade 150MB to 200MB | TBD | TBD | VS17157458 3094BSTP C11339240 | BREC997083ATI | TBD | TBD | TBD | TBD | TBD | NO REHOME 9/29: Order cancelled on 9/29. 9/28: UHG request order be cancelled. Pending confirmation. 9/25-8/28: DD scheduled for 9/27. Non SDM managed order. Order Manager Pamela Boyd is primary contact for order. 8/16: Sent to ordering to process, pending order number/USO. | Pamela Boyd pb623t@att.com | Not SDM Managed
UVA04-07-IM | 3645 Thirlane Road NW Roanoke, VA 24019 | Roanoke, VA | 100MB Port/200MB Ethernet | 2017-08-18 | 2017-08-14 | VS17149920 30942055 | BKEC995224 ATI | Verizon HES02835022 | 44KFGS303808CV | 2017-11-03 | TBD | 1ST FLR, DATA ROOM, RACK MOUNTED (TOP), CANOGA #2, TAGGED | 10/9: Order completed 10/9. 10/3: Submitted business case for AEP order and drop dead date of 10/15. 10/2: End to End testing is scheduled for 10/27. 9/27: Design & wiring complete on 9/26, testing scheduled for 10/27. Sent request to provisioning for earlier testing. 9/25: Facility design is scheduled for 10/18, end to end wiring- 10/24, overall DD-11/03. 9/21: Verizon has delivered access w/ demarc posted. Facility design is scheduled for 10/18, end to end wiring- 10/24, overall DD-11/03 9/18: FOC completed 9/18, estimated access install scheduled for 9/22. 9/11: Special construction being evaluated. Quote or FOC to follow. FOC scheduled for 10/5. Hot List. 9/5-8/28: Target FOC date scheduled for 10/5. 8/21: Received USO on 8/18, pending FOC date. 8/14: Sent order to ordering team for processing, pending order number/ USO. | Need drop dead and business case.
MO050-13-IM | 13655 RIVERPORT DR Building , Floor 3, Room TELCO MARYLAND HEIGHTS, MO, 63043 | Maryland Heights, MO | 100MB Port/ 250MB Access 1000 Base-SX | 2017-09-26 | 2017-09-20 | VS17174254 30942882 3094BSWJ | BREC885080 ATI | ATT SW HMS02236891 | 41KRGN705743SW | TBD | 2017-10-10 | Demarc: MAIN TELCO RM NEXT TO DOCK PATCH PNL 2POS 3/4 | 10/11: Order completed 10/10, completion letter sent. 10/9: FOC completed 10/3, estimated access install date scheduled for 10/13. 10/2: USO received 9/27, FOC scheduled for 10/23.
FL220-02-IM | 6545 Corporate Center Blvd. - Suite 240 Orlando, FL 32822 | Orlando, FL | 10MB Port/50MB Access | 2017-09-18 | 2017-09-07 | VS17169155 30942792 3094BSVZ C11341383 SITE ID: 527684 | BBEC528558 ATI | ATT SE HSS03433819 | 58KRGN702103SB | 2017-11-17 | 2017-10-10 | 2ND FLR UNIT IN MPOE OF 2ND FLR ABOVEDOOR | 10/11: Order complete 10/10, completion letter sent 10/9: Estimated access install scheduled for 10/13. 10/2: Fiber Plc/Splc completed 9/29. Access install scheduled for 10/13. 9/25: Estimated access install is scheduled for 11/10. Fiber Plc/Splc is scheduled for 10/31. 9/19: FOC completed on 9/19, estimated access install is scheduled for 11/10. Fiber Plc/Splc is scheduled for 10/31. 9/18-9/11: Order confirmed placed on 9/7, pending order/USO.
MA003-05-CM | 1 Main Cambridge, MA 02142 | Cambridge, MA | Upgrade port to 20mg on circuit IUEC.704887..ATI | 2017-09-27 | 2017-09-27 | VS17175688 3094BSWL 3094BSWK C11328726 VS17084128 30943667 | VLEC011512587ATI | TBD HNSV3830585 | TBD | TBD | 10/17/2017 | TBD | SIMPLE REHOME 10/17: Order completed on 10/17. 10/16: DD scheduled for 10/27, request has been made to have completed earlier. 10/9: FOC completed, access install scheduled for 10/11. DD scheduled for 10/27. 10/2: Estimated FOC date scheduled for 10/6. 9/25-9/18: Pending new USO's for new order. Working to clear old tail migration order. 9/11: If not complex request cut complete with OM 9/11: Pending order number/USO. Issue with tail migration. 9/5-8/28: New order placed to process on 8/28. Pending new order numbers. Hot order. 8/21: Sup for new lcon pending new firm dates. 8/14: Pending new LCON information. 7/27-Site visit delayed, pending construction 7/13-Site visit scheduled for 7/20 7/12-Site visit delayed but scheduled 7/5-New LCON Doug Downie 617 497-7713, 866 737-8844 6/27-LCON Michael Accardi 781 716-5611 michael_accardi@optum.com 6/27-Invalid LCON 6/26-FOC missed, sent request for AIM engagement 6/2-Pending FOC 6/22 5/15-FOD missed, sent follow up 5/9-Rcvd USO, pending FOD 5/12 5/10-Rcvd order request | Pamela Boyd pb623t@att.com
C1246-09-10 | 200 N Nash El Segundo, CA | El Segundo, CA | 300M to 500M | TBD | 2017-09-12 | VS17170786 3094BSWD 3094BSWF | IZEC565704ATI | TBD | TBD | 2017-09-27 | TBD | TBD | NO REHOME 10/16: Order completed on 10/11. 10/9: Order manager is escalating for completion. 10/3: Order manager has escalated or DD completion with provisioning team. 9/21: Received USO. DD scheduled for 9/27. Managed by order manager Dana Lewis. 9/18: Order placed 9/12, pending order number/USO | DANA LEWIS dl0427@att.com | Not SDM Managed
AZ047-01-IJ | 1669 West Ina Road | Tucson #1, AZ | 10MB/10MB | 2017-01-20 | TBD | C11314627 30942934 3094BRZP | MLEC712105 ATI | CenturyLink HWS03570396 | 19KXGS211079MS | TBD | 2017-10-23 | FIRST FLOOR MAIN IT, WALL MOUNTED 3916 MINI. PORT3 OPTICAL | 10/23: Order completed on 10/23. 10/16: Fiber job completed. This is now with design, pushing for delivery by end of week 10/20. will follow up on 10/23. 10/9: Easement issues have been straightened out Fiber plc/splc ECD 10/13. 10/2: Per AIM: There are two properties and 2 different owners. Must go through property A to get to Property B ( Customer). Property A has given permission to step on property to do work. Work and scope must be shown before they will sign ROW/easement papers. Engineer will get facilities blue staked/marked then surveyor will go out & prepare 2 exhibits an existing conditions. ECD should take approx. 2 weeks for above work to be completed. Nxt update 10/13. 9/25:Per AIM: Pending update from CL pm regarding ROW completion. 9/18: Per AIM: ROW is not complete, pending signature from property owner at UHG building. Job remains held for easement to the alley. No ECD, all quoted dates are now void. 9/11: ECD is 10/13, estimated based on ROW/ Easement from property owner. 9/5: PER AIM: ROW group is in process of buying 10 ft of easement in alley. Job is issued to construction (pending ROW), permit has been secured. ECD is 10/13. Estimated pending ROW/Easement from property owner. 8/28-8/14: Per AIM: Century link contractor will not proceed with work due to trespass issues in alley. Century link real estate has to go back to the city and buy more easement. ECD for this will take 6-8 weeks. 8/7: Per AIM: Fiber splicing ECD-8/14, Overall install date scheduled for 8/22. 7/31: PER AIM: Fiber placing is completed, splicing ECD is 8/14. Overall install date is scheduled for 8/22. 7/22-2 site meetings this week. CTL/FISHEL is going to proceed in placing the fiber, the easement issue is going to be taken care of through CTL Real Estate, placing ETA 8/2, next f/u 8/3 7/18-Change to LCON Gundy, Linda A <linda.gundy@optum.com> Phone Number +1(520) 573-0966 Business Email linda.gundy@optum.com 7/12-CC reached out to CTL asking for further details around the private property issue. asked to confirm where on the facility delivery are they hitting the private property issue. Is it the pathway/conduit, the entrance facility or most likely the MPOE or demark room. They are working to ID where the issue is so we can get you more involved so we can work on this together with the property. 7/10-THE SITE DID GET RESURVEYED BUT THERE ARE STILL ISSUES WITH THE JOB. IT NEEDS TO REMAIN PROJ DELAYED. ENGINEER, FISHEL (CONTRACTOR) & THE CPA REVIEWED THE STAKING. HAWKEYE (SURVEY COMPANY) NEEDS TO VERIFY ONE END WHERE THE EXISTING PEDESTAL IS LOCATED. WE COULD POSSIBLY BE VIOLATING PRIVATE PROPERTY, THE NEW BIGSHOT IS SLIGHTLY WIDER AND WE COULD BE IMPEDING THE EASEMENT APPROX 3-INCHES BUT THE EASEMENT AS IT WAS ORIGINALLY STAKED TAKES A BUMP/OFFSET AT THE PEDESTAL. HAWKEYE NEEDS TO DOUBLE CHECK THIS ONE SPOT. THERE ARE ADDITIONAL CORRECTIONS FISHEL MUST TAKE AS WELL BUT WILL NOT DO ANYTHING MORE UNTIL WE GET THE SURVEY BACK. FISHEL WILL GET A COPY OF THE EASEMENT HAWKEYE CONFIRMS AND SEND TO ENGINEERING. NO ETA AT THIS TIME. NEXT FU 7/13. 7/5-Update from CTL PM, Per the engineer, the property owner claiming violation of private property. Job will be delayed pending easement with property owner, no ECD. 6/30-No response from CTL engineer, escalated to their director 6/23-CTL Engineers are still trying to find a route that does not go through the alley 6/20-Pending response from CTL engineer if found a solution to bypassing the alley 6/16-CTL PM stated that customer is claiming that trench is in trespass in the alley, CTL sent back to engineer to resolve-job on delay 6/12-Permit received, Qwest currently has a placing date of 6/16, next follow up 6/19 6/5-AIM is following up on permits 6/9 6/1-The manhole is in the street so they need a traffic control permit for lane closure. 5/26-PER CLT ENGINEER THIS JOB CANNOT BE SENT FOR APPROVAL DUE TO PENDING MH ACCESS PERMIT BEING REQUIRED. THE PERMIT HAD TO BE REVISED AND RESENT BACK ON FRIDAY NEXT FOLLOW UP 6/9 5/24-AVM emld LEC PM for status 5/23-Follow-up with AVM of update from Qwest 5/19-AVM pushing Qwest for ECD 5/16-Pending update from AVM 5/11-AVM tkt issued 5/9-LEC DD missed, escalated for status 4/24-LEC DD 5/4, OVERALL COMPLETION 5/17 4/17-LEC DD 5/4, OVERALL COMPLETION 5/17 4/10-LEC DD 5/4 3/27-LEC DD pulled back to 5/4 3/13 - LEC DD pushed to 5/8 2/22 - All milestones through WOT have posted, pending LEC DD and EAD 5/4 2/16 - FOC rcvd, LEC DD 5/4 2/1 - USO rcvd, pending FOC 3/8 1/23 - c-project received, pending uso 1/20 - John sent request | PAM WALLACE 404-745-6306
NJ113-01 | 800 COOPER ST Camden, NJ 08102 | Camden, NJ | 2XT1 | 2017-09-11 | TBD | VS17165731 30944169 30944170 30944171 3094BSVL | DHEC.975012.811 DHEC.975012.812 | Verizon- S | HCGS858999NJ HCGS859000NJ | 2017-10-17 | 2017-10-18 | BSNT,1,RM TELCO,UTIL RM,,RJ48C,LP Y,CAB N,,SHELF,2,POS,4 BSNT,BSMT,RM TELCO,TEL RM,,RJ48C,LP Y,CAB N,,SHELF,1,POS,1, | 10/23: Order completed on 10/18. 10/16-10/9: Access install scheduled for 10/20. 10/3: Sent request for soonest re-dispatch date available. 10/3: UHG ready need install date needed. 10/2-9/28: CNR per LCON; not ready for install, please provide site ready date. 9/25: FOC completed 9/20, estimated access install date scheduled for 9/27. 9/18: Estimated FOC date scheduled for 9/21. 9/18: USO received on 9/13.
IR777-01-IM | UHG | 300MB Ethernet | ISR17082288971 | Unit 14 Northwest Business Park, Ballycoo, Db4 1 Telco, Dublin, IE |  | Ireland | Dublin | JAROSLAV BOSANSKY | 10/23: Demark: Optical on XIAW62-37b_FEC2/10, TID sent. 10/16: Cabling waiting for Interxion to complete the cross connect within MMR. 10/9: Fiber work completed. Firm date scheduled for 10/30/17 10/2-9/11: Firm date schedule for 10/30/17. 9/5: Circuit to be planned, then surveyed for fiber, once the survey is completed a workpack is then drawn up and sent to KN our cabling contractors, KN to schedule fiber works, once fiber works have been completed the BT surveyor will update the fiber records, in parallel cct software build, Mux configs then to be applied followed by testing and Mux install, then a final operations acceptance. 9/5-8/7: Pending order numbers.
C1563-04-CM | 5215 W WILEY POST WAY SALT LAKE CITY, UT USA 84116 Room: STE 200 Floor: 1 | Salt Lake, UT | ASN Change | TBD | 2017-09-18 | VS17175881 3094BSWN C11342503 | VLEC012825992ATI | TBD | TBD | 2017-10-05 | TBD | TBD | 10/30: Order marked as completed on 10/26. 10/23: UHG confirmed ASN change. 10/16: Confirming with OM for ECD of ASN change. 10/9: UHG requested that order be completed without cut. 10/9: Order is ready to be scheduled 10/2: USO: Received 9/29. Estimated DD scheduled for 10/5. This is order is managed by Order manager Jeanette Boyd 9/25: Pending order/USO. 9/18: Order placed for ASN change. Pending USO. Hot List Need by 10/1. | Jeanette Boyd jb0933@att.com | Not SDM Managed
MA008-06-IM | 1325 Boylston Street | Boston, MA | 150MB/200MB 1000 BASE-SX | 2017-07-31 | 2017-07-11 | VS17138398 30943821 3094BSQD | BKEC994855 ATI | Verizon HNS01910208 | 95KFGS007514NE | 2017-10-16 | 2017-10-31 | 9TH FLOOR SERVER ROOM WALL MOUNTED TAGGED | 10/31: Order completed on 10/31. 10/30: Escalated to Executive Escalation team for testing completion assistance. 10/23: Access delivered on 10/20, wiring and design completed. Order is pending end to end testing completion. 10/16: Order pending UHG site requirements. Reached out to OM for details on site requirements. 10/9-9/18: Estimated access install date scheduled for 10/10. 9/11: FOC completed 9/8, Estimated access install scheduled for 10/10. 9/5-8/29: Update LCON information with Order manager. Pending new dispatch date. 8/28: Access install not complete due to Verizon not having access to the building. 8/21-8/14: Target access install scheduled for 8/23. 8/7: FOC completed on 8/1, Target access install date scheduled for 8/23. 7/31: Pending order number/ USO. 7/20-Order sent to CSS 7/10-Rcvd order request
UNJ08-09-CM | 131 MORRISTOWN RD BASKING RIDGE, NJ USA 07920 | BASKING RIDGE, NJ | 150M to 200M | TBD |  | VS17147940 30940071 3094BSRD | BKEC981253ATI | TBD | TBD | 2017-09-14 | TBD | TBD | No REHOME 10/30: Order completed on 10/24. 10/23-10/9: OM is escalating for DD completion. 10/2: Pending status for escalation of DD. 9/25: OM escalating with provisioning team for completion. 9/18: DD scheduled for 9/14 Non SDM managed order. Order Manager Roberta Parker is primary contact. | Roberta Parker rp8624@att.com | Not SDM Managed
FL213-04-IM | 8380 BAYMEADOWS RD Building , Floor 1, Room JKVL, FL 32256 | Jacksonville, FL | 7XT1 | 2017-10-10 | TBD | VS17183616 30944260 30944261 30944262 30944263 30944264 30944265 30944266 | DHEC.949819.811.ATI DHEC.949819.812.ATI DHEC.949819.813.ATI DHEC.949819.814.ATI DHEC.949819.815.ATI DHEC.949819.816.ATI DHEC.949819.817.ATI | ATT SE GSS03439246 GSS03439254 GSS03439256 GSS03439255 GSS03439249 GSS03439248 GSS03439284 | 52HCGS778174SB 52HCGS778179SB 52HCGS778178SB 52HCGS778177SB 52HCGS778175SB 52HCGS778176SB 52HCGS778180SB | 2017-11-10 | TBD | TBD | 11/6: Order completed on 11/2. 10/30: Escalation ticket created to complete access install. 10/23-10/16: FOC completed on 10/14, estimated access install date scheduled for 10/27. 10/11: Received order on 10/10, Pending USO/Order number.
TX341-04-IM | 1313 E Alton Gloor Blvd Brownsville, TX 78526 | Brownsville, TX | 7Xt1 | TBD | TBD | VS17183309 30944252 30944253 30944254 30944255 30944256 30944257 30944258 | DHEC.914825.811.ATI DHEC.914825.812.ATI DHEC.914825.813.ATI DHEC.914825.814.ATI DHEC.914825.815.ATI DHEC.914825.816.ATI DHEC.914825.817.ATI | ATT SW GMS02238801 GMS02238800 GMS02238789 GMS02238791 GMS02238792 GMS02238793 GMS02238790 | TBD | 2017-11-02 | 2017-11-02 | ONI 2, POS 7, LOCATED AT REAR OF BUIDIOF BUIDING ONI 2, POS 6, LOCATED AT REAR OF BUILDOF BUILDING ONI 2, POS 2, LOCATED AT REAR OF BUILDING ONI 2, POS 3, LOCATED AT REAR OF BUILDOF BUILDING ONI 2, POS 4, LOCATED AT THE REAR OFREAR OF BUILDING ONI 2, POS 5, LOCATED AT THE REAR OFBUILDING ONI 2, POS 1, LOCATED AT REAR OF BUILDOF BUILDING | 11/3: Order completed 11/2. 10/30: 10/30: Escalation ticket opened up to assist with completing access install. 10/23: Estimated access install date scheduled for 10/27. 10/16: FOC completed 10/12, estimated access install scheduled for 10/23. 10/11: Received order on 10/10, Pending USO/Order number.
UTX12-07-IM | 2000 West Loop Houston, TX | Houston, TX | 100M Port/ 250 Access | TBD | TBD | VS17181801 30944239 3094BSXC Site ID: 539151 | BREC973535 ATI | ATT SW HMS02239691 | 28KRGN746081SW | 2017-12-27 | 2017-11-03 | 6TH FLR MPOE TELCO RM, WALL MNT,CIENA 3930,TAGD, PNL 1 SLOT | 11/6: Order completed on 11/3. 10/30: FOC completed on 10/27, estimated access install date scheduled for 11/9. 10/23: FOC scheduled for 11/8. LCON requested site survey 10/24. Checking with assigned engineer for site visit details and date. -Employees move in first week of Nov. 10/16: Pending PON completion, once PON is generated FOC will be provided. 10/10: Received USO. 10/9: Pending USO. Hot Order 10/4: Order has been processed, pending order number/USO.
C1624-02-IM | 2335 South Ellis Street Chandler Bldg D50 Chandler, AZ 85286 | Chandler, AZ | 300MB port/ 500MB Access 1000 Base-SX | 2017-10-11 | 2017-09-27 | VS17183353 30944242 | BMEC740195 ATI | Qwest HWS03634472 | 19KXGS270320MS | 2017-12-28 | 2017-11-01 | 1ST FLOOR ROOM CCB-185, RELAY RACK CB17, SHELF-2. PATCHED TO | 11/6: Order completed on 11/1. 10/30-10/23: Demarc posted by LEC, pending end to end design, wiring testing. Overall DD scheduled for 12/28/2017. 10/16: FOC completed 10/12, estimated access install date scheduled for 10/24. 10/9: Pending USO, reached out to Ordering team. 10/2: Order placed on 9/27, pending order number /USO.
C1626-01-IM | 12655 Edison Dr Alpharetta, GA 30022 | Alpharetta, GA | 300MB port/ 500MB Access 1000 Base-SX | TBD | 2017-10-23 | VS17194109 30943157 3094BSYS | BMEC881816 ATI | ATT SE HSS03443392 | 38KRGN612343SB | 2018-01-18 | 2017-11-08 | RACK MOUNT AL28(ATT#1) PNL 3 JK 1 | 11/13: Order completed on 11/8. 11/6: FOC completed on 11/1, estimated access install date scheduled for 11/10. 10/30: Received cproject number 10/2, pending order number/USO. 10/23: Order sent to ordering team for processing. 10/16: Order received on 10/12, pending processing.
UMD11-06-IJ | 800 King Farm Blvd, Rockville, MD 20850 | Rockville, MD | 50MB port/ 100MB Access 100 Base-SX | 2017-09-18 | 2017-09-06 | VS17168895 30942573 3094BSVX | IUEC886607 ATI | Verizon HES02838217 | 36KFGS307691CD | 2017-12-05 | TBD | 6TH FLR SUITE 600 IT CLOSET RACK MOUNTED NID 1 TAGGED | 11/13: Order completed on 11/10. 11/6: End to end testing scheduled for 11/28, overall DD scheduled for 12/5. 11/1: Lec installed demarc. 10/31: Pull string and conduit were completed and order reissued. 10/30: Customer not ready. OM has requested CNR details from Verizon. 10/23-10/16: Estimated access install date schedule for 10/26. 10/9: FOC completed 10/5, estimated access install date scheduled for 10/26. 10/2: Updated altLCON number, new FOC scheduled for 11/2. 9/25: Estimated FOC date scheduled for 10/30. 9/19: Received USO, PON scheduled to be issued on 9/21. Once PON is issued and received FOC will be provided. 9/18: Order has been placed, details are being confirmed with order manager, Pending USO.
UCA9Z-01-IM | 5995 Plaza Drive 1st Floor/MDF room Cypress, CA 90630 | Cypress, CA | 150MB Ethernet LC - Multi Mode Fiber 1000BSX | 2017-08-09 | 2017-08-02 | VS17144087 30944117 3094BSRC Site ID: 514694 | BMEC998150 ATI | Pac Bell HWS03619353 | 13KRGN591280PT | 2017-11-30 | 2017-11-17 | 1ST FLR, 1.1 MPOE, WALL MOUNTED. PORTHANDOFF TO VIRTUAL EDGE PNL | 11/13: Order completed on 11/13. 11/6-10/30: Estimates access install date scheduled for 11/10. 10/23-10/16: Customer prem- completed. Fiber Plc/Splc- 11/3, access install scheduled for 11/10. 10/9-9/18: Estimated access install date scheduled for 11/10 Permits- 10/5 Cust Prem- 10/13 C&E Fiber Pl/Splc- 11/3 9/11: FOC completed on 9/7, Estimated access install date scheduled for 11/10. 9/5-8/21: FOC has been rescheduled for 9/7. 8/14: Target FOC date is scheduled for 8/31. 8/7: Order processed 8/2, pending order number/USO.
UIL44-07-IJ | 1300 River Drive, Suite 200 | Moline, IL | 100MB/200MB | 2016-09-16 | 2016-09-21 | C11299194 3094BRRF 3094BRRG 30942272 | BKEC990989 ATI | MCC Telephony HCS03606280 | 10KFE020269QMN | 2016-09-21 | 2017-11-14 | DMARC: ON IN THE 2ND FLOOR IT ROOM, THE LOWER THIRD OF THE EQUIPMENT | 11/13: Pending testing for overall completion. Confirming circuit was delivered as optical. 11/6: Reroute has been completed. AIM has requested details on next steps and ckt install date. 10/30: Per AIM: A reroute is needed to correct issue for completion. This is scheduled to take place overnight on 11/1 10/23: Escalated to executive team for assistance with completion. 10/23-10/16: Circuit delivered AIM has provided completion letter to provisioning team to conduct testing. 10/9: Per construction manager install scheduled for 10/9. 10/3: Splicing is complete. Pending install date. 10/2: Splicing scheduled ECD 10/3. 9/26: Needed to clear debris from conduit. 9/25: Per AIM: Splicing ECD 9/25. Will follow up for status. 9/18: Per AIM: Due to issue with getting to the conduit splicing has not yet completed. Splicing is scheduled to start 9/14. 9/11: Per AIM: Construction has build has completed & new splicing is needed. Pending firm date for splicing completion. Once splicing is complete tech will be scheduled for install. 9/5-8/29: Per Mediacom: Construction is to be completed by end of week. Installer is looking to schedule install some time next week, barring any construction delays. 8/28: Pending update from AIM team regarding construction. 8/21: Per AIM: Site visit was a success, we were granted approval w/UHG to begin pulling fiber into the bldg. Now team is preparing to resume construction & target ECD by end or week 8/25. 8/14: Per AIM: Pending response from construction manager to confirm site visit. Will provide full update by EOW. 8/8: PER AIM: Construction manager is working on scheduling a second site visit to evaluate the UHG portion of the building & construction crew will begin pulling fiber next week. Pending timeline 7/27-Emld Tech requesting status of end to end testing 7/24-2nd level escalation for AIM engagement to provide status from MCC 7/20-Follow-up for AIM engagement 7/18-Request AIM engagement 7/14-Mediacom sent signed agreement to Rick 7/10-MC advised that nothing else should be required of John Deere 7/5-Another follow up with Mediacom 6/30-Follow up with Mediacom 6/23-Sent John Deere form over to Mediacom 6/14-Checking with AIM to see if provider has updated AIM in regards to the ROA 6/9-MEDIACOM REPORTS: WE ARE CURRENTLY PENDING A RIGHT OF ACCESS AGREEMENT FROM JOHN DEERE. OUR END HAS BEEN SUBMITTED, BUT WE ARE STILL WAITING ON THE FULLY EXECUTED COPY TO BE COMPLETED. I HAVE BEEN WORKING WITH RICK BARKER AT JOHN DEERE TO TRY AND GET THIS MOVING A LITTLE FASTER - 6/8-Emld backlog team to provide update on EAD 6/5-Backlog team has Escalated for EAD 6/1-MCC does not believe site is ready for testing yet 5/31-Arranging testing with MCC 5/30-MCC manager informed us that the order has been assigned to an engineer, MCC will be calling us for TTU possibly by the end of week 5/16-LEC DD 6/15 5/9-LEC DD 6/15 4/28-FOC rcvd on EVC PON, LEC completion 6/15/17 4/24-FOC 4/26 on EVC PON 4/17-Pending FOC 4/26 on EVC PON 4/10-Pending FOC scheduled for 4/26 on PON 3/31/2017 Redesign completed and confirmed firm timeline for delivery will be provided on 4/26 3/21-Sent ROE to Mediacom 3/20-Rcvd eml from MC that PM stated we should have ROE from John Deere on 3/21 3/20- Emld for ROE status, order will be cancelled 3/13 - Emld JS to check status of ROE 2/28- JS checking status of ROE 2/13 - Eml sent to Dale's replacements to please provide status of signed ROE 2/6 - Dale is checking on ROE 2/1 - Sent approved ROE back for John Deere's signature 1/23 - Emld Dale to ask if has status of ROE 1/16 - We will need 2 items: 1 – Fiber termination (which can either be 1RU or a wall mount box about 8”x 8”x 4”) and 1 – switch (1RU or wall mount (2” x 9” x 10”). Pending ROE sign off from John Deer 1/16 - Eml sent to AVM to engage LEC PM on how much equipment will be installed at the bldg. demarc before john deere legal will sign off on the roe 1/10 - Pending ROE document to be delivered to Mediacom by the client 1/9 - Need completed ROE signed and provided to Mediacom 1/6 - Emld LEC PM to provide status if ROE form has been received 1/5 - f/u sent to LEC if ROE has been received so LEC may gain access to building to bring in fiber 1/3 - SENT EMAIL TO THE LEC TO ADVISE IF THE ROE FORM WAS RECEIVED 11/28 - Pre-Construction Phase. It is scheduled for completion on 12/19/2016 for the site(s) and product(s) listed below. Pre-Construction Phase for several weeks as there are multiple steps required to complete this stage, including: - Route surveys - Route engineering - Equipment design - Permit acquisition from multiple agencies and municipalities 11/23 - End user has ownership, bldg owner will not allow us access, emld sent for clarification 11/21 AVM has escalation in with MCC mgr for FOC 11/17 FU sent to AVM to re-engage MCC for FOC status. 11/15 - 11/10 AVM has escalated to LEC for current firm delivery status. Updates to follow from LEC response. 11/8 - 11/3 Assembler has reached out to the MCC contact Dennis Jarding to work to schedule the site visit with customer. 11/1 Provisioning spoke with MediaCom and advised that they are still working on engineering and is made priority. No current commitment to FOC. 10/25 Assembler has contacted MCC to provide FOC status. Meanwhile this order has been addressed with the customer by MCC stating activation target. 10/18-10/14 MCC advised that they have the order and are pending FOC information. 10/11 - 9/27 ASR sent to LEC on 9/22/16 9/20 - 9/16 Order submitted. ASR to be sent on 9/21 or earlier. 9/16 Assigned to Christine Quintas; Pending USO release 9/8 Order has been submitted on 09-08-2016. C-project # is C11299194 8/23 - 8/16 Sold notice - Currently with sales. 8/12 Monitoring for USO release. 8/8 Assigned to Roy Velasco. 8/1 Order has been submitted for processing on 08-01-2016. C-project # is C11294598 7/29 Request sent to CSS for submission 7/26 Pending special bid process 7/18 - 6/21 Pending special bid 6/16 Follow-up sent to Chris 6/2 John sent in request | Sherryl Mendevil SM961Y@ATT.COM 7816026896 |  | UHGATTbgpyI6HYRM |  |  | 2016-09-16 | 2016-09-22
NY015-06-IJ | 50 Fulton Avenue | Hempstead, NY | 5MB/10MB 1000 Base-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | 2017-02-21 | TBD | C11319294 VS17041965 30943381 3094BSDX 3094BSDY | MLEC537161 ATI | VERIZON N NEW-HNS01900650 HNS01897603 | 32KFGS212125NY | TBD | 11/8/2017 | 1ST FLR/SERVER ROOM/WLLMTD CANOGA-TAGGED | 11/13: Order completed on 11/8. 11/6: Access install completed on 11/3. Pending end to end testing for overall completion. 10/30: Access install scheduled for 11/3. 10/23: Confirmed with OM that EUCR form was completed and Verizon has installed previous circuits in this location. Pending response from LEC. 10/16: Pending confirmation that EUCR form has been sent to Verizon OSPE. Access install scheduled for 11/2. 10/9-9/18: Estimated install date 11/2. Scope of Work: place fiber riser/dark fiber jumper (any length). 9/11: UHG confirmed hole was completed 9/6. Order has been supped and FOC completed on 9/6. Estimated access install date scheduled for 11/2. 9/5: Hole was scheduled to be completed by 8/30 pending status. 8/28: Pending completion of site readiness. 8/21: Verizon Pending Site readiness date to complete install/ Provide proper hole size. 8/14-7/31: Target Access install date scheduled for 8/16. 7/27-PON noted with CRD 7/25, Verizon access DD 8/16 7/25-Drill hole completed, VZ engineer contacted 7/17-Was drill hole completed? 7/11-Per customer, drill hole should be completed by EOW 7/10-Pending update on drill hole 7/5-Pending drill hole 6/27-Verizon meeting site contact to say where to place hole 6/26-No ECD on the drilled hole (customer) 6/19-CNR-UHG drilling new hole, still need FOC and RID on EVC PON 6/14-6/14, 6/13 escalate to design team; evc needs foc and RID per provisioning center. HNSV3718190---EVC for 6/13-Verizon has CNR'd-Hole too close, fiber unable to bend, drill new hole 6/5-Rcvd FOC, LEC DD 6/12, overall completion 6/30 6/1-Emld OM advising the site requirements have been met, need order supp'd to have Verizon re-dispatch 5/31-MC emailed and advised site requirements complete today 5/30-Eml MC asking if any updates on completion of work 5/16-Hole needs to be dug through concrete wall 5/11-LEC DD missed, CNR 5/9-LEC DD 5/9 4/24-Rcvd FOC with LEC DD 5/9 WTH OVERALL COMPLETION 5/18 4/12-Rcvd FOC with LEC DD 5/9 WTH OVERALL COMPLETION 5/23 4/10-PON cancelled, request to have done asap so can receive FOC 3/27-Pending FOC 4/10 3/22-OM changed address without cancelling order 3/22-Emld OM asking to cancel the order, will re-submit with correct address 3/20-FOC pending 4/10 3/8- PON sent to LEC, Pending FOC 4/10 3/6 - USO rcvd, pending PON 2/28 - C proj # rcvd, pending USO 2/27 - Order sent to SD, JS advised to go with 10M optical 2/21 - John sent request | Daisy Sambo 470 719-7904 ds8468@att.com
CO038-01-IM | 8051 E Maplewood Ave, STE 300, RM MDF, FLR 3 | Greenwood Village, CO | 10MB/20MB 1000BSX | 2017-04-24 | TBD | C11327688 VS17079162 30943679 3094BSKX C11326342 | MMEC554500 ATI | QWEST HWS03597301 | 29KXGS234075MS | TBD | TBD | MAIN IT 2ND FLR, WALL MOUNTED CIENA TYPE: OPTICAL PORT: 3 | 11/9: Order completed. 11/6: Per CL: Pending confirmation from field tech on install. 10/30 Per CL: Fiber Plc & Splc completed 10/26. Order was sent to design and expedited, expecting tech to dispatch Monday 10/30. 10/23: Access install scheduled for 11/1. 10/16: Confirmation sent to OM that site is ready. Order has been supped for new firm dates. 10/9-10/2: Working with CL for resolution on conduit issue. 9/25: Pending confirmation from UHG on pulling fiber through mule tape. Pending conduit location working w/ CL for a resolution. 9/18: Permits received and work is done. UHG is checking with cable vendor on pulling fiber through with mule tape. 9/11: Per CL: The permits are being issued, dates will be provided once they are received. 9/5: CL is pending permits from the city of Greenwood. The city allows 1 contractor at a time in their city for utility work. There is currently another utility co. doing work in the city, until their work is completed permits will not be approved. 8/28: Target access install date of 9/27 due to minor build per OSP team. Hot list 8/24: UHG confirmed site is ready, notified OM to sup for dispatch. 8/21: Pending confirmation of site readiness. 8/14-8/7: Pending site readiness date confirmation, pending AC outlet. 7/31: Target access install date scheduled for 8/2. 7/25-Qwest access 8/2, overall DD 8/8 (major build) 7/17-Qwest access 8/2, overall DD 8/8 (major build) 7/10-Qwest access 8/2, overall DD 8/8 (major build) 6/27-Qwest access 8/2, overall DD 8/8 (Major build) 6/20-Qwest DD 8/2, overall DD 8/8 (Major Build) 6/13-Qest DD 8/2, overall DD 8/8 6/6-LEC DD 8/2, overall DD 8/8 5/19-FOC rcvd, LEC DD 8/2 5/15-PON sent, Pending FOC 6/15 5/11-Rcvd USOs 5/9-New ip addresses rcvd and rcvd new C proj #, pending USOs 5/2-Order rejected due to IP address overlapping/in use 4/28-Request for new IP addresses 4/24-Rcvd order request | Sherryl Mendevil SM961Y@ATT.COM 7816026896
UIL24-16-IJ | 712 Eleventh Street Main Flr MPOE | Lawrenceville, IL | 50MB/150MB LC - Multi Mode Fiber 1000BSX | 2017-06-06 | TBD | C11331190 VS17112396 30941568 3094BSNF | BCEC515891 | Frontier HCS03766731 | 30KRGS566999FTNC | 10/19/2017 | 11/10/2017 | 1ST FLR TELCO ROOM RACK MOUNTED ON RAD NID AND TAGGED ON PORT 5 WITH CKT ID TAGGED OPT-MMF, AUTO NEG OFF, 1000FULL | 11/10: Order completed on 11/10. 11/6: Engineering has issued the planning revision to change the design on this ckt. Engr will have to order 850NM multimode SFP for cust prem & 1310NM SFP's for the POP and CO. ECD will be determined once materials are in hand. HOT order List 10/30: Escalated with AIM for update from LEC resolving issue. 10/23: Per Frontier tech: Order was written incorrectly on their side. Physical path order was written but not the virtual path order. Engineer is engaged and working to resolve issue. 10/16: Overall DD scheduled for 10/19. 10/9: Access delivered, wiring scheduled for 10/10, testing scheduled for 10/12 & overall DD 10/19. 10/2-8/28: Target access install date is scheduled for 10/6 due to minor build. Pending DLR from Frontier. 8/21-8/14: Per provisioning: DLR ( Design Layout Record) is not ready from Frontier. Minor build required; Place fiber riser/dark fiber jumper. Access install scheduled for 10/6. 8/7: Escalated with provisioning for AIM engagement with access install completion. 7/31: Order is pending Engineering team to create central office projects and submit for approval. Pending firm dates. 7/27-Per Frontier, no SC charges are not required and the order has been released to be worked, Pending engineering to create central office engineering projects and submit for approvals 7/25-Frontier access 7/25, overall DD 9/15 7/18-LEC DD 7/25, Overall DD 9/15 6/30-FOC rcvd, LEC DD 7/25, overall completion 9/15 6/20-Rcvd USOs 6/8-Rcvd C proj #, pending USOs 6/6-Rcvd order request
TX371-04-IM | 850 W. US Hwy 77 San Benito, TX 78586 | San Benito, TX | 7XT1 | 2017-10-05 | TBD | VS17180182 30944276 30944277 30944278 30944279 30944280 30944281 30944282 | DHEC.928362.817.ATI DHEC.928362.816.ATI DHEC.928362.815.ATI DHEC.928362.814.ATI DHEC.928362.813.ATI DHEC.928362.812.ATI DHEC.928362.811.ATI | ATT SW GMS02238953 GMS02238955 GMS02238992 GMS02238991 GMS02238952 GMS02238954 RWS03634655 | 38HCGS631185SW 38HCGS631182SW 38HCGS631187SW 38HCGS631186SW 38HCGS631183SW 38HCGS631184SW 38HCGS631174SW | 2017-11-03 | 2017-11-03 | 1ST FLR, TELCO RM, CAB 1, POS 5 INSTALLED IN PHONE ROOM ON MULT MTSLT 2 R INSIDE 850 BUS 77 SUITE C MM 1 SLOT 7 INSIDE 850 BUS 77 SUITE C SERVER ROOM MM 1 POS 6 INSIDE 850 BUS 77 SUITE C SERVER RSERVER ROOM MM 1 POS 3 1ST FLR, TELCO RM, CAB 1, POS 4 INSIDE 850 BUS 77 SERVER ROOM QM 1 SLOQM 1 SLOT 1 | 11/3: Order completed. 10/30: Access delivered and circuits tested. Overall DD scheduled for 11/3. 10/23: Estimated access install date scheduled for 10/25. 10/16: Received USO's for 7Xt1 order. 10/10: Replace with 7xT1 order cancel Ethernet. 10/9: UHG sent over valid address to use to move forward. 10/4: Pending new IP numbers, IP numbers provided are in use. 10/2: Order placed on 9/28, pending USO/ order number.
TX031-04-CM | 1250 S Capital of TX Hwy Bldg. 1 FL 3 Rm 360 | Austin, TX | MLPPP - Upgrade to 4xT1 (Existing is 2xT1) DHEC.646841.811-812 | 2017-06-05 | TBD | 30944017 30944018 30944019 30944020 30944021 | DHEC.646841.811-812 4020-DHEC646841813ATI 4021-DHEC646841814ATI | AT&T GMS02216798 GMS02216725 | 32HCGS697150SW 32HCGS697151SW | TBD | 11/8/2017 | MPOE...BLDG-2...TELCOM RM...NCTRM...NCTE CAB-4...SLOT-3 MPOE...BLDG-2...TELCO RM...NCTRM...NCTE CAB-4...SLOT-1 | 11/6: CUT scheduled for 11/8 @ 22:30 CST. 10/30-10/16: Planning on having work done by the end of October. 10/9-9/26: Pending wiring form bldg1 to bldg. 2. UHG will provide update once available for CUT scheduling. 9/25: Pending hot cut for order. 9/18-9/5: Pending inside wiring. 9/5-8/14: Order completed pending cutover scheduling. 8/7-7/31: Order is being managed by Executive Escalation team for design completion. 7/27-Sent OM business case with a drop dead date of 8/4 7/24-Request status of RID 7/20-Request status of RID 7/18-Director escalation for RID 7/11-Request to be added to assembler escalations for design on existing circuits 7/6-OM's AM requested status update 6/30-OM's AM escalated 6/26-Escalation sent for design on existing ckts 6/20-Access installed on both new ckts, pending end-to-end testing, overall DD 6/28 6/9-LEC DD 6/19, overall completion DD 6/28 6/6-Rcvd USOs, pending FOC 6/8 6/5-Rcvd order request | Ehzra Javines 8664375085 mj803f@att.com
FL212-04-IM | 809 S ORLANDO AVE Building , Floor 1, Room J WINTER PARK, FL 32789 | Winter Park, FL | 7XT1 | 2017-10-10 | TBD | VS17183533 30944268 30944269 30944270 30944271 30944272 30944273 30944274 | DHEC.975574.811.ATI DHEC.975574.812.ATI DHEC.975574.813.ATI DHEC.975574.814.ATI DHEC.975574.815.ATI DHEC.975574.816.ATI DHEC.975574.817.ATI | Century Link GSS03439286 GSS03439264 GSS03439261 GSS03439262 GSS03439260 GSS03439287 GSS03439287 | 25HCGS313340UFLG 25HCGS313344UFLG 25HCGS313318UFLG 25HCGS313322UFLG 25HCGS313323UFLG 25HCGS313345UFLG 25HCGS313339UFLG | 2017-11-21 | 2017-11-20 | FIRST FLOOR DATA ROOM SLOT 5 OF 8 FIRST FLOOR DATA ROOM SLOT 7 OF 8 FIRST FLOOR DATA ROOM FIRST FLOOR DATA ROOM SLOT 2 OF 8 FIRST FLOOR DATA ROOM SLOT 3 OF 8 FIRST FLOOR DATA ROOM SLOT 6 OF 8 FIRST FLOOR DATA ROOM SLOT 4 OF 8 | 11/20: Order completed. 11/13: All T1's installed overall DD scheduled for 11/21. 11/6: Per AIM: Order is delayed due to lack of facilities. Recovery of cable pairs needed, CL has not provided a DD next follow up scheduled for 11/14. 10/30: Escalation ticket created to complete access install. 10/23: Estimated access install scheduled for 10/27. 10/16: Estimated FOC date scheduled for 10/17.
TX263-07-CM | 8107 SPRINGDALE RD AUSTIN, TX USA 78724 | Austin, TX | Upgrade 3XT1 to 7XT1 | 2017-10-04 | 2017-10-04 | VS17179331 30944192 30944193 30944194 30944195 | DHEC353324814ATI DHEC353324815ATI DHEC353324816ATI DHEC353324817ATI | ATT SW GMS02237948 GMS02237884 GMS02237883 GMS02237983 | 32HCGS697336SW 32HCGS697329SW 32HCGS697328SW 32HCGS697337SW | 2017-10-27 | TBD | STE 110 TELCO WALL CAB 3 SLOT 3 STE 110 TELCO WALL CAB 3 SLOT 2 STE 110 TELCO WALL CAB 3 SLOT 4 STE 110 TELCO WALL CAB 3 SLOT 4.4. | 11/20: Order completed on 11/16. 11/13: Pending CUT scheduling. 11/6-10/30 Order is ready for CUT scheduling. UHG has been informed by OM. 10/23: Access delivered, Overall DD scheduled for 10/27. 10/16: Scheduled for install on 10/16, will follow up on 10/18. 10/9: Received USO, FOC completed 10/5. Estimated access install scheduled for 10/16. 10/4: Order received from UHG pending processing.
TX342-04-CM | 1701 S STAPLES ST CORPUS CHRISTI, TX USA 78404 | Corpus Christi, TX | Upgrade 3XT1 to 7XT1 | 2017-10-04 | 2017-10-04 | VS17179358 30944216 30944217 30944218 30944219 | DHEC346006814ATI DHEC346006815ATI DHEC346006816ATI DHEC346006817ATI | ATT SW GMS02237916 GMS02237922 GMS02237917 GMS02237915 | 34HCGS629648SW 34HCGS629650SW 34HCGS629647SW 34HCGS629649SW | TBD | 2017-11-16 | ST FLR PHN BOARD, CAB 10, POS 2JT=RJ48C ST FLR PHN BOARD, CAB 10, POS 4JT=RJ48C 1ST FL PHN BOARD, 4-SLOT,POS 1 ST FLR PHN BOARD, CAB 10, SLOT 3JT=RJ48C | 11/20: Order completed 11/16. 1/13: Order is ready for CUT scheduling. 11/6: Access install and demarc posted on 11/6. Pending overall completion. 10/30: Cable repair Tech dispatched to site, pending update. 10/23: BUPM is working with engineering team to clear defective pairs. 10/16: Scheduled for install on 10/16, will follow up on 10/18. 10/9: Received USO, FOC completed 10/5. Estimated access install scheduled for 10/16. 10/4: Order received from UHG pending processing.
C1627-01-IM | 1001 E Cambell Rd Richardson, TX 75081 | Richardson, TX | 50MB port/ 100MB Access | 2017-11-01 | 2017-10-24 | VS17194153 30943184 3094BSYW | IUEC972292 ATI | ATT SW HMS02242323 | 14KRGN881507SW | 2018-01-19 | 2017-11-15 | 1ST FLR, 3RD PARTY RM, R.RPANEL 1 TAGGED | 11/20: Order completed on 11/15. 11/13-11/6: FOC completed 11/6, estimated access install scheduled for 11/15. 10/30: Order processed on 10/24, pending order number / USO
FL219-01-IM | 2155 Southeast Federal Highway Stuart, FL 34994 | Stuart, FL | 10MB port/50MB Access | 2017-11-06 | TBD | VS17197066 30943227 3094BSZF | BBEC583434 ATI | ATT SE HSS03444516 | TBD | 2018-01-24 | 2017-11-14 | 1ST FL METER RM, WALL MOUNT PORT 5LABELED W/CKT ID | 11/20: Order completed on 11/14. 11/13: FOC completed on 11/7, estimated access install date scheduled for 11/16. 11/6: FOC scheduled for 11/30. Address has been changed to 2155. 10/31: Address needs to change 2155 instead of 2151. 10/30: Received Cproject order, pending order number/USO. 10/23-10/16: order received on 10/13, pending processing.
NY432-01-IM | 2425 James Street Syracuse, NY 13206 | Syracuse, NY | 100MB Port/ 200MB Access 1000 Base-SX | 2017-08-20 | 2017-08-14 | VS17152522 30942493 3094BSRX | BKEC995266 ATI | Level 3/Time Warner HNS01911979 | TBD | TBD | TBD | TBD | 11/21: Order completed 11/21. 11/20: AT&T received completion notice from Lvl 3 and completed design verification/ wiring. Pending End to end testing for handover. 11/16: Equip is installed and UHG confirmed that extension was done. L3 tech working on having circuit testing to handover to AT&T. 11/14: Per AIM: please confirm UHG has completed extension from MPOE to suite ( ISW) L3 needs to install AVDA equipment scheduled for thur or Friday. 11/13: Per AIM: Lvl 3 is escalating with internal teams for status on the build and ECD. Next follow up 11/17. 11/6-10/30: Pending build completion before firm dates are provided. ECD 11/8 10/23-10/16: Per AIM: Per Level 3 requires a build ECD 11/8. 10/10: Escalated to SDM leadership to assist wit reason for missed FOC. 10/9: AIM escalating with TW for FOC completion. 10/2: Provisioning has reached out to Time Warner for explanation of missed FOC. 9/28: Escalated for AIM engagement with FOC completion. 9/25-8/28: Target FOC date scheduled for 9/26. 8/21: Received USO, pending FOC date. 8/14: Sale sent order to ordering team for processing. Pending order number/ USO. 8/7: Received order request on 8/7, Pending processing,
UMO15-17-IM | 13655 RIVERPORT DR MARYLAND HEIGHTS, MO 63043 | MARYLAND HEIGHTS, MO | Upgrade to 200M | TBD | TBD | VS17189336 3094BSYB 3094BSYC | BREC885080ATI | TDB | TDB | 2017-11-21 | 2017-11-16 | TDB | No REHOME 11/20: Order completed on 11/16. 11/13-11/6: DD scheduled for 11/21. 10/31: No hot cut needed. 10/30-10/23: Estimated DD schedule for 11/21. Order is managed by OM Pamela Boyd. 10/12: Order for speed upgrade sent to ordering team. Pending USO/Order number. | Pamela Boyd pb623t@att.com | Not SDM Managed
C1625-01-IM | 6900 S PEORIA ST Building , Floor 1, Room MDF CENTENNIAL, CO, 80112 | CENTENNIAL, CO | 200MB port/ 500MB access | 2017-11-01 | 2017-10-25 | VS17194191 30943169 3094BSYV | BMEC882033 ATI | Qwest HWS03639285 | 29KXGS274777MS | 2018-01-19 | 2017-11-21 | DATA CENTER MDF-02, 1ST FLR RR B5 CIENA 3916 REG SHELF 3 OPT | 11/20: Access install completed, end to end testing scheduled for 1/12 & overall DD 1/19/18 11/13-11/6: FOC completed on 11/2, estimated access install scheduled for 11/14.
TX349-04-IM | 6513-C Smithfield Rd North Richland Hills, TX 76182 | North Richland Hills, TX | 7Xt1 | 2017-10-10 | TBD | VS17183248 30944244 30944245 30944246 30944247 30944248 30944249 30944250 | DHEC.412091.811.ATI DHEC.412091.812.ATI DHEC.412091.813.ATI DHEC.412091.814.ATI DHEC.412091.815.ATI DHEC.412091.816.ATI DHEC.412091.817.ATI | ATT SW GMS02238784 GMS02238783 GMS02238781 GMS02238782 GMS02238799 GMS02238786 GMS02238787 | 14HCGS161671SW 14HCGS161670SW 14HCGS161669SW 14HCGS161668SW 14HCGS161677SW 14HCGS161672SW 14HCGS161673SW | 2017-11-02 | TBD | TBD | 11/27: Order completed on 11/21. 11/20: All T1's delivered overall completion scheduled for 11/30. 11/13: Order supped for redispatch by OM. Tech was not able to gain access to site. They have been advised to call to gain access to the warehouse. 11/6: New Lcon info provided and order supped for install on 11/10 10/30: Escalation ticket created to complete access install. 10/23-10/16: FOC completed on 10/11, estimated access install date scheduled for 10/25. 10/11: Received order on 10/10, Pending USO/Order number.
TX347-04-CM | 1317 E JASMINE AVE MCALLEN, TX USA 78501 | McAllen, TX | Upgrade 3XT1 to 7XT1 | 2017-10-04 | 2017-10-04 | VS17179343 30944200 30944201 30944202 30944203 | DHEC572438814ATI DHEC572438815ATI DHEC572438816ATI DHEC572438817ATI | ATT SW GMS02237894 GMS02237893 GMS02237955 GMS02237895 | 38HCGS631162SW 38HCGS631141SW 38HCGS631142SW 38HCGS631161SW | 2017-10-27 | TBD | 1STFLRAL1STFLRALLWEATHERMNT#5POS#2NEXTTOPOWERMET 1STFLRAL1STFLRALLWEATHERMNT#4POS#1NEXTTOPOWERMET 1STFLRAL1STFLRALLWEATHERMNT#4POS#2NEXTTOPOWERMET 1STFLRAL1STFLRALLWEATHERMNT#5POS#1NEXTTOPOWERMET | 11/27: Order completed on 11/21. 11/20: Cut reschedule 11/21/2017 @ 07:00 PM CST 11/13: CUT scheduled for 11/15 @ 6:00pm CST 11/6: Pending CUT scheduling date/time from UHG team. 10/30: Email sent to UHG for cut scheduling by OM. 10/23: Access install complete. Overall DD is scheduled for 10/27. 10/16: Scheduled for install on 10/16, will follow up on 10/18. 10/9: Received USO, FOC completed 10/5. Estimated access install scheduled for 10/16. 10/4: Order received from UHG pending processing.
UTX43-09-IM | UnitedHealth care Student Resources 2301 W. Plano Pkwy Suite 300 Plano, TX 75075 | Plano, TX | 10M port/ 20M Access | TBD | TBD | 1004966499 30943465 3094BSWS | MMEC554994 ATI | AT&T of Texas RMS02238086 | TBD | TBD | TBD | TBD | 11/27: Pending new USO for order reissue. 11/20-11/13: Order has been cancelled. Need to replace order. Pending USO. 11/6: New FOC date of 11/27 provided. 10/30: PON is being supped by provisioning, pending new FOC date. 10/23-10/10: FOC scheduled for 10/31. 10/9-10/2: Pending order number/USO. 9/25-9/18: Order placed 9/15, pending USO. 9/11: Order sent by UHG on 8/24. 9/5: Order sent by UHG on 8/24. Hot List
CA250-01-IM | 7 Technology Drive Irvine, CA 92618 | Irvine, CA | 100MB Port/ 1GB Access | TBD | 2017-11-09 | C11348831 VS17169083 30942863 3094BSWB | IZEC566690 ATI | Pac Bell HWS03629398 | 13KRGN591529PT | TBD | TBD | 1.1 MPOE, WALL MNT D, WE ADDED OPTICALPORT#3(SM) TO VIRTUALEDGE | 11/27-11/13: Order submitted for processing pending USO. 11/13-10/30: Pending new IP's for new order. Pending lease 10/23-10/10: Pending USO for new order. Pending new IP's 10/9: Pending new order being placed or transfer local loop. 10/2: Access install completed and circuit tested. Pending TTU scheduling. Pending confirmation of address change for order. Should have been ordered for 4 technology dr and not 7. Possible new order & new IP's** 9/25: Estimated access install date scheduled for 9/29. 9/22: FOC completed 9/20, estimated access install scheduled for 9/29. 9/18: Received USO. Estimated FOC date is scheduled for 10/11. 9/11-9/5: Order placed pending USO.
TX342-06-CM | 1701 S STAPLES ST Building , Floor 1, Room MDF CORPUS CHRISTI, TX, 78404 | Corpus Christi, TX | 10MB port / 50MB access | 2017-11-06 | 2017-10-25 | VS17196197 30943209 3094BSZB | BBEC534650 ATI | ATT SW HMS02242796 | 34KRGN613735SW | 2018-01-23 | TBD | INSIDE BLDG, BACK WH AREA, WALL MNT3903, PORT 6 | 12/4: Order completed on 11/30. 11/27-11/13: Estimated access install date is scheduled for 12/26. 11/6: FOC completed on 11/6, estimated access install scheduled for 12/26.
AZ045-01-IJ | 1460 West Valencia Road | Tucson #2, AZ | 10MB/10MB | 2017-01-20 | TBD | C11314718 30942864 3094BRYY | MLEC603578 ATI | CenturyLink HWS03568769 | 19KXGS209735MS | TBD | TBD | 1ST FLOOR EAST END TELEPHONE ROOM TYPE: OPTICAL PORT: 3 | 12/4: Order is completed on 11/29. 11/27-11/20: Overall DD scheduled for 11/30. 11/13: Access delivered and demarc posted. Sent order to executive escalation team for testing and completion asap. 11/6-10/2: FOC completed 9/28, estimated access install scheduled for 11/30. Customer Requirements: Done -Provide inner duct with mule tape inside occupied conduit from MPOP to meet point( approx. 390'). Please provide confirmation work is done or ECD. 9/27: AIM ticket has been opened and assigned. AIM will engage CL for FOC completion. 9/25: Escalated with provisioning manager for FOC completion of AIM engagement. 9/18-9/11: Estimated FOC date scheduled for 9/19. 9/5: Order has been supped for 9/19. 8/28-8/14: Target Access install date scheduled for 9/5. 8/7: Site requirements confirmed ready on 8/2. Order supped on 8/3 with new access install date of 9/5. Pending confirmation of CRD. 7/24-CRD 7/28 7/18-All site requirements will be met by 7/28 7/18-Pllywood and power in place, checking on inner duct 7/12-1.CUSTOMER TO PLACE INNER DUCT INSIDE OCCUPIED CONDUIT FROM MPOP TO MEETPOINT. 2. PROVIDE PLYWOOD BACK BOARD IN MPOP 3. PROVIDE POWER OUTLET TO THE BACKBOARD. (STANDARD 120V) 7/10-Pending customer, place cable conduit entrance facilities 6/30-CTL advised order is not ready, fiber not placed and still being engineered 6/26-missed EAD; engaging provisioning team so ticket can be open to engage AIM 6/19-CTL DD 6/26, overall completion 6/26 6/14-RID met on 6/13, CenturyLink DD 6/26 6/8-PON supp'd, new FOC 6/13/17 6/12-new LEC DD 6/26, overall completion 6/26 6/5-CTL stated to UHG PM on 6/2 that they had everything they needed to complete install 5/30-Per CTL not ready, waiting on permits from city 5/25-LEC DD missed, will escalate on 5/30 5/23-LEC DD 5/24 5/11-Rcvd new FOC with LEC DD of 5/24 5/9-Pending re-dispatch 5/1-Eml LEC for ECD 4/26-Site requirements met 3/21 4/26-Emld team asking to confirm site requirements have been met, notes show pending customer site requirements to be met + city permits for CenturyLink. 4/21-Missed EAD, pending a city permit, next follow up is 4/26, no ECD at this time 4/17-LEC DD 4/20 with overall completion 4/26 4/10-LEC DD 4/20 4/3-New FOC rcvd, LEC DD/EAD/CTA 4/20 3/24-LEC advised of site readiness and re-dispatching, pending permit for engineering job 3/21-MC emld and stated PM says site requirements have been met, requested re-dispatch to CTL 3/20-Pending site requirements being met 3/13 - Emld JS to check on site requirements 3/7 - Customer not ready 2/10 - SITE REQUIREMENTS WERE RECEIVED TODAY AND FORWARDED OUT TO THE OS LISTED ON THE USO. CENTURYLINK WILL NEED AFFIRMATION THE CUSTOMER IS MOVING FORWARD WITHIN 10 BUSINESS DAYS OR THE ORDER WILL BE PLACED ON CUSTOMER HOLD: - 1.CUSTOMER TO PLACE INNER DUCT INSIDE OCCUPIED CONDUIT FROM MPOP TO MEETPOINT. 2. PROVIDE PLYWOOD BACK BOARD IN MPOP 3. PROVIDE POWER OUTLET TO THE BACKBOARD. (STANDARD 120V) - 2/9 - Customer not ready 1/25 - USO rcvd pending FOC 3/1/17 1/20 - John sent request | Sherryl Mendevil SM961Y@ATT.COM 7816026896
AZ124-04-IJ | 6245 E. Broadway Suite 600 | Tucson, AZ | 20MB/50MB SIP Upgrade Proj | 2017-02-06 | TBD | C11321853 VS17059204 30942714 3094BSQ | BBEC517865 ATI | QWEST HWS03585243 HWS03626337 | 19KXGS224064MS | TBD | 11/29/2017 | 6TH FLOOR CUSTOMERS SERVER ROOM, WALL MOUNTED CIENA 3916 TYP | 12/4: Order completed 11/29. 11/27: Pending overall completion. Sent to 3rd level for overall completion. 11/20: Access installed on 11/17, overall DD scheduled for 11/27. 11/13: Order is being supped for new dispatch/install date of 11/27. 11/6: AIM engaged for escalating with Qwest for access install. 10/30-9/25: FOC completed 9/20, estimated access install date scheduled for 11/2. Minor facility build required. 9/18-9/11: Order supped with Century Link new FOC date scheduled for 10/11. 9/5-8/28: Pending completion of site requirement before order can move forward. Per UHG project will begin 8/29. 8/21: Pending confirmation that Lcon has been updated about the order. 8/14: Century link called and new LCON did not know about order. Please provide another LCON to work with Century Link. 8/7: New LCON info provided on 8/7. Pending sup completion with new LCON info 7/25-Site working with property mngr 7/17-Pending site requirements 7/10-Pending site requirements-1. ONE (1) 15-AMP NEMA 5-15R (STANDARD 3-PRONG 15AMP 120V OUTLET. 2. PROVIDE-1.25" INNER DUCT FROM THE MPOP TO THE 6TH FLOOR APOP AND IT NEEDS TO BE EQUIPPED WITH A 200LB CALIBRATED MULE PON HWS03585243 CKL 0002 TAPE. 6/30-Pending site requirements 6/27-Pending site requirements 6/15-Pending site requirements, Qwest DD 6/28 6/13-LEC DD 6/28, overall completion 6/28 6/6-LEC DD 6/28, overall completion 6/28 5/30-LEC DD 6/28, overall completion 6/28 5/19-Order supp'd with new LCON info, LEC DD 6/28 5/18-Sent new LCON information to assembler and OM, Ron Arrieta, email as engineernova@netzero.net. Number is 520-304-4262. 5/15-LCON has no knowledge of order and not allowing in to pull in fiber 5/9-LEC DD 5/25, overall DD 6/14 4/25-LEC DD 5/25 with overall completion 6/14 4/17-LEC DD 5/25 with overall completion 6/14 4/10-Build required, FOC will be delayed appx 10 business days 3/29-USO rcvd and PON sent to LEC, pending FOC 5/3 3/27-Technical Document sent to JS, replied to all adding MC 2/9 - John confirmed ESP Qwest 2/6 - John sent request | Jenny Cabotaje 16172491335 jc587j@att.com
UIL55-02-IM | 1001 Jefferson Street Lawrenceville, IL 62439 | Lawrenceville, IL | 50MB Port/ 150MB Access 100 Base-SX |  | 2017-09-12 | VS17181590 30944240 3094BSXD | BCEC541238 ATI | Frontier HCS03837745 | TBD | TBD | TBD | TBD | 12/5: Order confirmed cancelled. 12/5: Sent request to cancel to OM. 12/5: Request to cancel the order. UHG will work with Frontier directly. Due to special constr. 12/4-11/13: Pending SC approval. 11/6-10/30: This requires special construction. Cost: $28,254.00 SOW: 1500 ft. of fiber, engineering, directional boring, placing & splicing labor. Quote expires 12/19/17. 10/23-10/16: Estimated FOC date rescheduled for 11/17. 10/11: Estimated FOC date scheduled for 11/14. 10/9: Order assigned to OM with Cproject number. UHG confirmed order details with OM pending USO. 10/2-9/18: Order placed on 9/12, pending order number/USO.
PH550-04-CM | UHG | Upgrade 400MB to 900MB | ISR17101370295 | Canley Rd Corner C5 Service Rd, Idc Bldg. 4 1, Pasig City, PH | Philippines | Pasic City | TBD | 12/5: Order complete. 12/4: Pending window from UHG for testing. 11/27-11/20: New schedule for 11/28 reserved. 11/20: DTAC: ,We did roll back the change because AT&T BW test tool was in maintenance and was unable to do bandwidth test. Customer does not know how to verify exact BW from their end. So, he requested to roll back the changes and will reschedule it., 11/13--10/23: - Booked for 11/17 @ 11:15 PM central time 10/16: Ready to schedule. 10/16-10/10: Pending order/ISR
CO008-09-IM | 9945 FEDERAL DR Colorado Springs, CO 80908 | Colorado Springs, CO | Upgrade 100M to 200M | TBD | 2017-11-28 | VS17214545 30943531 | BKEC988955ATI | TBD | TBD | 2018-01-04 | 2017-12-06 | TBD | 12/11: Order completed on 12/6. 12/6: Received USO, DD scheduled for 1/4/18 12/4: Received Cproject number on 11/28. Pending order number/ USO.
TX361-01-IJ | 8888 Interchange Dr. Houston, TX 77054 | Houston, TX | 10MB Port/50MB Access | TBD | 2017-08-14 | VS17152823 30942613 3094BSRZ Site ID: 516944 | BBEC535872 ATI | ATT SW HMS02230371 | 28KRGN745904SW | 2017-11-06 | 2017-12-07 | 1ST FLR IN WAREHOUSE,WALL MOUNTED, Demarc L2: 1 TO HANDOFF PORTS 1 & | 12/11: Order completed. 12/4: FOC is scheduled for 12/8, after FOC completion LEC will schedule access install. 11/28: Site ready. 11/27: Pending confirmation of site readiness. 11/21: Scheduled for site readiness on 11/27. 11/20: Pending confirmation of site readiness and new supp date for install. 11/13-10/30: Site requirements ECD is scheduled for 11/17. Notified OM of estimated completion date. 10/30-10/16: Site requirements: Permanent power, backboard & ground conduit. Pending ECD from UHG team. 10/9: Order showing room not ready. path/power/ground/space needed. 10/2-9/11: Estimated access install date scheduled for 10/5. 9/5: FOC completed 9/1, Target access install date scheduled for 10/5. 8/28: Received USO 8/21, Target FOC date scheduled for 9/13. Pending update due to tropical storm Harvey. 8/14: Sent to ordering team for processing, pending order number/USO.
UMD14-07-IM | 2111 Van Deman St Flr 1 Telco | Baltimore, MD | 20MB/50MB SIP Upgrade Proj | 2017-04-06 | TBD | C11324297 VS17068549 30943024 3094BSHZ 3094BSJB | BBEC550304 ATI | VERIZON HES02815082 | TBD | TBD | TBD | TBD | 8/14-8/7: Pending new order, pending site requirements. 7/14-Order cancelled due to CNR, will need to re-issue 7/10-Pending CRD 6/27-Pending CRD 6/20-Pending CRD 6/14-ASR still in CNR status, customer has crushed conduit, asked them to reach out to Verizon and have FOC date pushed back if can 6/13-LCON needs to provide VZ CRD, FOC 6/26 6/6-LCON needs to provide VZ CRD, FOC 6/26 5/30-LCON needs to contact VZ to provide CRD, FOC pushed to 6/26 due to no contact 5/22-Need LCON to contact VZ to provide CRD 5/19-LCON updated 5/18, Escalated for LCON update so PON can be supp'd 5/16, Emld OM to update LCON to Site contact Michael O'neal (3019777884 michael_oneal@uhg.com) 5/15-LCON on order unable to be reached Ryan Guthrie 443-957-6632 rguthrie@uhc.com 5/9-FOC 5/24 4/24-LEC pushed FOC to 5/24 4/13-Rcvd USO, PON released, pending FOC 5/18 4/7-Sent for order creation 4/6-Rcvd order request | Marites Balben 16172492393 mb874v@att.com
TX064-07-CM | 2222 S 77 Sunshine Control Plane, Harlingen, TX 78550 | Harlingen, TX | Upgrade 100M to 200M | TBD | 2017-10-25 | VS17196220 3094BSYY | BREC958969ATI | TBD | TBD | 2017-12-05 | 2017-12-01 | TBD | No RHOME 12/4: Order completed on 12/1. 11/20-11/13: Estimated DD scheduled for 12/5. 11/6: Received USO 11/6. Estimated DD scheduled for 12/5. Order is managed by OM John Allan Musni am463b@att.com | John Allan Musni am463b@att.com | Not SDM Managed
II523-07-CM | UHG | Upgrade to 500M | TBD | Oxygen Blvd - Tower D Floors Ground through 3 Plot No 7 Sec 144 Noida Uttar Pradesh 201304 | India Noida | Pradesh | TBD | 12/12: Order cancelled. 12/11-12/5: Order is in place pending ISR. 12/4-11/20: Pending contract signing for ISR 11/20-11/13: Contract sent to UHG on 11/10. 11/9: Order requested for upgrade by UHG.
NV095-01-IM | 3175 ST ROSE PARKWAY, SUITE 200 HENDERSON, NV 89052 | HENDERSON, NV | 2XT1 | TBD | 2017-12-01 | C11351282 | TBD | TBD | TBD | TBD | TBD | TBD | 12/11: UHG Requested that order be cancelled. 12/4: Received Cproject number on 12/1. Pending order number/ USO.
TX346-04-CM | 7198 MERCHANT AVE EL PASO, TX USA 79915 | El Paso, TX | Upgrade 3XT1 to 7XT1 | 2017-10-04 | 2017-10-04 | VS17179336 30944208 30944209 30944210 30944211 | DHEC776505814ATI DHEC776505815ATI DHEC776505816ATI DHEC776505817ATI | ATT SW GCS03834166 GCS03834177 GCS03834164 GCS03834178 | 30HCGS631056SW 30HCGS631058SW 30HCGS631055SW 30HCGS631057SW | TBD | TBD | TBD | 12/19: Per OM hot cut completed on 12/13. 12/18: Pending confirmation of cut completion. 12/11: 12/13/2017 @ 06:00PM CST TECHNICIAN ASSIGNED: BRENDA EDWARDS ¦BE1852@ATT.COM PHONE # : (404) 486-1086 APPOINTMENT ID: 69559 11/29: Access install completed. OM has sent out cust request, please provide cut date/time & contact. 11/27: Access install scheduled for 11/28. 11/20: New FOC date completed on 11/16, Access install scheduled for 11/28. 11/13: Site ready on 11/8. Pending sup for new FOC date. 11/7: Looking to complete site work by 11/8. 11/6: Pending ECD for site requirements. 10/30-10/16: Site not ready, need entrance conduit/pull string. Pending site requirements completion date. 10/9: Received USO, FOC completed 10/5. Estimated access install scheduled for 10/16. 10/4: Order received from UHG pending processing. | Gemalyn ( Gem) Hufana gh031g@att.com Contact for Cut scheduling
IR512-01-IM | UHG | 200mg access 100port Ethernet | ISR17062351303 | Letterkenny Office Park, Windy Hall Campus Donegal County, Ireland | Ireland | Donegal City | JAROSLAV BOSANSKY | 12/18: Order completed, completion letter sent on 12/18 12/11: Circuit delivered on 12/8, OM is working having testing scheduled & completed. 12/11-12/4: Enet works schedule Cabling & Splicing completed NTU install 12/7/17 with handover to AT&T to follow network acceptance testing Access arranged. 11/27-11/20: Advised fit out schedule from Optum.- Building 2 new comms room will be ready after 17.11.17 Provisional enet works schedule Cabling w/c 20.11.17 Splicing w/c 27.11.17 NTU install 12/7/17. Room is ready. Check with OM for splicing. 11/13-10/16: Will be ready Nov 17th. Provisional enet works scheduled cabling 11/20/17. 10/16-8/14: Circuit to terminate in building 2 ground floor comms room. Advised that this wont be ready until October, order on hold. 7/18-Order on hold-site not ready until October
IL090-04-CM | 2655 WARRENVILLE RD DOWNRS GRV, IL USA 60515 Room: MDF Floor: 1 | Downers Grove, IL | Handoff Change 1000 bsx (MMF) to 1000 BLX (SMF). | 2017-11-06 | 2017-10-30 | VS17199945 30943239 | BREC919562 ATI | ATT MW HCS03863144 | KRGN117329 LB | 2018-01-03 | TBD | 1ST FL TELCO RM SHELF 1 PORT 12 OF 12 | 12/26: Order completed on 12/22. 12/19: OM working on auto completing order with provisioning. 12/11: Pending OM response regarding auto complete request. 12/4: Order is ready, requires coordination with UHG. 11/27: Tech posted demarc and changed SFP from 1000sx to 1000lx. Pending design and testing. 11/21: Tech manager will try to dispatch a tech on 11/22 to assist with bringing in DD. 11/20: FOC completed on 11/20, access install scheduled for 12/1. 11/13: PON scheduled to be sent to the Lec 11/14. Once PON is received FOC date will be provided. Hot order. Site moving in by end of month. 11/6-10/30: Order processed 10/30, pending order number/ USO.
C1584-03-CM | 1649 W FRANKFO RD Carrolton, TX 75007 | Carrolton, TX | Port upgrade 300M to 400M | TBD | 2017-11-13 | VS17207303 30940565 3094BSZV | BLEC861039ATI | TBD | TBD | TBD | TBD | TBD | SIMPLE REHOME 12/26: Order completed on 12/22. 12/19: Order is ready to schedule cut. Email OM for cut scheduling. : OM Ana Lorica Chavez ac4200@abs.att-mail.com 12/11-12/4: DD scheduled for 12/22. Order not managed by SDM. OM Ana Lorica Chavez ac4200@abs.att-mail.com 11/20 Pending order number/USO. Check for OM and USO assign 11/13: Order placed and Cproject number generated. Pending order number/USO. | Ana Lorica Chavez ac4200@abs.att-mail.com | N
TX343-04-IM | 1711 S STAPLES ST Building , Floor 1, Room TELCO CORPUS CHRISTI, TX 78404 | Corpus Christi, TX | 7Xt1 | 2017-10-10 | TBD | VS17183372 30944284 30944285 30944286 30944287 30944288 30944289 30944290 | DHEC.924664.811.ATI DHEC.924664.812.ATI DHEC.924664.813.ATI DHEC.924664.814.ATI DHEC.924664.815.ATI DHEC.924664.816.ATI DHEC.924664.817.ATI | ATT SW GMS02238936 GMS02238985 GMS02238939 GMS02238935 GMS02238938 GMS02238942 GMS02238940 | 34HCGS629667SW 34HCGS629672SW 34HCGS629666SW 34HCGS629669SW 34HCGS629668SW 34HCGS629670SW 34HCGS629665SW | 2017-11-03 | TBD | TBD | 12/26-11/28: UHG will order Ethernet. 11/27: Due to old copper at site it has been suggested to place Ethernet order instead. Pending response from UHG on Ethernet order. 11/21: Want to move forward with T1 order. 11/20: Pending confirmation on how to move forward. 11/13: Per OM: Order needs to be cancelled due to all copper cables are defective. Fiber order needing to be placed. 11/6: Order referred back to engineering team due to not enough signal transmitted. Engr has issued work order to add repeater. 10/30: Escalation ticket opened up to assist with completing access install. 10/23-10/16: FOC completed 10/12, estimated access install scheduled for 10/25. 10/11: Received order on 10/10, Pending USO/Order number.
VA060-04-IJ | 12018 Sunrise Valley Drive, Suite 400 | Reston , VA | 20MB/50MB SIP Upgrade Proj | 2017-02-06 | TBD | C11316825 VS17026784 30943153 3094BSBK 3094BSBJ | BBEC591926 ATI | VERIZON S HES02819528 HES02814530 HES02806785 | TBD | TBD | TBD | TBD | 12/26-12/11: Pending new USO. 12/4: Order has been replaced, pending new USO. 11/27-10/30: Pending order reissue for new USO. 10/23-10/3: Received new IP's. Pending order reissue. 10/2: Pending new IP's for order reissue. 9/25: Pending order reissue confirmation. 9/18-9/11: Pending order reissue for new firm dates. 9/5: Order must be reissued due 8/28-8/21: Provided new LCON info pending new firm dates. 8/14: Verizon is needing a new LCON to contact for scheduling and access to complete fiber job. 8/7: Escalating with provisioning team for new PON 7/17-CNR, need new PON and VZ engineer contacted 7/7-Verizon cancelled order on their end due to CNR 7/5-Pending site requirements 6/27-Pending interduct site requirements 6/20-Interduct site requirements to be met, pending EUCRD 6/20-Due to CNR, PON cancelled 6/13-CNR, pending FOC 6/20 6/5-CNR, pending FOC 6/20 5/19-CNR-LCON needs to reach out to VZ and let them know when will be ready, FOC 6/20 5/16-New PON had to be issued, pushing for FOC 5/16-Escalated on FOC and requested AVM engagement to see if Verizon has issue with PON 5/9-FOC 5/15 4/24-Pending FOC 5/15 4/17-Pending FOC 5/15 4/10-Verizon cancelled PON due to ono response from cust when will be ready, new PON already in effect and currently new FOC scheduled for 5/15 4/3-Pending Customer Ready Date 3/29/2017 Customer confirmed not CRD. 3/27-PON has been cancelled by Verizon due to CNR and no ECD provided. Would you please provide an ECD so we can request a new PON. 3/20-FOC scheduled for 3/27 3/2 Bldg/Rm not ready, FOC pushed to 3/27 2/20 - PON released, pending FOC 3/24/17 2/17 - Escalation to provisioning on PON + 2 2/10 - USO rcvd, PON pending release 2/15 2/6 - John sent request | Jenny Cabotaje 16172491335 jc587j@att.com
AZ002-06-IJ | 3003 Central Ave | Phoenix, AZ | 10MB/50MB 1000-SX LC - Multi Mode Fiber 1000BSX SIP Upgrade Proj | TBD | TBD | C11319667 VS17042907 30943482 3094BSFX | BBEC536002 ATI | QWEST HWS03579028 | 19KXGS218491MS | TBD | TBD | TBD | 8/7 Will follow up on disconnect status. 6/19-Pending disconnect 5/9-Pending disconnect order to be placed 4/18-DDTS # 1835904 is in system and has been assigned, the actual disco order has not been placed yet. 4/17-Do not show disconnect in system 4/10-Advised PON is now inventoried, need a disconnect issued 4/4-Rcvd approval to cancel order from MC and sent to OM 3/7 - Rcvd FOC, pending EAD 3/24, DON'T GET EXCITED! 3/2 - Rcvd C project #, pending USO 2/27 - JS advised to go with CenturyLink 2/23 - John sent request | Sherryl Mendevil SM961Y@ATT.COM 7816026896
CT720-02-CM | 2 ENTERPRISE DR Shelton, CT 06484 | Shelton, CT | 100M Upgrade to 150M | TBD | 2017-11-30 | VS17212954 30943523 3094BTBC | BDEC984170ATI | CABLEVISION LIGHTPATH | TBD | 2018-01-04 | 2017-12-27 | TBD | NO RHOME 1/2: Order completed. 12/26-12/11: Received USO, DD is scheduled for 1/4/2018. Order not tracked by SDM. Order is managed by OM Angel Cadiao ac744u@att.com | Angel Cadiao ac744u@att.com | Not SDM Managed
TX367-01-IM | 1320 Inwood Rd Dallas, TX 75247 | Dallas, TX | 10MB port/50MB Access | 2017-11-06 | 2017-10-23 | VS17195074 30943213 3094BSZC | BBEC547253 ATI | ATT SW HMS02242923 | 14KRGN881534SW | 2018-01-24 | 2018-01-08 | 1ST FLR-SERVER RM-TELCO BB-WALL MOUNT TAGGED/LABELED | 1/8: Order completed on 1/5. 1/2-12/26: Request for re-dispatch has been made by OM. Pending dispatch date/time. 12/18: Per tech: Site requires- Path/PWR/GRND/SPACE. UHG is confirming site requirements. 12/11-11/13: FOC completed on 11/7, estimated access install date scheduled for 12/15. 11/6: FOC is scheduled for 11/30. 10/30-10/23: Order received & processed. Pending order numbers & USO.
UMO15-18-IM | TBD | Maryland Heights, MO | MACD for IP change | TBD | TBD | C11350489 | TBD | TBD | TBD | TBD | TBD | TBD | Hot order Tab Order can be completed anytime not in use. 1/16: Order completed 1/16: Order is assigned to OM and being escalated for USO's and firm dates. 1/16: Pending USO Check OM for status. 1/8: Pending USO for order.
HI015-01-IM | 1132 Bishop Street, Suite 400 | Honolulu, HI | 30MB/50MB | 2017-04-27 | TBD | VS17093624 30943736 3094BSLW | BBEC516905 ATI | TIME WARNER | 1GKFFN003638LVLC | TBD | 2018-01-15 | 15TH FLOOR ELECTRICAL/TELCO ROOM, TW TELECOM CABINET, CISCO 3600, PORT 20, 1000F - AUTO DISABLED, TAGGED W/CKT ID AND MTC NBR. | 1/15: Order completed. 1/8-12/26: Time warner advised they will be ready on 1/15 for final testing. 12/18: Pending date/time from UHG for ttu to complete order. 12/11-11/27: Executive manager working with tech team for completion. 11/20: POP collector mismatch has been resolved. Ticket has been opened up with LEC for testing. 11/13: Provisioning leadership working on resolving pop collector mismatch. VP team engaged. 11/6: Ckt has a pop collector mismatch with LEC. Order has been sent to design team to resolve. 10/30: Tech team is testing with Lvl 3 and continues to work to resolve EVC issue. 10/23: EVC ( Logical) portion of circuit complete. Tech team is working to have a tester assigned. 10/16: Ticket has been opened for testing completion. 10/9: Access install completed testing scheduled for 10/12. 10/2: Executive escalation team assisting with completing access install. 9/25: Pending access install completion. 9/18-9/11: FOC completed 9/8, estimated access install date scheduled for 9/25. 9/5; Pending FOC completion since order was supped for new dispatch date. 8/28: Per AIM; Order has been supped for re-dispatch pending install date. 8/21: Executive escalation team working with AIM to provide install date. 8/14: Per AIM ; LEC is investigating and is expected to provide details on next scheduled Exec call scheduled for 8/15. 8/7: AIM team is engaged and has order escalated to LVL 3 Exec mgmt. within LEC. There is discrepancy with the RUID ( Logical ports). Exec call is scheduled for 8/8 with AIM and LEC. Will follow up on 8/9. 7/31: Service delivery Executive Escalation team is engaged with provisioning for AIM engagement. Provisioning manager confirmed manual AIM ticket has been submitted and pending assignment. 724-Escalation sent for AIM engagement 7/20-Follow-up sent on AIM engagement 7/18-Assembler coach requested L63 be added for AIM engagement 7/17-Escalation in for missed FOC, requested AIM engagement 7/10-Will escalate on 7/15 if no FOC 7/5-Will escalate on 7/15 if no FOC. 6/26-Unable to escalate for foc until 7/15. That is the date the provider has to respond by. 6/21-SUP issued to correct the pop collector , FOC due 7/11, requesting 7/5 6/15-PON not supp'd yet updating to Time Warner Cable 6/13 discrepancy with the provider; pop is Time warner Cable and current pon has Time warner/Level 3. If provider needs to change to Time warner Cable the pon will be cancelled and reissued 6/7-Pending FOC 7/11 6/1-Rcvd USOs, pending FOD 6/6 5/17-Rcvd new C proj # 5/16-New order submitted with updated token with corrected IGLOO quote 5/10-Rcvd C proj #, pending USO 5/4-Order sent for processing 4/27-Rcvd order request | ` | `` | `` | ` | ` | `` | ````````````````````
UTX43-09-IM | UnitedHealth care Student Resources 2301 W. Plano Pkwy Suite 300 Plano, TX 75075 | Plano, TX | 10M port/ 20M Access | TBD | TBD | 30940054 3094BSZT | MMEC972270 ATI | AT&T of Texas RMS02245864 | 50KRGN881816SWDL | 2018-02-08 | TBD | TBD | 1/15: Per Halo team: demarc cannot be moved to 2nd floor since the order is already completed. Order will have to be replaced with request for 2nd floor. 1/8: Checking with backend team to see if demarc can be moved to 2nd floor. 1/8: Order completed on 1/4. 1/2-12/18: FOC completed 12/18, access install scheduled for 1/3/2018. 12/11: FOC scheduled for 12/29. 12/4: Halo/ MIS escalation ticket is opened to assist with providing FOC date. Order has been raised to next level Halo manager for assistance.

## Sales & Service Contact List
UHG ACCOUNT SALES & SERVICE TEAM CONTACTS
AT&T Executive Support | Name | Office | Cell | Email | Role
Sales Director | Charlie Penland | 612-376-5258 | 612-804-3600 | rp7505@att.com | Global Account Sales
Sales Center VP | Ron Edgar | 612-376-5727 | 763-350-1633 | redgar@att.com | Global Account Sales
Regional VP | Sheri Eichelberger | 312- 458-0330 | 908-612-7959 | se2134@att.com | Global Account Sales
Sr VP | John Finnegan | 973-326-4900 |  | john.finnegan@att.com | Global Account Sales
President GBS | Frank Jules | 214-757-7560 |  | fj8938@att.com | Global Account Sales
Director Service | John Cusack | 708-828-5273 | 312-972-4280 | jc2675@att.com | Service Management
AVP Service Management | Kimberly Gunter | (816) 251-8400 | 816-728-9472 | kb6769@att.com | Service Management
VP Service Management | Laquita Hall | (214) 782-6129 | 908-313-3660 | lh2136@att.com | Service Management
SVP Service Management | Thomas Harvey | 214-757-7510 | 214-536-3701 | th3921@att.com | Service Management
EVP Service Management | Xavier Williams | 214-464-0011 | 214-536-3701 | xw2829@att.com | Service Management
AT&T Sales Contacts: | Name | Office | Cell | Email | Role
Client Solutions Executive | Kim Phillips | 612-376-5812 | 612-770-6878 | kp1279@att.com | Global Account Sales NI, BVOIP, Contact Center, Telepresence, WiF, (Inventory as related to assigned projects)
Client Solutions Executive | Chris Cowan | 612- 376-5650 | 612-325-4821 | cc9719@att.com | Global Account Sales SDN/API’s, Consulting, Cloud/NetBond, Ethernet, MIS, Legacy 22 Voice & Data (Inventory as related to assigned projects)
Client Solutions Executive | Christine Isaacs | 612-376-5342 | 612-889-1006 | ci0213@tt.com | Global Account Sales Security, Rings, International Data/GMIS, UC, ACDN, AT&T Connect, Transfer of Service Agreements (Inventory as related to assigned projects)
Client Solutions Manager- Mobility | Chris Cowan | 612- 376-5650 | 612-325-4821 | cc9719@att.com | Mobility Products & Solutions
Card Specialist | Michael Snyder | 800-458-9409 prompt 1, ext 60008 |  | ms1836@att.com | Card Specialist
Chief Architect | Charlie Betz | 612-801-4013 | 612-801-4013 | cb611h@att.com | Technical Design
Technical Sales Consultant | Erik Westgard | 952-446-6294 | 952-446-6294 | ew1814@att.com | Technical Design
AT&T Service Contacts | Name | Office | Cell | Email | Role
Universal Service Executive - Maintenance | John Larson | 612-376-6087 | 612-803-1113 | jelarson@att.com | Service Maintenance Escalations, Stewardship
Universal Service Executive | Cameron Turner | 612-803-0990 | 612-803-0990 | ct8432@att.com | Service Provisioning Escalations
Universal Service Executive | Vince Templin | 847-228-6563 |  | vt8495@att.com | Service Provisioning Escalations
Service Delivery Manager- Voice & Data Provisioning | Brian S Cooper | 610-866-9857 | Not Available | bc2783@att.com | Service Delivery Management
Service Delivery Manager- Area Manager -Voice & Data Provisioning | Jane Tansor | 630-499-8233 | Not Available | jt3128@att.com | Service Delivery Management
Universal Service Executive - Mobility | Cameron Turner | 612-803-0990 | 612-803-0990 | ct8432@att.com | Mobility Service management
Customer Resolution Specialist - EMEA | Daniela Pleskova | +421-2-322-177-73 |  | dp352b@att.com | Service Escalations, UK/EMEA
Sales Execuitve- Lead- EMEA | Huub Goossens | 31703376604 | 31653259733 | hg2353@att.com | Sevice UK/EMEA Director
Sr. Associate Complex order services | Jaroslav Bosansky | 42-12-50210613 |  | jb324y@att.com | International PIM
Customer Resolution Specialist - Asia Pac | Ahmad Badri Rali | 60383177858 Ext: 77858 | 60192115049 | ar7091@att.com | Service Escalations, Asia Pac
Service Director- Asia Pac | Vishal Sharma | 91-124-4868707 |  | vishals@att.com | Service Escalations, Asia Pac
Sales- Latam | Thiago Almeida | 55-11-2141-3740 |  | thiago.almeida@intl.att.com | service escalations, LATAM
AT&T Billing Contacts | Name | Office | Cell | Email | Role
Billing Service Manager | Kim Burns | 585-293-0696 |  | kc6571@att.com | Complex Billing Escalation
Assoc. Director - Billing Operations | Amanda Morales | 407-251-7713 | 407-361-3404 | am4978@att.com | Complex Billing Escalation
Customer Care Billing specialists- Data & MIS CSSS | Rosemary Sniper | 877-811-4040 x 24569 |  | rs8712@att.com | Billing Data and MIS CSSS
Customer Care Billing specialists- Voice CSSS | Sandy Epolito | 877-811-4040 x 24047 |  | se1625@att.com | Billing Voice
AT&T Ordering Contacts | Name | Office | Cell | Email | Role
UVN Lifecycle Manager | Igor Sebej |  | 17706583575 | is345g@att.com | UVN Change Requests
ACCU-ring Lifecycle Manager | Jaroslav Janidzar | 816-200-5590 |  | jj461h@att.com | ACCURing change requests
AT&T West Local | Resource Mailbox | 877-428-5018 | Not Available | westdes@rdsmail.ims.att.com | Local Telco Service POTS
AT&T Southwest Local | Resource Mailbox | 877-428-5018 | Not Available | swdes@rdsmail.ims.att.com | Local Telco Service POTS
AT&T Southeast Local | Resource Mailbox | 704-733-1149 | Not Available | attgateway.complex@att.com | Local Telco Service POTS
AT&T Midwest Local | Resource Mailbox | 877-499-1207 | Not Available | mwdes@rdsmail.ims.att.com | Local Telco Service POTS
AT&T East Local | Resource Mailbox | 800-424-5112 | Not Available | ct-orders@rdsmail.ims.att.com | Local Telco Service POTS
LSSD Order Specialist | Mary Ramos | 402-399-4030 |  | mr363u@att.com | Low Speed Service Delivery T1 and below
Nodal Voice Order Specialist | Carol Ringgenberg | 402-548-9963 |  | cr5901@att.com | Nodal Voice Service Delivery
Nodal Voice Order Mgr | Larry Siref | 402-548-9966 |  | ls2902@att.com | Nodal Voice Service Delivery MGR
Nodal Voice OS Area Manager | Jeff Herr | 402-548-9973 |  | jh6832@att.com | Nodal Voice servicee Area Mgr
Client Support Specialist | Sharon Davis | 312-220-1550 |  | sd2374@att.com | Pre-sales & Ordering Support
Advanced Features Order Specialist | KAREN KAY ALMOJUELA | 402 392-9260 |  | ka2684@att.com | Advanced Feature Service Delivery